## Currently Certified Projects
State | Projected In Service Date (RSP Date) | Major Project | Project Component | RSP Project Number | I.3.9 Approval | TCA Approval | Responsible TO | FCM Certified In Service Date
ME | 2012-12-01 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation to Harrington Substation. | 143 | 05/10/2006 | 2008-06-03 | BHE | 2012-12-01
ME | 2013-12-01 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station | 1031 | No | No | BHE | 2013-12-01
ME | 2011-12-01 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | 1116 | No | No | BHE | 2011-12-01
ME | 12/2013 | Maine Power Reliability Program (MPRP) | Rebuild Line 66 | 1154 | No | No | BHE | 2013-12-01
| 12/2011 | Maine Power Reliability Program (MPRP) | Orrington Shunt Cap Reconfiguration | 1156 | No | No | BHE | 2012-12-01
ME | 2011-07-01 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (New Page - Rumford Industrial Park). | 624 | 2007-11-30 | No | CMP | 2011-07-01
ME | 2014-08-01 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | 905 | 2008-07-31 | 2010-01-29 | CMP | 2014-07-01
ME | 2014-05-01 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Larrabee Road-Middle St,Middle St -Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | 906 | 7/31/2008 & 2/26/09 | 2010-01-29 | CMP | 2014-07-01
ME | 2012-08-01 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 203 (Detroit-Orrington), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | 907 | 7/31/2008 & 2/26/09 | 2010-01-29 | CMP | 2014-04-01
ME | 2013-08-01 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road) | 908 | 7/31/2008 & 2/26/09 | 2010-01-29 | CMP | 2014-06-01
ME | 2014-09-01 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast forming Sections 86 & 266 | 909 | 7/31/2008 & 2/26/09 | 2010-01-29 | CMP | 2014-07-01
ME | 2014-02-01 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377, 115kV Bucksport 65/205) | 1025 | 7/31/2008 & 2/26/09 | 2010-01-29 | CMP | 2015-05-01
ME | 2010-11-01 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformer at South Gorham | 1029 | 7/31/2008 & 2/26/09 | 2010-01-29 | CMP | 2011-05-01
ME | 2013-11-01 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Maguire Road) | 1030 | 7/31/2008 & 2/26/09 | 2010-01-29 | CMP | 2013-11-01
ME | 2012-05-01 | Heywood Road Project | New 115kV line between Wyman Hydro and Heywood Rd. parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | 1129 | 2009-01-26 | No | CMP | 2012-05-01
ME | 2011-07-01 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | 1131 | No | NR | CMP | 2011-12-01
ME | 2011-12-01 | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer | 1135 | 2007-12-21 | NR | CMP | 2011-12-01
ME | 12/2012 | Starks Switching Station | Add 4-115kV circuit breakers in a breaker-and a-half configuration on Section 63 and 2-18 MVAr cap banks at a new Starks Switching Station | 1184 | No | No | CMP | 2012-06-01
ME | 2013-12-01 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Three Rivers) | 1026 | 7/31/2008 & 2/26/09 | 2010-01-29 | CMP/NU | 2013-12-01
ME | 2013-12-01 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | 1028 | 7/31/2008 & 2/26/09 | 2010-01-29 | CMP/NU | 2013-11-01
NH | 2011-04-01 | Seabrook Substation Reliability Upgrade Project | Seabrook Station Reconfiguration and Circuit Breaker addition Stage s 1 & 2 6 | 1142 | 2008-11-20 | No | FPL | 2011-04-01
MA | 2013-07-01 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | 59 | 03/12/2002 | 2003-01-31 | NGRID | 2012-12-01
MA | 2012-12-01 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | 673 | 2009-02-27 | No | NGRID | 2012-12-01
MA | 2012-12-01 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | 676 | 2009-02-27 | No | NGRID | 2012-12-01
RI | 2011-05-01 | Greater Rhode Island Transmission Reinforcements | Terminal upgrades at Drumrock, Chartley Pond and Brayton Point | 786 | 2008-04-25 | No | NGRID | 2012-12-01
MA | 2012-12-01 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation | 919 | 2008-01-28 | No | NGRID | 2013-06-01
MA | 2012-10-01 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Buswork and convert to BPS substation | 921 | 2008-01-28 | No | NGRID | 2012-12-01
MA | 2010-12-01 | Central/Western Massachusetts Upgrades | Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | 924 | 12/17/2007 | No | NGRID | 2011-04-01
MA | 2012-11-01 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | 925 | 12/17/2007 | No | NGRID | 2012-10-01
MA | 2012-01-01 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | 926 | 12/17/2007 | No | NGRID | 2012-10-01
MA | 2012-12-01 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | 928 | 12/17/2007 | No | NGRID | 2013-06-01
MA | 2012-07-01 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | 929 | 12/17/2007 | No | NGRID | 2013-06-01
MA | 2012-11-01 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | 932 | 12/17/2007 | No | NGRID | 2012-11-01
MA | 2011-12-01 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | 934 | 12/17/2007 | No | NGRID | 2013-12-01
MA | 2012-03-01 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | 935 | 12/17/2007 | No | NGRID | 2013-12-01
MA | 2012-05-01 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | 937 | 12/17/2007 | No | NGRID | 2013-05-01
MA | 2012-05-01 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | 938 | 12/17/2007 | No | NGRID | 2013-02-01
MA | 2011-01-01 | Central/Western Massachusetts Upgrades | Reconductor and retension (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | 939 | 12/17/2007 | No | NGRID | 2011-12-01
MA | 2013-12-01 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS (A127 West reconductoring. Tower 510 to Paxton, French King to French King). | 940 | 12/17/2007 | No | NGRID | 2014-02-01
MA | 2011-12-01 | Central/Western Massachusetts Upgrades | Install new Z126 Millbury - Tower #510 115 kV line. | 941 | 12/17/2007 | No | NGRID | 2013-06-01
MA | 2012-09-01 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers, | 942 | 12/17/2007 | No | NGRID | 2013-06-01
MA | 2011-12-01 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | 943 | 12/17/2007 | No | NGRID | 2012-10-01
MA | 2011-12-01 | Central/Western Massachusetts Upgrades | Adams - install third 115 kV breaker to In Service ring bus. | 945 | 12/17/2007 | No | NGRID | 2014-05-01
NH | 2013-12-01 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | 674 | 04/01/2008 | No | NGRID | 2013-12-01
RI | 2011-06-01 | Greater Rhode Island Transmission Reinforcements | Kent County substation expansion | 788 | 2008-04-25 | No | NGRID | 2011-03-01
RI | 2011-12-01 | Greater Rhode Island Transmission Reinforcements | Berry Street 345/115 kV substation. | 790 | 04/25/2008 | No | NGRID | 2011-12-01
RI | 2012-06-01 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV line. | 795 | 2008-09-24 | No | NGRID | 2014-03-01
RI | 2012-06-01 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | 798 | 2008-09-24 | No | NGRID | 2012-06-01
RI | 2012-06-01 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | 799 | 2008-09-24 | No | NGRID | 2012-06-01
RI | 2012-06-01 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S, T-172N and T-172S with associated terminal equipment upgrades. | 800 | 2008-09-24 | No | NGRID | 2013-12-01
RI | 2014-12-01 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | 1095 | 2008-09-24 | No | NGRID | 2013-12-01
RI | 2012-06-01 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | 1096 | 2008-09-24 | No | NGRID | 2012-12-01
RI | 2012-06-01 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County | 1097 | 2008-09-24 | No | NGRID | 2013-12-01
NH | 2013-03-01 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | 680 | 01/28/2008 | No | NGRID | 2013-04-01
RI | 2011-12-01 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | 1098 | 2008-04-25 | No | NGRID | 2011-12-01
RI | 2012-06-01 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | 1099 | 2008-09-24 | No | NGRID | 2012-06-01
RI | 2012-06-01 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | 1106 | 2008-09-24 | No | NGRID | 2012-05-01
RI | 2011-06-01 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | 1109 | 2008-09-24 | No | NGRID | 2012-12-01
MA | 2010-12-01 |  | Install KSt Breaker #31 | 1113 | 2009-12-15 | No | NSTAR | 2010-12-01
CT | 2010-12-01 |  | Separate 310 and 368 345-KV lines and create 368/1767 DCT | 582 | 2008-07-18 | No | NU | 2010-12-01
CT | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | 816 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | 196 | 2008-09-24 | No | NU | 2013-12-01
CT | 2013-12-01 | NEEWS (Ancillary Greater Springfield Reliability Project) | Manchester - Meekvile Jct. line (395/1448) separation. | 1054 | 2008-09-24 | No | NU | 2013-12-01
MA | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | 259 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | 687 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | 688 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115kV line South Agawam to Southwick (1768) | 818 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | 819 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | 820 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVAR Capacitor additions | 823 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | 826 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | 828 | 2008-09-24 | No | NU | 2013-12-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) and Agawam to Chicopee (1314) 115 kV lines. | 829 | 2008-09-24 | No | NU | 2013-12-01
MA | 2011-12-01 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | 1000 | 2008-06-27 | No | NU | 2011-01-01
NH | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Add a 345/115-kV 400 MVA autotransformer at Deerfield. | 277 | 2009-06-29 | No | NU | 2012-04-01
MA | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | 1010 | 2008-09-24 | No | NU | 2013-12-01
CT | 12/2011 | LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | 1056 | 2008-12-12 | No | NU | 2012-06-01
CT | 2011 |  | Waterside Substation - install a three-breaker 115kV ring bus | 1147 | 2009-09-29 | No | NU | 2011-05-01
MA | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | 1070 | 2008-09-24 | No | NU | 2013-12-01
MA | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | 1071 | 2008-09-24 | No | NU | 2013-12-01
MA | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | 1072 | 2008-09-24 | No | NU | 2013-12-01
MA | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | 1073 | 2008-09-24 | No | NU | 2013-12-01
MA | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | 1074 | 2008-09-24 | No | NU | 2013-12-01
MA | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | 1075 | 2008-09-24 | No | NU | 2013-12-01
MA | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | 1076 | 2008-09-24 | No | NU | 2013-06-01
MA | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115kV line | 1077 | 2008-09-24 | No | NU | 2013-06-01
MA | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | 1078 | 2008-09-24 | No | NU | 2013-12-01
MA | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | 1079 | 2008-09-24 | No | NU | 2013-12-01
MA | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | 1080 | 2008-09-24 | No | NU | 2013-12-01
MA | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | 1100 | 2008-09-24 | No | NU | 2013-12-01
MA | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | 1101 | 2008-09-24 | No | NU | 2013-12-01
MA | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | 1102 | 2008-09-24 | No | NU | 2013-12-01
MA | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | 1103 | 2008-09-24 | No | NU | 2013-12-01
MA | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | 1104 | 2008-09-24 | No | NU | 2013-12-01
MA | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | 1105 | 2008-09-24 | No | NU | 2013-12-01
NH | 2011-06-01 |  | Littleton 115kV breaker addition and reconfiguration | 1143 | 2009-10-20 | No | NU | 2011-05-01
NH | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115kV breakers and add 1-115kV breaker at Deerfield Substation | 1137 | 2009-06-29 | No | NU | 2011-04-01
NH | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | 1140 | 2009-06-29 | No | NU | 2013-12-01
CT | 2012 | LSP New Eagle Substation and 115/34.5KV transformer | New 115kV Eagle Substation connected to 115/34.5kV Thornton Substation | 1182 | 2010-07-27 | No | NU | 2012-06-01
CT | 2011 |  | Waterside Substation - install a three-breaker 115kV ring bus | 1147 | No | No | NU | 2011-05-01
CT | 2013-04-01 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | 974 | NR | NR | UI | 2011-06-01
CT | 2012-05-01 |  | Grand Avenue 115 kV Switching Station Rebuild. | 976 | 2009-01-07 | No | UI | 2012-05-01
CT | 2011-03-01 |  | Water Street 115kV Circuit Breaker Replacement | 1112 | NA | NA | UI | 2011-02-01
CT | 2011-09-01 |  | West River 115kV Switching Station Fault Duty Migration | 1151 | NR | NR | UI | 2011-06-01
VT | 12/2012 | Lyndonville Project | Installation of a 3-breaker 115kV righ station consisting of two 115kV 12.5 MVAR capacitor banks and 115/34.5 kV transformer interconnecting to the Irasburg - St. Johnsbury 115kV line | 1146 | 2009-06-01 | 2010-05-17 | VELCO | 2011-04-01
VT | 12/2012 | Shunt Reactors | Install 345kV 60 MVAr shunt reactors (two at Coolidge and one at Vernon) to address high voltage concerns | 1172 | No | No | VELCO | 2011-03-01
VT | 03/2012 | West Rutland Capacitor Rebuild | Install two 115kV 25 MVAr capacitor banks at West Rutland to address low voltage concerns | 1171 | No | No | VELCO | 2012-03-01
MA | 2012-09-01 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | 887 | 2008-01-28 | No | NGRID | 2012-09-01
MA |  |  | Reconductor 115kV Circuits 320-507 and 320-508 (Lexington-Waltham) |  |  |  | NSTAR | 2011-12-01
MA |  |  | Reconductor 1.2 mile length of line 336 from ANP Blackstone to NEA Bellingham Tap with 2-900 ACSS and replace five 345 kV 2000 amp disconnect switches with 3000 amp disconnect switches at W. Medway Station. |  |  |  | NSTAR | 2013-06-01