## Exhibit
Asset Condition Project Forecast
DRAFT - DO NOT QUOTE OR CITE
Project Stage
Developed – Full scope/conceptual cost estimates have been developed and project has been presented to PAC; ISD Year and Estimated Costs available
Under Development – Project planning is underway; project scope and conceptual cost estimates are currently being developed; Cost Category information available
Under Evaluation – Currently being evaluated for possible asset condition project, but no formal scope/cost estimates have been developed; Planning Horizon information available
[8 empty] | Developed Projects |  |  |  | Under Development & Under Evaluation
Project Stage | ACL ID | Line Number or Substation Name | kV | Primary Equipment Owner | State/Territory | Current Asset Condition | Anticipated Solution | PAC Presentation Date | Status (Concept, Proposed, Planned, Under Construction) | Estimated Cost | Estimated ISD Year | Anticipated PAC presentation date | Cost Category (Under Development) | Planning Horizon
Developed | 213 | 1000 | 115 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2019-12-19 | Under Construction | 13690000 | 2023
Developed | 260 | 1825 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and/or conductor | 2021-01-21 | Under Construction | 7286000 | 2023
Developed | 371 | 1580, 1560, 1808, Stevenson SS, Pootatuck SS | 345/115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-02-15 | Under Construction | 87289000 | 2023
Developed | 361 | 1261/1598 | 115 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2022-12-13 | Under Construction | 7273000 | 2023
Developed | 26 | Bourne SS | 115 | Eversource | EMA | Aging substation infrastructure | Rebuild substation as a breaker and one half scheme | 2016-11-29 | Under Construction | 69893000 | 2023
Developed | 27 | Kingston SS | 115 | Eversource | EMA | Aging substation infrastructure | Rebuild substation as a breaker and one half scheme | 2016-12-14 | Under Construction | 10428000 | 2023
Developed | 43 | K Street #385 SS | 115 | Eversource | EMA | Aging substation infrastructure | Installation of new 115-kV relay and control enclosure with new relay systems and upgrade of existing 115-kV protection system | 2017-06-21 | Under Construction | 18402000 | 2023
Developed | 63 | Lexington #320 SS | 115 | Eversource | EMA | Aging substation infrastructure | Installation of new 115-kV relay and control enclosure with new relay systems and upgrade of existing 115-kV protection system | 2017-09-28 | Under Construction | 16612000 | 2023
Developed | 194 | 110-510 & 110-511 | 115 | Eversource | EMA | Degradation of pipes and underground conductor | Rebuild lines with HPFF, repair infrastructure | 2019-08-08 | Under Construction | 97995000 | 2023
Developed | 315 | 191 | 115 | Eversource | EMA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2021-12-15 | Under Construction | 27840000 | 2023
Developed | 340 | Holbrook #478 SS | 345/115 | Eversource | EMA | Aging substation infrastructure, autotransformer | Replace autotransformer | 2022-08-24 | Under Construction | 10155000 | 2023
Developed | 280 | E115 | 115 | Eversource | NH | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2020-12-16 | Under Construction | 64147000 | 2023
Developed | 367 | P106 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2022-09-21 | Under Construction | 5634000 | 2023
Developed | 368 | Q171 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2022-09-21 | Under Construction | 14966000 | 2023
Developed | 380 | H123 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-03-16 | Under Construction | 5800000 | 2023
Developed | 389 | 391 | 345 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-05-18 | Proposed | 12370000 | 2023
Developed | 390 | 373 | 345 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-05-18 | Proposed | 10280000 | 2023
Developed | 391 | R193 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-05-18 | Proposed | 7700000 | 2023
Developed | 392 | S153 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-05-18 | Proposed | 5000000 | 2023
Developed | 393 | A126 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-05-18 | Proposed | 8370000 | 2023
Developed | 394 | E194 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-05-18 | Under Construction | 8670000 | 2023
Developed | 395 | U181 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-05-18 | Under Construction | 8510000 | 2023
Developed | 396 | D121 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-05-18 | Proposed | 5000000 | 2023
Developed | 397 | 307 | 345 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-05-18 | Under Construction | 9417000 | 2023
Developed | 399 | J114 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-05-18 | Under Construction | 9709000 | 2023
Developed | 178 | 3754 | 345 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2019-08-08 | Under Construction | 8200000 | 2024
Developed | 216 | 1080 | 115 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2019-12-19 | Under Construction | 23574000 | 2024
Developed | 266 | 387 | 345 | Eversource | CT | Degradation of poles and/or towers and PINCO insulators | Replace of poles and/or towers and PINCO insulators | 2021-01-21 | Under Construction | 12781000 | 2024
Developed | 267 | 3041 | 345 | Eversource | CT | Degradation of poles and/or towers and PINCO insulators | Replace of poles and/or towers and PINCO insulators | 2021-01-21 | Under Construction | 14534000 | 2024
Developed | 269 | 3754 | 345 | Eversource | CT | Degradation of poles and/or towers and PINCO insulators | Replace of poles and/or towers and PINCO insulators | 2021-01-23 | Under Construction | 4400000 | 2024
Developed | 357 | 1772 | 115 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2022-09-21 | Under Construction | 20730000 | 2024
Developed | 359 | 362 | 345 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2022-11-15 | Under Construction | 19163000 | 2024
Developed | 360 | East Devon | 345/115 | Eversource | CT | Aging substation infrastructure, relays | Relay Upgrades | 2022-10-19 | Under Construction | 6720000 | 2024
Developed | 258 | 1268/1485/1887/1622 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2021-01-19 | Proposed | 47200000 | 2024
Developed | 259 | 1163/1550 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-01-19 | Proposed | 34500000 | 2024
Developed | 356 | 348 | 345 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2022-09-21 | Proposed | 8400000 | 2024
Developed | 358 | 3041 | 345 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2022-10-19 | Proposed | 11600000 | 2024
Developed | 362 | 1355/1610 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2022-12-13 | Proposed | 50400000 | 2024
Developed | 363 | 1208 | 115 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-01-19 | Proposed | 5842000 | 2024
Developed | 377 | 376 | 345 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-03-16 | Proposed | 9020000 | 2024
Developed | 378 | 1620 | 345 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-03-16 | Under Construction | 8821000 | 2024
Developed | 379 | 1132/1505 | 115 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-04-20 | Proposed | 13383000 | 2024
Developed | 413 | 364 | 345 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-07-27 | Proposed | 12610000 | 2024
Developed | 414 | 348 | 345 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-07-27 | Proposed | 9700000 | 2024
Developed | 416 | Southington SS | 115 | Eversource | CT | Aging substation infrastructure, Relays | Relay upgrades | 2023-08-16 | Proposed | 13850000 | 2024
Developed | 90 | Canal Station #980 SS | 345/115 | Eversource | EMA | BPS Separation and Asset Condition Project | Installation of new 345-kV relay and control enclosure with new relay systems and upgrade of existing 115-kV protection system | 2018-06-13 | Under Construction | 41237000 | 2024
Developed | 364 | High Hill #644 SS | 115 | Eversource | EMA | Aging substation infrastructure | Installation of new 115-kV relay and control enclosure with new relay systems and upgrade of existing 115-kV protection system | 2022-12-13 | Under Construction | 19270000 | 2024
Developed | 365 | 389 | 345 | Eversource | EMA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-01-19 | Planned | 6648000 | 2024
Developed | 281 | Z180 | 115 | Eversource | NH | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2020-12-16 | Under Construction | 14529000 | 2024
Developed | 343 | Timber Swamp SS | 345 | Eversource | NH | Aging substation infrastructure, 345KV Breakers | Replace circuit breakers | 2022-05-18 | Under Construction | 7431000 | 2024
Developed | 351 | Greggs SS | 115 | Eversource | NH | Aging substation infrastructure | Rebuild substation as a breaker and one half scheme | 2022-10-15 | Under Construction | 72193000 | 2024
Developed | 386 | B112 | 115 | Eversource | NH | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-05-18 | Under Construction | 105432000 | 2024
Developed | 398 | B143 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-05-18 | Proposed | 17275000 | 2024
Developed | 401 | C189 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-06-15 | Under Construction | 12808000 | 2024
Developed | 402 | H137 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-06-15 | Under Construction | 7788000 | 2024
Developed | 403 | M108 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-06-15 | Proposed | 13399000 | 2024
Developed | 404 | V182 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-06-15 | Proposed | 32915000 | 2024
Developed | 405 | H141 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-06-15 | Under Construction | 18750000 | 2024
Developed | 407 | R169 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-06-15 | Proposed | 8400000 | 2024
Developed | 408 | F162 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-06-15 | Proposed | 21840000 | 2024
Developed | 410 | I158 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-06-15 | Proposed | 28630000 | 2024
Developed | 370 | 381/379 | 345 | Eversource | NH/WMA | Degradation of shieldwire | Replace shieldwire with OPGW | 2023-01-19 | Under Construction | 8238000 | 2024
Developed | 250 | 1231/1242 | 115 | Eversource | WMA | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2022-08-24 | Under Construction | 158504000 | 2024
Developed | 339 | Northfield Mountain SS | 345 | Eversource | WMA | Aging substation infrastructure, 345KV Breakers | Replace circuit breakers | 2022-05-18 | Under Construction | 9005000 | 2024
Developed | 376 | 1000, 1090, 1070, 1080, 1490 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-03-16 | Under Construction | 37198000 | 2025
Developed | 352 | 1637/1720 and 1714/1720/1222 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2022-11-15 | Under Construction | 159590000 | 2025
Developed | 372 | 1241, 1483, 1545, 1580, Pootatuck SS | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-02-15 | Proposed | 46090000 | 2025
Developed | 373 | 1483, 1545,1580, 1710, 1730, Devon SS | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-02-15 | Proposed | 41110000 | 2025
Developed | 374 | 1580, 1808, Christian St SS, Stevenson SS | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-02-15 | Proposed | 52960000 | 2025
Developed | 375 | 1142, 1319, 1403, 1580, 1808, Towantic SS, Christian Rd SS, Beacon Falls SS, South Naugatuck SS | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-02-15 | Proposed | 115100000 | 2025
Developed | 415 | 1726 | 115 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-07-27 | Proposed | 8863000 | 2025
Developed | 297 | 282-520 & 282-521 | 115 | Eversource | EMA | Degradation of pipes and underground conductor | Rebuild lines with LPP, repair infrastructure | 2021-07-22 | Planned | 69600000 | 2025
Developed | 317 | Edgar Station #150 SS | 115 | Eversource | EMA | Failing brown glass insulators | Replace brown glass insulators and additional aging substation components | 2021-12-15 | Under Construction | 4000000 | 2025
Developed | 421 | NERC CIP-014 - Physical Security Upgrades - Round 1 | 345/115 | Eversource | EMA | CIP-014 Physical Security Upgrades | CIP-014 Physical Security Upgrades | 2016-07-13 | Under Construction | 121092000 | 2025
Developed | 349 | Scobie Pond SS | 345 | Eversource | NH | Aging control house infrastructure, trench system | Replace and install new secondary trench system, and expand control house | 2022-06-15 | Under Construction | 19652000 | 2025
Developed | 382 | F139 | 115 | Eversource | NH | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-03-16 | Proposed | 46628000 | 2025
Developed | 406 | A164 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-06-15 | Proposed | 66960000 | 2025
Developed | 409 | G146 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-06-15 | Proposed | 58380000 | 2025
Developed | 411 | Deerfield SS | 345/115 | Eversource | NH | Aging substation infrastructure, relays | Relay Upgrades | 2023-06-16 | Proposed | 5820000 | 2025
Developed | 338 | Millstone | 345 | Eversource | CT | Aging substation infrastructure, 345KV Breakers | Replace circuit breakers | 2022-05-18 | Proposed | 17600000 | 2026
Developed | 412 | 1704 | 115 | Eversource | CT | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2023-06-15 | Proposed | 169300000 | 2026
Developed | 423 | 1722 | 115 | Eversource | CT | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2023-06-15 | Proposed | 132300000 | 2026
Developed | 387 | Q195 | 115 | Eversource | NH | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-05-18 | Proposed | 100000000 | 2026
Developed | 388 | U199 | 115 | Eversource | NH | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-05-18 | Proposed | 51180000 | 2026
Developed | 293 | Ludlow 19S SS | 345/115 | Eversource | WMA | BPS Separation and Asset Condition Project | Installation of new 345-kV relay and control enclosure with new relay systems and upgrade of existing 115-kV protection system | 2021-02-17 | Proposed | 61520000 | 2026
Developed | 44 | Mystic #20 SS | 115 | Eversource | EMA | Aging substation infrastructure | Installation of new 115-kV relay and control enclosure with new relay systems and upgrade of existing 115-kV protection system | 2017-06-21 | Under Construction | 41113000 | 2028
Developed | ACL 146 | 327 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2019-02-13 | Under Construction | 87877000 | 2024
Developed | ACL 145 | Carpenter Hill Substation | 345/115 | New England Power | MA | Aging substation infrastructure, relays | Rebuild control house | 2018-09-27 | Under Construction | 18750347.1769 | 2024
Developed | ACL 418 | 308 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-08-16 | Proposed | 15770000 | 2024
Developed | ACL 354 | Maplewood Substation | 115 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation | 2023-01-19 | Proposed | 11584041.6045 | 2024
Developed | TBD | Northboro Rd | 115/69 | New England Power | MA | Aging substation infrastructure, relays | Circuit breaker replacement | 2023-07-25 | Under Construction | 5230000 | 2024
Developed | ACL 333 | Stafford St Substation | 115 | New England Power | MA | Aging substation infrastructure, relays | Build new substation | 2022-07-20 | Under Construction | 35620750.7934 | 2025
Developed | ACL 294 | Millbury 2 Substation | 115 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation | 2021-05-19 | Under Construction | 28040000 | 2025
Developed | ACL 237 | Royalston 701 Substation | 69 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation | 2021-09-22 | Planned | 12604808.4931 | 2025
Developed | ACL 419 | S8 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-07-25 | Proposed | 88000000 | 2026
Developed | ACL 235 | Vernon Substation | 69 | New England Power | NH | Aging substation infrastructure, relays | Relocate substation | 2021-11-17 | Proposed | 22080924.3619 | 2026
Developed | ACL 336 | Tewksbury Sub 22 Substation | 230/115 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation | 2022-08-24 | Proposed | 35490000 | 2027
Developed | ACL 328 | Bridgewater Substation | 345/115 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation | 2022-04-28 | Proposed | 25950000 | 2027
Developed | ACL 385 | E131 | 115 | New England Power | MA/VT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-04-20 | Proposed | 138300000 | 2027
Developed | ACL 384 | Shutesbury Substation | 69 | New England Power | MA | Aging substation infrastructure, relays | Rebuild substation | 2023-03-16 | Proposed | 8900000 | 2028
Developed | ACL 308 | Moore 20 Substation | 230/115 | New England Power | NH | Aging substation infrastructure, relays | Partial rebuild substation | 2021-09-22 | Planned | 49307000 | 2028
Developed | ACL-98 | L-190 & G-185S | 115 | Rhode Island Energy | RI | NPCC Directory # 1 Protection Modification - Phase 5 | Solution covered under RSP 1815 & ACL 335. | 2017-12-20 | Concept | 0 | 2024
Developed | ACL-335 | L-190 & G-185S | 115 | Rhode Island Energy | RI | Degradation of poles, towers, shield wire, and/or conductor. NPCC Directory # 1 Protection Modification - Phase 5 | Replace poles, towers, shield wire, and conductor. | 2022-07-20 | Under Construction | 8493000 | 2024
Developed | ACL-99 | R-144, Q-143S, & V-148N | 115 | Rhode Island Energy | RI | NPCC Directory # 1 Protection Modification - Phase 4. | Upgrade line protection to dual high speed systems. | 2017-12-20 | Concept | 5100000 | 2025
Developed | ACL-150 | 315 | 345 | Rhode Island Energy | RI | Degradation of poles, towers, and/or shield wire. | Replace poles, towers and shield wire | 2019-02-05 | Planned | 25107000 | 2025
Developed | 19 | Congress | 115 | United Illuminating Company | CT | Coastal Substation Flood Mitigation Study Project | Install flood wall | 2015-09-16 | Under Construction | 35190000 | 2023
Developed | 20 | Grand Avenue | 115 | United Illuminating Company | CT | Coastal Substation Flood Mitigation Study Project | Install flood wall | 2015-09-16 | Planned | 41800000 | 2024
Developed | 21 | Singer | 345 | United Illuminating Company | CT | Coastal Substation Flood Mitigation Study Project | Install flood wall | 2015-09-16 | Under Construction | 26450000 | 2024
Developed | 22 | Pequannock | 115 | United Illuminating Company | CT | Coastal Substation Flood Mitigation Study Project | Rebuild on new site with higher equipment elevation | 2015-09-16 | Under Construction | 106106899 | 2024
Developed | 239 | 1560-3, 1594, 1808 | 115 | United Illuminating Company | CT | Derby Junction to Ansonia Corridor 115 kV Transmission Upgrades | Replace poles, towers, conductor, and shield wire | 2019-10-24 | Planned | 71000000 | 2024
Developed | 91 | 8809A-2 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Planned | 17422320 | 2025
Developed | 151 | 8809B-2 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Planned | 17422320 | 2025
Developed | 159 | 88003A-3 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Planned | 25905000 | 2025
Developed | 160 | 88003B-3 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Planned | 25905000 | 2025
Developed | 161 | 88003A-2 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Planned | 25905000 | 2025
Developed | 162 | 88003B-2 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Planned | 25905000 | 2025
Developed | 154 | 91001-1 & 91001-2 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Planned | 51963324 | 2026
Developed | 155 | 88005A-1 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Planned | 69080000 | 2026
Developed | 156 | 88005B-1 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Planned | 69080000 | 2026
Developed | 157 | 8804A | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Planned | 51810000 | 2027
Developed | 158 | 8804B | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Planned | 51810000 | 2027
Developed | 152 | 1130 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Planned | 21493614 | 2028
Developed | 153 | 1430 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Planned | 71391220 | 2028
Developed | ACL 350 | Middlebury substation | 115 | Vermont Electric Power Co | VT | Aging substation infrastructure, relays | Partial rebuild substation | 2022-11-09 | Under Construction | 9000000 | 2024
Developed | ACL 232 | Line 340 | 345 | Vermont Electric Power Co | VT | Degradation of structures | Replace poles, crossarm and insulators | 2020-03-13 | Under Construction | 37200000 | 2025
Developed | ACL 284 | Line K24 | 115 | Vermont Electric Power Co | VT | Degradation of structures | Replace poles, crossarm and insulators | 2021-02-12 | Under Construction | 15240000 | 2025
Developed | ACL 305 | Line K42 | 115 | Vermont Electric Power Co | VT | Degradation of structures | Complete line rebuild | 2023-10-19 | Under Construction | 84000000 | 2026
Developed | ACL 330 | Line K21 | 115 | Vermont Electric Power Co | VT | Degradation of structures | Replace poles, crossarm and insulators | 2022-05-12 | Under Construction | 20550000 | 2026
Developed | ACL 331 | Line K32 | 115 | Vermont Electric Power Co | VT | Degradation of structures | Replace poles, crossarm and insulators | 2022-05-12 | Under Construction | 14320000 | 2026
Developed | ACL 383 | Line K43 | 115 | Vermont Electric Power Co | VT | Degradation of structures | Replace poles, crossarm and insulators | 2023-04-14 | Under Construction | 16900000 | 2026
Developed | ACL 332 | Line K50 | 115 | Vermont Electric Power Co | VT | Degradation of structures | Replace poles, crossarm and insulators | 2022-05-12 | Under Construction | 31280000 | 2027
Under Development | TBD | S3038 | 345 | CMP | ME | Woodpecker damaged structures | Structure replacements |  |  |  |  | TBD | Group 1: $5-10M | 2 Year
Under Development | TBD | S207 | 115 | CMP | ME | Woodpecker damaged structures | Structure replacements |  |  |  |  | TBD | Group 1: $5-10M | 2 Year
Under Development | TBD | S375 | 345 | CMP | ME | Woodpecker damaged structures | Structure replacements |  |  |  |  | TBD | Group 1: $5-10M | 2 Year
Under Development | TBD | S374 | 345 | CMP | ME | Woodpecker damaged structures | Structure replacements |  |  |  |  | TBD | Group 1: $5-10M | 2 Year
Under Development | TBD | S385 | 345 | CMP | ME | Woodpecker damaged structures | Structure replacements |  |  |  |  | TBD | Group 1: $5-10M | 2 Year
Under Development | TBD | 3403C and 3403D | 345 | Eversource | CT | Installation of stop joints to address overall reliability and enviornental risk of fluid leakage | Installation/replacement of Motor Operated Valves on underground lines |  |  |  |  | 2023-12-20 | Group 2: $10-25M | 2 Year
Under Development | TBD | 3252 | 115 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-02-01 | Group 1: $5-10M | 2 Year
Under Development | TBD | 387 | 115 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-02-01 | TBD | 2 Year
Under Development | TBD | 1759 | 115 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-02-01 | TBD | 2 Year
Under Development | TBD | A152 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2023-12-20 | Group 1: $5-10M | 2 Year
Under Development | TBD | M127 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2023-12-20 | Group 1: $5-10M | 2 Year
Under Development | TBD | Scobie Pond SS | 115 | Eversource | NH | Aging substation infrastructure, Relays | Relay upgrades |  |  |  |  | 2024-02-01 | Group 1: $5-10M | 2 Year
Under Development | TBD | Long Mountain SS | 345 | Eversource | CT | Aging substation infrastructure and BPS/Directory 4 compliance | BPS/DIR4 upgrades, breaker replacement |  |  |  |  | 2024-04-01 | Group 2: $10-25M | 3-5 Year
Under Development | TBD | Compo SS | 115 | Eversource | CT | Aging substation infrastructure, Relays | Relay upgrades |  |  |  |  | 2024-12-01 | Group 1: $5-10M | 3-5 Year
Under Development | TBD | 362, 376, 1772 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2024-01-17 | TBD | 3-5 Year
Under Development | TBD | 1440 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2024-08-01 | TBD | 3-5 Year
Under Development | TBD | 1977 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2024-08-01 | TBD | 3-5 Year
Under Development | TBD | 1771 , 1670-1, 1670-2 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2024-03-01 | TBD | 3-5 Year
Under Development | TBD | Holbrook #478 SS | 115 | Eversource | EMA | Failing brown glass insulators | Replace brown glass insulators and additional aging substation components |  |  |  |  | 2025-10-01 | Group 2: $10-25M | 3-5 Year
Under Development | TBD | K Street #385 SS | 115 | Eversource | EMA | Failing brown glass insulators | Replace brown glass insulators and additional aging substation components |  |  |  |  | 2025-10-01 | Group 2: $10-25M | 3-5 Year
Under Development | TBD | Baker St #110 SS | 115 | Eversource | EMA | Failing brown glass insulators | Replace brown glass insulators and additional aging substation components |  |  |  |  | 2025-10-01 | Group 2: $10-25M | 3-5 Year
Under Development | TBD | Pilgrim #725 SS | 345 | Eversource | EMA | Aging substation infrastructure and BPS/Directory 4 compliance | BPS/DIR4 upgrades, breaker replacement |  |  |  |  | 2025-03-01 | TBD | 3-5 Year
Under Development | TBD | 211-514X | 115 | Eversource | EMA | Degradation of pipes and underground conductor | Reconductor or rebuild lines |  |  |  |  | 2024-10-18 | TBD | 3-5 Year
Under Development | TBD | X-178 | 115 | Eversource | NH | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2024-01-17 | Group 4: $100M+ | 3-5 Year
Under Development | TBD | Amherst SS | 345 | Eversource | NH | Aging substation infrastructure, 345KV Breakers | Replace circuit breakers |  |  |  |  | 2024-06-01 | Group 1: $5-10M | 3-5 Year
Under Development | TBD | Northfield Mountain SS | 345 | Eversource | WMA | BPS Separation and Asset Condition Project | Review of existing control house and primary and secondary protection schemes |  |  |  |  | 2024-06-01 | TBD | 3-5 Year
Under Development | TBD | 1028 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2024-08-01 | TBD | 6-10 Year
Under Development | TBD | 1430 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2024-08-01 | TBD | 6-10 Year
Under Development | TBD | 1578 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2024-08-01 | TBD | 6-10 Year
Under Development | TBD | 1146 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2024-08-01 | TBD | 6-10 Year
Under Development | TBD | 1608 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2024-08-01 | TBD | 6-10 Year
Under Development | TBD | 1867-1/1880-1 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2024-08-01 | Group 3: $25-100M | 6-10 Year
Under Development | TBD | Mystic #250 SS | 115 | Eversource | EMA | Failing brown glass insulators | Replace brown glass insulators and additional aging substation components |  |  |  |  | 2025-10-01 | Group 2: $10-25M | 6-10 Year
Under Development | TBD | 1450 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2024-08-01 | TBD | TBD
Under Development | TBD | 1750 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2024-08-01 | TBD | TBD
Under Development | TBD | E205E | 230 | New England Power | MA | urgent repairs | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 1: $5-10M | 2 Year
Under Development | TBD | 314 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | TBD | 323 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | TBD | 337 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | TBD | 343 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | TBD | 339 349 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | TBD | A179 Q169 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year
Under Development | TBD | Ayer Substation | 115/69 | New England Power | MA | Aging substation infrastructure, relays | Rebuild substation |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | TBD | Chartley Pond Substation | 115 | New England Power | MA | Aging substation infrastructure, relays | Rebuild substation |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year
Under Development | TBD | D156 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | ACL 236 | Deerfield #4 Substation | 115/69 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | TBD | E183/F184 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2023-12-20 | Group 2: $10-25M | 3-5 Year
Under Development | TBD | I1355S J136S | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | TBD | K137E L138E | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | TBD | M165 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | TBD | O141 P142 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year
Under Development | TBD | O15N | 69 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | TBD | S145E T146E | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | TBD | W23 | 69 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | TBD | Westminster Switch Tower | 69 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | TBD | Y177 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | TBD | Z126 A127 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 1: $5-10M | 3-5 Year
Under Development | N/A | M13 & L14 | 115 | Rhode Island Energy | RI | Degradation of poles, towers, shield wire, and/or conductor. | Replace poles, towers, shield wire, and conductor. |  |  |  |  | 2023-10-18 | Group 3: $25-100M | 2 Year
Under Development | N/A | E-183W | 115 | Rhode Island Energy | RI | Degradation of poles, towers, shield wire, and/or conductor. | Replace poles, towers, shield wire, and conductor. |  |  |  |  | 2023-10-18 | Group 2: $10-25M | 2 Year
Under Development | N/A | S-171N, T-172N, S-171S, & T-172S | 115 | Rhode Island Energy | RI | Degradation of poles, towers, shield wire, and/or conductor. | Replace targeted poles, towers, shield wire, and conductor. |  |  |  |  | 2023-10-18 | Group 2: $10-25M | 2 Year
Under Development |  | St. Johnsbury substation | 115 | Vermont Electric Power Co | VT | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | TBD | Group 1: $5-10M | 3-5 year
Under Evaluation | N/A | 165 | 115 | Central Maine Power | ME | Aging Line, Needs Assessment underway | Partial rebuild |  |  |  |  | TBD | Group 3: $25-100M | 6-10 Year
Under Evaluation | TBD | Middletown SS | 115 | Eversource | CT | Aging substation infrastructure, Relays | Relay upgrades |  |  |  |  | TBD | TBD | 2 Year
Under Evaluation | TBD | Haddam SS | 115 | Eversource | CT | Aging substation infrastructure, Relays | Relay upgrades |  |  |  |  | TBD | TBD | 2 Year
Under Evaluation | TBD | 342/355 | 345 | Eversource | EMA | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | TBD | TBD | 2 Year
Under Evaluation | TBD | Line 1867-2/1880-3 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Evaluation | TBD | Montville SS | 345/115 | Eversource | CT | BPS/DIR4 upgrades, preimary and secondary relay upgrades, control house upgrades, etc. | Review of existing control house and primary and secondary protection schemes |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Evaluation | TBD | Manchester SS | 345 | Eversource | CT | Aging substation infrastructure, 345KV Breakers | Replace circuit breakers |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | TBD | 325 | 345 | Eversource | EMA | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | TBD | 331 | 345 | Eversource | EMA | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | TBD | Mystic #250 SS | 345/115 | Eversource | EMA | BPS/DIR4 upgrades, preimary and secondary relay upgrades, control house upgrades, etc. | Review of existing control house and primary and secondary protection schemes |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | TBD | Fitzwilliam SS | 345 | Eversource | NH | Aging substation infrastructure, 345KV Breakers | Replace circuit breakers |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | TBD | Newington SS | 345/115 | Eversource | NH | BPS Separation and Asset Condition Project | Review of existing control house and primary and secondary protection schemes |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | TBD | Ludlow SS | 345 | Eversource | WMA | Aging substation infrastructure, 345KV Breakers | Replace circuit breakers |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | TBD | Gunn 15A SS | 115 | Eversource | WMA | Aging substation infrastructure, Relays | Relay upgrades |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | TBD | 346 | 345 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | Group 4: $100M+ | 6-10 Year
Under Evaluation | TBD | 365 | 345 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | Group 4: $100M+ | 6-10 Year
Under Evaluation | TBD | 351/358 | 345 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | Group 4: $100M+ | 6-10 Year
Under Evaluation | TBD | 385-510/511 | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | Lines 329-530/1 | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | 514-512/513 | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | 329-520/521 | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | 148/522X/Y | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | 282-507/602 | 230/115 | Eversource | EMA | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | 488-518XY | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | 423-515 | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | 514-510/511 | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | TBD | TBD
Under Evaluation | TBD | 329-530/531 | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | TBD | TBD
Under Evaluation | TBD | K Street #385 SS | 345/115 | Eversource | EMA | BPS/DIR4 upgrades, preimary and secondary relay upgrades, control house upgrades, etc. | Review of existing control house and primary and secondary protection schemes |  |  |  |  | TBD | TBD | TBD
Under Evaluation | TBD | 496-528/529 | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | TBD | TBD
Under Evaluation | TBD | White Lake | 115 | Eversource | NH | Aging substation infrastructure | TBD |  |  |  |  | TBD | TBD | TBD
Under Evaluation | TBD | 396/3001 | 345 | MEPCO | ME | Aging Line, inspections underway | Structure replacements |  |  |  |  | TBD | Group 4: $100M+ | TBD
Under Evaluation | ACL 400 | Adams Substation | 115/69 | New England Power | MA | Aging substation infrastructure, relays | Relocate substation outside of flood zone |  |  |  |  | TBD | Group 3: $25-100M | 6-10 Year
Under Evaluation | ACL 337 | E-5/F-5 | 69 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 4: $100M+ | 6-10 Year
Under Evaluation | TBD | V5/U6 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 4: $100M+ | 6-10 Year
Under Evaluation | TBD | 301 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | 313 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | 331 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | E205E | 230 | New England Power | MA | rebuild to 345kV design | Replace poles, towers and/or shield wire |  |  |  |  | 2023-11-30 | Group 4: $100M+ | 6-10 Year
Under Evaluation | TBD | Gardner Twr Sub Motorized switches | 69 | New England Power | MA | Aging substation infrastructure, relays | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 2: $10-25M | 6-10 Year
Under Evaluation | TBD | Otter River Substation | 69 | New England Power | MA | Aging substation infrastructure, relays | Rebuild substation |  |  |  |  | TBD | Group 3: $25-100M | 6-10 Year
Under Evaluation | TBD | Palmer #503 Substation | 115/69 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | TBD | Group 3: $25-100M | 6-10 Year
Under Evaluation | TBD | 356 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | 357 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | A127 B128 Z126 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | D130 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | E1 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | M39 | 69 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | Swansea 11 Substation | 115 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | Brayton Point | 345/115 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | Ware Substation | 69 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | ACL 237 | A-1/B-2 | 69 | New England Power | MA/VT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 4: $100M+ | 6-10 Year
Under Evaluation | TBD | E205W | 230 | New England Power | MA/VT | rebuild to 345kV design | Replace poles, towers and/or shield wire |  |  |  |  | 2023-11-30 | Group 4: $100M+ | 6-10 Year
Under Evaluation | N/A | 1870S | 115 | Rhode Island Energy | RI | Aging Line, inspections underway | Partial rebuild or targeted refurbishment |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Evaluation | N/A | 332 | 345 | Rhode Island Energy | RI | Aging Line, inspections underway | Partial rebuild or targeted refurbishment |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Evaluation | N/A | 347 | 345 | Rhode Island Energy | RI | Aging Line, inspections underway | Partial rebuild or targeted refurbishment |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Evaluation | N/A | Q-143 | 115 | Rhode Island Energy | RI | Aging Line, inspections underway | Partial rebuild or targeted refurbishment |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year
Under Evaluation | N/A | R-144N | 115 | Rhode Island Energy | RI | Aging Line, inspections underway | Partial rebuild or targeted refurbishment |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year
Under Evaluation | N/A | Franklin Square/Manchester St | 115 | Rhode Island Energy | RI | Aging relays, substation infrastructure | Relay Upgrades |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Evaluation | N/A | V-148N | 115 | Rhode Island Energy | RI | Aging Line | Partial rebuild or targeted refurbishment |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | N/A | R9 | 115 | Rhode Island Energy | RI | Aging Line | Partial rebuild or targeted refurbishment |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | N/A | Kent County 22 | 345/115 | Rhode Island Energy | RI | Aging relays | Relay Upgrades |  |  |  |  | TBD | Group 1: $5-10M | 6-10 Year
Under Evaluation | N/A | West Farnum | 345/115 | Rhode Island Energy | RI | Aging relays | Relay Upgrades |  |  |  |  | TBD | Group 1: $5-10M | 6-10 Year
Under Evaluation | N/A | Sherman Farm Rd | 345 | Rhode Island Energy | RI | Aging relays | Relay Upgrades |  |  |  |  | TBD | Group 1: $5-10M | 6-10 Year
Under Evaluation | N/A | 8500, 8700, 8702 | 115 | United Illuminating Company | CT | Obsolete LPFF UG cables, aging ducts and manholes | Replace with XLPE |  |  |  |  | TBD | Group 4: $100M+ | 6-10 Year
Under Evaluation |  | Line K19 | 115 | Vermont Electric Power Co | VT | Degradation of structures | Replace poles, crossarm and insulators |  |  |  |  | TBD | Group 1: $5-10M | 2 year
Under Evaluation |  | Line K51 | 115 | Vermont Electric Power Co | VT | Degradation of structures | Replace poles, crossarm and insulators |  |  |  |  | TBD | Group 2: $10-25M | 2 year
Under Evaluation |  | Sand Bar PST | 115 | Vermont Electric Power Co | VT | History of PST issues | Add smart valves device |  |  |  |  | TBD | Group 3: $25-100M | 3-5 year
Under Evaluation |  | Vermont Yankee substation | 115 | Vermont Electric Power Co | VT | Aging substation infrastructure | Partial rebuild substation |  |  |  |  | TBD | Group 1: $5-10M | 3-5 year
Under Evaluation |  | Granite Sync cond | 115 | Vermont Electric Power Co | VT | Aging controls | Control replacments |  |  |  |  | TBD | Group 1: $5-10M | 3-5 year
Under Evaluation |  | Line K54 | 115 | Vermont Electric Power Co | VT | Degradation of structures | Complete line rebuild |  |  |  |  | TBD | Group 3: $25-100M | 3-5 year
Under Evaluation |  | Line F206 | 230 | Vermont Electric Power Co | VT | Degradation of structures | Complete line rebuild |  |  |  |  | TBD | Group 3: $25-100M | 3-5 year
Under Evaluation |  | Cold River | 115 | Vermont Electric Power Co | VT | Aging substation infrastructure | Partial rebuild substation |  |  |  |  | TBD | Group 1: $5-10M | 3-5 year
Under Evaluation |  | Essex substation | 115 | Vermont Electric Power Co | VT | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | TBD | Group 1: $5-10M | 5-10 year
Under Evaluation |  | Coolidge transformer | 345/115 | Vermont Electric Power Co | VT | Aging transformer | Partial rebuild substation |  |  |  |  | TBD | Group 2: $10-25M | 5-10 year
Under Evaluation |  | Highgate Converter | 115 | Vermont Electric Power Co | VT | Aging substation infrastructure | Greenfield substation |  |  |  |  | TBD | Group 4: $100M+ | 5-10 year

## Contact information
For questions please contact the individuals below
Company | Name | Email
Avangrid (including UI, CMP and MEPCO) | Zachary Logan | zachary.logan@cmpco.com
Eversource | Dave Burnham | david.burnham@eversource.com
National Grid | Rafael Panos | rafael.panos@nationalgrid.com
Rhode Island Energy | Brian Thomson | BKThomson@pplweb.com
VELCO | Frank Ettori | fettori@velco.com
Versant* | Dave Norman | david.norman@versantpower.com
*Note: there are no current or forecasted projects by Versant that meet the conditions for inclusion