## Exhibit
New England Transmission Owner Asset Condition Project Forecast
NOTE: "Under Evaluation" and "Under Development" projects are provided for illustrative purposes only and are not necessarily indicative of actual projects and identified needs.
Project Stages
Developed – Full scope/conceptual cost estimates have been developed and project has been presented to PAC; ISD Year and Estimated Costs available
Under Development – Project planning is underway; project scope and conceptual cost estimates are currently being developed; Cost Category information available
Under Evaluation – Currently being evaluated for possible asset condition project, but no formal scope/cost estimates have been developed; Planning Horizon information available
[8 empty] | Developed Projects |  |  |  | Under Development
Project Stage | ACL ID | Line Number or Substation Name | kV | Primary Equipment Owner | State | Current Asset Condition | Anticipated Solution | PAC Presentation Date | Status (Concept, Proposed, Planned, Under Construction) | Estimated Cost | Estimated ISD | Anticipated PAC Presentation Date | Cost Category | Planning Horizon
Developed | 259 | 1163/1550 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-01-19 | Under Construction | 34486000 | 2024
Developed | 267 | 3041 | 345 | Eversource | CT | Degradation of poles and/or towers and PINCO insulators | Replace of poles and/or towers and PINCO insulators | 2021-01-21 | Under Construction | 14534000 | 2024
Developed | 269 | 3754 | 345 | Eversource | CT | Degradation of poles and/or towers and PINCO insulators | Replace of poles and/or towers and PINCO insulators | 2021-01-23 | Under Construction | 4400000 | 2024
Developed | 358 | 3041 | 345 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2022-10-19 | Planned | 11600000 | 2024
Developed | 360 | East Devon SS | 345/115 | Eversource | CT | Aging substation infrastructure, relays | Relay Upgrades | 2022-10-19 | Under Construction | 6720000 | 2024
Developed | 362 | 1355/1610 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2022-12-13 | Under Construction | 50398000 | 2024
Developed | 363 | 1208 | 115 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-01-19 | Under Construction | 9373000 | 2024
Developed | 372 | 1241, 1483, 1545, 1580, Pootatuck SS | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-02-15 | Under Construction | 52236000 | 2024
Developed | 376 | 1000, 1090, 1070, 1080, 1490 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-03-16 | Under Construction | 37198000 | 2024
Developed | 416 | Southington SS | 115 | Eversource | CT | Aging substation infrastructure, Relays | Relay upgrades | 2023-08-16 | Under Construction | 13850000 | 2024
Developed | 425 | M127 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-12-20 | Under Construction | 9834000 | 2024
Developed | 435 | NERC CIP-014 - Physical Security Upgrades - Round2/Site 1 | 115 | Eversource | CT | CIP-014 Physical Security Upgrades | CIP-014 Physical Security Upgrades | 2016-07-18 | Under Construction | 2213000 | 2024
Developed | 90 | Canal #980 SS | 345/115 | Eversource | EMA | BPS Separation and Asset Condition Project | Installation of new 345-kV relay and control enclosure with new relay systems and upgrade of existing 115-kV protection system | 2018-06-13 | Under Construction | 41237000 | 2024
Developed | 315 | 191 | 115 | Eversource | EMA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2021-12-15 | Under Construction | 27840000 | 2024
Developed | 340 | Holbrook #478 SS | 345/115 | Eversource | EMA | Aging substation infrastructure, autotransformer | Replace autotransformer | 2022-08-24 | Under Construction | 10155000 | 2024
Developed | 364 | High Hill #644 SS | 115 | Eversource | EMA | Aging substation infrastructure | Installation of new 115-kV relay and control enclosure with new relay systems and upgrade of existing 115-kV protection system | 2022-12-13 | Under Construction | 19270000 | 2024
Developed | 365 | 389 | 345 | Eversource | EMA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-01-19 | Under Construction | 6648000 | 2024
Developed | 367 | P106 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2022-09-21 | Under Construction | 5634000 | 2024
Developed | 368 | Q171 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2022-09-21 | Under Construction | 14966000 | 2024
Developed | 386 | B112 | 115 | Eversource | NH | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-05-18 | Under Construction | 105432000 | 2024
Developed | 389 | 391 | 345 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-05-18 | Under Construction | 12367000 | 2024
Developed | 391 | R193 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-05-18 | Under Construction | 7704000 | 2024
Developed | 399 | J114 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-05-18 | Under Construction | 9709000 | 2024
Developed | 404 | V182 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-06-15 | Under Construction | 32915000 | 2024
Developed | 405 | H141 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-06-15 | Under Construction | 18750000 | 2024
Developed | 370 | 381/379 | 345 | Eversource | NH/WMA | Degradation of shieldwire | Replace shieldwire with OPGW | 2023-01-19 | Under Construction | 8238000 | 2024
Developed | 250 | 1231/1242 | 115 | Eversource | WMA | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2022-08-24 | Under Construction | 158504000 | 2024
Developed | 339 | Northfield Mountain SS | 345 | Eversource | WMA | Aging substation infrastructure, 345KV Breakers | Replace circuit breakers | 2022-05-18 | Under Construction | 9005000 | 2024
Developed | 178 | 3754 | 345 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2019-08-08 | Under Construction | 8200000 | 2025
Developed | 258 | 1268/1485/1887/1622 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2021-01-19 | Under Construction | 49522000 | 2025
Developed | 266 | 387 | 345 | Eversource | CT | Degradation of poles and/or towers and PINCO insulators | Replace of poles and/or towers and PINCO insulators | 2021-01-21 | Under Construction | 12781000 | 2025
Developed | 352 | 1637/1720 and 1714/1720/1222 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2022-11-15 | Under Construction | 159590000 | 2025
Developed | 356 | 348 | 345 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2022-09-21 | Proposed | 8400000 | 2025
Developed | 357 | 1772 | 115 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2022-09-21 | Under Construction | 20730000 | 2025
Developed | 359 | 362 | 345 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2022-11-15 | Under Construction | 19163000 | 2025
Developed | 373 | 1483, 1545,1580, 1710, 1730, Devon SS | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-02-15 | Planned | 41110000 | 2025
Developed | 374 | 1580, 1808, Christian St SS, Stevenson SS | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-02-15 | Planned | 52960000 | 2025
Developed | 375 | 1142, 1319, 1403, 1580, 1808, Towantic SS, Christian Rd SS, Beacon Falls SS, South Naugatuck SS | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-02-15 | Planned | 115100000 | 2025
Developed | 377 | 376 | 345 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-03-16 | Under Construction | 9020000 | 2025
Developed | 413 | 364 | 345 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-07-27 | Under Construction | 13398000 | 2025
Developed | 414 | 348 | 345 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-07-27 | Planned | 9700000 | 2025
Developed | 431 | 362, 376, 1773 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2024-01-18 | Proposed | 43600000 | 2025
Developed | 432 | 362, 376, 1772 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2024-01-18 | Proposed | 13300000 | 2025
Developed | 317 | Edgar Station #150 SS | 115 | Eversource | EMA | Failing brown glass insulators | Replace brown glass insulators and additional aging substation components | 2021-12-15 | Under Construction | 4000000 | 2025
Developed | 421 | NERC CIP-014 - Physical Security Upgrades - Round 1 | 345/115 | Eversource | EMA | CIP-014 Physical Security Upgrades | CIP-014 Physical Security Upgrades | 2016-07-13 | Under Construction | 121092000 | 2025
Developed | 343 | Timber Swamp SS | 345 | Eversource | NH | Aging substation infrastructure, 345KV Breakers | Replace circuit breakers | 2022-05-18 | Under Construction | 7431000 | 2025
Developed | 349 | Scobie Pond SS | 345 | Eversource | NH | Aging control house infrastructure, trench system | Replace and install new secondary trench system, and expand control house | 2022-06-15 | Under Construction | 19652000 | 2025
Developed | 351 | Greggs SS | 115 | Eversource | NH | Aging substation infrastructure | Rebuild substation as a breaker and one half scheme | 2022-10-15 | Under Construction | 72193000 | 2025
Developed | 382 | F139 | 115 | Eversource | NH | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-03-16 | Under Construction | 46628000 | 2025
Developed | 406 | A164 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-06-15 | Planned | 66960000 | 2025
Developed | 407 | R169 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-06-15 | Under Construction | 8677000 | 2025
Developed | 408 | F162 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-06-15 | Under Construction | 18780000 | 2025
Developed | 409 | G146 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-06-15 | Under Construction | 53586000 | 2025
Developed | 410 | I158 | 115 | Eversource | NH | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-06-15 | Planned | 28630000 | 2025
Developed | 411 | Deerfield SS | 345/115 | Eversource | NH | Aging substation infrastructure, relays | Relay Upgrades | 2023-06-16 | Under Construction | 5820000 | 2025
Developed | 338 | Millstone SS | 345 | Eversource | CT | Aging substation infrastructure, 345KV Breakers | Replace circuit breakers | 2022-05-18 | Planned | 17600000 | 2026
Developed | 412 | 1704 | 115 | Eversource | CT | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2023-06-15 | Proposed | 169300000 | 2026
Developed | 423 | 1722 | 115 | Eversource | CT | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes | 2023-06-15 | Proposed | 132300000 | 2026
Developed | 297 | 282-520 & 282-521 | 115 | Eversource | EMA | Degradation of pipes and underground conductor | Rebuild lines with LPP, repair infrastructure | 2021-07-22 | Planned | 69598000 | 2026
Developed | 387 | Q195 | 115 | Eversource | NH | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-05-18 | Proposed | 100000000 | 2026
Developed | 388 | U199 | 115 | Eversource | NH | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2023-05-18 | Planned | 51180000 | 2026
Developed | TBD | X178 | 115 | Eversource | NH | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor | 2024-02-28 | Proposed | 384610000 | 2026
Developed | 293 | Ludlow 19S SS | 345/115 | Eversource | WMA | BPS Separation and Asset Condition Project | Installation of new 345-kV relay and control enclosure with new relay systems and upgrade of existing 115-kV protection system | 2021-02-17 | Under Construction | 61520000 | 2026
Developed | 44 | Mystic #20 SS | 115 | Eversource | EMA | Aging substation infrastructure | Installation of new 115-kV relay and control enclosure with new relay systems and upgrade of existing 115-kV protection system | 2017-06-21 | Under Construction | 41113000 | 2028
Developed | TBD | 396/3001 | 345 | MEPCO | ME | Asset Condition structure replacement program | Structure replacements | 2024-06-20 | Planned | 344380000 | 2039
Developed | 145 | Carpenter Hill Substation | 345/115 | New England Power | MA | Aging substation infrastructure, relays | Rebuild control house | 2018-09-27 | Under Construction | 14485000 | 2024
Developed | ACL 149 | 315 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2019-02-13 | Under Construction | 99072000 | 2024
Developed | 354 | Maplewood Substation | 115 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation | 2023-01-19 | Proposed | 6170000 | 2024
Developed | 417 | Northboro Rd Substation | 115/69 | New England Power | MA | Aging substation infrastructure, relays | Circuit breaker replacement | 2023-07-25 | Under Construction | 5230000 | 2024
Developed | 294 | Millbury 2 Substation | 115 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation | 2021-05-19 | Under Construction | 39127000 | 2025
Developed | 333 | Stafford St Substation | 115 | New England Power | MA | Aging substation infrastructure, relays | Build new substation | 2022-07-20 | Under Construction | 59953000 | 2025
Developed | 434 | M-165 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2024-02-28 | Under Construction | 15179309 | 2025
Developed | 439 | O-141/P-142 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2024-05-15 | Under Construction | 46746000 | 2025
Developed | 419 | S8 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-07-25 | Planned | 89338000 | 2026
Developed | 437 | 339/349 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2024-04-18 | Proposed | 72591000 | 2026
Developed | 235 | Vernon Substation | 69 | New England Power | NH | Aging substation infrastructure, relays | Relocate substation | 2021-11-17 | Proposed | 39690000 | 2026
Developed | 328 | Bridgewater Substation | 345/115 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation | 2022-04-28 | Proposed | 25950000 | 2027
Developed | 336 | Tewksbury Sub 22 Substation | 230/115 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation | 2022-08-24 | Proposed | 46360710 | 2027
Developed | 385 | E-131 | 115 | New England Power | MA/VT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-04-20 | Proposed | 138300000 | 2027
Developed | 384 | Shutesbury Substation | 69 | New England Power | MA | Aging substation infrastructure, relays | Rebuild substation | 2023-03-16 | Proposed | 8900000 | 2028
Developed | 236 | Deerfield #4 Substation | 115/69 | New England Power | MA | Aging substation infrastructure, relays | Full station rebuild | 2020-04-23 | Concept |  | 2028
Developed | 308 | Moore 20 Substation | 230/115 | New England Power | NH | Aging substation infrastructure, relays | Partial rebuild substation | 2021-09-22 | Planned | 49307000 | 2028
Developed | 420 | V5/U6 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2023-07-25 | Planned | 131980000 | 2029
Developed | 237 | A-1/B-2 | 69 | New England Power | MA/VT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2022-07-14 | Planned | 475831000 | 2029
Developed | 400 | Adams Substation | 115/69 | New England Power | MA | Aging substation infrastructure, relays | Relocate substation outside of flood zone | 2023-05-12 | Proposed | 55100000 | 2030
Developed | 337 | E-5/F-6 | 69 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2022-06-15 | Concept |  | 2030
Developed | 440 | W-149 | 115 | New England Power | NH/VT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers, conductor and shield wire | 2024-05-24 | Proposed | 491150000 | 2030
Developed | 433 | A-201/B-202 | 230 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire | 2024-01-11 | Concept |  | 2031
Developed | 438 | E-205E | 230 | New England Power | MA | rebuild to 345kV design | Replace poles, towers and/or shield wire | 2024-04-11 | Concept |  | 2033
Developed | 438 | E-205W | 230 | New England Power | MA/VT | rebuild to 345kV design | Replace poles, towers and/or shield wire | 2024-04-11 | Concept |  | 2033
Developed | 150 | 315 | 345 | Rhode Island Energy | RI | Degradation of poles, towers, and/or shield wire. | Replace poles, towers and shield wire | 2019-02-05 | Under Construction | 25107000 | 2024
Developed | 335 | L-190 & G-185S | 115 | Rhode Island Energy | RI | Degradation of poles, towers, shield wire, and/or conductor. NPCC Directory # 1 Protection Modification - Phase 5 | Replace poles, towers, shield wire, and conductor. | 2022-07-20 | Under Construction | 8493000 | 2024
Developed | 99 | R-144, Q-143S, & V-148N | 115 | Rhode Island Energy | RI | NPCC Directory # 1 Protection Modification - Phase 4. | Upgrade line protection to dual high speed systems. | 2017-12-20 | Concept | 5100000 | 2025
Developed | 430 | E-183W | 115 | Rhode Island Energy | RI | Degradation of poles, towers, shield wire, and/or conductor. | Replace poles, towers, shield wire, and conductor. | 2023-10-18 | Proposed | 10600000 | 2026
Developed | 426 | S-171N, T-172N, S-171S, & T-172S | 115 | Rhode Island Energy | RI | Degradation of poles, towers, shield wire, and/or conductor. | Replace targeted poles, towers, shield wire, and conductor. | 2023-10-18 | Planned | 10400000 | 2026
Developed | 427 | S-171N, T-172N, S-171S, & T-172S | 115 | Rhode Island Energy | RI | Degradation of poles, towers, shield wire, and/or conductor. | Replace targeted poles, towers, shield wire, and conductor. | 2023-10-18 | Planned | 10400000 | 2026
Developed | 22 | Pequannock | 115 | United Illuminating Company | CT | Coastal Substation Flood Mitigation Study Project | Rebuild on new site with higher equipment elevation | 2015-09-16 | Under Construction | 106106899 | 2025
Developed | 91 | 8809A-2 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Planned | 17422320 | 2025
Developed | 151 | 8809B-2 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Planned | 17422320 | 2025
Developed | 157 | 8804A | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Under Construction | 51810000 | 2025
Developed | 159 | 88003A-3 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Under Construction | 25905000 | 2025
Developed | 160 | 88003B-3 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Under Construction | 25905000 | 2025
Developed | 161 | 88003A-2 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Under Construction | 25905000 | 2025
Developed | 162 | 88003B-2 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Under Construction | 25905000 | 2025
Developed | 239 | 1560-3, 1594, 1808 | 115 | United Illuminating Company | CT | Derby Junction to Ansonia Corridor 115 kV Transmission Upgrades | Replace poles, towers, conductor, and shield wire | 2019-10-24 | Under Construction | 70986666 | 2025
Developed | 20 | Grand Avenue | 115 | United Illuminating Company | CT | Coastal Substation Flood Mitigation Study Project | Install flood wall | 2015-09-16 | Planned | 41800000 | 2026
Developed | 21 | Singer | 345 | United Illuminating Company | CT | Coastal Substation Flood Mitigation Study Project | Install flood wall | 2015-09-16 | Planned | 26450000 | 2026
Developed | 154 | 91001-1 & 91001-2 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Planned | 51963324 | 2026
Developed | 158 | 8804B | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Under Construction | 51810000 | 2026
Developed | 155 | 88005A-1 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Under Construction | 69080000 | 2027
Developed | 156 | 88005B-1 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Under Construction | 69080000 | 2027
Developed | 152 | 1130 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Planned | 21493614 | 2028
Developed | 153 | 1430 | 115 | United Illuminating Company | CT | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild in new location with new monopoles, conductor and shield wire | 2018-06-13 | Planned | 71391220 | 2030
Developed | 350 | Middlebury substation | 115 | Vermont Electric Power Co | VT | Aging substation infrastructure, relays | Partial rebuild substation | 2022-11-09 | Under Construction | 9640000 | 2024
Developed | 232 | Line 340 | 345 | Vermont Electric Power Co | VT | Degradation of structures | Replace poles, crossarm and insulators | 2020-03-13 | Under Construction | 39040000 | 2025
Developed | 284 | Line K24 | 115 | Vermont Electric Power Co | VT | Degradation of structures | Replace poles, crossarm and insulators | 2021-02-12 | Under Construction | 15240000 | 2025
Developed | 305 | Line K42 | 115 | Vermont Electric Power Co | VT | Degradation of structures | Complete line rebuild | 2023-10-19 | Under Construction | 84644000 | 2026
Developed | 330 | Line K21 | 115 | Vermont Electric Power Co | VT | Degradation of structures | Replace poles, crossarm and insulators | 2022-05-12 | Under Construction | 20550000 | 2026
Developed | 331 | Line K32 | 115 | Vermont Electric Power Co | VT | Degradation of structures | Replace poles, crossarm and insulators | 2022-05-12 | Under Construction | 14320000 | 2026
Developed | 383 | Line K43 | 115 | Vermont Electric Power Co | VT | Degradation of structures | Replace poles, crossarm and insulators | 2023-04-14 | Under Construction | 13980000 | 2026
Developed |  | St. Johnsbury substation | 115 | Vermont Electric Power Co | VT | Aging substation infrastructure, relays | Partial rebuild substation | Less than $5M PTFExpected to Start 10/1/24 |  | 18437234 | 2026
Developed | 436 | Sand Bar PST | 115 | Vermont Electric Power Co | VT | History of PST issues | Add smart valves device | 2024-02-28 |  | 47700000 | 2026
Developed | 332 | Line K50 | 115 | Vermont Electric Power Co | VT | Degradation of structures | Replace poles, crossarm and insulators | 2022-05-12 | Under Construction | 31280000 | 2027
Under Development | TBD | S3038 | 345 | CMP | ME | Woodpecker damaged structures | Structure replacements |  |  |  |  | 2024-10-23 | Group 1: $0-10M | 2 Year
Under Development | TBD | S207 | 115 | CMP | ME | Woodpecker damaged structures | Structure replacements |  |  |  |  | 2024-10-23 | Group 2: $10-25M | 2 Year
Under Development | TBD | S375 | 345 | CMP | ME | Woodpecker damaged structures | Structure replacements |  |  |  |  | 2024-10-23 | Group 1: $0-10M | 2 Year
Under Development | TBD | S374 | 345 | CMP | ME | Woodpecker damaged structures | Structure replacements |  |  |  |  | 2024-10-23 | Group 1: $0-10M | 2 Year
Under Development | TBD | S385 | 345 | CMP | ME | Woodpecker damaged structures | Structure replacements |  |  |  |  | 2024-10-23 | Group 1: $0-10M | 2 Year
Under Development | TBD | Manchester SS | 345 | Eversource | CT | Aging substation infrastructure, 345KV Breakers | Replace circuit breakers |  |  |  |  | 2024-09-01 | Group 2: $10-25M | 2 Year
Under Development | TBD | 1759 | 115 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-11-01 | Group 2: $10-25M | 2 Year
Under Development | TBD | 1752 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2024-11-01 | TBD | 2 Year
Under Development | TBD | 1773 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2024-11-01 | TBD | 2 Year
Under Development | TBD | 387 | 115 | Eversource | CT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-12-01 | Group 2: $10-25M | 2 Year
Under Development | TBD | 3403C and 3403D | 345 | Eversource | CT | Installation of stop joints to address overall reliability and enviornental risk of fluid leakage | Installation/replacement of Motor Operated Valves on underground lines |  |  |  |  | 2025-03-01 | Group 2: $10-25M | 2 Year
Under Development | TBD | 211-514X | 115 | Eversource | EMA | Degradation of pipes and underground conductor | Reconductor or rebuild lines |  |  |  |  | 2024-12-01 | Group 3: $25-100M | 2 Year
Under Development | TBD | 1356 (old 1525) | 115 | Eversource | WMA | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2024-11-01 | Group 1: $0-10M | 2 Year
Under Development | TBD | 1771 , 1670-1, 1670-2 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2024-11-01 | Group 3: $25-100M | 3-5 Year
Under Development | TBD | Long Mountain SS | 345 | Eversource | CT | Aging substation infrastructure and BPS/Directory 4 compliance | BPS/DIR4 upgrades, breaker replacement |  |  |  |  | 2025-03-01 | Group 2: $10-25M | 3-5 Year
Under Development | TBD | Compo SS | 115 | Eversource | CT | Aging substation infrastructure, Relays | Relay upgrades |  |  |  |  | 2025-05-01 | Group 1: $0-10M | 3-5 Year
Under Development | TBD | 1867-1/1880-1 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2025-09-01 | TBD | 3-5 Year
Under Development | TBD | 1440 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2025-09-01 | TBD | 3-5 Year
Under Development | TBD | Line 1867-2/1880-3 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | TBD | Montville SS | 345/115 | Eversource | CT | BPS/DIR4 upgrades, preimary and secondary relay upgrades, control house upgrades, etc. | Review of existing control house and primary and secondary protection schemes |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | TBD | 488-518XY | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | 2024-11-01 | TBD | 3-5 Year
Under Development | TBD | 65-502 | 115 | Eversource | EMA | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2025-02-01 | TBD | 3-5 Year
Under Development | TBD | Pilgrim #725 SS | 345 | Eversource | EMA | Aging substation infrastructure and BPS/Directory 4 compliance | BPS/DIR4 upgrades, breaker replacement |  |  |  |  | 2025-03-01 | TBD | 3-5 Year
Under Development | TBD | 342/355 | 345 | Eversource | EMA | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2025-03-01 | TBD | 3-5 Year
Under Development | TBD | 325 | 345 | Eversource | EMA | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2025-03-01 | TBD | 3-5 Year
Under Development | TBD | 331 | 345 | Eversource | EMA | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2025-03-01 | TBD | 3-5 Year
Under Development | TBD | Holbrook #478 SS | 115 | Eversource | EMA | Failing brown glass insulators | Replace brown glass insulators and additional aging substation components |  |  |  |  | 2025-10-01 | Group 2: $10-25M | 3-5 Year
Under Development | TBD | K Street #385 SS | 115 | Eversource | EMA | Failing brown glass insulators | Replace brown glass insulators and additional aging substation components |  |  |  |  | 2025-10-01 | Group 2: $10-25M | 3-5 Year
Under Development | TBD | Baker St #110 SS | 115 | Eversource | EMA | Failing brown glass insulators | Replace brown glass insulators and additional aging substation components |  |  |  |  | 2025-10-01 | Group 2: $10-25M | 3-5 Year
Under Development | TBD | Amherst SS | 345 | Eversource | NH | Aging substation infrastructure, 345KV Breakers | Replace circuit breakers |  |  |  |  | 2024-09-01 | Group 1: $0-10M | 3-5 Year
Under Development | TBD | Scobie Pond SS | 115 | Eversource | NH | Aging substation infrastructure, Relays | Relay upgrades |  |  |  |  | 2025-01-01 | Group 1: $0-10M | 3-5 Year
Under Development | TBD | Fitzwilliam SS | 345 | Eversource | NH | Aging substation infrastructure, 345KV Breakers | Replace circuit breakers |  |  |  |  | TBD | TBD | 3-5 Year
Under Development | TBD | Newington SS | 345/115 | Eversource | NH | BPS Separation and Asset Condition Project | Review of existing control house and primary and secondary protection schemes |  |  |  |  | TBD | TBD | 3-5 Year
Under Development | TBD | Ludlow SS | 345 | Eversource | WMA | Aging substation infrastructure, 345KV Breakers | Replace circuit breakers |  |  |  |  | 2025-09-01 | Group 2: $10-25M | 3-5 Year
Under Development | TBD | 1028 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2025-09-01 | TBD | 6-10 Year
Under Development | TBD | 1430 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2025-09-01 | TBD | 6-10 Year
Under Development | TBD | 1578 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2025-09-01 | TBD | 6-10 Year
Under Development | TBD | 1146 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2025-09-01 | TBD | 6-10 Year
Under Development | TBD | 1608 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2025-09-01 | TBD | 6-10 Year
Under Development | TBD | 282-507/602 | 115/230 | Eversource | EMA | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2025-03-01 | TBD | 6-10 Year
Under Development | TBD | Mystic #250 SS | 115 | Eversource | EMA | Failing brown glass insulators | Replace brown glass insulators and additional aging substation components |  |  |  |  | 2025-10-01 | Group 2: $10-25M | 6-10 Year
Under Development | TBD | 346 | 345 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | Group 4: $100M+ | 6-10 Year
Under Development | TBD | 365 | 345 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | Group 4: $100M+ | 6-10 Year
Under Development | TBD | 351/358 | 345 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | Group 4: $100M+ | 6-10 Year
Under Development | TBD | 329-520/521 | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | TBD | 6-10 Year
Under Development | TBD | 148/522X/Y | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | TBD | 6-10 Year
Under Development | TBD | 496-528/529 | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | TBD | 6-10 Year
Under Development | TBD | 314 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-12-24 | Group 3: $25-100M | 3-5 Year
Under Development | TBD | E-157/E-157W | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2025-03-01 | Group 4: $100M+ | 3-5 Year
Under Development | TBD | 323 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-11-24 | Group 3: $25-100M | 3-5 Year
Under Development | TBD | 337 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-10-24 | Group 4: $100M+ | 3-5 Year
Under Development | TBD | 343 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-08-01 | Group 3: $25-100M | 3-5 Year
Under Development | TBD | 394/397 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-12-24 | Group 4: $100M+ | 3-5 Year
Under Development | TBD | A-179/Q-169 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-11-01 | Group 3: $25-100M | 3-5 Year
Under Development | TBD | D-156 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-11-01 | Group 2: $10-25M | 3-5 Year
Under Development | TBD | Northboro Rd Substation | 115/69 | New England Power | MA | Control House | Control House Rebuild |  |  |  |  | 2024-12-01 | Group 3: $25-100M | 3-5 Year
Under Development | TBD | I-135S/J-136S | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2025-07-01 | Group 2: $10-25M | 3-5 Year
Under Development | TBD | K-137E/L-138E | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-09-01 | Group 4: $100M+ | 3-5 Year
Under Development | TBD | M-39 | 69 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-12-24 | Group 2: $10-25M | 3-5 Year
Under Development | TBD | O-15N | 69 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2025-05-01 | Group 3: $25-100M | 3-5 Year
Under Development | TBD | Y-151/L-164 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2025-01-01 | Group 3: $25-100M | 3-5 Year
Under Development | TBD | S-145E/T-146E | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-12-24 | Group 3: $25-100M | 3-5 Year
Under Development | TBD | W-23 | 69 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-12-24 | Group 2: $10-25M | 3-5 Year
Under Development | TBD | Westminster Switch Tower | 69 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | 2024-11-01 | Group 2: $10-25M | 3-5 Year
Under Development | TBD | Y-177 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-12-24 | Group 3: $25-100M | 3-5 Year
Under Development | TBD | 326 | 345 | New England Power | MA | Degradation of poles | Replace poles |  |  |  |  | 2025-01-01 | Group 3: $25-100M | 3-5 Year
Under Development | TBD | 302 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-10-24 | Group 2: $10-25M | 3-5 Year
Under Development | TBD | 338 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-10-24 | Group 2: $10-25M | 3-5 Year
Under Development | TBD | 301 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-10-24 | Group 4: $100M+ | 3-5 Year
Under Development | TBD | 313 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-08-01 | Group 2: $10-25M | 3-5 Year
Under Development | TBD | Brayton Point Substation | 345/115 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | 2024-08-24 | Group 3: $25-100M | 3-5 Year
Under Development | TBD | Q-117 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2025-03-01 | Group 3: $25-100M | 3-5 Year
Under Development | TBD | Z-126/A-127 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 1: $5-10M | 3-5 Year
Under Development | TBD | O-167/P-168 | 115 | New England Power | MA | HPFF UG Cable Replacement | Replace HPFF with solid dielectric cable |  |  |  |  | 2024-12-24 | Group 3: $25-100M | 3-5 Year
Under Development | TBD | Otter River Substation | 69 | New England Power | MA | Aging substation infrastructure, relays | Rebuild substation |  |  |  |  | TBD | Group 3: $25-100M | 6-10 Year
Under Development | TBD | Palmer #503 Substation | 115/69 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | TBD | Group 2: $10-25M | 6-10 Year
Under Development | TBD | U2 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2025-02-01 | Group 3: $25-100M | 6-10 Year
Under Development | N/A | REDACTED | REDACTED | Rhode Island Energy | RI | Insufficient security, unmonitored assets | Upgrade security perimeter, install interior lighting, install equipment monitoring |  |  |  |  | TBD | Group 1: $0-10M | 2 Year
Under Development | N/A | 1870S | 115 | Rhode Island Energy | RI | Aging conductor and shieldwire, and degradation of poles. | Replace poles, shield wire, and conductor. |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Development | N/A | H17 | 115 | Rhode Island Energy | RI | Aging wood poles | Replace wood poles |  |  |  |  | TBD | Group 1: $0-10M | 3-5 Year
Under Evaluation | N/A | 165 | 115 | Central Maine Power | ME | Aging Line, Needs Assessment underway | Partial rebuild |  |  |  |  | TBD | Group 3: $25-100M | 6-10 Year
Under Evaluation | TBD | 423-515 | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | 2024-11-01 | TBD | 2 Year
Under Evaluation | TBD | B172 | 115 | Eversource | NH | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | TBD | TBD | 2 Year
Under Evaluation | TBD | T198 | 115 | Eversource | NH | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | TBD | TBD | 2 Year
Under Evaluation | TBD | Northfield Mountain SS | 345 | Eversource | WMA | BPS Separation and Asset Condition Project | Review of existing control house and primary and secondary protection schemes |  |  |  |  | 2025-03-01 | TBD | 2 Year
Under Evaluation | TBD | 1977 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2025-09-01 | TBD | 3-5 Year
Under Evaluation | TBD | Middletown SS | 115 | Eversource | CT | Aging substation infrastructure, Relays | Relay upgrades |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | TBD | Haddam SS | 115 | Eversource | CT | Aging substation infrastructure, Relays | Relay upgrades |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | TBD | North Bloomfield SS | 345/115 | Eversource | CT | Aging substation infrastructure, autotransformer | Replace autotransformer |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | TBD | Tunnel SS | 345/115 | Eversource | CT | Aging substation infrastructure, autotransformer | Replace autotransformer |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | TBD | Millstone SS | 345/115 | Eversource | CT | BPS/DIR4 upgrades, preimary and secondary relay upgrades, control house upgrades, etc. | Review of existing control house and primary and secondary protection schemes |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | TBD | Mystic #250 SS | 345/115 | Eversource | EMA | BPS/DIR4 upgrades, preimary and secondary relay upgrades, control house upgrades, etc. | Review of existing control house and primary and secondary protection schemes |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | TBD | K Street #385 SS | 345/115 | Eversource | EMA | BPS/DIR4 upgrades, preimary and secondary relay upgrades, control house upgrades, etc. | Review of existing control house and primary and secondary protection schemes |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | TBD | Canal #980 SS | 345/115 | Eversource | EMA | Aging substation infrastructure, autotransformer | Replace autotransformer |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | TBD | Canal #980 SS | 345/115 | Eversource | EMA | Aging substation infrastructure, autotransformer | Replace autotransformer |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | TBD | North Cambridge #509 SS | 345/115 | Eversource | EMA | BPS/DIR4 upgrades, preimary and secondary relay upgrades, control house upgrades, etc. | Review of existing control house and primary and secondary protection schemes |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | TBD | 1785 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | TBD | TBD | 3-5 Years
Under Evaluation | TBD | 385 | 115 | Eversource | NH | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | TBD | TBD | 3-5 Years
Under Evaluation | TBD | 385-510/511 | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | 329-530/531 | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | 514-512/513 | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | 1450 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2025-09-01 | TBD | TBD
Under Evaluation | TBD | 1750 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | 2025-09-01 | TBD | TBD
Under Evaluation | TBD | 310 | 115 | Eversource | CT | Degradation of poles, towers, shieldwire and/or conductor | Replace poles, towers, shield wire and /or conductor |  |  |  |  | TBD | TBD | TBD
Under Evaluation | TBD | 514-510/511 | 115 | Eversource | EMA | Deterioration of vaults/ducts, water leaks | Replace HPFF lines with XLPE cables and install new manholes |  |  |  |  | TBD | TBD | TBD
Under Evaluation | TBD | E-183/F-184 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 3: $25-100M | 6-10 Year
Under Evaluation | TBD | O-215/N-214 | 230 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2025-06-30 | Group 4: $100M+ | 6-10 Year
Under Evaluation | TBD | 331 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-11-24 | Group 4: $100M+ | 6-10 Year
Under Evaluation | TBD | Gardner Twr Sub Motorized switches | 69 | New England Power | MA | Aging substation infrastructure, relays | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 2: $10-25M | 6-10 Year
Under Evaluation | TBD | 356 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 1: $0-10M | 6-10 Year
Under Evaluation | TBD | 357 | 345 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2025-05-01 | Group 2: $10-25M | 6-10 Year
Under Evaluation | TBD | A-127/B-128/Z-126 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | Read St Substation | 115/69 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | 2026-06-01 | Group 3: $25-100M | 6-10 Year
Under Evaluation | TBD | D-130 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | TBD | F19/G18/S1 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2025-03-01 | Group 3: $25-100M | 6-10 Year
Under Evaluation | TBD | M13/L14/N12 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 3: $25-100M | 6-10 Year
Under Evaluation | TBD | Pratts Junction Substation | 115 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | 2026-01-01 | Group 3: $25-100M | 6-10 Year
Under Evaluation | TBD | Westborough Substation | 69 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | 2025-11-01 | Group 2: $10-25M | 6-10 Year
Under Evaluation | TBD | B-154N, C-155N, B-154S and C-155S | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2024-12-24 | Group 4: $100M+ | 6-10 Year
Under Evaluation | TBD | E1 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | TBD | Group 1: $0-10M | 6-10 Year
Under Evaluation | TBD | Sandy Pond Substation | 345 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | 2025-12-01 | Group 2: $10-25M | 6-10 Year
Under Evaluation | TBD | Ware Substation | 69 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | 2025-11-01 | Group 2: $10-25M | 6-10 Year
Under Evaluation | TBD | F-132 | 115 | New England Power | MA | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2026-12-30 | Group 2: $10-25M | 6-10 Year
Under Evaluation | TBD | Millbury 5 Indoor GIS | 115/69 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | 2027-12-30 | Group 3: $25-100M | 6-10 Year
Under Evaluation | TBD | Robinson Ave | 115/69 | New England Power | MA | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | 2031-12-30 | Group 1: $0-10M | 6-10 Year
Under Evaluation | TBD | N-40 | 69 | New England Power | MA/VT | Degradation of poles, towers, and/or shieldwire | Replace poles, towers and/or shield wire |  |  |  |  | 2025-11-01 | Group 3: $25-100M | 6-10 Year
Under Evaluation | N/A | 1870 | 115 | Rhode Island Energy | RI | Aging line, wood poles | Full rebuild or targeted refurbishment |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | N/A | 1870N | 115 | Rhode Island Energy | RI | Aging line, wood poles | Full rebuild or targeted refurbishment |  |  |  |  | TBD | TBD | 3-5 Year
Under Evaluation | N/A | 332 | 345 | Rhode Island Energy | RI | Aging line with deteriorating wood poles | Full rebuild or targeted refurbishment |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Evaluation | N/A | 347 | 345 | Rhode Island Energy | RI | Aging line with deteriorating wood poles | Full rebuild or targeted refurbishment |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Evaluation | N/A | Q-143 | 115 | Rhode Island Energy | RI | Aging conductor and shieldwire, and degradation of poles. | Full rebuild or targeted refurbishment |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year
Under Evaluation | N/A | R-144N | 115 | Rhode Island Energy | RI | Aging conductor and shieldwire, and degradation of poles. | Full rebuild or targeted refurbishment |  |  |  |  | TBD | Group 2: $10-25M | 3-5 Year
Under Evaluation | N/A | Franklin Square/Manchester St | 115 | Rhode Island Energy | RI | Aging relays, substation infrastructure | Relay Upgrades |  |  |  |  | TBD | Group 3: $25-100M | 3-5 Year
Under Evaluation | N/A | V-148N | 115 | Rhode Island Energy | RI | Aging line | Full rebuild or targeted refurbishment |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | N/A | R9 | 115 | Rhode Island Energy | RI | Aging line | Full rebuild or targeted refurbishment |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | N/A | West Kingston | 115 | Rhode Island Energy | RI | Aging relays | Relay Upgrades / new transmission control cubicle |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | N/A | Kenyon | 115 | Rhode Island Energy | RI | Aging relays | Relay Upgrades / new transmission control cubicle |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | N/A | Wood River | 115 | Rhode Island Energy | RI | Aging relays | Relay Upgrades / new transmission control cubicle |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | N/A | Staples | 115 | Rhode Island Energy | RI | Aging relays | Relay Upgrades / new transmission control cubicle |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | N/A | Valley Sub | 115 | Rhode Island Energy | RI | Aging relays | Relay Upgrades / new transmission control cubicle |  |  |  |  | TBD | TBD | 6-10 Year
Under Evaluation | N/A | E-105 | 115 | Rhode Island Energy | RI | Aging equipment and equipment failures | Full rebuild or targeted refurbishment |  |  |  |  | TBD | TBD | TBD
Under Evaluation | N/A | F-106 | 115 | Rhode Island Energy | RI | Aging equipment and equipment failures | Full rebuild or targeted refurbishment |  |  |  |  | TBD | TBD | TBD
Under Evaluation | N/A | 8500, 8700, 8702 | 115 | United Illuminating Company | CT | Obsolete LPFF UG cables, aging ducts and manholes | Replace with XLPE |  |  |  |  | TBD | Group 4: $100M+ | 6-10 Year
Under Evaluation | N/A | Essex substation | 115 | Vermont Electric Power Co | VT | Aging substation infrastructure, relays | Partial rebuild substation |  |  |  |  | TBD | Group 1: $0-10M | 3-5 year
Under Evaluation | N/A | Vermont Yankee substation | 115 | Vermont Electric Power Co | VT | Aging substation infrastructure | Partial rebuild substation |  |  |  |  | TBD | Group 1: $0-10M | 3-5 year
Under Evaluation | N/A | Coolidge transformer | 345/115 | Vermont Electric Power Co | VT | Aging transformer | Partial rebuild substation |  |  |  |  | TBD | Group 2: $10-25M | 5-10 year
Under Evaluation | N/A | Granite Sync cond | 115 | Vermont Electric Power Co | VT | Aging controls | Control replacments |  |  |  |  | TBD | Group 1: $0-10M | 3-5 year
Under Evaluation | N/A | Line K54 | 115 | Vermont Electric Power Co | VT | Degradation of structures | Complete line rebuild |  |  |  |  | TBD | Group 3: $25-100M | 3-5 year
Under Evaluation | N/A | Line F206 | 230 | Vermont Electric Power Co | VT | Degradation of structures | Complete line rebuild |  |  |  |  | TBD | Group 3: $25-100M | 3-5 year
Under Evaluation | N/A | Highgate Converter | 115 | Vermont Electric Power Co | VT | Aging substation infrastructure | Greenfield substation |  |  |  |  | TBD | Group 4: $100M+ | 5-10 year
Under Evaluation | N/A | Cold River | 115 | Vermont Electric Power Co | VT | Aging substation infrastructure | Partial rebuild substation |  |  |  |  | TBD | Group 1: $0-10M | 2 year
Under Evaluation | N/A | Line K19 | 115 | Vermont Electric Power Co | VT | Degradation of structures | Replace poles, crossarm and insulators |  |  |  |  | TBD | Group 1: $0-10M | 2 year
Under Evaluation | N/A | Line K51 | 115 | Vermont Electric Power Co | VT | Degradation of structures | Replace poles, crossarm and insulators |  |  |  |  | TBD | Group 2: $10-25M | 2 year
Note on I9: Author: Is this the initial PAC presentation date or the latest presented?

## Contact Information
For questions please contact the individuals below
Company | Name | Email
Avangrid (including UI, CMP and MEPCO) | Zachary Logan | zachary.logan@cmpco.com
Eversource | Dave Burnham | david.burnham@eversource.com
National Grid | Rafael Panos | rafael.panos@nationalgrid.com
Rhode Island Energy | Kyra Lagunilla | KLagunilla@pplweb.com
VELCO | Frank Ettori | fettori@velco.com
Versant* | Dave Norman | david.norman@versantpower.com
*Note: there are no current or forecasted projects by Versant that meet the conditions for inclusion