## RSP_sortable
Primary Driver | Part# | Project ID | State | Primary Equipment Owner | Other Equipment Owner(s) | Footnote Number | Projected In-Service Month/Year | Major Project | Project | Oct-10 Status | Apr-11 Status | Jun-11 Status | Nov-11 Status | Mar-12 Status | Jun-12 Status | Oct-12 Status | Mar-13 Status | Jun-13 Status | Oct-13 Status | Mar-14 Status | Jun-14 Status | Oct-14 Status | Mar-15 Status | Jun-15 Status | Oct-15 Status | Mar-16 Status | Jun-16 Status | Oct-16 Status | Mar-17 Status | Jun-17 Status | Oct-17 Status | Mar-18 Status | Jun-18 Status | Oct-18 Status | Mar-19 Status | Jun-19 Status | Oct-19 Status | Mar-20 Status | Jun-20 Status | Oct-20 Status | Mar-21 Status | Jun-21 Status | Oct-21 Status | Mar-22 Status | Jun-22 Status | Oct-22 Status | Mar-23 Status | Jun-23 Status | Oct-23 Status | Mar-24 Status | Jun-24 Status | Oct-24 Status | Mar-25 Status | Jun-25 Status | Oct-25 Status | Mar-26 Status | Jun-26 Status | Is the project Grandfathered on May 18, 2015 (not updated since March 2017) | PPA (I.3.9) Approval | TCA Approval | Oct-10 Estimated PTF Costs | Apr-11 Estimated PTF Costs | Jun-11 Estimated PTF Costs | Nov-11 Estimated PTF Costs | Mar-12 Estimated PTF Costs | Jun-12 Estimated PTF Costs | Oct-12 Estimated PTF Costs | Mar-13 Estimated PTF Costs | Jun-13 Estimated PTF Costs | Oct-13 Estimated PTF Costs | Mar-14 Estimated PTF Costs | Jun-14 Estimated PTF Costs | Oct-14 Estimated PTF Costs | Mar-15 Estimated PTF Costs | Jun-15 Estimated PTF Costs | Oct-15 Estimated PTF Costs | Mar-16 Estimated PTF Costs | Jun-16 Estimated PTF Costs | Oct-16 Estimated PTF Costs | Mar-17 Estimated PTF Costs | Jun-17 Estimated PTF Costs | Oct-17 Estimated PTF Costs | Mar-18 Estimated PTF Costs | Jun-18 Estimated PTF Costs | Oct-18 Estimated PTF Costs | Mar-19 Estimated PTF Costs | Jun-19 Estimated PTF Costs | Oct-19 Estimated PTF Costs | Mar-20 Estimated PTF Costs | Jun-20 Estimated PTF Costs | Oct-20 Estimated PTF Costs | Mar-21 Estimated PTF Costs | Jun-21 Estimated PTF Costs | Oct-21 Estimated PTF Costs | Mar-22 Estimated PTF Costs | Jun-22 Estimated PTF Costs | Oct-22 Estimated PTF Costs | Mar-23 Estimated PTF Costs | Jun-23 Estimated PTF Costs | Oct-23 Estimated PTF Costs | Mar-24 Estimated PTF Costs | Jun-24 Estimated PTF Costs | Oct-24 Estimated PTF Costs | Mar-25 Estimated PTF Costs | Jun-25 Estimated PTF Costs | Oct-25 Estimated PTF Costs | Mar-26 Estimated PTF Costs | Jun-26 Estimated PTF Costs | DIFF
Generator Interconnection Upgrade | 2a | 1939 | MA | National Grid, USA |  |  | 2026-11-01 | Queue Position 1320 | Install a new 115 kV three breaker ring bus substation, to be named Quaker St., on NEP’s R-144N line, between NEP’s Millbury Substation and RIE’s Woonsocket Substation, to interconnect QP1320 | [47 empty] | Under Construction |  | 2024-12-05 | NR | [47 empty] | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1938 | CT | Eversource |  |  | 2028-10-01 | Queue Position 1245 | Installation of a new 345 kV, 3-breaker ring bus switchyard on the line 3419 in Ellington, CT | [46 empty] | Planned | Planned |  | 2024-10-01 | NR | [46 empty] | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1937 | ME | Central Maine Power Company |  |  | 2029-11-01 | Queue Position 1100 | Replace structure to increase the Summer Long Time Emergency rating of the 6.5 mile 82-2 segment of 115 kV line Section 82, from Detroit to the Section 82A Tap | [46 empty] | Planned | Planned |  | 2025-09-24 | NR | [46 empty] | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1936 | ME | Central Maine Power Company |  |  | 2029-11-01 | Queue Position 1100 | Install two static 10 MVAR, 115 kV shunt capacitor blocks, with necessary switchgear, at the Dogtown 115 kV bus. | [46 empty] | Planned | Planned |  | 2025-09-24 | NR | [46 empty] | NR | NR | #VALUE!
Generator Interconnection Upgrade | 1b | 1935 | MA | National Grid, USA |  |  | 2031-08-01 | Queue Position 1252 | Reconductor National Grid owned portion of the 338 (Tewksbury - Woburn) 345 kV line | [44 empty] | Proposed | Proposed | Cancelled | Cancelled |  | 2024-10-01 | NR | [44 empty] | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1934 | MA | Eversource |  |  | 2027-03-01 | Boston 2033 Solutions Study | Protection systems modification associated with the Stoughton RAS at three 345 kV substations (Stoughton, West Walpole and Holbrook) and two 115 kV substations (Hyde Park and K-Street) | [44 empty] | Proposed | Proposed | Proposed | Proposed |  | No | No | [44 empty] | 3700000 | 3700000 | 3700000 | 3700000 | 0
Reliability Upgrade | 1b | 1933 | MA | Eversource |  |  | 2028-12-01 | Boston 2033 Solutions Study | Install one 80 MVAR shunt reactor at the 115 kV Electric Avenue Substation | [44 empty] | Proposed | Proposed | Proposed | Proposed |  | No | No | [44 empty] | 22300000 | 22300000 | 22300000 | 22300000 | 0
Generator Interconnection Upgrade | 2a | 1932 | MA | Eversource |  |  | 2028-05-02 | Queue Position 1148 | Add one bay with two breakers to the existing Electric Ave substation #315 | [44 empty] | Planned | Planned | Planned | Planned |  | 2025-01-06 | NR | [44 empty] | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1931 | MA | Eversource |  |  | 2028-05-02 | Queue Position 1143 | Add a series breaker to the 115 kV Medway Ring #65 Substation | [44 empty] | Planned | Planned | Cancelled | Cancelled |  | 2023-08-29 | NR | [44 empty] | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1930 | CT | Eversource |  |  | 2027-10-02 | Queue Position 1192 | Installation of a new 345 kV, 3-breaker ring bus switchyard in East Granby | [44 empty] | Planned | Planned | Planned | Planned |  | 2024-05-28 | NR | [44 empty] | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1929 | CT | Eversource |  |  | 2029-05-01 | Queue Position 1138 | Addition of a 115 kV 3-breaker ring-bus switchyard on the 1316 Line between Canterbury substation and Tunnel substation | [44 empty] | Planned | Planned | Planned | Planned |  | 2024-06-28 | NR | [44 empty] | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1928 | RI | Rhode Island Energy |  |  | 2028-12-02 | Queue Position 1163 | Construct new 115 kV Switching Station in North Kingstown | [44 empty] | Proposed | Proposed | Planned | Planned |  | 2025-03-20 | NR | [44 empty] | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1927 | MA | Eversource |  |  | 2027-02-01 | Queue Position 1320 | Add a series breaker to the 115 kV Medway Ring #65 Substation | [44 empty] | Planned | Planned | Planned | Planned |  | 2024-12-05 | NR | [44 empty] | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1926 | RI | Rhode Island Energy |  |  | 2026-06-01 | Queue Position 1320 | Replace one 115 kV circuit breaker at the Woonsocket substation | [44 empty] | Planned | Planned | Planned | Under Construction |  | 2024-12-05 | NR | [44 empty] | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1925 | MA | Eversource |  |  | 2031-08-02 | Queue Position 1252 | Reconductor Eversource Energy owned portion of the 338 (Tewksbury - Woburn) 345 kV line | [43 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled |  | 2024-10-01 | NR | [43 empty] | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1924 | MA | Eversource |  |  | 2028-03-01 | Queue Position 1110 | Install a 115 kV tie line between the existing Mystic 9 Unit 93 terminal and the Mystic substation fence line | [42 empty] | Planned | Planned | Planned | Planned | Planned | Planned |  | 2022-07-11 | NR | [42 empty] | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1923 | ME | Versant Power |  |  | 2026-09-11 | Queue Position 1299 | Addition of a new 115 kV Switching Station on line 57 near Trenton Substation | [42 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled |  | 2024-06-28 | NR | [42 empty] | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1922 | CT | Eversource |  |  | 2028-10-01 | Queue Position 1089 | Addition of a 115 kV disconnect switch at Devon substation and other supporting substation equipment | [41 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2022-12-19 | NR | [41 empty] | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1921 | MA | Eversource |  |  | 2027-05-01 | Queue Position 1117 | Upgrade Buck Pond station via a ring bus expansion and new gas insulated breaker | [41 empty] | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled |  | 2023-05-31 | NR | [41 empty] | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1920 | MA | Eversource |  |  | 2028-05-01 | Queue Position 1143 | Install new duct bank, termination stanchions, disconnect switch, CCVTs and other associated station upgrades at the Mystic #250 345 kV substation | [41 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2023-08-29 | NR | [41 empty] | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1919 | MA | Eversource |  |  | 2027-08-01 | Queue Position 1115 | Install one 115 kV circuit breaker, two 115 kV breaker disconnect switches and other associated substation upgrades at Chelsea #488 substation | [41 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2022-10-19 | NR | [41 empty] | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1918 | MA | Eversource |  |  | 2027-11-01 | SEMA 2028 Short Circuit Solutions | Replace six 115 kV circuit breakers at Barnstable substation | [41 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction |  | NR | No | [41 empty] | 13300000 | 13300000 | 13300000 | 13300000 | 13300000 | 16526000 | 16526000 | 0
Reliability Upgrade | 1a | 1917 | ME | Central Maine Power Company |  |  | 2028-12-31 | ME 2028 Short Circuit Solutions | Replace six 115 kV circuit breakers at Larrabee Road substation | [41 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | NR | No | [41 empty] | 5501609 | 5501609 | 5501609 | 5501609 | 5501609 | 5501609 | 5501609 | 0
Reliability Upgrade | 1a | 1916 | MA | National Grid, USA |  |  | 2026-03-01 | Western and Central Massachusetts 2028 Short Circuit Solutions | Replace one 115 kV circuit breaker at the Millbury substation | [40 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service |  | NR | NR | [40 empty] | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 0
Reliability Upgrade | 1a | 1915 | RI | Rhode Island Energy |  |  | 2025-11-01 | RI 2028 Short Circuit Solutions | Replace three 115 kV circuit breakers at the Woonsocket substation | [40 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service |  | NR | NR | [40 empty] | 1524700 | 1524700 | 1524700 | 1524700 | 1524700 | 2281000 | 2890000 | 2890000 | 0
Reliability Upgrade | 1a | 1914 | ME | Versant Power |  |  | 2026-12-01 | UME 2029 Solutions | Install a new 80 MVAR reactor, reconfigure the existing two reactors at the 345 kV Orrington substation | [40 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction |  | 2024-04-23 | 2026-02-13 | [40 empty] | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 0
Generator Interconnection Upgrade | 2a | 1913 | MA | Eversource |  |  | 2025-11-01 | Queue Position 844 | Install a new 345 kV circuit breaker at West Medway Station 446 | [39 empty] | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service |  | 2021-09-03 | NR | [39 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1912 | NH | Eversource |  |  | 2025-09-01 | Queue Position 1101 | Installation of a 5.95 Ohm series reactor on the 363 line at the 345 kV Scobie Pond substation | [37 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Proposed | Cancelled | Cancelled | Cancelled | Cancelled |  | 2022-10-19 | NR | [37 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1911 | ME | Versant Power |  |  | 2023-12-01 | Queue Position 1029 | Addition of a new 115 kV Switching Station on line 97 between Graham and Passadumkeag Stations | [37 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2022-12-19 | NR | [37 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1910 | ME | Versant Power |  |  | 2024-12-01 | Queue Position 1015 | Breaker additions at Orrington 115kV Switching Station to accommodate QP1015 | [37 empty] | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2022-09-30 | NR | [37 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1909 | ME | Versant Power |  |  | 2024-06-01 | Queue Position 1014 | Breaker additions at Keene Rd 115kV Switching Station to accommodate QP1014 | [37 empty] | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2022-09-01 | NR | [37 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1908 | MA | National Grid, USA |  |  | 2029-03-01 | D-4 Protection System | Install a POTT protection system on the D-4 line via the A1/B2 lines | [37 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2022-07-20 | No | [37 empty] | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 0
Generator Interconnection Upgrade | 2a | 1907 | NH | Eversource |  |  | 2024-10-01 | Queue Position 936 | Install a 115 kV tie line and 115 kV circuit breaker at the Paris 115 kV substation | [36 empty] | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2022-08-12 | NR | [36 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1906 | NH | Eversource |  |  | 2024-10-01 | Queue Position 936 | Install a new 10 MVAR Shunt Capacitor and 115 kV circuit breaker at the Lost Nation 115 kV substation | [36 empty] | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2022-08-12 | NR | [36 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1905 | ME | Versant Power |  |  | 2026-08-01 | Queue Position 833 | Addition of a new 115 kV Three Rivers Switching Station on line 93 between Bull Hill and Deblois | [36 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction |  | 11/8/2021 05/31/2023 | NR | [36 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1904 | CT | CMEEC |  |  | 2023-12-01 | Eastern CT 2029 Solutions | Convert 69kV equipment at Buddington to 115 kV to facilitate the conversion of the 400-2 line to 115 kV | [36 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [36 empty] | 5500000 | 5500000 | 6073478 | 6155823 | 6344392.8699 | 6397083.49 | 6397083.49 | 6397083.49 | 6397083.49 | 6397083.49 | 6397083.49 | 6397083.49 | 0
Generator Interconnection Upgrade | 2a | 1903 | CT | Eversource |  |  | 2023-12-01 | Queue Position 787 | Install a 115 kV breaker to the existing three-breaker ring bus at Canterbury 67F | [35 empty] | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-04-17 | NR | [35 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1902 | MA | National Grid, USA |  |  | 2027-07-01 | Queue Position 877 | Convert the South Wrentham substation into a five breaker ring bus and upgrades of terminal equipment | [35 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 5/6/2022 4/27/2023 | NR | [35 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1901 | MA | National Grid, USA |  |  | 2027-07-01 | Queue Position 877 | Reconductor the C129S 115 kV line from South Wrentham to Union Street and C181N/D182N 115 kV lines from South Wrentham to Berry Street | [35 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 5/6/2022 4/27/2023 | NR | [35 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1900 | ME | Central Maine Power Company |  |  | 2026-11-01 | Queue Position 1086 | Increase the LTE rating of line Section 80 to 109 MVA by increasing the sag temperature and replacing two 115 kV structures | [35 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled |  | 2022-03-21 | NR | [35 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1899 | ME | Central Maine Power Company |  |  | 2028-05-01 | Queue Position 1086 | Install a 115 kV three-breaker ring bus on CMP Section 80, approximately 2 miles from Highland Station | [35 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2022-03-21 | NR | [35 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1898 | MA | Eversource |  |  | 2022-09-01 |  | K Street 345 kV 103S Breaker - Operate as Normally Open | [35 empty] | Proposed | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2022-08-19 | NR | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Elective Upgrade | 4a | 1897 | NH | Eversource |  |  | 2025-02-01 | Queue Position 889 | Add a series breaker at the Deerfield 345 kV Substation | [34 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service |  | 2021-11-19 | NR | [34 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1896 | NH | Eversource |  |  | 2025-12-01 | Queue Position 889 | Add a series breaker at the Scobie Pond 345 kV Substation | [34 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service |  | 2021-11-19 | NR | [34 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1895 | ME | Central Maine Power Company |  |  | 2025-02-01 | Queue Position 889 | Reconductor the Section 64 115kV | [34 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service |  | 2021-11-19 | NR | [34 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1894 | ME | Central Maine Power Company |  |  | 2025-07-01 | Queue Position 889 | Reconductor the Section 62 115 kV line | [34 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service |  | 2021-11-19 | NR | [34 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1893 | ME | Central Maine Power Company |  |  | 2025-12-01 | Queue Position 889 | Install two +300/-300 MVAR STATCOMs at the Buxton 345 kV Substation with one new 345 kV breaker | [34 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service |  | 2021-11-19 | NR | [34 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1892 | ME | Versant Power |  |  | 2024-04-01 | Queue Position 760 | Rebuild of 3.25 miles of Line 59 between Epping and Columbia | [33 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-07-01 | NR | [33 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1891 | ME | Versant Power |  |  | 2025-05-01 | Queue Position 760 | Addition of a +/-150 MVAR STATCOM at Tunk Lake | [33 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service |  | 2021-07-01 | NR | [33 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1890 | ME | Versant Power |  |  | 2024-11-01 | Queue Position 760 | Addition of a new 115 kV Baseline Switching Station on line 52 between Deblois and Epping | [33 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service |  | 2021-07-01 | NR | [33 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1889 | ME | Versant Power |  |  | 2024-12-01 | UME 2029 Solutions | Install three remotely monitored and controlled switches to split the existing Orrington reactors between the two Orrington 345/115 kV autotransformers | [33 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2022-02-16 | No | [33 empty] | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 0
Reliability Upgrade | 1a | 1888 | ME | Versant Power |  |  | 2024-07-01 | UME 2029 Solutions | Install a 10 MVAR reactor at Keene Road 115 kV substation | [33 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service |  | 2022-02-16 | 2026-02-13 | [33 empty] | 6000000 | 6000000 | 6000000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 0
Reliability Upgrade | 1a | 1887 | ME | Versant Power |  |  | 2024-10-30 | UME 2029 Solutions | Install a 25 MVAR reactor at Boggy Brook 115 kV substation | [33 empty] | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service |  | 2022-02-16 | 2026-02-13 | [33 empty] | 3400000 | 3400000 | 3400000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 0
Reliability Upgrade | 1a | 1886 | ME | Versant Power |  |  | 2025-08-01 | UME 2029 Solutions | Install a +50/-25 MVAR synchronous condenser at Boggy Brook 115 kV substation, and install a new 115 kV breaker to separate Line 67 from the proposed solution elements | [33 empty] | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service |  | 2022-02-16 | 2026-02-13 | [33 empty] | 35500000 | 35500000 | 35500000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 25900000 | 25900000 | 25900000 | 25900000 | 25900000 | 25900000 | 0
Reliability Upgrade | 1a | 1885 | ME | Central Maine Power Company |  |  | 2029-12-31 | UME 2029 Solutions | Install a +50/-25 MVAR synchronous condenser at Highland 115 kV substation | [33 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2023-08-29 | No | [33 empty] | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 0
Reliability Upgrade | 1a | 1884 | ME | Central Maine Power Company |  |  | 2029-12-31 | UME 2029 Solutions | Install a 15 MVAR capacitor at Belfast 115 kV substation | [33 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2023-08-29 | No | [33 empty] | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 0
Reliability Upgrade | 1a | 1883 | ME | Central Maine Power Company |  |  | 2028-12-31 | UME 2029 Solutions | Convert the Highland 115 kV substation to an eight breaker, breaker-and-a-half configuration with a bus connected 115/34.5 kV transformer | [33 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2023-08-29 | No | [33 empty] | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 0
Reliability Upgrade | 1a | 1882 | ME | Central Maine Power Company |  |  | 2024-08-01 | UME 2029 Solutions | Rebuild 21.7 miles of the existing 115 kV line Section 80 Highland – Coopers Mills 115 kV line | [33 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service |  | 2022-05-24 | No | [33 empty] | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 0
Reliability Upgrade | 1a | 1881 | NH | New Hampshire Transmission, LLC | Eversource | 2 | 2023-10-01 | NH 2029 Solutions | Install two 50 MVAR capacitors on Line 363 near Seabrook station with three 345 kV breakers | [33 empty] | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2022-01-19 | 2024-07-16 | [33 empty] | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 22861441 | 26591441 | 26591441 | 26591441 | 28180513.78 | 28180513.78 | 28180513.78 | 28180513.78 | 28180513.78 | 28180513.78 | 0
Reliability Upgrade | 1a | 1880 | NH | Eversource |  |  | 2024-12-01 | NH 2029 Solutions | Install a +127/-50 MVAR synchronous condenser at Amherst 345 kV Substation with three 345 kV circuit breakers and a 13.8 kV circuit breaker | [33 empty] | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service |  | 2022-06-15 | 2024-07-16 | [33 empty] | 53600000 | 53600000 | 53600000 | 53600000 | 66996000 | 66996000 | 66996000 | 66996000 | 66996000 | 66996000 | 66996000 | 66996000 | 66996000 | 66996000 | 66996000 | 0
Reliability Upgrade | 1a | 1879 | NH | Eversource |  |  | 2024-10-01 | NH 2029 Solutions | Install a +55/-32.2 MVAR synchronous condenser at Huckins Hill 115 kV Substation with a 115 kV breaker and a 13.8 kV breaker | [33 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service |  | 2022-06-15 | 2024-07-16 | [33 empty] | 36200000 | 36200000 | 36200000 | 33449000 | 33449000 | 33449000 | 33449000 | 33449000 | 33449000 | 33449000 | 33449000 | 33449000 | 33449000 | 33449000 | 33449000 | 0
Reliability Upgrade | 1a | 1878 | NH | Eversource |  |  | 2025-06-01 | NH 2029 Solutions | Install a +55/-32.2 MVAR synchronous condenser at N. Keene 115 kV Substation with a 115 kV breaker and a 13.8 kV breaker | [33 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service |  | 2022-06-15 | 2024-07-16 | [33 empty] | 36200000 | 36200000 | 36200000 | 32375000 | 32375000 | 32375000 | 32375000 | 32375000 | 32375000 | 32375000 | 32375000 | 32375000 | 32375000 | 32375000 | 32375000 | 0
Generator Interconnection Upgrade | 2a | 1877 | MA | Eversource |  |  | 2024-12-01 | Queue Position 726 | Construct a new substation with three-breakers to accommodate the interconnection of QP 726 on the existing Line 127 115 kV line | [32 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service |  | 2021-03-03 | NR | [32 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1876 | MA | National Grid, USA |  |  | 2023-06-01 | Boston Area Optimized Solution | Install one +/- 167 MVAR STATCOM at Tewksbury 345 kV substation | [31 empty] | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 5/21/2021 1/18/2023 | 2022-04-08 | [31 empty] | 33400000 | 31300000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 0
Reliability Upgrade | 1a | 1875 | MA | National Grid, USA |  |  | 2022-04-01 | Boston Area Optimized Solution | Install a direct transfer trip (DTT) scheme between Ward Hill and West Amesbury Substations for Line 394 | [31 empty] | Proposed | Proposed | Planned | Planned | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-05-21 | 2022-04-08 | [31 empty] | 800000 | 800000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 0
Reliability Upgrade | 1a | 1874 | MA | Eversource |  |  | 2021-12-01 | Boston Area Optimized Solution | Install two 11.9 ohm series reactors at North Cambridge Station on Lines 346 and 365 | [31 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-05-21 | 2022-04-08 | [31 empty] | 14400000 | 14400000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 0
Generator Interconnection Upgrade | 2b | 1873 | CT | Eversource |  |  | 2024-03-01 | Queue Position 831 | Rebuild the 69 kV 400-1 Line (Ledyard Junction to Tunnel OH/UG Transition structure), install approximately 200 feet of XLPE cable from Tunnel OH/UG Transition structure to Tunnel S/S’ | [31 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2021-01-25 | NR | [31 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1872 | CT | Eversource |  |  | 2024-03-01 | Queue Position 831 | Install two new 345 kV circuit breakers at the Killingly 345 kV substation and expand the 345 kV bus into a 4-breaker ring bus | [31 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2021-01-25 | NR | [31 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1871 | CT | Eversource |  |  | 2023-12-01 | Queue Position 788 | Install a 69 kV circuit breaker at the Montville 4J Substation. | [31 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2021-01-25 | NR | [31 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1870 | MA | Eversource |  |  | 2029-12-01 | Queue Position 700 | Convert the planned 115 kV Mid-Cape line to 345 kV | [31 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction |  | 2021-01-04 | NR | [31 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1869 | MA | Eversource |  |  | 2029-12-01 | Queue Position 700 | Install a second 345/115 kV transformer at the West Barnstable substation | [31 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2021-01-04 | NR | [31 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1868 | MA | Eversource |  |  | 2029-12-01 | Queue Position 700 | Add a third 115 kV breaker at the 115 kV West Barnstable substation | [31 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2021-01-04 | NR | [31 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1867 | MA | Eversource |  |  | 2029-12-01 | Queue Position 700 | Upgrade the West Barnstable 345 kV substation to a four bay GIS breaker-and-a-half design | [31 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2021-01-04 | NR | [31 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1866 | MA | Eversource |  |  | 2029-12-01 | Queue Position 700 | Construct a new Bourne 345 kV station as a breaker-and-a-half substation | [31 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2021-01-04 | NR | [31 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1865 | ME | Central Maine Power Company |  |  | 2024-10-01 | Queue Position 931 | Install a 115 kV circuit breaker at the Roxbury substation bus #1 adjacent to the KGT1-1 breaker. | [31 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-12-14 | NR | [31 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1864 | CT | CMEEC |  |  | 2023-02-28 | Eastern CT 2029 Solutions | Convert the 400-2 Line Section to 115 kV (Border Bus to Buddington) | [30 empty] | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service |  | 2021-06-17 | No | [30 empty] | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 3200000 | 3200000 | 2792733 | 2833477 | 2836388 | 2858821 | 2858821 | 2858821 | 2858821 | 2858821 | 2858821 | 2858821 | 0
Reliability Upgrade | 1a | 1863 | CT | Eversource |  |  | 2022-03-01 | Eastern CT 2029 Solutions | Install a 1% series reactor with bypass switch at Mystic, CT on the 1465 Line | [30 empty] | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 4780000 | 4780000 | 4780000 | 4780000 | 4780000 | 4780000 | 4780000 | 4780000 | 4780000 | 4780000 | 4780000 | 4780000 | 0
Reliability Upgrade | 1a | 1862 | CT | Eversource |  |  | 2023-12-01 | Eastern CT 2029 Solutions | Install a +55/-29 MVAR synchronous condenser with two 115 kV breakers at Shunock | [30 empty] | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 43800000 | 43800000 | 43800000 | 43800000 | 43800000 | 43800000 | 40518000 | 40518000 | 40518000 | 40518000 | 40518000 | 40518000 | 40518000 | 40518000 | 40518000 | 40518000 | 40518000 | 40518000 | 0
Reliability Upgrade | 1a | 1861 | CT | Eversource |  |  | 2021-11-01 | Eastern CT 2029 Solutions | Install one 345 kV series breaker with the Montville 1T breaker | [30 empty] | Proposed | Proposed | Proposed | Planned | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3973000 | 3973000 | 3973000 | 3973000 | 3973000 | 3973000 | 3973000 | 3973000 | 3973000 | 3973000 | 3973000 | 3973000 | 0
Reliability Upgrade | 1a | 1860 | CT | Eversource |  |  | 2021-12-01 | Eastern CT 2029 Solutions | Install a 25.2 MVAR 115 kV capacitor and one breaker at Killingly | [30 empty] | Proposed | Proposed | Proposed | Planned | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 4823000 | 4823000 | 4823000 | 4823000 | 4823000 | 4823000 | 4823000 | 4823000 | 4823000 | 4823000 | 4823000 | 4823000 | 0
Reliability Upgrade | 1a | 1859 | CT | Eversource |  |  | 2023-02-01 | Eastern CT 2029 Solutions | Rebuild the 400-3 Line Section to allow operation at 115 kV (Gales Ferry to Ledyard Jct) | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service |  | 2021-06-17 | No | [30 empty] | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 6855000 | 6855000 | 6855000 | 6855000 | 6855000 | 6855000 | 6855000 | 6855000 | 6855000 | 6855000 | 6855000 | 6855000 | 0
Reliability Upgrade | 1a | 1858 | CT | Eversource |  |  | 2022-09-01 | Eastern CT 2029 Solutions | Rebuild 400-2 Line section to allow operation at 115 kV (Ledyard Jct. to Border Bus with CMEEC) | [30 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 15133000 | 15133000 | 15133000 | 15133000 | 15133000 | 15133000 | 15133000 | 15133000 | 15133000 | 15133000 | 15133000 | 15133000 | 0
Reliability Upgrade | 1a | 1857 | CT | Eversource |  |  | 2023-02-01 | Eastern CT 2029 Solutions | Add one 115 kV circuit breaker and re-terminate the 400-1 line section into Tunnel substation. Energize 400 Line at 115 kV | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service |  | 2021-06-17 | No | [30 empty] | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 7439000 | 7439000 | 7439000 | 7439000 | 7439000 | 7439000 | 7439000 | 7439000 | 7439000 | 7439000 | 7439000 | 7439000 | 0
Reliability Upgrade | 1a | 1856 | CT | Eversource |  |  | 2023-02-01 | Eastern CT 2029 Solutions | Rebuild 400-1 Line section to allow operation at 115 kV (Tunnel to Ledyard Jct.) | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service |  | 2021-06-17 | No | [30 empty] | 31600000 | 31600000 | 31600000 | 31600000 | 31600000 | 31600000 | 42917000 | 42917000 | 42917000 | 42917000 | 42917000 | 42917000 | 42917000 | 42917000 | 42917000 | 42917000 | 42917000 | 42917000 | 0
Reliability Upgrade | 1a | 1855 | CT | Eversource |  |  | 2023-06-01 | Eastern CT 2029 Solutions | Reterminate the 100 Line at Montville station and associated work. Energize the 100 Line at 115 kV | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8407000 | 8407000 | 8407000 | 8407000 | 8407000 | 8407000 | 8407000 | 8407000 | 8407000 | 8407000 | 8407000 | 8407000 | 0
Reliability Upgrade | 1a | 1854 | CT | Eversource |  |  | 2023-06-01 | Eastern CT 2029 Solutions | Rebuild the 100 Line from Montville to Gales Ferry to allow operation at 115 kV | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 0
Reliability Upgrade | 1a | 1853 | CT | Eversource |  |  | 2023-11-01 | Eastern CT 2029 Solutions | Convert Gales Ferry substation from 69 kV to 115 kV | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 13100000 | 13100000 | 13100000 | 13100000 | 13100000 | 13100000 | 17256000 | 17256000 | 17256000 | 17256000 | 17256000 | 17256000 | 17256000 | 17256000 | 17256000 | 17256000 | 17256000 | 17256000 | 0
Reliability Upgrade | 1a | 1852 | CT | Eversource |  |  | 2023-02-01 | Eastern CT 2029 Solutions | Install one 115 kV circuit breaker in series with Card substation 4T | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 1952000 | 1952000 | 1952000 | 1952000 | 1952000 | 1952000 | 1952000 | 1952000 | 1952000 | 1952000 | 1952000 | 1952000 | 0
Reliability Upgrade | 1a | 1851 | CT | Eversource |  |  | 2022-12-01 | Eastern CT 2029 Solutions | Upgrade Card 115 kV to BPS standards | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 20300000 | 20300000 | 20300000 | 20300000 | 20300000 | 20300000 | 17502000 | 17502000 | 17502000 | 17502000 | 17502000 | 17502000 | 17502000 | 17502000 | 17502000 | 17502000 | 17502000 | 17502000 | 0
Reliability Upgrade | 1a | 1850 | CT | Eversource |  |  | 2022-12-01 | Eastern CT 2029 Solutions | Install a second 345/115 kV autotransformer (4X) and one 345 kV breaker at Card substation | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 20100000 | 20100000 | 20100000 | 20100000 | 20100000 | 20100000 | 17394000 | 17394000 | 17394000 | 17394000 | 17394000 | 17394000 | 17394000 | 17394000 | 17394000 | 17394000 | 17394000 | 17394000 | 0
Generator Interconnection Upgrade | 2a | 1849 | RI | Rhode Island Energy |  |  | 2025-03-01 | Queue Position 781 | Drumrock Substation Upgrades | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1848 | RI | Rhode Island Energy |  |  | 2024-10-01 | Queue Position 781 | Reconductor G-185S/L-190 Lines | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1847 | RI | Rhode Island Energy |  |  | 2024-12-02 | Queue Position 781 | Reconductor G-185N/K-189 Lines | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1846 | RI | Rhode Island Energy |  |  | 2025-04-01 | Queue Position 781 | Rebuild Davisville Substation | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1845 | RI | National Grid, USA |  |  | 2021-07-01 | Western Rhode Island Cluster | Reconductor G-185N & Uprate K-189 Lines | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1844 | RI | National Grid, USA |  |  | 2021-07-01 | Western Rhode Island Cluster | Construct new Wickford Junction Substation | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1843 | MA | Eversource |  |  | 2021-07-01 | Wareham Cluster | Wareham Station #714 upgrade the existing single ended station with transformer #2 | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-07-31 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1842 | MA | National Grid, USA |  |  | 2027-01-01 | Western Massachusetts Cluster Group 2 | A-1 B-2 69 kV reconductoring | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1841 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Ware 69 kV breaker addition | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1840 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | North Oxford breaker and transformer addition | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1839 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Leicester Substation retirement | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1838 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Westminster Substation retirement | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1837 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Palmer 115 kV transformer addition and replacement | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1836 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Thorndike 115 kV breaker and transformer additions | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1835 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Little Rest Road 115 kV breaker and transformer additions | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1834 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Lashaway 69 kV transformer replacements | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1833 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Ware 69/13.2 kV transformer addition | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1832 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Meadow Street 69 kV breaker and transformer addition | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1831 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Construct new Stafford Street 115/13.8 kV Substation | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1830 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Construct new Powder Mill 115/34.5 kV Substation | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1829 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Barre transformer replacements | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1828 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Construct new Lost Town 115/13.8 kV Substation | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1827 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Wendell Depot transformer addition | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1826 | MA | National Grid, USA |  |  | 2027-09-01 | Western Massachusetts Cluster Group 2 | Otter River 69 kV Ring Bus addition and DVAR | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1825 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | East Winchendon transformer addition | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1824 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Construct new Whitmanville 115/34/13.8 kV Substation | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1823 | CT | Eversource |  |  | 2022-10-01 | Queue Position 892 | Construct new substation on the 115 kV Eversource Line 1200 between Barbour Hill 23J Substation and Windsor Locks 14K Substation to allow the interconnection of QP892 | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-07-27 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1822 | NH | Eversource |  |  | 2024-12-01 | Queue Position 639 | Thermal Uprate of 115 kV Line B112 | [30 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-07-09 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1821 | ME | NECEC Transmission LLC |  |  | 2025-05-01 | Queue Position 639 | Construct 1.6 miles of new 345 kV AC transmission line from Merrill Road 345 kV Substation to Larrabee Road 345 kV Substation. | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service |  | 2020-07-09 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1820 | ME | NECEC Transmission LLC |  |  | 2025-12-01 | Queue Position 639 | Construct a new HVDC Converter Terminal at Merrill Road Substation. | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service |  | 2020-07-09 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1819 | ME | NECEC Transmission LLC |  |  | 2025-12-01 | Queue Position 639 | Construct 207 miles of new 320 kV symmetrical monopole HVDC transmission line from Appalaches Substation in Saint-Adrien-d’Irlande, Quebec to Merrill Road Substation in Lewiston, ME. | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service |  | 2020-07-09 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1818 | ME | Central Maine Power Company |  |  | 2023-05-01 | Queue Position 639 | Install one (1) 50 MVAR reactor bank on Bus #1 of the Buxton 345 kV Substation | [30 empty] | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-07-09 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1817 | ME | Central Maine Power Company |  |  | 2025-06-01 | Queue Position 639 | Install 2nd Larrabee Road 345/115 kV autotransformer | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service |  | 2020-07-09 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1816 | ME | Central Maine Power Company |  |  | 2025-09-01 | Queue Position 639 | Construct new Coopers Mills to Maine Yankee 345 kV line | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service |  | 2020-07-09 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1815 | RI | Rhode Island Energy |  | 1 | 2025-01-01 | Eastern CT 2029 Solutions | Reconductor the L190-4 and L190-5 line sections | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 40000000 | 40000000 | 31100000 | 31100000 | 31100000 | 31100000 | 54707000 | 54707000 | 54707000 | 54707000 | 54707000 | 54707000 | 54707000 | 54707000 | 54707000 | 54707000 | 54707000 | 54707000 | 0
Generator Interconnection Upgrade | 2a | 1814 | CT | Eversource |  |  | 2025-09-01 | Queue Position 787 | Install a 115 kV breaker to the existing three-breaker ring bus at Canterbury 67F. | [29 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-04-17 | NR | [29 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1813 | VT | Vermont Electric Power Company |  |  | 2028-10-01 | Queue Position 807 | Expand bus work and add a 115 kV breaker to connect QP 807 Solar PV project to the Vergennes 115 kV Substation. | [29 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2020-03-24 | NR | [29 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1812 | NH | National Grid, USA |  |  | 2024-12-01 | Queue Position 727 | Construct a new 115 kV three-breaker ring bus substation in Hinsdale, NH to interconnect the QP 727 solar project. | [29 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2019-08-26 | NR | [29 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1811 | NH | National Grid, USA |  |  | 2024-07-01 | Queue Position 754 | Install a new three-breaker 115 kV ring bus substation, to be named later, at the proposed QP 754 site in Fitzwilliam, NH. | [29 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-04-17 | NR | [29 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1810 | ME | Central Maine Power Company |  |  | 2022-12-01 | Queue Position 623 | Construct a new three-breaker 345 kV ring bus configured substation to accommodate the interconnection of the QP 623 project on the existing Section 391 between Buxton Substation and Scobie Pond Substation. | [29 empty] | Proposed | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2019-12-13 | NR | [29 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1809 | ME | Central Maine Power Company |  |  | 2020-10-01 | Queue Position 583 | Construct a new three-breaker ring bus configured substation to accommodate the interconnection of QP 583 on the existing Section 237 115 kV transmission line between Maguire Road and Sanford Substation. | [29 empty] | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2017-07-17 | NR | [29 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1808 | ME | Central Maine Power Company |  |  | 2021-09-01 | Queue Position 557 | Construct a new three-breaker ring bus configured substation to accommodate the interconnection of Farmington Solar on the existing Section 278 115 kV Line between Livermore Substation and Sturtevant Substation. | [29 empty] | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2019-05-01 | NR | [29 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1807 | MA | National Grid, USA |  |  | 2022-08-01 | Boston 2028 Project | Install a 160 MVAR reactor at Golden Hills 345 kV | [28 empty] | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2020-03-27 | 2022-04-08 | [28 empty] | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 0
Reliability Upgrade | 1a | 1806 | MA | Eversource |  |  | 2021-12-01 | Boston 2028 Project | Install a 115 kV breaker in series with breaker 4 at Mystic | [28 empty] | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2020-02-21 | 2022-04-08 | [28 empty] | 3250000 | 3250000 | 3250000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 0
Generator Interconnection Upgrade | 2a | 1805 | CT | Eversource |  |  | 2020-03-01 | Queue Position 784 | Upgrade the 1029-2 line from Bunker Hill - Baldwin Tap | [28 empty] | Planned | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2019-12-30 | NR | [28 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1804 | ME | Emera Maine |  |  | 2020-12-01 | Queue Position 833 | Addition of new115 kV Switching Station on line 93 to Accomdate QP-833 | [27 empty] | Concept | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [27 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1803 | ME | Emera Maine |  |  | 2023-10-01 | Queue Position 760 | Addition of new115 kV Switching Station on line 52 to Accomdate QP-760 | [27 empty] | Concept | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [27 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1802 | ME | Versant Power |  |  | 2022-09-01 | Queue Position 649 | Addition of new 115 kV Switching Station on line 66 to accomdate QP 649 | [27 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2019-08-26 | NR | [27 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1801 | MA | Eversource |  |  | 2023-10-01 | Queue Position 624 | Upgrade the protection systems to meet the NPCC BPS design requirements at the Tremont #713 substation | [26 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 4/2/2019 4/27/2023 | NR | [26 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1800 | MA | Eversource |  |  | 2023-05-01 | Queue Position 624 | Install two 115 kV breakers and associated equipment at the Barnstable #958 substation | [26 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 4/2/2019 4/27/2023 | NR | [26 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1799 | CT | Eversource |  |  | 2025-02-01 | Queue Position 724 | Sectionalize the 3271 345 kV line with a tap in and out of the Cotton Bridge Substation | [26 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2019-05-01 | NR | [26 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1798 | CT | Eversource |  |  | 2025-02-01 | Queue Position 724 | Construct a new 345 kV three breaker ring bus Cotton Bridge Substation | [26 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2019-05-01 | NR | [26 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1797 | CT | Eversource |  |  | 2022-05-01 | Queue Position 647 | Uprate the 1766 115 kV line | [26 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2019-03-20 | NR | [26 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1796 | CT | Eversource |  |  | 2022-05-01 | Queue Position 647 | Install P&C changes associated with the four 115 kV breakers | [26 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2019-03-20 | NR | [26 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1795 | CT | Eversource |  |  | 2022-05-01 | Queue Position 647 | Disconnect existing unit 2 and 3 and connect new unit 5 to the unit position 2 | [26 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2019-03-20 | NR | [26 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1794 | CT | Eversource |  |  | 2021-12-01 | Queue Position 588 | Split the existing 115 kV 1000/1080 double circuit tower | [25 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2018-10-24 | NR | [25 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1793 | CT | Eversource |  |  | 2021-12-01 | Queue Position 588 | Construct a new three breaker ring bus Quinebaug 115 kV substation | [25 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2018-10-24 | NR | [25 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1792 | NH | Eversource |  |  | 2019-08-01 | Antrim Wind QP 543 | Bifurcate the L-163 115 kV line and construct a 115 kV three breaker ring bus (Tuttle Hill) | [25 empty] | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2017-02-24 | NR | [25 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1791 | ME | Versant Power |  |  | 2022-05-01 | Queue Position 620 | Addition of Deblois 115 kV Switching Station to Accomdate QP-620 | [24 empty] | Concept | Concept | Concept | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2019-08-26 | NR | [24 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1790 | MA | Eversource |  |  | 2020-11-01 | Southeast Massachusetts/Rhode Island Reliability Project | Medway 115 kV Circuit Breaker Replacements | [24 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-05-01 | No | [24 empty] | 4865000 | 4865000 | 4865000 | 4865000 | 4865000 | 4865000 | 4865000 | 4865000 | 4865000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 0
Reliability Upgrade | 1a | 1789 | MA | Eversource |  |  | 2021-04-01 | Southeast Massachusetts/Rhode Island Reliability Project | West Medway 345 kV circuit breaker upgrades | [24 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-05-01 | No | [24 empty] | 6309000 | 6309000 | 6309000 | 6309000 | 6309000 | 6309000 | 6309000 | 6309000 | 6309000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 0
Generator Interconnection Upgrade | 2a | 1788 | MA | National Grid, USA |  |  | 2026-05-01 | Queue Position 618 | Install four 345 kV breakers at the Brayton Point substation to convert from a ring bus to a breaker and a half configuration | [24 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-10-11 | NR | [24 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1787 | MA | Eversource |  |  | 2026-05-01 | Queue Position 618 | Installation of a .52 mile underground 3500 kcmil CU XLPE 345 kV line from Brayton Point Substation to the Bay State Wind 1 345/275 kV | [24 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-10-11 | NR | [24 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1786 | MA | Eversource |  |  | 2026-05-01 | Queue Position 618 | Installation of a two 275/66 kV transformers at the Bay State Wind substation | [24 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-10-11 | NR | [24 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1785 | MA | Eversource |  |  | 2026-05-01 | Queue Position 618 | Installation of two 59 mile 275 kV submarine cables from the Bay State Wind 275/66 kV substation, off-shore to the Bay State Wind 345/275 kV substation | [24 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-10-11 | NR | [24 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1784 | MA | Eversource |  |  | 2026-05-01 | Queue Position 618 | Installation of a two 345/275 kV transformers at the Bay State Wind substation | [24 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-10-11 | NR | [24 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1783 | MA | Eversource |  |  | 2026-05-01 | Queue Position 618 | Installation of two 140 MVAR STATCOMs at the Bay State Wind 345/275 kV substation | [24 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-10-11 | NR | [24 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1782 | RI | National Grid, USA |  |  | 2022-05-01 | Southeast Massachusetts/Rhode Island Reliability Project | Reconductor the J16S line | [23 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [23 empty] | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 0
Generator Interconnection Upgrade | 2a | 1781 | MA | National Grid, USA |  |  | 2020-08-01 | Queue Position 592 | Install a second 115 kV capacitor bank (63 MVAR) and increase the size of the first 115 kV capacitor bank from 50 MVAR to 63 MVAR to address negative impact on Bear Swamp area voltages during pumping conditions | [22 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2017-06-02 | NR | [22 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1780 | MA | Eversource |  |  | 2021-12-01 | Queue Position 651 | 600 MW 345 kV HVDC Tie (import only) NY Alps Substation to Eversource Berkshire Substation | [22 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [22 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1779 | MA | Eversource |  |  | 2022-12-01 | Queue Position 640 | 1000 MW 345 kV HVDC Tie (import only) New Brunswick, Canada Coleson Cove Substation to Eversource Pilgrim Substation | [22 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [22 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1778 | MA | Eversource |  |  | 2027-10-01 | Queue Position 506 | Add four 345 kV breakers at K St. | [22 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-10-31 | NR | [22 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1777 | MA | Eversource |  |  | 2027-10-01 | Queue Position 506 | HVDC Terminal to K St. | [22 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-10-31 | NR | [22 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1776 | ME | Emera Maine |  |  | 2019-12-01 | Queue Position 657 | Downeast Loop Transfer Increase | [22 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [22 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1775 | ME | Versant Power |  |  | 2020-11-01 | Queue Position 420 | Upgrades at Bull Hill Switching Station to accommodate QP 420 | [22 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2018-03-26 | NR | [22 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1774 | MA | Eversource |  |  | 2019-08-01 | Queue Position 508 | Upgrade Montague substation to include replacement of one 800A wave trap with a 1200A wave trap as well as upgrade the substation conductor to 1590 MCM ACSR | [21 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-07-10 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1773 | MA | Eversource |  |  | 2019-08-01 | Queue Position 508 | Upgrade Cumberland substation including replacement of one 800A wave trap with a 1200A wave trap as well as changes to relay settings | [21 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-07-10 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1772 | MA | Eversource |  |  | 2019-08-01 | Queue Position 508 | Installation of a 23.3 mile overhead 345 kV transmission line from Berkshire to Alps in New York using 954 MCM ACSS | [21 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-07-10 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1771 | MA | Eversource |  |  | 2019-08-01 | Queue Position 508 | Addition of a 600 MW HVDC Conveter at the Berkshire Substation | [21 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-07-10 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1770 | MA | Eversource |  |  | 2019-08-01 | Queue Position 508 | Replacement of the 345/115 kV 2X transformer at the Berkshire substation. Modify Berkshire to a six circuit breaker ring bus and the new autotransformer will have isolation devices on the primary and secondary side of the autotransformer | [21 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-07-10 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1769 | MA | Eversource |  |  | 2019-08-01 | Queue Position 508 | Rebuild of the 7.8 mile overhead 115 kV 1211 Line Doreen substation to North Tap and North Tap to Oswald substation using 556 MCM ACSS | [21 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-07-10 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1768 | MA | Eversource |  |  | 2019-08-01 | Queue Position 508 | Rebuild of the 26.2 mile overhead 115 kV 1242 Line from Berkshire to Plainfield Tap. Plainfield Tap to the Ashfield Tap and Ashfield Tap to the Cumberland substation using 556 MCM ACSS | [21 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-07-10 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1767 | MA | Eversource |  |  | 2019-08-01 | Queue Position 508 | Rebuild of the 26.2 mile overhead 115 kV 1231 Line from Berkshire to Plainfield Tap. Plainfield Tap to the Ashfield Tap and Ashfield Tap to the Cumberland substation using 556 MCM ACSS | [21 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-07-10 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1766 | CT | Eversource |  |  | 2019-09-01 | Queue Position 598 | Construct new substation on the 3271 345 kV line between Lake Road and Card substations | [21 empty] | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1765 | CT | Eversource |  |  | 2019-12-01 | Queue Position 588 | New 115 kV three breaker ring bus and rebuild the Tunnel to Ledyard Jct. portion of the 69 kV 400 line | [21 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1764 | CT | Eversource |  |  | 2020-10-01 | Nutmeg Solar QP 552 | Install two 115 kV circuit breakers at Scitico substation and underground line to generator | [21 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2016-11-08 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1763 | MA | Eversource |  |  | 2018-09-01 | Medway Peaker QP 444 | Replace switch conductors, cable bus at Medway #65 | [21 empty] | Proposed | Proposed | Proposed | Proposed | in-service | in-service | in-service | in-service | in-service | in-service | in-service | in-service | in-service | in-service | in-service | in-service | in-service | in-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | No | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1762 | MA | National Grid, USA |  |  | 2022-05-01 | Queue Position 489 | Relocate existing 328/341/347 345kV lines to make way for new 3502 interconnection line to QP489 | [21 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-10-21 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1761 | ME | Central Maine Power Company |  |  | 2020-11-01 | Queue Position 659 | 1200 MW Construction of 140 miles of new 345 kV AC transmission line from new Gold Brook 345 kV Substation in Skinner Township, ME to existing Larrabee Road 345 kV Substation in Lewiston ME | [21 empty] | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1760 | ME | Central Maine Power Company |  |  | 2020-11-01 | Queue Position 658 | 660 MW Construction of 140 miles of new 345 kV AC transmission line from new Gold Brook 345 kV Substation in Skinner Township, ME to existing Larrabee Road 345 kV Substation in Lewiston ME | [21 empty] | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1759 | CT | Eversource |  |  | 2019-05-01 | Queue Position 501 | Uprate ES's section of the 398 (Long Mountain - Pleasant Valley) 345 kV line | [20 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2018-06-22 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1758 | NH | Eversource |  |  | 2027-12-01 | Queue Position 501 | Uprate the A152 (Chestnut Hill - Westport - A152 Tap) 115 kV line | [20 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2016-11-01 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1757 | NH | Eversource |  |  | 2027-12-01 | Queue Position 501 | Uprate the N186 (Vernon Road Tap - Chestnut Hill) 115 kV line | [20 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2016-11-01 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1756 | VT | Green Mountain Power |  |  | 2019-05-01 | Queue Position 501 | Upgrade the Cross Road - Mosher's Tap 46 kV line, reconductor 69 miles of 46 kV lines, and upgrade the Lowell 46/34.5 kV transformer | [20 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1755 | VT | Vermont Electric Power Company |  |  | 2019-05-01 | Queue Position 501 | Replace the North Rutland and Irasburg 115/46 kV transformers; replace a relay for the Middlebury 115/46 kV transformer and increase cooling on the Newfane 115/46 kV transformer | [20 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-11-01 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1754 | VT | Vermont Electric Power Company |  |  | 2027-12-01 | Queue Position 501 | Reconductor the K43 (New Haven - Williston) 115 kV line | [20 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2016-11-01 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1753 | VT | Vermont Electric Power Company |  |  | 2027-12-01 | Queue Position 501 | Reconductor the K27 (Williston - Tafts Corner) 115 kV line | [20 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2016-11-01 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1752 | VT | Vermont Electric Power Company |  |  | 2027-12-01 | Queue Position 501 | Replace a line drop for the K30 (Middlebury - Florance) 115 kV line | [20 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2016-11-01 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1751 | VT | Vermont Electric Power Company |  |  | 2019-05-01 | Queue Position 501 | Reconductor the K32 (Coolidge - Cold River) 115 kV line | [20 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-11-01 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1750 | VT | Vermont Electric Power Company |  |  | 2027-12-01 | Queue Position 501 | Reconductor VELCO's section of the 381 (Vernon - Northfield) 345 kV line | [20 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2016-11-01 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1749 | VT | Vermont Electric Power Company |  |  | 2027-12-01 | Queue Position 501 | Add two 345 kV circuit breakers at the Coolidge 345 kV substation | [20 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2016-11-01 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1748 | VT | Vermont Electric Power Company |  |  | 2020-12-01 | Queue Position 498 | Increase the LTE ratings of both New Haven 345/115 kV autotransformers | [20 empty] | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1747 | VT | Vermont Electric Power Company |  |  | 2020-12-01 | Queue Position 498 | Reconductor the K43 (New Haven - Williston) 115 kV line | [20 empty] | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-12-28 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1746 | VT | Vermont Electric Power Company |  |  | 2020-12-01 | Queue Position 498 | Add two 345 kV circuit breakers at New Haven and close the New Haven 345 kV ring station | [20 empty] | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-12-28 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1745 | MA | Eversource |  |  | 2025-11-01 |  | New East Eagle 115 kV station between Mystic and Chelsea | [20 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | Y-Proposed | 2016-06-09 | No | [20 empty] | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 74800000 | 74204000 | 73264000 | 73264000 | 73264000 | 73264000 | 73264000 | 73264000 | 62854945 | 62854945 | 0
Elective Upgrade | 4b | 1744 | MA | National Grid, USA | Eversource |  | 2023-12-01 | Queue Position 625 | 1600 MW 345 kV AC line Brayton Point Substation interconnection | [20 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1743 | NH | National Grid, USA |  |  | 2022-12-01 | Queue Position 627 | 400 kV HVDC Tie-Import only project connecting to Comerford 230 kV substation | [20 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1742 | RI | National Grid, USA |  |  | 2020-10-01 | Southeast Massachusetts/Rhode Island Reliability Project | Remote terminal station work (Wampanoag and Pawtucket 115 kV) for new 115 kV Grand Army GIS switching station to tie the E-183E, F-184, X3 and W4 lines (associated with RSP 1714) | [20 empty] | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [20 empty] | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 0
Reliability Upgrade | 1a | 1741 | MA | Middleborough Gas and Electric |  |  | 2019-04-01 | Southeast Massachusetts/Rhode Island Reliability Project | Rebuild the Middleborough Gas and Electric (MGED) portion of the E1 line from Bridgewater to Middleborough (2.5 miles) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 0
Generator Interconnection Upgrade | 2a | 1740 | MA | Eversource |  |  | 2018-12-01 | Milford 2 QP 527 | Install one pilot protection scheme on 201-501 line at Medway #65 | [19 empty] | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2016-12-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1739 | MA | Eversource |  |  | 2018-05-01 |  | Build a new 115kV Substation - Seafood Way | [19 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-07-19 | 4/14/2021 12/10/2021 | [19 empty] | 60000000 | 60000000 | 52616000 | 52616000 | 52616000 | 52616000 | 52616000 | 52616000 | 52616000 | 52616000 | 52616000 | 52616000 | 52616000 | 38016000 | 38016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 0
Reliability Upgrade | 1a | 1738 | MA | Eversource |  |  | 2021-07-01 | Greater Boston - Stability | Chelsea Station #488 BPS upgrade | [19 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | NR | No | [19 empty] | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 0
Reliability Upgrade | 1a | 1737 | MA | Eversource |  |  | 2020-08-01 | Southeast Massachusetts/Rhode Island Reliability Project | Replace disconnect switches 107A, 107B, 108A and 108B on Line 323 at West Medway Substation #446. Replace 8 line structures with taller structures | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 200000 | 200000 | 200000 | 200000 | 2064000 | 2064000 | 2064000 | 2064000 | 2064000 | 2064000 | 2064000 | 2064000 | 2064000 | 2064000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 0
Reliability Upgrade | 1a | 1736 | MA | Eversource |  |  | 2018-10-01 | Southeast Massachusetts/Rhode Island Reliability Project | Reconductor the 108 line from Bourne Substation #917 to Horse Pond Tap | [19 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 5/4/2017 12/20/2018 | No | [19 empty] | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 2756000 | 2756000 | 2756000 | 2756000 | 2756000 | 2756000 | 2756000 | 2756000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 0
Reliability Upgrade | 1b | 1735 | MA | Eversource |  |  | 2021-12-01 | Southeast Massachusetts/Rhode Island Reliability Project | Replace wave trap on 114 line at Tremont Substation #713 | [19 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [19 empty] | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 0
Reliability Upgrade | 1a | 1734 | MA | Eversource |  |  | 2018-06-01 | Southeast Massachusetts/Rhode Island Reliability Project | Reconductor/Upgrade 112 Line Tremont Substation #713 to Industrial Tap and terminal equipment | [19 empty] | Proposed | Proposed | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2017-05-04 | No | [19 empty] | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 0
Reliability Upgrade | 1a | 1733 | MA | Eversource |  |  | 2021-12-01 | Southeast Massachusetts/Rhode Island Reliability Project | Separate the 325/344 DCT lines - West Medway to West Walpole | [19 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | 2017-05-04 | No | [19 empty] | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 0
Reliability Upgrade | 1a | 1732 | MA | Eversource |  |  | 2025-11-01 | Southeast Massachusetts/Rhode Island Reliability Project | Loop 201-502 line into Medway #65 Substation to form the 201-502N and 201-502S lines | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 22684000 | 22684000 | 0
Reliability Upgrade | 1a | 1731 | MA | Eversource |  |  | 2021-12-01 | Southeast Massachusetts/Rhode Island Reliability Project | Install 35.3 MVAR 115 kV capacitors at High Hill Substation #644 and Wing Lane Substation #624 | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 0
Reliability Upgrade | 1a | 1730 | MA | Eversource |  |  | 2026-12-01 | Southeast Massachusetts/Rhode Island Reliability Project | Extend the 115 kV 114 line from Eversource/National Grid border to Industrial Park Tap | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | No | 2018-04-30 | No | [19 empty] | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 0
Reliability Upgrade | 1a | 1729 | MA | Eversource |  |  | 2023-08-01 | Southeast Massachusetts/Rhode Island Reliability Project | Install a new bay position at Kingston for Carver line | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 0
Reliability Upgrade | 1a | 1728 | MA | Eversource |  |  | 2023-08-01 | Southeast Massachusetts/Rhode Island Reliability Project | Build a new Carver to Kingston 115 kV line and Carver terminal | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 0
Reliability Upgrade | 1a | 1727 | MA | Eversource |  |  | 2021-11-01 | Southeast Massachusetts/Rhode Island Reliability Project | Retire Barnstable SPS | [19 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2017-05-04 | No | [19 empty] | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 0
Reliability Upgrade | 1a | 1726 | MA | Eversource |  |  | 2021-12-01 | Southeast Massachusetts/Rhode Island Reliability Project | Separate the 135/122 DCT lines - West Barnstable to Barnstable | [19 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2017-05-04 | No | [19 empty] | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 0
Reliability Upgrade | 1a | 1725 | MA | Eversource |  |  | 2024-05-01 | Southeast Massachusetts/Rhode Island Reliability Project | Build a new Bourne #917 to West Barnstable #921 115 kV line and associated terminal work | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 59100000 | 59100000 | 59100000 | 59100000 | 59100000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 0
Reliability Upgrade | 1a | 1724 | RI | National Grid, USA |  |  | 2022-03-01 | Southeast Massachusetts/Rhode Island Reliability Project | Kent County T3 345/115 kV transformer replacement | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 8100000 | 8100000 | 8100000 | 8100000 | 8100000 | 8100000 | 8100000 | 8100000 | 4714000 | 4714000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 0
Reliability Upgrade | 1a | 1723 | MA | National Grid, USA |  |  | 2021-09-01 | Southeast Massachusetts/Rhode Island Reliability Project | Reconductor L14 and M13 from Bell Rock to Bates Tap (8.3 miles each) | [19 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | 2017-05-04 | No | [19 empty] | 29200000 | 29200000 | 29200000 | 29200000 | 29200000 | 29200000 | 29200000 | 29200000 | 29200000 | 29200000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 0
Reliability Upgrade | 1a | 1722 | MA | National Grid, USA |  |  | 2026-12-01 | Southeast Massachusetts/Rhode Island Reliability Project | Extend Line 114 - Dartmouth town line (Eversource- NGRID border) to Bell Rock (~4.2 miles) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | No | 2018-04-30 | No | [19 empty] | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 13944000 | 13944000 | 13944000 | 13944000 | 13944000 | 13944000 | 13944000 | 13944000 | 13944000 | 13944000 | 22616000 | 22616000 | 22616000 | 22616000 | 22616000 | 0
Reliability Upgrade | 1a | 1721 | MA | National Grid, USA |  |  | 2023-08-01 | Southeast Massachusetts/Rhode Island Reliability Project | Reconfigure Bell Rock to breaker and a half station, and upgrade to BPS standards, split M13 line at Bell Rock and terminate 114 line at Bell Rock. Install new breaker in series with N12/D21 tie breaker, upgrade D21 line switch and install 37.5 MVAR capacitor. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 4/30/2018 12/20/2018 | No | [19 empty] | 18900000 | 18900000 | 18900000 | 18900000 | 18900000 | 18900000 | 18900000 | 18900000 | 18900000 | 18900000 | 30800000 | 30800000 | 30800000 | 30800000 | 30800000 | 30800000 | 30800000 | 30800000 | 35500000 | 35500000 | 36180000 | 36180000 | 36180000 | 36180000 | 36180000 | 36180000 | 36180000 | 36180000 | 36180000 | 0
Reliability Upgrade | 1a | 1720 | MA | National Grid, USA |  |  | 2027-03-01 | Southeast Massachusetts/Rhode Island Reliability Project | Separate N12/M13 DCT & reconductor N12 & M13 between Somerset and Bell Rock (~3.5 miles) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | No | 10/24/2023 4/30/2018 | No | [19 empty] | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 80000000 | 101120000 | 101120000 | 101120000 | 101120000 | 101120000 | 101120000 | 101120000 | 101120000 | 101120000 | 101120000 | 0
Reliability Upgrade | 1a | 1719 | MA | National Grid, USA |  |  | 2020-12-01 | Southeast Massachusetts/Rhode Island Reliability Project | Install 45.0 MVAR capacitor bank at Berry Street | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | 2018-04-30 | No | [19 empty] | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 3565000 | 3565000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 0
Reliability Upgrade | 1a | 1718 | MA | National Grid, USA |  |  | 2022-03-01 | Southeast Massachusetts/Rhode Island Reliability Project | Robinson Ave 115 kV circuit breaker addition and reterminate Q10 line | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 1039000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 0
Reliability Upgrade | 1a | 1717 | MA | National Grid, USA |  |  | 2019-11-01 | Southeast Massachusetts/Rhode Island Reliability Project | Separate X3/W4 DCT and reconductor X3, W4 lines between Somerset and Grand Army (~2.7 miles each). Reconfigure Y2 and Z1 | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 14600000 | 14600000 | 14900000 | 14900000 | 14900000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 16196000 | 16196000 | 16196000 | 16196000 | 16196000 | 16196000 | 16196000 | 0
Reliability Upgrade | 1a | 1716 | MA | National Grid, USA |  |  | 2019-11-01 | Southeast Massachusetts/Rhode Island Reliability Project | Increase clearances on E-183E & F-184 lines between Brayton Point & Grand Army (~1.5 miles each) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4283000 | 4283000 | 4283000 | 4283000 | 4283000 | 4283000 | 4283000 | 4283000 | 0
Reliability Upgrade | 1a | 1715 | MA | National Grid, USA |  |  | 2020-10-01 | Southeast Massachusetts/Rhode Island Reliability Project | Upgrades at Brayton Point (new 115 kV breaker, new 345/115 kV transformer and upgrades to E183E, F184 station equipment) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 13100000 | 13100000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 15381000 | 15381000 | 15381000 | 15381000 | 15381000 | 15381000 | 15381000 | 15381000 | 15381000 | 15644000 | 15644000 | 15644000 | 15644000 | 15644000 | 15644000 | 15644000 | 15644000 | 0
Reliability Upgrade | 1a | 1714 | MA | National Grid, USA |  |  | 2020-10-01 | Southeast Massachusetts/Rhode Island Reliability Project | New Grand Army 115 kV GIS switching station built to BPS standards, remote terminal station work (Brayton Point and Somerset) & loop E-183E, F-184, X3 and W4 lines (associated with RSP 1742) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 43800000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 52080000 | 52080000 | 52080000 | 52080000 | 52080000 | 52080000 | 52080000 | 52080000 | 52080000 | 51919000 | 51919000 | 51919000 | 51919000 | 51919000 | 51919000 | 51919000 | 51919000 | 0
Generator Interconnection Upgrade | 2a | 1713 | RI | National Grid, USA |  |  | 2022-05-01 | Queue Position 489 | Install an additional 345 kV bay at Sherman Road switching station for the interconnection of the new generator | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-10-21 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1712 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Thermal uprate of the 115 kV K189 line. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1711 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Riverside 115 kV substation upgrades | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1710 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Valley 115 kV substation upgrades | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1709 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Reconductor the 115 kV G185N line. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1708 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Reconductor the 115 kV H17 line. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1707 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Reconductor the 115 kV R9 (RI portion) line. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1706 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Replace West Farnum substation 345/115 kV 175T transformer. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1705 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Replace West Farnum substation 345/115 kV 174T transformer. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1704 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Reconductor the 115 kV T172N tap line to West Farnum. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1703 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Reconductor the 115 kV S171N tap line to West Farnum. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1702 | MA | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Reconductor the 115 kV R9 line (MA portion) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1701 | CT | Eversource |  |  | 2018-11-01 | PSEG Bridgeport Harbor FCA 10 QP 412 | Reconductor the 115 kV 1670-1 from ACSR to ACSS | [18 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2016-12-28 | NR | [18 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1700 | CT | Eversource |  |  | 2022-01-01 | Beacon Falls | Reconfigure the Beacon Falls substation to a 115 kV ring bus | [18 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-11-08 | NR | [18 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1699 | MA | Eversource |  |  | 2023-03-01 | Queue Position 501 | Reconductor ES's section of the 381 (Vernon - Northfield) 345 kV line. (MA portion) | [18 empty] | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-11-01 | NR | [18 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1698 | MA | Eversource |  |  | 2022-01-01 | Queue Position 489 | Reconductor the 345 kV 3361 line | [18 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-10-21 | NR | [18 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1697 | NH | Eversource |  |  | 2027-12-01 | Queue Position 501 | Reconductor ES's section of the 381 (Vernon - Northfield) 345 kV line. (NH portion) | [18 empty] | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2016-11-01 | NR | [18 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1696 | ME | Emera Maine |  |  | 2019-10-01 | Queue Position 400 | Add breaker to existing Epping Switching station to accommodate QP-400 | [17 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-06-30 | NR | [17 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1695 | ME | New Hampshire Transmission, LLC |  |  | 2019-10-01 | Queue Position 591 | 400 MW of Incremental Transfer Capability on 345 kV AC lines in the Surowiec, ME area | [16 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [16 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1694 | ME | Central Maine Power Company and Emera Maine |  |  | 2019-12-01 | Queue Position 590 | 1200 MW 345 kV AC line from Hammond, ME to Pittsfield, ME | [16 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [16 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1693 | ME | Central Maine Power Company |  |  | 2019-10-01 | Queue Position 589 | 550 MW 345 kV AC line from Johnson Mountain Township, ME to Pittsfield, ME | [16 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [16 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1692 | MA | Eversource | Central Maine Power Company |  | 2020-12-01 | Queue Position 585 | 900 MW 345 kV HVDC Tie. New Brunswick, Canada Coleson Cove Substation to Eversource Mystic Substation | [16 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [16 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1691 | ME | Next Era |  |  | 2019-10-01 | Queue Position 571 | 850 MW of Energy Transfer Capability from the proxy Concord Switching Station to Larrabee Road 345 kV Substation | [16 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [16 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1690 | MA | Eversource | Emera Maine |  | 2021-12-01 | Queue Position 569 | 1200 MW 345 kV HVDC Tie. Emera Orrington Substation in ME to Eversource Jordan Rd, MA | [16 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [16 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1689 | ME | Emera Maine |  |  | 2021-12-01 | Queue Position 569 | 1200 MW 345 kV HVDC Tie. Emera Orrington Substation in ME to Eversource Jordan Rd, MA | [16 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [16 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1688 | MA | Eversource |  |  | 2018-12-01 | Canal 3 | Install 0.3 mile overhead 345 kV line and disconnect switch at Canal substation at existing bus position between breakers 812P and 812S | [16 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-11-05 | NR | [16 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1687 | CT | Town of Wallingford, Department of Public Utilities (“WED”) |  |  | 2018-03-01 | Queue Position 440 | Replace the 795 kcml ACSR 115 kV transmission line from the Wallingford 13M 1305 Line to the Wallingford Energy 6G 1305 Line with 1590 kcml ACSR | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2/10/2015 | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1686 | CT | United Illuminating Company |  |  | 2019-06-01 | Queue Position 412 | Terminate and connect the 345 kV underground line from QP 412 to the Singer 345 kV Substation | [15 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2/10/2015 | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1685 | MA | Eversource |  |  | 2018-03-01 | Queue Position 541 | Upgrade the necessary terminal equipment at Agawam 16C Substation to match or exceed the 1302 line conductor ratings | [15 empty] | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 4/16/2015 | No | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1684 | MA | Eversource |  |  | 2018-03-01 | Queue Position 541 | Reconductoring of the 1657-3 line section (approximately 160 feet) from Southampton Junction to the Eversource / HG&E border using 795 kcmil ACSS conductor | [15 empty] | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 4/16/2015 | No | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1683 | MA | Eversource |  |  | 2018-03-01 | Queue Position 541 | Construct a new 115-kV four breaker ring bus switching station in Westfield, MA. Loop the existing line 1302 (between Buck Pond and Pochassic tap) into the new switching station and terminate to establish new lines from Buck Pond 34B Substation to PVEC | [15 empty] | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 4/16/2015 | No | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1682 | NH | Eversource |  |  | 2017-09-01 | Spruce Ridge | Thermal upgrade of the 11 mile 115 kV A111 Line from Webster Substation in Webster, NH to Pemigewassett Substation in Littleton, NH from 135 MVA to 138 MVA | [15 empty] | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 4/16/2015 | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1681 | NH | Eversource |  |  | 2017-09-01 | Spruce Ridge | Thermal upgrade of the 8 mile 115 kV E115-2 Line from Ashland Tap in Ashland, NH to the Pemigewassett Substation in Littleton, NH from 135 MVA to 138 MVA | [15 empty] | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 4/16/2015 | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1680 | NH | National Grid, USA |  |  | 2019-01-01 | Spruce Ridge | Construct a 230 kV three breaker interconnection substation in Groton, NH. Construct a 0.05 mile long, 230 kV tap line connecting the interconnection substation to the 230 kV A-201 transmission line. | [15 empty] | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 4/16/2015 | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1679 | CT | Town of Wallingford Department of Public Utilities |  |  | 2015-04-01 | SWCT | 1630 13M Terminal Upgrade | [15 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | [15 empty] | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 0
Reliability Upgrade | 1b | 1678 | MA | National Grid, USA |  |  | 2020-06-01 |  | Salem Harbor Substation Rebuild (Asset Condition) | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Proposed | NR | No | [15 empty] | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 0
Generator Interconnection Upgrade | 2a | 1677 | CT | Eversource |  |  | 2018-06-01 | CPV Towantic | Rebuild 115 kV 1730 Line section between Devon to the UI Border/Trumbull 115 kV substation | [15 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 8/25/2015 | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1676 | CT | Eversource |  |  | 2018-06-01 | CPV Towantic | Rebuild 115 kV 1710 Line section between Devon to Trumbull | [15 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1675 | CT | Eversource |  |  | 2017-09-01 | CPV Towantic | Rebuild 115 kV 1575N-1 QP384 to Baldwin Tap | [15 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 8/25/2015 | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1674 | MA | National Grid, USA |  |  | 2018-11-01 | Deerfield Wind | Reconductor the 69 kV J-10 line between the Adams and Deerfield #5 substations with 477 ACSR | [15 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-07-09 | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1673 | VT | Green Mountain Power |  |  | 2017-12-01 | Deerfield Wind | Installation of 3-breaker 69 kV ring bus interconnecting to the Bennington - Searsburg 69 kV Y25N line. | [15 empty] | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-08-25 | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1672 | MA | Hudson Light and Power |  |  | 2025-06-01 | Greater Boston - Western Suburbs | Forest Ave Substation modification required to build a new 115 kV line from Sudbury Station 342 substation to Hudson substation (This is the HLP portion of the line and terminal work) | [14 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [14 empty] | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5500000 | 5500000 | 5500000 | 5500000 | 5500000 | 5500000 | 5500000 | 5500000 | 5500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 8300000 | 8300000 | 8500000 | 8500000 | 8500000 | 0
Reliability Upgrade | 1a | 1671 | RI | National Grid, USA |  |  | 2021-03-01 | Aquidneck Island Reliability Project | Convert lines 61/62 from 69 kV to 115 kV | [14 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2017-03-31 | No | [14 empty] | 22100000 | 22100000 | 22100000 | 22100000 | 22100000 | 22100000 | 22100000 | 22100000 | 25444620 | 25444620 | 25444620 | 33947000 | 33947000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 0
Reliability Upgrade | 1a | 1670 | RI | National Grid, USA |  |  | 2021-03-01 | Aquidneck Island Reliability Project | Remove 115kV to 69 kV transformer at Dexter Substation | [14 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2017-03-31 | No | [14 empty] | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 2190000 | 2120000 | 2120000 | 2177000 | 2177000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 0
Reliability Upgrade | 1a | 1669 | RI | National Grid, USA |  |  | 2021-03-01 | Aquidneck Island Reliability Project | Conversion of Jepson 69 kV substation to 115 kV substation | [14 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2017-03-31 | No | [14 empty] | 9500000 | 9500000 | 9500000 | 9500000 | 9500000 | 9500000 | 9500000 | 9500000 | 13437000 | 12840000 | 12840000 | 13468000 | 13468000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 0
Reliability Upgrade | 1a | 1668 | MA | Norwood Municipal Light Department |  |  | 2016-12-01 |  | Rebuild 115 kV lines 447-508 and 447-509 from the Eversource tap in Sharon to Dean St. #496 substation in Norwood | [14 empty] | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-02-25 | 2015-04-30 | [14 empty] | 12700000 | 12700000 | 12700000 | 12700000 | 12700000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 0
Generator Interconnection Upgrade | 2a | 1667 | ME | Emera Maine |  |  | 2016-12-01 | Queue Position 397 | Add tap to existing Bull Hill Switching station to accommodate QP 397 | [14 empty] | Proposed | Proposed | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-07-07 | NR | [14 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1666 | MA | Eversource |  |  | 2016-04-01 | Acushnet to Pine St. Reliability Project | Install one 115 kV breaker in series with existing Acushnet Sub EW22 breaker | [14 empty] | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-07-17 | NR | [14 empty] | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 0
Reliability Upgrade | 1a | 1665 | MA | Eversource |  |  | 2017-12-01 | Pittsfield / Greenfield Project | Install a 75-150 MVAR variable reactor at Ludlow substation | [14 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-01-26 | 2019-02-15 | [14 empty] | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 0
Reliability Upgrade | 1a | 1664 | MA | Eversource |  |  | 2017-12-01 | Pittsfield / Greenfield Project | Install a 75-150 MVAR variable reactor at Northfield substation | [14 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-01-26 | 2019-02-15 | [14 empty] | 14400000 | 14400000 | 14400000 | 14400000 | 14400000 | 14400000 | 14400000 | 14400000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 0
Reliability Upgrade | 1a | 1663 | MA | Eversource |  |  | 2020-06-01 | Pittsfield / Greenfield Project | Construct a 115 kV three breaker ring bus at or adjacent to Pochassic 37R Substation, loop line 1512-1 into the new three breaker ring bus, construct a new line connecting the new three breaker ring bus to the Buck Pond 115 kV Substation on the vacant side of the double circuit towers that carry line 1302-2, add a new breaker to the Buck Pond 115-kV straight bus and reconnect lines 1302-2, 1657-2 and transformer 2X into new positions | [14 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-05-05 | 2019-02-15 | [14 empty] | 39600000 | 39600000 | 39600000 | 39600000 | 39600000 | 39600000 | 39600000 | 39600000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 0
Reliability Upgrade | 1a | 1662 | MA | Eversource |  |  | 2017-12-01 | Pittsfield / Greenfield Project | Install a 115 kV 20.6 MVAR capacitor at Doreen substation and operate the 115kV 13T breaker N.O. | [14 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-01-26 | 2019-02-15 | [14 empty] | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 0
Reliability Upgrade | 1a | 1661 | NH | Eversource |  |  | 2016-10-01 | LSP-Rimmon Substation Project | Rebuild Rimmon substation and add three 115 kV breakers, install a 2nd 115/34.5 kV transformer and two 115 kV 13.3 MVAR capaciters, connect the Rimmon substation to the J114 line; install a series 115 kV breaker at Greggs substation | [14 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y- Proposed | 2015-11-05 | 2016-01-07 | [14 empty] | 15500000 | 15500000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 0
Reliability Upgrade | 1a | 1660 | NH | Eversource |  |  | 2016-12-01 | LSP-North Keene Substation Project | Replace four of the existing transformers at Keene substation with one 115/12.47 kV 30 MVA transformer;Construct a N. Keene Substation, loop in the L163 line with two 115 kV breakers, install one 115/12.47 kV 30 MVA transformer | [14 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y- Proposed | 2015-11-05 | 2016-01-07 | [14 empty] | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 0
Reliability Upgrade | 1a | 1659 | CT | Eversource |  |  | 2017-03-01 | GHCC | Increase the size of the existing 115 kV capacitor at Branford substation from 37.8 to 50.4 MVAR | [14 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [14 empty] | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 0
Elective Upgrade | 4b | 1658 | MA | Eversource |  |  | 2018-12-01 | Queue Position 518 | 1000 MW HVDC from CMP ME Yankee 345 kV substation to Eversource K street 115 kV substation | [13 empty] | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1657 | MA | Eversource |  |  | 2018-12-01 | Queue Position 517 | 1000 MW HVDC from CMP ME Yankee 345 kV substation to Eversource Mystic 345 kV substation | [13 empty] | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1656 | MA | Eversource |  |  | 2020-12-01 | Queue Position 511 | 1000 MW HVDC line to Eversource Barnstable 345 kV | [13 empty] | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1655 | NH | Eversource |  |  | 2019-04-01 | Queue Position 519 | 1200 MW HVDC connection (Des Cantons-Deerfield) | [13 empty] | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1654 | NH | Eversource |  |  | 2022-12-01 | Queue Position 499 | 300 kV 1090 MW HVDC connection (Des Cantons-Deerfield) | [13 empty] | Concept | Concept | Concept | Concept | Concept | Planned | Planned | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-07-19 | NR | [12 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1653 | ME | Emera Maine |  |  | 2016-10-01 | Queue Position 333 | Install a new 13.6 Ohm series capacitor in the 345 kV transmission line (388) between Orrington to Coopers Mills | [13 empty] | Concept | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-03-02 | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1652 | ME | Emera Maine |  |  | 2016-10-01 | Queue Position 333 | Move the existing Orrington series capacitor from the 345 kV transmission line (388) between Orrington to Coopers Mills to the 345 kV transmission line (3023) between Orrington to Albion Road due to line configuration change and reduce the size from 25 Ohm to 22.32 Ohm. | [13 empty] | Concept | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-03-02 | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1651 | ME | Blue Sky |  |  | 2016-12-01 | Queue Position 333 | Add a new 115 kV line Blue Sky West to Guilford substation | [13 empty] | Concept | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-03-02 | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1650 | ME | Blue Sky |  |  | 2016-12-01 | Queue Position 333 | Add a new 34.5/115 kV substation Blue Sky West | [13 empty] | Concept | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-03-02 | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1649 | ME | Central Maine Power Company |  |  | 2016-08-01 | Queue Position 333 | Add a new 3-breaker ring bus to Guilford 115 kV Substation | [13 empty] | Concept | Proposed | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-03-02 | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1648 | ME | Central Maine Power Company |  |  | 2016-03-01 | Queue Position 333 | Re-rate 115 kV line section 85 between Detroit and Guilford substations | [13 empty] | Concept | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-03-02 | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1647 | MA | Eversource |  |  | 2017-03-01 | Greater Boston - Western Suburbs | Add a new 115 kV breaker in series with breaker 5 at Framingham | [13 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No | [13 empty] | TBD | 1033000 | 1033000 | 1033000 | 1033000 | 1033000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 0
Reliability Upgrade | 1a | 1646 | MA | Eversource |  |  | 2019-12-01 | Greater Boston - Western Suburbs | Add a new 345 kV 160 MVAR shunt reactor at K Street | [13 empty] | Concept | Concept | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [13 empty] | TBD | TBD | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 0
Reliability Upgrade | 1a | 1645 | MA | Eversource |  |  | 2017-06-01 | Greater Boston - Western Suburbs | Add a new 115 kV 36.7 MVAR capacitor bank at Hartwell Station | [13 empty] | Concept | Concept | Proposed | Proposed | Proposed | Planned | Under Construction | in-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [13 empty] | TBD | TBD | 1400000 | 1400000 | 2300000 | 2300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 0
Reliability Upgrade | 1a | 1644 | MA | Eversource |  |  | 2019-06-01 |  | Upgrade the Medway 115 kV station to BPS standards | [13 empty] | Proposed | Proposed | Proposed | Planned | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Proposed | 2016-01-26 | No | [13 empty] | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | #VALUE!
Reliability Upgrade | 1a | 1643 | ME | Central Maine Power Company |  |  | 2018-11-01 | Greater Boston - Stability | Install a new +/- 200 MVAR STATCOM at Coopers Mills 345 kV substation | [13 empty] | Concept | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [13 empty] | TBD | 58000000 | 58000000 | 58000000 | 58000000 | 58000000 | 58000000 | 51700000 | 51700000 | 51700000 | 51700000 | 51700000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 0
Reliability Upgrade | 1b | 1642 | MA | Eversource |  |  | 2017-10-01 | Greater Boston - Stability | Upgrade the Dover 115 kV station to BPS standards | [13 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Proposed | No | No | [13 empty] | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 0
Reliability Upgrade | 1b | 1641 | MA | Eversource |  |  | 2019-06-01 | Greater Boston - Stability | Upgrade the Edgar 115 kV station to BPS standards | [13 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Proposed | No | No | [13 empty] | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 0
Reliability Upgrade | 1a | 1640 | MA | Eversource |  |  | 2017-01-01 | Greater Boston - North | Reconductor the Eversource portion of the M-139/211-503 and N-140/211-504 115 kV lines between Pinehurst – North Woburn tap | [13 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No | [13 empty] | 4700000 | 4700000 | 4700000 | 4700000 | 7000000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 0
Reliability Upgrade | 1a | 1639 | MA | Eversource |  |  | 2016-08-01 |  | Reconductor the 345 kV underground cable (372) between Mystic and Kingston substations. | [13 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | 09/25/2015 09/13/2017 | [13 empty] | 15100000 | 15100000 | 15100000 | 18530000 | 18530000 | 22745000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 0
Reliability Upgrade | 1a | 1638 | MA | Eversource |  |  | 2015-01-01 |  | Installation of 2, 20 MVAR shunt reactors at Sudbury 115kV Substation | [13 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2014-11-20 | NR | [13 empty] | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 0
Reliability Upgrade | 1a | 1637 | MA | National Grid, USA |  |  | 2017-05-01 | Greater Boston - North | Reconductor the National Grid portion of the M-139/211-503 and N-140/211-504 115 kV lines between Pinehurst – North Woburn tap | [13 empty] | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No | [13 empty] | 1560000 | 1560000 | 1560000 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | #VALUE!
Reliability Upgrade | 1a | 1636 | MA | National Grid, USA |  |  | 2018-06-01 | Greater Boston - Stability | Upgrade the West Methuen115 kV station to BPS standards | [13 empty] | Proposed | Proposed | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Proposed | NR | No | [13 empty] | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 0
Reliability Upgrade | 1a | 1635 | MA | National Grid, USA |  |  | 2020-11-01 | Somerset Asset Condition | Rebuild the Somerset Substation to resolve asset condition issues | [13 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Proposed | 2018-04-30 | 2019-12-10 | [13 empty] | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 37900000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 42327000 | 42327000 | 42327000 | 42327000 | 42327000 | 42327000 | 42327000 | 0
Reliability Upgrade | 1a | 1634 | MA | National Grid, USA |  |  | 2017-04-01 |  | Reconductor Webster St Tap #1 | [13 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-12-01 | NR | [13 empty] | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 0
Elective Upgrade | 4b | 1633 | MA | Eversource |  |  | 2019-08-01 | Queue Position 508 and Queue Positon 584 | 600 MW 345 kV HVDC Tie. Alps Substation in NY to Eversource's Berkshire Substation in MA | [12 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [12 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1632 | MA | Eversource |  |  | 2027-10-01 | Queue Position 506 | 1000 MW HVDC Tie. NMISA to Eversource's K St 345 kV Substation | [12 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-10-31 | NR | [12 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1631 | MA | Eversource |  |  | 2017-12-01 | Queue Position 456 | 1200 MW HVDC Tie. HQ to Eversource's 345 kV Mystic Substation | [12 empty] | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [12 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Elective Upgrade | 4b | 1630 | VT | Vermont Electric Power Company |  |  | 2018-06-01 | Queue Position 516 | 425 MW HVDC Tie HQ to VELCO 345 kV New Haven Substation | [12 empty] | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | No | [12 empty] | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1629 | VT | Vermont Electric Power Company |  |  | 2018-06-01 | Queue Position 515 | 425 MW HVDC Tie HQ to VELCO 115 kV Williston Substation | [12 empty] | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | No | [12 empty] | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1628 | VT | Vermont Electric Power Company |  |  | 2017-12-01 | Queue Position 457 | 500 MW HVDC Tie HQ to VELCO 115 kV Georgia Substation | [12 empty] | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | No | [12 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Elective Upgrade | 4b | 1627 | VT | Vermont Electric Power Company |  |  | 2017-12-01 | Queue Position 505 | 1000 MW HVDC Tie HQ to VELCO 345 kV Coolidge Substation | [12 empty] | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | No | [12 empty] | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1626 | ME | Emera Maine |  |  | 2018-06-01 | Queue Position 507 | 75 MW AC Tie NMISA Mullen Substation to Emera ME Rd Substation | [12 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [12 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1625 | NH | National Grid, USA |  |  | 2017-10-01 |  | Pelham Substation - Install 115 kV Tap and inline breaker (Associated with the 2nd 115/13.2 kV transformer addition) | [12 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-07-17 | NR | [12 empty] | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 1938670 | 1938670 | 1938670 | 1938670 | 1938670 | 1938670 | 1938670 | 1938670 | 1938670 | 0
Reliability Upgrade | 1a | 1624 | MA | National Grid, USA |  |  | 2022-02-01 | North Oxford Breaker Addition | Install a 115 kV breaker at the North Oxford substation and segment the V-174 line | [12 empty] | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Proposed | 2015-07-23 | NR | [12 empty] | TBD | TBD | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 0
Reliability Upgrade | 1a | 1623 | RI | National Grid, USA |  |  | 2016-06-01 | Brayton Point Non-Price Retirement | Reconductor V-148N Line between Washington and Woonsocket Substations | [12 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-09-09 | 2016-03-21 | [11 empty] | 12300000 | 12300000 | 12300000 | 7000000 | 7000000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 0
Reliability Upgrade | 1a | 1622 | CT | United Illuminating Company |  |  | 2021-02-01 | SWCT | Baird to Housatonic River Crossing 88006A - 89006B 115 kV Line Upgrades | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2015-04-16 | 4/28/2020 | [12 empty] | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 0
Reliability Upgrade | 1a | 1621 | CT | United Illuminating Company |  |  | 2018-08-01 | SWCT | Pootatuck 115 kV Ring Bus Expansion & Capacitor Bank Addition | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2017-01-03 | [12 empty] | 11900000 | 11900000 | 11900000 | 11900000 | 11900000 | 11900000 | 11900000 | 11900000 | 11900000 | 11560000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 0
Reliability Upgrade | 1a | 1620 | CT | United Illuminating Company |  |  | 2018-10-01 | SWCT | Ansonia 115 kV Capacitor Bank Additions | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2018-08-24 | [12 empty] | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 10030000 | 10030000 | 10030000 | 9700000 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 0
Reliability Upgrade | 1a | 1619 | CT | United Illuminating Company |  |  | 2014-12-01 | SWCT | Mill River 115 kV Fault Duty & TRV Mitigation | [12 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2018-08-24 | [12 empty] | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 0
Reliability Upgrade | 1a | 1618 | CT | United Illuminating Company |  |  | 2030-04-01 |  | Old Town 115/13.8 kV Substation Rebuild | [12 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Y-Planned | 2014-09-09 | No | [12 empty] | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 0
Reliability Upgrade | 1a | 1617 | VT | Vermont Electric Power Company |  |  | 2018-01-01 | Connecticut River Valley | Rebuild Chelsea Station to a three-breaker ring bus | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2017-12-01 | [12 empty] | 19800000 | 19800000 | 19800000 | 19800000 | 14900000 | 14900000 | 14900000 | 14900000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 0
Reliability Upgrade | 1a | 1616 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | Connecticut River Valley | Split Hartford 25 MVAR capacitor bank into two 12.5 MVAR banks | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2017-12-01 | [12 empty] | 3800000 | 3800000 | 3800000 | 3800000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 0
Reliability Upgrade | 1a | 1615 | VT | Vermont Electric Power Company |  |  | 2018-11-01 | Connecticut River Valley | Install one +50/-25 MVAR dynamic voltage support device at Ascutney | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2017-12-01 | [12 empty] | 40000000 | 40000000 | 40000000 | 40000000 | 41000000 | 41000000 | 41000000 | 41000000 | 35900000 | 35900000 | 35900000 | 35900000 | 32000000 | 32000000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 0
Reliability Upgrade | 1a | 1614 | VT | Vermont Electric Power Company |  |  | 2017-08-01 | Connecticut River Valley | Rebuild K31 (Coolidge - Ascutney) 115 kV line | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2017-12-01 | [12 empty] | 70100000 | 70100000 | 70100000 | 70100000 | 51100000 | 51100000 | 51100000 | 51100000 | 41800000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 0
Reliability Upgrade | 1a | 1613 | VT | Vermont Electric Power Company | NYPA |  | 2017-12-01 |  | Replace the PV20 submarine cables | [12 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-10-21 | 2019-12-16 | [12 empty] | 35000000 | 35000000 | 35000000 | 40000000 | 41600000 | 41600000 | 41600000 | 41600000 | 41600000 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 0
Reliability Upgrade | 1a | 1612 | MA | Eversource |  |  | 2017-04-01 | K St to Dewar/Andrew Sq Cable Project | Install one 115 kV breaker to separate K ST 345B bus connection from line 483-525 | [12 empty] | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-08-08 | NR | [12 empty] | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 0
Generator Interconnection Upgrade | 2a | 1611 | ME | Emera Maine |  |  | 2015-12-01 | Queue Position 357 | Installation of 115 kV ring bus on line 64 between Graham and Keene Road to accommodate QP 357 | [12 empty] | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2014-08-11 | NR | [12 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1610 | CT | Eversource |  |  | 2017-09-01 | CPV Towantic | Reconductor 115 kV 1575S Line section between QP 384 and Oxford Substations | [12 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 8/8/2014 8/25/2015 | NR | [12 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1609 | CT | Eversource |  |  | 2017-09-01 | CPV Towantic | Reconductor 115 kV 1585N Line section between QP 384 and Bunker Hill Substations | [12 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 8/8/2014 8/25/2015 | NR | [12 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1608 | CT | Eversource |  |  | 2017-09-01 | CPV Towantic | Build new QP 384 115 kV Substation and Terminate 1575, 1585, and 1990 115 kV Lines into QP 384 115 kV Substation | [12 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2014-08-08 | NR | [12 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1607 | CT | Eversource |  |  | 2015-12-01 | Asset Replacement | Replace both 345/115 kV Montville autotransformers | [12 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2014-08-08 | 2015-10-02 | [12 empty] | 18900000 | 18900000 | 17000000 | 17000000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 0
Reliability Upgrade | 1a | 1606 | CT | Eversource |  |  | 2018-08-01 |  | 1779 Line Partial Rebuild | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2/25/2015 10/21/2016 | 2016-06-30 | [12 empty] | 29000000 | 29000000 | 29000000 | 29000000 | 29000000 | 29000000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 0
Reliability Upgrade | 1a | 1605 | CT | Eversource |  |  | 2016-12-01 | GHCC | Separation of 115 kV double circuit towers corresponding to the Middletown – Pratt and Whitney line (1572) and the Middletown to Haddam (1620) line | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 0
Reliability Upgrade | 1a | 1604 | CT | Eversource |  |  | 2015-12-01 | GHCC | Add a 37.8 MVAR capacitor bank at Hopewell 115 kV substation | [12 empty] | Proposed | Proposed | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2015-11-25 | [12 empty] | 4300000 | 4300000 | 4300000 | 4300000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 0
Reliability Upgrade | 1a | 1603 | CT | Eversource |  |  | 2018-06-01 | GHCC | Redesign the Green Hill 115 kV substation from a straight bus to a ring bus and add two 25.2 MVAR capacitor banks | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 7600000 | 7600000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 0
Reliability Upgrade | 1a | 1602 | CT | Eversource |  |  | 2015-12-01 | GHCC | Terminal Equipment upgrades on the Middletown to Portland Line (1443) | [12 empty] | Proposed | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | 2021-04-14 | [12 empty] | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 0
Reliability Upgrade | 1a | 1601 | CT | Eversource |  |  | 2015-12-01 | GHCC | Terminal Equipment upgrades on the Middletown to Dooley Line (1050) | [12 empty] | Proposed | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | 2021-04-14 | [12 empty] | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 0
Reliability Upgrade | 1a | 1600 | CT | Eversource |  |  | 2017-03-01 | GHCC | Separation of 115 kV double circuit towers corresponding to the Branford – Branford RR line (1537) and the Branford to North Haven (1655) line and adding a series breaker at Branford 115 kV substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 0
Reliability Upgrade | 1a | 1599 | CT | Eversource |  |  | 2017-02-01 | GHCC | Terminal equipment upgrades on the 345 kV line between Haddam and Beseck (362) | [12 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | 2021-04-14 | [12 empty] | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 0
Reliability Upgrade | 1a | 1598 | CT | Eversource |  |  | 2017-04-01 | GHCC | Add a 2nd 345/115 kV autotransformer at Haddam substation and reconfigure the 3-terminal 345 kV 348 line into 2 two-terminal lines | [12 empty] | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2015-11-25 | [12 empty] | 46700000 | 46700000 | 46700000 | 46730000 | 46730000 | 46730000 | 46730000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 0
Reliability Upgrade | 1a | 1597 | CT | Eversource |  |  | 2017-12-01 | GHCC | Separation of 115 kV DCT corresponding to the Bloomfield to North Bloomfield (1777) line and the North Bloomfield – Rood Avenue – Northwest Hartford (1751) line and add a breaker at North Bloomfield 115 kV substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 20100000 | 20100000 | 20100000 | 20100000 | 20100000 | 20100000 | 20100000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 0
Reliability Upgrade | 1a | 1596 | CT | Eversource |  |  | 2020-07-01 | GHCC | Install a 115 kV 3% series reactor on the underground cable between South Meadow and Southwest Hartford (1704) | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 0
Reliability Upgrade | 1a | 1595 | CT | Eversource |  |  | 2017-12-01 | GHCC | Separation of 115 kV DCT corresponding to the Bloomfield to South Meadow (1779) line and the Bloomfield to North Bloomfield (1777) line and add a breaker at Bloomfield 115 kV substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 0
Reliability Upgrade | 1a | 1594 | CT | Eversource |  |  | 2020-03-01 | GHCC | Reconductor the 115 kV line between Newington and Newington Tap (1783) - 0.01 mile | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 0
Reliability Upgrade | 1a | 1593 | CT | Eversource |  |  | 2018-06-01 | GHCC | Add a 115 kV 25.2 MVAR capacitor at Westside 115 kV substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 0
Reliability Upgrade | 1a | 1592 | CT | Eversource |  |  | 2017-11-01 | GHCC | Reconfigure the Berlin 115 kV substation including the addition of two 115 kV breakers and the relocation of a capacitor bank | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 0
Reliability Upgrade | 1a | 1591 | CT | Eversource |  |  | 2017-05-01 | GHCC | Loop the 1779 line between South Meadow and Bloomfield into the Rood Avenue substation and reconfigure the Rood Avenue substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 0
Reliability Upgrade | 1a | 1590 | CT | Eversource |  |  | 2020-09-01 | GHCC | Add a 3.7 mile 115 kV hybrid overhead/underground line from Newington to Southwest Hartford and associated terminal equipment including a 1.4% series reactor | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 4/16/2015 7/25/2018 | 2021-04-14 | [12 empty] | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 61200000 | 61200000 | 61200000 | 61200000 | 61200000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 0
Reliability Upgrade | 1a | 1589 | CT | Eversource |  |  | 2018-12-01 | GHCC | Add a new control house at Southington 115 kV substation | [12 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | 2021-04-14 | [12 empty] | 22600000 | 22600000 | 22600000 | 22600000 | 22600000 | 22600000 | 22600000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 0
Reliability Upgrade | 1a | 1588 | CT | Eversource |  |  | 2017-05-01 | GHCC | Add a breaker in series with breaker 5T at the Southington 345 kV switchyard | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 0
Reliability Upgrade | 1a | 1587 | CT | Eversource |  |  | 2019-06-01 | GHCC | Replace the normally open 19T breaker at Southington with a 3% series reactor between Southington Ring 1 and Southington Ring 2 and associated substation upgrades | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 0
Reliability Upgrade | 1a | 1586 | CT | Eversource |  |  | 2018-12-01 | GHCC | Replace the existing 3% series reactors on the 115 kV lines between Southington and Todd (1910) and between Southington and Canal (1950) with 5% series reactors | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 5200000 | 5200000 | 5200000 | 5200000 | 5200000 | 5200000 | 5200000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 0
Reliability Upgrade | 1a | 1585 | CT | Eversource |  |  | 2016-12-01 | GHCC | Upgrade terminal equipment on the 115 kV line between Chippen Hill and Lake Avenue Junction (1810-3). Reconductor the 115 kV line between Southington and Lake Avenue Junction (1810-1) – 5.2 miles | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2016-10-04 | [12 empty] | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 0
Reliability Upgrade | 1a | 1584 | CT | Eversource |  |  | 2018-06-01 | GHCC | Separation of 115 kV DCT corresponding to the Frost Bridge to Campville (1191) line and the Thomaston to Campville (1921) line and add a breaker at Campville 115 kV substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2016-10-04 | [12 empty] | 5500000 | 5500000 | 5500000 | 5500000 | 5500000 | 5500000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 0
Reliability Upgrade | 1a | 1583 | CT | Eversource |  |  | 2017-12-01 | GHCC | Add a new 10.35 mile, 115 kV line from Frost Bridge to Campville and associated terminal equipment | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2016-10-04 | [12 empty] | 45500000 | 45500000 | 45500000 | 45500000 | 45500000 | 45500000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 0
Reliability Upgrade | 1a | 1582 | CT | Eversource |  |  | 2015-12-01 | GHCC | Add a 345 kV breaker in series with breaker 24T at the Manchester 345 kV switchyard | [12 empty] | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2015-11-25 | [12 empty] | 2100000 | 2100000 | 2100000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 0
Reliability Upgrade | 1a | 1581 | CT | Eversource |  |  | 2016-04-01 | GHCC | Reconductor the 115 kV line between Manchester and Barbour Hill (1763) – 7.6 miles | [12 empty] | Proposed | Proposed | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2015-11-25 | [12 empty] | 13500000 | 13500000 | 13500000 | 13600000 | 13600000 | 13600000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 0
Reliability Upgrade | 1a | 1580 | CT | Eversource |  |  | 2015-12-01 | GHCC | Add a new 345/115 kV autotransformer at Barbour Hill and associated terminal equipment | [12 empty] | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2015-11-25 | [12 empty] | 31200000 | 31200000 | 31200000 | 31200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 0
Reliability Upgrade | 1a | 1579 | CT | Eversource |  |  | 2018-12-01 | SWCT | Separate 3827-1610 DCT (0.38 miles) | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 2017-05-23 | No | [12 empty] | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 0
Reliability Upgrade | 1a | 1578 | CT | Eversource |  |  | 2018-06-01 | SWCT | Install a synchronous condenser (+25/-12.5 MVAR) @ Stony Hill | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 0
Reliability Upgrade | 1a | 1577 | CT | Eversource |  |  | 2018-05-01 | SWCT | Reconfigure 1887 line into a 3 terminal line (Plumtree - W. Brookfield - Shepaug) and Reconfigure 1770 line into 2 two terminal lines between Plumtree - Stony Hill and Stony Hill - Bates Rock | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 0
Reliability Upgrade | 1a | 1576 | CT | Eversource |  |  | 2018-05-01 | SWCT | Relocate 22K 115 kV capacitor bank (37.8 MVAR) to the same side as the 10K (25.2 MVAR) cap bank at Stony Hill | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 0
Reliability Upgrade | 1a | 1575 | CT | Eversource |  |  | 2016-12-01 | SWCT | Reconductor the 1575 Line (Bunker Hill – Baldwin Junction; 3.0 miles) | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 0
Reliability Upgrade | 1a | 1574 | CT | Eversource |  |  | 2019-12-01 | SWCT | Reconductor the 1470-3 line from Peaceable to Ridgefield Junction (0.04 miles) | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 0
Reliability Upgrade | 1a | 1573 | CT | Eversource |  |  | 2019-12-01 | SWCT | Reconductor the 1470-1 line from Wilton to Ridgefield Junction (5.1 miles) | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 0
Reliability Upgrade | 1a | 1572 | CT | Eversource |  |  | 2017-05-01 | SWCT | Rebuild a portion of 1682 line from Wilton to Norwalk and upgrade Wilton Substation terminal equipment (1.5 miles) | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 0
Reliability Upgrade | 1a | 1571 | CT | Eversource |  |  | 2018-12-01 | SWCT | Rebuild Bunker Hill to a 9 breaker substation in breaker-and-a-half configuration | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 2017-05-23 | No | [12 empty] | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 0
Reliability Upgrade | 1a | 1570 | CT | Eversource |  |  | 2015-12-01 | SWCT | Replace two Freight breakers with new breakers having 63 kA interrupting capability | [12 empty] | Proposed | Proposed | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2016-04-15 | [12 empty] | 1100000 | 1100000 | 1100000 | 1050000 | 1050000 | 1050000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 0
Reliability Upgrade | 1a | 1569 | CT | Eversource |  |  | 2018-12-01 | SWCT | Loop the 1990 line in and out of Bunker Hill Substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 2017-05-23 | No | [12 empty] | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 0
Reliability Upgrade | 1a | 1568 | CT | Eversource |  |  | 2018-07-01 | SWCT | Loop the 1570 line in and out of Pootatuck Substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 1800000 | 1800000 | 890000 | 890000 | 890000 | 890000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 0
Reliability Upgrade | 1a | 1567 | CT | Eversource |  |  | 2017-04-01 | SWCT | Reduce 12Y-10K (25.2 MVAR) capacitor cans @ Rocky River to 14.4 MVAR | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 0
Reliability Upgrade | 1a | 1566 | CT | Eversource |  |  | 2015-12-01 | SWCT | Upgrade 1876 line terminal equipment at Newtown Substation | [12 empty] | Proposed | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | 2016-04-15 | [12 empty] | 100000 | 100000 | 100000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 0
Reliability Upgrade | 1a | 1565 | CT | Eversource |  |  | 2017-04-01 | SWCT | Relocate the existing 37.8 MVAR capacitor bank from 115 kV B bus to 115 kV A bus at Plumtree Substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2810000 | 2810000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 0
Reliability Upgrade | 1a | 1564 | CT | Eversource |  |  | 2018-06-01 | SWCT | Install a new 115 kV line from Plumtree to Brookfield Junction (3.4 miles) | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 0
Reliability Upgrade | 1a | 1563 | CT | Eversource |  |  | 2017-12-01 | SWCT | Install 2 x 14.4 MVAR capacitor banks at West Brookfield Substation on 1618 line terminal | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 0
Reliability Upgrade | 1a | 1562 | CT | Eversource |  |  | 2016-05-01 | SWCT | Install a 115 kV circuit breaker (63 kA interrupting capability) in series with the existing 29T breaker at Plumtree Substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2016-06-30 | [12 empty] | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 0
Reliability Upgrade | 1a | 1561 | CT | Eversource |  |  | 2020-11-01 | SWCT | Reconductor the 1887 line between West Brookfield and West Brookfield Junction (1.4 miles) | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 0
Reliability Upgrade | 1a | 1560 | CT | Eversource |  |  | 2017-09-01 | SWCT | Close the normally open 115 kV 2T circuit breaker at Baldwin Substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 0
Reliability Upgrade | 1a | 1559 | CT | Eversource |  |  | 2016-03-01 | SWCT | Install a 115 kV 25.2 MVAR capacitor bank at Oxford Substation on 1319 line terminal | [12 empty] | Proposed | Proposed | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2015-04-15 | [12 empty] | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 0
Reliability Upgrade | 1a | 1558 | MA | Eversource |  |  | 2016-05-01 | Greater Boston - South | Add a new 345 kV breaker in series with the 104 breaker at Stoughton | [11 empty] | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2015-05-01 | No | [11 empty] | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1500000 | 893000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 0
Reliability Upgrade | 1a | 1557 | NH | Eversource |  |  | 2015-09-01 | LSP - New Mill Pond Substation | Add three 115 kV switches associated with the new Mill Pond Substation | [11 empty] | Concept | Concept | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-04-28 | NR | [11 empty] | TBD | TBD | 1900000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 0
Generator Interconnection Upgrade | 2a | 1556 | ME | Emera Maine |  |  | 2016-10-01 | QP 327 | Installation of 20 MVAR DVAR system on 115 kV bus at Chester Station to accommodate QP 327 | [11 empty] | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2014-02-18 | NR | [11 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1555 | CT | United Illuminating Company |  |  | 2017-08-01 |  | Housatonic River Crossing 88006A & 89006B 115 kV line rebuild project - Housatonic River between Milford and Stratford CT | [11 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-07-17 | 2015-12-17 | [11 empty] | 16000000 | 16000000 | 16900000 | 17700000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 0
Reliability Upgrade | 1a | 1554 | MA | Eversource |  |  | 2017-04-01 | Greater Boston - Central | Add one 115 kV breaker at K street in series with the 29 breaker | [10 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | in-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No | [10 empty] | Part of RSP 1353 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 1300000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 0
Reliability Upgrade | 1a | 1553 | MA | Eversource |  |  | 2017-06-01 | Greater Boston - Western Suburbs | Add a breaker in series with breaker 104 at Woburn 345 kV switchyard | [10 empty] | Concept | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No | [10 empty] | TBD | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 0
Reliability Upgrade | 1a | 1552 | MA | Eversource |  |  | 2024-03-01 | Greater Boston - North | Add a new 345 kV cable from Woburn substation to the Wakefield substation and terminal equipment at Woburn including a 160 MVAR 345 kV reactor | [10 empty] | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 6/9/2016 7/25/2019 | No | [10 empty] | TBD | 87100000 | 87100000 | 87100000 | 87100000 | 87100000 | 87100000 | 117100000 | 117100000 | 117100000 | 117100000 | 78742045 | 78742045 | 78742045 | 78742045 | 78742045 | 78742045 | 121800000 | 121800000 | 121800000 | 121800000 | 121800000 | 121800000 | 121800000 | 121800000 | 121800000 | 121800000 | 121800000 | 152644000 | 152644000 | 152644000 | 152644000 | 152644000 | 152644000 | 152644000 | 152644000 | 152644000 | 152644000 | 0
Reliability Upgrade | 1a | 1551 | MA | National Grid, USA |  |  | 2024-03-01 | Greater Boston - North | Cable and terminal work at Wakefield 345 kV substation for the new 345 kV cable between Woburn and Wakefield including the addition of a 160 MVAR variable shunt reactor | [10 empty] | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [10 empty] | TBD | 20242797 | 20242797 | 20242797 | 20242797 | 20242797 | 20242797 | 20242797 | 20242797 | 20242797 | 20242045 | 58600000 | 58600000 | 58600000 | 58600000 | 58600000 | 58600000 | 79364000 | 79364000 | 79364000 | 79364000 | 79364000 | 79364000 | 79364000 | 79364000 | 79364000 | 79364000 | 89429000 | 89429000 | 89429000 | 89429000 | 89429000 | 89429000 | 89429000 | 89429000 | 89429000 | 89429000 | 89429000 | 0
Reliability Upgrade | 1a | 1550 | MA | National Grid, USA |  |  | 2019-06-01 | Greater Boston - North | 115 kV Line reconductoring of the F-158S Maplewood - Everett | [10 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No | [10 empty] | Part of RSP 1260 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 4840000 | 4840000 | 4840000 | 5289716 | 5289716 | 5289716 | 5289716 | 5289716 | 6935000 | 6935000 | 6935000 | 6935000 | 6935000 | 6935000 | 6935000 | 6935000 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 0
Reliability Upgrade | 1a | 1549 | MA | National Grid, USA |  |  | 2017-05-01 | Greater Boston - North | 115 kV Line Reconductoring of M-139 between Billerica Tap and Pinehurst and reconductoring of N-140 between Tewksbury and Pinehurst and associated work at Tewksbury | [10 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No | [10 empty] | Part of RSP 1212 | 13160000 | 13160000 | 13160000 | 13160000 | 13160000 | 19970000 | 19970000 | 19970000 | 19970000 | 19967805 | 19967805 | 19967805 | 19967805 | 19967805 | 19967805 | 19967805 | 19967805 | 19967805 | 19967805 | 19967805 | 19967805 | 19967805 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 0
Elective Upgrade | 4b | 1548 | MA | National Grid, USA |  |  | 2019-03-01 | Queue Position 512 | 1200 MW AC to HVDC Tie. NB 345 kV Keswick or St. Andre substation to NGRID 345 kV Wakefield substation | [10 empty] | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [10 empty] | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1547 | VT | Vermont Electric Power Company |  |  | 2018-12-01 | Queue Position 504 | 1000 MW HVDC Tie V3 HQ 735 kV substation to VELCO 345 kV New Haven substation | [10 empty] | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | No | [10 empty] | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1546 | VT | Vermont Electric Power Company |  |  | 2018-12-01 | Queue Position 503 | 1000 MW HVDC Tie V2 HQ 735 kV substation to VELCO 345 kV West Rutland substation | [10 empty] | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | No | [10 empty] | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1545 | VT | Vermont Electric Power Company |  |  | 2027-12-01 | Queue Position 501 | New 1000 MW 320 kV HVDC Line, complete with two HVDC terminal stations, from a HQ station near Monteregie substation in Quebec to the VELCO 345/115 kV Coolidge substation in VT | [10 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2016-11-01 | NR | [10 empty] | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1544 | NH | Eversource |  |  | 2016-07-01 | Queue Position 513 | Coos ETU - Transmission Reinforcement | [10 empty] | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [10 empty] | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1543 | ME | Emera Maine |  |  | 2017-11-01 | Queue Position 514 | Expand NB/NE Interface by 350 MW | [10 empty] | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [10 empty] | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1542 | ME | Emera Maine |  |  | 2018-12-01 | Queue Position 500 | Keene Road ETU at Penobscot ME | [10 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [10 empty] | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1541 | NH | Eversource |  |  | 2018-12-01 | Queue Position 519 | Increase the 326 Line SPS summer thermal mode set point | [10 empty] | Proposed | Proposed | Proposed | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-12-31 | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1540 | NH | Eversource |  |  | 2018-12-01 | Queue Position 519 | Upgrade the 345 kV 373 line from Deerfield to Scobie Pond | [10 empty] | Proposed | Proposed | Proposed | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-12-31 | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1539 | NH | Eversource |  |  | 2018-12-01 | Queue Position 519 | Install 210 Mvar of 345 kV capacitor banks at the 345 kV Scobie Pond Substation. The capacitor banks will be connected to 345-kV Scobie Pond Bus #2 via five 345 kV circuit breakers. In addition to the capacitor banks, two new 345 kV circuit breakers will be installed at the 345 kV Scobie Pond Substation. One circuit breaker is to be installed in series with the existing 9126 circuit breaker, and the other circuit breaker installed in series with the 262 circuit breaker. | [10 empty] | Proposed | Proposed | Proposed | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-12-31 | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1538 | NH | Eversource |  |  | 2018-12-01 | Queue Position 519 | Reconfigure the Deerfield 345 kV Substation to accommodate the new NPT Project AC transmission line 3132 interconnection, the re-termination of the 345 kV Buxton to Scobie Pond transmission line 391, the addition of 200 MVAR shunt capacitor banks, and the addition of one 0/+400 Mvar SVC. The existing 373 line will be re-positioned to its own new bay position. The existing 345 kV AC transmission line 391 that will be looped into and terminated at the 345 kV Deerfield Substation | [10 empty] | Proposed | Proposed | Proposed | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-12-31 | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1537 | NH | Eversource |  |  | 2018-12-01 | Queue Position 519 | Install new 345 kV AC transmission line, 3132, from the Franklin Converter Terminal Substation to the Deerfield 345 kV Substation. | [10 empty] | Proposed | Proposed | Proposed | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-12-31 | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1536 | NH | Eversource |  |  | 2018-12-01 | Queue Position 519 | Install NPT terminal consisting of a 345 kV substation with an eight circuit breaker ring bus in Franklin, NH, a 1,200 MW nominal, bi-directional, bi-polar, HVDC line commutated converter station, and a 0/100 Mvar Static Var Compensator (SVC). The Franklin terminal will have two 600 MW line commutated converters with reactive compensation | [10 empty] | Proposed | Proposed | Proposed | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-12-31 | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1535 | CT | Eversource |  |  | 2016 | Queue Position 277 | Reconductor 345 kV 398 line CL&P portion of the Long Mountain to Pleasant Valley (NY) line | [10 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1534 | CT | Eversource |  |  | 2015-10-01 | Newtown Breaker Addition | Newtown Substation 115 kV circuit breaker addition | [10 empty] | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2014-02-11 | NR | [10 empty] | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 0
Reliability Upgrade | 1a | 1533 | CT | Eversource |  |  | 2019-12-01 | Cos Cob Breaker Addition | Add two new 115 kV circuit breakers at the Cos Cob Substation and reposition 1750 line termination to accommodate Greenwich area Substation | [10 empty] | Concept | Concept | Concept | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2/11/2014 5/1/2015 | No | [10 empty] | TBD | TBD | TBD | TBD | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 0
Reliability Upgrade | 1a | 1532 | MA | Eversource |  |  | 2014-12-01 | Pittsfield / Greenfield Project | Remove the sag elimination on the 1512 115 kV line from Blandford substation to Granville Junction and also remove the limitation on the 1421 115 kV line from Pleasant to Blandford substation | [10 empty] | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-12-07 | 2016-02-11 | [10 empty] | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | #VALUE!
Reliability Upgrade | 1a | 1531 | NH | Eversource |  |  | 2014-01-01 |  | Reeds Ferry breaker project | [10 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-10-02 | NR | [10 empty] | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 0
Generator Interconnection Upgrade | 2a | 1530 | MA | National Grid, USA |  |  | 2016-10-01 | Footprint Combined Cycle Unit | Add a 115 kV bay with 2 breakers at Salem Harbor 115 kV substation for the interconnection of the new generator | [10 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2014-02-03 | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1529 | VT | National Grid, USA |  |  | 2017-12-01 |  | Y25N Bennington - Harriman + Taps (Knox Insulator refurbishment) | [10 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | 2021-01-29 | [10 empty] | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5500000 | 5500000 | 5758000 | 5758000 | 5758000 | 5924000 | 5924000 | 5924000 | 5924000 | 5924000 | 5924000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 0
Reliability Upgrade | 1a | 1528 | NH | National Grid, USA |  |  | 2017-04-01 | Greater Boston - North | Reconductoring National Grid's portion of the Y-151 between Dracut Jct and Power Street (NH portion of the line) | [10 empty] | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | in-service | in-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [10 empty] | TBD | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | #VALUE!
Reliability Upgrade | 1a | 1527 | MA | National Grid, USA |  |  | 2017-04-01 | Greater Boston - North | Reconductoring National Grid's portion of the Y-151 between Dracut Jct and Power Street (MA portion of the line) | [10 empty] | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [10 empty] | TBD | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | #VALUE!
Reliability Upgrade | 1a | 1526 | MA | National Grid, USA |  |  | 2018-06-01 | Sandy Pond Asset Condition | Sandy Pond Substation refurbishment | [10 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | 2017-07-17 | [10 empty] | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 0
Reliability Upgrade | 1a | 1525 | MA | National Grid, USA |  |  | 2017-03-01 | Pittsfield / Greenfield Project | Loop the A127W line between Cabot Tap and French King into the new Erving Substation | [10 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-12-07 | 2017-07-17 | [10 empty] | 2920000 | 2920000 | 2920000 | 2920000 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | 2920000 | 2920000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 0
Generator Interconnection Upgrade | 2a | 1524 | MA | Eversource |  |  | 2018-10-01 | Cape Wind | Installation of (1) 40 MVAR shunt reactor at the West Barnstable 115 kV Substation | [10 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2014-02-11 | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1523 | MA | Eversource |  |  | 2018-10-01 | Cape Wind | Modification of the Barnstable SVC to enable continuous inductive operation with a limit of 70.5 MVAR | [10 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2014-02-11 | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1522 | MA | Eversource |  |  | 2017-05-01 | Greater Boston - Central | Add a new 115 kV 36.7 MVAR capacitor bank at Sudbury Station | [10 empty] | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [10 empty] | TBD | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1800000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 0
Reliability Upgrade | 1b | 1521 | MA | Eversource |  |  | 2016-12-01 | Greater Boston - Central | Add a new 115 kV 54 MVAR capacitor bank at Newton Station | [10 empty] | Concept | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [10 empty] | TBD | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 0
Reliability Upgrade | 1a | 1520 | MA | Eversource |  |  | 2017-12-01 | Greater Boston - Central | Equipment termination changes at North Cambridge Station to mitigate 115 kV stuck breaker 5 and 10 contingencies | [10 empty] | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2015-10-01 | No | [10 empty] | TBD | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 0
Reliability Upgrade | 1a | 1519 | MA | Eversource |  |  | 2016-12-01 | Greater Boston - Central | Relocate Chelsea capacitor bank 128-518 termination position | [10 empty] | Concept | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No | [10 empty] | TBD | 860000 | 860000 | 860000 | 860000 | 860000 | 860000 | 870000 | 870000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 0
Reliability Upgrade | 1a | 1518 | MA | Eversource |  |  | 2019-03-01 | Greater Boston - Central | Station upgrades to create a second normally closed 115 kV bus tie at Kingston Station and reconfigure the 345 kV switchyard | [10 empty] | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [10 empty] | TBD | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 0
Reliability Upgrade | 1a | 1517 | MA | Eversource |  |  | 2018-05-01 |  | Build a new 115kV Substation - Electric Ave | [10 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-30 | 2017-07-17 | [10 empty] | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 57200000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 0
Reliability Upgrade | 1a | 1516 | MA | Eversource |  |  | 2020-09-01 | Greater Boston - South | Construct a new 115 KV three breaker switching station in Sharon MA to segment the three 115 kV circuits that extend from West Walpole to Holbrook | [10 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Proposed | 2016-06-09 | No | [10 empty] | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 18100000 | 18100000 | 18100000 | 18100000 | 18100000 | 18100000 | 18100000 | 18100000 | 18100000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 0
Reliability Upgrade | 1b | 1515 | ME | Central Maine Power Company |  |  | 2020-12-01 | CMP- LSP New Waterford Substation | Add a new substation at New Waterford | [10 empty] | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | N-Concept | No | No | [10 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 1514 | ME | Central Maine Power Company |  |  | 2020-05-01 | CMP- LSP County Road Substation | Construct a new County Road Substation that sectionalizes Section 241 by adding four 115 kV circuit breakers in a ring bus configuration and install two 115/34.5 kV 30/56 MVA transformers at a new green field site. This new substation will replace the existing Rice Rips Substation. Construct 6.5 miles of new 115 kV (1192 kcmil 45/7 ACSR) conductor from the Section 241A tap point to the new County Road Substation. | [9 empty] | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2014-03-20 | 9/13/2017 12/16/2019 | [9 empty] | TBD | 21900000 | 21900000 | 21900000 | 24780000 | 24780000 | 24490000 | 24490000 | 24490000 | 24490000 | 24490000 | 24841000 | 24841000 | 24841000 | 24841000 | 24841000 | 24841000 | 24841000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 0
Reliability Upgrade | 1a | 1513 | ME | Central Maine Power Company |  |  | 2015-11-01 | Section 242 Rebuild | Rebuild entire length (1.1 mile) of transmission line Section 242 | [9 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2013-10-04 | NR | [9 empty] | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 0
Reliability Upgrade | 1b | 1512 | ME | Central Maine Power Company |  |  | 2020-05-01 | CMP- LSP Lakes Region | New Gloucester 115/34 kV S/S with a four breaker ring bus and 115/34 kV transformer and (10 mile) 115 kV transmission line to Surowiec | [9 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | N-Concept | No | No | [9 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 1511 | MA | National Grid, USA |  |  | 2015-11-01 | New Wakefield Municipal Wallace Substation | Reconductor the S-145/T-146 115 kV lines from Wakefield Junction to new Wallace Substation. | [9 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2013-07-25 | NR | [9 empty] | 1000000 | 1000000 | 1000000 | 1551000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 0
Reliability Upgrade | 1a | 1510 | RI | National Grid, USA |  |  | 2014-06-01 | New Highland Park Substation Project | Add a new 115/13.8 kV Highland Park Substation by looping the J-16 line in and out of this new substation | [9 empty] | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-01-18 | 2018-01-03 | [9 empty] | 3000000 | 3000000 | 3824000 | 3824000 | 3824000 | 3824000 | 3824000 | 3824000 | 3824000 | 3824000 | 3824000 | 3824000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 0
Reliability Upgrade | 1b | 1509 | MA | National Grid, USA |  |  | 2017-03-01 |  | 303/327/3520 Brayton Point - West Medway Asset Condition Refurbishment (ACR) | [9 empty] | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [9 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1508 | RI | National Grid, USA |  |  | 2018-12-01 |  | 315 Brayton Point - West Farnum Asset Condition Refurbishment (ACR) - RI portion | [9 empty] | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [9 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1507 | MA | National Grid, USA |  |  | 2018-12-01 |  | 315 Brayton Point - West Farnum Asset Condition Refurbishment (ACR) - MA portion | [9 empty] | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [9 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 1506 | ME | Emera Maine |  |  | 2014-06-01 | Chester SVC Control System Replacement | Like kind replacement of control system at Chester SVC | [9 empty] | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2012-04-17 | [9 empty] | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 0
Reliability Upgrade | 1a | 1505 | MA | SELCO |  |  | 2015-04-01 | New Centech Substation | Add a new 115/13.8 kV Centech Substation by looping the E157 W line in and out of this new substation | [8 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-02-28 | NR | [8 empty] | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 0
Reliability Upgrade | 1a | 1504 | MA | National Grid, USA |  |  | 2014-11-01 |  | Install 115 kV breaker and tap lines at E. Main St Substation | [8 empty] | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-05-03 | NR | [8 empty] | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 0
Reliability Upgrade | 1a | 1503 | NH | National Grid, USA |  |  | 2016-10-01 |  | Install in-line breaker at Mount Support Substation and loop the 115 kV W-149N line. Relay work at Wilder and Slayton Hill for the pilot protection system. | [8 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2013-04-04 | 2016-12-16 | [8 empty] | 5000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 0
Reliability Upgrade | 1a | 1502 | MA | National Grid, USA |  |  | 2017-12-01 |  | C-181/D-182 Brayton Point - S. Wrentham line refurbishment | [8 empty] | Concept | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | 2016-12-16 | [8 empty] | TBD | TBD | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 24930000 | 24930000 | 24930000 | 24930000 | 24930000 | 24930000 | 24930000 | 24930000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 0
Reliability Upgrade | 1a | 1501 | ME | Central Maine Power Company |  |  | 2023-12-01 | CMP- LSP Lakes Region | Add a second 115/34.5 kV autotransformer at the existing Kimball Road 115 kV Substation and move one of the 115 kV 30 MVAR capacitor banks from bus 4 to bus 3 | [7 empty] | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 2013-10-02 | NR | [7 empty] | TBD | TBD | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 0
Reliability Upgrade | 1b | 1500 | ME | Central Maine Power Company |  |  | 2020-12-01 | CMP- LSP Topsham 115 kV Substation | Add six 115 kV circuit breakers a the existing 115 kV Topsham substation to reconfigure the existing 115 kV bus to a 6-breaker ring and upgrade the 115 kV T1 and T3 115/34.5 kV autotransformers at the existing Topsham 115 kV substation | [7 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | N-Concept | No | No | [7 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 1499 | ME | Central Maine Power Company |  |  | 2020-07-01 | Newcastle Substation Upgrades Project | Addition of two 115 kV circuit breakers at the existing 115 kV bus at Newcastle substation to reconfigure the existing 115 kV bus to a 4-breaker ring bus | [7 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 2013-08-07 | No | [7 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 6600000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 0
Reliability Upgrade | 1a | 1498 | CT | Eversource |  |  | 2013-12-01 | SNEW 115 kV Substation | Construct a new 115 kV substation by looping the 1890 line into the new substation | [7 empty] | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/7/2012 | 2015-02-20 | [7 empty] | 13200000 | 13200000 | 13200000 | 9600000 | 9600000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 0
Reliability Upgrade | 1a | 1497 | CT | Eversource |  |  | 2013-12-01 | TTD's Fitch St 115 kV Substation | Loop the 1416 line into the new TTD 115 kV substation | [7 empty] | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/17/2012 | 2015-08-04 | [7 empty] | 1500000 | 1500000 | 1500000 | 2120000 | 2120000 | 2120000 | 2120000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 0
Generator Interconnection Upgrade | 2b | 1496 | NH | Eversource |  |  | 2014-12-01 | QP 371 | New 115 kV Tuttle Hill Switching Station bifurcating the L163 115 kV line | [7 empty] | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-01-18 | NR | [7 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1495 | NH | Eversource |  |  | 2015-06-01 | Southern New Hampshire Solution | Merrimack Substation - replace (1) 115 kV circuit breaker (Q171). (This circuit breaker is a different breaker than identified in project 1312) | [7 empty] | Concept | Concept | Concept | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2013-03-07 | 2015-11-05 | [7 empty] | TBD | TBD | TBD | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | #VALUE!
Reliability Upgrade | 1a | 1494 | MA | National Grid, USA |  |  | 2015-04-01 | New Centech Substation | Add a new 115/13.8 kV Centech Substation by looping the E157 W line in and out of this new substation. | [7 empty] | Concept | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-02-28 | NR | [7 empty] | TBD | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 0
Reliability Upgrade | 1a | 1493 | MA | National Grid, USA |  |  | 2017-05-01 | New Highland Park Substation Project | Terminal upgrades at Robinson Ave Substation (V-148S) | [7 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2013-01-18 | 2018-01-03 | [7 empty] | Part of Highland Dr Substation Project - ID 1491 | Part of Highland Dr Substation Project - ID 1491 | Part of Highland Dr Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | #VALUE!
Reliability Upgrade | 1a | 1492 | RI | National Grid, USA |  |  | 2015-05-01 | New Highland Park Substation Project | Bus upgrades at Riverside Substation (J16) | [7 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-01-18 | 2018-01-03 | [7 empty] | Part of Highland Dr Substation Project - ID 1491 | Part of Highland Dr Substation Project - ID 1491 | Part of Highland Dr Substation Project - ID 1491 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 0
Reliability Upgrade | 1a | 1491 | RI | National Grid, USA |  |  | 2016-12-01 | New Highland Park Substation Project | Re-conductoring of J16 (Riverside - Highland Dr) | [7 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2013-01-18 | 2018-01-03 | [7 empty] | 4600000 | 4600000 | 4600000 | 4343000 | 4343000 | 4343000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5060000 | 5060000 | 5060000 | 5060000 | 5060000 | 5060000 | 5060000 | 5060000 | 5060000 | 5060000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 0
Reliability Upgrade | 1a | 1490 | MA | National Grid, USA |  |  | 2014-11-01 |  | Y-177 Harriman - Montague Asset Condition Replacement (ACR) | [7 empty] | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2014-05-19 | [7 empty] | 8000000 | 8000000 | 8000000 | 8370000 | 8370000 | 8370000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 0
Reliability Upgrade | 1a | 1489 | MA | National Grid, USA |  |  | 2018-06-01 | Sandy Pond Asset Condition | Sandy Pond Control House Rebuild | [7 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | 2017-07-17 | [7 empty] | 10000000 | 10000000 | 10000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 0
Reliability Upgrade | 1a | 1488 | VT | National Grid, USA |  |  | 2017-11-01 | Harriman Asset Condition | Harriman Station - Breaker replacement and terminal equipment upgrades (Asset Condition) | [7 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-12-07 | 2017-07-17 | [7 empty] | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7310000 | 7310000 | 7310000 | 8000000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 0
Elective Upgrade | 4b | 1487 | MA | Eversource |  |  | 2020-06-01 | Queue Position 510 | 1000 MW HVDC line to Eversource Carver 345 kV and to Barnstable 345 kV | [6 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [6 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1486 | CT | United Illuminating Company |  |  | 2016-06-01 | Queue Position 355 | HVDC line between UI Singer 345 kV substation and LIPA Pt Jefferson 138 kV substation or LIPA Shoreham 138 kV substation | [6 empty] | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [6 empty] | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1485 | MA | Northeast Utilities - NSTAR | Emera Maine |  | 2014-12-01 | Queue Position 341 | Massachusetts portion of HVDC line between MEPCO 345 kV at Haynesville or MPC 345 kV and NSTAR 345 kV K-Street Substation | [6 empty] | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [6 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Elective Upgrade | 4b | 1484 | ME | Emera Maine | Eversource |  | 2014-12-01 | Queue Position 341 | Maine portion of HVDC line between MEPCO 345 kV at Haynesville or MPC 345 kV and NSTAR 345 kV K-Street Substation | [6 empty] | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [6 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Generator Interconnection Upgrade | 2a | 1483 | ME | Central Maine Power Company |  |  | 2016-12-01 | Queue Position 333 | Install a 0/+70 MVAR SVC at new Dogtown Road S/S near Detroit S/S 115 kV Substation (CMP-15-T01) | [6 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-03-02 | NR | [6 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1482 | ME | Central Maine Power Company |  |  | 2014-09-01 | Saddleback Ridge Wind | New Ludden Lane 115 kV Substation consisting of a three-breaker ring bus interconnecting QP 287 and QP 300 facilities to the CMP transmission system. Section 229 will be sectionalized into two sections with two new transmission segments constructed and extended into the new Ludden Lane Substation, a distance of approximately 0.2 miles each. | [6 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-06-07 | NR | [6 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1481 | ME | Central Maine Power Company |  |  | 2011-06-01 | Maine Power Reliability Program (MPRP) | Upgrade terminal equipment on 115 kV transmission line 68 at Mason substation | [6 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1480 | ME | Central Maine Power Company |  |  | 2012-05-01 | Maine Power Reliability Program (MPRP) | Add a new Monmouth 115/34/12 kV Substation interconnecting line 212 to Larrabee Road and line 269 to Bowman Street (original 212 from Bowman Street to Gulf Island) | [6 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1479 | ME | Central Maine Power Company |  |  | 2012-02-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (238) between Louden and Maguire Road | [6 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1478 | ME | Central Maine Power Company |  |  | 2012-05-01 | Maine Power Reliability Program (MPRP) | Rebuild the entire length of the 115 kV transmission line (269) between Bowman Street and Monmouth. (Formerly Section 212) | [6 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1477 | ME | Central Maine Power Company |  |  | 2011-11-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (167) between Surowiec and Moshers | [6 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1476 | ME | Central Maine Power Company |  |  | 2011-11-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (166) between Surowiec and Spring Street | [6 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1475 | ME | Central Maine Power Company |  |  | 2012-02-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (203) between Detroit and Bucksport | [6 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1474 | ME | Central Maine Power Company |  |  | 2011-05-01 | Maine Power Reliability Program (MPRP) | Rebuild portion of 115 kV transmission line (66) from Detroit to new Athens Substation. Section 66 from Detroit to Athens renamed Section 82 | [6 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1473 | ME | Central Maine Power Company |  |  | 2010-11-01 | Maine Power Reliability Program (MPRP) | Replace all 115 kV breakers at the South Gorham station with independent pole tripping capability | [6 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1472 | ME | Central Maine Power Company |  |  | 2013-04-01 | Maine Power Reliability Program (MPRP) | Replace K374/377 breaker at Surowiec 345 kV Substation with independent pole tripping capability | [6 empty] | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1471 | ME | Central Maine Power Company |  |  | 2014-12-01 | Maine Power Reliability Program (MPRP) | Modify existing control settings at existing Mason 115 kV substation to switch out Mason 115 kV capacitors for 115 kV voltage above 1.05pu | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1470 | ME | Central Maine Power Company |  |  | 2013-06-01 | Maine Power Reliability Program (MPRP) | Add new automatic 115 kV switching controls at existing Rumford Industrial Park 115 kV substation to switch out 115 kV capacitors for 115 kV voltages above 1.05pu | [6 empty] | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1469 | ME | Central Maine Power Company |  |  | 2013-06-01 | Maine Power Reliability Program (MPRP) | Add new automatic 115 kV switching controls at existing Riley 115 kV substation to switch out 115 kV capacitors for 115 kV voltages above 1.05pu | [6 empty] | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1468 | ME | Central Maine Power Company |  |  | 2015-04-01 | Maine Power Reliability Program (MPRP) | Modify the Maritimes Islanding Special Protection System to remove the inputs from the New England transmission system | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1467 | ME | Central Maine Power Company |  |  | 2015-04-01 | Maine Power Reliability Program (MPRP) | Remove the Orrington T1 SPS (NPCC # 182 – Type III) Special Protection Systems | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1466 | ME | Central Maine Power Company |  |  | 2015-04-01 | Maine Power Reliability Program (MPRP) | Remove the Bucksport 65/205 Reverse Power SPS (NPCC # 22 – Type III) Special Protection Systems | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1465 | ME | Central Maine Power Company |  |  | 2014-02-01 | Maine Power Reliability Program (MPRP) | Remove the Section 386 Temporary SPS (NPCC #198 – Type I) Special Protection Systems | [6 empty] | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1464 | ME | Central Maine Power Company |  |  | 2015-04-01 | Maine Power Reliability Program (MPRP) | Remove the Maine Yankee Double Circuit Tower SPS, (NPCC # 141, Type I) Special Protection Systems | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1463 | ME | Central Maine Power Company |  |  | 2015-04-01 | Maine Power Reliability Program (MPRP) | Remove the Maxcys-Bucksport (SPS # 178 – Type I) Special Protection Systems | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1462 | ME | Central Maine Power Company |  |  | 2012-12-01 | Maine Power Reliability Program (MPRP) | Install two new 40 Mvar 13.8 kV reactors on the tertiary of 345/115/13.8 kV autotransformers at the new Larrabee Road 345/115 kV substation | [6 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1461 | ME | Central Maine Power Company |  |  | 2015-03-01 | Maine Power Reliability Program (MPRP) | Install two new 40 MVAR 13.8 kV reactors on the tertiary of 345/115/13.8 autotransformer at Coopers Mills 345/115 kV substation (formerly Maxcys) | [6 empty] | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1460 | ME | Central Maine Power Company |  |  | 2013-05-01 | Maine Power Reliability Program (MPRP) | Install two new 40 Mvar 13.8 kV reactors on the tertiary of 345/115/13.8kV autotransformer at the new Albion Rd 345/115 kV substation | [6 empty] | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1459 | ME | Central Maine Power Company |  |  | 2014-02-01 | Maine Power Reliability Program (MPRP) | Install a new 10.8 Mvar 34.5 kV capacitor bank at existing Belfast 115/34.5 kV substation | [6 empty] | Planned | Under Construction | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1458 | ME | Central Maine Power Company |  |  | 2015-02-01 | Maine Power Reliability Program (MPRP) | Re-rate of the 115 kV Line 88 between Coopers Mills substation and Augusta East Side substation | [6 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1457 | ME | Central Maine Power Company |  |  | 2014-10-01 | Maine Power Reliability Program (MPRP) | Re-rate of the 115 kV Line 61A between Hotel Road substation and 61A Tap | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1456 | ME | Central Maine Power Company |  |  | 2015-02-01 | Maine Power Reliability Program (MPRP) | Re-rate of the 345 kV Line 378 between Maine Yankee substation and Mason substation | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1455 | ME | Central Maine Power Company |  |  | 2014-12-01 | Maine Power Reliability Program (MPRP) | Re-rate of the 115 kV Line 241A (formerly 67A) between Rice Rips substation and 241A Tap | [6 empty] | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1454 | ME | Central Maine Power Company |  |  | 2015-06-01 | Maine Power Reliability Program (MPRP) | Re-rate of the 115 kV Line 83C between Sappi Hinckley substation and 83C Tap | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1453 | ME | Central Maine Power Company |  |  | 2014-12-01 | Maine Power Reliability Program (MPRP) | Re-rate of the 115 kV Line 241B (formerly 83B) between Lakewood substation and 241B Tap | [6 empty] | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1452 | ME | Central Maine Power Company |  |  | 2013-12-01 | Maine Power Reliability Program (MPRP) | Reterminate 115 kV line Section 268 from Larrabee Road to Gulf Island Substation (original line section 212 from Gulf Island to Bowman Street) | [6 empty] | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1451 | ME | Central Maine Power Company |  |  | 2013-09-01 | Maine Power Reliability Program (MPRP) | Reterminate 115 kV line Section 61 from Norway to Gulf Island at new Larrabee Substation | [6 empty] | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1450 | ME | Central Maine Power Company |  |  | 2013-02-01 | Maine Power Reliability Program (MPRP) | Reterminate 115 kV line Section 200 from Livermore Falls to Gulf Island at new Larrabee Substation | [6 empty] | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1449 | ME | Central Maine Power Company |  |  | 2013-01-01 | Maine Power Reliability Program (MPRP) | Reterminate 115 kV line Section 201 from Crowleys to Gulf Island at new Larrabee Substation | [6 empty] | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1448 | ME | Central Maine Power Company |  |  | 2012-12-01 | Maine Power Reliability Program (MPRP) | Reterminate 115 kV line Section 64 from Surowiec to Gulf Island at new Larrabee Substation | [6 empty] | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1447 | ME | Central Maine Power Company |  |  | 2014-04-01 | Maine Power Reliability Program (MPRP) | Remove Section 232 (Spring Street to Westbrook) and Section 234 (Spring Street to Redbrook) at the Spring Street 115 kV Substation and tie lines together in the right-of-way to bypass the Spring Street Substation | [6 empty] | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1446 | ME | Central Maine Power Company |  |  | 2014-06-01 | Maine Power Reliability Program (MPRP) | Separation of 115 kV Double Circuit Tower of lines 65 and 205 between Bucksport and Orrington | [6 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1445 | ME | Central Maine Power Company |  |  | 2014-12-01 | Maine Power Reliability Program (MPRP) | Separation of 345 kV Double Circuit Tower of lines 375 and 377 between Surowiec and Maine Yankee at Kennebec River Crossing | [6 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1444 | ME | Central Maine Power Company |  |  | 2013-12-01 | Maine Power Reliability Program (MPRP) | Modify the 115 kV Gulf Island Substation to interconnect Section 268 (original 212) to Larrabee Road substation. 115kV Sections 61, 64, 200, 201 and cap bank relocated to Larrabee Road | [6 empty] | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1443 | ME | Central Maine Power Company |  |  | 2017-08-01 | Maine Power Reliability Program (MPRP) | Add a new Middle Street 115/34/12 kV Substation interconnecting lines 255 and 256 between Lewiston Lower and new Larrabee Road (Lewiston Loop) | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1442 | ME | Central Maine Power Company |  |  | 2018-12-01 | Maine Power Reliability Program (MPRP) | Expand Lewiston Lower 115 kV Substation interconnecting lines 256 and 202 between stations Middle Street and Crowleys (Lewiston Loop) | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 0
Reliability Upgrade | 1a | 1441 | ME | Central Maine Power Company |  |  | 2018-05-01 | Maine Power Reliability Program (MPRP) | Expand Norway 115 kV Substation interconnecting lines 61, 61A and 87 between stations Larrabee Road, Hotel Road and Kimball Road (Lewiston Loop) | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | 5200000 | 5200000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 0
Reliability Upgrade | 1a | 1440 | ME | Central Maine Power Company |  |  | 2014-05-01 | Maine Power Reliability Program (MPRP) | Expand the existing Livermore Falls 115 kV Substation interconnecting lines 243A, 251, 89, 278 between substations Rumford I.P., Larrabee Road, Riley and Sturtevant | [6 empty] | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1439 | ME | Central Maine Power Company |  |  | 2014-07-01 | Maine Power Reliability Program (MPRP) | Expand the existing Belfast 115 kV Substation interconnecting lines 86 and 266 between substations Bucksport and Lincolnville | [6 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1438 | ME | Central Maine Power Company |  |  | 2012-11-01 | Maine Power Reliability Program (MPRP) | Replace K392-1 breaker at Maine Yankee 345 kV Substation with independent pole tripping capability | [6 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1437 | ME | Central Maine Power Company | Eversource |  | 2013-11-01 | Maine Power Reliability Program (MPRP) | Add a new Eliot 345 kV switchyard interconnecting lines 3022, 3240 and 3341 between substations Maguire Road, Newington and Deerfield (costs reflects Eversource portion only, costs of CMP portion is covered in total MPRP costs in Proj. #1411) | [6 empty] | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 0
Reliability Upgrade | 1a | 1436 | ME | Central Maine Power Company |  |  | 2013-11-01 | Maine Power Reliability Program (MPRP) | Add a new Raven Farm 345 kV switchyard interconnecting lines 3020 to Surowiec, line 3039 to W.F. Wyman and line 3040 to South Gorham | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1435 | ME | Central Maine Power Company |  |  | 2014-08-01 | Maine Power Reliability Program (MPRP) | Expand the existing Maguire Rd 115 kV substation to include a new 345kV transformer and switchyard that interconnects line 3021 to South Gorham and line 3022 to the NU Eliot Switching Station | [6 empty] | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1434 | ME | Central Maine Power Company |  |  | 2015-04-01 | Maine Power Reliability Program (MPRP) | Add a new Larrabee Road 345/115 kV substation interconnecting lines 3025, 3026, 200, 212, 251, 255 and 268 between substations Coopers Mills, Surowiec, Leeds, Monmouth, Livermore Falls, Middle Street and Gulf Island | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1433 | ME | Central Maine Power Company |  |  | 2015-03-01 | Maine Power Reliability Program (MPRP) | Add a new Coopers Mills 345/115 kV substation interconnecting lines 3024, 3025, 60, 254, 257 and 258 between substations Albion Road, Larrabee Road and Browns Crossing | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1432 | ME | Central Maine Power Company |  |  | 2015-03-01 | Maine Power Reliability Program (MPRP) | Add new Albion Road 345/115 kV substation interconnecting lines 3023, 3024, 67, 254, 257 and 258 between substations Orrington, Coopers Mills and Detroit | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1431 | ME | Central Maine Power Company |  |  | 2013-11-01 | Maine Power Reliability Program (MPRP) | Expand the 345/115 kV Surowiec Substation to interconnect the new 3026 345kV line to Larrabee Road, new 3020 345kV line to Raven Farm, also allow for the existing 345 kV Section 375 to be looped in and out of the expanded 345 kV Surowiec Substation. The existing Section 375 will be separated into Section 375 (Maine Yankee – Surowiec) and Section 3038 (Surowiec – Buxton). | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1430 | ME | Central Maine Power Company |  |  | 2014-04-01 | Maine Power Reliability Program (MPRP) | Expand the 345/115 kV South Gorham Substation to interconnect the new 3021 345kV line to Maguire Road | [6 empty] | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1429 | ME | Central Maine Power Company |  |  | 2015-03-01 | Maine Power Reliability Program (MPRP) | Expand the 345/115 kV Orrington Substation to interconnect the new 3023 345kV line to Albion Road and the new 254 115kV line to Coopers Mills | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1428 | ME | Central Maine Power Company |  |  | 2014-04-01 | Maine Power Reliability Program (MPRP) | Add a new 345/115 kV autotransformer #1 at the expanded Maguire Road Substation | [6 empty] | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1427 | ME | Central Maine Power Company |  |  | 2012-12-01 | Maine Power Reliability Program (MPRP) | Add a new 345/115 kV autotransformer #1 at the new Larrabee Road Substation | [6 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1426 | ME | Central Maine Power Company |  |  | 2015-03-01 | Maine Power Reliability Program (MPRP) | Replace the existing T3 autotransformer at Maxcys with the new Coopers Mills 345/115 kV autotransformer #1 at the new Coopers Mills substation | [6 empty] | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1425 | ME | Central Maine Power Company |  |  | 2013-05-01 | Maine Power Reliability Program (MPRP) | Add a new 345/115 kV autotransformer #1 at the new Albion Road Substation | [6 empty] | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1424 | ME | Central Maine Power Company |  |  | 2014-04-01 | Maine Power Reliability Program (MPRP) | Reconductor the entire length of the 115 kV transmission line (160) between Cape and Hinckley Pond | [6 empty] | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1423 | ME | Central Maine Power Company |  |  | 2012-02-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (86) between Bucksport and Belfast | [6 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1422 | ME | Central Maine Power Company |  |  | 2013-12-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (250) between Maguire Road and Three Rivers | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1421 | ME | Central Maine Power Company |  |  | 2013-05-01 | Maine Power Reliability Program (MPRP) | Rebuild the entire length of the 115 kV transmission line (212) between Monmouth and Larrabee Road | [6 empty] | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1420 | ME | Central Maine Power Company |  |  | 2013-05-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (229) between Riley and Rumford IP | [6 empty] | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1419 | ME | Central Maine Power Company |  |  | 2014-05-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (89) between Livermore Falls and Riley | [6 empty] | Under Construction | Under Construction | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1418 | ME | Central Maine Power Company |  |  | 2015-02-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (88) between Coopers Mills and Augusta East Side | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1417 | ME | Central Maine Power Company |  |  | 2015-02-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (60) between Coopers Mills and Bowman Street | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1416 | ME | Central Maine Power Company |  |  | 2014-12-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (258 (formerly 84)) between Coopers Mills and Albion Rd | [6 empty] | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1415 | ME | Central Maine Power Company |  |  | 2014-11-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (257 (formerly 67)) between Coopers Mills and Albion Rd | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1414 | ME | Central Maine Power Company |  |  | 2013-05-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (67) between Detroit and Albion Road | [6 empty] | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1413 | ME | Central Maine Power Company |  |  | 2018-12-01 | Maine Power Reliability Program (MPRP) | Add a new 115 kV transmission line (256) between Middle Street and Lewiston Lower (Lewiston Loop) | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 0
Reliability Upgrade | 1a | 1412 | ME | Central Maine Power Company |  |  | 2014-06-01 | Maine Power Reliability Program (MPRP) | Convert the 3-terminal 115 kV 86 line into 2 lines: 115 kV (266) between Belfast and Lincolnville and 115 kV (86) between Belfast and Bucksport | [6 empty] | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1411 | ME | Central Maine Power Company |  |  | 2017-08-01 | Maine Power Reliability Program (MPRP) | Add a new 115 kV transmission line (255) between Larrabee Road and Middle Street (Lewiston Loop) | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | 1378500000 | 1369000000 | 1369000000 | 1369000000 | 1369000000 | 1369000000 | 1369000000 | 1369000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 0
Reliability Upgrade | 1a | 1410 | ME | Central Maine Power Company |  |  | 2014-05-01 | Maine Power Reliability Program (MPRP) | Add a new 115 kV transmission line (251) between Livermore Falls and Larrabee Road | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1409 | ME | Central Maine Power Company |  |  | 2014-05-01 | Maine Power Reliability Program (MPRP) | Tap the 243 115kV line between Rumford and Rumford IP at junction Section 243 and extend the new 243A to Livermore Falls | [6 empty] | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1408 | ME | Central Maine Power Company |  |  | 2015-03-01 | Maine Power Reliability Program (MPRP) | Add a new 115 kV transmission line (254) between Orrington and Coopers Mills (separate TCA) | [6 empty] | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2011-06-16 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1407 | ME | Central Maine Power Company |  |  | 2014-08-01 | Maine Power Reliability Program (MPRP) | Add a new 345 kV transmission line (3022) between Maguire Road and Eliot (formerly called Three Rivers) | [6 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1406 | ME | Central Maine Power Company |  |  | 2014-04-01 | Maine Power Reliability Program (MPRP) | Add a new 345 kV transmission line (3021) between South Gorham and Maguire Road | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1405 | ME | Central Maine Power Company |  |  | 2013-11-01 | Maine Power Reliability Program (MPRP) | Add a new 345 kV transmission line (3020) between Surowiec and Raven Farm | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1404 | ME | Central Maine Power Company |  |  | 2012-12-01 | Maine Power Reliability Program (MPRP) | Add a new 345 kV transmission line (3026) between Larrabee Road and Surowiec | [6 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1403 | ME | Central Maine Power Company |  |  | 2015-04-01 | Maine Power Reliability Program (MPRP) | Add a new 345 kV transmission line (3025) between Coopers Mills and Larrabee Road | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1402 | ME | Central Maine Power Company |  |  | 2015-03-01 | Maine Power Reliability Program (MPRP) | Add a new 345 kV transmission line (3024) between Albion Rd and Coopers Mills | [6 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | 1320000000 | 1470187000 | 1470187000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364500000 | 1362500000 | 1362500000 | 1362500000 | 1362500000 | 1362500000 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1401 | ME | Central Maine Power Company |  |  | 2013-05-01 | Maine Power Reliability Program (MPRP) | Add a new 345 kV transmission line (3023) between Orrington and Albion Rd | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1400 | CT | Eversource |  |  | 2014-09-01 | SWCT | Add a 150 MVAR 345 kV shunt reactor at the Haddam Neck Station | [6 empty] | Concept | Proposed | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 5/4/2012 7/2/2013 | 2015-02-20 | [6 empty] | TBD | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 0
Reliability Upgrade | 1a | 1399 | CT | Eversource |  |  | 2015-12-01 | SWCT | East Devon 345 kV voltage 11T Series Breaker addition | [6 empty] | Proposed | Concept | Concept | Concept | Concept | Concept | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2016-04-15 | [6 empty] | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 1936000 | 1936000 | 1936000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 0
Reliability Upgrade | 1b | 1398 | CT | Eversource |  |  | 2015-12-01 | SWCT | Reconductor/rebuild 115 kV 1630-1 Wallingford - Walrec to 1590 kcmil ACSS (0.15 miles) | [6 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [6 empty] | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 0
Reliability Upgrade | 1b | 1397 | CT | Eversource |  |  | TBD | SWCT | Reconductor 115 kV 1610-1 Cook Hill - Southington to 795 kcmil ACSS (10.6 miles) | [6 empty] | Proposed | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [6 empty] | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 0
Reliability Upgrade | 1a | 1396 | MA | Eversource |  |  | 2013-12-01 | CELD 115/13.8 kV Substation | Loop the 1904 Line into the proposed Memorial Drive Substation | [6 empty] | Concept | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-10-09 | 2015-04-17 | [6 empty] | TBD | 6000000 | 6000000 | 3800000 | 3200000 | 3200000 | 3200000 | 3200000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 0
Reliability Upgrade | 1a | 1395 | MA | National Grid, USA |  |  | 2016-12-01 |  | Tewksbury 22A 345 kV GIS Substation rebuild | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-07-17 | 2016-02-05 | [6 empty] | 31680000 | 31680000 | 31680000 | 31680000 | 31680000 | 31680000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 49099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 0
Reliability Upgrade | 1a | 1394 | MA | Eversource |  |  | 2014-12-01 |  | Add 345 kV breaker at Carver Station to double existing 862 breaker | [6 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | NR | [6 empty] | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 0
Reliability Upgrade | 1a | 1393 | MA | Eversource |  |  | 2016-11-01 |  | Add two 115 kV breakers to Mashpee Station to support double-ending station | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-03-20 | 2015-10-02 | [6 empty] | 10600000 | 10600000 | 10600000 | 10600000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 0
Reliability Upgrade | 1a | 1392 | MA | Eversource |  |  | 2013-12-01 |  | Reconductor 3.5 mile section of the 115 kV line from Barnstable Station to location of new West Barnstable Station | [6 empty] | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-12-07 | NR | [6 empty] | 1700000 | 1700000 | 1700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 0
Generator Interconnection Upgrade | 2a | 1391 | ME | Emera Maine |  |  | 2016-11-01 | Queue Position 349 | Installation of 115 kV tap on line 66 between Graham and Rebel Hill to accommodate QP 349 | [6 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-08-05 | NR | [6 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1390 | ME | Emera Maine |  |  | 2015-10-01 | Queue Position 272 | Installation of new 345 kV breaker at Keene Road Substation to accommodate QP 272 | [6 empty] | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-07-17 | NR | [6 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1389 | CT | United Illuminating Company |  |  | 2016-03-01 | SWCT | Hawthorne 115 kV Capacitor Bank Addition | [6 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 10/5/2012 2/27/2014 | 2015-12-17 | [6 empty] | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 0
Reliability Upgrade | 1a | 1388 | CT | United Illuminating Company |  |  | 2015-12-01 | SWCT | Sackett 115 kV Capacitor Bank Addition | [6 empty] | Proposed | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2012-10-05 | NR | [6 empty] | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 0
Reliability Upgrade | 1a | 1387 | CT | United Illuminating Company |  |  | 2015-12-01 | SWCT | Grand Avenue 115 kV Capacitor Bank Addition | [6 empty] | Proposed | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2012-10-05 | No | [6 empty] | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 0
Reliability Upgrade | 1a | 1386 | CT | United Illuminating Company |  |  | 2016-12-01 | SWCT | Mix Avenue 115 kV Capacitor Bank Additions, Series Reactor Addition and Terminal Modifications | [6 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 10/5/2012 11/8/2012 4/16/2015 | 2016-12-06 | [6 empty] | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 22000000 | 22000000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 0
Reliability Upgrade | 1a | 1385 | CT | United Illuminating Company |  |  | 2017-03-01 | SWCT | Sackett 115 kV PAR Removal - Terminal Modifications | [6 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-11-08 | NR | [6 empty] | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 0
Reliability Upgrade | 1a | 1384 | CT | United Illuminating Company |  |  | 2016-11-01 | SWCT | Milvon to Devon Tie 88005A - 89005B 115 kV Line Upgrade | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-08-27 | 2015-04-17 | [6 empty] | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 27300000 | 37500000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 0
Reliability Upgrade | 1a | 1383 | CT | United Illuminating Company |  |  | 2017-01-01 | SWCT | North Haven to Walrec 1630-3 115 kV relay upgrade (formerly known as North Haven to Walrec 1630-3 line & relay upgrade) | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-08-27 | NR | [6 empty] | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 0
Reliability Upgrade | 1a | 1382 | CT | United Illuminating Company |  |  | 2015-12-01 | SWCT | Glen Lake Junction - Mix Avenue 1610-2 115 kV Line Upgrade | [6 empty] | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2012-08-27 | No | [6 empty] | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 0
Reliability Upgrade | 1a | 1381 | CT | United Illuminating Company |  |  | 2018-05-01 | SWCT | Baird 115/13.8 kV Substation Rebuild (formerly known as Baird 115 kV Bus Upgrade) | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 8/27/2012 9/9/2014 | 2017-01-03 | [6 empty] | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 8900000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 20400000 | 20400000 | 17820000 | 17820000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 0
Reliability Upgrade | 1a | 1380 | CT | United Illuminating Company |  |  | 2018-12-01 | SWCT | Baird to Congress 8809A - 8909B 115 kV Line Upgrades | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-08-27 | 2016-10-04 | [6 empty] | 33100000 | 33100000 | 33100000 | 33100000 | 33100000 | 44300000 | 56300000 | 56300000 | 56300000 | 56300000 | 73300000 | 73300000 | 73300000 | 73300000 | 73300000 | 73300000 | 73300000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 0
Reliability Upgrade | 1a | 1379 | NH | Eversource |  |  | 2013-12-01 | Southern New Hampshire Solution | J114-2 Greggs - Rimmon 115 kV thermal upgrade | [5 empty] | Proposed | Proposed | Proposed | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2016-01-07 | [5 empty] | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 800000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 0
Reliability Upgrade | 1a | 1378 | CT | Eversource |  |  | 2013-03-01 | NEEWS (Greater Springfield Reliability Project) | Build new 345 kV Line (3216) Agawam (MA) - North Bloomfield (CT) (CT portion) | [5 empty] | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 5/4/2012 | 2014-02-25 | [5 empty] | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1377 | CT | Eversource |  |  | 2013-12-01 | Central/Western Massachusetts Upgrades - Group 4 - E. Longmeadow Projects | Substation work at Scitico (CT) associated with the new Hampden (MA) Substation project (NGRID) | [5 empty] | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 10/17//2007 | NR | [5 empty] | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | #VALUE!
Reliability Upgrade | 1a | 1376 | NH | Eversource |  |  | 2013-12-01 | Southern New Hampshire Solution | Add two 115 kV circuit breakers at Merrimack Substation | [5 empty] | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-05-16 | 2015-11-05 | [5 empty] | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | #VALUE!
Generator Interconnection Upgrade | 2a | 1375 | NH | Eversource |  |  | 2013-06-01 | Groton Wind | Upgrade the E115 115 kV line from Huckins Hill Switching Station to Ashland Tap | [5 empty] | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-05-16 | NR | [5 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1374 | NH | Eversource |  |  | 2012-10-01 | Groton Wind | New 115 kV Huckins Hill Switching Station bifurcating the E115 115 kV line | [5 empty] | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-05-16 | NR | [5 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1373 | CT | Eversource |  |  | 2017 | NEEWS | Add the 2nd Beseck 9F Substation Variable Shunt Reactor (75-150 MVAR) | [5 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 5/4/2012 7/25/2013 | No | [5 empty] | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 0
Reliability Upgrade | 1a | 1372 | CT | Eversource |  |  | 2017 | NEEWS | North Bloomfield 2A Substation Expansion which includes a 3rd bay with two breakers and associated substation work | [5 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2012-05-04 | No | [5 empty] | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | #VALUE!
Reliability Upgrade | 1a | 1371 | CT | Eversource |  |  | 2013-07-01 | NEEWS | Add the first Beseck 9F Substation Variable Shunt Reactor (75-150 MVAR) | [5 empty] | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 5/4/2012 7/25/2013 | 2014-12-09 | [5 empty] | 9000000 | 9000000 | 9000000 | 9000000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 0
Reliability Upgrade | 1a | 1370 | CT | Eversource |  |  | 2013-12-01 | NEEWS | Replace existing 115 kV series reactor at North Bloomfield | [5 empty] | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-05-04 | 2014-12-09 | [5 empty] | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 0
Reliability Upgrade | 1a | 1369 | CT | Eversource |  |  | 2013-06-01 | NEEWS | Reconductor 115 kV line 1784, North Bloomfield - Northeast Simsbury | [5 empty] | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-05-04 | 2014-12-09 | [5 empty] | 6000000 | 6000000 | 6000000 | 6000000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 0
Reliability Upgrade | 1a | 1368 | MA | Eversource |  |  | 2012-12-01 | NEEWS (Greater Springfield Reliability Project) | Chicopee 18L Substation replace 115 kV circuit breakers 1T and 2 T | [5 empty] | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-05-04 | 2014-02-25 | [5 empty] | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Elective Upgrade | 4b | 1367 | ME | Central Maine Power Company |  |  | TBD | Queue Position 378 | 800 MW HVDC from MEPCO to Salem MA | [5 empty] | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [5 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 1366 | ME | Central Maine Power Company |  |  | 2013-12-01 | Maine Power Reliability Program (MPRP) | Section 160 reconductor from Hinckley Pond Substation to Cape Substation | [5 empty] | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2/26/09 & 11/22/10 | NR | [5 empty] | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1365 | NH | National Grid, USA |  |  | 2017-12-01 | Greater Boston - North | Install new 345 kV (3124) circuit between Eversource border and NH/MA border (NH portion of National Grid's portion of new Scobie - Tewksbury line) | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [5 empty] | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | #VALUE!
Reliability Upgrade | 1a | 1364 | NH | Eversource |  |  | 2016-11-01 | Greater Boston - North | Reconductoring Eversource's portion of Y-151 between Hudson and Power Street | [5 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [5 empty] | TBD | TBD | TBD | TBD | TBD | TBD | 8536000 | 8536000 | 8536000 | 8536000 | 8536000 | 8536000 | 8536000 | 8536000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 0
Reliability Upgrade | 1a | 1363 | MA | National Grid, USA |  |  | 2015-12-01 | Greater Boston - Central | Separation of double Circuit Towers on Q-169/F-158N lines | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No | [5 empty] | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 750000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 560000 | 560000 | 560000 | 557000 | 557000 | 557000 | 557000 | 557000 | 557000 | 557000 | 557000 | 557000 | 557000 | 557000 | 557000 | 557000 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 0
Reliability Upgrade | 1b | 1362 | MA | National Grid, USA |  |  | 2016-12-01 | Greater Boston - North | Reconductor the 337 Sandy Pond - Tewksbury 345 kV line | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [5 empty] | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 0
Reliability Upgrade | 1b | 1361 | MA | National Grid, USA |  |  | 2018 | Greater Boston - North | New 345 kV line between Wakefield and Ward Hill and associated substation work | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [5 empty] | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 0
Reliability Upgrade | 1a | 1360 | MA | National Grid, USA |  |  | 2016-03-01 | Auburn Area Transmission System Upgrades | Harrison Blvd substation A94 Tap | [5 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2010-02-10 | NR | [5 empty] | 400000 | 400000 | 900000 | 900000 | 1200000 | 1200000 | 1200000 | 1200000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 0
Reliability Upgrade | 1a | 1359 | VT | Vermont Electric Power Company |  |  | 2013-11-01 | Bennington Substation Rebuild | Install two 12.5 MVAR capacitor banks at Bennington 115 kV substation. | [5 empty] | Proposed | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-09-19 | 2013-12-05 | [5 empty] | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | #VALUE!
Generator Interconnection Upgrade | 2a | 1358 | ME | Bangor Hydro-Electric Company |  |  | 2012-09-01 | Queue Position 317 | Installation of new 3 breaker 115 kV ring bus switching station on line 68 between Rebel Hill and Debois in order to accommodate QP-317 | [5 empty] | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-03-13 | NR | [5 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1357 | MA | Eversource |  |  | 2019-05-01 | Greater Boston - Central | Open up lines 329-510/511 and 250-516/517 at Mystic and Chatham respectively. Operate K Street as Normally Closed station | [5 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [5 empty] | TBD | TBD | TBD | TBD | TBD | TBD | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 0
Reliability Upgrade | 1a | 1356 | MA | Eversource |  |  | 2024-03-01 | Greater Boston - Central | Add a 2nd Mystic-Woburn 115 kV cable to create a bifurcated 211-514 Mystic-Woburn 115 kV circuit | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [5 empty] | 48000000 | 48000000 | 48000000 | 48000000 | 48000000 | 48000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 81500000 | 81500000 | 81500000 | 81500000 | 81500000 | 81500000 | 81500000 | 81500000 | 81500000 | 138786000 | 138786000 | 138786000 | 138786000 | 138786000 | 138786000 | 138786000 | 138786000 | 138786000 | 138786000 | 138786000 | 223133000 | 223133000 | 223133000 | 223133000 | 223133000 | 223133000 | 223133000 | 223133000 | 223133000 | 223133000 | 0
Reliability Upgrade | 1a | 1355 | MA | Eversource |  |  | 2021-03-01 | Greater Boston - Central | Split existing 110-522/240-510 DCT from Baker St. Station to Needham for a portion of the way and then install a new underground 115 kV line for the remainder of the way | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [5 empty] | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 38000000 | 38000000 | 38000000 | 38000000 | 38000000 | 38000000 | 38000000 | 38000000 | 38000000 | 38000000 | 45700000 | 45700000 | 45700000 | 45700000 | 45700000 | 45700000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 0
Reliability Upgrade | 1a | 1354 | MA | Eversource |  |  | 2020-10-01 | Greater Boston - Central | Add Mystic-Chelsea 115 kV cable | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [5 empty] | 25000000 | 25000000 | 25000000 | 25000000 | 25000000 | 25000000 | 53500000 | 53500000 | 53500000 | 53500000 | 53500000 | 53500000 | 53500000 | 53500000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 0
Reliability Upgrade | 1a | 1353 | MA | Eversource |  |  | 2016-06-01 | Greater Boston - Central | Install K St. tie breaker #33 on the East bus | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2015-11-05 | No | [5 empty] | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 1300000 | 1804000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 0
Reliability Upgrade | 1a | 1352 | MA | Eversource |  |  | 2019-05-01 | Greater Boston - Central | Add a second Mystic 345/115 kV autotransformer and Mystic bus reconfiguration | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [5 empty] | 16000000 | 16000000 | 16000000 | 16000000 | 16000000 | 16000000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 19400000 | 19400000 | 19400000 | 19400000 | 19400000 | 19400000 | 19400000 | 19400000 | 19400000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 0
Reliability Upgrade | 1a | 1351 | MA | Eversource |  |  | 2013-06-01 | Long Term Lower SEMA Upgrades | Install a new 345 kV line from Carver to the vicinity of the Bourne substation and interconnect to the segment of the #120 line section between Bourne and the vicinity of Oak Street. This line will terminate at a new 345/115 kV autotransformer at the West Barnstable Substation | [5 empty] | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 07/2011 | 2011-12-16 | [5 empty] | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | #VALUE!
Reliability Upgrade | 1a | 1350 | MA | Eversource |  |  | 2014-08-01 | Long Term Lower SEMA Upgrades | Expand the existing Bourne 115 kV Substation by adding a new breaker to terminate the existing #120 line between Canal and Barnstable at Bourne | [5 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 07/2011 | 2011-12-16 | [5 empty] | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | #VALUE!
Reliability Upgrade | 1a | 1349 | MA | Eversource |  |  | 2014-08-01 | Long Term Lower SEMA Upgrades | Reconfigure the existing #120 line between Canal and Barnstable into three segments : Canal - Bourne, Bourne to vicinity of Oak Street (to become part of 399 Line), and West Barnstable to Barnstable. | [5 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 07/2011 | 2011-12-16 | [5 empty] | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 0
Reliability Upgrade | 1a | 1348 | CT | United Illuminating Company |  |  | 2014-12-01 | SWCT | Pequonnock 115 kV disconnect switch & bus upgrade (Pequonnock 115 kV Fault Duty Mitigation. - Phase I) | [5 empty] | Concept | Concept | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2014-09-05 | [5 empty] | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 6000000 | 6080000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 0
Reliability Upgrade | 1b | 1347 | NH | New Hampshire Transmission, LLC |  |  | 2015-11-01 | Greater Boston - North | Seabrook 345 kV substation: Replace two 345 kV GIS breakers, 1000 feet of GIS bus, and open-air equipment at the GIS transition yard associated with the 394 line termination. These upgrades eliminate terminal equipment restrictions on the New Hampshire Transmission section of the 345 kV line (394) from Seabrook to West Amesbury to Ward Hill | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [5 empty] | 21201727 | 21201727 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 0
Reliability Upgrade | 1a | 1346 | NH | Eversource |  |  | 2013-06-01 | Western New Hampshire Solution | Upgrade the 381 345kV line between MA/NH border and the NH/VT border |  |  |  |  | Proposed | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-12-07 | 2015-12-17 |  |  |  |  | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | #VALUE!
Reliability Upgrade | 1a | 1345 | MA | Eversource |  |  | 2013-12-01 |  | Build a new 115 kV Bay at Brook Street with the addition of two new 115 kV breakers and a new 115/23 kV transformer |  |  |  |  | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-03-05 | NR |  |  |  |  | 1360000 | 1360000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 0
Reliability Upgrade | 1a | 1344 | MA | Eversource |  |  | 2018-03-01 |  | Framingham BPS station upgrade |  |  |  |  | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | NR | 2017-07-17 |  |  |  |  | TBD | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 11804300 | 11804300 | 11804300 | 11804300 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 0
Reliability Upgrade | 1a | 1343 | MA | Eversource |  |  | 2016-12-01 |  | Relay systems upgrade at Lexington and Woburn to make Lexington station non-BPS |  |  |  |  | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | NR | NR |  |  |  |  | TBD | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 0
Reliability Upgrade | 1a | 1342 | MA | Eversource |  |  | 2015-05-01 | NEEWS | Add a new 345 kV Series breaker to the existing 106 breaker at West Medway |  |  |  |  | Concept | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-07-17 | NR |  |  |  |  | 3000000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 0
Reliability Upgrade | 1a | 1341 | MA | Eversource |  |  | 2012-12-01 | Greater Boston - Western Suburbs | Add a new 115 kV 36.7 MVAR capacitor bank at Hartwell Ave |  |  |  |  | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-08-06 | No |  |  |  |  | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 0
Reliability Upgrade | 1b | 1340 | MA | Eversource |  |  | 2015-12-01 | Greater Boston - Western Suburbs | Upgrade 115 kV terminal equipment at Lexington substation for 320-507/508 lines |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR |  |  |  |  | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 0
Reliability Upgrade | 1a | 1339 | MA | Eversource |  |  | 2016-08-01 | Greater Boston - Western Suburbs | Upgrade 115 kV line 533-508 Lexington-Hartwell Ave by removing line clearance limitation and upgrading station equipment |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | No |  |  |  |  | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 415000 | 415000 | 415000 | 415000 | 415000 | 415000 | 415000 | 145000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 0
Reliability Upgrade | 1a | 1338 | MA | Eversource |  |  | 2014-11-01 | Greater Boston - Western Suburbs | Reconductor of the 115 kV line 211-508 from Woburn-Burlington |  |  |  |  | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-07-17 | No |  |  |  |  | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 0
Reliability Upgrade | 1a | 1337 | MA | Eversource |  |  | 2017-12-01 | Greater Boston - Western Suburbs | Reconfigure Waltham Substation and one (1) 115 kV breaker. Includes relocating terminations for PARs and 282-507 line. |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No |  |  |  |  | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 14000000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 0
Reliability Upgrade | 1a | 1336 | MA | Eversource |  |  | 2019-12-01 | Greater Boston - Western Suburbs | Replace the existing 345/115 kV autotransformer with a higher rating transformer and 345 kV and 115 kV switchgear and breakers at Woburn |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No |  |  |  |  | 6100000 | 6100000 | 6100000 | 6100000 | 6100000 | 6100000 | 6100000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 49100000 | 49100000 | 49100000 | 49100000 | 49100000 | 49100000 | 49100000 | 49100000 | 49100000 | 49100000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 0
Reliability Upgrade | 1a | 1335 | MA | Eversource |  |  | 2024-12-01 | Greater Boston - Western Suburbs | Build a new 115 kV line from Sudbury Station 342 substation to Hudson substation and add a 30 MVAR shunt reactor at the Sudbury station |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 06/09/2016 10/05/2020 | No |  |  |  |  | 41000000 | 41000000 | 41000000 | 41000000 | 41000000 | 41000000 | 41000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 45300000 | 45300000 | 45300000 | 45300000 | 45300000 | 45300000 | 45300000 | 45300000 | 45300000 | 45300000 | 45300000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 105440000 | 105440000 | 105440000 | 128520000 | 128520000 | 128520000 | 128520000 | 128520000 | 128520000 | 128520000 | 128520000 | 128520000 | 128520000 | 0
Generator Interconnection Upgrade | 2b | 1334 | ME | Central Maine Power Company |  |  | 2012-10-01 | Queue Position 310 | Four +/- 4 MVAR dynamic reactive sources (including a 115/34.5 transformer with High-side and Low-side breakers) at Bigelow Substation. Automate high-voltage switching controls for both 18 MVAR capacitor banks at Wyman Hydro Substation. Install 5.4 MVAR of shunt capacitance at Starks Substation to interconnect QP #310 |  |  |  |  | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2012-03-05 | NR |  |  |  |  | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1333 | ME | Central Maine Power Company |  |  | 2014-03-01 | CMP-LSP Augusta | Add two 115 kV circuit breakers and 115/34.5 kV transformer at North Augusta Substation |  |  |  |  | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-03-05 | NR |  |  |  |  | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 0
Reliability Upgrade | 1b | 1332 | MA | National Grid, USA |  |  | 2017-06-01 | Southern New Hampshire Solution | Reconductoring the 345 kV 326 line portion from Sandy Pond to MA/NH state line |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-03-08 | No |  |  |  |  | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 0
Reliability Upgrade | 1a | 1331 | RI | National Grid, USA |  |  | 2013-05-01 | NEEWS (Rhode Island Reliability Project) | 115 kV Breaker addition at Kent County |  |  |  |  | Concept | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-05-04 | 2015-12-17 |  |  |  |  | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | #VALUE!
Reliability Upgrade | 1a | 1330 | MA | National Grid, USA |  |  | 2018-12-01 | Greater Boston - Western Suburbs | X-24/E-157W DCT Separation |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No |  |  |  |  | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 0
Reliability Upgrade | 1a | 1329 | MA | National Grid, USA |  |  | 2015-12-01 | Greater Boston - Western Suburbs | Refurbishment of 69 kV line X-24 Millbury-Northboro Rd |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | No |  |  |  |  | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 6060000 | 6060000 | 6060000 | 5793000 | 5793000 | 5793000 | 5793000 | 5793000 | 5793000 | 5793000 | 5576000 | 5576000 | 5576000 | 5576000 | 5576000 | 5576000 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 0
Reliability Upgrade | 1b | 1328 | MA | National Grid, USA |  |  | 2015-12-01 | Greater Boston - Western Suburbs | 115 kV Line reconductoring of E-157W Millbury-E. Main St |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 0
Reliability Upgrade | 1a | 1327 | MA | National Grid, USA |  |  | 2019-06-01 | Greater Boston - Western Suburbs | 69 kV Line reconductoring of W-23W Woodside-Northboro Rd |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No |  |  |  |  | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 0
Reliability Upgrade | 1b | 1326 | MA | National Grid, USA |  |  | 2015-12-01 | Greater Boston - Western Suburbs | 69 kV Line reconductoring of W-23 Fitch Rd-Woodside |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 0
Reliability Upgrade | 1a | 1325 | NH | Eversource |  |  | 2014-12-01 | Seacoast New Hampshire Solution | Upgrade 115 kV line R193, Scobie Pond-Kingston Tap |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-11-05 |  |  |  |  | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 2000000 | 2000000 | 1550000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 0
Reliability Upgrade | 1a | 1324 | NH | Eversource |  |  | 2014-12-01 | Seacoast New Hampshire Solution | Upgrade 115 kV line H141, Chester-Great Bay |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-11-05 |  |  |  |  | 8400000 | 8400000 | 8400000 | 8400000 | 8400000 | 8400000 | 8400000 | 8400000 | 6000000 | 6000000 | 3400000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 0
Reliability Upgrade | 1a | 1323 | NH | Eversource |  |  | 2015-11-01 | Seacoast New Hampshire Solution | Schiller 115 kV Substation-Add: (3) 115 kV circuit breakers (6) 13.3 MVAR 115 kV capacitor banks |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2013-03-07 | 2015-11-05 |  |  |  |  | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 14600000 | 14600000 | 12811000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 0
Reliability Upgrade | 1a | 1322 | NH | Eversource |  |  | 2014-12-01 | Seacoast New Hampshire Solution | Three Rivers Substation-Add: (1) 115 kV circuit breaker |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-11-05 |  |  |  |  | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 2200000 | 2200000 | 2200000 | 1300000 | 1300000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 0
Reliability Upgrade | 1a | 1321 | NH | Eversource |  |  | 2014-12-01 | Seacoast New Hampshire Solution | Scobie Pond Substation-Add: (1) 115 kV circuit breaker (associated with new circuit, Scobie Pond-Chester) |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-11-05 |  |  |  |  | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 2400000 | 2400000 | 2400000 | 2400000 | 2000000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 0
Reliability Upgrade | 1a | 1320 | NH | Eversource |  |  | 2015-12-01 | Seacoast New Hampshire Solution | Chester 115 kV Substation-Add: (5) 115 kV circuit breakers (associated with new circuit, Scobie Pond-Chester), |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2013-03-07 | 2015-11-05 |  |  |  |  | 24200000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 17017000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 0
Reliability Upgrade | 1a | 1319 | NH | Eversource |  |  | 2015-12-01 | Seacoast New Hampshire Solution | New 115 kV overhead circuit, Scobie Pond-Chester |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2013-03-07 | 2015-11-05 |  |  |  |  | 13700000 | 13700000 | 13700000 | 13700000 | 13700000 | 13700000 | 13700000 | 13700000 | 13700000 | 13700000 | 13700000 | 15210000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 0
Reliability Upgrade | 1a | 1318 | NH | Eversource |  |  | 2020-05-01 | Seacoast New Hampshire Solution | New 115 kV overhead/submarine circuit, Madbury-Portsmouth |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2013-03-07 | 2015-11-05 |  |  |  |  | 27200000 | 27200000 | 27200000 | 27200000 | 27200000 | 27200000 | 27200000 | 27200000 | 27200000 | 27200000 | 64400000 | 64400000 | 64400000 | 64400000 | 64400000 | 64400000 | 80800000 | 80800000 | 80800000 | 80800000 | 80800000 | 80800000 | 80800000 | 117654000 | 117654000 | 117654000 | 117654000 | 117654000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 0
Reliability Upgrade | 1a | 1317 | NH | Eversource |  |  | 2020-05-01 | Seacoast New Hampshire Solution | Portsmouth Substation- Add: (1) 115 kV circuit breaker (associated with new circuit, Madbury-Portsmouth) |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2013-03-07 | 2015-11-05 |  |  |  |  | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 5681000 | 5681000 | 5681000 | 5681000 | 5681000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 0
Reliability Upgrade | 1a | 1316 | NH | Eversource |  |  | 2020-05-01 | Seacoast New Hampshire Solution | Madbury Substation- Add: (1) 115 kV circuit breaker (associated with new circuit, Madbury-Portsmouth) |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2013-03-07 | 2015-11-05 |  |  |  |  | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 3477000 | 3477000 | 3477000 | 3477000 | 3477000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 0
Reliability Upgrade | 1a | 1315 | NH | Eversource |  |  | 2013-12-01 | Southern New Hampshire Solution | Upgrade 345 kV line 326, Scobie Pond-NH/MA Border |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2016-01-07 |  |  |  |  | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 4500000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 0
Reliability Upgrade | 1a | 1314 | NH | Eversource |  |  | 2014-12-01 | Southern New Hampshire Solution | Oak Hill Substation - Loop in 115 kV line V182, Garvins-Webster, add (6) 115 kV circuit breakers. |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-11-05 |  |  |  |  | 22600000 | 22600000 | 22600000 | 22600000 | 22600000 | 22600000 | 22600000 | 22600000 | 22600000 | 20600000 | 20600000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 0
Reliability Upgrade | 1b | 1313 | NH | Eversource |  |  | 2017 | Southern New Hampshire Solution | Greggs Substation - Add (1) 115 kV series circuit breaker, replace (1) 115 kV circuit breaker, includes associated 115kV substation work |  |  |  |  | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 0
Reliability Upgrade | 1a | 1312 | NH | Eversource |  |  | 2014-12-01 | Southern New Hampshire Solution | Upgrade Merrimack 230/ 115 kV substation and relocate existing capacitor banks to Bus 1 and Bus 3 |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-11-05 |  |  |  |  | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 14900000 | 14900000 | 14900000 | 15500000 | 15500000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 0
Reliability Upgrade | 1b | 1311 | NH | Eversource |  |  | 2016 | Southern New Hampshire Solution | Terminal upgrades for 115 kV line V182, Garvins-Webster |  |  |  |  | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 0
Reliability Upgrade | 1a | 1310 | NH | Eversource |  |  | 2013-06-01 | Southern New Hampshire Solution | Rebuild 115 kV line H137, Merrimack-Garvins |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2016-01-07 |  |  |  |  | 4900000 | 4900000 | 4900000 | 4900000 | 4900000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 0
Reliability Upgrade | 1a | 1309 | NH | Eversource |  |  | 2014-12-01 | Southern New Hampshire Solution | Rebuild 115 kV line D118, Deerfield-Pine Hill |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2016-01-07 |  |  |  |  | 22700000 | 22700000 | 22700000 | 22700000 | 22700000 | 22700000 | 17400000 | 17400000 | 17400000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 0
Reliability Upgrade | 1a | 1308 | NH | Eversource |  |  | 2014-05-01 | Southern New Hampshire Solution | Up rate 115 kV line P145, Oak Hill-Merrimack |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2016-01-07 |  |  |  |  | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 1700000 | 1700000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 0
Reliability Upgrade | 1a | 1307 | NH | Eversource |  |  | 2015-03-01 | Southern New Hampshire Solution | Uprate 115 kV line G146, Garvins-Deerfield |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2016-01-07 |  |  |  |  | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 3300000 | 3300000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 0
Reliability Upgrade | 1a | 1306 | NH | Eversource |  |  | 2015-05-01 | Southern New Hampshire Solution | Rebuild 115 kV line K165, W157 tap (H123 renamed) - Eagle-Power St. |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2016-01-07 |  |  |  |  | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 0
Reliability Upgrade | 1b | 1305 | NH | Eversource |  |  | 2020 | Southern New Hampshire Solution | Uprate 115 kV line O161, Pine Hill-Greggs |  |  |  |  | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 0
Reliability Upgrade | 1a | 1304 | NH | Eversource |  |  | 2015-12-01 | Southern New Hampshire Solution | New 115 kV overhead circuit, Scobie Pond-Huse Rd (W144) |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2013-03-07 | 2016-01-07 |  |  |  |  | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 0
Reliability Upgrade | 1a | 1303 | NH | Eversource |  |  | 2015-11-01 | Southern New Hampshire Solution | Huse Rd Substation- Add:(2) 115 kV circuit breakers (associated with new circuit, Scobie Pond-Huse Rd) |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2013-03-07 | 2016-01-07 |  |  |  |  | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 0
Reliability Upgrade | 1a | 1302 | NH | Eversource |  |  | 2014-12-01 | Southern New Hampshire Solution | Scobie Pond Substation- Add: (1) 115 kV circuit breaker (associated with new circuit, Scobie Pond-Huse Rd - W144) (1) 345 kV circuit breaker in series with circuit breaker 802 (802S) |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2016-01-07 |  |  |  |  | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 0
Reliability Upgrade | 1a | 1301 | NH | Eversource |  |  | 2016-12-01 | Southern New Hampshire Solution | Eagle Substation Add: 345kV yard, (3) 345 kV circuit breakers, (4) 115kV circuit breakers, (1) 345/115 kV auto-transformer, (4) 26.6 MVAR 115 kV capacitor banks |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2013-03-07 | 2016-01-07 |  |  |  |  | 59700000 | 59700000 | 59700000 | 59700000 | 59700000 | 59700000 | 59700000 | 59700000 | 59700000 | 59700000 | 59700000 | 59700000 | 59700000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 0
Reliability Upgrade | 1a | 1300 | ME | Central Maine Power Company |  |  | 2022-12-01 | Central New Hampshire Solution | Install transfer trip at Kimball Road disconnect Lovell from 115 kV, Lovell load will continue to be served from CMP subtransmission |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 2013-03-07 | No |  |  |  |  | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 0
Generator Interconnection Upgrade | 2a | 1299 | CT | Eversource |  |  | 2014-12-01 | Meriden Gas Turbine | 1.1 mile radial 345 kV line from the new three breaker ring bus to Meriden generating facility |  |  |  |  | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2010-03-23 | NR |  |  |  |  | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1298 | RI | National Grid, USA |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | New 345 kV (366) line MA/RI Border to West Farnum (4.8 miles) |  |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 9/24/2008 5/4/2012 | 2015-12-17 |  |  |  |  | 19500000 | 19500000 | 19500000 | 19500000 | 19500000 | 19500000 | 27700000 | 27700000 | 36325000 | 36325000 | 36325000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 0
Reliability Upgrade | 1a | 1297 | RI | National Grid, USA |  |  | 2014-09-01 | NEEWS (Interstate Reliability Project) | Hartford Ave Substation Relay Upgrades |  |  |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2015-12-17 |  |  |  |  | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 0
Reliability Upgrade | 1a | 1296 | RI | National Grid, USA |  |  | 2014-09-01 | NEEWS (Interstate Reliability Project) | Woonsocket Substation Relay Upgrades |  |  |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2015-12-17 |  |  |  |  | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 0
Reliability Upgrade | 1a | 1295 | RI | National Grid, USA |  |  | 2014-09-01 | NEEWS (Interstate Reliability Project) | Riverside Substation Relay Upgrades |  |  |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2015-12-17 |  |  |  |  | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 900000 | 900000 | 900000 | 900000 | 900000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 0
Reliability Upgrade | 1a | 1294 | RI | National Grid, USA |  |  | 2012-05-01 | NEEWS (Rhode Island Reliability Project) | West Farnum Substation 345 kV additions |  |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 9/24/2008 5/4/2012 | 2015-12-17 |  |  |  |  | 18600000 | 18600000 | 18600000 | 18600000 | 18600000 | 18600000 | 18600000 | 18600000 | 14000000 | 14000000 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | #VALUE!
Reliability Upgrade | 1a | 1293 | MA | National Grid, USA |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | Carpenter Hill Substation Relay Upgrades |  |  |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | NR | 2015-12-17 |  |  |  |  | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1715000 | 1715000 | 1715000 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | #VALUE!
Reliability Upgrade | 1a | 1292 | CT | United Illuminating Company |  |  | 2013-07-01 |  | East Shore 115/13.8 kV Substation Capacity Upgrade |  |  |  |  | Proposed | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-03-05 | NR |  |  |  |  | 2000000 | 3200000 | 3200000 | 3200000 | 3000000 | 3000000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 0
Generator Interconnection Upgrade | 2a | 1291 | VT | Vermont Electric Power Company |  |  | 2014-03-01 | Kingdom Community Wind | Installation of a 46 kV dynamic reactive device with 25 MVARs of capacitive reserves at Jay Substation |  |  |  |  | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-10-21 | NR |  |  |  |  | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1290 | VT | Vermont Electric Power Company |  |  | 2015-05-01 | VELCO-LSP - Georgia Substation | Install a 115/34.5 kV transformer at the Georgia Substation |  |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-10-19 | NR |  |  |  |  | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reliability Upgrade | 1b | 1289 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | Southeastern VT Solution | Upgrade the 381 345 kV line between Vernon and the NH/VT border |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 0
Reliability Upgrade | 1b | 1288 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | Connecticut River Solution | Rebuild the 2 mile Ascutney - Ascutney 115 kV Tap line (10) |  |  |  |  | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 13000000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1287 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | Northern VT Solution | Install two 12.5 MVAR capacitor banks at Jay 115 kV substation |  |  |  |  | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 4400000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1286 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | Connecticut River Valley | Construct a new 15 mile 115 kV line from Coolidge to Ascutney |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 0
Reliability Upgrade | 1b | 1285 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | Central VT Solution | Construct a new 27 mile 345 kV line from West Rutland to Coolidge |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 0
Reliability Upgrade | 1b | 1284 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | Northwestern VT Solution | K30 West Rutland - Middlebury 115 kV line rebuild |  |  |  |  | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 113000000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1283 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | Northwestern VT Solution | K43 New Haven - Williston 115 kV line rebuild |  |  |  |  | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 96000000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1282 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | Northwestern VT Solution | Upgrade K27 Williston-Tafts Corner 115 kV line |  |  |  |  | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 12000000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1281 | VT | Vermont Electric Power Company |  |  | 2014-12-01 | Northwestern VT Solution | Install a SPS to cross trip the PV-20 line for low voltage at South Hero |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 0
Reliability Upgrade | 1b | 1280 | ME | Central Maine Power Company |  |  | 2022-12-01 | Mid-Coast Spur | New 115 kV line section 244 and upgraded line section 80 between Coopers Mill and Highland Substations |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Proposed | No | No |  |  |  | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 0
Reliability Upgrade | 1b | 1279 | ME | Central Maine Power Company |  |  | 2017-12-01 |  | New 345/115 kV Autotransformer and 115 kV switchyard at Raven Farm substation consisting of a four-bay breaker and a half configuration of eleven (11) breakers |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 0
Reliability Upgrade | 1a | 1278 | NH | Eversource |  |  | 2016-08-01 | Central New Hampshire Solution | Saco Valley Substation - Add two 25 MVAR synchronous condensers |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2013-03-07 | 2015-11-25 |  |  |  | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 18977000 | 18977000 | 19368000 | 19368000 | 22498000 | 22498000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 0
Reliability Upgrade | 1a | 1277 | NH | Eversource |  |  | 2014-02-01 | Central New Hampshire Solution | Webster Substation - Add four 26.6 MVAR 115 kV capacitors |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-11-25 |  |  |  | 11900000 | 11900000 | 11900000 | 11900000 | 11900000 | 9000000 | 9000000 | 9000000 | 7100000 | 7100000 | 7100000 | 7100000 | 7047000 | 7047000 | 7047000 | 7047000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 0
Reliability Upgrade | 1a | 1276 | NH | Eversource |  |  | 2014-12-01 | Northern New Hampshire Solution | Littleton Substation - Add a second 230/115kV autotransformer and associated 115 kV substation work |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 3/7/2013 12/22/2014 | 2015-08-04 |  |  |  | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 9700000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 0
Reliability Upgrade | 1a | 1275 | MA | Eversource |  |  | 2013-06-01 | Western New Hampshire Solution | Upgrade the 381 345 kV line between Northfield and the NH/VT border |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-12-07 | 2015-12-17 |  |  |  | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 2500000 | 2500000 | 2500000 | 2000000 | 2000000 | 2000000 | 2000000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 0
Reliability Upgrade | 1a | 1274 | NH | Eversource |  |  | 2016 | Western New Hampshire Solution | Rebuild N186 115 kV line |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-03-07 | No |  |  |  | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 0
Reliability Upgrade | 1a | 1273 | NH | Eversource |  |  | 2016 | Western New Hampshire Solution | Rebuild A152 115 kV line |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-03-07 | No |  |  |  | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 0
Reliability Upgrade | 1a | 1272 | NH | Eversource |  |  | 2013-09-01 | Western New Hampshire Solution | Weare Substation - Add two 13.3 MVAR 115 kV capacitors |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-12-17 |  |  |  | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3000000 | 3000000 | 3000000 | 3000000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 0
Reliability Upgrade | 1a | 1271 | NH | Eversource |  |  | 2013-11-01 | Western New Hampshire Solution | Upgrade the Keene to Monadnock (T198) 115 kV line |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-12-17 |  |  |  | 11900000 | 11900000 | 11900000 | 11900000 | 11900000 | 11900000 | 2000000 | 1038000 | 1038000 | 1038000 | 1038000 | 1038000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 0
Reliability Upgrade | 1a | 1270 | NH | Eversource |  |  | 2017-02-01 | Western New Hampshire Solution | New 115 kV line from Fitzwilliam to Monadnock and associated substation work |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2013-03-07 | 2015-12-17 |  |  |  | 10500000 | 10500000 | 10500000 | 10500000 | 10500000 | 10500000 | 10500000 | 10500000 | 10500000 | 16500000 | 16500000 | 16500000 | 18547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 0
Reliability Upgrade | 1a | 1269 | NH | Eversource |  |  | 2018 | Western New Hampshire Solution | Amherst Substation - New 345 kV breaker and two 25 MVAR Capacitor Banks |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 2013-03-07 | No |  |  |  | 19600000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 0
Reliability Upgrade | 1a | 1268 | MA | Eversource |  |  | 2013-12-01 |  | 345 kV Northfield Mountain to Berkshire (portion of 312) line structure replacements |  |  |  | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2015-04-17 |  |  |  | 7900000 | 7900000 | 8900000 | 8900000 | 9050000 | 9050000 | 9050000 | 8900000 | 8900000 | 8900000 | 8900000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 0
Reliability Upgrade | 1a | 1267 | MA | Eversource |  |  | 2011-12-01 |  | 115 kV Blandford to Southwick (portion of 1512) Line structure replacement |  |  |  | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2015-04-17 |  |  |  | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 0
Reliability Upgrade | 1a | 1266 | MA | Eversource |  |  | 2012-12-01 |  | 115kV Pleasant to Blandford (portion of 1421) Line structure replacement |  |  |  | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2015-04-17 |  |  |  | 9960000 | 9960000 | 12200000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 0
Generator Interconnection Upgrade | 2a | 1265 | VT | Vermont Electric Power Company |  |  | 2016-03-01 | Fair Haven Biomass | Installation of 3-breaker 115 kV ring bus interconnection to the Whitehall-Blissville 115 kV K7 line. Construction of 2.5 mile line to the plant |  |  |  |  | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2011-08-29 | NR |  |  |  | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1264 | RI | National Grid, USA |  |  | 2011-06-01 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. |  |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2015-12-17 |  |  |  | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | #VALUE!
Reliability Upgrade | 1a | 1263 | NH | National Grid, USA |  |  | 2014-11-01 | Northern New Hampshire Solution | New C-203 230kV line tap to Littleton NH Substation associated with 2nd 230/115 kV auto project |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-08-04 |  |  |  | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1500000 | 1500000 | 1500000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 0
Reliability Upgrade | 1b | 1262 | MA | National Grid, USA |  |  | 2015-12-01 | Greater Boston - North | 115 kV Line reconductoring of theY-151 from Tewksbury Junction - Tewksbury Substation |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 0
Reliability Upgrade | 1b | 1261 | MA | National Grid, USA |  |  | 2015-12-01 | Greater Boston - North | 115 kV Line reconductoring of the S-145T-146 from North Reading Tap - Wakefield Jct |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 0
Reliability Upgrade | 1a | 1260 | MA | National Grid, USA |  |  | 2015-12-01 | Greater Boston - North | Reconductor the F-158N 115kV line form Wakefield Jct - Maplewood and associated Maplewood Substation work |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No |  |  |  | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 5400000 | 5400000 | 6100000 | 6100000 | 6100000 | 6100000 | 6030000 | 6030000 | 6030000 | 6028295 | 6028295 | 6028295 | 6028295 | 6028295 | 6028295 | 6028295 | 6028295 | 6028295 | 6028295 | 6028295 | 6028295 | 6028295 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 0
Reliability Upgrade | 1a | 1259 | MA | National Grid, USA |  |  | 2013-02-01 | Salem Harbor Retirement | 115 kV line Reconductoring of the B154N/C-155N from King St Tap - South Danvers |  |  |  | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-07-28 | 2014-03-12 |  |  |  | 20000000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 0
Reliability Upgrade | 1a | 1258 | MA | National Grid, USA |  |  | 2014-02-01 | Salem Harbor Retirement | 115 kV line Reconductoring of the Y-151 from Tewksbury Junction - West Methuen |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-07-28 | 2017-12-01 |  |  |  | 11500000 | 14500000 | 14500000 | 21000000 | 18600000 | 18600000 | 18600000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 24250000 | 24250000 | 24250000 | 24250000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 0
Reliability Upgrade | 1a | 1257 | MA | National Grid, USA |  |  | 2013-08-01 | Salem Harbor Retirement | 115 kV line Reconductoring of the S-145/T-146 from Tewksbury-North Reading Tap |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/28/2011 3/7/2013 | 2014-03-12 |  |  |  | 29000000 | 29000000 | 29000000 | 10500000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 0
Reliability Upgrade | 1a | 1256 | MA | Unitil |  |  | 2012-06-01 | Flagg Pond Upgrades | At Flagg Pond Substation upgrade terminal equipment on the I-135, I-135S, J-136N and J-136S 115 kV lines and Zone 3 relay upgrades for the J-136N 115 kV line. |  |  |  | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR |  |  |  | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 0
Reliability Upgrade | 1a | 1255 | MA | CELD (Chicopee Electric Light Department) |  |  | 2014-01-01 | CELD 115/13.8 kV Substation | 115/13.8 kV substation on Memorial Dr. with two transformers and twelve feeders looped into 1904 (1723) line between Piper and Fairmont substations - includes .7 miles x 2 of transmission line construction (1638/1904 lines) |  |  |  | Concept | Concept | Proposed | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-10-09 | 2015-04-17 |  |  |  | TBD | TBD | 2900000 | 2900000 | 2900000 | 3800000 | 3800000 | 4000000 | 4386352 | 4386352 | 4386352 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 0
Reliability Upgrade | 1b | 1254 | MA | National Grid, USA |  |  | 2015-12-01 | Greater Boston - North | Substation work at Revere Substation to increase ratings on the 128-515P/168 line between Chelsea and Revere |  |  | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | No |  |  | TBD | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 0
Reliability Upgrade | 1a | 1253 | RI | National Grid, USA |  |  | 2017-03-01 |  | Chase Hill Substation 115/13 kV substation addition |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | in-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 6/7/2011 5/26/2015 | NR |  |  | 5000000 | 3000000 | 3000000 | 3000000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 2600000 | 2600000 | 2600000 | 3200000 | 3200000 | 3200000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 0
Reliability Upgrade | 1a | 1252 | RI | National Grid, USA |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | Re-conductor 345 kV 328 line (West Farnum-Sherman Rd) |  |  | Concept | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2012-05-04 | 2015-12-17 |  |  | TBD | 36500000 | 36500000 | 36500000 | 36500000 | 36500000 | 36500000 | 36500000 | 36500000 | 36500000 | 36200000 | 36200000 | 36200000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 0
Reliability Upgrade | 1a | 1251 | ME | Central Maine Power Company |  |  | 2015-05-01 | Lakewood Substation Expansion | Sectionalize Section 241 by adding four 115 kV circuit breakers at Lakewood Substation and install a second 115/34.5 kV transformer Construct 4 miles of new 115kV from the existing Section 83B Tap point to the Lakewood Substation & rebuild the existing 115kV Section 83B |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2011-04-21 | 2013-12-05 |  |  | 13700000 | 13700000 | 13700000 | 13700000 | 13700000 | 17506000 | 17506000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 0
Reliability Upgrade | 1b | 1250 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | VELCO LSP - West Rutland Substation | Installation of a 115/46 kV transformer at West Rutland between breakers K30 and K34 |  |  | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1249 | MA | Eversource |  |  | 2013-12-01 |  | Rebuild the Wareham Substation to a breaker and a half scheme |  |  | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1248 | MA | Eversource |  |  | 2014-12-01 |  | Rebuild the Kingston Substation to a breaker and a half scheme |  |  | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1247 | MA | Eversource |  |  | TBD |  | Rebuild the Acushnet 115 kV Substation |  |  | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 1246 | CT | United Illuminating Company |  |  | 2013-07-01 | SWCT | Reconfiguration of 115 kV (8300) line from Mill River to Quinnipiac |  |  | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2/3/2012 1/18/21013 | 2012-09-20 |  |  | 17400000 | 17400000 | 18800000 | 18000000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 0
Reliability Upgrade | 1a | 1245 | CT | CMEEC |  |  | 2015-11-01 | NEEWS | Sag elimination on 1410 Line (Montville-Buddington) |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2011-06-09 | NR |  |  | 60000 | 60000 | 60000 | 60000 | 60000 | 390150 | 390150 | 390150 | 390150 | 390150 | 390150 | 390150 | 450000 | 533000 | 454162 | 454162 | 454162 | 454162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 0
Reliability Upgrade | 1a | 1244 | CT | CMEEC |  |  | 2012-04-01 | 115kV Circuit Breaker Installation | Install 115 kV Bus Tie Circuit Breaker at Stock House Rd Substation |  |  | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-02-14 | NR |  |  | 750000 | 750000 | 750000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 0
Reliability Upgrade | 1a | 1243 | CT | CMEEC |  |  | 2013-10-01 | TTD's Fitch St 115 kV Substation | TTD 115/27 kV substation with two transformers and a 115kV circuit breaker looped into 1416 line (between Compo and Darien substations) |  |  | Concept | Concept | Concept | Concept | Concept | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/17/2012 | 2015-08-04 |  |  | TBD | TBD | TBD | TBD | TBD | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 0
Reliability Upgrade | 1a | 1242 | CT | CMEEC |  |  | 2014-05-01 | SNEW 115kV Substation | SNEW 115/13.8 kV substation with two transformers and a 115kV circuit breaker looped into the 1890 line (between Sherwood Substation - Ely Ave Jct) |  |  | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 1/17/2012 12/7/2012 | NR |  |  | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reliability Upgrade | 1a | 1241 | RI | National Grid, USA |  |  | 2015-06-01 |  | Reconductor G-185S (Kent County - Davisville Tap) |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2010-12-27 | 2016-02-17 |  | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 0
Generator Interconnection Upgrade | 2a | 1240 | MA | Eversource |  |  | 2015-04-01 | Pioneer Valley Energy Center (PVEC) | Upgrade the substation conductor, manual switch, wave trap, primary and back up relays and metering at Buck Pond substation for the 1657 (Buck Pond - Southampton Jct.) line terminal to match or exceed the conductor ratings. |  | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2010-10-20 | NR |  | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1239 | MA | Eversource |  |  | 2015-04-01 | Pioneer Valley Energy Center (PVEC) | Upgrade the substation conductor, manual switch, wave trap, primary and backup relays and metering at Buck Pond 34B substation for the 1302 (Buck Pond - QP236) line terminal to match or exceed the conductor ratings |  | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2010-10-20 | NR |  | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1238 | MA | Eversource |  |  | 2015-04-01 | Pioneer Valley Energy Center (PVEC) | Upgrade the substation conductor, manual switch, wave trap, Watt/VAR transducer inside breaker 16C-35T-2 control cabinet, primary and backup relays and metering at Agawam 16C substation for the 1302 (Agawam - Pochassic tap) line terminal to match or exceed the conductor ratings. |  | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2010-10-20 | NR |  | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1237 | MA | Eversource |  |  | 2015-04-01 | Pioneer Valley Energy Center (PVEC) | Upgrade Fairmont 16H switching station to be NPCC Bulk Power System (BPS) compliant by adding a second DC system |  | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2010-10-20 | NR |  | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1236 | MA | Eversource |  |  | 2015-04-01 | Pioneer Valley Energy Center (PVEC) | Install an NPCC type III SPS at the PVEC substation to monitor flow in (Southampton Jct. - Ingleside) section of 1657 line. |  | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2010-10-20 | NR |  | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1235 | CT | Eversource |  |  | 2012-11-01 | NEEWS | Sag elimination on 1410 Line (Montville-Buddington) |  | Proposed | Proposed | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-06-09 | NR |  | 3500000 | 3500000 | 3000000 | 3000000 | 3000000 | 3000000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 0
Reliability Upgrade | 1a | 1234 | RI | National Grid, USA |  |  | 2014-09-01 | NEEWS (Interstate Reliability Project) | West Farnum Substation 115 kV upgrades |  | Concept | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-05-04 | 2015-12-17 |  | TBD | TBD | TBD | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 0
Reliability Upgrade | 1a | 1233 | RI | National Grid, USA |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | New Sherman Road 345 kV AIS Substation |  | Concept | Concept | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2012-05-04 | 2015-12-17 |  | TBD | TBD | 36600000 | 36600000 | 36600000 | 36600000 | 36600000 | 36600000 | 36600000 | 36600000 | 36600000 | 38685000 | 38685000 | 38685000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 0
Elective Upgrade | 4b | 1231 | NH | Eversource |  |  | 2017-06-01 | Queue Position 348 | 1200 MW HVDC connection (Des Cantons-Franklin) with 345 kV connection (Franklin-Deerfield) |  | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-12-31 | NR |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 1230 | CT | Eversource |  |  | 2013-12-01 | LSP - NE Simsbury Breaker Addition | 115 kV breaker addition at Northeast Simsbury Substation |  | Concept | Concept | Concept | Concept | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-03-30 | 2014-12-09 |  | TBD | TBD | TBD | TBD | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 0
Reliability Upgrade | 1a | 1229 | CT | Eversource |  |  | 2014-12-01 | Asset Replacement | Replace 115 kV 1990 line lattice structures Frost Bridge to Stevenson |  | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-01-18 | 2015-09-25 |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 70000000 | 63000000 | 63000000 | 63000000 | 67800000 | 67800000 | 68500000 | 68500000 | 68500000 | 68500000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 0
Reliability Upgrade | 1a | 1228 | CT | Eversource |  |  | 2014-11-01 | SWCT | Install new 1.8 mile, 115 kV cable between Glenbrook and Southend Substation and associated substation work at both stations |  | Concept | Concept | Concept | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-07-17 | 2016-05-12 |  | TBD | TBD | TBD | 46000000 | 46000000 | 46000000 | 47000000 | 47000000 | 47000000 | 47000000 | 47000000 | 41500000 | 37000000 | 37000000 | 36701000 | 36701000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 0
Reliability Upgrade | 1a | 1227 | CT | Eversource |  |  | 2012-10-01 | LSP - Stamford Area | Add 4th transformer and build a five breaker ring bus at South End Substation |  | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-06-09 | 2014-12-09 |  | 9100000 | 9100000 | 6400000 | 6400000 | 6400000 | 6400000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 0
Reliability Upgrade | 1a | 1226 | MA | Eversource |  |  | 2016 | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115 kV line and terminal work at Woodland substation. |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 12/7/2012 1/26/2016 | No |  | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | #VALUE!
Reliability Upgrade | 1a | 1225 | MA | Eversource |  |  | 2016-11-01 | Pittsfield / Greenfield Project | Rebuild the Cumberland to Montague 1361/1242 115 kV double circuit line and terminal work at Cumberland and Montague. At Montague substation, reconnect Y177 115 kV line into 3T/4T position, and perform other associated substation work |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 12/7/2012 1/26/2016 | 2016-02-11 |  | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | #VALUE!
Reliability Upgrade | 1a | 1224 | MA | Eversource |  |  | 2015-12-01 | Pittsfield / Greenfield Project | Install 115 kV 14.4 MVAR capacitor banks at Cumberland, Podick and Amherst Substations |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2012-12-07 | 2016-02-11 |  | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | #VALUE!
Reliability Upgrade | 1a | 1223 | MA | Eversource |  |  | 2017-06-01 | Pittsfield / Greenfield Project | Build a new 115 kV line from Northfield Mountain to the new Erving Switching Station |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-12-07 | 2016-02-11 |  | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | #VALUE!
Reliability Upgrade | 1a | 1222 | MA | Eversource |  |  | 2017-03-01 | Pittsfield / Greenfield Project | Build a new 115 kV three breaker Switching Station (Erving) ring bus |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-12-07 | 2016-02-11 |  | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | #VALUE!
Reliability Upgrade | 1a | 1221 | MA | Eversource |  |  | 2017-06-01 | Pittsfield / Greenfield Project | Modify Northfield Mountain 16R substation and install a 345/115 kV autotransformer |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-12-07 | 2016-02-11 |  | 108500000 | 108500000 | 108500000 | 108500000 | 108500000 | 108500000 | 109500000 | 109500000 | 109500000 | 113400000 | 113400000 | 113400000 | 113400000 | 113400000 | 113400000 | 113400000 | 113400000 | 113400000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 0
Reliability Upgrade | 1a | 1220 | NH | Eversource |  |  | 2017-12-01 | Greater Boston - North | Install a new 345 kV (3124) circuit between Scobie and Hudson NH (this is Eversource's portion of the new Scobie-Tewksbury circuit) |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No |  | 40100000 | 40100000 | 40100000 | 40100000 | 40100000 | 40100000 | 40100000 | 40100000 | 40100000 | 40100000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 0
Reliability Upgrade | 1a | 1219 | NH | Eversource |  |  | 2011-12-01 |  | Install 115 kV two 13.3 MVAR capacitor banks at Oak Hill substation |  | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-02-28 | NR |  | 3800000 | 3800000 | 4000000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 0
Reliability Upgrade | 1a | 1218 | CT | Eversource |  |  | 2013-03-01 | Millstone 345kV Circuit Separation project & SLOD SPS System Retirement | Separate the 345 kV Double Circuit Tower 310/348 and 371/383 configuration and disable the SLOD SPS scheme. |  | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-11-02 | 2013-07-26 |  | 22000000 | 25600000 | 25600000 | 27200000 | 27200000 | 27200000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 0
Reliability Upgrade | 1a | 1217 | MA | Eversource |  |  | 2014-10-01 | Central/Western Massachusetts Upgrades - Group 4 - E. Longmeadow Projects | 1515 Line work and substation work at Ludlow (MA) associated with the new Hampden (MA) substation project (NGRID) |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2016-10-04 |  | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 0
Reliability Upgrade | 1a | 1216 | MA | Eversource |  |  | 2012-04-01 |  | 345 kV Ludlow - Northfield (portion of 354) Line Structure replacements |  | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2015-04-17 |  | 17000000 | 17000000 | 25100000 | 25100000 | 25100000 | 25100000 | 25100000 | 25100000 | 25100000 | 25100000 | 25100000 | 25100000 | 25100000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 0
Reliability Upgrade | 1b | 1215 | MA | National Grid, USA |  |  | 2015-12-01 | Greater Boston - North | New 115 kV line between Wakefield - Everett |  | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 0
Reliability Upgrade | 1a | 1214 | MA | National Grid, USA |  |  | 2013-07-01 | Greater Boston - South | Line reconductoring of the C-129N Beaver Pond - Depot St. Tap) and D-130 (Depot St. Tap - Medway) 115 kV lines |  | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-10-26 | No |  | 500000 | 500000 | 500000 | 500000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 0
Reliability Upgrade | 1a | 1213 | MA | National Grid, USA |  |  | 2017-12-01 | Greater Boston - North | Install new 345 kV (3124) circuit between NH/MA border and Tewksbury (this is the MA portion of NGRID's portion of the new Scobie-Tewksbury circuit) and associated substation work at Tewksbury |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No |  | 23370000 | 23370000 | 23370000 | 23370000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 86027382 | 86027382 | 86027382 | 86027382 | 86027382 | 86027382 | 86027382 | 86027382 | 86027382 | 83285224 | 83285224 | 83285224 | 83285224 | 83285224 | 83285224 | 83285224 | 83285224 | 83285224 | 83285224 | 83285224 | 83285224 | 83285224 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 0
Reliability Upgrade | 1a | 1212 | MA | National Grid, USA |  |  | 2016-12-01 | Greater Boston - North | 115 kV Line Reconductoring of M-139 between Tewksbury-Billerica Tap and associated work at Tewksbury |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No |  | 57000000 | 57000000 | 11600000 | 11600000 | 12150000 | 12150000 | 12150000 | 12150000 | 12150000 | 12150000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | #VALUE!
Reliability Upgrade | 1b | 1211 | MA | National Grid, USA |  |  | 2017-12-01 | Greater Boston - North | Install 2nd 345 kV circuit between Tewksbury - Billerica/Burlington Town Line (NSTAR Border) and associated substation work at Tewksbury |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  | 32700000 | 32700000 | 32700000 | 32700000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 0
Reliability Upgrade | 1a | 1210 | VT | National Grid, USA |  |  | 2017-11-01 | Pittsfield / Greenfield Project | Harriman Station - Installation of 115 kV tie breaker with associated buswork, reconductor of buswork and new control house. |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-12-07 | 2017-07-17 |  | 1100000 | 1100000 | 1100000 | 5000000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 0
Reliability Upgrade | 1a | 1209 | MA | National Grid, USA |  |  | 2015-04-01 | Pittsfield / Greenfield Project | Reconductoring of A127 between Erving and Cabot Tap with 2-477 ACCR includes switch replacements at Wendell Depot |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-12-07 | 2017-07-17 |  | 12000000 | 12000000 | 12000000 | 12000000 | 8760000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 0
Reliability Upgrade | 1a | 1208 | MA | National Grid, USA |  |  | 2017-03-01 | Pittsfield / Greenfield Project | Separation and reconductoring of Cabot Taps (A-127 and Y-177 115kV lines). This involves 795 ACSS for the Y-177 line and 1590 ACSS for the A-127 tap. |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-12-07 | 2017-07-17 |  | 7400000 | 7400000 | 7400000 | 7400000 | 10500000 | 13100000 | 13100000 | 13100000 | 13100000 | 12580000 | 12580000 | 12970000 | 12970000 | 12970000 | 12970000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 0
Reliability Upgrade | 1a | 1207 | MA | Eversource | Belmont Municipal Light Department |  | 2016-12-01 | Blair Pond Substation Project | Build a new 115kV Substation, the Blair Pond Substation Facilities being constructed by Belmont Municipal Light Department |  | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 71103000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 0
Reliability Upgrade | 1b | 1206 | MA | Eversource |  |  | 2011-12-01 |  | Install a new 230 kV breaker for line 282-602 (West Medway-Waltham) at W. Medway for system restoration |  | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1205 | MA | Eversource |  |  | 2013-12-01 | Mid-Cape Reliability Project | Separate 120 (Canal-Barnstable) /122 (Oak St-Barnstable) DCT |  | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1204 | MA | Eversource |  |  | 2013-06-01 |  | Rebuild the Mashpee Substation to a Ring Bus and install an overvoltage trip relay on the Mashpee 115 kV Capacitor Bank |  | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  | TBD | TBD | TBD | 13000000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1203 | MA | Eversource |  |  | TBD |  | Build a new 115kV switching facility at Mendall Road on line 112 |  | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 1202 | MA | Eversource |  |  | 2014-12-01 | NEEWS | Rebuild 1.2 mile length of line 336 with 2-900 ACSS conductor and replace 5, 345 kV 2000 amp disconnect switches with 3000 amp switches at W. Medway station |  | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-03-30 | NR |  | 2200000 | 1700000 | 1700000 | 1700000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 0
Reliability Upgrade | 1a | 1201 | MA | Eversource | National Grid, USA |  | 2012-12-01 | Greater Boston - North | 115 kV line Reconductoring of the P168/128-518 Line between Chelsea and Revere (NSTAR Portion of the line) |  | Proposed | Proposed | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-06-07 | No |  | 1200000 | 800000 | 1500000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 0
Reliability Upgrade | 1b | 1200 | MA | Eversource |  |  | 2017-12-01 | Greater Boston - North | Add a new 345 kV UG circuit between Woburn and North Cambridge |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 0
Reliability Upgrade | 1a | 1199 | MA | Eversource |  |  | 2017-12-01 | Greater Boston - Western Suburbs | Install a new 230/115 kV autotransformer at Sudbury Loop 230 kV line 282-602 in and out of a new 230 kV switchyard at Sudbury |  | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2015-07-23 | No |  | TBD | TBD | TBD | 23500000 | 23500000 | 23500000 | 23500000 | 23500000 | 23500000 | 25000000 | 28100000 | 28100000 | 28100000 | 28100000 | 28100000 | 28100000 | 34920000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 0
Reliability Upgrade | 1b | 1198 | MA | Eversource |  |  | 2017-12-01 | Greater Boston - Western Suburbs | Add a 115 kV line from Woburn to Hartwell Ave |  | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  | TBD | TBD | TBD | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 0
Reliability Upgrade | 1a | 1197 | ME | Emera Maine |  |  | 2013-12-01 | Keene Rd Autotransformer | Orrington 345 kV Series Breaker Addition |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-10-22 | 2011-06-16 |  | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 0
Reliability Upgrade | 1a | 1196 | ME | Bangor Hydro-Electric Company |  |  | 2012-01-01 | SVC Filter Upgrade (Part of Keene Rd Auto-transformer ID 144) | Upgrade of filter bank at Chester SVC facility |  | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-07-15 | 2011-07-15 |  | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 0
Reliability Upgrade | 1a | 1195 | VT | Vermont Electric Power Company |  |  | 2012-11-01 | Highgate Refurbishment | Replace Highgate controls and cooling system |  | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2011-08-09 |  | 38400000 | 35600000 | 35600000 | 35600000 | 35600000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 0
Reliability Upgrade | 1a | 1194 | VT | Vermont Electric Power Company |  |  | 2012-09-01 | VELCO LSP Jay Substation | Construct a new 4-breaker ring substation at Jay with two 115/46 kV transformers |  | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-02-07 | 2012-03-07 |  | 6500000 | 6500000 | 6500000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 0
Reliability Upgrade | 1a | 1193 | CT | United Illuminating Company |  |  | 2013-01-01 |  | North Haven 115 kV Capacitor Bank TRV Mitigation Project |  | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR |  | 4100000 | 5100000 | 4900000 | 4900000 | 4900000 | 4900000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 0
Reliability Upgrade | 1a | 1192 | VT | Vermont Electric Power Company |  |  | 2011-01-01 | Essex Switch Closing | Operate the Essex #230 115 kV switch normally closed. | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-11-02 | NR | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 0
Reliability Upgrade | 1a | 1191 | MA | Eversource |  |  | 2012-12-01 |  | Rebuild Section of Line 322 (Canal-Carver) | Concept | Concept | Concept | Concept | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 11700000 | 12200000 | 12200000 | 12200000 | 13000000 | 13000000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 0
Reliability Upgrade | 1b | 1190 | MA | Eversource |  |  | 2017-12-01 | Greater Boston - North | Install a second 345/115 kV autotransformer and 345 kV and 115 kV switchgear and breakers at Woburn | Concept | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 0
Reliability Upgrade | 1b | 1189 | MA | Eversource |  |  | 2015-12-01 | Greater Boston - Central | Install 3rd 115 kV Circuit between Waltham and Brighton | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Generator Interconnection Upgrade | 2a | 1188 | MA | Eversource |  |  | 2015-06-01 | Cape Wind | Reconductor/Rebuild Brook Street-Kingston Line #117 | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1187 | MA | National Grid, USA |  |  | 2015-04-01 | A127/B128 Conductor Refurbishment | A127/B128 Conductor Refurbishment - Tower 510 to Harriman Substation, VT | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 01/20/2011 | 2011-12-16 | 65000000 | 65000000 | 65000000 | 65000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 0
Generator Interconnection Upgrade | 2a | 1186 | CT | United Illuminating Company |  |  | 2011-06-01 | New Haven Peaking Plant 2-4 | New Haven Harbor Peaking Plant - West River 115 kV series breaker additions | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-06-03 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1185 | CT | United Illuminating Company |  |  | 2012-05-01 | New Haven Peaking Plant 2-4 | New Haven Harbor Peaking Plant - Transmission generator lead & new 115 kV breakers | Concept | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-11-22 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1184 | ME | Central Maine Power Company |  |  | 2012-11-01 | Starks Switching Station | Add 4-115 kV circuit breakers in a breaker-and a-half configuration on Section 63 and 2-18 MVAR cap banks at a new Starks Switching Station | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-09-28 | 2011-03-25 | 10750000 | 10750000 | 10750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 0
Reliability Upgrade | 1a | 1183 | NH | Eversource |  |  | 2016-06-01 | LSP New Peaslee Substation and 115/34.5 kV transformer | New 115 kV Peaslee Substation with a five 115 kV breaker ring bus configuration. New 115 kV lines to supply a new Unitil substation and the existing Kingston Substation | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2014-02-11 | 2015-11-05 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 34000000 | 28200000 | 28200000 | 28200000 | 28200000 | 28200000 | 28200000 | 28200000 | 26900000 | 26900000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 0
Reliability Upgrade | 1a | 1182 | NH | Eversource |  |  | 2012-12-01 | LSP New Eagle Substation and 115/34.5 kV transformer | New 115 kV Eagle Substation connected to 115/34.5 kV Thornton Substation | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-07-27 | 2012-02-20 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 0
Reliability Upgrade | 1b | 1181 | MA | Eversource |  |  | 2013-12-01 |  | Rebuild the High Hill 115 kV Substation to a Breaker and a half design | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1180 | MA | Eversource |  |  | 2013-12-01 |  | Install an over voltage trip relay on the Mashpee 115 kV Capacitor Bank | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1179 | MA | Eversource |  |  | 2017-12-01 | Greater Boston - North | Install 2nd 345 kV circuit between Bellerica/Burlington town line to Woburn (NSTAR portion of new Tewksbury -Woburn 345 kV line) | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 0
Reliability Upgrade | 1b | 1178 | MA | Eversource |  |  | 2015-12-01 | Greater Boston - North | Install 115 kV Capacitor Bank at North Woburn | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1177 | MA | Eversource |  |  | 2015-12-01 | Greater Boston - North | Reconductor 211-503/504 from North Woburn Tap to Reading | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1176 | MA | Eversource |  |  | TBD | Greater Boston - Central | Install an oil circulation pipe and heat exchangers at K Street and Chatham Street sections of 250-516/517 circuits | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1175 | MA | Eversource |  |  | 2014-05-01 | Greater Boston - South | Upgrade the 115 kV line 201-501 (Medway-Depot St.) and the 201-502 (Beaver Pond - Depot Street Tap) to a higher capacity line | Concept | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service |  | 2011-10-26 | No | TBD | 3700000 | 3700000 | 3700000 | 4110000 | 4110000 | 4110000 | 4110000 | 4110000 | 4110000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 4550000 | 4550000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 0
Reliability Upgrade | 1b | 1174 | MA | Eversource |  |  | 2013-12-01 | Greater Boston Reliability Project | Upgrade the 115 kV line 211-514 to a higher capacity line | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1172 | VT | Vermont Electric Power Company |  |  | 2013-03-01 | Vermont Shunt Reactors | Install 345 kV 60 MVAR shunt reactors (two at Coolidge and one at New Haven and relocate the New Haven reactor to Vernon) to address high voltage concerns | Concept | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-03-23 | 2012-12-13 | 20000000 | 26700000 | 20000000 | 20000000 | 20000000 | 20000000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 0
Reliability Upgrade | 1a | 1171 | VT | Vermont Electric Power Company |  |  | 2011-12-01 | West Rutland Capacitor Rebuild | Install two 115 kV 25 MVAR capacitor banks at West Rutland to address low voltage concerns | Proposed | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-11-02 | NR | 2500000 | 2400000 | 2400000 | 2400000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 0
Reliability Upgrade | 1a | 1170 | VT | Vermont Electric Power Company | Green Mountain Power |  | 2013-11-01 | Bennington Substation Rebuild | Rebuild the exiting Bennington substation 115 kV bus into a ring bus to address reliability problems due to breaker failure contingencies | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-11-22 | 2013-12-05 | 20000000 | 23000000 | 23000000 | 28000000 | 19200000 | 19200000 | 19200000 | 19200000 | 19200000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 0
Reliability Upgrade | 1a | 1169 | VT | Vermont Electric Power Company |  |  | 2013-08-01 | Ascutney Substation Rebuild | Rebuild the existing Ascutney substation 115 kV bus into a ring bus, to address reliability problems due to breaker failure contingencies | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-11-22 | 2012-12-13 | 22000000 | 14500000 | 14500000 | 14500000 | 18000000 | 18000000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 0
Reliability Upgrade | 1a | 1168 | MA | Holyoke Gas & Electric |  |  | 2012-12-01 | North Canal 44P | Loop the 1525 (Holyoke Fairmont South 115 kV) line into the new North Canal 44P Substation. | Concept | Concept | Proposed | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-05-25 | NR | TBD | TBD | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 0
Reliability Upgrade | 1a | 1167 | MA | Northeast Utilities - NSTAR |  |  | 2010-12-01 |  | Replace three 40 kA 115 kV circuit breakers at Carver with 63 kV breakers | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 1000000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 0
Reliability Upgrade | 1a | 1166 | MA | Northeast Utilities - NSTAR |  |  | 2010-12-01 |  | Terminal upgrades at W. Walpole and W, Medway for #325 line | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 1200000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 0
Reliability Upgrade | 1a | 1165 | MA | Eversource |  |  | 2012-11-01 | Mystic Breaker Additions Project | Move Transformer 110B Connection at Mystic | Planned | Planned | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-03-10 | NR | 1700000 | 1700000 | 1900000 | 2600000 | 2600000 | 2600000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 0
Elective Upgrade | 4b | 1164 | ME | Central Maine Power Company | Emera Maine |  | 2016-12-01 | Queue Position 502 | 345 kV Tie Phase 1: 200 MW Houlton, ME to MEPCO 396 Line and Phase 2: MEPCO 396 Line to Bridgewater, ME | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1163 | ME | Maine Electric Power Company |  |  | TBD | Queue Position 322 | 345 kV Tie Line - between Houlton, ME and MEPCO Line | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Elective Upgrade | 4b | 1161 |  | United Illuminating Company |  |  | TBD | Queue Position 271 | 1000 MW HVDC between Hertel, QC or Clay NY and Singer, CT | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1160 | ME | Central Maine Power Company |  |  | 2017-03-01 | Queue Position 278 | 1000 MW HVDC between Maine Yankee, ME and South Boston, MA | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Generator Interconnection Upgrade | 2a | 1159 | ME | Central Maine Power Company |  |  | 2011-11-01 | Queue Position 197 | Add a new 115 kV breaker and new 115 kV line termination at the former T2 position at Rumford 115 kV substation | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-09-29 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1158 | ME | Central Maine Power Company |  |  | 2014-07-01 | Maine Power Reliability Program (MPRP) | Two 40 MVAR reactors at Albion Road, two 40 MVAR reactors at Larrabee Road, two 40 MVAR at Coopers Mills | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1157 | ME | Bangor Hydro-Electric Company |  |  | 2011-03-01 |  | Bangor Hydro Synchrophasors | Concept | Concept | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | No | NR | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 0
Reliability Upgrade | 1a | 1156 | ME | Bangor Hydro-Electric Company |  |  | 2012-04-01 | Maine Power Reliability Program (MPRP) | Orrington Shunt Cap Reconfiguration | Concept | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-10-22 | 2011-06-16 | TBD | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 0
Reliability Upgrade | 1a | 1155 | ME | Bangor Hydro-Electric Company |  |  | 2013-06-01 | Maine Power Reliability Program (MPRP) | Capacitor Bank Addition (10 MVAR at Trenton 34.5 kV and Epping) | Concept | Concept | Concept | Concept | Concept | Concept | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-10-22 | 2011-06-16 | TBD | TBD | TBD | TBD | TBD | TBD | 650000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 0
Reliability Upgrade | 1a | 1154 | ME | Emera Maine |  |  | 2013-12-01 | Maine Power Reliability Program (MPRP) | Rerate Line 66 | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 10/22/2010 1/18/2013 | 2013-01-09 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 17500000 | 17500000 | 17500000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 0
Reliability Upgrade | 1b | 1153 | MA | Eversource |  |  | 2012-12-01 | Boston Area 115 kV Enhancements | Add a new 115 kV breaker on the West Framingham end of the 455-507 line such that 110B transformer is isolated from any faults on the 455-507 line | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 0
Reliability Upgrade | 1a | 1152 | MA | National Grid, USA |  |  | 2010-08-01 |  | Bear Swamp - Pratts Junction 230 kV Line Refurbishment Project (E205E) | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 0
Reliability Upgrade | 1a | 1151 | CT | United Illuminating Company |  |  | 2011-06-01 |  | West River 115 kV Switching Station Fault Duty Mitigation | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 3800000 | 3800000 | 3500000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 0
Reliability Upgrade | 1a | 1150 | CT | United Illuminating Company |  |  | 2010-12-01 |  | Grand Avenue - West River 115 kV Pumping Plant Replacements | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 3000000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 0
Generator Interconnection Upgrade | 2a | 1149 | CT | Northeast Utilities |  |  | 2010-07-01 | GENCONN Devon | Four units connected at Devon Substation | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2007-12-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1148 | CT | Eversource |  |  | 2011-05-01 |  | Add a 2nd high speed relay on the Glennbrook to Waterside 115 kV 1440 | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-09-29 | NR | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | #VALUE!
Reliability Upgrade | 1a | 1147 | CT | Eversource |  |  | 2011-07-01 |  | Waterside Substation - install a three-breaker 115 kV ring bus | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-09-29 | NR | 5055000 | 5055000 | 5055000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 0
Reliability Upgrade | 1a | 1146 | VT | Vermont Electric Power Company |  |  | 2010-12-01 | Lyndonville Project | Installation of a 4-breaker ring 115 kV substation consisting of two 115 kV 12.5 MVAR capacitor banks and 115/34.5 kV transformer interconnecting to the Irasburg - St. Johnsbury 115 kV line | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-06-01 | 2010-05-17 | 9000000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 0
Reliability Upgrade | 1a | 1145 | VT | Vermont Electric Power Company |  |  | 2010-12-01 | Burlington Gorge Project | Installation of a 3-breaker 115 kV ring substation and 115/34. 5 kV transformer on the East Ave. - Tafts Corners 115 kV line | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 10/24/2006 | 2010-05-17 | 12100000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 0
Reliability Upgrade | 1a | 1144 | ME | Central Maine Power Company |  |  | 2010-09-01 | Heywood Road Project | Circuit Switcher replacements at Detroit, Lakewood, Rice Rips and Winslow | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-03-20 | 2009-07-20 | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | #VALUE!
Reliability Upgrade | 1a | 1143 | NH | Eversource |  |  | 2011-06-01 |  | Littleton 115 kV breaker addition and reconfiguration | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-10-20 | 2011-04-14 | 6590000 | 6590000 | 6590000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 0
Reliability Upgrade | 1a | 1142 | NH | New Hampshire Transmission, LLC |  |  | 2011-04-01 |  | Seabrook 345 kV Station Reconfiguration and 345 kV Circuit Breaker Additions | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-11-20 | 2012-06-22 | TBD | TBD | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 0
Reliability Upgrade | 1a | 1141 | NH | Eversource |  |  | 2013-12-01 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-06-29 | 2011-07-15 | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | #VALUE!
Reliability Upgrade | 1a | 1140 | NH | Eversource |  |  | 2011-10-01 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115 kV C129 Line | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-06-29 | 2011-07-15 | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | #VALUE!
Reliability Upgrade | 1a | 1139 | MA | Northeast Utilities |  |  | 2010-10-01 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115 kV M183 Line | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-06-29 | 2011-07-15 | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | #VALUE!
Reliability Upgrade | 1a | 1138 | NH | Northeast Utilities |  |  | 2010-12-01 | 2nd Deerfield 345/115kV Autotransformer Project | Rebuild 115 kV L175 line | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-06-29 | 2011-07-15 | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | #VALUE!
Reliability Upgrade | 1a | 1137 | NH | Eversource |  |  | 2011-04-01 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115 kV breakers and add 1-115 kV breaker at Deerfield Substation | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-06-29 | 2011-07-15 | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | #VALUE!
Reliability Upgrade | 1b | 1136 |  | National Grid, USA |  |  | 2012-12-01 |  | New 115kV Switching Station at Devens Convert 69kV lines to 115kV, Reconfigure 115kV Supply at Ayer Substation | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2009-07-28 | No | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 0
Reliability Upgrade | 1a | 1135 | ME | Central Maine Power Company |  |  | 2012-04-01 | CMP-Athens Substation LSP | Add two 115 kV circuit breakers on Section 66; and 115/12 kV transformer | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2007-12-21 | NR | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 0
Reliability Upgrade | 1a | 1133 | ME | Central Maine Power Company |  |  | 2012-04-01 | CMP-LSP Leeds Substation | Add 115/34 kV Leeds Substation and new 34 kV line from Leeds to Turner | Proposed | Proposed | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | No | NR | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 0
Reliability Upgrade | 1a | 1132 | ME | Central Maine Power Company |  |  | 2014-08-01 | Maine Power Reliability Program (MPRP) | Add 115/12 kV transformer at Coopers Mills | Proposed | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/08 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1131 | ME | Central Maine Power Company |  |  | 2011-11-01 | CMP-LSP Bowman St. Substation | Add 115/34 kV transformer | Proposed | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-11-22 | NR | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 0
Reliability Upgrade | 1b | 1130 |  | Central Maine Power Company |  |  | 2011-12-01 | Sturtevant Improvements | Add 115 kV circuit breakers & 25 MVAR capacitor bank at Sturtevant Substation; Re-rate Section 63 between Wyman Hydro & Madison Substation | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2009-07-28 | No | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 0
Reliability Upgrade | 1a | 1129 | ME | Central Maine Power Company |  |  | 2012-06-01 |  | New 115 kV line between Wyman Hydro and Rice Rips Tap, parallel to exiting Section 83. Install a 115 kV circuit breaker at Wyman Hydro termination | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-01-26 | 2010-12-28 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 0
Reliability Upgrade | 1a | 1128 | ME | Central Maine Power Company |  |  | 2010-11-01 | CMP-LSP Hotel Road Substation | Add 115/34kV transformer with 115 kV breaker at Hotel Rd. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-08-20 | NR | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 0
Generator Interconnection Upgrade | 2b | 1125 | CT | Eversource |  |  | TBD | Queue Position 240 | 345 kV on Montville Substation | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1124 | CT | Eversource |  |  | 2014-12-01 | Meriden Gas Turbine | Three breaker 345 kV ring bus splitting the 3754 line from Southington to Beseck | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2010-03-23 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1123 | MA | Eversource |  |  | 2015-04-01 | Pioneer Valley Energy Center (PVEC) | Installation of new four breaker 115 kV switching station in a ring bus configuration for PVEC and loop line 1302 (between Buck Pond and Pochassic Tap) into the new switching substation and terminate to establish new lines from Buck Pond 34B substation to PVEC switching station (length approximately 1.0 mile) and from Pochassic substation tap to PVEC switching station (length approximately 2.12 miles) | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1122 | CT | Eversource |  |  | 2012-03-01 | Queue Position 191 | One turbine connected to #1238 Line (Frost Bridge to Carmel) via a new 3-breaker ring bus Substation | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2009-02-24 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1121 | CT | Eversource |  |  | 2011 | Middletown 12-15 | Four units connected to 384 line through a new 345 kV Substation: unit #4 will also connect to Substation | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-12-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1119 | MA | Northeast Utilities - NSTAR |  |  | 2010-04-01 | Greater Boston Reliability Project | Upgrade West Medway-West Walpole 345 kV line #325 | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | NR | NR | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 0
Reliability Upgrade | 1a | 1118 | MA | National Grid, USA | Eversource |  | 2013-05-01 | Long Term Lower SEMA Upgrades | Upgrade 115 kV line D21 (Bellrock-High Hill) | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 07/2011 | 2014-09-08 | TBD | Part of Long Term Lower SEMA | 6000000 | 6000000 | 6000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 0
Reliability Upgrade | 1a | 1116 | ME | Bangor Hydro-Electric Company |  |  | 2011-12-01 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-10-22 | 2011-06-16 | 37126000 | 37126000 | 37126000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 0
Reliability Upgrade | 1a | 1114 | CT | Eversource |  |  | 2017 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R Substation expansion - Add a 345/115 kV autotransformer. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 9/24/2008 5/4/2012 | No | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | #VALUE!
Reliability Upgrade | 1a | 1113 | VT | Northeast Utilities - NSTAR |  |  | 2010-12-01 |  | Install 115 kV Breaker #31 at K St. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-12-15 | NR | 2200000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 0
Reliability Upgrade | 1a | 1112 | CT | United Illuminating Company |  |  | 2011-02-01 |  | Water Street 115 kV circuit breaker and switch replacements. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 2840000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 0
Reliability Upgrade | 1a | 1111 | CT | United Illuminating Company |  |  | 2011-11-01 |  | Union Avenue 115/26.4 kV Substation | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 1/7/2009 12/16/2011 | 2009-11-10 | 10543000 | 10543000 | 10543000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 0
Reliability Upgrade | 1a | 1110 | CT | United Illuminating Company |  |  | 2010-12-01 |  | Broadway 115/13.8 kV Substation Addition | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-12-08 | NR | 1300000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 0
Reliability Upgrade | 1a | 1109 | MA | National Grid, USA |  |  | 2011-12-01 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115 kV terminal equipment upgrades | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2015-12-17 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 0
Generator Interconnection Upgrade | 2a | 1108 | CT | Eversource |  |  | 2013-06-01 | Towantic Energy | Installation of a 2.5% series reactor on the 1990S Line at the new substation. | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-26 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1107 | CT | Eversource |  |  | 2013-06-01 | Towantic Energy | Interconnection to new 115 kV substation consisting of (14) circuit breakers in a breaker and a half configuration that sectionalizes the existing 1575, 1585, and 1990 lines. | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-26 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1106 | RI | National Grid, USA |  |  | 2012-05-01 | NEEWS (Rhode Island Reliability Project) | Kent County Substation Upgrades related to third 345/115 kV autotransformer. | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 5/4/2012 | 2015-12-17 | Part of $99,900,000 above | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 0
Reliability Upgrade | 1a | 1105 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV line 1601, Fairmont to Shawinigan and add a 2nd High Speed Protection | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1104 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV 1803, Fairmont to Cadwell | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1103 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV line 1702 Fairmont t to Chicopee | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1102 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV line 1904, Fairmont to Piper | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1101 | MA | Eversource |  |  | 2012-10-01 | NEEWS (Greater Springfield Reliability Project) | Reconductor 115 kV line 1552, Ludlow to Orchard | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1100 | MA | Eversource |  |  | 2012-01-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV line 1314, Agawam to Chicopee | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1099 | RI | National Grid, USA |  |  | 2012-05-01 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115 kV terminal equipment upgrades | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2015-12-17 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 0
Reliability Upgrade | 1a | 1098 | MA | National Grid, USA |  |  | 2011-12-01 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115 kV line interconnections at Berry Street | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-04-25 | 2012-06-06 | 37529000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 0
Reliability Upgrade | 1a | 1097 | RI | National Grid, USA |  |  | 2013-03-01 | NEEWS (Rhode Island Reliability Project) | Relocate and rebuild 115kV lines in the same ROW associated with new 345 kV line from W. Farnum to Kent County and reconductor short segments of the S-171 and T-172S lines (along with upgrading associated limiting terminal equipment). | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2015-12-17 | 129800000 | 129800000 | 129800000 | 129800000 | 129800000 | 129800000 | 129800000 | 129800000 | 129800000 | 129800000 | 139800000 | 139800000 | 139800000 | 139800000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 0
Reliability Upgrade | 1a | 1096 | RI | National Grid, USA |  |  | 2012-12-01 | NEEWS (Rhode Island Reliability Project) | Drumrock Substation: Terminal equipment upgrades, protection modifications and upgrades to meet BPS standards | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2015-12-17 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 0
Reliability Upgrade | 1a | 1095 | RI | National Grid, USA |  |  | 2012-05-01 | NEEWS (Rhode Island Reliability Project) | Upgrade and expand the 345 kV West Farnum Substation Equipment | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 5/4/2012 | 2015-12-17 | 73800000 | 73800000 | 73800000 | 73800000 | 55200000 | 55200000 | 55200000 | 55200000 | 55200000 | 55200000 | 55200000 | 55200000 | 55200000 | 55200000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 0
Reliability Upgrade | 1a | 1094 | MA | National Grid, USA |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345 kV Millbury Substation equipment | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 9/24/2008 5/4/2012 | 2015-12-17 | 25000000 | 25000000 | 25000000 | 25000000 | 30700000 | 30700000 | 30700000 | 30700000 | 30700000 | 30700000 | 30700000 | 30700000 | 27480000 | 27480000 | 27480000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 0
Reliability Upgrade | 1a | 1092 | MA | Eversource |  |  | 2014-06-01 | NEEWS | Upgrade the Agawam 115 kV Substation to BPS standards together with other misc. substation upgrades | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2014-02-25 | 37000000 | 13600000 | 13600000 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 0
Reliability Upgrade | 1a | 1091 | CT | Eversource |  |  | 2010-05-01 | NEEWS (Interstate Reliability Project) | Southington 4C substation breaker 19T upgrade to 63 kA | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 0
Reliability Upgrade | 1a | 1090 | CT | Eversource |  |  | 2010-04-01 | NEEWS (Interstate Reliability Project) | Millstone 15G substation breaker 14T upgrade 50 kA | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 0
Reliability Upgrade | 1a | 1089 | CT | Eversource |  |  | 2015 | NEEWS (Interstate Reliability Project) | Killingly 3G substation 345 kV breaker addition | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1088 | CT | Eversource |  |  | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to 115 kV line 1786, East Hartford to Riverside to South Meadow | Planned | Planned | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1087 | CT | Eversource |  |  | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to line 115 kV 1722 SW Hartford NW Hartford | Planned | Planned | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1086 | CT | Eversource |  |  | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to 115 kV line 1704, SW Hartford to South Meadow | Planned | Planned | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 1085 | CT | Eversource |  |  | 2014-12-01 | NEEWS (Interstate Reliability Project) | Card 11F 345 kV Substation expansion | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 5/4/2012 | 2015-12-17 | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | #VALUE!
Reliability Upgrade | 1b | 1084 | CT | Eversource |  |  | TBD | Greater Hartford Central Connecticut Project | Loop the Millstone - Manchester (310) 345 kV line into the Card substation | Planned | Planned | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 1080 | MA | Eversource |  |  | 2012-12-01 | NEEWS (Greater Springfield Reliability Project) | Shawinigan 55E Substation Replace 115 kV circuit breakers 1T, 2T, 4T and 6T | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1079 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115 kV line | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | #VALUE!
Reliability Upgrade | 1a | 1078 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115 kV line | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | #VALUE!
Reliability Upgrade | 1a | 1077 | MA | Eversource |  |  | 2011-04-01 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115 kV line | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2014-02-25 | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | #VALUE!
Reliability Upgrade | 1a | 1076 | MA | Eversource |  |  | 2011-12-01 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115 kV line | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2014-02-25 | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | #VALUE!
Reliability Upgrade | 1a | 1075 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115 kV line Russell Biomass Plant | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1074 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Reterminate 115 kV line 1645, Cadwell to East Springfield | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1073 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Reterminate 115 kV line 1556, Cadwell to East Springfield | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1072 | MA | Eversource |  |  | 2012-11-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV line 1845, Ludlow to Shawinigan and add 2nd High Speed Protection | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1071 | MA | Eversource |  |  | 2012-11-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV line 1782 Agawam to South Agawam and add 2nd High Speed Protection | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1070 | MA | Eversource |  |  | 2012-11-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV line 1781, Agawam to South Agawam and add 2nd High Speed Protection | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1068 | MA | Eversource |  |  | 2013-09-01 | Long Term Lower SEMA Upgrades | Install the new West Barnstable 345/115 kV substation 3 miles west of the existing Barnstable 115 kV substation by looping the #115 line between Mashpee and Barnstable. The substation will have a 8 breakers in a double breaker configuration on the 115 kV switchyard | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 07/2011 2/11/2014 | 2011-12-16 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | #VALUE!
Reliability Upgrade | 1a | 1067 | MA | Northeast Utilities - NSTAR |  |  | 2010-12-01 | NPCC BPS Compliance | Tremont Station | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2015-12-17 | 10000000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 6655000 | 6655000 | 6655000 | 6655000 | 6655000 | 6655000 | 6655000 | 6655000 | 6655000 | 6655000 | 6655000 | 6655000 | 0
Reliability Upgrade | 1a | 1066 | MA | Eversource |  |  | 2011-12-01 | NPCC BPS Compliance | Needham Station | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2011-12-28 | 9500000 | 9500000 | 6500000 | 8000000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 0
Reliability Upgrade | 1a | 1065 | MA | Eversource |  |  | 2013-06-01 | NPCC BPS Compliance | Waltham Station | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2012-12-13 | 23190000 | 14700000 | 14700000 | 14700000 | 17000000 | 17000000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 0
Generator Interconnection Upgrade | 2a | 1062 | MA | National Grid, USA |  |  | 2011-06-01 | Billerica Power | Upgrade #137T and #K-137W 115 kV circuit breakers at Sandy Pond (if not completed as part of Merrimack Valley/North Shore Project). | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1061 | MA | National Grid, USA |  |  | 2011-06-01 | Billerica Power | Replace (16) 115 kV circuit breakers at Tewksbury 22 w/ IPT capability if all generators w/ higher Queue Position are constructed. The quantity of breaker upgrades subject to Queued generators constructed. | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1060 | MA | National Grid, USA |  |  | 2011-06-01 | Billerica Power | Reconductor 2.8 mi. of the M-139 115 kV line. | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1059 | MA | National Grid, USA |  |  | 2011-06-01 | Billerica Power | Re-terminate line tap section (Perry Street) of J-162 Line to new bay position at Tewksbury. | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1058 | MA | National Grid, USA |  |  | 2011-06-01 | Billerica Power | Interconnection to Tewksbury 115 kV Substation via O-193 Line and refurbish section of J-162 line. | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1056 | CT | Eversource |  |  | 2011-12-01 | LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8 kV substation with two transformers and a 115 kV circuit breaker. | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-12-12 | 2011-04-14 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 0
Reliability Upgrade | 1a | 1055 | CT | Northeast Utilities |  |  | 2010-12-01 | LSP - Waterside Substation | Waterside Substation - add a 115/13.2 kV transformer and a 115 kV circuit breaker. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-09-29 | NR | 2804000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 0
Reliability Upgrade | 1a | 1054 | CT | Eversource |  |  | 2012-10-01 | NEEWS | Separate the three-terminal 345 kV Line 395 at Meekville Junction and build new Manchester to Meekville Junction 345 kV line portion and add a 345 kV circuit breaker 24T at Manchester 3A | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 5/4/2012 | 2014-02-25 | 14000000 | 31000000 | 31000000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 0
Reliability Upgrade | 1a | 1050 | CT | United Illuminating Company |  |  | 2011-12-01 |  | Devon Tie 115 kV Switching Station BPS Compliance | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 3240000 | 3800000 | 4000000 | 4000000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 0
Reliability Upgrade | 1a | 1049 | CT | United Illuminating Company |  |  | 2011-03-01 |  | Add additional capacitor, reactors and circuit switches at East Shore 115 kV substation | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 4400000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 0
Generator Interconnection Upgrade | 2a | 1048 | MA | Eversource |  |  | 2015-06-01 | Cape Wind | Convert Canal 345 kV SPS to include tripping of Cape Wind for the simultaneous loss of 342 and 322 345 kV lines. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1047 | MA | National Grid, USA |  |  | 2019-01-01 | Brockton Power | Replace Bridgewater 115 kV 1631 circuit breaker with 63 kA breaker. | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-03-10 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1046 | MA | National Grid, USA |  |  | 2019-01-01 | Brockton Power | Reconductor 115 kV F19 Line (Auburn - Brockton Tap). | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-03-10 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1044 | MA | Eversource |  |  | 2015-02-01 | Russell BioMass | Upgrade the 1512 line terminal equipment at Southwick Substation. | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 06/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1043 | MA | Eversource |  |  | 2015-02-01 | Russell BioMass | Upgrade the 1768 line terminal equipment at Southwick Substation. | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 06/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1042 | MA | National Grid, USA |  |  | 2013-06-01 | Queue Position 165 | Replace (2) 345 kV circuit breakers at Sandy Pond | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1037 | VT | Vermont Electric Power Company | Green Mountain Power |  | 2013-12-01 | Deerfield Wind | Installation of 3-breaker 69 kV ring bus interconnecting to the Bennington-Searsburg 69 kV Y25N line | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2010-06-03 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1036 | VT | Vermont Electric Power Company |  |  | 2011-10-01 | Sheffield Wind | Installation of 3-breaker 115 kV ring bus interconnecting to the St. Johnsbury-Irasburg 115 kV K39 line. | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 08/16/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1035 | VT | Vermont Electric Power Company |  |  | 2010-12-01 | Vermont Southern Loop Project | Expansion of Coolidge 345 kV substation | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-10-01 | 2010-05-17 | 20117000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 0
Reliability Upgrade | 1a | 1034 | VT | Vermont Electric Power Company |  |  | 2010-12-01 | Vermont Southern Loop Project | Loop new 345 kV Line into Newfane Substation. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-10-01 | 2010-05-17 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | #VALUE!
Reliability Upgrade | 1a | 1033 | VT | Vermont Electric Power Company |  |  | 2010-12-01 | Vermont Southern Loop Project (VELCO LSP - Newfane Substation) | Installation of a new 345/115 kV substation called Newfane | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-10-01 | 2010-05-17 | 16664000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 0
Reliability Upgrade | 1a | 1032 | VT | Vermont Electric Power Company |  |  | 2010-12-01 | Vermont Southern Loop Project | Installation of a new 345/115 kV substation called Vernon including a new 345/115 kV autotransformer | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-10-01 | 2010-05-17 | 55000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 0
Reliability Upgrade | 1a | 1031 | ME | Emera Maine |  |  | 2013-12-01 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-10-22 | 2013-02-28 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 9300000 | 9300000 | 9300000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 0
Reliability Upgrade | 1a | 1030 | ME | Central Maine Power Company |  |  | 2013-11-01 | Maine Power Reliability Program (MPRP) | New 345/115 kV Autotransformers (Maguire Road) | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1029 | ME | Central Maine Power Company |  |  | 2010-05-01 | Maine Power Reliability Program (MPRP) | New 345/115 kV Autotransformer at South Gorham and substation expansion | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1028 | ME | Central Maine Power Company | Eversource |  | 2013-12-01 | Maine Power Reliability Program (MPRP) | Rebuild existing 115 kV Line (Section 250, Maguire Rd-Three Rivers Switching Station) | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 1/29/2010 (CMP) 4/14/2011 (NU) | Portion of CMP $1.32B and portion of NU is TBD | Portion of CMP $1.47B and portion of NU is $36.0M | Portion of CMP $1.47B and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | #VALUE!
Reliability Upgrade | 1a | 1027 |  | Central Maine Power Company |  |  | 2012-12-01 | Maine Power Reliability Program (MPRP) | New 115 kV Line Construction (Raven Farm - East Deering, East Deering -Cape) | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1026 | ME | Central Maine Power Company | Eversource |  | 2013-11-01 | Maine Power Reliability Program (MPRP) | New 345 kV Line Construction associated with (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Elliot Switching Station) line work | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 1/29/2010 (CMP) 4/14/2011 (NU) | Portion of CMP $1.32B and portion of NU is $36.0M | Portion of CMP $1.47B and portion of NU is $36.0M | Portion of CMP $1.47B and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | #VALUE!
Reliability Upgrade | 1a | 1025 | ME | Central Maine Power Company |  |  | 2015-02-01 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345 kV Kennebec River Crossing 375/377, 115 kV Bucksport 65/205) | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Elective Upgrade | 4b | 1018 | ME | Emera Maine | National Grid, USA |  | 2017-06-01 | Queue Position 509 | 1100 MW HVDC between Orrington substation to Tewksbury substation | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1010 | MA | Eversource |  |  | 2011-12-01 | NEEWS (Greater Springfield Reliability Project) | Build 115 kV Cadwell switching 50F station. | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1000 | MA | Eversource |  |  | 2011-04-01 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-06-27 | 2012-09-20 | 26000000 | 26000000 | 26000000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 0
Generator Interconnection Upgrade | 2a | 983 | CT | Eversource |  |  | 2013-06-01 | Towantic Energy | Rebuild 115 kV 1585N Line between new substation and Bunker Hill. | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-26 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 976 | CT | United Illuminating Company |  |  | 2012-05-01 |  | Grand Avenue 115 kV Switching Station Rebuild. | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 1/7/2009 10/20/2011 4/30/2012 | 2011-10-20 | 66000000 | 70000000 | 70000000 | 70000000 | 70000000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 0
Reliability Upgrade | 1b | 975 | CT | United Illuminating Company |  |  | TBD | SWCT | Pequonnock 115 kV Fault Duty Mitigation. - Phase II | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | 65000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 0
Reliability Upgrade | 1a | 974 | CT | United Illuminating Company |  |  | 2013-11-01 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2012-05-16 | 11500000 | 15400000 | 16900000 | 16900000 | 15000000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 0
Reliability Upgrade | 1b | 971 | MA | Eversource |  |  | TBD | Greater Boston - Central | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 970 | MA | Eversource |  |  | TBD | Greater Boston - Central | Add a new 345 kV line from Lexington to Waltham. | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 969 | MA | Eversource |  |  | 2012-11-01 | Greater Boston - North | Add a new 115 kV 36.7 MVAR capacitor bank at Chelsea. | Concept | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-03-30 | No | 1600000 | 1500000 | 1500000 | 1500000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 0
Reliability Upgrade | 1a | 965 | MA | Eversource |  |  | 2020-09-01 | Greater Boston - South | Add third 115 kV line from W. Walpole to Holbrook | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Proposed | 2016-06-09 | No | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 17300000 | 17300000 | 17300000 | 17300000 | 17300000 | 17300000 | 17300000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 0
Reliability Upgrade | 1b | 964 | MA | Eversource |  |  | 2011-12-01 | Boston Area 115 kV Enhancements | Relocate 115 kV terminals at W. Walpole to mitigate breaker failure #8. | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | 1500000 | 1500000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 956 | MA | National Grid, USA |  |  | 2016-06-01 | Central/Western Massachusetts Upgrades - Group 7 - Carpenter Hill Autotransformer Upgrade | Carpenter Hill - replace one 345 kV autotransformer with a new autotransformer of 448 MVA and upgrade thermal rating of bus to at least 580 MVA. | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2007-12-17 | No | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 0
Reliability Upgrade | 1a | 955 | MA | National Grid, USA |  |  | 2016-12-01 | Central/Western Massachusetts Upgrades - Group 4 - E. Longmeadow Projects | Refurbish and reconductor (W175) West Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 12/17/2007 | 2016-10-04 | 13800000 | 13800000 | 13800000 | 13800000 | 13800000 | 13800000 | 13800000 | 13800000 | 13800000 | 13800000 | 23970000 | 23970000 | 23970000 | 26000000 | 26000000 | 26000000 | 28000000 | 28000000 | 28000000 | 28000000 | 28000000 | 28000000 | 28000000 | 28000000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 0
Reliability Upgrade | 1a | 954 | MA | National Grid, USA |  |  | 2022-12-01 | Central/Western Massachusetts Upgrades Group - 5 - A-1/B - 2 Projects | Westminster - install new 69 kV breaker, including disconnect switches. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 12/17/2007 | No | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 0
Reliability Upgrade | 1a | 953 | MA | National Grid, USA |  |  | 2022-12-01 | Central/Western Massachusetts Upgrades Group - 5 - A-1/B - 2 Projects | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 12/17/2007 | No | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 0
Reliability Upgrade | 1a | 951 | MA | National Grid, USA |  |  | 2022-12-01 | Central/Western Massachusetts Upgrades - Group 5 A-1/B- 2 Projects | Install new Otter River - E Winchendon (H-134) 115 kV line. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 12/17/2007 | No | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 0
Reliability Upgrade | 1a | 950 | MA | National Grid, USA |  |  | 2022-12-01 | Central/Western Massachusetts Upgrades - Group 5 - A-1/B - 2 Projects | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 12/17/2007 | No | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 0
Reliability Upgrade | 1a | 949 | MA | National Grid, USA |  |  | 2015-11-01 | Central/Western Massachusetts Upgrades - Group 4 - E. Longmeadow Projects | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2011-03-29 | 2016-10-04 | 1500000 | 1500000 | 1600000 | 1600000 | 1600000 | 1600000 | 2280000 | 2280000 | 2280000 | 1500000 | 1520000 | 1520000 | 1520000 | 1600000 | 1600000 | 1600000 | 2258000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 0
Reliability Upgrade | 1a | 948 | MA | National Grid, USA |  |  | 2014-10-01 | Central/Western Massachusetts Upgrades - Group 4 - E. Longmeadow Projects | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-03-29 | 2016-10-04 | 5649430 | 5649430 | 13400000 | 13400000 | 13400000 | 13400000 | 19700000 | 19700000 | 19700000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 0
Reliability Upgrade | 1a | 947 | MA | National Grid, USA |  |  | 2012-12-01 | Central/Western Massachusetts Upgrades | Reconductor 115 kV line from Palmer to new Hampden Substation. | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 12/17/2007 | No | 2632635 | 2632635 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 946 | MA | National Grid, USA |  |  | 2015-12-01 | Central/Western Massachusetts Upgrades - Group 4 - E. Longmeadow Projects | Convert 69 kV (O-15S) Palmer- W. Hampden to 115 kV. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2011-03-29 | 2016-10-04 | 9962060 | 9962060 | 16000000 | 16000000 | 16000000 | 16000000 | 19803000 | 19803000 | 19803000 | 19803000 | 19803000 | 19803000 | 19803000 | 21700000 | 21700000 | 21700000 | 21700000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 0
Reliability Upgrade | 1a | 945 | MA | National Grid, USA |  |  | 2018-12-01 | Central/Western Massachusetts Upgrades - Group 6 - Miscellaneous Western Ma Projects | Adams - install two new 115 kV breakers and replace two existing 115 kV breakers and associated line relocations | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 12/17/2007 12/7/2012 | 2018-10-16 | 1584841 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16918000 | 16918000 | 16918000 | 16918000 | 16918000 | 16918000 | 16918000 | 16918000 | 0
Reliability Upgrade | 1a | 944 | MA | National Grid, USA |  |  | 2012-03-01 | Central/Western Massachusetts Upgrades - Group 1 Central MA supply improvements | Wachusett - install one 345 kV, 448 MVA transformer, one 345 kV breaker, and one 115 kV breaker. | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2012-02-29 | 16530000 | 16530000 | 16530000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 0
Reliability Upgrade | 1a | 943 | MA | National Grid, USA |  |  | 2013-06-01 | Central/Western Massachusetts Upgrades - Group 2 - Webster St. Supply Improvements | Millbury - new 115 kV breaker position for new line to Tower 510. | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | No | 1073995 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 0
Reliability Upgrade | 1a | 942 | MA | National Grid, USA |  |  | 2013-06-01 | Central/Western Massachusetts Upgrades - Group 2 - Webster St. Supply Improvements | Webster St. - add two 115 kV circuit breakers. | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | No | 3650000 | 3650000 | 3650000 | 3650000 | 3650000 | 3650000 | 3650000 | 3650000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 0
Reliability Upgrade | 1a | 941 | MA | National Grid, USA |  |  | 2014-07-01 | Central/Western Massachusetts Upgrades - Group 2 - Webster St. Supply Improvements | Install new Z126 Millbury - Tower #510 115 kV line | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2014-04-23 | 13748000 | 13748000 | 13748000 | 13748000 | 13748000 | 13748000 | 13748000 | 13748000 | 13748000 | 13748000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 0
Reliability Upgrade | 1a | 940 | MA | National Grid, USA |  |  | 2015-04-01 | A127/B128 Conductor Refurbishment | Reconductor sections of A127W line w/477 ACSS (A127 West reconductoring. Tower 510 to Paxton, Wendell Depot to Cabot Tap). | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-05-30 | 2011-12-16 | 18000000 | 18000000 | 18000000 | 18000000 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | #VALUE!
Reliability Upgrade | 1a | 939 | MA | National Grid, USA |  |  | 2011-02-01 | Central/Western Massachusetts Upgrades | Reconductor and retention (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2012-09-20 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 0
Reliability Upgrade | 1a | 938 | MA | National Grid, USA |  |  | 2013-11-01 | Central/Western Massachusetts Upgrades - Group 6 - Miscellaneous Western Ma Projects | Deerfield - install a new 115/69 kV autotransformer and a 69 kV breaker and disconnect switches | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2014-04-23 | 3068556 | 3068556 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 0
Reliability Upgrade | 1a | 937 | MA | National Grid, USA |  |  | 2017-12-01 | Central/Western Massachusetts Upgrades - Group 3 Bear Swamp/Pratts Junction Projects | Bear Swamp - install one 230/115 kV 333 MVA auto transformer, one 115 kV breaker, four 230 kV breaker replacements and upgrade various terminal equipment. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 12/17/2007 | 2018-04-17 | 6602875 | 6602875 | 6602875 | 6602875 | 6602875 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 20480000 | 21135000 | 21135000 | 21135000 | 20470000 | 20470000 | 20470000 | 20470000 | 20470000 | 20470000 | 20470000 | 20470000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 0
Reliability Upgrade | 1a | 935 | MA | National Grid, USA |  |  | 2014-04-01 | Central/Western Massachusetts Upgrades - Group 2 - Webster St. Supply Improvements | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2014-04-23 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 0
Reliability Upgrade | 1a | 934 | MA | National Grid, USA |  |  | 2013-02-01 | Central/Western Massachusetts Upgrades - Group 2 - Webster St. Supply Improvements | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2014-04-23 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | #VALUE!
Reliability Upgrade | 1a | 932 | MA | National Grid, USA |  |  | 2012-10-01 | Central/Western Massachusetts Upgrades - Group 3 Bear Swamp/Pratts Junction Projects | Pratts Jct. - increase thermal rating of I-135 and J-136 bus work. | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2012-02-29 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | #VALUE!
Reliability Upgrade | 1a | 931 | MA | National Grid, USA |  |  | 2013-01-01 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 12/17/2007 | No | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 0
Reliability Upgrade | 1a | 929 | MA | National Grid, USA |  |  | 2014-12-01 | Central/Western Massachusetts Upgrades - Group 6 - Miscellaneous Western Ma Projects | Searsburg - install in-line 69 kV breaker | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | No | 1381849 | 1381849 | 2500000 | 2500000 | 2500000 | 2500000 | 3300000 | 3300000 | 3300000 | 3000000 | 3957000 | 3957000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 0
Reliability Upgrade | 1a | 928 | MA | National Grid, USA |  |  | 2013-12-01 | Central/Western Massachusetts Upgrades - Group 1 Central MA supply improvements | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2012-02-29 | 2300000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 0
Reliability Upgrade | 1a | 926 | MA | National Grid, USA |  |  | 2012-05-01 | Central/Western Massachusetts Upgrades - Group 3 Bear Swamp/Pratts Junction Projects | Pratts Jct. - replace T8 autotransformer with 230 kV 333 MVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2012-12-27 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 0
Reliability Upgrade | 1a | 925 | MA | National Grid, USA |  |  | 2013-12-01 | Central/Western Massachusetts Upgrades - Group 3 Bear Swamp/Pratts Junction Projects | Pratts Jct. - supply 13 kV from T3 and T4 | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2012-12-27 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | #VALUE!
Reliability Upgrade | 1a | 924 | MA | National Grid, USA |  |  | 2011-07-01 | Central/Western Massachusetts Upgrades | Carpenter Hill - Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2012-02-29 | 3600000 | 3600000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 0
Reliability Upgrade | 1a | 921 | MA | National Grid, USA |  |  | 2013-06-01 | Auburn Area Transmission System Upgrades | Bridgewater substation ; Upgrade 115 kV and 345 kV switchyards to BPS. Add two 115 kV breakers for E1 line; replace five 115 kV breakers and two 345 kV breakers; includes bus work. | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 1/28/2008 10/27/2003 | 2014-02-03 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 0
Reliability Upgrade | 1a | 919 | MA | National Grid, USA |  |  | 2014-04-01 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade bus work and convert to BPS substation. Includes adding 5 breakers ring bus configuration and a second distribution transformer. Terminal upgrades to increase ratings on G18 and C2 | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-02-10 | 2014-02-03 | 4600000 | 4600000 | 9200000 | 13600000 | 13600000 | 13600000 | 13600000 | 12000000 | 12000000 | 12000000 | 12000000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 0
Reliability Upgrade | 1b | 918 | RI | National Grid, USA |  |  | 2017-12-01 | Greater Rhode Island Transmission Reinforcements | Dexter substation changes | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-04-25 | No | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 917 | MA | National Grid, USA |  |  | 2019-12-01 | Greater Rhode Island Transmission Reinforcements | Bell Rock substation expansion. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-04-25 | No | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 916 | RI | National Grid, USA |  |  | 2017-12-01 | Greater Rhode Island Transmission Reinforcements | Conversion of Jepson 69 kV substation to 115 kV substation | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-04-25 | No | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 915 | RI | National Grid, USA |  |  | 2017-12-01 | Greater Rhode Island Transmission Reinforcements | Reconductor M13 and L14 between Bell Rock and Dexter | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-04-25 | No | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 914 | MA | National Grid, USA |  |  | 2018-12-01 | Greater Rhode Island Transmission Reinforcements | New third circuit between Somerset and Bell Rock. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-04-25 | No | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 913 | MA | National Grid, USA |  |  | 2018-12-01 | Greater Rhode Island Transmission Reinforcements | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-04-25 | No | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 909 | ME | Central Maine Power Company |  |  | 2014-08-01 | Maine Power Reliability Program (MPRP) | Add 2-115 kV breakers & rebuild 86A, new .25 mile transmission at Belfast forming Sections 86 & 266 | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 908 | ME | Central Maine Power Company |  |  | 2014-01-01 | Maine Power Reliability Program (MPRP) | New 345/115 kV Autotransformers (Albion Road, Larrabee Road); Coopers Mills autotransformer replaces Maxcy's autotransformer | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 907 | ME | Central Maine Power Company |  |  | 2014-05-01 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115 kV lines: Sections 86 (Bucksport-Belfast), Section 203 (Detroit-Orrington), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 906 | ME | Central Maine Power Company |  |  | 2014-12-01 | Maine Power Reliability Program (MPRP) | New 115 kV line construction (Orrington-Coopers Mills, Larrabee Road-Middle St,Middle St -Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 905 | ME | Central Maine Power Company |  |  | 2014-09-01 | Maine Power Reliability Program (MPRP) | New 345 kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | 1320000000 | 1470187000 | 1470187000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 0
Reliability Upgrade | 1a | 904 | MA | Northeast Utilities - NSTAR |  |  | 2010-12-01 | Mystic IPT Breaker Project | Upgrade (5) 115 kV breakers #1, #7, #15 #19 and #20 at Mystic to IPT. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 1500000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 0
Reliability Upgrade | 1a | 902 | MA | National Grid, USA |  |  | 2010-10-01 | Middleboro Municipal | Close the E1-M1 loop at Middleboro's Wareham St Sub. | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/01/2006 | NR | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 0
Reliability Upgrade | 1a | 887 | MA | National Grid, USA |  |  | 2014-03-01 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to BPS standards with 2nd 345/115 kV autotransformer and 345 kV ring bus to accommodate 2nd autotransformer. Includes breaker and a third scheme | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-02-10 | 2014-02-03 | 76000000 | 76000000 | 66300000 | 58000000 | 58000000 | 58000000 | 58000000 | 58000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 0
Generator Interconnection Upgrade | 2b | 881 | RI | National Grid, USA | Northeast Utilities |  | 2012-06-01 | Queue Position 201 | RISEP - 345 kV RISE Substation. | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 880 | MA | National Grid, USA | Northeast Utilities |  | 2011-06-01 | Queue Position 177 | Sutton Energy (Project doe not have 1A replaced with QP 177) - 345 kV Carpenter Hill-Millbury Line. | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 879 | CT | Bangor Hydro-Electric Company | New England Power Company, Eversource |  | 2012-12-01 | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 03/01/2007 | NR | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 0
Reliability Upgrade | 1a | 843 | MA | Eversource |  |  | 2013-12-01 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | Concept | Concept | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-01-05 | NR | TBD | TBD | 3200000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 0
Reliability Upgrade | 1a | 840 | MA | Eversource |  |  | 2012-12-01 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-04-01 | 2011-01-10 | 5900000 | 5900000 | 5900000 | 5900000 | 5900000 | 5900000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 0
Reliability Upgrade | 1a | 829 | MA | Eversource |  |  | 2012-04-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV line 1230 Agawam to Piper | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 828 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115 kV circuit 1322 Reactor Bypass and Open Breckwood Substation 1T breaker and maintain breaker in the normally open position | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 826 | MA | Eversource |  |  | 2013-03-01 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigured | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1b | 825 | MA | Eversource |  |  | TBD | Pittsfield / Greenfield Project | Upgrade the Pleasant to Blandford 115 kV line and the Blandford to Granville Jct. portion of the 115 kV line 1512. | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 824 | MA | Eversource |  |  | TBD | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115 kV line and terminal work at Woodland substation. | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 823 | MA | Eversource |  |  | 2012-12-01 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115 kV autotransformer replacements. | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 820 | MA | Eversource |  |  | 2012-12-01 | NEEWS (Greater Springfield Reliability Project) | Agawam 16C 115 kV Substation expansion, two 345/115 kV autotransformer additions, BPS Classification | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 819 | MA | Eversource |  |  | 2012-11-01 | NEEWS (Greater Springfield Reliability Project) | Build new 345 kV line 3196, Ludlow - Agawam | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 818 | MA | Eversource |  |  | 2013-02-01 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115 kV 1768 line South Agawam to Southwick | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 816 | CT | Eversource |  |  | 2013-04-01 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion add a second 345/115 kV autotransformer | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 5/4/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 814 | CT | Northeast Utilities |  |  | 2010-05-01 | Middletown Area Project | Reconductor a portion of the Manchester to Scovill Rock 353 345 kV line and terminal work. | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | NR | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 0
Reliability Upgrade | 1a | 810 | CT | Eversource |  |  | 2014-12-01 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV Substation expansion | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 5/4/2012 | 2015-12-17 | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | #VALUE!
Reliability Upgrade | 1a | 809 | CT | Northeast Utilities |  |  | 2010-12-01 |  | Upgrade terminal equipment at Bunker Hill 115 kV substation. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 516000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 0
Reliability Upgrade | 1a | 807 | CT | Eversource |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | Install 480 MVAR's of capacitors at the Montville 345 kV substation | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | 33000000 | 33000000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 802 | CT | Eversource |  |  | 2015-08-01 | NEEWS (Interstate Reliability Project) | Build new 345 kV line 3271 Card - Lake Road | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 9/24/2008 5/4/2012 | 2015-12-17 | 251000000 | 301000000 | 251000000 | 218000000 | 218000000 | 218000000 | 218000000 | 218000000 | 218000000 | 218000000 | 218000000 | 218000000 | 218000000 | 218000000 | 218000000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 0
Reliability Upgrade | 1b | 801 | CT | Eversource |  |  | TBD |  | Build Manchester to East Hartford 115 kV cable with a series reactor. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 800 | RI | National Grid, USA |  |  | 2012-09-01 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S and T-172S with associated terminal equipment upgrades | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-11-05 | 2015-12-17 | 10000000 | 10000000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 0
Reliability Upgrade | 1a | 799 | RI | National Grid, USA |  |  | 2011-07-01 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2015-12-17 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 0
Reliability Upgrade | 1a | 798 | RI | National Grid, USA |  |  | 2011-12-01 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115 kV terminal equipment at Franklin Square. | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2015-12-17 | 4900000 | 4900000 | 4900000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 0
Reliability Upgrade | 1a | 797 | RI | National Grid, USA |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | 3361 Upgrade 345 kV terminal equipment at Sherman Road. | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | 8300000 | 8300000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 796 | RI | National Grid, USA |  |  | 2014-12-01 | NEEWS (Interstate Reliability Project) | 347 Reconductor from Sherman Road to CT/RI Border. | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | 16400000 | 16400000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 795 | RI | National Grid, USA |  |  | 2013-05-01 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345 kV (359) line. | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2015-12-17 | 99900000 | 69000000 | 69000000 | 69000000 | 69000000 | 69000000 | 69000000 | 69000000 | 69000000 | 69000000 | 69000000 | 69000000 | 69000000 | 69000000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 0
Reliability Upgrade | 1a | 794 | RI | National Grid, USA |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345 kV line (to Lake Road) | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 9/24/2008 5/4/2012 | 2015-12-17 | 55800000 | 71700000 | 71700000 | 71700000 | 71700000 | 71700000 | 71700000 | 71700000 | 71700000 | 71700000 | 71700000 | 71700000 | 71350000 | 71350000 | 71350000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 0
Reliability Upgrade | 1b | 793 | MA | National Grid, USA |  |  | 2018-12-01 | Greater Rhode Island Transmission Reinforcements | Somerset Substation Reinforcements | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-04-25 | No | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 792 | RI | National Grid, USA |  |  | 2014-12-01 | Greater Rhode Island Transmission Reinforcements 1 | Admiral St-Franklin Square (Q143 and R144) 115 kV UG recabling. | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-04-25 | No | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 0
Reliability Upgrade | 1b | 791 | MA | National Grid, USA |  |  | 2018-12-01 | Greater Rhode Island Transmission Reinforcements | New 115 kV circuit between Somerset and Brayton Point. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-04-25 | No | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 790 | MA | National Grid, USA |  |  | 2011-12-01 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-04-25 | 2012-06-06 | 50600000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 0
Reliability Upgrade | 1a | 788 | RI | National Grid, USA |  |  | 2011-01-01 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Kent County substation expansion. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-04-25 | 2012-06-07 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 0
Reliability Upgrade | 1a | 786 | MA | National Grid, USA |  |  | 2011-05-01 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Terminal upgrades at Drumrock, Chartley Pond, and Brayton Point | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-04-25 | 2012-06-06 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 0
Reliability Upgrade | 1b | 785 | MA | National Grid, USA |  |  | 2017-07-01 | Merrimack Valley/North Shore Reliability Project | Re-conductor F-158N (Golden Hills-Maplewood-Everett) 115 kV line. | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | 1330000 | 1330000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 783 | MA | National Grid, USA |  |  | 2011-04-01 | Merrimack Valley/North Shore Reliability Project | Extend the 115 kV by addition of 115 kV Breaker and K-163 line from King St. to W. Amesbury 115 kV station. (W. Amesbury 345/115 kV Station becomes PTF) | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-04-01 | 2012-08-03 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 0
Reliability Upgrade | 1a | 782 | MA | National Grid, USA |  |  | 2016-06-01 |  | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor and Railyard. | Planned | Planned | Planned | Planned | Planned | Concept | Concept | Concept | Concept | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-02-11 | 2016-12-16 | 43912000 | 43912000 | 43912000 | 43912000 | 43912000 | 41523000 | 41523000 | 41523000 | 41523000 | 41523000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 0
Reliability Upgrade | 1a | 776 | MA | National Grid, USA |  |  | 2013-04-01 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-06-27 | 2012-06-01 | 3125000 | 3125000 | 3125000 | 3125000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 0
Reliability Upgrade | 1a | 775 | MA | National Grid, USA |  |  | 2012-06-01 | Merrimack Valley/North Shore Reliability Project | Addition of 4 breakers and relocation of T1 and T2 into new bays at Sandy Pond. | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-06-27 | No | 20100000 | 20100000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 724 | NH | National Grid, USA |  |  | 2013-03-01 | NGRID Comerford Substation | NGRID Comerford Substation. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2007-06-12 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 721 | CT | United Illuminating Company | Eversource |  | 2015-06-01 |  | New Pootatuck 115/13.8 kV substation (formerly known as Shelton Substation) (Other equipment owner for line 1560: Eversource) | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2009-11-05 | 2014-03-06 | 19500000 | 19500000 | 19500000 | 19500000 | 19500000 | 19500000 | 19500000 | 19500000 | 19500000 | 19500000 | 19800000 | 19936000 | 19936000 | 19936000 | 19936000 | 19936000 | 19936000 | 19936000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 0
Reliability Upgrade | 1b | 699 | CT | United Illuminating Company |  |  | 2016-12-01 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 0
Reliability Upgrade | 1a | 688 | MA | Eversource |  |  | 2012-11-01 | NEEWS (Greater Springfield Reliability Project) | Reconductor/rebuild 115 kV line 1481, Ludlow to Cadwell | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 687 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont 16H 115 kV Switching Station | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | 714000000 | 795000000 | 795000000 | 718000000 | 718000000 | 718000000 | 718000000 | 718000000 | 718000000 | 718000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 0
Reliability Upgrade | 1a | 680 | NH | National Grid, USA |  |  | 2013-09-01 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-01-28 | 2014-03-06 | 7393000 | 7393000 | 7393000 | 7393000 | 10300000 | 10300000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 0
Reliability Upgrade | 1a | 676 | MA | National Grid, USA |  |  | 2012-06-01 | Worcester Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115 kV breaker at Bloomingdale & Vernon Hill | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-02-27 | 2011-07-15 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 0
Reliability Upgrade | 1a | 674 | NH | National Grid, USA |  |  | 2014-07-01 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-04-01 | 2016-06-30 | 19460000 | 19460000 | 19460000 | 19460000 | 19460000 | 19460000 | 19460000 | 19460000 | 19460000 | 19460000 | 34390000 | 34390000 | 34390000 | 34390000 | 34390000 | 34390000 | 34390000 | 34390000 | 36630000 | 36630000 | 36630000 | 36630000 | 36630000 | 36630000 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 0
Reliability Upgrade | 1a | 673 | MA | National Grid, USA |  |  | 2012-03-01 | Worcester Area Reinforcements | Add new 115 kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-02-27 | 2011-07-15 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 0
Reliability Upgrade | 1a | 624 | ME | Central Maine Power Company |  |  | 2011-07-01 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (Rumford Industrial Park - Rumford) | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 11/30/2007 5/4/2010 | 2011-08-22 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | #VALUE!
Generator Interconnection Upgrade | 2a | 622 | MA | Eversource |  |  | 2015-02-01 | Russell BioMass | Install a 3-breaker ring bus on the 1512 line between Granville Jct. and Elm Substation. Build new line from this new station to the plant | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 06/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 600 | MA | Eversource |  |  | 2015-06-01 | Cape Wind | Installation of differential insulation and additional grounding at each tower that is common for the 342 and 322 345 kV lines. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 599 | MA | Eversource |  |  | 2018-10-01 | Cape Wind | Upgrade the Bourne 115 kV breaker #12272 with an IPT breaker. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 598 | MA | Eversource |  |  | 2018-10-01 | Cape Wind | At Canal 345 kV substation, install a redundant breaker in series with breaker #312. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 596 | MA | Eversource |  |  | 2018-10-01 | Cape Wind | Installation of (2) 115 kV circuits out of Barnstable substation to interconnect Cape Wind. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 10/6/2005 2/11/2014 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 595 | MA | Eversource |  |  | 2018-10-01 | Cape Wind | Expansion of Barnstable 115 kV substation to include a circuit breaker in the fourth bay and a circuit breaker in the fifth bay. Installation of (4) 35 MVAR shunt reactors and (2) capacitor filter banks at the Barnstable 115 kV substation. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 10/6/2005 2/11/2014 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 593 | MA | Eversource |  |  | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Bourne and Barnstable/Falmouth/equivalent | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 592 | MA | Eversource |  |  | 2013-06-01 | Long Term Lower SEMA Upgrades | Separate existing 345 kV double circuit Cape Cod Canal crossing. The lines being separated are 322 (Canal-Carver) and 342 (Canal-Pilgrim-Auburn) | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 07/2011 | 2011-12-16 | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | #VALUE!
Reliability Upgrade | 1a | 582 | CT | Eversource |  |  | 2011-06-01 |  | Separate 310 (Manchester-Millstone) and 368 (Manchester-Card) 345 kV lines and create 368/1767 DCT | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-07-18 | 2011-03-25 | 10456000 | 10456000 | 10456000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 0
Reliability Upgrade | 1a | 576 | CT | Eversource |  |  | 2017 | NEEWS (Central Connecticut Reliability Project) | Build new 345 kV line 3208 North Bloomfield - Frost Bridge. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 9/24/2008 5/4/2012 | No | 313000000 | 338000000 | 338000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 0
Generator Interconnection Upgrade | 2a | 505 | MA | National Grid, USA |  |  | 2012-12-01 | Hoosac Wind Farm | Tap Y-25S line between Harriman and Deerfield 5. Construct 69/34.5 kV substation and 34.5 kV line connecting 30 MW generating facility with the 69 kV system. | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 02/01/2005 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 484 | RI | National Grid, USA |  |  | 2012-02-01 | Greater Rhode Island Transmission Reinforcements | Add (1) new 115 kV breaker at Woonsocket. | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-04-25 | No | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 0
Generator Interconnection Upgrade | 2a | 331 | CT | Eversource |  |  | 2011-06-01 | Kleen Energy | Install 5-breaker ring bus interconnecting between Scovill Rock and Manchester on the 345 kV 353 Line. | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 10/08/2003 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 325 | VT | Vermont Electric Power Company |  |  | TBD | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 324 | VT | Vermont Electric Power Company |  |  | TBD |  | Granite to Middlesex 230 kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 323 | VT | Vermont Electric Power Company |  |  | 2010-12-01 | Vermont Southern Loop Project | New VY - Newfane - Coolidge 345 kV line with requisite station upgrades. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-10-01 | 2010-05-17 | 116000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 0
Reliability Upgrade | 1a | 318 | VT | Vermont Electric Power Company |  |  | 2012-10-01 | Georgia Substation Rebuild | Rebuild the existing Georgia substation 115 kV bus into a ring bus | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-11-22 | 2012-12-13 | 20000000 | 18000000 | 16000000 | 16000000 | 16000000 | 16000000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 0
Reliability Upgrade | 1a | 301 | MA | Eversource |  |  | 2011-12-01 | Greater Boston - Central | Reconductor 115 kV circuits 320-507 and 320-508. (Lexington - Waltham) | Concept | Concept | Concept | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-02-15 | 2011-12-16 | 8400000 | 8400000 | 8400000 | 9600000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 0
Reliability Upgrade | 1a | 277 | NH | Eversource |  |  | 2011-11-01 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345 kV breakers at Deerfield substation. | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-06-29 | 2011-07-15 | 52000000 | 52000000 | 52000000 | 52000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 0
Reliability Upgrade | 1a | 259 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV line 1426, Cadwell to Orchard | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 196 | MA | Eversource |  |  | 2013-03-01 | NEEWS (Greater Springfield Reliability Project) | Build new 345 kV line (3216), Agawam (MA) - North Bloomfield (CT) (MA portion) | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 191 | CT | Eversource |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | Build new 345 kV Line 341, Lake Road - CT/RI border West Farnum | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 9/24/2008 5/4/2012 | 2015-12-17 | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | #VALUE!
Reliability Upgrade | 1a | 190 | MA | National Grid, USA |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | New 345 kV (366) line Millbury to MA/RI state line | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 9/24/2008 5/4/2012 | 2015-12-17 | 69600000 | 81800000 | 81800000 | 81800000 | 67300000 | 62300000 | 62300000 | 62300000 | 62300000 | 62300000 | 69500000 | 69500000 | 80560000 | 80560000 | 80560000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 0
Reliability Upgrade | 1a | 162 | MA | National Grid, USA |  |  | 2010-10-01 |  | Q-169 Golden Hills to Lynn 115 kV line upgrade. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2005-09-02 | 2008-04-25 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 0
Reliability Upgrade | 1a | 144 | ME | Bangor Hydro-Electric Company |  |  | 2010-12-01 | Keene Rd Autotransformer | Installation of a 345/115 kV autotransformer at Keene Rd Substation. | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-10-22 | 2011-07-15 | 29000000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 0
Reliability Upgrade | 1a | 143 | ME | Bangor Hydro-Electric Company |  |  | 2012-12-01 | Down East Reliability Improvement | Construct 115 kV line from Trenton tap (Waltham Road Junction) to new Tunk Lake Substation (3 new breakers) to Harrington (Columbia Tap) & new Epping Switching Station (5 new breakers) | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2006-05-10 | 2008-06-13 | 66100000 | 66100000 | 66100000 | 66100000 | 66100000 | 61000000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 0
Reliability Upgrade | 1b | 139 | VT | Vermont Electric Power Company |  |  | TBD | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Planned | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 01/10/2003 | 03/31/2003 | TBD | TBD | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 85 | CT | Eversource |  |  | 2013-12-01 |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | Concept | Concept | Concept | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 08/04/2004 Updated 9/7/2011 | 2014-12-09 | TBD | TBD | TBD | TBD | 13600000 | 13600000 | 13600000 | 13600000 | 13600000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 0
Reliability Upgrade | 1a | 59 | MA | National Grid, USA |  |  | 2012-12-01 | Auburn Area Transmission System Upgrades | G18, F19 line terminal 115 kV upgrades at Bridgewater sub | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-01-28 | 2014-02-03 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | #VALUE!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## 06_2026_RSP
June 2026 ISO-NEW ENGLAND Project List Update - ISO-NE Public
Primary Driver | Part# | Project ID | State | Primary Equipment Owner | Other Equipment Owner(s) | Footnote Number | Projected In-Service Month/Year | Major Project | Project | Oct-10 Status | Apr-11 Status | Jun-11 Status | Nov-11 Status | Mar-12 Status | Jun-12 Status | Oct-12 Status | Mar-13 Status | Jun-13 Status | Oct-13 Status | Mar-14 Status | Jun-14 Status | Oct-14 Status | Mar-15 Status | Jun-15 Status | Oct-15 Status | Mar-16 Status | Jun-16 Status | Oct-16 Status | Mar-17 Status | Jun-17 Status | Oct-17 Status | Mar-18 Status | Jun-18 Status | Oct-18 Status | Mar-19 Status | Jun-19 Status | Oct-19 Status | Mar-20 Status | Jun-20 Status | Oct-20 Status | Mar-21 Status | Jun-21 Status | Oct-21 Status | Mar-22 Status | Jun-22 Status | Oct-22 Status | Mar-23 Status | Jun-23 Status | Oct-23 Status | Mar-24 Status | Jun-24 Status | Oct-24 Status | Mar-25 Status | Jun-25 Status | Oct-25 Status | Mar-26 Status | Jun-26 Status | Is the project Grandfathered on May 18, 2015 (not updated since March 2017) | PPA (I.3.9) Approval | TCA Approval | Oct-10 Estimated PTF Costs | Apr-11 Estimated PTF Costs | Jun-11 Estimated PTF Costs | Nov-11 Estimated PTF Costs | Mar-12 Estimated PTF Costs | Jun-12 Estimated PTF Costs | Oct-12 Estimated PTF Costs | Mar-13 Estimated PTF Costs | Jun-13 Estimated PTF Costs | Oct-13 Estimated PTF Costs | Mar-14 Estimated PTF Costs | Jun-14 Estimated PTF Costs | Oct-14 Estimated PTF Costs | Mar-15 Estimated PTF Costs | Jun-15 Estimated PTF Costs | Oct-15 Estimated PTF Costs | Mar-16 Estimated PTF Costs | Jun-16 Estimated PTF Costs | Oct-16 Estimated PTF Costs | Mar-17 Estimated PTF Costs | Jun-17 Estimated PTF Costs | Oct-17 Estimated PTF Costs | Mar-18 Estimated PTF Costs | Jun-18 Estimated PTF Costs | Oct-18 Estimated PTF Costs | Mar-19 Estimated PTF Costs | Jun-19 Estimated PTF Costs | Oct-19 Estimated PTF Costs | Mar-20 Estimated PTF Costs | Jun-20 Estimated PTF Costs | Oct-20 Estimated PTF Costs | Mar-21 Estimated PTF Costs | Jun-21 Estimated PTF Costs | Oct-21 Estimated PTF Costs | Mar-22 Estimated PTF Costs | Jun-22 Estimated PTF Costs | Oct-22 Estimated PTF Costs | Mar-23 Estimated PTF Costs | Jun-23 Estimated PTF Costs | Oct-23 Estimated PTF Costs | Mar-24 Estimated PTF Costs | Jun-24 Estimated PTF Costs | Oct-24 Estimated PTF Costs | Mar-25 Estimated PTF Costs | Jun-25 Estimated PTF Costs | Oct-25 Estimated PTF Costs | Mar-26 Estimated PTF Costs | Jun-26 Estimated PTF Costs
TABLE A
MAINE
Generator Interconnection Upgrade | 2a | 1937 | ME | Central Maine Power Company |  |  | 2029-11-01 | Queue Position 1100 | Replace structure to increase the Summer Long Time Emergency rating of the 6.5 mile 82-2 segment of 115 kV line Section 82, from Detroit to the Section 82A Tap | [46 empty] | Planned | Planned |  | 2025-09-24 | NR | [46 empty] | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1936 | ME | Central Maine Power Company |  |  | 2029-11-01 | Queue Position 1100 | Install two static 10 MVAR, 115 kV shunt capacitor blocks, with necessary switchgear, at the Dogtown 115 kV bus. | [46 empty] | Planned | Planned |  | 2025-09-24 | NR | [46 empty] | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1917 | ME | Central Maine Power Company |  |  | 2028-12-31 | ME 2028 Short Circuit Solutions | Replace six 115 kV circuit breakers at Larrabee Road substation | [41 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | NR | No | [41 empty] | 5501609 | 5501609 | 5501609 | 5501609 | 5501609 | 5501609 | 5501609 | 0
Reliability Upgrade | 1a | 1914 | ME | Versant Power |  |  | 2026-12-01 | UME 2029 Solutions | Install a new 80 MVAR reactor, reconfigure the existing two reactors at the 345 kV Orrington substation | [40 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction |  | 2024-04-23 | 2026-02-13 | [40 empty] | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 0
Generator Interconnection Upgrade | 2a | 1905 | ME | Versant Power |  |  | 2026-08-01 | Queue Position 833 | Addition of a new 115 kV Three Rivers Switching Station on line 93 between Bull Hill and Deblois | [36 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction |  | 11/8/2021 05/31/2023 | NR | [36 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1899 | ME | Central Maine Power Company |  |  | 2028-05-01 | Queue Position 1086 | Install a 115 kV three-breaker ring bus on CMP Section 80, approximately 2 miles from Highland Station | [35 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2022-03-21 | NR | [35 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1885 | ME | Central Maine Power Company |  |  | 2029-12-31 | UME 2029 Solutions | Install a +50/-25 MVAR synchronous condenser at Highland 115 kV substation | [33 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2023-08-29 | No | [33 empty] | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 0
Reliability Upgrade | 1a | 1884 | ME | Central Maine Power Company |  |  | 2029-12-31 | UME 2029 Solutions | Install a 15 MVAR capacitor at Belfast 115 kV substation | [33 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2023-08-29 | No | [33 empty] | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 0
Reliability Upgrade | 1a | 1883 | ME | Central Maine Power Company |  |  | 2028-12-31 | UME 2029 Solutions | Convert the Highland 115 kV substation to an eight breaker, breaker-and-a-half configuration with a bus connected 115/34.5 kV transformer | [33 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2023-08-29 | No | [33 empty] | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 0
NEW HAMPSHIRE
Elective Upgrade | 4a | 1758 | NH | Eversource |  |  | 2027-12-01 | Queue Position 501 | Uprate the A152 (Chestnut Hill - Westport - A152 Tap) 115 kV line | [20 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2016-11-01 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1757 | NH | Eversource |  |  | 2027-12-01 | Queue Position 501 | Uprate the N186 (Vernon Road Tap - Chestnut Hill) 115 kV line | [20 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2016-11-01 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1697 | NH | Eversource |  |  | 2027-12-01 | Queue Position 501 | Reconductor ES's section of the 381 (Vernon - Northfield) 345 kV line. (NH portion) | [18 empty] | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2016-11-01 | NR | [18 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
VERMONT
Generator Interconnection Upgrade | 2a | 1813 | VT | Vermont Electric Power Company |  |  | 2028-10-01 | Queue Position 807 | Expand bus work and add a 115 kV breaker to connect QP 807 Solar PV project to the Vergennes 115 kV Substation. | [29 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2020-03-24 | NR | [29 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1754 | VT | Vermont Electric Power Company |  |  | 2027-12-01 | Queue Position 501 | Reconductor the K43 (New Haven - Williston) 115 kV line | [20 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2016-11-01 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1753 | VT | Vermont Electric Power Company |  |  | 2027-12-01 | Queue Position 501 | Reconductor the K27 (Williston - Tafts Corner) 115 kV line | [20 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2016-11-01 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1752 | VT | Vermont Electric Power Company |  |  | 2027-12-01 | Queue Position 501 | Replace a line drop for the K30 (Middlebury - Florance) 115 kV line | [20 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2016-11-01 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1750 | VT | Vermont Electric Power Company |  |  | 2027-12-01 | Queue Position 501 | Reconductor VELCO's section of the 381 (Vernon - Northfield) 345 kV line | [20 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2016-11-01 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1749 | VT | Vermont Electric Power Company |  |  | 2027-12-01 | Queue Position 501 | Add two 345 kV circuit breakers at the Coolidge 345 kV substation | [20 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2016-11-01 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1545 | VT | Vermont Electric Power Company |  |  | 2027-12-01 | Queue Position 501 | New 1000 MW 320 kV HVDC Line, complete with two HVDC terminal stations, from a HQ station near Monteregie substation in Quebec to the VELCO 345/115 kV Coolidge substation in VT | [10 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2016-11-01 | NR | [10 empty] | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
MASSACHUSETTS
Generator Interconnection Upgrade | 2a | 1939 | MA | National Grid, USA |  |  | 2026-11-01 | Queue Position 1320 | Install a new 115 kV three breaker ring bus substation, to be named Quaker St., on NEP’s R-144N line, between NEP’s Millbury Substation and RIE’s Woonsocket Substation, to interconnect QP1320 | [47 empty] | Under Construction |  | 2024-12-05 | NR | [47 empty] | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1932 | MA | Eversource |  |  | 2028-05-02 | Queue Position 1148 | Add one bay with two breakers to the existing Electric Ave substation #315 | [44 empty] | Planned | Planned | Planned | Planned |  | 2025-01-06 | NR | [44 empty] | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1927 | MA | Eversource |  |  | 2027-02-01 | Queue Position 1320 | Add a series breaker to the 115 kV Medway Ring #65 Substation | [44 empty] | Planned | Planned | Planned | Planned |  | 2024-12-05 | NR | [44 empty] | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1924 | MA | Eversource |  |  | 2028-03-01 | Queue Position 1110 | Install a 115 kV tie line between the existing Mystic 9 Unit 93 terminal and the Mystic substation fence line | [42 empty] | Planned | Planned | Planned | Planned | Planned | Planned |  | 2022-07-11 | NR | [42 empty] | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1920 | MA | Eversource |  |  | 2028-05-01 | Queue Position 1143 | Install new duct bank, termination stanchions, disconnect switch, CCVTs and other associated station upgrades at the Mystic #250 345 kV substation | [41 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2023-08-29 | NR | [41 empty] | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1919 | MA | Eversource |  |  | 2027-08-01 | Queue Position 1115 | Install one 115 kV circuit breaker, two 115 kV breaker disconnect switches and other associated substation upgrades at Chelsea #488 substation | [41 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2022-10-19 | NR | [41 empty] | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1918 | MA | Eversource |  |  | 2027-11-01 | SEMA 2028 Short Circuit Solutions | Replace six 115 kV circuit breakers at Barnstable substation | [41 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction |  | NR | No | [41 empty] | 13300000 | 13300000 | 13300000 | 13300000 | 13300000 | 16526000 | 16526000 | 0
Reliability Upgrade | 1a | 1908 | MA | National Grid, USA |  |  | 2029-03-01 | D-4 Protection System | Install a POTT protection system on the D-4 line via the A1/B2 lines | [37 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2022-07-20 | No | [37 empty] | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 430000 | 0
Generator Interconnection Upgrade | 2a | 1902 | MA | National Grid, USA |  |  | 2027-07-01 | Queue Position 877 | Convert the South Wrentham substation into a five breaker ring bus and upgrades of terminal equipment | [35 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 5/6/2022 4/27/2023 | NR | [35 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1901 | MA | National Grid, USA |  |  | 2027-07-01 | Queue Position 877 | Reconductor the C129S 115 kV line from South Wrentham to Union Street and C181N/D182N 115 kV lines from South Wrentham to Berry Street | [35 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 5/6/2022 4/27/2023 | NR | [35 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1870 | MA | Eversource |  |  | 2029-12-01 | Queue Position 700 | Convert the planned 115 kV Mid-Cape line to 345 kV | [31 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction |  | 2021-01-04 | NR | [31 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1869 | MA | Eversource |  |  | 2029-12-01 | Queue Position 700 | Install a second 345/115 kV transformer at the West Barnstable substation | [31 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2021-01-04 | NR | [31 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1868 | MA | Eversource |  |  | 2029-12-01 | Queue Position 700 | Add a third 115 kV breaker at the 115 kV West Barnstable substation | [31 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2021-01-04 | NR | [31 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1867 | MA | Eversource |  |  | 2029-12-01 | Queue Position 700 | Upgrade the West Barnstable 345 kV substation to a four bay GIS breaker-and-a-half design | [31 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2021-01-04 | NR | [31 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1866 | MA | Eversource |  |  | 2029-12-01 | Queue Position 700 | Construct a new Bourne 345 kV station as a breaker-and-a-half substation | [31 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2021-01-04 | NR | [31 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1730 | MA | Eversource |  |  | 2026-12-01 | Southeast Massachusetts/Rhode Island Reliability Project | Extend the 115 kV 114 line from Eversource/National Grid border to Industrial Park Tap | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | No | 2018-04-30 | No | [19 empty] | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 0
Reliability Upgrade | 1a | 1722 | MA | National Grid, USA |  |  | 2026-12-01 | Southeast Massachusetts/Rhode Island Reliability Project | Extend Line 114 - Dartmouth town line (Eversource- NGRID border) to Bell Rock (~4.2 miles) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | No | 2018-04-30 | No | [19 empty] | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 13944000 | 13944000 | 13944000 | 13944000 | 13944000 | 13944000 | 13944000 | 13944000 | 13944000 | 13944000 | 22616000 | 22616000 | 22616000 | 22616000 | 22616000 | 0
Reliability Upgrade | 1a | 1720 | MA | National Grid, USA |  |  | 2027-03-01 | Southeast Massachusetts/Rhode Island Reliability Project | Separate N12/M13 DCT & reconductor N12 & M13 between Somerset and Bell Rock (~3.5 miles) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | No | 10/24/2023 4/30/2018 | No | [19 empty] | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 80000000 | 101120000 | 101120000 | 101120000 | 101120000 | 101120000 | 101120000 | 101120000 | 101120000 | 101120000 | 101120000 | 0
RHODE ISLAND
Generator Interconnection Upgrade | 2a | 1928 | RI | Rhode Island Energy |  |  | 2028-12-02 | Queue Position 1163 | Construct new 115 kV Switching Station in North Kingstown | [44 empty] | Proposed | Proposed | Planned | Planned |  | 2025-03-20 | NR | [44 empty] | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1926 | RI | Rhode Island Energy |  |  | 2026-06-01 | Queue Position 1320 | Replace one 115 kV circuit breaker at the Woonsocket substation | [44 empty] | Planned | Planned | Planned | Under Construction |  | 2024-12-05 | NR | [44 empty] | NR | NR | NR | NR | #VALUE!
CONNECTICUT
Generator Interconnection Upgrade | 2a | 1938 | CT | Eversource |  |  | 2028-10-01 | Queue Position 1245 | Installation of a new 345 kV, 3-breaker ring bus switchyard on the line 3419 in Ellington, CT | [46 empty] | Planned | Planned |  | 2024-10-01 | NR | [46 empty] | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1930 | CT | Eversource |  |  | 2027-10-02 | Queue Position 1192 | Installation of a new 345 kV, 3-breaker ring bus switchyard in East Granby | [44 empty] | Planned | Planned | Planned | Planned |  | 2024-05-28 | NR | [44 empty] | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1929 | CT | Eversource |  |  | 2029-05-01 | Queue Position 1138 | Addition of a 115 kV 3-breaker ring-bus switchyard on the 1316 Line between Canterbury substation and Tunnel substation | [44 empty] | Planned | Planned | Planned | Planned |  | 2024-06-28 | NR | [44 empty] | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1922 | CT | Eversource |  |  | 2028-10-01 | Queue Position 1089 | Addition of a 115 kV disconnect switch at Devon substation and other supporting substation equipment | [41 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2022-12-19 | NR | [41 empty] | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1618 | CT | United Illuminating Company |  |  | 2030-04-01 |  | Old Town 115/13.8 kV Substation Rebuild | [12 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Y-Planned | 2014-09-09 | No | [12 empty] | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 28187834
TABLE B
MAINE
NEW HAMPSHIRE
VERMONT
MASSACHUSETTS
Reliability Upgrade | 1b | 1934 | MA | Eversource |  |  | 2027-03-01 | Boston 2033 Solutions Study | Protection systems modification associated with the Stoughton RAS at three 345 kV substations (Stoughton, West Walpole and Holbrook) and two 115 kV substations (Hyde Park and K-Street) | [44 empty] | Proposed | Proposed | Proposed | Proposed |  | No | No | [44 empty] | 3700000 | 3700000 | 3700000 | 3700000
Reliability Upgrade | 1b | 1933 | MA | Eversource |  |  | 2028-12-01 | Boston 2033 Solutions Study | Install one 80 MVAR shunt reactor at the 115 kV Electric Avenue Substation | [44 empty] | Proposed | Proposed | Proposed | Proposed |  | No | No | [44 empty] | 22300000 | 22300000 | 22300000 | 22300000
RHODE ISLAND
CONNECTICUT
In-service
CONNECTICUT
Reliability Upgrade | 1a | 1904 | CT | CMEEC |  |  | 2023-12-01 | Eastern CT 2029 Solutions | Convert 69kV equipment at Buddington to 115 kV to facilitate the conversion of the 400-2 line to 115 kV | [36 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [36 empty] | 5500000 | 5500000 | 6073478 | 6155823 | 6344392.8699 | 6397083.49 | 6397083.49 | 6397083.49 | 6397083.49 | 6397083.49 | 6397083.49 | 6397083.49 | 0
Reliability Upgrade | 1a | 1864 | CT | CMEEC |  |  | 2023-02-28 | Eastern CT 2029 Solutions | Convert the 400-2 Line Section to 115 kV (Border Bus to Buddington) | [30 empty] | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service |  | 2021-06-17 | No | [30 empty] | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 3200000 | 3200000 | 2792733 | 2833477 | 2836388 | 2858821 | 2858821 | 2858821 | 2858821 | 2858821 | 2858821 | 2858821 | 0
Reliability Upgrade | 1a | 1863 | CT | Eversource |  |  | 2022-03-01 | Eastern CT 2029 Solutions | Install a 1% series reactor with bypass switch at Mystic, CT on the 1465 Line | [30 empty] | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 4780000 | 4780000 | 4780000 | 4780000 | 4780000 | 4780000 | 4780000 | 4780000 | 4780000 | 4780000 | 4780000 | 4780000 | 0
Reliability Upgrade | 1a | 1862 | CT | Eversource |  |  | 2023-12-01 | Eastern CT 2029 Solutions | Install a +55/-29 MVAR synchronous condenser with two 115 kV breakers at Shunock | [30 empty] | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 43800000 | 43800000 | 43800000 | 43800000 | 43800000 | 43800000 | 40518000 | 40518000 | 40518000 | 40518000 | 40518000 | 40518000 | 40518000 | 40518000 | 40518000 | 40518000 | 40518000 | 40518000 | 0
Reliability Upgrade | 1a | 1861 | CT | Eversource |  |  | 2021-11-01 | Eastern CT 2029 Solutions | Install one 345 kV series breaker with the Montville 1T breaker | [30 empty] | Proposed | Proposed | Proposed | Planned | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3973000 | 3973000 | 3973000 | 3973000 | 3973000 | 3973000 | 3973000 | 3973000 | 3973000 | 3973000 | 3973000 | 3973000 | 0
Reliability Upgrade | 1a | 1860 | CT | Eversource |  |  | 2021-12-01 | Eastern CT 2029 Solutions | Install a 25.2 MVAR 115 kV capacitor and one breaker at Killingly | [30 empty] | Proposed | Proposed | Proposed | Planned | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 4823000 | 4823000 | 4823000 | 4823000 | 4823000 | 4823000 | 4823000 | 4823000 | 4823000 | 4823000 | 4823000 | 4823000 | 0
Reliability Upgrade | 1a | 1859 | CT | Eversource |  |  | 2023-02-01 | Eastern CT 2029 Solutions | Rebuild the 400-3 Line Section to allow operation at 115 kV (Gales Ferry to Ledyard Jct) | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service |  | 2021-06-17 | No | [30 empty] | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 6855000 | 6855000 | 6855000 | 6855000 | 6855000 | 6855000 | 6855000 | 6855000 | 6855000 | 6855000 | 6855000 | 6855000 | 0
Reliability Upgrade | 1a | 1858 | CT | Eversource |  |  | 2022-09-01 | Eastern CT 2029 Solutions | Rebuild 400-2 Line section to allow operation at 115 kV (Ledyard Jct. to Border Bus with CMEEC) | [30 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 15133000 | 15133000 | 15133000 | 15133000 | 15133000 | 15133000 | 15133000 | 15133000 | 15133000 | 15133000 | 15133000 | 15133000 | 0
Reliability Upgrade | 1a | 1857 | CT | Eversource |  |  | 2023-02-01 | Eastern CT 2029 Solutions | Add one 115 kV circuit breaker and re-terminate the 400-1 line section into Tunnel substation. Energize 400 Line at 115 kV | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service |  | 2021-06-17 | No | [30 empty] | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 7439000 | 7439000 | 7439000 | 7439000 | 7439000 | 7439000 | 7439000 | 7439000 | 7439000 | 7439000 | 7439000 | 7439000 | 0
Reliability Upgrade | 1a | 1856 | CT | Eversource |  |  | 2023-02-01 | Eastern CT 2029 Solutions | Rebuild 400-1 Line section to allow operation at 115 kV (Tunnel to Ledyard Jct.) | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service |  | 2021-06-17 | No | [30 empty] | 31600000 | 31600000 | 31600000 | 31600000 | 31600000 | 31600000 | 42917000 | 42917000 | 42917000 | 42917000 | 42917000 | 42917000 | 42917000 | 42917000 | 42917000 | 42917000 | 42917000 | 42917000 | 0
Reliability Upgrade | 1a | 1855 | CT | Eversource |  |  | 2023-06-01 | Eastern CT 2029 Solutions | Reterminate the 100 Line at Montville station and associated work. Energize the 100 Line at 115 kV | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8407000 | 8407000 | 8407000 | 8407000 | 8407000 | 8407000 | 8407000 | 8407000 | 8407000 | 8407000 | 8407000 | 8407000 | 0
Reliability Upgrade | 1a | 1854 | CT | Eversource |  |  | 2023-06-01 | Eastern CT 2029 Solutions | Rebuild the 100 Line from Montville to Gales Ferry to allow operation at 115 kV | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 0
Reliability Upgrade | 1a | 1853 | CT | Eversource |  |  | 2023-11-01 | Eastern CT 2029 Solutions | Convert Gales Ferry substation from 69 kV to 115 kV | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 13100000 | 13100000 | 13100000 | 13100000 | 13100000 | 13100000 | 17256000 | 17256000 | 17256000 | 17256000 | 17256000 | 17256000 | 17256000 | 17256000 | 17256000 | 17256000 | 17256000 | 17256000 | 0
Reliability Upgrade | 1a | 1852 | CT | Eversource |  |  | 2023-02-01 | Eastern CT 2029 Solutions | Install one 115 kV circuit breaker in series with Card substation 4T | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 1952000 | 1952000 | 1952000 | 1952000 | 1952000 | 1952000 | 1952000 | 1952000 | 1952000 | 1952000 | 1952000 | 1952000 | 0
Reliability Upgrade | 1a | 1851 | CT | Eversource |  |  | 2022-12-01 | Eastern CT 2029 Solutions | Upgrade Card 115 kV to BPS standards | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 20300000 | 20300000 | 20300000 | 20300000 | 20300000 | 20300000 | 17502000 | 17502000 | 17502000 | 17502000 | 17502000 | 17502000 | 17502000 | 17502000 | 17502000 | 17502000 | 17502000 | 17502000 | 0
Reliability Upgrade | 1a | 1850 | CT | Eversource |  |  | 2022-12-01 | Eastern CT 2029 Solutions | Install a second 345/115 kV autotransformer (4X) and one 345 kV breaker at Card substation | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 20100000 | 20100000 | 20100000 | 20100000 | 20100000 | 20100000 | 17394000 | 17394000 | 17394000 | 17394000 | 17394000 | 17394000 | 17394000 | 17394000 | 17394000 | 17394000 | 17394000 | 17394000 | 0
Generator Interconnection Upgrade | 2a | 1805 | CT | Eversource |  |  | 2020-03-01 | Queue Position 784 | Upgrade the 1029-2 line from Bunker Hill - Baldwin Tap | [28 empty] | Planned | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2019-12-30 | NR | [28 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1794 | CT | Eversource |  |  | 2021-12-01 | Queue Position 588 | Split the existing 115 kV 1000/1080 double circuit tower | [25 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2018-10-24 | NR | [25 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1793 | CT | Eversource |  |  | 2021-12-01 | Queue Position 588 | Construct a new three breaker ring bus Quinebaug 115 kV substation | [25 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2018-10-24 | NR | [25 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1764 | CT | Eversource |  |  | 2020-10-01 | Nutmeg Solar QP 552 | Install two 115 kV circuit breakers at Scitico substation and underground line to generator | [21 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2016-11-08 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1759 | CT | Eversource |  |  | 2019-05-01 | Queue Position 501 | Uprate ES's section of the 398 (Long Mountain - Pleasant Valley) 345 kV line | [20 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2018-06-22 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1701 | CT | Eversource |  |  | 2018-11-01 | PSEG Bridgeport Harbor FCA 10 QP 412 | Reconductor the 115 kV 1670-1 from ACSR to ACSS | [18 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2016-12-28 | NR | [18 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1687 | CT | Town of Wallingford, Department of Public Utilities (“WED”) |  |  | 2018-03-01 | Queue Position 440 | Replace the 795 kcml ACSR 115 kV transmission line from the Wallingford 13M 1305 Line to the Wallingford Energy 6G 1305 Line with 1590 kcml ACSR | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2/10/2015 | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1686 | CT | United Illuminating Company |  |  | 2019-06-01 | Queue Position 412 | Terminate and connect the 345 kV underground line from QP 412 to the Singer 345 kV Substation | [15 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2/10/2015 | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1679 | CT | Town of Wallingford Department of Public Utilities |  |  | 2015-04-01 | SWCT | 1630 13M Terminal Upgrade | [15 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | [15 empty] | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 82664 | 0
Generator Interconnection Upgrade | 2a | 1677 | CT | Eversource |  |  | 2018-06-01 | CPV Towantic | Rebuild 115 kV 1730 Line section between Devon to the UI Border/Trumbull 115 kV substation | [15 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 8/25/2015 | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1676 | CT | Eversource |  |  | 2018-06-01 | CPV Towantic | Rebuild 115 kV 1710 Line section between Devon to Trumbull | [15 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1675 | CT | Eversource |  |  | 2017-09-01 | CPV Towantic | Rebuild 115 kV 1575N-1 QP384 to Baldwin Tap | [15 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 8/25/2015 | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1659 | CT | Eversource |  |  | 2017-03-01 | GHCC | Increase the size of the existing 115 kV capacitor at Branford substation from 37.8 to 50.4 MVAR | [14 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [14 empty] | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 740000 | 0
Reliability Upgrade | 1a | 1622 | CT | United Illuminating Company |  |  | 2021-02-01 | SWCT | Baird to Housatonic River Crossing 88006A - 89006B 115 kV Line Upgrades | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2015-04-16 | 4/28/2020 | [12 empty] | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 59200000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 46390000 | 0
Reliability Upgrade | 1a | 1621 | CT | United Illuminating Company |  |  | 2018-08-01 | SWCT | Pootatuck 115 kV Ring Bus Expansion & Capacitor Bank Addition | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2017-01-03 | [12 empty] | 11900000 | 11900000 | 11900000 | 11900000 | 11900000 | 11900000 | 11900000 | 11900000 | 11900000 | 11560000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 11040000 | 0
Reliability Upgrade | 1a | 1620 | CT | United Illuminating Company |  |  | 2018-10-01 | SWCT | Ansonia 115 kV Capacitor Bank Additions | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2018-08-24 | [12 empty] | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 10030000 | 10030000 | 10030000 | 9700000 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 9518528 | 0
Reliability Upgrade | 1a | 1619 | CT | United Illuminating Company |  |  | 2014-12-01 | SWCT | Mill River 115 kV Fault Duty & TRV Mitigation | [12 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2018-08-24 | [12 empty] | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 0
Generator Interconnection Upgrade | 2a | 1610 | CT | Eversource |  |  | 2017-09-01 | CPV Towantic | Reconductor 115 kV 1575S Line section between QP 384 and Oxford Substations | [12 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 8/8/2014 8/25/2015 | NR | [12 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1609 | CT | Eversource |  |  | 2017-09-01 | CPV Towantic | Reconductor 115 kV 1585N Line section between QP 384 and Bunker Hill Substations | [12 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 8/8/2014 8/25/2015 | NR | [12 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1608 | CT | Eversource |  |  | 2017-09-01 | CPV Towantic | Build new QP 384 115 kV Substation and Terminate 1575, 1585, and 1990 115 kV Lines into QP 384 115 kV Substation | [12 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2014-08-08 | NR | [12 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1607 | CT | Eversource |  |  | 2015-12-01 | Asset Replacement | Replace both 345/115 kV Montville autotransformers | [12 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2014-08-08 | 2015-10-02 | [12 empty] | 18900000 | 18900000 | 17000000 | 17000000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 16979000 | 0
Reliability Upgrade | 1a | 1606 | CT | Eversource |  |  | 2018-08-01 |  | 1779 Line Partial Rebuild | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2/25/2015 10/21/2016 | 2016-06-30 | [12 empty] | 29000000 | 29000000 | 29000000 | 29000000 | 29000000 | 29000000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 26592000 | 0
Reliability Upgrade | 1a | 1605 | CT | Eversource |  |  | 2016-12-01 | GHCC | Separation of 115 kV double circuit towers corresponding to the Middletown – Pratt and Whitney line (1572) and the Middletown to Haddam (1620) line | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 0
Reliability Upgrade | 1a | 1604 | CT | Eversource |  |  | 2015-12-01 | GHCC | Add a 37.8 MVAR capacitor bank at Hopewell 115 kV substation | [12 empty] | Proposed | Proposed | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2015-11-25 | [12 empty] | 4300000 | 4300000 | 4300000 | 4300000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 0
Reliability Upgrade | 1a | 1603 | CT | Eversource |  |  | 2018-06-01 | GHCC | Redesign the Green Hill 115 kV substation from a straight bus to a ring bus and add two 25.2 MVAR capacitor banks | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 7600000 | 7600000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 0
Reliability Upgrade | 1a | 1602 | CT | Eversource |  |  | 2015-12-01 | GHCC | Terminal Equipment upgrades on the Middletown to Portland Line (1443) | [12 empty] | Proposed | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | 2021-04-14 | [12 empty] | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 0
Reliability Upgrade | 1a | 1601 | CT | Eversource |  |  | 2015-12-01 | GHCC | Terminal Equipment upgrades on the Middletown to Dooley Line (1050) | [12 empty] | Proposed | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | 2021-04-14 | [12 empty] | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 0
Reliability Upgrade | 1a | 1600 | CT | Eversource |  |  | 2017-03-01 | GHCC | Separation of 115 kV double circuit towers corresponding to the Branford – Branford RR line (1537) and the Branford to North Haven (1655) line and adding a series breaker at Branford 115 kV substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 0
Reliability Upgrade | 1a | 1599 | CT | Eversource |  |  | 2017-02-01 | GHCC | Terminal equipment upgrades on the 345 kV line between Haddam and Beseck (362) | [12 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | 2021-04-14 | [12 empty] | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 0
Reliability Upgrade | 1a | 1598 | CT | Eversource |  |  | 2017-04-01 | GHCC | Add a 2nd 345/115 kV autotransformer at Haddam substation and reconfigure the 3-terminal 345 kV 348 line into 2 two-terminal lines | [12 empty] | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2015-11-25 | [12 empty] | 46700000 | 46700000 | 46700000 | 46730000 | 46730000 | 46730000 | 46730000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 42000000 | 0
Reliability Upgrade | 1a | 1597 | CT | Eversource |  |  | 2017-12-01 | GHCC | Separation of 115 kV DCT corresponding to the Bloomfield to North Bloomfield (1777) line and the North Bloomfield – Rood Avenue – Northwest Hartford (1751) line and add a breaker at North Bloomfield 115 kV substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 20100000 | 20100000 | 20100000 | 20100000 | 20100000 | 20100000 | 20100000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 20128000 | 0
Reliability Upgrade | 1a | 1596 | CT | Eversource |  |  | 2020-07-01 | GHCC | Install a 115 kV 3% series reactor on the underground cable between South Meadow and Southwest Hartford (1704) | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 0
Reliability Upgrade | 1a | 1595 | CT | Eversource |  |  | 2017-12-01 | GHCC | Separation of 115 kV DCT corresponding to the Bloomfield to South Meadow (1779) line and the Bloomfield to North Bloomfield (1777) line and add a breaker at Bloomfield 115 kV substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 7104000 | 0
Reliability Upgrade | 1a | 1594 | CT | Eversource |  |  | 2020-03-01 | GHCC | Reconductor the 115 kV line between Newington and Newington Tap (1783) - 0.01 mile | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 0
Reliability Upgrade | 1a | 1593 | CT | Eversource |  |  | 2018-06-01 | GHCC | Add a 115 kV 25.2 MVAR capacitor at Westside 115 kV substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 0
Reliability Upgrade | 1a | 1592 | CT | Eversource |  |  | 2017-11-01 | GHCC | Reconfigure the Berlin 115 kV substation including the addition of two 115 kV breakers and the relocation of a capacitor bank | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 4234000 | 0
Reliability Upgrade | 1a | 1591 | CT | Eversource |  |  | 2017-05-01 | GHCC | Loop the 1779 line between South Meadow and Bloomfield into the Rood Avenue substation and reconfigure the Rood Avenue substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 0
Reliability Upgrade | 1a | 1590 | CT | Eversource |  |  | 2020-09-01 | GHCC | Add a 3.7 mile 115 kV hybrid overhead/underground line from Newington to Southwest Hartford and associated terminal equipment including a 1.4% series reactor | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 4/16/2015 7/25/2018 | 2021-04-14 | [12 empty] | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 61200000 | 61200000 | 61200000 | 61200000 | 61200000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 0
Reliability Upgrade | 1a | 1589 | CT | Eversource |  |  | 2018-12-01 | GHCC | Add a new control house at Southington 115 kV substation | [12 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | 2021-04-14 | [12 empty] | 22600000 | 22600000 | 22600000 | 22600000 | 22600000 | 22600000 | 22600000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 22626000 | 0
Reliability Upgrade | 1a | 1588 | CT | Eversource |  |  | 2017-05-01 | GHCC | Add a breaker in series with breaker 5T at the Southington 345 kV switchyard | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 1807000 | 0
Reliability Upgrade | 1a | 1587 | CT | Eversource |  |  | 2019-06-01 | GHCC | Replace the normally open 19T breaker at Southington with a 3% series reactor between Southington Ring 1 and Southington Ring 2 and associated substation upgrades | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 0
Reliability Upgrade | 1a | 1586 | CT | Eversource |  |  | 2018-12-01 | GHCC | Replace the existing 3% series reactors on the 115 kV lines between Southington and Todd (1910) and between Southington and Canal (1950) with 5% series reactors | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 | [12 empty] | 5200000 | 5200000 | 5200000 | 5200000 | 5200000 | 5200000 | 5200000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 5185000 | 0
Reliability Upgrade | 1a | 1585 | CT | Eversource |  |  | 2016-12-01 | GHCC | Upgrade terminal equipment on the 115 kV line between Chippen Hill and Lake Avenue Junction (1810-3). Reconductor the 115 kV line between Southington and Lake Avenue Junction (1810-1) – 5.2 miles | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2016-10-04 | [12 empty] | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 0
Reliability Upgrade | 1a | 1584 | CT | Eversource |  |  | 2018-06-01 | GHCC | Separation of 115 kV DCT corresponding to the Frost Bridge to Campville (1191) line and the Thomaston to Campville (1921) line and add a breaker at Campville 115 kV substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2016-10-04 | [12 empty] | 5500000 | 5500000 | 5500000 | 5500000 | 5500000 | 5500000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 5530000 | 0
Reliability Upgrade | 1a | 1583 | CT | Eversource |  |  | 2017-12-01 | GHCC | Add a new 10.35 mile, 115 kV line from Frost Bridge to Campville and associated terminal equipment | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2016-10-04 | [12 empty] | 45500000 | 45500000 | 45500000 | 45500000 | 45500000 | 45500000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 45523000 | 0
Reliability Upgrade | 1a | 1582 | CT | Eversource |  |  | 2015-12-01 | GHCC | Add a 345 kV breaker in series with breaker 24T at the Manchester 345 kV switchyard | [12 empty] | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2015-11-25 | [12 empty] | 2100000 | 2100000 | 2100000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 0
Reliability Upgrade | 1a | 1581 | CT | Eversource |  |  | 2016-04-01 | GHCC | Reconductor the 115 kV line between Manchester and Barbour Hill (1763) – 7.6 miles | [12 empty] | Proposed | Proposed | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2015-11-25 | [12 empty] | 13500000 | 13500000 | 13500000 | 13600000 | 13600000 | 13600000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 8750000 | 0
Reliability Upgrade | 1a | 1580 | CT | Eversource |  |  | 2015-12-01 | GHCC | Add a new 345/115 kV autotransformer at Barbour Hill and associated terminal equipment | [12 empty] | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2015-11-25 | [12 empty] | 31200000 | 31200000 | 31200000 | 31200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 26200000 | 0
Reliability Upgrade | 1a | 1578 | CT | Eversource |  |  | 2018-06-01 | SWCT | Install a synchronous condenser (+25/-12.5 MVAR) @ Stony Hill | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 22200000 | 0
Reliability Upgrade | 1a | 1577 | CT | Eversource |  |  | 2018-05-01 | SWCT | Reconfigure 1887 line into a 3 terminal line (Plumtree - W. Brookfield - Shepaug) and Reconfigure 1770 line into 2 two terminal lines between Plumtree - Stony Hill and Stony Hill - Bates Rock | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 4376000 | 0
Reliability Upgrade | 1a | 1576 | CT | Eversource |  |  | 2018-05-01 | SWCT | Relocate 22K 115 kV capacitor bank (37.8 MVAR) to the same side as the 10K (25.2 MVAR) cap bank at Stony Hill | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 0
Reliability Upgrade | 1a | 1575 | CT | Eversource |  |  | 2016-12-01 | SWCT | Reconductor the 1575 Line (Bunker Hill – Baldwin Junction; 3.0 miles) | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 2450000 | 0
Reliability Upgrade | 1a | 1574 | CT | Eversource |  |  | 2019-12-01 | SWCT | Reconductor the 1470-3 line from Peaceable to Ridgefield Junction (0.04 miles) | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 0
Reliability Upgrade | 1a | 1573 | CT | Eversource |  |  | 2019-12-01 | SWCT | Reconductor the 1470-1 line from Wilton to Ridgefield Junction (5.1 miles) | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 0
Reliability Upgrade | 1a | 1572 | CT | Eversource |  |  | 2017-05-01 | SWCT | Rebuild a portion of 1682 line from Wilton to Norwalk and upgrade Wilton Substation terminal equipment (1.5 miles) | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 0
Reliability Upgrade | 1a | 1570 | CT | Eversource |  |  | 2015-12-01 | SWCT | Replace two Freight breakers with new breakers having 63 kA interrupting capability | [12 empty] | Proposed | Proposed | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2016-04-15 | [12 empty] | 1100000 | 1100000 | 1100000 | 1050000 | 1050000 | 1050000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 0
Reliability Upgrade | 1a | 1568 | CT | Eversource |  |  | 2018-07-01 | SWCT | Loop the 1570 line in and out of Pootatuck Substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 1800000 | 1800000 | 890000 | 890000 | 890000 | 890000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 0
Reliability Upgrade | 1a | 1567 | CT | Eversource |  |  | 2017-04-01 | SWCT | Reduce 12Y-10K (25.2 MVAR) capacitor cans @ Rocky River to 14.4 MVAR | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 0
Reliability Upgrade | 1a | 1566 | CT | Eversource |  |  | 2015-12-01 | SWCT | Upgrade 1876 line terminal equipment at Newtown Substation | [12 empty] | Proposed | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | 2016-04-15 | [12 empty] | 100000 | 100000 | 100000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | 0
Reliability Upgrade | 1a | 1565 | CT | Eversource |  |  | 2017-04-01 | SWCT | Relocate the existing 37.8 MVAR capacitor bank from 115 kV B bus to 115 kV A bus at Plumtree Substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2810000 | 2810000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000 | 0
Reliability Upgrade | 1a | 1564 | CT | Eversource |  |  | 2018-06-01 | SWCT | Install a new 115 kV line from Plumtree to Brookfield Junction (3.4 miles) | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 20500000 | 0
Reliability Upgrade | 1a | 1563 | CT | Eversource |  |  | 2017-12-01 | SWCT | Install 2 x 14.4 MVAR capacitor banks at West Brookfield Substation on 1618 line terminal | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 0
Reliability Upgrade | 1a | 1562 | CT | Eversource |  |  | 2016-05-01 | SWCT | Install a 115 kV circuit breaker (63 kA interrupting capability) in series with the existing 29T breaker at Plumtree Substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2016-06-30 | [12 empty] | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 2770000 | 0
Reliability Upgrade | 1a | 1561 | CT | Eversource |  |  | 2020-11-01 | SWCT | Reconductor the 1887 line between West Brookfield and West Brookfield Junction (1.4 miles) | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 0
Reliability Upgrade | 1a | 1560 | CT | Eversource |  |  | 2017-09-01 | SWCT | Close the normally open 115 kV 2T circuit breaker at Baldwin Substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2019-02-15 | [12 empty] | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 1585000 | 0
Reliability Upgrade | 1a | 1559 | CT | Eversource |  |  | 2016-03-01 | SWCT | Install a 115 kV 25.2 MVAR capacitor bank at Oxford Substation on 1319 line terminal | [12 empty] | Proposed | Proposed | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2015-04-15 | [12 empty] | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 0
Reliability Upgrade | 1a | 1555 | CT | United Illuminating Company |  |  | 2017-08-01 |  | Housatonic River Crossing 88006A & 89006B 115 kV line rebuild project - Housatonic River between Milford and Stratford CT | [11 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-07-17 | 2015-12-17 | [11 empty] | 16000000 | 16000000 | 16900000 | 17700000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 19750000 | 0
Reliability Upgrade | 1a | 1534 | CT | Eversource |  |  | 2015-10-01 | Newtown Breaker Addition | Newtown Substation 115 kV circuit breaker addition | [10 empty] | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2014-02-11 | NR | [10 empty] | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 0
Reliability Upgrade | 1a | 1533 | CT | Eversource |  |  | 2019-12-01 | Cos Cob Breaker Addition | Add two new 115 kV circuit breakers at the Cos Cob Substation and reposition 1750 line termination to accommodate Greenwich area Substation | [10 empty] | Concept | Concept | Concept | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2/11/2014 5/1/2015 | No | [10 empty] | TBD | TBD | TBD | TBD | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 0
Reliability Upgrade | 1a | 1498 | CT | Eversource |  |  | 2013-12-01 | SNEW 115 kV Substation | Construct a new 115 kV substation by looping the 1890 line into the new substation | [7 empty] | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/7/2012 | 2015-02-20 | [7 empty] | 13200000 | 13200000 | 13200000 | 9600000 | 9600000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 0
Reliability Upgrade | 1a | 1497 | CT | Eversource |  |  | 2013-12-01 | TTD's Fitch St 115 kV Substation | Loop the 1416 line into the new TTD 115 kV substation | [7 empty] | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/17/2012 | 2015-08-04 | [7 empty] | 1500000 | 1500000 | 1500000 | 2120000 | 2120000 | 2120000 | 2120000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 2267000 | 0
Reliability Upgrade | 1a | 1400 | CT | Eversource |  |  | 2014-09-01 | SWCT | Add a 150 MVAR 345 kV shunt reactor at the Haddam Neck Station | [6 empty] | Concept | Proposed | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 5/4/2012 7/2/2013 | 2015-02-20 | [6 empty] | TBD | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 9425000 | 0
Reliability Upgrade | 1a | 1399 | CT | Eversource |  |  | 2015-12-01 | SWCT | East Devon 345 kV voltage 11T Series Breaker addition | [6 empty] | Proposed | Concept | Concept | Concept | Concept | Concept | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2016-04-15 | [6 empty] | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 1936000 | 1936000 | 1936000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 0
Reliability Upgrade | 1a | 1389 | CT | United Illuminating Company |  |  | 2016-03-01 | SWCT | Hawthorne 115 kV Capacitor Bank Addition | [6 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 10/5/2012 2/27/2014 | 2015-12-17 | [6 empty] | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 9460000 | 0
Reliability Upgrade | 1a | 1386 | CT | United Illuminating Company |  |  | 2016-12-01 | SWCT | Mix Avenue 115 kV Capacitor Bank Additions, Series Reactor Addition and Terminal Modifications | [6 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 10/5/2012 11/8/2012 4/16/2015 | 2016-12-06 | [6 empty] | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 22000000 | 22000000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 21700000 | 0
Reliability Upgrade | 1a | 1385 | CT | United Illuminating Company |  |  | 2017-03-01 | SWCT | Sackett 115 kV PAR Removal - Terminal Modifications | [6 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-11-08 | NR | [6 empty] | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 0
Reliability Upgrade | 1a | 1384 | CT | United Illuminating Company |  |  | 2016-11-01 | SWCT | Milvon to Devon Tie 88005A - 89005B 115 kV Line Upgrade | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-08-27 | 2015-04-17 | [6 empty] | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 27300000 | 37500000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 30900000 | 0
Reliability Upgrade | 1a | 1383 | CT | United Illuminating Company |  |  | 2017-01-01 | SWCT | North Haven to Walrec 1630-3 115 kV relay upgrade (formerly known as North Haven to Walrec 1630-3 line & relay upgrade) | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-08-27 | NR | [6 empty] | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 0
Reliability Upgrade | 1a | 1381 | CT | United Illuminating Company |  |  | 2018-05-01 | SWCT | Baird 115/13.8 kV Substation Rebuild (formerly known as Baird 115 kV Bus Upgrade) | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 8/27/2012 9/9/2014 | 2017-01-03 | [6 empty] | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 8900000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 20400000 | 20400000 | 17820000 | 17820000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 15487000 | 0
Reliability Upgrade | 1a | 1380 | CT | United Illuminating Company |  |  | 2018-12-01 | SWCT | Baird to Congress 8809A - 8909B 115 kV Line Upgrades | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-08-27 | 2016-10-04 | [6 empty] | 33100000 | 33100000 | 33100000 | 33100000 | 33100000 | 44300000 | 56300000 | 56300000 | 56300000 | 56300000 | 73300000 | 73300000 | 73300000 | 73300000 | 73300000 | 73300000 | 73300000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 56629000 | 0
Reliability Upgrade | 1a | 1378 | CT | Eversource |  |  | 2013-03-01 | NEEWS (Greater Springfield Reliability Project) | Build new 345 kV Line (3216) Agawam (MA) - North Bloomfield (CT) (CT portion) | [5 empty] | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 5/4/2012 | 2014-02-25 | [5 empty] | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1377 | CT | Eversource |  |  | 2013-12-01 | Central/Western Massachusetts Upgrades - Group 4 - E. Longmeadow Projects | Substation work at Scitico (CT) associated with the new Hampden (MA) Substation project (NGRID) | [5 empty] | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 10/17//2007 | NR | [5 empty] | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | Part of Central/Western Massachusetts Upgrades Group 4 - E. Longmeadow Projects. Project ID 1217 | #VALUE!
Reliability Upgrade | 1a | 1371 | CT | Eversource |  |  | 2013-07-01 | NEEWS | Add the first Beseck 9F Substation Variable Shunt Reactor (75-150 MVAR) | [5 empty] | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 5/4/2012 7/25/2013 | 2014-12-09 | [5 empty] | 9000000 | 9000000 | 9000000 | 9000000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 0
Reliability Upgrade | 1a | 1370 | CT | Eversource |  |  | 2013-12-01 | NEEWS | Replace existing 115 kV series reactor at North Bloomfield | [5 empty] | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-05-04 | 2014-12-09 | [5 empty] | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 370000 | 0
Reliability Upgrade | 1a | 1369 | CT | Eversource |  |  | 2013-06-01 | NEEWS | Reconductor 115 kV line 1784, North Bloomfield - Northeast Simsbury | [5 empty] | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-05-04 | 2014-12-09 | [5 empty] | 6000000 | 6000000 | 6000000 | 6000000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 0
Reliability Upgrade | 1a | 1348 | CT | United Illuminating Company |  |  | 2014-12-01 | SWCT | Pequonnock 115 kV disconnect switch & bus upgrade (Pequonnock 115 kV Fault Duty Mitigation. - Phase I) | [5 empty] | Concept | Concept | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2014-09-05 | [5 empty] | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 6000000 | 6080000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 6046000 | 0
Reliability Upgrade | 1a | 1292 | CT | United Illuminating Company |  |  | 2013-07-01 |  | East Shore 115/13.8 kV Substation Capacity Upgrade |  |  |  |  | Proposed | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-03-05 | NR |  |  |  |  | 2000000 | 3200000 | 3200000 | 3200000 | 3000000 | 3000000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 4152000 | 0
Reliability Upgrade | 1a | 1246 | CT | United Illuminating Company |  |  | 2013-07-01 | SWCT | Reconfiguration of 115 kV (8300) line from Mill River to Quinnipiac |  |  | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2/3/2012 1/18/21013 | 2012-09-20 |  |  | 17400000 | 17400000 | 18800000 | 18000000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 0
Reliability Upgrade | 1a | 1245 | CT | CMEEC |  |  | 2015-11-01 | NEEWS | Sag elimination on 1410 Line (Montville-Buddington) |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2011-06-09 | NR |  |  | 60000 | 60000 | 60000 | 60000 | 60000 | 390150 | 390150 | 390150 | 390150 | 390150 | 390150 | 390150 | 450000 | 533000 | 454162 | 454162 | 454162 | 454162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 486162 | 0
Reliability Upgrade | 1a | 1244 | CT | CMEEC |  |  | 2012-04-01 | 115kV Circuit Breaker Installation | Install 115 kV Bus Tie Circuit Breaker at Stock House Rd Substation |  |  | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-02-14 | NR |  |  | 750000 | 750000 | 750000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 955000 | 0
Reliability Upgrade | 1a | 1243 | CT | CMEEC |  |  | 2013-10-01 | TTD's Fitch St 115 kV Substation | TTD 115/27 kV substation with two transformers and a 115kV circuit breaker looped into 1416 line (between Compo and Darien substations) |  |  | Concept | Concept | Concept | Concept | Concept | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/17/2012 | 2015-08-04 |  |  | TBD | TBD | TBD | TBD | TBD | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 0
Reliability Upgrade | 1a | 1235 | CT | Eversource |  |  | 2012-11-01 | NEEWS | Sag elimination on 1410 Line (Montville-Buddington) |  | Proposed | Proposed | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-06-09 | NR |  | 3500000 | 3500000 | 3000000 | 3000000 | 3000000 | 3000000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 0
Reliability Upgrade | 1a | 1230 | CT | Eversource |  |  | 2013-12-01 | LSP - NE Simsbury Breaker Addition | 115 kV breaker addition at Northeast Simsbury Substation |  | Concept | Concept | Concept | Concept | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-03-30 | 2014-12-09 |  | TBD | TBD | TBD | TBD | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 0
Reliability Upgrade | 1a | 1229 | CT | Eversource |  |  | 2014-12-01 | Asset Replacement | Replace 115 kV 1990 line lattice structures Frost Bridge to Stevenson |  | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-01-18 | 2015-09-25 |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 70000000 | 63000000 | 63000000 | 63000000 | 67800000 | 67800000 | 68500000 | 68500000 | 68500000 | 68500000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 58910000 | 0
Reliability Upgrade | 1a | 1228 | CT | Eversource |  |  | 2014-11-01 | SWCT | Install new 1.8 mile, 115 kV cable between Glenbrook and Southend Substation and associated substation work at both stations |  | Concept | Concept | Concept | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-07-17 | 2016-05-12 |  | TBD | TBD | TBD | 46000000 | 46000000 | 46000000 | 47000000 | 47000000 | 47000000 | 47000000 | 47000000 | 41500000 | 37000000 | 37000000 | 36701000 | 36701000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 36474000 | 0
Reliability Upgrade | 1a | 1227 | CT | Eversource |  |  | 2012-10-01 | LSP - Stamford Area | Add 4th transformer and build a five breaker ring bus at South End Substation |  | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-06-09 | 2014-12-09 |  | 9100000 | 9100000 | 6400000 | 6400000 | 6400000 | 6400000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 5700000 | 0
Reliability Upgrade | 1a | 1218 | CT | Eversource |  |  | 2013-03-01 | Millstone 345kV Circuit Separation project & SLOD SPS System Retirement | Separate the 345 kV Double Circuit Tower 310/348 and 371/383 configuration and disable the SLOD SPS scheme. |  | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-11-02 | 2013-07-26 |  | 22000000 | 25600000 | 25600000 | 27200000 | 27200000 | 27200000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 0
Reliability Upgrade | 1a | 1193 | CT | United Illuminating Company |  |  | 2013-01-01 |  | North Haven 115 kV Capacitor Bank TRV Mitigation Project |  | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR |  | 4100000 | 5100000 | 4900000 | 4900000 | 4900000 | 4900000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 0
Generator Interconnection Upgrade | 2a | 1186 | CT | United Illuminating Company |  |  | 2011-06-01 | New Haven Peaking Plant 2-4 | New Haven Harbor Peaking Plant - West River 115 kV series breaker additions | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-06-03 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1185 | CT | United Illuminating Company |  |  | 2012-05-01 | New Haven Peaking Plant 2-4 | New Haven Harbor Peaking Plant - Transmission generator lead & new 115 kV breakers | Concept | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-11-22 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1151 | CT | United Illuminating Company |  |  | 2011-06-01 |  | West River 115 kV Switching Station Fault Duty Mitigation | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 3800000 | 3800000 | 3500000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 0
Reliability Upgrade | 1a | 1150 | CT | United Illuminating Company |  |  | 2010-12-01 |  | Grand Avenue - West River 115 kV Pumping Plant Replacements | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 3000000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 3900000 | 0
Generator Interconnection Upgrade | 2a | 1149 | CT | Northeast Utilities |  |  | 2010-07-01 | GENCONN Devon | Four units connected at Devon Substation | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2007-12-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1148 | CT | Eversource |  |  | 2011-05-01 |  | Add a 2nd high speed relay on the Glennbrook to Waterside 115 kV 1440 | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-09-29 | NR | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | Part of Project #1147 | #VALUE!
Reliability Upgrade | 1a | 1147 | CT | Eversource |  |  | 2011-07-01 |  | Waterside Substation - install a three-breaker 115 kV ring bus | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-09-29 | NR | 5055000 | 5055000 | 5055000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 4616000 | 0
Generator Interconnection Upgrade | 2a | 1121 | CT | Eversource |  |  | 2011 | Middletown 12-15 | Four units connected to 384 line through a new 345 kV Substation: unit #4 will also connect to Substation | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-12-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1112 | CT | United Illuminating Company |  |  | 2011-02-01 |  | Water Street 115 kV circuit breaker and switch replacements. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 2840000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 0
Reliability Upgrade | 1a | 1111 | CT | United Illuminating Company |  |  | 2011-11-01 |  | Union Avenue 115/26.4 kV Substation | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 1/7/2009 12/16/2011 | 2009-11-10 | 10543000 | 10543000 | 10543000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 0
Reliability Upgrade | 1a | 1110 | CT | United Illuminating Company |  |  | 2010-12-01 |  | Broadway 115/13.8 kV Substation Addition | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-12-08 | NR | 1300000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 0
Reliability Upgrade | 1a | 1091 | CT | Eversource |  |  | 2010-05-01 | NEEWS (Interstate Reliability Project) | Southington 4C substation breaker 19T upgrade to 63 kA | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 426500 | 0
Reliability Upgrade | 1a | 1090 | CT | Eversource |  |  | 2010-04-01 | NEEWS (Interstate Reliability Project) | Millstone 15G substation breaker 14T upgrade 50 kA | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 902800 | 0
Reliability Upgrade | 1a | 1085 | CT | Eversource |  |  | 2014-12-01 | NEEWS (Interstate Reliability Project) | Card 11F 345 kV Substation expansion | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 5/4/2012 | 2015-12-17 | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | #VALUE!
Reliability Upgrade | 1a | 1056 | CT | Eversource |  |  | 2011-12-01 | LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8 kV substation with two transformers and a 115 kV circuit breaker. | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-12-12 | 2011-04-14 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 10969000 | 0
Reliability Upgrade | 1a | 1055 | CT | Northeast Utilities |  |  | 2010-12-01 | LSP - Waterside Substation | Waterside Substation - add a 115/13.2 kV transformer and a 115 kV circuit breaker. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-09-29 | NR | 2804000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 2816000 | 0
Reliability Upgrade | 1a | 1054 | CT | Eversource |  |  | 2012-10-01 | NEEWS | Separate the three-terminal 345 kV Line 395 at Meekville Junction and build new Manchester to Meekville Junction 345 kV line portion and add a 345 kV circuit breaker 24T at Manchester 3A | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 5/4/2012 | 2014-02-25 | 14000000 | 31000000 | 31000000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 28800000 | 0
Reliability Upgrade | 1a | 1050 | CT | United Illuminating Company |  |  | 2011-12-01 |  | Devon Tie 115 kV Switching Station BPS Compliance | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 3240000 | 3800000 | 4000000 | 4000000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 0
Reliability Upgrade | 1a | 1049 | CT | United Illuminating Company |  |  | 2011-03-01 |  | Add additional capacitor, reactors and circuit switches at East Shore 115 kV substation | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 4400000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 0
Reliability Upgrade | 1a | 976 | CT | United Illuminating Company |  |  | 2012-05-01 |  | Grand Avenue 115 kV Switching Station Rebuild. | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 1/7/2009 10/20/2011 4/30/2012 | 2011-10-20 | 66000000 | 70000000 | 70000000 | 70000000 | 70000000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 63400000 | 0
Reliability Upgrade | 1a | 974 | CT | United Illuminating Company |  |  | 2013-11-01 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2012-05-16 | 11500000 | 15400000 | 16900000 | 16900000 | 15000000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 0
Reliability Upgrade | 1a | 879 | CT | Bangor Hydro-Electric Company | New England Power Company, Eversource |  | 2012-12-01 | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 03/01/2007 | NR | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 0
Reliability Upgrade | 1a | 816 | CT | Eversource |  |  | 2013-04-01 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion add a second 345/115 kV autotransformer | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 5/4/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 814 | CT | Northeast Utilities |  |  | 2010-05-01 | Middletown Area Project | Reconductor a portion of the Manchester to Scovill Rock 353 345 kV line and terminal work. | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | NR | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 2402000 | 0
Reliability Upgrade | 1a | 810 | CT | Eversource |  |  | 2014-12-01 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV Substation expansion | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 5/4/2012 | 2015-12-17 | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | #VALUE!
Reliability Upgrade | 1a | 809 | CT | Northeast Utilities |  |  | 2010-12-01 |  | Upgrade terminal equipment at Bunker Hill 115 kV substation. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 516000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 349000 | 0
Reliability Upgrade | 1a | 802 | CT | Eversource |  |  | 2015-08-01 | NEEWS (Interstate Reliability Project) | Build new 345 kV line 3271 Card - Lake Road | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 9/24/2008 5/4/2012 | 2015-12-17 | 251000000 | 301000000 | 251000000 | 218000000 | 218000000 | 218000000 | 218000000 | 218000000 | 218000000 | 218000000 | 218000000 | 218000000 | 218000000 | 218000000 | 218000000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 217858000 | 0
Reliability Upgrade | 1a | 721 | CT | United Illuminating Company | Eversource |  | 2015-06-01 |  | New Pootatuck 115/13.8 kV substation (formerly known as Shelton Substation) (Other equipment owner for line 1560: Eversource) | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2009-11-05 | 2014-03-06 | 19500000 | 19500000 | 19500000 | 19500000 | 19500000 | 19500000 | 19500000 | 19500000 | 19500000 | 19500000 | 19800000 | 19936000 | 19936000 | 19936000 | 19936000 | 19936000 | 19936000 | 19936000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 20826000 | 0
Reliability Upgrade | 1a | 582 | CT | Eversource |  |  | 2011-06-01 |  | Separate 310 (Manchester-Millstone) and 368 (Manchester-Card) 345 kV lines and create 368/1767 DCT | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-07-18 | 2011-03-25 | 10456000 | 10456000 | 10456000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 11350000 | 0
Generator Interconnection Upgrade | 2a | 331 | CT | Eversource |  |  | 2011-06-01 | Kleen Energy | Install 5-breaker ring bus interconnecting between Scovill Rock and Manchester on the 345 kV 353 Line. | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 10/08/2003 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 191 | CT | Eversource |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | Build new 345 kV Line 341, Lake Road - CT/RI border West Farnum | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 9/24/2008 5/4/2012 | 2015-12-17 | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | Part of NEEWS (Interstate Reliability Project) Project ID 802 | #VALUE!
Reliability Upgrade | 1a | 85 | CT | Eversource |  |  | 2013-12-01 |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | Concept | Concept | Concept | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 08/04/2004 Updated 9/7/2011 | 2014-12-09 | TBD | TBD | TBD | TBD | 13600000 | 13600000 | 13600000 | 13600000 | 13600000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 16800000 | 0
RHODE ISLAND
Reliability Upgrade | 1a | 1915 | RI | Rhode Island Energy |  |  | 2025-11-01 | RI 2028 Short Circuit Solutions | Replace three 115 kV circuit breakers at the Woonsocket substation | [40 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service |  | NR | NR | [40 empty] | 1524700 | 1524700 | 1524700 | 1524700 | 1524700 | 2281000 | 2890000 | 2890000 | 0
Generator Interconnection Upgrade | 2a | 1849 | RI | Rhode Island Energy |  |  | 2025-03-01 | Queue Position 781 | Drumrock Substation Upgrades | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1848 | RI | Rhode Island Energy |  |  | 2024-10-01 | Queue Position 781 | Reconductor G-185S/L-190 Lines | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1847 | RI | Rhode Island Energy |  |  | 2024-12-02 | Queue Position 781 | Reconductor G-185N/K-189 Lines | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1846 | RI | Rhode Island Energy |  |  | 2025-04-01 | Queue Position 781 | Rebuild Davisville Substation | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1815 | RI | Rhode Island Energy |  | 1 | 2025-01-01 | Eastern CT 2029 Solutions | Reconductor the L190-4 and L190-5 line sections | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service |  | 2021-06-17 | No | [30 empty] | 40000000 | 40000000 | 31100000 | 31100000 | 31100000 | 31100000 | 54707000 | 54707000 | 54707000 | 54707000 | 54707000 | 54707000 | 54707000 | 54707000 | 54707000 | 54707000 | 54707000 | 54707000 | 0
Reliability Upgrade | 1a | 1782 | RI | National Grid, USA |  |  | 2022-05-01 | Southeast Massachusetts/Rhode Island Reliability Project | Reconductor the J16S line | [23 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [23 empty] | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 0
Reliability Upgrade | 1a | 1742 | RI | National Grid, USA |  |  | 2020-10-01 | Southeast Massachusetts/Rhode Island Reliability Project | Remote terminal station work (Wampanoag and Pawtucket 115 kV) for new 115 kV Grand Army GIS switching station to tie the E-183E, F-184, X3 and W4 lines (associated with RSP 1714) | [20 empty] | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [20 empty] | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 0
Reliability Upgrade | 1a | 1724 | RI | National Grid, USA |  |  | 2022-03-01 | Southeast Massachusetts/Rhode Island Reliability Project | Kent County T3 345/115 kV transformer replacement | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 8100000 | 8100000 | 8100000 | 8100000 | 8100000 | 8100000 | 8100000 | 8100000 | 4714000 | 4714000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 0
Reliability Upgrade | 1a | 1671 | RI | National Grid, USA |  |  | 2021-03-01 | Aquidneck Island Reliability Project | Convert lines 61/62 from 69 kV to 115 kV | [14 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2017-03-31 | No | [14 empty] | 22100000 | 22100000 | 22100000 | 22100000 | 22100000 | 22100000 | 22100000 | 22100000 | 25444620 | 25444620 | 25444620 | 33947000 | 33947000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 33890000 | 0
Reliability Upgrade | 1a | 1670 | RI | National Grid, USA |  |  | 2021-03-01 | Aquidneck Island Reliability Project | Remove 115kV to 69 kV transformer at Dexter Substation | [14 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2017-03-31 | No | [14 empty] | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 2190000 | 2120000 | 2120000 | 2177000 | 2177000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 2470000 | 0
Reliability Upgrade | 1a | 1669 | RI | National Grid, USA |  |  | 2021-03-01 | Aquidneck Island Reliability Project | Conversion of Jepson 69 kV substation to 115 kV substation | [14 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2017-03-31 | No | [14 empty] | 9500000 | 9500000 | 9500000 | 9500000 | 9500000 | 9500000 | 9500000 | 9500000 | 13437000 | 12840000 | 12840000 | 13468000 | 13468000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 14910000 | 0
Reliability Upgrade | 1a | 1623 | RI | National Grid, USA |  |  | 2016-06-01 | Brayton Point Non-Price Retirement | Reconductor V-148N Line between Washington and Woonsocket Substations | [12 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-09-09 | 2016-03-21 | [11 empty] | 12300000 | 12300000 | 12300000 | 7000000 | 7000000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 5740000 | 0
Reliability Upgrade | 1a | 1510 | RI | National Grid, USA |  |  | 2014-06-01 | New Highland Park Substation Project | Add a new 115/13.8 kV Highland Park Substation by looping the J-16 line in and out of this new substation | [9 empty] | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-01-18 | 2018-01-03 | [9 empty] | 3000000 | 3000000 | 3824000 | 3824000 | 3824000 | 3824000 | 3824000 | 3824000 | 3824000 | 3824000 | 3824000 | 3824000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 2570000 | 0
Reliability Upgrade | 1a | 1492 | RI | National Grid, USA |  |  | 2015-05-01 | New Highland Park Substation Project | Bus upgrades at Riverside Substation (J16) | [7 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-01-18 | 2018-01-03 | [7 empty] | Part of Highland Dr Substation Project - ID 1491 | Part of Highland Dr Substation Project - ID 1491 | Part of Highland Dr Substation Project - ID 1491 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 340000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 360000 | 0
Reliability Upgrade | 1a | 1491 | RI | National Grid, USA |  |  | 2016-12-01 | New Highland Park Substation Project | Re-conductoring of J16 (Riverside - Highland Dr) | [7 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2013-01-18 | 2018-01-03 | [7 empty] | 4600000 | 4600000 | 4600000 | 4343000 | 4343000 | 4343000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5060000 | 5060000 | 5060000 | 5060000 | 5060000 | 5060000 | 5060000 | 5060000 | 5060000 | 5060000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 5344000 | 0
Reliability Upgrade | 1a | 1331 | RI | National Grid, USA |  |  | 2013-05-01 | NEEWS (Rhode Island Reliability Project) | 115 kV Breaker addition at Kent County |  |  |  |  | Concept | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-05-04 | 2015-12-17 |  |  |  |  | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | Part of NEEWS refer to RSP 1106 | #VALUE!
Reliability Upgrade | 1a | 1298 | RI | National Grid, USA |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | New 345 kV (366) line MA/RI Border to West Farnum (4.8 miles) |  |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 9/24/2008 5/4/2012 | 2015-12-17 |  |  |  |  | 19500000 | 19500000 | 19500000 | 19500000 | 19500000 | 19500000 | 27700000 | 27700000 | 36325000 | 36325000 | 36325000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 34000000 | 0
Reliability Upgrade | 1a | 1297 | RI | National Grid, USA |  |  | 2014-09-01 | NEEWS (Interstate Reliability Project) | Hartford Ave Substation Relay Upgrades |  |  |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2015-12-17 |  |  |  |  | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 1340000 | 0
Reliability Upgrade | 1a | 1296 | RI | National Grid, USA |  |  | 2014-09-01 | NEEWS (Interstate Reliability Project) | Woonsocket Substation Relay Upgrades |  |  |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2015-12-17 |  |  |  |  | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 1270000 | 0
Reliability Upgrade | 1a | 1295 | RI | National Grid, USA |  |  | 2014-09-01 | NEEWS (Interstate Reliability Project) | Riverside Substation Relay Upgrades |  |  |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2015-12-17 |  |  |  |  | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 900000 | 900000 | 900000 | 900000 | 900000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 0
Reliability Upgrade | 1a | 1294 | RI | National Grid, USA |  |  | 2012-05-01 | NEEWS (Rhode Island Reliability Project) | West Farnum Substation 345 kV additions |  |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 9/24/2008 5/4/2012 | 2015-12-17 |  |  |  |  | 18600000 | 18600000 | 18600000 | 18600000 | 18600000 | 18600000 | 18600000 | 18600000 | 14000000 | 14000000 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | Part of RSP 1095 | #VALUE!
Reliability Upgrade | 1a | 1264 | RI | National Grid, USA |  |  | 2011-06-01 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. |  |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2015-12-17 |  |  |  | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | Part of RSP 1106 | #VALUE!
Reliability Upgrade | 1a | 1253 | RI | National Grid, USA |  |  | 2017-03-01 |  | Chase Hill Substation 115/13 kV substation addition |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | in-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 6/7/2011 5/26/2015 | NR |  |  | 5000000 | 3000000 | 3000000 | 3000000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 2600000 | 2600000 | 2600000 | 3200000 | 3200000 | 3200000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 1742000 | 0
Reliability Upgrade | 1a | 1252 | RI | National Grid, USA |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | Re-conductor 345 kV 328 line (West Farnum-Sherman Rd) |  |  | Concept | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2012-05-04 | 2015-12-17 |  |  | TBD | 36500000 | 36500000 | 36500000 | 36500000 | 36500000 | 36500000 | 36500000 | 36500000 | 36500000 | 36200000 | 36200000 | 36200000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 0
Reliability Upgrade | 1a | 1241 | RI | National Grid, USA |  |  | 2015-06-01 |  | Reconductor G-185S (Kent County - Davisville Tap) |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2010-12-27 | 2016-02-17 |  | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 0
Reliability Upgrade | 1a | 1234 | RI | National Grid, USA |  |  | 2014-09-01 | NEEWS (Interstate Reliability Project) | West Farnum Substation 115 kV upgrades |  | Concept | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-05-04 | 2015-12-17 |  | TBD | TBD | TBD | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 6740000 | 0
Reliability Upgrade | 1a | 1233 | RI | National Grid, USA |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | New Sherman Road 345 kV AIS Substation |  | Concept | Concept | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2012-05-04 | 2015-12-17 |  | TBD | TBD | 36600000 | 36600000 | 36600000 | 36600000 | 36600000 | 36600000 | 36600000 | 36600000 | 36600000 | 38685000 | 38685000 | 38685000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 0
Reliability Upgrade | 1a | 1106 | RI | National Grid, USA |  |  | 2012-05-01 | NEEWS (Rhode Island Reliability Project) | Kent County Substation Upgrades related to third 345/115 kV autotransformer. | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 5/4/2012 | 2015-12-17 | Part of $99,900,000 above | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 24000000 | 0
Reliability Upgrade | 1a | 1099 | RI | National Grid, USA |  |  | 2012-05-01 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115 kV terminal equipment upgrades | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2015-12-17 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 0
Reliability Upgrade | 1a | 1097 | RI | National Grid, USA |  |  | 2013-03-01 | NEEWS (Rhode Island Reliability Project) | Relocate and rebuild 115kV lines in the same ROW associated with new 345 kV line from W. Farnum to Kent County and reconductor short segments of the S-171 and T-172S lines (along with upgrading associated limiting terminal equipment). | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2015-12-17 | 129800000 | 129800000 | 129800000 | 129800000 | 129800000 | 129800000 | 129800000 | 129800000 | 129800000 | 129800000 | 139800000 | 139800000 | 139800000 | 139800000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 140100000 | 0
Reliability Upgrade | 1a | 1096 | RI | National Grid, USA |  |  | 2012-12-01 | NEEWS (Rhode Island Reliability Project) | Drumrock Substation: Terminal equipment upgrades, protection modifications and upgrades to meet BPS standards | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2015-12-17 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 0
Reliability Upgrade | 1a | 1095 | RI | National Grid, USA |  |  | 2012-05-01 | NEEWS (Rhode Island Reliability Project) | Upgrade and expand the 345 kV West Farnum Substation Equipment | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 5/4/2012 | 2015-12-17 | 73800000 | 73800000 | 73800000 | 73800000 | 55200000 | 55200000 | 55200000 | 55200000 | 55200000 | 55200000 | 55200000 | 55200000 | 55200000 | 55200000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 55000000 | 0
Reliability Upgrade | 1a | 800 | RI | National Grid, USA |  |  | 2012-09-01 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S and T-172S with associated terminal equipment upgrades | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-11-05 | 2015-12-17 | 10000000 | 10000000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 0
Reliability Upgrade | 1a | 799 | RI | National Grid, USA |  |  | 2011-07-01 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2015-12-17 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 0
Reliability Upgrade | 1a | 798 | RI | National Grid, USA |  |  | 2011-12-01 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115 kV terminal equipment at Franklin Square. | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2015-12-17 | 4900000 | 4900000 | 4900000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 0
Reliability Upgrade | 1a | 795 | RI | National Grid, USA |  |  | 2013-05-01 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345 kV (359) line. | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2015-12-17 | 99900000 | 69000000 | 69000000 | 69000000 | 69000000 | 69000000 | 69000000 | 69000000 | 69000000 | 69000000 | 69000000 | 69000000 | 69000000 | 69000000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 102200000 | 0
Reliability Upgrade | 1a | 794 | RI | National Grid, USA |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345 kV line (to Lake Road) | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 9/24/2008 5/4/2012 | 2015-12-17 | 55800000 | 71700000 | 71700000 | 71700000 | 71700000 | 71700000 | 71700000 | 71700000 | 71700000 | 71700000 | 71700000 | 71700000 | 71350000 | 71350000 | 71350000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 61320000 | 0
Reliability Upgrade | 1a | 788 | RI | National Grid, USA |  |  | 2011-01-01 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Kent County substation expansion. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-04-25 | 2012-06-07 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 0
Reliability Upgrade | 1a | 484 | RI | National Grid, USA |  |  | 2012-02-01 | Greater Rhode Island Transmission Reinforcements | Add (1) new 115 kV breaker at Woonsocket. | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-04-25 | No | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 580000 | 0
MASSACHUSETTS
Reliability Upgrade | 1a | 1916 | MA | National Grid, USA |  |  | 2026-03-01 | Western and Central Massachusetts 2028 Short Circuit Solutions | Replace one 115 kV circuit breaker at the Millbury substation | [40 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service |  | NR | NR | [40 empty] | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 750000 | 0
Generator Interconnection Upgrade | 2a | 1913 | MA | Eversource |  |  | 2025-11-01 | Queue Position 844 | Install a new 345 kV circuit breaker at West Medway Station 446 | [39 empty] | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service |  | 2021-09-03 | NR | [39 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1898 | MA | Eversource |  |  | 2022-09-01 |  | K Street 345 kV 103S Breaker - Operate as Normally Open | [35 empty] | Proposed | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2022-08-19 | NR | [35 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Generator Interconnection Upgrade | 2a | 1877 | MA | Eversource |  |  | 2024-12-01 | Queue Position 726 | Construct a new substation with three-breakers to accommodate the interconnection of QP 726 on the existing Line 127 115 kV line | [32 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service |  | 2021-03-03 | NR | [32 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1876 | MA | National Grid, USA |  |  | 2023-06-01 | Boston Area Optimized Solution | Install one +/- 167 MVAR STATCOM at Tewksbury 345 kV substation | [31 empty] | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 5/21/2021 1/18/2023 | 2022-04-08 | [31 empty] | 33400000 | 31300000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 32919000 | 0
Reliability Upgrade | 1a | 1875 | MA | National Grid, USA |  |  | 2022-04-01 | Boston Area Optimized Solution | Install a direct transfer trip (DTT) scheme between Ward Hill and West Amesbury Substations for Line 394 | [31 empty] | Proposed | Proposed | Planned | Planned | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-05-21 | 2022-04-08 | [31 empty] | 800000 | 800000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 815000 | 0
Reliability Upgrade | 1a | 1874 | MA | Eversource |  |  | 2021-12-01 | Boston Area Optimized Solution | Install two 11.9 ohm series reactors at North Cambridge Station on Lines 346 and 365 | [31 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-05-21 | 2022-04-08 | [31 empty] | 14400000 | 14400000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 15183000 | 0
Reliability Upgrade | 1a | 1807 | MA | National Grid, USA |  |  | 2022-08-01 | Boston 2028 Project | Install a 160 MVAR reactor at Golden Hills 345 kV | [28 empty] | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2020-03-27 | 2022-04-08 | [28 empty] | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 5470000 | 0
Reliability Upgrade | 1a | 1806 | MA | Eversource |  |  | 2021-12-01 | Boston 2028 Project | Install a 115 kV breaker in series with breaker 4 at Mystic | [28 empty] | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2020-02-21 | 2022-04-08 | [28 empty] | 3250000 | 3250000 | 3250000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 3184000 | 0
Generator Interconnection Upgrade | 2a | 1801 | MA | Eversource |  |  | 2023-10-01 | Queue Position 624 | Upgrade the protection systems to meet the NPCC BPS design requirements at the Tremont #713 substation | [26 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 4/2/2019 4/27/2023 | NR | [26 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1800 | MA | Eversource |  |  | 2023-05-01 | Queue Position 624 | Install two 115 kV breakers and associated equipment at the Barnstable #958 substation | [26 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 4/2/2019 4/27/2023 | NR | [26 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1790 | MA | Eversource |  |  | 2020-11-01 | Southeast Massachusetts/Rhode Island Reliability Project | Medway 115 kV Circuit Breaker Replacements | [24 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-05-01 | No | [24 empty] | 4865000 | 4865000 | 4865000 | 4865000 | 4865000 | 4865000 | 4865000 | 4865000 | 4865000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 0
Reliability Upgrade | 1a | 1789 | MA | Eversource |  |  | 2021-04-01 | Southeast Massachusetts/Rhode Island Reliability Project | West Medway 345 kV circuit breaker upgrades | [24 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-05-01 | No | [24 empty] | 6309000 | 6309000 | 6309000 | 6309000 | 6309000 | 6309000 | 6309000 | 6309000 | 6309000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 0
Generator Interconnection Upgrade | 2a | 1781 | MA | National Grid, USA |  |  | 2020-08-01 | Queue Position 592 | Install a second 115 kV capacitor bank (63 MVAR) and increase the size of the first 115 kV capacitor bank from 50 MVAR to 63 MVAR to address negative impact on Bear Swamp area voltages during pumping conditions | [22 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2017-06-02 | NR | [22 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1763 | MA | Eversource |  |  | 2018-09-01 | Medway Peaker QP 444 | Replace switch conductors, cable bus at Medway #65 | [21 empty] | Proposed | Proposed | Proposed | Proposed | in-service | in-service | in-service | in-service | in-service | in-service | in-service | in-service | in-service | in-service | in-service | in-service | in-service | in-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | No | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1745 | MA | Eversource |  |  | 2025-11-01 |  | New East Eagle 115 kV station between Mystic and Chelsea | [20 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | Y-Proposed | 2016-06-09 | No | [20 empty] | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 42730000 | 74800000 | 74204000 | 73264000 | 73264000 | 73264000 | 73264000 | 73264000 | 73264000 | 62854945 | 62854945 | 0
Reliability Upgrade | 1a | 1741 | MA | Middleborough Gas and Electric |  |  | 2019-04-01 | Southeast Massachusetts/Rhode Island Reliability Project | Rebuild the Middleborough Gas and Electric (MGED) portion of the E1 line from Bridgewater to Middleborough (2.5 miles) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 0
Generator Interconnection Upgrade | 2a | 1740 | MA | Eversource |  |  | 2018-12-01 | Milford 2 QP 527 | Install one pilot protection scheme on 201-501 line at Medway #65 | [19 empty] | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2016-12-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1739 | MA | Eversource |  |  | 2018-05-01 |  | Build a new 115kV Substation - Seafood Way | [19 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-07-19 | 4/14/2021 12/10/2021 | [19 empty] | 60000000 | 60000000 | 52616000 | 52616000 | 52616000 | 52616000 | 52616000 | 52616000 | 52616000 | 52616000 | 52616000 | 52616000 | 52616000 | 38016000 | 38016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 39016000 | 0
Reliability Upgrade | 1a | 1738 | MA | Eversource |  |  | 2021-07-01 | Greater Boston - Stability | Chelsea Station #488 BPS upgrade | [19 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | NR | No | [19 empty] | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 11458000 | 0
Reliability Upgrade | 1a | 1737 | MA | Eversource |  |  | 2020-08-01 | Southeast Massachusetts/Rhode Island Reliability Project | Replace disconnect switches 107A, 107B, 108A and 108B on Line 323 at West Medway Substation #446. Replace 8 line structures with taller structures | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 200000 | 200000 | 200000 | 200000 | 2064000 | 2064000 | 2064000 | 2064000 | 2064000 | 2064000 | 2064000 | 2064000 | 2064000 | 2064000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 0
Reliability Upgrade | 1a | 1736 | MA | Eversource |  |  | 2018-10-01 | Southeast Massachusetts/Rhode Island Reliability Project | Reconductor the 108 line from Bourne Substation #917 to Horse Pond Tap | [19 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 5/4/2017 12/20/2018 | No | [19 empty] | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 2756000 | 2756000 | 2756000 | 2756000 | 2756000 | 2756000 | 2756000 | 2756000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 0
Reliability Upgrade | 1a | 1734 | MA | Eversource |  |  | 2018-06-01 | Southeast Massachusetts/Rhode Island Reliability Project | Reconductor/Upgrade 112 Line Tremont Substation #713 to Industrial Tap and terminal equipment | [19 empty] | Proposed | Proposed | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2017-05-04 | No | [19 empty] | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 0
Reliability Upgrade | 1a | 1732 | MA | Eversource |  |  | 2025-11-01 | Southeast Massachusetts/Rhode Island Reliability Project | Loop 201-502 line into Medway #65 Substation to form the 201-502N and 201-502S lines | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 22684000 | 22684000 | 0
Reliability Upgrade | 1a | 1731 | MA | Eversource |  |  | 2021-12-01 | Southeast Massachusetts/Rhode Island Reliability Project | Install 35.3 MVAR 115 kV capacitors at High Hill Substation #644 and Wing Lane Substation #624 | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 0
Reliability Upgrade | 1a | 1729 | MA | Eversource |  |  | 2023-08-01 | Southeast Massachusetts/Rhode Island Reliability Project | Install a new bay position at Kingston for Carver line | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 0
Reliability Upgrade | 1a | 1728 | MA | Eversource |  |  | 2023-08-01 | Southeast Massachusetts/Rhode Island Reliability Project | Build a new Carver to Kingston 115 kV line and Carver terminal | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 0
Reliability Upgrade | 1a | 1727 | MA | Eversource |  |  | 2021-11-01 | Southeast Massachusetts/Rhode Island Reliability Project | Retire Barnstable SPS | [19 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2017-05-04 | No | [19 empty] | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 0
Reliability Upgrade | 1a | 1726 | MA | Eversource |  |  | 2021-12-01 | Southeast Massachusetts/Rhode Island Reliability Project | Separate the 135/122 DCT lines - West Barnstable to Barnstable | [19 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2017-05-04 | No | [19 empty] | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 0
Reliability Upgrade | 1a | 1725 | MA | Eversource |  |  | 2024-05-01 | Southeast Massachusetts/Rhode Island Reliability Project | Build a new Bourne #917 to West Barnstable #921 115 kV line and associated terminal work | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 59100000 | 59100000 | 59100000 | 59100000 | 59100000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 0
Reliability Upgrade | 1a | 1721 | MA | National Grid, USA |  |  | 2023-08-01 | Southeast Massachusetts/Rhode Island Reliability Project | Reconfigure Bell Rock to breaker and a half station, and upgrade to BPS standards, split M13 line at Bell Rock and terminate 114 line at Bell Rock. Install new breaker in series with N12/D21 tie breaker, upgrade D21 line switch and install 37.5 MVAR capacitor. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 4/30/2018 12/20/2018 | No | [19 empty] | 18900000 | 18900000 | 18900000 | 18900000 | 18900000 | 18900000 | 18900000 | 18900000 | 18900000 | 18900000 | 30800000 | 30800000 | 30800000 | 30800000 | 30800000 | 30800000 | 30800000 | 30800000 | 35500000 | 35500000 | 36180000 | 36180000 | 36180000 | 36180000 | 36180000 | 36180000 | 36180000 | 36180000 | 36180000 | 0
Reliability Upgrade | 1a | 1718 | MA | National Grid, USA |  |  | 2022-03-01 | Southeast Massachusetts/Rhode Island Reliability Project | Robinson Ave 115 kV circuit breaker addition and reterminate Q10 line | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 1039000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 0
Reliability Upgrade | 1a | 1717 | MA | National Grid, USA |  |  | 2019-11-01 | Southeast Massachusetts/Rhode Island Reliability Project | Separate X3/W4 DCT and reconductor X3, W4 lines between Somerset and Grand Army (~2.7 miles each). Reconfigure Y2 and Z1 | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 14600000 | 14600000 | 14900000 | 14900000 | 14900000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 16196000 | 16196000 | 16196000 | 16196000 | 16196000 | 16196000 | 16196000 | 0
Reliability Upgrade | 1a | 1716 | MA | National Grid, USA |  |  | 2019-11-01 | Southeast Massachusetts/Rhode Island Reliability Project | Increase clearances on E-183E & F-184 lines between Brayton Point & Grand Army (~1.5 miles each) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4283000 | 4283000 | 4283000 | 4283000 | 4283000 | 4283000 | 4283000 | 4283000 | 0
Reliability Upgrade | 1a | 1715 | MA | National Grid, USA |  |  | 2020-10-01 | Southeast Massachusetts/Rhode Island Reliability Project | Upgrades at Brayton Point (new 115 kV breaker, new 345/115 kV transformer and upgrades to E183E, F184 station equipment) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 13100000 | 13100000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 15381000 | 15381000 | 15381000 | 15381000 | 15381000 | 15381000 | 15381000 | 15381000 | 15381000 | 15644000 | 15644000 | 15644000 | 15644000 | 15644000 | 15644000 | 15644000 | 15644000 | 0
Reliability Upgrade | 1a | 1714 | MA | National Grid, USA |  |  | 2020-10-01 | Southeast Massachusetts/Rhode Island Reliability Project | New Grand Army 115 kV GIS switching station built to BPS standards, remote terminal station work (Brayton Point and Somerset) & loop E-183E, F-184, X3 and W4 lines (associated with RSP 1742) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 43800000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 52080000 | 52080000 | 52080000 | 52080000 | 52080000 | 52080000 | 52080000 | 52080000 | 52080000 | 51919000 | 51919000 | 51919000 | 51919000 | 51919000 | 51919000 | 51919000 | 51919000 | 0
Generator Interconnection Upgrade | 2a | 1688 | MA | Eversource |  |  | 2018-12-01 | Canal 3 | Install 0.3 mile overhead 345 kV line and disconnect switch at Canal substation at existing bus position between breakers 812P and 812S | [16 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-11-05 | NR | [16 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1674 | MA | National Grid, USA |  |  | 2018-11-01 | Deerfield Wind | Reconductor the 69 kV J-10 line between the Adams and Deerfield #5 substations with 477 ACSR | [15 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-07-09 | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1672 | MA | Hudson Light and Power |  |  | 2025-06-01 | Greater Boston - Western Suburbs | Forest Ave Substation modification required to build a new 115 kV line from Sudbury Station 342 substation to Hudson substation (This is the HLP portion of the line and terminal work) | [14 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [14 empty] | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5500000 | 5500000 | 5500000 | 5500000 | 5500000 | 5500000 | 5500000 | 5500000 | 5500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 8300000 | 8300000 | 8500000 | 8500000 | 8500000 | 0
Reliability Upgrade | 1a | 1668 | MA | Norwood Municipal Light Department |  |  | 2016-12-01 |  | Rebuild 115 kV lines 447-508 and 447-509 from the Eversource tap in Sharon to Dean St. #496 substation in Norwood | [14 empty] | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-02-25 | 2015-04-30 | [14 empty] | 12700000 | 12700000 | 12700000 | 12700000 | 12700000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 0
Reliability Upgrade | 1a | 1666 | MA | Eversource |  |  | 2016-04-01 | Acushnet to Pine St. Reliability Project | Install one 115 kV breaker in series with existing Acushnet Sub EW22 breaker | [14 empty] | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-07-17 | NR | [14 empty] | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 0
Reliability Upgrade | 1a | 1665 | MA | Eversource |  |  | 2017-12-01 | Pittsfield / Greenfield Project | Install a 75-150 MVAR variable reactor at Ludlow substation | [14 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-01-26 | 2019-02-15 | [14 empty] | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 7455000 | 0
Reliability Upgrade | 1a | 1664 | MA | Eversource |  |  | 2017-12-01 | Pittsfield / Greenfield Project | Install a 75-150 MVAR variable reactor at Northfield substation | [14 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-01-26 | 2019-02-15 | [14 empty] | 14400000 | 14400000 | 14400000 | 14400000 | 14400000 | 14400000 | 14400000 | 14400000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 10886000 | 0
Reliability Upgrade | 1a | 1663 | MA | Eversource |  |  | 2020-06-01 | Pittsfield / Greenfield Project | Construct a 115 kV three breaker ring bus at or adjacent to Pochassic 37R Substation, loop line 1512-1 into the new three breaker ring bus, construct a new line connecting the new three breaker ring bus to the Buck Pond 115 kV Substation on the vacant side of the double circuit towers that carry line 1302-2, add a new breaker to the Buck Pond 115-kV straight bus and reconnect lines 1302-2, 1657-2 and transformer 2X into new positions | [14 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-05-05 | 2019-02-15 | [14 empty] | 39600000 | 39600000 | 39600000 | 39600000 | 39600000 | 39600000 | 39600000 | 39600000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 35632000 | 0
Reliability Upgrade | 1a | 1662 | MA | Eversource |  |  | 2017-12-01 | Pittsfield / Greenfield Project | Install a 115 kV 20.6 MVAR capacitor at Doreen substation and operate the 115kV 13T breaker N.O. | [14 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-01-26 | 2019-02-15 | [14 empty] | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 2664000 | 0
Reliability Upgrade | 1a | 1647 | MA | Eversource |  |  | 2017-03-01 | Greater Boston - Western Suburbs | Add a new 115 kV breaker in series with breaker 5 at Framingham | [13 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No | [13 empty] | TBD | 1033000 | 1033000 | 1033000 | 1033000 | 1033000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 0
Reliability Upgrade | 1a | 1646 | MA | Eversource |  |  | 2019-12-01 | Greater Boston - Western Suburbs | Add a new 345 kV 160 MVAR shunt reactor at K Street | [13 empty] | Concept | Concept | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [13 empty] | TBD | TBD | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 0
Reliability Upgrade | 1a | 1645 | MA | Eversource |  |  | 2017-06-01 | Greater Boston - Western Suburbs | Add a new 115 kV 36.7 MVAR capacitor bank at Hartwell Station | [13 empty] | Concept | Concept | Proposed | Proposed | Proposed | Planned | Under Construction | in-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [13 empty] | TBD | TBD | 1400000 | 1400000 | 2300000 | 2300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 0
Reliability Upgrade | 1a | 1640 | MA | Eversource |  |  | 2017-01-01 | Greater Boston - North | Reconductor the Eversource portion of the M-139/211-503 and N-140/211-504 115 kV lines between Pinehurst – North Woburn tap | [13 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No | [13 empty] | 4700000 | 4700000 | 4700000 | 4700000 | 7000000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 4748000 | 0
Reliability Upgrade | 1a | 1639 | MA | Eversource |  |  | 2016-08-01 |  | Reconductor the 345 kV underground cable (372) between Mystic and Kingston substations. | [13 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | 09/25/2015 09/13/2017 | [13 empty] | 15100000 | 15100000 | 15100000 | 18530000 | 18530000 | 22745000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 23175000 | 0
Reliability Upgrade | 1a | 1638 | MA | Eversource |  |  | 2015-01-01 |  | Installation of 2, 20 MVAR shunt reactors at Sudbury 115kV Substation | [13 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2014-11-20 | NR | [13 empty] | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 0
Reliability Upgrade | 1a | 1637 | MA | National Grid, USA |  |  | 2017-05-01 | Greater Boston - North | Reconductor the National Grid portion of the M-139/211-503 and N-140/211-504 115 kV lines between Pinehurst – North Woburn tap | [13 empty] | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No | [13 empty] | 1560000 | 1560000 | 1560000 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | #VALUE!
Reliability Upgrade | 1a | 1635 | MA | National Grid, USA |  |  | 2020-11-01 | Somerset Asset Condition | Rebuild the Somerset Substation to resolve asset condition issues | [13 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Proposed | 2018-04-30 | 2019-12-10 | [13 empty] | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 45000000 | 37900000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 41850000 | 42327000 | 42327000 | 42327000 | 42327000 | 42327000 | 42327000 | 42327000 | 0
Reliability Upgrade | 1a | 1634 | MA | National Grid, USA |  |  | 2017-04-01 |  | Reconductor Webster St Tap #1 | [13 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-12-01 | NR | [13 empty] | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 2800000 | 0
Reliability Upgrade | 1a | 1612 | MA | Eversource |  |  | 2017-04-01 | K St to Dewar/Andrew Sq Cable Project | Install one 115 kV breaker to separate K ST 345B bus connection from line 483-525 | [12 empty] | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-08-08 | NR | [12 empty] | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 659000 | 0
Reliability Upgrade | 1a | 1558 | MA | Eversource |  |  | 2016-05-01 | Greater Boston - South | Add a new 345 kV breaker in series with the 104 breaker at Stoughton | [11 empty] | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2015-05-01 | No | [11 empty] | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1500000 | 893000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 936000 | 0
Reliability Upgrade | 1a | 1554 | MA | Eversource |  |  | 2017-04-01 | Greater Boston - Central | Add one 115 kV breaker at K street in series with the 29 breaker | [10 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | in-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No | [10 empty] | Part of RSP 1353 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 1300000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 1323000 | 0
Reliability Upgrade | 1a | 1553 | MA | Eversource |  |  | 2017-06-01 | Greater Boston - Western Suburbs | Add a breaker in series with breaker 104 at Woburn 345 kV switchyard | [10 empty] | Concept | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No | [10 empty] | TBD | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 6967500 | 0
Reliability Upgrade | 1a | 1552 | MA | Eversource |  |  | 2024-03-01 | Greater Boston - North | Add a new 345 kV cable from Woburn substation to the Wakefield substation and terminal equipment at Woburn including a 160 MVAR 345 kV reactor | [10 empty] | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 6/9/2016 7/25/2019 | No | [10 empty] | TBD | 87100000 | 87100000 | 87100000 | 87100000 | 87100000 | 87100000 | 117100000 | 117100000 | 117100000 | 117100000 | 78742045 | 78742045 | 78742045 | 78742045 | 78742045 | 78742045 | 121800000 | 121800000 | 121800000 | 121800000 | 121800000 | 121800000 | 121800000 | 121800000 | 121800000 | 121800000 | 121800000 | 152644000 | 152644000 | 152644000 | 152644000 | 152644000 | 152644000 | 152644000 | 152644000 | 152644000 | 152644000 | 0
Reliability Upgrade | 1a | 1551 | MA | National Grid, USA |  |  | 2024-03-01 | Greater Boston - North | Cable and terminal work at Wakefield 345 kV substation for the new 345 kV cable between Woburn and Wakefield including the addition of a 160 MVAR variable shunt reactor | [10 empty] | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [10 empty] | TBD | 20242797 | 20242797 | 20242797 | 20242797 | 20242797 | 20242797 | 20242797 | 20242797 | 20242797 | 20242045 | 58600000 | 58600000 | 58600000 | 58600000 | 58600000 | 58600000 | 79364000 | 79364000 | 79364000 | 79364000 | 79364000 | 79364000 | 79364000 | 79364000 | 79364000 | 79364000 | 89429000 | 89429000 | 89429000 | 89429000 | 89429000 | 89429000 | 89429000 | 89429000 | 89429000 | 89429000 | 89429000 | 0
Reliability Upgrade | 1a | 1550 | MA | National Grid, USA |  |  | 2019-06-01 | Greater Boston - North | 115 kV Line reconductoring of the F-158S Maplewood - Everett | [10 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No | [10 empty] | Part of RSP 1260 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 4840000 | 4840000 | 4840000 | 5289716 | 5289716 | 5289716 | 5289716 | 5289716 | 6935000 | 6935000 | 6935000 | 6935000 | 6935000 | 6935000 | 6935000 | 6935000 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 7099128 | 0
Reliability Upgrade | 1a | 1549 | MA | National Grid, USA |  |  | 2017-05-01 | Greater Boston - North | 115 kV Line Reconductoring of M-139 between Billerica Tap and Pinehurst and reconductoring of N-140 between Tewksbury and Pinehurst and associated work at Tewksbury | [10 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No | [10 empty] | Part of RSP 1212 | 13160000 | 13160000 | 13160000 | 13160000 | 13160000 | 19970000 | 19970000 | 19970000 | 19970000 | 19967805 | 19967805 | 19967805 | 19967805 | 19967805 | 19967805 | 19967805 | 19967805 | 19967805 | 19967805 | 19967805 | 19967805 | 19967805 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 18138264 | 0
Reliability Upgrade | 1a | 1532 | MA | Eversource |  |  | 2014-12-01 | Pittsfield / Greenfield Project | Remove the sag elimination on the 1512 115 kV line from Blandford substation to Granville Junction and also remove the limitation on the 1421 115 kV line from Pleasant to Blandford substation | [10 empty] | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-12-07 | 2016-02-11 | [10 empty] | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | #VALUE!
Generator Interconnection Upgrade | 2a | 1530 | MA | National Grid, USA |  |  | 2016-10-01 | Footprint Combined Cycle Unit | Add a 115 kV bay with 2 breakers at Salem Harbor 115 kV substation for the interconnection of the new generator | [10 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2014-02-03 | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1527 | MA | National Grid, USA |  |  | 2017-04-01 | Greater Boston - North | Reconductoring National Grid's portion of the Y-151 between Dracut Jct and Power Street (MA portion of the line) | [10 empty] | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [10 empty] | TBD | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | #VALUE!
Reliability Upgrade | 1a | 1526 | MA | National Grid, USA |  |  | 2018-06-01 | Sandy Pond Asset Condition | Sandy Pond Substation refurbishment | [10 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | 2017-07-17 | [10 empty] | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 14050000 | 0
Reliability Upgrade | 1a | 1525 | MA | National Grid, USA |  |  | 2017-03-01 | Pittsfield / Greenfield Project | Loop the A127W line between Cabot Tap and French King into the new Erving Substation | [10 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-12-07 | 2017-07-17 | [10 empty] | 2920000 | 2920000 | 2920000 | 2920000 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | 2920000 | 2920000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 1311000 | 0
Reliability Upgrade | 1a | 1522 | MA | Eversource |  |  | 2017-05-01 | Greater Boston - Central | Add a new 115 kV 36.7 MVAR capacitor bank at Sudbury Station | [10 empty] | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [10 empty] | TBD | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1800000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 1834000 | 0
Reliability Upgrade | 1a | 1520 | MA | Eversource |  |  | 2017-12-01 | Greater Boston - Central | Equipment termination changes at North Cambridge Station to mitigate 115 kV stuck breaker 5 and 10 contingencies | [10 empty] | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2015-10-01 | No | [10 empty] | TBD | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 0
Reliability Upgrade | 1a | 1519 | MA | Eversource |  |  | 2016-12-01 | Greater Boston - Central | Relocate Chelsea capacitor bank 128-518 termination position | [10 empty] | Concept | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No | [10 empty] | TBD | 860000 | 860000 | 860000 | 860000 | 860000 | 860000 | 870000 | 870000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 0
Reliability Upgrade | 1a | 1518 | MA | Eversource |  |  | 2019-03-01 | Greater Boston - Central | Station upgrades to create a second normally closed 115 kV bus tie at Kingston Station and reconfigure the 345 kV switchyard | [10 empty] | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [10 empty] | TBD | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 0
Reliability Upgrade | 1a | 1517 | MA | Eversource |  |  | 2018-05-01 |  | Build a new 115kV Substation - Electric Ave | [10 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-30 | 2017-07-17 | [10 empty] | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 57200000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 53460000 | 0
Reliability Upgrade | 1a | 1516 | MA | Eversource |  |  | 2020-09-01 | Greater Boston - South | Construct a new 115 KV three breaker switching station in Sharon MA to segment the three 115 kV circuits that extend from West Walpole to Holbrook | [10 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Proposed | 2016-06-09 | No | [10 empty] | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 18100000 | 18100000 | 18100000 | 18100000 | 18100000 | 18100000 | 18100000 | 18100000 | 18100000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 20286000 | 0
Reliability Upgrade | 1a | 1511 | MA | National Grid, USA |  |  | 2015-11-01 | New Wakefield Municipal Wallace Substation | Reconductor the S-145/T-146 115 kV lines from Wakefield Junction to new Wallace Substation. | [9 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2013-07-25 | NR | [9 empty] | 1000000 | 1000000 | 1000000 | 1551000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 0
Reliability Upgrade | 1a | 1505 | MA | SELCO |  |  | 2015-04-01 | New Centech Substation | Add a new 115/13.8 kV Centech Substation by looping the E157 W line in and out of this new substation | [8 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-02-28 | NR | [8 empty] | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 0
Reliability Upgrade | 1a | 1504 | MA | National Grid, USA |  |  | 2014-11-01 |  | Install 115 kV breaker and tap lines at E. Main St Substation | [8 empty] | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-05-03 | NR | [8 empty] | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 0
Reliability Upgrade | 1a | 1502 | MA | National Grid, USA |  |  | 2017-12-01 |  | C-181/D-182 Brayton Point - S. Wrentham line refurbishment | [8 empty] | Concept | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | 2016-12-16 | [8 empty] | TBD | TBD | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 17400000 | 24930000 | 24930000 | 24930000 | 24930000 | 24930000 | 24930000 | 24930000 | 24930000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 26459000 | 0
Reliability Upgrade | 1a | 1494 | MA | National Grid, USA |  |  | 2015-04-01 | New Centech Substation | Add a new 115/13.8 kV Centech Substation by looping the E157 W line in and out of this new substation. | [7 empty] | Concept | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-02-28 | NR | [7 empty] | TBD | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 0
Reliability Upgrade | 1a | 1493 | MA | National Grid, USA |  |  | 2017-05-01 | New Highland Park Substation Project | Terminal upgrades at Robinson Ave Substation (V-148S) | [7 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2013-01-18 | 2018-01-03 | [7 empty] | Part of Highland Dr Substation Project - ID 1491 | Part of Highland Dr Substation Project - ID 1491 | Part of Highland Dr Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | Part of Highland Park Substation Project - ID 1491 | #VALUE!
Reliability Upgrade | 1a | 1490 | MA | National Grid, USA |  |  | 2014-11-01 |  | Y-177 Harriman - Montague Asset Condition Replacement (ACR) | [7 empty] | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2014-05-19 | [7 empty] | 8000000 | 8000000 | 8000000 | 8370000 | 8370000 | 8370000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 0
Reliability Upgrade | 1a | 1489 | MA | National Grid, USA |  |  | 2018-06-01 | Sandy Pond Asset Condition | Sandy Pond Control House Rebuild | [7 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | 2017-07-17 | [7 empty] | 10000000 | 10000000 | 10000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 12580000 | 0
Reliability Upgrade | 1a | 1396 | MA | Eversource |  |  | 2013-12-01 | CELD 115/13.8 kV Substation | Loop the 1904 Line into the proposed Memorial Drive Substation | [6 empty] | Concept | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-10-09 | 2015-04-17 | [6 empty] | TBD | 6000000 | 6000000 | 3800000 | 3200000 | 3200000 | 3200000 | 3200000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 3246000 | 0
Reliability Upgrade | 1a | 1395 | MA | National Grid, USA |  |  | 2016-12-01 |  | Tewksbury 22A 345 kV GIS Substation rebuild | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-07-17 | 2016-02-05 | [6 empty] | 31680000 | 31680000 | 31680000 | 31680000 | 31680000 | 31680000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 45384000 | 49099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 46099000 | 0
Reliability Upgrade | 1a | 1394 | MA | Eversource |  |  | 2014-12-01 |  | Add 345 kV breaker at Carver Station to double existing 862 breaker | [6 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | NR | [6 empty] | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 0
Reliability Upgrade | 1a | 1393 | MA | Eversource |  |  | 2016-11-01 |  | Add two 115 kV breakers to Mashpee Station to support double-ending station | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-03-20 | 2015-10-02 | [6 empty] | 10600000 | 10600000 | 10600000 | 10600000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 0
Reliability Upgrade | 1a | 1392 | MA | Eversource |  |  | 2013-12-01 |  | Reconductor 3.5 mile section of the 115 kV line from Barnstable Station to location of new West Barnstable Station | [6 empty] | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-12-07 | NR | [6 empty] | 1700000 | 1700000 | 1700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 0
Reliability Upgrade | 1a | 1368 | MA | Eversource |  |  | 2012-12-01 | NEEWS (Greater Springfield Reliability Project) | Chicopee 18L Substation replace 115 kV circuit breakers 1T and 2 T | [5 empty] | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-05-04 | 2014-02-25 | [5 empty] | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1363 | MA | National Grid, USA |  |  | 2015-12-01 | Greater Boston - Central | Separation of double Circuit Towers on Q-169/F-158N lines | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No | [5 empty] | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 750000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 560000 | 560000 | 560000 | 557000 | 557000 | 557000 | 557000 | 557000 | 557000 | 557000 | 557000 | 557000 | 557000 | 557000 | 557000 | 557000 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 517694 | 0
Reliability Upgrade | 1a | 1360 | MA | National Grid, USA |  |  | 2016-03-01 | Auburn Area Transmission System Upgrades | Harrison Blvd substation A94 Tap | [5 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2010-02-10 | NR | [5 empty] | 400000 | 400000 | 900000 | 900000 | 1200000 | 1200000 | 1200000 | 1200000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 0
Reliability Upgrade | 1a | 1357 | MA | Eversource |  |  | 2019-05-01 | Greater Boston - Central | Open up lines 329-510/511 and 250-516/517 at Mystic and Chatham respectively. Operate K Street as Normally Closed station | [5 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [5 empty] | TBD | TBD | TBD | TBD | TBD | TBD | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 1463000 | 0
Reliability Upgrade | 1a | 1356 | MA | Eversource |  |  | 2024-03-01 | Greater Boston - Central | Add a 2nd Mystic-Woburn 115 kV cable to create a bifurcated 211-514 Mystic-Woburn 115 kV circuit | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [5 empty] | 48000000 | 48000000 | 48000000 | 48000000 | 48000000 | 48000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 81500000 | 81500000 | 81500000 | 81500000 | 81500000 | 81500000 | 81500000 | 81500000 | 81500000 | 138786000 | 138786000 | 138786000 | 138786000 | 138786000 | 138786000 | 138786000 | 138786000 | 138786000 | 138786000 | 138786000 | 223133000 | 223133000 | 223133000 | 223133000 | 223133000 | 223133000 | 223133000 | 223133000 | 223133000 | 223133000 | 0
Reliability Upgrade | 1a | 1355 | MA | Eversource |  |  | 2021-03-01 | Greater Boston - Central | Split existing 110-522/240-510 DCT from Baker St. Station to Needham for a portion of the way and then install a new underground 115 kV line for the remainder of the way | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [5 empty] | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 38000000 | 38000000 | 38000000 | 38000000 | 38000000 | 38000000 | 38000000 | 38000000 | 38000000 | 38000000 | 45700000 | 45700000 | 45700000 | 45700000 | 45700000 | 45700000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 50200000 | 0
Reliability Upgrade | 1a | 1354 | MA | Eversource |  |  | 2020-10-01 | Greater Boston - Central | Add Mystic-Chelsea 115 kV cable | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [5 empty] | 25000000 | 25000000 | 25000000 | 25000000 | 25000000 | 25000000 | 53500000 | 53500000 | 53500000 | 53500000 | 53500000 | 53500000 | 53500000 | 53500000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 56700000 | 0
Reliability Upgrade | 1a | 1353 | MA | Eversource |  |  | 2016-06-01 | Greater Boston - Central | Install K St. tie breaker #33 on the East bus | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2015-11-05 | No | [5 empty] | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 1300000 | 1804000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 1953000 | 0
Reliability Upgrade | 1a | 1352 | MA | Eversource |  |  | 2019-05-01 | Greater Boston - Central | Add a second Mystic 345/115 kV autotransformer and Mystic bus reconfiguration | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [5 empty] | 16000000 | 16000000 | 16000000 | 16000000 | 16000000 | 16000000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 19400000 | 19400000 | 19400000 | 19400000 | 19400000 | 19400000 | 19400000 | 19400000 | 19400000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 25514000 | 0
Reliability Upgrade | 1a | 1351 | MA | Eversource |  |  | 2013-06-01 | Long Term Lower SEMA Upgrades | Install a new 345 kV line from Carver to the vicinity of the Bourne substation and interconnect to the segment of the #120 line section between Bourne and the vicinity of Oak Street. This line will terminate at a new 345/115 kV autotransformer at the West Barnstable Substation | [5 empty] | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 07/2011 | 2011-12-16 | [5 empty] | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | #VALUE!
Reliability Upgrade | 1a | 1350 | MA | Eversource |  |  | 2014-08-01 | Long Term Lower SEMA Upgrades | Expand the existing Bourne 115 kV Substation by adding a new breaker to terminate the existing #120 line between Canal and Barnstable at Bourne | [5 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 07/2011 | 2011-12-16 | [5 empty] | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | #VALUE!
Reliability Upgrade | 1a | 1349 | MA | Eversource |  |  | 2014-08-01 | Long Term Lower SEMA Upgrades | Reconfigure the existing #120 line between Canal and Barnstable into three segments : Canal - Bourne, Bourne to vicinity of Oak Street (to become part of 399 Line), and West Barnstable to Barnstable. | [5 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 07/2011 | 2011-12-16 | [5 empty] | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 0
Reliability Upgrade | 1a | 1345 | MA | Eversource |  |  | 2013-12-01 |  | Build a new 115 kV Bay at Brook Street with the addition of two new 115 kV breakers and a new 115/23 kV transformer |  |  |  |  | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-03-05 | NR |  |  |  |  | 1360000 | 1360000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 1800000 | 0
Reliability Upgrade | 1a | 1344 | MA | Eversource |  |  | 2018-03-01 |  | Framingham BPS station upgrade |  |  |  |  | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | NR | 2017-07-17 |  |  |  |  | TBD | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 11804300 | 11804300 | 11804300 | 11804300 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 12168000 | 0
Reliability Upgrade | 1a | 1342 | MA | Eversource |  |  | 2015-05-01 | NEEWS | Add a new 345 kV Series breaker to the existing 106 breaker at West Medway |  |  |  |  | Concept | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-07-17 | NR |  |  |  |  | 3000000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 0
Reliability Upgrade | 1a | 1341 | MA | Eversource |  |  | 2012-12-01 | Greater Boston - Western Suburbs | Add a new 115 kV 36.7 MVAR capacitor bank at Hartwell Ave |  |  |  |  | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-08-06 | No |  |  |  |  | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 1332000 | 0
Reliability Upgrade | 1a | 1339 | MA | Eversource |  |  | 2016-08-01 | Greater Boston - Western Suburbs | Upgrade 115 kV line 533-508 Lexington-Hartwell Ave by removing line clearance limitation and upgrading station equipment |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | No |  |  |  |  | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 415000 | 415000 | 415000 | 415000 | 415000 | 415000 | 415000 | 145000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 154000 | 0
Reliability Upgrade | 1a | 1338 | MA | Eversource |  |  | 2014-11-01 | Greater Boston - Western Suburbs | Reconductor of the 115 kV line 211-508 from Woburn-Burlington |  |  |  |  | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-07-17 | No |  |  |  |  | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 5382000 | 0
Reliability Upgrade | 1a | 1337 | MA | Eversource |  |  | 2017-12-01 | Greater Boston - Western Suburbs | Reconfigure Waltham Substation and one (1) 115 kV breaker. Includes relocating terminations for PARs and 282-507 line. |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No |  |  |  |  | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 14000000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 0
Reliability Upgrade | 1a | 1336 | MA | Eversource |  |  | 2019-12-01 | Greater Boston - Western Suburbs | Replace the existing 345/115 kV autotransformer with a higher rating transformer and 345 kV and 115 kV switchgear and breakers at Woburn |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No |  |  |  |  | 6100000 | 6100000 | 6100000 | 6100000 | 6100000 | 6100000 | 6100000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 49100000 | 49100000 | 49100000 | 49100000 | 49100000 | 49100000 | 49100000 | 49100000 | 49100000 | 49100000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 57519000 | 0
Reliability Upgrade | 1a | 1335 | MA | Eversource |  |  | 2024-12-01 | Greater Boston - Western Suburbs | Build a new 115 kV line from Sudbury Station 342 substation to Hudson substation and add a 30 MVAR shunt reactor at the Sudbury station |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 06/09/2016 10/05/2020 | No |  |  |  |  | 41000000 | 41000000 | 41000000 | 41000000 | 41000000 | 41000000 | 41000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 45300000 | 45300000 | 45300000 | 45300000 | 45300000 | 45300000 | 45300000 | 45300000 | 45300000 | 45300000 | 45300000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 91000000 | 105440000 | 105440000 | 105440000 | 128520000 | 128520000 | 128520000 | 128520000 | 128520000 | 128520000 | 128520000 | 128520000 | 128520000 | 128520000 | 0
Reliability Upgrade | 1a | 1330 | MA | National Grid, USA |  |  | 2018-12-01 | Greater Boston - Western Suburbs | X-24/E-157W DCT Separation |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No |  |  |  |  | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 0
Reliability Upgrade | 1a | 1329 | MA | National Grid, USA |  |  | 2015-12-01 | Greater Boston - Western Suburbs | Refurbishment of 69 kV line X-24 Millbury-Northboro Rd |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | No |  |  |  |  | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 8500000 | 6060000 | 6060000 | 6060000 | 5793000 | 5793000 | 5793000 | 5793000 | 5793000 | 5793000 | 5793000 | 5576000 | 5576000 | 5576000 | 5576000 | 5576000 | 5576000 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 5588743 | 0
Reliability Upgrade | 1a | 1327 | MA | National Grid, USA |  |  | 2019-06-01 | Greater Boston - Western Suburbs | 69 kV Line reconductoring of W-23W Woodside-Northboro Rd |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No |  |  |  |  | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 7080000 | 0
Reliability Upgrade | 1a | 1293 | MA | National Grid, USA |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | Carpenter Hill Substation Relay Upgrades |  |  |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | NR | 2015-12-17 |  |  |  |  | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1715000 | 1715000 | 1715000 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | Part of 1094 | #VALUE!
Reliability Upgrade | 1a | 1275 | MA | Eversource |  |  | 2013-06-01 | Western New Hampshire Solution | Upgrade the 381 345 kV line between Northfield and the NH/VT border |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-12-07 | 2015-12-17 |  |  |  | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 2500000 | 2500000 | 2500000 | 2000000 | 2000000 | 2000000 | 2000000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 2013000 | 0
Reliability Upgrade | 1a | 1268 | MA | Eversource |  |  | 2013-12-01 |  | 345 kV Northfield Mountain to Berkshire (portion of 312) line structure replacements |  |  |  | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2015-04-17 |  |  |  | 7900000 | 7900000 | 8900000 | 8900000 | 9050000 | 9050000 | 9050000 | 8900000 | 8900000 | 8900000 | 8900000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 8920000 | 0
Reliability Upgrade | 1a | 1267 | MA | Eversource |  |  | 2011-12-01 |  | 115 kV Blandford to Southwick (portion of 1512) Line structure replacement |  |  |  | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2015-04-17 |  |  |  | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 9220000 | 0
Reliability Upgrade | 1a | 1266 | MA | Eversource |  |  | 2012-12-01 |  | 115kV Pleasant to Blandford (portion of 1421) Line structure replacement |  |  |  | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2015-04-17 |  |  |  | 9960000 | 9960000 | 12200000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 14515000 | 0
Reliability Upgrade | 1a | 1260 | MA | National Grid, USA |  |  | 2015-12-01 | Greater Boston - North | Reconductor the F-158N 115kV line form Wakefield Jct - Maplewood and associated Maplewood Substation work |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No |  |  |  | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 5400000 | 5400000 | 6100000 | 6100000 | 6100000 | 6100000 | 6030000 | 6030000 | 6030000 | 6028295 | 6028295 | 6028295 | 6028295 | 6028295 | 6028295 | 6028295 | 6028295 | 6028295 | 6028295 | 6028295 | 6028295 | 6028295 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 5902479 | 0
Reliability Upgrade | 1a | 1259 | MA | National Grid, USA |  |  | 2013-02-01 | Salem Harbor Retirement | 115 kV line Reconductoring of the B154N/C-155N from King St Tap - South Danvers |  |  |  | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-07-28 | 2014-03-12 |  |  |  | 20000000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 17905000 | 0
Reliability Upgrade | 1a | 1258 | MA | National Grid, USA |  |  | 2014-02-01 | Salem Harbor Retirement | 115 kV line Reconductoring of the Y-151 from Tewksbury Junction - West Methuen |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-07-28 | 2017-12-01 |  |  |  | 11500000 | 14500000 | 14500000 | 21000000 | 18600000 | 18600000 | 18600000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 24250000 | 24250000 | 24250000 | 24250000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 23775000 | 0
Reliability Upgrade | 1a | 1257 | MA | National Grid, USA |  |  | 2013-08-01 | Salem Harbor Retirement | 115 kV line Reconductoring of the S-145/T-146 from Tewksbury-North Reading Tap |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/28/2011 3/7/2013 | 2014-03-12 |  |  |  | 29000000 | 29000000 | 29000000 | 10500000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 10737000 | 0
Reliability Upgrade | 1a | 1256 | MA | Unitil |  |  | 2012-06-01 | Flagg Pond Upgrades | At Flagg Pond Substation upgrade terminal equipment on the I-135, I-135S, J-136N and J-136S 115 kV lines and Zone 3 relay upgrades for the J-136N 115 kV line. |  |  |  | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR |  |  |  | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 0
Reliability Upgrade | 1a | 1255 | MA | CELD (Chicopee Electric Light Department) |  |  | 2014-01-01 | CELD 115/13.8 kV Substation | 115/13.8 kV substation on Memorial Dr. with two transformers and twelve feeders looped into 1904 (1723) line between Piper and Fairmont substations - includes .7 miles x 2 of transmission line construction (1638/1904 lines) |  |  |  | Concept | Concept | Proposed | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-10-09 | 2015-04-17 |  |  |  | TBD | TBD | 2900000 | 2900000 | 2900000 | 3800000 | 3800000 | 4000000 | 4386352 | 4386352 | 4386352 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 4465000 | 0
Reliability Upgrade | 1a | 1225 | MA | Eversource |  |  | 2016-11-01 | Pittsfield / Greenfield Project | Rebuild the Cumberland to Montague 1361/1242 115 kV double circuit line and terminal work at Cumberland and Montague. At Montague substation, reconnect Y177 115 kV line into 3T/4T position, and perform other associated substation work |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 12/7/2012 1/26/2016 | 2016-02-11 |  | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | #VALUE!
Reliability Upgrade | 1a | 1224 | MA | Eversource |  |  | 2015-12-01 | Pittsfield / Greenfield Project | Install 115 kV 14.4 MVAR capacitor banks at Cumberland, Podick and Amherst Substations |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2012-12-07 | 2016-02-11 |  | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | #VALUE!
Reliability Upgrade | 1a | 1223 | MA | Eversource |  |  | 2017-06-01 | Pittsfield / Greenfield Project | Build a new 115 kV line from Northfield Mountain to the new Erving Switching Station |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-12-07 | 2016-02-11 |  | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | #VALUE!
Reliability Upgrade | 1a | 1222 | MA | Eversource |  |  | 2017-03-01 | Pittsfield / Greenfield Project | Build a new 115 kV three breaker Switching Station (Erving) ring bus |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-12-07 | 2016-02-11 |  | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | #VALUE!
Reliability Upgrade | 1a | 1221 | MA | Eversource |  |  | 2017-06-01 | Pittsfield / Greenfield Project | Modify Northfield Mountain 16R substation and install a 345/115 kV autotransformer |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-12-07 | 2016-02-11 |  | 108500000 | 108500000 | 108500000 | 108500000 | 108500000 | 108500000 | 109500000 | 109500000 | 109500000 | 113400000 | 113400000 | 113400000 | 113400000 | 113400000 | 113400000 | 113400000 | 113400000 | 113400000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 94000000 | 0
Reliability Upgrade | 1a | 1217 | MA | Eversource |  |  | 2014-10-01 | Central/Western Massachusetts Upgrades - Group 4 - E. Longmeadow Projects | 1515 Line work and substation work at Ludlow (MA) associated with the new Hampden (MA) substation project (NGRID) |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2016-10-04 |  | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3140000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 3226000 | 0
Reliability Upgrade | 1a | 1216 | MA | Eversource |  |  | 2012-04-01 |  | 345 kV Ludlow - Northfield (portion of 354) Line Structure replacements |  | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2015-04-17 |  | 17000000 | 17000000 | 25100000 | 25100000 | 25100000 | 25100000 | 25100000 | 25100000 | 25100000 | 25100000 | 25100000 | 25100000 | 25100000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 23393000 | 0
Reliability Upgrade | 1a | 1214 | MA | National Grid, USA |  |  | 2013-07-01 | Greater Boston - South | Line reconductoring of the C-129N Beaver Pond - Depot St. Tap) and D-130 (Depot St. Tap - Medway) 115 kV lines |  | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-10-26 | No |  | 500000 | 500000 | 500000 | 500000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 676000 | 0
Reliability Upgrade | 1a | 1213 | MA | National Grid, USA |  |  | 2017-12-01 | Greater Boston - North | Install new 345 kV (3124) circuit between NH/MA border and Tewksbury (this is the MA portion of NGRID's portion of the new Scobie-Tewksbury circuit) and associated substation work at Tewksbury |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No |  | 23370000 | 23370000 | 23370000 | 23370000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 86027382 | 86027382 | 86027382 | 86027382 | 86027382 | 86027382 | 86027382 | 86027382 | 86027382 | 83285224 | 83285224 | 83285224 | 83285224 | 83285224 | 83285224 | 83285224 | 83285224 | 83285224 | 83285224 | 83285224 | 83285224 | 83285224 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 72180765 | 0
Reliability Upgrade | 1a | 1212 | MA | National Grid, USA |  |  | 2016-12-01 | Greater Boston - North | 115 kV Line Reconductoring of M-139 between Tewksbury-Billerica Tap and associated work at Tewksbury |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-05-01 | No |  | 57000000 | 57000000 | 11600000 | 11600000 | 12150000 | 12150000 | 12150000 | 12150000 | 12150000 | 12150000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | Part of Project RSP 1549 | #VALUE!
Reliability Upgrade | 1a | 1209 | MA | National Grid, USA |  |  | 2015-04-01 | Pittsfield / Greenfield Project | Reconductoring of A127 between Erving and Cabot Tap with 2-477 ACCR includes switch replacements at Wendell Depot |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-12-07 | 2017-07-17 |  | 12000000 | 12000000 | 12000000 | 12000000 | 8760000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 7200000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 6256000 | 0
Reliability Upgrade | 1a | 1208 | MA | National Grid, USA |  |  | 2017-03-01 | Pittsfield / Greenfield Project | Separation and reconductoring of Cabot Taps (A-127 and Y-177 115kV lines). This involves 795 ACSS for the Y-177 line and 1590 ACSS for the A-127 tap. |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-12-07 | 2017-07-17 |  | 7400000 | 7400000 | 7400000 | 7400000 | 10500000 | 13100000 | 13100000 | 13100000 | 13100000 | 12580000 | 12580000 | 12970000 | 12970000 | 12970000 | 12970000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 15723000 | 0
Reliability Upgrade | 1a | 1207 | MA | Eversource | Belmont Municipal Light Department |  | 2016-12-01 | Blair Pond Substation Project | Build a new 115kV Substation, the Blair Pond Substation Facilities being constructed by Belmont Municipal Light Department |  | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2021-04-14 |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 71103000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 70702000 | 0
Reliability Upgrade | 1a | 1202 | MA | Eversource |  |  | 2014-12-01 | NEEWS | Rebuild 1.2 mile length of line 336 with 2-900 ACSS conductor and replace 5, 345 kV 2000 amp disconnect switches with 3000 amp switches at W. Medway station |  | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-03-30 | NR |  | 2200000 | 1700000 | 1700000 | 1700000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 0
Reliability Upgrade | 1a | 1201 | MA | Eversource | National Grid, USA |  | 2012-12-01 | Greater Boston - North | 115 kV line Reconductoring of the P168/128-518 Line between Chelsea and Revere (NSTAR Portion of the line) |  | Proposed | Proposed | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-06-07 | No |  | 1200000 | 800000 | 1500000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 785000 | 0
Reliability Upgrade | 1a | 1199 | MA | Eversource |  |  | 2017-12-01 | Greater Boston - Western Suburbs | Install a new 230/115 kV autotransformer at Sudbury Loop 230 kV line 282-602 in and out of a new 230 kV switchyard at Sudbury |  | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2015-07-23 | No |  | TBD | TBD | TBD | 23500000 | 23500000 | 23500000 | 23500000 | 23500000 | 23500000 | 25000000 | 28100000 | 28100000 | 28100000 | 28100000 | 28100000 | 28100000 | 34920000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 34018000 | 0
Reliability Upgrade | 1a | 1191 | MA | Eversource |  |  | 2012-12-01 |  | Rebuild Section of Line 322 (Canal-Carver) | Concept | Concept | Concept | Concept | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 11700000 | 12200000 | 12200000 | 12200000 | 13000000 | 13000000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 0
Reliability Upgrade | 1a | 1187 | MA | National Grid, USA |  |  | 2015-04-01 | A127/B128 Conductor Refurbishment | A127/B128 Conductor Refurbishment - Tower 510 to Harriman Substation, VT | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 01/20/2011 | 2011-12-16 | 65000000 | 65000000 | 65000000 | 65000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 78000000 | 0
Reliability Upgrade | 1a | 1175 | MA | Eversource |  |  | 2014-05-01 | Greater Boston - South | Upgrade the 115 kV line 201-501 (Medway-Depot St.) and the 201-502 (Beaver Pond - Depot Street Tap) to a higher capacity line | Concept | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service |  | 2011-10-26 | No | TBD | 3700000 | 3700000 | 3700000 | 4110000 | 4110000 | 4110000 | 4110000 | 4110000 | 4110000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 4550000 | 4550000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 4535000 | 0
Reliability Upgrade | 1a | 1168 | MA | Holyoke Gas & Electric |  |  | 2012-12-01 | North Canal 44P | Loop the 1525 (Holyoke Fairmont South 115 kV) line into the new North Canal 44P Substation. | Concept | Concept | Proposed | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-05-25 | NR | TBD | TBD | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 4950546 | 0
Reliability Upgrade | 1a | 1167 | MA | Northeast Utilities - NSTAR |  |  | 2010-12-01 |  | Replace three 40 kA 115 kV circuit breakers at Carver with 63 kV breakers | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 1000000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 0
Reliability Upgrade | 1a | 1166 | MA | Northeast Utilities - NSTAR |  |  | 2010-12-01 |  | Terminal upgrades at W. Walpole and W, Medway for #325 line | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 1200000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 770000 | 0
Reliability Upgrade | 1a | 1165 | MA | Eversource |  |  | 2012-11-01 | Mystic Breaker Additions Project | Move Transformer 110B Connection at Mystic | Planned | Planned | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-03-10 | NR | 1700000 | 1700000 | 1900000 | 2600000 | 2600000 | 2600000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 0
Reliability Upgrade | 1a | 1152 | MA | National Grid, USA |  |  | 2010-08-01 |  | Bear Swamp - Pratts Junction 230 kV Line Refurbishment Project (E205E) | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 43596000 | 0
Reliability Upgrade | 1a | 1139 | MA | Northeast Utilities |  |  | 2010-10-01 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115 kV M183 Line | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-06-29 | 2011-07-15 | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | #VALUE!
Reliability Upgrade | 1a | 1119 | MA | Northeast Utilities - NSTAR |  |  | 2010-04-01 | Greater Boston Reliability Project | Upgrade West Medway-West Walpole 345 kV line #325 | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | NR | NR | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 950000 | 0
Reliability Upgrade | 1a | 1118 | MA | National Grid, USA | Eversource |  | 2013-05-01 | Long Term Lower SEMA Upgrades | Upgrade 115 kV line D21 (Bellrock-High Hill) | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 07/2011 | 2014-09-08 | TBD | Part of Long Term Lower SEMA | 6000000 | 6000000 | 6000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 0
Reliability Upgrade | 1a | 1109 | MA | National Grid, USA |  |  | 2011-12-01 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115 kV terminal equipment upgrades | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2015-12-17 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 0
Reliability Upgrade | 1a | 1105 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV line 1601, Fairmont to Shawinigan and add a 2nd High Speed Protection | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1104 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV 1803, Fairmont to Cadwell | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1103 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV line 1702 Fairmont t to Chicopee | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1102 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV line 1904, Fairmont to Piper | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1101 | MA | Eversource |  |  | 2012-10-01 | NEEWS (Greater Springfield Reliability Project) | Reconductor 115 kV line 1552, Ludlow to Orchard | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1100 | MA | Eversource |  |  | 2012-01-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV line 1314, Agawam to Chicopee | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1098 | MA | National Grid, USA |  |  | 2011-12-01 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115 kV line interconnections at Berry Street | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-04-25 | 2012-06-06 | 37529000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 0
Reliability Upgrade | 1a | 1094 | MA | National Grid, USA |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345 kV Millbury Substation equipment | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 9/24/2008 5/4/2012 | 2015-12-17 | 25000000 | 25000000 | 25000000 | 25000000 | 30700000 | 30700000 | 30700000 | 30700000 | 30700000 | 30700000 | 30700000 | 30700000 | 27480000 | 27480000 | 27480000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 26000000 | 0
Reliability Upgrade | 1a | 1092 | MA | Eversource |  |  | 2014-06-01 | NEEWS | Upgrade the Agawam 115 kV Substation to BPS standards together with other misc. substation upgrades | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2014-02-25 | 37000000 | 13600000 | 13600000 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 0
Reliability Upgrade | 1a | 1080 | MA | Eversource |  |  | 2012-12-01 | NEEWS (Greater Springfield Reliability Project) | Shawinigan 55E Substation Replace 115 kV circuit breakers 1T, 2T, 4T and 6T | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1077 | MA | Eversource |  |  | 2011-04-01 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115 kV line | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2014-02-25 | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | #VALUE!
Reliability Upgrade | 1a | 1076 | MA | Eversource |  |  | 2011-12-01 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115 kV line | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2014-02-25 | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | #VALUE!
Reliability Upgrade | 1a | 1074 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Reterminate 115 kV line 1645, Cadwell to East Springfield | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1073 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Reterminate 115 kV line 1556, Cadwell to East Springfield | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1072 | MA | Eversource |  |  | 2012-11-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV line 1845, Ludlow to Shawinigan and add 2nd High Speed Protection | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1071 | MA | Eversource |  |  | 2012-11-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV line 1782 Agawam to South Agawam and add 2nd High Speed Protection | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1070 | MA | Eversource |  |  | 2012-11-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV line 1781, Agawam to South Agawam and add 2nd High Speed Protection | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1068 | MA | Eversource |  |  | 2013-09-01 | Long Term Lower SEMA Upgrades | Install the new West Barnstable 345/115 kV substation 3 miles west of the existing Barnstable 115 kV substation by looping the #115 line between Mashpee and Barnstable. The substation will have a 8 breakers in a double breaker configuration on the 115 kV switchyard | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 07/2011 2/11/2014 | 2011-12-16 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | 106500000 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | Part of RSP 1349 | #VALUE!
Reliability Upgrade | 1a | 1067 | MA | Northeast Utilities - NSTAR |  |  | 2010-12-01 | NPCC BPS Compliance | Tremont Station | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2015-12-17 | 10000000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 6655000 | 6655000 | 6655000 | 6655000 | 6655000 | 6655000 | 6655000 | 6655000 | 6655000 | 6655000 | 6655000 | 6655000 | 0
Reliability Upgrade | 1a | 1066 | MA | Eversource |  |  | 2011-12-01 | NPCC BPS Compliance | Needham Station | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2011-12-28 | 9500000 | 9500000 | 6500000 | 8000000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 6705000 | 0
Reliability Upgrade | 1a | 1065 | MA | Eversource |  |  | 2013-06-01 | NPCC BPS Compliance | Waltham Station | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2012-12-13 | 23190000 | 14700000 | 14700000 | 14700000 | 17000000 | 17000000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 17750000 | 0
Reliability Upgrade | 1a | 1010 | MA | Eversource |  |  | 2011-12-01 | NEEWS (Greater Springfield Reliability Project) | Build 115 kV Cadwell switching 50F station. | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-09-24 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 1000 | MA | Eversource |  |  | 2011-04-01 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-06-27 | 2012-09-20 | 26000000 | 26000000 | 26000000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 27500000 | 0
Reliability Upgrade | 1a | 969 | MA | Eversource |  |  | 2012-11-01 | Greater Boston - North | Add a new 115 kV 36.7 MVAR capacitor bank at Chelsea. | Concept | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-03-30 | No | 1600000 | 1500000 | 1500000 | 1500000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 0
Reliability Upgrade | 1a | 965 | MA | Eversource |  |  | 2020-09-01 | Greater Boston - South | Add third 115 kV line from W. Walpole to Holbrook | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Proposed | 2016-06-09 | No | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 17300000 | 17300000 | 17300000 | 17300000 | 17300000 | 17300000 | 17300000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 29877000 | 0
Reliability Upgrade | 1a | 955 | MA | National Grid, USA |  |  | 2016-12-01 | Central/Western Massachusetts Upgrades - Group 4 - E. Longmeadow Projects | Refurbish and reconductor (W175) West Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 12/17/2007 | 2016-10-04 | 13800000 | 13800000 | 13800000 | 13800000 | 13800000 | 13800000 | 13800000 | 13800000 | 13800000 | 13800000 | 23970000 | 23970000 | 23970000 | 26000000 | 26000000 | 26000000 | 28000000 | 28000000 | 28000000 | 28000000 | 28000000 | 28000000 | 28000000 | 28000000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 27860000 | 0
Reliability Upgrade | 1a | 949 | MA | National Grid, USA |  |  | 2015-11-01 | Central/Western Massachusetts Upgrades - Group 4 - E. Longmeadow Projects | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2011-03-29 | 2016-10-04 | 1500000 | 1500000 | 1600000 | 1600000 | 1600000 | 1600000 | 2280000 | 2280000 | 2280000 | 1500000 | 1520000 | 1520000 | 1520000 | 1600000 | 1600000 | 1600000 | 2258000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 3350000 | 0
Reliability Upgrade | 1a | 948 | MA | National Grid, USA |  |  | 2014-10-01 | Central/Western Massachusetts Upgrades - Group 4 - E. Longmeadow Projects | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-03-29 | 2016-10-04 | 5649430 | 5649430 | 13400000 | 13400000 | 13400000 | 13400000 | 19700000 | 19700000 | 19700000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 13000000 | 0
Reliability Upgrade | 1a | 946 | MA | National Grid, USA |  |  | 2015-12-01 | Central/Western Massachusetts Upgrades - Group 4 - E. Longmeadow Projects | Convert 69 kV (O-15S) Palmer- W. Hampden to 115 kV. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2011-03-29 | 2016-10-04 | 9962060 | 9962060 | 16000000 | 16000000 | 16000000 | 16000000 | 19803000 | 19803000 | 19803000 | 19803000 | 19803000 | 19803000 | 19803000 | 21700000 | 21700000 | 21700000 | 21700000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 20400000 | 0
Reliability Upgrade | 1a | 945 | MA | National Grid, USA |  |  | 2018-12-01 | Central/Western Massachusetts Upgrades - Group 6 - Miscellaneous Western Ma Projects | Adams - install two new 115 kV breakers and replace two existing 115 kV breakers and associated line relocations | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 12/17/2007 12/7/2012 | 2018-10-16 | 1584841 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16900000 | 16918000 | 16918000 | 16918000 | 16918000 | 16918000 | 16918000 | 16918000 | 16918000 | 0
Reliability Upgrade | 1a | 944 | MA | National Grid, USA |  |  | 2012-03-01 | Central/Western Massachusetts Upgrades - Group 1 Central MA supply improvements | Wachusett - install one 345 kV, 448 MVA transformer, one 345 kV breaker, and one 115 kV breaker. | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2012-02-29 | 16530000 | 16530000 | 16530000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 0
Reliability Upgrade | 1a | 943 | MA | National Grid, USA |  |  | 2013-06-01 | Central/Western Massachusetts Upgrades - Group 2 - Webster St. Supply Improvements | Millbury - new 115 kV breaker position for new line to Tower 510. | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | No | 1073995 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 0
Reliability Upgrade | 1a | 942 | MA | National Grid, USA |  |  | 2013-06-01 | Central/Western Massachusetts Upgrades - Group 2 - Webster St. Supply Improvements | Webster St. - add two 115 kV circuit breakers. | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | No | 3650000 | 3650000 | 3650000 | 3650000 | 3650000 | 3650000 | 3650000 | 3650000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 3801000 | 0
Reliability Upgrade | 1a | 941 | MA | National Grid, USA |  |  | 2014-07-01 | Central/Western Massachusetts Upgrades - Group 2 - Webster St. Supply Improvements | Install new Z126 Millbury - Tower #510 115 kV line | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2014-04-23 | 13748000 | 13748000 | 13748000 | 13748000 | 13748000 | 13748000 | 13748000 | 13748000 | 13748000 | 13748000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 0
Reliability Upgrade | 1a | 940 | MA | National Grid, USA |  |  | 2015-04-01 | A127/B128 Conductor Refurbishment | Reconductor sections of A127W line w/477 ACSS (A127 West reconductoring. Tower 510 to Paxton, Wendell Depot to Cabot Tap). | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-05-30 | 2011-12-16 | 18000000 | 18000000 | 18000000 | 18000000 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | Part of RSP 1187 | #VALUE!
Reliability Upgrade | 1a | 939 | MA | National Grid, USA |  |  | 2011-02-01 | Central/Western Massachusetts Upgrades | Reconductor and retention (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2012-09-20 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 0
Reliability Upgrade | 1a | 938 | MA | National Grid, USA |  |  | 2013-11-01 | Central/Western Massachusetts Upgrades - Group 6 - Miscellaneous Western Ma Projects | Deerfield - install a new 115/69 kV autotransformer and a 69 kV breaker and disconnect switches | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2014-04-23 | 3068556 | 3068556 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 5430000 | 0
Reliability Upgrade | 1a | 937 | MA | National Grid, USA |  |  | 2017-12-01 | Central/Western Massachusetts Upgrades - Group 3 Bear Swamp/Pratts Junction Projects | Bear Swamp - install one 230/115 kV 333 MVA auto transformer, one 115 kV breaker, four 230 kV breaker replacements and upgrade various terminal equipment. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 12/17/2007 | 2018-04-17 | 6602875 | 6602875 | 6602875 | 6602875 | 6602875 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 17000000 | 20480000 | 21135000 | 21135000 | 21135000 | 20470000 | 20470000 | 20470000 | 20470000 | 20470000 | 20470000 | 20470000 | 20470000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 20853000 | 0
Reliability Upgrade | 1a | 935 | MA | National Grid, USA |  |  | 2014-04-01 | Central/Western Massachusetts Upgrades - Group 2 - Webster St. Supply Improvements | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2014-04-23 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 10200000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 12900000 | 0
Reliability Upgrade | 1a | 934 | MA | National Grid, USA |  |  | 2013-02-01 | Central/Western Massachusetts Upgrades - Group 2 - Webster St. Supply Improvements | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2014-04-23 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | Part of RSP 935 | #VALUE!
Reliability Upgrade | 1a | 932 | MA | National Grid, USA |  |  | 2012-10-01 | Central/Western Massachusetts Upgrades - Group 3 Bear Swamp/Pratts Junction Projects | Pratts Jct. - increase thermal rating of I-135 and J-136 bus work. | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2012-02-29 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | #VALUE!
Reliability Upgrade | 1a | 929 | MA | National Grid, USA |  |  | 2014-12-01 | Central/Western Massachusetts Upgrades - Group 6 - Miscellaneous Western Ma Projects | Searsburg - install in-line 69 kV breaker | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | No | 1381849 | 1381849 | 2500000 | 2500000 | 2500000 | 2500000 | 3300000 | 3300000 | 3300000 | 3000000 | 3957000 | 3957000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 3370000 | 0
Reliability Upgrade | 1a | 928 | MA | National Grid, USA |  |  | 2013-12-01 | Central/Western Massachusetts Upgrades - Group 1 Central MA supply improvements | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2012-02-29 | 2300000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 0
Reliability Upgrade | 1a | 926 | MA | National Grid, USA |  |  | 2012-05-01 | Central/Western Massachusetts Upgrades - Group 3 Bear Swamp/Pratts Junction Projects | Pratts Jct. - replace T8 autotransformer with 230 kV 333 MVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2012-12-27 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 14700000 | 0
Reliability Upgrade | 1a | 925 | MA | National Grid, USA |  |  | 2013-12-01 | Central/Western Massachusetts Upgrades - Group 3 Bear Swamp/Pratts Junction Projects | Pratts Jct. - supply 13 kV from T3 and T4 | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2012-12-27 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | Part of RSP 926 | #VALUE!
Reliability Upgrade | 1a | 924 | MA | National Grid, USA |  |  | 2011-07-01 | Central/Western Massachusetts Upgrades | Carpenter Hill - Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/17/2007 | 2012-02-29 | 3600000 | 3600000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 4200000 | 0
Reliability Upgrade | 1a | 921 | MA | National Grid, USA |  |  | 2013-06-01 | Auburn Area Transmission System Upgrades | Bridgewater substation ; Upgrade 115 kV and 345 kV switchyards to BPS. Add two 115 kV breakers for E1 line; replace five 115 kV breakers and two 345 kV breakers; includes bus work. | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 1/28/2008 10/27/2003 | 2014-02-03 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 31110000 | 0
Reliability Upgrade | 1a | 919 | MA | National Grid, USA |  |  | 2014-04-01 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade bus work and convert to BPS substation. Includes adding 5 breakers ring bus configuration and a second distribution transformer. Terminal upgrades to increase ratings on G18 and C2 | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-02-10 | 2014-02-03 | 4600000 | 4600000 | 9200000 | 13600000 | 13600000 | 13600000 | 13600000 | 12000000 | 12000000 | 12000000 | 12000000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 0
Reliability Upgrade | 1a | 904 | MA | Northeast Utilities - NSTAR |  |  | 2010-12-01 | Mystic IPT Breaker Project | Upgrade (5) 115 kV breakers #1, #7, #15 #19 and #20 at Mystic to IPT. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | NR | 1500000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 2250000 | 0
Reliability Upgrade | 1a | 902 | MA | National Grid, USA |  |  | 2010-10-01 | Middleboro Municipal | Close the E1-M1 loop at Middleboro's Wareham St Sub. | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 12/01/2006 | NR | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 0
Reliability Upgrade | 1a | 887 | MA | National Grid, USA |  |  | 2014-03-01 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to BPS standards with 2nd 345/115 kV autotransformer and 345 kV ring bus to accommodate 2nd autotransformer. Includes breaker and a third scheme | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-02-10 | 2014-02-03 | 76000000 | 76000000 | 66300000 | 58000000 | 58000000 | 58000000 | 58000000 | 58000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 73000000 | 0
Reliability Upgrade | 1a | 843 | MA | Eversource |  |  | 2013-12-01 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | Concept | Concept | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-01-05 | NR | TBD | TBD | 3200000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 3450000 | 0
Reliability Upgrade | 1a | 840 | MA | Eversource |  |  | 2012-12-01 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-04-01 | 2011-01-10 | 5900000 | 5900000 | 5900000 | 5900000 | 5900000 | 5900000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 0
Reliability Upgrade | 1a | 829 | MA | Eversource |  |  | 2012-04-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV line 1230 Agawam to Piper | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 828 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115 kV circuit 1322 Reactor Bypass and Open Breckwood Substation 1T breaker and maintain breaker in the normally open position | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 826 | MA | Eversource |  |  | 2013-03-01 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigured | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 823 | MA | Eversource |  |  | 2012-12-01 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115 kV autotransformer replacements. | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 820 | MA | Eversource |  |  | 2012-12-01 | NEEWS (Greater Springfield Reliability Project) | Agawam 16C 115 kV Substation expansion, two 345/115 kV autotransformer additions, BPS Classification | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 819 | MA | Eversource |  |  | 2012-11-01 | NEEWS (Greater Springfield Reliability Project) | Build new 345 kV line 3196, Ludlow - Agawam | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 818 | MA | Eversource |  |  | 2013-02-01 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115 kV 1768 line South Agawam to Southwick | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 790 | MA | National Grid, USA |  |  | 2011-12-01 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-04-25 | 2012-06-06 | 50600000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 0
Reliability Upgrade | 1a | 786 | MA | National Grid, USA |  |  | 2011-05-01 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Terminal upgrades at Drumrock, Chartley Pond, and Brayton Point | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-04-25 | 2012-06-06 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 0
Reliability Upgrade | 1a | 783 | MA | National Grid, USA |  |  | 2011-04-01 | Merrimack Valley/North Shore Reliability Project | Extend the 115 kV by addition of 115 kV Breaker and K-163 line from King St. to W. Amesbury 115 kV station. (W. Amesbury 345/115 kV Station becomes PTF) | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-04-01 | 2012-08-03 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 0
Reliability Upgrade | 1a | 782 | MA | National Grid, USA |  |  | 2016-06-01 |  | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor and Railyard. | Planned | Planned | Planned | Planned | Planned | Concept | Concept | Concept | Concept | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-02-11 | 2016-12-16 | 43912000 | 43912000 | 43912000 | 43912000 | 43912000 | 41523000 | 41523000 | 41523000 | 41523000 | 41523000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 62427000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 58042000 | 0
Reliability Upgrade | 1a | 776 | MA | National Grid, USA |  |  | 2013-04-01 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-06-27 | 2012-06-01 | 3125000 | 3125000 | 3125000 | 3125000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 0
Reliability Upgrade | 1a | 688 | MA | Eversource |  |  | 2012-11-01 | NEEWS (Greater Springfield Reliability Project) | Reconductor/rebuild 115 kV line 1481, Ludlow to Cadwell | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 687 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont 16H 115 kV Switching Station | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | 714000000 | 795000000 | 795000000 | 718000000 | 718000000 | 718000000 | 718000000 | 718000000 | 718000000 | 718000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 676000000 | 0
Reliability Upgrade | 1a | 676 | MA | National Grid, USA |  |  | 2012-06-01 | Worcester Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115 kV breaker at Bloomingdale & Vernon Hill | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-02-27 | 2011-07-15 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 0
Reliability Upgrade | 1a | 673 | MA | National Grid, USA |  |  | 2012-03-01 | Worcester Area Reinforcements | Add new 115 kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-02-27 | 2011-07-15 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 0
Reliability Upgrade | 1a | 592 | MA | Eversource |  |  | 2013-06-01 | Long Term Lower SEMA Upgrades | Separate existing 345 kV double circuit Cape Cod Canal crossing. The lines being separated are 322 (Canal-Carver) and 342 (Canal-Pilgrim-Auburn) | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 07/2011 | 2011-12-16 | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | Part of RSP 1068 | #VALUE!
Generator Interconnection Upgrade | 2a | 505 | MA | National Grid, USA |  |  | 2012-12-01 | Hoosac Wind Farm | Tap Y-25S line between Harriman and Deerfield 5. Construct 69/34.5 kV substation and 34.5 kV line connecting 30 MW generating facility with the 69 kV system. | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 02/01/2005 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 301 | MA | Eversource |  |  | 2011-12-01 | Greater Boston - Central | Reconductor 115 kV circuits 320-507 and 320-508. (Lexington - Waltham) | Concept | Concept | Concept | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-02-15 | 2011-12-16 | 8400000 | 8400000 | 8400000 | 9600000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 0
Reliability Upgrade | 1a | 259 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Rebuild 115 kV line 1426, Cadwell to Orchard | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 196 | MA | Eversource |  |  | 2013-03-01 | NEEWS (Greater Springfield Reliability Project) | Build new 345 kV line (3216), Agawam (MA) - North Bloomfield (CT) (MA portion) | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 9/24/2008 05/04/2012 | 2014-02-25 | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Reliability Upgrade | 1a | 190 | MA | National Grid, USA |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | New 345 kV (366) line Millbury to MA/RI state line | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 9/24/2008 5/4/2012 | 2015-12-17 | 69600000 | 81800000 | 81800000 | 81800000 | 67300000 | 62300000 | 62300000 | 62300000 | 62300000 | 62300000 | 69500000 | 69500000 | 80560000 | 80560000 | 80560000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 0
Reliability Upgrade | 1a | 162 | MA | National Grid, USA |  |  | 2010-10-01 |  | Q-169 Golden Hills to Lynn 115 kV line upgrade. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2005-09-02 | 2008-04-25 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 0
Reliability Upgrade | 1a | 59 | MA | National Grid, USA |  |  | 2012-12-01 | Auburn Area Transmission System Upgrades | G18, F19 line terminal 115 kV upgrades at Bridgewater sub | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-01-28 | 2014-02-03 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | Part of RSP 921 | #VALUE!
NEW HAMPSHIRE
Elective Upgrade | 4a | 1897 | NH | Eversource |  |  | 2025-02-01 | Queue Position 889 | Add a series breaker at the Deerfield 345 kV Substation | [34 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service |  | 2021-11-19 | NR | [34 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1896 | NH | Eversource |  |  | 2025-12-01 | Queue Position 889 | Add a series breaker at the Scobie Pond 345 kV Substation | [34 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service |  | 2021-11-19 | NR | [34 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1881 | NH | New Hampshire Transmission, LLC | Eversource | 2 | 2023-10-01 | NH 2029 Solutions | Install two 50 MVAR capacitors on Line 363 near Seabrook station with three 345 kV breakers | [33 empty] | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2022-01-19 | 2024-07-16 | [33 empty] | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 22861441 | 26591441 | 26591441 | 26591441 | 28180513.78 | 28180513.78 | 28180513.78 | 28180513.78 | 28180513.78 | 28180513.78 | 0
Reliability Upgrade | 1a | 1880 | NH | Eversource |  |  | 2024-12-01 | NH 2029 Solutions | Install a +127/-50 MVAR synchronous condenser at Amherst 345 kV Substation with three 345 kV circuit breakers and a 13.8 kV circuit breaker | [33 empty] | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service |  | 2022-06-15 | 2024-07-16 | [33 empty] | 53600000 | 53600000 | 53600000 | 53600000 | 66996000 | 66996000 | 66996000 | 66996000 | 66996000 | 66996000 | 66996000 | 66996000 | 66996000 | 66996000 | 66996000 | 0
Reliability Upgrade | 1a | 1879 | NH | Eversource |  |  | 2024-10-01 | NH 2029 Solutions | Install a +55/-32.2 MVAR synchronous condenser at Huckins Hill 115 kV Substation with a 115 kV breaker and a 13.8 kV breaker | [33 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service |  | 2022-06-15 | 2024-07-16 | [33 empty] | 36200000 | 36200000 | 36200000 | 33449000 | 33449000 | 33449000 | 33449000 | 33449000 | 33449000 | 33449000 | 33449000 | 33449000 | 33449000 | 33449000 | 33449000 | 0
Reliability Upgrade | 1a | 1878 | NH | Eversource |  |  | 2025-06-01 | NH 2029 Solutions | Install a +55/-32.2 MVAR synchronous condenser at N. Keene 115 kV Substation with a 115 kV breaker and a 13.8 kV breaker | [33 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service |  | 2022-06-15 | 2024-07-16 | [33 empty] | 36200000 | 36200000 | 36200000 | 32375000 | 32375000 | 32375000 | 32375000 | 32375000 | 32375000 | 32375000 | 32375000 | 32375000 | 32375000 | 32375000 | 32375000 | 0
Generator Interconnection Upgrade | 2a | 1792 | NH | Eversource |  |  | 2019-08-01 | Antrim Wind QP 543 | Bifurcate the L-163 115 kV line and construct a 115 kV three breaker ring bus (Tuttle Hill) | [25 empty] | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2017-02-24 | NR | [25 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1661 | NH | Eversource |  |  | 2016-10-01 | LSP-Rimmon Substation Project | Rebuild Rimmon substation and add three 115 kV breakers, install a 2nd 115/34.5 kV transformer and two 115 kV 13.3 MVAR capaciters, connect the Rimmon substation to the J114 line; install a series 115 kV breaker at Greggs substation | [14 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y- Proposed | 2015-11-05 | 2016-01-07 | [14 empty] | 15500000 | 15500000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 12493000 | 0
Reliability Upgrade | 1a | 1660 | NH | Eversource |  |  | 2016-12-01 | LSP-North Keene Substation Project | Replace four of the existing transformers at Keene substation with one 115/12.47 kV 30 MVA transformer;Construct a N. Keene Substation, loop in the L163 line with two 115 kV breakers, install one 115/12.47 kV 30 MVA transformer | [14 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y- Proposed | 2015-11-05 | 2016-01-07 | [14 empty] | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 0
Reliability Upgrade | 1a | 1625 | NH | National Grid, USA |  |  | 2017-10-01 |  | Pelham Substation - Install 115 kV Tap and inline breaker (Associated with the 2nd 115/13.2 kV transformer addition) | [12 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-07-17 | NR | [12 empty] | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 1938670 | 1938670 | 1938670 | 1938670 | 1938670 | 1938670 | 1938670 | 1938670 | 1938670 | 0
Reliability Upgrade | 1a | 1557 | NH | Eversource |  |  | 2015-09-01 | LSP - New Mill Pond Substation | Add three 115 kV switches associated with the new Mill Pond Substation | [11 empty] | Concept | Concept | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-04-28 | NR | [11 empty] | TBD | TBD | 1900000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 2750000 | 0
Reliability Upgrade | 1a | 1531 | NH | Eversource |  |  | 2014-01-01 |  | Reeds Ferry breaker project | [10 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-10-02 | NR | [10 empty] | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 0
Reliability Upgrade | 1a | 1528 | NH | National Grid, USA |  |  | 2017-04-01 | Greater Boston - North | Reconductoring National Grid's portion of the Y-151 between Dracut Jct and Power Street (NH portion of the line) | [10 empty] | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | in-service | in-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [10 empty] | TBD | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | #VALUE!
Reliability Upgrade | 1a | 1503 | NH | National Grid, USA |  |  | 2016-10-01 |  | Install in-line breaker at Mount Support Substation and loop the 115 kV W-149N line. Relay work at Wilder and Slayton Hill for the pilot protection system. | [8 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2013-04-04 | 2016-12-16 | [8 empty] | 5000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 8510000 | 0
Reliability Upgrade | 1a | 1495 | NH | Eversource |  |  | 2015-06-01 | Southern New Hampshire Solution | Merrimack Substation - replace (1) 115 kV circuit breaker (Q171). (This circuit breaker is a different breaker than identified in project 1312) | [7 empty] | Concept | Concept | Concept | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2013-03-07 | 2015-11-05 | [7 empty] | TBD | TBD | TBD | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | Part of RSP 1312 | #VALUE!
Reliability Upgrade | 1a | 1379 | NH | Eversource |  |  | 2013-12-01 | Southern New Hampshire Solution | J114-2 Greggs - Rimmon 115 kV thermal upgrade | [5 empty] | Proposed | Proposed | Proposed | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2016-01-07 | [5 empty] | 2100000 | 2100000 | 2100000 | 2100000 | 2100000 | 800000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 0
Reliability Upgrade | 1a | 1376 | NH | Eversource |  |  | 2013-12-01 | Southern New Hampshire Solution | Add two 115 kV circuit breakers at Merrimack Substation | [5 empty] | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-05-16 | 2015-11-05 | [5 empty] | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | Part of Project 1312 | #VALUE!
Generator Interconnection Upgrade | 2a | 1375 | NH | Eversource |  |  | 2013-06-01 | Groton Wind | Upgrade the E115 115 kV line from Huckins Hill Switching Station to Ashland Tap | [5 empty] | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-05-16 | NR | [5 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1374 | NH | Eversource |  |  | 2012-10-01 | Groton Wind | New 115 kV Huckins Hill Switching Station bifurcating the E115 115 kV line | [5 empty] | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-05-16 | NR | [5 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1365 | NH | National Grid, USA |  |  | 2017-12-01 | Greater Boston - North | Install new 345 kV (3124) circuit between Eversource border and NH/MA border (NH portion of National Grid's portion of new Scobie - Tewksbury line) | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [5 empty] | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | Part of RSP 1213 | #VALUE!
Reliability Upgrade | 1a | 1364 | NH | Eversource |  |  | 2016-11-01 | Greater Boston - North | Reconductoring Eversource's portion of Y-151 between Hudson and Power Street | [5 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [5 empty] | TBD | TBD | TBD | TBD | TBD | TBD | 8536000 | 8536000 | 8536000 | 8536000 | 8536000 | 8536000 | 8536000 | 8536000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 0
Reliability Upgrade | 1a | 1346 | NH | Eversource |  |  | 2013-06-01 | Western New Hampshire Solution | Upgrade the 381 345kV line between MA/NH border and the NH/VT border |  |  |  |  | Proposed | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-12-07 | 2015-12-17 |  |  |  |  | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | Part of Project ID # 1275 | #VALUE!
Reliability Upgrade | 1a | 1325 | NH | Eversource |  |  | 2014-12-01 | Seacoast New Hampshire Solution | Upgrade 115 kV line R193, Scobie Pond-Kingston Tap |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-11-05 |  |  |  |  | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 2000000 | 2000000 | 1550000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 1504000 | 0
Reliability Upgrade | 1a | 1324 | NH | Eversource |  |  | 2014-12-01 | Seacoast New Hampshire Solution | Upgrade 115 kV line H141, Chester-Great Bay |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-11-05 |  |  |  |  | 8400000 | 8400000 | 8400000 | 8400000 | 8400000 | 8400000 | 8400000 | 8400000 | 6000000 | 6000000 | 3400000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 3415000 | 0
Reliability Upgrade | 1a | 1323 | NH | Eversource |  |  | 2015-11-01 | Seacoast New Hampshire Solution | Schiller 115 kV Substation-Add: (3) 115 kV circuit breakers (6) 13.3 MVAR 115 kV capacitor banks |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2013-03-07 | 2015-11-05 |  |  |  |  | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 21800000 | 14600000 | 14600000 | 12811000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 10345000 | 0
Reliability Upgrade | 1a | 1322 | NH | Eversource |  |  | 2014-12-01 | Seacoast New Hampshire Solution | Three Rivers Substation-Add: (1) 115 kV circuit breaker |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-11-05 |  |  |  |  | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 2200000 | 2200000 | 2200000 | 1300000 | 1300000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 1295000 | 0
Reliability Upgrade | 1a | 1321 | NH | Eversource |  |  | 2014-12-01 | Seacoast New Hampshire Solution | Scobie Pond Substation-Add: (1) 115 kV circuit breaker (associated with new circuit, Scobie Pond-Chester) |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-11-05 |  |  |  |  | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 2400000 | 2400000 | 2400000 | 2400000 | 2000000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 1963000 | 0
Reliability Upgrade | 1a | 1320 | NH | Eversource |  |  | 2015-12-01 | Seacoast New Hampshire Solution | Chester 115 kV Substation-Add: (5) 115 kV circuit breakers (associated with new circuit, Scobie Pond-Chester), |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2013-03-07 | 2015-11-05 |  |  |  |  | 24200000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 17017000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 16756000 | 0
Reliability Upgrade | 1a | 1319 | NH | Eversource |  |  | 2015-12-01 | Seacoast New Hampshire Solution | New 115 kV overhead circuit, Scobie Pond-Chester |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2013-03-07 | 2015-11-05 |  |  |  |  | 13700000 | 13700000 | 13700000 | 13700000 | 13700000 | 13700000 | 13700000 | 13700000 | 13700000 | 13700000 | 13700000 | 15210000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 14908000 | 0
Reliability Upgrade | 1a | 1318 | NH | Eversource |  |  | 2020-05-01 | Seacoast New Hampshire Solution | New 115 kV overhead/submarine circuit, Madbury-Portsmouth |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2013-03-07 | 2015-11-05 |  |  |  |  | 27200000 | 27200000 | 27200000 | 27200000 | 27200000 | 27200000 | 27200000 | 27200000 | 27200000 | 27200000 | 64400000 | 64400000 | 64400000 | 64400000 | 64400000 | 64400000 | 80800000 | 80800000 | 80800000 | 80800000 | 80800000 | 80800000 | 80800000 | 117654000 | 117654000 | 117654000 | 117654000 | 117654000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 105319000 | 0
Reliability Upgrade | 1a | 1317 | NH | Eversource |  |  | 2020-05-01 | Seacoast New Hampshire Solution | Portsmouth Substation- Add: (1) 115 kV circuit breaker (associated with new circuit, Madbury-Portsmouth) |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2013-03-07 | 2015-11-05 |  |  |  |  | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 5681000 | 5681000 | 5681000 | 5681000 | 5681000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 0
Reliability Upgrade | 1a | 1316 | NH | Eversource |  |  | 2020-05-01 | Seacoast New Hampshire Solution | Madbury Substation- Add: (1) 115 kV circuit breaker (associated with new circuit, Madbury-Portsmouth) |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2013-03-07 | 2015-11-05 |  |  |  |  | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 1700000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 3477000 | 3477000 | 3477000 | 3477000 | 3477000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 0
Reliability Upgrade | 1a | 1315 | NH | Eversource |  |  | 2013-12-01 | Southern New Hampshire Solution | Upgrade 345 kV line 326, Scobie Pond-NH/MA Border |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2016-01-07 |  |  |  |  | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 4500000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 4300000 | 0
Reliability Upgrade | 1a | 1314 | NH | Eversource |  |  | 2014-12-01 | Southern New Hampshire Solution | Oak Hill Substation - Loop in 115 kV line V182, Garvins-Webster, add (6) 115 kV circuit breakers. |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-11-05 |  |  |  |  | 22600000 | 22600000 | 22600000 | 22600000 | 22600000 | 22600000 | 22600000 | 22600000 | 22600000 | 20600000 | 20600000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 19476000 | 0
Reliability Upgrade | 1a | 1312 | NH | Eversource |  |  | 2014-12-01 | Southern New Hampshire Solution | Upgrade Merrimack 230/ 115 kV substation and relocate existing capacitor banks to Bus 1 and Bus 3 |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-11-05 |  |  |  |  | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 10700000 | 14900000 | 14900000 | 14900000 | 15500000 | 15500000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 15501000 | 0
Reliability Upgrade | 1a | 1310 | NH | Eversource |  |  | 2013-06-01 | Southern New Hampshire Solution | Rebuild 115 kV line H137, Merrimack-Garvins |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2016-01-07 |  |  |  |  | 4900000 | 4900000 | 4900000 | 4900000 | 4900000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 0
Reliability Upgrade | 1a | 1309 | NH | Eversource |  |  | 2014-12-01 | Southern New Hampshire Solution | Rebuild 115 kV line D118, Deerfield-Pine Hill |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2016-01-07 |  |  |  |  | 22700000 | 22700000 | 22700000 | 22700000 | 22700000 | 22700000 | 17400000 | 17400000 | 17400000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 15700000 | 0
Reliability Upgrade | 1a | 1308 | NH | Eversource |  |  | 2014-05-01 | Southern New Hampshire Solution | Up rate 115 kV line P145, Oak Hill-Merrimack |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2016-01-07 |  |  |  |  | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 1700000 | 1700000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 1900000 | 0
Reliability Upgrade | 1a | 1307 | NH | Eversource |  |  | 2015-03-01 | Southern New Hampshire Solution | Uprate 115 kV line G146, Garvins-Deerfield |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2016-01-07 |  |  |  |  | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 3300000 | 3300000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 0
Reliability Upgrade | 1a | 1306 | NH | Eversource |  |  | 2015-05-01 | Southern New Hampshire Solution | Rebuild 115 kV line K165, W157 tap (H123 renamed) - Eagle-Power St. |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2016-01-07 |  |  |  |  | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 11500000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 0
Reliability Upgrade | 1a | 1304 | NH | Eversource |  |  | 2015-12-01 | Southern New Hampshire Solution | New 115 kV overhead circuit, Scobie Pond-Huse Rd (W144) |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2013-03-07 | 2016-01-07 |  |  |  |  | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 0
Reliability Upgrade | 1a | 1303 | NH | Eversource |  |  | 2015-11-01 | Southern New Hampshire Solution | Huse Rd Substation- Add:(2) 115 kV circuit breakers (associated with new circuit, Scobie Pond-Huse Rd) |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2013-03-07 | 2016-01-07 |  |  |  |  | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 10000000 | 0
Reliability Upgrade | 1a | 1302 | NH | Eversource |  |  | 2014-12-01 | Southern New Hampshire Solution | Scobie Pond Substation- Add: (1) 115 kV circuit breaker (associated with new circuit, Scobie Pond-Huse Rd - W144) (1) 345 kV circuit breaker in series with circuit breaker 802 (802S) |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2016-01-07 |  |  |  |  | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 0
Reliability Upgrade | 1a | 1301 | NH | Eversource |  |  | 2016-12-01 | Southern New Hampshire Solution | Eagle Substation Add: 345kV yard, (3) 345 kV circuit breakers, (4) 115kV circuit breakers, (1) 345/115 kV auto-transformer, (4) 26.6 MVAR 115 kV capacitor banks |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2013-03-07 | 2016-01-07 |  |  |  |  | 59700000 | 59700000 | 59700000 | 59700000 | 59700000 | 59700000 | 59700000 | 59700000 | 59700000 | 59700000 | 59700000 | 59700000 | 59700000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 32300000 | 0
Reliability Upgrade | 1a | 1278 | NH | Eversource |  |  | 2016-08-01 | Central New Hampshire Solution | Saco Valley Substation - Add two 25 MVAR synchronous condensers |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2013-03-07 | 2015-11-25 |  |  |  | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 15800000 | 18977000 | 18977000 | 19368000 | 19368000 | 22498000 | 22498000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 21789000 | 0
Reliability Upgrade | 1a | 1277 | NH | Eversource |  |  | 2014-02-01 | Central New Hampshire Solution | Webster Substation - Add four 26.6 MVAR 115 kV capacitors |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-11-25 |  |  |  | 11900000 | 11900000 | 11900000 | 11900000 | 11900000 | 9000000 | 9000000 | 9000000 | 7100000 | 7100000 | 7100000 | 7100000 | 7047000 | 7047000 | 7047000 | 7047000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 7919000 | 0
Reliability Upgrade | 1a | 1276 | NH | Eversource |  |  | 2014-12-01 | Northern New Hampshire Solution | Littleton Substation - Add a second 230/115kV autotransformer and associated 115 kV substation work |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 3/7/2013 12/22/2014 | 2015-08-04 |  |  |  | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 11000000 | 11000000 | 11000000 | 11000000 | 11000000 | 9700000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 8980000 | 0
Reliability Upgrade | 1a | 1272 | NH | Eversource |  |  | 2013-09-01 | Western New Hampshire Solution | Weare Substation - Add two 13.3 MVAR 115 kV capacitors |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-12-17 |  |  |  | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3000000 | 3000000 | 3000000 | 3000000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 2968000 | 0
Reliability Upgrade | 1a | 1271 | NH | Eversource |  |  | 2013-11-01 | Western New Hampshire Solution | Upgrade the Keene to Monadnock (T198) 115 kV line |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-12-17 |  |  |  | 11900000 | 11900000 | 11900000 | 11900000 | 11900000 | 11900000 | 2000000 | 1038000 | 1038000 | 1038000 | 1038000 | 1038000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 1031000 | 0
Reliability Upgrade | 1a | 1270 | NH | Eversource |  |  | 2017-02-01 | Western New Hampshire Solution | New 115 kV line from Fitzwilliam to Monadnock and associated substation work |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2013-03-07 | 2015-12-17 |  |  |  | 10500000 | 10500000 | 10500000 | 10500000 | 10500000 | 10500000 | 10500000 | 10500000 | 10500000 | 16500000 | 16500000 | 16500000 | 18547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 19547000 | 0
Reliability Upgrade | 1a | 1263 | NH | National Grid, USA |  |  | 2014-11-01 | Northern New Hampshire Solution | New C-203 230kV line tap to Littleton NH Substation associated with 2nd 230/115 kV auto project |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2013-03-07 | 2015-08-04 |  |  |  | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1100000 | 1500000 | 1500000 | 1500000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 1990000 | 0
Reliability Upgrade | 1a | 1220 | NH | Eversource |  |  | 2017-12-01 | Greater Boston - North | Install a new 345 kV (3124) circuit between Scobie and Hudson NH (this is Eversource's portion of the new Scobie-Tewksbury circuit) |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No |  | 40100000 | 40100000 | 40100000 | 40100000 | 40100000 | 40100000 | 40100000 | 40100000 | 40100000 | 40100000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 36916000 | 0
Reliability Upgrade | 1a | 1219 | NH | Eversource |  |  | 2011-12-01 |  | Install 115 kV two 13.3 MVAR capacitor banks at Oak Hill substation |  | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-02-28 | NR |  | 3800000 | 3800000 | 4000000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 0
Reliability Upgrade | 1a | 1183 | NH | Eversource |  |  | 2016-06-01 | LSP New Peaslee Substation and 115/34.5 kV transformer | New 115 kV Peaslee Substation with a five 115 kV breaker ring bus configuration. New 115 kV lines to supply a new Unitil substation and the existing Kingston Substation | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2014-02-11 | 2015-11-05 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 34000000 | 28200000 | 28200000 | 28200000 | 28200000 | 28200000 | 28200000 | 28200000 | 26900000 | 26900000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 27656000 | 0
Reliability Upgrade | 1a | 1182 | NH | Eversource |  |  | 2012-12-01 | LSP New Eagle Substation and 115/34.5 kV transformer | New 115 kV Eagle Substation connected to 115/34.5 kV Thornton Substation | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-07-27 | 2012-02-20 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 0
Reliability Upgrade | 1a | 1143 | NH | Eversource |  |  | 2011-06-01 |  | Littleton 115 kV breaker addition and reconfiguration | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-10-20 | 2011-04-14 | 6590000 | 6590000 | 6590000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 7011000 | 0
Reliability Upgrade | 1a | 1142 | NH | New Hampshire Transmission, LLC |  |  | 2011-04-01 |  | Seabrook 345 kV Station Reconfiguration and 345 kV Circuit Breaker Additions | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-11-20 | 2012-06-22 | TBD | TBD | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 31300000 | 0
Reliability Upgrade | 1a | 1141 | NH | Eversource |  |  | 2013-12-01 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-06-29 | 2011-07-15 | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | #VALUE!
Reliability Upgrade | 1a | 1140 | NH | Eversource |  |  | 2011-10-01 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115 kV C129 Line | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-06-29 | 2011-07-15 | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | #VALUE!
Reliability Upgrade | 1a | 1138 | NH | Northeast Utilities |  |  | 2010-12-01 | 2nd Deerfield 345/115kV Autotransformer Project | Rebuild 115 kV L175 line | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-06-29 | 2011-07-15 | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | #VALUE!
Reliability Upgrade | 1a | 1137 | NH | Eversource |  |  | 2011-04-01 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115 kV breakers and add 1-115 kV breaker at Deerfield Substation | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-06-29 | 2011-07-15 | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | #VALUE!
Generator Interconnection Upgrade | 2a | 724 | NH | National Grid, USA |  |  | 2013-03-01 | NGRID Comerford Substation | NGRID Comerford Substation. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2007-06-12 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 680 | NH | National Grid, USA |  |  | 2013-09-01 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-01-28 | 2014-03-06 | 7393000 | 7393000 | 7393000 | 7393000 | 10300000 | 10300000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 10900000 | 0
Reliability Upgrade | 1a | 674 | NH | National Grid, USA |  |  | 2014-07-01 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-04-01 | 2016-06-30 | 19460000 | 19460000 | 19460000 | 19460000 | 19460000 | 19460000 | 19460000 | 19460000 | 19460000 | 19460000 | 34390000 | 34390000 | 34390000 | 34390000 | 34390000 | 34390000 | 34390000 | 34390000 | 36630000 | 36630000 | 36630000 | 36630000 | 36630000 | 36630000 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 36556800 | 0
Reliability Upgrade | 1a | 277 | NH | Eversource |  |  | 2011-11-01 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345 kV breakers at Deerfield substation. | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-06-29 | 2011-07-15 | 52000000 | 52000000 | 52000000 | 52000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 46000000 | 0
VERMONT
Generator Interconnection Upgrade | 2a | 1673 | VT | Green Mountain Power |  |  | 2017-12-01 | Deerfield Wind | Installation of 3-breaker 69 kV ring bus interconnecting to the Bennington - Searsburg 69 kV Y25N line. | [15 empty] | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-08-25 | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1617 | VT | Vermont Electric Power Company |  |  | 2018-01-01 | Connecticut River Valley | Rebuild Chelsea Station to a three-breaker ring bus | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2017-12-01 | [12 empty] | 19800000 | 19800000 | 19800000 | 19800000 | 14900000 | 14900000 | 14900000 | 14900000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 0
Reliability Upgrade | 1a | 1616 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | Connecticut River Valley | Split Hartford 25 MVAR capacitor bank into two 12.5 MVAR banks | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2017-12-01 | [12 empty] | 3800000 | 3800000 | 3800000 | 3800000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 0
Reliability Upgrade | 1a | 1615 | VT | Vermont Electric Power Company |  |  | 2018-11-01 | Connecticut River Valley | Install one +50/-25 MVAR dynamic voltage support device at Ascutney | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2017-12-01 | [12 empty] | 40000000 | 40000000 | 40000000 | 40000000 | 41000000 | 41000000 | 41000000 | 41000000 | 35900000 | 35900000 | 35900000 | 35900000 | 32000000 | 32000000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 32200000 | 0
Reliability Upgrade | 1a | 1614 | VT | Vermont Electric Power Company |  |  | 2017-08-01 | Connecticut River Valley | Rebuild K31 (Coolidge - Ascutney) 115 kV line | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2015-04-16 | 2017-12-01 | [12 empty] | 70100000 | 70100000 | 70100000 | 70100000 | 51100000 | 51100000 | 51100000 | 51100000 | 41800000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 32000000 | 0
Reliability Upgrade | 1a | 1613 | VT | Vermont Electric Power Company | NYPA |  | 2017-12-01 |  | Replace the PV20 submarine cables | [12 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2014-10-21 | 2019-12-16 | [12 empty] | 35000000 | 35000000 | 35000000 | 40000000 | 41600000 | 41600000 | 41600000 | 41600000 | 41600000 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 45978450 | 0
Reliability Upgrade | 1a | 1529 | VT | National Grid, USA |  |  | 2017-12-01 |  | Y25N Bennington - Harriman + Taps (Knox Insulator refurbishment) | [10 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | NR | 2021-01-29 | [10 empty] | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5500000 | 5500000 | 5758000 | 5758000 | 5758000 | 5924000 | 5924000 | 5924000 | 5924000 | 5924000 | 5924000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 5760000 | 0
Reliability Upgrade | 1a | 1488 | VT | National Grid, USA |  |  | 2017-11-01 | Harriman Asset Condition | Harriman Station - Breaker replacement and terminal equipment upgrades (Asset Condition) | [7 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-12-07 | 2017-07-17 | [7 empty] | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7310000 | 7310000 | 7310000 | 8000000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 8010000 | 0
Reliability Upgrade | 1a | 1359 | VT | Vermont Electric Power Company |  |  | 2013-11-01 | Bennington Substation Rebuild | Install two 12.5 MVAR capacitor banks at Bennington 115 kV substation. | [5 empty] | Proposed | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-09-19 | 2013-12-05 | [5 empty] | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | Part of Bennington Substation Rebuild (Project ID 1170 | #VALUE!
Generator Interconnection Upgrade | 2a | 1291 | VT | Vermont Electric Power Company |  |  | 2014-03-01 | Kingdom Community Wind | Installation of a 46 kV dynamic reactive device with 25 MVARs of capacitive reserves at Jay Substation |  |  |  |  | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-10-21 | NR |  |  |  |  | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1290 | VT | Vermont Electric Power Company |  |  | 2015-05-01 | VELCO-LSP - Georgia Substation | Install a 115/34.5 kV transformer at the Georgia Substation |  |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-10-19 | NR |  |  |  |  | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Reliability Upgrade | 1a | 1210 | VT | National Grid, USA |  |  | 2017-11-01 | Pittsfield / Greenfield Project | Harriman Station - Installation of 115 kV tie breaker with associated buswork, reconductor of buswork and new control house. |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2012-12-07 | 2017-07-17 |  | 1100000 | 1100000 | 1100000 | 5000000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 0
Reliability Upgrade | 1a | 1195 | VT | Vermont Electric Power Company |  |  | 2012-11-01 | Highgate Refurbishment | Replace Highgate controls and cooling system |  | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2011-08-09 |  | 38400000 | 35600000 | 35600000 | 35600000 | 35600000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 30500000 | 0
Reliability Upgrade | 1a | 1194 | VT | Vermont Electric Power Company |  |  | 2012-09-01 | VELCO LSP Jay Substation | Construct a new 4-breaker ring substation at Jay with two 115/46 kV transformers |  | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-02-07 | 2012-03-07 |  | 6500000 | 6500000 | 6500000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 6995000 | 0
Reliability Upgrade | 1a | 1192 | VT | Vermont Electric Power Company |  |  | 2011-01-01 | Essex Switch Closing | Operate the Essex #230 115 kV switch normally closed. | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-11-02 | NR | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 0
Reliability Upgrade | 1a | 1172 | VT | Vermont Electric Power Company |  |  | 2013-03-01 | Vermont Shunt Reactors | Install 345 kV 60 MVAR shunt reactors (two at Coolidge and one at New Haven and relocate the New Haven reactor to Vernon) to address high voltage concerns | Concept | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-03-23 | 2012-12-13 | 20000000 | 26700000 | 20000000 | 20000000 | 20000000 | 20000000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 0
Reliability Upgrade | 1a | 1171 | VT | Vermont Electric Power Company |  |  | 2011-12-01 | West Rutland Capacitor Rebuild | Install two 115 kV 25 MVAR capacitor banks at West Rutland to address low voltage concerns | Proposed | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-11-02 | NR | 2500000 | 2400000 | 2400000 | 2400000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 0
Reliability Upgrade | 1a | 1170 | VT | Vermont Electric Power Company | Green Mountain Power |  | 2013-11-01 | Bennington Substation Rebuild | Rebuild the exiting Bennington substation 115 kV bus into a ring bus to address reliability problems due to breaker failure contingencies | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-11-22 | 2013-12-05 | 20000000 | 23000000 | 23000000 | 28000000 | 19200000 | 19200000 | 19200000 | 19200000 | 19200000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 0
Reliability Upgrade | 1a | 1169 | VT | Vermont Electric Power Company |  |  | 2013-08-01 | Ascutney Substation Rebuild | Rebuild the existing Ascutney substation 115 kV bus into a ring bus, to address reliability problems due to breaker failure contingencies | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-11-22 | 2012-12-13 | 22000000 | 14500000 | 14500000 | 14500000 | 18000000 | 18000000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 0
Reliability Upgrade | 1a | 1146 | VT | Vermont Electric Power Company |  |  | 2010-12-01 | Lyndonville Project | Installation of a 4-breaker ring 115 kV substation consisting of two 115 kV 12.5 MVAR capacitor banks and 115/34.5 kV transformer interconnecting to the Irasburg - St. Johnsbury 115 kV line | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-06-01 | 2010-05-17 | 9000000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 0
Reliability Upgrade | 1a | 1145 | VT | Vermont Electric Power Company |  |  | 2010-12-01 | Burlington Gorge Project | Installation of a 3-breaker 115 kV ring substation and 115/34. 5 kV transformer on the East Ave. - Tafts Corners 115 kV line | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 10/24/2006 | 2010-05-17 | 12100000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 0
Reliability Upgrade | 1a | 1113 | VT | Northeast Utilities - NSTAR |  |  | 2010-12-01 |  | Install 115 kV Breaker #31 at K St. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-12-15 | NR | 2200000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 0
Generator Interconnection Upgrade | 2a | 1036 | VT | Vermont Electric Power Company |  |  | 2011-10-01 | Sheffield Wind | Installation of 3-breaker 115 kV ring bus interconnecting to the St. Johnsbury-Irasburg 115 kV K39 line. | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 08/16/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1035 | VT | Vermont Electric Power Company |  |  | 2010-12-01 | Vermont Southern Loop Project | Expansion of Coolidge 345 kV substation | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-10-01 | 2010-05-17 | 20117000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 0
Reliability Upgrade | 1a | 1034 | VT | Vermont Electric Power Company |  |  | 2010-12-01 | Vermont Southern Loop Project | Loop new 345 kV Line into Newfane Substation. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-10-01 | 2010-05-17 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | #VALUE!
Reliability Upgrade | 1a | 1033 | VT | Vermont Electric Power Company |  |  | 2010-12-01 | Vermont Southern Loop Project (VELCO LSP - Newfane Substation) | Installation of a new 345/115 kV substation called Newfane | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-10-01 | 2010-05-17 | 16664000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 13500000 | 0
Reliability Upgrade | 1a | 1032 | VT | Vermont Electric Power Company |  |  | 2010-12-01 | Vermont Southern Loop Project | Installation of a new 345/115 kV substation called Vernon including a new 345/115 kV autotransformer | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-10-01 | 2010-05-17 | 55000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 51000000 | 0
Reliability Upgrade | 1a | 323 | VT | Vermont Electric Power Company |  |  | 2010-12-01 | Vermont Southern Loop Project | New VY - Newfane - Coolidge 345 kV line with requisite station upgrades. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-10-01 | 2010-05-17 | 116000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 0
Reliability Upgrade | 1a | 318 | VT | Vermont Electric Power Company |  |  | 2012-10-01 | Georgia Substation Rebuild | Rebuild the existing Georgia substation 115 kV bus into a ring bus | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-11-22 | 2012-12-13 | 20000000 | 18000000 | 16000000 | 16000000 | 16000000 | 16000000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 15900000 | 0
MAINE
Elective Upgrade | 4a | 1895 | ME | Central Maine Power Company |  |  | 2025-02-01 | Queue Position 889 | Reconductor the Section 64 115kV | [34 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service |  | 2021-11-19 | NR | [34 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1894 | ME | Central Maine Power Company |  |  | 2025-07-01 | Queue Position 889 | Reconductor the Section 62 115 kV line | [34 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service |  | 2021-11-19 | NR | [34 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1893 | ME | Central Maine Power Company |  |  | 2025-12-01 | Queue Position 889 | Install two +300/-300 MVAR STATCOMs at the Buxton 345 kV Substation with one new 345 kV breaker | [34 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service |  | 2021-11-19 | NR | [34 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1892 | ME | Versant Power |  |  | 2024-04-01 | Queue Position 760 | Rebuild of 3.25 miles of Line 59 between Epping and Columbia | [33 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2021-07-01 | NR | [33 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1891 | ME | Versant Power |  |  | 2025-05-01 | Queue Position 760 | Addition of a +/-150 MVAR STATCOM at Tunk Lake | [33 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service |  | 2021-07-01 | NR | [33 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1890 | ME | Versant Power |  |  | 2024-11-01 | Queue Position 760 | Addition of a new 115 kV Baseline Switching Station on line 52 between Deblois and Epping | [33 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service |  | 2021-07-01 | NR | [33 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1888 | ME | Versant Power |  |  | 2024-07-01 | UME 2029 Solutions | Install a 10 MVAR reactor at Keene Road 115 kV substation | [33 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service |  | 2022-02-16 | 2026-02-13 | [33 empty] | 6000000 | 6000000 | 6000000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 0
Reliability Upgrade | 1a | 1887 | ME | Versant Power |  |  | 2024-10-30 | UME 2029 Solutions | Install a 25 MVAR reactor at Boggy Brook 115 kV substation | [33 empty] | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service |  | 2022-02-16 | 2026-02-13 | [33 empty] | 3400000 | 3400000 | 3400000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 0
Reliability Upgrade | 1a | 1886 | ME | Versant Power |  |  | 2025-08-01 | UME 2029 Solutions | Install a +50/-25 MVAR synchronous condenser at Boggy Brook 115 kV substation, and install a new 115 kV breaker to separate Line 67 from the proposed solution elements | [33 empty] | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service |  | 2022-02-16 | 2026-02-13 | [33 empty] | 35500000 | 35500000 | 35500000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 25900000 | 25900000 | 25900000 | 25900000 | 25900000 | 25900000 | 0
Reliability Upgrade | 1a | 1882 | ME | Central Maine Power Company |  |  | 2024-08-01 | UME 2029 Solutions | Rebuild 21.7 miles of the existing 115 kV line Section 80 Highland – Coopers Mills 115 kV line | [33 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service |  | 2022-05-24 | No | [33 empty] | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 0
Elective Upgrade | 4a | 1821 | ME | NECEC Transmission LLC |  |  | 2025-05-01 | Queue Position 639 | Construct 1.6 miles of new 345 kV AC transmission line from Merrill Road 345 kV Substation to Larrabee Road 345 kV Substation. | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service |  | 2020-07-09 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1820 | ME | NECEC Transmission LLC |  |  | 2025-12-01 | Queue Position 639 | Construct a new HVDC Converter Terminal at Merrill Road Substation. | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service |  | 2020-07-09 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1819 | ME | NECEC Transmission LLC |  |  | 2025-12-01 | Queue Position 639 | Construct 207 miles of new 320 kV symmetrical monopole HVDC transmission line from Appalaches Substation in Saint-Adrien-d’Irlande, Quebec to Merrill Road Substation in Lewiston, ME. | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service |  | 2020-07-09 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1817 | ME | Central Maine Power Company |  |  | 2025-06-01 | Queue Position 639 | Install 2nd Larrabee Road 345/115 kV autotransformer | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service |  | 2020-07-09 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1816 | ME | Central Maine Power Company |  |  | 2025-09-01 | Queue Position 639 | Construct new Coopers Mills to Maine Yankee 345 kV line | [30 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service |  | 2020-07-09 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1809 | ME | Central Maine Power Company |  |  | 2020-10-01 | Queue Position 583 | Construct a new three-breaker ring bus configured substation to accommodate the interconnection of QP 583 on the existing Section 237 115 kV transmission line between Maguire Road and Sanford Substation. | [29 empty] | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2017-07-17 | NR | [29 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1808 | ME | Central Maine Power Company |  |  | 2021-09-01 | Queue Position 557 | Construct a new three-breaker ring bus configured substation to accommodate the interconnection of Farmington Solar on the existing Section 278 115 kV Line between Livermore Substation and Sturtevant Substation. | [29 empty] | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2019-05-01 | NR | [29 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1802 | ME | Versant Power |  |  | 2022-09-01 | Queue Position 649 | Addition of new 115 kV Switching Station on line 66 to accomdate QP 649 | [27 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2019-08-26 | NR | [27 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1775 | ME | Versant Power |  |  | 2020-11-01 | Queue Position 420 | Upgrades at Bull Hill Switching Station to accommodate QP 420 | [22 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2018-03-26 | NR | [22 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1667 | ME | Emera Maine |  |  | 2016-12-01 | Queue Position 397 | Add tap to existing Bull Hill Switching station to accommodate QP 397 | [14 empty] | Proposed | Proposed | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-07-07 | NR | [14 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1653 | ME | Emera Maine |  |  | 2016-10-01 | Queue Position 333 | Install a new 13.6 Ohm series capacitor in the 345 kV transmission line (388) between Orrington to Coopers Mills | [13 empty] | Concept | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-03-02 | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1652 | ME | Emera Maine |  |  | 2016-10-01 | Queue Position 333 | Move the existing Orrington series capacitor from the 345 kV transmission line (388) between Orrington to Coopers Mills to the 345 kV transmission line (3023) between Orrington to Albion Road due to line configuration change and reduce the size from 25 Ohm to 22.32 Ohm. | [13 empty] | Concept | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-03-02 | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1651 | ME | Blue Sky |  |  | 2016-12-01 | Queue Position 333 | Add a new 115 kV line Blue Sky West to Guilford substation | [13 empty] | Concept | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-03-02 | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1650 | ME | Blue Sky |  |  | 2016-12-01 | Queue Position 333 | Add a new 34.5/115 kV substation Blue Sky West | [13 empty] | Concept | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-03-02 | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1649 | ME | Central Maine Power Company |  |  | 2016-08-01 | Queue Position 333 | Add a new 3-breaker ring bus to Guilford 115 kV Substation | [13 empty] | Concept | Proposed | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-03-02 | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1648 | ME | Central Maine Power Company |  |  | 2016-03-01 | Queue Position 333 | Re-rate 115 kV line section 85 between Detroit and Guilford substations | [13 empty] | Concept | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-03-02 | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1643 | ME | Central Maine Power Company |  |  | 2018-11-01 | Greater Boston - Stability | Install a new +/- 200 MVAR STATCOM at Coopers Mills 345 kV substation | [13 empty] | Concept | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Proposed | 2016-06-09 | No | [13 empty] | TBD | 58000000 | 58000000 | 58000000 | 58000000 | 58000000 | 58000000 | 51700000 | 51700000 | 51700000 | 51700000 | 51700000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 53107000 | 0
Generator Interconnection Upgrade | 2a | 1611 | ME | Emera Maine |  |  | 2015-12-01 | Queue Position 357 | Installation of 115 kV ring bus on line 64 between Graham and Keene Road to accommodate QP 357 | [12 empty] | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2014-08-11 | NR | [12 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1514 | ME | Central Maine Power Company |  |  | 2020-05-01 | CMP- LSP County Road Substation | Construct a new County Road Substation that sectionalizes Section 241 by adding four 115 kV circuit breakers in a ring bus configuration and install two 115/34.5 kV 30/56 MVA transformers at a new green field site. This new substation will replace the existing Rice Rips Substation. Construct 6.5 miles of new 115 kV (1192 kcmil 45/7 ACSR) conductor from the Section 241A tap point to the new County Road Substation. | [9 empty] | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | Y-Planned | 2014-03-20 | 9/13/2017 12/16/2019 | [9 empty] | TBD | 21900000 | 21900000 | 21900000 | 24780000 | 24780000 | 24490000 | 24490000 | 24490000 | 24490000 | 24490000 | 24841000 | 24841000 | 24841000 | 24841000 | 24841000 | 24841000 | 24841000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 32260000 | 0
Reliability Upgrade | 1a | 1513 | ME | Central Maine Power Company |  |  | 2015-11-01 | Section 242 Rebuild | Rebuild entire length (1.1 mile) of transmission line Section 242 | [9 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 2013-10-04 | NR | [9 empty] | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 0
Reliability Upgrade | 1a | 1506 | ME | Emera Maine |  |  | 2014-06-01 | Chester SVC Control System Replacement | Like kind replacement of control system at Chester SVC | [9 empty] | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | NR | 2012-04-17 | [9 empty] | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 8030000 | 0
Generator Interconnection Upgrade | 2a | 1483 | ME | Central Maine Power Company |  |  | 2016-12-01 | Queue Position 333 | Install a 0/+70 MVAR SVC at new Dogtown Road S/S near Detroit S/S 115 kV Substation (CMP-15-T01) | [6 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2015-03-02 | NR | [6 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1482 | ME | Central Maine Power Company |  |  | 2014-09-01 | Saddleback Ridge Wind | New Ludden Lane 115 kV Substation consisting of a three-breaker ring bus interconnecting QP 287 and QP 300 facilities to the CMP transmission system. Section 229 will be sectionalized into two sections with two new transmission segments constructed and extended into the new Ludden Lane Substation, a distance of approximately 0.2 miles each. | [6 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-06-07 | NR | [6 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1481 | ME | Central Maine Power Company |  |  | 2011-06-01 | Maine Power Reliability Program (MPRP) | Upgrade terminal equipment on 115 kV transmission line 68 at Mason substation | [6 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1480 | ME | Central Maine Power Company |  |  | 2012-05-01 | Maine Power Reliability Program (MPRP) | Add a new Monmouth 115/34/12 kV Substation interconnecting line 212 to Larrabee Road and line 269 to Bowman Street (original 212 from Bowman Street to Gulf Island) | [6 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1479 | ME | Central Maine Power Company |  |  | 2012-02-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (238) between Louden and Maguire Road | [6 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1478 | ME | Central Maine Power Company |  |  | 2012-05-01 | Maine Power Reliability Program (MPRP) | Rebuild the entire length of the 115 kV transmission line (269) between Bowman Street and Monmouth. (Formerly Section 212) | [6 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1477 | ME | Central Maine Power Company |  |  | 2011-11-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (167) between Surowiec and Moshers | [6 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1476 | ME | Central Maine Power Company |  |  | 2011-11-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (166) between Surowiec and Spring Street | [6 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1475 | ME | Central Maine Power Company |  |  | 2012-02-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (203) between Detroit and Bucksport | [6 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1474 | ME | Central Maine Power Company |  |  | 2011-05-01 | Maine Power Reliability Program (MPRP) | Rebuild portion of 115 kV transmission line (66) from Detroit to new Athens Substation. Section 66 from Detroit to Athens renamed Section 82 | [6 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1473 | ME | Central Maine Power Company |  |  | 2010-11-01 | Maine Power Reliability Program (MPRP) | Replace all 115 kV breakers at the South Gorham station with independent pole tripping capability | [6 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1472 | ME | Central Maine Power Company |  |  | 2013-04-01 | Maine Power Reliability Program (MPRP) | Replace K374/377 breaker at Surowiec 345 kV Substation with independent pole tripping capability | [6 empty] | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1471 | ME | Central Maine Power Company |  |  | 2014-12-01 | Maine Power Reliability Program (MPRP) | Modify existing control settings at existing Mason 115 kV substation to switch out Mason 115 kV capacitors for 115 kV voltage above 1.05pu | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1470 | ME | Central Maine Power Company |  |  | 2013-06-01 | Maine Power Reliability Program (MPRP) | Add new automatic 115 kV switching controls at existing Rumford Industrial Park 115 kV substation to switch out 115 kV capacitors for 115 kV voltages above 1.05pu | [6 empty] | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1469 | ME | Central Maine Power Company |  |  | 2013-06-01 | Maine Power Reliability Program (MPRP) | Add new automatic 115 kV switching controls at existing Riley 115 kV substation to switch out 115 kV capacitors for 115 kV voltages above 1.05pu | [6 empty] | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1468 | ME | Central Maine Power Company |  |  | 2015-04-01 | Maine Power Reliability Program (MPRP) | Modify the Maritimes Islanding Special Protection System to remove the inputs from the New England transmission system | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1467 | ME | Central Maine Power Company |  |  | 2015-04-01 | Maine Power Reliability Program (MPRP) | Remove the Orrington T1 SPS (NPCC # 182 – Type III) Special Protection Systems | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1466 | ME | Central Maine Power Company |  |  | 2015-04-01 | Maine Power Reliability Program (MPRP) | Remove the Bucksport 65/205 Reverse Power SPS (NPCC # 22 – Type III) Special Protection Systems | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1465 | ME | Central Maine Power Company |  |  | 2014-02-01 | Maine Power Reliability Program (MPRP) | Remove the Section 386 Temporary SPS (NPCC #198 – Type I) Special Protection Systems | [6 empty] | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1464 | ME | Central Maine Power Company |  |  | 2015-04-01 | Maine Power Reliability Program (MPRP) | Remove the Maine Yankee Double Circuit Tower SPS, (NPCC # 141, Type I) Special Protection Systems | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1463 | ME | Central Maine Power Company |  |  | 2015-04-01 | Maine Power Reliability Program (MPRP) | Remove the Maxcys-Bucksport (SPS # 178 – Type I) Special Protection Systems | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1462 | ME | Central Maine Power Company |  |  | 2012-12-01 | Maine Power Reliability Program (MPRP) | Install two new 40 Mvar 13.8 kV reactors on the tertiary of 345/115/13.8 kV autotransformers at the new Larrabee Road 345/115 kV substation | [6 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1461 | ME | Central Maine Power Company |  |  | 2015-03-01 | Maine Power Reliability Program (MPRP) | Install two new 40 MVAR 13.8 kV reactors on the tertiary of 345/115/13.8 autotransformer at Coopers Mills 345/115 kV substation (formerly Maxcys) | [6 empty] | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1460 | ME | Central Maine Power Company |  |  | 2013-05-01 | Maine Power Reliability Program (MPRP) | Install two new 40 Mvar 13.8 kV reactors on the tertiary of 345/115/13.8kV autotransformer at the new Albion Rd 345/115 kV substation | [6 empty] | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1459 | ME | Central Maine Power Company |  |  | 2014-02-01 | Maine Power Reliability Program (MPRP) | Install a new 10.8 Mvar 34.5 kV capacitor bank at existing Belfast 115/34.5 kV substation | [6 empty] | Planned | Under Construction | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1458 | ME | Central Maine Power Company |  |  | 2015-02-01 | Maine Power Reliability Program (MPRP) | Re-rate of the 115 kV Line 88 between Coopers Mills substation and Augusta East Side substation | [6 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1457 | ME | Central Maine Power Company |  |  | 2014-10-01 | Maine Power Reliability Program (MPRP) | Re-rate of the 115 kV Line 61A between Hotel Road substation and 61A Tap | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1456 | ME | Central Maine Power Company |  |  | 2015-02-01 | Maine Power Reliability Program (MPRP) | Re-rate of the 345 kV Line 378 between Maine Yankee substation and Mason substation | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1454 | ME | Central Maine Power Company |  |  | 2015-06-01 | Maine Power Reliability Program (MPRP) | Re-rate of the 115 kV Line 83C between Sappi Hinckley substation and 83C Tap | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1452 | ME | Central Maine Power Company |  |  | 2013-12-01 | Maine Power Reliability Program (MPRP) | Reterminate 115 kV line Section 268 from Larrabee Road to Gulf Island Substation (original line section 212 from Gulf Island to Bowman Street) | [6 empty] | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1451 | ME | Central Maine Power Company |  |  | 2013-09-01 | Maine Power Reliability Program (MPRP) | Reterminate 115 kV line Section 61 from Norway to Gulf Island at new Larrabee Substation | [6 empty] | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1450 | ME | Central Maine Power Company |  |  | 2013-02-01 | Maine Power Reliability Program (MPRP) | Reterminate 115 kV line Section 200 from Livermore Falls to Gulf Island at new Larrabee Substation | [6 empty] | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1449 | ME | Central Maine Power Company |  |  | 2013-01-01 | Maine Power Reliability Program (MPRP) | Reterminate 115 kV line Section 201 from Crowleys to Gulf Island at new Larrabee Substation | [6 empty] | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1448 | ME | Central Maine Power Company |  |  | 2012-12-01 | Maine Power Reliability Program (MPRP) | Reterminate 115 kV line Section 64 from Surowiec to Gulf Island at new Larrabee Substation | [6 empty] | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1447 | ME | Central Maine Power Company |  |  | 2014-04-01 | Maine Power Reliability Program (MPRP) | Remove Section 232 (Spring Street to Westbrook) and Section 234 (Spring Street to Redbrook) at the Spring Street 115 kV Substation and tie lines together in the right-of-way to bypass the Spring Street Substation | [6 empty] | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1446 | ME | Central Maine Power Company |  |  | 2014-06-01 | Maine Power Reliability Program (MPRP) | Separation of 115 kV Double Circuit Tower of lines 65 and 205 between Bucksport and Orrington | [6 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1445 | ME | Central Maine Power Company |  |  | 2014-12-01 | Maine Power Reliability Program (MPRP) | Separation of 345 kV Double Circuit Tower of lines 375 and 377 between Surowiec and Maine Yankee at Kennebec River Crossing | [6 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1444 | ME | Central Maine Power Company |  |  | 2013-12-01 | Maine Power Reliability Program (MPRP) | Modify the 115 kV Gulf Island Substation to interconnect Section 268 (original 212) to Larrabee Road substation. 115kV Sections 61, 64, 200, 201 and cap bank relocated to Larrabee Road | [6 empty] | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1443 | ME | Central Maine Power Company |  |  | 2017-08-01 | Maine Power Reliability Program (MPRP) | Add a new Middle Street 115/34/12 kV Substation interconnecting lines 255 and 256 between Lewiston Lower and new Larrabee Road (Lewiston Loop) | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1442 | ME | Central Maine Power Company |  |  | 2018-12-01 | Maine Power Reliability Program (MPRP) | Expand Lewiston Lower 115 kV Substation interconnecting lines 256 and 202 between stations Middle Street and Crowleys (Lewiston Loop) | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 0
Reliability Upgrade | 1a | 1441 | ME | Central Maine Power Company |  |  | 2018-05-01 | Maine Power Reliability Program (MPRP) | Expand Norway 115 kV Substation interconnecting lines 61, 61A and 87 between stations Larrabee Road, Hotel Road and Kimball Road (Lewiston Loop) | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | 5200000 | 5200000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 0
Reliability Upgrade | 1a | 1440 | ME | Central Maine Power Company |  |  | 2014-05-01 | Maine Power Reliability Program (MPRP) | Expand the existing Livermore Falls 115 kV Substation interconnecting lines 243A, 251, 89, 278 between substations Rumford I.P., Larrabee Road, Riley and Sturtevant | [6 empty] | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1439 | ME | Central Maine Power Company |  |  | 2014-07-01 | Maine Power Reliability Program (MPRP) | Expand the existing Belfast 115 kV Substation interconnecting lines 86 and 266 between substations Bucksport and Lincolnville | [6 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1438 | ME | Central Maine Power Company |  |  | 2012-11-01 | Maine Power Reliability Program (MPRP) | Replace K392-1 breaker at Maine Yankee 345 kV Substation with independent pole tripping capability | [6 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1437 | ME | Central Maine Power Company | Eversource |  | 2013-11-01 | Maine Power Reliability Program (MPRP) | Add a new Eliot 345 kV switchyard interconnecting lines 3022, 3240 and 3341 between substations Maguire Road, Newington and Deerfield (costs reflects Eversource portion only, costs of CMP portion is covered in total MPRP costs in Proj. #1411) | [6 empty] | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 24100000 | 0
Reliability Upgrade | 1a | 1436 | ME | Central Maine Power Company |  |  | 2013-11-01 | Maine Power Reliability Program (MPRP) | Add a new Raven Farm 345 kV switchyard interconnecting lines 3020 to Surowiec, line 3039 to W.F. Wyman and line 3040 to South Gorham | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1435 | ME | Central Maine Power Company |  |  | 2014-08-01 | Maine Power Reliability Program (MPRP) | Expand the existing Maguire Rd 115 kV substation to include a new 345kV transformer and switchyard that interconnects line 3021 to South Gorham and line 3022 to the NU Eliot Switching Station | [6 empty] | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1434 | ME | Central Maine Power Company |  |  | 2015-04-01 | Maine Power Reliability Program (MPRP) | Add a new Larrabee Road 345/115 kV substation interconnecting lines 3025, 3026, 200, 212, 251, 255 and 268 between substations Coopers Mills, Surowiec, Leeds, Monmouth, Livermore Falls, Middle Street and Gulf Island | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1433 | ME | Central Maine Power Company |  |  | 2015-03-01 | Maine Power Reliability Program (MPRP) | Add a new Coopers Mills 345/115 kV substation interconnecting lines 3024, 3025, 60, 254, 257 and 258 between substations Albion Road, Larrabee Road and Browns Crossing | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1432 | ME | Central Maine Power Company |  |  | 2015-03-01 | Maine Power Reliability Program (MPRP) | Add new Albion Road 345/115 kV substation interconnecting lines 3023, 3024, 67, 254, 257 and 258 between substations Orrington, Coopers Mills and Detroit | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1431 | ME | Central Maine Power Company |  |  | 2013-11-01 | Maine Power Reliability Program (MPRP) | Expand the 345/115 kV Surowiec Substation to interconnect the new 3026 345kV line to Larrabee Road, new 3020 345kV line to Raven Farm, also allow for the existing 345 kV Section 375 to be looped in and out of the expanded 345 kV Surowiec Substation. The existing Section 375 will be separated into Section 375 (Maine Yankee – Surowiec) and Section 3038 (Surowiec – Buxton). | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1430 | ME | Central Maine Power Company |  |  | 2014-04-01 | Maine Power Reliability Program (MPRP) | Expand the 345/115 kV South Gorham Substation to interconnect the new 3021 345kV line to Maguire Road | [6 empty] | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1429 | ME | Central Maine Power Company |  |  | 2015-03-01 | Maine Power Reliability Program (MPRP) | Expand the 345/115 kV Orrington Substation to interconnect the new 3023 345kV line to Albion Road and the new 254 115kV line to Coopers Mills | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1428 | ME | Central Maine Power Company |  |  | 2014-04-01 | Maine Power Reliability Program (MPRP) | Add a new 345/115 kV autotransformer #1 at the expanded Maguire Road Substation | [6 empty] | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1427 | ME | Central Maine Power Company |  |  | 2012-12-01 | Maine Power Reliability Program (MPRP) | Add a new 345/115 kV autotransformer #1 at the new Larrabee Road Substation | [6 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1426 | ME | Central Maine Power Company |  |  | 2015-03-01 | Maine Power Reliability Program (MPRP) | Replace the existing T3 autotransformer at Maxcys with the new Coopers Mills 345/115 kV autotransformer #1 at the new Coopers Mills substation | [6 empty] | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1425 | ME | Central Maine Power Company |  |  | 2013-05-01 | Maine Power Reliability Program (MPRP) | Add a new 345/115 kV autotransformer #1 at the new Albion Road Substation | [6 empty] | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1424 | ME | Central Maine Power Company |  |  | 2014-04-01 | Maine Power Reliability Program (MPRP) | Reconductor the entire length of the 115 kV transmission line (160) between Cape and Hinckley Pond | [6 empty] | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1423 | ME | Central Maine Power Company |  |  | 2012-02-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (86) between Bucksport and Belfast | [6 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1422 | ME | Central Maine Power Company |  |  | 2013-12-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (250) between Maguire Road and Three Rivers | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1421 | ME | Central Maine Power Company |  |  | 2013-05-01 | Maine Power Reliability Program (MPRP) | Rebuild the entire length of the 115 kV transmission line (212) between Monmouth and Larrabee Road | [6 empty] | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1420 | ME | Central Maine Power Company |  |  | 2013-05-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (229) between Riley and Rumford IP | [6 empty] | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1419 | ME | Central Maine Power Company |  |  | 2014-05-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (89) between Livermore Falls and Riley | [6 empty] | Under Construction | Under Construction | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1418 | ME | Central Maine Power Company |  |  | 2015-02-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (88) between Coopers Mills and Augusta East Side | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1417 | ME | Central Maine Power Company |  |  | 2015-02-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (60) between Coopers Mills and Bowman Street | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1416 | ME | Central Maine Power Company |  |  | 2014-12-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (258 (formerly 84)) between Coopers Mills and Albion Rd | [6 empty] | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1415 | ME | Central Maine Power Company |  |  | 2014-11-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (257 (formerly 67)) between Coopers Mills and Albion Rd | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1414 | ME | Central Maine Power Company |  |  | 2013-05-01 | Maine Power Reliability Program (MPRP) | Rebuild a portion of the 115 kV transmission line (67) between Detroit and Albion Road | [6 empty] | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1413 | ME | Central Maine Power Company |  |  | 2018-12-01 | Maine Power Reliability Program (MPRP) | Add a new 115 kV transmission line (256) between Middle Street and Lewiston Lower (Lewiston Loop) | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 9100000 | 0
Reliability Upgrade | 1a | 1412 | ME | Central Maine Power Company |  |  | 2014-06-01 | Maine Power Reliability Program (MPRP) | Convert the 3-terminal 115 kV 86 line into 2 lines: 115 kV (266) between Belfast and Lincolnville and 115 kV (86) between Belfast and Bucksport | [6 empty] | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1411 | ME | Central Maine Power Company |  |  | 2017-08-01 | Maine Power Reliability Program (MPRP) | Add a new 115 kV transmission line (255) between Larrabee Road and Middle Street (Lewiston Loop) | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | 1378500000 | 1369000000 | 1369000000 | 1369000000 | 1369000000 | 1369000000 | 1369000000 | 1369000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 1357000000 | 0
Reliability Upgrade | 1a | 1410 | ME | Central Maine Power Company |  |  | 2014-05-01 | Maine Power Reliability Program (MPRP) | Add a new 115 kV transmission line (251) between Livermore Falls and Larrabee Road | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1409 | ME | Central Maine Power Company |  |  | 2014-05-01 | Maine Power Reliability Program (MPRP) | Tap the 243 115kV line between Rumford and Rumford IP at junction Section 243 and extend the new 243A to Livermore Falls | [6 empty] | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1408 | ME | Central Maine Power Company |  |  | 2015-03-01 | Maine Power Reliability Program (MPRP) | Add a new 115 kV transmission line (254) between Orrington and Coopers Mills (separate TCA) | [6 empty] | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2011-06-16 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1407 | ME | Central Maine Power Company |  |  | 2014-08-01 | Maine Power Reliability Program (MPRP) | Add a new 345 kV transmission line (3022) between Maguire Road and Eliot (formerly called Three Rivers) | [6 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1406 | ME | Central Maine Power Company |  |  | 2014-04-01 | Maine Power Reliability Program (MPRP) | Add a new 345 kV transmission line (3021) between South Gorham and Maguire Road | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1405 | ME | Central Maine Power Company |  |  | 2013-11-01 | Maine Power Reliability Program (MPRP) | Add a new 345 kV transmission line (3020) between Surowiec and Raven Farm | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1404 | ME | Central Maine Power Company |  |  | 2012-12-01 | Maine Power Reliability Program (MPRP) | Add a new 345 kV transmission line (3026) between Larrabee Road and Surowiec | [6 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1403 | ME | Central Maine Power Company |  |  | 2015-04-01 | Maine Power Reliability Program (MPRP) | Add a new 345 kV transmission line (3025) between Coopers Mills and Larrabee Road | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1402 | ME | Central Maine Power Company |  |  | 2015-03-01 | Maine Power Reliability Program (MPRP) | Add a new 345 kV transmission line (3024) between Albion Rd and Coopers Mills | [6 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | 1320000000 | 1470187000 | 1470187000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364500000 | 1362500000 | 1362500000 | 1362500000 | 1362500000 | 1362500000 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1401 | ME | Central Maine Power Company |  |  | 2013-05-01 | Maine Power Reliability Program (MPRP) | Add a new 345 kV transmission line (3023) between Orrington and Albion Rd | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Generator Interconnection Upgrade | 2a | 1391 | ME | Emera Maine |  |  | 2016-11-01 | Queue Position 349 | Installation of 115 kV tap on line 66 between Graham and Rebel Hill to accommodate QP 349 | [6 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-08-05 | NR | [6 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1390 | ME | Emera Maine |  |  | 2015-10-01 | Queue Position 272 | Installation of new 345 kV breaker at Keene Road Substation to accommodate QP 272 | [6 empty] | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-07-17 | NR | [6 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1358 | ME | Bangor Hydro-Electric Company |  |  | 2012-09-01 | Queue Position 317 | Installation of new 3 breaker 115 kV ring bus switching station on line 68 between Rebel Hill and Debois in order to accommodate QP-317 | [5 empty] | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-03-13 | NR | [5 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1333 | ME | Central Maine Power Company |  |  | 2014-03-01 | CMP-LSP Augusta | Add two 115 kV circuit breakers and 115/34.5 kV transformer at North Augusta Substation |  |  |  |  | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2012-03-05 | NR |  |  |  |  | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 895000 | 0
Reliability Upgrade | 1a | 1251 | ME | Central Maine Power Company |  |  | 2015-05-01 | Lakewood Substation Expansion | Sectionalize Section 241 by adding four 115 kV circuit breakers at Lakewood Substation and install a second 115/34.5 kV transformer Construct 4 miles of new 115kV from the existing Section 83B Tap point to the Lakewood Substation & rebuild the existing 115kV Section 83B |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | Y-Under Construction | 2011-04-21 | 2013-12-05 |  |  | 13700000 | 13700000 | 13700000 | 13700000 | 13700000 | 17506000 | 17506000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 17100000 | 0
Reliability Upgrade | 1a | 1197 | ME | Emera Maine |  |  | 2013-12-01 | Keene Rd Autotransformer | Orrington 345 kV Series Breaker Addition |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-10-22 | 2011-06-16 |  | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 1761250 | 0
Reliability Upgrade | 1a | 1196 | ME | Bangor Hydro-Electric Company |  |  | 2012-01-01 | SVC Filter Upgrade (Part of Keene Rd Auto-transformer ID 144) | Upgrade of filter bank at Chester SVC facility |  | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2011-07-15 | 2011-07-15 |  | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 0
Reliability Upgrade | 1a | 1184 | ME | Central Maine Power Company |  |  | 2012-11-01 | Starks Switching Station | Add 4-115 kV circuit breakers in a breaker-and a-half configuration on Section 63 and 2-18 MVAR cap banks at a new Starks Switching Station | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-09-28 | 2011-03-25 | 10750000 | 10750000 | 10750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 9750000 | 0
Generator Interconnection Upgrade | 2a | 1159 | ME | Central Maine Power Company |  |  | 2011-11-01 | Queue Position 197 | Add a new 115 kV breaker and new 115 kV line termination at the former T2 position at Rumford 115 kV substation | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-09-29 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1157 | ME | Bangor Hydro-Electric Company |  |  | 2011-03-01 |  | Bangor Hydro Synchrophasors | Concept | Concept | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | No | NR | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 100000 | 0
Reliability Upgrade | 1a | 1156 | ME | Bangor Hydro-Electric Company |  |  | 2012-04-01 | Maine Power Reliability Program (MPRP) | Orrington Shunt Cap Reconfiguration | Concept | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-10-22 | 2011-06-16 | TBD | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 2260262 | 0
Reliability Upgrade | 1a | 1155 | ME | Bangor Hydro-Electric Company |  |  | 2013-06-01 | Maine Power Reliability Program (MPRP) | Capacitor Bank Addition (10 MVAR at Trenton 34.5 kV and Epping) | Concept | Concept | Concept | Concept | Concept | Concept | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-10-22 | 2011-06-16 | TBD | TBD | TBD | TBD | TBD | TBD | 650000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 550000 | 0
Reliability Upgrade | 1a | 1154 | ME | Emera Maine |  |  | 2013-12-01 | Maine Power Reliability Program (MPRP) | Rerate Line 66 | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 10/22/2010 1/18/2013 | 2013-01-09 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 17500000 | 17500000 | 17500000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 16150000 | 0
Reliability Upgrade | 1a | 1144 | ME | Central Maine Power Company |  |  | 2010-09-01 | Heywood Road Project | Circuit Switcher replacements at Detroit, Lakewood, Rice Rips and Winslow | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-03-20 | 2009-07-20 | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | #VALUE!
Reliability Upgrade | 1a | 1135 | ME | Central Maine Power Company |  |  | 2012-04-01 | CMP-Athens Substation LSP | Add two 115 kV circuit breakers on Section 66; and 115/12 kV transformer | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2007-12-21 | NR | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 1500000 | 0
Reliability Upgrade | 1a | 1133 | ME | Central Maine Power Company |  |  | 2012-04-01 | CMP-LSP Leeds Substation | Add 115/34 kV Leeds Substation and new 34 kV line from Leeds to Turner | Proposed | Proposed | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | No | NR | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 0
Reliability Upgrade | 1a | 1131 | ME | Central Maine Power Company |  |  | 2011-11-01 | CMP-LSP Bowman St. Substation | Add 115/34 kV transformer | Proposed | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-11-22 | NR | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | 0
Reliability Upgrade | 1a | 1129 | ME | Central Maine Power Company |  |  | 2012-06-01 |  | New 115 kV line between Wyman Hydro and Rice Rips Tap, parallel to exiting Section 83. Install a 115 kV circuit breaker at Wyman Hydro termination | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2009-01-26 | 2010-12-28 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 32800000 | 0
Reliability Upgrade | 1a | 1128 | ME | Central Maine Power Company |  |  | 2010-11-01 | CMP-LSP Hotel Road Substation | Add 115/34kV transformer with 115 kV breaker at Hotel Rd. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2008-08-20 | NR | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 800000 | 0
Reliability Upgrade | 1a | 1116 | ME | Bangor Hydro-Electric Company |  |  | 2011-12-01 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-10-22 | 2011-06-16 | 37126000 | 37126000 | 37126000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 37626000 | 0
Reliability Upgrade | 1a | 1031 | ME | Emera Maine |  |  | 2013-12-01 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-10-22 | 2013-02-28 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 9300000 | 9300000 | 9300000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 0
Reliability Upgrade | 1a | 1029 | ME | Central Maine Power Company |  |  | 2010-05-01 | Maine Power Reliability Program (MPRP) | New 345/115 kV Autotransformer at South Gorham and substation expansion | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 624 | ME | Central Maine Power Company |  |  | 2011-07-01 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (Rumford Industrial Park - Rumford) | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 11/30/2007 5/4/2010 | 2011-08-22 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | #VALUE!
Reliability Upgrade | 1a | 144 | ME | Bangor Hydro-Electric Company |  |  | 2010-12-01 | Keene Rd Autotransformer | Installation of a 345/115 kV autotransformer at Keene Rd Substation. | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2010-10-22 | 2011-07-15 | 29000000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 33500000 | 0
Reliability Upgrade | 1a | 143 | ME | Bangor Hydro-Electric Company |  |  | 2012-12-01 | Down East Reliability Improvement | Construct 115 kV line from Trenton tap (Waltham Road Junction) to new Tunk Lake Substation (3 new breakers) to Harrington (Columbia Tap) & new Epping Switching Station (5 new breakers) | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service |  | 2006-05-10 | 2008-06-13 | 66100000 | 66100000 | 66100000 | 66100000 | 66100000 | 61000000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 61500000 | 0
CANCELLED PROJECTS
Generator Interconnection Upgrade | 1b | 1935 | MA | National Grid, USA |  |  | 2031-08-01 | Queue Position 1252 | Reconductor National Grid owned portion of the 338 (Tewksbury - Woburn) 345 kV line | [44 empty] | Proposed | Proposed | Cancelled | Cancelled |  | 2024-10-01 | NR | [44 empty] | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1931 | MA | Eversource |  |  | 2028-05-02 | Queue Position 1143 | Add a series breaker to the 115 kV Medway Ring #65 Substation | [44 empty] | Planned | Planned | Cancelled | Cancelled |  | 2023-08-29 | NR | [44 empty] | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1925 | MA | Eversource |  |  | 2031-08-02 | Queue Position 1252 | Reconductor Eversource Energy owned portion of the 338 (Tewksbury - Woburn) 345 kV line | [43 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled |  | 2024-10-01 | NR | [43 empty] | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1923 | ME | Versant Power |  |  | 2026-09-11 | Queue Position 1299 | Addition of a new 115 kV Switching Station on line 57 near Trenton Substation | [42 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled |  | 2024-06-28 | NR | [42 empty] | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1921 | MA | Eversource |  |  | 2027-05-01 | Queue Position 1117 | Upgrade Buck Pond station via a ring bus expansion and new gas insulated breaker | [41 empty] | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled |  | 2023-05-31 | NR | [41 empty] | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1912 | NH | Eversource |  |  | 2025-09-01 | Queue Position 1101 | Installation of a 5.95 Ohm series reactor on the 363 line at the 345 kV Scobie Pond substation | [37 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Proposed | Cancelled | Cancelled | Cancelled | Cancelled |  | 2022-10-19 | NR | [37 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1911 | ME | Versant Power |  |  | 2023-12-01 | Queue Position 1029 | Addition of a new 115 kV Switching Station on line 97 between Graham and Passadumkeag Stations | [37 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2022-12-19 | NR | [37 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1910 | ME | Versant Power |  |  | 2024-12-01 | Queue Position 1015 | Breaker additions at Orrington 115kV Switching Station to accommodate QP1015 | [37 empty] | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2022-09-30 | NR | [37 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1909 | ME | Versant Power |  |  | 2024-06-01 | Queue Position 1014 | Breaker additions at Keene Rd 115kV Switching Station to accommodate QP1014 | [37 empty] | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2022-09-01 | NR | [37 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1907 | NH | Eversource |  |  | 2024-10-01 | Queue Position 936 | Install a 115 kV tie line and 115 kV circuit breaker at the Paris 115 kV substation | [36 empty] | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2022-08-12 | NR | [36 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1906 | NH | Eversource |  |  | 2024-10-01 | Queue Position 936 | Install a new 10 MVAR Shunt Capacitor and 115 kV circuit breaker at the Lost Nation 115 kV substation | [36 empty] | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2022-08-12 | NR | [36 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1903 | CT | Eversource |  |  | 2023-12-01 | Queue Position 787 | Install a 115 kV breaker to the existing three-breaker ring bus at Canterbury 67F | [35 empty] | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-04-17 | NR | [35 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1900 | ME | Central Maine Power Company |  |  | 2026-11-01 | Queue Position 1086 | Increase the LTE rating of line Section 80 to 109 MVA by increasing the sag temperature and replacing two 115 kV structures | [35 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled |  | 2022-03-21 | NR | [35 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1889 | ME | Versant Power |  |  | 2024-12-01 | UME 2029 Solutions | Install three remotely monitored and controlled switches to split the existing Orrington reactors between the two Orrington 345/115 kV autotransformers | [33 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2022-02-16 | No | [33 empty] | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 0
Generator Interconnection Upgrade | 2b | 1873 | CT | Eversource |  |  | 2024-03-01 | Queue Position 831 | Rebuild the 69 kV 400-1 Line (Ledyard Junction to Tunnel OH/UG Transition structure), install approximately 200 feet of XLPE cable from Tunnel OH/UG Transition structure to Tunnel S/S’ | [31 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2021-01-25 | NR | [31 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1872 | CT | Eversource |  |  | 2024-03-01 | Queue Position 831 | Install two new 345 kV circuit breakers at the Killingly 345 kV substation and expand the 345 kV bus into a 4-breaker ring bus | [31 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2021-01-25 | NR | [31 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1871 | CT | Eversource |  |  | 2023-12-01 | Queue Position 788 | Install a 69 kV circuit breaker at the Montville 4J Substation. | [31 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2021-01-25 | NR | [31 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1865 | ME | Central Maine Power Company |  |  | 2024-10-01 | Queue Position 931 | Install a 115 kV circuit breaker at the Roxbury substation bus #1 adjacent to the KGT1-1 breaker. | [31 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-12-14 | NR | [31 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1845 | RI | National Grid, USA |  |  | 2021-07-01 | Western Rhode Island Cluster | Reconductor G-185N & Uprate K-189 Lines | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1844 | RI | National Grid, USA |  |  | 2021-07-01 | Western Rhode Island Cluster | Construct new Wickford Junction Substation | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1843 | MA | Eversource |  |  | 2021-07-01 | Wareham Cluster | Wareham Station #714 upgrade the existing single ended station with transformer #2 | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-07-31 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1842 | MA | National Grid, USA |  |  | 2027-01-01 | Western Massachusetts Cluster Group 2 | A-1 B-2 69 kV reconductoring | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1841 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Ware 69 kV breaker addition | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1840 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | North Oxford breaker and transformer addition | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1839 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Leicester Substation retirement | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1838 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Westminster Substation retirement | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1837 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Palmer 115 kV transformer addition and replacement | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1836 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Thorndike 115 kV breaker and transformer additions | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1835 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Little Rest Road 115 kV breaker and transformer additions | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1834 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Lashaway 69 kV transformer replacements | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1833 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Ware 69/13.2 kV transformer addition | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1832 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Meadow Street 69 kV breaker and transformer addition | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1831 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Construct new Stafford Street 115/13.8 kV Substation | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1830 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Construct new Powder Mill 115/34.5 kV Substation | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1829 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Barre transformer replacements | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1828 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Construct new Lost Town 115/13.8 kV Substation | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1827 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Wendell Depot transformer addition | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1826 | MA | National Grid, USA |  |  | 2027-09-01 | Western Massachusetts Cluster Group 2 | Otter River 69 kV Ring Bus addition and DVAR | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1825 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | East Winchendon transformer addition | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1824 | MA | National Grid, USA |  |  | 2023-09-01 | Western Massachusetts Cluster Group 2 | Construct new Whitmanville 115/34/13.8 kV Substation | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-06-02 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1823 | CT | Eversource |  |  | 2022-10-01 | Queue Position 892 | Construct new substation on the 115 kV Eversource Line 1200 between Barbour Hill 23J Substation and Windsor Locks 14K Substation to allow the interconnection of QP892 | [30 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-07-27 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1822 | NH | Eversource |  |  | 2024-12-01 | Queue Position 639 | Thermal Uprate of 115 kV Line B112 | [30 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-07-09 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1818 | ME | Central Maine Power Company |  |  | 2023-05-01 | Queue Position 639 | Install one (1) 50 MVAR reactor bank on Bus #1 of the Buxton 345 kV Substation | [30 empty] | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-07-09 | NR | [30 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1814 | CT | Eversource |  |  | 2025-09-01 | Queue Position 787 | Install a 115 kV breaker to the existing three-breaker ring bus at Canterbury 67F. | [29 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-04-17 | NR | [29 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1812 | NH | National Grid, USA |  |  | 2024-12-01 | Queue Position 727 | Construct a new 115 kV three-breaker ring bus substation in Hinsdale, NH to interconnect the QP 727 solar project. | [29 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2019-08-26 | NR | [29 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1811 | NH | National Grid, USA |  |  | 2024-07-01 | Queue Position 754 | Install a new three-breaker 115 kV ring bus substation, to be named later, at the proposed QP 754 site in Fitzwilliam, NH. | [29 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2020-04-17 | NR | [29 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1810 | ME | Central Maine Power Company |  |  | 2022-12-01 | Queue Position 623 | Construct a new three-breaker 345 kV ring bus configured substation to accommodate the interconnection of the QP 623 project on the existing Section 391 between Buxton Substation and Scobie Pond Substation. | [29 empty] | Proposed | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2019-12-13 | NR | [29 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1804 | ME | Emera Maine |  |  | 2020-12-01 | Queue Position 833 | Addition of new115 kV Switching Station on line 93 to Accomdate QP-833 | [27 empty] | Concept | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [27 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1803 | ME | Emera Maine |  |  | 2023-10-01 | Queue Position 760 | Addition of new115 kV Switching Station on line 52 to Accomdate QP-760 | [27 empty] | Concept | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [27 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1799 | CT | Eversource |  |  | 2025-02-01 | Queue Position 724 | Sectionalize the 3271 345 kV line with a tap in and out of the Cotton Bridge Substation | [26 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2019-05-01 | NR | [26 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1798 | CT | Eversource |  |  | 2025-02-01 | Queue Position 724 | Construct a new 345 kV three breaker ring bus Cotton Bridge Substation | [26 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2019-05-01 | NR | [26 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1797 | CT | Eversource |  |  | 2022-05-01 | Queue Position 647 | Uprate the 1766 115 kV line | [26 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2019-03-20 | NR | [26 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1796 | CT | Eversource |  |  | 2022-05-01 | Queue Position 647 | Install P&C changes associated with the four 115 kV breakers | [26 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2019-03-20 | NR | [26 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1795 | CT | Eversource |  |  | 2022-05-01 | Queue Position 647 | Disconnect existing unit 2 and 3 and connect new unit 5 to the unit position 2 | [26 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2019-03-20 | NR | [26 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1791 | ME | Versant Power |  |  | 2022-05-01 | Queue Position 620 | Addition of Deblois 115 kV Switching Station to Accomdate QP-620 | [24 empty] | Concept | Concept | Concept | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2019-08-26 | NR | [24 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1788 | MA | National Grid, USA |  |  | 2026-05-01 | Queue Position 618 | Install four 345 kV breakers at the Brayton Point substation to convert from a ring bus to a breaker and a half configuration | [24 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-10-11 | NR | [24 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1787 | MA | Eversource |  |  | 2026-05-01 | Queue Position 618 | Installation of a .52 mile underground 3500 kcmil CU XLPE 345 kV line from Brayton Point Substation to the Bay State Wind 1 345/275 kV | [24 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-10-11 | NR | [24 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1786 | MA | Eversource |  |  | 2026-05-01 | Queue Position 618 | Installation of a two 275/66 kV transformers at the Bay State Wind substation | [24 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-10-11 | NR | [24 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1785 | MA | Eversource |  |  | 2026-05-01 | Queue Position 618 | Installation of two 59 mile 275 kV submarine cables from the Bay State Wind 275/66 kV substation, off-shore to the Bay State Wind 345/275 kV substation | [24 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-10-11 | NR | [24 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1784 | MA | Eversource |  |  | 2026-05-01 | Queue Position 618 | Installation of a two 345/275 kV transformers at the Bay State Wind substation | [24 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-10-11 | NR | [24 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1783 | MA | Eversource |  |  | 2026-05-01 | Queue Position 618 | Installation of two 140 MVAR STATCOMs at the Bay State Wind 345/275 kV substation | [24 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-10-11 | NR | [24 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1780 | MA | Eversource |  |  | 2021-12-01 | Queue Position 651 | 600 MW 345 kV HVDC Tie (import only) NY Alps Substation to Eversource Berkshire Substation | [22 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [22 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1779 | MA | Eversource |  |  | 2022-12-01 | Queue Position 640 | 1000 MW 345 kV HVDC Tie (import only) New Brunswick, Canada Coleson Cove Substation to Eversource Pilgrim Substation | [22 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [22 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1778 | MA | Eversource |  |  | 2027-10-01 | Queue Position 506 | Add four 345 kV breakers at K St. | [22 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-10-31 | NR | [22 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1777 | MA | Eversource |  |  | 2027-10-01 | Queue Position 506 | HVDC Terminal to K St. | [22 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-10-31 | NR | [22 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1776 | ME | Emera Maine |  |  | 2019-12-01 | Queue Position 657 | Downeast Loop Transfer Increase | [22 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [22 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1774 | MA | Eversource |  |  | 2019-08-01 | Queue Position 508 | Upgrade Montague substation to include replacement of one 800A wave trap with a 1200A wave trap as well as upgrade the substation conductor to 1590 MCM ACSR | [21 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-07-10 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1773 | MA | Eversource |  |  | 2019-08-01 | Queue Position 508 | Upgrade Cumberland substation including replacement of one 800A wave trap with a 1200A wave trap as well as changes to relay settings | [21 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-07-10 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1772 | MA | Eversource |  |  | 2019-08-01 | Queue Position 508 | Installation of a 23.3 mile overhead 345 kV transmission line from Berkshire to Alps in New York using 954 MCM ACSS | [21 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-07-10 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1771 | MA | Eversource |  |  | 2019-08-01 | Queue Position 508 | Addition of a 600 MW HVDC Conveter at the Berkshire Substation | [21 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-07-10 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1770 | MA | Eversource |  |  | 2019-08-01 | Queue Position 508 | Replacement of the 345/115 kV 2X transformer at the Berkshire substation. Modify Berkshire to a six circuit breaker ring bus and the new autotransformer will have isolation devices on the primary and secondary side of the autotransformer | [21 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-07-10 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1769 | MA | Eversource |  |  | 2019-08-01 | Queue Position 508 | Rebuild of the 7.8 mile overhead 115 kV 1211 Line Doreen substation to North Tap and North Tap to Oswald substation using 556 MCM ACSS | [21 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-07-10 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1768 | MA | Eversource |  |  | 2019-08-01 | Queue Position 508 | Rebuild of the 26.2 mile overhead 115 kV 1242 Line from Berkshire to Plainfield Tap. Plainfield Tap to the Ashfield Tap and Ashfield Tap to the Cumberland substation using 556 MCM ACSS | [21 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-07-10 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1767 | MA | Eversource |  |  | 2019-08-01 | Queue Position 508 | Rebuild of the 26.2 mile overhead 115 kV 1231 Line from Berkshire to Plainfield Tap. Plainfield Tap to the Ashfield Tap and Ashfield Tap to the Cumberland substation using 556 MCM ACSS | [21 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-07-10 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1766 | CT | Eversource |  |  | 2019-09-01 | Queue Position 598 | Construct new substation on the 3271 345 kV line between Lake Road and Card substations | [21 empty] | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1765 | CT | Eversource |  |  | 2019-12-01 | Queue Position 588 | New 115 kV three breaker ring bus and rebuild the Tunnel to Ledyard Jct. portion of the 69 kV 400 line | [21 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1762 | MA | National Grid, USA |  |  | 2022-05-01 | Queue Position 489 | Relocate existing 328/341/347 345kV lines to make way for new 3502 interconnection line to QP489 | [21 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-10-21 | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1761 | ME | Central Maine Power Company |  |  | 2020-11-01 | Queue Position 659 | 1200 MW Construction of 140 miles of new 345 kV AC transmission line from new Gold Brook 345 kV Substation in Skinner Township, ME to existing Larrabee Road 345 kV Substation in Lewiston ME | [21 empty] | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1760 | ME | Central Maine Power Company |  |  | 2020-11-01 | Queue Position 658 | 660 MW Construction of 140 miles of new 345 kV AC transmission line from new Gold Brook 345 kV Substation in Skinner Township, ME to existing Larrabee Road 345 kV Substation in Lewiston ME | [21 empty] | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [21 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1756 | VT | Green Mountain Power |  |  | 2019-05-01 | Queue Position 501 | Upgrade the Cross Road - Mosher's Tap 46 kV line, reconductor 69 miles of 46 kV lines, and upgrade the Lowell 46/34.5 kV transformer | [20 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1755 | VT | Vermont Electric Power Company |  |  | 2019-05-01 | Queue Position 501 | Replace the North Rutland and Irasburg 115/46 kV transformers; replace a relay for the Middlebury 115/46 kV transformer and increase cooling on the Newfane 115/46 kV transformer | [20 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-11-01 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1751 | VT | Vermont Electric Power Company |  |  | 2019-05-01 | Queue Position 501 | Reconductor the K32 (Coolidge - Cold River) 115 kV line | [20 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-11-01 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1748 | VT | Vermont Electric Power Company |  |  | 2020-12-01 | Queue Position 498 | Increase the LTE ratings of both New Haven 345/115 kV autotransformers | [20 empty] | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1747 | VT | Vermont Electric Power Company |  |  | 2020-12-01 | Queue Position 498 | Reconductor the K43 (New Haven - Williston) 115 kV line | [20 empty] | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-12-28 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1746 | VT | Vermont Electric Power Company |  |  | 2020-12-01 | Queue Position 498 | Add two 345 kV circuit breakers at New Haven and close the New Haven 345 kV ring station | [20 empty] | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-12-28 | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1744 | MA | National Grid, USA | Eversource |  | 2023-12-01 | Queue Position 625 | 1600 MW 345 kV AC line Brayton Point Substation interconnection | [20 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1743 | NH | National Grid, USA |  |  | 2022-12-01 | Queue Position 627 | 400 kV HVDC Tie-Import only project connecting to Comerford 230 kV substation | [20 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [20 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1735 | MA | Eversource |  |  | 2021-12-01 | Southeast Massachusetts/Rhode Island Reliability Project | Replace wave trap on 114 line at Tremont Substation #713 | [19 empty] | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [19 empty] | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 0
Reliability Upgrade | 1a | 1733 | MA | Eversource |  |  | 2021-12-01 | Southeast Massachusetts/Rhode Island Reliability Project | Separate the 325/344 DCT lines - West Medway to West Walpole | [19 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | 2017-05-04 | No | [19 empty] | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 17900000 | 0
Reliability Upgrade | 1a | 1723 | MA | National Grid, USA |  |  | 2021-09-01 | Southeast Massachusetts/Rhode Island Reliability Project | Reconductor L14 and M13 from Bell Rock to Bates Tap (8.3 miles each) | [19 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | 2017-05-04 | No | [19 empty] | 29200000 | 29200000 | 29200000 | 29200000 | 29200000 | 29200000 | 29200000 | 29200000 | 29200000 | 29200000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 38700000 | 0
Reliability Upgrade | 1a | 1719 | MA | National Grid, USA |  |  | 2020-12-01 | Southeast Massachusetts/Rhode Island Reliability Project | Install 45.0 MVAR capacitor bank at Berry Street | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | 2018-04-30 | No | [19 empty] | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 1600000 | 3565000 | 3565000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 0
Generator Interconnection Upgrade | 2a | 1713 | RI | National Grid, USA |  |  | 2022-05-01 | Queue Position 489 | Install an additional 345 kV bay at Sherman Road switching station for the interconnection of the new generator | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-10-21 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1712 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Thermal uprate of the 115 kV K189 line. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1711 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Riverside 115 kV substation upgrades | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1710 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Valley 115 kV substation upgrades | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1709 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Reconductor the 115 kV G185N line. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1708 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Reconductor the 115 kV H17 line. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1707 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Reconductor the 115 kV R9 (RI portion) line. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1706 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Replace West Farnum substation 345/115 kV 175T transformer. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1705 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Replace West Farnum substation 345/115 kV 174T transformer. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1704 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Reconductor the 115 kV T172N tap line to West Farnum. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1703 | RI | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Reconductor the 115 kV S171N tap line to West Farnum. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1702 | MA | National Grid, USA |  |  | 2020-12-01 | Queue Position 489 | Reconductor the 115 kV R9 line (MA portion) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2018-05-16 | NR | [19 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1700 | CT | Eversource |  |  | 2022-01-01 | Beacon Falls | Reconfigure the Beacon Falls substation to a 115 kV ring bus | [18 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-11-08 | NR | [18 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1699 | MA | Eversource |  |  | 2023-03-01 | Queue Position 501 | Reconductor ES's section of the 381 (Vernon - Northfield) 345 kV line. (MA portion) | [18 empty] | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-11-01 | NR | [18 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1698 | MA | Eversource |  |  | 2022-01-01 | Queue Position 489 | Reconductor the 345 kV 3361 line | [18 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-10-21 | NR | [18 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1696 | ME | Emera Maine |  |  | 2019-10-01 | Queue Position 400 | Add breaker to existing Epping Switching station to accommodate QP-400 | [17 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-06-30 | NR | [17 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1695 | ME | New Hampshire Transmission, LLC |  |  | 2019-10-01 | Queue Position 591 | 400 MW of Incremental Transfer Capability on 345 kV AC lines in the Surowiec, ME area | [16 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [16 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1694 | ME | Central Maine Power Company and Emera Maine |  |  | 2019-12-01 | Queue Position 590 | 1200 MW 345 kV AC line from Hammond, ME to Pittsfield, ME | [16 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [16 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1693 | ME | Central Maine Power Company |  |  | 2019-10-01 | Queue Position 589 | 550 MW 345 kV AC line from Johnson Mountain Township, ME to Pittsfield, ME | [16 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [16 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1692 | MA | Eversource | Central Maine Power Company |  | 2020-12-01 | Queue Position 585 | 900 MW 345 kV HVDC Tie. New Brunswick, Canada Coleson Cove Substation to Eversource Mystic Substation | [16 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [16 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1691 | ME | Next Era |  |  | 2019-10-01 | Queue Position 571 | 850 MW of Energy Transfer Capability from the proxy Concord Switching Station to Larrabee Road 345 kV Substation | [16 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [16 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1690 | MA | Eversource | Emera Maine |  | 2021-12-01 | Queue Position 569 | 1200 MW 345 kV HVDC Tie. Emera Orrington Substation in ME to Eversource Jordan Rd, MA | [16 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [16 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1689 | ME | Emera Maine |  |  | 2021-12-01 | Queue Position 569 | 1200 MW 345 kV HVDC Tie. Emera Orrington Substation in ME to Eversource Jordan Rd, MA | [16 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [16 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1685 | MA | Eversource |  |  | 2018-03-01 | Queue Position 541 | Upgrade the necessary terminal equipment at Agawam 16C Substation to match or exceed the 1302 line conductor ratings | [15 empty] | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 4/16/2015 | No | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1684 | MA | Eversource |  |  | 2018-03-01 | Queue Position 541 | Reconductoring of the 1657-3 line section (approximately 160 feet) from Southampton Junction to the Eversource / HG&E border using 795 kcmil ACSS conductor | [15 empty] | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 4/16/2015 | No | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1683 | MA | Eversource |  |  | 2018-03-01 | Queue Position 541 | Construct a new 115-kV four breaker ring bus switching station in Westfield, MA. Loop the existing line 1302 (between Buck Pond and Pochassic tap) into the new switching station and terminate to establish new lines from Buck Pond 34B Substation to PVEC | [15 empty] | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 4/16/2015 | No | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1682 | NH | Eversource |  |  | 2017-09-01 | Spruce Ridge | Thermal upgrade of the 11 mile 115 kV A111 Line from Webster Substation in Webster, NH to Pemigewassett Substation in Littleton, NH from 135 MVA to 138 MVA | [15 empty] | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 4/16/2015 | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1681 | NH | Eversource |  |  | 2017-09-01 | Spruce Ridge | Thermal upgrade of the 8 mile 115 kV E115-2 Line from Ashland Tap in Ashland, NH to the Pemigewassett Substation in Littleton, NH from 135 MVA to 138 MVA | [15 empty] | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 4/16/2015 | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1680 | NH | National Grid, USA |  |  | 2019-01-01 | Spruce Ridge | Construct a 230 kV three breaker interconnection substation in Groton, NH. Construct a 0.05 mile long, 230 kV tap line connecting the interconnection substation to the 230 kV A-201 transmission line. | [15 empty] | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 4/16/2015 | NR | [15 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1678 | MA | National Grid, USA |  |  | 2020-06-01 |  | Salem Harbor Substation Rebuild (Asset Condition) | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Proposed | NR | No | [15 empty] | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 75000000 | 0
Elective Upgrade | 4b | 1658 | MA | Eversource |  |  | 2018-12-01 | Queue Position 518 | 1000 MW HVDC from CMP ME Yankee 345 kV substation to Eversource K street 115 kV substation | [13 empty] | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1657 | MA | Eversource |  |  | 2018-12-01 | Queue Position 517 | 1000 MW HVDC from CMP ME Yankee 345 kV substation to Eversource Mystic 345 kV substation | [13 empty] | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1656 | MA | Eversource |  |  | 2020-12-01 | Queue Position 511 | 1000 MW HVDC line to Eversource Barnstable 345 kV | [13 empty] | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1655 | NH | Eversource |  |  | 2019-04-01 | Queue Position 519 | 1200 MW HVDC connection (Des Cantons-Deerfield) | [13 empty] | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [13 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1654 | NH | Eversource |  |  | 2022-12-01 | Queue Position 499 | 300 kV 1090 MW HVDC connection (Des Cantons-Deerfield) | [13 empty] | Concept | Concept | Concept | Concept | Concept | Planned | Planned | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2016-07-19 | NR | [12 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1644 | MA | Eversource |  |  | 2019-06-01 |  | Upgrade the Medway 115 kV station to BPS standards | [13 empty] | Proposed | Proposed | Proposed | Planned | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Proposed | 2016-01-26 | No | [13 empty] | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | $6,900,000 Moved to Asset Condtion List | #VALUE!
Reliability Upgrade | 1b | 1642 | MA | Eversource |  |  | 2017-10-01 | Greater Boston - Stability | Upgrade the Dover 115 kV station to BPS standards | [13 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Proposed | No | No | [13 empty] | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 0
Reliability Upgrade | 1b | 1641 | MA | Eversource |  |  | 2019-06-01 | Greater Boston - Stability | Upgrade the Edgar 115 kV station to BPS standards | [13 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Proposed | No | No | [13 empty] | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 0
Reliability Upgrade | 1a | 1636 | MA | National Grid, USA |  |  | 2018-06-01 | Greater Boston - Stability | Upgrade the West Methuen115 kV station to BPS standards | [13 empty] | Proposed | Proposed | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Proposed | NR | No | [13 empty] | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 8900000 | 0
Elective Upgrade | 4b | 1633 | MA | Eversource |  |  | 2019-08-01 | Queue Position 508 and Queue Positon 584 | 600 MW 345 kV HVDC Tie. Alps Substation in NY to Eversource's Berkshire Substation in MA | [12 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [12 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4a | 1632 | MA | Eversource |  |  | 2027-10-01 | Queue Position 506 | 1000 MW HVDC Tie. NMISA to Eversource's K St 345 kV Substation | [12 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2017-10-31 | NR | [12 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1631 | MA | Eversource |  |  | 2017-12-01 | Queue Position 456 | 1200 MW HVDC Tie. HQ to Eversource's 345 kV Mystic Substation | [12 empty] | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [12 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Elective Upgrade | 4b | 1630 | VT | Vermont Electric Power Company |  |  | 2018-06-01 | Queue Position 516 | 425 MW HVDC Tie HQ to VELCO 345 kV New Haven Substation | [12 empty] | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | No | [12 empty] | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1629 | VT | Vermont Electric Power Company |  |  | 2018-06-01 | Queue Position 515 | 425 MW HVDC Tie HQ to VELCO 115 kV Williston Substation | [12 empty] | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | No | [12 empty] | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1628 | VT | Vermont Electric Power Company |  |  | 2017-12-01 | Queue Position 457 | 500 MW HVDC Tie HQ to VELCO 115 kV Georgia Substation | [12 empty] | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | No | [12 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Elective Upgrade | 4b | 1627 | VT | Vermont Electric Power Company |  |  | 2017-12-01 | Queue Position 505 | 1000 MW HVDC Tie HQ to VELCO 345 kV Coolidge Substation | [12 empty] | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | No | [12 empty] | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1626 | ME | Emera Maine |  |  | 2018-06-01 | Queue Position 507 | 75 MW AC Tie NMISA Mullen Substation to Emera ME Rd Substation | [12 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [12 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1624 | MA | National Grid, USA |  |  | 2022-02-01 | North Oxford Breaker Addition | Install a 115 kV breaker at the North Oxford substation and segment the V-174 line | [12 empty] | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Proposed | 2015-07-23 | NR | [12 empty] | TBD | TBD | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 0
Reliability Upgrade | 1a | 1579 | CT | Eversource |  |  | 2018-12-01 | SWCT | Separate 3827-1610 DCT (0.38 miles) | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 2017-05-23 | No | [12 empty] | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 0
Reliability Upgrade | 1a | 1571 | CT | Eversource |  |  | 2018-12-01 | SWCT | Rebuild Bunker Hill to a 9 breaker substation in breaker-and-a-half configuration | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 2017-05-23 | No | [12 empty] | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 35500000 | 0
Reliability Upgrade | 1a | 1569 | CT | Eversource |  |  | 2018-12-01 | SWCT | Loop the 1990 line in and out of Bunker Hill Substation | [12 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 2017-05-23 | No | [12 empty] | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 300000 | 0
Generator Interconnection Upgrade | 2a | 1556 | ME | Emera Maine |  |  | 2016-10-01 | QP 327 | Installation of 20 MVAR DVAR system on 115 kV bus at Chester Station to accommodate QP 327 | [11 empty] | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2014-02-18 | NR | [11 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1548 | MA | National Grid, USA |  |  | 2019-03-01 | Queue Position 512 | 1200 MW AC to HVDC Tie. NB 345 kV Keswick or St. Andre substation to NGRID 345 kV Wakefield substation | [10 empty] | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [10 empty] | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1547 | VT | Vermont Electric Power Company |  |  | 2018-12-01 | Queue Position 504 | 1000 MW HVDC Tie V3 HQ 735 kV substation to VELCO 345 kV New Haven substation | [10 empty] | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | No | [10 empty] | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1546 | VT | Vermont Electric Power Company |  |  | 2018-12-01 | Queue Position 503 | 1000 MW HVDC Tie V2 HQ 735 kV substation to VELCO 345 kV West Rutland substation | [10 empty] | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | No | [10 empty] | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1544 | NH | Eversource |  |  | 2016-07-01 | Queue Position 513 | Coos ETU - Transmission Reinforcement | [10 empty] | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [10 empty] | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1543 | ME | Emera Maine |  |  | 2017-11-01 | Queue Position 514 | Expand NB/NE Interface by 350 MW | [10 empty] | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [10 empty] | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1542 | ME | Emera Maine |  |  | 2018-12-01 | Queue Position 500 | Keene Road ETU at Penobscot ME | [10 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [10 empty] | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1541 | NH | Eversource |  |  | 2018-12-01 | Queue Position 519 | Increase the 326 Line SPS summer thermal mode set point | [10 empty] | Proposed | Proposed | Proposed | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-12-31 | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1540 | NH | Eversource |  |  | 2018-12-01 | Queue Position 519 | Upgrade the 345 kV 373 line from Deerfield to Scobie Pond | [10 empty] | Proposed | Proposed | Proposed | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-12-31 | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1539 | NH | Eversource |  |  | 2018-12-01 | Queue Position 519 | Install 210 Mvar of 345 kV capacitor banks at the 345 kV Scobie Pond Substation. The capacitor banks will be connected to 345-kV Scobie Pond Bus #2 via five 345 kV circuit breakers. In addition to the capacitor banks, two new 345 kV circuit breakers will be installed at the 345 kV Scobie Pond Substation. One circuit breaker is to be installed in series with the existing 9126 circuit breaker, and the other circuit breaker installed in series with the 262 circuit breaker. | [10 empty] | Proposed | Proposed | Proposed | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-12-31 | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1538 | NH | Eversource |  |  | 2018-12-01 | Queue Position 519 | Reconfigure the Deerfield 345 kV Substation to accommodate the new NPT Project AC transmission line 3132 interconnection, the re-termination of the 345 kV Buxton to Scobie Pond transmission line 391, the addition of 200 MVAR shunt capacitor banks, and the addition of one 0/+400 Mvar SVC. The existing 373 line will be re-positioned to its own new bay position. The existing 345 kV AC transmission line 391 that will be looped into and terminated at the 345 kV Deerfield Substation | [10 empty] | Proposed | Proposed | Proposed | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-12-31 | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1537 | NH | Eversource |  |  | 2018-12-01 | Queue Position 519 | Install new 345 kV AC transmission line, 3132, from the Franklin Converter Terminal Substation to the Deerfield 345 kV Substation. | [10 empty] | Proposed | Proposed | Proposed | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-12-31 | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1536 | NH | Eversource |  |  | 2018-12-01 | Queue Position 519 | Install NPT terminal consisting of a 345 kV substation with an eight circuit breaker ring bus in Franklin, NH, a 1,200 MW nominal, bi-directional, bi-polar, HVDC line commutated converter station, and a 0/100 Mvar Static Var Compensator (SVC). The Franklin terminal will have two 600 MW line commutated converters with reactive compensation | [10 empty] | Proposed | Proposed | Proposed | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-12-31 | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1535 | CT | Eversource |  |  | 2016 | Queue Position 277 | Reconductor 345 kV 398 line CL&P portion of the Long Mountain to Pleasant Valley (NY) line | [10 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1524 | MA | Eversource |  |  | 2018-10-01 | Cape Wind | Installation of (1) 40 MVAR shunt reactor at the West Barnstable 115 kV Substation | [10 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2014-02-11 | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1523 | MA | Eversource |  |  | 2018-10-01 | Cape Wind | Modification of the Barnstable SVC to enable continuous inductive operation with a limit of 70.5 MVAR | [10 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2014-02-11 | NR | [10 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1521 | MA | Eversource |  |  | 2016-12-01 | Greater Boston - Central | Add a new 115 kV 54 MVAR capacitor bank at Newton Station | [10 empty] | Concept | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [10 empty] | TBD | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 1400000 | 0
Reliability Upgrade | 1b | 1515 | ME | Central Maine Power Company |  |  | 2020-12-01 | CMP- LSP New Waterford Substation | Add a new substation at New Waterford | [10 empty] | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | N-Concept | No | No | [10 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1512 | ME | Central Maine Power Company |  |  | 2020-05-01 | CMP- LSP Lakes Region | New Gloucester 115/34 kV S/S with a four breaker ring bus and 115/34 kV transformer and (10 mile) 115 kV transmission line to Surowiec | [9 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | N-Concept | No | No | [9 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1509 | MA | National Grid, USA |  |  | 2017-03-01 |  | 303/327/3520 Brayton Point - West Medway Asset Condition Refurbishment (ACR) | [9 empty] | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [9 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1508 | RI | National Grid, USA |  |  | 2018-12-01 |  | 315 Brayton Point - West Farnum Asset Condition Refurbishment (ACR) - RI portion | [9 empty] | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [9 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1507 | MA | National Grid, USA |  |  | 2018-12-01 |  | 315 Brayton Point - West Farnum Asset Condition Refurbishment (ACR) - MA portion | [9 empty] | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [9 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 1501 | ME | Central Maine Power Company |  |  | 2023-12-01 | CMP- LSP Lakes Region | Add a second 115/34.5 kV autotransformer at the existing Kimball Road 115 kV Substation and move one of the 115 kV 30 MVAR capacitor banks from bus 4 to bus 3 | [7 empty] | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 2013-10-02 | NR | [7 empty] | TBD | TBD | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 0
Reliability Upgrade | 1b | 1500 | ME | Central Maine Power Company |  |  | 2020-12-01 | CMP- LSP Topsham 115 kV Substation | Add six 115 kV circuit breakers a the existing 115 kV Topsham substation to reconfigure the existing 115 kV bus to a 6-breaker ring and upgrade the 115 kV T1 and T3 115/34.5 kV autotransformers at the existing Topsham 115 kV substation | [7 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | N-Concept | No | No | [7 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 1499 | ME | Central Maine Power Company |  |  | 2020-07-01 | Newcastle Substation Upgrades Project | Addition of two 115 kV circuit breakers at the existing 115 kV bus at Newcastle substation to reconfigure the existing 115 kV bus to a 4-breaker ring bus | [7 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 2013-08-07 | No | [7 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 6600000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 7330000 | 0
Generator Interconnection Upgrade | 2b | 1496 | NH | Eversource |  |  | 2014-12-01 | QP 371 | New 115 kV Tuttle Hill Switching Station bifurcating the L163 115 kV line | [7 empty] | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-01-18 | NR | [7 empty] | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1487 | MA | Eversource |  |  | 2020-06-01 | Queue Position 510 | 1000 MW HVDC line to Eversource Carver 345 kV and to Barnstable 345 kV | [6 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [6 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1486 | CT | United Illuminating Company |  |  | 2016-06-01 | Queue Position 355 | HVDC line between UI Singer 345 kV substation and LIPA Pt Jefferson 138 kV substation or LIPA Shoreham 138 kV substation | [6 empty] | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [6 empty] | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1485 | MA | Northeast Utilities - NSTAR | Emera Maine |  | 2014-12-01 | Queue Position 341 | Massachusetts portion of HVDC line between MEPCO 345 kV at Haynesville or MPC 345 kV and NSTAR 345 kV K-Street Substation | [6 empty] | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [6 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Elective Upgrade | 4b | 1484 | ME | Emera Maine | Eversource |  | 2014-12-01 | Queue Position 341 | Maine portion of HVDC line between MEPCO 345 kV at Haynesville or MPC 345 kV and NSTAR 345 kV K-Street Substation | [6 empty] | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [6 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 1455 | ME | Central Maine Power Company |  |  | 2014-12-01 | Maine Power Reliability Program (MPRP) | Re-rate of the 115 kV Line 241A (formerly 67A) between Rice Rips substation and 241A Tap | [6 empty] | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1453 | ME | Central Maine Power Company |  |  | 2014-12-01 | Maine Power Reliability Program (MPRP) | Re-rate of the 115 kV Line 241B (formerly 83B) between Lakewood substation and 241B Tap | [6 empty] | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1b | 1398 | CT | Eversource |  |  | 2015-12-01 | SWCT | Reconductor/rebuild 115 kV 1630-1 Wallingford - Walrec to 1590 kcmil ACSS (0.15 miles) | [6 empty] | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | [6 empty] | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 0
Reliability Upgrade | 1b | 1397 | CT | Eversource |  |  | TBD | SWCT | Reconductor 115 kV 1610-1 Cook Hill - Southington to 795 kcmil ACSS (10.6 miles) | [6 empty] | Proposed | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [6 empty] | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 44700000 | 0
Reliability Upgrade | 1a | 1388 | CT | United Illuminating Company |  |  | 2015-12-01 | SWCT | Sackett 115 kV Capacitor Bank Addition | [6 empty] | Proposed | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2012-10-05 | NR | [6 empty] | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 0
Reliability Upgrade | 1a | 1387 | CT | United Illuminating Company |  |  | 2015-12-01 | SWCT | Grand Avenue 115 kV Capacitor Bank Addition | [6 empty] | Proposed | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2012-10-05 | No | [6 empty] | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 0
Reliability Upgrade | 1a | 1382 | CT | United Illuminating Company |  |  | 2015-12-01 | SWCT | Glen Lake Junction - Mix Avenue 1610-2 115 kV Line Upgrade | [6 empty] | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2012-08-27 | No | [6 empty] | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 11400000 | 0
Reliability Upgrade | 1a | 1373 | CT | Eversource |  |  | 2017 | NEEWS | Add the 2nd Beseck 9F Substation Variable Shunt Reactor (75-150 MVAR) | [5 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 5/4/2012 7/25/2013 | No | [5 empty] | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 0
Reliability Upgrade | 1a | 1372 | CT | Eversource |  |  | 2017 | NEEWS | North Bloomfield 2A Substation Expansion which includes a 3rd bay with two breakers and associated substation work | [5 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2012-05-04 | No | [5 empty] | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | #VALUE!
Elective Upgrade | 4b | 1367 | ME | Central Maine Power Company |  |  | TBD | Queue Position 378 | 800 MW HVDC from MEPCO to Salem MA | [5 empty] | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [5 empty] | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 1366 | ME | Central Maine Power Company |  |  | 2013-12-01 | Maine Power Reliability Program (MPRP) | Section 160 reconductor from Hinckley Pond Substation to Cape Substation | [5 empty] | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2/26/09 & 11/22/10 | NR | [5 empty] | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1b | 1362 | MA | National Grid, USA |  |  | 2016-12-01 | Greater Boston - North | Reconductor the 337 Sandy Pond - Tewksbury 345 kV line | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [5 empty] | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 0
Reliability Upgrade | 1b | 1361 | MA | National Grid, USA |  |  | 2018 | Greater Boston - North | New 345 kV line between Wakefield and Ward Hill and associated substation work | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [5 empty] | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 77600000 | 0
Reliability Upgrade | 1b | 1347 | NH | New Hampshire Transmission, LLC |  |  | 2015-11-01 | Greater Boston - North | Seabrook 345 kV substation: Replace two 345 kV GIS breakers, 1000 feet of GIS bus, and open-air equipment at the GIS transition yard associated with the 394 line termination. These upgrades eliminate terminal equipment restrictions on the New Hampshire Transmission section of the 345 kV line (394) from Seabrook to West Amesbury to Ward Hill | [5 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | [5 empty] | 21201727 | 21201727 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 27400000 | 0
Reliability Upgrade | 1a | 1343 | MA | Eversource |  |  | 2016-12-01 |  | Relay systems upgrade at Lexington and Woburn to make Lexington station non-BPS |  |  |  |  | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | NR | NR |  |  |  |  | TBD | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 0
Reliability Upgrade | 1b | 1340 | MA | Eversource |  |  | 2015-12-01 | Greater Boston - Western Suburbs | Upgrade 115 kV terminal equipment at Lexington substation for 320-507/508 lines |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR |  |  |  |  | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 0
Generator Interconnection Upgrade | 2b | 1334 | ME | Central Maine Power Company |  |  | 2012-10-01 | Queue Position 310 | Four +/- 4 MVAR dynamic reactive sources (including a 115/34.5 transformer with High-side and Low-side breakers) at Bigelow Substation. Automate high-voltage switching controls for both 18 MVAR capacitor banks at Wyman Hydro Substation. Install 5.4 MVAR of shunt capacitance at Starks Substation to interconnect QP #310 |  |  |  |  | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2012-03-05 | NR |  |  |  |  | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1332 | MA | National Grid, USA |  |  | 2017-06-01 | Southern New Hampshire Solution | Reconductoring the 345 kV 326 line portion from Sandy Pond to MA/NH state line |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-03-08 | No |  |  |  |  | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 39800000 | 0
Reliability Upgrade | 1b | 1328 | MA | National Grid, USA |  |  | 2015-12-01 | Greater Boston - Western Suburbs | 115 kV Line reconductoring of E-157W Millbury-E. Main St |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 0
Reliability Upgrade | 1b | 1326 | MA | National Grid, USA |  |  | 2015-12-01 | Greater Boston - Western Suburbs | 69 kV Line reconductoring of W-23 Fitch Rd-Woodside |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 0
Reliability Upgrade | 1b | 1313 | NH | Eversource |  |  | 2017 | Southern New Hampshire Solution | Greggs Substation - Add (1) 115 kV series circuit breaker, replace (1) 115 kV circuit breaker, includes associated 115kV substation work |  |  |  |  | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 3600000 | 0
Reliability Upgrade | 1b | 1311 | NH | Eversource |  |  | 2016 | Southern New Hampshire Solution | Terminal upgrades for 115 kV line V182, Garvins-Webster |  |  |  |  | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 0
Reliability Upgrade | 1b | 1305 | NH | Eversource |  |  | 2020 | Southern New Hampshire Solution | Uprate 115 kV line O161, Pine Hill-Greggs |  |  |  |  | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 0
Reliability Upgrade | 1a | 1300 | ME | Central Maine Power Company |  |  | 2022-12-01 | Central New Hampshire Solution | Install transfer trip at Kimball Road disconnect Lovell from 115 kV, Lovell load will continue to be served from CMP subtransmission |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 2013-03-07 | No |  |  |  |  | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 0
Generator Interconnection Upgrade | 2a | 1299 | CT | Eversource |  |  | 2014-12-01 | Meriden Gas Turbine | 1.1 mile radial 345 kV line from the new three breaker ring bus to Meriden generating facility |  |  |  |  | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2010-03-23 | NR |  |  |  |  | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1289 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | Southeastern VT Solution | Upgrade the 381 345 kV line between Vernon and the NH/VT border |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 6000000 | 0
Reliability Upgrade | 1b | 1288 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | Connecticut River Solution | Rebuild the 2 mile Ascutney - Ascutney 115 kV Tap line (10) |  |  |  |  | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 13000000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1287 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | Northern VT Solution | Install two 12.5 MVAR capacitor banks at Jay 115 kV substation |  |  |  |  | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 4400000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1286 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | Connecticut River Valley | Construct a new 15 mile 115 kV line from Coolidge to Ascutney |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 93000000 | 0
Reliability Upgrade | 1b | 1285 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | Central VT Solution | Construct a new 27 mile 345 kV line from West Rutland to Coolidge |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 157000000 | 0
Reliability Upgrade | 1b | 1284 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | Northwestern VT Solution | K30 West Rutland - Middlebury 115 kV line rebuild |  |  |  |  | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 113000000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1283 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | Northwestern VT Solution | K43 New Haven - Williston 115 kV line rebuild |  |  |  |  | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 96000000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1282 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | Northwestern VT Solution | Upgrade K27 Williston-Tafts Corner 115 kV line |  |  |  |  | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 12000000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1281 | VT | Vermont Electric Power Company |  |  | 2014-12-01 | Northwestern VT Solution | Install a SPS to cross trip the PV-20 line for low voltage at South Hero |  |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  |  | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 0
Reliability Upgrade | 1b | 1280 | ME | Central Maine Power Company |  |  | 2022-12-01 | Mid-Coast Spur | New 115 kV line section 244 and upgraded line section 80 between Coopers Mill and Highland Substations |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Proposed | No | No |  |  |  | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 62735000 | 0
Reliability Upgrade | 1b | 1279 | ME | Central Maine Power Company |  |  | 2017-12-01 |  | New 345/115 kV Autotransformer and 115 kV switchyard at Raven Farm substation consisting of a four-bay breaker and a half configuration of eleven (11) breakers |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 26126000 | 0
Reliability Upgrade | 1a | 1274 | NH | Eversource |  |  | 2016 | Western New Hampshire Solution | Rebuild N186 115 kV line |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-03-07 | No |  |  |  | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 0
Reliability Upgrade | 1a | 1273 | NH | Eversource |  |  | 2016 | Western New Hampshire Solution | Rebuild A152 115 kV line |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-03-07 | No |  |  |  | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 22500000 | 0
Reliability Upgrade | 1a | 1269 | NH | Eversource |  |  | 2018 | Western New Hampshire Solution | Amherst Substation - New 345 kV breaker and two 25 MVAR Capacitor Banks |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 2013-03-07 | No |  |  |  | 19600000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 0
Generator Interconnection Upgrade | 2a | 1265 | VT | Vermont Electric Power Company |  |  | 2016-03-01 | Fair Haven Biomass | Installation of 3-breaker 115 kV ring bus interconnection to the Whitehall-Blissville 115 kV K7 line. Construction of 2.5 mile line to the plant |  |  |  |  | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2011-08-29 | NR |  |  |  | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1262 | MA | National Grid, USA |  |  | 2015-12-01 | Greater Boston - North | 115 kV Line reconductoring of theY-151 from Tewksbury Junction - Tewksbury Substation |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 1250000 | 0
Reliability Upgrade | 1b | 1261 | MA | National Grid, USA |  |  | 2015-12-01 | Greater Boston - North | 115 kV Line reconductoring of the S-145T-146 from North Reading Tap - Wakefield Jct |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  |  | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 0
Reliability Upgrade | 1b | 1254 | MA | National Grid, USA |  |  | 2015-12-01 | Greater Boston - North | Substation work at Revere Substation to increase ratings on the 128-515P/168 line between Chelsea and Revere |  |  | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | NR | No |  |  | TBD | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 0
Reliability Upgrade | 1b | 1250 | VT | Vermont Electric Power Company |  |  | 2016-12-01 | VELCO LSP - West Rutland Substation | Installation of a 115/46 kV transformer at West Rutland between breakers K30 and K34 |  |  | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1249 | MA | Eversource |  |  | 2013-12-01 |  | Rebuild the Wareham Substation to a breaker and a half scheme |  |  | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1248 | MA | Eversource |  |  | 2014-12-01 |  | Rebuild the Kingston Substation to a breaker and a half scheme |  |  | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1247 | MA | Eversource |  |  | TBD |  | Rebuild the Acushnet 115 kV Substation |  |  | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 1242 | CT | CMEEC |  |  | 2014-05-01 | SNEW 115kV Substation | SNEW 115/13.8 kV substation with two transformers and a 115kV circuit breaker looped into the 1890 line (between Sherwood Substation - Ely Ave Jct) |  |  | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 1/17/2012 12/7/2012 | NR |  |  | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Generator Interconnection Upgrade | 2a | 1240 | MA | Eversource |  |  | 2015-04-01 | Pioneer Valley Energy Center (PVEC) | Upgrade the substation conductor, manual switch, wave trap, primary and back up relays and metering at Buck Pond substation for the 1657 (Buck Pond - Southampton Jct.) line terminal to match or exceed the conductor ratings. |  | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2010-10-20 | NR |  | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1239 | MA | Eversource |  |  | 2015-04-01 | Pioneer Valley Energy Center (PVEC) | Upgrade the substation conductor, manual switch, wave trap, primary and backup relays and metering at Buck Pond 34B substation for the 1302 (Buck Pond - QP236) line terminal to match or exceed the conductor ratings |  | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2010-10-20 | NR |  | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1238 | MA | Eversource |  |  | 2015-04-01 | Pioneer Valley Energy Center (PVEC) | Upgrade the substation conductor, manual switch, wave trap, Watt/VAR transducer inside breaker 16C-35T-2 control cabinet, primary and backup relays and metering at Agawam 16C substation for the 1302 (Agawam - Pochassic tap) line terminal to match or exceed the conductor ratings. |  | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2010-10-20 | NR |  | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1237 | MA | Eversource |  |  | 2015-04-01 | Pioneer Valley Energy Center (PVEC) | Upgrade Fairmont 16H switching station to be NPCC Bulk Power System (BPS) compliant by adding a second DC system |  | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2010-10-20 | NR |  | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1236 | MA | Eversource |  |  | 2015-04-01 | Pioneer Valley Energy Center (PVEC) | Install an NPCC type III SPS at the PVEC substation to monitor flow in (Southampton Jct. - Ingleside) section of 1657 line. |  | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2010-10-20 | NR |  | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1231 | NH | Eversource |  |  | 2017-06-01 | Queue Position 348 | 1200 MW HVDC connection (Des Cantons-Franklin) with 345 kV connection (Franklin-Deerfield) |  | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2013-12-31 | NR |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 1226 | MA | Eversource |  |  | 2016 | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115 kV line and terminal work at Woodland substation. |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 12/7/2012 1/26/2016 | No |  | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | Part of Pittsfield/Greenfield Project - ID 1221 | #VALUE!
Reliability Upgrade | 1b | 1215 | MA | National Grid, USA |  |  | 2015-12-01 | Greater Boston - North | New 115 kV line between Wakefield - Everett |  | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 0
Reliability Upgrade | 1b | 1211 | MA | National Grid, USA |  |  | 2017-12-01 | Greater Boston - North | Install 2nd 345 kV circuit between Tewksbury - Billerica/Burlington Town Line (NSTAR Border) and associated substation work at Tewksbury |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  | 32700000 | 32700000 | 32700000 | 32700000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 37500000 | 0
Reliability Upgrade | 1b | 1206 | MA | Eversource |  |  | 2011-12-01 |  | Install a new 230 kV breaker for line 282-602 (West Medway-Waltham) at W. Medway for system restoration |  | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1205 | MA | Eversource |  |  | 2013-12-01 | Mid-Cape Reliability Project | Separate 120 (Canal-Barnstable) /122 (Oak St-Barnstable) DCT |  | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1204 | MA | Eversource |  |  | 2013-06-01 |  | Rebuild the Mashpee Substation to a Ring Bus and install an overvoltage trip relay on the Mashpee 115 kV Capacitor Bank |  | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  | TBD | TBD | TBD | 13000000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1203 | MA | Eversource |  |  | TBD |  | Build a new 115kV switching facility at Mendall Road on line 112 |  | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1200 | MA | Eversource |  |  | 2017-12-01 | Greater Boston - North | Add a new 345 kV UG circuit between Woburn and North Cambridge |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 52000000 | 0
Reliability Upgrade | 1b | 1198 | MA | Eversource |  |  | 2017-12-01 | Greater Boston - Western Suburbs | Add a 115 kV line from Woburn to Hartwell Ave |  | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No |  | TBD | TBD | TBD | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 19000000 | 0
Reliability Upgrade | 1b | 1190 | MA | Eversource |  |  | 2017-12-01 | Greater Boston - North | Install a second 345/115 kV autotransformer and 345 kV and 115 kV switchgear and breakers at Woburn | Concept | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 22800000 | 0
Reliability Upgrade | 1b | 1189 | MA | Eversource |  |  | 2015-12-01 | Greater Boston - Central | Install 3rd 115 kV Circuit between Waltham and Brighton | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Generator Interconnection Upgrade | 2a | 1188 | MA | Eversource |  |  | 2015-06-01 | Cape Wind | Reconductor/Rebuild Brook Street-Kingston Line #117 | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1181 | MA | Eversource |  |  | 2013-12-01 |  | Rebuild the High Hill 115 kV Substation to a Breaker and a half design | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1180 | MA | Eversource |  |  | 2013-12-01 |  | Install an over voltage trip relay on the Mashpee 115 kV Capacitor Bank | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1179 | MA | Eversource |  |  | 2017-12-01 | Greater Boston - North | Install 2nd 345 kV circuit between Bellerica/Burlington town line to Woburn (NSTAR portion of new Tewksbury -Woburn 345 kV line) | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 0
Reliability Upgrade | 1b | 1178 | MA | Eversource |  |  | 2015-12-01 | Greater Boston - North | Install 115 kV Capacitor Bank at North Woburn | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1177 | MA | Eversource |  |  | 2015-12-01 | Greater Boston - North | Reconductor 211-503/504 from North Woburn Tap to Reading | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1176 | MA | Eversource |  |  | TBD | Greater Boston - Central | Install an oil circulation pipe and heat exchangers at K Street and Chatham Street sections of 250-516/517 circuits | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1174 | MA | Eversource |  |  | 2013-12-01 | Greater Boston Reliability Project | Upgrade the 115 kV line 211-514 to a higher capacity line | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1164 | ME | Central Maine Power Company | Emera Maine |  | 2016-12-01 | Queue Position 502 | 345 kV Tie Phase 1: 200 MW Houlton, ME to MEPCO 396 Line and Phase 2: MEPCO 396 Line to Bridgewater, ME | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1163 | ME | Maine Electric Power Company |  |  | TBD | Queue Position 322 | 345 kV Tie Line - between Houlton, ME and MEPCO Line | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Elective Upgrade | 4b | 1161 |  | United Illuminating Company |  |  | TBD | Queue Position 271 | 1000 MW HVDC between Hertel, QC or Clay NY and Singer, CT | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Elective Upgrade | 4b | 1160 | ME | Central Maine Power Company |  |  | 2017-03-01 | Queue Position 278 | 1000 MW HVDC between Maine Yankee, ME and South Boston, MA | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 1158 | ME | Central Maine Power Company |  |  | 2014-07-01 | Maine Power Reliability Program (MPRP) | Two 40 MVAR reactors at Albion Road, two 40 MVAR reactors at Larrabee Road, two 40 MVAR at Coopers Mills | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1b | 1153 | MA | Eversource |  |  | 2012-12-01 | Boston Area 115 kV Enhancements | Add a new 115 kV breaker on the West Framingham end of the 455-507 line such that 110B transformer is isolated from any faults on the 455-507 line | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 0
Reliability Upgrade | 1b | 1136 |  | National Grid, USA |  |  | 2012-12-01 |  | New 115kV Switching Station at Devens Convert 69kV lines to 115kV, Reconfigure 115kV Supply at Ayer Substation | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2009-07-28 | No | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 9200000 | 0
Reliability Upgrade | 1a | 1132 | ME | Central Maine Power Company |  |  | 2014-08-01 | Maine Power Reliability Program (MPRP) | Add 115/12 kV transformer at Coopers Mills | Proposed | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/08 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1b | 1130 |  | Central Maine Power Company |  |  | 2011-12-01 | Sturtevant Improvements | Add 115 kV circuit breakers & 25 MVAR capacitor bank at Sturtevant Substation; Re-rate Section 63 between Wyman Hydro & Madison Substation | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2009-07-28 | No | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 0
Generator Interconnection Upgrade | 2b | 1125 | CT | Eversource |  |  | TBD | Queue Position 240 | 345 kV on Montville Substation | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1124 | CT | Eversource |  |  | 2014-12-01 | Meriden Gas Turbine | Three breaker 345 kV ring bus splitting the 3754 line from Southington to Beseck | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2010-03-23 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1123 | MA | Eversource |  |  | 2015-04-01 | Pioneer Valley Energy Center (PVEC) | Installation of new four breaker 115 kV switching station in a ring bus configuration for PVEC and loop line 1302 (between Buck Pond and Pochassic Tap) into the new switching substation and terminate to establish new lines from Buck Pond 34B substation to PVEC switching station (length approximately 1.0 mile) and from Pochassic substation tap to PVEC switching station (length approximately 2.12 miles) | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1122 | CT | Eversource |  |  | 2012-03-01 | Queue Position 191 | One turbine connected to #1238 Line (Frost Bridge to Carmel) via a new 3-breaker ring bus Substation | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2009-02-24 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1114 | CT | Eversource |  |  | 2017 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R Substation expansion - Add a 345/115 kV autotransformer. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 9/24/2008 5/4/2012 | No | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | Part of NEEWS (Central Connecticut Reliability Project) Project ID 576 | #VALUE!
Generator Interconnection Upgrade | 2a | 1108 | CT | Eversource |  |  | 2013-06-01 | Towantic Energy | Installation of a 2.5% series reactor on the 1990S Line at the new substation. | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-26 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1107 | CT | Eversource |  |  | 2013-06-01 | Towantic Energy | Interconnection to new 115 kV substation consisting of (14) circuit breakers in a breaker and a half configuration that sectionalizes the existing 1575, 1585, and 1990 lines. | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-26 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1089 | CT | Eversource |  |  | 2015 | NEEWS (Interstate Reliability Project) | Killingly 3G substation 345 kV breaker addition | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 1088 | CT | Eversource |  |  | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to 115 kV line 1786, East Hartford to Riverside to South Meadow | Planned | Planned | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1087 | CT | Eversource |  |  | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to line 115 kV 1722 SW Hartford NW Hartford | Planned | Planned | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1086 | CT | Eversource |  |  | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to 115 kV line 1704, SW Hartford to South Meadow | Planned | Planned | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 1084 | CT | Eversource |  |  | TBD | Greater Hartford Central Connecticut Project | Loop the Millstone - Manchester (310) 345 kV line into the Card substation | Planned | Planned | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 1079 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115 kV line | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | #VALUE!
Reliability Upgrade | 1a | 1078 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115 kV line | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | #VALUE!
Reliability Upgrade | 1a | 1075 | MA | Eversource |  |  | 2013-12-01 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115 kV line Russell Biomass Plant | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | Part of NEEWS (Greater Springfield Reliability Project) Project ID 687 | #VALUE!
Generator Interconnection Upgrade | 2a | 1062 | MA | National Grid, USA |  |  | 2011-06-01 | Billerica Power | Upgrade #137T and #K-137W 115 kV circuit breakers at Sandy Pond (if not completed as part of Merrimack Valley/North Shore Project). | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1061 | MA | National Grid, USA |  |  | 2011-06-01 | Billerica Power | Replace (16) 115 kV circuit breakers at Tewksbury 22 w/ IPT capability if all generators w/ higher Queue Position are constructed. The quantity of breaker upgrades subject to Queued generators constructed. | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1060 | MA | National Grid, USA |  |  | 2011-06-01 | Billerica Power | Reconductor 2.8 mi. of the M-139 115 kV line. | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1059 | MA | National Grid, USA |  |  | 2011-06-01 | Billerica Power | Re-terminate line tap section (Perry Street) of J-162 Line to new bay position at Tewksbury. | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1058 | MA | National Grid, USA |  |  | 2011-06-01 | Billerica Power | Interconnection to Tewksbury 115 kV Substation via O-193 Line and refurbish section of J-162 line. | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1048 | MA | Eversource |  |  | 2015-06-01 | Cape Wind | Convert Canal 345 kV SPS to include tripping of Cape Wind for the simultaneous loss of 342 and 322 345 kV lines. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1047 | MA | National Grid, USA |  |  | 2019-01-01 | Brockton Power | Replace Bridgewater 115 kV 1631 circuit breaker with 63 kA breaker. | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-03-10 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1046 | MA | National Grid, USA |  |  | 2019-01-01 | Brockton Power | Reconductor 115 kV F19 Line (Auburn - Brockton Tap). | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-03-10 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1044 | MA | Eversource |  |  | 2015-02-01 | Russell BioMass | Upgrade the 1512 line terminal equipment at Southwick Substation. | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 06/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1043 | MA | Eversource |  |  | 2015-02-01 | Russell BioMass | Upgrade the 1768 line terminal equipment at Southwick Substation. | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 06/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 1042 | MA | National Grid, USA |  |  | 2013-06-01 | Queue Position 165 | Replace (2) 345 kV circuit breakers at Sandy Pond | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 1037 | VT | Vermont Electric Power Company | Green Mountain Power |  | 2013-12-01 | Deerfield Wind | Installation of 3-breaker 69 kV ring bus interconnecting to the Bennington-Searsburg 69 kV Y25N line | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2010-06-03 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 1030 | ME | Central Maine Power Company |  |  | 2013-11-01 | Maine Power Reliability Program (MPRP) | New 345/115 kV Autotransformers (Maguire Road) | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1028 | ME | Central Maine Power Company | Eversource |  | 2013-12-01 | Maine Power Reliability Program (MPRP) | Rebuild existing 115 kV Line (Section 250, Maguire Rd-Three Rivers Switching Station) | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 1/29/2010 (CMP) 4/14/2011 (NU) | Portion of CMP $1.32B and portion of NU is TBD | Portion of CMP $1.47B and portion of NU is $36.0M | Portion of CMP $1.47B and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | #VALUE!
Reliability Upgrade | 1a | 1027 |  | Central Maine Power Company |  |  | 2012-12-01 | Maine Power Reliability Program (MPRP) | New 115 kV Line Construction (Raven Farm - East Deering, East Deering -Cape) | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 1026 | ME | Central Maine Power Company | Eversource |  | 2013-11-01 | Maine Power Reliability Program (MPRP) | New 345 kV Line Construction associated with (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Elliot Switching Station) line work | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 1/29/2010 (CMP) 4/14/2011 (NU) | Portion of CMP $1.32B and portion of NU is $36.0M | Portion of CMP $1.47B and portion of NU is $36.0M | Portion of CMP $1.47B and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | #VALUE!
Reliability Upgrade | 1a | 1025 | ME | Central Maine Power Company |  |  | 2015-02-01 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345 kV Kennebec River Crossing 375/377, 115 kV Bucksport 65/205) | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Elective Upgrade | 4b | 1018 | ME | Emera Maine | National Grid, USA |  | 2017-06-01 | Queue Position 509 | 1100 MW HVDC between Orrington substation to Tewksbury substation | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 983 | CT | Eversource |  |  | 2013-06-01 | Towantic Energy | Rebuild 115 kV 1585N Line between new substation and Bunker Hill. | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-26 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 975 | CT | United Illuminating Company |  |  | TBD | SWCT | Pequonnock 115 kV Fault Duty Mitigation. - Phase II | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | 65000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 105000000 | 0
Reliability Upgrade | 1b | 971 | MA | Eversource |  |  | TBD | Greater Boston - Central | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 970 | MA | Eversource |  |  | TBD | Greater Boston - Central | Add a new 345 kV line from Lexington to Waltham. | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 964 | MA | Eversource |  |  | 2011-12-01 | Boston Area 115 kV Enhancements | Relocate 115 kV terminals at W. Walpole to mitigate breaker failure #8. | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | 1500000 | 1500000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 956 | MA | National Grid, USA |  |  | 2016-06-01 | Central/Western Massachusetts Upgrades - Group 7 - Carpenter Hill Autotransformer Upgrade | Carpenter Hill - replace one 345 kV autotransformer with a new autotransformer of 448 MVA and upgrade thermal rating of bus to at least 580 MVA. | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2007-12-17 | No | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 0
Reliability Upgrade | 1a | 954 | MA | National Grid, USA |  |  | 2022-12-01 | Central/Western Massachusetts Upgrades Group - 5 - A-1/B - 2 Projects | Westminster - install new 69 kV breaker, including disconnect switches. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 12/17/2007 | No | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 903909 | 0
Reliability Upgrade | 1a | 953 | MA | National Grid, USA |  |  | 2022-12-01 | Central/Western Massachusetts Upgrades Group - 5 - A-1/B - 2 Projects | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 12/17/2007 | No | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 0
Reliability Upgrade | 1a | 951 | MA | National Grid, USA |  |  | 2022-12-01 | Central/Western Massachusetts Upgrades - Group 5 A-1/B- 2 Projects | Install new Otter River - E Winchendon (H-134) 115 kV line. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 12/17/2007 | No | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 0
Reliability Upgrade | 1a | 950 | MA | National Grid, USA |  |  | 2022-12-01 | Central/Western Massachusetts Upgrades - Group 5 - A-1/B - 2 Projects | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Y-Planned | 12/17/2007 | No | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 0
Reliability Upgrade | 1a | 947 | MA | National Grid, USA |  |  | 2012-12-01 | Central/Western Massachusetts Upgrades | Reconductor 115 kV line from Palmer to new Hampden Substation. | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 12/17/2007 | No | 2632635 | 2632635 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 931 | MA | National Grid, USA |  |  | 2013-01-01 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 12/17/2007 | No | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 0
Reliability Upgrade | 1b | 918 | RI | National Grid, USA |  |  | 2017-12-01 | Greater Rhode Island Transmission Reinforcements | Dexter substation changes | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-04-25 | No | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 917 | MA | National Grid, USA |  |  | 2019-12-01 | Greater Rhode Island Transmission Reinforcements | Bell Rock substation expansion. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-04-25 | No | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 916 | RI | National Grid, USA |  |  | 2017-12-01 | Greater Rhode Island Transmission Reinforcements | Conversion of Jepson 69 kV substation to 115 kV substation | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-04-25 | No | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 915 | RI | National Grid, USA |  |  | 2017-12-01 | Greater Rhode Island Transmission Reinforcements | Reconductor M13 and L14 between Bell Rock and Dexter | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-04-25 | No | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 914 | MA | National Grid, USA |  |  | 2018-12-01 | Greater Rhode Island Transmission Reinforcements | New third circuit between Somerset and Bell Rock. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-04-25 | No | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 913 | MA | National Grid, USA |  |  | 2018-12-01 | Greater Rhode Island Transmission Reinforcements | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-04-25 | No | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 909 | ME | Central Maine Power Company |  |  | 2014-08-01 | Maine Power Reliability Program (MPRP) | Add 2-115 kV breakers & rebuild 86A, new .25 mile transmission at Belfast forming Sections 86 & 266 | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 908 | ME | Central Maine Power Company |  |  | 2014-01-01 | Maine Power Reliability Program (MPRP) | New 345/115 kV Autotransformers (Albion Road, Larrabee Road); Coopers Mills autotransformer replaces Maxcy's autotransformer | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 907 | ME | Central Maine Power Company |  |  | 2014-05-01 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115 kV lines: Sections 86 (Bucksport-Belfast), Section 203 (Detroit-Orrington), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 906 | ME | Central Maine Power Company |  |  | 2014-12-01 | Maine Power Reliability Program (MPRP) | New 115 kV line construction (Orrington-Coopers Mills, Larrabee Road-Middle St,Middle St -Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | #VALUE!
Reliability Upgrade | 1a | 905 | ME | Central Maine Power Company |  |  | 2014-09-01 | Maine Power Reliability Program (MPRP) | New 345 kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | 1320000000 | 1470187000 | 1470187000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 1364108000 | 0
Generator Interconnection Upgrade | 2b | 881 | RI | National Grid, USA | Northeast Utilities |  | 2012-06-01 | Queue Position 201 | RISEP - 345 kV RISE Substation. | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2b | 880 | MA | National Grid, USA | Northeast Utilities |  | 2011-06-01 | Queue Position 177 | Sutton Energy (Project doe not have 1A replaced with QP 177) - 345 kV Carpenter Hill-Millbury Line. | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 825 | MA | Eversource |  |  | TBD | Pittsfield / Greenfield Project | Upgrade the Pleasant to Blandford 115 kV line and the Blandford to Granville Jct. portion of the 115 kV line 1512. | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 824 | MA | Eversource |  |  | TBD | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115 kV line and terminal work at Woodland substation. | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 807 | CT | Eversource |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | Install 480 MVAR's of capacitors at the Montville 345 kV substation | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | 33000000 | 33000000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 801 | CT | Eversource |  |  | TBD |  | Build Manchester to East Hartford 115 kV cable with a series reactor. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 797 | RI | National Grid, USA |  |  | 2015-12-01 | NEEWS (Interstate Reliability Project) | 3361 Upgrade 345 kV terminal equipment at Sherman Road. | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | 8300000 | 8300000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 796 | RI | National Grid, USA |  |  | 2014-12-01 | NEEWS (Interstate Reliability Project) | 347 Reconductor from Sherman Road to CT/RI Border. | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-09-24 | No | 16400000 | 16400000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 793 | MA | National Grid, USA |  |  | 2018-12-01 | Greater Rhode Island Transmission Reinforcements | Somerset Substation Reinforcements | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-04-25 | No | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 792 | RI | National Grid, USA |  |  | 2014-12-01 | Greater Rhode Island Transmission Reinforcements 1 | Admiral St-Franklin Square (Q143 and R144) 115 kV UG recabling. | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-04-25 | No | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 0
Reliability Upgrade | 1b | 791 | MA | National Grid, USA |  |  | 2018-12-01 | Greater Rhode Island Transmission Reinforcements | New 115 kV circuit between Somerset and Brayton Point. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-04-25 | No | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 785 | MA | National Grid, USA |  |  | 2017-07-01 | Merrimack Valley/North Shore Reliability Project | Re-conductor F-158N (Golden Hills-Maplewood-Everett) 115 kV line. | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | 1330000 | 1330000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1a | 775 | MA | National Grid, USA |  |  | 2012-06-01 | Merrimack Valley/North Shore Reliability Project | Addition of 4 breakers and relocation of T1 and T2 into new bays at Sandy Pond. | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2008-06-27 | No | 20100000 | 20100000 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 699 | CT | United Illuminating Company |  |  | 2016-12-01 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 11100000 | 0
Generator Interconnection Upgrade | 2a | 622 | MA | Eversource |  |  | 2015-02-01 | Russell BioMass | Install a 3-breaker ring bus on the 1512 line between Granville Jct. and Elm Substation. Build new line from this new station to the plant | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 06/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 600 | MA | Eversource |  |  | 2015-06-01 | Cape Wind | Installation of differential insulation and additional grounding at each tower that is common for the 342 and 322 345 kV lines. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 599 | MA | Eversource |  |  | 2018-10-01 | Cape Wind | Upgrade the Bourne 115 kV breaker #12272 with an IPT breaker. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 598 | MA | Eversource |  |  | 2018-10-01 | Cape Wind | At Canal 345 kV substation, install a redundant breaker in series with breaker #312. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 596 | MA | Eversource |  |  | 2018-10-01 | Cape Wind | Installation of (2) 115 kV circuits out of Barnstable substation to interconnect Cape Wind. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 10/6/2005 2/11/2014 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Generator Interconnection Upgrade | 2a | 595 | MA | Eversource |  |  | 2018-10-01 | Cape Wind | Expansion of Barnstable 115 kV substation to include a circuit breaker in the fourth bay and a circuit breaker in the fifth bay. Installation of (4) 35 MVAR shunt reactors and (2) capacitor filter banks at the Barnstable 115 kV substation. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 10/6/2005 2/11/2014 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 593 | MA | Eversource |  |  | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Bourne and Barnstable/Falmouth/equivalent | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1a | 576 | CT | Eversource |  |  | 2017 | NEEWS (Central Connecticut Reliability Project) | Build new 345 kV line 3208 North Bloomfield - Frost Bridge. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 9/24/2008 5/4/2012 | No | 313000000 | 338000000 | 338000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 301000000 | 0
Reliability Upgrade | 1b | 325 | VT | Vermont Electric Power Company |  |  | TBD | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | #VALUE!
Reliability Upgrade | 1b | 324 | VT | Vermont Electric Power Company |  |  | TBD |  | Granite to Middlesex 230 kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | No | No | TBD | TBD | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Reliability Upgrade | 1b | 139 | VT | Vermont Electric Power Company |  |  | TBD | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Planned | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled |  | 01/10/2003 | 03/31/2003 | TBD | TBD | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR | #VALUE!
Notes
1 RSP #1815 covers ACL #98.
2 Eversource portion of the project ($3.7M) is added to RSP #1881.
3 On December 10, 2019, FERC accepted Tariff changes that removed the “Concept” category.
Local Project Listing Links | Eversource: |  |  |  | https://www.eversource.com/content/residential/about/transmission-distribution/projects
| Avangrid |  |  |  | https://www.cmpco.com/w/local-system-planning
https://www.uinet.com/documents/d/uinet/avangrid_2025_lsp_topac-presentation_final
| Versant Power |  |  |  | https://www.versantpower.com/docs/default-source/oasis/versant-power-lsp-2025-r0-251021.pdf?sfvrsn=67f9fe8c_1
| VELCO: |  |  |  | https://www.velco.com/sites/default/files/2025-10/VELCO_LSP_2025_Rev1.pdf
| NGRID |  |  |  | https://www.nationalgridus.com/media/oasis/filings-and-studies/national_grid_local_system_plan.pdf
| NHT |  |  |  | https://www.oasis.oati.com/woa/docs/NHT/NHTdocs/NHT_2025_LSP.pdf
| RIE |  |  |  | https://www.oasis.oati.com/woa/docs/RIE/RIEdocs/RIE_Local_System_Plan_2025.pdf
| CMEEC |  |  |  | https://cmeec.com/wp-content/uploads/2025/11/LSP-presentation-2025.pptx
Project Listing - Column Definitions:
The Part #'s designate the "need" category of the project. Original categories are not changed when a project is placed In-service or Cancelled
Part 1 - These projects are Reliability Upgrades
1a: Planned (must be the preferred solution to solve the needs and if required, have I.3.9. approval) or Under construction
1b: Proposed (is supported by a Solutions Study or a Competitive Solution Process)
Part 2 - These projects are Generator Interconnection Upgrades
2a: Planned (I.3.9 approval with Interconnection Agreement) or Under Construction
2b: Proposed (I.3.9 approval but without Interconnection Agreement)
Part 3 - These projects are Market Efficiency Upgrades
3a: Planned (must be the preferred solution to solve the needs and have I.3.9. approval) or Under construction
3b: Proposed (is supported by a Competitive Solution Process)
Part 4 - These projects may be promoted by any entity electing to support the cost of transmission changes. The entity sponsoring the changes will have their own justification for their actions
4a: Planned (I.3.9 approval with Interconnection Agreement) or Under construction
4b: Proposed (I.3.9 approval but without Interconnection Agreement)

## Boston 2033
Primary Driver | Part# | Project ID | State | Primary Equipment Owner | Other Equipment Owner(s) | Footnote Number | Projected In-Service Month/Year | Major Project | Project | Oct-10 Status | Apr-11 Status | Jun-11 Status | Nov-11 Status | Mar-12 Status | Jun-12 Status | Oct-12 Status | Mar-13 Status | Jun-13 Status | Oct-13 Status | Mar-14 Status | Jun-14 Status | Oct-14 Status | Mar-15 Status | Jun-15 Status | Oct-15 Status | Mar-16 Status | Jun-16 Status | Oct-16 Status | Mar-17 Status | Jun-17 Status | Oct-17 Status | Mar-18 Status | Jun-18 Status | Oct-18 Status | Mar-19 Status | Jun-19 Status | Oct-19 Status | Mar-20 Status | Jun-20 Status | Oct-20 Status | Mar-21 Status | Jun-21 Status | Oct-21 Status | Mar-22 Status | Jun-22 Status | Oct-22 Status | Mar-23 Status | Jun-23 Status | Oct-23 Status | Mar-24 Status | Jun-24 Status | Oct-24 Status | Mar-25 Status | Jun-25 Status | Oct-25 Status | Mar-26 Status | Jun-26 Status | Is the project Grandfathered on May 18, 2015 (not updated since March 2017) | PPA (I.3.9) Approval | TCA Approval | Oct-10 Estimated PTF Costs | Apr-11 Estimated PTF Costs | Jun-11 Estimated PTF Costs | Nov-11 Estimated PTF Costs | Mar-12 Estimated PTF Costs | Jun-12 Estimated PTF Costs | Oct-12 Estimated PTF Costs | Mar-13 Estimated PTF Costs | Jun-13 Estimated PTF Costs | Oct-13 Estimated PTF Costs | Mar-14 Estimated PTF Costs | Jun-14 Estimated PTF Costs | Oct-14 Estimated PTF Costs | Mar-15 Estimated PTF Costs | Jun-15 Estimated PTF Costs | Oct-15 Estimated PTF Costs | Mar-16 Estimated PTF Costs | Jun-16 Estimated PTF Costs | Oct-16 Estimated PTF Costs | Mar-17 Estimated PTF Costs | Jun-17 Estimated PTF Costs | Oct-17 Estimated PTF Costs | Mar-18 Estimated PTF Costs | Jun-18 Estimated PTF Costs | Oct-18 Estimated PTF Costs | Mar-19 Estimated PTF Costs | Jun-19 Estimated PTF Costs | Oct-19 Estimated PTF Costs | Mar-20 Estimated PTF Costs | Jun-20 Estimated PTF Costs | Oct-20 Estimated PTF Costs | Mar-21 Estimated PTF Costs | Jun-21 Estimated PTF Costs | Oct-21 Estimated PTF Costs | Mar-22 Estimated PTF Costs | Jun-22 Estimated PTF Costs | Oct-22 Estimated PTF Costs | Mar-23 Estimated PTF Costs | Jun-23 Estimated PTF Costs | Oct-23 Estimated PTF Costs | Mar-24 Estimated PTF Costs | Jun-24 Estimated PTF Costs | Oct-24 Estimated PTF Costs | Mar-25 Estimated PTF Costs | Jun-25 Estimated PTF Costs | Oct-25 Estimated PTF Costs | Mar-26 Estimated PTF Costs | Jun-26 Estimated PTF Costs
Reliability Upgrade | 1b | 1934 | MA | Eversource |  |  | 2027-03-01 | Boston 2033 Solutions Study | Protection systems modification associated with the Stoughton RAS at three 345 kV substations (Stoughton, West Walpole and Holbrook) and two 115 kV substations (Hyde Park and K-Street) | [44 empty] | Proposed | Proposed | Proposed | Proposed |  | No | No | [44 empty] | 3700000 | 3700000 | 3700000 | 3700000
Reliability Upgrade | 1b | 1933 | MA | Eversource |  |  | 2028-12-01 | Boston 2033 Solutions Study | Install one 80 MVAR shunt reactor at the 115 kV Electric Avenue Substation | [44 empty] | Proposed | Proposed | Proposed | Proposed |  | No | No | [44 empty] | 22300000 | 22300000 | 22300000 | 22300000
[107 empty] | 26000000 | 26000000

## UME 2029
Primary Driver | Part# | Project ID | State | Primary Equipment Owner | Other Equipment Owner(s) | Footnote Number | Projected In-Service Month/Year | Major Project | Project | Oct-10 Status | Apr-11 Status | Jun-11 Status | Nov-11 Status | Mar-12 Status | Jun-12 Status | Oct-12 Status | Mar-13 Status | Jun-13 Status | Oct-13 Status | Mar-14 Status | Jun-14 Status | Oct-14 Status | Mar-15 Status | Jun-15 Status | Oct-15 Status | Mar-16 Status | Jun-16 Status | Oct-16 Status | Mar-17 Status | Jun-17 Status | Oct-17 Status | Mar-18 Status | Jun-18 Status | Oct-18 Status | Mar-19 Status | Jun-19 Status | Oct-19 Status | Mar-20 Status | Jun-20 Status | Oct-20 Status | Mar-21 Status | Jun-21 Status | Oct-21 Status | Mar-22 Status | Jun-22 Status | Oct-22 Status | Mar-23 Status | Jun-23 Status | Oct-23 Status | Mar-24 Status | Jun-24 Status | Oct-24 Status | Mar-25 Status | Jun-25 Status | Oct-25 Status | Mar-26 Status | Jun-26 Status | Is the project Grandfathered on May 18, 2015 (not updated since March 2017) | PPA (I.3.9) Approval | TCA Approval | Oct-10 Estimated PTF Costs | Apr-11 Estimated PTF Costs | Jun-11 Estimated PTF Costs | Nov-11 Estimated PTF Costs | Mar-12 Estimated PTF Costs | Jun-12 Estimated PTF Costs | Oct-12 Estimated PTF Costs | Mar-13 Estimated PTF Costs | Jun-13 Estimated PTF Costs | Oct-13 Estimated PTF Costs | Mar-14 Estimated PTF Costs | Jun-14 Estimated PTF Costs | Oct-14 Estimated PTF Costs | Mar-15 Estimated PTF Costs | Jun-15 Estimated PTF Costs | Oct-15 Estimated PTF Costs | Mar-16 Estimated PTF Costs | Jun-16 Estimated PTF Costs | Oct-16 Estimated PTF Costs | Mar-17 Estimated PTF Costs | Jun-17 Estimated PTF Costs | Oct-17 Estimated PTF Costs | Mar-18 Estimated PTF Costs | Jun-18 Estimated PTF Costs | Oct-18 Estimated PTF Costs | Mar-19 Estimated PTF Costs | Jun-19 Estimated PTF Costs | Oct-19 Estimated PTF Costs | Mar-20 Estimated PTF Costs | Jun-20 Estimated PTF Costs | Oct-20 Estimated PTF Costs | Mar-21 Estimated PTF Costs | Jun-21 Estimated PTF Costs | Oct-21 Estimated PTF Costs | Mar-22 Estimated PTF Costs | Jun-22 Estimated PTF Costs | Oct-22 Estimated PTF Costs | Mar-23 Estimated PTF Costs | Jun-23 Estimated PTF Costs | Oct-23 Estimated PTF Costs | Mar-24 Estimated PTF Costs | Jun-24 Estimated PTF Costs | Oct-24 Estimated PTF Costs | Mar-25 Estimated PTF Costs | Jun-25 Estimated PTF Costs | Oct-25 Estimated PTF Costs | Mar-26 Estimated PTF Costs | Jun-26 Estimated PTF Costs
Reliability Upgrade | 1a | 1914 | ME | Versant Power |  |  | 2026-12-01 | UME 2029 Solutions | Install a new 80 MVAR reactor, reconfigure the existing two reactors at the 345 kV Orrington substation | [40 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction |  | 2024-04-23 | 2026-02-13 | [40 empty] | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000
Reliability Upgrade | 1a | 1888 | ME | Versant Power |  |  | 2024-07-01 | UME 2029 Solutions | Install a 10 MVAR reactor at Keene Road 115 kV substation | [33 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service |  | 2022-02-16 | 2026-02-13 | [33 empty] | 6000000 | 6000000 | 6000000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000
Reliability Upgrade | 1a | 1887 | ME | Versant Power |  |  | 2024-10-30 | UME 2029 Solutions | Install a 25 MVAR reactor at Boggy Brook 115 kV substation | [33 empty] | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service |  | 2022-02-16 | 2026-02-13 | [33 empty] | 3400000 | 3400000 | 3400000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000 | 4000000
Reliability Upgrade | 1a | 1886 | ME | Versant Power |  |  | 2025-08-01 | UME 2029 Solutions | Install a +50/-25 MVAR synchronous condenser at Boggy Brook 115 kV substation, and install a new 115 kV breaker to separate Line 67 from the proposed solution elements | [33 empty] | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service |  | 2022-02-16 | 2026-02-13 | [33 empty] | 35500000 | 35500000 | 35500000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 40000000 | 25900000 | 25900000 | 25900000 | 25900000 | 25900000 | 25900000
Reliability Upgrade | 1a | 1885 | ME | Central Maine Power Company |  |  | 2029-12-31 | UME 2029 Solutions | Install a +50/-25 MVAR synchronous condenser at Highland 115 kV substation | [33 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2023-08-29 | No | [33 empty] | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000 | 17500000
Reliability Upgrade | 1a | 1884 | ME | Central Maine Power Company |  |  | 2029-12-31 | UME 2029 Solutions | Install a 15 MVAR capacitor at Belfast 115 kV substation | [33 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2023-08-29 | No | [33 empty] | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000 | 5300000
Reliability Upgrade | 1a | 1883 | ME | Central Maine Power Company |  |  | 2028-12-31 | UME 2029 Solutions | Convert the Highland 115 kV substation to an eight breaker, breaker-and-a-half configuration with a bus connected 115/34.5 kV transformer | [33 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned |  | 2023-08-29 | No | [33 empty] | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000
Reliability Upgrade | 1a | 1882 | ME | Central Maine Power Company |  |  | 2024-08-01 | UME 2029 Solutions | Rebuild 21.7 miles of the existing 115 kV line Section 80 Highland – Coopers Mills 115 kV line | [33 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service |  | 2022-05-24 | No | [33 empty] | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000 | 63600000
[106 empty] | 150800000 | 150800000 | 150800000

## SEMARI
Primary Driver | Part# | Project ID | State | Primary Equipment Owner | Other Equipment Owner(s) | Footnote Number | Projected In-Service Month/Year | Major Project | Project | Oct-10 Status | Apr-11 Status | Jun-11 Status | Nov-11 Status | Mar-12 Status | Jun-12 Status | Oct-12 Status | Mar-13 Status | Jun-13 Status | Oct-13 Status | Mar-14 Status | Jun-14 Status | Oct-14 Status | Mar-15 Status | Jun-15 Status | Oct-15 Status | Mar-16 Status | Jun-16 Status | Oct-16 Status | Mar-17 Status | Jun-17 Status | Oct-17 Status | Mar-18 Status | Jun-18 Status | Oct-18 Status | Mar-19 Status | Jun-19 Status | Oct-19 Status | Mar-20 Status | Jun-20 Status | Oct-20 Status | Mar-21 Status | Jun-21 Status | Oct-21 Status | Mar-22 Status | Jun-22 Status | Oct-22 Status | Mar-23 Status | Jun-23 Status | Oct-23 Status | Mar-24 Status | Jun-24 Status | Oct-24 Status | Mar-25 Status | Jun-25 Status | Oct-25 Status | Mar-26 Status | Jun-26 Status | Is the project Grandfathered on May 18, 2015 (not updated since March 2017) | PPA (I.3.9) Approval | TCA Approval | Oct-10 Estimated PTF Costs | Apr-11 Estimated PTF Costs | Jun-11 Estimated PTF Costs | Nov-11 Estimated PTF Costs | Mar-12 Estimated PTF Costs | Jun-12 Estimated PTF Costs | Oct-12 Estimated PTF Costs | Mar-13 Estimated PTF Costs | Jun-13 Estimated PTF Costs | Oct-13 Estimated PTF Costs | Mar-14 Estimated PTF Costs | Jun-14 Estimated PTF Costs | Oct-14 Estimated PTF Costs | Mar-15 Estimated PTF Costs | Jun-15 Estimated PTF Costs | Oct-15 Estimated PTF Costs | Mar-16 Estimated PTF Costs | Jun-16 Estimated PTF Costs | Oct-16 Estimated PTF Costs | Mar-17 Estimated PTF Costs | Jun-17 Estimated PTF Costs | Oct-17 Estimated PTF Costs | Mar-18 Estimated PTF Costs | Jun-18 Estimated PTF Costs | Oct-18 Estimated PTF Costs | Mar-19 Estimated PTF Costs | Jun-19 Estimated PTF Costs | Oct-19 Estimated PTF Costs | Mar-20 Estimated PTF Costs | Jun-20 Estimated PTF Costs | Oct-20 Estimated PTF Costs | Mar-21 Estimated PTF Costs | Jun-21 Estimated PTF Costs | Oct-21 Estimated PTF Costs | Mar-22 Estimated PTF Costs | Jun-22 Estimated PTF Costs | Oct-22 Estimated PTF Costs | Mar-23 Estimated PTF Costs | Jun-23 Estimated PTF Costs | Oct-23 Estimated PTF Costs | Mar-24 Estimated PTF Costs | Jun-24 Estimated PTF Costs | Oct-24 Estimated PTF Costs | Mar-25 Estimated PTF Costs | Jun-25 Estimated PTF Costs | Oct-25 Estimated PTF Costs | Mar-26 Estimated PTF Costs | Jun-26 Estimated PTF Costs
Reliability Upgrade | 1a | 1790 | MA | Eversource |  |  | 2020-11-01 | Southeast Massachusetts/Rhode Island Reliability Project | Medway 115 kV Circuit Breaker Replacements | [24 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-05-01 | No | [24 empty] | 4865000 | 4865000 | 4865000 | 4865000 | 4865000 | 4865000 | 4865000 | 4865000 | 4865000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000 | 2256000
Reliability Upgrade | 1a | 1789 | MA | Eversource |  |  | 2021-04-01 | Southeast Massachusetts/Rhode Island Reliability Project | West Medway 345 kV circuit breaker upgrades | [24 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-05-01 | No | [24 empty] | 6309000 | 6309000 | 6309000 | 6309000 | 6309000 | 6309000 | 6309000 | 6309000 | 6309000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000 | 2947000
Reliability Upgrade | 1a | 1782 | RI | National Grid, USA |  |  | 2022-05-01 | Southeast Massachusetts/Rhode Island Reliability Project | Reconductor the J16S line | [23 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [23 empty] | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000 | 2189000
Reliability Upgrade | 1a | 1742 | RI | National Grid, USA |  |  | 2020-10-01 | Southeast Massachusetts/Rhode Island Reliability Project | Remote terminal station work (Wampanoag and Pawtucket 115 kV) for new 115 kV Grand Army GIS switching station to tie the E-183E, F-184, X3 and W4 lines (associated with RSP 1714) | [20 empty] | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [20 empty] | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000
Reliability Upgrade | 1a | 1741 | MA | Middleborough Gas and Electric |  |  | 2019-04-01 | Southeast Massachusetts/Rhode Island Reliability Project | Rebuild the Middleborough Gas and Electric (MGED) portion of the E1 line from Bridgewater to Middleborough (2.5 miles) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623 | 3303623
Reliability Upgrade | 1a | 1737 | MA | Eversource |  |  | 2020-08-01 | Southeast Massachusetts/Rhode Island Reliability Project | Replace disconnect switches 107A, 107B, 108A and 108B on Line 323 at West Medway Substation #446. Replace 8 line structures with taller structures | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 200000 | 200000 | 200000 | 200000 | 2064000 | 2064000 | 2064000 | 2064000 | 2064000 | 2064000 | 2064000 | 2064000 | 2064000 | 2064000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000 | 1929000
Reliability Upgrade | 1a | 1736 | MA | Eversource |  |  | 2018-10-01 | Southeast Massachusetts/Rhode Island Reliability Project | Reconductor the 108 line from Bourne Substation #917 to Horse Pond Tap | [19 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 5/4/2017 12/20/2018 | No | [19 empty] | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 2756000 | 2756000 | 2756000 | 2756000 | 2756000 | 2756000 | 2756000 | 2756000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000 | 3159000
Reliability Upgrade | 1a | 1734 | MA | Eversource |  |  | 2018-06-01 | Southeast Massachusetts/Rhode Island Reliability Project | Reconductor/Upgrade 112 Line Tremont Substation #713 to Industrial Tap and terminal equipment | [19 empty] | Proposed | Proposed | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2017-05-04 | No | [19 empty] | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000 | 5407000
Reliability Upgrade | 1a | 1732 | MA | Eversource |  |  | 2025-11-01 | Southeast Massachusetts/Rhode Island Reliability Project | Loop 201-502 line into Medway #65 Substation to form the 201-502N and 201-502S lines | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 7800000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 27000000 | 22684000 | 22684000
Reliability Upgrade | 1a | 1731 | MA | Eversource |  |  | 2021-12-01 | Southeast Massachusetts/Rhode Island Reliability Project | Install 35.3 MVAR 115 kV capacitors at High Hill Substation #644 and Wing Lane Substation #624 | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 2900000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000 | 8127000
Reliability Upgrade | 1a | 1730 | MA | Eversource |  |  | 2026-12-01 | Southeast Massachusetts/Rhode Island Reliability Project | Extend the 115 kV 114 line from Eversource/National Grid border to Industrial Park Tap | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | No | 2018-04-30 | No | [19 empty] | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 16200000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000 | 34285000
Reliability Upgrade | 1a | 1729 | MA | Eversource |  |  | 2023-08-01 | Southeast Massachusetts/Rhode Island Reliability Project | Install a new bay position at Kingston for Carver line | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 2700000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000
Reliability Upgrade | 1a | 1728 | MA | Eversource |  |  | 2023-08-01 | Southeast Massachusetts/Rhode Island Reliability Project | Build a new Carver to Kingston 115 kV line and Carver terminal | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 19600000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000 | 29700000
Reliability Upgrade | 1a | 1727 | MA | Eversource |  |  | 2021-11-01 | Southeast Massachusetts/Rhode Island Reliability Project | Retire Barnstable SPS | [19 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2017-05-04 | No | [19 empty] | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 200000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000
Reliability Upgrade | 1a | 1726 | MA | Eversource |  |  | 2021-12-01 | Southeast Massachusetts/Rhode Island Reliability Project | Separate the 135/122 DCT lines - West Barnstable to Barnstable | [19 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2017-05-04 | No | [19 empty] | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 7400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000 | 10230000
Reliability Upgrade | 1a | 1725 | MA | Eversource |  |  | 2024-05-01 | Southeast Massachusetts/Rhode Island Reliability Project | Build a new Bourne #917 to West Barnstable #921 115 kV line and associated terminal work | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 59100000 | 59100000 | 59100000 | 59100000 | 59100000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000 | 52324000
Reliability Upgrade | 1a | 1724 | RI | National Grid, USA |  |  | 2022-03-01 | Southeast Massachusetts/Rhode Island Reliability Project | Kent County T3 345/115 kV transformer replacement | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 8100000 | 8100000 | 8100000 | 8100000 | 8100000 | 8100000 | 8100000 | 8100000 | 4714000 | 4714000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 5850000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000 | 6224000
Reliability Upgrade | 1a | 1722 | MA | National Grid, USA |  |  | 2026-12-01 | Southeast Massachusetts/Rhode Island Reliability Project | Extend Line 114 - Dartmouth town line (Eversource- NGRID border) to Bell Rock (~4.2 miles) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | No | 2018-04-30 | No | [19 empty] | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 12300000 | 13944000 | 13944000 | 13944000 | 13944000 | 13944000 | 13944000 | 13944000 | 13944000 | 13944000 | 13944000 | 22616000 | 22616000 | 22616000 | 22616000 | 22616000
Reliability Upgrade | 1a | 1721 | MA | National Grid, USA |  |  | 2023-08-01 | Southeast Massachusetts/Rhode Island Reliability Project | Reconfigure Bell Rock to breaker and a half station, and upgrade to BPS standards, split M13 line at Bell Rock and terminate 114 line at Bell Rock. Install new breaker in series with N12/D21 tie breaker, upgrade D21 line switch and install 37.5 MVAR capacitor. | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 4/30/2018 12/20/2018 | No | [19 empty] | 18900000 | 18900000 | 18900000 | 18900000 | 18900000 | 18900000 | 18900000 | 18900000 | 18900000 | 18900000 | 30800000 | 30800000 | 30800000 | 30800000 | 30800000 | 30800000 | 30800000 | 30800000 | 35500000 | 35500000 | 36180000 | 36180000 | 36180000 | 36180000 | 36180000 | 36180000 | 36180000 | 36180000 | 36180000
Reliability Upgrade | 1a | 1720 | MA | National Grid, USA |  |  | 2027-03-01 | Southeast Massachusetts/Rhode Island Reliability Project | Separate N12/M13 DCT & reconductor N12 & M13 between Somerset and Bell Rock (~3.5 miles) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | No | 10/24/2023 4/30/2018 | No | [19 empty] | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 39000000 | 80000000 | 101120000 | 101120000 | 101120000 | 101120000 | 101120000 | 101120000 | 101120000 | 101120000 | 101120000 | 101120000
Reliability Upgrade | 1a | 1718 | MA | National Grid, USA |  |  | 2022-03-01 | Southeast Massachusetts/Rhode Island Reliability Project | Robinson Ave 115 kV circuit breaker addition and reterminate Q10 line | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 1039000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000 | 2000000
Reliability Upgrade | 1a | 1717 | MA | National Grid, USA |  |  | 2019-11-01 | Southeast Massachusetts/Rhode Island Reliability Project | Separate X3/W4 DCT and reconductor X3, W4 lines between Somerset and Grand Army (~2.7 miles each). Reconfigure Y2 and Z1 | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 14600000 | 14600000 | 14900000 | 14900000 | 14900000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 15230000 | 16196000 | 16196000 | 16196000 | 16196000 | 16196000 | 16196000 | 16196000
Reliability Upgrade | 1a | 1716 | MA | National Grid, USA |  |  | 2019-11-01 | Southeast Massachusetts/Rhode Island Reliability Project | Increase clearances on E-183E & F-184 lines between Brayton Point & Grand Army (~1.5 miles each) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 3400000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4206000 | 4283000 | 4283000 | 4283000 | 4283000 | 4283000 | 4283000 | 4283000 | 4283000
Reliability Upgrade | 1a | 1715 | MA | National Grid, USA |  |  | 2020-10-01 | Southeast Massachusetts/Rhode Island Reliability Project | Upgrades at Brayton Point (new 115 kV breaker, new 345/115 kV transformer and upgrades to E183E, F184 station equipment) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 13100000 | 13100000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 15381000 | 15381000 | 15381000 | 15381000 | 15381000 | 15381000 | 15381000 | 15381000 | 15381000 | 15644000 | 15644000 | 15644000 | 15644000 | 15644000 | 15644000 | 15644000 | 15644000
Reliability Upgrade | 1a | 1714 | MA | National Grid, USA |  |  | 2020-10-01 | Southeast Massachusetts/Rhode Island Reliability Project | New Grand Army 115 kV GIS switching station built to BPS standards, remote terminal station work (Brayton Point and Somerset) & loop E-183E, F-184, X3 and W4 lines (associated with RSP 1742) | [19 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2018-04-30 | No | [19 empty] | 43800000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 44920000 | 52080000 | 52080000 | 52080000 | 52080000 | 52080000 | 52080000 | 52080000 | 52080000 | 52080000 | 51919000 | 51919000 | 51919000 | 51919000 | 51919000 | 51919000 | 51919000 | 51919000
[106 empty] | 445238623 | 440922623 | 440922623

## ISO-NE Project Listing Upd copy (hidden)
April '10 ISO-NEW ENGLAND Project Listing Update (DRAFT)
Primary Driver | Part# | Project ID | Primary Equipment Owner | Other Equipment Owner(s) | Projected In-Service Month/Year | Major Project | Project | Oct-07 Status | Apr-08 Status | Jul-08 Status | Oct-08 Status | Apr -09 Status | Jul-09 Status | Oct-09 Status | Apr-10 Status | PPA (I.3.9) Approval | TCA Approval | Oct-07 Estimated Costs | Apr-08 Estimated PTF Costs | Jul-08 Estimated PTF Costs | Oct-08 Estimated PTF Costs | Apr-09 Estimated PTF Costs | Jul-09 Estimated PTF Costs | Oct-09 Estimated PTF Costs | Apr-10 Estimated PTF Costs | Column T | DELTA | Status Change
TABLE A | [26 empty] | Column T - Column S
MAINE
Reliability Upgrade | 1a | 144 | Bangor Hydro-Electric Company |  | 12/2010 | Keene Rd Autotransformer | Installation of a 345/115 kV autotransformer at Keene Rd Substation. | Concept | Concept | Concept | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | No | No | 20000000 | 20000000 | 20000000 | 20000000 | 29000000 | 29000000 | 29000000 | 29000000 | 29000000 | 0 | 0
Reliability Upgrade | 1a | 625 | Central Maine Power Company |  | 04/2010 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Rumford Industrial Park capacitor bank. | Proposed | Concept | Planned | Planned | Planned | Planned | Under Construction | Under Construction | 2007-11-30 | No | TBD | TBD | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 0 | 0
Reliability Upgrade | 1a | 1128 | Central Maine Power Company |  | 07/2010 | CMP-LSP Hotel Road Substation | Add 115/34kV transformer with 115kV breaker at Hotel Rd. |  |  |  |  | Planned | Planned | Planned | Planned | 2008-08-20 | NR | TBD | TBD | Portion of 5,400,000 (above) |  | 800000 | 800000 | 800000 | 800000 | 800000 | 0 | 0
Reliability Upgrade | 1a | 624 | Central Maine Power Company |  | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (New Page - Rumford Industrial Park) | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2007-11-30 | No | TBD | TBD | Portion of 5,400,000 (above) | Portion of 5,400,000 (above) | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 |  | 0
Reliability Upgrade | 1a | 905 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-07-31 | 2010-01-29 | TBD | TBD | 1354000000 | 1354000000 | 1510000000 | 1510000000 | 1510000000 | 1510000000 | 1510000000 | 0 | 0
Reliability Upgrade | 1a | 906 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Coopers Mills-Highland, Larrabee Road-Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | 0
Reliability Upgrade | 1a | 907 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 84 (Albion Road-Coopers Mills), Section 203 (Detroit-Orrington), Section 80 (Coopers Mills-Highland), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | 0
Reliability Upgrade | 1a | 908 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road) | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | 0
Reliability Upgrade | 1a | 909 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | 0
Reliability Upgrade | 1a | 1025 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377 & Maine Yankee 375/392, 115kV Bucksport 65/205) and Maine Yankee 345 kV re-termination | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | 0
Reliability Upgrade | 1a | 1026 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Three Rivers) | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | $70,000,000 (NU portion of MPRP) | $70,000,000 (NU portion of MPRP) | Portion of CMP $1.51B and portion of NU is $35.1M | Portion of CMP $1.51B and portion of NU is $35.1M | Portion of CMP $1.51B and portion of NU is $35.1M | Portion of CMP $1.51B and portion of NU is $36.0M | 36000000 | 900000 | 0
Reliability Upgrade | 1a | 1027 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV Line Construction (Elm Street-East Deering, East Deering -Cape) | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | 0
Reliability Upgrade | 1a | 1028 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Portion of CMP $1.354B and portion of NU $70M | Portion of CMP $1.354B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD |  | 0
Reliability Upgrade | 1a | 1029 | Central Maine Power Company |  | 11/2010 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformer at South Gorham | Concept | Concept | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | 0
Reliability Upgrade | 1a | 1158 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Two 40 MVAR reactors at Albion Road, two 40 MVAR reactors at Larabee Road, two 40 MVAR at Coopers Mills | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | 0
Reliability Upgrade | 1a | 1030 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Raven Farm, Maguire Road) | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | 0
Reliability Upgrade | 1a | 143 | Bangor Hydro-Electric Company |  | 12/2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation to Harrington Substation. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2006-05-10 | 2008-06-13 | 45000000 | 66100000 | 66100000 | 66100000 | 66100000 | 66100000 | 66100000 | 66100000 | 66100000 | 0 | 0
Reliability Upgrade | 1a | 1129 | Central Maine Power Company |  | 05/2012 |  | New 115kV line between Wyman Hydro and Heywood Rd. parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | Concept | Concept |  | Planned | Planned | Planned | Planned | 2009-01-26 | No | 10100000 | 10100000 | 6100000 |  | 19500000 | 19500000 | 19500000 | 32800000 | 32800000 | 13300000 | 0
Reliability Upgrade | 1a | 1144 | Central Maine Power Company |  | 09/2010 | Heywood Road Project | Circuit switcher replacements at Detroit, Lakewood, Rice Rips and Winslow | Concept | Concept | Concept | Concept |  | Under Construction | Under Construction | Under Construction | 2009-03-20 | 2009-07-20 | TBD | TBD | TBD | TBD |  | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of the Heywood Road Project |  | 1
Generator Interconnection Upgrade | 2a | 770 | Central Maine Power Company |  | 12/2010 | Queue Position 137 | Installation of New Page Substation (aka Railroad Street Substation) with (3) circuit breakers tapping Section 218 115kV. | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | 2007-03-18 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1159 | Central Maine Power Company |  | 07/2010 | Queue Position 197 | Add a new 115kV breaker and new 115kV line termination at the former T2 position at Rumford 115kV substation | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed |  | Planned | 2009-09-29 | NR | NR | NR | NR | NR | NR | NR |  | NR | NR |  | 0
NEW HAMPSHIRE | [27 empty] | 0
Reliability Upgrade | 1a | 277 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Proposed | Concept | Concept | Concept | Concept | Planned | Planned | Planned | 2009-06-29 | No | TBD | TBD | TBD | TBD | TBD | 56600000 | 56600000 | 56000000 | 56000000 | -600000 | 1
Reliability Upgrade | 1a | 1137 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115kV breakers and add 1-115kV breaker at Deerfield Substation | [5 empty] | Planned | Planned | Planned | 2009-06-29 | No | TBD | TBD | TBD | TBD |  | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project |  | 1
Reliability Upgrade | 1a | 1138 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rebuild 115kV L175 line | [5 empty] | Planned | Planned | Planned | 2009-06-29 | No | TBD | TBD | TBD | TBD |  | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project |  | 1
Reliability Upgrade | 1a | 1139 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV M183 Line | [5 empty] | Planned | Planned | Planned | 2009-06-29 | No | TBD | TBD | TBD | TBD |  | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project |  | 1
Reliability Upgrade | 1a | 1140 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | [5 empty] | Planned | Planned | Planned | 2009-06-29 | No | TBD | TBD | TBD | TBD |  | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project |  | 1
Reliability Upgrade | 1a | 1141 | Northeast Utilities |  | 2015 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | [5 empty] | Planned | Planned | Planned | 2009-06-29 | No | TBD | TBD | TBD | TBD |  | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project |  | 1
Reliability Upgrade | 1a | 680 | National Grid, USA |  | 03/2013 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2008-01-28 | No | 11497000 | 11497000 | 11497000 | 11497000 | 11497000 | 11497000 | 7393000 | 7393000 | 7393000 | 0 | 0
Reliability Upgrade | 1a | 674 | National Grid, USA |  | 12/2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-01 | No | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 7720000 | 22115000 | 22115000 | 14395000 | 0
Elective | 4a | 1142 | FPL New England Division |  | 04/2011 |  | Seabrook Station Reconfiguration and Circuit Breaker addition Stage s 1 & 2 | Concept | Concept | Concept | Concept |  | Planned | Planned | Planned | 2008-11-20 | NR | TBD | TBD | TBD | TBD |  | TBD | NR | TBD | TBD |  | 1
Generator Interconnection Upgrade | 2a | 724 | National Grid, USA |  | TBD | NGRID Comerford Substation | NGRID Comerford Substation. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2007-06-12 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
VERMONT | [27 empty] | 0
Reliability Upgrade | 1a | 139 | Vermont Electric Power Company |  | 12/2015 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Under Construction | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 01/10/2003 | 03/31/2003 | 11000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 0 | 0
Reliability Upgrade | 1a | 1145 | Vermont Electric Power Company |  | 12/2010 | Burlington Gorge Project | Installation of a 3-breaker 115kV ring substation and 115/34.5kV transformer on the East Ave. - Tafts Coners 115kV line | Planned | Planned | Planned | Planned | Under Construction |  | Planned | Planned | 10/24/2006 | No | 30000000 | 25142000 | 25142000 | 25142000 | 25142000 |  | 14000000 | 14000000 | 14000000 | 0 | 1
Reliability Upgrade | 1a | 323 | Vermont Electric Power Company |  | 12/2010 | Vermont Southern Loop Project | New VY - Newfane - Coolidge 345 kV line with requisite station upgrades. | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | 2008-10-01 | No | 200000000 | 135300000 | 135300000 | 135300000 | 136368000 | 136368000 | 136368000 | 136368000 | 136368000 | 0 | 0
Reliability Upgrade | 1a | 1032 | Vermont Electric Power Company |  | 09/2010 | Vermont Southern Loop Project | Installation of a new 345/115kV substation called Vernon including a new 345/115kV autotransformer | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | 2008-10-01 | No | Part of Vermont Southern Loop Project | 64600000 | 64600000 | 64600000 | 69815000 | 69815000 | 69815000 | 69815000 | 69815000 | 0 | 0
Reliability Upgrade | 1a | 1033 | Vermont Electric Power Company |  | 12/2010 | Vermont Southern Loop Project (VELCO LSP - Newfane Substation) | Installation of a new 345/115kV substation called Newfane | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | 2008-10-01 | No | Part of Vermont Southern Loop Project | 38500000 | 38500000 | 38500000 | 16664000 | 16664000 | 16664000 | 16664000 | 16664000 | 0 | 0
Reliability Upgrade | 1a | 1034 | Vermont Electric Power Company |  | 12/2010 | Vermont Southern Loop Project | Loop new 345kV Line into Newfane Substation. | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | 2008-10-01 | No | Part of Vermont Southern Loop Project | 18000000 | 18000000 | 18000000 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 |  | 0
Reliability Upgrade | 1a | 1035 | Vermont Electric Power Company |  | 12/2010 | Vermont Southern Loop Project | Expansion of Coolidge 345kV substation | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | 2008-10-01 | No | Part of Vermont Southern Loop Project | 18000000 | 18000000 | 18000000 | 20117000 | 20117000 | 20117000 | 20117000 | 20117000 | 0 | 0
Reliability Upgrade | 1a | 1146 | Vermont Electric Power Company |  | 02/2011 | Lyndonville Project | Installation of a 4-breaker ring 115 kV substation consisting of two 115kV 12.5 MVAR capacitor banks and 115/34.5 kV transformer interconnecting to the Irasburg - St. Johnsbury 115kV line | Proposed | Proposed | Proposed | Planned | Under Construction |  | Planned | Planned | 2009-06-01 | No | Part of Vermont Southern Loop Project | 18000000 | 18000000 | 18000000 | 20117000 |  | 9000000 | 9000000 | 9000000 | 0 | 1
Generator Interconnection Upgrade | 2a | 1036 | Vermont Electric Power Company |  | 10/2010 | Queue Position 172 | Installation of 3-breaker 115kV ring bus interconnection of the St. Johnsbury-Irasburg 115kV K39 line. |  | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | 08/16/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
MASSACHUSETTS | [27 empty] | 0
Reliability Upgrade | 1a | 1152 | National Grid, USA |  | 2010-08-01 |  | Bear Swamp - Pratts Jumction 230kV Line Refurbishment Project (E205E) |  |  | Proposed | Planned | Planned |  | Planned | Planned | NR | NR |  |  | TBD | 360000 | 360000 |  | 43596000 | 43596000 | 43596000 | 0 | 1
Reliability Upgrade | 1a | 887 | National Grid, USA |  | 09/2012 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Proposed | Concept | Concept | Planned | Planned | Planned | Planned | Planned | 2008-01-28 | No | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 76000000 | 76000000 | 46000000 | 0
Reliability Upgrade | 1a | 921 | National Grid, USA |  | 06/2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Proposed | Concept | Concept | Planned | Planned | Planned | Planned | Planned | 2008-01-28 | No | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 40000000 | 40000000 | 27900000 | 0
Reliability Upgrade | 1a | 919 | National Grid, USA |  | 12/2012 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Proposed | Concept | Concept | Planned | Planned | Planned | Planned | Planned | 2008-01-28 | No | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 0 | 0
Reliability Upgrade | 1a | 59 | National Grid, USA |  | 06/2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2007-11-01 | 2003-01-31 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | Part of RSP 921 | Part of RSP 921 |  | 0
Reliability Upgrade | 1a | 783 | National Grid, USA |  | 03/2011 | Merrimack Valley/North Shore Reliability Project | Extend the 115kV by addition of 115kV Breaker and K-153 line from King St. to W. Amesbury 115kV station. (W. Amesbury 345/115kV Station becomes PTF) | Proposed | Concept | Concept | Concept | Concept | Planned | Planned | Planned | 2008-04-01 | No | 7200000 | 29340000 | 29340000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 0 | 1
Reliability Upgrade | 1a | 779 | National Grid, USA |  | 04/2010 | Merrimack Valley/North Shore Reliability Project | Bypass and remove Golden Hills 345 kV substation. | Proposed | Concept | Concept | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | 2008-04-01 | No | 1600000 | 1600000 | 1600000 | 4000000 | 5132609 | 5132609 | 5132609 | 5507195 | 5507195 | 374586 | 0
Reliability Upgrade | 1a | 840 | NSTAR Electric Company |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Proposed | Concept | Concept | Concept | Planned | Planned | Planned | Planned | 2008-04-01 | No | 5400000 | 5400000 | 5400000 | 5400000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 0 | 0
Reliability Upgrade | 1a | 775 | National Grid, USA |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Addition of 4 breakers and relocation of T1 and T2 into new bays at Sandy Pond. | Proposed | Concept | Concept | Planned | Planned | Planned | Planned | Planned | 2008-06-27 | No | TBD | TBD | TBD | 20100000 | 20100000 | 20100000 | 20100000 | 20100000 | 20100000 | 0 | 0
Reliability Upgrade | 1a | 776 | National Grid, USA |  | 09/2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Proposed | Concept | Concept | Planned | Planned | Planned | Planned | Planned | 2008-06-27 | No | 640000 | 640000 | 640000 | 2865876 | 2865876 | 2865876 | 2865876 | 3125000 | 3125000 | 259124 | 0
Reliability Upgrade | 1a | 782 | National Grid, USA |  | 10/2014 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor n Railyard. | Proposed | Concept | Concept | Planned | Planned | Planned | Planned | Planned | 2008-06-27 | No | 37600000 | 37600000 | 37600000 | 37600000 | 38100000 | 38100000 | 38100000 | 43912000 | 43912000 | 5812000 | 0
Reliability Upgrade | 1a | 1165 | NSTAR Electric Company |  | 12/2011 | Mystic Breaker Additions Project | Move Transformer 110B Connection at Mystic | Proposed | Planned | Planned | Planned | Planned | Planned |  | Planned | 2008-03-10 | No | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 |  | 1700000 | 1700000 | 1700000 | 0
Reliability Upgrade | 1a | 904 | NSTAR Electric Company |  | 12/2010 | Mystic IPT Breaker Project | Upgrade (5) 115 kV breakers #1, #7, #15 #19 and #20 at Mystic to IPT. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | NR | NR | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 1500000 | 1500000 | 510000 | 0
Reliability Upgrade | 1a | 1119 | NSTAR Electric Company |  | 06/2010 | Greater Boston Reliability Project | Upgrade West Medway-West Walpole 345kV line #325 | Concept | Concept | Concept |  | Proposed | Proposed | Proposed | Under Construction | NR | NR | 5000000 | 5000000 | 5000000 |  | 1300000 | 2200000 | 2200000 | 2200000 | 2200000 | 0 | 0
Reliability Upgrade | 1a | 842 | NSTAR Electric Company |  | 06/2010 | Boston Area 115 kV Enhancements | Add 115 kV 54 MVAR capacitor bank at W. Framingham. | Proposed | Concept | Concept | Concept | Proposed | Proposed | Proposed | Planned | 2009-12-28 | NR | 1200000 | 1200000 | 1200000 | TBD | 3000000 | 3000000 | 3700000 | 2650000 | 2650000 | -1050000 | 0
Reliability Upgrade | 1a | 1120 | NSTAR Electric Company |  | 06/2010 |  | Install 345kV 160 MVAR shunt ractor at W. Walpole | Concept | Concept | Concept |  | Proposed | Proposed | Proposed | Under Construction | 2010-01-19 | No | 5000000 | 5000000 | 5000000 |  | 6000000 | 7200000 | 7200000 | 7200000 | 7200000 | 0 | 0
Reliability Upgrade | 1a | 1113 | NSTAR Electric Company |  | 12/2010 |  | Install 115kV Breaker #31 at K St. |  |  |  | Concept | Proposed | Proposed | Proposed | Planned | 2009-12-15 | No |  |  |  | TBD | 2100000 | 2100000 | 2960000 | 2800000 | 2800000 | -160000 | 0
Reliability Upgrade | 1a | 1068 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to vicinity of Bourne and connect to existing #120 line and install a 345KV - 115kV auto-transformer at new substation about 3 miles west of the Barnstable Substation 7 |  |  | Concept | Concept | Proposed | Proposed | Proposed | Planned | 11/2009 | No |  |  | TBD | TBD | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 0 | 0
Reliability Upgrade | 1a | 592 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing | Concept | Concept | Concept | Concept | Proposed | Proposed | Proposed | Planned | 11/2009 | No | 5000000 | 5000000 | 5000000 | TBD | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA |  | 0
Reliability Upgrade | 1a | 1118 | NSTAR Electric Company | National Grid, USA | 12/2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 |  |  |  | Concept | Proposed | Proposed | Proposed | Planned | 11/2009 | No | 5000000 | 5000000 | 5000000 | TBD | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA |  | 0
Reliability Upgrade | 1a | 929 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 1381849 | 1381849 | 1381849 | 1381849 | 1381849 | 1381849 | 1381849 | 1381849 | 1381849 | 0 | 0
Reliability Upgrade | 1a | 931 | National Grid, USA |  | 01/2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 0 | 0
Reliability Upgrade | 1a | 928 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 1945218 | 1945218 | 1945218 | 1945218 | 1945218 | 1945218 | 2300000 | 2300000 | 2300000 | 0 | 0
Reliability Upgrade | 1a | 934 | National Grid, USA |  | 09/2011 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | 12/17/2007 | No | 818480 | 818480 | 818480 | 818480 | 818480 | 818480 | 818480 | Part of RSP 935 | Part of RSP 935 |  | 0
Reliability Upgrade | 1a | 935 | National Grid, USA |  | 09/2011 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | 12/17/2007 | No | 5208509 | 5208509 | 5208509 | 5208509 | 5208509 | 5208509 | 5208509 | 10200000 | 10200000 | 4991491 | 0
Reliability Upgrade | 1a | 938 | National Grid, USA |  | 05/2012 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 3068556 | 3068556 | 3068556 | 3068556 | 3068556 | 3068556 | 3068556 | 3068556 | 3068556 | 0 | 0
Reliability Upgrade | 1a | 939 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Reconductor and retension (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 3287738 | 3287738 | 3287738 | 3287738 | 3389658 | 3389658 | 3389658 | 3389658 | 3389658 | 0 | 0
Reliability Upgrade | 1a | 940 | National Grid, USA |  | 04/2011 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 6235744 | 6235744 | 6235744 | 6235744 | 6235744 | 6235744 | 6235744 | 6235744 | 6235744 | 0 | 0
Reliability Upgrade | 1a | 942 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 2767180 | 2767180 | 2767180 | 2767180 | 2767180 | 2767180 | 2767180 | 3650000 | 3650000 | 882820 | 0
Reliability Upgrade | 1a | 927 | National Grid, USA |  | 07/2010 | Central/Western Massachusetts Upgrades | Greendale - replace 115 kV breaker and upgrade to 2000A. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 584629 | 584629 | 584629 | 584629 | 584629 | 584629 | 584629 | 680000 | 680000 | 95371 | 0
Reliability Upgrade | 1a | 925 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 318888 | 318888 | 318888 | 318888 | 318888 | 318888 | 318888 | 318888 | 318888 | 0 | 0
Reliability Upgrade | 1a | 926 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 4889621 | 4889621 | 4889621 | 4889621 | 6027520 | 6027520 | 6027520 | 6027520 | 6027520 | 0 | 0
Reliability Upgrade | 1a | 932 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 372036 | 372036 | 372036 | 372036 | 372036 | 372036 | 372036 | 372036 | 372036 | 0 | 0
Reliability Upgrade | 1a | 924 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 2147181 | 2147181 | 2147181 | 2147181 | 2147181 | 2147181 | 2147181 | 2147181 | 2147181 | 0 | 0
Reliability Upgrade | 1a | 941 | National Grid, USA |  | 06/2012 | Central/Western Massachusetts Upgrades | Install new Z126 Millbury - Tower #510 115 kV line. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 5753542 | 5753542 | 5753542 | 5753542 | 7909203 | 7909203 | 7909203 | 13748000 | 13748000 | 5838797 | 0
Reliability Upgrade | 1a | 943 | National Grid, USA |  | 01/2011 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 1073995 | 1073995 | 1073995 | 1073995 | 1073995 | 1073995 | 1073995 | 1073995 | 1073995 | 0 | 0
Reliability Upgrade | 1a | 944 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 11411849 | 11411849 | 11411849 | 9898000 | 11411849 | 11411849 | 11411849 | 16530000 | 16530000 | 5118151 | 0
Reliability Upgrade | 1a | 950 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 1016897 | 1016897 | 1016897 | 899312 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 0 | 0
Reliability Upgrade | 1a | 953 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 10846906 | 10846906 | 10846906 | 9444260 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 0 | 0
Reliability Upgrade | 1a | 954 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | E Westminster - install new 115 kV breaker, including disconnect switches. Assumes no new control house. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 903909 | 903909 | 903909 | 799506 | 903909 | 903909 | 903909 | 903909 | 903909 | 0 | 0
Reliability Upgrade | 1a | 945 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Adams - install third 115 kV breaker to complete ring bus. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 1581841 | 1581841 | 1581841 | 1581841 | 1581841 | 1581841 | 1584841 | 1584841 | 1584841 | 0 | 0
Reliability Upgrade | 1a | 946 | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer - E Longmeadow - Shaker Rd line to 115 kV. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 14809054 | 14809054 | 14809054 | 14809054 | 9604032 | 9604032 | 9604032 | 9962060 | 9962060 | 358028 | 0
Reliability Upgrade | 1a | 947 | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Reconductor 115 kV line from Palmer to new Hampden Substation. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 14170733 | 14170733 | 14170733 | 14170733 | 2632635 | 2632635 | 2632635 | 2632635 | 2632635 | 0 | 0
Reliability Upgrade | 1a | 948 | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 5649430 | 5649430 | 5649430 | 5649430 | 5649430 | 5649430 | 5649430 | 5649430 | 5649430 | 0 | 0
Reliability Upgrade | 1a | 949 | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 1694829 | 1694829 | 1694829 | 1694829 | 1694829 | 1694829 | 1500000 | 1500000 | 1500000 | 0 | 0
Reliability Upgrade | 1a | 952 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Reconductor E Winchendon - J136 Tap within I135/J136 ROW w/795 ACSR. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 932156 | 932156 | 932156 | 932156 | 932156 | 932156 | 932156 | 932156 | 932156 | 0 | 0
Reliability Upgrade | 1a | 937 | National Grid, USA |  | 05/2012 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 6602875 | 6602875 | 6602875 | 6602875 | 6602875 | 6602875 | 6602875 | 6602875 | 6602875 | 0 | 0
Reliability Upgrade | 1a | 955 | National Grid, USA |  | 11/2011 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 10779113 | 10779113 | 10779113 | 10779113 | 10779113 | 10779113 | 10779113 | 12213934 | 12213934 | 1434821 | 0
Reliability Upgrade | 1a | 162 | National Grid, USA |  | 04/2011 |  | Q-169 Golden Hills to Lynn 115 kV line upgrade. | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | 2005-09-02 | 2008-04-25 | 4335000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 0 | 0
Reliability Upgrade | 1a | 902 | National Grid, USA |  | 10/2010 | Middleboro Municipal | Close the E1-M1 loop at Middleboro's Wareham St Sub. | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | 12/01/2006 | NR | TBD | 715000 | 715000 | 715000 | 715000 | 715000 | 715000 | 715000 | 715000 | 0 | 0
Reliability Upgrade | 1a | 1000 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-06-27 | No | TBD | TBD | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 0 | 0
Reliability Upgrade | 1a | 951 | National Grid, USA |  | 02/2013 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon 115 kV line. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 7231271 | 7231271 | 7231271 | 6400522 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 0 | 0
Reliability Upgrade | 1a | 687 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | 714000000 | 714000000 | 714000000 | 714000000 | 714000000 | 714000000 | 714000000 | 0 | 0
Reliability Upgrade | 1a | 826 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 196 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 818 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115kV line South Agawam to Southwick (1768) | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 819 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 820 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 823 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVAR Capacitor additions | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 828 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 829 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1010 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 259 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 688 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1100 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1101 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1102 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1103 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1104 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1105 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1070 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1071 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1072 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1073 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1074 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1075 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1078 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1079 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1080 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1076 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project |  | 0
Reliability Upgrade | 1a | 1077 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project |  | 0
Reliability Upgrade | 1a | 673 | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Proposed | Concept | Concept | Concept | Planned | Planned | Planned | Planned | 2009-02-27 | No | 525000 | 525000 | 525000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 0 | 0
Reliability Upgrade | 1a | 676 | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Proposed | Concept | Concept | Concept | Planned | Planned | Planned | Planned | 2009-02-27 | No | 6800000 | 6800000 | 6800000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 0 | 0
Reliability Upgrade | 1a | 1067 | NSTAR Electric Company |  | 12/2010 | NPCC BPS Compliance | Tremont Station |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | NR | No |  |  |  | 7100000 | 11200000 | 11200000 | 12800000 | 12370000 | 12370000 | -430000 | 0
Reliability Upgrade | 1a | 1066 | NSTAR Electric Company |  | 09/2011 | NPCC BPS Compliance | Needham Station |  |  |  | Proposed | Proposed | Concept | Concept | Planned | NR | No |  |  |  | 7500000 | 9300000 | 9300000 | 9300000 | 10531000 | 10531000 | 1231000 | 1
Reliability Upgrade | 1a | 1065 | NSTAR Electric Company |  | 07/2012 | NPCC BPS Compliance | Waltham Station |  |  |  | Proposed | Proposed | Concept | Proposed | Planned | NR | No |  |  |  | 22000000 | 24300000 | 24300000 | 26600000 | 23190000 | 23190000 | -3410000 | 1
Generator Interconnection Upgrade | 2a | 1045 | National Grid, USA |  | 06/2010 | Lowell Power | Upgrade 137T and K-137W 115 kV circuit breakers at Sandy Pond. |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2006-07-25 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 505 | National Grid, USA |  | 12/2010 | Hoosac Wind Farm | Tap Y-25S line between Harriman and Deerfield 5. Construct 69/34.5 kV substation and 34.5 kV line connecting 30 MW generating facility with the 69 kV system. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 02/01/2005 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 595 | NSTAR Electric Company |  | 01/2012 | Cape Wind | Expansion of Barnstable 115 kV substation to include 5th bay and (2) circuit breakers, addition of a 3rd breaker in the planned 4th bay, and (2) 35MVAr shunt reactors. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 596 | NSTAR Electric Company |  | 01/2012 | Cape Wind | Installation of (2) 115 kV circuits out of Barnstable substation to interconnect Cape Wind. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 598 | NSTAR Electric Company |  | 01/2012 | Cape Wind | At Canal 345 kV substation, install a redundant breaker in series with breaker #312. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 599 | NSTAR Electric Company |  | 01/2012 | Cape Wind | Upgrade the Bourne 115 kV breaker #12272 with an IPT breaker. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 600 | NSTAR Electric Company |  | 01/2012 | Cape Wind | Installation of differential insulation and additional grounding at each tower that is common for the 342 and 322 345 kV lines. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1048 | NSTAR Electric Company |  | 01/2012 | Cape Wind | Convert Canal 345 kV SPS to include tripping of Cape Wind for the simultaneous loss of 342 and 322 345 kV lines. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1046 | National Grid, USA |  | 06/2011 | Queue Position 178 | Reconductor 115 kV F19 Line (Auburn - Brockton Tap). |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | 2008-03-10 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1047 | National Grid, USA |  | 06/2011 | Queue Position 178 | Replace Bridgewater 115 kV 1631 circuit breaker with 63 kA breaker. |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | 2008-03-10 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 622 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Interconnection to WMECO's 115-kV 1512 line through a new Substation. | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | 06/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1043 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Upgrade the 1768 line terminal equipment at Southwick Substation. | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | 06/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1044 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Upgrade the 1512 line terminal equipment at Southwick Substation. | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | 06/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1058 | National Grid, USA |  | 06/2011 | Billerica Power | Interconnection to Tewksbury 115 kV Substation via O-193 Line and refurbish section of J-162 line. |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1059 | National Grid, USA |  | 06/2011 | Billerica Power | Re-terminate line tap section (Perry Street) of J-162 Line to new bay position at Tewksbury. |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1060 | National Grid, USA |  | 06/2011 | Billerica Power | Reconductor 2.8 mi. of the M-139 115 kV line. |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1061 | National Grid, USA |  | 06/2011 | Billerica Power | Replace (16) 115 kV circuit breakers at Tewksbury 22 w/ IPT capability if all generators w/ higher Queue Position are constructed. The quantity of breaker upgrades subject to Queued generators constructed. |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1062 | National Grid, USA |  | 06/2011 | Billerica Power | Upgrade #137T and #K-137W 115 kV circuit breakers at Sandy Pond (if not completed as part of Merrimack Valley/North Shore Project). |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1014 | Northeast Utilities |  | 2014 | Queue Position 196 | Northfield Mountain 345 kV replace generator step-up transformer (3X) and associated generator equipment. This project also consists of upgrading four existing turbine generators one per year. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Under Construction | 2009-06-29 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Elective | 4a | 1057 | Braintree Electric Light Department |  | 06/2010 |  | Upgrade 115-10-16 underground 115 kV cable. |  |  | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-17 | No |  |  | TBD | TBD | TBD | TBD | NR | TBD | TBD |  | 0
RHODE ISLAND | [25 empty] | 0 | 0 | 0
Reliability Upgrade | 1a | 484 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 690000 | 690000 | 690000 | 690000 | 690000 | 690000 | 690000 | 580000 | 580000 | -110000 | 0
Reliability Upgrade | 1a | 791 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 0 | 0
Reliability Upgrade | 1a | 913 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 0 | 0
Reliability Upgrade | 1a | 914 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 0 | 0
Reliability Upgrade | 1a | 915 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 0 | 0
Reliability Upgrade | 1a | 916 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 0 | 0
Reliability Upgrade | 1a | 917 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 0 | 0
Reliability Upgrade | 1a | 918 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 0 | 0
Reliability Upgrade | 1a | 792 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Admiral St-Franklin Square (Q143 and R144) 115 kV UG recabling. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 22500000 | 22500000 | 22500000 | 22500000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 0 | 0
Reliability Upgrade | 1a | 793 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 0 | 0
Reliability Upgrade | 1a | 786 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Terminal upgrades at Drumrock, Chartley Pond, and Brayton Point. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Under Construction | 2008-04-25 | No | 2000000 | 2000000 | 2000000 | 565000 | 565000 | 565000 | 1000000 | 1000000 | 1000000 | 0 | 0
Reliability Upgrade | 1a | 787 | National Grid, USA |  | 06/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | West Farnum breaker replacements. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Under Construction | 2008-04-25 | No | 6500000 | 6500000 | 6500000 | 7600000 | 7631000 | 7631000 | 7631000 | 7631000 | 7631000 | 0 | 0
Reliability Upgrade | 1a | 788 | National Grid, USA |  | 06/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Kent County substation expansion. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Under Construction | 2008-04-25 | No | 25000000 | 25000000 | 25000000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 0 | 0
Reliability Upgrade | 1a | 790 | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Under Construction | 2008-04-25 | No | 24000000 | 24000000 | 24000000 | 50600000 | 50600000 | 50600000 | 50600000 | 50600000 | 50600000 | 0 | 0
Reliability Upgrade | 1a | 1098 | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street |  |  | Planned | Planned | Planned | Planned | Planned | Under Construction | 2008-04-25 | No |  |  | TBD | 23000000 | 37529000 | 37529000 | 37529000 | 37529000 | 37529000 | 0 | 0
Reliability Upgrade | 1a | 190 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | 53000000 | 53000000 | 53000000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 0 | 0
Reliability Upgrade | 1a | 1094 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | TBD | 20800000 | 20800000 | 20800000 | 25000000 | 25000000 | 25000000 | 0 | 0
Reliability Upgrade | 1a | 1095 | National Grid, USA |  | 06/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | TBD | 73800000 | 73800000 | 73800000 | 73800000 | 73800000 | 73800000 | 0 | 0
Reliability Upgrade | 1a | 794 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | 50000000 | 50000000 | 50000000 | 55800000 | 55800000 | 55800000 | 55800000 | 55800000 | 55800000 | 0 | 0
Reliability Upgrade | 1a | 796 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | 347 Reconductor from Sherman Road to CT/RI Border. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | 10000000 | 10000000 | 10000000 | 16400000 | 16400000 | 16400000 | 16400000 | 16400000 | 16400000 | 0 | 0
Reliability Upgrade | 1a | 797 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | 3361 Upgrade 345kV terminal equipment at Sherman Road. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | 3000000 | 3000000 | 3000000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 0 | 0
Reliability Upgrade | 1a | 795 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV line. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | 92000000 | 92000000 | 92000000 | 99900000 | 99900000 | 99900000 | 99900000 | 99900000 | 99900000 | 0 | 0
Reliability Upgrade | 1a | 1106 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | Part of $92,000,000 above | Part of $92,000,000 above | Part of $92,000,000 above | Part of $99,900,000 above | Part of $99,900,000 above | Part of $99,900,000 above | Part of $99,900,000 above | Part of $99,900,000 above | Part of $99,900,000 above |  | 0
Reliability Upgrade | 1a | 798 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | 500000 | 500000 | 500000 | 4900000 | 4900000 | 4900000 | 4900000 | 4900000 | 4900000 | 0 | 0
Reliability Upgrade | 1a | 799 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | 2200000 | 2200000 | 2200000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 0 | 0
Reliability Upgrade | 1a | 1096 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | TBD | 5800000 | 5800000 | 5800000 | 12000000 | 12000000 | 12000000 | 0 | 0
Reliability Upgrade | 1a | 800 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S, T-172N and T-172S with associated terminal equipment upgrades. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2009-11-05 | No | 62000000 | 62000000 | 62000000 | 7300000 | 7300000 | 7300000 | 10000000 | 10000000 | 10000000 | 0 | 0
Reliability Upgrade | 1a | 1097 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | TBD | 129800000 | 129800000 | 129800000 | 129800000 | 129800000 | 129800000 | 0 | 0
Reliability Upgrade | 1a | 1099 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | TBD | 4100000 | 4100000 | 4100000 | 6000000 | 6000000 | 6000000 | 0 | 0
Reliability Upgrade | 1a | 1109 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | TBD | 360000 | 360000 | 360000 | 1000000 | 1000000 | 1000000 | 0 | 0
CONNECTICUT | [27 empty] | 0
Reliability Upgrade | 1a | 1055 | Northeast Utilities |  | 2010 | CT LSP - Waterside Substation | Waterside Substation - add a 115/13.2-kV transformer and a 115-kV circuit breaker. |  |  | Concept | Concept | Concept | Concept | Concept | Planned | 2009-09-29 | NR |  |  | TBD | 4107000 | 4107000 | 4107000 | 4107000 | 2619000 | 2619000 | -1488000 | 0
Reliability Upgrade | 1a | 1049 | United Illuminating Company |  | 12/2010 |  | East Shore 115 kV Capacitor Bank Transient Recovery |  | Concept | Concept | Planned | Planned | Planned | Planned | Planned | NR | NR |  | 1200000 | 1200000 | 3000000 | 3000000 | 3000000 | 3000000 | 4050000 | 4050000 | 1050000 | 0
Reliability Upgrade | 1a | 582 | Northeast Utilities |  | 12/2010 |  | Separate 310 and 368 345-KV lines and create 368/1767 DCT | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-07-18 | No | TBD | TBD | 15500000 | 16000000 | 16000000 | 16000000 | 16000000 | 16000000 | 16000000 | 0 | 0
Reliability Upgrade | 1a | 1112 | United Illuminating Company |  | 12/2010 |  | Water Street 115kV circuit breaker and switch replacements. |  |  |  | Planned | Planned | Planned | Planned | Planned | NR | NR |  |  |  | 1000000 | 1000000 | 1000000 | 1000000 | 2840000 | 2840000 | 1840000 | 0
Reliability Upgrade | 1a | 809 | Northeast Utilities |  | 12/2010 |  | Upgrade terminal equipment at Bunker Hill 115 kV substation. | Proposed | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | NR | NR | TBD | TBD | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 516000 | 516000 | -484000 | 0
Reliability Upgrade | 1a | 1147 | Northeast Utilities |  | 2011 |  | Waterside Substation - install a three-breaker 115kV ring bus | Proposed | Concept | Concept | Concept | Concept |  | Proposed | Planned | 2009-09-29 | NR | TBD | TBD | TBD | TBD | TBD |  | 4000000 | 5055000 | 5055000 | 1055000 | 1
Reliability Upgrade | 1a | 1148 | Northeast Utilities |  | 2011 |  | Add a 2nd high speed relay on the Glennbrook to Waterside 115kV 1440 | Planned | Concept | Concept | Concept | Concept |  | Proposed | Planned | 2009-09-29 | NR | TBD | TBD | TBD | TBD | TBD |  | 600000 | Part of Project #1147 | Part of Project #1147 |  | 1
Reliability Upgrade | 1a | 974 | United Illuminating Company |  | 04/2013 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Proposed | Concept | Concept | Planned | Planned | Planned | Planned | Planned | NR | No | 4500000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 0 | 0
Reliability Upgrade | 1a | 816 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1054 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Manchester - Meekvile Jct. line (395/1448) separation. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 0 | 0
Reliability Upgrade | 1a | 576 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | 313000000 | 313000000 | 313000000 | 313000000 | 313000000 | 313000000 | 313000000 | 0 | 0
Reliability Upgrade | 1a | 1114 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) |  | 0
Reliability Upgrade | 1a | 814 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Central Connecticut Relaibility Project) | Reconductor a portion of the Manchester to Scovill Rock 353 345-kV line and terminal work. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | 15000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 0 | 0
Reliability Upgrade | 1a | 802 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | 251000000 | 251000000 | 251000000 | 251000000 | 251000000 | 251000000 | 251000000 | 0 | 0
Reliability Upgrade | 1a | 1084 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Loop the Millstone - Manchester (310) 345 kV line into the Card substation. |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 1085 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 1086 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 1087 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 1088 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 1089 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Killingly 3G substation 345kV breaker addition |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 1090 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Millstone 15G substation breaker 14T upgrade 50kA |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 1091 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Southington 4C substation breaker 19T upgrade to 63kA |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 810 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 191 | Northeast Utilities | National Grid, USA | 12/2013 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 807 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Interstate Reliability Project) | Install 480 MVAR's of capacitors at the Montville 345 kV substation | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | 21000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 0 | 0
Reliability Upgrade | 1a | 1092 | Northeast Utilities |  | 12/2013 | NEEWS (BPS) 2 | Upgrade the Card 115 kV, East Hartford 115 kV, Agawam 115 kV, Barbour Hill 115 kV, and North Bloomfield 345 kV Substations to BPS standards. |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | TBD | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 0 | 0
Reliability Upgrade | 1a | 1056 | Northeast Utilities |  | 12/2011 | CT LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. |  |  | Concept | Concept | Planned | Planned | Planned | Planned | 2008-12-12 | No |  |  | TBD | TBD | 9751000 | 9751000 | 9751000 | 10969000 | 10969000 | 1218000 | 0
Reliability Upgrade | 1a | 1110 | United Illuminating Company |  | 12/2010 |  | Broadway 115/13.8 kV Substation Addition |  |  |  | Proposed | Planned | Planned | Planned | Under Construction | 2008-12-08 | NR |  |  |  | 1000000 | 800000 | 1200000 | 1200000 | 1200000 | 1200000 | 0 | 0
Reliability Upgrade | 1a | 1111 | United Illuminating Company |  | 2011-08-01 |  | Metro North Union Avenue 115/26.4 kV Substation |  |  |  | Proposed | Planned | Planned | Planned | Planned | 2009-01-07 | 2009-11-10 |  |  |  | 8700000 | 8700000 | 10543000 | 10543000 | 10543000 | 10543000 | 0 | 0
Reliability Upgrade | 1a | 976 | United Illuminating Company |  | 05/2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Concept | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | 2009-01-07 | No | 40000000 | 38900000 | 38900000 | 48000000 | 48000000 | 48000000 | 48000000 | 66000000 | 66000000 | 18000000 | 0
Reliability Upgrade | 1a | 721 | United Illuminating Company |  | 06/2016 |  | New Shelton 115/13.8 kV substation | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Planned | 2009-11-05 | No | 5500000 | 26610000 | 7370000 | 11300000 | 11300000 | 11300000 | 11300000 | 19500000 | 19500000 | 8200000 | 0
Reliability Upgrade | 1a | 879 |  | Bangor Hydro-Electric Company, New England Power Company, Northeast Utilities System Com | TBD | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 03/01/2007 | NR | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 0 | 0
Generator Interconnection Upgrade | 2a | 983 | Northeast Utilities |  | 09/2012 | Queue Position 207/241 | Rebuild 115 kV 1585N Line between new substation and Bunker Hill. | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | 2008-09-26 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1107 | Northeast Utilities |  | 09/2012 | Queue Position 207/241 | Interconnection to new 115 kV substation consisting of (14) circuit breakers in a breaker and a half configuration that sectionalizes the existing 1575, 1585, and 1990 lines. |  |  | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | 2008-09-26 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1108 | Northeast Utilities |  | 09/2012 | Queue Position 207/241 | Installation of a 2.5% series reactor on the 1990S Line at the new substation. |  |  | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | 2008-09-26 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 331 | Northeast Utilities |  | TBD | Kleen Energy | Install 5-breaker ring bus interconnecting between Scovill Rock and Manchester on the 345 kV 353 Line. | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | See Note (5) | 10/08/2003 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 1
Generator Interconnection Upgrade | 2a | 1121 | Northeast Utilities |  | 06/2010 | Queue Position 161-2 | Four units connected to 384 line through a new 345kV Substation: unit #4 wll also connect to Substation | Planned | Planned | Planned |  | Proposed | Proposed | Planned | Planned | 2008-12-08 | NR | NR | NR | NR |  | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1149 | Northeast Utilities |  | 06/2010 | Queue Position 161-1 | Four units connected at Devon Substation | Planned | Planned | Planned |  | Proposed |  | Under Construction | Under Construction | 2007-12-08 | NR | NR | NR | NR |  | NR | NR | NR | NR | NR |  | 1
Generator Interconnection Upgrade | 2a | 1122 | Northeast Utilities |  | 11/2010 | Queue Position 191 | One turbine connected to #1238 Line (Frost Bridge to Carmel) via a new 3-breaker ring bus Substation | Planned | Planned | Planned |  | Proposed | Proposed | Proposed | Proposed | 2009-02-24 | NR | NR | NR | NR |  | NR | NR | NR | NR | NR |  | 0
Reliability Upgrade | 1a | 1050 | United Illuminating Company |  | 12/2011 |  | Devon Tie 115kV Switching Station BPS Compliance |  | Concept | Concept | Concept | Planned | Planned | Planned | Planned | NR | NR |  | 2620000 | 2620000 | 2620000 | 2620000 | 2620000 | 2620000 | 3240000 | 3240000 | 620000 | 0
TABLE B | [27 empty] | 0
MAINE | [27 empty] | 0
Reliability Upgrade | 1b | 148 | Central Maine Power Company |  | 06/2012 | CMP LSP - Saco Bay Area Reinforcement Project | Establish a new Vallee Lane 115/34.5 kV substation and 115 kV line from Louden S/S to Vallee Lane Substation. | Proposed | Proposed | Concept | Concept | Proposed | Proposed | Proposed | Proposed | No | NR | 14000000 | 14000000 | 16900000 | 16900000 | 16900000 | 100000 | 100000 | 100000 | 100000 | 0 | 0
Reliability Upgrade | 1b | 1116 | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Concept | Concept | Proposed |  | Concept | Concept | Concept | Proposed | No | No | TBD | TBD | Part of Maine Power Reliability Program |  | TBD | TBD | TBD | 37126000 | 37126000 | 37126000 | 0
Reliability Upgrade | 1b | 1031 | Bangor Hydro-Electric Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station | Concept | Concept | Proposed | Proposed | Concept | Concept | Concept | Concept | No | No | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | TBD | TBD | TBD | TBD | TBD |  | 0
Reliability Upgrade | 1b | 1154 | Bangor Hydro-Electric Company |  | 12/2013 | Maine Power Reliability Program (MPRP) | Rebuild Line 66 | Concept | Concept | Proposed | Proposed | Concept | Concept |  | Concept | No | No | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | TBD | TBD |  | TBD | TBD |  | 0
Reliability Upgrade | 1b | 1155 | Bangor Hydro-Electric Company |  | 12/2013 | Maine Power Reliability Program (MPRP) | Capacitor Bank Addition (10 MVAr at Trenton and Epping) | Concept | Concept | Proposed | Proposed | Concept | Concept |  | Concept | No | No | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | TBD | TBD |  | TBD | TBD |  | 0
Reliability Upgrade | 1b | 1156 | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | Orrington Shunt Cap Reconfiguration | Concept | Concept | Proposed | Proposed | Concept | Concept |  | Concept | No | No | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | TBD | TBD |  | TBD | TBD |  | 0
Reliability Upgrade | 1b | 1157 | Bangor Hydro-Electric Company |  | 12/2010 |  | Bangor Hydro Synchrophasors | Concept | Concept | Proposed | Proposed | Concept | Concept |  | Concept | No | No | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | TBD | TBD |  | 100000 | 100000 | 100000 | 0
Reliability Upgrade | 1b | 1130 | Central Maine Power Company |  | 12/2011 | Sturtevant Improvements | Add 115kV circuit breakers & 25 MVAR capacitor bank at Sturtevant Substation; Re-rate Section 63 between Wyman Hydro & Madison Substation | Planned | Concept | Concept |  | Proposed | Proposed | Proposed | Proposed | 2009-07-28 | No | 10100000 | 10100000 | 6100000 |  | 2000000 | 3000000 | 3000000 | 3000000 | 3000000 | 0 | 0
Reliability Upgrade | 1b | 1131 | Central Maine Power Company |  | 12/2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Planned | Concept | Concept |  | Proposed | Proposed | Proposed | Proposed | No | NR | 10100000 | 10100000 | 6100000 |  | 600000 | 600000 | 600000 | 600000 | 600000 | 0 | 0
Reliability Upgrade | 1b | 1132 | Central Maine Power Company |  | 12/2011 | CMP-LSP Maxcy's Substation | Add 115/34kV transformer (coordinate with MPRP) | Planned | Concept | Concept |  | Proposed | Proposed | Proposed | Proposed | No | NR | 10100000 | 10100000 | 6100000 |  | 600000 | 600000 | 600000 | 600000 | 600000 | 0 | 0
Reliability Upgrade | 1b | 1133 | Central Maine Power Company |  | 10/2010 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation & new 34kV line from Leeds to Turner | Planned | Concept | Concept |  | Proposed | Proposed | Proposed | Proposed | No | NR | 10100000 | 10100000 | 6100000 |  | 2500000 | 300000 | 300000 | 300000 | 300000 | 0 | 0
Reliability Upgrade | 1b | 1135 | Central Maine Power Company |  | TBD | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer | [5 empty] | Proposed | Proposed | Proposed | No | No | 10100000 | 10100000 | 6100000 |  |  | 1500000 | 1500000 | 1500000 | 1500000 | 0 | 1
Elective | 4b | 1018 | Bangor Hydro-Electric Company | NSTAR | TBD | QP-283 | HVDC between Orrington, ME and Boston, MA | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Elective | 4b | 1160 | Central Maine Power Company |  | TBD | QP-278 | 1000 MW HVDC between Maine Yankee, ME and South Boston, MA | Concept | Concept | Concept | Concept | Concept | Concept |  | Concept | No | No | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD |  | 0
Elective | 4b | 1163 | Maine Electric Power Company |  | TBD | QP-322 | 345kV Tie Line - between Houlton, ME and MEPCO Line | Concept | Concept | Concept | Concept | Concept | Concept |  | Concept | No | No | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD |  | 0
Elective | 4b | 1164 | Maine Electric Power Company |  | TBD | QP-324 | 345kV Tie Line - between Bridgewater, ME and MEPCO Line | Concept | Concept | Concept | Concept | Concept | Concept |  | Concept | No | No | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD |  | 0
NEW HAMPSHIRE | [27 empty] | 0
Reliability Upgrade | 1b | 1143 | Northeast Utilities |  | TBD |  | Littleton 115kV breaker addition and reconfiguration | Proposed | Concept | Concept | Concept |  | Proposed | Proposed | Proposed | No | No | TBD | TBD | TBD | TBD |  | 5338000 | 5338000 | 6642000 | 6642000 | 1304000 | 1
VERMONT | [27 empty] | 0
Reliability Upgrade | 1b | 318 | Vermont Electric Power Company |  | 12/2011 |  | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems through the 1,250 MW Vermont state load level. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 7000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 0 | 0
Reliability Upgrade | 1b | 325 | Vermont Electric Power Company |  | 12/2011 | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 3000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 0 | 0
Reliability Upgrade | 1b | 324 | Vermont Electric Power Company |  | TBD |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 60000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | TBD | TBD | #VALUE! | 0
Generator Interconnection Upgrade | 2b | 1037 | Vermont Electric Power Company | Central Vermont Public Service | 12/2010 | Queue Position 276 | Installation of 3-breaker 115kV ring bus interconnection of the Bennington-Searsburg 69kV Y25N line. | Proposed | Concept | Concept | Concept | Concept | Concept |  | Concept | No | NR | 60000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 |  | NR | NR |  | 0
Generator Interconnection Upgrade | 4b | 1162 | Vermont Electric Power Company |  | TBD | OP-314 | 345/230 kV DC line between Plattsburg, NY and New Haven, CT | Proposed | Concept | Concept | Concept | Concept | Concept |  | Concept | No | NR | 60000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 |  | NR | NR |  | 0
MASSACHUSETTS | [27 empty] | 0
Reliability Upgrade | 1b | 785 | National Grid, USA |  | 07/2017 | Merrimack Valley/North Shore Reliability Project | Re-conductor F-158N (Golden Hills-Maplewood-Everett) 115 kV line. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 1330000 | 1330000 | 1330000 | 1330000 | 1330000 | 1330000 | 1330000 | 1330000 | 1330000 | 0 | 0
Reliability Upgrade | 1b | 1153 | NSTAR Electric Company |  | 12/2011 | Boston Area 115 kV Enhancements | Reliability Upgrades at West Framingham Station | Concept | Concept | Concept | Concept | Proposed |  | Concept | Concept | No | No | TBD | TBD | TBD | TBD | Part of Long Term Lower SEMA |  | 3000000 | 3000000 | 3000000 | 0 | 1
Reliability Upgrade | 1b | 843 | NSTAR Electric Company |  | 12/2013 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 1200000 | 1200000 | 1200000 | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Reliability Upgrade | 1b | 965 | NSTAR Electric Company |  | 12/2012 | Boston Area 115 kV Enhancements | Add third 115kV line from W. Walpole to Holbrook | Proposed | Proposed | Proposed | Concept | Concept | Concept | Concept | Concept | No | No | 2500000 | 2500000 | 2500000 | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Reliability Upgrade | 1b | 964 | NSTAR Electric Company |  | 06/2011 | Boston Area 115 kV Enhancements | Relocate 115kV terminals at W. Walpole to mitigate breaker failure #8. | Proposed | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | No | No | 600000 | 600000 | 600000 | TBD | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 0 | 0
Reliability Upgrade | 1b | 969 | NSTAR Electric Company |  | 06/2015 | Boston Area 115 kV Enhancements | Add a new 54 MVAR capacitor bank at Chelsea. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 2780000 | 2780000 | 1580000 | 0
Reliability Upgrade | 1b | 301 | NSTAR Electric Company |  | 12/2011 | Boston Area 115 kV Enhancements | Reconductor 115-kV circuits 320-507 and 320-508. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 0 | 0
Reliability Upgrade | 1b | 593 | NSTAR Electric Company |  | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Canal to Barnstable/Falmouth | Concept | Concept | Concept | Concept | Proposed | Concept | Concept | Concept | No | No | TBD | TBD | TBD | TBD | Part of Long Term Lower SEMA | TBD | TBD | TBD | TBD |  | 1
Reliability Upgrade | 1b | 970 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345 kV line from Lexington to Waltham. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 15000000 | 15000000 | 15000000 | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Reliability Upgrade | 1b | 971 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 12000000 | 12000000 | 12000000 | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Reliability Upgrade | 1b | 1166 | NSTAR Electric Company |  | 12/2010 |  | Terminal upgrades at W. Walpole and W, Medway for #325 line | Concept | Concept | Concept |  | Proposed | Proposed |  | Proposed | NR | NR | 5000000 | 5000000 | 5000000 |  | 1300000 | 2200000 |  | 1350000 | 1350000 | 1350000 | 0
Reliability Upgrade | 1b | 1167 | NSTAR Electric Company |  | 12/2010 |  | Replace three 40kA 115kV circuit breakers at Carver with 63kV breakers | Concept | Concept | Concept |  | Proposed | Proposed |  | Concept | No | No | 5000000 | 5000000 | 5000000 |  | 6000000 | 7200000 |  | 850000 | 850000 | 850000 | 0
Reliability Upgrade | 1b | 956 | National Grid, USA |  | 01/2015 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 0 | 0
Reliability Upgrade | 1b | 1136 | National Grid, USA |  | 12/2012 |  | New 115kV Switching Station at Devens Convert 69kV lines to 115kV, Reconfigure 115kV Supply at Ayer Substation | [5 empty] | Proposed | Proposed | Proposed | 2009-07-28 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 9200000 | 9200000 | 9200000 | 9200000 | 0 | 1
Reliability Upgrade | 1b | 824 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Reliability Upgrade | 1b | 1168 | Holyoke Gas & Electric |  | TBD |  | Loop/extend the 1525 (Holyoke Fairmont South 115kV) line into the new Lyman Substation | Proposed | Concept | Concept | Concept | Concept | Concept |  | Concept | No | No | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD |  | 0
Reliability Upgrade | 1b | 825 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Upgrade the Pleasant to Blanford 115-kV line and the Blanford to Granville Jct. portion of the 115-kV line 1512. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Generator Interconnection Upgrade | 2b | 1123 | Northeast Utilities |  | TBD | Queue Position 236 | New Substation on 1302 Line; terminal upgrades at Buck Pond and Agawam | Concept | Concept | Concept |  | Concept | Concept | Concept | Concept | No | NR | NR | NR | NR |  | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2b | 880 | National Grid, USA | Northeast Utilities | 06/2011 | Queue Position 177 | Sutton Energy - 345 kV Carpenter Hill-Millbury Line. | Concept | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2b | 1042 | National Grid, USA |  | 06/2013 | Queue Position 165 | Replace (2) 345 kV circuit breakers at Sandy Pond | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
RHODE ISLAND | [27 empty] | 0
Generator Interconnection Upgrade | 2b | 881 | National Grid, USA | Northeast Utilities | 06/2012 | Queue Position 201 | RISEP - 345 kV RISE Substation. | Concept | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
CONNECTICUT | [27 empty] | 0
Reliability Upgrade | 1b | 1150 | United Illuminating Company |  | 12/2010 |  | Grand Avenue - West River 115 kV Pumping Plant Replacements | Concept | Concept | Concept | Proposed | Proposed |  | Proposed | Proposed | NR | NR | 5500000 | 26610000 | 7370000 | 11300000 | 11300000 |  | 1200000 | 2900000 | 2900000 | 1700000 | 1
Reliability Upgrade | 1b | 1151 | United Illuminating Company |  | 12/2011 |  | West River 115kV Switching Station Fault Duty Migration | Concept | Concept | Concept | Proposed | Proposed |  | Proposed | Proposed | NR | NR | 5500000 | 26610000 | 7370000 | 11300000 | 11300000 |  | 3500000 | 3500000 | 3500000 | 0 | 1
Reliability Upgrade | 1b | 975 | United Illuminating Company |  | 06/2015 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 33000000 | 44300000 | 44300000 | 44300000 | 44300000 | 44300000 | 44300000 | 65000000 | 65000000 | 20700000 | 0
Reliability Upgrade | 1b | 699 | United Illuminating Company |  | 12/2014 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 75000000 | 46540000 | 46540000 | 46540000 | 10000000 | 10000000 | 10000000 | 11100000 | 11100000 | 1100000 | 0
Reliability Upgrade | 1b | 801 | Northeast Utilities |  | TBD |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Reliability Upgrade | 1b | 85 | Northeast Utilities |  | TBD |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Planned | Concept | Concept | Concept | Concept | Concept | Concept | Concept | 08/04/2004 | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Generator Interconnection Upgrade | 2b | 1124 | Northeast Utilities |  | TBD | Queue Position 222 | New Substation on Haddam Neck-Southington 345kV line | Planned | Concept | Concept |  | Proposed | Proposed | Proposed | Proposed | No | NR | TBD | TBD | TBD |  | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2b | 1125 | Northeast Utilities |  | TBD | Queue Position 240 | 345kV on Montville Substation | Planned | Concept | Concept |  | Concept | Concept | Concept | Concept | No | NR | TBD | TBD | TBD |  | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 4b | 1161 | United Illuminating Company |  | TBD | Queue Position 271 | 1000 MW HVDC between Hertel, QC or Clay NY and Singer, CT | Planned | Concept | Concept |  | Concept | Concept |  | Concept | No | NR | TBD | TBD | TBD |  | NR | NR |  | NR | NR |  | 0
IN-SERVICE PROJECTS | [25 empty] | 5189345881 | #VALUE! | 25
Reliability Upgrade | 1a | 320 | Vermont Electric Power Company |  | 10/2009 | Lamoille County Project | Middlesex Substation 115 kV breaker addition. | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | 08/16/2007 | 02/07/2008 | 4000000 | 4857000 | 4857000 | 4857000 | 4857000 | 4857000 | 4857000 | 4857000 | 4857000 | 0 | 0
Reliability Upgrade | 1a | 322 | Vermont Electric Power Company |  | 10/2009 | Lamoille County Project | Installation of new Duxbury Substation that involves looping in and out of the Middlesex - Essex 115 kV (K24) line. | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | 08/16/2007 | 02/07/2008 | 3000000 | Part of Lamoille County Project | Part of Lamoille County Project | Part of Lamoille County Project | Part of Lamoille County Project | Part of Lamoille County Project | Part of Lamoille County Project | Part of Lamoille County Project | Part of Lamoille County Project |  | 0
Reliability Upgrade | 1a | 321 | Vermont Electric Power Company |  | 11/2009 | Burlington Project | Burlington 115kV Loop - 5 mi of new line & rebuilding 5 miles of existing line between two existing substations with expansion of the East Avenue substation. | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | 10/24/2006 | 05/23/2007 | 30000000 | 25142000 | 25142000 | 25142000 | 25142000 | 25142000 | 25142000 | 25142000 | 25142000 | 0 | 0
Reliability Upgrade | 1a | 1063 | NSTAR Electric Company |  | 12/2009 |  | Install (2) 115kV 40 MVAR shunt reactors at Edgar Station |  |  |  | Concept | Proposed | Planned | Under Construction | In-service | 05/2009 | No |  |  |  | TBD | 5400000 | 5400000 | 5400000 | 3745000 | 3745000 | -1655000 | 1
Reliability Upgrade | 1a | 777 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Build Wakefield Junction station with four 345/115 kV autotransformers. | Proposed | Concept | Concept | Under Construction | Under Construction | Under Construction | Under Construction | In-service | 2008-04-01 | No | 76840000 | 76840000 | 76840000 | 95000000 | 95000000 | 95000000 | 95000000 | 95000000 | 95000000 | 0 | 0
Reliability Upgrade | 1a | 161 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Loop 345 kV 339 line and 115 kV S-145/T-146 into new Wakefield Jct. Substation. | Proposed | Concept | Concept | Under Construction | Under Construction | Under Construction | Under Construction | In-service | 2008-04-01 | No | 14000000 | 14000000 | 14000000 | 3200000 | 4986431 | 4986431 | 4986431 | 5406900 | 5406900 | 420469 | 0
Reliability Upgrade | 1a | 961 | NSTAR Electric Company |  | 12/2009 | Mystic Breaker Additions Project | Install (2) new 115 kV East Bus breakers #30 and #32 at Mystic. | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | 2008-03-10 | No | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3689000 | 3689000 | -111000 | 0
Reliability Upgrade | 1a | 903 | NSTAR Electric Company |  | 12/2009 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #2, #4, #5, and #16 at Mystic to IPT and separate controls with Boston Gen units #5 and #6. | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | NR | NR | 1240000 | 1240000 | 1240000 | 1240000 | 1240000 | 1240000 | 1240000 | 1576000 | 1576000 | 336000 | 0
Reliability Upgrade | 1a | 930 | National Grid, USA |  | 11/2009 | Central/Western Massachusetts Upgrades | Reconductor Nashua St - Quinsigamond Jct (O141) 115 kV line w/636 ACSS. | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | 12/17/2007 | No | 1562553 | 1562553 | 1562553 | 1765000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 0 | 0
Reliability Upgrade | 1a | 933 | National Grid, USA |  | 01/2010 | Central/Western Massachusetts Upgrades | Reconductor Pratts Jct - Flagg Pond I-135S & J-136S 115 kV lines w/795 ACSS. | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | 12/17/2007 | No | 5952582 | 5952582 | 5952582 | 5952582 | 6137112 | 6137112 | 6137112 | 11200000 | 11200000 | 5062888 | 0
Reliability Upgrade | 1a | 211 | Northeast Utilities |  | 11/2009 | NU LSP - Rood Ave Substation | New Rood Ave (formally Windsor) distribution substation with 115kV terminal modifications. | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | 2008-04-25 | 02/15/2008 | TBD | 9162029 | 9162029 | 9162029 | 9162029 | 9162029 | 9162029 | 8681000 | 8681000 | -481029 | 0
Reliability Upgrade | 1a | 789 | National Grid, USA |  | 12/2009 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Reconductoring of T7 115 kV line. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | In-service | 2008-04-25 | No | 11200000 | 11200000 | 11200000 | 20900000 | 23304000 | 23304000 | 23304000 | 23304000 | 23304000 | 0 | 0
Reliability Upgrade | 1b | 963 | NSTAR Electric Company |  | 12/2009 | Boston Area 115 kV Enhancements | Add a new 115kV breaker # 11 Relocate 447-509 and add control and protection at Holbrook. | Proposed | Concept | Concept | Concept | Proposed | Proposed | Proposed | In-service | 2009-08-19 | NR | 600000 | 600000 | 600000 | TBD | 3400000 | 4000000 | 4000000 | 1276800 | 1276800 | -2723200 | 0
Generator Interconnection Upgrade | 2b | 863 | Northeast Utilities |  | 2008 | Queue Position 217 | Northfield Mountain 345 kV replace generator step-up transformer (1X) and associated generator equipment. | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | In-service | 2008-04-25 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Reliability Upgrade | 1a | 1051 | Central Maine Power Company |  | 09/2009 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Riley 115 kV capacitor bank. |  | Concept | Planned | Planned | Planned | Under Construction | In-service | In-service | 2007-11-30 | No | TBD | TBD | Portion of 5,400,000 (above) | Portion of 5,400,000 (above) | Part of Project 625 | Part of Project 625 | Part of Project 625 | Part of Project 625 | Part of Project 625 |  | 1
Generator Interconnection Upgrade | 2a | 1134 | Central Maine Power Company |  | 09/2009 | Kibby Wind Farm | Separate Section 215 from Section 63 and terminate Section 215 at newly established breaker position in Wyman Hydro S/S, which includes re-rating of Section 215. Expand Bigelow S/S & add capacitor banks at Lakewood, Guilford, Wyman Hydro Station & Sturtevant S/S's. |  |  |  |  | Planned | Under Construction | In-service | In-service | 2006-06-16 | NR |  |  |  |  | NR | NR | NR | NR | NR |  | 1
Reliability Upgrade | 1a | 579 | Central Maine Power Company |  | 06/2008 | Maguire Road Project | Addition of (4) 345 kV breakers at Buxton. | Planned | Planned | In-Service | In-Service |  |  |  |  | 03/01/2007 | No | 5000000 | 5000000 | 11700000 | 11700000 |  |  |  |  | #TBDs | 17
Reliability Upgrade | 1a | 587 | Northeast Utilities |  | 2008-05-13 |  | Install third 345/115-kV autotransformer at Scobie Substation. | Planned | Under Construction | In-Service | In-Service |  |  |  |  | 07/01/2007 | No | TBD | 19257000 | 12948000 | 12948000
Reliability Upgrade | 1a | 282 | Northeast Utilities |  | 2008-05-26 | NU LSP - Weare Substation | Install new 115 kV Weare Street Substation and Jackman capacitors. | Planned | Under Construction | In-Service | In-Service |  |  |  |  | 03/01/2007 | 05/01/2007 | 11643000 | 11633000 | 11633000 | 11633000
Reliability Upgrade | 1a | 580 | Northeast Utilities |  | 2008-05-30 | Scobie Pond to Hudson Reinforcement Project | Install new 115-kV Scobie - Hudson line. | Under Construction | Under Construction | In-Service | In-Service |  |  |  |  | 07/31/2006 | No | 30145000 | 30243000 | 30947000 | 30947000
Reliability Upgrade | 1a | 685 | National Grid, USA |  | 03/2008 |  | New 345 kV gas circuit breaker at Auburn St. Substation on the 335 Line. | Under Construction | Under Construction | In-Service | In-Service |  |  |  |  | 10/01/2006 | 10/01/2006 | 860000 | 860000 | 860000 | 860000
Reliability Upgrade | 1a | 293 | NSTAR Electric Company |  | 04/2008 |  | Upgrade Canal 345-kV breaker #612 to IPT. | Proposed | Under Construction | In-Service | In-Service |  |  |  |  | NR | NR | 450000 | 450000 | 450000 | 450000
Reliability Upgrade | 1a | 56 | Bangor Hydro-Electric Company |  | 12/2007 | Northeast Reliability Interconnect Project | Point Lepreau to Orrington - New 345 kV line as well as capacity expansion from Orrington to Maine Yankee. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 03/01/2003 | 09/28/2007 | 144000000 | 144000000 | 144000000 | 144000000 | 144000000 | 144000000 | 144000000 | 144000000
Reliability Upgrade | 1a | 154 | Central Maine Power Company | Northeast Utilities | 2008-08-01 | Maguire Road Project | Rebuild Louden - Maguire Road 115 kV Line S163. | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 03/01/2007 | No | 3000000 | 3000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000
Reliability Upgrade | 1a | 715 | Central Maine Power Company |  | 2008-08-01 | Maguire Road Project | Rebuild South Gorham to Louden 115 kV Line S219. | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 03/01/2007 | No | 3000000 | 3000000 | 4900000 | 4900000 | 4900000 | 4900000 | 4900000 | 4900000 | #TBDs | 17
Reliability Upgrade | 1a | 716 | Central Maine Power Company |  | 2008-08-01 | Maguire Road Project | Reconductor South Gorham to Louden 115 kV Line S220. | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 03/01/2007 | No | 3000000 | 3000000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
Reliability Upgrade | 1a | 149 | Central Maine Power Company |  | 2008-08-01 | Maguire Road Project | Convert Maguire Road to a switching substation by replacing switches with breakers. | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 03/01/2007 | No | 7500000 | 7500000 | 17700000 | 17700000 | 17700000 | 17700000 | 17700000 | 17700000
Reliability Upgrade | 1a | 717 | Central Maine Power Company |  | 2008-08-01 | Maguire Road Project | Install a 115 kV 50 MVAr capacitor bank at Maguire Road. | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 03/01/2007 | No | 1500000 | 1500000 | Portion of $17,700,000 (above) | Portion of $17,700,000 (above) | Portion of $17,700,000 (above) | Portion of $17,700,000 (above) | Portion of $17,700,000 (above) | Portion of $17,700,000 (above)
Reliability Upgrade | 1a | 155 | Central Maine Power Company | Northeast Utilities | 01/2009 | Maguire Road Project | Rebuild Three Rivers - Quaker Hill 115 kV Line K197. | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | 03/01/2007 | 2009-01-09 | 3000000 | 3000000 | 5500000 | 5500000 | 5500000 | 5500000 | 5500000 | 5500000
Reliability Upgrade | 1a | 461 | Central Maine Power Company |  | 12/2007 | MEPCO SPS | Redesign/replacement of the Maxcy's Cross Trip and Bucksport Overcurrent Type 1 Special Protection Systems. | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 03/24/2006 | No | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000
Reliability Upgrade | 1a | 147 | Central Maine Power Company |  | 02/2008 | Raymond Substation Project | Add 115/34.5 kV transformer at Raymond Substation on Section 208/209 along with (2) 115 kV in-line circuit breakers. | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 06/01/2006 | No | 4800000 | 1523000 | 1523000 | 1523000 | 1523000 | 1523000 | 1523000 | 1523000
Reliability Upgrade | 1a | 627 | Central Maine Power Company |  | 12/2007 | Rumford-Woodstock-Kimball Road Corridor Project | Reterminate (3) 115 kV lines and add (2) bus-tie breakers at Kimball Road. | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2007-11-30 | 2008-03-31 | TBD | 2441000 | 2441000 | 2441000 | 2441000 | 2441000 | 2441000 | 2441000
Reliability Upgrade | 1a | 910 | Central Maine Power Company |  | 12/2008 | Rumford-Woodstock-Kimball Road Corridor Project | Rebuild Section 211 Woodstock - Rumford. | Proposed | Concept | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 2007-11-30 | No | TBD | TBD | 6800000 | 6800000 | 8400000 | 8400000 | 8400000 | 8400000 |  | 0
Reliability Upgrade | 1a | 626 | Central Maine Power Company |  | 04/2009 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of 115/34.5 kV transformer and six new 115 kV breakers and a half substation at Woodstock. | Proposed | Concept | Planned | Planned | Planned | In-service | In-service | In-service | 2007-11-30 | No | TBD | TBD | 7400000 | 7400000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 0 | 0
Reliability Upgrade | 1a | 575 | Central Maine Power Company |  | 05/2009 | Heywood Road Project | New Heywood Rd 115kV switchyard with (6) 115kV circuit breakers (3) 115kV line retensionings and 115kV 20 MVAr capacitor bank at Heywood Rd. | Planned | Concept | Concept | Concept | Under Construction | In-service | In-service | In-service | 2009-03-20 | 2009-07-20 | 10100000 | 10100000 | 6100000 | 6100000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 0 | 1
Reliability Upgrade | 1a | 1127 | Central Maine Power Company |  | 05/2009 | CMP-LSP Newcastle Substation | Add 115/34kV transformer with two 115kV breakers |  | Concept | Planned |  | Under Construction | In-service | In-service | In-service | 2008-08-20 | 2008-08-20 | TBD | TBD | Portion of 5,400,000 (above) |  | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 0 | 1
Reliability Upgrade | 1a | 267 | Northeast Utilities | Central Maine Power Company | 2009-08-01 | Y138 Closing | White Lake - Saco Valley (Y138) Line Closing - Add PAR on Y138 at Saco Valley, retension lines, upgrade Beebe terminal, and add capacitor banks at White Lake and Beebe. | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | 01/01/2006 | No | 28565000 | 28412000 | 28412000 | 28412000 | 27775000 | 27775000 | 27775000 | 27775000 | 27775000 | 0 | 0
Reliability Upgrade | 1a | 936 | National Grid, USA |  | 07/2009 | Central/Western Massachusetts Upgrades | Reconductor (P142/P142S) Rolfe Avenue - West Bolyston 115 kV line w/1590 ACSR. | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | 12/17/2007 | No | 2107320 | 2107320 | 2107320 | 2890000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 0 | 1
Reliability Upgrade | 1a | 923 | National Grid, USA |  | 12/2008 | Auburn Area Transmission System Upgrades | Reconductor 115 kV A94 line and associated substation upgrades. | Proposed | Concept | Concept | Planned | In-Service | In-Service | In-Service | In-Service | 2008-01-28 | No | 2870000 | 2870000 | 2870000 | 3400000 | 2400000 | 2400000 | 2400000 | 2400000 |  | 0
Reliability Upgrade | 1a | 922 | National Grid, USA |  | 02/2009 | Auburn Area Transmission System Upgrades | Reconductor 115kV L1 line and associated substation upgrades. | Proposed | Concept | Concept | Planned | In-Service | In-Service | In-Service | In-Service | 2008-01-28 | No | 700000 | 700000 | 700000 | 1050000 | 800000 | 800000 | 800000 | 800000 |  | 0
Reliability Upgrade | 1a | 543 | National Grid, USA |  | 2008-08-01 | Greater Rhode Island Transmission Reinforcements | New Tower Hill Rd. Substation tapped off of (G185S) 115 kV line. | Proposed | Concept | Planned | In-Service | In-Service | In-Service | In-Service | In-Service | 2008-04-25 | No | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000
Reliability Upgrade | 1a | 774 | National Grid, USA |  | 10/2007 | Merrimack Valley/North Shore Reliability Project | Reconductor G-133W 115 kV line and replace terminal equipment at West Methuen. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 06/01/2007 | No | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000
Reliability Upgrade | 1a | 778 | National Grid, USA |  | 07/2008 | Merrimack Valley/North Shore Reliability Project | Reconductor S-145/T146 115 kV lines between Wakefield Jct. and Golden Hills Tap. | Proposed | Concept | Concept | In-Service | In-Service | In-Service | In-Service | In-Service | 2008-04-01 | No | 3750000 | 3750000 | 3750000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000
Reliability Upgrade | 1a | 781 | National Grid, USA |  | 10/2008 | Merrimack Valley/North Shore Reliability Project | Install 115 kV 30 MVAr capacitor bank at Revere. | Proposed | Concept | Concept | Planned | In-Service | In-Service | In-Service | In-Service | 2008-04-01 | No | 1900000 | 1900000 | 1900000 | 1500000 | 1727000 | 1727000 | 1727000 | 1727000 |  | 0
Reliability Upgrade | 1a | 169 | National Grid, USA |  | 11/2007 | Southwest Rhode Island Reliability Enhancements | Reconductor W. Kingston - Kenyon 115 kV 1870N line. | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 2005-01-01 | 03/29/2005 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000
Reliability Upgrade | 1a | 170 | National Grid, USA |  | 03/2008 | Southwest Rhode Island Reliability Enhancements | Extend L-190 line to W. Kingston. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 11/10/2004 | 03/29/2005 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000
Reliability Upgrade | 1a | 173 | National Grid, USA |  | 03/2008 | Southwest Rhode Island Reliability Enhancements | Rebuild W. Kingston to include 115 kV ring bus. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 11/10/2004 | 03/29/2005 | 4830000 | 4830000 | 4830000 | 4830000 | 4830000 | 4830000 | 4830000 | 4830000
Reliability Upgrade | 1a | 168 | National Grid, USA |  | 09/2008 | Southwest Rhode Island Reliability Enhancements | Reconductor Kenyon - Wood River 115 kV 1870 line. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 2005-01-01 | 03/29/2005 | 2600000 | 2600000 | 2600000 | 2600000 | 2234232 | 2234232 | 2234232 | 2234232 |  | 0
Reliability Upgrade | 1a | 171 | National Grid, USA |  | 10/2008 | Southwest Rhode Island Reliability Enhancements | Reconductoring L-190 between Kent Co. and Davisville. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 11/10/2004 | 03/29/2005 | 3000000 | 3000000 | 3000000 | 3000000 | 2666291 | 2666291 | 2666291 | 2666291 |  | 0
Reliability Upgrade | 1a | 900 | National Grid, USA |  | 11/2008 | Southwest Rhode Island Reliability Enhancements | Wood River substation upgrades. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 04/07/2007 | 05/07/2007 | 240000 | 240000 | 240000 | 240000 | 130000 | 130000 | 130000 | 130000 |  | 0
Reliability Upgrade | 1a | 899 | National Grid, USA |  | 12/2008 | Southwest Rhode Island Reliability Enhancements | Kenyon substation upgrades. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 04/07/2007 | 05/07/2007 | 278000 | 278000 | 278000 | 278000 | 278000 | 278000 | 278000 | 278000
Reliability Upgrade | 1a | 594 | National Grid, USA |  | 07/2008 |  | Upgrade the Auburn 345 kV breaker #2130 with an IPT breaker. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 10/01/2006 | 10/01/2006 | 720000 | 720000 | 720000 | 720000 | 720000 | 720000 | 720000 | 720000 |  | 0
Reliability Upgrade | 1a | 166 | National Grid, USA |  | 06/2009 |  | Replace (16) 115 kV breakers at Tewksbury 22. | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | NR | NR | 1500000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 0 | 0
Reliability Upgrade | 1a | 176 | Northeast Utilities |  | 07/2009 | Monadnock Area Reliability Project | New Fitzwilliam 345/115kV substation along with 345 kV breakers. | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | 2007-09-27 | No | 54358000 | 54358000 | 54358000 | 76100000 | 76100000 | 76100000 | 76100000 | 76100000 | 76100000 | 0 | 0
Reliability Upgrade | 1a | 174 | National Grid, USA |  | 06/2009 | Monadnock Area Reliability Project | Reconductor I-135 (Bellows Falls-Monadnock Tap-Flagg Pond) 115 kV line. | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | 03/24/2006 | No | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 15778000 | 15778000 | 15778000 | 15778000 | 0 | 0
Reliability Upgrade | 1a | 179 | Northeast Utilities |  | 02/2008 | Monadnock Area Reliability Project | Rebuild 115-kV Jackman to Greggs F-162 line. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 03/24/2006 | No | Portion of 54,358,000 (above) | Portion of 54,358,000 (above) | Portion of 54,358,000 (above) | Portion of 54,358,000 (above) | Portion of 54,358,000 (above) | Portion of 54,358,000 (above) | Portion of 54,358,000 (above) | Portion of 54,358,000 (above)
Reliability Upgrade | 1a | 177 | Northeast Utilities |  | 12/2008 | Monadnock Area Reliability Project | Replace limiting terminal equipment at Webster Substation on line to North Road. | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | 03/24/2006 | No | Portion of 54,358,000 (above) | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 180 | Northeast Utilities |  | 12/2008 | Monadnock Area Reliability Project | Rebuild 115 kV Keene to Swanzey A-152 line. | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | 03/24/2006 | No | Portion of 54,358,000 (above) | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 178 | Northeast Utilities |  | 02/2009 | Monadnock Area Reliability Project | Rebuild 115 kV Garvins to Webster V-182 line. | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 03/24/2006 | No | Portion of 54,358,000 (above) | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 569 | Northeast Utilities-CT |  | 2007 | Norwalk-Glenbrook Cable Project | Replace two 115-kV circuit breakers at Cos Cob. | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 08/01/2005 | No | 500000 | 500000 | 500000 | 500000 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 |  | -500000
Reliability Upgrade | 1a | 243 | Northeast Utilities |  | 09/2008 | Norwalk-Glenbrook Cable Project | Expand and upgrade to BPS and remove SPS at Glenbrook 115 kV substation. | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 08/01/2005 | No | 8350000 | 8390000 | 8390000 | 8390000 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 |  | -8390000
Reliability Upgrade | 1a | 570 | Northeast Utilities |  | 10/2008 | Norwalk-Glenbrook Cable Project | Add second high speed relay system on the 1450 line. | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 08/01/2005 | No | 792000 | 788000 | 788000 | 788000 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 |  | -788000
Reliability Upgrade | 1a | 571 | Northeast Utilities |  | 12/2008 | Norwalk-Glenbrook Cable Project | Upgrade Flax Hill Substation to BPS. | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 08/01/2005 | No | 2175000 | 2175000 | 2175000 | 2175000 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 |  | -2175000
Reliability Upgrade | 1a | 248 | Northeast Utilities |  | 12/2008 | Norwalk-Glenbrook Cable Project | Install two new 115 kV cables from Norwalk to Glenbrook (accommodate 345 kV class cable). | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 08/01/2005 | No | 183230000 | 222850000 | 222850000 | 222850000 | 249,372,000 3 | 249,372,000 3 | 249,372,000 3 | 249,372,000 3 |  | -222850000
Reliability Upgrade | 1a | 208 | Northeast Utilities |  | 12/2008 | NU LSP - Oxford Substation | Install new Oxford (previously Jack's Hill) 115 kV substation. | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | 06/01/2007 | 5710287 | 5710287 | 5710287 | 5710287 | 4459000 | 4459000 | 4459000 | 4459000 |  | 0
Reliability Upgrade | 1a | 201 | Northeast Utilities |  | 05/2008 | NU LSP - Wilton Substation | Install new 115 kV Wilton Substation. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 2008-04-25 | 08/01/2006 | 3915000 | 3915000 | 3915000 | 3915000 | 3915000 | 3915000 | 3915000 | 3915000
Reliability Upgrade | 1a | 551 | Northeast Utilities |  | 10/2007 | Southwest Connecticut Reliability Project PH II (M-N) | Rebuild the 1466 115-kV line from East Meriden to North Wallingford and the 1588 115-kV rebuild from North Wallingford to Colony. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 04/01/2007 | No | 805000 | 805000 | 805000 | 805000 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 |  | -805000
Reliability Upgrade | 1a | 236 | Northeast Utilities |  | 2008-03-01 | Southwest Connecticut Reliability Project PH II (M-N) | Rebuild 115 kV lines (1640,1685,1610) between Devon and Cook Hill Jct. (UG section of 1640 near Cook Hill). | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 228 | Northeast Utilities |  | 2008-03-19 | Southwest Connecticut Reliability Project PH II (M-N) | Installation of new Beseck Jct. 345 kV switching station in Wallingford. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 04/01/2007 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 222 | Northeast Utilities |  | 2008-03-27 | Southwest Connecticut Reliability Project PH II (M-N) | Install new 345 kV line from Scovill Rock to Chestnut Jct. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | 1047000000 | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 223 | Northeast Utilities | United Illuminating Company | 2008-03-28 | Southwest Connecticut Reliability Project PH II (M-N) | Install (2) new 345 kV lines from Black Pond Jct. to Beseck Jct. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 02/01/2007 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 225 | Northeast Utilities |  | 2008-03-28 | Southwest Connecticut Reliability Project PH II (M-N) | Install new 345 kV line from Oxbow Jct. to Beseck Jct. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 237 | Northeast Utilities |  | 2008-04-28 | Southwest Connecticut Reliability Project PH II (M-N) | Rebuild 115-kV lines-1975 from Beseck to Oxbow Junction and 1655 from East Wallingford Jct. to New Haven Jct. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 244 | Northeast Utilities |  | 2008-06-20 | Southwest Connecticut Reliability Project PH II (M-N) | Reconductor 115 kV 1570 and 1575 line taps into Beacon Falls Substation. | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 2008-04-25 | No | 5887000 | 5887000 | 5692000 | 5692000 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 |  | -5692000
Reliability Upgrade | 1a | 239 | Northeast Utilities |  | 07/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install (1) new 115 kV circuit breaker at Devon Substation in series with 7R-2T. | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | 5206000 | 5206000 | 5009000 | 5009000 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 |  | -5009000
Reliability Upgrade | 1a | 245 | Northeast Utilities |  | 07/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Disconnect Milford Power from Devon Substation and reconnect to East Devon Jct. Substation. | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 227 | Northeast Utilities |  | 2008-08-01 | Southwest Connecticut Reliability Project PH II (M-N) | Install new 345 kV line from Beseck Jct. to East Devon. | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 229 | Northeast Utilities | United Illuminating Company | 2008-08-01 | Southwest Connecticut Reliability Project PH II (M-N) | Install new East Devon 345 kV substation and new East Devon 115 kV substation in Milford. | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 232 | Northeast Utilities |  | 09/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install two 115 kV circuits between East Devon and Devon. | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | 1047000000 | 1047000000 | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 246 | Northeast Utilities |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Add second 345/115 kV autotransformer at Norwalk Substation along with shunt reactors and 345 kV circuit breakers. | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | 1047000000 | $978,182,000 4 | $978,182,000 4 | $978,182,000 4 | $978,182,000 4 |  | 0
Reliability Upgrade | 1a | 226 | Northeast Utilities | United Illuminating Company | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install two 345 kV underground cables from Singer(UI) to Norwalk. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 235 | Northeast Utilities |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Expand Norwalk 345-kV substation and install transfer trip relaying scheme on the 1389 115 kV line between Norwalk and Flax Hill. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 247 | Northeast Utilities |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Replace Norwalk Harbor 138/115 kV autotransformer. | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | 8351000 | 8351000 | 8351000 | 8351000 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 |  | -8351000
Reliability Upgrade | 1a | 684 | Northeast Utilities |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Replace (6) 115 kV breakers (4-Glenbrook, 1-Glenbrook Statcom, 1-Southington #1) and (3) 345-kV circuit breakers at Millstone and replace (4) 345- kV breakers with 500-kV breakers at Long Mountain substation. | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | 11321000 | 11321000 | 11321000 | 11321000 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 |  | -11321000
Reliability Upgrade | 1a | 202 | Northeast Utilities |  | 05/2008 |  | Install new 345/115 kV autotransformer at Barbour Hill Substation. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 09/30/2006 | 2008-02-07 | 44153000 | 44153000 | 44153000 | 44153000 | 44153000 | 44153000 | 44153000 | 44153000
Reliability Upgrade | 1a | 104 | Northeast Utilities |  | 07/2008 |  | Replace 138-kV Norwwalk (CT)-Northport(NY) 1385 cable. | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 2002-12-01 | 2007-06-01 | 71743727 | 71743727 | 71743727 | 71743727 | 71743727 | 71743727 | 71743727 | 71743727
Reliability Upgrade | 1a | 250 | Northeast Utilities |  | 12/2008 |  | Add a 345 kV breaker at Ludlow Substation. | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | 06/01/2007 | 2007-08-01 | 1800000 | 1644885 | 1644885 | 1644885 | 1644885 | 1644885 | 1644885 | 1644885
Reliability Upgrade | 1a | 1009 | Northeast Utilities |  | 05/2009 |  | Install a 2% reactor on the North Bloomfield-Canton 115kV line and also replacement fo the Frostbridge 345/115kV autotransformer | Proposed | Concept | Planned | Under Construction | Under Construction | In-service | In-service | In-service | 2007-10-20 | 2009-10-16 | TBD | TBD | 2075000 | 2075000 | 3638000 | 3089000 | 3089000 | 3089000 | 3089000 | 0 | 0
Reliability Upgrade | 1a | 203 | Northeast Utilities |  | 05/2009 | NU LSP - Stepstone Substation | Install new Stepstone 115 kV substation in Guilford. | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | 2005-11-08 | 2006-04-24 | 4465000 | 4465000 | 4465000 | 4465000 | 6332000 | 6332000 | 6332000 | 6332000 | 6332000 | 0 | 0
Reliability Upgrade | 1a | 841 | NSTAR Electric Company |  | 11/2008 | Mystic Breaker Additions Project | Install (2) new 115 kV West Bus breakers #29 and #31 at Mystic. | Proposed | Planned | Planned | Planned | In-Service | In-Service | In-Service | In-Service | 2008-03-10 | No | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000
Reliability Upgrade | 1a | 1040 | NSTAR Electric Company |  | 12/2008 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #11, #8, #17 and #3 at Mystic to IPT | Planned | Planned | Planned | Planned | In-Service | In-Service | In-Service | In-Service | NR | NR | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000
Reliability Upgrade | 1a | 116 | NSTAR Electric Company |  | 04/2009 | NSTAR 345 kV Transmission Reliability Project | Add 2nd 345 kV UG Cables from Stoughton to Mattapan Sq.to K Street and install another new autotransformer at K. St. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 02/10/2005 | 09/15/2005 | 283144600 | 283144600 | 283144600 | 307900000 | 307900000 | 307900000 | 307900000 | 307900000
Reliability Upgrade | 1a | 572 | NSTAR Electric Company |  | 04/2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 345 kV 160 MVAR shunt reactors at Stoughton. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 02/10/2005 | 09/15/2005 | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 573 | NSTAR Electric Company |  | 04/2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 345 kV 160 MVAR shunt reactors at K St. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 02/10/2005 | 09/15/2005 | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 772 | NSTAR Electric Company |  | 04/2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 115 kV breaker at K St. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 02/01/2005 | 09/01/2005 | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 574 | NSTAR Electric Company |  | 12/2007 | NSTAR LSP - Colburn St Substation | Add 4th 115/14 kV transformer and (2) 115 kV breakers at Colburn St. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 12/01/2004 | NR | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000
Reliability Upgrade | 1a | 694 | NSTAR Electric Company |  | 06/2008 | Short Term Lower SEMA Upgrades | Add new 115 kV line from Brook Street to Auburn Street. | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 08/17/2007 | No | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000
Reliability Upgrade | 1a | 833 | NSTAR Electric Company |  | 06/2008 | Short Term Lower SEMA Upgrades | Add (5) new 115 kV circuit breakers at Brook Street. | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 08/17/2007 | No | 7900000 | 7900000 | 7900000 | 7900000 | 7900000 | 7900000 | 7900000 | 7900000
Reliability Upgrade | 1a | 960 | NSTAR Electric Company |  | 06/2008 | Short Term Lower SEMA Upgrades | Install a new 115kV line termination at Auburn St south bus. | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 08/17/2007 | No | 3060000 | 3060000 | 3060000 | 3060000 | 3060000 | 3060000 | 3060000 | 3060000
Reliability Upgrade | 1a | 832 | NSTAR Electric Company |  | 07/2009 | Short Term Lower SEMA Upgrades | Add(1) 115kV SVC (0-112 MVARs lagging) at Barnstable. | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | 08/17/2007 | No | 16000000 | 16000000 | 16000000 | 16000000 | $86.6 M (Total NSTAR Project Cost | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade | 82000000 | -4600000 | 0
Reliability Upgrade | 1a | 695 | NSTAR Electric Company |  | 07/2009 | Short Term Lower SEMA Upgrades | Loop (355) 345 kV line in and out of Carver Substation and add (5) new 345 kV circuit breakers at Carver substation. | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | 08/17/2007 | No | 10800000 | 10800000 | 10800000 | 10800000 | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | -4600000 | 1
Reliability Upgrade | 1a | 830 | NSTAR Electric Company |  | 07/2009 | Short Term Lower SEMA Upgrades | Add a second 345/115 kV Auto transformer at Carver substation and add (1) new 345 kV circuit breaker and (3) new 115 kV circuit breakers at Carver substation. | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | 08/17/2007 | No | 8000000 | 8000000 | 8000000 | 8000000 | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA |  | 1
Reliability Upgrade | 1a | 831 | NSTAR Electric Company |  | 07/2009 | Short Term Lower SEMA Upgrades | Add a second 115 kV line from Carver to Tremont and add (2) new 115 kV circuit breakers at Carver substation and (1) new 115 kV circuit breaker at Tremont substation. | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | 08/17/2007 | No | 2500000 | 2500000 | 2500000 | 2500000 | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA |  | 1
Reliability Upgrade | 1a | 713 | NSTAR Electric Company |  | 09/2007 |  | Add 115 kV 20 MVAr capacitor bank at Harwich/Harwich Tap. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 06/01/2007 | NR | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000
Reliability Upgrade | 1a | 838 | NSTAR Electric Company |  | 10/2007 |  | Upgrade Canal 345 kV breaker #512 to IPT. | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000
Reliability Upgrade | 1a | 500 | NSTAR Electric Company |  | 11/2007 |  | Install new 115 kV circuit breaker at Sandwich. | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2008-02-05 | NR | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
Reliability Upgrade | 1a | 834 | NSTAR Electric Company |  | 06/2008 |  | Upgrade Canal 345 kV breaker #112 to IPT. | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | NR | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000
Reliability Upgrade | 1a | 1064 | NSTAR Electric Company |  | 04/2009 |  | Install (1) 345kV 160 MVAR shunt reactor at Mystic Station |  |  |  | Planned | Planned | In-service | In-service | In-service | 2008-09-26 | No |  |  |  | 8000000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 0 | 0
Reliability Upgrade | 1a | 302 | NSTAR Electric Company |  | 05/2009 | Boston Area 115 kV Enhancements | DCT separation of Framingham to Speen St. 433-507 circuit. | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | 01/18/2005 | 03/01/2005 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 0 | 0
Reliability Upgrade | 1a | 238 | United Illuminating Company |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Build new Singer 345 kV substation with (12) circuit breakers, (2) autos, (4) shunt reactors along with reconnecting Bridgeport Energy thru one of the new autos. Includes 115 kV connection from Singer to Pequonnock substation. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | 147000000 | 147000000 | 162264000 | 162264000 | 162264000 | 162264000 | 162264000 | 162264000
Reliability Upgrade | 1a | 224 | United Illuminating Company | Northeast Utilities | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install new 345 kV line from East Devon to Singer(UI). | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | 159000000 | 159000000 | 157476000 | 157476000 | 157476000 | 157476000 | 157476000 | 157476000
Reliability Upgrade | 1a | 313 | United Illuminating Company | Northeast Utilities | 06/2008 | UI LSP - Trumbull Substation | New Trumbull 115/13.8 kV Substation and 115 kV switching station. | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 2008-03-13 | No | 5500000 | 8930000 | 8930000 | 8930000 | 8930000 | 8930000 | 8930000 | 8930000
Reliability Upgrade | 1a | 845 | United Illuminating Company |  | 05/2008 |  | Replace Quinnipiac 115 kV Oil Circuit Breaker. | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | NR | 400000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000
Reliability Upgrade | 1a | 846 | United Illuminating Company |  | 11/2008 |  | Replace Mix Avenue 115 kV Oil Circuit Breaker & foundation. | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | NR | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 |  | 0
Reliability Upgrade | 1a | 410 | Vermont Electric Power Company |  | 12/2004 | Northwest Vermont Reliability Project | Sandbar PAR | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 01/10/2003 | 03/31/2003 | 6100000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 |  | 0
Reliability Upgrade | 1a | 132 | Vermont Electric Power Company |  | 12/2005 | Northwest Vermont Reliability Project | Hartford 115kV Breaker - Replace an existing 115kV motorized SCADA controlled disconnect switch with a circuit breaker at Hartford substation on the line toward Wilder sub and add one 25 MVAR cap. Bank | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 01/10/2003 | 03/31/2003 | 2200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 |  | 0
Reliability Upgrade | 1a | 133 | Vermont Electric Power Company |  | 12/2005 | Northwest Vermont Reliability Project | Essex K24 Line Breaker | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 01/10/2003 | 03/31/2003 | 800000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 |  | 0
Reliability Upgrade | 1a | 135 | Vermont Electric Power Company |  | 12/2006 | Northwest Vermont Reliability Project | Blissville PAR | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 01/10/2003 | 2006-12-18 | 8400000 | 10100000 | 10100000 | 10100000 | 10100000 | 10100000 | 10100000 | 10100000 |  | 0
Reliability Upgrade | 1a | 137 | Vermont Electric Power Company |  | 01/2007 | Northwest Vermont Reliability Project | New Haven-West Rutland 345kV line, 345/115 New Haven Sub with 115kV ring bus, and close the 345 kV ring bus at West Rutland | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 01/10/2003 | 2006-12-18 | 66400000 | 83300000 | 83300000 | 83300000 | 83300000 | 83300000 | 83300000 | 83300000 |  | 0
Reliability Upgrade | 1a | 134 | Vermont Electric Power Company |  | 11/2007 | Northwest Vermont Reliability Project | Convert Williston into a ring bus configuration. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 01/10/2003 | 03/31/2003 | 4300000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 |  | 0
Reliability Upgrade | 1a | 138 | Vermont Electric Power Company |  | 12/2008 | Northwest Vermont Reliability Project | N. Haven - Vergennes - Q. City 115 kV line. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/10/2003 | 2006-12-18 | 56200000 | 70200000 | 70200000 | 70200000 | 70200000 | 70200000 | 70200000 | 70200000 |  | 0
Reliability Upgrade | 1a | 136 | Vermont Electric Power Company |  | 04/2009 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 1: two 115 kV PARs, four 25 MVAR Cap. banks, four +25/-12.5 MVAR synchronous condenders, and two 230/115 transformers. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/10/2003 | 03/31/2003 | 60800000 | 62400000 | 62400000 | 62400000 | 62400000 | 62400000 | 62400000 | 62400000 |  | 0
Reliability Upgrade | 1a | 182 | Vermont Electric Power Company |  | 09/2009 | Monadnock Area Reliability Project | Upgrade bus cable at N. Rutland and K35 115 kV breaker at Rutland. | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | 03/24/2006 | NR | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 0 | 0
Generator Interconnection Upgrade | 2a | 847 | Bangor Hydro-Electric Company |  | 12/2008 | Stetson Wind | Interconnect 60 MW of wind via 115 kV generator lead into Keene Road Substation. | Proposed | Planned | Planned | Planned | In-Service | In-Service | In-Service | In-Service | 07/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2a | 621 | Northeast Utilities |  | 10/2007 | AL Pierce | Interconnection to Wallingford (CMEEC) substation. | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2007-03-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2a | 727 | Northeast Utilities |  | 12/2007 | CL&P P&WA Aircraft Substation | CL&p P&WA Aircraft Substation. | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 01/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2a | 728 | Northeast Utilities |  | 06/2008 | Cos Cob Redevelopment | Installation of a second high-speed protection system on the 1440 115 kV line. | Proposed | Planned | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 06/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR
CANCELLED PROJECTS
Elective | 4b | 984 | Central Maine Power Company | Maine Public Service | TBD | MEPCO-MPS 345 kV Interconnection | MEPCO-MPS 345 kV Interconnection. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Reliability Upgrade | 1b | 275 | Northeast Utilities |  | TBD |  | Merrimack 115-kV substation - Protection Separation Upgrade. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Generator Interconnection Upgrade | 2a | 327 | Central Maine Power Company |  | 12/2010 | Queue Position 138 | Separate Section 215 from Section 63 and terminate Section 215 at newly established breaker position in Wyman Hydro S/S, which includes re-rating of Section 215. Expand Bigelow S/S and add capacitor banks at Lakewood, Guilford, and Sturtevant S/S's. |  |  |  | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | 2003-12-03 | NR |  |  |  |  | NR | NR | NR | NR | 0
Reliability Upgrade | 1b | 912 | Central Maine Power Company |  | 12/2009 | CMP LSP - Anson Substation | Add 115 kV circuit breakers and transformer at Anson Section 63. | Proposed | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | TBD | TBD | TBD | NR | NR | NR | NR |  | 1
Reliability Upgrade | 1b | 106 | Northeast Utilities |  | TBD |  | Upgrade the Southwest Hartford Substation to Bulk Power System standards (BPS). | Planned | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | 08/04/2004 | No | TBD | TBD | TBD | TBD | TBD | NR | NR | NR | NR |  | 1
Reliability Upgrade | 1b | 1069 | NSTAR Electric Company |  | 07/2011 | NPCC BPS Compliance | Bourne Station |  |  |  | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | No | No |  |  |  | 8800000 | NR | NR | NR | NR | NR |  | 1
Reliability Upgrade | 1a | 187 | Vermont Electric Power Company |  | 12/2010 | Monadnock Area Reliability Project | Coolidge +/- 75 MVAr STATCOM with 50 MVArs of new capacitors at Coolidge and functional dynamic equivalent. | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | 03/24/2006 | No | 30000000 | 50000000 | 50000000 | NR | NR | NR | NR | NR | NR | -50000000 | 1
Reliability Upgrade | 1b | 920 | National Grid, USA |  | 06/2010 | Auburn Area Transmission System Upgrades | Belmont substation - Upgrade Bus work. | Proposed | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | 2008-01-28 | No | 470000 | 470000 | 470000 | NR | NR | NR | NR | NR | NR | -470000 | 1
Reliability Upgrade | 1b | 1117 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install 115kV 50 MVAR capacitor bank at Falmouth |  |  |  | Concept | Proposed | Proposed | Cancelled | Cancelled | No | No | 5000000 | 5000000 | 5000000 | TBD | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA |  | 0
Reliability Upgrade | 1b | 337 | NSTAR Electric Company |  | 12/2010 | Long Term Lower SEMA Upgrades | Canal to Oak Street #399 345 kV line. | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR |  | 1
Reliability Upgrade | 1b | 338 | NSTAR Electric Company |  | 12/2010 | Long Term Lower SEMA Upgrades | Move Canal 345/115 Auto-transformer to Oak Street. | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR |  | 1
Reliability Upgrade | 1b | 967 | NSTAR Electric Company |  | 12/2010 | Boston Area 115 kV Enhancements | Reconductor N. Woburn Tap to Reading Tap (Line 211-503 & 211-504). | Proposed | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | 2000000 | 2000000 | 2000000 | NR | NR | NR | NR | NR | NR | -2000000 | 1
Reliability Upgrade | 1b | 808 | Northeast Utilities |  | TBD |  | Upgrade Scitico substation. | Proposed | Concept | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | 9000000 | NR | NR | NR | NR | NR | NR | -9000000 | 1
Generator Interconnection Upgrade | 2b | 861 | Northeast Utilities |  | 01/2010 | Queue Position 190 | Mount Tom - W Mass. Mt. Tom 115 kV Substation. | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2b | 869 | Northeast Utilities |  | 06/2013 | Queue Position 226 | Rebuild 345 kV 326 Line | Proposed | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2b | 1041 | Northeast Utilities |  | 06/2013 | Queue Position 226 | Rebuild 115 kV U181 Line | Proposed | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Reliability Upgrade | 1b | 258 | Northeast Utilities |  | 2010-2011 | Springfield 115 kV Reinforcements | Retire low capacity Breckwood to East Springfield 115-kV cable. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 686 | Northeast Utilities |  | 2010-2011 | Springfield 115 kV Reinforcements | Installation of a new 115-kV cable circuit between East Springfield and Clinton Substations. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 827 | Northeast Utilities |  | 2010-2011 | Springfield 115 kV Reinforcements | Installation of two 115-kV cable circuits between East Springfield and Breckwood substations. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 496 | Northeast Utilities |  | 2011-2013 | Springfield 115 kV Reinforcements | Additional uprating or rebuilding of the existing 115 kV overhead lines in the Springfield area. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 822 | Massachusetts Municipal Whol | Northeast Utilities | 2011-2013 | NEEWS (Greater Springfield Reliability Project) | Install two new 115-kV lines from Stony Brook (MMWEC) to line tap#1113 and tap #1134. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 999 | Northeast Utilities |  | 2011-2013 | NEEWS (Greater Springfield Reliability Project) | Replace West Springfield to Breckwood 115 kV cable. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 821 | Northeast Utilities |  | 2011-2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild/Reconductor a portion of the Fairmont 1134 and 1113 115-kV lines up to where it taps the new Stony Brook lines. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 813 | Northeast Utilities |  | 2011-2013 | NEEWS (Central Connecticut Reliability Project) | Add 345-kV shunt reactors at Frost Bridge, and North Bloomfield substations. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 815 | Northeast Utilities |  | 2011-2013 | NEEWS (Central Connecticut Reliability Project) | Reconductor the East Hartford to the Riverside tap 1786 115-kV line. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 803 | Northeast Utilities |  | 2011-2013 | NEEWS (Interstate Reliability Project) | Reconfigure the Millstone to Manchester 310 line into Card 345-kV substation. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 805 | Northeast Utilities |  | 2011-2013 | NEEWS (Interstate Reliability Project) | Install new Northwest Hartford to Southwest Hartford 115kV cable. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 806 | Northeast Utilities |  | 2011-2013 | NEEWS (Interstate Reliability Project) | Install new Southwest Hartford to South Meadow 115 kV Cable. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1126 | Northeast Utilities |  | TBD | Queue Position 161-4 | Two units and repowering of #6 Montville 345kV Substation | Planned | Concept | Concept |  | Proposed | Cancelled | Cancelled | Cancelled | 2008-06-09 | NR | TBD | TBD | TBD |  | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 316 | United Illuminating Company |  | 06/2012 |  | New Fairfield 115/13.8 kV substation | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | No | No | 5500000 | 14030000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 0 | 0
Reliability Upgrade | 1b | 977 | United Illuminating Company |  | 06/2013 |  | New Orange 115/13.8 kV substation | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | No | No | 5500000 | 14450000 | 7550000 | 7550000 | 7550000 | 7550000 | 7550000 | 7550000 | 7550000 | 0 | 0
Reliability Upgrade | 1b | 980 | United Illuminating Company |  | 06/2014 |  | New Hamden 115/13.8 kV substation. | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | No | No | 5500000 | 15330000 | 7750000 | 7750000 | 7750000 | 7750000 | 7750000 | 7750000 | 7750000 | 0 | 0
Reliability Upgrade | 1b | 317 | United Illuminating Company |  | 06/2014 |  | New North Branford 115/13.8-kV substation. | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | No | No | 4000000 | 16260000 | 7750000 | 7750000 | 7750000 | 7750000 | 7750000 | 7750000 | 7750000 | 0 | 0
Reliability Upgrade | 1a | 608 | United Illuminating Company |  | 12/2012 |  | Upgrade Water Street, Broadway, Mill River, West River, Baird, Bridgeport RESCO, and Devon Tie substations to BPS standards. | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | 2006-01-20 | No | 19500000 | 19500000 | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 249 | Northeast Utilities |  | TBD |  | Install new 115 kV line from Norwalk Harbor Station to Glenbrook Substation (accommodate 345 kV class cable). | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Generators w/ NO Feasibility Study completed - hide from Project List for now!
Generator Interconnection Upgrade | 2b | 737 | Northeast Utilities |  | 06/2010 | Queue Position 161 | Montville Substation. | Proposed | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1017 | Northeast Utilities |  | 09/2009 | Queue Position 222 | Haddam Neck-Southington 345-kV line. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 882 | United Illuminating Company | Northeast Utilities | 12/2009 | Queue Position 193 | Ansonia - UI Ansonia 115 kV substation. | Concept | Proposed | Proposed | Proposed | Proposed |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 982 | Northeast Utilities |  | 05/2010 | Queue Position 181 | Lake Road #4 - tap the 345 kV line. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1037 | Vermont Electric Power Company | Central Vermont Public Service | 12/2010 | Queue Position 134 | Installation of 3-breaker 115kV ring bus interconnection on the Bennington-Searsburg 69kV Y25N Line. |  | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2b | 619 | Northeast Utilities |  | 07/2010 | Queue Position 125 | Interconnection to CL&P's Norwalk Harbor substation. | Proposed | Proposed | Proposed | Proposed | Proposed |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generators w/ NO interconnection upgrades required! (RESERVE IN SPITS and REMOVE FROM PROJECT LISTING)
Generator Interconnection Upgrade | 2b | 730 | Northeast Utilities |  | 05/2008 | Queue Position 160 | CL&P Middletown Substation. | Concept | Proposed | Proposed | Proposed | Proposed |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 849 | Northeast Utilities |  | 12/2008 | Queue Position 186 | Shepaug - 115 kV substation. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 857 | Northeast Utilities |  | 06/2010 | Queue Position 186 | Shepaug - 115 kV substation. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 736 | Northeast Utilities |  | 01/2009 | Queue Position 161 | CL&P Middletown Substation or CL&P Scovill Rock Substation. | Proposed | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 850 | Northeast Utilities |  | 06/2009 | Queue Position 175 | CL&P Stony Hill 115 kV Substation or 345 kV line # 321. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 852 | Northeast Utilities |  | 07/2009 | Queue Position 191 | Watertown - 115 kV line #1238 or #1191. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 853 | Northeast Utilities |  | 07/2009 | Queue Position 199 | CL&P Baldwin 115kV substation. | Concept | Concept | Proposed | Proposed | Proposed |  |  |  | 2008-06-09 | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 620 | Northeast Utilities |  | 12/2009 | Queue Position 145 | Interconnection to CL&P's 115-kV 1607 line. | Proposed | Proposed | Proposed | Proposed | Proposed |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 854 | Northeast Utilities |  | 01/2010 | Queue Position 190 | Falls Village - 69 kV Substation. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 855 | Northeast Utilities |  | 01/2010 | Queue Position 190 | Stevenson - CL&P Stevenson 115 kV Substation. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 856 | Northeast Utilities |  | 01/2010 | Queue Position 190 | Tunnel- CL&P Tunnel 115 kV Substation. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 851 | Northeast Utilities |  | 06/2010 | Queue Position 182 | CL&P Stony Hill 115 kV Substation #175. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 858 | Northeast Utilities |  | 06/2010 | Queue Position 192 | CPV Danbury - CL&P Plumtree Substation. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 883 | United Illuminating Company |  | 2009 | Queue Position 159 | Bridgeport Energy II - UI 345 kV Singer Substation. | Concept | Proposed | Proposed | Proposed | Proposed |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2a | 848 | Northeast Utilities |  | 11/2008 | Queue Position 183 | Millstone 3 - 345 kV Substation. | Concept | Proposed | Proposed | Proposed | Proposed |  |  |  | 08/15/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2a | 733 | Northeast Utilities |  | 12/2008 | Plainfield Renewable Energy Project | CL&P Fry Brook Substation. | Proposed | Planned | Planned | Planned | Planned |  |  |  | 06/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2a | 735 | Northeast Utilities |  | 01/2009 | Middletown 11 | NU Middletown Substation. | Proposed | Planned | Planned | Planned | Planned |  |  |  | 12/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2a | 734 | Northeast Utilities |  | 03/2009 | Devon Units | Devon Substation. | Proposed | Planned | Planned | Planned | Planned |  |  |  | 12/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR
REMOVE FROM SPITS and PROJECT LISTING
Reliability Upgrade | 1b | 817 (merged w/ ID 816) | Northeast Utilities |  | 2011-2013 | NEEWS (Greater Springfield Reliability Project) | Reconfigure/Modify North Bloomfield, Northwest Hartford, Southwest Hartford and South Meadow 115-kV substations. | Proposed | Concept | Concept | Concept | Concept |  |  |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Reliability Upgrade | 1a | 1081 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | BPS requirements for Springfield stations |  |  | Proposed | Planned | Planned |  |  |  | 2008-09-24 | No |  |  | TBD | 18500000 | 18500000 | 18500000 | 18500000 | 18500000 | 18500000 | 18500000 | 1
Reliability Upgrade | 1a | 1082 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | BPS Requirements for Connecticut stations |  |  | Proposed | Planned | Planned |  |  |  | 2008-09-24 | No |  |  | TBD | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 1
Reliability Upgrade | 1a | 1083 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Central Connecticut Relaibility Project) | BPS Requirements |  |  | Proposed | Planned | Planned |  |  |  | 2008-09-24 | No |  |  | TBD | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 1
Reliability Upgrade | 1a | 1093 | Northeast Utilities |  | 2011-2013 | NEEWS (Ancillary Project) | NU's BPS Requirements for NEEWS |  |  |  | Proposed | Proposed |  |  |  | No | No |  |  |  | 39000000 | 39000000 | 39000000 | 39000000 | 39000000
KEEP IN SPITS and DON'T SHOW I/S for JUL-08 PROJECT LISTING
Reliability Upgrade | 1a | 611 | Northeast Utilities |  | 2006-11-01 | Southwest Connecticut Reliability Project PH II (M-N) | Remove a portion of the 115 kV 1690 line from Devon to Cook Hill Jct. | Under Construction | Under Construction | In-Service | In-Service | In-Service |  |  |  | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 230 | Northeast Utilities |  | 2006-12-22 | Southwest Connecticut Reliability Project PH II (M-N) | Expand Scovill Rock 345 kV substation. | Under Construction | Under Construction | In-Service | In-Service | In-Service |  |  |  | 04/01/2007 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 231 | Northeast Utilities | United Illuminating Company | 2007-10-22 | Southwest Connecticut Reliability Project PH II (M-N) | Rebuild 115 kV Devon to Devon Switching Station(UI) 1780 and 1790 lines. | Planned | Under Construction | In-Service | In-Service | In-Service |  |  |  | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 6a | 780 | National Grid, USA |  | 2008-08-01 | Merrimack Valley/North Shore Reliability Project | Revise Melrose supply configuration. | Proposed | Concept | Concept | In-Service | In-Service |  |  |  | 2008-04-01 | No | 4100000 | 4100000 | 4100000 | 5100000 | 5100000 | 5100000 | 5100000 | 5100000 |  | -4100000
Reliability Upgrade | 6a | 1052 | National Grid, USA |  | 11/2010 | Merrimack Valley/North Shore Reliability Project | Reconductor I-161 115 kV line from Meadowbrook to North Chelmsford. |  | Concept | Concept | Planned | Planned |  |  |  | 2008-06-27 | No |  | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project
Reliability Upgrade | 6a | 1053 | National Grid, USA |  | 11/2010 | Merrimack Valley/North Shore Reliability Project | Reconductor A-153 115 kV line from Meadowbrook to North Chelmsford. |  | Concept | Concept | Planned | Planned |  |  |  | 2008-06-27 | No |  | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project
Notes
1 Project pending solution documentation for the Greater Rhode Island Transmission Reinforcements.
2 The Northeast Utilities' estimated costs for the NEEWS BPS upgrades are shared among the Greater Springfield, Central Connecticut, and Interstate portions of the NEEWS Project.
3 The total TCA (NU-07-TCA-24) PTF cost is $234.2 million for the Norwalk - Glenbrook Project. The forecasted PTF cost is $249.4 million.
4 The total TCA (NU-08-TCA-01) PTF cost is $1.05 billion for Northeast Utilities portion of the Middletown-Norwalk Project. The forecasted PTF cost is $978.2 million.
5 The project was completed in December 2009, and was energized and placed in service under the jurisdicition of CONVEX but has since been isolated and de-energized due to a significant incident at the power plant
Local Project Listing Links
| NSTAR: |  | http://www.nstar.com/business/rates_tariffs/open_access/
| CMP: |  | http://www.cmpco.com/SuppliersAndPartners/TransmissionServices/CMPTransmissionSvc/lsp.html
| BHE: |  | http://www.bhe.com/data/OASIS/LSP.html
| VELCO: |  | http://www.vermontspc.com/default.aspx
| NU: |  | http://www.transmission-nu.com/business/ferc890postings.asp
| NGRID: |  | http://www.nationalgridus.com/oasis/filings_studies.asp
| UI: |  | http://www.uinet.com/uinet/resources/file/ebcfda4ccb73dd/UI%20Local%20System%20Plan.pdf

## ISO-NEProject Oct 09Listing PAC (hidden)
October '09 ISO-NEW ENGLAND Project Listing Update
Primary Driver | Part# | Project ID | Primary Equipment Owner | Other Equipment Owner(s) | Projected In-Service Month/Year | Major Project | Project | Jul-09 Status | Oct-09 Status | PPA (I.3.9) Approval | TCA Approval | Jul-09 Estimated PTF Costs | Oct-09 Estimated PTF Costs
TABLE A
MAINE
Reliability Upgrade | 1a | 144 | Bangor Hydro-Electric Company |  | 12/2010 | Keene Rd Autotransformer | Installation of a 345/115 kV autotransformer at Keene Rd Substation. | Under Construction | Under Construction | No | No | 29000000 | 29000000
Reliability Upgrade | 1a | 625 | Central Maine Power Company |  | 02/2010 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Rumford Industrial Park capacitor bank. | Planned | Under Construction | 2007-11-30 | No | 5400000 | 5400000
Reliability Upgrade | 1a | 1128 | Central Maine Power Company |  | 07/2010 | CMP-LSP Hotel Road Substation | Add 115/34kV transformer with 115kV breaker at Hotel Rd. | Planned | Planned | 2008-08-20 | NR | 800000 | 800000
Reliability Upgrade | 1a | 624 | Central Maine Power Company |  | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (New Page - Rumford Industrial Park) | Planned | Planned | 2007-11-30 | No | Part of project 625 | Part of project 625
Reliability Upgrade | 1a | 905 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Planned | Planned | 2008-07-31 | No | 1510000000 | 1510000000
Reliability Upgrade | 1a | 906 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Coopers Mills-Highland, Larrabee Road-Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 907 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 84 (Albion Road-Coopers Mills), Section 203 (Detroit-Orrington), Section 80 (Coopers Mills-Highland), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 908 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377 & Maine Yankee 375/392, 115kV Bucksport 65/205) and Maine Yankee 345 kV re-termination | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1026 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Three Rivers) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Portion of CMP $1.51B and portion of NU is $35.1M | Portion of CMP $1.51B and portion of NU is $35.1M
Reliability Upgrade | 1a | 1027 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV Line Construction (Elm Street-East Deering, East Deering -Cape) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1028 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD
Reliability Upgrade | 1a | 1029 | Central Maine Power Company |  | 11/2010 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformer at South Gorham | Under Construction | Under Construction | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1030 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Raven Farm, Maguire Road) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 143 | Bangor Hydro-Electric Company |  | 12/2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation to Harrington Substation. | Planned | Planned | 2006-05-10 | 2008-06-13 | 66100000 | 66100000
Reliability Upgrade | 1a | 1129 | Central Maine Power Company |  | 05/2012 |  | New 115kV line between Wyman Hydro and Heywood Rd. parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | Planned | 2009-01-26 | No | 19500000 | 19500000
Reliability Upgrade | 1a | 1144 | Central Maine Power Company |  | 04/2010 | Heywood Road Project | Circuit switcher replacements at Detroit, Lakewood, Rice Rips and Winslow | Under Construction | Under Construction | 2009-03-20 | 2009-07-20 | Part of Heywood Road Project | Part of Heywood Road Project
Generator Interconnection Upgrade | 2a | 770 | Central Maine Power Company |  | 12/2010 | Queue Position 137 | Installation of New Page Substation (aka Railroad Street Substation) with (3) circuit breakers tapping Section 218 115kV. | Proposed | Proposed | 2007-03-18 | NR | NR | NR
NEW HAMPSHIRE
Reliability Upgrade | 1a | 277 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Planned | Planned | 2009-06-29 | No | 56600000 | 56600000
Reliability Upgrade | 1a | 1137 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115kV breakers and add 1-115kV breaker at Deerfield Substation | Planned | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1138 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rebuild 115kV L175 line | Planned | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1139 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV M183 Line | Planned | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1140 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | Planned | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1141 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | Planned | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 680 | National Grid, USA |  | 09/2012 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | Planned | 2008-01-28 | No | 11497000 | 7393000
Reliability Upgrade | 1a | 674 | National Grid, USA |  | 09/2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | Planned | 2008-04-01 | No | 12000000 | 7720000
Elective | 4a | 1142 | FPL New England Division |  | 10/2009 |  | Seabrook Station Reconfiguration and Circuit Breaker addition Stage s 1 & 2 | Planned | Planned | 2008-11-20 | NR | TBD | TBD
Generator Interconnection Upgrade | 2a | 724 | National Grid, USA |  | 11/2009 | NGRID Comerford Substation | NGRID Comerford Substation. | Planned | Planned | 2007-06-12 | NR | NR | NR
VERMONT
Reliability Upgrade | 1a | 320 | Vermont Electric Power Company |  | 10/2009 | Lamoille County Project | Middlesex Substation 115 kV breaker addition. | Under Construction | Under Construction | 08/16/2007 | 02/07/2008 | 4857000 | 4857000
Reliability Upgrade | 1a | 322 | Vermont Electric Power Company |  | 10/2009 | Lamoille County Project | Installation of new Duxbury Substation that involves looping in and out of the Middlesex - Essex 115 kV (K24) line. | Under Construction | Under Construction | 08/16/2007 | 02/07/2008 | Part of Lamoille County Project | Part of Lamoille County Project
Reliability Upgrade | 1a | 139 | Vermont Electric Power Company |  | 12/2010 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Planned | Planned | 01/10/2003 | 03/31/2003 | 20000000 | 20000000
Reliability Upgrade | 1a | 321 | Vermont Electric Power Company |  | 12/2009 | Burlington Project | Burlington 115kV Loop - 5 mi of new line & rebuilding 5 miles of existing line between two existing substations with expansion of the East Avenue substation. | Under Construction | Under Construction | 10/24/2006 | 05/23/2007 | 25142000 | 25142000
Reliability Upgrade | 1a | 1145 | Vermont Electric Power Company |  | 09/2011 | Burlington Project | Installation of a 3-breaker 115kV ring substation and 115/34.5kV transformer on the East Ave. - Tafts Coners 115kV line |  | Planned | 10/24/2006 | No |  | 14000000
Reliability Upgrade | 1a | 323 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | New VY - Newfane - Coolidge 345 kV line with requisite station upgrades. | Under Construction | Under Construction | 2008-10-01 | No | 136368000 | 136368000
Reliability Upgrade | 1a | 1032 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Installation of a new 345/115kV substation called Vernon including a new 345/115kV autotransformer | Under Construction | Under Construction | 2008-10-01 | No | 69815000 | 69815000
Reliability Upgrade | 1a | 1033 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project (VELCO LSP - Newfane Substation) | Installation of a new 345/115kV substation called Newfane | Under Construction | Under Construction | 2008-10-01 | No | 16664000 | 16664000
Reliability Upgrade | 1a | 1034 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Loop new 345kV Line into Newfane Substation. | Under Construction | Under Construction | 2008-10-01 | No | Part of project 323 | Part of project 323
Reliability Upgrade | 1a | 1035 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Expansion of Coolidge 345kV substation | Under Construction | Under Construction | 2008-10-01 | No | 20117000 | 20117000
Reliability Upgrade | 1a | 1146 | Vermont Electric Power Company |  | 12/2012 | Lyndonville Project | Installation of a 3-breaker 115kV righ station consisting of two 115kV 12.5 MVAR capacitor banks and 115/34.5 kV transformer interconnecting to the Irasburg - St. Johnsbury 115kV line |  | Planned | 2009-06-01 | No |  | 9000000
Generator Interconnection Upgrade | 2a | 1036 | Vermont Electric Power Company |  | 12/2009 | Queue Position 172 | Installation of 3-breaker 115kV ring bus interconnection of the St. Johnsbury-Irasburg 115kV K39 line. | Planned | Planned | 08/16/2007 | NR | NR | NR
MASSACHUSETTS
Reliability Upgrade | 1a | 1063 | NSTAR Electric Company |  | 12/2009 |  | Install (2) 115kV 40 MVAR shunt reactors at Edgar Station | Planned | Under Construction | 05/2009 | No | 5400000 | 5400000
Reliability Upgrade | 1a | 1152 | National Grid, USA |  | 2010-08-01 |  | Bear Swamp - Pratts Jumction 230kV Line Refurbishment Project (E205E) |  | Planned | NR | NR |  | 43596000
Reliability Upgrade | 1a | 887 | National Grid, USA |  | 09/2012 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Planned | Planned | 2008-01-28 | No | 30000000 | 30000000
Reliability Upgrade | 1a | 921 | National Grid, USA |  | 01/2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | Planned | 2008-01-28 | No | 12100000 | 12100000
Reliability Upgrade | 1a | 919 | National Grid, USA |  | 09/2012 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | Planned | 2008-01-28 | No | 4600000 | 4600000
Reliability Upgrade | 1a | 783 | National Grid, USA |  | 03/2011 | Merrimack Valley/North Shore Reliability Project | Extend the 115kV by addition of 115kV Breaker and K-153 line from King St. to W. Amesbury 115kV station. (W. Amesbury 345/115kV Station becomes PTF) | Planned | Planned | 2008-04-01 | No | 30349000 | 30349000
Reliability Upgrade | 1a | 777 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Build Wakefield Junction station with four 345/115 kV autotransformers. | Under Construction | Under Construction | 2008-04-01 | No | 95000000 | 95000000
Reliability Upgrade | 1a | 161 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Loop 345 kV 339 line and 115 kV S-145/T-146 into new Wakefield Jct. Substation. | Under Construction | Under Construction | 2008-04-01 | No | 4986431 | 4986431
Reliability Upgrade | 1a | 779 | National Grid, USA |  | 04/2010 | Merrimack Valley/North Shore Reliability Project | Bypass and remove Golden Hills 345 kV substation. | Under Construction | Under Construction | 2008-04-01 | No | 5132609 | 5132609
Reliability Upgrade | 1a | 840 | NSTAR Electric Company |  | 10/2010 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | Planned | 2008-04-01 | No | 7300000 | 7300000
Reliability Upgrade | 1a | 775 | National Grid, USA |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Addition of 4 breakers and relocation of T1 and T2 into new bays at Sandy Pond. | Planned | Planned | 2008-06-27 | No | 20100000 | 20100000
Reliability Upgrade | 1a | 776 | National Grid, USA |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | Planned | 2008-06-27 | No | 2865876 | 2865876
Reliability Upgrade | 1a | 782 | National Grid, USA |  | 10/2013 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor n Railyard. | Planned | Planned | 2008-06-27 | No | 38100000 | 38100000
Reliability Upgrade | 1a | 961 | NSTAR Electric Company |  | 11/2010 | Mystic Breaker Additions Project | Install (2) new 115 kV East Bus breakers #30 and #32 at Mystic and move Transformer 110B Connection. | Planned | Under Construction | 2008-03-10 | No | 3800000 | 3800000
Reliability Upgrade | 1a | 903 | NSTAR Electric Company |  | 12/2009 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #2, #4, #5, and #16 at Mystic to IPT and separate controls with Boston Gen units #5 and #6. | Planned | Under Construction | NR | NR | 1240000 | 1240000
Reliability Upgrade | 1a | 904 | NSTAR Electric Company |  | 12/2010 | Mystic IPT Breaker Project | Upgrade (5) 115 kV breakers #1, #7, #15 #19 and #20 at Mystic to IPT and separate controls with Boston Gen #4. | Planned | Planned | NR | NR | 990000 | 990000
Reliability Upgrade | 1a | 59 | National Grid, USA |  | 01/2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | Planned | 2007-11-01 | 2003-01-31 | 400000 | 400000
Reliability Upgrade | 1a | 929 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | Planned | 12/17/2007 | No | 1381849 | 1381849
Reliability Upgrade | 1a | 931 | National Grid, USA |  | 01/2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | Planned | 12/17/2007 | No | 531481 | 531481
Reliability Upgrade | 1a | 928 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | Planned | 12/17/2007 | No | 1945218 | 2300000
Reliability Upgrade | 1a | 930 | National Grid, USA |  | 12/2009 | Central/Western Massachusetts Upgrades | Reconductor Nashua St - Quinsigamond Jct (O141) 115 kV line w/636 ACSS. | Planned | Under Construction | 12/17/2007 | No | 2300000 | 2300000
Reliability Upgrade | 1a | 934 | National Grid, USA |  | 10/2010 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Planned | Planned | 12/17/2007 | No | 818480 | 818480
Reliability Upgrade | 1a | 935 | National Grid, USA |  | 07/2010 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Planned | Planned | 12/17/2007 | No | 5208509 | 5208509
Reliability Upgrade | 1a | 933 | National Grid, USA |  | 12/2009 | Central/Western Massachusetts Upgrades | Reconductor Pratts Jct - Flagg Pond I-135S & J-136S 115 kV lines w/795 ACSS. | Planned | Under Construction | 12/17/2007 | No | 6137112 | 6137112
Reliability Upgrade | 1a | 938 | National Grid, USA |  | 06/2010 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | Planned | 12/17/2007 | No | 3068556 | 3068556
Reliability Upgrade | 1a | 939 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Reconductor and retension (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | Planned | Planned | 12/17/2007 | No | 3389658 | 3389658
Reliability Upgrade | 1a | 940 | National Grid, USA |  | 04/2011 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS. | Planned | Planned | 12/17/2007 | No | 6235744 | 6235744
Reliability Upgrade | 1a | 942 | National Grid, USA |  | 10/2010 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | Planned | 12/17/2007 | No | 2767180 | 2767180
Reliability Upgrade | 1a | 927 | National Grid, USA |  | 07/2010 | Central/Western Massachusetts Upgrades | Greendale - replace 115 kV breaker and upgrade to 2000A. | Planned | Planned | 12/17/2007 | No | 584629 | 584629
Reliability Upgrade | 1a | 925 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | Planned | 12/17/2007 | No | 318888 | 318888
Reliability Upgrade | 1a | 926 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | Planned | 12/17/2007 | No | 6027520 | 6027520
Reliability Upgrade | 1a | 932 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | Planned | 12/17/2007 | No | 372036 | 372036
Reliability Upgrade | 1a | 924 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | Planned | Planned | 12/17/2007 | No | 2147181 | 2147181
Reliability Upgrade | 1a | 941 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Install new Millbury - Tower #510 115 kV line. | Planned | Planned | 12/17/2007 | No | 7909203 | 7909203
Reliability Upgrade | 1a | 943 | National Grid, USA |  | 01/2011 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | Planned | 12/17/2007 | No | 1073995 | 1073995
Reliability Upgrade | 1a | 944 | National Grid, USA |  | 07/2012 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Planned | Planned | 12/17/2007 | No | 11411849 | 11411849
Reliability Upgrade | 1a | 950 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | Planned | 12/17/2007 | No | 1016897 | 1016897
Reliability Upgrade | 1a | 953 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | Planned | 12/17/2007 | No | 10248067 | 10248067
Reliability Upgrade | 1a | 954 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | E Westminster - install new 115 kV breaker, including disconnect switches. Assumes no new control house. | Planned | Planned | 12/17/2007 | No | 903909 | 903909
Reliability Upgrade | 1a | 945 | National Grid, USA |  | 02/2013 | Central/Western Massachusetts Upgrades | Adams - install third 115 kV breaker to complete ring bus. | Planned | Planned | 12/17/2007 | No | 1581841 | 1584841
Reliability Upgrade | 1a | 946 | National Grid, USA |  | 04/2013 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer - E Longmeadow - Shaker Rd line to 115 kV. | Planned | Planned | 12/17/2007 | No | 9604032 | 9604032
Reliability Upgrade | 1a | 947 | National Grid, USA |  | 04/2013 | Central/Western Massachusetts Upgrades | Reconductor 115 kV line from Palmer to new Hampden Substation. | Planned | Planned | 12/17/2007 | No | 2632635 | 2632635
Reliability Upgrade | 1a | 948 | National Grid, USA |  | 07/2012 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | Planned | 12/17/2007 | No | 5649430 | 5649430
Reliability Upgrade | 1a | 949 | National Grid, USA |  | 07/2012 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | Planned | 12/17/2007 | No | 1694829 | 1500000
Reliability Upgrade | 1a | 952 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Reconductor E Winchendon - J136 Tap within I135/J136 ROW w/795 ACSR. | Planned | Planned | 12/17/2007 | No | 932156 | 932156
Reliability Upgrade | 1a | 937 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | Planned | 12/17/2007 | No | 6602875 | 6602875
Reliability Upgrade | 1a | 955 | National Grid, USA |  | 11/2011 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | Planned | 12/17/2007 | No | 10779113 | 10779113
Reliability Upgrade | 1a | 162 | National Grid, USA |  | 04/2011 |  | Q-169 Golden Hills to Lynn 115 kV line upgrade. | Under Construction | Under Construction | 2005-09-02 | 2008-04-25 | 12390000 | 12390000
Reliability Upgrade | 1a | 902 | National Grid, USA |  | 03/2012 | Middleboro Municipal | Close the E1-M1 loop at Middleboro's Wareham St Sub. | Under Construction | Under Construction | 12/01/2006 | NR | 715000 | 715000
Reliability Upgrade | 1a | 1000 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | Planned | Planned | 2008-06-27 | No | 22000000 | 22000000
Reliability Upgrade | 1a | 951 | National Grid, USA |  | 02/2013 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon 115 kV line. | Planned | Planned | 12/17/2007 | No | 7455440 | 7455440
Reliability Upgrade | 1a | 687 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | Planned | 2008-09-24 | No | 714000000 | 714000000
Reliability Upgrade | 1a | 826 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 196 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115kV line South Agawam to Southwick (1768) | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVAR Capacitor additions | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1074 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1076 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Planned | Planned | 2008-09-24 | No | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1077 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115kV line | Planned | Planned | 2008-09-24 | No | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1078 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 673 | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | Planned | 2009-02-27 | No | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Planned | Planned | 2009-02-27 | No | 30000000 | 30000000
Generator Interconnection Upgrade | 2a | 1045 | National Grid, USA |  | 06/2010 | Lowell Power | Upgrade 137T and K-137W 115 kV circuit breakers at Sandy Pond. | Planned | Planned | 2006-07-25 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 505 | National Grid, USA |  | 07/2010 | Hoosac Wind Farm | Tap Y-25S line between Harriman and Deerfield 5. Construct 69/34.5 kV substation and 34.5 kV line connecting 30 MW generating facility with the 69 kV system. | Planned | Planned | 02/01/2005 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 595 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Expansion of Barnstable 115 kV substation to include 5th bay and (2) circuit breakers, addition of a 3rd breaker in the planned 4th bay, and (2) 35MVAr shunt reactors. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 596 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Installation of (2) 115 kV circuits out of Barnstable substation to interconnect Cape Wind. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 598 | NSTAR Electric Company |  | 11/2010 | Cape Wind | At Canal 345 kV substation, install a redundant breaker in series with breaker #312. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 599 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Upgrade the Bourne 115 kV breaker #12272 with an IPT breaker. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 600 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Installation of differential insulation and additional grounding at each tower that is common for the 342 and 322 345 kV lines. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1048 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Convert Canal 345 kV SPS to include tripping of Cape Wind for the simultaneous loss of 342 and 322 345 kV lines. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1046 | National Grid, USA |  | 06/2011 | Queue Position 178 | Reconductor 115 kV F19 Line (Auburn - Brockton Tap). | Proposed | Proposed | 2008-03-10 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1047 | National Grid, USA |  | 06/2011 | Queue Position 178 | Replace Bridgewater 115 kV 1631 circuit breaker with 63 kA breaker. | Proposed | Proposed | 2008-03-10 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 622 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Interconnection to WMECO's 115-kV 1512 line through a new Substation. | Proposed | Proposed | 06/01/2007 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1043 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Upgrade the 1768 line terminal equipment at Southwick Substation. | Proposed | Proposed | 06/01/2007 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1044 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Upgrade the 1512 line terminal equipment at Southwick Substation. | Proposed | Proposed | 06/01/2007 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1058 | National Grid, USA |  | 06/2011 | Billerica Power | Interconnection to Tewksbury 115 kV Substation via O-193 Line and refurbish section of J-162 line. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1059 | National Grid, USA |  | 06/2011 | Billerica Power | Re-terminate line tap section (Perry Street) of J-162 Line to new bay position at Tewksbury. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1060 | National Grid, USA |  | 06/2011 | Billerica Power | Reconductor 2.8 mi. of the M-139 115 kV line. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1061 | National Grid, USA |  | 06/2011 | Billerica Power | Replace (16) 115 kV circuit breakers at Tewksbury 22 w/ IPT capability if all generators w/ higher Queue Position are constructed. The quantity of breaker upgrades subject to Queued generators constructed. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1062 | National Grid, USA |  | 06/2011 | Billerica Power | Upgrade #137T and #K-137W 115 kV circuit breakers at Sandy Pond (if not completed as part of Merrimack Valley/North Shore Project). | Planned | Planned | 2008-07-08 | NR | NR | NR
Elective | 4a | 1057 | Braintree Electric Light Department |  | 06/2010 |  | Upgrade 115-10-16 underground 115 kV cable. | Planned | Planned | 2008-04-17 | No | TBD | TBD
RHODE ISLAND
Reliability Upgrade | 1a | 484 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Planned | Planned | 2008-04-25 | No | 690000 | 690000
Reliability Upgrade | 1a | 791 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | Planned | 2008-04-25 | No | 11560000 | 11560000
Reliability Upgrade | 1a | 913 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | Planned | 2008-04-25 | No | 3250000 | 3250000
Reliability Upgrade | 1a | 914 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | Planned | 2008-04-25 | No | 28150000 | 28150000
Reliability Upgrade | 1a | 915 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | Planned | 2008-04-25 | No | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | Planned | 2008-04-25 | No | 11800000 | 11800000
Reliability Upgrade | 1a | 917 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | Planned | 2008-04-25 | No | 7000000 | 7000000
Reliability Upgrade | 1a | 918 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | Planned | 2008-04-25 | No | 3180000 | 3180000
Reliability Upgrade | 1a | 792 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Admiral St-Franklin Square (Q143 and R144) 115 kV UG recabling. | Planned | Planned | 2008-04-25 | No | 39200000 | 39200000
Reliability Upgrade | 1a | 793 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | Planned | 2008-04-25 | No | 6400000 | 6400000
Reliability Upgrade | 1a | 786 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Terminal upgrades at Drumrock, Chartley Pond, and Brayton Point. | Planned | Planned | 2008-04-25 | No | 565000 | 1000000
Reliability Upgrade | 1a | 787 | National Grid, USA |  | 12/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | West Farnum breaker replacements. | Planned | Planned | 2008-04-25 | No | 7631000 | 7631000
Reliability Upgrade | 1a | 788 | National Grid, USA |  | 06/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Kent County substation expansion. | Planned | Planned | 2008-04-25 | No | 42300000 | 42300000
Reliability Upgrade | 1a | 789 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Reconductoring of T7 115 kV line. | Planned | Planned | 2008-04-25 | No | 23304000 | 23304000
Reliability Upgrade | 1a | 790 | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Planned | Planned | 2008-04-25 | No | 50600000 | 50600000
Reliability Upgrade | 1a | 1098 | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Planned | Planned | 2008-04-25 | No | 37529000 | 37529000
Reliability Upgrade | 1a | 190 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | Planned | 2008-09-24 | No | 69600000 | 69600000
Reliability Upgrade | 1a | 1094 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | Planned | 2008-09-24 | No | 20800000 | 25000000
Reliability Upgrade | 1a | 1095 | National Grid, USA |  | 06/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | Planned | 2008-09-24 | No | 73800000 | 73800000
Reliability Upgrade | 1a | 794 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | Planned | 2008-09-24 | No | 55800000 | 55800000
Reliability Upgrade | 1a | 796 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | 347 Reconductor from Sherman Road to CT/RI Border. | Planned | Planned | 2008-09-24 | No | 16400000 | 16400000
Reliability Upgrade | 1a | 797 | National Grid, USA |  | 12/2012 | NEEWS (Interstate Reliability Project) | 3361 Upgrade 345kV terminal equipment at Sherman Road. | Planned | Planned | 2008-09-24 | No | 8300000 | 8300000
Reliability Upgrade | 1a | 795 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV line. | Planned | Planned | 2008-09-24 | No | 99900000 | 99900000
Reliability Upgrade | 1a | 1106 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | Planned | Planned | 2008-09-24 | No | Part of $99,900,000 above | Part of $99,900,000 above
Reliability Upgrade | 1a | 798 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Planned | Planned | 2008-09-24 | No | 4900000 | 4900000
Reliability Upgrade | 1a | 799 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | Planned | Planned | 2008-09-24 | No | 4500000 | 4500000
Reliability Upgrade | 1a | 1096 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | Planned | 2008-09-24 | No | 5800000 | 12000000
Reliability Upgrade | 1a | 800 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S, T-172N and T-172S with associated terminal equipment upgrades. | Planned | Planned | 2008-09-24 | No | 7300000 | 10000000
Reliability Upgrade | 1a | 1097 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County | Planned | Planned | 2008-09-24 | No | 129800000 | 129800000
Reliability Upgrade | 1a | 1099 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | Planned | 2008-09-24 | No | 4100000 | 6000000
Reliability Upgrade | 1a | 1109 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Planned | Planned | 2008-09-24 | No | 360000 | 1000000
CONNECTICUT
Reliability Upgrade | 1a | 211 | Northeast Utilities |  | 11/2009 | NU LSP - Rood Ave Substation | New Rood Ave (formally Windsor) distribution substation with 115kV terminal modifications. | Under Construction | Under Construction | 2008-04-25 | 02/15/2008 | 9162029 | 9162029
Reliability Upgrade | 1a | 1049 | United Illuminating Company |  | 12/2010 |  | East Shore 115 kV Capacitor Bank Transient Recovery | Planned | Planned | NR | NR | 3000000 | 3000000
Reliability Upgrade | 1a | 582 | Northeast Utilities |  | 12/2010 |  | Separate 310 and 368 345-KV lines and create 368/1767 DCT | Planned | Planned | 2008-07-18 | No | 16000000 | 16000000
Reliability Upgrade | 1a | 1112 | United Illuminating Company |  | 12/2010 |  | Water Street 115kV circuit breaker and switch replacements. | Planned | Planned | NR | NR | 1000000 | 1000000
Reliability Upgrade | 1a | 974 | United Illuminating Company |  | 12/2011 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Planned | Planned | NR | No | 6700000 | 6700000
Reliability Upgrade | 1a | 816 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1054 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Manchester - Meekvile Jct. line (395/1448) separation. | Planned | Planned | 2008-09-24 | No | 14000000 | 14000000
Reliability Upgrade | 1a | 576 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | Planned | 2008-09-24 | No | 313000000 | 313000000
Reliability Upgrade | 1a | 1114 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1a | 814 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Central Connecticut Relaibility Project) | Reconductor a portion of the Manchester to Scovill Rock 353 345-kV line and terminal work. | Planned | Planned | 2008-09-24 | No | 9000000 | 9000000
Reliability Upgrade | 1a | 802 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | Planned | 2008-09-24 | No | 251000000 | 251000000
Reliability Upgrade | 1a | 1084 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Loop the Millstone - Manchester (310) 345 kV line into the Card substation. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1085 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1086 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1087 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1088 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1089 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Killingly 3G substation 345kV breaker addition | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1090 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Millstone 15G substation breaker 14T upgrade 50kA | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1091 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Southington 4C substation breaker 19T upgrade to 63kA | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | Northeast Utilities | National Grid, USA | 12/2013 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 807 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Interstate Reliability Project) | Install 480 MVAR's of capacitors at the Montville 345 kV substation | Planned | Planned | 2008-09-24 | No | 33000000 | 33000000
Reliability Upgrade | 1a | 1092 | Northeast Utilities |  | 12/2013 | NEEWS (BPS) 2 | Upgrade the Card 115 kV, East Hartford 115 kV, Agawam 115 kV, Barbour Hill 115 kV, and North Bloomfield 345 kV Substations to BPS standards. | Planned | Planned | 2008-09-24 | No | 37000000 | 37000000
Reliability Upgrade | 1a | 1056 | Northeast Utilities |  | 12/2011 | CT LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Planned | Planned | 2008-12-12 | No | 9751000 | 9751000
Reliability Upgrade | 1a | 1110 | United Illuminating Company |  | 12/2010 |  | Broadway 115/13.8 kV Substation Additon | Planned | Planned | 2008-12-08 | No | 1200000 | 1200000
Reliability Upgrade | 1a | 1111 | United Illuminating Company |  | 12/2010 |  | Metro North Union Avenue 115/26.4 kV Substation | Planned | Planned | 2009-01-07 | No | 10543000 | 10543000
Reliability Upgrade | 1a | 976 | United Illuminating Company |  | 05/2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Planned | Planned | 2009-01-07 | No | 48000000 | 48000000
Reliability Upgrade | 1a | 879 |  | Bangor Hydro-Electric Company, New England Power Company, Northeast Utilities System Com | TBD | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | Planned | 03/01/2007 | NR | 420000 | 420000
Generator Interconnection Upgrade | 2a | 983 | Northeast Utilities |  | 09/2012 | Queue Position 207/241 | Rebuild 115 kV 1585N Line between new substation and Bunker Hill. | Proposed | Proposed | 2008-09-26 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1107 | Northeast Utilities |  | 09/2012 | Queue Position 207/241 | Interconnection to new 115 kV substation consisting of (14) circuit breakers in a breaker and a half configuration that sectionalizes the existing 1575, 1585, and 1990 lines. | Proposed | Proposed | 2008-09-26 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1108 | Northeast Utilities |  | 09/2012 | Queue Position 207/241 | Installation of a 2.5% series reactor on the 1990S Line at the new substation. | Proposed | Proposed | 2008-09-26 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 331 | Northeast Utilities |  | 10/2009 | Kleen Energy | Install 5-breaker ring bus interconnecting between Scovill Rock and Manchester on the 345 kV 353 Line. | Under Construction | Under Construction | 10/08/2003 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1121 | Northeast Utilities |  | 10/2009 | Queue Position 161-2 | Four units connected to 384 line through a new 345kV Substation: unit #4 wll also connect to Substation | Proposed | Planned | 2008-12-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1149 | Northeast Utilities |  | 06/2010 | Queue Position 161-1 | Four units connected at Devon Substation |  | Under Construction | 2007-12-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1122 | Northeast Utilities |  | 11/2010 | Queue Position 191 | One turbine connected to #1238 Line (Frost Bridge to Carmel) via a new 3-breaker ring bus Substation | Proposed | Proposed | 2009-02-24 | NR | NR | NR
Reliability Upgrade | 1a | 1050 | United Illuminating Company |  | 12/2011 |  | Devon Tie 115kV Switching Station BPS Compliance | Planned | Planned | NR | NR | 2620000 | 2620000
TABLE B
MAINE
Reliability Upgrade | 1b | 148 | Central Maine Power Company |  | 06/2012 | CMP LSP - Saco Bay Area Reinforcement Project | Establish a new Vallee Lane 115/34.5 kV substation and 115 kV line from Louden S/S to Vallee Lane Substation. | Proposed | Proposed | No | NR | 100000 | 100000
Reliability Upgrade | 1b | 1116 | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1031 | Bangor Hydro-Electric Company |  | 01/2012 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station, Rebuild Line 66, and Capacitior Bank Additions (10MVAr at Trenton, Downeast & Handcock County area) | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1130 | Central Maine Power Company |  | 12/2011 | Sturtevant Improvements | Add 115kV circuit breakers & 25 MVAR capacitor bank at Sturtevant Substation; Re-rate Section 63 between Wyman Hydro & Madison Substation | Proposed | Proposed | No | No | 3000000 | 3000000
Reliability Upgrade | 1b | 1131 | Central Maine Power Company |  | 12/2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Proposed | Proposed | No | NR | 600000 | 600000
Reliability Upgrade | 1b | 1132 | Central Maine Power Company |  | 12/2011 | CMP-LSP Maxcy's Substation | Add 115/34kV transformer (coordinate with MPRP) | Proposed | Proposed | No | NR | 600000 | 600000
Reliability Upgrade | 1b | 1133 | Central Maine Power Company |  | 10/2010 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation & new 34kV line from Leeds to Turner | Proposed | Proposed | No | NR | 300000 | 300000
Reliability Upgrade | 1b | 1135 | Central Maine Power Company |  | TBD | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer | Proposed | Proposed | No | No | 1500000 | 1500000
Elective | 4b | 1018 | Bangor Hydro-Electric Company |  | TBD | Orrington-Boston HVDC | Orrington substation reconfiguration and addition of new HVDC cable system terminating in Boston area. | Concept | Concept | No | No | TBD | TBD
Elective | 4b | 984 | Central Maine Power Company | Maine Public Service | TBD | MEPCO-MPS 345 kV Interconnection | MEPCO-MPS 345 kV Interconnection. | Concept | Concept | No | No | TBD | TBD
NEW HAMPSHIRE
Reliability Upgrade | 1b | 275 | Northeast Utilities |  | TBD |  | Merrimack 115-kV substation - Protection Separation Upgrade. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1143 | Northeast Utilities |  | TBD |  | Littleton 115kV breaker addition and reconfiguration | Proposed | Proposed | No | No | 5338000 | 5338000
VERMONT
Reliability Upgrade | 1b | 318 | Vermont Electric Power Company |  | 12/2011 |  | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems through the 1,250 MW Vermont state load level. | Concept | Concept | No | No | 9000000 | 9000000
Reliability Upgrade | 1b | 325 | Vermont Electric Power Company |  | 12/2011 | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | Concept | No | No | 5000000 | 5000000
Reliability Upgrade | 1b | 324 | Vermont Electric Power Company |  | 12/2012 |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | Concept | No | No | 100000000 | 100000000
MASSACHUSETTS
Reliability Upgrade | 1b | 785 | National Grid, USA |  | 07/2017 | Merrimack Valley/North Shore Reliability Project | Re-conductor F-158N (Golden Hills-Maplewood-Everett) 115 kV line. | Concept | Concept | No | No | 1330000 | 1330000
Reliability Upgrade | 1b | 963 | NSTAR Electric Company |  | 12/2009 | Boston Area 115 kV Enhancements | Add a new 115kV breaker # 11 Relocate 447-509 and add control and protect at Holbrook. | Proposed | Proposed | No | No | 4000000 | 4000000
Reliability Upgrade | 1b | 842 | NSTAR Electric Company |  | 06/2010 | Boston Area 115 kV Enhancements | Add 115 kV 54 MVAR capacitor bank at W. Framingham. | Proposed | Proposed | No | No | 3000000 | 3700000
Reliability Upgrade | 1b | 1153 | NSTAR Electric Company |  | 06/2010 | Boston Area 115 kV Enhancements | Reliability Upgrades at West Framingham Station |  | Concept | No | No |  | 3000000
Reliability Upgrade | 1b | 843 | NSTAR Electric Company |  | 12/2013 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 965 | NSTAR Electric Company |  | 12/2012 | Boston Area 115 kV Enhancements | Add third 115kV line from Walpole to Holbrook | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 964 | NSTAR Electric Company |  | 06/2011 | Boston Area 115 kV Enhancements | Relocate 115kV terminals at W. Walpole to mitigate breaker failure #8. | Proposed | Proposed | No | No | 5600000 | 5600000
Reliability Upgrade | 1b | 969 | NSTAR Electric Company |  | 06/2018 | Boston Area 115 kV Enhancements | Add a new 54 MVAR capacitor bank at Chelsea. | Concept | Concept | No | No | 1200000 | 1200000
Reliability Upgrade | 1b | 301 | NSTAR Electric Company |  | 12/2011 | Boston Area 115 kV Enhancements | Reconductor 115-kV circuits 320-507 and 320-508. | Concept | Concept | No | No | 4600000 | 4600000
Reliability Upgrade | 1b | 1113 | NSTAR Electric Company |  | 12/2010 |  | Install KSt Breaker #31 | Proposed | Proposed | No | No | 2100000 | 2960000
Reliability Upgrade | 1b | 593 | NSTAR Electric Company |  | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Canal to Barnstable/Falmouth | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1068 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to Sandwich and a a 345-115kV auto-transformer at Sandwich | Proposed | Proposed | No | No | 110000000 | 110000000
Reliability Upgrade | 1b | 592 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing | Proposed | Proposed | No | No | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1118 | NSTAR Electric Company | National Grid, USA | 12/2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 | Proposed | Proposed | No | No | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1067 | NSTAR Electric Company |  | 12/2010 | NPCC BPS Compliance | Tremont Station | Proposed | Proposed | No | No | 11200000 | 12800000
Reliability Upgrade | 1b | 1066 | NSTAR Electric Company |  | 09/2011 | NPCC BPS Compliance | Needham Station | Concept | Concept | No | No | 9300000 | 9300000
Reliability Upgrade | 1b | 1065 | NSTAR Electric Company |  | 07/2012 | NPCC BPS Compliance | Waltham Station | Concept | Proposed | No | No | 24300000 | 26600000
Reliability Upgrade | 1b | 970 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345 kV line from Lexington to Waltham. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 971 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1119 | NSTAR Electric Company |  | 12/2010 | Greater Boston Reliability Project | Upgrade West Medway-West Walpole 345kV line #325 | Proposed | Proposed | No | No | 2200000 | 2200000
Reliability Upgrade | 1b | 1120 | NSTAR Electric Company |  | 06/2010 |  | Install 345kV 160 MVAR shunt ractor at W. Walpole | Proposed | Proposed | No | No | 7200000 | 7200000
Reliability Upgrade | 1b | 956 | National Grid, USA |  | 05/2013 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Concept | Concept | No | No | 7021534 | 7021534
Reliability Upgrade | 1b | 1136 | National Grid, USA |  | 12/2012 |  | New 115kV Switching Station at Devens Convert 69kV lines to 115kV, Reconfigure 115kV Supply at Ayer Substation | Proposed | Proposed | 2009-07-28 | No | 9200000 | 9200000
Reliability Upgrade | 1b | 824 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 825 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Upgrade the Pleasant to Blanford 115-kV line and the Blanford to Granville Jct. portion of the 115-kV line 1512. | Concept | Concept | No | No | TBD | TBD
Generator Interconnection Upgrade | 2b | 863 | Northeast Utilities |  | 06/2010 | Queue Position 217 | Northfield Mountain - W. Mass Northfield 345 kV substation. | Proposed | Proposed | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1014 | Northeast Utilities |  | 06/2010 | Queue Position 196 | 345 kV Northfield Substation | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1123 | Northeast Utilities |  | TBD | Queue Position 236 | New Substation on 1302 Line; terminal upgrades at Buck Pond and Agawam | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 880 | National Grid, USA | Northeast Utilities | 06/2011 | Queue Position 177 | Sutton Energy - 345 kV Carpenter Hill-Millbury Line. | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1042 | National Grid, USA |  | 06/2013 | Queue Position 165 | Replace (2) 345 kV circuit breakers at Sandy Pond | Concept | Concept | No | NR | NR | NR
RHODE ISLAND
Generator Interconnection Upgrade | 2b | 881 | National Grid, USA | Northeast Utilities | 06/2012 | Queue Position 201 | RISEP - 345 kV RISE Substation. | Concept | Concept | No | NR | NR | NR
CONNECTICUT
Reliability Upgrade | 1b | 1055 | Northeast Utilities |  | 2010 | CT LSP - Waterside Substation | Waterside Substation - add a 115/13.2-kV transformer and a 115-kV circuit breaker. | Concept | Concept | No | No | 4107000 | 4107000
Reliability Upgrade | 1b | 809 | Northeast Utilities |  | 12/2009 |  | Upgrade terminal equipment at Bunker Hill 115 kV substation. | Proposed | Proposed | No | No | 1000000 | 1000000
Reliability Upgrade | 1b | 1150 | United Illuminating Company |  | 10/2011 |  | Grand Avenue - West River 115 kV Pumping Plant Replacements |  | Proposed | NR | NR |  | 1200000
Reliability Upgrade | 1b | 1151 | United Illuminating Company |  | 12/2011 |  | West River 115kV Switching Station Fault Duty Migration |  | Proposed | NR | NR |  | 3500000
Reliability Upgrade | 1b | 721 | United Illuminating Company |  | 06/2013 |  | New Shelton 115/13.8 kV substation | Proposed | Proposed | No | No | 11300000 | 11300000
Reliability Upgrade | 1b | 975 | United Illuminating Company |  | 12/2013 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | Concept | No | No | 44300000 | 44300000
Reliability Upgrade | 1b | 699 | United Illuminating Company |  | 12/2012 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | Concept | No | No | 10000000 | 10000000
Reliability Upgrade | 1b | 1147 | Northeast Utilities |  | 2011 |  | Waterside Substation - install a three-breaker 115kV ring bus |  | Proposed | No | No |  | 4000000
Reliability Upgrade | 1b | 1148 | Northeast Utilities |  | 2011 |  | Add a 2nd high speed relay on the Glennbrook to Waterside 115kV 1440 |  | Proposed | No | No |  | 600000
Reliability Upgrade | 1b | 801 | Northeast Utilities |  | TBD |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 85 | Northeast Utilities |  | TBD |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | Concept | 08/04/2004 | No | TBD | TBD
Generator Interconnection Upgrade | 2b | 1124 | Northeast Utilities |  | TBD | Queue Position 2422 | New Substation on Haddam Neck-Southington 345kV line | Proposed | Proposed | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1125 | Northeast Utilities |  | TBD | Queue Position 240 | 345kV on Montville Substation | Concept | Concept | No | NR | NR | NR
IN-SERVICE PROJECTS
Reliability Upgrade | 1a | 1051 | Central Maine Power Company |  | 09/2009 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Riley 115 kV capacitor bank. | Under Construction | In-service | 2007-11-30 | No | Part of Project 625 | Part of Project 625
Generator Interconnection Upgrade | 2a | 1134 | Central Maine Power Company |  | 09/2009 | Kibby Wind Farm | Separate Section 215 from Section 63 and terminate Section 215 at newly established breaker position in Wyman Hydro S/S, which includes re-rating of Section 215. Expand Bigelow S/S & add capacitor banks at Lakewood, Guilford, Wyman Hydro Station & Sturtevant S/S's. | Under Construction | In-service | 2006-06-16 | NR | NR | NR
Reliability Upgrade | 1a | 267 | Northeast Utilities | Central Maine Power Company | 2009-08-01 | Y138 Closing | White Lake - Saco Valley (Y138) Line Closing - Add PAR on Y138 at Saco Valley, retension lines, upgrade Beebe terminal, and add capacitor banks at White Lake and Beebe. | Under Construction | In-service | 01/01/2006 | No | 27775000 | 27775000
Reliability Upgrade | 1a | 936 | National Grid, USA |  | 07/2009 | Central/Western Massachusetts Upgrades | Reconductor (P142/P142S) Rolfe Avenue - West Bolyston 115 kV line w/1590 ACSR. | Under Construction | In-service | 12/17/2007 | No | 3000000 | 3000000
Reliability Upgrade | 1a | 176 | Northeast Utilities |  | 07/2009 | Monadnock Area Reliability Project | New Fitzwilliam 345/115kV substation along with 345 kV breakers. | Under Construction | In-service | 2007-09-27 | No | 76100000 | 76100000
Reliability Upgrade | 1a | 174 | National Grid, USA |  | 06/2009 | Monadnock Area Reliability Project | Reconductor I-135 (Bellows Falls-Monadnock Tap-Flagg Pond) 115 kV line. | Under Construction | In-service | 03/24/2006 | No | 15778000 | 15778000
Reliability Upgrade | 1a | 832 | NSTAR Electric Company |  | 07/2009 | Short Term Lower SEMA Upgrades | Add(1) 115kV SVC (0-112 MVARs lagging) at Barnstable. | Under Construction | In-service | 08/17/2007 | No | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade
Reliability Upgrade | 1a | 182 | Vermont Electric Power Company |  | 09/2009 | Monadnock Area Reliability Project | Upgrade bus cable at N. Rutland and K35 115 kV breaker at Rutland. | Under Construction | In-service | 03/24/2006 | NR | 1000000 | 1000000
CANCELLED PROJECTS
Reliability Upgrade | 1b | 1117 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install 115kV 50 MVAR capacitor bank at Falmouth | Proposed | Cancelled | No | No | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Notes
1 Project pending solution documentation for the Greater Rhode Island Transmission Reinforcements.
2 The Northeast Utilities' estimated costs for the NEEWS BPS upgrades are shared among the Greater Springfield, Central Connecticut, and Interstate portions of the NEEWS Project.
3 The total TCA (NU-07-TCA-24) PTF cost is $234.2 million for the Norwalk - Glenbrook Project. The forecasted PTF cost is $249.4 million.
4 The total TCA (NU-08-TCA-01) PTF cost is $1.05 billion for Northeast Utilities portion of the Middletown-Norwalk Project. The forecasted PTF cost is $978.2 million.
Local Project Listing Links
| NSTAR: |  | http://www.nstar.com/business/rates_tariffs/open_access/
| CMP: |  | http://www.cmpco.com/SuppliersAndPartners/TransmissionServices/CMPTransmissionSvc/lsp.html
| BHE: |  | http://www.bhe.com/data/OASIS/LSP.html
| VELCO: |  | http://www.vermontspc.com/default.aspx
| NU: |  | http://www.transmission-nu.com/business/ferc890postings.asp
| NGRID: |  | http://www.nationalgridus.com/oasis/filings_studies.asp
| UI: |  | http://www.uinet.com/uinet/resources/file/ebcfda4ccb73dd/UI%20Local%20System%20Plan.pdf

## ISO-NE JulyProject Listing-PAC (hidden)
July '09 ISO-NEW ENGLAND Project Listing Update (DRAFT)
Primary Driver | Part# | Project ID | Primary Equipment Owner | Other Equipment Owner(s) | Projected In-Service Month/Year | Major Project | Project | Apr -09 Status | Jul-09 Status | PPA (I.3.9) Approval | TCA Approval | Apr-09 Estimated PTF Costs | Jul-09 Estimated PTF Costs
TABLE A
MAINE
Reliability Upgrade | 1a | 1051 | Central Maine Power Company |  | 09/2009 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Riley 115 kV capacitor bank. | Planned | Under Construction | 2007-11-30 | No | Part of Project 625 | Part of Project 625
Reliability Upgrade | 1a | 144 | Bangor Hydro-Electric Company |  | 12/2010 | Keene Rd Autotransformer | Installation of a 345/115 kV autotransformer at Keene Rd Substation. | Under Construction | Under Construction | No | No | 29000000 | 29000000
Reliability Upgrade | 1a | 625 | Central Maine Power Company |  | 02/2010 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Rumford Industrial Park capacitor bank. | Planned | Planned | 2007-11-30 | No | 5400000 | 5400000
Reliability Upgrade | 1a | 1128 | Central Maine Power Company |  | 07/2010 | CMP-LSP Hotel Road Substation | Add 115/34kV transformer with 115kV breaker at Hotel Rd. | Planned | Planned | 2008-08-20 | NR | 800000 | 800000
Reliability Upgrade | 1a | 624 | Central Maine Power Company |  | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (New Page - Rumford Industrial Park). | Planned | Planned | 2007-11-30 | No | Part of project 625 | Part of project 625
Reliability Upgrade | 1a | 905 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Planned | Planned | 2008-07-31 | No | 1510000000 | 1510000000
Reliability Upgrade | 1a | 906 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Coopers Mills-Highland, Larrabee Road-Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 907 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 84 (Albion Road-Coopers Mills), Section 203 (Detroit-Orrington), Section 80 (Coopers Mills-Highland), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 908 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377 & Maine Yankee 375/392, 115kV Bucksport 65/205) and Maine Yankee 345 kV re-termination | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1026 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Three Rivers) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Portion of CMP $1.51B and portion of NU is $35.1M | Portion of CMP $1.51B and portion of NU is $35.1M
Reliability Upgrade | 1a | 1027 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV Line Construction (Elm Street-East Deering, East Deering -Cape) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1028 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD
Reliability Upgrade | 1a | 1029 | Central Maine Power Company |  | 12/2009 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformer at South Gorham | Under Construction | Under Construction | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1030 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Raven Farm, Maguire Road) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 143 | Bangor Hydro-Electric Company |  | 12/2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation to Harrington Substation. | Planned | Planned | 2006-05-10 | 2008-06-13 | 66100000 | 66100000
Reliability Upgrade | 1a | 1129 | Central Maine Power Company |  | 05/2012 |  | New 115kV line between Wyman Hydro and Heywood Rd. parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | Planned | 2009-01-26 | No | 19500000 | 19500000
Reliability Upgrade | 1a | 1144 | Central Maine Power Company |  | 04/2010 | Heywood Road Project | Circuit switcher replacements at Detroit, Lakewood, Rice Rips and Winslow |  | Under Construction | 2009-03-20 | 2009-07-20 |  | Part of Heywood Road Project
Generator Interconnection Upgrade | 2a | 1134 | Central Maine Power Company |  | 12/2010 | Kibby Wind Farm | Separate Section 215 from Section 63 and terminate Section 215 at newly established breaker position in Wyman Hydro S/S, which includes re-rating of Section 215. Expand Bigelow S/S & add capacitor banks at Lakewood, Guilford, Wyman Hydro Station & Sturtevant S/S's. | Planned | Under Construction | 2006-06-16 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 770 | Central Maine Power Company |  | TBD | Queue Position 137 | Installation of New Page Substation (aka Railroad Street Substation) with (3) circuit breakers tapping Section 218 115 kV. | Proposed | Proposed | 2007-03-18 | NR | NR | NR
NEW HAMPSHIRE
Reliability Upgrade | 1a | 267 | Northeast Utilities | Central Maine Power Company | 2009-08-01 | Y138 Closing | White Lake - Saco Valley (Y138) Line Closing - Add PAR on Y138 at Saco Valley, retension lines, upgrade Beebe terminal, and add capacitor banks at White Lake and Beebe. | Under Construction | Under Construction | 01/01/2006 | No | 27775000 | 27775000
Reliability Upgrade | 1a | 176 | Northeast Utilities |  | 2009-08-01 | Monadnock Area Reliability Project | New Fitzwilliam 345/115kV substation along with 345 kV breakers. | Under Construction | Under Construction | 2007-09-27 | No | 76100000 | 76100000
Reliability Upgrade | 1a | 174 | National Grid, USA |  | 2009-08-01 | Monadnock Area Reliability Project | Reconductor I-135 (Bellows Falls-Monadnock Tap-Flagg Pond) 115 kV line. | Under Construction | Under Construction | 03/24/2006 | No | 9600000 | 15778000
Reliability Upgrade | 1a | 277 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Concept | Planned | 2009-06-29 | No | TBD | 56600000
Reliability Upgrade | 1a | 1137 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115kV breakers and add 1-115kV breaker at Deerfield Substation |  | Planned | 2009-06-29 | No |  | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1138 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rebuild 115kV L175 line |  | Planned | 2009-06-29 | No |  | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1139 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV M183 Line |  | Planned | 2009-06-29 | No |  | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1140 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line |  | Planned | 2009-06-29 | No |  | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1141 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades |  | Planned | 2009-06-29 | No |  | Part of 2nd Deerfield 345/115kV Autotransformer Project
Elective | 4b | 1142 | FPL New England Division |  | 10/2009 |  | Seabrook Station Reconfiguration and Circuit Breaker addition Stages 1 &2 |  | Planned | 2008-11-20 | NR |  | TBD
Reliability Upgrade | 1a | 680 | National Grid, USA |  | 06/2012 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | Planned | 2008-01-28 | No | 11497000 | 11497000
Reliability Upgrade | 1a | 674 | National Grid, USA |  | 05/2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | Planned | 2008-04-01 | No | 12000000 | 12000000
Generator Interconnection Upgrade | 2a | 724 | National Grid, USA |  | 11/2009 | NGRID Comerford Substation | NGRID Comerford Substation. | Planned | Planned | 2007-06-12 | NR | NR | NR
VERMONT
Reliability Upgrade | 1a | 320 | Vermont Electric Power Company |  | 09/2009 | Lamoille County Project | Middlesex Substation 115 kV breaker addition. | Under Construction | Under Construction | 08/16/2007 | 02/07/2008 | 4857000 | 4857000
Reliability Upgrade | 1a | 322 | Vermont Electric Power Company |  | 09/2009 | Lamoille County Project | Installation of new Duxbury Substation that involves looping in and out of the Middlesex - Essex 115 kV (K24) line. | Under Construction | Under Construction | 08/16/2007 | 02/07/2008 | Part of Lamoille County Project | Part of Lamoille County Project
Reliability Upgrade | 1a | 139 | Vermont Electric Power Company |  | 12/2010 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Planned | Planned | 01/10/2003 | 03/31/2003 | 20000000 | 20000000
Reliability Upgrade | 1a | 182 | Vermont Electric Power Company |  | 09/2009 | Monadnock Area Reliability Project | Upgrade bus cable at N. Rutland and K35 115 kV breaker at Rutland. | Under Construction | Under Construction | 03/24/2006 | No | 1000000 | 1000000
Reliability Upgrade | 1a | 321 | Vermont Electric Power Company |  | 12/2009 |  | Burlington 115kV Loop - 5 mi of new line & rebuilding 5 miles of existing line between two existing substations with expansion of the East Avenue substation. | Under Construction | Under Construction | 10/24/2006 | 05/23/2007 | 25142000 | 25142000
Reliability Upgrade | 1a | 323 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | New VY - Newfane - Coolidge 345 kV line with requisite station upgrades. | Under Construction | Under Construction | 2008-10-01 | No | 136368000 | 136368000
Reliability Upgrade | 1a | 1032 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Installation of a new 345/115kV substation called Vernon including a new 345/115kV autotransformer | Under Construction | Under Construction | 2008-10-01 | No | 69815000 | 69815000
Reliability Upgrade | 1a | 1033 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project (VELCO LSP - Newfane Substation) | Installation of a new 345/115kV substation called Newfane | Under Construction | Under Construction | 2008-10-01 | No | 16664000 | 16664000
Reliability Upgrade | 1a | 1034 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Loop new 345kV Line into Newfane Substation. | Under Construction | Under Construction | 2008-10-01 | No | Part of project 323 | Part of project 323
Reliability Upgrade | 1a | 1035 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Expansion of Coolidge 345kV substation | Under Construction | Under Construction | 2008-10-01 | No | 20117000 | 20117000
Generator Interconnection Upgrade | 2a | 1036 | Vermont Electric Power Company |  | 12/2009 | Queue Position 172 | Installation of 3-breaker 115kV ring bus interconnection of the St. Johnsbury-Irasburg 115kV K39 line. | Planned | Planned | 08/16/2007 | NR | NR | NR
MASSACHUSETTS
Reliability Upgrade | 1a | 1063 | NSTAR Electric Company |  | 12/2009 |  | Install (2) 115kV 40 MVAR shunt reactors at Edgar Station | Proposed | Planned | 05/2009 | No | 5400000 | 5400000
Reliability Upgrade | 1a | 887 | National Grid, USA |  | 09/2012 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Planned | Planned | 2008-01-28 | No | 30000000 | 30000000
Reliability Upgrade | 1a | 921 | National Grid, USA |  | 01/2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | Planned | 2008-01-28 | No | 12100000 | 12100000
Reliability Upgrade | 1a | 919 | National Grid, USA |  | 12/2012 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | Planned | 2008-01-28 | No | 4600000 | 4600000
Reliability Upgrade | 1a | 783 | National Grid, USA |  | 03/2011 | Merrimack Valley/North Shore Reliability Project | Extend the 115kV by addition of 115kV Breaker and K-153 line from King St. to W. Amesbury 115kV station. (W. Amesbury 345/115kV Station becomes PTF) | Concept | Planned | 2008-04-01 | No | 30349000 | 30349000
Reliability Upgrade | 1a | 777 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Build Wakefield Junction station with four 345/115 kV autotransformers. | Under Construction | Under Construction | 2008-04-01 | No | 95000000 | 95000000
Reliability Upgrade | 1a | 161 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Loop 345 kV 339 line and 115 kV S-145/T-146 into new Wakefield Jct. Substation. | Under Construction | Under Construction | 2008-04-01 | No | 4986431 | 4986431
Reliability Upgrade | 1a | 779 | National Grid, USA |  | 04/2010 | Merrimack Valley/North Shore Reliability Project | Bypass and remove Golden Hills 345 kV substation. | Under Construction | Under Construction | 2008-04-01 | No | 5132609 | 5132609
Reliability Upgrade | 1a | 840 | NSTAR Electric Company |  | 10/2010 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | Planned | 2008-04-01 | No | 7300000 | 7300000
Reliability Upgrade | 1a | 775 | National Grid, USA |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Addition of 4 breakers and relocation of T1 and T2 into new bays at Sandy Pond. | Planned | Planned | 2008-06-27 | No | 20100000 | 20100000
Reliability Upgrade | 1a | 776 | National Grid, USA |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | Planned | 2008-06-27 | No | 2865876 | 2865876
Reliability Upgrade | 1a | 782 | National Grid, USA |  | 10/2013 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor n Railyard. | Planned | Planned | 2008-06-27 | No | 38100000 | 38100000
Reliability Upgrade | 1a | 961 | NSTAR Electric Company |  | 11/2010 | Mystic Breaker Additions Project | Install (2) new 115 kV East Bus breakers #30 and #32 at Mystic and move Transformer 110B Connection. | Planned | Planned | 2008-03-10 | No | 3800000 | 3800000
Reliability Upgrade | 1a | 903 | NSTAR Electric Company |  | 12/2009 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #2, #4, #5, and #16 at Mystic to IPT and separate controls with Boston Gen units #5 and #6. | Planned | Planned | NR | NR | 1240000 | 1240000
Reliability Upgrade | 1a | 904 | NSTAR Electric Company |  | 12/2010 | Mystic IPT Breaker Project | Upgrade (5) 115 kV breakers #1, #7, #15 #19 and #20 at Mystic to IPT and separate controls with Boston Gen #4. | Planned | Planned | NR | NR | 990000 | 990000
Reliability Upgrade | 1a | 59 | National Grid, USA |  | 01/2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | Planned | 2007-11-01 | 2003-01-31 | 400000 | 400000
Reliability Upgrade | 1a | 832 | NSTAR Electric Company |  | 2009-08-01 | Short Term Lower SEMA Upgrades | Add(1) 115kV SVC (0-112 MVARs lagging) at Barnstable. | Under Construction | Under Construction | 08/17/2007 | No | $86.6 M (Total NSTAR Project Cost | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade
Reliability Upgrade | 1a | 929 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | Planned | 12/17/2007 | No | 1381849 | 1381849
Reliability Upgrade | 1a | 931 | National Grid, USA |  | 01/2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | Planned | 12/17/2007 | No | 531481 | 531481
Reliability Upgrade | 1a | 936 | National Grid, USA |  | 07/2009 | Central/Western Massachusetts Upgrades | Reconductor (P142/P142S) Rolfe Avenue - West Bolyston 115 kV line w/1590 ACSR. | Planned | Under Construction | 12/17/2007 | No | 3000000 | 3000000
Reliability Upgrade | 1a | 928 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | Planned | 12/17/2007 | No | 1945218 | 1945218
Reliability Upgrade | 1a | 930 | National Grid, USA |  | 12/2009 | Central/Western Massachusetts Upgrades | Reconductor Nashua St - Quinsigamond Jct (O141) 115 kV line w/636 ACSS. | Planned | Planned | 12/17/2007 | No | 2300000 | 2300000
Reliability Upgrade | 1a | 934 | National Grid, USA |  | 10/2010 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Planned | Planned | 12/17/2007 | No | 818480 | 818480
Reliability Upgrade | 1a | 935 | National Grid, USA |  | 07/2010 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Planned | Planned | 12/17/2007 | No | 5208509 | 5208509
Reliability Upgrade | 1a | 933 | National Grid, USA |  | 04/2010 | Central/Western Massachusetts Upgrades | Reconductor Pratts Jct - Flagg Pond I-135S & J-136S 115 kV lines w/795 ACSS. | Planned | Planned | 12/17/2007 | No | 6137112 | 6137112
Reliability Upgrade | 1a | 938 | National Grid, USA |  | 06/2010 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | Planned | 12/17/2007 | No | 3068556 | 3068556
Reliability Upgrade | 1a | 939 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Reconductor and retension (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | Planned | Planned | 12/17/2007 | No | 3389658 | 3389658
Reliability Upgrade | 1a | 940 | National Grid, USA |  | 04/2011 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS. | Planned | Planned | 12/17/2007 | No | 6235744 | 6235744
Reliability Upgrade | 1a | 942 | National Grid, USA |  | 10/2010 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | Planned | 12/17/2007 | No | 2767180 | 2767180
Reliability Upgrade | 1a | 927 | National Grid, USA |  | 07/2010 | Central/Western Massachusetts Upgrades | Greendale - replace 115 kV breaker and upgrade to 2000A. | Planned | Planned | 12/17/2007 | No | 584629 | 584629
Reliability Upgrade | 1a | 925 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | Planned | 12/17/2007 | No | 318888 | 318888
Reliability Upgrade | 1a | 926 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | Planned | 12/17/2007 | No | 6027520 | 6027520
Reliability Upgrade | 1a | 932 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | Planned | 12/17/2007 | No | 372036 | 372036
Reliability Upgrade | 1a | 924 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | Planned | Planned | 12/17/2007 | No | 2147181 | 2147181
Reliability Upgrade | 1a | 941 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Install new Millbury - Tower #510 115 kV line. | Planned | Planned | 12/17/2007 | No | 7909203 | 7909203
Reliability Upgrade | 1a | 943 | National Grid, USA |  | 01/2011 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | Planned | 12/17/2007 | No | 1073995 | 1073995
Reliability Upgrade | 1a | 944 | National Grid, USA |  | 07/2012 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Planned | Planned | 12/17/2007 | No | 11411849 | 11411849
Reliability Upgrade | 1a | 950 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | Planned | 12/17/2007 | No | 1016897 | 1016897
Reliability Upgrade | 1a | 953 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | Planned | 12/17/2007 | No | 10248067 | 10248067
Reliability Upgrade | 1a | 954 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | E Westminster - install new 115 kV breaker, including disconnect switches. Assumes no new control house. | Planned | Planned | 12/17/2007 | No | 903909 | 903909
Reliability Upgrade | 1a | 945 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | Adams - install third 115 kV breaker to complete ring bus. | Planned | Planned | 12/17/2007 | No | 1581841 | 1581841
Reliability Upgrade | 1a | 946 | National Grid, USA |  | 04/2013 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer - E Longmeadow - Shaker Rd line to 115 kV. | Planned | Planned | 12/17/2007 | No | 9604032 | 9604032
Reliability Upgrade | 1a | 947 | National Grid, USA |  | 04/2013 | Central/Western Massachusetts Upgrades | Reconductor 115 kV line from Palmer to new Hampden Substation. | Planned | Planned | 12/17/2007 | No | 2632635 | 2632635
Reliability Upgrade | 1a | 948 | National Grid, USA |  | 07/2012 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | Planned | 12/17/2007 | No | 5649430 | 5649430
Reliability Upgrade | 1a | 949 | National Grid, USA |  | 07/2012 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | Planned | 12/17/2007 | No | 1694829 | 1694829
Reliability Upgrade | 1a | 952 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Reconductor E Winchendon - J136 Tap within I135/J136 ROW w/795 ACSR. | Planned | Planned | 12/17/2007 | No | 932156 | 932156
Reliability Upgrade | 1a | 937 | National Grid, USA |  | 03/2011 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | Planned | 12/17/2007 | No | 6602875 | 6602875
Reliability Upgrade | 1a | 955 | National Grid, USA |  | 11/2011 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | Planned | 12/17/2007 | No | 10779113 | 10779113
Reliability Upgrade | 1a | 951 | National Grid, USA |  | 02/2013 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon 115 kV line. | Planned | Planned | 12/17/2007 | No | 7455440 | 7455440
Reliability Upgrade | 1a | 162 | National Grid, USA |  | 04/2011 |  | Q-169 Golden Hills to Lynn 115 kV line upgrade. | Under Construction | Under Construction | 2005-09-02 | 2008-04-25 | 12390000 | 12390000
Reliability Upgrade | 1a | 902 | National Grid, USA |  | 03/2012 | Middleboro Municipal | Close the E1-M1 loop at Middleboro's Wareham St Sub. | Under Construction | Under Construction | 12/01/2006 | NR | 715000 | 715000
Reliability Upgrade | 1a | 1000 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | Planned | Planned | 2008-06-27 | No | 22000000 | 22000000
Reliability Upgrade | 1a | 687 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | Planned | 2008-09-24 | No | 714000000 | 714000000
Reliability Upgrade | 1a | 826 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 196 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115kV line South Agawam to Southwick (1768) | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVAR Capacitor additions | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1074 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1076 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Planned | Planned | 2008-09-24 | No | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1077 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115kV line | Planned | Planned | 2008-09-24 | No | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1078 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 673 | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | Planned | 2009-02-27 | No | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Planned | Planned | 2009-02-27 | No | 30000000 | 30000000
Generator Interconnection Upgrade | 2a | 1045 | National Grid, USA |  | 06/2010 | Lowell Power | Upgrade 137T and K-137W 115 kV circuit breakers at Sandy Pond. | Planned | Planned | 2006-07-25 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 505 | National Grid, USA |  | 07/2010 | Hoosac Wind Farm | Tap Y-25S line between Harriman and Deerfield 5. Construct 69/34.5 kV substation and 34.5 kV line connecting 30 MW generating facility with the 69 kV system. | Planned | Planned | 02/01/2005 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 595 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Expansion of Barnstable 115 kV substation to include 5th bay and (2) circuit breakers, addition of a 3rd breaker in the planned 4th bay, and (2) 35MVAr shunt reactors. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 596 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Installation of (2) 115 kV circuits out of Barnstable substation to interconnect Cape Wind. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 598 | NSTAR Electric Company |  | 11/2010 | Cape Wind | At Canal 345 kV substation, install a redundant breaker in series with breaker #312. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 599 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Upgrade the Bourne 115 kV breaker #12272 with an IPT breaker. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 600 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Installation of differential insulation and additional grounding at each tower that is common for the 342 and 322 345 kV lines. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1048 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Convert Canal 345 kV SPS to include tripping of Cape Wind for the simultaneous loss of 342 and 322 345 kV lines. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1046 | National Grid, USA |  | 06/2011 | Queue Position 178 | Reconductor 115 kV F19 Line (Auburn - Brockton Tap). | Proposed | Proposed | 2008-03-10 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1047 | National Grid, USA |  | 06/2011 | Queue Position 178 | Replace Bridgewater 115 kV 1631 circuit breaker with 63 kA breaker. | Proposed | Proposed | 2008-03-10 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 622 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Interconnection to WMECO's 115-kV 1512 line through a new Substation. | Proposed | Proposed | 06/01/2007 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1043 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Upgrade the 1768 line terminal equipment at Southwick Substation. | Proposed | Proposed | 06/01/2007 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1044 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Upgrade the 1512 line terminal equipment at Southwick Substation. | Proposed | Proposed | 06/01/2007 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1058 | National Grid, USA |  | 06/2011 | Billerica Power | Interconnection to Tewksbury 115 kV Substation via O-193 Line and refurbish section of J-162 line. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1059 | National Grid, USA |  | 06/2011 | Billerica Power | Re-terminate line tap section (Perry Street) of J-162 Line to new bay position at Tewksbury. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1060 | National Grid, USA |  | 06/2011 | Billerica Power | Reconductor 2.8 mi. of the M-139 115 kV line. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1061 | National Grid, USA |  | 06/2011 | Billerica Power | Replace (16) 115 kV circuit breakers at Tewksbury 22 w/ IPT capability if all generators w/ higher Queue Position are constructed. The quantity of breaker upgrades subject to Queued generators constructed. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1062 | National Grid, USA |  | 06/2011 | Billerica Power | Upgrade #137T and #K-137W 115 kV circuit breakers at Sandy Pond (if not completed as part of Merrimack Valley/North Shore Project). | Planned | Planned | 2008-07-08 | NR | NR | NR
Elective | 4a | 1057 | Braintree Electric Light Department |  | 06/2010 |  | Upgrade 115-10-16 underground 115 kV cable. | Planned | Planned | 2008-04-17 | No | TBD | TBD
RHODE ISLAND
Reliability Upgrade | 1a | 484 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Planned | Planned | 2008-04-25 | No | 690000 | 690000
Reliability Upgrade | 1a | 791 | National Grid, USA |  | 06/2013 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | Planned | 2008-04-25 | No | 11560000 | 11560000
Reliability Upgrade | 1a | 913 | National Grid, USA |  | 06/2013 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | Planned | 2008-04-25 | No | 3250000 | 3250000
Reliability Upgrade | 1a | 914 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | Planned | 2008-04-25 | No | 28150000 | 28150000
Reliability Upgrade | 1a | 915 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | Planned | 2008-04-25 | No | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | Planned | 2008-04-25 | No | 11800000 | 11800000
Reliability Upgrade | 1a | 917 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | Planned | 2008-04-25 | No | 7000000 | 7000000
Reliability Upgrade | 1a | 918 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | Planned | 2008-04-25 | No | 3180000 | 3180000
Reliability Upgrade | 1a | 792 | National Grid, USA |  | 06/2013 | Greater Rhode Island Transmission Reinforcements 1 | Admiral St-Franklin Square (Q143 and R144) 115 kV UG recabling. | Planned | Planned | 2008-04-25 | No | 39200000 | 39200000
Reliability Upgrade | 1a | 793 | National Grid, USA |  | 06/2013 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | Planned | 2008-04-25 | No | 6400000 | 6400000
Reliability Upgrade | 1a | 786 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Terminal upgrades at Drumrock, Chartley Pond, and Brayton Point. | Planned | Planned | 2008-04-25 | No | 565000 | 565000
Reliability Upgrade | 1a | 787 | National Grid, USA |  | 12/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | West Farnum breaker replacements. | Planned | Planned | 2008-04-25 | No | 7631000 | 7631000
Reliability Upgrade | 1a | 788 | National Grid, USA |  | 12/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Kent County substation expansion. | Planned | Planned | 2008-04-25 | No | 42300000 | 42300000
Reliability Upgrade | 1a | 789 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Reconductoring of T7 115 kV line. | Planned | Planned | 2008-04-25 | No | 23304000 | 23304000
Reliability Upgrade | 1a | 790 | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Planned | Planned | 2008-04-25 | No | 50600000 | 50600000
Reliability Upgrade | 1a | 1098 | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Planned | Planned | 2008-04-25 | No | 37529000 | 37529000
Reliability Upgrade | 1a | 190 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | Planned | 2008-09-24 | No | 69600000 | 69600000
Reliability Upgrade | 1a | 1094 | National Grid, USA |  | 06/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | Planned | 2008-09-24 | No | 20800000 | 20800000
Reliability Upgrade | 1a | 1095 | National Grid, USA |  | 06/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | Planned | 2008-09-24 | No | 73800000 | 73800000
Reliability Upgrade | 1a | 794 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | Planned | 2008-09-24 | No | 55800000 | 55800000
Reliability Upgrade | 1a | 796 | National Grid, USA |  | 11/2012 | NEEWS (Interstate Reliability Project) | 347 Reconductor from Sherman Road to CT/RI Border. | Planned | Planned | 2008-09-24 | No | 16400000 | 16400000
Reliability Upgrade | 1a | 797 | National Grid, USA |  | 12/2012 | NEEWS (Interstate Reliability Project) | 3361 Upgrade 345kV terminal equipment at Sherman Road. | Planned | Planned | 2008-09-24 | No | 8300000 | 8300000
Reliability Upgrade | 1a | 795 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV line. | Planned | Planned | 2008-09-24 | No | 99900000 | 99900000
Reliability Upgrade | 1a | 1106 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | Planned | Planned | 2008-09-24 | No | Part of $99,900,000 above | Part of $99,900,000 above
Reliability Upgrade | 1a | 798 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Planned | Planned | 2008-09-24 | No | 4900000 | 4900000
Reliability Upgrade | 1a | 799 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | Planned | Planned | 2008-09-24 | No | 4500000 | 4500000
Reliability Upgrade | 1a | 1096 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | Planned | 2008-09-24 | No | 5800000 | 5800000
Reliability Upgrade | 1a | 800 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S, T-172N and T-172S with associated terminal equipment upgrades. | Planned | Planned | 2008-09-24 | No | 7300000 | 7300000
Reliability Upgrade | 1a | 1097 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County | Planned | Planned | 2008-09-24 | No | 129800000 | 129800000
Reliability Upgrade | 1a | 1099 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | Planned | 2008-09-24 | No | 4100000 | 4100000
Reliability Upgrade | 1a | 1109 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Planned | Planned | 2008-09-24 | No | 360000 | 360000
CONNECTICUT
Reliability Upgrade | 1a | 211 | Northeast Utilities |  | 10/2009 | NU LSP - Rood Ave Substation | New Rood Ave (formally Windsor) distribution substation with 115kV terminal modifications. | Under Construction | Under Construction | 2008-04-25 | 02/15/2008 | 9162029 | 9162029
Reliability Upgrade | 1a | 1049 | United Illuminating Company |  | 12/2010 |  | East Shore 115 kV Capacitor Bank Transient Recovery | Planned | Planned | NR | NR | 3000000 | 3000000
Reliability Upgrade | 1a | 582 | Northeast Utilities |  | 12/2010 |  | Separate 310 and 368 345-KV lines and create 368/1767 DCT | Planned | Planned | 2008-07-18 | No | 16000000 | 16000000
Reliability Upgrade | 1a | 1112 | United Illuminating Company |  | 12/2010 |  | Water Street 115kV circuit breaker and switch replacements. | Planned | Planned | NR | NR | 1000000 | 1000000
Reliability Upgrade | 1a | 974 | United Illuminating Company |  | 12/2011 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Planned | Planned | NR | No | 6700000 | 6700000
Reliability Upgrade | 1a | 816 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1054 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Manchester - Meekvile Jct. line (395/1448) separation. | Planned | Planned | 2008-09-24 | No | 14000000 | 14000000
Reliability Upgrade | 1a | 576 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | Planned | 2008-09-24 | No | 313000000 | 313000000
Reliability Upgrade | 1a | 1114 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1a | 814 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Central Connecticut Relaibility Project) | Reconductor a portion of the Manchester to Scovill Rock 353 345-kV line and terminal work. | Planned | Planned | 2008-09-24 | No | 9000000 | 9000000
Reliability Upgrade | 1a | 802 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | Planned | 2008-09-24 | No | 251000000 | 251000000
Reliability Upgrade | 1a | 1084 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Loop the Millstone - Manchester (310) 345 kV line into the Card substation. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1085 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1086 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1087 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1088 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1089 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Killingly 3G substation 345kV breaker addition | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1090 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Millstone 15G substation breaker 14T upgrade 50kA | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1091 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Southington 4C substation breaker 19T upgrade to 63kA | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | Northeast Utilities | National Grid, USA | 12/2013 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 807 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Interstate Reliability Project) | Install 480 MVAR's of capacitors at the Montville 345 kV substation | Planned | Planned | 2008-09-24 | No | 33000000 | 33000000
Reliability Upgrade | 1a | 1092 | Northeast Utilities |  | 12/2013 | NEEWS (BPS) 2 | Upgrade the Card 115 kV, East Hartford 115 kV, Agawam 115 kV, Barbour Hill 115 kV, and North Bloomfield 345 kV Substations to BPS standards. | Planned | Planned | 2008-09-24 | No | 37000000 | 37000000
Reliability Upgrade | 1a | 1056 | Northeast Utilities |  | 12/2011 | CT LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Planned | Planned | 2008-12-12 | No | 9751000 | 9751000
Reliability Upgrade | 1a | 1110 | United Illuminating Company |  | 06/2010 |  | Broadway 115/13.8 kV Substation Additon | Planned | Planned | 2008-12-08 | No | 800000 | 1200000
Reliability Upgrade | 1a | 1111 | United Illuminating Company |  | 09/2010 |  | Metro North Union Avenue 115/26.4 kV Substation | Planned | Planned | 2009-01-07 | No | 8700000 | 10543000
Reliability Upgrade | 1a | 976 | United Illuminating Company |  | 05/2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Planned | Planned | 2009-01-07 | No | 48000000 | 48000000
Reliability Upgrade | 1a | 1050 | United Illuminating Company |  | 12/2011 |  | Devon Tie 115kV Switching Station BPS Compliance | Planned | Planned | NR | NR | 2620000 | 2620000
Reliability Upgrade | 1a | 879 |  | Bangor Hydro-Electric Company, New England Power Company, Northeast Utilities System Com | TBD | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | Planned | 03/01/2007 | NR | 420000 | 420000
Generator Interconnection Upgrade | 2a | 983 | Northeast Utilities |  | 10/2010 | Queue Position 207/241 | Rebuild 115 kV 1585N Line between new substation and Bunker Hill. | Proposed | Proposed | 2008-09-26 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1107 | Northeast Utilities |  | 10/2010 | Queue Position 207/241 | Interconnection to new 115 kV substation consisting of (14) circuit breakers in a breaker and a half configuration that sectionalizes the existing 1575, 1585, and 1990 lines. | Proposed | Proposed | 2008-09-26 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1108 | Northeast Utilities |  | 10/2010 | Queue Position 207/241 | Installation of a 2.5% series reactor on the 1990S Line at the new substation. | Proposed | Proposed | 2008-09-26 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 331 | Northeast Utilities |  | 11/2010 | Kleen Energy | Install 5-breaker ring bus interconnecting between Scovill Rock and Manchester on the 345 kV 353 Line. | Planned | Under Construction | 10/08/2003 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1121 | Northeast Utilities |  | 06/2010 | Queue Position 161-2 | Four units connected to 384 line through a new 345kV Substation: unit #4 wll also connect to Substation | Proposed | Proposed | 2008-12-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1122 | Northeast Utilities |  | 11/2010 | Queue Position 191 | One turbine connected to #1238 Line (Frost Bridge to Carmel) via a new 3-breaker ring bus Substation | Proposed | Proposed | 2009-02-24 | NR | NR | NR
TABLE B
MAINE
Reliability Upgrade | 1b | 148 | Central Maine Power Company |  | 06/2012 | CMP LSP - Saco Bay Area Reinforcement Project | Establish a new Vallee Lane 115/34.5 kV substation and 115 kV line. | Proposed | Proposed | No | NR | 16900000 | 100000
Reliability Upgrade | 1b | 1116 | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1031 | Bangor Hydro-Electric Company |  | 01/2012 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station, Rebuild Line 66, and Capacitior Bank Additions (10MVAr at Trenton, Downeast & Handcock County area) | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1130 | Central Maine Power Company |  | 12/2011 | Sturtevant Improvements | Add 115kV circuit breakers & 25 MVAR capacitor bank at Sturtevant Substation; Re-rate Section 63 between Wyman Hydro & Madison Substation | Proposed | Proposed | No | No | 2000000 | 3000000
Reliability Upgrade | 1b | 1131 | Central Maine Power Company |  | 12/2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Proposed | Proposed | No | NR | 600000 | 600000
Reliability Upgrade | 1b | 1132 | Central Maine Power Company |  | 12/2011 | CMP-LSP Maxcy's Substation | Add 115/34kV transformer (coordinate with MPRP) | Proposed | Proposed | No | NR | 600000 | 600000
Reliability Upgrade | 1b | 1133 | Central Maine Power Company |  | 10/2010 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation & new 34kV line from Leeds to Turner | Proposed | Proposed | No | NR | 2500000 | 300000
Reliability Upgrade | 1b | 1135 | Central Maine Power Company |  | TBD | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer |  | Proposed | No | No |  | 1500000
Elective | 4b | 1018 | Bangor Hydro-Electric Company |  | TBD | Orrington-Boston HVDC | Orrington substation reconfiguration and addition of new HVDC cable system terminating in Boston area. | Concept | Concept | No | No | TBD | TBD
Elective | 4b | 984 | Central Maine Power Company | Maine Public Service | TBD | MEPCO-MPS 345 kV Interconnection | MEPCO-MPS 345 kV Interconnection. | Concept | Concept | No | No | TBD | TBD
NEW HAMPSHIRE
Reliability Upgrade | 1b | 275 | Northeast Utilities |  | TBD |  | Merrimack 115-kV substation - Protection Separation Upgrade. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1143 | Northeast Utilities |  | TBD |  | Littleton 115kV breaker addition and reconfiguration |  | Proposed | No | No |  | 5338000
VERMONT
Reliability Upgrade | 1b | 318 | Vermont Electric Power Company |  | 12/2011 |  | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems through the 1,250 MW Vermont state load level. | Concept | Concept | No | No | 9000000 | 9000000
Reliability Upgrade | 1b | 325 | Vermont Electric Power Company |  | 12/2011 | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | Concept | No | No | 5000000 | 5000000
Reliability Upgrade | 1b | 324 | Vermont Electric Power Company |  | 12/2012 |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | Concept | No | No | 100000000 | 100000000
MASSACHUSETTS
Reliability Upgrade | 1b | 785 | National Grid, USA |  | 07/2017 | Merrimack Valley/North Shore Reliability Project | Re-conductor F-158N (Golden Hills-Maplewood-Everett) 115 kV line. | Concept | Concept | No | No | 1330000 | 1330000
Reliability Upgrade | 1b | 963 | NSTAR Electric Company |  | 12/2009 | Boston Area 115 kV Enhancements | Add a new 115kV breaker # 11 Relocate 447, 509 and add control and protect at Holbrook. | Proposed | Proposed | No | No | 3400000 | 4000000
Reliability Upgrade | 1b | 842 | NSTAR Electric Company |  | 06/2010 | Boston Area 115 kV Enhancements | Add 115 kV 54 MVAR capacitor bank at W. Framingham. | Proposed | Proposed | No | No | 3000000 | 3000000
Reliability Upgrade | 1b | 843 | NSTAR Electric Company |  | 12/2013 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 965 | NSTAR Electric Company |  | 12/2012 | Boston Area 115 kV Enhancements | Add third 115kV line from Walpole to Holbrook | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 964 | NSTAR Electric Company |  | 06/2011 | Boston Area 115 kV Enhancements | Relocate 115kV terminals at W. Walpole to mitigate breaker failure #8. | Proposed | Proposed | No | No | 5600000 | 5600000
Reliability Upgrade | 1b | 969 | NSTAR Electric Company |  | 06/2018 | Boston Area 115 kV Enhancements | Add a new 54 MVAR capacitor bank at Chelsea. | Concept | Concept | No | No | 1200000 | 1200000
Reliability Upgrade | 1b | 301 | NSTAR Electric Company |  | 12/2011 | Boston Area 115 kV Enhancements | Reconductor 115-kV circuits 320-507 and 320-508. | Concept | Concept | No | No | 4600000 | 4600000
Reliability Upgrade | 1b | 1113 | NSTAR Electric Company |  | 06/2010 |  | Install KSt Breaker #31 | Proposed | Proposed | No | No | 2100000 | 2100000
Reliability Upgrade | 1b | 593 | NSTAR Electric Company |  | 2013 | Mid-Cape Reliability | Add a new 115 kV line from Canal to Barnstable. | Proposed | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1068 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to Sandwich and a a 345-115kV auto-transformer at Sandwich | Proposed | Proposed | No | No | 110000000 | 110000000
Reliability Upgrade | 1b | 592 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing | Proposed | Proposed | No | No | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1117 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install 115kV 50 MVAR capacitor bank at Falmouth | Proposed | Proposed | No | No | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1118 | NSTAR Electric Company | National Grid, USA | 12/2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 and 111 | Proposed | Proposed | No | No | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1067 | NSTAR Electric Company |  | 12/2010 | NPCC BPS Compliance | Tremont Station | Proposed | Proposed | No | No | 11200000 | 14122000
Reliability Upgrade | 1b | 1066 | NSTAR Electric Company |  | 09/2011 | NPCC BPS Compliance | Needham Station | Proposed | Concept | No | No | 9300000 | 9300000
Reliability Upgrade | 1b | 1065 | NSTAR Electric Company |  | 07/2012 | NPCC BPS Compliance | Waltham Station | Proposed | Concept | No | No | 24300000 | 24300000
Reliability Upgrade | 1b | 970 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345 kV line from Lexington to Waltham. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 971 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1119 | NSTAR Electric Company |  | 12/2010 | Greater Boston Reliability Project | Upgrade West Medway-West Walpole 345kV line (#325 ) | Proposed | Proposed | No | No | 1300000 | 2200000
Reliability Upgrade | 1b | 1120 | NSTAR Electric Company |  | 06/2010 |  | Install 345kV 160 MVAR shunt ractor at W. Walpole | Proposed | Proposed | No | No | 6000000 | 7200000
Reliability Upgrade | 1b | 956 | National Grid, USA |  | 05/2013 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Concept | Concept | No | No | 7021534 | 7021534
Reliability Upgrade | 1b | 824 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 825 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Upgrade the Pleasant to Blanford 115-kV line and the Blanford to Granville Jct. portion of the 115-kV line 1512. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1136 | National Grid, USA |  | 06/2011 |  | New 115kV Switching Station at Devens Convert 69kV lines to 115kV, Reconfigure 115kV Supply at Ayer Substation |  | Proposed |  | No |  | 9200000
Generator Interconnection Upgrade | 2b | 863 | Northeast Utilities |  | 06/2010 | Queue Position 217 | Northfield Mountain - W. Mass Northfield 345 kV substation. | Proposed | Proposed | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1014 | Northeast Utilities |  | 06/2010 | Queue Position 196 | 345 kV Northfield Substation | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1123 | Northeast Utilities |  | TBD | Queue Position 236 | New Substation on 1302 Line; terminal upgrades at Buck Pond and Agawam | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 880 | National Grid, USA | Northeast Utilities | 06/2011 | Queue Position 177 | Sutton Energy - 345 kV Carpenter Hill-Millbury Line. | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1042 | National Grid, USA |  | 06/2013 | Queue Position 165 | Replace (2) 345 kV circuit breakers at Sandy Pond | Concept | Concept | No | NR | NR | NR
RHODE ISLAND
Generator Interconnection Upgrade | 2b | 881 | National Grid, USA | Northeast Utilities | 06/2012 | Queue Position 201 | RISEP - 345 kV RISE Substation. | Concept | Concept | No | NR | NR | NR
CONNECTICUT
Reliability Upgrade | 1b | 1055 | Northeast Utilities |  | 2010 | CT LSP - Waterside Substation | Waterside Substation - add a 115/13.2-kV transformer and a 115-kV circuit breaker. | Concept | Concept | No | No | 4107000 | 4107000
Reliability Upgrade | 1b | 809 | Northeast Utilities |  | 12/2009 |  | Upgrade terminal equipment at Bunker Hill 115 kV substation. | Proposed | Proposed | No | No | 1000000 | 1000000
Reliability Upgrade | 1b | 721 | United Illuminating Company |  | 06/2013 |  | New Shelton 115/13.8 kV substation | Proposed | Proposed | No | No | 11300000 | 11300000
Reliability Upgrade | 1b | 975 | United Illuminating Company |  | 12/2013 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | Concept | No | No | 44300000 | 44300000
Reliability Upgrade | 1b | 699 | United Illuminating Company |  | 12/2012 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | Concept | No | No | 10000000 | 10000000
Reliability Upgrade | 1b | 801 | Northeast Utilities |  | TBD |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 85 | Northeast Utilities |  | TBD |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | Concept | 08/04/2004 | No | TBD | TBD
Generator Interconnection Upgrade | 2b | 1124 | Northeast Utilities |  | TBD | Queue Position 2422 | New Substation on Haddam Neck-Southington 345kV line | Proposed | Proposed | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1125 | Northeast Utilities |  | TBD | Queue Position 240 | 345kV on Montville Substation | Concept | Concept | No | NR | NR | NR
IN-SERVICE PROJECTS
Reliability Upgrade | 1a | 626 | Central Maine Power Company |  | 04/2009 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of 115/34.5 kV transformer and six new 115 kV breakers and a half substation at Woodstock. | Planned | In-service | 2007-11-30 | No | 8000000 | 8000000
Reliability Upgrade | 1a | 575 | Central Maine Power Company |  | 05/2009 | Heywood Road Project | New Heywood Rd 115kV switchyard with (6) 115kV circuit breakers (3) 115kV line retensionings and 115kV 20 MVAr capacitor bank at Heywood Rd. | Under Construction | In-service | 2009-03-20 | 2009-07-20 | 7000000 | 7000000
Reliability Upgrade | 1a | 1127 | Central Maine Power Company |  | 05/2009 | CMP-LSP Newcastle Substation | Add 115/34kV transformer with two 115kV breakers | Under Construction | In-service | 2008-08-20 | 2008-08-20 | 1300000 | 1300000
Reliability Upgrade | 1a | 166 | National Grid, USA |  | 06/2009 |  | Replace (16) 115 kV breakers at Tewksbury 22. | Under Construction | In-service | NR | NR | 3300000 | 3300000
Reliability Upgrade | 1a | 1009 | Northeast Utilities |  | 05/2009 |  | Install a 2% reactor on the North Bloomfield-Canton 115kV line and also replacement fo the Frostbridge 345/115kV autotransformer | Under Construction | In-service | 2007-10-20 | 2009-10-16 | 3638000 | 3089000
Reliability Upgrade | 1a | 203 | Northeast Utilities |  | 05/2009 | NU LSP - Stepstone Substation | Install new Stepstone 115 kV substation in Guilford. | Under Construction | In-service | 2005-11-08 | 2006-04-24 | 6332000 | 6332000
Reliability Upgrade | 1a | 1064 | NSTAR Electric Company |  | 04/2009 |  | Install (1) 345kV 160 MVAR shunt reactor at Mystic Station | Planned | In-service | 2008-09-26 | No | 10400000 | 10400000
Reliability Upgrade | 1a | 302 | NSTAR Electric Company |  | 05/2009 | Boston Area 115 kV Enhancements | DCT separation of Framingham to Speen St. 433-507 circuit. | Under Construction | In-service | 01/18/2005 | 03/01/2005 | 3100000 | 3100000
Reliability Upgrade | 1a | 695 | NSTAR Electric Company |  | 07/2009 | Short Term Lower SEMA Upgrades | Loop (355) 345 kV line in and out of Carver Substation and add (5) new 345 kV circuit breakers at Carver substation. | Under Construction | In-service | 08/17/2007 | No | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 830 | NSTAR Electric Company |  | 07/2009 | Short Term Lower SEMA Upgrades | Add a second 345/115 kV Auto transformer at Carver substation and add (1) new 345 kV circuit breaker and (3) new 115 kV circuit breakers at Carver substation. | Under Construction | In-service | 08/17/2007 | No | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 831 | NSTAR Electric Company |  | 07/2009 | Short Term Lower SEMA Upgrades | Add a second 115 kV line from Carver to Tremont and add (2) new 115 kV circuit breakers at Carver substation and (1) new 115 kV circuit breaker at Tremont substation. | Under Construction | In-service | 08/17/2007 | No | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA
CANCELLED PROJECTS
Generator Interconnection Upgrade | 2b | 861 | Northeast Utilities |  | 01/2010 | Queue Position 190 | Mount Tom - W Mass. Mt. Tom 115 kV Substation. | Concept | Cancelled | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 869 | Northeast Utilities |  | 06/2013 | Queue Position 226 | Rebuild 345 kV 326 Line | Concept | Cancelled | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1041 | Northeast Utilities |  | 06/2013 | Queue Position 226 | Rebuild 115 kV U181 Line | Concept | Cancelled | No | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1126 | Northeast Utilities |  | TBD | Queue Position 161-4 | Two units and repowering of #6 Montville 345kV Substation | Proposed | Cancelled | 2008-06-09 | NR | NR | NR
Reliability Upgrade | 1b | 316 | United Illuminating Company |  | 06/2012 |  | New Fairfield 115/13.8 kV substation | Concept | Cancelled | No | No | 7450000 | 7450000
Reliability Upgrade | 1b | 977 | United Illuminating Company |  | 06/2013 |  | New Orange 115/13.8 kV substation | Concept | Cancelled | No | No | 7550000 | 7550000
Reliability Upgrade | 1b | 980 | United Illuminating Company |  | 06/2014 |  | New Hamden 115/13.8 kV substation. | Concept | Cancelled | No | No | 7750000 | 7750000
Reliability Upgrade | 1b | 317 | United Illuminating Company |  | 06/2014 |  | New North Branford 115/13.8-kV substation. | Concept | Cancelled | No | No | 7750000 | 7750000
Notes
1 Project pending solution documentation for the Greater Rhode Island Transmission Reinforcements.
2 The Northeast Utilities' estimated costs for the NEEWS BPS upgrades are shared among the Greater Springfield, Central Connecticut, and Interstate portions of the NEEWS Project.
3 The total TCA (NU-07-TCA-24) PTF cost is $234.2 million for the Norwalk - Glenbrook Project. The forecasted PTF cost is $249.4 million.
4 The total TCA (NU-08-TCA-01) PTF cost is $1.05 billion for Northeast Utilities portion of the Middletown-Norwalk Project. The forecasted PTF cost is $978.2 million.
Local Project Listing Links
| NSTAR: |  | http://www.nstar.com/business/rates_tariffs/open_access/
| CMP: |  | http://www.cmpco.com/SuppliersAndPartners/TransmissionServices/CMPTransmissionSvc/lsp.html
| BHE: |  | http://www.bhe.com/data/OASIS/LSP.html
| VELCO: |  | http://www.vermontspc.com/About%20the%20VSPC/Home.aspx
| NU: |  | http://www.transmission-nu.com/business/pdfs/NU_Local_Transmission_Studies_List.pdf
| NGRID: |  | http://www.nationalgridus.com/oasis/
| UI: |  | http://www.uinet.com/uinet/resources/file/ebcfda4ccb73dd/UI%20Local%20System%20Plan.pdf

## Project List-April09 post (hidden)
April '09 ISO-NEW ENGLAND Project Listing Update (FINAL)
Primary Driver | Part# | Project ID | Primary Equipment Owner | Other Equipment Owner(s) | Projected In-Service Month/Year | Major Project | Project | Oct-08 Status | Apr -09 Status | PPA (I.3.9) Approval | TCA Approval | Oct-08 Estimated PTF Costs | Apr-09 Estimated PTF Costs
TABLE A
MAINE
Reliability Upgrade | 1a | 575 | Central Maine Power Company |  | 05/2009 | Heywood Road Project | New Heywood Rd 115kV switchyard with (6) 115kV circuit breakers (3) 115kV line retensionings and 115kV 20 MVAr capacitor bank at Heywood Rd. | Concept | Under Construction | 01/01/2007 | 2009-01-26 | 6100000 | 7000000
Reliability Upgrade | 1a | 1129 | Central Maine Power Company |  | 12/2012 | Heywood Road Project | New 115kV line between Wyman Hydro and Heywood Rd. parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination |  | Planned | 2009-01-26 | No |  | 19500000
Reliability Upgrade | 1a | 626 | Central Maine Power Company |  | 04/2009 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of 115/34.5 kV transformer and six new 115 kV breakers and a half substation at Woodstock. | Planned | Planned | 2007-11-30 | No | 7400000 | 8000000
Reliability Upgrade | 1a | 1051 | Central Maine Power Company |  | 05/2009 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Riley 115 kV capacitor bank. | Planned | Planned | 2007-11-30 | No | Portion of 5,400,000 (above) | Part of Project 625
Reliability Upgrade | 1a | 625 | Central Maine Power Company |  | 02/2010 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Rumford Industrial Park capacitor bank. | Planned | Planned | 2007-11-30 | No | 5400000 | 5400000
Reliability Upgrade | 1a | 624 | Central Maine Power Company |  | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (New Page - Rumford Industrial Park). | Planned | Planned | 2007-11-30 | No | Portion of 5,400,000 (above) | Part of project 625
Reliability Upgrade | 1a | 1127 | Central Maine Power Company |  | 05/2009 | CMP-LSP Newcastle Substation | Add 115/34kV transformer with two 115kV breakers |  | Under Construction | 2008-08-20 | 2008-08-20 |  | 1300000
Reliability Upgrade | 1a | 1128 | Central Maine Power Company |  | 07/2010 | CMP-LSP Hotel Road Substation | Add 115/34kV transformer with 115kV breaker at Hotel Rd. |  | Planned | 2008-08-20 | No |  | 800000
Reliability Upgrade | 1a | 144 | Bangor Hydro-Electric Company |  | 12/2010 | Keene Rd Autotransformer | Installation of a 345/115 kV autotransformer at Keene Rd Substation. | Proposed | Under Construction | No | No | 20000000 | 29000000
Reliability Upgrade | 1a | 905 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Planned | Planned | 2008-07-31 | No | 1354000000 | 1510000000
Reliability Upgrade | 1a | 906 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Coopers Mills-Highland, Larrabee Road-Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 907 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 84 (Albion Road-Coopers Mills), Section 203 (Detroit-Orrington), Section 80 (Coopers Mills-Highland), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 908 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New capacitor (10.8 MVAr at Belfast) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377 & Maine Yankee 375/392, 115kV Bucksport 65/205) and Maine Yankee 345 kV re-termination | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1026 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Three Rivers) | Planned | Planned | 7/31/2008 & 2/26/09 | No | $70,000,000 (NU portion of MPRP) | Portion of CMP $1.51B and portion of NU is $35.1M
Reliability Upgrade | 1a | 1027 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV Line Construction (Elm Street-East Deering, East Deering -Cape) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1028 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Portion of CMP $1.354B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD
Reliability Upgrade | 1a | 1029 | Central Maine Power Company |  | 12/2009 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformer at South Gorham | Planned | Under Construction | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1030 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Raven Farm, Maguire Road) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 143 | Bangor Hydro-Electric Company |  | 12/2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation to Harrington Substation. | Planned | Planned | 2006-05-10 | 2008-06-13 | 66100000 | 66100000
Generator Interconnection Upgrade | 2a | 1134 | Central Maine Power Company |  | 12/2010 | Kibby Wind Farm | Separate Section 215 from Section 63 and terminate Section 215 at newly established breaker position in Wyman Hydro S/S, which includes re-rating of Section 215. Expand Bigelow S/S & add capacitor banks at Lakewood, Guilford, Wyman Hydro Station & Sturtevant S/S's. |  | Planned | 2006-06-16 | NR |  | NR
Generator Interconnection Upgrade | 2a | 770 | Central Maine Power Company |  | TBD | Queue Position 137 | Installation of New Page Substation (aka Railroad Street Substation) with (3) circuit breakers tapping Section 218 115 kV. | Proposed | Proposed | 2007-03-18 | NR | NR | NR
NEW HAMPSHIRE
Reliability Upgrade | 1a | 267 | Northeast Utilities | Central Maine Power Company | 07/2009 | Y138 Closing | White Lake - Saco Valley (Y138) Line Closing - Add PAR on Y138 at Saco Valley, retension lines, upgrade Beebe terminal, and add capacitor banks at White Lake and Beebe. | Under Construction | Under Construction | 01/01/2006 | No | 28412000 | 27775000
Reliability Upgrade | 1a | 174 | National Grid, USA |  | 07/2009 | Monadnock Area Reliability Project | Reconductor I-135 (Bellows Falls-Monadnock Tap-Flagg Pond) 115 kV line. | Planned | Under Construction | 03/24/2006 | No | 9600000 | 9600000
Reliability Upgrade | 1a | 176 | Northeast Utilities |  | 2009-08-01 | Monadnock Area Reliability Project | New Fitzwilliam 345/115kV substation along with 345 kV breakers. | Under Construction | Under Construction | 2007-09-27 | No | 76100000 | 76100000
Reliability Upgrade | 1a | 680 | National Grid, USA |  | 11/2011 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | Planned | 2008-01-28 | No | 11497000 | 11497000
Reliability Upgrade | 1a | 674 | National Grid, USA |  | 10/2012 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | Planned | 2008-04-01 | No | 12000000 | 12000000
Generator Interconnection Upgrade | 2a | 724 | National Grid, USA |  | 11/2009 | NGRID Comerford Substation | NGRID Comerford Substation. | Planned | Planned | 2007-06-12 | NR | NR | NR
VERMONT
Reliability Upgrade | 1a | 320 | Vermont Electric Power Company |  | 09/2009 | Lamoille County Project | Middlesex Substation 115 kV breaker addition. | Under Construction | Under Construction | 08/16/2007 | 02/07/2008 | 4857000 | 4857000
Reliability Upgrade | 1a | 322 | Vermont Electric Power Company |  | 09/2009 | Lamoille County Project | Installation of new Duxbury Substation that involves looping in and out of the Middlesex - Essex 115 kV (K24) line. | Under Construction | Under Construction | 08/16/2007 | 02/07/2008 | Part of Lamoille County Project | Part of Lamoille County Project
Reliability Upgrade | 1a | 139 | Vermont Electric Power Company |  | 12/2010 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Planned | Planned | 01/10/2003 | 03/31/2003 | 20000000 | 20000000
Reliability Upgrade | 1a | 182 | Vermont Electric Power Company |  | 09/2009 | Monadnock Area Reliability Project | Upgrade bus cable at N. Rutland and K35 115 kV breaker at Rutland. | Planned | Under Construction | 03/24/2006 | No | 1000000 | 1000000
Reliability Upgrade | 1a | 321 | Vermont Electric Power Company |  | 12/2009 |  | Burlington 115kV Loop - 5 mi of new line & rebuilding 5 miles of existing line between two existing substations with expansion of the East Avenue substation. | Planned | Under Construction | 10/24/2006 | 05/23/2007 | 25142000 | 25142000
Reliability Upgrade | 1a | 323 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | New VY - Newfane - Coolidge 345 kV line with requisite station upgrades. | Planned | Under Construction | 2008-10-01 | No | 135300000 | 136368000
Reliability Upgrade | 1a | 1032 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Installation of a new 345/115kV substation called Vernon including a new 345/115kV autotransformer | Planned | Under Construction | 2008-10-01 | No | 64600000 | 69815000
Reliability Upgrade | 1a | 1033 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project (VELCO LSP - Newfane Substation) | Installation of a new 345/115kV substation called Newfane | Planned | Under Construction | 2008-10-01 | No | 38500000 | 16664000
Reliability Upgrade | 1a | 1034 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Loop new 345kV Line into Newfane Substation. | Planned | Under Construction | 2008-10-01 | No | 18000000 | Part of project 323
Reliability Upgrade | 1a | 1035 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Expansion of Coolidge 345kV substation | Planned | Under Construction | 2008-10-01 | No | 18000000 | 20117000
Generator Interconnection Upgrade | 2a | 1036 | Vermont Electric Power Company |  | 12/2009 | Queue Position 172 | Installation of 3-breaker 115kV ring bus interconnection of the St. Johnsbury-Irasburg 115kV K39 line. | Planned | Planned | 08/16/2007 | NR | NR | NR
MASSACHUSETTS
Reliability Upgrade | 1a | 887 | National Grid, USA |  | 05/2012 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Planned | Planned | 2008-01-28 | No | 30000000 | 30000000
Reliability Upgrade | 1a | 921 | National Grid, USA |  | 01/2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | Planned | 2008-01-28 | No | 12100000 | 12100000
Reliability Upgrade | 1a | 919 | National Grid, USA |  | 12/2012 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | Planned | 2008-01-28 | No | 4600000 | 4600000
Reliability Upgrade | 1a | 840 | NSTAR Electric Company |  | 10/2010 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Concept | Planned | 2008-04-01 | No | 5400000 | 7300000
Reliability Upgrade | 1a | 775 | National Grid, USA |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Addition of 4 breakers and relocation of T1 and T2 into new bays at Sandy Pond. | Planned | Planned | 2008-06-27 | No | 20100000 | 20100000
Reliability Upgrade | 1a | 777 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Build Wakefield Junction station with four 345/115 kV autotransformers. | Under Construction | Under Construction | 2008-04-01 | No | 95000000 | 95000000
Reliability Upgrade | 1a | 161 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Loop 345 kV 339 line and 115 kV S-145/T-146 into new Wakefield Jct. Substation. | Under Construction | Under Construction | 2008-04-01 | No | 3200000 | 4986431
Reliability Upgrade | 1a | 779 | National Grid, USA |  | 04/2010 | Merrimack Valley/North Shore Reliability Project | Bypass and remove Golden Hills 345 kV substation. | Under Construction | Under Construction | 2008-04-01 | No | 4000000 | 5132609
Reliability Upgrade | 1a | 776 | National Grid, USA |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | Planned | 2008-06-27 | No | 2865876 | 2865876
Reliability Upgrade | 1a | 782 | National Grid, USA |  | 10/2013 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor n Railyard. | Planned | Planned | 2008-06-27 | No | 37600000 | 38100000
Reliability Upgrade | 1a | 961 | NSTAR Electric Company |  | 11/2010 | Mystic Breaker Additions Project | Install (2) new 115 kV East Bus breakers #30 and #32 at Mystic and move Transformer 110B Connection. | Planned | Planned | 2008-03-10 | No | 3800000 | 3800000
Reliability Upgrade | 1a | 302 | NSTAR Electric Company |  | 07/2009 | Boston Area 115 kV Enhancements | DCT separation of Framingham to Speen St. 433-507 circuit. | Under Construction | Under Construction | 01/18/2005 | 03/01/2005 | 3100000 | 3100000
Reliability Upgrade | 1a | 903 | NSTAR Electric Company |  | 12/2009 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #2, #4, #5, and #16 at Mystic to IPT and separate controls with Boston Gen units #5 and #6. | Planned | Planned | NR | NR | 1240000 | 1240000
Reliability Upgrade | 1a | 904 | NSTAR Electric Company |  | 12/2010 | Mystic IPT Breaker Project | Upgrade (5) 115 kV breakers #1, #7, #15 #19 and #20 at Mystic to IPT and separate controls with Boston Gen #4. | Planned | Planned | NR | NR | 990000 | 990000
Reliability Upgrade | 1a | 59 | National Grid, USA |  | 01/2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | Planned | 03/12/2002 | 2003-01-31 | 400000 | 400000
Reliability Upgrade | 1a | 695 | NSTAR Electric Company |  | 04/2009 | Short Term Lower SEMA Upgrades | Loop (355) 345 kV line in and out of Carver Substation and add (5) new 345 kV circuit breakers at Carver substation. | Planned | Under Construction | 08/17/2007 | No | 10800000 | $86.6 M (Total NSTAR Project Cost)
Reliability Upgrade | 1a | 830 | NSTAR Electric Company |  | 04/2009 | Short Term Lower SEMA Upgrades | Add a second 345/115 kV Auto transformer at Carver substation and add (1) new 345 kV circuit breaker and (3) new 115 kV circuit breakers at Carver substation. | Planned | Under Construction | 08/17/2007 | No | 8000000 | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 831 | NSTAR Electric Company |  | 06/2009 | Short Term Lower SEMA Upgrades | Add a second 115 kV line from Carver to Tremont and add (2) new 115 kV circuit breakers at Carver substation and (1) new 115 kV circuit breaker at Tremont substation. | Planned | Under Construction | 08/17/2007 | No | 2500000 | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 832 | NSTAR Electric Company |  | 09/2009 | Short Term Lower SEMA Upgrades | Add(1) 115kV SVC (0-112 MVARs lagging) at Barnstable. | Planned | Under Construction | 08/17/2007 | No | 16000000 | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 931 | National Grid, USA |  | 06/2009 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | Planned | 12/17/2007 | No | 531481 | 531481
Reliability Upgrade | 1a | 930 | National Grid, USA |  | 12/2009 | Central/Western Massachusetts Upgrades | Reconductor Nashua St - Quinsigamond Jct (O141) 115 kV line w/636 ACSS. | Planned | Planned | 12/17/2007 | No | 1765000 | 2300000
Reliability Upgrade | 1a | 934 | National Grid, USA |  | 12/2009 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Planned | Planned | 12/17/2007 | No | 818480 | 818480
Reliability Upgrade | 1a | 933 | National Grid, USA |  | 04/2010 | Central/Western Massachusetts Upgrades | Reconductor Pratts Jct - Flagg Pond I-135S & J-136S 115 kV lines w/795 ACSS. | Planned | Planned | 12/17/2007 | No | 5952582 | 6137112
Reliability Upgrade | 1a | 938 | National Grid, USA |  | 06/2010 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | Planned | 12/17/2007 | No | 3068556 | 3068556
Reliability Upgrade | 1a | 942 | National Grid, USA |  | 06/2010 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | Planned | 12/17/2007 | No | 2767180 | 2767180
Reliability Upgrade | 1a | 935 | National Grid, USA |  | 07/2010 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Planned | Planned | 12/17/2007 | No | 5208509 | 5208509
Reliability Upgrade | 1a | 927 | National Grid, USA |  | 07/2010 | Central/Western Massachusetts Upgrades | Greendale - replace 115 kV breaker and upgrade to 2000A. | Planned | Planned | 12/17/2007 | No | 584629 | 584629
Reliability Upgrade | 1a | 929 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | Planned | 12/17/2007 | No | 1381849 | 1381849
Reliability Upgrade | 1a | 936 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Reconductor (P142/P142S) Rolfe Avenue - West Bolyston 115 kV line w/1590 ACSR. | Planned | Planned | 12/17/2007 | No | 2890000 | 3000000
Reliability Upgrade | 1a | 928 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | Planned | 12/17/2007 | No | 1945218 | 1945218
Reliability Upgrade | 1a | 924 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | Planned | Planned | 12/17/2007 | No | 2147181 | 2147181
Reliability Upgrade | 1a | 943 | National Grid, USA |  | 01/2011 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | Planned | 12/17/2007 | No | 1073995 | 1073995
Reliability Upgrade | 1a | 946 | National Grid, USA |  | 03/2011 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer - E Longmeadow - Shaker Rd line to 115 kV. | Planned | Planned | 12/17/2007 | No | 14809054 | 9604032
Reliability Upgrade | 1a | 947 | National Grid, USA |  | 03/2011 | Central/Western Massachusetts Upgrades | Reconductor 115 kV line from Palmer to new Hampden Substation. | Planned | Planned | 12/17/2007 | No | 14170733 | 2632635
Reliability Upgrade | 1a | 940 | National Grid, USA |  | 04/2011 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS. | Planned | Planned | 12/17/2007 | No | 6235744 | 6235744
Reliability Upgrade | 1a | 945 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Adams - install third 115 kV breaker to complete ring bus. | Planned | Planned | 12/17/2007 | No | 1581841 | 1581841
Reliability Upgrade | 1a | 948 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | Planned | 12/17/2007 | No | 5649430 | 5649430
Reliability Upgrade | 1a | 949 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | Planned | 12/17/2007 | No | 1694829 | 1694829
Reliability Upgrade | 1a | 952 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Reconductor E Winchendon - J136 Tap within I135/J136 ROW w/795 ACSR. | Planned | Planned | 12/17/2007 | No | 932156 | 932156
Reliability Upgrade | 1a | 925 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | Planned | 12/17/2007 | No | 318888 | 318888
Reliability Upgrade | 1a | 926 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | Planned | 12/17/2007 | No | 4889621 | 6027520
Reliability Upgrade | 1a | 932 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | Planned | 12/17/2007 | No | 372036 | 372036
Reliability Upgrade | 1a | 937 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | Planned | 12/17/2007 | No | 6602875 | 6602875
Reliability Upgrade | 1a | 955 | National Grid, USA |  | 11/2011 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | Planned | 12/17/2007 | No | 10779113 | 10779113
Reliability Upgrade | 1a | 939 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Reconductor and retension (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | Planned | Planned | 12/17/2007 | No | 3287738 | 3389658
Reliability Upgrade | 1a | 941 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Install new Millbury - Tower #510 115 kV line. | Planned | Planned | 12/17/2007 | No | 5753542 | 7909203
Reliability Upgrade | 1a | 944 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Planned | Planned | 12/17/2007 | No | 9898000 | 11411849
Reliability Upgrade | 1a | 950 | National Grid, USA |  | 02/2012 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | Planned | 12/17/2007 | No | 899312 | 1016897
Reliability Upgrade | 1a | 953 | National Grid, USA |  | 02/2012 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | Planned | 12/17/2007 | No | 9444260 | 10248067
Reliability Upgrade | 1a | 954 | National Grid, USA |  | 02/2012 | Central/Western Massachusetts Upgrades | E Westminster - install new 115 kV breaker, including disconnect switches. Assumes no new control house. | Planned | Planned | 12/17/2007 | No | 799506 | 903909
Reliability Upgrade | 1a | 951 | National Grid, USA |  | 02/2013 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon 115 kV line. | Planned | Planned | 12/17/2007 | No | 6400522 | 7455440
Reliability Upgrade | 1a | 1064 | NSTAR Electric Company |  | 04/2009 |  | Install (1) 345kV 160 MVAR shunt reactor at Mystic Station | Planned | Planned | 2008-09-26 | No | 8000000 | 10400000
Reliability Upgrade | 1a | 166 | National Grid, USA |  | 06/2009 |  | Replace (16) 115 kV breakers at Tewksbury 22. | Under Construction | Under Construction | NR | NR | 3300000 | 3300000
Reliability Upgrade | 1a | 162 | National Grid, USA |  | 04/2010 |  | Q-169 Golden Hills to Lynn 115 kV line upgrade. | Under Construction | Under Construction | 2005-09-02 | 2008-04-25 | 12390000 | 12390000
Reliability Upgrade | 1a | 673 | National Grid, USA |  | 07/2010 | Worcestor Area Reinforcements | Bloomingdale Substation - #27 install 115 kV breaker. | Concept | Planned | 2009-02-27 | No | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | National Grid, USA |  | 03/2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) | Concept | Planned | 2009-02-27 | No | 30000000 | 30000000
Reliability Upgrade | 1a | 1000 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | Planned | Planned | 2008-06-27 | No | 22000000 | 22000000
Reliability Upgrade | 1a | 1076 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1077 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 902 | National Grid, USA |  | 03/2012 | Middleboro Municipal | Close the E1-M1 loop at Middleboro's Wareham St Sub. | Under Construction | Under Construction | 12/01/2006 | NR | 715000 | 715000
Reliability Upgrade | 1a | 687 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | Planned | 2008-09-24 | No | 714000000 | 714000000
Reliability Upgrade | 1a | 826 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 196 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115kV line South Agawam to Southwick (1768) | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVAR Capacitor additions | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1074 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1078 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Generator Interconnection Upgrade | 2a | 1045 | National Grid, USA |  | 06/2010 | Lowell Power | Upgrade 137T and K-137W 115 kV circuit breakers at Sandy Pond. | Planned | Planned | 2006-07-25 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 505 | National Grid, USA |  | 07/2010 | Hoosac Wind Farm | Tap Y-25S line between Harriman and Deerfield 5. Construct 69/34.5 kV substation and 34.5 kV line connecting 30 MW generating facility with the 69 kV system. | Planned | Planned | 02/01/2005 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 595 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Expansion of Barnstable 115 kV substation to include 5th bay and (2) circuit breakers, addition of a 3rd breaker in the planned 4th bay, and (2) 35MVAr shunt reactors. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 596 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Installation of (2) 115 kV circuits out of Barnstable substation to interconnect Cape Wind. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 598 | NSTAR Electric Company |  | 11/2010 | Cape Wind | At Canal 345 kV substation, install a redundant breaker in series with breaker #312. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 599 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Upgrade the Bourne 115 kV breaker #12272 with an IPT breaker. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 600 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Installation of differential insulation and additional grounding at each tower that is common for the 342 and 322 345 kV lines. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1048 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Convert Canal 345 kV SPS to include tripping of Cape Wind for the simultaneous loss of 342 and 322 345 kV lines. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1046 | National Grid, USA |  | 06/2011 | Queue Position 178 | Reconductor 115 kV F19 Line (Auburn - Brockton Tap). | Proposed | Proposed | 2008-03-10 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1047 | National Grid, USA |  | 06/2011 | Queue Position 178 | Replace Bridgewater 115 kV 1631 circuit breaker with 63 kA breaker. | Proposed | Proposed | 2008-03-10 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 622 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Interconnection to WMECO's 115-kV 1512 line through a new Substation. | Proposed | Proposed | 06/01/2007 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1043 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Upgrade the 1768 line terminal equipment at Southwick Substation. | Proposed | Proposed | 06/01/2007 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1044 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Upgrade the 1512 line terminal equipment at Southwick Substation. | Proposed | Proposed | 06/01/2007 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1058 | National Grid, USA |  | 06/2011 | Billerica Power | Interconnection to Tewksbury 115 kV Substation via O-193 Line and refurbish section of J-162 line. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1059 | National Grid, USA |  | 06/2011 | Billerica Power | Re-terminate line tap section (Perry Street) of J-162 Line to new bay position at Tewksbury. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1060 | National Grid, USA |  | 06/2011 | Billerica Power | Reconductor 2.8 mi. of the M-139 115 kV line. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1061 | National Grid, USA |  | 06/2011 | Billerica Power | Replace (16) 115 kV circuit breakers at Tewksbury 22 w/ IPT capability if all generators w/ higher Queue Position are constructed. The quantity of breaker upgrades subject to Queued generators constructed. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1062 | National Grid, USA |  | 06/2011 | Billerica Power | Upgrade #137T and #K-137W 115 kV circuit breakers at Sandy Pond (if not completed as part of Merrimack Valley/North Shore Project). | Planned | Planned | 2008-07-08 | NR | NR | NR
Elective | 4a | 1057 | Braintree Electric Light Department |  | 06/2010 |  | Upgrade 115-10-16 underground 115 kV cable. | Planned | Planned | 2008-04-17 | No | TBD | TBD
RHODE ISLAND
Reliability Upgrade | 1a | 484 | National Grid, USA |  | 01/2010 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Planned | Planned | 2008-04-25 | No | 690000 | 690000
Reliability Upgrade | 1a | 792 | National Grid, USA |  | 01/2011 | Greater Rhode Island Transmission Reinforcements 1 | Admiral St-Franklin Square (Q143 and R144) 115 kV UG recabling. | Planned | Planned | 2008-04-25 | No | 22500000 | 39200000
Reliability Upgrade | 1a | 913 | National Grid, USA |  | 02/2011 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | Planned | 2008-04-25 | No | 3250000 | 3250000
Reliability Upgrade | 1a | 793 | National Grid, USA |  | 02/2011 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | Planned | 2008-04-25 | No | 6400000 | 6400000
Reliability Upgrade | 1a | 791 | National Grid, USA |  | 06/2011 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | Planned | 2008-04-25 | No | 11560000 | 11560000
Reliability Upgrade | 1a | 914 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | Planned | 2008-04-25 | No | 28150000 | 28150000
Reliability Upgrade | 1a | 915 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | Planned | 2008-04-25 | No | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | Planned | 2008-04-25 | No | 11800000 | 11800000
Reliability Upgrade | 1a | 917 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | Planned | 2008-04-25 | No | 7000000 | 7000000
Reliability Upgrade | 1a | 918 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | Planned | 2008-04-25 | No | 3180000 | 3180000
Reliability Upgrade | 1a | 786 | National Grid, USA |  | 06/2009 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Terminal upgrades at Drumrock, Chartley Pond, and Brayton Point. | Planned | Planned | 2008-04-25 | No | 565000 | 565000
Reliability Upgrade | 1a | 789 | National Grid, USA |  | 11/2009 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Reconductoring of T7 115 kV line. | Planned | Planned | 2008-04-25 | No | 20900000 | 23304000
Reliability Upgrade | 1a | 787 | National Grid, USA |  | 12/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | West Farnum breaker replacements. | Planned | Planned | 2008-04-25 | No | 7600000 | 7631000
Reliability Upgrade | 1a | 788 | National Grid, USA |  | 12/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Kent County substation expansion. | Planned | Planned | 2008-04-25 | No | 42300000 | 42300000
Reliability Upgrade | 1a | 790 | National Grid, USA |  | 10/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Planned | Planned | 2008-04-25 | No | 50600000 | 50600000
Reliability Upgrade | 1a | 1098 | National Grid, USA |  | 10/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Planned | Planned | 2008-04-25 | No | 23000000 | 37529000
Reliability Upgrade | 1a | 1094 | National Grid, USA |  | 06/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | Planned | 2008-09-24 | No | 20800000 | 20800000
Reliability Upgrade | 1a | 1095 | National Grid, USA |  | 06/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | Planned | 2008-09-24 | No | 73800000 | 73800000
Reliability Upgrade | 1a | 795 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV line. | Planned | Planned | 2008-09-24 | No | 99900000 | 99900000
Reliability Upgrade | 1a | 1106 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | Planned | Planned | 2008-09-24 | No | Part of $99,900,000 above | Part of $99,900,000 above
Reliability Upgrade | 1a | 798 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | E-183E upgrade of 115kV terminal equipment at Franklin Square. | Planned | Planned | 2008-09-24 | No | 4900000 | 4900000
Reliability Upgrade | 1a | 799 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | Planned | Planned | 2008-09-24 | No | 4500000 | 4500000
Reliability Upgrade | 1a | 1096 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | Planned | 2008-09-24 | No | 5800000 | 5800000
Reliability Upgrade | 1a | 800 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S, T-172N and T-172S with associated terminal equipment upgrades. | Planned | Planned | 2008-09-24 | No | 7300000 | 7300000
Reliability Upgrade | 1a | 1097 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County | Planned | Planned | 2008-09-24 | No | 129800000 | 129800000
Reliability Upgrade | 1a | 1099 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | Planned | 2008-09-24 | No | 4100000 | 4100000
Reliability Upgrade | 1a | 1109 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Planned | Planned | 2008-09-24 | No | 360000 | 360000
Reliability Upgrade | 1a | 796 | National Grid, USA |  | 11/2012 | NEEWS (Interstate Reliability Project) | 347 Reconductor from Sherman Road to CT/RI Border. | Planned | Planned | 2008-09-24 | No | 16400000 | 16400000
Reliability Upgrade | 1a | 797 | National Grid, USA |  | 12/2012 | NEEWS (Interstate Reliability Project) | 3361 Upgrade 345kV terminal equipment at Sherman Road. | Planned | Planned | 2008-09-24 | No | 8300000 | 8300000
Reliability Upgrade | 1a | 190 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | Planned | 2008-09-24 | No | 69600000 | 69600000
Reliability Upgrade | 1a | 794 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | Planned | 2008-09-24 | No | 55800000 | 55800000
CONNECTICUT
Reliability Upgrade | 1a | 1009 | Northeast Utilities |  | 05/2009 |  | Install a 2% reactor on the North Bloomfield-Canton 115kV line. | Under Construction | Under Construction | 2007-10-20 | No | 2075000 | 3638000
Reliability Upgrade | 1a | 203 | Northeast Utilities |  | 05/2009 | NU LSP - Stepstone Substation | Install new Stepstone 115 kV substation in Guilford. | Under Construction | Under Construction | 2005-11-08 | 2006-04-24 | 4465000 | 6332000
Reliability Upgrade | 1a | 211 | Northeast Utilities |  | 10/2009 | NU LSP - Rood Ave Substation | New Rood Ave (formally Windsor) distribution substation with 115kV terminal modifications. | Under Construction | Under Construction | 2008-04-25 | 02/15/2008 | 9162029 | 9162029
Reliability Upgrade | 1a | 1110 | United Illuminating Company |  | 06/2010 |  | Broadway 115/13.8 kV Substation Additon | Proposed | Planned | 2008-12-08 | NR | 1000000 | 800000
Reliability Upgrade | 1a | 1111 | United Illuminating Company |  | 09/2010 |  | Metro North Union Avenue 115/26.4 kV Substation | Proposed | Planned | 2009-01-07 | No | 8700000 | 8700000
Reliability Upgrade | 1a | 1049 | United Illuminating Company |  | 12/2010 |  | East Shore 115 kV Capacitor Bank Transient Recovery | Planned | Planned | NR | NR | 3000000 | 3000000
Reliability Upgrade | 1a | 582 | Northeast Utilities |  | 12/2010 |  | Separate 310 and 368 345-KV lines and create 368/1767 DCT | Planned | Planned | 2008-07-18 | No | 16000000 | 16000000
Reliability Upgrade | 1a | 1050 | United Illuminating Company |  | 12/2010 |  | Devon Tie 115kV Switching Station BPS Compliance | Concept | Planned | NR | NR | 2620000 | 2620000
Reliability Upgrade | 1a | 1112 | United Illuminating Company |  | 12/2010 |  | Water Street 115kV circuit breaker and switch replacements. | Planned | Planned | NR | NR | 1000000 | 1000000
Reliability Upgrade | 1a | 1056 | Northeast Utilities |  | 12/2011 | CT LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Concept | Planned | 2008-12-12 | No | TBD | 9751000
Reliability Upgrade | 1a | 974 | United Illuminating Company |  | 12/2011 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Planned | Planned | NR | No | 6700000 | 6700000
Reliability Upgrade | 1a | 976 | United Illuminating Company |  | 05/2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Proposed | Planned | 2009-01-07 | No | 48000000 | 48000000
Reliability Upgrade | 1a | 816 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1054 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Manchester - Meekvile Jct. line (395/1448) separation. | Planned | Planned | 2008-09-24 | No | 14000000 | 14000000
Reliability Upgrade | 1a | 576 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | Planned | 2008-09-24 | No | 313000000 | 313000000
Reliability Upgrade | 1a | 1114 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1a | 814 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Central Connecticut Relaibility Project) | Reconductor a portion of the Manchester to Scovill Rock 353 345-kV line and terminal work. | Planned | Planned | 2008-09-24 | No | 9000000 | 9000000
Reliability Upgrade | 1a | 802 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | Planned | 2008-09-24 | No | 251000000 | 251000000
Reliability Upgrade | 1a | 1084 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Loop the Millstone - Manchester (310) 345 kV line into the Card substation. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1085 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1086 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1087 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1088 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1089 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Killingly 3G substation 345kV breaker addition | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1090 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Millstone 15G substation breaker 14T upgrade 50kA | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1091 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Southington 4C substation breaker 19T upgrade to 63kA | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | Northeast Utilities | National Grid, USA | 12/2013 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 807 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Interstate Reliability Project) | Install 480 MVAR's of capacitors at the Montville 345 kV substation | Planned | Planned | 2008-09-24 | No | 33000000 | 33000000
Reliability Upgrade | 1a | 1092 | Northeast Utilities |  | 12/2013 | NEEWS (BPS) 2 | Upgrade the Card 115 kV, East Hartford 115 kV, Agawam 115 kV, Barbour Hill 115 kV, and North Bloomfield 345 kV Substations to BPS standards. | Planned | Planned | 2008-09-24 | No | 37000000 | 37000000
Reliability Upgrade | 1a | 879 |  | Bangor Hydro-Electric Company, New England Power Company, Northeast Utilities System Com | TBD | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | Planned | 03/01/2007 | NR | 420000 | 420000
Generator Interconnection Upgrade | 2a | 983 | Northeast Utilities |  | 10/2010 | Queue Position 207 | Rebuild 115 kV 1585N Line between new substation and Bunker Hill. | Proposed | Proposed | 2008-09-26 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1107 | Northeast Utilities |  | 10/2010 | Queue Position 207 | Interconnection to new 115 kV substation consisting of (14) circuit breakers in a breaker and a half configuration that sectionalizes the existing 1575, 1585, and 1990 lines. | Proposed | Proposed | 2008-09-26 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1108 | Northeast Utilities |  | 10/2010 | Queue Position 207 | Installation of a 2.5% series reactor on the 1990S Line at the new substation. | Proposed | Proposed | 2008-09-26 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 331 | Northeast Utilities |  | 11/2010 | Kleen Energy | Install 5-breaker ring bus interconnecting between Scovill Rock and Manchester on the 345 kV 353 Line. | Planned | Planned | 10/08/2003 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1121 | Northeast Utilities |  | 06/2010 | Queue Position 161-2 | Four units connected to 384 line through a new 345kV Substation: unit #4 wll also connect to Substation |  | Proposed | 2008-12-08 | NR |  | NR
Generator Interconnection Upgrade | 2a | 1122 | Northeast Utilities |  | 11/2010 | Queue Position 191 | One turbine connected to #1238 Line (Frost Bridge to Carmel) via a new 3-breaker ring bus Substation |  | Proposed | 2009-02-24 | NR |  | NR
Generator Interconnection Upgrade | 2a | 1126 | Northeast Utilities |  | TBD | Queue Position 161-4 | Two units and repowering of #6 Montville 345kV Substation |  | Proposed | 2008-06-09 | NR |  | NR
TABLE B
MAINE
Reliability Upgrade | 1b | 1130 | Central Maine Power Company |  | 12/2009 | Sturtevant Improvements | Add 115kV circuit breakers & capacitor bank at Sturtevant Substation |  | Proposed | No | No |  | 2000000
Reliability Upgrade | 1b | 148 | Central Maine Power Company |  | 06/2010 | CMP LSP - Saco Bay Area Reinforcement Project | Establish a new Old Orchard Beach 115/34.5 kV substation and 115 kV line. | Concept | Proposed | No | No | 16900000 | 16900000
Reliability Upgrade | 1b | 1133 | Central Maine Power Company |  | 10/2010 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation & new 34kV line from Leeds to Turner |  | Proposed | No | No |  | 300000
Reliability Upgrade | 1b | 1116 | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild |  | Concept | No | No |  | TBD
Reliability Upgrade | 1b | 1031 | Bangor Hydro-Electric Company |  | 01/2012 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station, Rebuild Line 66, and Capacitior Bank Additions (10MVAr at Treneton, Downeast & Handcock County area) | Proposed | Concept | No | No | Part of Maine Power Reliability Program | TBD
Reliability Upgrade | 1b | 1131 | Central Maine Power Company |  | 12/2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer |  | Proposed | No | No |  | 600000
Reliability Upgrade | 1b | 1132 | Central Maine Power Company |  | 12/2011 | CMP-LSP Maxcy's Substation | Add 115/34kV transformer (coordinate with MPRP) |  | Proposed | No | No |  | 600000
Elective | 4b | 1018 | Bangor Hydro-Electric Company |  | TBD | Orrington-Boston HVDC | Orrington substation reconfiguration and addition of new HVDC cable system terminating in Boston area. | Concept | Concept | No | No | TBD | TBD
Elective | 4b | 984 | Central Maine Power Company | Maine Public Service | TBD | MEPCO-MPS 345 kV Interconnection | MEPCO-MPS 345 kV Interconnection. | Concept | Concept | No | No | TBD | TBD
NEW HAMPSHIRE
Reliability Upgrade | 1b | 275 | Northeast Utilities |  | TBD |  | Merrimack 115-kV substation - Protection Separation Upgrade. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 277 | Northeast Utilities |  | TBD |  | Add 2nd 345 kV autotransformer at Deerfield and associated substation work | Concept | Concept | No | No | TBD | TBD
Generator Interconnection Upgrade | 2b | 869 | Northeast Utilities |  | 06/2013 | Queue Position 165 | Rebuild 345 kV 326 Line | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1041 | Northeast Utilities |  | 06/2013 | Queue Position 165 | Rebuild 115 kV U181 Line | Concept | Concept | No | NR | NR | NR
VERMONT
Reliability Upgrade | 1b | 318 | Vermont Electric Power Company |  | 12/2011 |  | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems through the 1,250 MW Vermont state load level. | Concept | Concept | No | No | 9000000 | 9000000
Reliability Upgrade | 1b | 325 | Vermont Electric Power Company |  | 12/2011 | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | Concept | No | No | 5000000 | 5000000
Reliability Upgrade | 1b | 324 | Vermont Electric Power Company |  | 12/2012 |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | Concept | No | No | 100000000 | 100000000
MASSACHUSETTS
Reliability Upgrade | 1b | 1063 | NSTAR Electric Company |  | 12/2009 |  | Install (2) 115kV 40 MVAR shunt reactors at Edgar Station | Concept | Proposed | No | No | TBD | 5400000
Reliability Upgrade | 1b | 963 | NSTAR Electric Company |  | 12/2009 | Boston Area 115 kV Enhancements | Add a new 115kV breaker # 11 at Holbrook. | Concept | Proposed | No | No | TBD | 3400000
Reliability Upgrade | 1b | 842 | NSTAR Electric Company |  | 06/2010 | Boston Area 115 kV Enhancements | Add 115 kV 54 MVAR capacitor bank at W. Framingham. | Concept | Proposed | No | No | TBD | 3000000
Reliability Upgrade | 1b | 964 | NSTAR Electric Company |  | 12/2011 | Boston Area 115 kV Enhancements | Add a new series breaker # 8 at W. Walpole. | Concept | Proposed | No | No | TBD | 5600000
Reliability Upgrade | 1b | 965 | NSTAR Electric Company |  | 12/2012 | Boston Area 115 kV Enhancements | Add third 115kV line from Walpole to Holbrook | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 969 | NSTAR Electric Company |  | 12/2012 | Boston Area 115 kV Enhancements | Add a new 54 MVAR capacitor bank at Chelsea. | Concept | Concept | No | No | 1200000 | 1200000
Reliability Upgrade | 1b | 301 | NSTAR Electric Company |  | 12/2012 | Boston Area 115 kV Enhancements | Reconductor 115-kV circuits 320-507 and 320-508. | Concept | Concept | No | No | 4600000 | 4600000
Reliability Upgrade | 1b | 843 | NSTAR Electric Company |  | 12/2013 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1119 | NSTAR Electric Company |  | 12/2009 | Greater Boston Reliability Project | Remove limiting ground clearance conditions on West Medway-West Walpole 345kV line (#325 ) |  | Proposed | No | No |  | 1300000
Reliability Upgrade | 1b | 970 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345 kV line from Lexington to Waltham. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 971 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1113 | NSTAR Electric Company |  | 06/2010 |  | Install KSt Breaker #301 | Concept | Proposed | No | No | TBD | 2100000
Reliability Upgrade | 1b | 1120 | NSTAR Electric Company |  | 06/2010 |  | Install 345kV 160 MVAR shunt ractor at W. Walpole |  | Proposed | No | No |  | 6000000
Reliability Upgrade | 1b | 1067 | NSTAR Electric Company |  | 12/2010 | NPCC BPS Compliance | Tremont Station | Proposed | Proposed | No | No | 7100000 | 11200000
Reliability Upgrade | 1b | 1066 | NSTAR Electric Company |  | 09/2011 | NPCC BPS Compliance | Needham Station | Proposed | Proposed | No | No | 7500000 | 9300000
Reliability Upgrade | 1b | 1065 | NSTAR Electric Company |  | 07/2012 | NPCC BPS Compliance | Waltham Station | Proposed | Proposed | No | No | 22000000 | 24300000
Reliability Upgrade | 1b | 783 | National Grid, USA |  | 12/2010 | Merrimack Valley/North Shore Reliability Project | Extend the 115kV by addition of 115kV Breaker and K-153 line from King St. to W. Amesbury 115kV station. (W. Amesbury 345/115kV Station becomes PTF) | Concept | Concept | 2008-04-01 | No | 30349000 | 30349000
Reliability Upgrade | 1b | 785 | National Grid, USA |  | 07/2017 | Merrimack Valley/North Shore Reliability Project | Re-conductor F-158N (Golden Hills-Maplewood-Everett) 115 kV line. | Concept | Concept | No | No | 1330000 | 1330000
Reliability Upgrade | 1b | 1068 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to Sandwich and a a 345-115kV auto-transformer at Sandwich | Concept | Proposed | No | No | TBD | 110000000
Reliability Upgrade | 1b | 593 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Add a new 115 kV line from Canal to Barnstable. | Concept | Proposed | No | No | TBD | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 592 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing | Concept | Proposed | No | No | TBD | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1117 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install 115kV 50 MVAR capacitor bank at Falmouth | Concept | Proposed | No | No | TBD | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1118 | NSTAR Electric Company | National Grid, USA | 12/2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 and 111 | Concept | Proposed | No | No | TBD | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 956 | National Grid, USA |  | 05/2013 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Concept | Concept | No | No | 7021534 | 7021534
Reliability Upgrade | 1b | 824 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 825 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Upgrade the Pleasant to Blanford 115-kV line and the Blanford to Granville Jct. portion of the 115-kV line 1512. | Concept | Concept | No | No | TBD | TBD
Generator Interconnection Upgrade | 2b | 861 | Northeast Utilities |  | 01/2010 | Queue Position 190 | Mount Tom - W Mass. Mt. Tom 115 kV Substation. | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 863 | Northeast Utilities |  | 06/2010 | Queue Position 217 | Northfield Mountain - W. Mass Northfield 345 kV substation. | Proposed | Proposed | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1014 | Northeast Utilities |  | 06/2010 | Queue Position 196 | 345 kV Northfield Substation | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 880 | National Grid, USA | Northeast Utilities | 06/2011 | Queue Position 177 | Sutton Energy - 345 kV Carpenter Hill-Millbury Line. | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1042 | National Grid, USA |  | 06/2013 | Queue Position 165 | Replace (2) 345 kV circuit breakers at Sandy Pond | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1123 | Northeast Utilities |  | TBD | Queue Position 236 | New Substation on 1302 Line; terminal upgrades at Buck Pond and Agawam |  | Concept | No | NR |  | NR
RHODE ISLAND
Generator Interconnection Upgrade | 2b | 881 | National Grid, USA | Northeast Utilities | 06/2012 | Queue Position 201 | RISEP - 345 kV RISE Substation. | Concept | Concept | No | NR | NR | NR
CONNECTICUT
Reliability Upgrade | 1b | 809 | Northeast Utilities |  | 12/2009 |  | Upgrade terminal equipment at Bunker Hill 115 kV substation. | Proposed | Proposed | No | No | 1000000 | 1000000
Reliability Upgrade | 1b | 1055 | Northeast Utilities |  | 2010 | CT LSP - Waterside Substation | Waterside Substation - add a 115/13.2-kV transformer and a 115-kV circuit breaker. | Concept | Concept | No | No | 4107000 | 4107000
Reliability Upgrade | 1b | 721 | United Illuminating Company |  | 06/2011 |  | New Shelton 115/13.8 kV substation | Proposed | Proposed | No | No | 11300000 | 11300000
Reliability Upgrade | 1b | 316 | United Illuminating Company |  | 06/2012 |  | New Fairfield 115/13.8 kV substation | Concept | Concept | No | No | 7450000 | 7450000
Reliability Upgrade | 1b | 699 | United Illuminating Company |  | 12/2012 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | Concept | No | No | 46540000 | 10000000
Reliability Upgrade | 1b | 977 | United Illuminating Company |  | 06/2013 |  | New Orange 115/13.8 kV substation | Concept | Concept | No | No | 7550000 | 7550000
Reliability Upgrade | 1b | 975 | United Illuminating Company |  | 12/2013 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | Concept | No | No | 44300000 | 44300000
Reliability Upgrade | 1b | 980 | United Illuminating Company |  | 06/2014 |  | New Hamden 115/13.8 kV substation. | Concept | Concept | No | No | 7750000 | 7750000
Reliability Upgrade | 1b | 317 | United Illuminating Company |  | 06/2014 |  | New North Branford 115/13.8-kV substation. | Concept | Concept | No | No | 7750000 | 7750000
Reliability Upgrade | 1b | 801 | Northeast Utilities |  | TBD |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 85 | Northeast Utilities |  | TBD |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | Concept | 08/04/2004 | No | TBD | TBD
Generator Interconnection Upgrade | 2b | 1124 | Northeast Utilities |  | TBD | Queue Position 222 | New Substation on Haddam Neck-Southington 345kV line |  | Proposed | No | NR |  | NR
Generator Interconnection Upgrade | 2b | 1125 | Northeast Utilities |  | TBD | Queue Position 240 | 345kV on Montville Substation |  | Concept | No | NR |  | NR
IN-SERVICE PROJECTS
Reliability Upgrade | 1a | 579 | Central Maine Power Company |  | 06/2008 | Maguire Road Project | Addition of (4) 345 kV breakers at Buxton. | In-Service |  | 03/01/2007 | No | 11700000
Reliability Upgrade | 1a | 587 | Northeast Utilities |  | 2008-05-13 |  | Install third 345/115-kV autotransformer at Scobie Substation. | In-Service |  | 07/01/2007 | No | 12948000
Reliability Upgrade | 1a | 282 | Northeast Utilities |  | 2008-05-26 | NU LSP - Weare Substation | Install new 115 kV Weare Street Substation and Jackman capacitors. | In-Service |  | 03/01/2007 | 05/01/2007 | 11633000
Reliability Upgrade | 1a | 580 | Northeast Utilities |  | 2008-05-30 | Scobie Pond to Hudson Reinforcement Project | Install new 115-kV Scobie - Hudson line. | In-Service |  | 07/31/2006 | No | 30947000
Reliability Upgrade | 1a | 685 | National Grid, USA |  | 03/2008 |  | New 345 kV gas circuit breaker at Auburn St. Substation on the 335 Line. | In-Service |  | 10/01/2006 | 10/01/2006 | 860000
Reliability Upgrade | 1a | 293 | NSTAR Electric Company |  | 04/2008 |  | Upgrade Canal 345-kV breaker #612 to IPT. | In-Service |  | NR | NR | 450000
Reliability Upgrade | 1a | 155 | Central Maine Power Company | Northeast Utilities | 01/2009 | Maguire Road Project | Rebuild Three Rivers - Quaker Hill 115 kV Line K197. | Under Construction | In-Service | 03/01/2007 | 2009-01-09 | 5500000 | 5500000
Reliability Upgrade | 1a | 910 | Central Maine Power Company |  | 12/2008 | Rumford-Woodstock-Kimball Road Corridor Project | Rebuild Section 211 Woodstock - Rumford. | Under Construction | In-Service | 2007-11-30 | No | 6800000 | 8400000
Reliability Upgrade | 1a | 923 | National Grid, USA |  | 12/2008 | Auburn Area Transmission System Upgrades | Reconductor 115 kV A94 line and associated substation upgrades. | Planned | In-Service | 2008-01-28 | No | 3400000 | 2400000
Reliability Upgrade | 1a | 922 | National Grid, USA |  | 02/2009 | Auburn Area Transmission System Upgrades | Reconductor 115kV L1 line and associated substation upgrades. | Planned | In-Service | 2008-01-28 | No | 1050000 | 800000
Reliability Upgrade | 1a | 781 | National Grid, USA |  | 10/2008 | Merrimack Valley/North Shore Reliability Project | Install 115 kV 30 MVAr capacitor bank at Revere. | Planned | In-Service | 2008-04-01 | No | 1500000 | 1727000
Reliability Upgrade | 1a | 168 | National Grid, USA |  | 09/2008 | Southwest Rhode Island Reliability Enhancements | Reconductor Kenyon - Wood River 115 kV 1870 line. | Under Construction | In-Service | 2005-01-01 | 03/29/2005 | 2600000 | 2234232
Reliability Upgrade | 1a | 171 | National Grid, USA |  | 10/2008 | Southwest Rhode Island Reliability Enhancements | Reconductoring L-190 between Kent Co. and Davisville. | Under Construction | In-Service | 11/10/2004 | 03/29/2005 | 3000000 | 2666291
Reliability Upgrade | 1a | 900 | National Grid, USA |  | 11/2008 | Southwest Rhode Island Reliability Enhancements | Wood River substation upgrades. | Under Construction | In-Service | 04/07/2007 | 05/07/2007 | 240000 | 130000
Reliability Upgrade | 1a | 899 | National Grid, USA |  | 12/2008 | Southwest Rhode Island Reliability Enhancements | Kenyon substation upgrades. | Under Construction | In-Service | 04/07/2007 | 05/07/2007 | 278000 | 278000
Reliability Upgrade | 1a | 177 | Northeast Utilities |  | 12/2008 | Monadnock Area Reliability Project | Replace limiting terminal equipment at Webster Substation on line to North Road. | Under Construction | In-Service | 03/24/2006 | No | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 180 | Northeast Utilities |  | 12/2008 | Monadnock Area Reliability Project | Rebuild 115 kV Keene to Swanzey A-152 line. | Under Construction | In-Service | 03/24/2006 | No | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 178 | Northeast Utilities |  | 02/2009 | Monadnock Area Reliability Project | Rebuild 115 kV Garvins to Webster V-182 line. | Under Construction | In-Service | 03/24/2006 | No | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 248 | Northeast Utilities |  | 12/2008 | Norwalk-Glenbrook Cable Project | Install two new 115 kV cables from Norwalk to Glenbrook (accommodate 345 kV class cable). | Under Construction | In-Service | 08/01/2005 | No | 222850000 | $249,372,000 3
Reliability Upgrade | 1a | 569 | Northeast Utilities-CT |  | 2007 | Norwalk-Glenbrook Cable Project | Replace two 115-kV circuit breakers at Cos Cob. | In-Service | In-Service | 08/01/2005 | No | 500000 | Part of Norwalk-Glenbrook Cable Project 3
Reliability Upgrade | 1a | 243 | Northeast Utilities |  | 09/2008 | Norwalk-Glenbrook Cable Project | Expand and upgrade to BPS and remove SPS at Glenbrook 115 kV substation. | In-Service | In-Service | 08/01/2005 | No | 8390000 | Part of Norwalk-Glenbrook Cable Project 3
Reliability Upgrade | 1a | 570 | Northeast Utilities |  | 10/2008 | Norwalk-Glenbrook Cable Project | Add second high speed relay system on the 1450 line. | In-Service | In-Service | 08/01/2005 | No | 788000 | Part of Norwalk-Glenbrook Cable Project 3
Reliability Upgrade | 1a | 571 | Northeast Utilities |  | 12/2008 | Norwalk-Glenbrook Cable Project | Upgrade Flax Hill Substation to BPS. | Under Construction | In-Service | 08/01/2005 | No | 2175000 | Part of Norwalk-Glenbrook Cable Project 3
Reliability Upgrade | 1a | 208 | Northeast Utilities |  | 12/2008 | NU LSP - Oxford Substation | Install new Oxford (previously Jack's Hill) 115 kV substation. | Under Construction | In-Service | 01/14/2006 | 06/01/2007 | 5710287 | 4459000
Reliability Upgrade | 1a | 246 | Northeast Utilities |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Add second 345/115 kV autotransformer at Norwalk Substation along with shunt reactors and 345 kV circuit breakers. | Under Construction | In-Service | 01/14/2006 | No | 1047000000 | $978,182,000 4
Reliability Upgrade | 1a | 226 | Northeast Utilities | United Illuminating Company | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install two 345 kV underground cables from Singer(UI) to Norwalk. | Under Construction | In-Service | 01/14/2006 | No | Part of SWCT (M-N) Reliability Project | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 235 | Northeast Utilities |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Expand Norwalk 345-kV substation and install transfer trip relaying scheme on the 1389 115 kV line between Norwalk and Flax Hill. | Under Construction | In-Service | 01/14/2006 | No | Part of SWCT (M-N) Reliability Project | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 247 | Northeast Utilities |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Replace Norwalk Harbor 138/115 kV autotransformer. | Under Construction | In-Service | 01/14/2006 | No | 8351000 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 684 | Northeast Utilities |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Replace (6) 115 kV breakers (4-Glenbrook, 1-Glenbrook Statcom, 1-Southington #1) and (3) 345-kV circuit breakers at Millstone and replace (4) 345- kV breakers with 500-kV breakers at Long Mountain substation. | Under Construction | In-Service | 01/14/2006 | No | 11321000 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 551 | Northeast Utilities |  | 10/2007 | Southwest Connecticut Reliability Project PH II (M-N) | Rebuild the 1466 115-kV line from East Meriden to North Wallingford and the 1588 115-kV rebuild from North Wallingford to Colony. | In-Service | In-Service | 04/01/2007 | No | 805000 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 244 | Northeast Utilities |  | 2008-06-20 | Southwest Connecticut Reliability Project PH II (M-N) | Reconductor 115 kV 1570 and 1575 line taps into Beacon Falls Substation. | In-Service | In-Service | 04/01/2007 | No | 5692000 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 239 | Northeast Utilities |  | 07/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install (1) new 115 kV circuit breaker at Devon Substation in series with 7R-2T. | In-Service | In-Service | 04/01/2007 | No | 5009000 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 250 | Northeast Utilities |  | 12/2008 |  | Add a 345 kV breaker at Ludlow Substation. | Planned | In-service | 06/01/2007 | 2007-08-01 | 1644885 | 1644885
Reliability Upgrade | 1a | 841 | NSTAR Electric Company |  | 11/2008 | Mystic Breaker Additions Project | Install (2) new 115 kV West Bus breakers #29 and #31 at Mystic. | Planned | In-Service | 2008-03-10 | No | 2300000 | 2300000
Reliability Upgrade | 1a | 1040 | NSTAR Electric Company |  | 12/2008 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #11, #8, #17 and #3 at Mystic to IPT | Planned | In-Service | NR | NR | 990000 | 990000
Reliability Upgrade | 1a | 116 | NSTAR Electric Company |  | 04/2009 | NSTAR 345 kV Transmission Reliability Project | Add 2nd 345 kV UG Cables from Stoughton to Mattapan Sq.to K Street and install another new autotransformer at K. St. | Under Construction | In-Service | 02/10/2005 | 09/15/2005 | 307900000 | 307900000
Reliability Upgrade | 1a | 572 | NSTAR Electric Company |  | 04/2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 345 kV 160 MVAR shunt reactors at Stoughton. | Under Construction | In-Service | 02/10/2005 | 09/15/2005 | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 573 | NSTAR Electric Company |  | 04/2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 345 kV 160 MVAR shunt reactors at K St. | Under Construction | In-Service | 02/10/2005 | 09/15/2005 | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 772 | NSTAR Electric Company |  | 04/2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 115 kV breaker at K St. | Under Construction | In-Service | 02/01/2005 | 09/01/2005 | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 238 | United Illuminating Company |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Build new Singer 345 kV substation with (12) circuit breakers, (2) autos, (4) shunt reactors along with reconnecting Bridgeport Energy thru one of the new autos. Includes 115 kV connection from Singer to Pequonnock substation. | Under Construction | In-Service | 01/14/2006 | No | 162264000 | 162264000
Reliability Upgrade | 1a | 224 | United Illuminating Company | Northeast Utilities | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) 4 | Install new 345 kV line from East Devon to Singer(UI). | Under Construction | In-Service | 01/14/2006 | No | 157476000 | 157476000
Reliability Upgrade | 1a | 846 | United Illuminating Company |  | 11/2008 |  | Replace Mix Avenue 115 kV Oil Circuit Breaker & foundation. | Under Construction | In-Service | NR | NR | 450000 | 450000
Reliability Upgrade | 1a | 138 | Vermont Electric Power Company |  | 12/2008 | Northwest Vermont Reliability Project | N. Haven - Vergennes - Q. City 115 kV line. | Under Construction | In-Service | 01/10/2003 | 2006-12-18 | 70200000 | 70200000
Reliability Upgrade | 1a | 136 | Vermont Electric Power Company |  | 04/2009 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 1: two 115 kV PARs, four 25 MVAR Cap. banks, four +25/-12.5 MVAR synchronous condenders, and two 230/115 transformers. | Under Construction | In-Service | 01/10/2003 | 03/31/2003 | 62400000 | 62400000
Generator Interconnection Upgrade | 2a | 847 | Bangor Hydro-Electric Company |  | 12/2008 | Stetson Wind | Interconnect 60 MW of wind via 115 kV generator lead into Keene Road Substation. | Planned | In-Service | 07/01/2007 | NR | NR | NR
CANCELLED PROJECTS
Reliability Upgrade | 1b | 912 | Central Maine Power Company |  | 12/2009 | CMP LSP - Anson Substation | Add 115 kV circuit breakers and transformer at Anson Section 63. | Concept | Cancelled | No | No | TBD | NR
Reliability Upgrade | 1b | 106 | Northeast Utilities |  | TBD |  | Upgrade the Southwest Hartford Substation to Bulk Power System standards (BPS). | Concept | Cancelled | 08/04/2004 | No | TBD | NR
Reliability Upgrade | 1b | 1069 | NSTAR Electric Company |  | 07/2011 | NPCC BPS Compliance | Bourne Station | Proposed | Cancelled | No | No | 8800000 | NR
Notes
1 Project pending solution documentation for the Greater Rhode Island Transmission Reinforcements.
2 The Northeast Utilities' estimated costs for the NEEWS BPS upgrades are shared among the Greater Springfield, Central Connecticut, and Interstate portions of the NEEWS Project.
3 The total TCA (NU-07-TCA-24) PTF cost is $234.2 million for the Norwalk - Glenbrook Project. The forecasted PTF cost is $249.4 million.
4 The total TCA (NU-08-TCA-01) PTF cost is $1.05 billion for Northeast Utilities portion of the Middletown-Norwalk Project. The forecasted PTF cost is $978.2 million.
Local Project Listing Links
| NSTAR: |  | http://www.nstar.com/business/rates_tariffs/open_access/
| CMP: |  | http://www.cmpco.com/SuppliersAndPartners/TransmissionServices/CMPTransmissionSvc/lsp.html
| BHE: |  | http://www.bhe.com/data/OASIS/LSP.html
| VELCO: |  | http://www.vermontspc.com/About%20the%20VSPC/Home.aspx
| NU: |  | http://www.transmission-nu.com/business/pdfs/NU_Local_Transmission_Studies_List.pdf
| NGRID: |  | http://www.nationalgridus.com/oasis/
| UI: |  | http://www.uinet.com/uinet/resources/file/ebcfda4ccb73dd/UI%20Local%20System%20Plan.pdf

## CostSumW-TBD-Mar 12 (hidden)
COST COMPARISON OF RELIABILITY PROJECTS November 2011 vs March 2012
| RTEP02 (in millions $) | RTEP03 (in millions $) | As of April '04 Plan Update (in millions $) | As of July '04 Plan Update (in millions $) | As of October '04 Plan Update (in millions $) | As of April '05 Plan Update (in millions $) | As of July '05 Plan Update (in millions $) | As of Oct '05 Plan Update (in millions $) | As of April '06 Plan Update (in millions $) | As of July 2006 Plan Update (in millions $) | As of October 2006 Plan Update (in millions $) | As of April 2007 Plan Update (in millions $) | As of July 2007 Plan Update (in millions $) | As of October 2007 Plan Update (in millions $) | As of April 2008 Plan Update (in millions $) | As of July 2008 Plan Update (in millions $) | As of October 2008 Plan Update (in millions $) | As of April 2009 Plan Update (in millions $) | As of June 2011 Plan Update (in millions $) | As of November 2011 Plan Update (in millions $) | As of March 2012 Plan Update (in millions $) | Change in Plan Estimate (in millions $) | Reasons for Change
MAJOR PROJECTS
Maine Power Reliability Program | [14 empty] | TBD | 1424 | 1424 | 1545.1 | 1546 | 1440 | 1440 | 0
Merrimack Valley / North Shore Reliability Project | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | 14 | 133.82 | 151.56 | 151.56 | 151.56 | 151.56 | 207.1649 | 212.7109 | 216.8471 | 197 | 198 | 1
Long Term Lower SEMA Upgrades | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | 14 | 133.82 | 151.56 | 151.56 | 151.56 | 151.56 | TBD | 110 | 113 | 112.5 | 112.5 | 0
New England East - West Solution (NEEWS) | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | TBD | TBD | 272.7 (3) | 272.7 (2) | 272.7 (2) | 1600.7 | 1872.36 | 1872.36 | 1928 | 1845 | 1878.14 | 33.14
NEEWS (Greater Springfield Reliability Project) $746.80
NEEWS (Rhode Island Reliability Project) $225.8
NEEWS (Central Connecticut Reliability Project) $301.00
NEEWS (Interstate Reliability Project) $604.66
Greater Rhode Island Transmission Reinforcements (including Advanced NEEWS) | [18 empty] | 279 | 242 | 242 | 0
Pittsfield/Greenfield Project | [18 empty] | 129 | 129 | 133 | 4
Greater Boston - North, South, Central, Western Suburbs | [18 empty] | 292 | 265 | 417 | 152
New Hampshire Solution - Southern, Central, Seacoast, Northern | [18 empty] | 278.805 |  | 453 | 453
Vermont Solution - Northwestern, Central, Southwestern | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | TBD | 194.8 | 181.99 | 181.99 | 181.99 | 181.99 | 258.945 | 292.609 | 278.805 |  | 485 | 485
SUBTOTAL (2) | 0 | 125 | 202 | 125 | 125 | 125 | 125 | 125 | 125 | 357 | 385 | 805.64 | 1101.01 | 758.11 | 757.81 | 2085.81 | 3762.4699 | 4032.7799 | 5061.4571 | 4230.5 | 5358.64 | 1128.14
OTHER PROJECTS | 149.9 | 181.3 | 187.6 | 792.2 | 828.9 | 1025.5 | 1287 | 1369.896 | 1430.112 | 1472.4118 | 1589.3948 | 1666.3467 | 2180.5252 | 2678.5122 | 2576.6241 | 2594.6841 | 2594.934 | 2690.4727 | 5282 | 5351.55 | 5482.0719 | 130.5219 | Various | MAJOR PROJECTS | 5358.64
[24 empty] | NEW PROJECTS | 3.9
NEW PROJECTS | 0 | 521.7 | 567.1 | 0 | 0 | 14.4 | [14 empty] | 3.9 | 3.9 | Preliminary estimates reported for 8 of 17 new projects | TBD NOW W/ COSTS | 132.3
[24 empty] | OTHER PROJECTS | 5482.0719 | 5482.0719 | VERIFICATION of RED CELL
PROJECTS WHOSE COST ESTIMATES WERE PREVIOUSLY REPORTED AS TO BE DETERMINED (TBD) | [5 empty] | 0 | [14 empty] | 132.3 | 132.3 | First estimates reported for projects. | GRAND TOTAL | 10976.9119
TOTAL (2) | 149.9 | 828 | 2201.1 1 | 2270.4 1 | 953.9 | 1164.9 | 1412 | 1495 | 1555.112 | 1829.412 | 1974.395 | 2471.987 | 3281.836 | 3436.623 | 3334.4341 | 4680.4941 | 6357.4039 | 6723.2526 | 10343.4571 | 9582.05 | 10976.9119 | 633.4548
Minus 'concept' | [18 empty] | -142 | -128.3 | -132
Minus 'in-service' |  | In-Service Projects | 76.2 | -130.8 | -143.4 | -172.2 | -216.8 | -265.726 | -410.4503 | -429 | -503.791 | -899.8087 | -973.8387 | -977.7067 | -1165.1757 | -1328.4137 | -1452.0644 | -3452.6538 | -4386.6457 | -4421.2027 | -4661.3677
Aggregate estimate of active projects in the Plan (2) |  |  | 2124.9 | 2139.6 | 2159.5 | 992.7 | 1195.2 | 1229.274 | 1144.6617 | 1400.412 | 1470.504 | 1572.1783 | 2307.9973 | 2458.9163 | 2169.2584 | 3352.0804 | 4905.3395 | 3270.5988 | 5814.8114 | 5032.5473 | 6183.5442 |  |  | ACTIVE COSTS | 6315.5442 | (typed in Project Total from Master File)
[24 empty] | IN SERVICE | 240.165 | (typed in from In-service tab)
[20 empty] | 5160.8473 | 6315.5442

## CostSumW-TBD-Jun11-final (hidden)
COST COMPARISON OF RELIABILITY PROJECTS April 2011 vs June 2011
| RTEP02 (in millions $) | RTEP03 (in millions $) | As of April '04 Plan Update (in millions $) | As of July '04 Plan Update (in millions $) | As of October '04 Plan Update (in millions $) | As of April '05 Plan Update (in millions $) | As of July '05 Plan Update (in millions $) | As of Oct '05 Plan Update (in millions $) | As of April '06 Plan Update (in millions $) | As of July 2006 Plan Update (in millions $) | As of October 2006 Plan Update (in millions $) | As of April 2007 Plan Update (in millions $) | As of July 2007 Plan Update (in millions $) | As of October 2007 Plan Update (in millions $) | As of April 2008 Plan Update (in millions $) | As of July 2008 Plan Update (in millions $) | As of October 2008 Plan Update (in millions $) | As of April 2009 Plan Update (in millions $) | As of April 2011 Plan Update (in millions $) | As of June 2011 Plan Update (in millions $) | Change in Plan Estimate (in millions $) | Reasons for Change
MAJOR 345 kV PROJECTS
Maine Power Reliability Program | [14 empty] | TBD | 1424 | 1424 | 1545.1 | 1546 | 1546 | 0
Merrimack Valley / North Shore Reliability Project | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | 14 | 133.82 | 151.56 | 151.56 | 151.56 | 151.56 | 207.1649 | 212.7109 | 216.8471 | 216.8471 | 0
Long Term Lower SEMA Upgrades | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | 14 | 133.82 | 151.56 | 151.56 | 151.56 | 151.56 | TBD | 110 | 106.5 | 112.5 | 6
New England East - West Solution (NEEWS) (including Ancillary components) | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | TBD | TBD | 272.7 (3) | 272.7 (2) | 272.7 (2) | 1600.7 | 1872.36 | 1872.36 | 1991.8 | 1928 | -63.8
Pittsfield/Greenfield Project | [18 empty] | 129 | 129 | 0
Greater Boston - North, South, Central | [18 empty] | 292 | 292 | 0
Greater Rhode Island Transmission Reinforcements (including Advanced NEEWS) | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | TBD | 194.8 | 181.99 | 181.99 | 181.99 | 181.99 | 258.945 | 292.609 | 278.805 | 278.805 | 0
SUBTOTAL (2) | 0 | 125 | 202 | 125 | 125 | 125 | 125 | 125 | 125 | 357 | 385 | 805.64 | 1101.01 | 758.11 | 757.81 | 2085.81 | 3762.4699 | 4032.7799 | 4560.9521 | 4503.1521 | -57.8
OTHER PROJECTS | 149.9 | 181.3 | 187.6 | 792.2 | 828.9 | 1025.5 | 1287 | 1369.896 | 1430.112 | 1472.4118 | 1589.3948 | 1666.3467 | 2180.5252 | 2678.5122 | 2576.6241 | 2594.6841 | 2594.934 | 2690.4727 | 5061.3612 | 5282 | 220.6388 | Various | MAJOR PROJECTS | 4503.1521
[23 empty] | NEW PROJECTS | 39
NEW PROJECTS | 0 | 521.7 | 567.1 | 0 | 0 | 14.4 | [13 empty] | 39 | 39 | Preliminary estimates reported for 8 of 17 new projects | TBD NOW W/ COSTS | 7.3
[23 empty] | OTHER PROJECTS | 5475.0793 | 5282 | VERIFICATION of RED CELL
PROJECTS WHOSE COST ESTIMATES WERE PREVIOUSLY REPORTED AS TO BE DETERMINED (TBD) | [5 empty] | 0 | [13 empty] | 7.3 | 7.3 | First estimates reported for projects. | GRAND TOTAL | 9830.5314
TOTAL (2) | 149.9 | 828 | 2201.1 1 | 2270.4 1 | 953.9 | 1164.9 | 1412 | 1495 | 1555.112 | 1829.412 | 1974.395 | 2471.987 | 3281.836 | 3436.623 | 3334.4341 | 4680.4941 | 6357.4039 | 6723.2526 | 9622.3133 | 9831.4521 | 209.1388
Minus 'concept' | [18 empty] | -139.1 | -142.2
Minus 'in-service' |  | In-Service Projects | 76.2 | -130.8 | -143.4 | -172.2 | -216.8 | -265.726 | -410.4503 | -429 | -503.791 | -899.8087 | -973.8387 | -977.7067 | -1165.1757 | -1328.4137 | -1452.0644 | -3452.6538 | -4328.1457 | -4386.6457
Aggregate estimate of active projects in the Plan (2) |  |  | 2124.9 | 2139.6 | 2159.5 | 992.7 | 1195.2 | 1229.274 | 1144.6617 | 1400.412 | 1470.504 | 1572.1783 | 2307.9973 | 2458.9163 | 2169.2584 | 3352.0804 | 4905.3395 | 3270.5988 | 5155.0676 | 5302.6064 |  |  | ACTIVE COSTS | 5443.8857 | (typed in from Master File)
[23 empty] | IN SERVICE | 58.5 | (typed in from In-service tab)

## CostSumW-TBD-Apr11-RV-Input (hidden)
COST COMPARISON OF RELIABILITY PROJECTS October 2010 vs April 2011
| RTEP02 (in millions $) | RTEP03 (in millions $) | As of April '04 Plan Update (in millions $) | As of July '04 Plan Update (in millions $) | As of October '04 Plan Update (in millions $) | As of April '05 Plan Update (in millions $) | As of July '05 Plan Update (in millions $) | As of Oct '05 Plan Update (in millions $) | As of April '06 Plan Update (in millions $) | As of July 2006 Plan Update (in millions $) | As of October 2006 Plan Update (in millions $) | As of April 2007 Plan Update (in millions $) | As of July 2007 Plan Update (in millions $) | As of October 2007 Plan Update (in millions $) | As of April 2008 Plan Update (in millions $) | As of July 2008 Plan Update (in millions $) | As of October 2008 Plan Update (in millions $) | As of April 2009 Plan Update (in millions $) | As of October 2010 Plan Update (in millions $) | As of April 2011 Plan Update (in millions $) | Change in Plan Estimate (in millions $) | Reasons for Change
MAJOR 345 kV PROJECTS
Maine Power Reliability Program | [14 empty] | TBD | 1424 | 1424 | 1545.1 | 1356 | 1547 | 191
Vermont Southern Loop Project | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | 14 | 72 | 200 | 200 | 274.4 | 274.4 | 274.4 | 242.964 | 207.781 | 193.5 | -14.281
Merrimack Valley / North Shore Reliability Project | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | 14 | 133.82 | 151.56 | 151.56 | 151.56 | 151.56 | 207.1649 | 212.7109 | 218 | 216.8471 | -1.1529
Long Term Lower SEMA Upgrades | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | 14 | 133.82 | 151.56 | 151.56 | 151.56 | 151.56 | TBD | 110 | 106.5 | 106.5 | 0
New England East - West Solution (NEEWS) (including Ancillary components) | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | TBD | TBD | 272.7 (3) | 272.7 (2) | 272.7 (2) | 1600.7 | 1872.36 | 1872.36 | 1881 | 1991.8 | 110.8
Pittsfield/Greenfield Project | [19 empty] | 129 | 129
Greater Boston - North, South, Central | [19 empty] | 292 | 292
Greater Rhode Island Transmission Reinforcements (including Advanced NEEWS) | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | TBD | 194.8 | 181.99 | 181.99 | 181.99 | 181.99 | 258.945 | 292.609 | 292.609 | 278.805 | -13.804
SUBTOTAL (2) | 0 | 250 | 327 | 250 | 250 | 250 | 125 | 125 | 125 | 357 | 399 | 877.64 | 1301.01 | 958.11 | 1032.21 | 2360.21 | 4036.8699 | 4275.7439 | 4062.59 | 4755.4521 | 692.8621
OTHER PROJECTS | 149.9 | 181.3 | 187.6 | 792.2 | 828.9 | 1025.5 | 1287 | 1369.896 | 1430.112 | 1472.4118 | 1589.3948 | 1666.3467 | 2180.5252 | 2678.5122 | 2576.6241 | 2594.6841 | 2594.934 | 2690.4727 | 4966 | 4952 | -14 | Various | MAJOR PROJECTS | 4755.4521
[23 empty] | NEW PROJECTS | 110.3612
NEW PROJECTS | 0 | 521.7 | 567.1 | 0 | 0 | 14.4 | [13 empty] | 110.3612 | 110.3612 | Preliminary estimates reported for 8 of 17 new projects | TBD NOW W/ COSTS | 0
[23 empty] | OTHER PROJECTS | 4950.1226 | 4952 | VERIFICATION of RED CELL
PROJECTS WHOSE COST ESTIMATES WERE PREVIOUSLY REPORTED AS TO BE DETERMINED (TBD) | [5 empty] | 0 | [13 empty] | 0 | 0 | First estimates reported for projects. | GRAND TOTAL | 9815.9359
TOTAL (2) | 149.9 | 953 | 2201.1 1 | 2270.4 1 | 1078.9 | 1289.9 | 1412 | 1495 | 1555.112 | 1829.412 | 1988.395 | 2543.987 | 3481.836 | 3636.623 | 3608.8341 | 4954.8941 | 6631.8039 | 6966.2166 | 9028.59 | 9817.8133 | 789.2233
Minus 'concept' | [18 empty] | -141 | -139.1
Minus 'in-service' |  | In-Service Projects | 76.2 | -130.8 | -143.4 | -172.2 | -216.8 | -265.726 | -410.4503 | -429 | -503.791 | -899.8087 | -973.8387 | -977.7067 | -1165.1757 | -1328.4137 | -1452.0644 | -3452.6538 | -3960.0717 | -4328.1457
Aggregate estimate of active projects in the Plan (2) |  |  | 2124.9 | 2139.6 | 2159.5 | 1117.7 | 1195.2 | 1229.274 | 1144.6617 | 1400.412 | 1484.504 | 1644.1783 | 2507.9973 | 2658.9163 | 2443.6584 | 3626.4804 | 5179.7395 | 3513.5628 | 4927.5183 | 5350.5676 |  |  | ACTIVE COSTS | 5487.7902 | (typed in from Master File)
[23 empty] | IN SERVICE | 368.074 | (typed in from In-service tab)

## Projects I-S for October09 (hidden)
April 10 -NEW ENGLAND Project Listing Update (DRAFT)
Primary Driver | Part# | Project ID | Primary Equipment Owner | Other Equipment Owner(s) | Projected In-Service Month/Year | Major Project | Project | Oct-07 Status | Apr-08 Status | Jul-08 Status | Jul-09 Status | Oct-09 Status | I.3.9 Approval | TCA Approval | Oct-07 Estimated Costs | Apr-08 Estimated Costs | Jul-08 Estimated Costs | Jul-09 Estimated Costs | Oct 09 Estimated Costs | Why Needed
IN-SERVICE PROJECTS
Reliability Upgrade | 1a | 1051 | Central Maine Power Company |  | 09/2009 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Riley 115 kV capacitor bank. |  | Concept | Planned | Under Construction | In-service | 2007-11-30 | No | TBD | TBD |  | Part of Project 625 | Part of Project 625 |  | 8000000
Reliability Upgrade | 1a | 267 | Northeast Utilities | Central Maine Power Company | 2009-08-01 | Y138 Closing | White Lake - Saco Valley (Y138) Line Closing - Add PAR on Y138 at Saco Valley, retension lines, upgrade Beebe terminal, and add capacitor banks at White Lake and Beebe. | Planned | Under Construction | Under Construction | Under Construction | In-service | 01/01/2006 | No | 28565000 | 28412000 |  | 27775000 | 27775000 |  | 1300000
Reliability Upgrade | 1a | 936 | National Grid, USA |  | 07/2009 | Central/Western Massachusetts Upgrades | Reconductor (P142/P142S) Rolfe Avenue - West Bolyston 115 kV line w/1590 ACSR. | Proposed | Planned | Planned | Under Construction | In-service | 12/17/2007 | No | 2107320 | 2107320 |  | 3000000 | 3000000 |  | 3300000
Reliability Upgrade | 1a | 176 | Northeast Utilities |  | 07/2009 | Monadnock Area Reliability Project | New Fitzwilliam 345/115kV substation along with 345 kV breakers. | Planned | Under Construction | Under Construction | Under Construction | In-service | 2007-09-27 | No | 54358000 | 54358000 |  | 76100000 | 76100000 |  | 3089000
Reliability Upgrade | 1a | 174 | National Grid, USA |  | 06/2009 | Monadnock Area Reliability Project | Reconductor I-135 (Bellows Falls-Monadnock Tap-Flagg Pond) 115 kV line. | Planned | Planned | Planned | Under Construction | In-service | 03/24/2006 | No | 9600000 | 9600000 |  | 15778000 | 15778000 |  | 6332000
Reliability Upgrade | 1a | 832 | NSTAR Electric Company |  | 07/2009 | Short Term Lower SEMA Upgrades | Add(1) 115kV SVC (0-112 MVARs lagging) at Barnstable. | Planned | Planned | Planned | Under Construction | In-service | 08/17/2007 | No | 16000000 | 16000000 |  | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade |  | 10400000
Reliability Upgrade | 1a | 182 | Vermont Electric Power Company |  | 09/2009 | Monadnock Area Reliability Project | Upgrade bus cable at N. Rutland and K35 115 kV breaker at Rutland. | Planned | Planned | Planned | Under Construction | In-service | 03/24/2006 | NR | 03/24/2006 | No | 1000000 | 1000000 | 1000000 |  | 3100000
[18 empty] | Total | 205653000
1000000

## Sorted by Status Nov 11 (hidden)
November 2011 ISO-NEW ENGLAND Project Listing Update (DRAFT)(7)
Primary Driver | Part# | Project ID | State | Primary Equipment Owner | Other Equipment Owner(s) | Projected In-Service Month/Year | Major Project | Project | Jun-11 Status | Oct-11 Status | PPA (I.3.9) Approval | TCA Approval | Jun-11 Estimated PTF Costs | Oct-11 Estimated PTF Costs
Reliability Upgrade | 1b | 1031 | ME | Bangor Hydro-Electric Company |  | 12/2013 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station | Concept | Concept | 2010-10-22 | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1154 | ME | Bangor Hydro-Electric Company |  | 12/2013 | Maine Power Reliability Program (MPRP) | Rerate Line 66 | Concept | Concept | 2010-10-22 | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1155 | ME | Bangor Hydro-Electric Company |  | 12/2014 | Maine Power Reliability Program (MPRP) | Capacitor Bank Addition (10 MVAr at Trenton 34.5kV and Epping) | Concept | Concept | 2010-10-22 | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 325 | VT | Vermont Electric Power Company |  | TBD | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 324 | VT | Vermont Electric Power Company |  | TBD |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 139 | VT | Vermont Electric Power Company |  | TBD | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Concept | Concept | 01/10/2003 | 03/31/2003 | TBD | TBD | TBD
Reliability Upgrade | 1b | 1250 | VT | Vermont Electric Power Company |  | 2016 | VELCO LSP - West Rutland Substation | Installation of a 115/46kV transformer at West Rutland between breakers K30 and K34 | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 593 | MA | NSTAR Electric Company |  | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Bourne and Barnstable/Falmouth/equivalent | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1177 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - North | Reconductor 211-503/504 from North Woburn Tap to Reading | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1178 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - North | Install 115kV Capacitor Bank at North Woburn | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1190 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - North | Install a second 345/115kV Auto Transformer at Woburn | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 970 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Add a new 345 kV line from Lexington to Waltham. | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 971 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1176 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Install an oil circulation pipe and heat exchangers at K Street and Chatham Street sections of 250-516/517 circuits | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1189 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - Central | Install 3rd 115kV Circuit between Waltham and Brighton | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1198 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Add a second 115kV line from Woburn to Burlington | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1199 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Install a new 230/115kV auto transformer at Sudbury or equivalent | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1191 | MA | NSTAR Electric Company |  | 12/2012 |  | Rebuild Section of Line 322 (Canal-Carver) | Concept | Concept | No | No | 12200000 | 12200000 | 12200000
Reliability Upgrade | 1b | 1181 | MA | NSTAR Electric Company |  | 12/2013 |  | Rebuild the High Hill 115kV Substation to a Breaker and a half desgin | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1204 | MA | NSTAR Electric Company |  | 06/2012 |  | Rebuild the Mashpee Substation to a Ring Bus and install an overvoltage trip relay on the Mashpee 115kV Capacitor Bank | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1205 | MA | NSTAR Electric Company |  | 12/2013 | Mid-Cape Reliability Project | Separate 120 (Canal-Barnstable) /122 (Oak St-Barnstable) DCT | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1206 | MA | NSTAR Electric Company |  | 12/2011 |  | Install a new 230kV breaker for line 282-602 (West Medway-Waltham) at W. Medway for system resoration | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1247 | MA | NSTAR Electric Company |  | TBD |  | Rebuild the Acushnet 115kV Substation | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1248 | MA | NSTAR Electric Company |  | 12/2014 |  | Rebuild the Kingston Substation to a breaker and a half scheme | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1249 | MA | NSTAR Electric Company |  | 12/2013 |  | Rebuild the Wareham Substation to a breaker and a half scheme | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1207 | MA | NSTAR Electric Company |  | 2012 | Belmont Transmission Interconnection | Build a new 115kV Substation for the Belmont Transmission Interconnection | Concept | Concept | 2010-02-26 | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1255 | MA | CELD (Chicopee Electric Light Department) |  | 12/2013 | CELD 115/13.8kV Substation | 115/13.8kV substation on Memorial Dr. with two transformers and twelve feeders looped into 1904 (1723) line between Piper and Fairmont substations |  | Concept | No | No |  | TBD | TBD
Reliability Upgrade | 1b | 1234 | RI | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | Install a 115kV redundant breaker in series with breaker #1713 at West Farmum Substation and upgrade to current BPS standards | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1084 | CT | Northeast Utilities |  | TBD | Greater Hartford Central Connecticut Project | Loop the Millstone - Manchester (310) 345 kV line into the Card substation (2) | Concept | Concept | 2008-09-24 | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1086 | CT | Northeast Utilities |  | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow (2) | Concept | Concept | 2008-09-24 | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1087 | CT | Northeast Utilities |  | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford (2) | Concept | Concept | 2008-09-24 | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1088 | CT | Northeast Utilities |  | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow (2) | Concept | Concept | 2008-09-24 | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 975 | CT | United Illuminating Company |  | 06/2015 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | Concept | No | No | 105000000 | 105000000 | 105000000
Reliability Upgrade | 1b | 699 | CT | United Illuminating Company |  | 12/2014 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | Concept | No | No | 11100000 | 11100000 | 11100000
Reliability Upgrade | 1b | 801 | CT | Northeast Utilities |  | TBD |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 85 | CT | Northeast Utilities |  | TBD |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | Concept | 08/04/2004 | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1228 | CT | Northeast Utilities |  | TBD | Stamford Area | Additional circuit into the Stamford Area (Glenbrook-South End) | Concept | Concept | No | No | TBD | TBD | TBD |  | Concept
Reliability Upgrade | 1b | 1229 | CT | Northeast Utilities |  | TBD |  | Replace 115kV 1990 (Frost Bridge-Stevenson) lattice structure | Concept | Concept | No | No | TBD | TBD | TBD | 40 | 128300000 |  | 128300000
Reliability Upgrade | 1b | 1230 | CT | Northeast Utilities |  | TBD | LSP - Greater Hartford Area | 115kV breaker addition at Northeast Simsbury Substation | Concept | Concept | 2011-03-30 | No | TBD | TBD | TBD | 40 | 128300000 |  | 128300000
Reliability Upgrade | 1b | 1243 | CT | CMEEC |  | 10/2013 | TTD's Fitch St 115kV Substation | TTD 115/27kV substation with two transformers and a 115kV circuit breaker looped into 1416 line (between Compo and Darien substations) | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1a | 1197 | ME | Bangor Hydro-Electric Company |  | 12/2013 | Keene Rd Autotransformer | Orrington 345kV Series Breaker Addition | Planned | Planned | 2010-10-22 | 2011-06-16 | 1761250 | 1761250 | 1761250
Reliability Upgrade | 1a | 907 | ME | Central Maine Power Company |  | 05/2014 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 203 (Detroit-Orrington), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | ME | Central Maine Power Company |  | 2014-08-02 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast forming Sections 86 & 266 | Planned | Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | ME | Central Maine Power Company |  | 05/2014 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377, 115kV Bucksport 65/205) | Planned | Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1026 | ME | Central Maine Power Company | Northeast Utilities | 12/2013 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction associated with (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Elliot Switching Station) line work | Planned | Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 1/29/2010 (CMP) 4/14/2011 (NU) | Portion of CMP $1.47B and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | 36000000
Reliability Upgrade | 1a | 1028 | ME | Central Maine Power Company | Northeast Utilities | 12/2013 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 1/29/2010 (CMP) 4/14/2011 (NU) | Portion of CMP $1.47B and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M
Reliability Upgrade | 1a | 1030 | ME | Central Maine Power Company |  | 11/2013 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Maguire Road) | Planned | Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1132 | ME | Central Maine Power Company |  | 2014-08-02 | Maine Power Reliability Program (MPRP) | Add 115/34kV transformer at Coopers Mills | Planned | Planned | 7/31/08 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1129 | ME | Central Maine Power Company |  | 05/2012 |  | New 115kV line between Wyman Hydro and Rice Rips Tap, parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | Planned | 2009-01-26 | 2010-12-28 | 32800000 | 32800000 | 32800000
Reliability Upgrade | 1a | 1135 | ME | Central Maine Power Company |  | 02/2012 | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer | Planned | Planned | 2007-12-21 | NR | 1500000 | 1500000 | 1500000
Reliability Upgrade | 1a | 1184 | ME | Central Maine Power Company |  | 05/2012 | Starks Switching Station | Add 4-115kV circuit breakers in a breaker-and a-half configuration on Section 63 and 2-18 MVAr cap banks at a new Starks Switching Station | Planned | Planned | 2010-09-20 | 2011-03-25 | 10750000 | 9750000 | 9750000
Reliability Upgrade | 1a | 1251 | ME | Central Maine Power Company |  | 12/2012 | Lakewood Substation Expansion | Sectionalize Section 241 by adding four 115kV circuit breakers at Lakewood Substation and install a second 115/34.5 kV transformer | Planned | Planned | 2011-04-21 | No | 13700000 | 13700000 | 13700000
Reliability Upgrade | 1a | 1141 | NH | Northeast Utilities |  | 2015 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | Planned | Planned | 2009-06-29 | 2011-07-15 | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 680 | NH | National Grid, USA |  | 06/2013 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | Planned | 2008-01-28 | No | 7393000 | 7393000 | 7393000
Reliability Upgrade | 1a | 674 | NH | National Grid, USA |  | 12/2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | Planned | 2008-04-01 | No | 19460000 | 19460000 | 19460000
Reliability Upgrade | 1a | 1172 | VT | Vermont Electric Power Company |  | 06/2012 | Vermont Shunt Reactors | Install 345kV 60 MVAr shunt reactors (two at Coolidge and one at New Haven and relocate the New Haven reactor to Vernon) to address high voltage concerns | Planned | Planned | 2011-03-23 | No | 20000000 | 20000000 | 20000000
Reliability Upgrade | 1a | 318 | VT | Vermont Electric Power Company |  | 12/2012 | Georgia Substation Rebuild | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems due to breaker failure contingencies | Planned | Planned | 2010-11-22 | No | 16000000 | 16000000 | 16000000
Reliability Upgrade | 1a | 1169 | VT | Vermont Electric Power Company |  | 12/2012 | Ascutney Substation Rebuild | Rebuild the existing Ascutney substation 115kV bus into a ring bus, to address reliability problems due to breaker failure contingencies | Planned | Planned | 2010-11-22 | No | 14500000 | 14500000 | 14500000
Reliability Upgrade | 1a | 1170 | VT | Vermont Electric Power Company |  | 06/2013 | Bennington Substation Rebuild | Rebuild the exiting Bennington substation 115kV bus into a ring bus to address reliability problems due to breaker failure contingencies | Planned | Planned | 2010-11-22 | No | 23000000 | 28000000 | 28000000
Reliability Upgrade | 1a | 1171 | VT | Vermont Electric Power Company |  | 12/2011 | West Rutland Capacitor Rebuild | Install two 115kV 25 MVAr capacitor banks at West Rutland to address low voltage concerns | Planned | Planned | 2010-11-02 | NR | 2400000 | 2400000 | 2400000
Reliability Upgrade | 1a | 1194 | VT | Vermont Electric Power Company |  | 12/2012 | LSP Jay Substation | Construct a new 4-breaker ring substation at Jay with two 115/46kV transformers | Planned | Planned | 2011-02-07 | No | 6500000 | 6500000 | 6500000
Reliability Upgrade | 1a | 1195 | VT | Vermont Electric Power Company |  | 03/2013 | Highgate Refurbishment | Replace Highgate controls and cooling system | Planned | Planned | NR | No | 35600000 | 35600000 | 35600000
Reliability Upgrade | 1a | 921 | MA | National Grid, USA |  | 12/2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | Planned | 2008-01-28 | No | 40000000 | 40000000 | 40000000
Reliability Upgrade | 1a | 919 | MA | National Grid, USA |  | 04/2014 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | Planned | 2010-02-10 | No | 9200000 | 13600000 | 13600000
Reliability Upgrade | 1a | 59 | MA | National Grid, USA |  | 12/2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | Planned | 2008-01-28 | No | Part of RSP 921 | Part of RSP 921 | Part of RSP 921
Reliability Upgrade | 1a | 840 | MA | NSTAR Electric Company |  | 12/2012 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | Planned | 2008-04-01 | 2011-01-10 | 5900000 | 5900000 | 5900000
Reliability Upgrade | 1a | 776 | MA | National Grid, USA |  | 11/2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | Planned | 2008-06-27 | No | 3125000 | 3125000 | 3125000
Reliability Upgrade | 1a | 782 | MA | National Grid, USA |  | 01/2016 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor and Railyard. | Planned | Planned | 2008-06-27 | No | 43912000 | 43912000 | 43912000
Reliability Upgrade | 1a | 1068 | MA | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to vicinity of Bourne and connect to existing #120 line and install a 345KV - 115kV auto-transformer at new substation about 3 miles west of the Barnstable Substation Loop Line #115 in and out of the new Substation. Create a new line position at the Bourne Substation and connect the Bourne-Canal section of Line #120 | Planned | Planned | 07/2011 | No | 106500000 | 106500000 | 106500000
Reliability Upgrade | 1a | 592 | MA | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing. The lines being separated are 322 (Canal-Carver) and 342 (Canal-Pilgrim-Auburn) | Planned | Planned | 07/2011 | No | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1a | 1118 | MA | National Grid, USA | NSTAR Electric Company | 12/2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 (Bellrock-High Hill) | Planned | Planned | 07/2011 | No | 6000000 | 6000000 | 6000000
Reliability Upgrade | 1a | 1187 | MA | National Grid, USA |  | 06/2014 | A127/B128 Conductor Refurbishment | A127/B128 Conductor Refurbishment - Tower 510 to Harriman Substation, VT | Planned | Planned | 12/17/2007 01/20/11 | NR | 65000000 | 65000000 | 65000000
Reliability Upgrade | 1a | 929 | MA | National Grid, USA |  | 09/2013 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | Planned | 12/17/2007 | No | 2500000 | 2500000 | 2500000
Reliability Upgrade | 1a | 931 | MA | National Grid, USA |  | 01/2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | Planned | 12/17/2007 | No | 531481 | 531481 | 531481
Reliability Upgrade | 1a | 928 | MA | National Grid, USA |  | 06/2013 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | Planned | 12/17/2007 | No | 3400000 | 3400000 | 3400000
Reliability Upgrade | 1a | 938 | MA | National Grid, USA |  | 05/2013 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | Planned | 12/17/2007 | No | 5430000 | 5430000 | 5430000
Reliability Upgrade | 1a | 940 | MA | National Grid, USA |  | 06/2014 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS (A127 West reconductoring. Tower 510 to Paxton, French King to French King). | Planned | Planned | 12/17/2007 | No | 18000000 | 18000000 | 18000000
Reliability Upgrade | 1a | 942 | MA | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | Planned | 12/17/2007 | No | 3650000 | 3650000 | 3650000
Reliability Upgrade | 1a | 925 | MA | National Grid, USA |  | 11/2012 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | Planned | 12/17/2007 | No | Part of RSP 926 | Part of RSP 926 | Part of RSP 926
Reliability Upgrade | 1a | 926 | MA | National Grid, USA |  | 11/2012 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | Planned | 12/17/2007 | No | 14700000 | 14700000 | 14700000
Reliability Upgrade | 1a | 932 | MA | National Grid, USA |  | 11/2012 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | Planned | 12/17/2007 | No | Part of RSP 926 | Part of RSP 926 | Part of RSP 926
Reliability Upgrade | 1a | 941 | MA | National Grid, USA |  | 2013-08-01 | Central/Western Massachusetts Upgrades | Install new Z126 Millbury - Tower #510 115 kV line. | Planned | Planned | 12/17/2007 | No | 13748000 | 13748000 | 13748000
Reliability Upgrade | 1a | 943 | MA | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | Planned | 12/17/2007 | No | 4100000 | 4100000 | 4100000
Reliability Upgrade | 1a | 950 | MA | National Grid, USA |  | 02/2015 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | Planned | 12/17/2007 | No | 1016897 | 1016897 | 1016897
Reliability Upgrade | 1a | 953 | MA | National Grid, USA |  | 02/2015 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | Planned | 12/17/2007 | No | 10248067 | 10248067 | 10248067
Reliability Upgrade | 1a | 954 | MA | National Grid, USA |  | 02/2015 | Central/Western Massachusetts Upgrades | Westminster - install new 69kV breaker, including disconnect switches. | Planned | Planned | 12/17/2007 | No | 903909 | 903909 | 903909
Reliability Upgrade | 1a | 945 | MA | National Grid, USA |  | 05/2014 | Central/Western Massachusetts Upgrades | Adams - install two new 115 kV breakers and replace two existing 115kV breakers | Planned | Planned | 12/17/2007 | No | 5000000 | 5000000 | 5000000
Reliability Upgrade | 1a | 946 | MA | National Grid, USA |  | 04/2015 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer- Hampden to 115 kV. | Planned | Planned | 2011-03-29 | No | 16000000 | 16000000 | 16000000
Reliability Upgrade | 1a | 948 | MA | National Grid, USA |  | 05/2014 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | Planned | 2011-03-29 | No | 13400000 | 13400000 | 13400000
Reliability Upgrade | 1a | 949 | MA | National Grid, USA |  | 04/2015 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | Planned | 2011-03-29 | No | 1600000 | 1600000 | 1600000
Reliability Upgrade | 1a | 937 | MA | National Grid, USA |  | 12/2015 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | Planned | 12/17/2007 | No | 6602875 | 6602875 | 6602875
Reliability Upgrade | 1a | 955 | MA | National Grid, USA |  | 10/2012 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | Planned | 12/17/2007 | No | 13800000 | 13800000 | 13800000
Reliability Upgrade | 1a | 951 | MA | National Grid, USA |  | 01/2014 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon (H-134) 115 kV line. | Planned | Planned | 12/17/2007 | No | 7455440 | 7455440 | 7455440
Reliability Upgrade | 1a | 1217 | MA | Northeast Utilities |  | 12/2012 | Central/Western Massachusetts Upgrades | Subatation work at Ludlow (MA) and Scitico (CT) assoicaited with the new Hampden (MA) subsation project (Ngrid) | Planned | Planned | 12/17/2007 | No | 3140000 | 3140000 | 3140000
Reliability Upgrade | 1a | 687 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | Planned | 2008-09-24 | No | 795000000 | 718000000 | 718000000
Reliability Upgrade | 1a | 826 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1078 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1094 | MA | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | Planned | 2008-09-24 | No | 25000000 | 25000000 | 25000000
Reliability Upgrade | 1a | 1202 | MA | NSTAR Electric Company |  | 06/2013 | NEEWS (Ancillary Interstate Reliability Project) | Rebuild 1.2 mile length of line 336 with 2-900 ACSS conductor and replace 5, 345kV 2000 amp disconnect switches with 3000 amp switches at W. Medway station | Planned | Planned | 2011-03-30 | NR | 1700000 | 1700000 | 1700000
Reliability Upgrade | 1a | 791 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | Planned | 2008-04-25 | No | 11560000 | 11560000 | 11560000
Reliability Upgrade | 1a | 913 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | Planned | 2008-04-25 | No | 3250000 | 3250000 | 3250000
Reliability Upgrade | 1a | 914 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | Planned | 2008-04-25 | No | 28150000 | 28150000 | 28150000
Reliability Upgrade | 1a | 917 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | Planned | 2008-04-25 | No | 7000000 | 7000000 | 7000000
Reliability Upgrade | 1a | 793 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | Planned | 2008-04-25 | No | 6400000 | 6400000 | 6400000
Reliability Upgrade | 1a | 1268 | MA | Northeast Utilities |  | 12/2012 |  | 345kV Northfield Mountain to Berkshire (portion of 312) line structure replacements |  | Planned | NR | No |  | 7900000 | 7900000
Reliability Upgrade | 1a | 673 | MA | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | Planned | 2009-02-27 | No | 2200000 | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | MA | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Planned | Planned | 2009-02-27 | No | 30000000 | 30000000 | 30000000
Reliability Upgrade | 1a | 1257 | MA | National Grid, USA |  | 06/2014 | Salem Harbor Retirement | 115kV line Reconductoring of the S-145/T-146 from Tewksbury-North Reading Tap (9.3 miles each) |  | Planned | 2011-07-28 | No |  | 29000000 | 29000000
Reliability Upgrade | 1a | 1258 | MA | National Grid, USA |  | 06/2014 | Salem Harbor Retirement | 115kV line Reconductoring of the Y-151 from Tewksbury Junction - West Methuen (8.2 miles) |  | Planned | 2011-07-28 | No |  | 11500000 | 11500000
Reliability Upgrade | 1a | 1259 | MA | National Grid, USA |  | 06/2014 | Salem Harbor Retirement | 115kV line Reconductoring of the B154/C-155N from King St Tap - South Danvers (14.5 miles each way) |  | Planned | 2011-07-28 | No |  | 20000000 | 20000000
Reliability Upgrade | 1a | 1201 | MA | NSTAR Electric Company | NGRID | 12/2012 | Greater Boston - North | 115kV line Reconductoring of the P168/128-518 Line between Chelsea and Revere (NSTAR Portion of the line) | Proposed | Planned | 2011-03-25 | NR | 800000 | 1500000 | 1500000
Reliability Upgrade | 1a | 1168 | MA | Holyoke Gas & Electric |  | 12/2012 | North Canal 44P | Loop the 1525 (Holyoke Fairmont South 115kV) line into the new North Canal 44P | Proposed | Planned | 2011-05-25 | No | 4100000 | 4100000 | 4100000
Reliability Upgrade | 1a | 1256 | MA | Unitil |  | 06/2013 | Flagg Pond Upgrades | At Flagg Pond Substation upgrade terminal equipment on the I-135N, I-135S, J-136N and J-136S 115kV lines and Zone 3 relay upgrades for the J-136N 115kV line. |  | Planned | NR | NR |  | 2750000 | 2750000
Reliability Upgrade | 1a | 915 | RI | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | Planned | 2008-04-25 | No | 19450000 | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | RI | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | Planned | 2008-04-25 | No | 11800000 | 11800000 | 11800000
Reliability Upgrade | 1a | 918 | RI | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | Planned | 2008-04-25 | No | 3180000 | 3180000 | 3180000
Reliability Upgrade | 1a | 190 | RI | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | Planned | 2008-09-24 | No | 81800000 | 81800000 | 81800000
Reliability Upgrade | 1a | 1095 | RI | National Grid, USA |  | 12/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | Planned | 2008-09-24 | No | 73800000 | 73800000 | 73800000
Reliability Upgrade | 1a | 794 | RI | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | Planned | 2008-09-24 | No | 71700000 | 71700000 | 71700000
Reliability Upgrade | 1a | 795 | RI | National Grid, USA |  | 04/2013 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV (359) line. | Planned | Planned | 2008-09-24 | No | 69000000 | 69000000 | 69000000
Reliability Upgrade | 1a | 1106 | RI | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Kent County Substation Upgrades related to third 345/115 kV Autotransformer. | Planned | Planned | 2008-09-24 | No | 26000000 | 26000000 | 26000000
Reliability Upgrade | 1a | 798 | RI | National Grid, USA |  | 12/2011 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Planned | Planned | 2008-09-24 | No | 4900000 | 600000 | 600000
Reliability Upgrade | 1a | 1096 | RI | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | Planned | 2008-09-24 | No | 12000000 | 12000000 | 12000000
Reliability Upgrade | 1a | 1097 | RI | National Grid, USA |  | 01/2013 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County including S-175, T172N and T-172S with associated terminal equipment upgrade. | Planned | Planned | 2008-09-24 | No | 129800000 | 129800000 | 129800000
Reliability Upgrade | 1a | 1099 | RI | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | Planned | 2008-09-24 | No | 6000000 | 6000000 | 6000000
Reliability Upgrade | 1a | 1253 | RI | National Grid, USA |  | 04/2015 |  | New Crandall St. Substation 115-13 kV substation addition | Proposed | Planned | 2011-06-07 | No | 5000000 | 3000000 | 3000000
Reliability Upgrade | 1a | 1241 | RI | National Grid, USA |  | 06/2013 |  | Re-condustor G-185S (Kent County - Davisville Tap) | Planned | Planned | 2010-12-27 | No | 4200000 | 4200000 | 4200000
Reliability Upgrade | 1a | 1054 | CT | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Build a new 345 kV line from Manchester to Meekville Junction and re-terminate the 395 line at Meekville Junction | Planned | Planned | 2008-09-24 | No | 31000000 | 28800000 | 28800000
Reliability Upgrade | 1a | 576 | CT | Northeast Utilities |  | 2016 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | Planned | 2008-09-24 | No | 338000000 | 301000000 | 301000000
Reliability Upgrade | 1a | 1114 | CT | Northeast Utilities |  | 2016 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1a | 802 | CT | Northeast Utilities |  | 2015 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | Planned | 2008-09-24 | No | 251000000 | 218000000 | 218000000
Reliability Upgrade | 1a | 1085 | CT | Northeast Utilities |  | 2015 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | CT | Northeast Utilities |  | 2015 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | CT | Northeast Utilities | National Grid, USA | 2015 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1235 | CT | Northeast Utilities |  | 12/2015 | NEEWS (Ancillary Interstate Reliability Project) | Sag elimination on 1410 Line (Montville-Buddington) | Proposed | Planned | 2011-06-09 | No | 3500000 | 3000000 | 3000000
Reliability Upgrade | 1a | 1245 | CT | CMEEC |  | 12/2015 | NEEWS (Ancillary Interstate Reliability Project) | Sag elimination on 1410 Line (Montville-Buddington) | Proposed | Planned | 2011-06-09 | No | 60000 | 60000 | 60000
Reliability Upgrade | 1a | 1227 | CT | Northeast Utilities |  | 2012 | LSP - Stamford Area | Add 4th transformer and build a five breaker ring bus at South End Substation | Proposed | Planned | 2011-06-09 | No | 9100000 | 6400000 | 6400000
Reliability Upgrade | 1a | 1218 | CT | Northeast Utilities |  | 12/2013 | Millstone 345kV Circuit Separation project & SLOD SPS System Retirement | Separate the 345kV Double Circuit Tower 310/348 and 371/383 Tower configuration | Planned | Planned | 2010-11-02 | No | 25600000 | 25600000 | 25600000 | 104 | Planned |  | -25% | 25%
Reliability Upgrade | 1a | 721 | CT | United Illuminating Company |  | 06/2015 |  | New Shelton 115/13.8 kV substation | Planned | Planned | 2009-11-05 | No | 19500000 | 19500000 | 19500000 | 104 | 2699747919 |  | 2024810939.25 | 3374684898.75
Reliability Upgrade | 1a | 879 | CT | Bangor Hydro-Electric Company | New England Power Company, Northeast Utilities System Com | TBD | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | Planned | 03/01/2007 | NR | 420000 | 420000 | 420000
Reliability Upgrade | 1b | 1133 | ME | Central Maine Power Company |  | 12/2011 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation and new 34kV line from Leeds to Turner | Proposed | Proposed | No | NR | 300000 | 300000 | 300000
Reliability Upgrade | 1b | 1279 | ME | Central Maine Power Company |  | 12/2014 |  | New 345/115kV Autotransformer and 115kV switchyard at Raven Farm substation consisting of a four-bay breaker and a half configuration of eleven (11) breakers |  | Proposed | 2010-01-29 | No |  | 26126000 | 26126000
Reliability Upgrade | 1b | 1280 | ME | Central Maine Power Company |  | 12/2014 |  | New 115kV line section 244 and upgraded line section 80 between Coopers Mill and Highland Substations |  | Proposed | 2010-01-29 | No |  | 62735000 | 62735000
Reliability Upgrade | 1b | 1183 | NH | Northeast Utilities |  | 2014 | LSP New Peaselee Substation and 115/34.5KV transformer | New 115kV Peaselee Substation and transmission line work | Proposed | Proposed | No | No | 12400000 | 12400000 | 12400000
Reliability Upgrade | 1b | 1220 | NH | Northeast Utilities |  | 12/2015 | Greater Boston - North | Install a new 345kV circuit between Scobie and Pelham NH (this is NU's portion of the new Scobie-Tewksbury circuit) | Proposed | Proposed | No | No | 40100000 | 40100000 | 40100000
Reliability Upgrade | 1b | 1269 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Amherst Substation - New 345kV breaker and three 25MVar Capacitor Banks |  | Proposed | No | No |  | 19600000 | 19600000
Reliability Upgrade | 1b | 1270 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | New 115kV line from Fitzwilliiams to Monadnock |  | Proposed | No | No |  | 10500000 | 10500000
Reliability Upgrade | 1b | 1271 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Upgrade the Keene to Monadnock (T198) 115kV line |  | Proposed | No | No |  | 11900000 | 11900000
Reliability Upgrade | 1b | 1272 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Weare Substation - Add two 13.3 MVar 115V capacitors |  | Proposed | No | No |  | 3600000 | 3600000
Reliability Upgrade | 1b | 1273 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Rebuild A152 115kV line |  | Proposed | No | No |  | 22500000 | 22500000
Reliability Upgrade | 1b | 1274 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Rebuild N186 115kV line |  | Proposed | No | No |  | 2300000 | 2300000
Reliability Upgrade | 1b | 1275 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Upgrade the 381 345kV line |  | Proposed | No | No |  | 4200000 | 4200000
Reliability Upgrade | 1b | 1276 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Littleton Substation - Add a second 230/115kV autotransformer and associated 115kV substation work |  | Proposed | No | No |  | 16700000 | 16700000
Reliability Upgrade | 1b | 1277 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Webster Substation - Add four 26.6 MVar 115kV capacitors |  | Proposed | No | No |  | 11900000 | 11900000
Reliability Upgrade | 1b | 1278 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Saco Valley Substation - Add two 25 MVar dynamic Var devices |  | Proposed | No | No |  | 15800000 | 15800000
Reliability Upgrade | 1b | 1263 | NH | National Grid, USA |  | TBD | Northern New Hsmpshire Solution | New C-203 230kV line tap to Littleton NH Substation associated with 2nd 230/115kV auto project |  | Proposed | No | No |  | 1100000 | 1100000
Reliability Upgrade | 1b | 843 | MA | NSTAR Electric Company |  | 06/2012 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | Proposed | No | NR | 3200000 | 3450000 | 3450000
Reliability Upgrade | 1b | 965 | MA | NSTAR Electric Company |  | 06/2014 | Greater Boston - South | Add third 115kV line from W. Walpole to Holbrook | Proposed | Proposed | No | No | 19000000 | 19000000 | 19000000
Reliability Upgrade | 1b | 1175 | MA | NSTAR Electric Company |  | 12/2013 | Greater Boston - South | Upgrade the 115kV line 201-501 (Medway-Depot St.) and the 201-502 (Beaver Pond - Depot Street Tap) to a higher capacity line | Proposed | Proposed | No | NR | 3700000 | 3700000 | 3700000
Reliability Upgrade | 1b | 1214 | MA | National Grid, USA |  | 12/2015 | Greater Boston - South | Line Reconductoring of the C-129 Beaver Pond - Depot St. Tap) and D-130 (Depot St. Tap - Medway) 115kV lines | Proposed | Proposed | No | No | 500000 | 500000 | 500000
Reliability Upgrade | 1b | 1179 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - North | Install 2nd 345kV circuit between Bellerica/Burlington town line to Tewksbury | Proposed | Proposed | No | No | 33000000 | 33000000 | 33000000
Reliability Upgrade | 1b | 1200 | MA | NSTAR Electric Company |  | TBD | Greater Boston - North | Add a new 345kV UG circuit between Woburn and North Cambridge | Proposed | Proposed | No | No | 52000000 | 52000000 | 52000000
Reliability Upgrade | 1b | 1211 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | Install 2nd 345kV circuit between Tewksbury - Billerica/Burlington Town Line (NSTAR Border) | Proposed | Proposed | No | No | 32700000 | 32700000 | 32700000
Reliability Upgrade | 1b | 1212 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | 115kV Line Reconductoring of M-139/N-140 Tewksbury-Pinehurst (6.1 miles each) | Proposed | Proposed | No | No | 57000000 | 11600000 | 11600000
Reliability Upgrade | 1b | 1213 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | Install new 345kV circuit between NH/MA border and Tewksbury (this is NGRID's portion of the new Scobie-Tewksbury circuit) | Proposed | Proposed | No | No | 23370000 | 23370000 | 23370000
Reliability Upgrade | 1b | 1215 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | New 115kV line between Wakefield - Everett | Proposed | Proposed | No | No | 20000000 | 20000000 | 20000000
Reliability Upgrade | 1b | 1254 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | Substation work at Revere Substation to increase ratings on the 128-515P/168 line between Chelsea and Revere | Concept | Proposed | No | No | TBD | 1000000 | 1000000
Reliability Upgrade | 1b | 1260 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | 115kV Line reconductoring of the F-158N/S Wakefield Jct - Everett (7.36 miles) |  | Proposed | No | No | TBD | 3500000 | 3500000
Reliability Upgrade | 1b | 1261 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | 115kV Line reconductoring of the S-145T-146 from North Reading Tap - Wakefield Jct (5.1 miles each) |  | Proposed | No | No | TBD | 10800000 | 10800000
Reliability Upgrade | 1b | 1262 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | 115kV Line reconductoring of theY-151 from Tewksbury Junction - Tewksbury Substation (1.6 miles) |  | Proposed | No | No | TBD | 1250000 | 1250000
Reliability Upgrade | 1b | 1208 | MA | National Grid, USA |  | 12/2014 | Pittsfield / Greenfield Project | Separation and reconductoring of Cabot Taps (A-127 and Y-177 115kV lines) | Proposed | Proposed | No | No | 7400000 | 7400000 | 7400000
Reliability Upgrade | 1b | 1209 | MA | National Grid, USA |  | 12/2014 | Pittsfield / Greenfield Project | Reconductoring of A-127 between Erving and Cabot Tap with 1590 ACSS | Proposed | Proposed | No | No | 12000000 | 12000000 | 12000000
Reliability Upgrade | 1b | 1210 | MA | National Grid, USA |  | 12/2014 | Pittsfield / Greenfield Project | Harriman 115kV breaker upgrades | Proposed | Proposed | No | No | 1100000 | 1100000 | 1100000
Reliability Upgrade | 1b | 1221 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Modify Northfield Mountain 16R substation and install a 345/115Kv autotransformer | Proposed | Proposed | No | No | 108500000 | 108500000 | 108500000
Reliability Upgrade | 1b | 1222 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Build a new 115kV three breaker Swithching Station (Erving) ring bus | Proposed | Proposed | No | No | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1223 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Build a new 115kV line from Northfield Mountain to the new Erving Switching Station | Proposed | Proposed | No | No | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1224 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Install 115kV 14.4 MVAR capacitor banks at Cumberland, Podick and Amherst Substations | Proposed | Proposed | No | No | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1225 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Rebuild the Cumberland to Montague 1361 115kV line and terminal work at Cumberland and Montague | Proposed | Proposed | No | No | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1226 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Proposed | Proposed | No | No | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 956 | MA | National Grid, USA |  | 01/2015 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Proposed | Proposed | No | No | 7021534 | 7021534 | 7021534
Reliability Upgrade | 1b | 1252 | MA | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | Re-conductor 345kV 328 line (West Farnum-Sherman Rd) | Concept | Proposed | No | No | TBD | 36500000 | 36500000
Reliability Upgrade | 1b | 1233 | RI | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | New Sherman Road 345kV AIS Substation | Concept | Proposed | No | No | TBD | 36600000 | 36600000 | 45 | Proposed |  | -25% | 25%
Reliability Upgrade | 1b | 1242 | CT | CMEEC |  | 10/2012 | SNEW 115kV substation | SNEW 115/13.8kV substation with two transformers and a 115kV circuit breaker looped into the 1890 line (between Norwalk Hbr - Ely Ave) | Proposed | Proposed | No | No | 2000000 | 2000000 | 2000000 | 45 | 706902534 |  | 530176900.5 | 883628167.5
Reliability Upgrade | 1b | 1244 | CT | CMEEC |  | 10/2011 | 115kV Circuit Breaker Installation | Install 115kV Bus Tie Circuit Breaker at Stock House Rd Substation | Proposed | Proposed | No | No | 750000 | 750000 | 750000
Reliability Upgrade | 1b | 1246 | CT | United Illuminating Company |  | 09/2013 | 8300 Line Reconfiguration Project | Reconfiguration of 115kV (8300) line from Mill River to Quinnipiac | Proposed | Proposed | No | No | 17400000 | 17400000 | 17400000
Reliability Upgrade | 1a | 1116 | ME | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Under Construction | Under Construction | 2010-10-22 | 2011-06-16 | 37126000 | 37626000 | 37626000
Reliability Upgrade | 1a | 1156 | ME | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | Orrington Shunt Cap Reconfiguration | Under Construction | Under Construction | 2010-10-22 | 2011-06-16 | 2260262 | 2260262 | 2260262
Reliability Upgrade | 1a | 905 | ME | Central Maine Power Company |  | 2014-08-02 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Under Construction | Under Construction | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | 1470187000 | 1364108000 | 1364108000
Reliability Upgrade | 1a | 906 | ME | Central Maine Power Company |  | 05/2014 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Larrabee Road-Middle St,Middle St -Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Under Construction | Under Construction | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 908 | ME | Central Maine Power Company |  | 07/2014 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road); Coopers Mills autotransforme replaces Maxcy's autotransformer | Under Construction | Under Construction | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1158 | ME | Central Maine Power Company |  | 07/2014 | Maine Power Reliability Program (MPRP) | Two 40 MVAR reactors at Albion Road, two 40 MVAR reactors at Larabee Road, two 40 MVAR at Coopers Mills | Under Construction | Under Construction | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 143 | ME | Bangor Hydro-Electric Company |  | 12/2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation (2 new breakers) to Harrington Substation to Epping Substation (3 new breakers) | Under Construction | Under Construction | 2006-05-10 | 2008-06-13 | 66100000 | 66100000 | 66100000
Reliability Upgrade | 1a | 1131 | ME | Central Maine Power Company |  | 11/2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Planned | Under Construction | 2010-11-22 | NR | 600000 | 600000 | 600000
Reliability Upgrade | 1a | 1196 | ME | Bangor Hydro-Electric Company |  | 01/2012 | SVC Filter Upgrade (Part of Keene Rd Auto-transformer ID 144) | Upgrade of filter bank at Chester SVC facility | Under Construction | Under Construction | 2011-07-15 | 2011-07-15 | 3500000 | 3500000 | 3500000
Reliability Upgrade | 1a | 1219 | NH | Northeast Utilities |  | 12/2011 |  | Install 115kV two 13.3 MVAR capacitor banks at Oak Hill substation | Planned | Under Construction | 2011-02-28 | NR | 3800000 | 4000000 | 4000000
Reliability Upgrade | 1a | 277 | NH | Northeast Utilities |  | 11/2011 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Under Construction | Under Construction | 2009-06-29 | 2011-07-15 | 52000000 | 52000000 | 52000000
Reliability Upgrade | 1a | 1140 | NH | Northeast Utilities |  | 10/2011 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | Under Construction | Under Construction | 2009-06-29 | 2011-07-15 | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1182 | NH | Northeast Utilities |  | 06/2012 | LSP New Eagle Substation and 115/34.5KV transformer | New 115kV Eagle Substation connected to 115/34.5kV Thornton Substation | Planned | Under Construction | 2010-07-27 | No | 22800000 | 22800000 | 22800000
Reliability Upgrade | 1a | 887 | MA | National Grid, USA |  | 06/2013 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Under Construction | Under Construction | 2010-02-10 | No | 66300000 | 58000000 | 58000000
Reliability Upgrade | 1a | 1165 | MA | NSTAR Electric Company |  | 12/2011 | Mystic Breaker Additions Project | Move Transformer 110B Connection at Mystic | Planned | Under Construction | 2008-03-10 | NR | 1700000 | 2600000 | 2600000
Reliability Upgrade | 1a | 934 | MA | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Under Construction | Under Construction | 12/17/2007 | No | Part of RSP 935 | Part of RSP 935 | Part of RSP 935
Reliability Upgrade | 1a | 935 | MA | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Under Construction | Under Construction | 12/17/2007 | No | 10200000 | 10200000 | 10200000
Reliability Upgrade | 1a | 944 | MA | National Grid, USA |  | 03/2012 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Planned | Under Construction | 12/17/2007 | No | 16530000 | 15700000 | 15700000
Reliability Upgrade | 1a | 1076 | MA | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Under Construction | Under Construction | 2008-09-24 | No | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 196 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct the 115kV line South Agawam to Southwick (1768) | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Under Construction | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Under Construction | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVar Capacitor additions | Under Construction | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Under Construction | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Under Construction | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Under Construction | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1074 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1109 | MA | National Grid, USA |  | 12/2011 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Planned | Under Construction | 2008-09-24 | No | 1000000 | 1000000 | 1000000
Reliability Upgrade | 1a | 790 | MA | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Under Construction | Under Construction | 2008-04-25 | No | 52000000 | 52000000 | 52000000
Reliability Upgrade | 1a | 1098 | MA | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Under Construction | Under Construction | 2008-04-25 | No | 22000000 | 22000000 | 22000000
Reliability Upgrade | 1a | 1092 | MA | Northeast Utilities |  | 12/2013 | Agawam (BPS) | Upgrade the Agawam 115kV, Subtations to BPS standards together with other misc. subatation upgrades | Under Construction | Under Construction | 2008-09-24 | No | 13600000 | 12100000 | 12100000
Reliability Upgrade | 1a | 1216 | MA | Northeast Utilities |  | 04/2012 |  | 345kV Ludlow - Northfield (portion of 354) Line Structure replacements | Under Construction | Under Construction | NR | No | 17000000 | 25100000 | 25100000
Reliability Upgrade | 1a | 1266 | MA | Northeast Utilities |  | 12/2011 |  | 115kV Pleasant to Blandford (portion of 1421) Line structure replacement |  | Under Construction | NR | No |  | 9960000 | 9960000
Reliability Upgrade | 1a | 1267 | MA | Northeast Utilities |  | 12/2011 |  | 115kV Blandford to Southwick (portion of 1512) Line structure replacement |  | Under Construction | NR | No |  | 9600000 | 9600000
Reliability Upgrade | 1a | 969 | MA | NSTAR Electric Company |  | 11/2012 | Greater Boston - North | Add a new 115kV 36.7 MVAR capacitor bank at Chelsea. | Planned | Under Construction | 2011-03-30 | NR | 1500000 | 1500000 | 1500000
Reliability Upgrade | 1a | 301 | MA | NSTAR Electric Company |  | 12/2011 | Greater Boston - Central | Reconductor 115-kV circuits 320-507 and 320-508. (Lexington - Waltham) | Concept | Under Construction | 2011-02-15 | No | 8400000 | 9600000 | 9600000
Reliability Upgrade | 1a | 1066 | MA | NSTAR Electric Company |  | 12/2011 | NPCC BPS Compliance | Needham Station | Under Construction | Under Construction | NR | No | 6500000 | 8000000 | 8000000
Reliability Upgrade | 1a | 1065 | MA | NSTAR Electric Company |  | 07/2012 | NPCC BPS Compliance | Waltham Station | Under Construction | Under Construction | NR | No | 14700000 | 14700000 | 14700000
Reliability Upgrade | 1a | 484 | RI | National Grid, USA |  | 11/2011 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Planned | Under Construction | 2008-04-25 | No | 580000 | 580000 | 580000
Reliability Upgrade | 1a | 1193 | CT | United Illuminating Company |  | 12/2012 |  | North Haven 115kV Capacitor Bank TRV Mitigation Project | Under Construction | Under Construction | NR | NR | 5100000 | 4900000 | 4900000
Reliability Upgrade | 1a | 974 | CT | United Illuminating Company |  | 05/2013 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Under Construction | Under Construction | NR | No | 16900000 | 16900000 | 16900000
Reliability Upgrade | 1a | 816 | CT | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1056 | CT | Northeast Utilities |  | 12/2011 | LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Under Construction | Under Construction | 2008-12-12 | 2011-04-14 | 10969000 | 10969000 | 10969000
Reliability Upgrade | 1a | 1111 | CT | United Illuminating Company |  | 01/2012 |  | Union Avenue 115/26.4 kV Substation | Under Construction | Under Construction | 2009-01-07 | 2009-11-10 | 10543000 | 13500000 | 13500000 | 58 | UnderConstruction |  | -10% | 10%
Reliability Upgrade | 1a | 976 | CT | United Illuminating Company |  | 05/2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Under Construction | Under Construction | 1/7/2009 & 11/22/2010 | No | 70000000 | 70000000 | 70000000 | 58 | 1925903262 |  | 1733312935.8 | 2118493588.2
Reliability Upgrade | 1a | 1050 | CT | United Illuminating Company |  | 12/2011 |  | Devon Tie 115kV Switching Station BPS Compliance | Under Construction | Under Construction | NR | NR | 4000000 | 4000000 | 4000000 | Total w/ Concept | 5460853715 | 247 | 4416600775.55 | 2118493588.2
[15 empty] | 5460853715 | Total w/o Concept | 5332553715 | 207 | 4288300775.55 | 5348690245

## Sorted by status 10-09 (hidden)
October '09 ISO-NEW ENGLAND Project Listing Update (DRAFT)
Primary Driver | Part# | Project ID | Primary Equipment Owner | Other Equipment Owner(s) | Projected In-Service Month/Year | Major Project | Project | Oct-09 Status | PPA (I.3.9) Approval | TCA Approval | Jul-09 Estimated PTF Costs | Oct-09 Estimated PTF Costs | Column T | Min Tolerance | Max Tolerance | # of Projects
Reliability Upgrade | 1b | 1116 | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1031 | Bangor Hydro-Electric Company |  | 01/2012 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station, Rebuild Line 66, and Capacitior Bank Additions (10MVAr at Trenton, Downeast & Handcock County area) | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 275 | Northeast Utilities |  | TBD |  | Merrimack 115-kV substation - Protection Separation Upgrade. | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 318 | Vermont Electric Power Company |  | 12/2011 |  | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems through the 1,250 MW Vermont state load level. | Concept | No | No | 9000000 | 9000000 | 9000000
Reliability Upgrade | 1b | 325 | Vermont Electric Power Company |  | 12/2011 | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | No | No | 5000000 | 5000000 | 5000000
Reliability Upgrade | 1b | 324 | Vermont Electric Power Company |  | 12/2012 |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | No | No | 100000000 | 100000000 | 100000000
Reliability Upgrade | 1b | 785 | National Grid, USA |  | 07/2017 | Merrimack Valley/North Shore Reliability Project | Re-conductor F-158N (Golden Hills-Maplewood-Everett) 115 kV line. | Concept | No | No | 1330000 | 1330000 | 1330000
Reliability Upgrade | 1b | 1153 | NSTAR Electric Company |  | 06/2010 | Boston Area 115 kV Enhancements | Reliability Upgrades at West Framingham Station | Concept | No | No |  | 3000000 | 3000000
Reliability Upgrade | 1b | 843 | NSTAR Electric Company |  | 12/2013 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 965 | NSTAR Electric Company |  | 12/2012 | Boston Area 115 kV Enhancements | Add third 115kV line from Walpole to Holbrook | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 969 | NSTAR Electric Company |  | 06/2018 | Boston Area 115 kV Enhancements | Add a new 54 MVAR capacitor bank at Chelsea. | Concept | No | No | 1200000 | 1200000 | 1200000
Reliability Upgrade | 1b | 301 | NSTAR Electric Company |  | 12/2011 | Boston Area 115 kV Enhancements | Reconductor 115-kV circuits 320-507 and 320-508. | Concept | No | No | 4600000 | 4600000 | 4600000
Reliability Upgrade | 1b | 593 | NSTAR Electric Company |  | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Canal to Barnstable/Falmouth | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1066 | NSTAR Electric Company |  | 09/2011 | NPCC BPS Compliance | Needham Station | Concept | No | No | 9300000 | 9300000 | 9300000
Reliability Upgrade | 1b | 970 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345 kV line from Lexington to Waltham. | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 971 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 956 | National Grid, USA |  | 05/2013 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Concept | No | No | 7021534 | 7021534 | 7021534
Reliability Upgrade | 1b | 824 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 825 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Upgrade the Pleasant to Blanford 115-kV line and the Blanford to Granville Jct. portion of the 115-kV line 1512. | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1055 | Northeast Utilities |  | 2010 | CT LSP - Waterside Substation | Waterside Substation - add a 115/13.2-kV transformer and a 115-kV circuit breaker. | Concept | No | No | 4107000 | 4107000 | 4107000
Reliability Upgrade | 1b | 975 | United Illuminating Company |  | 12/2013 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | No | No | 44300000 | 44300000 | 44300000
Reliability Upgrade | 1b | 699 | United Illuminating Company |  | 12/2012 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | No | No | 10000000 | 10000000 | 10000000
Reliability Upgrade | 1b | 801 | Northeast Utilities |  | TBD |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 85 | Northeast Utilities |  | TBD |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | 08/04/2004 | No | TBD | TBD | TBD | -50% | 200%
[13 empty] | 198858534 | 99429267 | 596575602 | 24
Reliability Upgrade | 1a | 1128 | Central Maine Power Company |  | 07/2010 | CMP-LSP Hotel Road Substation | Add 115/34kV transformer with 115kV breaker at Hotel Rd. | Planned | 2008-08-20 | NR | 800000 | 800000 | 800000
Reliability Upgrade | 1a | 624 | Central Maine Power Company |  | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (New Page - Rumford Industrial Park) | Planned | 2007-11-30 | No | Part of project 625 | Part of project 625 | Part of project 625
Reliability Upgrade | 1a | 905 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Planned | 2008-07-31 | No | 1510000000 | 1510000000 | 1510000000
Reliability Upgrade | 1a | 906 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Coopers Mills-Highland, Larrabee Road-Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 907 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 84 (Albion Road-Coopers Mills), Section 203 (Detroit-Orrington), Section 80 (Coopers Mills-Highland), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 908 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road) | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377 & Maine Yankee 375/392, 115kV Bucksport 65/205) and Maine Yankee 345 kV re-termination | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1026 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Three Rivers) | Planned | 7/31/2008 & 2/26/09 | No | Portion of CMP $1.51B and portion of NU is $35.1M | Portion of CMP $1.51B and portion of NU is $35.1M | 35100000
Reliability Upgrade | 1a | 1027 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV Line Construction (Elm Street-East Deering, East Deering -Cape) | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1028 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | 7/31/2008 & 2/26/09 | No | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD
Reliability Upgrade | 1a | 1030 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Raven Farm, Maguire Road) | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 143 | Bangor Hydro-Electric Company |  | 12/2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation to Harrington Substation. | Planned | 2006-05-10 | 2008-06-13 | 66100000 | 66100000 | 66100000
Reliability Upgrade | 1a | 1129 | Central Maine Power Company |  | 05/2012 |  | New 115kV line between Wyman Hydro and Heywood Rd. parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | 2009-01-26 | No | 19500000 | 19500000 | 19500000
Reliability Upgrade | 1a | 277 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Planned | 2009-06-29 | No | 56600000 | 56600000 | 56600000
Reliability Upgrade | 1a | 1137 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115kV breakers and add 1-115kV breaker at Deerfield Substation | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1138 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rebuild 115kV L175 line | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1139 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV M183 Line | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1140 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1141 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 680 | National Grid, USA |  | 09/2012 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | 2008-01-28 | No | 11497000 | 7393000 | 7393000
Reliability Upgrade | 1a | 674 | National Grid, USA |  | 09/2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | 2008-04-01 | No | 12000000 | 7720000 | 7720000
Reliability Upgrade | 1a | 139 | Vermont Electric Power Company |  | 12/2010 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Planned | 01/10/2003 | 03/31/2003 | 20000000 | 20000000 | 20000000
Reliability Upgrade | 1a | 1145 | Vermont Electric Power Company |  | 09/2011 | Burlington Project | Installation of a 3-breaker 115kV ring substation and 115/34.5kV transformer on the East Ave. - Tafts Coners 115kV line | Planned | 10/24/2006 | No |  | 14000000 | 14000000
Reliability Upgrade | 1a | 1146 | Vermont Electric Power Company |  | 12/2012 | Lyndonville Project | Installation of a 3-breaker 115kV righ station consisting of two 115kV 12.5 MVAR capacitor banks and 115/34.5 kV transformer interconnecting to the Irasburg - St. Johnsbury 115kV line | Planned | 2009-06-01 | No |  | 9000000 | 9000000
Reliability Upgrade | 1a | 887 | National Grid, USA |  | 09/2012 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Planned | 2008-01-28 | No | 30000000 | 30000000 | 30000000
Reliability Upgrade | 1a | 921 | National Grid, USA |  | 01/2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | 2008-01-28 | No | 12100000 | 12100000 | 12100000
Reliability Upgrade | 1a | 919 | National Grid, USA |  | 09/2012 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | 2008-01-28 | No | 4600000 | 4600000 | 4600000
Reliability Upgrade | 1a | 783 | National Grid, USA |  | 03/2011 | Merrimack Valley/North Shore Reliability Project | Extend the 115kV by addition of 115kV Breaker and K-153 line from King St. to W. Amesbury 115kV station. (W. Amesbury 345/115kV Station becomes PTF) | Planned | 2008-04-01 | No | 30349000 | 30349000 | 30349000
Reliability Upgrade | 1a | 840 | NSTAR Electric Company |  | 10/2010 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | 2008-04-01 | No | 7300000 | 7300000 | 7300000
Reliability Upgrade | 1a | 775 | National Grid, USA |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Addition of 4 breakers and relocation of T1 and T2 into new bays at Sandy Pond. | Planned | 2008-06-27 | No | 20100000 | 20100000 | 20100000
Reliability Upgrade | 1a | 776 | National Grid, USA |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | 2008-06-27 | No | 2865876 | 2865876 | 2865876
Reliability Upgrade | 1a | 782 | National Grid, USA |  | 10/2013 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor n Railyard. | Planned | 2008-06-27 | No | 38100000 | 38100000 | 38100000
Reliability Upgrade | 1a | 904 | NSTAR Electric Company |  | 12/2010 | Mystic IPT Breaker Project | Upgrade (5) 115 kV breakers #1, #7, #15 #19 and #20 at Mystic to IPT and separate controls with Boston Gen #4. | Planned | NR | NR | 990000 | 990000 | 990000
Reliability Upgrade | 1a | 59 | National Grid, USA |  | 01/2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | 2007-11-01 | 2003-01-31 | 400000 | 400000 | 400000
Reliability Upgrade | 1a | 929 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | 12/17/2007 | No | 1381849 | 1381849 | 1381849
Reliability Upgrade | 1a | 931 | National Grid, USA |  | 01/2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | 12/17/2007 | No | 531481 | 531481 | 531481
Reliability Upgrade | 1a | 928 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | 12/17/2007 | No | 1945218 | 2300000 | 2300000
Reliability Upgrade | 1a | 934 | National Grid, USA |  | 10/2010 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Planned | 12/17/2007 | No | 818480 | 818480 | 818480
Reliability Upgrade | 1a | 935 | National Grid, USA |  | 07/2010 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Planned | 12/17/2007 | No | 5208509 | 5208509 | 5208509
Reliability Upgrade | 1a | 938 | National Grid, USA |  | 06/2010 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | 12/17/2007 | No | 3068556 | 3068556 | 3068556
Reliability Upgrade | 1a | 939 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Reconductor and retension (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | Planned | 12/17/2007 | No | 3389658 | 3389658 | 3389658
Reliability Upgrade | 1a | 940 | National Grid, USA |  | 04/2011 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS. | Planned | 12/17/2007 | No | 6235744 | 6235744 | 6235744
Reliability Upgrade | 1a | 942 | National Grid, USA |  | 10/2010 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | 12/17/2007 | No | 2767180 | 2767180 | 2767180
Reliability Upgrade | 1a | 927 | National Grid, USA |  | 07/2010 | Central/Western Massachusetts Upgrades | Greendale - replace 115 kV breaker and upgrade to 2000A. | Planned | 12/17/2007 | No | 584629 | 584629 | 584629
Reliability Upgrade | 1a | 925 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | 12/17/2007 | No | 318888 | 318888 | 318888
Reliability Upgrade | 1a | 926 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | 12/17/2007 | No | 6027520 | 6027520 | 6027520
Reliability Upgrade | 1a | 932 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | 12/17/2007 | No | 372036 | 372036 | 372036
Reliability Upgrade | 1a | 924 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | Planned | 12/17/2007 | No | 2147181 | 2147181 | 2147181
Reliability Upgrade | 1a | 941 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Install new Millbury - Tower #510 115 kV line. | Planned | 12/17/2007 | No | 7909203 | 7909203 | 7909203
Reliability Upgrade | 1a | 943 | National Grid, USA |  | 01/2011 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | 12/17/2007 | No | 1073995 | 1073995 | 1073995
Reliability Upgrade | 1a | 944 | National Grid, USA |  | 07/2012 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Planned | 12/17/2007 | No | 11411849 | 11411849 | 11411849
Reliability Upgrade | 1a | 950 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | 12/17/2007 | No | 1016897 | 1016897 | 1016897
Reliability Upgrade | 1a | 953 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | 12/17/2007 | No | 10248067 | 10248067 | 10248067
Reliability Upgrade | 1a | 954 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | E Westminster - install new 115 kV breaker, including disconnect switches. Assumes no new control house. | Planned | 12/17/2007 | No | 903909 | 903909 | 903909
Reliability Upgrade | 1a | 945 | National Grid, USA |  | 02/2013 | Central/Western Massachusetts Upgrades | Adams - install third 115 kV breaker to complete ring bus. | Planned | 12/17/2007 | No | 1581841 | 1584841 | 1584841
Reliability Upgrade | 1a | 946 | National Grid, USA |  | 04/2013 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer - E Longmeadow - Shaker Rd line to 115 kV. | Planned | 12/17/2007 | No | 9604032 | 9604032 | 9604032
Reliability Upgrade | 1a | 947 | National Grid, USA |  | 04/2013 | Central/Western Massachusetts Upgrades | Reconductor 115 kV line from Palmer to new Hampden Substation. | Planned | 12/17/2007 | No | 2632635 | 2632635 | 2632635
Reliability Upgrade | 1a | 948 | National Grid, USA |  | 07/2012 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | 12/17/2007 | No | 5649430 | 5649430 | 5649430
Reliability Upgrade | 1a | 949 | National Grid, USA |  | 07/2012 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | 12/17/2007 | No | 1694829 | 1500000 | 1500000
Reliability Upgrade | 1a | 952 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Reconductor E Winchendon - J136 Tap within I135/J136 ROW w/795 ACSR. | Planned | 12/17/2007 | No | 932156 | 932156 | 932156
Reliability Upgrade | 1a | 937 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | 12/17/2007 | No | 6602875 | 6602875 | 6602875
Reliability Upgrade | 1a | 955 | National Grid, USA |  | 11/2011 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | 12/17/2007 | No | 10779113 | 10779113 | 10779113
Reliability Upgrade | 1a | 1000 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | Planned | 2008-06-27 | No | 22000000 | 22000000 | 22000000
Reliability Upgrade | 1a | 951 | National Grid, USA |  | 02/2013 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon 115 kV line. | Planned | 12/17/2007 | No | 7455440 | 7455440 | 7455440
Reliability Upgrade | 1a | 687 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | 2008-09-24 | No | 714000000 | 714000000 | 714000000
Reliability Upgrade | 1a | 826 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 196 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115kV line South Agawam to Southwick (1768) | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVAR Capacitor additions | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1074 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1076 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Planned | 2008-09-24 | No | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1077 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115kV line | Planned | 2008-09-24 | No | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1078 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 673 | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | 2009-02-27 | No | 2200000 | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Planned | 2009-02-27 | No | 30000000 | 30000000 | 30000000
Reliability Upgrade | 1a | 484 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Planned | 2008-04-25 | No | 690000 | 690000 | 690000
Reliability Upgrade | 1a | 791 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | 2008-04-25 | No | 11560000 | 11560000 | 11560000
Reliability Upgrade | 1a | 913 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | 2008-04-25 | No | 3250000 | 3250000 | 3250000
Reliability Upgrade | 1a | 914 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | 2008-04-25 | No | 28150000 | 28150000 | 28150000
Reliability Upgrade | 1a | 915 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | 2008-04-25 | No | 19450000 | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | 2008-04-25 | No | 11800000 | 11800000 | 11800000
Reliability Upgrade | 1a | 917 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | 2008-04-25 | No | 7000000 | 7000000 | 7000000
Reliability Upgrade | 1a | 918 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | 2008-04-25 | No | 3180000 | 3180000 | 3180000
Reliability Upgrade | 1a | 792 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Admiral St-Franklin Square (Q143 and R144) 115 kV UG recabling. | Planned | 2008-04-25 | No | 39200000 | 39200000 | 39200000
Reliability Upgrade | 1a | 793 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | 2008-04-25 | No | 6400000 | 6400000 | 6400000
Reliability Upgrade | 1a | 786 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Terminal upgrades at Drumrock, Chartley Pond, and Brayton Point. | Planned | 2008-04-25 | No | 565000 | 1000000 | 1000000
Reliability Upgrade | 1a | 787 | National Grid, USA |  | 12/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | West Farnum breaker replacements. | Planned | 2008-04-25 | No | 7631000 | 7631000 | 7631000
Reliability Upgrade | 1a | 788 | National Grid, USA |  | 06/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Kent County substation expansion. | Planned | 2008-04-25 | No | 42300000 | 42300000 | 42300000
Reliability Upgrade | 1a | 789 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Reconductoring of T7 115 kV line. | Planned | 2008-04-25 | No | 23304000 | 23304000 | 23304000
Reliability Upgrade | 1a | 790 | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Planned | 2008-04-25 | No | 50600000 | 50600000 | 50600000
Reliability Upgrade | 1a | 1098 | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Planned | 2008-04-25 | No | 37529000 | 37529000 | 37529000
Reliability Upgrade | 1a | 190 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | 2008-09-24 | No | 69600000 | 69600000 | 69600000
Reliability Upgrade | 1a | 1094 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | 2008-09-24 | No | 20800000 | 25000000 | 25000000
Reliability Upgrade | 1a | 1095 | National Grid, USA |  | 06/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | 2008-09-24 | No | 73800000 | 73800000 | 73800000
Reliability Upgrade | 1a | 794 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | 2008-09-24 | No | 55800000 | 55800000 | 55800000
Reliability Upgrade | 1a | 796 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | 347 Reconductor from Sherman Road to CT/RI Border. | Planned | 2008-09-24 | No | 16400000 | 16400000 | 16400000
Reliability Upgrade | 1a | 797 | National Grid, USA |  | 12/2012 | NEEWS (Interstate Reliability Project) | 3361 Upgrade 345kV terminal equipment at Sherman Road. | Planned | 2008-09-24 | No | 8300000 | 8300000 | 8300000
Reliability Upgrade | 1a | 795 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV line. | Planned | 2008-09-24 | No | 99900000 | 99900000 | 99900000
Reliability Upgrade | 1a | 1106 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | Planned | 2008-09-24 | No | Part of $99,900,000 above | Part of $99,900,000 above | Part of $99,900,000 above
Reliability Upgrade | 1a | 798 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Planned | 2008-09-24 | No | 4900000 | 4900000 | 4900000
Reliability Upgrade | 1a | 799 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | Planned | 2008-09-24 | No | 4500000 | 4500000 | 4500000
Reliability Upgrade | 1a | 1096 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | 2008-09-24 | No | 5800000 | 12000000 | 12000000
Reliability Upgrade | 1a | 800 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S, T-172N and T-172S with associated terminal equipment upgrades. | Planned | 2008-09-24 | No | 7300000 | 10000000 | 10000000
Reliability Upgrade | 1a | 1097 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County | Planned | 2008-09-24 | No | 129800000 | 129800000 | 129800000
Reliability Upgrade | 1a | 1099 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | 2008-09-24 | No | 4100000 | 6000000 | 6000000
Reliability Upgrade | 1a | 1109 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Planned | 2008-09-24 | No | 360000 | 1000000 | 1000000
Reliability Upgrade | 1a | 1152 | National Grid, USA |  | 2010-08-01 |  | E205E Refurbishment Project | Planned | NR | NR |  | 43596000 | 43596000
Reliability Upgrade | 1a | 1049 | United Illuminating Company |  | 12/2010 |  | East Shore 115 kV Capacitor Bank Transient Recovery | Planned | NR | NR | 3000000 | 3000000 | 3000000
Reliability Upgrade | 1a | 582 | Northeast Utilities |  | 12/2010 |  | Separate 310 and 368 345-KV lines and create 368/1767 DCT | Planned | 2008-07-18 | No | 16000000 | 16000000 | 16000000
Reliability Upgrade | 1a | 1112 | United Illuminating Company |  | 12/2010 |  | Water Street 115kV circuit breaker and switch replacements. | Planned | NR | NR | 1000000 | 1000000 | 1000000
Reliability Upgrade | 1a | 974 | United Illuminating Company |  | 12/2011 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Planned | NR | No | 6700000 | 6700000 | 6700000
Reliability Upgrade | 1a | 816 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1054 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Manchester - Meekvile Jct. line (395/1448) separation. | Planned | 2008-09-24 | No | 14000000 | 14000000 | 14000000
Reliability Upgrade | 1a | 576 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | 2008-09-24 | No | 313000000 | 313000000 | 313000000
Reliability Upgrade | 1a | 1114 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | 2008-09-24 | No | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1a | 814 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Central Connecticut Relaibility Project) | Reconductor a portion of the Manchester to Scovill Rock 353 345-kV line and terminal work. | Planned | 2008-09-24 | No | 9000000 | 9000000 | 9000000
Reliability Upgrade | 1a | 802 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | 2008-09-24 | No | 251000000 | 251000000 | 251000000
Reliability Upgrade | 1a | 1084 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Loop the Millstone - Manchester (310) 345 kV line into the Card substation. | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1085 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1086 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1087 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1088 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1089 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Killingly 3G substation 345kV breaker addition | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1090 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Millstone 15G substation breaker 14T upgrade 50kA | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1091 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Southington 4C substation breaker 19T upgrade to 63kA | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | Northeast Utilities | National Grid, USA | 12/2013 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 807 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Interstate Reliability Project) | Install 480 MVAR's of capacitors at the Montville 345 kV substation | Planned | 2008-09-24 | No | 33000000 | 33000000 | 33000000
Reliability Upgrade | 1a | 1092 | Northeast Utilities |  | 12/2013 | NEEWS (BPS) 2 | Upgrade the Card 115 kV, East Hartford 115 kV, Agawam 115 kV, Barbour Hill 115 kV, and North Bloomfield 345 kV Substations to BPS standards. | Planned | 2008-09-24 | No | 37000000 | 37000000 | 37000000
Reliability Upgrade | 1a | 1056 | Northeast Utilities |  | 12/2011 | CT LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Planned | 2008-12-12 | No | 9751000 | 9751000 | 9751000
Reliability Upgrade | 1a | 1110 | United Illuminating Company |  | 12/2010 |  | Broadway 115/13.8 kV Substation Additon | Planned | 2008-12-08 | No | 1200000 | 1200000 | 1200000
Reliability Upgrade | 1a | 1111 | United Illuminating Company |  | 12/2010 |  | Metro North Union Avenue 115/26.4 kV Substation | Planned | 2009-01-07 | No | 10543000 | 10543000 | 10543000
Reliability Upgrade | 1a | 976 | United Illuminating Company |  | 05/2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Planned | 2009-01-07 | No | 48000000 | 48000000 | 48000000
Reliability Upgrade | 1a | 879 |  | Bangor Hydro-Electric Company, New England Power Company, Northeast Utilities System Com | TBD | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | 03/01/2007 | NR | 420000 | 420000 | 420000
Reliability Upgrade | 1a | 1050 | United Illuminating Company |  | 12/2011 |  | Devon Tie 115kV Switching Station BPS Compliance | Planned | NR | NR | 2620000 | 2620000 | 2620000 | -25% | 25%
[13 empty] | 4385548029 | 3289161021.75 | 5481935036.25 | 156
Reliability Upgrade | 1b | 148 | Central Maine Power Company |  | 06/2012 | CMP LSP - Saco Bay Area Reinforcement Project | Establish a new Vallee Lane 115/34.5 kV substation and 115 kV line from Louden S/S to Vallee Lane Substation. | Proposed | No | NR | 100000 | 100000 | 100000
Reliability Upgrade | 1b | 1130 | Central Maine Power Company |  | 12/2011 | Sturtevant Improvements | Add 115kV circuit breakers & 25 MVAR capacitor bank at Sturtevant Substation; Re-rate Section 63 between Wyman Hydro & Madison Substation | Proposed | No | No | 3000000 | 3000000 | 3000000
Reliability Upgrade | 1b | 1131 | Central Maine Power Company |  | 12/2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Proposed | No | NR | 600000 | 600000 | 600000
Reliability Upgrade | 1b | 1132 | Central Maine Power Company |  | 12/2011 | CMP-LSP Maxcy's Substation | Add 115/34kV transformer (coordinate with MPRP) | Proposed | No | NR | 600000 | 600000 | 600000
Reliability Upgrade | 1b | 1133 | Central Maine Power Company |  | 10/2010 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation & new 34kV line from Leeds to Turner | Proposed | No | NR | 300000 | 300000 | 300000
Reliability Upgrade | 1b | 1135 | Central Maine Power Company |  | TBD | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer | Proposed | No | No | 1500000 | 1500000 | 1500000
Reliability Upgrade | 1b | 1143 | Northeast Utilities |  | TBD |  | Littleton 115kV breaker addition and reconfiguration | Proposed | No | No | 5338000 | 5338000 | 5338000
Reliability Upgrade | 1b | 963 | NSTAR Electric Company |  | 12/2009 | Boston Area 115 kV Enhancements | Add a new 115kV breaker # 11 Relocate 447-509 and add control and protect at Holbrook. | Proposed | No | No | 4000000 | 4000000 | 4000000
Reliability Upgrade | 1b | 842 | NSTAR Electric Company |  | 06/2010 | Boston Area 115 kV Enhancements | Add 115 kV 54 MVAR capacitor bank at W. Framingham. | Proposed | No | No | 3000000 | 3700000 | 3700000
Reliability Upgrade | 1b | 964 | NSTAR Electric Company |  | 06/2011 | Boston Area 115 kV Enhancements | Relocate 115kV terminals at W. Walpole to mitigate breaker failure #8. | Proposed | No | No | 5600000 | 5600000 | 5600000
Reliability Upgrade | 1b | 1113 | NSTAR Electric Company |  | 12/2010 |  | Install KSt Breaker #31 | Proposed | No | No | 2100000 | 2960000 | 2960000
Reliability Upgrade | 1b | 1068 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to Sandwich and a a 345-115kV auto-transformer at Sandwich | Proposed | No | No | 110000000 | 110000000 | 110000000
Reliability Upgrade | 1b | 592 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing | Proposed | No | No | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1118 | NSTAR Electric Company | National Grid, USA | 12/2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 | Proposed | No | No | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1067 | NSTAR Electric Company |  | 12/2010 | NPCC BPS Compliance | Tremont Station | Proposed | No | No | 11200000 | 12800000 | 12800000
Reliability Upgrade | 1b | 1065 | NSTAR Electric Company |  | 07/2012 | NPCC BPS Compliance | Waltham Station | Proposed | No | No | 24300000 | 26600000 | 26600000
Reliability Upgrade | 1b | 1119 | NSTAR Electric Company |  | 12/2010 | Greater Boston Reliability Project | Upgrade West Medway-West Walpole 345kV line #325 | Proposed | No | No | 2200000 | 2200000 | 2200000
Reliability Upgrade | 1b | 1120 | NSTAR Electric Company |  | 06/2010 |  | Install 345kV 160 MVAR shunt ractor at W. Walpole | Proposed | No | No | 7200000 | 7200000 | 7200000
Reliability Upgrade | 1b | 1136 | National Grid, USA |  | 12/2012 |  | New 115kV Switching Station at Devens Convert 69kV lines to 115kV, Reconfigure 115kV Supply at Ayer Substation | Proposed | 2009-07-28 | No | 9200000 | 9200000 | 9200000
Reliability Upgrade | 1b | 809 | Northeast Utilities |  | 12/2009 |  | Upgrade terminal equipment at Bunker Hill 115 kV substation. | Proposed | No | No | 1000000 | 1000000 | 1000000
Reliability Upgrade | 1b | 1150 | United Illuminating Company |  | 10/2011 |  | Grand Avenue - West River 115 kV Pumping Plant Replacements | Proposed | NR | NR |  | 1200000 | 1200000
Reliability Upgrade | 1b | 1151 | United Illuminating Company |  | 12/2011 |  | West River 115kV Switching Station Fault Duty Migration | Proposed | NR | NR |  | 3500000 | 3500000
Reliability Upgrade | 1b | 721 | United Illuminating Company |  | 06/2013 |  | New Shelton 115/13.8 kV substation | Proposed | No | No | 11300000 | 11300000 | 11300000
Reliability Upgrade | 1b | 1147 | Northeast Utilities |  | 2011 |  | Waterside Substation - install a three-breaker 115kV ring bus | Proposed | No | No |  | 4000000 | 4000000
Reliability Upgrade | 1b | 1148 | Northeast Utilities |  | 2011 |  | Add a 2nd high speed relay on the Glennbrook to Waterside 115kV 1440 | Proposed | No | No |  | 600000 | 600000 | -25% | 25%
[13 empty] | 217298000 | 162973500 | 271622500 | 25
Reliability Upgrade | 1a | 144 | Bangor Hydro-Electric Company |  | 12/2010 | Keene Rd Autotransformer | Installation of a 345/115 kV autotransformer at Keene Rd Substation. | Under Construction | No | No | 29000000 | 29000000 | 29000000
Reliability Upgrade | 1a | 625 | Central Maine Power Company |  | 02/2010 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Rumford Industrial Park capacitor bank. | Under Construction | 2007-11-30 | No | 5400000 | 5400000 | 5400000
Reliability Upgrade | 1a | 1029 | Central Maine Power Company |  | 11/2010 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformer at South Gorham | Under Construction | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1144 | Central Maine Power Company |  | 04/2010 | Heywood Road Project | Circuit switcher replacements at Detroit, Lakewood, Rice Rips and Winslow | Under Construction | 2009-03-20 | 2009-07-20 | Part of Heywood Road Project | Part of Heywood Road Project | Part of the Heywood Road Project
Reliability Upgrade | 1a | 320 | Vermont Electric Power Company |  | 10/2009 | Lamoille County Project | Middlesex Substation 115 kV breaker addition. | Under Construction | 08/16/2007 | 02/07/2008 | 4857000 | 4857000 | 4857000
Reliability Upgrade | 1a | 322 | Vermont Electric Power Company |  | 10/2009 | Lamoille County Project | Installation of new Duxbury Substation that involves looping in and out of the Middlesex - Essex 115 kV (K24) line. | Under Construction | 08/16/2007 | 02/07/2008 | Part of Lamoille County Project | Part of Lamoille County Project | Part of Lamoille County Project
Reliability Upgrade | 1a | 321 | Vermont Electric Power Company |  | 12/2009 | Burlington Project | Burlington 115kV Loop - 5 mi of new line & rebuilding 5 miles of existing line between two existing substations with expansion of the East Avenue substation. | Under Construction | 10/24/2006 | 05/23/2007 | 25142000 | 25142000 | 25142000
Reliability Upgrade | 1a | 323 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | New VY - Newfane - Coolidge 345 kV line with requisite station upgrades. | Under Construction | 2008-10-01 | No | 136368000 | 136368000 | 136368000
Reliability Upgrade | 1a | 1032 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Installation of a new 345/115kV substation called Vernon including a new 345/115kV autotransformer | Under Construction | 2008-10-01 | No | 69815000 | 69815000 | 69815000
Reliability Upgrade | 1a | 1033 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project (VELCO LSP - Newfane Substation) | Installation of a new 345/115kV substation called Newfane | Under Construction | 2008-10-01 | No | 16664000 | 16664000 | 16664000
Reliability Upgrade | 1a | 1034 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Loop new 345kV Line into Newfane Substation. | Under Construction | 2008-10-01 | No | Part of project 323 | Part of project 323 | Part of project 323
Reliability Upgrade | 1a | 1035 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Expansion of Coolidge 345kV substation | Under Construction | 2008-10-01 | No | 20117000 | 20117000 | 20117000
Reliability Upgrade | 1a | 1063 | NSTAR Electric Company |  | 12/2009 |  | Install (2) 115kV 40 MVAR shunt reactors at Edgar Station | Under Construction | 05/2009 | No | 5400000 | 5400000 | 5400000
Reliability Upgrade | 1a | 777 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Build Wakefield Junction station with four 345/115 kV autotransformers. | Under Construction | 2008-04-01 | No | 95000000 | 95000000 | 95000000
Reliability Upgrade | 1a | 161 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Loop 345 kV 339 line and 115 kV S-145/T-146 into new Wakefield Jct. Substation. | Under Construction | 2008-04-01 | No | 4986431 | 4986431 | 4986431
Reliability Upgrade | 1a | 779 | National Grid, USA |  | 04/2010 | Merrimack Valley/North Shore Reliability Project | Bypass and remove Golden Hills 345 kV substation. | Under Construction | 2008-04-01 | No | 5132609 | 5132609 | 5132609
Reliability Upgrade | 1a | 961 | NSTAR Electric Company |  | 11/2010 | Mystic Breaker Additions Project | Install (2) new 115 kV East Bus breakers #30 and #32 at Mystic and move Transformer 110B Connection. | Under Construction | 2008-03-10 | No | 3800000 | 3800000 | 3800000
Reliability Upgrade | 1a | 903 | NSTAR Electric Company |  | 12/2009 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #2, #4, #5, and #16 at Mystic to IPT and separate controls with Boston Gen units #5 and #6. | Under Construction | NR | NR | 1240000 | 1240000 | 1240000
Reliability Upgrade | 1a | 930 | National Grid, USA |  | 12/2009 | Central/Western Massachusetts Upgrades | Reconductor Nashua St - Quinsigamond Jct (O141) 115 kV line w/636 ACSS. | Under Construction | 12/17/2007 | No | 2300000 | 2300000 | 2300000
Reliability Upgrade | 1a | 933 | National Grid, USA |  | 12/2009 | Central/Western Massachusetts Upgrades | Reconductor Pratts Jct - Flagg Pond I-135S & J-136S 115 kV lines w/795 ACSS. | Under Construction | 12/17/2007 | No | 6137112 | 6137112 | 6137112
Reliability Upgrade | 1a | 162 | National Grid, USA |  | 04/2011 |  | Q-169 Golden Hills to Lynn 115 kV line upgrade. | Under Construction | 2005-09-02 | 2008-04-25 | 12390000 | 12390000 | 12390000
Reliability Upgrade | 1a | 902 | National Grid, USA |  | 03/2012 | Middleboro Municipal | Close the E1-M1 loop at Middleboro's Wareham St Sub. | Under Construction | 12/01/2006 | NR | 715000 | 715000 | 715000
Reliability Upgrade | 1a | 211 | Northeast Utilities |  | 11/2009 | NU LSP - Rood Ave Substation | New Rood Ave (formally Windsor) distribution substation with 115kV terminal modifications. | Under Construction | 2008-04-25 | 02/15/2008 | 9162029 | 9162029 | 9162029 | -10% | 10%
[13 empty] | 453626181 | 408263562.9 | 498988799.1 | 23
[12 empty] | GRAND TOTAL | 5255330744 | 3796853851.4 | 6849121937.35 | 228
[14 empty] | 99429267 | 596575602 | 24

## Sorted by ISD then status 10-09 (hidden)
October '09 ISO-NEW ENGLAND Project Listing Update (DRAFT)
Primary Driver | Part# | Project ID | Primary Equipment Owner | Projected In-Service Month/Year |  | Major Project | Project | Oct-09 Status | Oct-09 Estimated PTF Costs | Column T
Reliability Upgrade | 1b | 963 | NSTAR Electric Company | 12/2009 | 2009 | Boston Area 115 kV Enhancements | Add a new 115kV breaker # 11 Relocate 447-509 and add control and protect at Holbrook. | Proposed | 4000000 | 4000000
Reliability Upgrade | 1b | 809 | Northeast Utilities | 12/2009 | 2009 |  | Upgrade terminal equipment at Bunker Hill 115 kV substation. | Proposed | 1000000 | 1000000
Reliability Upgrade | 1a | 320 | Vermont Electric Power Company | 10/2009 | 2009 | Lamoille County Project | Middlesex Substation 115 kV breaker addition. | Under Construction | 4857000 | 4857000
Reliability Upgrade | 1a | 322 | Vermont Electric Power Company | 10/2009 | 2009 | Lamoille County Project | Installation of new Duxbury Substation that involves looping in and out of the Middlesex - Essex 115 kV (K24) line. | Under Construction | Part of Lamoille County Project | Part of Lamoille County Project
Reliability Upgrade | 1a | 321 | Vermont Electric Power Company | 12/2009 | 2009 | Burlington Project | Burlington 115kV Loop - 5 mi of new line & rebuilding 5 miles of existing line between two existing substations with expansion of the East Avenue substation. | Under Construction | 25142000 | 25142000
Reliability Upgrade | 1a | 1063 | NSTAR Electric Company | 12/2009 | 2009 |  | Install (2) 115kV 40 MVAR shunt reactors at Edgar Station | Under Construction | 5400000 | 5400000
Reliability Upgrade | 1a | 777 | National Grid, USA | 11/2009 | 2009 | Merrimack Valley/North Shore Reliability Project | Build Wakefield Junction station with four 345/115 kV autotransformers. | Under Construction | 95000000 | 95000000
Reliability Upgrade | 1a | 161 | National Grid, USA | 11/2009 | 2009 | Merrimack Valley/North Shore Reliability Project | Loop 345 kV 339 line and 115 kV S-145/T-146 into new Wakefield Jct. Substation. | Under Construction | 4986431 | 4986431
Reliability Upgrade | 1a | 903 | NSTAR Electric Company | 12/2009 | 2009 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #2, #4, #5, and #16 at Mystic to IPT and separate controls with Boston Gen units #5 and #6. | Under Construction | 1240000 | 1240000
Reliability Upgrade | 1a | 930 | National Grid, USA | 12/2009 | 2009 | Central/Western Massachusetts Upgrades | Reconductor Nashua St - Quinsigamond Jct (O141) 115 kV line w/636 ACSS. | Under Construction | 2300000 | 2300000
Reliability Upgrade | 1a | 933 | National Grid, USA | 12/2009 | 2009 | Central/Western Massachusetts Upgrades | Reconductor Pratts Jct - Flagg Pond I-135S & J-136S 115 kV lines w/795 ACSS. | Under Construction | 6137112 | 6137112
Reliability Upgrade | 1a | 211 | Northeast Utilities | 11/2009 | 2009 | NU LSP - Rood Ave Substation | New Rood Ave (formally Windsor) distribution substation with 115kV terminal modifications. | Under Construction | 9162029 | 9162029
Reliability Upgrade | 1b | 1153 | NSTAR Electric Company | 06/2010 | 2010 | Boston Area 115 kV Enhancements | Reliability Upgrades at West Framingham Station | Concept | 3000000 | 3000000
Reliability Upgrade | 1b | 1055 | Northeast Utilities | 2010 | 2010 | CT LSP - Waterside Substation | Waterside Substation - add a 115/13.2-kV transformer and a 115-kV circuit breaker. | Concept | 4107000 | 4107000
Reliability Upgrade | 1a | 1128 | Central Maine Power Company | 07/2010 | 2010 | CMP-LSP Hotel Road Substation | Add 115/34kV transformer with 115kV breaker at Hotel Rd. | Planned | 800000 | 800000
Reliability Upgrade | 1a | 624 | Central Maine Power Company | 2010 | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (New Page - Rumford Industrial Park) | Planned | Part of project 625 | Part of project 625
Reliability Upgrade | 1a | 139 | Vermont Electric Power Company | 12/2010 | 2010 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Planned | 20000000 | 20000000
Reliability Upgrade | 1a | 840 | NSTAR Electric Company | 10/2010 | 2010 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | 7300000 | 7300000
Reliability Upgrade | 1a | 904 | NSTAR Electric Company | 12/2010 | 2010 | Mystic IPT Breaker Project | Upgrade (5) 115 kV breakers #1, #7, #15 #19 and #20 at Mystic to IPT and separate controls with Boston Gen #4. | Planned | 990000 | 990000
Reliability Upgrade | 1a | 928 | National Grid, USA | 12/2010 | 2010 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | 2300000 | 2300000
Reliability Upgrade | 1a | 934 | National Grid, USA | 10/2010 | 2010 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Planned | 818480 | 818480
Reliability Upgrade | 1a | 935 | National Grid, USA | 07/2010 | 2010 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Planned | 5208509 | 5208509
Reliability Upgrade | 1a | 938 | National Grid, USA | 06/2010 | 2010 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | 3068556 | 3068556
Reliability Upgrade | 1a | 942 | National Grid, USA | 10/2010 | 2010 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | 2767180 | 2767180
Reliability Upgrade | 1a | 927 | National Grid, USA | 07/2010 | 2010 | Central/Western Massachusetts Upgrades | Greendale - replace 115 kV breaker and upgrade to 2000A. | Planned | 584629 | 584629
Reliability Upgrade | 1a | 484 | National Grid, USA | 11/2010 | 2010 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Planned | 690000 | 690000
Reliability Upgrade | 1a | 786 | National Grid, USA | 11/2010 | 2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Terminal upgrades at Drumrock, Chartley Pond, and Brayton Point. | Planned | 1000000 | 1000000
Reliability Upgrade | 1a | 787 | National Grid, USA | 12/2010 | 2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | West Farnum breaker replacements. | Planned | 7631000 | 7631000
Reliability Upgrade | 1a | 789 | National Grid, USA | 11/2010 | 2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Reconductoring of T7 115 kV line. | Planned | 23304000 | 23304000
Reliability Upgrade | 1a | 1152 | National Grid, USA | 2010-08-01 | 2010 |  | E205E Refurbishment Project | Planned | 43596000 | 43596000
Reliability Upgrade | 1a | 1049 | United Illuminating Company | 12/2010 | 2010 |  | East Shore 115 kV Capacitor Bank Transient Recovery | Planned | 3000000 | 3000000
Reliability Upgrade | 1a | 582 | Northeast Utilities | 12/2010 | 2010 |  | Separate 310 and 368 345-KV lines and create 368/1767 DCT | Planned | 16000000 | 16000000
Reliability Upgrade | 1a | 1112 | United Illuminating Company | 12/2010 | 2010 |  | Water Street 115kV circuit breaker and switch replacements. | Planned | 1000000 | 1000000
Reliability Upgrade | 1a | 1110 | United Illuminating Company | 12/2010 | 2010 |  | Broadway 115/13.8 kV Substation Additon | Planned | 1200000 | 1200000
Reliability Upgrade | 1a | 1111 | United Illuminating Company | 12/2010 | 2010 |  | Metro North Union Avenue 115/26.4 kV Substation | Planned | 10543000 | 10543000
Reliability Upgrade | 1b | 1133 | Central Maine Power Company | 10/2010 | 2010 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation & new 34kV line from Leeds to Turner | Proposed | 300000 | 300000
Reliability Upgrade | 1b | 842 | NSTAR Electric Company | 06/2010 | 2010 | Boston Area 115 kV Enhancements | Add 115 kV 54 MVAR capacitor bank at W. Framingham. | Proposed | 3700000 | 3700000
Reliability Upgrade | 1b | 1113 | NSTAR Electric Company | 12/2010 | 2010 |  | Install KSt Breaker #31 | Proposed | 2960000 | 2960000
Reliability Upgrade | 1b | 1067 | NSTAR Electric Company | 12/2010 | 2010 | NPCC BPS Compliance | Tremont Station | Proposed | 12800000 | 12800000
Reliability Upgrade | 1b | 1119 | NSTAR Electric Company | 12/2010 | 2010 | Greater Boston Reliability Project | Upgrade West Medway-West Walpole 345kV line #325 | Proposed | 2200000 | 2200000
Reliability Upgrade | 1b | 1120 | NSTAR Electric Company | 06/2010 | 2010 |  | Install 345kV 160 MVAR shunt ractor at W. Walpole | Proposed | 7200000 | 7200000
Reliability Upgrade | 1a | 144 | Bangor Hydro-Electric Company | 12/2010 | 2010 | Keene Rd Autotransformer | Installation of a 345/115 kV autotransformer at Keene Rd Substation. | Under Construction | 29000000 | 29000000
Reliability Upgrade | 1a | 625 | Central Maine Power Company | 02/2010 | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Rumford Industrial Park capacitor bank. | Under Construction | 5400000 | 5400000
Reliability Upgrade | 1a | 1029 | Central Maine Power Company | 11/2010 | 2010 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformer at South Gorham | Under Construction | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1144 | Central Maine Power Company | 04/2010 | 2010 | Heywood Road Project | Circuit switcher replacements at Detroit, Lakewood, Rice Rips and Winslow | Under Construction | Part of Heywood Road Project | Part of the Heywood Road Project
Reliability Upgrade | 1a | 779 | National Grid, USA | 04/2010 | 2010 | Merrimack Valley/North Shore Reliability Project | Bypass and remove Golden Hills 345 kV substation. | Under Construction | 5132609 | 5132609
Reliability Upgrade | 1a | 961 | NSTAR Electric Company | 11/2010 | 2010 | Mystic Breaker Additions Project | Install (2) new 115 kV East Bus breakers #30 and #32 at Mystic and move Transformer 110B Connection. | Under Construction | 3800000 | 3800000
Reliability Upgrade | 1b | 1116 | Bangor Hydro-Electric Company | 12/2011 | 2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Concept | TBD | TBD
Reliability Upgrade | 1b | 318 | Vermont Electric Power Company | 12/2011 | 2011 |  | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems through the 1,250 MW Vermont state load level. | Concept | 9000000 | 9000000
Reliability Upgrade | 1b | 325 | Vermont Electric Power Company | 12/2011 | 2011 | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | 5000000 | 5000000
Reliability Upgrade | 1b | 301 | NSTAR Electric Company | 12/2011 | 2011 | Boston Area 115 kV Enhancements | Reconductor 115-kV circuits 320-507 and 320-508. | Concept | 4600000 | 4600000
Reliability Upgrade | 1b | 1066 | NSTAR Electric Company | 09/2011 | 2011 | NPCC BPS Compliance | Needham Station | Concept | 9300000 | 9300000
Reliability Upgrade | 1a | 1145 | Vermont Electric Power Company | 09/2011 | 2011 | Burlington Project | Installation of a 3-breaker 115kV ring substation and 115/34.5kV transformer on the East Ave. - Tafts Coners 115kV line | Planned | 14000000 | 14000000
Reliability Upgrade | 1a | 783 | National Grid, USA | 03/2011 | 2011 | Merrimack Valley/North Shore Reliability Project | Extend the 115kV by addition of 115kV Breaker and K-153 line from King St. to W. Amesbury 115kV station. (W. Amesbury 345/115kV Station becomes PTF) | Planned | 30349000 | 30349000
Reliability Upgrade | 1a | 929 | National Grid, USA | 06/2011 | 2011 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | 1381849 | 1381849
Reliability Upgrade | 1a | 939 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor and retension (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | Planned | 3389658 | 3389658
Reliability Upgrade | 1a | 940 | National Grid, USA | 04/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS. | Planned | 6235744 | 6235744
Reliability Upgrade | 1a | 925 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | 318888 | 318888
Reliability Upgrade | 1a | 926 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | 6027520 | 6027520
Reliability Upgrade | 1a | 932 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | 372036 | 372036
Reliability Upgrade | 1a | 924 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | Planned | 2147181 | 2147181
Reliability Upgrade | 1a | 941 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Install new Millbury - Tower #510 115 kV line. | Planned | 7909203 | 7909203
Reliability Upgrade | 1a | 943 | National Grid, USA | 01/2011 | 2011 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | 1073995 | 1073995
Reliability Upgrade | 1a | 952 | National Grid, USA | 06/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor E Winchendon - J136 Tap within I135/J136 ROW w/795 ACSR. | Planned | 932156 | 932156
Reliability Upgrade | 1a | 937 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | 6602875 | 6602875
Reliability Upgrade | 1a | 955 | National Grid, USA | 11/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | 10779113 | 10779113
Reliability Upgrade | 1a | 1000 | Northeast Utilities | 12/2011 | 2011 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | Planned | 22000000 | 22000000
Reliability Upgrade | 1a | 1076 | Northeast Utilities | 12/2011 | 2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Planned | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1077 | Northeast Utilities | 12/2011 | 2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115kV line | Planned | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 788 | National Grid, USA | 06/2011 | 2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Kent County substation expansion. | Planned | 42300000 | 42300000
Reliability Upgrade | 1a | 790 | National Grid, USA | 12/2011 | 2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Planned | 50600000 | 50600000
Reliability Upgrade | 1a | 1098 | National Grid, USA | 12/2011 | 2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Planned | 37529000 | 37529000
Reliability Upgrade | 1a | 974 | United Illuminating Company | 12/2011 | 2011 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Planned | 6700000 | 6700000
Reliability Upgrade | 1a | 1056 | Northeast Utilities | 12/2011 | 2011 | CT LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Planned | 9751000 | 9751000
Reliability Upgrade | 1a | 1050 | United Illuminating Company | 12/2011 | 2011 |  | Devon Tie 115kV Switching Station BPS Compliance | Planned | 2620000 | 2620000
Reliability Upgrade | 1b | 1130 | Central Maine Power Company | 12/2011 | 2011 | Sturtevant Improvements | Add 115kV circuit breakers & 25 MVAR capacitor bank at Sturtevant Substation; Re-rate Section 63 between Wyman Hydro & Madison Substation | Proposed | 3000000 | 3000000
Reliability Upgrade | 1b | 1131 | Central Maine Power Company | 12/2011 | 2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Proposed | 600000 | 600000
Reliability Upgrade | 1b | 1132 | Central Maine Power Company | 12/2011 | 2011 | CMP-LSP Maxcy's Substation | Add 115/34kV transformer (coordinate with MPRP) | Proposed | 600000 | 600000
Reliability Upgrade | 1b | 964 | NSTAR Electric Company | 06/2011 | 2011 | Boston Area 115 kV Enhancements | Relocate 115kV terminals at W. Walpole to mitigate breaker failure #8. | Proposed | 5600000 | 5600000
Reliability Upgrade | 1b | 1150 | United Illuminating Company | 10/2011 | 2011 |  | Grand Avenue - West River 115 kV Pumping Plant Replacements | Proposed | 1200000 | 1200000
Reliability Upgrade | 1b | 1151 | United Illuminating Company | 12/2011 | 2011 |  | West River 115kV Switching Station Fault Duty Migration | Proposed | 3500000 | 3500000
Reliability Upgrade | 1b | 1147 | Northeast Utilities | 2011 | 2011 |  | Waterside Substation - install a three-breaker 115kV ring bus | Proposed | 4000000 | 4000000
Reliability Upgrade | 1b | 1148 | Northeast Utilities | 2011 | 2011 |  | Add a 2nd high speed relay on the Glennbrook to Waterside 115kV 1440 | Proposed | 600000 | 600000
Reliability Upgrade | 1a | 323 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project | New VY - Newfane - Coolidge 345 kV line with requisite station upgrades. | Under Construction | 136368000 | 136368000
Reliability Upgrade | 1a | 1032 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project | Installation of a new 345/115kV substation called Vernon including a new 345/115kV autotransformer | Under Construction | 69815000 | 69815000
Reliability Upgrade | 1a | 1033 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project (VELCO LSP - Newfane Substation) | Installation of a new 345/115kV substation called Newfane | Under Construction | 16664000 | 16664000
Reliability Upgrade | 1a | 1034 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project | Loop new 345kV Line into Newfane Substation. | Under Construction | Part of project 323 | Part of project 323
Reliability Upgrade | 1a | 1035 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project | Expansion of Coolidge 345kV substation | Under Construction | 20117000 | 20117000
Reliability Upgrade | 1a | 162 | National Grid, USA | 04/2011 | 2011 |  | Q-169 Golden Hills to Lynn 115 kV line upgrade. | Under Construction | 12390000 | 12390000
Reliability Upgrade | 1b | 1031 | Bangor Hydro-Electric Company | 01/2012 | 2012 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station, Rebuild Line 66, and Capacitior Bank Additions (10MVAr at Trenton, Downeast & Handcock County area) | Concept | TBD | TBD
Reliability Upgrade | 1b | 324 | Vermont Electric Power Company | 12/2012 | 2012 |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | 100000000 | 100000000
Reliability Upgrade | 1b | 965 | NSTAR Electric Company | 12/2012 | 2012 | Boston Area 115 kV Enhancements | Add third 115kV line from Walpole to Holbrook | Concept | TBD | TBD
Reliability Upgrade | 1b | 970 | NSTAR Electric Company | 12/2012 | 2012 | Greater Boston Reliability Project | Add a new 345 kV line from Lexington to Waltham. | Concept | TBD | TBD
Reliability Upgrade | 1b | 971 | NSTAR Electric Company | 12/2012 | 2012 | Greater Boston Reliability Project | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | TBD | TBD
Reliability Upgrade | 1b | 699 | United Illuminating Company | 12/2012 | 2012 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | 10000000 | 10000000
Reliability Upgrade | 1a | 905 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Planned | 1510000000 | 1510000000
Reliability Upgrade | 1a | 906 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Coopers Mills-Highland, Larrabee Road-Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 907 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 84 (Albion Road-Coopers Mills), Section 203 (Detroit-Orrington), Section 80 (Coopers Mills-Highland), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 908 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377 & Maine Yankee 375/392, 115kV Bucksport 65/205) and Maine Yankee 345 kV re-termination | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1026 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Three Rivers) | Planned | Portion of CMP $1.51B and portion of NU is $35.1M | 35100000
Reliability Upgrade | 1a | 1027 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 115kV Line Construction (Elm Street-East Deering, East Deering -Cape) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1028 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD
Reliability Upgrade | 1a | 1030 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Raven Farm, Maguire Road) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 143 | Bangor Hydro-Electric Company | 12/2012 | 2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation to Harrington Substation. | Planned | 66100000 | 66100000
Reliability Upgrade | 1a | 1129 | Central Maine Power Company | 05/2012 | 2012 |  | New 115kV line between Wyman Hydro and Heywood Rd. parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | 19500000 | 19500000
Reliability Upgrade | 1a | 277 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Planned | 56600000 | 56600000
Reliability Upgrade | 1a | 1137 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115kV breakers and add 1-115kV breaker at Deerfield Substation | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1138 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rebuild 115kV L175 line | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1139 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV M183 Line | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1140 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1141 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 680 | National Grid, USA | 09/2012 | 2012 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | 7393000 | 7393000
Reliability Upgrade | 1a | 1146 | Vermont Electric Power Company | 12/2012 | 2012 | Lyndonville Project | Installation of a 3-breaker 115kV righ station consisting of two 115kV 12.5 MVAR capacitor banks and 115/34.5 kV transformer interconnecting to the Irasburg - St. Johnsbury 115kV line | Planned | 9000000 | 9000000
Reliability Upgrade | 1a | 887 | National Grid, USA | 09/2012 | 2012 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Planned | 30000000 | 30000000
Reliability Upgrade | 1a | 921 | National Grid, USA | 01/2012 | 2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | 12100000 | 12100000
Reliability Upgrade | 1a | 919 | National Grid, USA | 09/2012 | 2012 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | 4600000 | 4600000
Reliability Upgrade | 1a | 775 | National Grid, USA | 06/2012 | 2012 | Merrimack Valley/North Shore Reliability Project | Addition of 4 breakers and relocation of T1 and T2 into new bays at Sandy Pond. | Planned | 20100000 | 20100000
Reliability Upgrade | 1a | 776 | National Grid, USA | 06/2012 | 2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | 2865876 | 2865876
Reliability Upgrade | 1a | 59 | National Grid, USA | 01/2012 | 2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | 400000 | 400000
Reliability Upgrade | 1a | 944 | National Grid, USA | 07/2012 | 2012 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Planned | 11411849 | 11411849
Reliability Upgrade | 1a | 948 | National Grid, USA | 07/2012 | 2012 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | 5649430 | 5649430
Reliability Upgrade | 1a | 949 | National Grid, USA | 07/2012 | 2012 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | 1500000 | 1500000
Reliability Upgrade | 1a | 673 | National Grid, USA | 12/2012 | 2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | National Grid, USA | 12/2012 | 2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Planned | 30000000 | 30000000
Reliability Upgrade | 1a | 1095 | National Grid, USA | 06/2012 | 2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | 73800000 | 73800000
Reliability Upgrade | 1a | 797 | National Grid, USA | 12/2012 | 2012 | NEEWS (Interstate Reliability Project) | 3361 Upgrade 345kV terminal equipment at Sherman Road. | Planned | 8300000 | 8300000
Reliability Upgrade | 1a | 795 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV line. | Planned | 99900000 | 99900000
Reliability Upgrade | 1a | 1106 | National Grid, USA | 05/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | Planned | Part of $99,900,000 above | Part of $99,900,000 above
Reliability Upgrade | 1a | 798 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Planned | 4900000 | 4900000
Reliability Upgrade | 1a | 799 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | Planned | 4500000 | 4500000
Reliability Upgrade | 1a | 1096 | National Grid, USA | 05/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | 12000000 | 12000000
Reliability Upgrade | 1a | 800 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S, T-172N and T-172S with associated terminal equipment upgrades. | Planned | 10000000 | 10000000
Reliability Upgrade | 1a | 1097 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County | Planned | 129800000 | 129800000
Reliability Upgrade | 1a | 1099 | National Grid, USA | 05/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | 6000000 | 6000000
Reliability Upgrade | 1a | 1109 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Planned | 1000000 | 1000000
Reliability Upgrade | 1a | 976 | United Illuminating Company | 05/2012 | 2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Planned | 48000000 | 48000000
Reliability Upgrade | 1b | 148 | Central Maine Power Company | 06/2012 | 2012 | CMP LSP - Saco Bay Area Reinforcement Project | Establish a new Vallee Lane 115/34.5 kV substation and 115 kV line from Louden S/S to Vallee Lane Substation. | Proposed | 100000 | 100000
Reliability Upgrade | 1b | 1068 | NSTAR Electric Company | 12/2012 | 2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to Sandwich and a a 345-115kV auto-transformer at Sandwich | Proposed | 110000000 | 110000000
Reliability Upgrade | 1b | 592 | NSTAR Electric Company | 12/2012 | 2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing | Proposed | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1118 | NSTAR Electric Company | 12/2012 | 2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 | Proposed | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1065 | NSTAR Electric Company | 07/2012 | 2012 | NPCC BPS Compliance | Waltham Station | Proposed | 26600000 | 26600000
Reliability Upgrade | 1b | 1136 | National Grid, USA | 12/2012 | 2012 |  | New 115kV Switching Station at Devens Convert 69kV lines to 115kV, Reconfigure 115kV Supply at Ayer Substation | Proposed | 9200000 | 9200000
Reliability Upgrade | 1a | 902 | National Grid, USA | 03/2012 | 2012 | Middleboro Municipal | Close the E1-M1 loop at Middleboro's Wareham St Sub. | Under Construction | 715000 | 715000
Reliability Upgrade | 1b | 843 | NSTAR Electric Company | 12/2013 | 2013 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | TBD | TBD
Reliability Upgrade | 1b | 593 | NSTAR Electric Company | 2013 | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Canal to Barnstable/Falmouth | Concept | TBD | TBD
Reliability Upgrade | 1b | 956 | National Grid, USA | 05/2013 | 2013 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Concept | 7021534 | 7021534
Reliability Upgrade | 1b | 975 | United Illuminating Company | 12/2013 | 2013 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | 44300000 | 44300000
Reliability Upgrade | 1a | 674 | National Grid, USA | 09/2013 | 2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | 7720000 | 7720000
Reliability Upgrade | 1a | 782 | National Grid, USA | 10/2013 | 2013 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor n Railyard. | Planned | 38100000 | 38100000
Reliability Upgrade | 1a | 931 | National Grid, USA | 01/2013 | 2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | 531481 | 531481
Reliability Upgrade | 1a | 950 | National Grid, USA | 12/2013 | 2013 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | 1016897 | 1016897
Reliability Upgrade | 1a | 953 | National Grid, USA | 12/2013 | 2013 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | 10248067 | 10248067
Reliability Upgrade | 1a | 954 | National Grid, USA | 12/2013 | 2013 | Central/Western Massachusetts Upgrades | E Westminster - install new 115 kV breaker, including disconnect switches. Assumes no new control house. | Planned | 903909 | 903909
Reliability Upgrade | 1a | 945 | National Grid, USA | 02/2013 | 2013 | Central/Western Massachusetts Upgrades | Adams - install third 115 kV breaker to complete ring bus. | Planned | 1584841 | 1584841
Reliability Upgrade | 1a | 946 | National Grid, USA | 04/2013 | 2013 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer - E Longmeadow - Shaker Rd line to 115 kV. | Planned | 9604032 | 9604032
Reliability Upgrade | 1a | 947 | National Grid, USA | 04/2013 | 2013 | Central/Western Massachusetts Upgrades | Reconductor 115 kV line from Palmer to new Hampden Substation. | Planned | 2632635 | 2632635
Reliability Upgrade | 1a | 951 | National Grid, USA | 02/2013 | 2013 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon 115 kV line. | Planned | 7455440 | 7455440
Reliability Upgrade | 1a | 687 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | 714000000 | 714000000
Reliability Upgrade | 1a | 826 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 196 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115kV line South Agawam to Southwick (1768) | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVAR Capacitor additions | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1074 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1078 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 190 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | 69600000 | 69600000
Reliability Upgrade | 1a | 1094 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | 25000000 | 25000000
Reliability Upgrade | 1a | 794 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | 55800000 | 55800000
Reliability Upgrade | 1a | 796 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | 347 Reconductor from Sherman Road to CT/RI Border. | Planned | 16400000 | 16400000
Reliability Upgrade | 1a | 816 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1054 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Manchester - Meekvile Jct. line (395/1448) separation. | Planned | 14000000 | 14000000
Reliability Upgrade | 1a | 576 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | 313000000 | 313000000
Reliability Upgrade | 1a | 1114 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1a | 814 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Ancillary Central Connecticut Relaibility Project) | Reconductor a portion of the Manchester to Scovill Rock 353 345-kV line and terminal work. | Planned | 9000000 | 9000000
Reliability Upgrade | 1a | 802 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | 251000000 | 251000000
Reliability Upgrade | 1a | 1084 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Loop the Millstone - Manchester (310) 345 kV line into the Card substation. | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1085 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1086 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1087 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1088 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1089 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Killingly 3G substation 345kV breaker addition | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1090 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Millstone 15G substation breaker 14T upgrade 50kA | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1091 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Southington 4C substation breaker 19T upgrade to 63kA | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 807 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Ancillary Interstate Reliability Project) | Install 480 MVAR's of capacitors at the Montville 345 kV substation | Planned | 33000000 | 33000000
Reliability Upgrade | 1a | 1092 | Northeast Utilities | 12/2013 | 2013 | NEEWS (BPS) 2 | Upgrade the Card 115 kV, East Hartford 115 kV, Agawam 115 kV, Barbour Hill 115 kV, and North Bloomfield 345 kV Substations to BPS standards. | Planned | 37000000 | 37000000
Reliability Upgrade | 1b | 721 | United Illuminating Company | 06/2013 | 2013 |  | New Shelton 115/13.8 kV substation | Proposed | 11300000 | 11300000
Reliability Upgrade | 1a | 791 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | 11560000 | 11560000
Reliability Upgrade | 1a | 913 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | 3250000 | 3250000
Reliability Upgrade | 1a | 914 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | 28150000 | 28150000
Reliability Upgrade | 1a | 915 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | 11800000 | 11800000
Reliability Upgrade | 1a | 917 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | 7000000 | 7000000
Reliability Upgrade | 1a | 918 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | 3180000 | 3180000
Reliability Upgrade | 1a | 792 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Admiral St-Franklin Square (Q143 and R144) 115 kV UG recabling. | Planned | 39200000 | 39200000
Reliability Upgrade | 1a | 793 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | 6400000 | 6400000
Reliability Upgrade | 1b | 785 | National Grid, USA | 07/2017 | 2017 | Merrimack Valley/North Shore Reliability Project | Re-conductor F-158N (Golden Hills-Maplewood-Everett) 115 kV line. | Concept | 1330000 | 1330000
Reliability Upgrade | 1b | 969 | NSTAR Electric Company | 06/2018 | 2018 | Boston Area 115 kV Enhancements | Add a new 54 MVAR capacitor bank at Chelsea. | Concept | 1200000 | 1200000
Reliability Upgrade | 1b | 275 | Northeast Utilities | TBD | tbd |  | Merrimack 115-kV substation - Protection Separation Upgrade. | Concept | TBD | TBD
Reliability Upgrade | 1b | 824 | Northeast Utilities | TBD | tbd | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Concept | TBD | TBD
Reliability Upgrade | 1b | 825 | Northeast Utilities | TBD | tbd | Pittsfield / Greenfield Project | Upgrade the Pleasant to Blanford 115-kV line and the Blanford to Granville Jct. portion of the 115-kV line 1512. | Concept | TBD | TBD
Reliability Upgrade | 1b | 801 | Northeast Utilities | TBD | tbd |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Concept | TBD | TBD
Reliability Upgrade | 1b | 85 | Northeast Utilities | TBD | tbd |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | TBD | TBD
Reliability Upgrade | 1a | 879 |  | TBD | tbd | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | 420000 | 420000
Reliability Upgrade | 1b | 1135 | Central Maine Power Company | TBD | tbd | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer | Proposed | 1500000 | 1500000
Reliability Upgrade | 1b | 1143 | Northeast Utilities | TBD | tbd |  | Littleton 115kV breaker addition and reconfiguration | Proposed | 5338000 | 5338000
5255330774

## Macro1 (hidden)
Macro1 | Auto_Open
Macro10
Macro11
Macro12
Macro13
Macro14
Macro15
Macro16
Macro2
Macro3
Macro4
Macro5
Macro6
Macro7
Macro8
Macro9
Recover

## SortbyISD-StatusWInS-Nov11 (hidden)
October 2011 ISO-NEW ENGLAND Project Listing Update (DRAFT)(7)
Primary Driver | Part# | Project ID | State | Primary Equipment Owner |  | Projected In-Service Month/Year | Major Project | Project | Oct-11 Status | Oct-11 Estimated PTF Costs
Reliability Upgrade | 1a | 1197 | ME | Bangor Hydro-Electric Company |  | 12/2013 | Keene Rd Autotransformer | Orrington 345kV Series Breaker Addition | Planned | 1761250 | 1761250
Reliability Upgrade | 1a | 1116 | ME | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Under Construction | 37626000 | 37626000
Reliability Upgrade | 1a | 1156 | ME | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | Orrington Shunt Cap Reconfiguration | Under Construction | 2260262 | 2260262
Reliability Upgrade | 1a | 905 | ME | Central Maine Power Company |  | 2014-08-02 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Under Construction | 1364108000 | 1364108000
Reliability Upgrade | 1a | 906 | ME | Central Maine Power Company |  | 05/2014 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Larrabee Road-Middle St,Middle St -Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Under Construction | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 907 | ME | Central Maine Power Company |  | 05/2014 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 203 (Detroit-Orrington), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 908 | ME | Central Maine Power Company |  | 07/2014 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road); Coopers Mills autotransforme replaces Maxcy's autotransformer | Under Construction | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | ME | Central Maine Power Company |  | 2014-08-02 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast forming Sections 86 & 266 | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | ME | Central Maine Power Company |  | 05/2014 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377, 115kV Bucksport 65/205) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1026 | ME | Central Maine Power Company |  | 12/2013 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction associated with (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Elliot Switching Station) line work | Planned | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | 36000000
Reliability Upgrade | 1a | 1028 | ME | Central Maine Power Company |  | 12/2013 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M
Reliability Upgrade | 1a | 1158 | ME | Central Maine Power Company |  | 07/2014 | Maine Power Reliability Program (MPRP) | Two 40 MVAR reactors at Albion Road, two 40 MVAR reactors at Larabee Road, two 40 MVAR at Coopers Mills | Under Construction | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1030 | ME | Central Maine Power Company |  | 11/2013 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Maguire Road) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1132 | ME | Central Maine Power Company |  | 2014-08-02 | Maine Power Reliability Program (MPRP) | Add 115/34kV transformer at Coopers Mills | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 143 | ME | Bangor Hydro-Electric Company |  | 12/2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation (2 new breakers) to Harrington Substation to Epping Substation (3 new breakers) | Under Construction | 66100000 | 66100000
Reliability Upgrade | 1a | 1129 | ME | Central Maine Power Company |  | 05/2012 |  | New 115kV line between Wyman Hydro and Rice Rips Tap, parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | 32800000 | 32800000
Reliability Upgrade | 1a | 1131 | ME | Central Maine Power Company |  | 11/2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Under Construction | 600000 | 600000
Reliability Upgrade | 1a | 1135 | ME | Central Maine Power Company |  | 02/2012 | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer | Planned | 1500000 | 1500000
Reliability Upgrade | 1a | 1196 | ME | Bangor Hydro-Electric Company |  | 01/2012 | SVC Filter Upgrade (Part of Keene Rd Auto-transformer ID 144) | Upgrade of filter bank at Chester SVC facility | Under Construction | 3500000 | 3500000
Reliability Upgrade | 1a | 1184 | ME | Central Maine Power Company |  | 05/2012 | Starks Switching Station | Add 4-115kV circuit breakers in a breaker-and a-half configuration on Section 63 and 2-18 MVAr cap banks at a new Starks Switching Station | Planned | 9750000 | 9750000
Reliability Upgrade | 1a | 1251 | ME | Central Maine Power Company |  | 12/2012 | Lakewood Substation Expansion | Sectionalize Section 241 by adding four 115kV circuit breakers at Lakewood Substation and install a second 115/34.5 kV transformer | Planned | 13700000 | 13700000
Reliability Upgrade | 1a | 1219 | NH | Northeast Utilities |  | 12/2011 |  | Install 115kV two 13.3 MVAR capacitor banks at Oak Hill substation | Under Construction | 4000000 | 4000000
Reliability Upgrade | 1a | 277 | NH | Northeast Utilities |  | 11/2011 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Under Construction | 52000000 | 52000000
Reliability Upgrade | 1a | 1140 | NH | Northeast Utilities |  | 10/2011 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | Under Construction | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1141 | NH | Northeast Utilities |  | 2015 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1182 | NH | Northeast Utilities |  | 06/2012 | LSP New Eagle Substation and 115/34.5KV transformer | New 115kV Eagle Substation connected to 115/34.5kV Thornton Substation | Under Construction | 22800000 | 22800000
Reliability Upgrade | 1a | 680 | NH | National Grid, USA |  | 06/2013 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | 7393000 | 7393000
Reliability Upgrade | 1a | 674 | NH | National Grid, USA |  | 12/2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | 19460000 | 19460000
Reliability Upgrade | 1a | 1172 | VT | Vermont Electric Power Company |  | 06/2012 | Vermont Shunt Reactors | Install 345kV 60 MVAr shunt reactors (two at Coolidge and one at New Haven and relocate the New Haven reactor to Vernon) to address high voltage concerns | Planned | 20000000 | 20000000
Reliability Upgrade | 1a | 318 | VT | Vermont Electric Power Company |  | 12/2012 | Georgia Substation Rebuild | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems due to breaker failure contingencies | Planned | 16000000 | 16000000
Reliability Upgrade | 1a | 1169 | VT | Vermont Electric Power Company |  | 12/2012 | Ascutney Substation Rebuild | Rebuild the existing Ascutney substation 115kV bus into a ring bus, to address reliability problems due to breaker failure contingencies | Planned | 14500000 | 14500000
Reliability Upgrade | 1a | 1170 | VT | Vermont Electric Power Company |  | 06/2013 | Bennington Substation Rebuild | Rebuild the exiting Bennington substation 115kV bus into a ring bus to address reliability problems due to breaker failure contingencies | Planned | 28000000 | 28000000
Reliability Upgrade | 1a | 1171 | VT | Vermont Electric Power Company |  | 12/2011 | West Rutland Capacitor Rebuild | Install two 115kV 25 MVAr capacitor banks at West Rutland to address low voltage concerns | Planned | 2400000 | 2400000
Reliability Upgrade | 1a | 1194 | VT | Vermont Electric Power Company |  | 12/2012 | LSP Jay Substation | Construct a new 4-breaker ring substation at Jay with two 115/46kV transformers | Planned | 6500000 | 6500000
Reliability Upgrade | 1a | 1195 | VT | Vermont Electric Power Company |  | 03/2013 | Highgate Refurbishment | Replace Highgate controls and cooling system | Planned | 35600000 | 35600000
Reliability Upgrade | 1a | 887 | MA | National Grid, USA |  | 06/2013 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Under Construction | 58000000 | 58000000
Reliability Upgrade | 1a | 921 | MA | National Grid, USA |  | 12/2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | 40000000 | 40000000
Reliability Upgrade | 1a | 919 | MA | National Grid, USA |  | 04/2014 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | 13600000 | 13600000
Reliability Upgrade | 1a | 59 | MA | National Grid, USA |  | 12/2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | Part of RSP 921 | Part of RSP 921
Reliability Upgrade | 1a | 840 | MA | NSTAR Electric Company |  | 12/2012 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | 5900000 | 5900000
Reliability Upgrade | 1a | 776 | MA | National Grid, USA |  | 11/2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | 3125000 | 3125000
Reliability Upgrade | 1a | 782 | MA | National Grid, USA |  | 01/2016 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor and Railyard. | Planned | 43912000 | 43912000
Reliability Upgrade | 1a | 1165 | MA | NSTAR Electric Company |  | 12/2011 | Mystic Breaker Additions Project | Move Transformer 110B Connection at Mystic | Under Construction | 2600000 | 2600000
Reliability Upgrade | 1a | 1068 | MA | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to vicinity of Bourne and connect to existing #120 line and install a 345KV - 115kV auto-transformer at new substation about 3 miles west of the Barnstable Substation Loop Line #115 in and out of the new Substation. Create a new line position at the Bourne Substation and connect the Bourne-Canal section of Line #120 | Planned | 106500000 | 106500000
Reliability Upgrade | 1a | 592 | MA | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing. The lines being separated are 322 (Canal-Carver) and 342 (Canal-Pilgrim-Auburn) | Planned | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1a | 1118 | MA | National Grid, USA |  | 12/2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 (Bellrock-High Hill) | Planned | 6000000 | 6000000
Reliability Upgrade | 1a | 1187 | MA | National Grid, USA |  | 06/2014 | A127/B128 Conductor Refurbishment | A127/B128 Conductor Refurbishment - Tower 510 to Harriman Substation, VT | Planned | 65000000 | 65000000
Reliability Upgrade | 1a | 929 | MA | National Grid, USA |  | 09/2013 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | 2500000 | 2500000
Reliability Upgrade | 1a | 931 | MA | National Grid, USA |  | 01/2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | 531481 | 531481
Reliability Upgrade | 1a | 928 | MA | National Grid, USA |  | 06/2013 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | 3400000 | 3400000
Reliability Upgrade | 1a | 934 | MA | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Under Construction | Part of RSP 935 | Part of RSP 935
Reliability Upgrade | 1a | 935 | MA | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Under Construction | 10200000 | 10200000
Reliability Upgrade | 1a | 938 | MA | National Grid, USA |  | 05/2013 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | 5430000 | 5430000
Reliability Upgrade | 1a | 940 | MA | National Grid, USA |  | 06/2014 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS (A127 West reconductoring. Tower 510 to Paxton, French King to French King). | Planned | 18000000 | 18000000
Reliability Upgrade | 1a | 942 | MA | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | 3650000 | 3650000
Reliability Upgrade | 1a | 925 | MA | National Grid, USA |  | 11/2012 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | Part of RSP 926 | Part of RSP 926
Reliability Upgrade | 1a | 926 | MA | National Grid, USA |  | 11/2012 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | 14700000 | 14700000
Reliability Upgrade | 1a | 932 | MA | National Grid, USA |  | 11/2012 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | Part of RSP 926 | Part of RSP 926
Reliability Upgrade | 1a | 941 | MA | National Grid, USA |  | 2013-08-01 | Central/Western Massachusetts Upgrades | Install new Z126 Millbury - Tower #510 115 kV line. | Planned | 13748000 | 13748000
Reliability Upgrade | 1a | 943 | MA | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | 4100000 | 4100000
Reliability Upgrade | 1a | 944 | MA | National Grid, USA |  | 03/2012 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Under Construction | 15700000 | 15700000
Reliability Upgrade | 1a | 950 | MA | National Grid, USA |  | 02/2015 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | 1016897 | 1016897
Reliability Upgrade | 1a | 953 | MA | National Grid, USA |  | 02/2015 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | 10248067 | 10248067
Reliability Upgrade | 1a | 954 | MA | National Grid, USA |  | 02/2015 | Central/Western Massachusetts Upgrades | Westminster - install new 69kV breaker, including disconnect switches. | Planned | 903909 | 903909
Reliability Upgrade | 1a | 945 | MA | National Grid, USA |  | 05/2014 | Central/Western Massachusetts Upgrades | Adams - install two new 115 kV breakers and replace two existing 115kV breakers | Planned | 5000000 | 5000000
Reliability Upgrade | 1a | 946 | MA | National Grid, USA |  | 04/2015 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer- Hampden to 115 kV. | Planned | 16000000 | 16000000
Reliability Upgrade | 1a | 948 | MA | National Grid, USA |  | 05/2014 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | 13400000 | 13400000
Reliability Upgrade | 1a | 949 | MA | National Grid, USA |  | 04/2015 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | 1600000 | 1600000
Reliability Upgrade | 1a | 937 | MA | National Grid, USA |  | 12/2015 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | 6602875 | 6602875
Reliability Upgrade | 1a | 955 | MA | National Grid, USA |  | 10/2012 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | 13800000 | 13800000
Reliability Upgrade | 1a | 951 | MA | National Grid, USA |  | 01/2014 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon (H-134) 115 kV line. | Planned | 7455440 | 7455440
Reliability Upgrade | 1a | 1217 | MA | Northeast Utilities |  | 12/2012 | Central/Western Massachusetts Upgrades | Subatation work at Ludlow (MA) and Scitico (CT) assoicaited with the new Hampden (MA) subsation project (Ngrid) | Planned | 3140000 | 3140000
Reliability Upgrade | 1a | 1076 | MA | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Under Construction | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 687 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | 718000000 | 718000000
Reliability Upgrade | 1a | 826 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 196 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct the 115kV line South Agawam to Southwick (1768) | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVar Capacitor additions | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1074 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1078 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1109 | MA | National Grid, USA |  | 12/2011 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Under Construction | 1000000 | 1000000
Reliability Upgrade | 1a | 1094 | MA | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | 25000000 | 25000000
Reliability Upgrade | 1a | 1202 | MA | NSTAR Electric Company |  | 06/2013 | NEEWS (Ancillary Interstate Reliability Project) | Rebuild 1.2 mile length of line 336 with 2-900 ACSS conductor and replace 5, 345kV 2000 amp disconnect switches with 3000 amp switches at W. Medway station | Planned | 1700000 | 1700000
Reliability Upgrade | 1a | 791 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | 11560000 | 11560000
Reliability Upgrade | 1a | 913 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | 3250000 | 3250000
Reliability Upgrade | 1a | 914 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | 28150000 | 28150000
Reliability Upgrade | 1a | 917 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | 7000000 | 7000000
Reliability Upgrade | 1a | 793 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | 6400000 | 6400000
Reliability Upgrade | 1a | 790 | MA | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Under Construction | 52000000 | 52000000
Reliability Upgrade | 1a | 1098 | MA | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Under Construction | 22000000 | 22000000
Reliability Upgrade | 1a | 1092 | MA | Northeast Utilities |  | 12/2013 | Agawam (BPS) | Upgrade the Agawam 115kV, Subtations to BPS standards together with other misc. subatation upgrades | Under Construction | 12100000 | 12100000
Reliability Upgrade | 1a | 1216 | MA | Northeast Utilities |  | 04/2012 |  | 345kV Ludlow - Northfield (portion of 354) Line Structure replacements | Under Construction | 25100000 | 25100000
Reliability Upgrade | 1a | 1266 | MA | Northeast Utilities |  | 12/2011 |  | 115kV Pleasant to Blandford (portion of 1421) Line structure replacement | Under Construction | 9960000 | 9960000
Reliability Upgrade | 1a | 1267 | MA | Northeast Utilities |  | 12/2011 |  | 115kV Blandford to Southwick (portion of 1512) Line structure replacement | Under Construction | 9600000 | 9600000
Reliability Upgrade | 1a | 1268 | MA | Northeast Utilities |  | 12/2012 |  | 345kV Northfield Mountain to Berkshire (portion of 312) line structure replacements | Planned | 7900000 | 7900000
Reliability Upgrade | 1a | 673 | MA | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | MA | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Planned | 30000000 | 30000000
Reliability Upgrade | 1a | 1257 | MA | National Grid, USA |  | 06/2014 | Salem Harbor Retirement | 115kV line Reconductoring of the S-145/T-146 from Tewksbury-North Reading Tap (9.3 miles each) | Planned | 29000000 | 29000000
Reliability Upgrade | 1a | 1258 | MA | National Grid, USA |  | 06/2014 | Salem Harbor Retirement | 115kV line Reconductoring of the Y-151 from Tewksbury Junction - West Methuen (8.2 miles) | Planned | 11500000 | 11500000
Reliability Upgrade | 1a | 1259 | MA | National Grid, USA |  | 06/2014 | Salem Harbor Retirement | 115kV line Reconductoring of the B154/C-155N from King St Tap - South Danvers (14.5 miles each way) | Planned | 20000000 | 20000000
Reliability Upgrade | 1a | 969 | MA | NSTAR Electric Company |  | 11/2012 | Greater Boston - North | Add a new 115kV 36.7 MVAR capacitor bank at Chelsea. | Under Construction | 1500000 | 1500000
Reliability Upgrade | 1a | 1201 | MA | NSTAR Electric Company |  | 12/2012 | Greater Boston - North | 115kV line Reconductoring of the P168/128-518 Line between Chelsea and Revere (NSTAR Portion of the line) | Planned | 1500000 | 1500000
Reliability Upgrade | 1a | 301 | MA | NSTAR Electric Company |  | 12/2011 | Greater Boston - Central | Reconductor 115-kV circuits 320-507 and 320-508. (Lexington - Waltham) | Under Construction | 9600000 | 9600000
Reliability Upgrade | 1a | 1066 | MA | NSTAR Electric Company |  | 12/2011 | NPCC BPS Compliance | Needham Station | Under Construction | 8000000 | 8000000
Reliability Upgrade | 1a | 1065 | MA | NSTAR Electric Company |  | 07/2012 | NPCC BPS Compliance | Waltham Station | Under Construction | 14700000 | 14700000
Reliability Upgrade | 1a | 1168 | MA | Holyoke Gas & Electric |  | 12/2012 | North Canal 44P | Loop the 1525 (Holyoke Fairmont South 115kV) line into the new North Canal 44P | Planned | 4100000 | 4100000
Reliability Upgrade | 1a | 1256 | MA | Unitil |  | 06/2013 | Flagg Pond Upgrades | At Flagg Pond Substation upgrade terminal equipment on the I-135N, I-135S, J-136N and J-136S 115kV lines and Zone 3 relay upgrades for the J-136N 115kV line. | Planned | 2750000 | 2750000
Reliability Upgrade | 1a | 484 | RI | National Grid, USA |  | 11/2011 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Under Construction | 580000 | 580000
Reliability Upgrade | 1a | 915 | RI | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | RI | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | 11800000 | 11800000
Reliability Upgrade | 1a | 918 | RI | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | 3180000 | 3180000
Reliability Upgrade | 1a | 190 | RI | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | 81800000 | 81800000
Reliability Upgrade | 1a | 1095 | RI | National Grid, USA |  | 12/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | 73800000 | 73800000
Reliability Upgrade | 1a | 794 | RI | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | 71700000 | 71700000
Reliability Upgrade | 1a | 795 | RI | National Grid, USA |  | 04/2013 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV (359) line. | Planned | 69000000 | 69000000
Reliability Upgrade | 1a | 1106 | RI | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Kent County Substation Upgrades related to third 345/115 kV Autotransformer. | Planned | 26000000 | 26000000
Reliability Upgrade | 1a | 798 | RI | National Grid, USA |  | 12/2011 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Planned | 600000 | 600000
Reliability Upgrade | 1a | 1096 | RI | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | 12000000 | 12000000
Reliability Upgrade | 1a | 1097 | RI | National Grid, USA |  | 01/2013 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County including S-175, T172N and T-172S with associated terminal equipment upgrade. | Planned | 129800000 | 129800000
Reliability Upgrade | 1a | 1099 | RI | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | 6000000 | 6000000
Reliability Upgrade | 1a | 1253 | RI | National Grid, USA |  | 04/2015 |  | New Crandall St. Substation 115-13 kV substation addition | Planned | 3000000 | 3000000
Reliability Upgrade | 1a | 1241 | RI | National Grid, USA |  | 06/2013 |  | Re-condustor G-185S (Kent County - Davisville Tap) | Planned | 4200000 | 4200000
Reliability Upgrade | 1a | 1193 | CT | United Illuminating Company |  | 12/2012 |  | North Haven 115kV Capacitor Bank TRV Mitigation Project | Under Construction | 4900000 | 4900000
Reliability Upgrade | 1a | 974 | CT | United Illuminating Company |  | 05/2013 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Under Construction | 16900000 | 16900000
Reliability Upgrade | 1a | 816 | CT | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1054 | CT | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Build a new 345 kV line from Manchester to Meekville Junction and re-terminate the 395 line at Meekville Junction | Planned | 28800000 | 28800000
Reliability Upgrade | 1a | 576 | CT | Northeast Utilities |  | 2016 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | 301000000 | 301000000
Reliability Upgrade | 1a | 1114 | CT | Northeast Utilities |  | 2016 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1a | 802 | CT | Northeast Utilities |  | 2015 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | 218000000 | 218000000
Reliability Upgrade | 1a | 1085 | CT | Northeast Utilities |  | 2015 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | CT | Northeast Utilities |  | 2015 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | CT | Northeast Utilities |  | 2015 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1235 | CT | Northeast Utilities |  | 12/2015 | NEEWS (Ancillary Interstate Reliability Project) | Sag elimination on 1410 Line (Montville-Buddington) | Planned | 3000000 | 3000000
Reliability Upgrade | 1a | 1245 | CT | CMEEC |  | 12/2015 | NEEWS (Ancillary Interstate Reliability Project) | Sag elimination on 1410 Line (Montville-Buddington) | Planned | 60000 | 60000
Reliability Upgrade | 1a | 1227 | CT | Northeast Utilities |  | 2012 | LSP - Stamford Area | Add 4th transformer and build a five breaker ring bus at South End Substation | Planned | 6400000 | 6400000
Reliability Upgrade | 1a | 1056 | CT | Northeast Utilities |  | 12/2011 | LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Under Construction | 10969000 | 10969000
Reliability Upgrade | 1a | 1218 | CT | Northeast Utilities |  | 12/2013 | Millstone 345kV Circuit Separation project & SLOD SPS System Retirement | Separate the 345kV Double Circuit Tower 310/348 and 371/383 Tower configuration | Planned | 25600000 | 25600000
Reliability Upgrade | 1a | 1111 | CT | United Illuminating Company |  | 01/2012 |  | Union Avenue 115/26.4 kV Substation | Under Construction | 13500000 | 13500000
Reliability Upgrade | 1a | 976 | CT | United Illuminating Company |  | 05/2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Under Construction | 70000000 | 70000000
Reliability Upgrade | 1a | 721 | CT | United Illuminating Company |  | 06/2015 |  | New Shelton 115/13.8 kV substation | Planned | 19500000 | 19500000
Reliability Upgrade | 1a | 879 | CT | Bangor Hydro-Electric Company |  | TBD | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | 420000 | 420000
Reliability Upgrade | 1a | 1050 | CT | United Illuminating Company |  | 12/2011 |  | Devon Tie 115kV Switching Station BPS Compliance | Under Construction | 4000000 | 4000000
Reliability Upgrade | 1b | 1031 | ME | Bangor Hydro-Electric Company |  | 12/2013 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station | Concept | TBD | TBD
Reliability Upgrade | 1b | 1154 | ME | Bangor Hydro-Electric Company |  | 12/2013 | Maine Power Reliability Program (MPRP) | Rerate Line 66 | Concept | TBD | TBD
Reliability Upgrade | 1b | 1155 | ME | Bangor Hydro-Electric Company |  | 12/2014 | Maine Power Reliability Program (MPRP) | Capacitor Bank Addition (10 MVAr at Trenton 34.5kV and Epping) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1133 | ME | Central Maine Power Company |  | 12/2011 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation and new 34kV line from Leeds to Turner | Proposed | 300000 | 300000
Reliability Upgrade | 1b | 1279 | ME | Central Maine Power Company |  | 12/2014 |  | New 345/115kV Autotransformer and 115kV switchyard at Raven Farm substation consisting of a four-bay breaker and a half configuration of eleven (11) breakers | Proposed | 26126000 | 26126000
Reliability Upgrade | 1b | 1280 | ME | Central Maine Power Company |  | 12/2014 |  | New 115kV line section 244 and upgraded line section 80 between Coopers Mill and Highland Substations | Proposed | 62735000 | 62735000
Reliability Upgrade | 1b | 1183 | NH | Northeast Utilities |  | 2014 | LSP New Peaselee Substation and 115/34.5KV transformer | New 115kV Peaselee Substation and transmission line work | Proposed | 12400000 | 12400000
Reliability Upgrade | 1b | 1220 | NH | Northeast Utilities |  | 12/2015 | Greater Boston - North | Install a new 345kV circuit between Scobie and Pelham NH (this is NU's portion of the new Scobie-Tewksbury circuit) | Proposed | 40100000 | 40100000
Reliability Upgrade | 1b | 1269 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Amherst Substation - New 345kV breaker and three 25MVar Capacitor Banks | Proposed | 19600000 | 19600000
Reliability Upgrade | 1b | 1270 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | New 115kV line from Fitzwilliiams to Monadnock | Proposed | 10500000 | 10500000
Reliability Upgrade | 1b | 1271 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Upgrade the Keene to Monadnock (T198) 115kV line | Proposed | 11900000 | 11900000
Reliability Upgrade | 1b | 1272 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Weare Substation - Add two 13.3 MVar 115V capacitors | Proposed | 3600000 | 3600000
Reliability Upgrade | 1b | 1273 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Rebuild A152 115kV line | Proposed | 22500000 | 22500000
Reliability Upgrade | 1b | 1274 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Rebuild N186 115kV line | Proposed | 2300000 | 2300000
Reliability Upgrade | 1b | 1275 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Upgrade the 381 345kV line | Proposed | 4200000 | 4200000
Reliability Upgrade | 1b | 1276 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Littleton Substation - Add a second 230/115kV autotransformer and associated 115kV substation work | Proposed | 16700000 | 16700000
Reliability Upgrade | 1b | 1277 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Webster Substation - Add four 26.6 MVar 115kV capacitors | Proposed | 11900000 | 11900000
Reliability Upgrade | 1b | 1278 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Saco Valley Substation - Add two 25 MVar dynamic Var devices | Proposed | 15800000 | 15800000
Reliability Upgrade | 1b | 1263 | NH | National Grid, USA |  | TBD | Northern New Hsmpshire Solution | New C-203 230kV line tap to Littleton NH Substation associated with 2nd 230/115kV auto project | Proposed | 1100000 | 1100000
Reliability Upgrade | 1b | 325 | VT | Vermont Electric Power Company |  | TBD | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | TBD | TBD
Reliability Upgrade | 1b | 324 | VT | Vermont Electric Power Company |  | TBD |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | TBD | TBD
Reliability Upgrade | 1b | 139 | VT | Vermont Electric Power Company |  | TBD | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Concept | TBD | TBD
Reliability Upgrade | 1b | 1250 | VT | Vermont Electric Power Company |  | 2016 | VELCO LSP - West Rutland Substation | Installation of a 115/46kV transformer at West Rutland between breakers K30 and K34 | Concept | TBD | TBD
Reliability Upgrade | 1b | 843 | MA | NSTAR Electric Company |  | 06/2012 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Proposed | 3450000 | 3450000
Reliability Upgrade | 1b | 593 | MA | NSTAR Electric Company |  | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Bourne and Barnstable/Falmouth/equivalent | Concept | TBD | TBD
Reliability Upgrade | 1b | 965 | MA | NSTAR Electric Company |  | 06/2014 | Greater Boston - South | Add third 115kV line from W. Walpole to Holbrook | Proposed | 19000000 | 19000000
Reliability Upgrade | 1b | 1175 | MA | NSTAR Electric Company |  | 12/2013 | Greater Boston - South | Upgrade the 115kV line 201-501 (Medway-Depot St.) and the 201-502 (Beaver Pond - Depot Street Tap) to a higher capacity line | Proposed | 3700000 | 3700000
Reliability Upgrade | 1b | 1214 | MA | National Grid, USA |  | 12/2015 | Greater Boston - South | Line Reconductoring of the C-129 Beaver Pond - Depot St. Tap) and D-130 (Depot St. Tap - Medway) 115kV lines | Proposed | 500000 | 500000
Reliability Upgrade | 1b | 1177 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - North | Reconductor 211-503/504 from North Woburn Tap to Reading | Concept | TBD | TBD
Reliability Upgrade | 1b | 1178 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - North | Install 115kV Capacitor Bank at North Woburn | Concept | TBD | TBD
Reliability Upgrade | 1b | 1179 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - North | Install 2nd 345kV circuit between Bellerica/Burlington town line to Tewksbury | Proposed | 33000000 | 33000000
Reliability Upgrade | 1b | 1190 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - North | Install a second 345/115kV Auto Transformer at Woburn | Concept | TBD | TBD
Reliability Upgrade | 1b | 1200 | MA | NSTAR Electric Company |  | TBD | Greater Boston - North | Add a new 345kV UG circuit between Woburn and North Cambridge | Proposed | 52000000 | 52000000
Reliability Upgrade | 1b | 1211 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | Install 2nd 345kV circuit between Tewksbury - Billerica/Burlington Town Line (NSTAR Border) | Proposed | 32700000 | 32700000
Reliability Upgrade | 1b | 1212 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | 115kV Line Reconductoring of M-139/N-140 Tewksbury-Pinehurst (6.1 miles each) | Proposed | 11600000 | 11600000
Reliability Upgrade | 1b | 1213 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | Install new 345kV circuit between NH/MA border and Tewksbury (this is NGRID's portion of the new Scobie-Tewksbury circuit) | Proposed | 23370000 | 23370000
Reliability Upgrade | 1b | 1215 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | New 115kV line between Wakefield - Everett | Proposed | 20000000 | 20000000
Reliability Upgrade | 1b | 1254 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | Substation work at Revere Substation to increase ratings on the 128-515P/168 line between Chelsea and Revere | Proposed | 1000000 | 1000000
Reliability Upgrade | 1b | 1260 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | 115kV Line reconductoring of the F-158N/S Wakefield Jct - Everett (7.36 miles) | Proposed | 3500000 | 3500000
Reliability Upgrade | 1b | 1261 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | 115kV Line reconductoring of the S-145T-146 from North Reading Tap - Wakefield Jct (5.1 miles each) | Proposed | 10800000 | 10800000
Reliability Upgrade | 1b | 1262 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | 115kV Line reconductoring of theY-151 from Tewksbury Junction - Tewksbury Substation (1.6 miles) | Proposed | 1250000 | 1250000
Reliability Upgrade | 1b | 970 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Add a new 345 kV line from Lexington to Waltham. | Concept | TBD | TBD
Reliability Upgrade | 1b | 971 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | TBD | TBD
Reliability Upgrade | 1b | 1176 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Install an oil circulation pipe and heat exchangers at K Street and Chatham Street sections of 250-516/517 circuits | Concept | TBD | TBD
Reliability Upgrade | 1b | 1189 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - Central | Install 3rd 115kV Circuit between Waltham and Brighton | Concept | TBD | TBD
Reliability Upgrade | 1b | 1198 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Add a second 115kV line from Woburn to Burlington | Concept | TBD | TBD
Reliability Upgrade | 1b | 1199 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Install a new 230/115kV auto transformer at Sudbury or equivalent | Concept | TBD | TBD
Reliability Upgrade | 1b | 1208 | MA | National Grid, USA |  | 12/2014 | Pittsfield / Greenfield Project | Separation and reconductoring of Cabot Taps (A-127 and Y-177 115kV lines) | Proposed | 7400000 | 7400000
Reliability Upgrade | 1b | 1209 | MA | National Grid, USA |  | 12/2014 | Pittsfield / Greenfield Project | Reconductoring of A-127 between Erving and Cabot Tap with 1590 ACSS | Proposed | 12000000 | 12000000
Reliability Upgrade | 1b | 1210 | MA | National Grid, USA |  | 12/2014 | Pittsfield / Greenfield Project | Harriman 115kV breaker upgrades | Proposed | 1100000 | 1100000
Reliability Upgrade | 1b | 1221 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Modify Northfield Mountain 16R substation and install a 345/115Kv autotransformer | Proposed | 108500000 | 108500000
Reliability Upgrade | 1b | 1222 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Build a new 115kV three breaker Swithching Station (Erving) ring bus | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1223 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Build a new 115kV line from Northfield Mountain to the new Erving Switching Station | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1224 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Install 115kV 14.4 MVAR capacitor banks at Cumberland, Podick and Amherst Substations | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1225 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Rebuild the Cumberland to Montague 1361 115kV line and terminal work at Cumberland and Montague | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1226 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 956 | MA | National Grid, USA |  | 01/2015 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Proposed | 7021534 | 7021534
Reliability Upgrade | 1b | 1252 | MA | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | Re-conductor 345kV 328 line (West Farnum-Sherman Rd) | Proposed | 36500000 | 36500000
Reliability Upgrade | 1b | 1191 | MA | NSTAR Electric Company |  | 12/2012 |  | Rebuild Section of Line 322 (Canal-Carver) | Concept | 12200000 | 12200000
Reliability Upgrade | 1b | 1181 | MA | NSTAR Electric Company |  | 12/2013 |  | Rebuild the High Hill 115kV Substation to a Breaker and a half desgin | Concept | TBD | TBD
Reliability Upgrade | 1b | 1204 | MA | NSTAR Electric Company |  | 06/2012 |  | Rebuild the Mashpee Substation to a Ring Bus and install an overvoltage trip relay on the Mashpee 115kV Capacitor Bank | Concept | TBD | TBD
Reliability Upgrade | 1b | 1205 | MA | NSTAR Electric Company |  | 12/2013 | Mid-Cape Reliability Project | Separate 120 (Canal-Barnstable) /122 (Oak St-Barnstable) DCT | Concept | TBD | TBD
Reliability Upgrade | 1b | 1206 | MA | NSTAR Electric Company |  | 12/2011 |  | Install a new 230kV breaker for line 282-602 (West Medway-Waltham) at W. Medway for system resoration | Concept | TBD | TBD
Reliability Upgrade | 1b | 1247 | MA | NSTAR Electric Company |  | TBD |  | Rebuild the Acushnet 115kV Substation | Concept | TBD | TBD
Reliability Upgrade | 1b | 1248 | MA | NSTAR Electric Company |  | 12/2014 |  | Rebuild the Kingston Substation to a breaker and a half scheme | Concept | TBD | TBD
Reliability Upgrade | 1b | 1249 | MA | NSTAR Electric Company |  | 12/2013 |  | Rebuild the Wareham Substation to a breaker and a half scheme | Concept | TBD | TBD
Reliability Upgrade | 1b | 1207 | MA | NSTAR Electric Company |  | 2012 | Belmont Transmission Interconnection | Build a new 115kV Substation for the Belmont Transmission Interconnection | Concept | TBD | TBD
Reliability Upgrade | 1b | 1255 | MA | CELD (Chicopee Electric Light Department) |  | 12/2013 | CELD 115/13.8kV Substation | 115/13.8kV substation on Memorial Dr. with two transformers and twelve feeders looped into 1904 (1723) line between Piper and Fairmont substations | Concept | TBD | TBD
Reliability Upgrade | 1b | 1233 | RI | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | New Sherman Road 345kV AIS Substation | Proposed | 36600000 | 36600000
Reliability Upgrade | 1b | 1234 | RI | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | Install a 115kV redundant breaker in series with breaker #1713 at West Farmum Substation and upgrade to current BPS standards | Concept | TBD | TBD
Reliability Upgrade | 1b | 1084 | CT | Northeast Utilities |  | TBD | Greater Hartford Central Connecticut Project | Loop the Millstone - Manchester (310) 345 kV line into the Card substation (2) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1086 | CT | Northeast Utilities |  | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow (2) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1087 | CT | Northeast Utilities |  | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford (2) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1088 | CT | Northeast Utilities |  | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow (2) | Concept | TBD | TBD
Reliability Upgrade | 1b | 975 | CT | United Illuminating Company |  | 06/2015 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | 105000000 | 105000000
Reliability Upgrade | 1b | 699 | CT | United Illuminating Company |  | 12/2014 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | 11100000 | 11100000
Reliability Upgrade | 1b | 801 | CT | Northeast Utilities |  | TBD |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Concept | TBD | TBD
Reliability Upgrade | 1b | 85 | CT | Northeast Utilities |  | TBD |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | TBD | TBD
Reliability Upgrade | 1b | 1228 | CT | Northeast Utilities |  | TBD | Stamford Area | Additional circuit into the Stamford Area (Glenbrook-South End) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1229 | CT | Northeast Utilities |  | TBD |  | Replace 115kV 1990 (Frost Bridge-Stevenson) lattice structure | Concept | TBD | TBD
Reliability Upgrade | 1b | 1230 | CT | Northeast Utilities |  | TBD | LSP - Greater Hartford Area | 115kV breaker addition at Northeast Simsbury Substation | Concept | TBD | TBD
Reliability Upgrade | 1b | 1242 | CT | CMEEC |  | 10/2012 | SNEW 115kV substation | SNEW 115/13.8kV substation with two transformers and a 115kV circuit breaker looped into the 1890 line (between Norwalk Hbr - Ely Ave) | Proposed | 2000000 | 2000000
Reliability Upgrade | 1b | 1243 | CT | CMEEC |  | 10/2013 | TTD's Fitch St 115kV Substation | TTD 115/27kV substation with two transformers and a 115kV circuit breaker looped into 1416 line (between Compo and Darien substations) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1244 | CT | CMEEC |  | 10/2011 | 115kV Circuit Breaker Installation | Install 115kV Bus Tie Circuit Breaker at Stock House Rd Substation | Proposed | 750000 | 750000
Reliability Upgrade | 1b | 1246 | CT | United Illuminating Company |  | 09/2013 | 8300 Line Reconfiguration Project | Reconfiguration of 115kV (8300) line from Mill River to Quinnipiac | Proposed | 17400000 | 17400000
IN-SERVICE PROJECTS | [10 empty] | 5460853715
Reliability Upgrade | 1a | 582 | CT | Northeast Utilities | 2011 | 06/2011 |  | Separate 310(Manchester-Millstone) and 368 (Manchester-Card) 345-KV lines and create 368/1767 DCT | In-service | 11350000 | 11350000
Reliability Upgrade | 1a | 1147 | CT | Northeast Utilities | 2011 | 07/2011 |  | Waterside Substation - install a three-breaker 115kV ring bus | In-service | 4616000 | 4616000
Reliability Upgrade | 1a | 1151 | CT | United Illuminating Company | 2011 | 06/2011 |  | West River 115kV Switching Station Fault Duty Mitigation | In-service | 2900000 | 2900000
Reliability Upgrade | 1a | 799 | RI | National Grid, USA | 2011 | 07/2011 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | In-service | 4500000 | 4500000
Reliability Upgrade | 1a | 1264 | RI | National Grid, USA | 2011 | 06/2011 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | In-service | Part of RSP 1105 | Part of RSP 1105
Reliability Upgrade | 1a | 924 | MA | National Grid, USA | 2011 | 07/2011 | Central/Western Massachusetts Upgrades | Carpenter Hill - Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | In-service | 4200000 | 4200000
Reliability Upgrade | 1a | 1137 | NH | Northeast Utilities | 2011 | 04/2011 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115kV breakers and add 1-115kV breaker at Deerfield Substation | In-service | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1143 | NH | Northeast Utilities | 2011 | 06/2011 |  | Littleton 115kV breaker addition and reconfiguration | In-service | 7011000 | 7011000
Reliability Upgrade | 1a | 624 | ME | Central Maine Power Company | 2011 | 07/2011 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (Rumford Industrial Park - Rumford) | In-service | Part of project 625 | Part of project 625
34577000

## Sorted by ISDthenStatus Nov11 (hidden)
November 2011 ISO-NEW ENGLAND Project Listing Update (DRAFT)(7)
Primary Driver | Part# | Project ID | Primary Equipment Owner |  | Projected In-Service Month/Year | Major Project | Project | Nov-11 Status | Nov-11 Estimated PTF Costs
Reliability Upgrade | 1b | 1206 | NSTAR Electric Company | 2011 | 12/2011 |  | Install a new 230kV breaker for line 282-602 (West Medway-Waltham) at W. Medway for system resoration | Concept | TBD | TBD
Reliability Upgrade | 1a | 1171 | Vermont Electric Power Company | 2011 | 12/2011 | West Rutland Capacitor Rebuild | Install two 115kV 25 MVAr capacitor banks at West Rutland to address low voltage concerns | Planned | 2400000 | 2400000
Reliability Upgrade | 1a | 798 | National Grid, USA | 2011 | 12/2011 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Planned | 600000 | 600000
Reliability Upgrade | 1b | 1133 | Central Maine Power Company | 2011 | 12/2011 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation and new 34kV line from Leeds to Turner | Proposed | 300000 | 300000
Reliability Upgrade | 1b | 1244 | CMEEC | 2011 | 10/2011 | 115kV Circuit Breaker Installation | Install 115kV Bus Tie Circuit Breaker at Stock House Rd Substation | Proposed | 750000 | 750000
Reliability Upgrade | 1a | 1116 | Bangor Hydro-Electric Company | 2011 | 12/2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Under Construction | 37626000 | 37626000
Reliability Upgrade | 1a | 1156 | Bangor Hydro-Electric Company | 2011 | 12/2011 | Maine Power Reliability Program (MPRP) | Orrington Shunt Cap Reconfiguration | Under Construction | 2260262 | 2260262
Reliability Upgrade | 1a | 1131 | Central Maine Power Company | 2011 | 11/2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Under Construction | 600000 | 600000
Reliability Upgrade | 1a | 1219 | Northeast Utilities | 2011 | 12/2011 |  | Install 115kV two 13.3 MVAR capacitor banks at Oak Hill substation | Under Construction | 4000000 | 4000000
Reliability Upgrade | 1a | 277 | Northeast Utilities | 2011 | 11/2011 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Under Construction | 52000000 | 52000000
Reliability Upgrade | 1a | 1140 | Northeast Utilities | 2011 | 10/2011 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | Under Construction | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1165 | NSTAR Electric Company | 2011 | 12/2011 | Mystic Breaker Additions Project | Move Transformer 110B Connection at Mystic | Under Construction | 2600000 | 2600000
Reliability Upgrade | 1a | 1076 | Northeast Utilities | 2011 | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Under Construction | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1109 | National Grid, USA | 2011 | 12/2011 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Under Construction | 1000000 | 1000000
Reliability Upgrade | 1a | 790 | National Grid, USA | 2011 | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Under Construction | 52000000 | 52000000
Reliability Upgrade | 1a | 1098 | National Grid, USA | 2011 | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Under Construction | 22000000 | 22000000
Reliability Upgrade | 1a | 1266 | Northeast Utilities | 2011 | 12/2011 |  | 115kV Pleasant to Blandford (portion of 1421) Line structure replacement | Under Construction | 9960000 | 9960000
Reliability Upgrade | 1a | 1267 | Northeast Utilities | 2011 | 12/2011 |  | 115kV Blandford to Southwick (portion of 1512) Line structure replacement | Under Construction | 9600000 | 9600000
Reliability Upgrade | 1a | 301 | NSTAR Electric Company | 2011 | 12/2011 | Greater Boston - Central | Reconductor 115-kV circuits 320-507 and 320-508. (Lexington - Waltham) | Under Construction | 9600000 | 9600000 | 1-2011 Concept
Reliability Upgrade | 1a | 1066 | NSTAR Electric Company | 2011 | 12/2011 | NPCC BPS Compliance | Needham Station | Under Construction | 8000000 | 8000000 | 2-2011 Planned
Reliability Upgrade | 1a | 484 | National Grid, USA | 2011 | 11/2011 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Under Construction | 580000 | 580000 | 2-2011 Proposed
Reliability Upgrade | 1a | 1056 | Northeast Utilities | 2011 | 12/2011 | LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Under Construction | 10969000 | 10969000 | 18-2011 UnderConstruct
Reliability Upgrade | 1a | 1050 | United Illuminating Company | 2011 | 12/2011 |  | Devon Tie 115kV Switching Station BPS Compliance | Under Construction | 4000000 | 4000000
Reliability Upgrade | 1b | 1191 | NSTAR Electric Company | 2012 | 12/2012 |  | Rebuild Section of Line 322 (Canal-Carver) | Concept | 12200000 | 12200000
Reliability Upgrade | 1b | 1204 | NSTAR Electric Company | 2012 | 06/2012 |  | Rebuild the Mashpee Substation to a Ring Bus and install an overvoltage trip relay on the Mashpee 115kV Capacitor Bank | Concept | TBD | TBD
Reliability Upgrade | 1b | 1207 | NSTAR Electric Company | 2012 | 2012 | Belmont Transmission Interconnection | Build a new 115kV Substation for the Belmont Transmission Interconnection | Concept | TBD | TBD
Reliability Upgrade | 1a | 1129 | Central Maine Power Company | 2012 | 05/2012 |  | New 115kV line between Wyman Hydro and Rice Rips Tap, parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | 32800000 | 32800000
Reliability Upgrade | 1a | 1135 | Central Maine Power Company | 2012 | 02/2012 | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer | Planned | 1500000 | 1500000
Reliability Upgrade | 1a | 1184 | Central Maine Power Company | 2012 | 05/2012 | Starks Switching Station | Add 4-115kV circuit breakers in a breaker-and a-half configuration on Section 63 and 2-18 MVAr cap banks at a new Starks Switching Station | Planned | 9750000 | 9750000
Reliability Upgrade | 1a | 1251 | Central Maine Power Company | 2012 | 12/2012 | Lakewood Substation Expansion | Sectionalize Section 241 by adding four 115kV circuit breakers at Lakewood Substation and install a second 115/34.5 kV transformer | Planned | 13700000 | 13700000
Reliability Upgrade | 1a | 1172 | Vermont Electric Power Company | 2012 | 06/2012 | Vermont Shunt Reactors | Install 345kV 60 MVAr shunt reactors (two at Coolidge and one at New Haven and relocate the New Haven reactor to Vernon) to address high voltage concerns | Planned | 20000000 | 20000000
Reliability Upgrade | 1a | 318 | Vermont Electric Power Company | 2012 | 12/2012 | Georgia Substation Rebuild | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems due to breaker failure contingencies | Planned | 16000000 | 16000000
Reliability Upgrade | 1a | 1169 | Vermont Electric Power Company | 2012 | 12/2012 | Ascutney Substation Rebuild | Rebuild the existing Ascutney substation 115kV bus into a ring bus, to address reliability problems due to breaker failure contingencies | Planned | 14500000 | 14500000
Reliability Upgrade | 1a | 1194 | Vermont Electric Power Company | 2012 | 12/2012 | LSP Jay Substation | Construct a new 4-breaker ring substation at Jay with two 115/46kV transformers | Planned | 6500000 | 6500000
Reliability Upgrade | 1a | 921 | National Grid, USA | 2012 | 12/2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | 40000000 | 40000000
Reliability Upgrade | 1a | 59 | National Grid, USA | 2012 | 12/2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | Part of RSP 921 | Part of RSP 921
Reliability Upgrade | 1a | 840 | NSTAR Electric Company | 2012 | 12/2012 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | 5900000 | 5900000
Reliability Upgrade | 1a | 776 | National Grid, USA | 2012 | 11/2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | 3125000 | 3125000
Reliability Upgrade | 1a | 1068 | NSTAR Electric Company | 2012 | 12/2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to vicinity of Bourne and connect to existing #120 line and install a 345KV - 115kV auto-transformer at new substation about 3 miles west of the Barnstable Substation Loop Line #115 in and out of the new Substation. Create a new line position at the Bourne Substation and connect the Bourne-Canal section of Line #120 | Planned | 106500000 | 106500000
Reliability Upgrade | 1a | 592 | NSTAR Electric Company | 2012 | 12/2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing. The lines being separated are 322 (Canal-Carver) and 342 (Canal-Pilgrim-Auburn) | Planned | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1a | 1118 | National Grid, USA | 2012 | 12/2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 (Bellrock-High Hill) | Planned | 6000000 | 6000000
Reliability Upgrade | 1a | 942 | National Grid, USA | 2012 | 12/2012 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | 3650000 | 3650000
Reliability Upgrade | 1a | 925 | National Grid, USA | 2012 | 11/2012 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | Part of RSP 926 | Part of RSP 926
Reliability Upgrade | 1a | 926 | National Grid, USA | 2012 | 11/2012 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | 14700000 | 14700000
Reliability Upgrade | 1a | 932 | National Grid, USA | 2012 | 11/2012 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | Part of RSP 926 | Part of RSP 926
Reliability Upgrade | 1a | 943 | National Grid, USA | 2012 | 12/2012 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | 4100000 | 4100000
Reliability Upgrade | 1a | 955 | National Grid, USA | 2012 | 10/2012 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | 13800000 | 13800000
Reliability Upgrade | 1a | 1217 | Northeast Utilities | 2012 | 12/2012 | Central/Western Massachusetts Upgrades | Subatation work at Ludlow (MA) and Scitico (CT) assoicaited with the new Hampden (MA) subsation project (Ngrid) | Planned | 3140000 | 3140000
Reliability Upgrade | 1a | 1268 | Northeast Utilities | 2012 | 12/2012 |  | 345kV Northfield Mountain to Berkshire (portion of 312) line structure replacements | Planned | 7900000 | 7900000
Reliability Upgrade | 1a | 673 | National Grid, USA | 2012 | 12/2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | National Grid, USA | 2012 | 12/2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Planned | 30000000 | 30000000
Reliability Upgrade | 1a | 1201 | NSTAR Electric Company | 2012 | 12/2012 | Greater Boston - North | 115kV line Reconductoring of the P168/128-518 Line between Chelsea and Revere (NSTAR Portion of the line) | Planned | 1500000 | 1500000
Reliability Upgrade | 1a | 1168 | Holyoke Gas & Electric | 2012 | 12/2012 | North Canal 44P | Loop the 1525 (Holyoke Fairmont South 115kV) line into the new North Canal 44P | Planned | 4100000 | 4100000
Reliability Upgrade | 1a | 1095 | National Grid, USA | 2012 | 12/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | 73800000 | 73800000
Reliability Upgrade | 1a | 1106 | National Grid, USA | 2012 | 06/2012 | NEEWS (Rhode Island Reliability Project) | Kent County Substation Upgrades related to third 345/115 kV Autotransformer. | Planned | 26000000 | 26000000
Reliability Upgrade | 1a | 1096 | National Grid, USA | 2012 | 06/2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | 12000000 | 12000000
Reliability Upgrade | 1a | 1099 | National Grid, USA | 2012 | 06/2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | 6000000 | 6000000
Reliability Upgrade | 1a | 1227 | Northeast Utilities | 2012 | 2012 | LSP - Stamford Area | Add 4th transformer and build a five breaker ring bus at South End Substation | Planned | 6400000 | 6400000
Reliability Upgrade | 1b | 843 | NSTAR Electric Company | 2012 | 06/2012 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Proposed | 3450000 | 3450000
Reliability Upgrade | 1b | 1242 | CMEEC | 2012 | 10/2012 | SNEW 115kV substation | SNEW 115/13.8kV substation with two transformers and a 115kV circuit breaker looped into the 1890 line (between Norwalk Hbr - Ely Ave) | Proposed | 2000000 | 2000000
Reliability Upgrade | 1a | 143 | Bangor Hydro-Electric Company | 2012 | 12/2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation (2 new breakers) to Harrington Substation to Epping Substation (3 new breakers) | Under Construction | 66100000 | 66100000
Reliability Upgrade | 1a | 1182 | Northeast Utilities | 2012 | 06/2012 | LSP New Eagle Substation and 115/34.5KV transformer | New 115kV Eagle Substation connected to 115/34.5kV Thornton Substation | Under Construction | 22800000 | 22800000
Reliability Upgrade | 1a | 934 | National Grid, USA | 2012 | 12/2012 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Under Construction | Part of RSP 935 | Part of RSP 935
Reliability Upgrade | 1a | 935 | National Grid, USA | 2012 | 12/2012 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Under Construction | 10200000 | 10200000
Reliability Upgrade | 1a | 944 | National Grid, USA | 2012 | 03/2012 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Under Construction | 15700000 | 15700000
Reliability Upgrade | 1a | 1216 | Northeast Utilities | 2012 | 04/2012 |  | 345kV Ludlow - Northfield (portion of 354) Line Structure replacements | Under Construction | 25100000 | 25100000 | 3-2012 Concept
Reliability Upgrade | 1a | 969 | NSTAR Electric Company | 2012 | 11/2012 | Greater Boston - North | Add a new 115kV 36.7 MVAR capacitor bank at Chelsea. | Under Construction | 1500000 | 1500000 | 32-2012 Planned
Reliability Upgrade | 1a | 1065 | NSTAR Electric Company | 2012 | 07/2012 | NPCC BPS Compliance | Waltham Station | Under Construction | 14700000 | 14700000 | 2 -2012 Proposed
Reliability Upgrade | 1a | 1193 | United Illuminating Company | 2012 | 12/2012 |  | North Haven 115kV Capacitor Bank TRV Mitigation Project | Under Construction | 4900000 | 4900000 | 12 -2012 UnderConstruct
Reliability Upgrade | 1a | 1111 | United Illuminating Company | 2012 | 01/2012 |  | Union Avenue 115/26.4 kV Substation | Under Construction | 13500000 | 13500000
Reliability Upgrade | 1a | 976 | United Illuminating Company | 2012 | 05/2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Under Construction | 70000000 | 70000000
Reliability Upgrade | 1a | 1196 | Bangor Hydro-Electric Company | 2012 | 01/2012 | SVC Filter Upgrade (Part of Keene Rd Auto-transformer ID 144) | Upgrade of filter bank at Chester SVC facility | Under Construction | 3500000 | 3500000
Reliability Upgrade | 1b | 1031 | Bangor Hydro-Electric Company | 2013 | 12/2013 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station | Concept | TBD | TBD
Reliability Upgrade | 1b | 1154 | Bangor Hydro-Electric Company | 2013 | 12/2013 | Maine Power Reliability Program (MPRP) | Rerate Line 66 | Concept | TBD | TBD
Reliability Upgrade | 1b | 1155 | Bangor Hydro-Electric Company | 2013 | 12/2014 | Maine Power Reliability Program (MPRP) | Capacitor Bank Addition (10 MVAr at Trenton 34.5kV and Epping) | Concept | TBD | TBD
Reliability Upgrade | 1b | 593 | NSTAR Electric Company | 2013 | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Bourne and Barnstable/Falmouth/equivalent | Concept | TBD | TBD
Reliability Upgrade | 1b | 1181 | NSTAR Electric Company | 2013 | 12/2013 |  | Rebuild the High Hill 115kV Substation to a Breaker and a half desgin | Concept | TBD | TBD
Reliability Upgrade | 1b | 1205 | NSTAR Electric Company | 2013 | 12/2013 | Mid-Cape Reliability Project | Separate 120 (Canal-Barnstable) /122 (Oak St-Barnstable) DCT | Concept | TBD | TBD
Reliability Upgrade | 1b | 1249 | NSTAR Electric Company | 2013 | 12/2013 |  | Rebuild the Wareham Substation to a breaker and a half scheme | Concept | TBD | TBD
Reliability Upgrade | 1b | 1255 | CELD (Chicopee Electric Light Department) | 2013 | 12/2013 | CELD 115/13.8kV Substation | 115/13.8kV substation on Memorial Dr. with two transformers and twelve feeders looped into 1904 (1723) line between Piper and Fairmont substations | Concept | TBD | TBD
Reliability Upgrade | 1b | 1243 | CMEEC | 2013 | 10/2013 | TTD's Fitch St 115kV Substation | TTD 115/27kV substation with two transformers and a 115kV circuit breaker looped into 1416 line (between Compo and Darien substations) | Concept | TBD | TBD
Reliability Upgrade | 1a | 1197 | Bangor Hydro-Electric Company | 2013 | 12/2013 | Keene Rd Autotransformer | Orrington 345kV Series Breaker Addition | Planned | 1761250 | 1761250
Reliability Upgrade | 1a | 1026 | Central Maine Power Company | 2013 | 12/2013 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction associated with (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Elliot Switching Station) line work | Planned | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | 36000000
Reliability Upgrade | 1a | 1028 | Central Maine Power Company | 2013 | 12/2013 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M
Reliability Upgrade | 1a | 1030 | Central Maine Power Company | 2013 | 11/2013 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Maguire Road) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 680 | National Grid, USA | 2013 | 06/2013 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | 7393000 | 7393000
Reliability Upgrade | 1a | 674 | National Grid, USA | 2013 | 12/2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | 19460000 | 19460000
Reliability Upgrade | 1a | 1170 | Vermont Electric Power Company | 2013 | 06/2013 | Bennington Substation Rebuild | Rebuild the exiting Bennington substation 115kV bus into a ring bus to address reliability problems due to breaker failure contingencies | Planned | 28000000 | 28000000
Reliability Upgrade | 1a | 1195 | Vermont Electric Power Company | 2013 | 03/2013 | Highgate Refurbishment | Replace Highgate controls and cooling system | Planned | 35600000 | 35600000
Reliability Upgrade | 1a | 929 | National Grid, USA | 2013 | 09/2013 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | 2500000 | 2500000
Reliability Upgrade | 1a | 931 | National Grid, USA | 2013 | 01/2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | 531481 | 531481
Reliability Upgrade | 1a | 928 | National Grid, USA | 2013 | 06/2013 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | 3400000 | 3400000
Reliability Upgrade | 1a | 938 | National Grid, USA | 2013 | 05/2013 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | 5430000 | 5430000
Reliability Upgrade | 1a | 941 | National Grid, USA | 2013 | 2013-08-01 | Central/Western Massachusetts Upgrades | Install new Z126 Millbury - Tower #510 115 kV line. | Planned | 13748000 | 13748000
Reliability Upgrade | 1a | 687 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | 718000000 | 718000000
Reliability Upgrade | 1a | 826 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1078 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1202 | NSTAR Electric Company | 2013 | 06/2013 | NEEWS (Ancillary Interstate Reliability Project) | Rebuild 1.2 mile length of line 336 with 2-900 ACSS conductor and replace 5, 345kV 2000 amp disconnect switches with 3000 amp switches at W. Medway station | Planned | 1700000 | 1700000
Reliability Upgrade | 1a | 1256 | Unitil | 2013 | 06/2013 | Flagg Pond Upgrades | At Flagg Pond Substation upgrade terminal equipment on the I-135N, I-135S, J-136N and J-136S 115kV lines and Zone 3 relay upgrades for the J-136N 115kV line. | Planned | 2750000 | 2750000
Reliability Upgrade | 1a | 795 | National Grid, USA | 2013 | 04/2013 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV (359) line. | Planned | 69000000 | 69000000
Reliability Upgrade | 1a | 1097 | National Grid, USA | 2013 | 01/2013 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County including S-175, T172N and T-172S with associated terminal equipment upgrade. | Planned | 129800000 | 129800000
Reliability Upgrade | 1a | 1241 | National Grid, USA | 2013 | 06/2013 |  | Re-condustor G-185S (Kent County - Davisville Tap) | Planned | 4200000 | 4200000
Reliability Upgrade | 1a | 1054 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Build a new 345 kV line from Manchester to Meekville Junction and re-terminate the 395 line at Meekville Junction | Planned | 28800000 | 28800000
Reliability Upgrade | 1a | 1218 | Northeast Utilities | 2013 | 12/2013 | Millstone 345kV Circuit Separation project & SLOD SPS System Retirement | Separate the 345kV Double Circuit Tower 310/348 and 371/383 Tower configuration | Planned | 25600000 | 25600000
Reliability Upgrade | 1b | 1175 | NSTAR Electric Company | 2013 | 12/2013 | Greater Boston - South | Upgrade the 115kV line 201-501 (Medway-Depot St.) and the 201-502 (Beaver Pond - Depot Street Tap) to a higher capacity line | Proposed | 3700000 | 3700000
Reliability Upgrade | 1b | 1246 | United Illuminating Company | 2013 | 09/2013 | 8300 Line Reconfiguration Project | Reconfiguration of 115kV (8300) line from Mill River to Quinnipiac | Proposed | 17400000 | 17400000
Reliability Upgrade | 1a | 887 | National Grid, USA | 2013 | 06/2013 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Under Construction | 58000000 | 58000000
Reliability Upgrade | 1a | 196 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct the 115kV line South Agawam to Southwick (1768) | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVar Capacitor additions | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | 9-2013 Concept
Reliability Upgrade | 1a | 1074 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | 27 - 2013 Planned
Reliability Upgrade | 1a | 1092 | Northeast Utilities | 2013 | 12/2013 | Agawam (BPS) | Upgrade the Agawam 115kV, Subtations to BPS standards together with other misc. subatation upgrades | Under Construction | 12100000 | 12100000 | 2 -2013 Proposed
Reliability Upgrade | 1a | 974 | United Illuminating Company | 2013 | 05/2013 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Under Construction | 16900000 | 16900000 | 24 -2013 UnderConstruct
Reliability Upgrade | 1a | 816 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1b | 1248 | NSTAR Electric Company | 2014 | 12/2014 |  | Rebuild the Kingston Substation to a breaker and a half scheme | Concept | TBD | TBD
Reliability Upgrade | 1b | 699 | United Illuminating Company | 2014 | 12/2014 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | 11100000 | 11100000
Reliability Upgrade | 1a | 907 | Central Maine Power Company | 2014 | 05/2014 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 203 (Detroit-Orrington), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | Central Maine Power Company | 2014 | 2014-08-02 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast forming Sections 86 & 266 | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | Central Maine Power Company | 2014 | 05/2014 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377, 115kV Bucksport 65/205) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1132 | Central Maine Power Company | 2014 | 2014-08-02 | Maine Power Reliability Program (MPRP) | Add 115/34kV transformer at Coopers Mills | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 919 | National Grid, USA | 2014 | 04/2014 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | 13600000 | 13600000
Reliability Upgrade | 1a | 1187 | National Grid, USA | 2014 | 06/2014 | A127/B128 Conductor Refurbishment | A127/B128 Conductor Refurbishment - Tower 510 to Harriman Substation, VT | Planned | 65000000 | 65000000
Reliability Upgrade | 1a | 940 | National Grid, USA | 2014 | 06/2014 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS (A127 West reconductoring. Tower 510 to Paxton, French King to French King). | Planned | 18000000 | 18000000
Reliability Upgrade | 1a | 945 | National Grid, USA | 2014 | 05/2014 | Central/Western Massachusetts Upgrades | Adams - install two new 115 kV breakers and replace two existing 115kV breakers | Planned | 5000000 | 5000000
Reliability Upgrade | 1a | 948 | National Grid, USA | 2014 | 05/2014 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | 13400000 | 13400000
Reliability Upgrade | 1a | 951 | National Grid, USA | 2014 | 01/2014 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon (H-134) 115 kV line. | Planned | 7455440 | 7455440
Reliability Upgrade | 1a | 791 | National Grid, USA | 2014 | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | 11560000 | 11560000
Reliability Upgrade | 1a | 913 | National Grid, USA | 2014 | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | 3250000 | 3250000
Reliability Upgrade | 1a | 914 | National Grid, USA | 2014 | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | 28150000 | 28150000
Reliability Upgrade | 1a | 917 | National Grid, USA | 2014 | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | 7000000 | 7000000
Reliability Upgrade | 1a | 793 | National Grid, USA | 2014 | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | 6400000 | 6400000
Reliability Upgrade | 1a | 1257 | National Grid, USA | 2014 | 06/2014 | Salem Harbor Retirement | 115kV line Reconductoring of the S-145/T-146 from Tewksbury-North Reading Tap (9.3 miles each) | Planned | 29000000 | 29000000
Reliability Upgrade | 1a | 1258 | National Grid, USA | 2014 | 06/2014 | Salem Harbor Retirement | 115kV line Reconductoring of the Y-151 from Tewksbury Junction - West Methuen (8.2 miles) | Planned | 11500000 | 11500000
Reliability Upgrade | 1a | 1259 | National Grid, USA | 2014 | 06/2014 | Salem Harbor Retirement | 115kV line Reconductoring of the B154/C-155N from King St Tap - South Danvers (14.5 miles each way) | Planned | 20000000 | 20000000
Reliability Upgrade | 1a | 915 | National Grid, USA | 2014 | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | National Grid, USA | 2014 | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | 11800000 | 11800000
Reliability Upgrade | 1a | 918 | National Grid, USA | 2014 | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | 3180000 | 3180000
Reliability Upgrade | 1b | 1279 | Central Maine Power Company | 2014 | 12/2014 |  | New 345/115kV Autotransformer and 115kV switchyard at Raven Farm substation consisting of a four-bay breaker and a half configuration of eleven (11) breakers | Proposed | 26126000 | 26126000
Reliability Upgrade | 1b | 1280 | Central Maine Power Company | 2014 | 12/2014 |  | New 115kV line section 244 and upgraded line section 80 between Coopers Mill and Highland Substations | Proposed | 62735000 | 62735000
Reliability Upgrade | 1b | 1183 | Northeast Utilities | 2014 | 2014 | LSP New Peaselee Substation and 115/34.5KV transformer | New 115kV Peaselee Substation and transmission line work | Proposed | 12400000 | 12400000
Reliability Upgrade | 1b | 965 | NSTAR Electric Company | 2014 | 06/2014 | Greater Boston - South | Add third 115kV line from W. Walpole to Holbrook | Proposed | 19000000 | 19000000
Reliability Upgrade | 1b | 1208 | National Grid, USA | 2014 | 12/2014 | Pittsfield / Greenfield Project | Separation and reconductoring of Cabot Taps (A-127 and Y-177 115kV lines) | Proposed | 7400000 | 7400000
Reliability Upgrade | 1b | 1209 | National Grid, USA | 2014 | 12/2014 | Pittsfield / Greenfield Project | Reconductoring of A-127 between Erving and Cabot Tap with 1590 ACSS | Proposed | 12000000 | 12000000
Reliability Upgrade | 1b | 1210 | National Grid, USA | 2014 | 12/2014 | Pittsfield / Greenfield Project | Harriman 115kV breaker upgrades | Proposed | 1100000 | 1100000
Reliability Upgrade | 1b | 1221 | Northeast Utilities | 2014 | 11/2014 | Pittsfield / Greenfield Project | Modify Northfield Mountain 16R substation and install a 345/115Kv autotransformer | Proposed | 108500000 | 108500000
Reliability Upgrade | 1b | 1222 | Northeast Utilities | 2014 | 11/2014 | Pittsfield / Greenfield Project | Build a new 115kV three breaker Swithching Station (Erving) ring bus | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1223 | Northeast Utilities | 2014 | 11/2014 | Pittsfield / Greenfield Project | Build a new 115kV line from Northfield Mountain to the new Erving Switching Station | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1224 | Northeast Utilities | 2014 | 11/2014 | Pittsfield / Greenfield Project | Install 115kV 14.4 MVAR capacitor banks at Cumberland, Podick and Amherst Substations | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1225 | Northeast Utilities | 2014 | 11/2014 | Pittsfield / Greenfield Project | Rebuild the Cumberland to Montague 1361 115kV line and terminal work at Cumberland and Montague | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1226 | Northeast Utilities | 2014 | 11/2014 | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | 2-2014 Concept
Reliability Upgrade | 1a | 905 | Central Maine Power Company | 2014 | 2014-08-02 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Under Construction | 1364108000 | 1364108000 | 21 - 2014 Planned
Reliability Upgrade | 1a | 906 | Central Maine Power Company | 2014 | 05/2014 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Larrabee Road-Middle St,Middle St -Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Under Construction | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | 13 -2014 Proposed
Reliability Upgrade | 1a | 908 | Central Maine Power Company | 2014 | 07/2014 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road); Coopers Mills autotransforme replaces Maxcy's autotransformer | Under Construction | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | 4 -2014 UnderConstruct
Reliability Upgrade | 1a | 1158 | Central Maine Power Company | 2014 | 07/2014 | Maine Power Reliability Program (MPRP) | Two 40 MVAR reactors at Albion Road, two 40 MVAR reactors at Larabee Road, two 40 MVAR at Coopers Mills | Under Construction | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1b | 1177 | NSTAR Electric Company | 2015 | 12/2015 | Greater Boston - North | Reconductor 211-503/504 from North Woburn Tap to Reading | Concept | TBD | TBD
Reliability Upgrade | 1b | 1178 | NSTAR Electric Company | 2015 | 12/2015 | Greater Boston - North | Install 115kV Capacitor Bank at North Woburn | Concept | TBD | TBD
Reliability Upgrade | 1b | 1190 | NSTAR Electric Company | 2015 | 12/2015 | Greater Boston - North | Install a second 345/115kV Auto Transformer at Woburn | Concept | TBD | TBD
Reliability Upgrade | 1b | 1189 | NSTAR Electric Company | 2015 | 12/2015 | Greater Boston - Central | Install 3rd 115kV Circuit between Waltham and Brighton | Concept | TBD | TBD
Reliability Upgrade | 1b | 1234 | National Grid, USA | 2015 | 12/2015 | NEEWS (Interstate Reliability Project) | Install a 115kV redundant breaker in series with breaker #1713 at West Farmum Substation and upgrade to current BPS standards | Concept | TBD | TBD
Reliability Upgrade | 1b | 975 | United Illuminating Company | 2015 | 06/2015 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | 105000000 | 105000000
Reliability Upgrade | 1a | 1141 | Northeast Utilities | 2015 | 2015 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 950 | National Grid, USA | 2015 | 02/2015 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | 1016897 | 1016897
Reliability Upgrade | 1a | 953 | National Grid, USA | 2015 | 02/2015 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | 10248067 | 10248067
Reliability Upgrade | 1a | 954 | National Grid, USA | 2015 | 02/2015 | Central/Western Massachusetts Upgrades | Westminster - install new 69kV breaker, including disconnect switches. | Planned | 903909 | 903909
Reliability Upgrade | 1a | 946 | National Grid, USA | 2015 | 04/2015 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer- Hampden to 115 kV. | Planned | 16000000 | 16000000
Reliability Upgrade | 1a | 949 | National Grid, USA | 2015 | 04/2015 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | 1600000 | 1600000
Reliability Upgrade | 1a | 937 | National Grid, USA | 2015 | 12/2015 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | 6602875 | 6602875
Reliability Upgrade | 1a | 1094 | National Grid, USA | 2015 | 12/2015 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | 25000000 | 25000000
Reliability Upgrade | 1a | 190 | National Grid, USA | 2015 | 12/2015 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | 81800000 | 81800000
Reliability Upgrade | 1a | 794 | National Grid, USA | 2015 | 12/2015 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | 71700000 | 71700000
Reliability Upgrade | 1a | 1253 | National Grid, USA | 2015 | 04/2015 |  | New Crandall St. Substation 115-13 kV substation addition | Planned | 3000000 | 3000000
Reliability Upgrade | 1a | 802 | Northeast Utilities | 2015 | 2015 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | 218000000 | 218000000
Reliability Upgrade | 1a | 1085 | Northeast Utilities | 2015 | 2015 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | Northeast Utilities | 2015 | 2015 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | Northeast Utilities | 2015 | 2015 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1235 | Northeast Utilities | 2015 | 12/2015 | NEEWS (Ancillary Interstate Reliability Project) | Sag elimination on 1410 Line (Montville-Buddington) | Planned | 3000000 | 3000000
Reliability Upgrade | 1a | 1245 | CMEEC | 2015 | 12/2015 | NEEWS (Ancillary Interstate Reliability Project) | Sag elimination on 1410 Line (Montville-Buddington) | Planned | 60000 | 60000
Reliability Upgrade | 1a | 721 | United Illuminating Company | 2015 | 06/2015 |  | New Shelton 115/13.8 kV substation | Planned | 19500000 | 19500000
Reliability Upgrade | 1b | 1220 | Northeast Utilities | 2015 | 12/2015 | Greater Boston - North | Install a new 345kV circuit between Scobie and Pelham NH (this is NU's portion of the new Scobie-Tewksbury circuit) | Proposed | 40100000 | 40100000
Reliability Upgrade | 1b | 1214 | National Grid, USA | 2015 | 12/2015 | Greater Boston - South | Line Reconductoring of the C-129 Beaver Pond - Depot St. Tap) and D-130 (Depot St. Tap - Medway) 115kV lines | Proposed | 500000 | 500000
Reliability Upgrade | 1b | 1179 | NSTAR Electric Company | 2015 | 12/2015 | Greater Boston - North | Install 2nd 345kV circuit between Bellerica/Burlington town line to Tewksbury | Proposed | 33000000 | 33000000
Reliability Upgrade | 1b | 1211 | National Grid, USA | 2015 | 12/2015 | Greater Boston - North | Install 2nd 345kV circuit between Tewksbury - Billerica/Burlington Town Line (NSTAR Border) | Proposed | 32700000 | 32700000
Reliability Upgrade | 1b | 1212 | National Grid, USA | 2015 | 12/2015 | Greater Boston - North | 115kV Line Reconductoring of M-139/N-140 Tewksbury-Pinehurst (6.1 miles each) | Proposed | 11600000 | 11600000
Reliability Upgrade | 1b | 1213 | National Grid, USA | 2015 | 12/2015 | Greater Boston - North | Install new 345kV circuit between NH/MA border and Tewksbury (this is NGRID's portion of the new Scobie-Tewksbury circuit) | Proposed | 23370000 | 23370000
Reliability Upgrade | 1b | 1215 | National Grid, USA | 2015 | 12/2015 | Greater Boston - North | New 115kV line between Wakefield - Everett | Proposed | 20000000 | 20000000
Reliability Upgrade | 1b | 1254 | National Grid, USA | 2015 | 12/2015 | Greater Boston - North | Substation work at Revere Substation to increase ratings on the 128-515P/168 line between Chelsea and Revere | Proposed | 1000000 | 1000000
Reliability Upgrade | 1b | 1260 | National Grid, USA | 2015 | 12/2015 | Greater Boston - North | 115kV Line reconductoring of the F-158N/S Wakefield Jct - Everett (7.36 miles) | Proposed | 3500000 | 3500000 | 6 -2015 Concept
Reliability Upgrade | 1b | 1261 | National Grid, USA | 2015 | 12/2015 | Greater Boston - North | 115kV Line reconductoring of the S-145T-146 from North Reading Tap - Wakefield Jct (5.1 miles each) | Proposed | 10800000 | 10800000 | 18 - 2015 Planned
Reliability Upgrade | 1b | 1262 | National Grid, USA | 2015 | 12/2015 | Greater Boston - North | 115kV Line reconductoring of theY-151 from Tewksbury Junction - Tewksbury Substation (1.6 miles) | Proposed | 1250000 | 1250000 | 14 -2015 Proposed
Reliability Upgrade | 1b | 956 | National Grid, USA | 2015 | 01/2015 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Proposed | 7021534 | 7021534 | 0 -2015 UnderConstruct
Reliability Upgrade | 1b | 1252 | National Grid, USA | 2015 | 12/2015 | NEEWS (Interstate Reliability Project) | Re-conductor 345kV 328 line (West Farnum-Sherman Rd) | Proposed | 36500000 | 36500000
Reliability Upgrade | 1b | 1233 | National Grid, USA | 2015 | 12/2015 | NEEWS (Interstate Reliability Project) | New Sherman Road 345kV AIS Substation | Proposed | 36600000 | 36600000 | 1 -2016 Concept
Reliability Upgrade | 1b | 1250 | Vermont Electric Power Company | 2016 | 2016 | VELCO LSP - West Rutland Substation | Installation of a 115/46kV transformer at West Rutland between breakers K30 and K34 | Concept | TBD | TBD | 3 - 2016 Planned
Reliability Upgrade | 1a | 782 | National Grid, USA | 2016 | 01/2016 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor and Railyard. | Planned | 43912000 | 43912000 | 0 -2016 Proposed
Reliability Upgrade | 1a | 576 | Northeast Utilities | 2016 | 2016 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | 301000000 | 301000000 | 0 -2016 UnderConstruct
Reliability Upgrade | 1a | 1114 | Northeast Utilities | 2016 | 2016 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1b | 325 | Vermont Electric Power Company | TBD | TBD | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | TBD | TBD
Reliability Upgrade | 1b | 324 | Vermont Electric Power Company | TBD | TBD |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | TBD | TBD
Reliability Upgrade | 1b | 139 | Vermont Electric Power Company | TBD | TBD | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Concept | TBD | TBD | 18 - Concept TBD
Reliability Upgrade | 1b | 970 | NSTAR Electric Company | TBD | TBD | Greater Boston - Central | Add a new 345 kV line from Lexington to Waltham. | Concept | TBD | TBD | 1- Planned TBD
Reliability Upgrade | 1b | 971 | NSTAR Electric Company | TBD | TBD | Greater Boston - Central | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | TBD | TBD | 12- Proposed TBD
Reliability Upgrade | 1b | 1176 | NSTAR Electric Company | TBD | TBD | Greater Boston - Central | Install an oil circulation pipe and heat exchangers at K Street and Chatham Street sections of 250-516/517 circuits | Concept | TBD | TBD
Reliability Upgrade | 1b | 1198 | NSTAR Electric Company | TBD | TBD | Greater Boston - Central | Add a second 115kV line from Woburn to Burlington | Concept | TBD | TBD
Reliability Upgrade | 1b | 1199 | NSTAR Electric Company | TBD | TBD | Greater Boston - Central | Install a new 230/115kV auto transformer at Sudbury or equivalent | Concept | TBD | TBD
Reliability Upgrade | 1b | 1247 | NSTAR Electric Company | TBD | TBD |  | Rebuild the Acushnet 115kV Substation | Concept | TBD | TBD
Reliability Upgrade | 1b | 1084 | Northeast Utilities | TBD | TBD | Greater Hartford Central Connecticut Project | Loop the Millstone - Manchester (310) 345 kV line into the Card substation (2) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1086 | Northeast Utilities | TBD | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow (2) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1087 | Northeast Utilities | TBD | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford (2) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1088 | Northeast Utilities | TBD | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow (2) | Concept | TBD | TBD
Reliability Upgrade | 1b | 801 | Northeast Utilities | TBD | TBD |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Concept | TBD | TBD
Reliability Upgrade | 1b | 85 | Northeast Utilities | TBD | TBD |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | TBD | TBD
Reliability Upgrade | 1b | 1228 | Northeast Utilities | TBD | TBD | Stamford Area | Additional circuit into the Stamford Area (Glenbrook-South End) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1229 | Northeast Utilities | TBD | TBD |  | Replace 115kV 1990 (Frost Bridge-Stevenson) lattice structure | Concept | TBD | TBD
Reliability Upgrade | 1b | 1230 | Northeast Utilities | TBD | TBD | LSP - Greater Hartford Area | 115kV breaker addition at Northeast Simsbury Substation | Concept | TBD | TBD
Reliability Upgrade | 1a | 879 | Bangor Hydro-Electric Company | TBD | TBD | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | 420000 | 420000
Reliability Upgrade | 1b | 1269 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | Amherst Substation - New 345kV breaker and three 25MVar Capacitor Banks | Proposed | 19600000 | 19600000
Reliability Upgrade | 1b | 1270 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | New 115kV line from Fitzwilliiams to Monadnock | Proposed | 10500000 | 10500000
Reliability Upgrade | 1b | 1271 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | Upgrade the Keene to Monadnock (T198) 115kV line | Proposed | 11900000 | 11900000
Reliability Upgrade | 1b | 1272 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | Weare Substation - Add two 13.3 MVar 115V capacitors | Proposed | 3600000 | 3600000
Reliability Upgrade | 1b | 1273 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | Rebuild A152 115kV line | Proposed | 22500000 | 22500000
Reliability Upgrade | 1b | 1274 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | Rebuild N186 115kV line | Proposed | 2300000 | 2300000
Reliability Upgrade | 1b | 1275 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | Upgrade the 381 345kV line | Proposed | 4200000 | 4200000
Reliability Upgrade | 1b | 1276 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | Littleton Substation - Add a second 230/115kV autotransformer and associated 115kV substation work | Proposed | 16700000 | 16700000
Reliability Upgrade | 1b | 1277 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | Webster Substation - Add four 26.6 MVar 115kV capacitors | Proposed | 11900000 | 11900000
Reliability Upgrade | 1b | 1278 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | Saco Valley Substation - Add two 25 MVar dynamic Var devices | Proposed | 15800000 | 15800000
Reliability Upgrade | 1b | 1263 | National Grid, USA | TBD | TBD | Northern New Hsmpshire Solution | New C-203 230kV line tap to Littleton NH Substation associated with 2nd 230/115kV auto project | Proposed | 1100000 | 1100000
Reliability Upgrade | 1b | 1200 | NSTAR Electric Company | TBD | TBD | Greater Boston - North | Add a new 345kV UG circuit between Woburn and North Cambridge | Proposed | 52000000 | 52000000
5460853715

## SORTED-ByISD-Then STATUS10-09-2 (hidden)
October '09 ISO-NEW ENGLAND Project Listing Update (DRAFT)
Primary Driver | Part# | Project ID | Primary Equipment Owner | Projected In-Service Month/Year | Projected In-Service Year | Major Project | Project | Oct -09 Status | Oct-09 Estimated PTF Costs
Data Set for Investment Chart by Status
[11 empty] | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | TBD
[10 empty] | In-Service | 2006: 493.8219; Data Set for Investment Chart by Status 2007: 326.52; Data Set for Investment Chart by Status 2008: 1912.1831; Data Set for Investment Chart by Status 2009: 800; Data Set for Investment Chart by Status 2010: 11.2
[10 empty] | Under Construction | Data Set for Investment Chart by Status 2010: 304.8332; Data Set for Investment Chart by Status 2011: 153.019
[10 empty] | Planned | Data Set for Investment Chart by Status 2010: 107.4322; Data Set for Investment Chart by Status 2011: 157.0976; Data Set for Investment Chart by Status 2012: 2468.4786; Data Set for Investment Chart by Status 2013: 1602.4638; Data Set for Investment Chart by Status 2014: 173.902; Data Set for Investment Chart by Status 2015: 20 | 0.42
[10 empty] | Proposed | Data Set for Investment Chart by Status 2010: 4.55; Data Set for Investment Chart by Status 2011: 50.426; Data Set for Investment Chart by Status 2012: 9.3 | 6.838
[10 empty] | Concept |  |  |  |  | 0.95 | 21.6 | 0 | 0 | 11.1 | 74.8015 |  | 1.33 | 1.2 | 0
[10 empty] | total |  |  | 1912.1831 | 800 | 428.9654 | 382.1426 | 2477.7786 | 1602.4638 | 185.002 | 94.8015 | 0 | 1.33 | 1.2 | 7.258
[13 empty] | NOTE- Total I/S costs as of Oct 2008 Update: |  |  | 1431150385
Data Set for Investment Chart - cumulative
[13 empty] | In-Service | UC+PL+PR | UC+PL+PR+C
[12 empty] | 2002 | 15.8
[12 empty] | 2009-10-09 | 3876.3238 | 3876.3238 | 3876.3238 | 131315 | 0.0059039
[12 empty] | 2009-12-09 | 3876.3238 | 3876.3238 | 3876.3238 | 131315 | 0.0059039
[12 empty] | 2010 | 3876.3238 | 4293.1392 | 4294.0892 | 131330 | 0.0065379
[12 empty] | 2011 | 3876.3238 | 4653.6818 | 4676.2318 | 132350 | 0.0070324
[12 empty] | 2012 | 3876.3238 | 7131.4603 | 7154.0103 | 134015 | 0.010643
[12 empty] | 2013 | 3876.3238 | 8733.9241 | 8756.4741 | 134635 | 0.012974
Reliability Upgrade | 1a | 910 | Central Maine Power Company | 12/2008 | 2008 | Rumford-Woodstock-Kimball Road Corridor Project | Rebuild Section 211 Woodstock - Rumford. | In-Service | 8400000 | 8400000
Reliability Upgrade | 1a | 177 | Northeast Utilities | 12/2008 | 2008 | Monadnock Area Reliability Project | Replace limiting terminal equipment at Webster Substation on line to North Road. | In-Service | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 180 | Northeast Utilities | 12/2008 | 2008 | Monadnock Area Reliability Project | Rebuild 115 kV Keene to Swanzey A-152 line. | In-Service | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 138 | Vermont Electric Power Company | 12/2008 | 2008 | Northwest Vermont Reliability Project | N. Haven - Vergennes - Q. City 115 kV line. | In-Service | 70200000 | 70200000
Reliability Upgrade | 1a | 923 | National Grid, USA | 12/2008 | 2008 | Auburn Area Transmission System Upgrades | Reconductor 115 kV A94 line and associated substation upgrades. | In-Service | 2400000 | 2400000
Reliability Upgrade | 1a | 781 | National Grid, USA | 10/2008 | 2008 | Merrimack Valley/North Shore Reliability Project | Install 115 kV 30 MVAr capacitor bank at Revere. | In-Service | 1727000 | 1727000
Reliability Upgrade | 1a | 841 | NSTAR Electric Company | 11/2008 | 2008 | Mystic Breaker Additions Project | Install (2) new 115 kV West Bus breakers #29 and #31 at Mystic. | In-Service | 2300000 | 2300000
Reliability Upgrade | 1a | 1040 | NSTAR Electric Company | 12/2008 | 2008 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #11, #8, #17 and #3 at Mystic to IPT | In-Service | 990000 | 990000
Reliability Upgrade | 1a | 168 | National Grid, USA | 09/2008 | 2008 | Southwest Rhode Island Reliability Enhancements | Reconductor Kenyon - Wood River 115 kV 1870 line. | In-Service | 2234232 | 2234232
Reliability Upgrade | 1a | 899 | National Grid, USA | 12/2008 | 2008 | Southwest Rhode Island Reliability Enhancements | Kenyon substation upgrades. | In-Service | 278000 | 278000
Reliability Upgrade | 1a | 171 | National Grid, USA | 10/2008 | 2008 | Southwest Rhode Island Reliability Enhancements | Reconductoring L-190 between Kent Co. and Davisville. | In-Service | 2666291 | 2666291
Reliability Upgrade | 1a | 900 | National Grid, USA | 11/2008 | 2008 | Southwest Rhode Island Reliability Enhancements | Wood River substation upgrades. | In-Service | 130000 | 130000
Reliability Upgrade | 1a | 846 | United Illuminating Company | 11/2008 | 2008 |  | Replace Mix Avenue 115 kV Oil Circuit Breaker & foundation. | In-Service | 450000 | 450000
Reliability Upgrade | 1a | 208 | Northeast Utilities | 12/2008 | 2008 | NU LSP - Oxford Substation | Install new Oxford (previously Jack's Hill) 115 kV substation. | In-Service | 4459000 | 4459000
Reliability Upgrade | 1a | 571 | Northeast Utilities | 12/2008 | 2008 | Norwalk-Glenbrook Cable Project | Upgrade Flax Hill Substation to BPS. | In-Service | Part of project 248 | Part of project 248
Reliability Upgrade | 1a | 248 | Northeast Utilities | 12/2008 | 2008 | Norwalk-Glenbrook Cable Project | Install two new 115 kV cables from Norwalk to Glenbrook (accommodate 345 kV class cable). | In-Service | 249372000 | 249372000
Reliability Upgrade | 1a | 246 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Add second 345/115 kV autotransformer at Norwalk Substation along with shunt reactors and 345 kV circuit breakers. | In-Service | 978182000 | 978182000
Reliability Upgrade | 1a | 238 | United Illuminating Company | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Build new Singer 345 kV substation with (12) circuit breakers, (2) autos, (4) shunt reactors along with reconnecting Bridgeport Energy thru one of the new autos. Includes 115 kV connection from Singer to Pequonnock substation. | In-Service | 162264000 | 162264000
Reliability Upgrade | 1a | 224 | United Illuminating Company | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install new 345 kV line from East Devon to Singer(UI). | In-Service | 157476000 | 157476000
Reliability Upgrade | 1a | 226 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install two 345 kV underground cables from Singer(UI) to Norwalk. | In-Service | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 235 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Expand Norwalk 345-kV substation and install transfer trip relaying scheme on the 1389 115 kV line between Norwalk and Flax Hill. | In-Service | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 247 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Replace Norwalk Harbor 138/115 kV autotransformer. | In-Service | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 684 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Replace (6) 115 kV breakers (4-Glenbrook, 1-Glenbrook Statcom, 1-Southington #1) and (3) 345-kV circuit breakers at Millstone and replace (4) 345- kV breakers with 500-kV breakers at Long Mountain substation. | In-Service | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 250 | Northeast Utilities | 12/2008 | 2008 |  | Add a 345 kV breaker at Ludlow Substation. | In-Service | 1644885 | 1644885
Reliability Upgrade | 1a | 155 | Central Maine Power Company | Northeast Utilities | 2009 | Maguire Road Project | Rebuild Three Rivers - Quaker Hill 115 kV Line K197. | In-Service | 5500000 | 5500000
Reliability Upgrade | 1a | 178 | Northeast Utilities | 02/2009 | 2009 | Monadnock Area Reliability Project | Rebuild 115 kV Garvins to Webster V-182 line. | In-Service | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 922 | National Grid, USA | 02/2009 | 2009 | Auburn Area Transmission System Upgrades | Reconductor 115kV L1 line and associated substation upgrades. | In-Service | 800000 | 800000
Reliability Upgrade | 1a | 116 | NSTAR Electric Company | 04/2009 | 2009 | NSTAR 345 kV Transmission Reliability Project | Add 2nd 345 kV UG Cables from Stoughton to Mattapan Sq.to K Street and install another new autotransformer at K. St. | In-Service | 307900000 | 307900000
Reliability Upgrade | 1a | 572 | NSTAR Electric Company | 04/2009 | 2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 345 kV 160 MVAR shunt reactors at Stoughton. | In-Service | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 573 | NSTAR Electric Company | 04/2009 | 2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 345 kV 160 MVAR shunt reactors at K St. | In-Service | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 772 | NSTAR Electric Company | 04/2009 | 2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 115 kV breaker at K St. | In-Service | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 136 | Vermont Electric Power Company | 04/2009 | 2009 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 1: two 115 kV PARs, four 25 MVAR Cap. banks, four +25/-12.5 MVAR synchronous condenders, and two 230/115 transformers. | In-Service | 62400000 | 62400000
Reliability Upgrade | 1a | 695 | NSTAR Electric Company | 07/2009 | 2009 | Short Term Lower SEMA Upgrades | Loop (355) 345 kV line in and out of Carver Substation and add (5) new 345 kV circuit breakers at Carver substation. | In-Service | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 830 | NSTAR Electric Company | 07/2009 | 2009 | Short Term Lower SEMA Upgrades | Add a second 345/115 kV Auto transformer at Carver substation and add (1) new 345 kV circuit breaker and (3) new 115 kV circuit breakers at Carver substation. | In-Service | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 831 | NSTAR Electric Company | 07/2009 | 2009 | Short Term Lower SEMA Upgrades | Add a second 115 kV line from Carver to Tremont and add (2) new 115 kV circuit breakers at Carver substation and (1) new 115 kV circuit breaker at Tremont substation. | In-Service | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 626 | Central Maine Power Company | 04/2009 |  | Rumford-Woodstock-Kimball Road Corridor Project | Addition of 115/34.5 kV transformer and six new 115 kV breakers and a half substation at Woodstock. | In-service | 8000000 | 8000000
Reliability Upgrade | 1a | 575 | Central Maine Power Company | 05/2009 |  | Heywood Road Project | New Heywood Rd 115kV switchyard with (6) 115kV circuit breakers (3) 115kV line retensionings and 115kV 20 MVAr capacitor bank at Heywood Rd. | In-service | 7000000 | 7000000
Reliability Upgrade | 1a | 1127 | Central Maine Power Company | 05/2009 |  | CMP-LSP Newcastle Substation | Add 115/34kV transformer with two 115kV breakers | In-service | 1300000 | 1300000
Reliability Upgrade | 1a | 166 | National Grid, USA | 06/2009 |  |  | Replace (16) 115 kV breakers at Tewksbury 22. | In-service | 3300000 | 3300000
Reliability Upgrade | 1a | 1009 | Northeast Utilities | 05/2009 |  |  | Install a 2% reactor on the North Bloomfield-Canton 115kV line and also replacement fo the Frostbridge 345/115kV autotransformer | In-service | 3089000 | 3089000
Reliability Upgrade | 1a | 203 | Northeast Utilities | 05/2009 |  | NU LSP - Stepstone Substation | Install new Stepstone 115 kV substation in Guilford. | In-service | 6332000 | 6332000
Reliability Upgrade | 1a | 1064 | NSTAR Electric Company | 04/2009 |  |  | Install (1) 345kV 160 MVAR shunt reactor at Mystic Station | In-service | 10400000 | 10400000
Reliability Upgrade | 1a | 1051 | Central Maine Power Company | 09/2009 |  | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Riley 115 kV capacitor bank. | In-service | Part of Project 625 | Part of Project 625
Reliability Upgrade | 1a | 267 | Northeast Utilities | 2009-08-01 |  | Y138 Closing | White Lake - Saco Valley (Y138) Line Closing - Add PAR on Y138 at Saco Valley, retension lines, upgrade Beebe terminal, and add capacitor banks at White Lake and Beebe. | In-service | 27775000 | 27775000
Reliability Upgrade | 1a | 936 | National Grid, USA | 07/2009 |  | Central/Western Massachusetts Upgrades | Reconductor (P142/P142S) Rolfe Avenue - West Bolyston 115 kV line w/1590 ACSR. | In-service | 3000000 | 3000000
Reliability Upgrade | 1a | 176 | Northeast Utilities | 07/2009 |  | Monadnock Area Reliability Project | New Fitzwilliam 345/115kV substation along with 345 kV breakers. | In-service | 76100000 | 76100000 | bar: 2006
Reliability Upgrade | 1a | 174 | National Grid, USA | 06/2009 |  | Monadnock Area Reliability Project | Reconductor I-135 (Bellows Falls-Monadnock Tap-Flagg Pond) 115 kV line. | In-service | 15778000 | 15778000
Reliability Upgrade | 1a | 832 | NSTAR Electric Company | 07/2009 |  | Short Term Lower SEMA Upgrades | Add(1) 115kV SVC (0-112 MVARs lagging) at Barnstable. | In-service | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade | 82000000
Reliability Upgrade | 1a | 182 | Vermont Electric Power Company | 09/2009 |  | Monadnock Area Reliability Project | Upgrade bus cable at N. Rutland and K35 115 kV breaker at Rutland. | In-service | 1000000 | 1000000 | bar: 2006
Reliability Upgrade | 1a | 302 | NSTAR Electric Company | 05/2009 |  | Boston Area 115 kV Enhancements | DCT separation of Framingham to Speen St. 433-507 circuit. | In-service | 3100000 | 3100000 | bar: 2006
Reliability Upgrade | 1a | 320 | Vermont Electric Power Company | 10/2009 | 2009 | Lamoille County Project | Middlesex Substation 115 kV breaker addition. | In-service | 4857000 | 4857000
Reliability Upgrade | 1a | 322 | Vermont Electric Power Company | 10/2009 | 2009 | Lamoille County Project | Installation of new Duxbury Substation that involves looping in and out of the Middlesex - Essex 115 kV (K24) line. | In-service | Part of Lamoille County Project | Part of Lamoille County Project
Reliability Upgrade | 1a | 321 | Vermont Electric Power Company | 11/2009 | 2009 | Burlington Project | Burlington 115kV Loop - 5 mi of new line & rebuilding 5 miles of existing line between two existing substations with expansion of the East Avenue substation. | In-service | 25142000 | 25142000
Reliability Upgrade | 1a | 1063 | NSTAR Electric Company | 12/2009 | 2009 |  | Install (2) 115kV 40 MVAR shunt reactors at Edgar Station | In-service | 3745000 | 3745000
Reliability Upgrade | 1a | 777 | National Grid, USA | 11/2009 | 2009 | Merrimack Valley/North Shore Reliability Project | Build Wakefield Junction station with four 345/115 kV autotransformers. | In-service | 95000000 | 95000000
Reliability Upgrade | 1a | 161 | National Grid, USA | 11/2009 | 2009 | Merrimack Valley/North Shore Reliability Project | Loop 345 kV 339 line and 115 kV S-145/T-146 into new Wakefield Jct. Substation. | In-service | 5406900 | 5406900
Reliability Upgrade | 1a | 961 | NSTAR Electric Company | 12/2009 | 2009 | Mystic Breaker Additions Project | Install (2) new 115 kV East Bus breakers #30 and #32 at Mystic. | In-service | 3689000 | 3689000
Reliability Upgrade | 1a | 903 | NSTAR Electric Company | 12/2009 | 2009 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #2, #4, #5, and #16 at Mystic to IPT and separate controls with Boston Gen units #5 and #6. | In-service | 1576000 | 1576000
Reliability Upgrade | 1a | 930 | National Grid, USA | 11/2009 | 2009 | Central/Western Massachusetts Upgrades | Reconductor Nashua St - Quinsigamond Jct (O141) 115 kV line w/636 ACSS. | In-service | 2300000 | 2300000
Reliability Upgrade | 1a | 211 | Northeast Utilities | 11/2009 | 2009 | NU LSP - Rood Ave Substation | New Rood Ave (formally Windsor) distribution substation with 115kV terminal modifications. | In-service | 8681000 | 8681000
Reliability Upgrade | 1a | 789 | National Grid, USA | 12/2009 | 2009 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Reconductoring of T7 115 kV line. | In-service | 23304000 | 23304000
Reliability Upgrade | 1b | 963 | NSTAR Electric Company | 12/2009 | 2009 | Boston Area 115 kV Enhancements | Add a new 115kV breaker # 11 Relocate 447-509 and add control and protection at Holbrook. | In-service | 1276800 | 1276800 | 2006: inservice; Data Set for Investment Chart by Status 2007: 2009 additional $174,977,700
Reliability Upgrade | 1a | 933 | National Grid, USA | 01/2010 | 2010 | Central/Western Massachusetts Upgrades | Reconductor Pratts Jct - Flagg Pond I-135S & J-136S 115 kV lines w/795 ACSS. | In-service | 11200000 | 11200000 | 2006: inservice; Data Set for Investment Chart by Status 2007: 2010 $11,200,00
Reliability Upgrade | 1b | 1167 | NSTAR Electric Company | 12/2010 | 2010 |  | Replace three 40kA 115kV circuit breakers at Carver with 63kV breakers | Concept | 850000 | 850000
Reliability Upgrade | 1b | 1157 | Bangor Hydro-Electric Company | 12/2010 | 2010 |  | Bangor Hydro Synchrophasors | Concept | 100000 | 100000
Reliability Upgrade | 1a | 1128 | Central Maine Power Company | 07/2010 | 2010 | CMP-LSP Hotel Road Substation | Add 115/34kV transformer with 115kV breaker at Hotel Rd. | Planned | 800000 | 800000 | Data Set for Investment Chart by Status 2007: 2010; Data Set for Investment Chart by Status 2008: Concept; Data Set for Investment Chart by Status 2009: 2
Reliability Upgrade | 1a | 624 | Central Maine Power Company | 2010 | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (New Page - Rumford Industrial Park) | Planned | Part of project 625 | Part of project 625 | Data Set for Investment Chart by Status 2007: 2010; Data Set for Investment Chart by Status 2008: Planned; Data Set for Investment Chart by Status 2009: 15
Reliability Upgrade | 1a | 1145 | Vermont Electric Power Company | 12/2010 | 2010 | Burlington Gorge Project | Installation of a 3-breaker 115kV ring substation and 115/34.5kV transformer on the East Ave. - Tafts Coners 115kV line | Planned | 14000000 | 14000000 | Data Set for Investment Chart by Status 2007: 2010; Data Set for Investment Chart by Status 2008: Proposed; Data Set for Investment Chart by Status 2009: 1
Reliability Upgrade | 1a | 1152 | National Grid, USA | 2010-08-01 | 2010 |  | Bear Swamp - Pratts Jumction 230kV Line Refurbishment Project (E205E) | Planned | 43596000 | 43596000 | Data Set for Investment Chart by Status 2007: 2010; Data Set for Investment Chart by Status 2008: Under Construction; Data Set for Investment Chart by Status 2009: 18
Reliability Upgrade | 1a | 842 | NSTAR Electric Company | 06/2010 | 2010 | Boston Area 115 kV Enhancements | Add 115 kV 54 MVAR capacitor bank at W. Framingham. | Planned | 2650000 | 2650000
Reliability Upgrade | 1a | 1113 | NSTAR Electric Company | 12/2010 | 2010 |  | Install 115kV Breaker #31 at K St. | Planned | 2800000 | 2800000
Reliability Upgrade | 1a | 928 | National Grid, USA | 12/2010 | 2010 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | 2300000 | 2300000
Reliability Upgrade | 1a | 927 | National Grid, USA | 07/2010 | 2010 | Central/Western Massachusetts Upgrades | Greendale - replace 115 kV breaker and upgrade to 2000A. | Planned | 680000 | 680000
Reliability Upgrade | 1a | 924 | National Grid, USA | 12/2010 | 2010 | Central/Western Massachusetts Upgrades | Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | Planned | 2147181 | 2147181
Reliability Upgrade | 1a | 1067 | NSTAR Electric Company | 12/2010 | 2010 | NPCC BPS Compliance | Tremont Station | Planned | 12370000 | 12370000
Reliability Upgrade | 1a | 484 | National Grid, USA | 11/2010 | 2010 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Planned | 580000 | 580000
Reliability Upgrade | 1a | 1055 | Northeast Utilities | 2010 | 2010 | CT LSP - Waterside Substation | Waterside Substation - add a 115/13.2-kV transformer and a 115-kV circuit breaker. | Planned | 2619000 | 2619000
Reliability Upgrade | 1a | 1049 | United Illuminating Company | 12/2010 | 2010 |  | East Shore 115 kV Capacitor Bank Transient Recovery | Planned | 4050000 | 4050000
Reliability Upgrade | 1a | 582 | Northeast Utilities | 12/2010 | 2010 |  | Separate 310 and 368 345-KV lines and create 368/1767 DCT | Planned | 16000000 | 16000000
Reliability Upgrade | 1a | 1112 | United Illuminating Company | 12/2010 | 2010 |  | Water Street 115kV circuit breaker and switch replacements. | Planned | 2840000 | 2840000
Reliability Upgrade | 1b | 1133 | Central Maine Power Company | 10/2010 | 2010 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation & new 34kV line from Leeds to Turner | Proposed | 300000 | 300000
Reliability Upgrade | 1a | 1166 | NSTAR Electric Company | 12/2010 | 2010 | Greater Boston Reliability Project | Terminal upgrades at W. Walpole and W, Medway for #325 line | Proposed | 1350000 | 1350000
Reliability Upgrade | 1b | 1150 | United Illuminating Company | 12/2010 | 2010 |  | Grand Avenue - West River 115 kV Pumping Plant Replacements | Proposed | 2900000 | 2900000
Reliability Upgrade | 1a | 144 | Bangor Hydro-Electric Company | 12/2010 | 2010 | Keene Rd Autotransformer | Installation of a 345/115 kV autotransformer at Keene Rd Substation. | Under Construction | 29000000 | 29000000
Reliability Upgrade | 1a | 625 | Central Maine Power Company | 04/2010 | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Rumford Industrial Park capacitor bank. | Under Construction | 5400000 | 5400000
Reliability Upgrade | 1a | 1029 | Central Maine Power Company | 11/2010 | 2010 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformer at South Gorham | Under Construction | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1144 | Central Maine Power Company | 09/2010 | 2010 | Heywood Road Project | Circuit switcher replacements at Detroit, Lakewood, Rice Rips and Winslow | Under Construction | Part of Heywood Road Project | Part of the Heywood Road Project
Reliability Upgrade | 1a | 323 | Vermont Electric Power Company | 12/2010 | 2010 | Vermont Southern Loop Project | New VY - Newfane - Coolidge 345 kV line with requisite station upgrades. | Under Construction | 136368000 | 136368000
Reliability Upgrade | 1a | 1032 | Vermont Electric Power Company | 09/2010 | 2010 | Vermont Southern Loop Project | Installation of a new 345/115kV substation called Vernon including a new 345/115kV autotransformer | Under Construction | 69815000 | 69815000
Reliability Upgrade | 1a | 1033 | Vermont Electric Power Company | 12/2010 | 2010 | Vermont Southern Loop Project (VELCO LSP - Newfane Substation) | Installation of a new 345/115kV substation called Newfane | Under Construction | 16664000 | 16664000
Reliability Upgrade | 1a | 1034 | Vermont Electric Power Company | 12/2010 | 2010 | Vermont Southern Loop Project | Loop new 345kV Line into Newfane Substation. | Under Construction | Part of project 323 | Part of project 323
Reliability Upgrade | 1a | 1035 | Vermont Electric Power Company | 12/2010 | 2010 | Vermont Southern Loop Project | Expansion of Coolidge 345kV substation | Under Construction | 20117000 | 20117000
Reliability Upgrade | 1a | 779 | National Grid, USA | 04/2010 | 2010 | Merrimack Valley/North Shore Reliability Project | Bypass and remove Golden Hills 345 kV substation. | Under Construction | 5507195 | 5507195
Reliability Upgrade | 1a | 904 | NSTAR Electric Company | 12/2010 | 2010 | Mystic IPT Breaker Project | Upgrade (5) 115 kV breakers #1, #7, #15 #19 and #20 at Mystic to IPT. | Under Construction | 1500000 | 1500000
Reliability Upgrade | 1a | 1119 | NSTAR Electric Company | 06/2010 | 2010 | Greater Boston Reliability Project | Upgrade West Medway-West Walpole 345kV line #325 | Under Construction | 2200000 | 2200000
Reliability Upgrade | 1a | 1120 | NSTAR Electric Company | 06/2010 | 2010 |  | Install 345kV 160 MVAR shunt ractor at W. Walpole | Under Construction | 7200000 | 7200000
Reliability Upgrade | 1a | 902 | National Grid, USA | 10/2010 | 2010 | Middleboro Municipal | Close the E1-M1 loop at Middleboro's Wareham St Sub. | Under Construction | 715000 | 715000
Reliability Upgrade | 1a | 786 | National Grid, USA | 11/2010 | 2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Terminal upgrades at Drumrock, Chartley Pond, and Brayton Point. | Under Construction | 1000000 | 1000000
Reliability Upgrade | 1a | 787 | National Grid, USA | 06/2010 | 2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | West Farnum breaker replacements. | Under Construction | 7631000 | 7631000
Reliability Upgrade | 1a | 809 | Northeast Utilities | 12/2010 | 2010 |  | Upgrade terminal equipment at Bunker Hill 115 kV substation. | Under Construction | 516000 | 516000 | Data Set for Investment Chart by Status 2007: 2011; Data Set for Investment Chart by Status 2008: Concept; Data Set for Investment Chart by Status 2009: 5
Reliability Upgrade | 1a | 1110 | United Illuminating Company | 12/2010 | 2010 |  | Broadway 115/13.8 kV Substation Addition | Under Construction | 1200000 | 1200000 | Data Set for Investment Chart by Status 2007: 2011; Data Set for Investment Chart by Status 2008: Planned; Data Set for Investment Chart by Status 2009: 24
Reliability Upgrade | 1b | 301 | NSTAR Electric Company | 12/2011 | 2011 | Boston Area 115 kV Enhancements | Reconductor 115-kV circuits 320-507 and 320-508. | Concept | 4600000 | 4600000 | Data Set for Investment Chart by Status 2007: 2011; Data Set for Investment Chart by Status 2008: Proposed; Data Set for Investment Chart by Status 2009: 6
Reliability Upgrade | 1b | 1156 | Bangor Hydro-Electric Company | 12/2011 | 2011 | Maine Power Reliability Program (MPRP) | Orrington Shunt Cap Reconfiguration | Concept | TBD | TBD | Data Set for Investment Chart by Status 2007: 2011; Data Set for Investment Chart by Status 2008: Under Construction; Data Set for Investment Chart by Status 2009: 6
Reliability Upgrade | 1b | 318 | Vermont Electric Power Company | 12/2011 | 2011 |  | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems through the 1,250 MW Vermont state load level. | Concept | 9000000 | 9000000
Reliability Upgrade | 1b | 325 | Vermont Electric Power Company | 12/2011 | 2011 | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | 5000000 | 5000000
Reliability Upgrade | 1b | 1153 | NSTAR Electric Company | 12/2011 | 2011 | Boston Area 115 kV Enhancements | Reliability Upgrades at West Framingham Station | Concept | 3000000 | 3000000
Reliability Upgrade | 1a | 1146 | Vermont Electric Power Company | 02/2011 | 2011 | Lyndonville Project | Installation of a 4-breaker ring 115 kV substation consisting of two 115kV 12.5 MVAR capacitor banks and 115/34.5 kV transformer interconnecting to the Irasburg - St. Johnsbury 115kV line | Planned | 9000000 | 9000000
Reliability Upgrade | 1a | 783 | National Grid, USA | 03/2011 | 2011 | Merrimack Valley/North Shore Reliability Project | Extend the 115kV by addition of 115kV Breaker and K-153 line from King St. to W. Amesbury 115kV station. (W. Amesbury 345/115kV Station becomes PTF) | Planned | 30349000 | 30349000
Reliability Upgrade | 1a | 1165 | NSTAR Electric Company | 12/2011 | 2011 | Mystic Breaker Additions Project | Move Transformer 110B Connection at Mystic | Planned | 1700000 | 1700000
Reliability Upgrade | 1a | 929 | National Grid, USA | 06/2011 | 2011 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | 1381849 | 1381849
Reliability Upgrade | 1a | 939 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor and retension (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | Planned | 3389658 | 3389658
Reliability Upgrade | 1a | 940 | National Grid, USA | 04/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS. | Planned | 6235744 | 6235744
Reliability Upgrade | 1a | 942 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | 3650000 | 3650000
Reliability Upgrade | 1a | 925 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | 318888 | 318888
Reliability Upgrade | 1a | 926 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | 6027520 | 6027520
Reliability Upgrade | 1a | 932 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | 372036 | 372036
Reliability Upgrade | 1a | 943 | National Grid, USA | 01/2011 | 2011 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | 1073995 | 1073995
Reliability Upgrade | 1a | 944 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Planned | 16530000 | 16530000
Reliability Upgrade | 1a | 945 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Adams - install third 115 kV breaker to complete ring bus. | Planned | 1584841 | 1584841
Reliability Upgrade | 1a | 952 | National Grid, USA | 06/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor E Winchendon - J136 Tap within I135/J136 ROW w/795 ACSR. | Planned | 932156 | 932156
Reliability Upgrade | 1a | 955 | National Grid, USA | 11/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | 12213934 | 12213934
Reliability Upgrade | 1a | 1000 | Northeast Utilities | 12/2011 | 2011 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | Planned | 22000000 | 22000000
Reliability Upgrade | 1a | 1076 | Northeast Utilities | 12/2011 | 2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Planned | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1077 | Northeast Utilities | 12/2011 | 2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115kV line | Planned | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1066 | NSTAR Electric Company | 09/2011 | 2011 | NPCC BPS Compliance | Needham Station | Planned | 10531000 | 10531000
Reliability Upgrade | 1a | 1147 | Northeast Utilities | 2011 | 2011 |  | Waterside Substation - install a three-breaker 115kV ring bus | Planned | 5055000 | 5055000
Reliability Upgrade | 1a | 1148 | Northeast Utilities | 2011 | 2011 |  | Add a 2nd high speed relay on the Glennbrook to Waterside 115kV 1440 | Planned | Part of Project #1147 | Part of Project #1147
Reliability Upgrade | 1a | 1056 | Northeast Utilities | 12/2011 | 2011 | CT LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Planned | 10969000 | 10969000
Reliability Upgrade | 1a | 1111 | United Illuminating Company | 2011-08-01 | 2011 |  | Metro North Union Avenue 115/26.4 kV Substation | Planned | 10543000 | 10543000
Reliability Upgrade | 1a | 1050 | United Illuminating Company | 12/2011 | 2011 |  | Devon Tie 115kV Switching Station BPS Compliance | Planned | 3240000 | 3240000
Reliability Upgrade | 1b | 1116 | Bangor Hydro-Electric Company | 12/2011 | 2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Proposed | 37126000 | 37126000
Reliability Upgrade | 1b | 1130 | Central Maine Power Company | 12/2011 | 2011 | Sturtevant Improvements | Add 115kV circuit breakers & 25 MVAR capacitor bank at Sturtevant Substation; Re-rate Section 63 between Wyman Hydro & Madison Substation | Proposed | 3000000 | 3000000
Reliability Upgrade | 1b | 1131 | Central Maine Power Company | 12/2011 | 2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Proposed | 600000 | 600000
Reliability Upgrade | 1b | 1132 | Central Maine Power Company | 12/2011 | 2011 | CMP-LSP Maxcy's Substation | Add 115/34kV transformer (coordinate with MPRP) | Proposed | 600000 | 600000
Reliability Upgrade | 1b | 964 | NSTAR Electric Company | 06/2011 | 2011 | Boston Area 115 kV Enhancements | Relocate 115kV terminals at W. Walpole to mitigate breaker failure #8. | Proposed | 5600000 | 5600000
Reliability Upgrade | 1b | 1151 | United Illuminating Company | 12/2011 | 2011 |  | West River 115kV Switching Station Fault Duty Migration | Proposed | 3500000 | 3500000
Reliability Upgrade | 1a | 934 | National Grid, USA | 09/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Under Construction | Part of RSP 935 | Part of RSP 935 | Data Set for Investment Chart by Status 2007: 2012; Data Set for Investment Chart by Status 2008: Concept; Data Set for Investment Chart by Status 2009: 4
Reliability Upgrade | 1a | 935 | National Grid, USA | 09/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Under Construction | 10200000 | 10200000 | Data Set for Investment Chart by Status 2007: 2012; Data Set for Investment Chart by Status 2008: Planned; Data Set for Investment Chart by Status 2009: 49
Reliability Upgrade | 1a | 162 | National Grid, USA | 04/2011 | 2011 |  | Q-169 Golden Hills to Lynn 115 kV line upgrade. | Under Construction | 12390000 | 12390000 | Data Set for Investment Chart by Status 2007: 2012; Data Set for Investment Chart by Status 2008: Proposed; Data Set for Investment Chart by Status 2009: 2
Reliability Upgrade | 1a | 788 | National Grid, USA | 06/2011 | 2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Kent County substation expansion. | Under Construction | 42300000 | 42300000 | Data Set for Investment Chart by Status 2007: 2012; Data Set for Investment Chart by Status 2008: Under Construction; Data Set for Investment Chart by Status 2009: 10
Reliability Upgrade | 1a | 790 | National Grid, USA | 12/2011 | 2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Under Construction | 50600000 | 50600000
Reliability Upgrade | 1a | 1098 | National Grid, USA | 12/2011 | 2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Under Construction | 37529000 | 37529000
Reliability Upgrade | 1b | 970 | NSTAR Electric Company | 12/2012 | 2012 | Greater Boston Reliability Project | Add a new 345 kV line from Lexington to Waltham. | Concept | TBD | TBD
Reliability Upgrade | 1b | 971 | NSTAR Electric Company | 12/2012 | 2012 | Greater Boston Reliability Project | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | TBD | TBD
Reliability Upgrade | 1b | 1031 | Bangor Hydro-Electric Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station | Concept | TBD | TBD
Reliability Upgrade | 1b | 965 | NSTAR Electric Company | 12/2012 | 2012 | Boston Area 115 kV Enhancements | Add third 115kV line from W. Walpole to Holbrook | Concept | TBD | TBD
Reliability Upgrade | 1a | 905 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Planned | 1510000000 | 1510000000
Reliability Upgrade | 1a | 906 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Coopers Mills-Highland, Larrabee Road-Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 907 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 84 (Albion Road-Coopers Mills), Section 203 (Detroit-Orrington), Section 80 (Coopers Mills-Highland), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 908 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377 & Maine Yankee 375/392, 115kV Bucksport 65/205) and Maine Yankee 345 kV re-termination | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1026 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Three Rivers) | Planned | Portion of CMP $1.51B and portion of NU is $36.0M | 36000000
Reliability Upgrade | 1a | 1027 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 115kV Line Construction (Elm Street-East Deering, East Deering -Cape) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1028 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD
Reliability Upgrade | 1a | 1158 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Two 40 MVAR reactors at Albion Road, two 40 MVAR reactors at Larabee Road, two 40 MVAR at Coopers Mills | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1030 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Raven Farm, Maguire Road) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 143 | Bangor Hydro-Electric Company | 12/2012 | 2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation to Harrington Substation. | Planned | 66100000 | 66100000
Reliability Upgrade | 1a | 1129 | Central Maine Power Company | 05/2012 | 2012 |  | New 115kV line between Wyman Hydro and Heywood Rd. parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | 32800000 | 32800000
Reliability Upgrade | 1a | 277 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Planned | 56000000 | 56000000
Reliability Upgrade | 1a | 1137 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115kV breakers and add 1-115kV breaker at Deerfield Substation | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1138 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rebuild 115kV L175 line | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1139 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV M183 Line | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1140 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 887 | National Grid, USA | 09/2012 | 2012 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Planned | 76000000 | 76000000
Reliability Upgrade | 1a | 921 | National Grid, USA | 06/2012 | 2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | 40000000 | 40000000
Reliability Upgrade | 1a | 919 | National Grid, USA | 12/2012 | 2012 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | 4600000 | 4600000
Reliability Upgrade | 1a | 840 | NSTAR Electric Company | 06/2012 | 2012 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | 7300000 | 7300000
Reliability Upgrade | 1a | 775 | National Grid, USA | 06/2012 | 2012 | Merrimack Valley/North Shore Reliability Project | Addition of 4 breakers and relocation of T1 and T2 into new bays at Sandy Pond. | Planned | 20100000 | 20100000
Reliability Upgrade | 1a | 776 | National Grid, USA | 09/2012 | 2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | 3125000 | 3125000
Reliability Upgrade | 1a | 59 | National Grid, USA | 06/2012 | 2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | Part of RSP 921 | Part of RSP 921
Reliability Upgrade | 1a | 1068 | NSTAR Electric Company | 12/2012 | 2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to vicinity of Bourne and connect to existing #120 line and install a 345KV - 115kV auto-transformer at new substation about 3 miles west of the Barnstable Substation 7 | Planned | 110000000 | 110000000 | bar: 2006
Reliability Upgrade | 1a | 592 | NSTAR Electric Company | 12/2012 | 2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing | Planned | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1a | 1118 | NSTAR Electric Company | 12/2012 | 2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 | Planned | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1a | 938 | National Grid, USA | 05/2012 | 2012 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | 3068556 | 3068556
Reliability Upgrade | 1a | 941 | National Grid, USA | 06/2012 | 2012 | Central/Western Massachusetts Upgrades | Install new Z126 Millbury - Tower #510 115 kV line. | Planned | 13748000 | 13748000
Reliability Upgrade | 1a | 946 | National Grid, USA | 12/2012 | 2012 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer - E Longmeadow - Shaker Rd line to 115 kV. | Planned | 9962060 | 9962060
Reliability Upgrade | 1a | 947 | National Grid, USA | 12/2012 | 2012 | Central/Western Massachusetts Upgrades | Reconductor 115 kV line from Palmer to new Hampden Substation. | Planned | 2632635 | 2632635
Reliability Upgrade | 1a | 948 | National Grid, USA | 12/2012 | 2012 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | 5649430 | 5649430
Reliability Upgrade | 1a | 949 | National Grid, USA | 12/2012 | 2012 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | 1500000 | 1500000
Reliability Upgrade | 1a | 937 | National Grid, USA | 05/2012 | 2012 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | 6602875 | 6602875
Reliability Upgrade | 1a | 673 | National Grid, USA | 12/2012 | 2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | National Grid, USA | 12/2012 | 2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Planned | 30000000 | 30000000
Reliability Upgrade | 1a | 1065 | NSTAR Electric Company | 07/2012 | 2012 | NPCC BPS Compliance | Waltham Station | Planned | 23190000 | 23190000
Reliability Upgrade | 1a | 1095 | National Grid, USA | 06/2012 | 2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | 73800000 | 73800000
Reliability Upgrade | 1a | 795 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV line. | Planned | 99900000 | 99900000
Reliability Upgrade | 1a | 1106 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | Planned | Part of $99,900,000 above | Part of $99,900,000 above
Reliability Upgrade | 1a | 798 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Planned | 4900000 | 4900000
Reliability Upgrade | 1a | 799 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | Planned | 4500000 | 4500000
Reliability Upgrade | 1a | 1096 | National Grid, USA | 05/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | 12000000 | 12000000
Reliability Upgrade | 1a | 800 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S, T-172N and T-172S with associated terminal equipment upgrades. | Planned | 10000000 | 10000000
Reliability Upgrade | 1a | 1097 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County | Planned | 129800000 | 129800000
Reliability Upgrade | 1a | 1099 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | 6000000 | 6000000
Reliability Upgrade | 1a | 1109 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Planned | 1000000 | 1000000
Reliability Upgrade | 1a | 976 | United Illuminating Company | 05/2012 | 2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Planned | 66000000 | 66000000
Reliability Upgrade | 1b | 148 | Central Maine Power Company | 06/2012 | 2012 | CMP LSP - Saco Bay Area Reinforcement Project | Establish a new Vallee Lane 115/34.5 kV substation and 115 kV line from Louden S/S to Vallee Lane Substation. | Proposed | 100000 | 100000
Reliability Upgrade | 1b | 1136 | National Grid, USA | 12/2012 | 2012 |  | New 115kV Switching Station at Devens Convert 69kV lines to 115kV, Reconfigure 115kV Supply at Ayer Substation | Proposed | 9200000 | 9200000
Reliability Upgrade | 1b | 593 | NSTAR Electric Company | 2013 | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Canal to Barnstable/Falmouth | Concept | TBD | TBD | Data Set for Investment Chart by Status 2007: 2013; Data Set for Investment Chart by Status 2008: Concept; Data Set for Investment Chart by Status 2009: 4
Reliability Upgrade | 1b | 1154 | Bangor Hydro-Electric Company | 12/2013 | 2013 | Maine Power Reliability Program (MPRP) | Rebuild Line 66 | Concept | TBD | TBD | Data Set for Investment Chart by Status 2007: 2013; Data Set for Investment Chart by Status 2008: Planned; Data Set for Investment Chart by Status 2009: 58
Reliability Upgrade | 1b | 1155 | Bangor Hydro-Electric Company | 12/2013 | 2013 | Maine Power Reliability Program (MPRP) | Capacitor Bank Addition (10 MVAr at Trenton and Epping) | Concept | TBD | TBD | Data Set for Investment Chart by Status 2007: 2013; Data Set for Investment Chart by Status 2008: Proposed; Data Set for Investment Chart by Status 2009: 6
Reliability Upgrade | 1b | 843 | NSTAR Electric Company | 12/2013 | 2013 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | TBD | TBD | Data Set for Investment Chart by Status 2007: 2013; Data Set for Investment Chart by Status 2008: Under Construction; Data Set for Investment Chart by Status 2009: 6
Reliability Upgrade | 1a | 680 | National Grid, USA | 03/2013 | 2013 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | 7393000 | 7393000
Reliability Upgrade | 1a | 674 | National Grid, USA | 12/2013 | 2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | 22115000 | 22115000
Reliability Upgrade | 1a | 931 | National Grid, USA | 01/2013 | 2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | 531481 | 531481
Reliability Upgrade | 1a | 950 | National Grid, USA | 12/2013 | 2013 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | 1016897 | 1016897
Reliability Upgrade | 1a | 953 | National Grid, USA | 12/2013 | 2013 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | 10248067 | 10248067
Reliability Upgrade | 1a | 954 | National Grid, USA | 12/2013 | 2013 | Central/Western Massachusetts Upgrades | E Westminster - install new 115 kV breaker, including disconnect switches. Assumes no new control house. | Planned | 903909 | 903909
Reliability Upgrade | 1a | 951 | National Grid, USA | 02/2013 | 2013 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon 115 kV line. | Planned | 7455440 | 7455440
Reliability Upgrade | 1a | 687 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | 714000000 | 714000000
Reliability Upgrade | 1a | 826 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 196 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115kV line South Agawam to Southwick (1768) | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVAR Capacitor additions | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1074 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1078 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 190 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | 69600000 | 69600000
Reliability Upgrade | 1a | 1094 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | 25000000 | 25000000
Reliability Upgrade | 1a | 794 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | 55800000 | 55800000
Reliability Upgrade | 1a | 796 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | 347 Reconductor from Sherman Road to CT/RI Border. | Planned | 16400000 | 16400000
Reliability Upgrade | 1a | 797 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | 3361 Upgrade 345kV terminal equipment at Sherman Road. | Planned | 8300000 | 8300000
Reliability Upgrade | 1a | 974 | United Illuminating Company | 04/2013 | 2013 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Planned | 6700000 | 6700000
Reliability Upgrade | 1a | 816 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1054 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Manchester - Meekvile Jct. line (395/1448) separation. | Planned | 14000000 | 14000000
Reliability Upgrade | 1a | 576 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | 313000000 | 313000000
Reliability Upgrade | 1a | 1114 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1a | 814 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Ancillary Central Connecticut Relaibility Project) | Reconductor a portion of the Manchester to Scovill Rock 353 345-kV line and terminal work. | Planned | 9000000 | 9000000
Reliability Upgrade | 1a | 802 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | 251000000 | 251000000
Reliability Upgrade | 1a | 1084 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Loop the Millstone - Manchester (310) 345 kV line into the Card substation. | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1085 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1086 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1087 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1088 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1089 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Killingly 3G substation 345kV breaker addition | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1090 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Millstone 15G substation breaker 14T upgrade 50kA | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1091 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Southington 4C substation breaker 19T upgrade to 63kA | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 807 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Ancillary Interstate Reliability Project) | Install 480 MVAR's of capacitors at the Montville 345 kV substation | Planned | 33000000 | 33000000
Reliability Upgrade | 1a | 1092 | Northeast Utilities | 12/2013 | 2013 | NEEWS (BPS) 2 | Upgrade the Card 115 kV, East Hartford 115 kV, Agawam 115 kV, Barbour Hill 115 kV, and North Bloomfield 345 kV Substations to BPS standards. | Planned | 37000000 | 37000000
Reliability Upgrade | 1b | 699 | United Illuminating Company | 12/2014 | 2014 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | 11100000 | 11100000 | Data Set for Investment Chart by Status 2008: 2014; Data Set for Investment Chart by Status 2009: Concept; Data Set for Investment Chart by Status 2010: 1
Reliability Upgrade | 1a | 782 | National Grid, USA | 10/2014 | 2014 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor n Railyard. | Planned | 43912000 | 43912000 | Data Set for Investment Chart by Status 2008: 2014; Data Set for Investment Chart by Status 2009: Planned; Data Set for Investment Chart by Status 2010: 10
Reliability Upgrade | 1a | 791 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | 11560000 | 11560000 | Data Set for Investment Chart by Status 2008: 2014; Data Set for Investment Chart by Status 2009: Proposed; Data Set for Investment Chart by Status 2010: 0
Reliability Upgrade | 1a | 913 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | 3250000 | 3250000 | Data Set for Investment Chart by Status 2008: 2014; Data Set for Investment Chart by Status 2009: Under Construction; Data Set for Investment Chart by Status 2010: 0
Reliability Upgrade | 1a | 914 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | 28150000 | 28150000
Reliability Upgrade | 1a | 915 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | 11800000 | 11800000
Reliability Upgrade | 1a | 917 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | 7000000 | 7000000
Reliability Upgrade | 1a | 918 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | 3180000 | 3180000
Reliability Upgrade | 1a | 792 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Admiral St-Franklin Square (Q143 and R144) 115 kV UG recabling. | Planned | 39200000 | 39200000
Reliability Upgrade | 1a | 793 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | 6400000 | 6400000
Reliability Upgrade | 1b | 969 | NSTAR Electric Company | 06/2015 | 2015 | Boston Area 115 kV Enhancements | Add a new 54 MVAR capacitor bank at Chelsea. | Concept | 2780000 | 2780000
Reliability Upgrade | 1b | 956 | National Grid, USA | 01/2015 | 2015 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Concept | 7021534 | 7021534
Reliability Upgrade | 1b | 975 | United Illuminating Company | 06/2015 | 2015 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | 65000000 | 65000000
Reliability Upgrade | 1a | 1141 | Northeast Utilities | 2015 | 2015 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 139 | Vermont Electric Power Company | 12/2015 | 2015 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Planned | 20000000 | 20000000
Reliability Upgrade | 1a | 721 | United Illuminating Company | 06/2016 | 2016 |  | New Shelton 115/13.8 kV substation | Planned | 19500000 | 19500000
Reliability Upgrade | 1b | 785 | National Grid, USA | 07/2017 | 2017 | Merrimack Valley/North Shore Reliability Project | Re-conductor F-158N (Golden Hills-Maplewood-Everett) 115 kV line. | Concept | 1330000 | 1330000
Reliability Upgrade | 1b | 824 | Northeast Utilities | TBD | TBD | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Concept | TBD | TBD
Reliability Upgrade | 1b | 825 | Northeast Utilities | TBD | TBD | Pittsfield / Greenfield Project | Upgrade the Pleasant to Blanford 115-kV line and the Blanford to Granville Jct. portion of the 115-kV line 1512. | Concept | TBD | TBD
Reliability Upgrade | 1a | 910 | Central Maine Power Company | 12/2008 | 2008 | Rumford-Woodstock-Kimball Road Corridor Project | Rebuild Section 211 Woodstock - Rumford. | In-Service | 8400000 | 8400000 | bar: 2006 to Data Set for Investment Chart by Status 2011
Reliability Upgrade | 1a | 177 | Northeast Utilities | 12/2008 | 2008 | Monadnock Area Reliability Project | Replace limiting terminal equipment at Webster Substation on line to North Road. | In-Service | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 180 | Northeast Utilities | 12/2008 | 2008 | Monadnock Area Reliability Project | Rebuild 115 kV Keene to Swanzey A-152 line. | In-Service | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 138 | Vermont Electric Power Company | 12/2008 | 2008 | Northwest Vermont Reliability Project | N. Haven - Vergennes - Q. City 115 kV line. | In-Service | 70200000 | 70200000
Reliability Upgrade | 1a | 923 | National Grid, USA | 12/2008 | 2008 | Auburn Area Transmission System Upgrades | Reconductor 115 kV A94 line and associated substation upgrades. | In-Service | 2400000 | 2400000
Reliability Upgrade | 1a | 781 | National Grid, USA | 10/2008 | 2008 | Merrimack Valley/North Shore Reliability Project | Install 115 kV 30 MVAr capacitor bank at Revere. | In-Service | 1727000 | 1727000
Reliability Upgrade | 1a | 841 | NSTAR Electric Company | 11/2008 | 2008 | Mystic Breaker Additions Project | Install (2) new 115 kV West Bus breakers #29 and #31 at Mystic. | In-Service | 2300000 | 2300000
Reliability Upgrade | 1a | 1040 | NSTAR Electric Company | 12/2008 | 2008 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #11, #8, #17 and #3 at Mystic to IPT | In-Service | 990000 | 990000
Reliability Upgrade | 1a | 168 | National Grid, USA | 09/2008 | 2008 | Southwest Rhode Island Reliability Enhancements | Reconductor Kenyon - Wood River 115 kV 1870 line. | In-Service | 2234232 | 2234232
Reliability Upgrade | 1a | 899 | National Grid, USA | 12/2008 | 2008 | Southwest Rhode Island Reliability Enhancements | Kenyon substation upgrades. | In-Service | 278000 | 278000
Reliability Upgrade | 1a | 171 | National Grid, USA | 10/2008 | 2008 | Southwest Rhode Island Reliability Enhancements | Reconductoring L-190 between Kent Co. and Davisville. | In-Service | 2666291 | 2666291
Reliability Upgrade | 1a | 900 | National Grid, USA | 11/2008 | 2008 | Southwest Rhode Island Reliability Enhancements | Wood River substation upgrades. | In-Service | 130000 | 130000
Reliability Upgrade | 1a | 846 | United Illuminating Company | 11/2008 | 2008 |  | Replace Mix Avenue 115 kV Oil Circuit Breaker & foundation. | In-Service | 450000 | 450000
Reliability Upgrade | 1a | 208 | Northeast Utilities | 12/2008 | 2008 | NU LSP - Oxford Substation | Install new Oxford (previously Jack's Hill) 115 kV substation. | In-Service | 4459000 | 4459000
Reliability Upgrade | 1a | 571 | Northeast Utilities | 12/2008 | 2008 | Norwalk-Glenbrook Cable Project | Upgrade Flax Hill Substation to BPS. | In-Service | Part of project 248 | Part of project 248
Reliability Upgrade | 1a | 248 | Northeast Utilities | 12/2008 | 2008 | Norwalk-Glenbrook Cable Project | Install two new 115 kV cables from Norwalk to Glenbrook (accommodate 345 kV class cable). | In-Service | 249372000 | 249372000
Reliability Upgrade | 1a | 246 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Add second 345/115 kV autotransformer at Norwalk Substation along with shunt reactors and 345 kV circuit breakers. | In-Service | 978182000 | 978182000
Reliability Upgrade | 1a | 238 | United Illuminating Company | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Build new Singer 345 kV substation with (12) circuit breakers, (2) autos, (4) shunt reactors along with reconnecting Bridgeport Energy thru one of the new autos. Includes 115 kV connection from Singer to Pequonnock substation. | In-Service | 162264000 | 162264000
Reliability Upgrade | 1a | 224 | United Illuminating Company | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install new 345 kV line from East Devon to Singer(UI). | In-Service | 157476000 | 157476000
Reliability Upgrade | 1a | 226 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install two 345 kV underground cables from Singer(UI) to Norwalk. | In-Service | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 235 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Expand Norwalk 345-kV substation and install transfer trip relaying scheme on the 1389 115 kV line between Norwalk and Flax Hill. | In-Service | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 247 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Replace Norwalk Harbor 138/115 kV autotransformer. | In-Service | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 684 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Replace (6) 115 kV breakers (4-Glenbrook, 1-Glenbrook Statcom, 1-Southington #1) and (3) 345-kV circuit breakers at Millstone and replace (4) 345- kV breakers with 500-kV breakers at Long Mountain substation. | In-Service | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 250 | Northeast Utilities | 12/2008 | 2008 |  | Add a 345 kV breaker at Ludlow Substation. | In-Service | 1644885 | 1644885
Reliability Upgrade | 1a | 155 | Central Maine Power Company | Northeast Utilities | 2009 | Maguire Road Project | Rebuild Three Rivers - Quaker Hill 115 kV Line K197. | In-Service | 5500000 | 5500000
Reliability Upgrade | 1a | 178 | Northeast Utilities | 02/2009 | 2009 | Monadnock Area Reliability Project | Rebuild 115 kV Garvins to Webster V-182 line. | In-Service | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 922 | National Grid, USA | 02/2009 | 2009 | Auburn Area Transmission System Upgrades | Reconductor 115kV L1 line and associated substation upgrades. | In-Service | 800000 | 800000
Reliability Upgrade | 1a | 116 | NSTAR Electric Company | 04/2009 | 2009 | NSTAR 345 kV Transmission Reliability Project | Add 2nd 345 kV UG Cables from Stoughton to Mattapan Sq.to K Street and install another new autotransformer at K. St. | In-Service | 307900000 | 307900000
Reliability Upgrade | 1a | 572 | NSTAR Electric Company | 04/2009 | 2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 345 kV 160 MVAR shunt reactors at Stoughton. | In-Service | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 573 | NSTAR Electric Company | 04/2009 | 2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 345 kV 160 MVAR shunt reactors at K St. | In-Service | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 772 | NSTAR Electric Company | 04/2009 | 2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 115 kV breaker at K St. | In-Service | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 136 | Vermont Electric Power Company | 04/2009 | 2009 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 1: two 115 kV PARs, four 25 MVAR Cap. banks, four +25/-12.5 MVAR synchronous condenders, and two 230/115 transformers. | In-Service | 62400000 | 62400000
Reliability Upgrade | 1a | 695 | NSTAR Electric Company | 07/2009 | 2009 | Short Term Lower SEMA Upgrades | Loop (355) 345 kV line in and out of Carver Substation and add (5) new 345 kV circuit breakers at Carver substation. | In-Service | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 830 | NSTAR Electric Company | 07/2009 | 2009 | Short Term Lower SEMA Upgrades | Add a second 345/115 kV Auto transformer at Carver substation and add (1) new 345 kV circuit breaker and (3) new 115 kV circuit breakers at Carver substation. | In-Service | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 831 | NSTAR Electric Company | 07/2009 | 2009 | Short Term Lower SEMA Upgrades | Add a second 115 kV line from Carver to Tremont and add (2) new 115 kV circuit breakers at Carver substation and (1) new 115 kV circuit breaker at Tremont substation. | In-Service | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 626 | Central Maine Power Company | 04/2009 |  | Rumford-Woodstock-Kimball Road Corridor Project | Addition of 115/34.5 kV transformer and six new 115 kV breakers and a half substation at Woodstock. | In-service | 8000000 | 8000000
Reliability Upgrade | 1a | 575 | Central Maine Power Company | 05/2009 |  | Heywood Road Project | New Heywood Rd 115kV switchyard with (6) 115kV circuit breakers (3) 115kV line retensionings and 115kV 20 MVAr capacitor bank at Heywood Rd. | In-service | 7000000 | 7000000
Reliability Upgrade | 1a | 1127 | Central Maine Power Company | 05/2009 |  | CMP-LSP Newcastle Substation | Add 115/34kV transformer with two 115kV breakers | In-service | 1300000 | 1300000
Reliability Upgrade | 1a | 166 | National Grid, USA | 06/2009 |  |  | Replace (16) 115 kV breakers at Tewksbury 22. | In-service | 3300000 | 3300000
Reliability Upgrade | 1a | 1009 | Northeast Utilities | 05/2009 |  |  | Install a 2% reactor on the North Bloomfield-Canton 115kV line and also replacement fo the Frostbridge 345/115kV autotransformer | In-service | 3089000 | 3089000
Reliability Upgrade | 1a | 203 | Northeast Utilities | 05/2009 |  | NU LSP - Stepstone Substation | Install new Stepstone 115 kV substation in Guilford. | In-service | 6332000 | 6332000
Reliability Upgrade | 1a | 1064 | NSTAR Electric Company | 04/2009 |  |  | Install (1) 345kV 160 MVAR shunt reactor at Mystic Station | In-service | 10400000 | 10400000
Reliability Upgrade | 1a | 1051 | Central Maine Power Company | 09/2009 |  | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Riley 115 kV capacitor bank. | In-service | Part of Project 625 | Part of Project 625
Reliability Upgrade | 1a | 267 | Northeast Utilities | 2009-08-01 |  | Y138 Closing | White Lake - Saco Valley (Y138) Line Closing - Add PAR on Y138 at Saco Valley, retension lines, upgrade Beebe terminal, and add capacitor banks at White Lake and Beebe. | In-service | 27775000 | 27775000
Reliability Upgrade | 1a | 936 | National Grid, USA | 07/2009 |  | Central/Western Massachusetts Upgrades | Reconductor (P142/P142S) Rolfe Avenue - West Bolyston 115 kV line w/1590 ACSR. | In-service | 3000000 | 3000000
Reliability Upgrade | 1a | 176 | Northeast Utilities | 07/2009 |  | Monadnock Area Reliability Project | New Fitzwilliam 345/115kV substation along with 345 kV breakers. | In-service | 76100000 | 76100000 | bar: 2006
Reliability Upgrade | 1a | 174 | National Grid, USA | 06/2009 |  | Monadnock Area Reliability Project | Reconductor I-135 (Bellows Falls-Monadnock Tap-Flagg Pond) 115 kV line. | In-service | 15778000 | 15778000
Reliability Upgrade | 1a | 832 | NSTAR Electric Company | 07/2009 |  | Short Term Lower SEMA Upgrades | Add(1) 115kV SVC (0-112 MVARs lagging) at Barnstable. | In-service | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade | 82000000
Reliability Upgrade | 1a | 182 | Vermont Electric Power Company | 09/2009 |  | Monadnock Area Reliability Project | Upgrade bus cable at N. Rutland and K35 115 kV breaker at Rutland. | In-service | 1000000 | 1000000 | bar: 2006
Reliability Upgrade | 1a | 302 | NSTAR Electric Company | 05/2009 |  | Boston Area 115 kV Enhancements | DCT separation of Framingham to Speen St. 433-507 circuit. | In-service | 3100000 | 3100000 | bar: 2006
Reliability Upgrade | 1b | 963 | NSTAR Electric Company | 12/2009 | 2009 | Boston Area 115 kV Enhancements | Add a new 115kV breaker # 11 Relocate 447-509 and add control and protect at Holbrook. | Proposed | 4000000 | 4000000
Reliability Upgrade | 1b | 809 | Northeast Utilities | 12/2009 | 2009 |  | Upgrade terminal equipment at Bunker Hill 115 kV substation. | Proposed | 1000000 | 1000000
Reliability Upgrade | 1a | 320 | Vermont Electric Power Company | 10/2009 | 2009 | Lamoille County Project | Middlesex Substation 115 kV breaker addition. | Under Construction | 4857000 | 4857000
Reliability Upgrade | 1a | 322 | Vermont Electric Power Company | 10/2009 | 2009 | Lamoille County Project | Installation of new Duxbury Substation that involves looping in and out of the Middlesex - Essex 115 kV (K24) line. | Under Construction | Part of Lamoille County Project | Part of Lamoille County Project
Reliability Upgrade | 1a | 321 | Vermont Electric Power Company | 12/2009 | 2009 | Burlington Project | Burlington 115kV Loop - 5 mi of new line & rebuilding 5 miles of existing line between two existing substations with expansion of the East Avenue substation. | Under Construction | 25142000 | 25142000 | Data Set for Investment Chart by Status 2007: 2009; Data Set for Investment Chart by Status 2008: Concept; Data Set for Investment Chart by Status 2009: 0
Reliability Upgrade | 1a | 1063 | NSTAR Electric Company | 12/2009 | 2009 |  | Install (2) 115kV 40 MVAR shunt reactors at Edgar Station | Under Construction | 5400000 | 5400000 | Data Set for Investment Chart by Status 2007: 2009; Data Set for Investment Chart by Status 2008: Planned; Data Set for Investment Chart by Status 2009: 0
Reliability Upgrade | 1a | 777 | National Grid, USA | 11/2009 | 2009 | Merrimack Valley/North Shore Reliability Project | Build Wakefield Junction station with four 345/115 kV autotransformers. | Under Construction | 95000000 | 95000000 | Data Set for Investment Chart by Status 2007: 2009; Data Set for Investment Chart by Status 2008: Proposed; Data Set for Investment Chart by Status 2009: 2
Reliability Upgrade | 1a | 161 | National Grid, USA | 11/2009 | 2009 | Merrimack Valley/North Shore Reliability Project | Loop 345 kV 339 line and 115 kV S-145/T-146 into new Wakefield Jct. Substation. | Under Construction | 4986431 | 4986431 | Data Set for Investment Chart by Status 2007: 2009; Data Set for Investment Chart by Status 2008: Under Construction; Data Set for Investment Chart by Status 2009: 10
Reliability Upgrade | 1a | 903 | NSTAR Electric Company | 12/2009 | 2009 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #2, #4, #5, and #16 at Mystic to IPT and separate controls with Boston Gen units #5 and #6. | Under Construction | 1240000 | 1240000
Reliability Upgrade | 1a | 930 | National Grid, USA | 12/2009 | 2009 | Central/Western Massachusetts Upgrades | Reconductor Nashua St - Quinsigamond Jct (O141) 115 kV line w/636 ACSS. | Under Construction | 2300000 | 2300000
Reliability Upgrade | 1a | 933 | National Grid, USA | 12/2009 | 2009 | Central/Western Massachusetts Upgrades | Reconductor Pratts Jct - Flagg Pond I-135S & J-136S 115 kV lines w/795 ACSS. | Under Construction | 6137112 | 6137112
Reliability Upgrade | 1a | 211 | Northeast Utilities | 11/2009 | 2009 | NU LSP - Rood Ave Substation | New Rood Ave (formally Windsor) distribution substation with 115kV terminal modifications. | Under Construction | 9162029 | 9162029
Reliability Upgrade | 1b | 1153 | NSTAR Electric Company | 06/2010 | 2010 | Boston Area 115 kV Enhancements | Reliability Upgrades at West Framingham Station | Concept | 3000000 | 3000000
Reliability Upgrade | 1b | 1055 | Northeast Utilities | 2010 | 2010 | CT LSP - Waterside Substation | Waterside Substation - add a 115/13.2-kV transformer and a 115-kV circuit breaker. | Concept | 4107000 | 4107000
Reliability Upgrade | 1a | 1128 | Central Maine Power Company | 07/2010 | 2010 | CMP-LSP Hotel Road Substation | Add 115/34kV transformer with 115kV breaker at Hotel Rd. | Planned | 800000 | 800000 | Data Set for Investment Chart by Status 2007: 2010; Data Set for Investment Chart by Status 2008: Concept; Data Set for Investment Chart by Status 2009: 2
Reliability Upgrade | 1a | 624 | Central Maine Power Company | 2010 | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (New Page - Rumford Industrial Park) | Planned | Part of project 625 | Part of project 625 | Data Set for Investment Chart by Status 2007: 2010; Data Set for Investment Chart by Status 2008: Planned; Data Set for Investment Chart by Status 2009: 21
Reliability Upgrade | 1a | 139 | Vermont Electric Power Company | 12/2010 | 2010 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Planned | 20000000 | 20000000 | Data Set for Investment Chart by Status 2007: 2010; Data Set for Investment Chart by Status 2008: Proposed; Data Set for Investment Chart by Status 2009: 6
Reliability Upgrade | 1a | 840 | NSTAR Electric Company | 10/2010 | 2010 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | 7300000 | 7300000 | Data Set for Investment Chart by Status 2007: 2010; Data Set for Investment Chart by Status 2008: Under Construction; Data Set for Investment Chart by Status 2009: 6
Reliability Upgrade | 1a | 904 | NSTAR Electric Company | 12/2010 | 2010 | Mystic IPT Breaker Project | Upgrade (5) 115 kV breakers #1, #7, #15 #19 and #20 at Mystic to IPT and separate controls with Boston Gen #4. | Planned | 990000 | 990000
Reliability Upgrade | 1a | 928 | National Grid, USA | 12/2010 | 2010 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | 2300000 | 2300000
Reliability Upgrade | 1a | 934 | National Grid, USA | 10/2010 | 2010 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Planned | 818480 | 818480
Reliability Upgrade | 1a | 935 | National Grid, USA | 07/2010 | 2010 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Planned | 5208509 | 5208509
Reliability Upgrade | 1a | 938 | National Grid, USA | 06/2010 | 2010 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | 3068556 | 3068556
Reliability Upgrade | 1a | 942 | National Grid, USA | 10/2010 | 2010 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | 2767180 | 2767180
Reliability Upgrade | 1a | 927 | National Grid, USA | 07/2010 | 2010 | Central/Western Massachusetts Upgrades | Greendale - replace 115 kV breaker and upgrade to 2000A. | Planned | 584629 | 584629
Reliability Upgrade | 1a | 484 | National Grid, USA | 11/2010 | 2010 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Planned | 690000 | 690000
Reliability Upgrade | 1a | 786 | National Grid, USA | 11/2010 | 2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Terminal upgrades at Drumrock, Chartley Pond, and Brayton Point. | Planned | 1000000 | 1000000
Reliability Upgrade | 1a | 787 | National Grid, USA | 12/2010 | 2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | West Farnum breaker replacements. | Planned | 7631000 | 7631000
Reliability Upgrade | 1a | 789 | National Grid, USA | 11/2010 | 2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Reconductoring of T7 115 kV line. | Planned | 23304000 | 23304000
Reliability Upgrade | 1a | 1152 | National Grid, USA | 2010-08-01 | 2010 |  | E205E Refurbishment Project | Planned | 43596000 | 43596000
Reliability Upgrade | 1a | 1049 | United Illuminating Company | 12/2010 | 2010 |  | East Shore 115 kV Capacitor Bank Transient Recovery | Planned | 3000000 | 3000000
Reliability Upgrade | 1a | 582 | Northeast Utilities | 12/2010 | 2010 |  | Separate 310 and 368 345-KV lines and create 368/1767 DCT | Planned | 16000000 | 16000000
Reliability Upgrade | 1a | 1112 | United Illuminating Company | 12/2010 | 2010 |  | Water Street 115kV circuit breaker and switch replacements. | Planned | 1000000 | 1000000
Reliability Upgrade | 1a | 1110 | United Illuminating Company | 12/2010 | 2010 |  | Broadway 115/13.8 kV Substation Additon | Planned | 1200000 | 1200000
Reliability Upgrade | 1a | 1111 | United Illuminating Company | 12/2010 | 2010 |  | Metro North Union Avenue 115/26.4 kV Substation | Planned | 10543000 | 10543000
Reliability Upgrade | 1b | 1133 | Central Maine Power Company | 10/2010 | 2010 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation & new 34kV line from Leeds to Turner | Proposed | 300000 | 300000
Reliability Upgrade | 1b | 842 | NSTAR Electric Company | 06/2010 | 2010 | Boston Area 115 kV Enhancements | Add 115 kV 54 MVAR capacitor bank at W. Framingham. | Proposed | 3700000 | 3700000
Reliability Upgrade | 1b | 1113 | NSTAR Electric Company | 12/2010 | 2010 |  | Install KSt Breaker #31 | Proposed | 2960000 | 2960000
Reliability Upgrade | 1b | 1067 | NSTAR Electric Company | 12/2010 | 2010 | NPCC BPS Compliance | Tremont Station | Proposed | 12800000 | 12800000
Reliability Upgrade | 1b | 1119 | NSTAR Electric Company | 12/2010 | 2010 | Greater Boston Reliability Project | Upgrade West Medway-West Walpole 345kV line #325 | Proposed | 2200000 | 2200000
Reliability Upgrade | 1b | 1120 | NSTAR Electric Company | 06/2010 | 2010 |  | Install 345kV 160 MVAR shunt ractor at W. Walpole | Proposed | 7200000 | 7200000
Reliability Upgrade | 1a | 144 | Bangor Hydro-Electric Company | 12/2010 | 2010 | Keene Rd Autotransformer | Installation of a 345/115 kV autotransformer at Keene Rd Substation. | Under Construction | 29000000 | 29000000
Reliability Upgrade | 1a | 625 | Central Maine Power Company | 02/2010 | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Rumford Industrial Park capacitor bank. | Under Construction | 5400000 | 5400000
Reliability Upgrade | 1a | 1029 | Central Maine Power Company | 11/2010 | 2010 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformer at South Gorham | Under Construction | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1144 | Central Maine Power Company | 04/2010 | 2010 | Heywood Road Project | Circuit switcher replacements at Detroit, Lakewood, Rice Rips and Winslow | Under Construction | Part of Heywood Road Project | Part of the Heywood Road Project
Reliability Upgrade | 1a | 779 | National Grid, USA | 04/2010 | 2010 | Merrimack Valley/North Shore Reliability Project | Bypass and remove Golden Hills 345 kV substation. | Under Construction | 5132609 | 5132609
Reliability Upgrade | 1a | 961 | NSTAR Electric Company | 11/2010 | 2010 | Mystic Breaker Additions Project | Install (2) new 115 kV East Bus breakers #30 and #32 at Mystic and move Transformer 110B Connection. | Under Construction | 3800000 | 3800000
Reliability Upgrade | 1b | 1116 | Bangor Hydro-Electric Company | 12/2011 | 2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Concept | TBD | TBD
Reliability Upgrade | 1b | 318 | Vermont Electric Power Company | 12/2011 | 2011 |  | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems through the 1,250 MW Vermont state load level. | Concept | 9000000 | 9000000 | Data Set for Investment Chart by Status 2007: 2011; Data Set for Investment Chart by Status 2008: Concept; Data Set for Investment Chart by Status 2009: 5
Reliability Upgrade | 1b | 325 | Vermont Electric Power Company | 12/2011 | 2011 | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | 5000000 | 5000000 | Data Set for Investment Chart by Status 2007: 2011; Data Set for Investment Chart by Status 2008: Planned; Data Set for Investment Chart by Status 2009: 23
Reliability Upgrade | 1b | 301 | NSTAR Electric Company | 12/2011 | 2011 | Boston Area 115 kV Enhancements | Reconductor 115-kV circuits 320-507 and 320-508. | Concept | 4600000 | 4600000 | Data Set for Investment Chart by Status 2007: 2011; Data Set for Investment Chart by Status 2008: Proposed; Data Set for Investment Chart by Status 2009: 8
Reliability Upgrade | 1b | 1066 | NSTAR Electric Company | 09/2011 | 2011 | NPCC BPS Compliance | Needham Station | Concept | 9300000 | 9300000 | Data Set for Investment Chart by Status 2007: 2011; Data Set for Investment Chart by Status 2008: Under Construction; Data Set for Investment Chart by Status 2009: 6
Reliability Upgrade | 1a | 1145 | Vermont Electric Power Company | 09/2011 | 2011 | Burlington Project | Installation of a 3-breaker 115kV ring substation and 115/34.5kV transformer on the East Ave. - Tafts Coners 115kV line | Planned | 14000000 | 14000000
Reliability Upgrade | 1a | 783 | National Grid, USA | 03/2011 | 2011 | Merrimack Valley/North Shore Reliability Project | Extend the 115kV by addition of 115kV Breaker and K-153 line from King St. to W. Amesbury 115kV station. (W. Amesbury 345/115kV Station becomes PTF) | Planned | 30349000 | 30349000
Reliability Upgrade | 1a | 929 | National Grid, USA | 06/2011 | 2011 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | 1381849 | 1381849
Reliability Upgrade | 1a | 939 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor and retension (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | Planned | 3389658 | 3389658
Reliability Upgrade | 1a | 940 | National Grid, USA | 04/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS. | Planned | 6235744 | 6235744
Reliability Upgrade | 1a | 925 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | 318888 | 318888
Reliability Upgrade | 1a | 926 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | 6027520 | 6027520
Reliability Upgrade | 1a | 932 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | 372036 | 372036
Reliability Upgrade | 1a | 924 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | Planned | 2147181 | 2147181
Reliability Upgrade | 1a | 941 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Install new Millbury - Tower #510 115 kV line. | Planned | 7909203 | 7909203
Reliability Upgrade | 1a | 943 | National Grid, USA | 01/2011 | 2011 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | 1073995 | 1073995
Reliability Upgrade | 1a | 952 | National Grid, USA | 06/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor E Winchendon - J136 Tap within I135/J136 ROW w/795 ACSR. | Planned | 932156 | 932156
Reliability Upgrade | 1a | 937 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | 6602875 | 6602875
Reliability Upgrade | 1a | 955 | National Grid, USA | 11/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | 10779113 | 10779113
Reliability Upgrade | 1a | 1000 | Northeast Utilities | 12/2011 | 2011 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | Planned | 22000000 | 22000000
Reliability Upgrade | 1a | 1076 | Northeast Utilities | 12/2011 | 2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Planned | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1077 | Northeast Utilities | 12/2011 | 2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115kV line | Planned | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 788 | National Grid, USA | 06/2011 | 2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Kent County substation expansion. | Planned | 42300000 | 42300000
Reliability Upgrade | 1a | 790 | National Grid, USA | 12/2011 | 2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Planned | 50600000 | 50600000
Reliability Upgrade | 1a | 1098 | National Grid, USA | 12/2011 | 2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Planned | 37529000 | 37529000
Reliability Upgrade | 1a | 974 | United Illuminating Company | 12/2011 | 2011 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Planned | 6700000 | 6700000
Reliability Upgrade | 1a | 1056 | Northeast Utilities | 12/2011 | 2011 | CT LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Planned | 9751000 | 9751000
Reliability Upgrade | 1a | 1050 | United Illuminating Company | 12/2011 | 2011 |  | Devon Tie 115kV Switching Station BPS Compliance | Planned | 2620000 | 2620000
Reliability Upgrade | 1b | 1130 | Central Maine Power Company | 12/2011 | 2011 | Sturtevant Improvements | Add 115kV circuit breakers & 25 MVAR capacitor bank at Sturtevant Substation; Re-rate Section 63 between Wyman Hydro & Madison Substation | Proposed | 3000000 | 3000000
Reliability Upgrade | 1b | 1131 | Central Maine Power Company | 12/2011 | 2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Proposed | 600000 | 600000
Reliability Upgrade | 1b | 1132 | Central Maine Power Company | 12/2011 | 2011 | CMP-LSP Maxcy's Substation | Add 115/34kV transformer (coordinate with MPRP) | Proposed | 600000 | 600000
Reliability Upgrade | 1b | 964 | NSTAR Electric Company | 06/2011 | 2011 | Boston Area 115 kV Enhancements | Relocate 115kV terminals at W. Walpole to mitigate breaker failure #8. | Proposed | 5600000 | 5600000
Reliability Upgrade | 1b | 1150 | United Illuminating Company | 10/2011 | 2011 |  | Grand Avenue - West River 115 kV Pumping Plant Replacements | Proposed | 1200000 | 1200000
Reliability Upgrade | 1b | 1151 | United Illuminating Company | 12/2011 | 2011 |  | West River 115kV Switching Station Fault Duty Migration | Proposed | 3500000 | 3500000
Reliability Upgrade | 1b | 1147 | Northeast Utilities | 2011 | 2011 |  | Waterside Substation - install a three-breaker 115kV ring bus | Proposed | 4000000 | 4000000
Reliability Upgrade | 1b | 1148 | Northeast Utilities | 2011 | 2011 |  | Add a 2nd high speed relay on the Glennbrook to Waterside 115kV 1440 | Proposed | 600000 | 600000
Reliability Upgrade | 1a | 323 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project | New VY - Newfane - Coolidge 345 kV line with requisite station upgrades. | Under Construction | 136368000 | 136368000
Reliability Upgrade | 1a | 1032 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project | Installation of a new 345/115kV substation called Vernon including a new 345/115kV autotransformer | Under Construction | 69815000 | 69815000
Reliability Upgrade | 1a | 1033 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project (VELCO LSP - Newfane Substation) | Installation of a new 345/115kV substation called Newfane | Under Construction | 16664000 | 16664000 | Data Set for Investment Chart by Status 2007: 2012; Data Set for Investment Chart by Status 2008: Concept; Data Set for Investment Chart by Status 2009: 6
Reliability Upgrade | 1a | 1034 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project | Loop new 345kV Line into Newfane Substation. | Under Construction | Part of project 323 | Part of project 323 | Data Set for Investment Chart by Status 2007: 2012; Data Set for Investment Chart by Status 2008: Planned; Data Set for Investment Chart by Status 2009: 43
Reliability Upgrade | 1a | 1035 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project | Expansion of Coolidge 345kV substation | Under Construction | 20117000 | 20117000 | Data Set for Investment Chart by Status 2007: 2012; Data Set for Investment Chart by Status 2008: Proposed; Data Set for Investment Chart by Status 2009: 6
Reliability Upgrade | 1a | 162 | National Grid, USA | 04/2011 | 2011 |  | Q-169 Golden Hills to Lynn 115 kV line upgrade. | Under Construction | 12390000 | 12390000 | Data Set for Investment Chart by Status 2007: 2012; Data Set for Investment Chart by Status 2008: Under Construction; Data Set for Investment Chart by Status 2009: 1
Reliability Upgrade | 1b | 1031 | Bangor Hydro-Electric Company | 01/2012 | 2012 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station, Rebuild Line 66, and Capacitior Bank Additions (10MVAr at Trenton, Downeast & Handcock County area) | Concept | TBD | TBD
Reliability Upgrade | 1b | 324 | Vermont Electric Power Company | 12/2012 | 2012 |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | 100000000 | 100000000
Reliability Upgrade | 1b | 965 | NSTAR Electric Company | 12/2012 | 2012 | Boston Area 115 kV Enhancements | Add third 115kV line from Walpole to Holbrook | Concept | TBD | TBD
Reliability Upgrade | 1b | 970 | NSTAR Electric Company | 12/2012 | 2012 | Greater Boston Reliability Project | Add a new 345 kV line from Lexington to Waltham. | Concept | TBD | TBD
Reliability Upgrade | 1b | 971 | NSTAR Electric Company | 12/2012 | 2012 | Greater Boston Reliability Project | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | TBD | TBD
Reliability Upgrade | 1b | 699 | United Illuminating Company | 12/2012 | 2012 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | 10000000 | 10000000
Reliability Upgrade | 1a | 905 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Planned | 1510000000 | 1510000000
Reliability Upgrade | 1a | 906 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Coopers Mills-Highland, Larrabee Road-Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 907 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 84 (Albion Road-Coopers Mills), Section 203 (Detroit-Orrington), Section 80 (Coopers Mills-Highland), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 908 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377 & Maine Yankee 375/392, 115kV Bucksport 65/205) and Maine Yankee 345 kV re-termination | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1026 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Three Rivers) | Planned | Portion of CMP $1.51B and portion of NU is $35.1M | 35100000
Reliability Upgrade | 1a | 1027 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 115kV Line Construction (Elm Street-East Deering, East Deering -Cape) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1028 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD
Reliability Upgrade | 1a | 1030 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Raven Farm, Maguire Road) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 143 | Bangor Hydro-Electric Company | 12/2012 | 2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation to Harrington Substation. | Planned | 66100000 | 66100000
Reliability Upgrade | 1a | 1129 | Central Maine Power Company | 05/2012 | 2012 |  | New 115kV line between Wyman Hydro and Heywood Rd. parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | 19500000 | 19500000
Reliability Upgrade | 1a | 277 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Planned | 56600000 | 56600000
Reliability Upgrade | 1a | 1137 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115kV breakers and add 1-115kV breaker at Deerfield Substation | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1138 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rebuild 115kV L175 line | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1139 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV M183 Line | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1140 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1141 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 680 | National Grid, USA | 09/2012 | 2012 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | 7393000 | 7393000
Reliability Upgrade | 1a | 1146 | Vermont Electric Power Company | 12/2012 | 2012 | Lyndonville Project | Installation of a 3-breaker 115kV righ station consisting of two 115kV 12.5 MVAR capacitor banks and 115/34.5 kV transformer interconnecting to the Irasburg - St. Johnsbury 115kV line | Planned | 9000000 | 9000000
Reliability Upgrade | 1a | 887 | National Grid, USA | 09/2012 | 2012 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Planned | 30000000 | 30000000
Reliability Upgrade | 1a | 921 | National Grid, USA | 01/2012 | 2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | 12100000 | 12100000
Reliability Upgrade | 1a | 919 | National Grid, USA | 09/2012 | 2012 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | 4600000 | 4600000
Reliability Upgrade | 1a | 775 | National Grid, USA | 06/2012 | 2012 | Merrimack Valley/North Shore Reliability Project | Addition of 4 breakers and relocation of T1 and T2 into new bays at Sandy Pond. | Planned | 20100000 | 20100000
Reliability Upgrade | 1a | 776 | National Grid, USA | 06/2012 | 2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | 2865876 | 2865876
Reliability Upgrade | 1a | 59 | National Grid, USA | 01/2012 | 2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | 400000 | 400000 | bar: 2006
Reliability Upgrade | 1a | 944 | National Grid, USA | 07/2012 | 2012 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Planned | 11411849 | 11411849
Reliability Upgrade | 1a | 948 | National Grid, USA | 07/2012 | 2012 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | 5649430 | 5649430
Reliability Upgrade | 1a | 949 | National Grid, USA | 07/2012 | 2012 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | 1500000 | 1500000
Reliability Upgrade | 1a | 673 | National Grid, USA | 12/2012 | 2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | National Grid, USA | 12/2012 | 2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Planned | 30000000 | 30000000
Reliability Upgrade | 1a | 1095 | National Grid, USA | 06/2012 | 2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | 73800000 | 73800000
Reliability Upgrade | 1a | 797 | National Grid, USA | 12/2012 | 2012 | NEEWS (Interstate Reliability Project) | 3361 Upgrade 345kV terminal equipment at Sherman Road. | Planned | 8300000 | 8300000
Reliability Upgrade | 1a | 795 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV line. | Planned | 99900000 | 99900000
Reliability Upgrade | 1a | 1106 | National Grid, USA | 05/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | Planned | Part of $99,900,000 above | Part of $99,900,000 above
Reliability Upgrade | 1a | 798 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Planned | 4900000 | 4900000
Reliability Upgrade | 1a | 799 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | Planned | 4500000 | 4500000
Reliability Upgrade | 1a | 1096 | National Grid, USA | 05/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | 12000000 | 12000000
Reliability Upgrade | 1a | 800 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S, T-172N and T-172S with associated terminal equipment upgrades. | Planned | 10000000 | 10000000
Reliability Upgrade | 1a | 1097 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County | Planned | 129800000 | 129800000
Reliability Upgrade | 1a | 1099 | National Grid, USA | 05/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | 6000000 | 6000000
Reliability Upgrade | 1a | 1109 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Planned | 1000000 | 1000000
Reliability Upgrade | 1a | 976 | United Illuminating Company | 05/2012 | 2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Planned | 48000000 | 48000000
Reliability Upgrade | 1b | 148 | Central Maine Power Company | 06/2012 | 2012 | CMP LSP - Saco Bay Area Reinforcement Project | Establish a new Vallee Lane 115/34.5 kV substation and 115 kV line from Louden S/S to Vallee Lane Substation. | Proposed | 100000 | 100000
Reliability Upgrade | 1b | 1068 | NSTAR Electric Company | 12/2012 | 2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to Sandwich and a a 345-115kV auto-transformer at Sandwich | Proposed | 110000000 | 110000000
Reliability Upgrade | 1b | 592 | NSTAR Electric Company | 12/2012 | 2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing | Proposed | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1118 | NSTAR Electric Company | 12/2012 | 2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 | Proposed | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1065 | NSTAR Electric Company | 07/2012 | 2012 | NPCC BPS Compliance | Waltham Station | Proposed | 26600000 | 26600000
Reliability Upgrade | 1b | 1136 | National Grid, USA | 12/2012 | 2012 |  | New 115kV Switching Station at Devens Convert 69kV lines to 115kV, Reconfigure 115kV Supply at Ayer Substation | Proposed | 9200000 | 9200000
Reliability Upgrade | 1a | 902 | National Grid, USA | 03/2012 | 2012 | Middleboro Municipal | Close the E1-M1 loop at Middleboro's Wareham St Sub. | Under Construction | 715000 | 715000
Reliability Upgrade | 1b | 843 | NSTAR Electric Company | 12/2013 | 2013 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | TBD | TBD
Reliability Upgrade | 1b | 593 | NSTAR Electric Company | 2013 | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Canal to Barnstable/Falmouth | Concept | TBD | TBD | Data Set for Investment Chart by Status 2007: 2013; Data Set for Investment Chart by Status 2008: Concept; Data Set for Investment Chart by Status 2009: 4
Reliability Upgrade | 1b | 956 | National Grid, USA | 05/2013 | 2013 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Concept | 7021534 | 7021534 | Data Set for Investment Chart by Status 2007: 2013; Data Set for Investment Chart by Status 2008: Planned; Data Set for Investment Chart by Status 2009: 59
Reliability Upgrade | 1b | 975 | United Illuminating Company | 12/2013 | 2013 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | 44300000 | 44300000 | Data Set for Investment Chart by Status 2007: 2013; Data Set for Investment Chart by Status 2008: Proposed; Data Set for Investment Chart by Status 2009: 1
Reliability Upgrade | 1a | 674 | National Grid, USA | 09/2013 | 2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | 7720000 | 7720000 | Data Set for Investment Chart by Status 2007: 2013; Data Set for Investment Chart by Status 2008: Under Construction; Data Set for Investment Chart by Status 2009: 0
Reliability Upgrade | 1a | 782 | National Grid, USA | 10/2013 | 2013 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor n Railyard. | Planned | 38100000 | 38100000
Reliability Upgrade | 1a | 931 | National Grid, USA | 01/2013 | 2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | 531481 | 531481
Reliability Upgrade | 1a | 950 | National Grid, USA | 12/2013 | 2013 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | 1016897 | 1016897
Reliability Upgrade | 1a | 953 | National Grid, USA | 12/2013 | 2013 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | 10248067 | 10248067
Reliability Upgrade | 1a | 954 | National Grid, USA | 12/2013 | 2013 | Central/Western Massachusetts Upgrades | E Westminster - install new 115 kV breaker, including disconnect switches. Assumes no new control house. | Planned | 903909 | 903909
Reliability Upgrade | 1a | 945 | National Grid, USA | 02/2013 | 2013 | Central/Western Massachusetts Upgrades | Adams - install third 115 kV breaker to complete ring bus. | Planned | 1584841 | 1584841
Reliability Upgrade | 1a | 946 | National Grid, USA | 04/2013 | 2013 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer - E Longmeadow - Shaker Rd line to 115 kV. | Planned | 9604032 | 9604032
Reliability Upgrade | 1a | 947 | National Grid, USA | 04/2013 | 2013 | Central/Western Massachusetts Upgrades | Reconductor 115 kV line from Palmer to new Hampden Substation. | Planned | 2632635 | 2632635
Reliability Upgrade | 1a | 951 | National Grid, USA | 02/2013 | 2013 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon 115 kV line. | Planned | 7455440 | 7455440
Reliability Upgrade | 1a | 687 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | 714000000 | 714000000
Reliability Upgrade | 1a | 826 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 196 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115kV line South Agawam to Southwick (1768) | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVAR Capacitor additions | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1074 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1078 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 190 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | 69600000 | 69600000
Reliability Upgrade | 1a | 1094 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | 25000000 | 25000000
Reliability Upgrade | 1a | 794 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | 55800000 | 55800000
Reliability Upgrade | 1a | 796 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | 347 Reconductor from Sherman Road to CT/RI Border. | Planned | 16400000 | 16400000
Reliability Upgrade | 1a | 816 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1054 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Manchester - Meekvile Jct. line (395/1448) separation. | Planned | 14000000 | 14000000
Reliability Upgrade | 1a | 576 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | 313000000 | 313000000
Reliability Upgrade | 1a | 1114 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1a | 814 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Ancillary Central Connecticut Relaibility Project) | Reconductor a portion of the Manchester to Scovill Rock 353 345-kV line and terminal work. | Planned | 9000000 | 9000000
Reliability Upgrade | 1a | 802 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | 251000000 | 251000000
Reliability Upgrade | 1a | 1084 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Loop the Millstone - Manchester (310) 345 kV line into the Card substation. | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1085 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1086 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1087 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1088 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1089 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Killingly 3G substation 345kV breaker addition | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1090 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Millstone 15G substation breaker 14T upgrade 50kA | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1091 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Southington 4C substation breaker 19T upgrade to 63kA | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 807 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Ancillary Interstate Reliability Project) | Install 480 MVAR's of capacitors at the Montville 345 kV substation | Planned | 33000000 | 33000000
Reliability Upgrade | 1a | 1092 | Northeast Utilities | 12/2013 | 2013 | NEEWS (BPS) 2 | Upgrade the Card 115 kV, East Hartford 115 kV, Agawam 115 kV, Barbour Hill 115 kV, and North Bloomfield 345 kV Substations to BPS standards. | Planned | 37000000 | 37000000
Reliability Upgrade | 1b | 721 | United Illuminating Company | 06/2013 | 2013 |  | New Shelton 115/13.8 kV substation | Proposed | 11300000 | 11300000
Reliability Upgrade | 1a | 791 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | 11560000 | 11560000
Reliability Upgrade | 1a | 913 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | 3250000 | 3250000
Reliability Upgrade | 1a | 914 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | 28150000 | 28150000
Reliability Upgrade | 1a | 915 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | 11800000 | 11800000
Reliability Upgrade | 1a | 917 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | 7000000 | 7000000
Reliability Upgrade | 1a | 918 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | 3180000 | 3180000
Reliability Upgrade | 1a | 792 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Admiral St-Franklin Square (Q143 and R144) 115 kV UG recabling. | Planned | 39200000 | 39200000
Reliability Upgrade | 1a | 793 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | 6400000 | 6400000
Reliability Upgrade | 1b | 785 | National Grid, USA | 07/2017 | 2017 | Merrimack Valley/North Shore Reliability Project | Re-conductor F-158N (Golden Hills-Maplewood-Everett) 115 kV line. | Concept | 1330000 | 1330000
Reliability Upgrade | 1b | 969 | NSTAR Electric Company | 06/2018 | 2018 | Boston Area 115 kV Enhancements | Add a new 54 MVAR capacitor bank at Chelsea. | Concept | 1200000 | 1200000
Reliability Upgrade | 1b | 275 | Northeast Utilities | TBD | tbd |  | Merrimack 115-kV substation - Protection Separation Upgrade. | Concept | TBD | TBD
Reliability Upgrade | 1b | 824 | Northeast Utilities | TBD | tbd | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Concept | TBD | TBD
Reliability Upgrade | 1b | 825 | Northeast Utilities | TBD | tbd | Pittsfield / Greenfield Project | Upgrade the Pleasant to Blanford 115-kV line and the Blanford to Granville Jct. portion of the 115-kV line 1512. | Concept | TBD | TBD
Reliability Upgrade | 1b | 801 | Northeast Utilities | TBD | tbd |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Concept | TBD | TBD
Reliability Upgrade | 1b | 85 | Northeast Utilities | TBD | tbd |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | TBD | TBD
Reliability Upgrade | 1a | 879 |  | TBD | tbd | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | 420000 | 420000
Reliability Upgrade | 1b | 1135 | Central Maine Power Company | TBD | tbd | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer | Proposed | 1500000 | 1500000
Reliability Upgrade | 1b | 1143 | Northeast Utilities | TBD | tbd |  | Littleton 115kV breaker addition and reconfiguration | Proposed | 5338000 | 5338000