## All Approved 18.4 & I.3.9
ISO-NE Public
Application ID | Application Date | Facility/Station | General Description | Expected In Service Date | ISO Action | ISO Action Date
http://www.iso-ne.com/system-planning/transmission-planning/proposed-plan-applications
GLE-25-G01 | 2025-04-10 | Queue Position 1239 (QP 1239) Solar and Battery Project | Generator application from Glenvale LLC on behalf of Woodstock Meadow Solar Station LLC for the installation of a 75 MW Solar PV and 100 MW/ 300 MWh Battery (120 MW net facility output) facility in Woodstock and interconnecting to Woodstock Substation. | 2028-08-01 | Approved | 2025-04-17
GLE-25-T01 | 2025-04-10 | Queue Position 1239 (QP 1239) Solar and Battery Project | Transmission application from Glenvale LLC on behalf of Woodstock Meadow Solar Station LLC for the installation of 115 kV 0.65-mile generation lead line to Woodstock Substation. | 2028-08-01 | Approved | 2025-04-17
CMP-25-X01 | 2025-04-02 | Queue Position 1239 (QP 1239) Solar and Battery Project | Transmission application from Central Maine Power for the installation of additional redundant differential bus protection at Kimball Substation. | 2028-08-01 | Approved | 2025-04-17
CMP-25-T01 | 2025-04-02 | Queue Position 1239 (QP 1239) Solar and Battery Project | Transmission application from Central Maine Power for the installation of a third 115 kV bay and two 115 kV circuit breakers at Woodstock Substation. | 2028-08-01 | Approved | 2025-04-17
CMP-23-G67 Rev.2 | 2025-04-02 | BD Solar Dexter LLC - 445 Corinna Road Solar Rev.2 | Generator notification from Central Maine Power on behalf of BD Solar Dexter LLC for the installation of 1.999 MW Solar PV in Dexter, ME and interconnecting to 445 Corinna Road Dexter, ME via circuit 813D1 out of Dexter Substation. | 2026-06-30 | Notification | 2025-04-17
CMP-23-G77 Rev.1 | 2025-04-02 | Swan River Solar - 1312 Canton Point Road Solar Rev.1 | Generator notification from Central Maine Power on behalf of Swan River Solar, LLC for the installation of 0.975 MW Solar PV in Dixfield, ME and interconnecting to the Ludden Lane Substation via the 461D1 circuit. | 2026-06-30 | Notification | 2025-04-17
CMP-24-G03 Rev.1 | 2025-04-02 | ER Carlton Road Solar, LLC - 35 Carlton Poind Road Solar Rev.1 | Generator notification from Central Maine Power on behalf of ER Carlton Road Solar, LLC for the installation of 0.995 MW PV facility in Winthrop, ME and interconnecting to the Manchester substation via the 233D2 circuit. | 2025-09-19 | Notification | 2025-04-17
CMP-24-G16 Rev.1 | 2025-04-02 | 510 PV Project Development LLC - 720 US Route 1 Solar Rev.1 | Generator notification from Central Maine Power on behalf of 510 PV Project Development LLC for the installation of 0.999 MW Solar PV in Scarborough, ME and interconnecting to the Dunstan Substation via the 617D2 circuit. | 2025-07-15 | Notification | 2025-04-17
GMP-24-G10 Rev.1 | 2025-05-14 | Williston H Solar, LLC - 1022 Redmond Road Solar Rev.1 | Generator notification from Green Mountain Power on behalf of Williston H Solar, LLC for the installation of 2.75 MW Solar PV in Williston, VT and interconnecting to 1022 Redmond Road Williston, VT via circuit G2 out of Williston Substation. | 2026-09-01 | Notification | 2025-04-17
LWL-25-G01 | 2025-04-02 | Kearsarge Littleton LLC - Industrial Park Road | Generator notification from Littleton Water & Light on behalf of Kearsarge Littleton LLC for the installation of 2.6 MW Solar PV in Littleton, NH and interconnecting to Industrial Park Road Littleton, NH via Bus B21 out of Burndy 12.47 kV Substation. | 2025-12-01 | Notification | 2025-04-17
VPPSA-25-G01 | 2025-03-11 | Kearsarge PV Orleans LLC - 1765 Baird Road Solar | Generator notification from Vermont Public Power Supply Authority on behalf of Kearsarge PV Orleans LLC for the installation of 4.928 MW Solar PV in Barton, VT and interconnecting to 81765 Baird Road Barton, VT via Orleans distribution feeder. | 2025-09-30 | Notification | 2025-04-17
ES-21-G82 Rev.2 | 2025-03-24 | Float Lane Plymouth Solar, LLC - 17 Plymouth Street Solar and Battery | Generator notification from Eversource Energy on behalf of Float Lane Plymouth Solar, LLC for the installation of 2.0 MW Solar PV and 2.0 MW/6.0 MWh DC Coupled Battery in Carver, MA and interconnecting to 17 Plymouth Street Carver, MA via circuit 3-10-10 out of West Pond Substation. | 2025-09-30 | Notification | 2025-04-17
GELD-25-G01 | 2025-03-13 | Groton MA BESS 3 LLC - 600 Cow Pond Brook Road Battery | Generator notification from Groton Electric Light Department on behalf of Groton MA BESS 3 LLC for the installation of a 4.999 MW/25.0 MWh Battery in Groton, MA and interconnecting to 600 Cow Pond Brook Road Groton, MA via circuit 7 out of Lowell Road Substation. | 2026-06-30 | Notification | 2025-04-17
NEP-24-G06 Rev.1 | 2025-04-01 | Thorndike Street DESS - 3166 Thorndike Street Battery Rev.1 | Generator notification from New England Power on behalf of Thorndike Street BESS for the installation of a 4.948 MW/19.792 MWh Battery in Palmer, MA and interconnecting to 3166 Thorndike Street Palmer, MA via circuit 523L3 out of Thorndike Substation. | 2029-04-01 | Notification | 2025-04-17
PML-25-G01 | 2025-03-19 | Princeton BESS 1 LLC - 168 Worcester Road Battery | Generator notification from Princeton Municipal Light Department on behalf of Princeton BESS 1 LLC for the installation of a 3.5 MW/10.03 MWh Battery in Princeton, MA and interconnecting to 168 Worcester Road Princeton, MA via PMLD service feeder out of East Westminster Substation. | 2025-10-01 | Notification | 2025-04-17
GDQ-25-G01 | 2025-02-28 | Queue Position 1163 (QP 1163) Battery Project | Generator application from Green Development, LLC on behalf of GDQ ESS, LLC for the installation of a 201.43 MW/402.86 MWh Battery facility in North Kingston, RI and interconnecting to a 115 kV substation. | 2026-06-01 | Approved | 2025-03-20
GDQ-25-T01 | 2025-02-28 | Queue Position 1163 (QP 1163) Battery Project | Transmission application from Green Development, LLC on behalf of GDQ ESS, LLC for the installation of a 115/34.5/13.8 kV transformer and a 115 kV generation lead line. | 2026-06-01 | Approved | 2025-03-20
RIE-25-T01 | 2025-03-03 | Queue Position 1163 (QP 1163) Battery Project | Transmission application from Rhode Island Energy for the construction of a new 115 kV Switching Station, in North Kingstown, RI. | 2028-12-31 | Approved | 2025-03-20
ES-25-T01 | 2025-02-28 | Eversource Energy - Greater Cambridge Energy Program | Transmission application from Eversource Energy for the construction of a new 115 kV Substation, Station 8025, in Cambridge, MA. | 2031-06-30 | Approved | 2025-04-02
ES-25-T02 | 2025-02-28 | Eversource Energy - Greater Cambridge Energy Program | Transmission application from Eversource Energy for the construction of two series reactors at North Cambridge Substation. | 2031-06-30 | Approved | 2025-04-02
ES-25-T03 | 2025-02-28 | Eversource Energy - Greater Cambridge Energy Program | Transmission application from Eversource Energy for the replacement of the 115kV transmission Lines 329-510 and 329-511 between the Brighton Substation and Somerville Substation with two XLPE cables in addition to looping the circuits into Substation 8025. | 2031-06-30 | Approved | 2025-04-02
ES-25-T04 | 2025-02-28 | Eversource Energy - Greater Cambridge Energy Program | Transmission application from Eversource Energy for the construction of lines 250-510 and 250-511 between Substation 8025 and Somerville Substation. | 2031-06-30 | Approved | 2025-04-02
ES-25-T05 | 2025-02-28 | Eversource Energy - Greater Cambridge Energy Program | Transmission application from Eversource Energy for the reconfiguration of Line 831-538 to loop into the 8025 Substation. | 2031-06-30 | Approved | 2025-04-02
ES-25-T06 | 2025-02-28 | Eversource Energy - Greater Cambridge Energy Program | Transmission application from Eversource Energy for the reconfiguration of Line 850-539 to loop into the 8025 Substation. | 2031-06-30 | Approved | 2025-04-02
ESR-21-G02 Rev.1 | 2025-03-04 | Queue Position 874 (QP 874) Battery Project Revision | Generation application from Energy Storage Resources, LLC on behalf of Cross Town Energy Storage, LLC for the installation of a 175.0 MW/350.0 MWh Battery facility in Gorham, ME and interconnecting to 115 kV Moshers substation. | 2025-08-25 | Approved | 2025-03-20
ESR-21-T02 Rev.1 | 2025-03-04 | Queue Position 874 (QP 874) Battery Project Revision | Transmission application from Energy Storage Resources, LLC on behalf of Cross Town Energy Storage, LLC for the construction of a new 115/34.5/12.8 kV Transformer at the Moshers 115 kV substation along with a 0.15 mile generation lead from the generation project to the substation. | 2025-05-22 | Approved | 2025-03-20
CMP-21-T01 Rev.1 | 2025-03-03 | Queue Position 874 (QP 874) Battery Project Revision | Transmission application from Central Maine Power for installation of one 115 kV breaker at the Mothers Substation. | 2025-05-22 | Approved | 2025-03-20
GMP-25-G03 | 2025-02-19 | Queue Position 1226 (QP 1226) Solar Project | Generator notification from Green Mountain Power Inc. on behalf of Power Investments LLC for the installation of 4.99 MW Solar PV in Claremont, NH and interconnecting to 124/125 Grissom Lane Claremont, NH via Green Mountain Power 46 kV TL102B line. | 2025-05-15 | Notification | 2025-03-20
NEP-19-G30-057 Rev.4 | 2025-03-03 | Ecos Energy, LLC - 875 Spring Street Solar | Generator notification from New England Power on behalf of Ecos Energy, LLC for the installation of 3.9 MW Solar PV in Winchendon, MA and interconnecting to 875 Spring Street Winchendon, MA via circuit 612W3 out of East Winchendon Substation. | 2025-01-15 | Notification | 2025-03-20
NEP-25-GNF01 | 2025-03-03 | Bluewave Solar, LLC - 283 Winter Street Solar | Generator notification from New England Power on behalf of Bluewave Solar, LLC for the installation of 2.0 MW Solar PV in Norwell, MA and interconnecting to 283 Winter Street Norwell, MA via circuit 915W35 out of Scituate Substation. | 2028-03-01 | Notification | 2025-03-20
RIE-24-G04 Rev.1 | 2025-02-24 | Nautilus Solar - 148 Mail Road Solar | Generator notification from Rhode Island Energy on behalf of Nautilus Solar for the installation of 4.945 MW Solar PV in Exeter, RI and interconnecting to 148 Mail Road Exeter, RI via circuit 88F1 out of Tower Hill Substation. | 2024-12-31 | Notification | 2025-03-20
WMGLD-24-G01 Rev.1 | 2025-02-24 | Wakefield BESS 1 LLC - 23 Hemlock Road Battery | Generator notification from Wakefield Municipal Gas & Light Department on behalf of BESS 1 LLC for the installation of a 4.99 MW/22.0 MWh Battery in Wakefield, MA and interconnecting to 23 Hemlock Road Wakefield, MA via circuit 12 out of Beebe Substation. | 2025-06-01 | Notification | 2025-03-20
ES-25-T08 | 2025-03-03 | Hyannis Junction Station T2 Transformer Replacement | Transmission notification from Eversource Energy for the replacement of the existing T2 115/24 kV 83 MVA transformer with a 115/24 kV 73 MVA transformer. | 2025-03-31 | Notification | 2025-03-20
ES-25-T11 | 2025-03-03 | Blandford Breaker Replacement and Series Breaker Addition | Transmission notification from Eversource Energy for the replacement of the existing 1T 115 kV breaker with new 1T and 2T 115 kV breakers. | 2027-11-01 | Notification | 2025-03-26
VEC-25-G10 | 2025-01-24 | Brighton Basil Hill Solar LLC - Basil Hill Road Solar | Generator notification from Vermont Electric Coop on behalf of Brighton Basil Hill Solar LLC for the installation of 2.0 MW Solar PV in Essex, VT and interconnecting to Basil Hill Rd Essex, VT via circuit 47-4A out of Island Pond Substation. | 2025-12-31 | Notification | 2025-02-14
GMP-25-G02 | 2025-01-30 | Williston F Mountain View Solar, LLC - 1101 Mountain View Road Solar | Generator notification from Green Mountain Power on behalf of Williston F Mountain View Solar, LLC for the installation of 1.375 MW Solar PV in Williston, VT and interconnecting to 1101 Mountain View Road Williston, VT via circuit G3 out of Essex Substation. | 2026-05-15 | Notification | 2025-02-14
ES-20-G17 Rev.1 | 2025-01-29 | Kearsarge Energy LP - 10 Cranberry Road Solar and Battery | Generator notification from Eversource Energy on behalf of Kearsarge Energy LP for the installation of 0.882 MW Solar PV and 0.882 MW/4.457 MWh DC Coupled Battery in Kingston, MA and interconnecting to 10 Cranberry Road Kingston, MA via circuit 3-17-17 out of Kingston Substation. | 2025-07-31 | Notification | 2025-02-14
ES-21-G15 Rev.1 | 2025-01-29 | SunConnect - 0 Quarry Solar and Battery | Generator notification from Eversource Energy on behalf of SunConnect for the installation of 4.89 MW Solar PV and 4.0 MW/8.0 MWh DC Coupled Battery in Freetown, MA and interconnecting to 0 Quarry Drive Freetown, MA via circuit 2-605-605 out of Assonet Substation. | 2025-07-31 | Notification | 2025-02-14
ES-21-G17 Rev.3 | 2025-01-29 | Sup Set Main Street Plympton Solar and Battery | Generator notification from Eversource Energy on behalf of Sup Set Main Street Plympton Solar and Battery for the installation of 0.999 MW Solar PV and 0.999 MW/4.54351 MWh DC Coupled Battery in Plympton, MA and interconnecting to 399 Main Street Plympton, MA via circuit 3-50-50 out of Brook Street Substation. | 2025-07-31 | Notification | 2025-02-14
ES-23-G61 Rev.1 | 2025-01-29 | 510 PV Project Development, LLC - 73 Tremont Street Solar and Battery | Generator notification from Eversource Energy on behalf of 510 PV Project Development, LLC for the installation of 4.98 MW Solar PV and 4.98 MW/20.365 MWh DC Coupled Battery in Carver, MA and interconnecting to 73 Tremont Street Carver, MA via circuit 3-11-11 out of West Pond Substation. | 2025-07-31 | Notification | 2025-02-14
ES-23-G71 Rev.1 | 2025-01-29 | Soland, LLC - 107 Wareham Street Solar and Battery | Generator notification from Eversource Energy on behalf of Soland, LLC for the installation of 4.98 MW Solar PV and 4.98 MW/19.92 MWh DC Coupled Battery in Carver, MA and interconnecting to 107 Wareham Street Carver, MA via circuit 3-86-86 out of Tremont Substation. | 2025-07-31 | Notification | 2025-02-14
ES-25-G01 | 2025-01-21 | Renew Energy - 41 Mall Road Battery | Generator notification from Eversource Energy on behalf of Renew Energy for the installation of a 4.998 MW/14.994 MWh Battery in Burlington, MA and interconnecting to 41 Mall Road Burlington, MA via circuit 391-H13 out of Burlington Substation. | 2025-05-21 | Notification | 2025-02-14
ESR-24-G01 | 2024-12-24 | Queue Position 726 (QP 726) Revision | Generator application from Energy Storage Resources, LLC on behalf of Cranberry Point Energy Storage, LLC for the installation of a 150.0 MW/300.0 MWh Battery facility in Carver, MA and interconnecting to a new three-breaker ring bus 115 kV substation. | 2025-05-30 | Approved | 2025-01-22
ESR-24-T01 | 2024-12-24 | Queue Position 726 (QP 726) Revision | Transmission application from Energy Storage Resources, LLC on behalf of Cranberry Point Energy Storage, LLC for the installation of 115/34.5/13.8 kV transformer and a 115 kV generation lead line. | 2025-05-30 | Approved | 2025-01-22
ES-21-T10 Rev.1 | 2024-12-27 | Queue Position 726 (QP 726) Revision | Transmission application from Eversource Energy for the installation of a 3-breaker ring bus station that will split Line 127 between Carver and Semass Substations. | 2025-06-01 | Approved | 2025-01-22
TMLP-25-G01 | 2025-01-06 | Taunton Landfill Solar - 330 Britania Street Solar | Generator application from Taunton Municipal Lighting Plant on behalf of Taunton Landfill Solar for the installation of a 2.99 MW Solar facility in Taunton, MA and interconnecting to Station 18 via the 1814.32 Feeder. | 2025-10-01 | Approved | 2025-02-07
RMLD-25-G01 | 2025-01-07 | Reading Municipal Light Department Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Kearsarge - 500 Riverpark Drive Battery | Generator application from Reading Municipal Light Department on behalf of Kearsarge BESS for the installation of a 4.996 MW/11.182 MWh Battery facility in Reading, MA and interconnecting to Reading Substation via the 4W10 Circuit. | 2025-02-17 | Approved | 2025-02-07
RMLD-25-G02 | 2025-01-07 | Reading Municipal Light Department Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Citizen's Energy BESS - 166R Chestnut Street 3W17 Battery | Generator application from Reading Municipal Light Department on behalf of Citizen's Energy BESS for the installation of a 4.99 MW/14.4 MWh Battery facility in Reading, MA and interconnecting to North Reading Substation via the 3W17 Circuit. | 2025-05-15 | Approved | 2025-02-07
RMLD-25-G03 | 2025-01-07 | Reading Municipal Light Department Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Citizen's Energy BESS - 166R Chestnut Street 3W3 Battery | Generator application from Reading Municipal Light Department on behalf of Citizen's Energy BESS South for the installation of a 4.99 MW/14.4 MWh Battery facility in Reading, MA and interconnecting to North Reading Substation via the 3W3 Circuit. | 2025-05-15 | Approved | 2025-02-07
ES-24-T35 Rev.1 | 2025-01-08 | Somerville Third Transformer Addition Rev.1 | Transmission application from Eversource Energy for the installation of an additional 115/13.8 kV transformer at Somerville Substation. This revision reflects the change of normally open points of the 115 kV lines 329-510 and 329-511 from Brighton 115 kV side at Somerville Substation to be at Mystic 115 kV. | 6/31/2025 | Approved | 2025-01-22
GMP-24-11 | 2024-12-11 | MHG Solar LLC - 1157 Furnace Road Solar | Generator notification from Green Mountain Power on behalf of MHG Solar LLC for the installation of 3.0 MW Solar PV in Pittsford, VT and interconnecting to Furnace Road Pittsford, VT via circuit G11 out of Pittsford Substation. | 2026-12-31 | Notification | 2025-02-07
GMP-24-12 | 2024-12-11 | MHG Solar LLC - 801 VT Route 103S Solar | Generator notification from Green Mountain Power on behalf of MHG Solar LLC for the installation of 2.75 MW Solar PV in Chester, VT and interconnecting to 801 VT Route 103S Chester, VT via circuit G11 out of Chester Substation. | 2026-12-31 | Notification | 2025-02-07
GMP-24-13 | 2024-12-11 | Furnace Brook Solar LLC - 359 Shields Drive Solar | Generator notification from Green Mountain Power on behalf of Furnace Brook Solar LLC for the installation of 1.65 MW Solar PV in Bennington, VT and interconnecting to 359 Shields Drive Bennington, VT via circuit G61 out of Lyons Street Substation. | 2026-12-31 | Notification | 2025-02-07
GMP-25-01 | 2025-01-06 | Williston D Solar, LLC - 470 IBM Road Solar | Generator notification from Green Mountain Power on behalf of Williston D solar, LLC for the installation of 3.25 MW Solar PV in Williston, VT and interconnecting to 470 IBM Road Williston, VT via circuit G2 out of Williston Substation. | 2027-10-12 | Notification | 2025-02-07
LU-24-GNF1 | 2024-12-17 | ReVision Energy Inc. - 470 Meriden Road Solar | Generator notification from Liberty Utilities on behalf of ReVision Energy Inc. for the installation of 1.875 MW Solar PV in Lebanon, NH and interconnecting to 470 Meriden Road Lebanon, NH via circuit 1L2 out of Lebanon Substation. | 2025-12-31 | Notification | 2025-02-07
CMP-21-G28 Rev.1 | 2025-01-07 | MEVS, LLC - 22 W Beech Ridge Road Solar | Generator notification from Central Maine Power on behalf of MEVS, LLC for the installation of 1.95 MW Solar PV in Scarborough, ME and interconnecting to 22 W Beech Ridge Road Scarborough, ME via circuit 617D3 out of Dunstan Substation. | 2024-12-23 | Notification | 2025-02-07
ES-24-G111 | 2024-12-11 | NextGrid Guiana LLC - 136 S Main Street Solar and Battery | Generator notification from Eversource Energy on behalf of NextGrid Guiana LLC for the installation of 4.8 MW Solar PV and 4.8 MW/24.288 MWh DC Coupled Battery in Freetown, MA and interconnecting to 136 S Main Street Freetown, MA via circuit 2-605-605 out of Assonet Substation. | 2025-06-30 | Notification | 2025-02-07
NEP-24-GNF28 | 2025-01-06 | Parallel Products - 591 Walnut Street Solar and Battery | Generator notification from New England Power on behalf of Parallel Products for the installation of 4.999 MW Solar PV and 10.0 MW/48.74 MWh DC Coupled Battery in West Bridgewater, MA and interconnecting to 591 Walnut Street West Bridgewater, MA via circuit 98W19 out of Belmont Substation. | 2027-03-01 | Notification | 2025-02-07
NEP-24-GNF29 | 2025-01-06 | ZeroPoint Development, LLC - 50 Old Providence Road Solar and Battery | Generator notification from New England Power on behalf of ZeroPoint Development, LLC for the installation of 4.999 MW Solar PV and 4.999 MW/19.92 MWh DC Coupled Battery in Swansea, MA and interconnecting to 50 Old Providence Road Swansea, MA via circuit 11W81 out of Swansea Substation. | 2027-03-01 | Notification | 2025-02-07
UI-24-G03 | 2024-12-12 | HyAxiom, Inc - 540 Longbrook Avenue Natural Gas | Generator notification from Avangrid on behalf of HyAxiom, Inc for the installation of 4.999 MW Natural Gas Generator in Stratford, CT and interconnecting to 540 Longbrook Avenue Stratford, CT via circuit 2737 out of Barnum Substation. | 2025-07-01 | Notification | 2025-02-07
ES-24-G110 | 2024-12-12 | Verizon New England Inc. - 51 S. Bedford Street Natural Gas | Generator notification from Eversource Energy on behalf of Verizon New England Inc. for the installation of 4.999 MW Natural Gas Generator in Burlington, MA and interconnecting to 51 S. Bedford Street Burlington, MA via circuit 391-H13 out of Burlington Substation. | 2025-06-30 | Notification | 2025-02-07
ES-25-T07 | 2024-12-31 | Baker Street Substation Transformer 110A | Transmission notification from Eversource Energy to replace transformer 110A at Baker Street Substation. | 2025-03-31 | Notification | 2025-01-22
FLA-24-G01 | 2024-12-04 | Queue Position 1148 (QP 1148) Battery Project | Generator application from Flatiron Energy on behalf of Lite Brite Storage LLC for the installation of a 300.0 MW (150 MW Charging) /1200.0 MWh Battery facility in Boston, MA and interconnecting to Electric Avenue Substation via a new 115 kV bay. | 2028-05-26 | Approved | 2025-01-06
FLA-24-T01 | 2024-12-04 | Queue Position 1148 (QP 1148) Battery Project | Transmission application from Flatiron Energy on behalf of Lite Brite Storage LLC for the installation of a 0.08 mile 115 kV transmission line from the new generation facility to Electric Avenue Substation. | 2028-05-26 | Approved | 2025-01-06
ES-24-T45 | 2024-11-05 | Queue Position 1148 (QP 1148) Battery Project | Transmission application from Eversource Energy for the installation of termination equipment and a new gas insulated switchgear (GIS) bay with two breakers at Electric Avenue Substation to accommodate the interconnection of the generation facility. | 2028-05-26 | Approved | 2025-01-06
WRD-24-G01 | 2024-12-05 | Queue Position 1136 (QP 1136) Solar Project | Generator application from Walden Renewables Development LLC, on behalf of Nutes Solar LLC for the installation of a 20.28 MW Solar facility in Farmington, NH and interconnecting to 34.5 kV Line 3174. | 2026-05-15 | Approved | 2025-01-06
ES-24-G25 | 2024-11-26 | Eversource Energy Southeast Massachusetts & Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - ReWild Renewables, LLC - 1094 Main Street Solar and Battery Project | Generator application from Eversource Energy on behalf of ReWild Renewables, LLC for the installation a 4.999 MW Solar PV and 4.999 MW/20.0 MWh DC Coupled Battery facility in Acushnet, MA and interconnecting to the Wing Lane Substation via the 2-241-241 circuit. plication from Eversource Energy on behalf of ReWild Renewables, LLC for the installation a 4.999 MW Solar PV and 4.999 MW/20.0 MWh DC Coupled Battery facility in Acushnet, MA and interconnecting to the Wing Lane Substation via the 2-241-241 circuit. | 2025-04-30 | Approved | 2025-01-06
ES-24-G29 | 2024-11-26 | Eversource Energy Southeast Massachusetts & Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Mattapoisett Solar 1, LLC - Crystal Spring Road Solar and Battery Project | Generator application from Eversource Energy on behalf of Mattapoisett Solar 1, LLC for the installation a 4.98 MW Solar PV and 4.98 MW/19.92 MWh DC Coupled Battery facility in Crystal Spring, MA and interconnecting to the Crystal Spring Substation via the 2-301-301 circuit. | 2025-12-31 | Approved | 2025-01-06
ES-24-G31 | 2024-11-26 | Eversource Energy Southeast Massachusetts & Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Parallel Products, LLC - 320 County Road Solar and Battery | Generator application from Eversource Energy on behalf of Parallel Products for the installation a 2.0 MW Solar PV and 1.0 MW/2.0 MWh DC Coupled Battery facility in Wareham, MA and interconnecting to the Tremont Substation via the 3-85-85 circuit. | 2025-05-30 | Approved | 2025-01-06
ES-24-G32 | 2024-11-26 | Eversource Energy Southeast Massachusetts & Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - High Street Solar 1, LLC - High Street Solar and Battery Project | Generator application from Eversource Energy on behalf of High Street Solar 1, LLC for the installation a 4.98 MW Solar PV and 4.98 MW/20.365 MWh DC Coupled Battery facility in Rochester, MA and interconnecting to the Tremont Substation via the 3-85-85 circuit. | 2025-11-01 | Approved | 2025-01-06
ES-24-G35 | 2024-11-26 | Eversource Energy Southeast Massachusetts & Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - High Street Solar 4, LLC - 0 Ryder Road Solar and Battery Project | Generator application from Eversource Energy on behalf of High Street Solar 4, LLC for the installation a 4.98 MW Solar PV and 4.98 MW/20.365 MWh DC Coupled Battery facility in Rochester, MA and interconnecting to the Tremont Substation via the 3-85-85 circuit. | 2025-11-01 | Approved | 2025-01-06
ES-24-G38 | 2024-11-26 | Eversource Energy Southeast Massachusetts & Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Rewild Renewables, LLC - 134 Brook Street Solar and Battery Project | Generator application from Eversource Energy on behalf of Rewild Renewables, LLC for the installation a 4.999 MW Solar PV and 4.999 MW/15.0 MWh DC Coupled Battery facility in Plympton, MA and interconnecting to the Brook Street Substation via the 3-51-51 circuit. | 2025-06-16 | Approved | 2025-01-06
ES-24-G40 | 2024-11-26 | Eversource Energy Southeast Massachusetts & Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Duxbury Energy Storage - 711 West Street Battery Project | Generator application from Eversource Energy on behalf of Duxbury Energy Storage, LLC for the installation a 4.99 MW/19.96 MWh Battery facility in Duxbury, MA and interconnecting to the Duxbury Substation via the 3-25-25 circuit. | 2026-05-25 | Approved | 2025-01-06
ES-24-G42 | 2024-11-26 | Eversource Energy Southeast Massachusetts & Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Next Grid Sequoia 2, LLC - 93 Old Colony Lane Battery Project | Generator application from Eversource Energy on behalf of NextGrid Sequoia 2, LLC for the installation a 4.9992 MW/18.342 MWh Battery facility in Marshfield, MA and interconnecting to the Marshfield Substation via the 3-22-973 circuit. | 2025-05-30 | Approved | 2025-01-06
ES-24-G43 | 2024-11-26 | Eversource Energy Southeast Massachusetts & Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Dexter Lane Solar 1, LLC - 53 Dexter Lane Solar and Battery Project | Generator application from Eversource Energy on behalf of Dexter Lane Solar 1, LLC for the installation a 4.98 MW Solar PV and 4.98 MW/19.92 MWh DC Coupled Battery facility in Rochester, MA and interconnecting to the Rochester Substation via the 3-702-702 circuit. | 2025-08-01 | Approved | 2025-01-06
ES-24-G44 | 2024-11-26 | Eversource Energy Southeast Massachusetts & Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Rewild Renewables, LLC - 600 Snipatuit Road Solar and Battery Project | Generator application from Eversource Energy on behalf of Rewild Renewables, LLC for the installation a 4.999 MW Solar PV and 4.999 MW/30.0 MWh DC Coupled Battery facility in Rochester, MA and interconnecting to the Rochester Substation via the 3-703-703 circuit. | 2026-07-01 | Approved | 2025-01-06
ES-24-G45 | 2024-11-26 | Eversource Energy Southeast Massachusetts & Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Ameresco Inc - Meshacket Road Solar Project | Generator application from Eversource Energy on behalf of Ameresco Inc for the installation a 2.49 MW Solar PV facility in Edgartown, MA and interconnecting to the Falmouth Substation via the 4-75-223 circuit. | 2025-05-30 | Approved | 2025-01-06
GF-24-G01 | 2024-12-02 | GF Power LLC - Essex VT BESS 1 Battery Project | Generator application from VELCO on behalf of GF Power LLC for the installation of a 16.0 MW/60.2 MWh Battery facility in Essex, VT and interconnecting to VT Transco IBM Substation via feeder 15. | 2026-04-01 | Approved | 2025-01-06
ES-24-G109 | 2024-12-02 | Tunnel BESS - 2 Roosevelt Ave Extension Battery Project | Generator application from Eversource Energy on behalf of Tunnel BESS for the installation of a 16.02 MW/72 MWh Battery facility in Preston, CT and interconnecting to Tunnel Substation. | 2026-04-15 | Approved | 2025-01-06
CEL-24-G01 | 2024-11-15 | Convergent Energy and Power LP - 1975 Westover Road Battery | Generator application from Chicopee Electric Light on behalf of Convergent Energy and Power LP for the installation of a 4.99 MW/15 MWh Battery in Chicopee, MA and interconnecting to Westover Road Chicopee, MA via circuit 7P8 out of Memorial Substation. | 2026-09-30 | Approved | 2025-01-06
GMP-23-G23 Rev.1 | 2024-11-05 | Williston E Chip Alley Solar LLC - 326 IBM Road Solar | Generator notification from Green Mountain Power on behalf of Williston E Chip Alley Solar LLC for the installation of 2.5 MW Solar PV in Williston, VT and interconnecting to IBM Road Williston, VT via circuit G2 out of Williston Substation. | 2026-05-01 | Notification | 2025-01-06
GMP-24-G09 | 2024-12-02 | Williston G Solar - 483 Mountain View Road Solar | Generator notification from Green Mountain Power on behalf of Williston G Solar, LLC for the installation of 2.375 MW Solar PV in Williston, VT and interconnecting to Mountain View Road Williston, VT via circuit G3 out of Essex Substation. | 2027-04-01 | Notification | 2025-01-06
GMP-24-G10 | 2024-12-02 | Williston H Solar, LLC - 1022 Redmond Road Solar | Generator notification from Green Mountain Power on behalf of Williston H Solar, LLC for the installation of 3.25 MW Solar PV in Williston, VT and interconnecting to Redmond Road Williston, VT via circuit G2 out of Williston Substation. | 2026-09-01 | Notification | 2025-01-06
UES-23-G03 Rev.1 | 2024-11-15 | Merrimack County NH - 325 Daniel Webster highway Solar | Generator notification from Unitil on behalf of Merrimack County NH for the installation of 2.625 MW Solar PV in Boscawen, NH and interconnecting to Daniel Webster Highway Boscawen, NH via circuit 13W3 out of Oak Hill Substation. | 2025-12-31 | Notification | 2025-01-06
VEC-24-G09 | 2024-11-27 | MHG Solar LLC - 2305 VT Route 100 Solar | Generator notification from Vermont Electric Coop on behalf of MHG Solar LLC for the installation of 4.749 MW Solar PV in Lowell, VT and interconnecting to VT Route 100 Lowell, VT via a recloser out of Lowell Substation. | 2026-12-01 | Notification | 2025-01-06
ES-21-G121 Rev.1 | 2024-11-21 | BWC Trumble Brook, LLC - 123 Barnard Road Solar and Battery | Generator notification from Eversource Energy on behalf of BWC Trumble Brook, LLC for the installation of 1.999 MW Solar PV and 1.3 MW/2.6 MWh DC Coupled Battery in Granville, MA and interconnecting to Barnard Road Granville, MA via circuit 29A5 out of Southwick Substation. | 2025-05-31 | Notification | 2025-01-06
LELWD-24-G01 | 2024-11-07 | Citizens Enterprises Corporation - 97 Mill Road Battery | Generator notification from Littleton Electric Light and Water Department on behalf of Citizens Enterprises Corporation for the installation of 4.99 MW/15 MWh Battery in Littleton, MA and interconnecting to Mill Road Littleton, MA via circuit 2502 out of Beaver Brook Substation. | 2026-05-01 | Notification | 2025-01-06
RIE-24-G13 | 2024-12-03 | Green Development - 0 Cross-Park Avenue Biomass Gas | Generator notification from Rhode Island Energy on behalf of Green Developmen for the installation of a 2.2 MW Natural Gas Generator in North Kingston, RI and interconnecting to Cross-park Avenue North Kingston, RI via circuit 84T3 out of Davisville Substation. | 2026-03-01 | Notification | 2025-01-06
HGE-24-G04 | 2024-12-03 | ESG-H2 - Water Street Natural Gas | Generator notification from Holyoke Gas and Electric on behalf of ESG-H2 for the installation of a 4.2 MW Natural Gas Generator in Holyoke, MA and interconnecting to North Canal Substation via a new feeder. | 2025-07-01 | Notification | 2025-01-06
ES-24-G108 | 2024-12-02 | University of Connecticut - 39 King Hill Road Natural Gas | Generator notification from Eversource Energy on behalf of University of Connecticut for the installation of a 26.4 MW Natural Gas Generator in Storrs, CT and interconnecting to King Hill Road Storrs, CT via UConn 5G Substation. | 2025-05-30 | Notification | 2025-01-06
RIE-24-T08 | 2024-11-08 | S-171-2 and T172S-2 Johnston Tap 115 kV Line Rebuilds Project | Transmission notification from Rhode Island Energy for the rebuild of the S-171-2 and T-172S-2 Johnston Tap 115 kV Lines. The proposed in-service date is July 3, 2026. | 2026-07-03 | Notification | 2024-12-20
NEP-24-T10 | 2024-12-05 | L-164 115 kV Line Reconductoring from Tewksbury Substation to Tewksbury Junction Project | Transmission notification from New England Power for the reconductoring of the Power L-164 115 kV Line between Tewksbury Substation to Tewksbury Junction. | 2028-01-20 | Notification | 2024-12-20
WIN-24-G01 | 2024-11-06 | Queue Position 1193 (QP 1193) Battery Project | Generator application from Daymark Energy on behalf of Windham Energy Center LLC for the installation of a 325.0 MW/650.0 MWh Battery facility in Killingly, CT and interconnecting to Eversource’s 3271 345 kV transmission line between Lake Road and Card 345 kV Substations. | 2026-06-01 | Approved | 2024-12-05
WIN-24-T01 | 2024-11-06 | Queue Position 1193 (QP 1193) Battery Project | Transmission application from Daymark Energy on behalf of Windham Energy Center LLC for the installation of a 345 kV transformer and 345 kV transmission line to the interconnection point on the 3271 Line. | 2026-06-01 | Approved | 2024-12-05
ES-24-T43 | 2024-11-05 | Queue Position 1193 (QP 1193) Battery Project | Transmission application from Eversource Energy for the bifurcation of the 3271 Line and installation of a three breaker ring-bus to accommodate the interconnection of the generation facility transmission line. | 2026-06-01 | Approved | 2024-12-05
FLA-24-G02 | 2024-11-11 | Queue Position 1319 (QP 1319) Battery Project | Generator application from Flatiron Energy for on behalf of Treebeard BESS ProjectCo, LLC the installation of a 140.0 MW/560.0 MWh Battery facility in New Milford, CT and interconnecting to Eversource’s 1555 115 kV transmission line between Bull Bridge and Rocky River 115 kV Substations. | 2028-02-23 | Approved | 2024-12-05
FLA-24-T02 | 2024-11-11 | Queue Position 1319 (QP 1319) Battery Project | Transmission application from Flatiron Energy on behalf of Treebeard BESS ProjectCo, LLC for the installation of a 115 kV transformer and 115 kV transmission line to the interconnection point on the 1555 Line. | 2027-12-27 | Approved | 2024-12-05
ES-24-T42 | 2024-11-05 | Queue Position 1319 (QP 1319) Battery Project | Transmission application from Eversource Energy for the installation of equipment to tap the 1555 Line to accommodate the interconnection of the generation facility transmission line. | 2028-02-23 | Approved | 2024-12-05
FLA-24-G03 | 2024-11-11 | Queue Position 1320 (QP 1320) Battery Project | Generator application from Flatiron Energy for on behalf of FE Taft LLC for the installation of a 200.0 MW/800.0 MWh Battery facility in Uxbridge, MA and interconnecting to R-144N 115 kV transmission line between Woonsocket and Millbury 115 kV Substations. | 2027-11-16 | Approved | 2024-12-05
FLA-24-T03 | 2024-11-11 | Queue Position 1320 (QP 1320) Battery Project | Transmission application from Flatiron Energy on behalf of FE Taft LLC for the installation of two 115 kV transformers and 115 kV transmission line to the new 115 kV switching station. | 2027-11-16 | Approved | 2024-12-05
NEP-24-T04 | 2024-11-06 | Queue Position 1320 (QP 1320) Battery Project | Transmission application from New England Power for the installation of a new 115 kV three-circuit-breaker ring-bus substation to interconnect QP1320. The existing 115kV line R-144N will be looped in and out of the new ring-bus sub switching station. | 2027-11-16 | Approved | 2024-12-05
ES-24-T44 | 2024-11-05 | Queue Position 1320 (QP 1320) Battery Project | Transmission application from Eversource Energy for the conversion of a breaker configuration from single to double breaker. | 2027-11-16 | Approved | 2024-12-05
ES-24-T35 | 2024-10-09 | Somerville Third Transformer Addition Project | Transmission application from Eversource Energy for the installation of an additional 115/13.8 kV transformer at Somerville Substation. | 2025-05-31 | Approved | 2024-11-20
WRD-24-G01 | 2024-11-05 | Queue Position 1136 (QP 1136) Solar Project | Generator application from Walden Renewables Development LLC, on behalf of Nutes Solar LLC for the installation of a 20.28 MW Solar facility in Farmington, NH and interconnecting to 34.5 kV Line 3174. | 2026-05-15
HE-24-G01 | 2024-11-01 | Holyoke Gas and Electric Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Cabot Street BESS - `102 Cabot Street Battery | Generator application from Holyoke Gas and Electric, on behalf of Cabot Street BESS for the installation of a 4.99 MW/15.0 MWh Battery facility in Holyoke, MA and interconnecting to the Holyoke Substation via the 17L16 feeder. | 2025-08-01 | Approved | 2024-12-05
HE-24-G02 | 2024-11-01 | Holyoke Gas and Electric Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Whitney Ave BESS - 361 Whitney Ave Battery | Generator application from Holyoke Gas and Electric, on behalf of Whitney Ave BESS for the installation of a 4.99 MW/15.0 MWh Battery facility in Holyoke, MA and interconnecting to the Ingelside Substation via a new feeder. | 2026-01-01 | Approved | 2024-12-05
HE-24-G03 | 2024-11-01 | Holyoke Gas and Electric Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Kelly Way BESS - Kelly Way Battery | Generator application from Holyoke Gas and Electric, on behalf of Kelly Way BESS for the installation of a 3.0 MW/9.0 MWh Battery facility in Holyoke, MA and interconnecting to the Holyoke Substation via the 52W2 feeder. | 2025-05-01 | Approved | 2024-12-05
HE-24-G05 | 2024-11-01 | Holyoke Gas and Electric Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - CEP BESS 2 - Holyoke Street Battery | Generator application from Holyoke Gas and Electric, on behalf of CEP BESS 2 for the installation of a 4.99 MW/15.0 MWh Battery facility in Holyoke, MA and interconnecting to the Holyoke Substation via a new feeder. | 2025-05-01 | Approved | 2024-12-05
ES-24-G103 | 2024-11-04 | Eversource Affected System Operator (ASO) Connecticut Distributed Energy Resource (DER) Group Study Battery Projects - Queue Position 1539 (QP 1539) Battery Project | Generator application from Eversource Energy on behalf of Long Hill Energy Center LLC for the installation of a 10.0 MW/40.0 MWh Battery facility in Middletown, CT and interconnecting to Dooley Substation via express feeder 1. | 2027-04-05 | Approved | 2024-12-05
ES-24-G104 | 2024-11-04 | Eversource Affected System Operator (ASO) Connecticut Distributed Energy Resource (DER) Group Study Battery Projects - Queue Position 1539 (QP 1539) Battery Project | Generator application from Eversource Energy on behalf of Long Hill Energy Center LLC for the installation of a 10.0 MW/40.0 MWh Battery facility in Middletown, CT and interconnecting to Dooley Substation via express feeder 2. | 2027-04-05 | Approved | 2024-12-05
ES-24-G105 | 2024-11-04 | Eversource Affected System Operator (ASO) Connecticut Distributed Energy Resource (DER) Group Study Battery Projects - Queue Position 1540 (QP 1540) Battery Position | Generator application from Eversource Energy on behalf of Delorean Power LLC for the installation of a 19.99 MW/80.0 MWh Battery facility in Enfield, CT and interconnecting to Enfield Substation via an express feeder. | 4/31/2025 | Approved | 2024-12-05
ES-24-G106 | 2024-11-04 | Eversource Affected System Operator (ASO) Connecticut Distributed Energy Resource (DER) Group Study Battery Projects - Queue Position 1537 (QP 1537) Battery Project | Generator application from Eversource Energy on behalf of BlueWave Storage Origination, LLC for the installation of a 4.99 MW/19.96 MWh Battery facility in Montville, CT and interconnecting to Uncasville Substation via circuit 1Q03. | 2025-05-31 | Approved | 2024-12-05
ES-24-G107 | 2024-11-04 | Eversource Affected System Operator (ASO) Connecticut Distributed Energy Resource (DER) Group Study Battery Projects - Queue Position 1538 (QP 1538) Battery Project | Generator application from Eversource Energy on behalf of BlueWave Storage Origination, LLC for the installation of a 4.99 MW/20.0 MWh Battery facility in Salem, CT and interconnecting to Flanders Substation via circuit 11Y1. | 2025-05-31 | Approved | 2024-12-05
CMP-24-G23 | 2024-11-04 | Bowdoin College - 100 Harpswell Road Battery Project | Generator application from Central Maine Power Company on behalf of Bowdoin College for the installation of a 3.00 MW/11.75 MWh Battery facility in Brunswick, ME and interconnecting to Brunswick Hydro Substation via a feeder. | 2025-05-01 | Approved | 2024-12-05
CMP-24-G24 | 2024-11-04 | City of Portland - 1001 Westbrook Street Battery Project | Generator application from Central Maine Power Company on behalf of City of Portland for the installation of a 1.9 MW/7.8 MWh Battery facility in Portland, ME and interconnecting to Sewall Street Substation via a feeder. | 2025-05-01 | Approved | 2024-12-05
EPM-24-G01 | 2024-11-05 | Queue Position 1272 (QP 1272) Battery Project | Generator application from Essential Power Massachusetts LLC for the installation of a 45.0 MW/180.0 MWh Battery facility in West Springfield, MA and interconnecting to West Springfield Substation via an existing transformer. | 2025-05-01 | Approved | 2024-12-05
EPM-24-T01 | 2024-11-05 | Queue Position 1272 (QP 1272) Battery Project | Transmission application from Essential Power Massachusetts LLC the use of an existing 115/13.8 kV step-up transformer in Eversource’s West Springfield Substation. The transformer was previously used by a now retired generator. | 2025-12-01 | Approved | 2024-12-05
RIE-24-G01-001 | 2024-11-05 | Rhode Island Energy Affected System Operator (ASO) Western Rhode Island Distributed Energy Resource (DER) Project - EDP Energy - 561 Nooseneck Hill Road Solar | Generator application from Rhode Island Energy on behalf of EDP Energy for the installation of a 4.95 MW PV facility in Hopkinton, RI and interconnecting to Wood River Substation via the 85T3 circuit. | 2026-12-31 | Approved | 2024-12-05
RIE-24-G01-002 | 2024-11-05 | Rhode Island Energy Affected System Operator (ASO) Western Rhode Island Distributed Energy Resource (DER) Project - EDP - Shunk Hill Road Solar | Generator application from Rhode Island Energy on behalf of EDP Energy for the installation of a 20.0 MW PV facility in Hopkinton, RI and interconnecting to Wood River Substation via the 85T2 circuit. | 2026-12-31 | Approved | 2024-12-05
RIE-24-G01-003 | 2024-11-05 | Rhode Island Energy Affected System Operator (ASO) Western Rhode Island Distributed Energy Resource (DER) Project - BlueWave Solar - Kingstown Road Solar | Generator application from Rhode Island Energy on behalf of BlueWave Solar for the installation of a 9.0 MW PV facility in Richmond, RI and interconnecting to Wood River Substation via the 85T2 circuit. | 2026-12-31 | Approved Withdrawn | 12/5/2024 3/18/2025
RIE-24-G01-004 | 2024-11-05 | Rhode Island Energy Affected System Operator (ASO) Western Rhode Island Distributed Energy Resource (DER) Project - Kearsarge Solar - Oak Hill Road Solar | Generator application from Rhode Island Energy on behalf of Kearsarge Solar for the installation of a 3.06 MW PV facility in North Kingstown, RI and interconnecting to Tower Hill Substation via the 88F7 circuit. | 2026-12-31 | Approved | 2024-12-05
RIE-24-G01-005 | 2024-11-05 | Rhode Island Energy Affected System Operator (ASO) Western Rhode Island Distributed Energy Resource (DER) Project - Revity Energy LLC - Frontier Road Solar | Generator application from Rhode Island Energy on behalf of Revity Energy LLC for the installation of a 15.05 MW PV facility in Hopkinton, RI and interconnecting to Wood River Substation via the 85T3 circuit. | 2026-12-31 | Approved | 2024-12-05
RIE-24-G01-006 | 2024-11-05 | Rhode Island Energy Affected System Operator (ASO) Western Rhode Island Distributed Energy Resource (DER) Project - Direct Energy - Quarry Road Solar | Generator application from Rhode Island Energy on behalf of Direct Energy for the installation of a 2.375 MW PV facility in Bradford, RI and interconnecting to Chase Hill Substation via the 155F2 circuit. | 2026-12-31 | Approved | 2024-12-05
RIE-24-G01-007 | 2024-11-05 | Rhode Island Energy Affected System Operator (ASO) Western Rhode Island Distributed Energy Resource (DER) Project - Green Development - 689A Victory Highway Solar | Generator application from Rhode Island Energy on behalf of Green Development for the installation of a 3.3 MW PV facility in West Greenwich, RI and interconnecting to Kent Count Substation via the 3311 circuit. | 2026-12-31 | Approved | 2024-12-05
RIE-24-G01-008 | 2024-11-05 | Rhode Island Energy Affected System Operator (ASO) Western Rhode Island Distributed Energy Resource (DER) Project - Revity Energy LLC - Hopkins Hill Road Solar | Generator application from Rhode Island Energy on behalf of Revity Energy LLC for the installation of an 18.448 MW PV facility in West Greenwich, RI and interconnecting to Kent Count Substation via the 3309 circuit. | 2026-12-31 | Approved | 2024-12-05
RIE-24-G01-009 | 2024-11-05 | Rhode Island Energy Affected System Operator (ASO) Western Rhode Island Distributed Energy Resource (DER) Project - Dry Bridge Solar - Dry Bridge Road Solar | Generator application from Rhode Island Energy on behalf of Dry Bridge Solar for the installation of a 40.0 MW PV facility in North Kingstown, RI and interconnecting to Wickford Junction Substation via the 8089 circuit. | 2023-09-29 | Approved | 2024-12-05
RIE-24-T06 | 2024-11-05 | Rhode Island Energy Affected System Operator (ASO) Western Rhode Island Distributed Energy Resource (DER) Project - T10 Transformer Wood River Substation | Transmission application from Rhode Island Energy for the replacement of the T10 transformer at Wood River Substation. | 2026-12-31 | Approved | 2024-12-05
RIE-24-T07 | 2024-11-05 | Rhode Island Energy Affected System Operator (ASO) Western Rhode Island Distributed Energy Resource (DER) Project - Rebuild West Kingston Substation | Transmission application from Rhode Island Energy for the rebuild of the West Kingston Substation. | 2026-12-31 | Approved | 2024-12-05
CMP-22-G09 Rev.1 | 2024-11-04 | ME West Lebanon Road Solar, LLC - 429 West Lebanon Road Solar | Generator notification from Central Maine Power on behalf of ME West Lebanon Road Solar, LLC for the installation of 1.998 MW Solar PV in Lebanon, ME and interconnecting to Lebanon Road Lebanon, ME via circuit 695D2 out of Lebanon Substation. | 2024-12-19 | Notification | 2024-12-05
CMP-22-G12 Rev.1 | 2024-11-04 | Lebanon West Lebanon Solar 1, LLC - 252 Lebanon Rd Solar | Generator notification from Central Maine Power on behalf of Lebanon West Lebanon Solar 1, LLC for the installation of 1.999 MW Solar PV in Lebanon, ME and interconnecting to West Lebanon Road Lebanon, ME via circuit 695D1 out of Lebanon Substation. | 2024-11-15 | Notification | 2024-12-05
ES-19-G54 Rev.2 | 2024-11-16 | ECA SEMA CAN2, LLC - 28 Draper Lane Solar | Generator notification from Eversource Energy on behalf of ECA SEMA CAN2, LLC for the installation of 1.279 MW Solar PV in Canton, MA and interconnecting to Draper Lane Canton, MA via circuit 470-H6 out of Station 470. | 2025-04-01 | Notification | 2024-12-05
ES-20-G60 Rev.1 | 2024-10-16 | ECA Solar, LLC - 135 Will Drive Solar | Generator notification from Eversource Energy on behalf of ECA Solar, LLC for the installation of 2.0 MW Solar PV in Canton, MA and interconnecting to Draper Lane Canton, MA via circuit 470-H4 out of Station 470. | 2025-04-01 | Notification | 2024-12-05
ES-24-G83 | 11/5/22024 | World Energy Services LLC - 136 Nooks Hill Road Solar | Generator notification from Eversource Energy on behalf of World Energy Services LLC for the installation of 4.95 MW Solar PV in Cromwell, CT and interconnecting to Nooks Hill Road Cromwell, CT via circuit 3R06 out of Rocky Hill Substation. | 2025-12-31 | Notification | 2024-12-05
NEP-24-GNF25 | 2024-11-01 | US Solar Works - 85 Winter Street Solar | Generator notification from New England Power on behalf of US Solar Works for the installation of 1.5 MW Solar PV in Hanover, MA and interconnecting to Winter Street Hanover, MA via circuit 95W2 out of Phillips Lane Substation. | 2027-01-01 | Notification | 2024-12-05
NEP-24-GNF26 | 2024-11-01 | ECA Solar, LLC - 105 Industrial Boulevard Solar | Generator notification from New England Power on behalf of ECA Solar, LLC 1.68 MW Solar PV in Brockton, MA and interconnecting to Industrial Boulevard Brockton, MA via circuit 91W48, out of Dupont Substation. | 2027-01-01 | Notification | 2024-12-05
NEP-24-GNF27 | 2024-11-01 | Sunnova Energy - 50 Constitution Boulevard Solar | Generator notification from New England Power on behalf of Sunnova Energy for the installation of 3.935 MW Solar PV in Franklin, MA and interconnecting to Constitution Boulevard Franklin, MA via circuit 348W1, out of Union Street Substation. | 2025-02-01 | Notification | 2024-12-05
ES-20-G106 Rev.1 | 2024-10-16 | NextGrid Hakea, LLC - 45 Dan Road Solar and Battery | Generator notification from Eversource Energy on behalf of NextGrid Hakea, LLC for the installation of 0.499 MW Solar PV and 0.499 MW/4.0 MWh DC Coupled Battery in Canton, MA and interconnecting to Dan Road Canton, MA via circuit 470-H10 out of Station 470. | 2025-04-01 | Notification | 2024-12-05
ES-24-G100 | 2024-11-01 | BlueWave Origination, LLC - 190 Ridge Road Solar and Battery | Generator notification from Eversource Energy on behalf of BlueWave Origination, LLC for the installation of 2.0 MW Solar PV and 1.0 MW/2.0 MWh DC Coupled Battery in Worthington, MA and interconnecting to Ridge Road Worthington, MA via circuit 18K2 out of Plainfield Substation. | 2025-04-30 | Notification | 2024-12-05
ES-24-G101 | 2024-11-01 | BlueWave Origination, LLC - 20 East Street Solar and Battery | Generator notification from Eversource Energy on behalf of BlueWave Origination, LLC for the installation of 4.98 MW Solar PV and 1.75 MW/3.5 MWh DC Coupled Battery in Plainfield, MA and interconnecting to East Street Plainfield, MA via circuit 18K3 out of Plainfield Substation. | 2024-04-30 | Notification | 2024-12-05
ES-24-G97 | 2024-11-01 | ReWild Renewables, LLC - 3400 Jacobs Ladder Road Solar and Battery | Generator notification from Eversource Energy on behalf of ReWild Renewables, LLC for the installation of 4.99 MW Solar PV and 4.99 MW/30.0 MWh DC Coupled Battery in Becket, MA and interconnecting to Jacobs Ladder Road Becket, MA via circuit 16B1 out of Pleasant Substation. | 2025-12-30 | Notification | 2024-12-05
ES-24-G98 | 2024-11-01 | North Union Solar 1, LLC - 66 North Union Street Solar and Battery | Generator notification from Eversource Energy on behalf of North Union Solar 1, LLC for the installation of 4.98 MW Solar PV and 4.98 MW/19.92 MWh DC Coupled Battery in Plainfield, MA and interconnecting to North Union Street Plainfield, MA via circuit 18K3 out of Plainfield Substation. | 2025-02-02 | Notification | 2024-12-05
ES-24-G99 | 2024-11-01 | BlueWave Origination, LLC - 105 Old Post Road Solar and Battery | Generator notification from Eversource Energy on behalf of BlueWave Origination, LLC for the installation of 2.988 MW Solar PV and 2.539 MW/10.155 MWh DC Coupled Battery in Worthington, MA and interconnecting to Old Post Road Worthington, MA via circuit 18K3 out of Plainfield Substation. | 2025-04-30 | Notification | 2024-12-05
NEP-20-GNF31 Rev.1 | 2024-11-01 | Pacifico Energy Na, LLC - 103 Richardson Avenue Solar and Battery | Generator notification from New England Power on behalf of Pacifico Energy Na, LLC for the installation of 4.482 MW Solar PV and 3.0 MW/6.7092 MWh DC Coupled Battery in Attleboro, MA and interconnecting to Richardson Avenue Attleboro, MA via circuit 8L3, out of Chartley Pond Substation. | 2027-01-01 | Notification | 2024-12-05
ES-23-G70 Rev.1 | 2024-10-16 | Silo Electric LLC - 15 University Road Battery | Generator notification from Eversource Energy on behalf of Silo Electric LLC for the installation of 2.5 MW/11.008 MWh Battery in Canton, MA and interconnecting to University Road Canton, MA via circuit 470-H1 out of Station 470. | 2025-04-01 | Notification | 2024-12-05
ES-24-G93 | 2024-10-09 | Convergent Energy Soultions LLC - 415 South Street F1356 Battery | Generator notification from Eversource Energy on behalf of Convergent Solutions LLC for the installation of 1.5 MW/4.5 MWh Battery in Waltham, MA and interconnecting to South Street Waltham, MA via circuit 386-1356 out of Station 386. | 2026-05-01 | Notification | 2024-12-05
ES-24-G95 | 2024-10-09 | Convergent Energy Soultions LLC - 415 South Street F1366 Battery | Generator notification from Eversource Energy on behalf of Convergent Solutions LLC for the installation of 1.5 MW/4.5 MWh Battery in Waltham, MA and interconnecting to South Street Waltham, MA via circuit 386-1366 out of Station 386. | 2026-05-15 | Notification | 2024-12-05
NEP-24-GNF19 Rev.1 | 2024-11-01 | Bluewave Solar - 921 Wood Street Battery | Generator notification from New England Power on behalf of Bluewave Solar for the installation of 4.99 MW/19.96 MWh Battery in Swansea, MA and interconnecting to Wood Street Swansea, MA via circuit 11W84 out of Swansea Substation. | 2027-01-01 | Notification | 2024-12-05
ES-24-G102 | 2024-11-04 | Verizon New England Inc. - 210 Bent Street Natural Gas | Generator notification from Eversource Energy on behalf of Verizon New England Inc. for the installation of a 1.55 MW Natural Gas Generator in East Cambridge, MA and interconnecting to Bent Street East Cambridge, MA via circuit 875-1N23B out of Station 875. | 2025-05-01 | Notification | 2024-12-05
UI-24-G02 | 2024-11-04 | BE Development, Inc. - 195 McDermott Road Natural Gas | Generator notification from Avangrid on behalf of BE Development, Inc. for the installation of a 2.3 MW Natural Gas Generator in North Haven, CT and interconnecting to McDermott Road North Haven, CT via circuit 1701 out of East Shore Substation. | 2025-10-07 | Notification | 2024-12-05
NEP-22-T22 Rev.1 | 2024-10-30 | Moore/Fifteen Mile Falls Substation Rebuild | Transmission notification from New England Power for the rebuild of the New England Power portion of the Moore #20 substation at a new substation named Fifteen Mile Falls #3027 in Littleton, NH. | 2027-09-15 | Notification | 2024-11-20
ES-24-G89 | 2024-09-27 | Queue Position 1166 (QP 1166) and Queue Position 1487 (QP 1487) Battery Projects | Generator application from Eversource Energy on behalf of Oxford Energy Center LLC for the installation of a 14.3 MW/57.2 MWh Battery facility in Oxford, CT and interconnecting to Oxford Substation via an express feeder. | 2025-12-31 | Approved | 2024-11-01
ES-24-G90 | 2024-09-27 | Queue Position 1166 (QP 1166) and Queue Position 1487 (QP 1487) Battery Projects | Generator application from Eversource Energy on behalf of Oxford Energy Center LLC for the installation of a 3.0 MW/12.0 MWh Battery facility in Oxford, CT and interconnecting to Oxford Substation via the 26N1 circuit. | 2025-12-31 | Approved | 2024-11-01
ES-24-G91 | 2024-09-27 | Queue Position 1166 (QP 1166) and Queue Position 1487 (QP 1487) Battery Projects | Generator application from Eversource Energy on behalf of Michaud Law Group for the installation of a 4.984 MW Solar facility in Oxford, CT and interconnecting to Oxford Substation via the 26N7 circuit. | 2024-12-31 | Approved | 2024-11-01
WBMLP-24-G02 | 2024-09-30 | Queue Position 1587 (QP 1587) Battery Project | Generator application from West Boylston Municipal Light Plant on behalf of West Boylston Energy Storage 1 LLC for the installation of a 3.0 MW/11.008 MWh Battery facility in West Boylston, MA and interconnecting to West Boylston Benton Lovell Substation via the F23 circuit. | 2024-06-01 | Approved | 2024-11-01
NEP-24-G08 | 2024-10-03 | New England Power Northeast Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Onsite Renewables - 128 Newburyport Battery | Generator application from New England Power on behalf of Onsite Renewables for the installation of a 4.9992 MW/18.432 MWh Battery facility in Newburyport, MA and interconnecting to King Street Substation via the 2405 circuit. | 2025-12-01 | Approved Withdrawn | 11/1/2024 12/17/2024
NEP-24-G09 | 2024-10-03 | New England Power Northeast Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Next Grid - 23 Low Street Battery | Generator application from New England Power on behalf of Next Grid for the installation of a 4.998 MW/ 8.432 MWh Battery facility in Newburyport, MA and interconnecting to King Street Substation via the 2405 circuit. | 2025-12-01 | Approved | 2024-11-01
NEP-24-G10 | 2024-10-03 | New England Power Northeast Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - PureSky - 70 Scotland Road Solar and Battery | Generator application from New England Power on behalf of PureSky Development for the installation of a 4.9992 MW Solar PV and 3.5 MW/10.395 MWh DC Coupled Battery facility in Newbury, MA and interconnecting to Newbury Substation via the 60L4 circuit. | 2025-12-01 | Approved | 2024-11-01
NEP-24-G11 | 2024-10-03 | New England Power Northeast Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - New Leaf Energy - 1312 South Street Battery | Generator application from New England Power on behalf of New Leaf Energy for the installation of a 5.0 MW/20 MWh Battery facility in Tewksbury, MA and interconnecting to East Tewksbury Substation via the 59L3 circuit. | 2025-12-01 | Approved | 2024-11-01
CMP-21-G32 Rev.1 | 2024-09-30 | Queue Position 923 (QP 923) Solar Project Revision | Generation application from Central Maine Power Company on behalf of Walden Solar Maine for the installation 20.0 MW PV facility in Leeds, ME and interconnecting to the Leeds Substation via the 471D2 circuit. | 2024-11-07 | Approved | 2024-11-01
ES-24-G65 | 2024-09-03 | Eversource Energy Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - CVE North America, Inc. - Colebrook River Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of CVE North America, Inc. for the installation a 4.999 MW Solar PV and 2.752 MW/11.008 MWh DC Coupled Battery facility in Tolland, MA and interconnecting to the Blandford Substation via the 19J4 circuit. | 2025-02-28 | Notification | 2024-11-01
ES-24-G66 | 2024-09-03 | Eversource Energy Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Kearsarge Energy - 17 Lyman Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Kearsarge Energy for the installation a 4.250 MW Solar PV and 1.5 MW/6.0 MWh AC Coupled Battery facility in Huntington, MA and interconnecting to the Blandford Substation via the 19J4 circuit. | 2025-02-28 | Notification | 2024-11-01
ES-24-G67 | 2024-09-03 | Eversource Energy Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Kearsarge Energy - 17A Lyman Road Solar | Generator application from Eversource Energy (ES) on behalf of Kearsarge Energy for the installation a 4.999 MW PV facility in Huntington, MA and interconnecting to the Blandford Substation via the 19J5 circuit. | 2025-02-28 | Notification | 2024-11-01
ES-24-G68 | 2024-09-03 | Eversource Energy Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Amp Solar Development, Inc - Josh Cross Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Amp Solar Development for the installation a 4.998 MW Solar PV and 4.831 MW/21.283 MWh DC Coupled Battery facility in Blandford, MA and interconnecting to the Blandford Substation via the 19J5 circuit. | 2024-12-03 | Notification | 2024-11-01
ES-24-G69 | 2024-09-03 | Eversource Energy Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - BlueWave Origination, LLC - 30 Huntington Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of BlueWave Origination, LLC for the installation a 2.0 MW Solar PV and 2.0 MW/8.0 MWh DC Coupled Battery facility in Blandford, MA and interconnecting to the Blandford Substation via the 19J2 circuit. | 2025-02-28 | Notification | 2024-11-01
ES-24-G70 | 2024-09-03 | Eversource Energy Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - BlueWave Origination, LLC - Jacobs Latter Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of BlueWave Origination, LLC for the installation a 2.7 MW Solar PV and 2.7 MW/10.8 MWh DC Coupled Battery facility in Becket, MA and interconnecting to the Blandford Substation via the 19J3 circuit. | 2025-02-28 | Notification | 2024-11-01
ES-24-G71 | 2024-09-03 | Eversource Energy Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Amp Solar Development, Inc - Off Huntington Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Amp Solar Development, Inc for the installation a 4.988 MW Solar PV and 3.826 MW/21.283 MWh DC Coupled Battery facility in Blandford, MA and interconnecting to the Blandford Substation via the 19J2 circuit. | 2024-12-01 | Notification | 2024-11-01
ES-24-G72 | 2024-09-03 | Eversource Energy Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Ameresco - 190 Fiberloaid Street Solar | Generator application from Eversource Energy (ES) on behalf of Ameresco for the installation a 2.04 MW PV facility in Indian Orchard, MA and interconnecting to the Orchard Substation via the 27A10 circuit. | 2025-02-28 | Notification | 2024-11-01
ES-24-G73 | 2024-09-03 | Eversource Energy Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Ameresco - 115 West Street Solar | Generator application from Eversource Energy (ES) on behalf of Ameresco for the installation a 1.992 MW PV facility in Ludlow, MA and interconnecting to the Orchard Substation via the 27A5 circuit. | 2025-02-28 | Notification | 2024-11-01
ES-24-G74 | 2024-09-03 | Eversource Energy Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Ameresco Inc. - Nelson Drive Solar | Generator application from Eversource Energy (ES) on behalf of Ameresco Inc. for the installation a 2.0 MW PV facility in Bernardston, MA and interconnecting to the French King Substation via the 21B8 circuit. | 2025-02-28 | Notification | 2024-11-01
ES-24-G75 | 2024-09-03 | Eversource Energy Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - BlueWave Storage Origination LLC - 0 Williams Street Battery | Generator application from Eversource Energy (ES) on behalf of BlueWave Storage Origination LLC for the installation a 4.99 MW/19.96 MWh AC Coupled Battery facility in Pittsfield, MA and interconnecting to the Doreen Substation via the 19A1 circuit. | 2025-02-28 | Notification | 2024-11-01
ES-24-G76 | 2024-09-03 | Eversource Energy Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - BlueWave Storage Origination LLC - 0 Ingalls Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of BlueWave Storage Origination LLC for the installation a 3.8 MW Solar PV and 2.0 MW/8.0 MWh DC Coupled Battery facility in Cheshire, MA and interconnecting to the Doreen Substation via the 19A5 circuit. | 2025-02-28 | Notification | 2024-11-01
ES-24-G77 | 2024-09-03 | Eversource Energy Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Catalyze Holdings LLC - 405 South Main Street Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Catalyze Holdings LLC for the installation a 4.0 MW Solar PV and 2.5 MW/5.0 MWh DC Coupled Battery facility in Lanesborough, MA and interconnecting to the Partridge Substation via the 15E1 circuit. | 2025-02-28 | Notification | 2024-11-01
ES-24-G78 | 2024-09-03 | Eversource Energy Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Hadley Agrivoltaics, LLC - 38 North Maple Street Solar | Generator application from Eversource Energy (ES) on behalf of Hadley Agrivoltaics, LLC for the installation a 2.0 MW PV facility in Hadley, MA and interconnecting to the Amherst Substation via the 17K5 circuit. | 2025-02-28 | Notification | 2024-11-01
ES-24-G79 | 2024-09-03 | Eversource Energy Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Cabot BESS, LLC - 26 Power Streey Battery | Generator application from Eversource Energy (ES) on behalf of Cabot BESS, LLC for the installation a 4.99 MW/19.96 MWh AC Coupled Battery facility in Turner Falls, MA and interconnecting to the Montague Substation via the 21C5 circuit. | 2027-05-31 | Notification | 2024-11-01
ES-24-G80 | 2024-09-03 | Eversource Energy Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - LSE Equuleus, LLC - 96 College Highway Solar and Battery | Generator application from Eversource Energy (ES) on behalf of LSE Equuleus, LLC for the installation a 3.984 MW Solar PV and 3.984 MW/8.4 MWh DC Coupled Battery facility in Southwick, MA and interconnecting to the Southwick Substation via the 29A3 circuit. | 2025-02-28 | Notification | 2024-11-01
ES-24-G81 | 2024-09-03 | Eversource Energy Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - BlueWave Origination, LLC - North Lane Solar and Battery | Generator application from Eversource Energy (ES) on behalf of BlueWave Origination, LLC for the installation a 3.0 MW Solar PV and 3.0 MW/12.0 MWh DC Coupled Battery facility in Granville, MA and interconnecting to the Southwick Substation via the 29A5 circuit. | 2025-02-28 | Approved | 2024-11-01
ES-24-G82 | 2024-09-03 | Eversource Energy Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - BE Development, Inc. - 425 Meadow Street Natural Gas | Generator application from Eversource Energy (ES) on behalf of BE Development, Inc. for the installation a 4.1 MW Natural Gas facility in Chicopee, MA and interconnecting to the Piper Substation via the 21N7 circuit. | 2025-02-28 | Approved | 2024-11-01
NEP-24-G12 | 2024-10-09 | New England Power Florence Junction and Five Corners Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Agilitas Energy - 0 River Road Solar and Battery | Generator application from New England Power on behalf of Agilitas Energy for the installation of a 3.9 MW Solar PV and 4.0 MW/8.928 MWh DC Coupled Battery in Willamsburg, MA and interconnecting to Florence Junction Substation via the 909W3 circuit. | 2026-12-01 | Approved | 2024-11-01
NEP-24-G13 | 2024-10-09 | New England Power Florence Junction and Five Corners Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Ameresco Solar - 46 Crescent Street Solar and Battery | Generator application from New England Power on behalf of Ameresco Solar for the installation of a 3.0 MW Solar PV and 3.0 MW/9.0 MWh DC Coupled Battery in Granby, MA and interconnecting to Five Corners Substation via the 527L3 circuit. | 2026-12-01 | Approved | 2024-11-01
NEP-24-G14 | 2024-10-09 | New England Power Florence Junction and Five Corners Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Prometheus Power - 92 Chicopee Street Solar and Battery | Generator application from New England Power on behalf of Prometheus Power for the installation of a 4.98 MW Solar PV and 5.0 MW/10.0 MWh DC Coupled Battery in Granby, MA and interconnecting to Five Corners Substation via the 527L3 circuit. | 2026-12-01 | Approved | 2024-11-01
NEP-24-T09 | 2024-10-09 | New England Power Florence Junction and Five Corners Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Five Corners Substation Transformer Replacements | Transmission application from New England Power for the replacement of the 115/13.2 kV transformers T1 and T2 at Five Corners substation with 33/44/55 MVA units. | 2026-12-01 | Approved | 2024-11-01
PMLD-24-G02 | 2024-10-09 | Paxton BESS 1 LLC - 299 Marshall Street Battery Project | Generator application from Paxton Municipal Light Department on behalf of Paxton BESS 1 LLC for the installation of a 3.0 MW/8.92 MWh Battery in Paxton, MA and interconnecting to 299 Marshall Street Paxton, MA via circuit 2 out of Wentworth Substation. | 2024-10-20 | Approved | 2024-10-23
ES-24-G22 | 2024-08-30 | Hunters Mountain 2 - Hunters Mountain Road Solar | Generator notification from Eversource Energy on behalf of Hunters Mountain 2 for the installation of 1.999 MW Solar PV in Naugatuck, CT and interconnecting to Hunters Mountain Road Naugatuck, CT via circuit 21L3 out of South Naugatuck Substation. | 2025-02-28 | Notification | 2024-11-01
UES-24-G04 | 2024-08-13 | Family Farm Solar LLC - 115 River Road Solar | Generator notification from Unitil on behalf of Family Farm Solar LLC for the installation of 4.99 MW Solar PV in Concord, NH and interconnecting to 115 River Road Concord, NH on Circuit 4X1 out of Oak Hill Substation. | 2026-10-31 | Notification | 2024-11-01
UES-24-G06 | 2024-08-06 | Continental Paving, Inc - 822 Ricker Road Solar | Generator notification from Unitil on behalf of Contienental Paving, Inc for the installation of 4.999 MW Solar PV in Loudon, NH and interconnecting to 822 Ricker Road Loudon, NH on Circuit 8X3 out of Broken Ground Substation. | 2026-06-30 | Notification | 2024-11-01
UES-24-G07 | 2024-08-23 | Kearsarge Solar, LLC - 45 Allen Road Solar | Generator notification from Unitil on behalf of Kearsarge Solar, LLC for the installation of 2.816 MW Solar PV in Bow, NH and interconnecting to 45 Allen Road Bow, NH on Circuit 7W3 out of Garvins Substation. | 2025-09-01 | Notification | 2024-11-01
UES-24-G08 | 2024-08-13 | Kearsarge Solar, LLC - 0 Falcon Way Solar | Generator notification from Unitil on behalf of Kearsarge Solar, LLC for the installation of 1.76 MW Solar PV in Bow, NH and interconnecting to 0 Falcon Way Bow, NH on Circuit 22W3 out of Garvins Substation. | 2025-09-01 | Notification | 2024-11-01
ES-24-G87 | 2024-09-05 | CEFIA Solar Services, Inc - 2800 Berlin Turnpike Solar | Generator notification from Eversource Energy on behalf of CEFIA Solar Services, Inc for the installation of 1.7 MW Solar PV in Newington, CT and interconnecting to 2800 Berlin Turnpike Newington, CT via Circuit 7L81 out of East New Britain Substation. | 2025-12-31 | Notification | 2024-11-01
ES-24-G84 | 2024-09-05 | Verogy - 0 Exley Road Solar | Generator notification from Eversource Energy on behalf of Verogy for the installation of 4.0 MW Solar PV in Plainfield, CT and interconnecting to 0 Exley Road Plainfield, CT via Circuit 13B9 out of Frybrook Substation. | 2026-12-31 | Notification | 2024-11-01
GMP-24-G08 | 2024-09-24 | Essex A north Lot Solar LLC - 1040 Robinson Parkway Solar | Generator notification from Green Mountain Power on behalf of Essex A North Lot Solar LLC for the installation of 3.5 MW Solar PV in Essex, VT and interconnecting to 1040 Robinson Parkway Essex, VT via Circuit G4 out of Essex Substation. | 2026-04-01 | Notification | 2024-11-01
NEP-24-GNF20 | 2024-08-30 | ECA Solar, LLC - 0 Pondview Drive Solar and Battery | Generator notification from New England Power on behalf of ECA Solar, LLC for the installation of 4.999 MW Solar PV and 4.999 MW/20.0 MWh DC Coupled Battery in Clinton, MA and interconnecting 0 Pondview Drive Clinton, MA on Circuit 216W2 out of Fitch Road Substation. | 2026-12-01 | Notification | 2024-11-01
ES-24-G94 | 2024-10-03 | GOVT USAF AFCS ESD - Access Road Solar and Battery | Generator notification from Eversource Energy on behalf of GOVT USAF AFCS ESD for the installation of 0.15 MW Solar PV and 1.686 MW/3.372 MWh AC Coupled Battery in Lexington, MA and interconnecting Access Road Lexington, MA on Circuit FDR3 out of Station 319. | 2025-07-01 | Notification | 2024-11-01
RIE-24-GNF12 | 2024-08-30 | Oak Square Partners - 0 Clinton Street Battery | Generator notification from Rhode Island Energy on behalf of Oak Square Partners for the installation of 4.995 MW/10.0 MWh Battery in Woonsocket, RI and interconnecting to 0 Clinton Street Woonsocket, RI via Circuit 108W51 out of Riverside Substation. | 2025-12-31 | Notification | 2024-11-01
VPPSA-24-G02 | 2024-09-01 | Lyndon VT BESS 1 LLC - 815 Industrial Parkway Battery | Generator notification from Lyndon Electric Department on behalf of Lyndon VT BESS 1 LLC for the installation of 4.999 MW/24.0 MWh Battery in St. Johnsbury, VT and interconnecting to 815 Industrial Parkway St. Johnsbury, VT via a circuit out of Industrial Parkway Substation. | 2026-09-01 | Notification | 2024-11-01
ES-24-G86 | 2024-10-01 | Endurant Consulting Solutions, LLC - 170 Long Lane Battery | Generator notification from Eversource Energy on behalf of Endurant Consulting Solutions, LLC for the installation of 4.9 MW/9.8 MWh Battery in Middletown, CT and interconnecting to 170 Long Lane Middletown, CT via circuit 7A74 out of Westside Substation. | 2025-12-30 | Notification | 2024-11-01
NEP-24-GNF15 | 2024-10-07 | Onsite Renewables, LLC - 159 Pelham Street Battery | Generator notification from New England Power on behalf of Onsite Renewables, LLC for the installation of 4.9992 MW/18.432 MWh Battery in Methuen, MA and interconnecting to 159 Pelham Street Methuen, MA via circuit 63L4 out of West Methuen Substation. | 2026-12-01 | Notification | 2024-11-01
NEP-24-GNF21 | 2024-10-07 | Onsite Renewables, LLC - 447 West Lowell Avenue Battery | Generator notification from New England Power on behalf of Onsite Renewables, LLC for the installation of 4.999 MW/18.432 MWh Battery in Haverhill, MA and interconnecting to 447 West Lowell Avenue Haverhill, MA via circuit 74L5 out of East Methuen Substation. | 2026-12-01 | Notification Withdrawn | 11/1/2024 12/17/2024
NEP-24-GNF22 | 2024-10-07 | Onsite Renewables, LLC - 207 East Street Battery | Generator notification from New England Power on behalf of Onsite Renewables, LLC for the installation of 4.9992 MW/18.432 MWh Battery in Methuen, MA and interconnecting to 207 East Street Methuen, MA via circuit 74L3 out of East Methuen Substation. | 2026-12-01 | Notification Withdrawn | 11/1/2024 12/17/2024
NEP-24-GNF23 | 2024-10-07 | UGE USA Inc - 267 Providence Street Battery | Generator notification from New England Power on behalf of UGE USA Inc for the installation of 4.99 MW/19.96 MWh Battery in Worcester, MA and interconnecting to 267 Providence Street Worcester, MA via circuit 8W3 out of Vernon Hill Substation. | 2026-12-01 | Notification | 2024-11-01
NEP-24-GNF24 | 2024-10-07 | Endurant Energy - 200 Boston Scientific Way Battery | Generator notification from New England Power on behalf of Endurant Energy for the installation of 4.99 MW/19.96 MWh Battery in Marlborough, MA and interconnecting to 200 Boston Scientific Way Marlborough, MA via circuit 311W7 out of Marlboro Substation. | 2026-12-01 | Notification | 2024-11-01
ES-24-G96 | 2024-09-30 | Qcells - State Pier Road Battery | Generator notification from Eversource Energy on behalf of QCells for the instalaltion of 4.896 MW/19.584 MWh Battery in New London, CT and interconnecting to State Pier Road New London, CT via circuit 9L09 out of Williams St Substation. (This project has been re-submitted as PPA ID ES-24-G96 to replace the previously submitted Level I PPA ES-24-G61. The PPA ID ES-24-G61 was already assigned to a different project.) | 2025-06-30 | Notification | 2024-11-01
HP-24-G01 | 2024-09-26 | Hartree Partners, LP - 1241 Whitefield Road Wood Waste Solid | Generator notification from Hartree Partners, LP for the installation of a 15.0 MW Wood Waste Generator in Bethlehem, NH and interconnecting to 1241 Whitefield Road, Bethlehem, NH via the 348 line out of Whitefield Substation. | 2025-01-01 | Notification | 2024-11-01
ES-24-G08 | 2024-09-30 | RTX Corporation - Pratt and Whitney Aircraft - 400 Aircraft Rd Natural Gas | Generator notification from Eversource Energy on behalf of RTX Corporation Pratt and Whitney Aircraft for the move of 2.038 MW of existing 7.5 MW Natural Gas generator moving metering point to front of meter in Middletown, CT and interconnecting to 400 Aircraft Road, Middletown, CT via Middletown Substation behind the Pratt and Whitney owned distribution equipment. | 2024-10-01 | Notification | 2024-11-01
ES-24-T37 | 2024-09-27 | North Woburn Substation Transformer Replacement | Transmission notification from Eversource Energy for the replacement of transformer 110B at North Woburn Substation in North Woburn, MA. | 2024-12-31 | Notification | 2024-10-23
NEP-24-G07 | 2024-08-01 | Queue Position 1252 (QP 1252) 310 MW Battery Project | Generator application from New England Power on behalf of Hecate Energy LLC for the installation of a 310 MW Battery facility interconnecting to New England Power’s Ward Hill Substation in Haverhill, MA. | 2026-06-01 | Approved | 2024-10-01
NEP-24-T02 | 2024-08-01 | Queue Position 1252 (QP 1252) 310 MW Battery Project | Transmission application from New England Power for the installation of a new circuit breaker at Ward Hill Substation to interconnect the proposed battery facility. | 2028-12-01 | Approved | 2024-10-01
NEP-24-T03 | 2024-08-01 | Queue Position 1252 (QP 1252) 310 MW Battery Project | Transmission application from New England Power the reconductoring of the New England Power owned portion of the 338 Line. | 2029-07-01 | Approved | 2024-10-01
NEP-24-T06 | 2024-08-01 | Queue Position 1252 (QP 1252) 310 MW Battery Project | Transmission application from New England Power on behalf of Hecate Energy LLC for the installation of a generator lead line from the proposed battery facility location to Ward Hill Substation in Haverhill, MA. | 2026-06-01 | Approved | 2024-10-01
ES-24-T36 | 2024-09-04 | Queue Position 1252 (QP 1252) 310 MW Battery Project | Transmission application from Eversource Energy for the reconductoring of the Eversource Energy owned portion of the 338 Line. | 2029-07-01 | Approved | 2024-10-01
ES-24-G61 | 2024-09-10 | Queue Position 1245 (QP 1245) 150 MW (NET) Solar Project | Generator Application from Eversource Energy on behalf Saltbox Solar Project, LLC for the installation of a 150 MW (net) Solar facility interconnecting to a new substation in East Windsor and Ellington, CT. | 2028-11-11 | Approved | 2024-10-01
ES-24-T37 | 2024-09-10 | Queue Position 1245 (QP 1245) 150 MW (NET) Solar Project | Transmission application from Eversource Energy for the installation of a new substation in East Windsor and Ellington, CT that will bifurcate Line 3419 between Barbour Hill and Ludlow 345 kV Substations. | 2028-11-11 | Approved | 2024-10-01
ES-24-T38 | 2024-09-10 | Queue Position 1245 (QP 1245) 150 MW (NET) Solar Project | Transmission application from Eversource Energy on behalf of Saltbox Solar Project, LLC for the installation of a new 345 kV/ 34.5 kV /13.8 kV step up transformer to a new substation in East Windsor and Ellington, CT. | 2028-11-11 | Approved | 2024-10-01
GPS-23-G01 Rev.2 | 2024-08-08 | Queue Position 1357 (QP 1357) 150 MW Solar Project | Generator application from Gravel Pit Solar, LLC (GPS) for installation of 150 MW solar facility in East Windsor, CT and interconnecting to the Gravel Pit 35E Substation. | 2025-11-01 | Approved | 2024-10-01
GPS-23-T01 Rev.2 | 2024-08-08 | Queue Position 1357 (QP 1357) 150 MW Solar Project | Transmission application from Gravel Pit Solar, LLC for the installation of two 115/34.5/13.8 kV 51/68/85 MVA step-up transformers. | 2024-09-14 | Approved | 2024-10-01
ES-20-T34 Rev.3 | 2024-08-08 | Queue Position 1357 (QP 1357) 150 MW Solar Project | Transmission application from Eversource Energy for the installation of a three-breaker ring bus tapped on the 115 kV Line 1200 between Barbour Hill and Windsor Locks substations. | 2024-09-30 | Approved | 2024-10-01
MGED-24-T01 | 2024-08-02 | Middleborough Gas and Electric Department - South Middleborough Substation Project | Transmission application from Middleborough Gas and Electric Department for the installation of a 115 kV/13.8 kV substation connecting between Carver and Tremont substations. | 2026-07-01 | Approved | 2024-10-01
ES-24-T34 | 2024-08-05 | Middleborough Gas and Electric Department - South Middleborough Substation Project | Transmission application from Eversource Energy to bifurcate the 115 kV 134 line between Carver and Tremont substations to allow for the interconnection to the new South Middleborough substation. | 2026-07-01 | Approved | 2024-10-01
NEP-24-T08 | 2024-08-30 | Brayton Point 345 kV Transformer Replacements | Transmission application from New England Power for the replacement of the T3A and T3B 345 kV/115 kV transformers and installation of two new series breakers at Brayton Point Substation. | 2029-11-28 | Approved | 2024-09-23
ES-24-G64 | 2024-08-08 | Greenskies Clean Energy LLC - Old Maids Lane Solar | Generator notification from Eversource Energy on behalf of Greenskies Clean Energy LLC for the installation of 4.999 MW Solar PV in Portland, CT and interconnecting to Old Maids Lane Portland, CT on Circuit 22R4 out of Hopewell Substation. | 2026-12-31 | Notification | 2024-10-01
NEP-24-GNF16 | 2024-08-30 | Solar Design Associates, LLC - 24 Hunt Road Solar | Generator notification from New England Power on behalf of Solar Design Associates, LLC for the installation of 2.0 MW Solar PV in Amesbury, MA and interconnecting to 24 South Hunt Road Amesbury, MA on Circuit 275L6 out of West Amesbury Substation. | 2026-12-01 | Notification | 2024-10-01
UES-24-G05 | 2024-08-01 | Revision Energy Inc - 269 NH Route 125 Solar | Generator notification from Unitil on behalf of Revision Energy Inc fot the installation of 4.0 MW Solar PV in Kingston, NH and interconnecting to 269 NH Route 125 Kingston, NH on Circuit 6W2 out of Kingston Substation. | 2025-12-31 | Notification | 2024-10-01
UES-24-G09 | 2024-08-01 | Ameresco Inc, LLC - 134 NH Route 125 Solar | Generator notification from Unitil on behalf of Ameresco Inc for the installation of 2.75 MW Solar PV in Kingston, NH and interconnecting to 134 NH Route 125 Kingston, NH on Circuit 54X2 out of Kingston Substation. | 2025-12-31 | Notification | 2024-10-01
ES-24-G85 | 2024-09-03 | Amp Solar Development, Inc - 191 West Pomeroy Lane Solar and Battery | Generator notification from Eversource Energy on behalf of Amp Solar Development, Inc for the installation of 3.83 MW Solar PV and 3.3451 MW/10.346 MWh DC Coupled Battery in Amherst, MA and interconnecting 191 West Pomeroy Lane, Amherst, MA on Circuit 17K8 out of Amherst Substation. | 2025-02-28 | Notification | 2024-10-01
NEP-24-GNF17 | 2024-08-30 | Next Grid, Inc - 2118 Grand Army of the Republic Highway Solar and Battery | Generator notification from New England Power on behalf of Next Grid, Inc for the installation of 2.40 MW Solar PV and 1.0 MW/2.0 MWh DC Coupled Battery in Swansea, MA and interconnecting 2118 Grand Army of the Republic Highway Swansea, MA on Circuit 11W81 out of Swansea Substation. | 2026-12-01 | Notification Withdrawn | 10/1/2024 11/19/2024
NEP-24-GNF18 | 2024-08-30 | Next Grid, Inc - 262 Swansea Mall Drive Solar and Battery | Generator notification from New England Power on behalf of Next Grid, Inc for the installation of 1.5 MW Solar PV and 0.5 MW/1.0 MWh DC Coupled Battery in Swansea, MA and interconnecting 262 Swansea Mall Drive Swansea, MA on Circuit 11W85 out of Swansea Substation. | 2026-12-01 | Notification | 2024-10-01
ES-24-G61 | 2024-08-08 | QCells - State Pier Road Battery | Generator notification from Eversource Energy on behalf of QCells for the installation of 4.896 MW/19.584 MWh Battery in New London, CT and interconnecting to State Pier Road New London, CT via circuit 9L09 out of Williams St Substation. (This project has been re-submitted as PPA ID ES-24-G96 to replace the previously submitted Level I PPA ES-24-G61. The PPA ID ES-24-G61 was already assigned to a different project.) | 6/30/2025 | Withdrawn | 2024-10-22
GMP-24-G03 | 2024-08-12 | Delorean Power, LLC - 4678 US Rte 5 Battery | Generator notification from Green Mountain Power on behalf of Delorean Power, LLC for the installation of 4.99 MW/25.0 MWh Battery in St. Albans Town, VT and interconnecting to 798 Maquam Shore Rd St. Albans Town, VT via Circuit G16 out of North Elm Substation. | 2026-06-01 | Notification | 2024-10-01
GMP-24-G05 | 2024-08-12 | Delorean Power, LLC - 798 Maquann Shore Rd Battery | Generator notification from Green Mountain Power on behalf of Delorean Power, LLC for the installation of 4.99 MW/25.0 MWh Battery in St. Albans Town, VT and interconnecting to 798 Maquam Shore Rd St. Albans Town, VT via Circuit G16 out of North Elm Substation. | 2026-06-01 | Notification | 2024-10-01
GMP-24-G06 | 2024-08-14 | Delorean Power, LLC - 99 Panton Road Battery | Generator notification from Green Mountain Power on behalf of Delorean Power, LLC for the installation of 4.99 MW/25.0 MWh Battery in Vergennes, VT and interconnecting to 99 Panton Road Vergennes, VT via Circuit G2 out of Vergennes Substation. | 2026-06-01 | Notification | 2024-10-01
GMP-24-G07 | 2024-08-14 | Delorean Power, LLC - 1800 Higgins Hill Road Battery | Generator notification from Green Mountain Power on behalf of Delorean Power, LLC for the installation of 4.99 MW/25.0 MWh Battery in Waterford, VT and interconnecting to 1800 Higgins Hill Road Waterford, VT via Circuit G4 out of Bay Street Substation. | 2026-06-01 | Notification | 2024-10-01
NEP-24-GNF08 Rev.1 | 2024-08-30 | Onsite Renewables, LLC - 334 Clark Street Battery | Generator notification from New England Power on behalf of Onsite Renewables, LLC for the installation of 4.9992 MW/18.432 MWh Battery in North Andover, MA and interconnecting to 334 Clark Street North Andover, MA via Circuit 56L4 out of Woodchuck Hill Substation. | 2026-02-15 | Notification Withdrawn | 10/1/2024 4/16/2025
NEP-24-GNF19 | 2024-08-30 | BlueWave Solar - 921 Wood Street Battery | Generator notification from New England Power on behalf of BlueWave Solar for the installation of 4.999 MW/19.2 MWh Battery in Swansea, MA and interconnecting to 921 Wood Street Swansea, MA via Circuit 11W84 out of Swansea Substation. | 2026-12-01 | Notification | 2024-10-01
WED-24-G01 | 2024-08-15 | Lightshift Energy - 528 South Cherry Street F2 Battery | Generator notification from Wallingford Electric Division on behalf of Lightshift Energy for the installation of 4.99 MW/20.0 MWh Battery in Wallingford, CT and interconnecting to 528 South Cherry Street, Wallingford, CT via circuit 2 out of Wallingford Substation. | 2025-06-01 | Notification | 2024-10-01
WED-24-G02 | 2024-08-15 | Lightshift Energy - 528 South Cherry Street F13 Battery | Generator notification from Wallingford Electric Division on behalf of Lightshift Energy for the installation of 4.99 MW/20.0 MWh Battery in Wallingford, CT and int.erconnecting to 528 South Cherry Street, Wallingford, CT via circuit 13 out of Wallingford Substation | 2025-06-01 | Notification | 2024-10-01
WED-24-G03 | 2024-08-15 | Convergent Energy and Power LP - 130 Thorpe Avenue F2 Battery | Generator notification from Wallingford Electric Division on behalf of Convergent Energy and Power LP for the installation of 4.99 MW/15.0 MWh Battery in Wallingford, CT and interconnecting to 130 Thorpe Avenue, Wallingford, CT via circuit 21 out of North Wallingford Substation. | 2026-09-30 | Notification | 2024-10-01
WED-24-G04 | 2024-08-15 | Convergent Energy and Power LP - 130 Thorpe Avenue F26 Battery | Generator notification from Wallingford Electric Division on behalf of Convergent Energy and Power LP for the installation of 4.99 MW/15.0 MWh Battery in Wallingford, CT and interconnecting to 130 Thorpe Avenue, Wallingford, CT via circuit 26 out of North Wallingford Substation. | 2026-09-30 | Notification | 2024-10-01
NEP-24-T05 | 2024-08-21 | Wilder Transformer Addition and Replacements | Transmission notification from New England Power for the replacement of the existing T1 and T2 13.8/46 kV transformers with a single 115/46 kV 50 MVA autotransformer, and the addition of a 115/13.8 kV 55 MVA load serving transformer. | 2029-08-01 | Notification | 2024-09-26
ES-24-T39 | 2024-09-10 | Partial Rebuild of Line 362 | Transmission notification from Eversource for the partial rebuild of Line 362 replacing 5.19-miles of existing structures and associated 954-kcmil ACSR and 1192-kcmil ACSR conductor with new structures and 1590-kcmil ACSS conductor. | 2025-12-31 | Notification | 2024-09-23
ES-24-T40 | 2024-09-10 | Rebuild of Line 376 | Transmission notification from Eversource for the rebuild of Line 376 replacing 4.99 miles of existing structures and associated 954-kcmil ACSR and 1192-kcmil ACSR conductor with new structures and 1590-kcmil ACSS conductor between Haddam Neck Substation and Scovill Rock Substation. | 2025-12-31 | Notification | 2024-09-23
NEP-24-G01 | 7/5/2024 | New England Power Affected System Operator (ASO) Fall River North Area Distributed Energy Resource (DER) Group Study Project - Onsite Renewables LLC | Generation application from New England Power on behalf of Onsite Renewables LLC for the installation of a 4.9992 MW/18.432 MWh Battery facility connecting to feeder 28W51 out of Sykes Road substation. | 2025-12-01 | Approved | 2024-08-27
NEP-24-G02 | 7/5/2024 | New England Power Affected System Operator (ASO) Fall River North Area Distributed Energy Resource (DER) Group Study Project - Onsite Renewables LLC | Generation application from New England Power on behalf of Onsite Renewables LLC for the installation of a 4.9992 MW/18.432 MWh Battery facility connecting to feeder 28W52 out of Sykes Road substation. | 2025-12-01 | Approved | 2024-08-27
NEP-24-G03 | 7/5/2024 | New England Power Affected System Operator (ASO) Western Central Massachussets Area Group 4 Distributed Energy Resource (DER) Group Study Project - New Leaf Energy | Generation application from New England Power on behalf of New Leaf Energy for the installation of a 11.45 MW/46.8 MWh Battery facility connecting to feeder 207W4 out of the Litchfield Street substation. | 2026-08-01 | Approved | 2024-08-27
NEP-24-G04 | 7/5/2024 | New England Power Affected System Operator (ASO) Western Central Massachussets Area Group 4 Distributed Energy Resource (DER) Group Study Project - Bloom Energy | Generation application from New England Power on behalf of Bloom Energy for the installation of a 4.25 MW Fuel Cell facility connecting to feeder 522L2 out of Shaker Road substation. | 2026-08-01 | Approved | 2024-08-27
NEP-24-G05 | 7/5/2024 | New England Power Affected System Operator (ASO) Western Central Massachussets Area Group 4 Distributed Energy Resource (DER) Group Study Project - Zero Point Development | Generation application from New England Power on behalf of Zero Point Development for the installation of a 4.948 MW/19.792 MWh Battery facility connecting to feeder 523L3 out of the Thorndike substation. | 2026-08-01 | Approved | 2024-08-27
NEP-24-G06 | 7/5/2024 | New England Power Affected System Operator (ASO) Western Central Massachussets Area Group 4 Distributed Energy Resource (DER) Group Study Project - Aero Point Development | Generation application from New England Power on behalf of Zero Point Development for the installation of a 4.996 MW/19.792 MWh Battery facility connecting to feeder 523L3 out of the Thorndike substation. | 2026-08-01 | Approved | 2024-08-27
ES-24-G07 | 2024-07-29 | Endurant Energy - 22 Deerfield Road Battery Project | Generation application from Eversource Energy on behalf of Endurant Energy for the installation of a 7.0 MW/14.0 MWh Battery facility connecting to feeder 2N05 out of the NW Hartford substation. | 2024-12-29 | Approved | 2024-08-27
NMLD-24-G01 | 2024-07-15 | Tangent Development, LLC - 370 Winter Street Solar | Generator notification from the Town of Norwood Municipal Light Department on behalf of Tangent Development, LLC for the installation of 2.6 MW Solar PV in Norwood, MA and interconnecting to 370 Winter Street, Norwood, MA via Feeder 495/27-28 out of Winter Street Substation. | 2025-05-01 | Notification | 2024-08-27
ES-24-G62 | 2024-07-30 | Greenskies Clean Energy LLC - 54 South Street Solar | Generator notification from Eversource Energy on behalf of Greenskies Clean Energy LLC for the installation of 4.999 MW Solar PV in Morris, CT and interconnecting to 54 South Street, Morris, CT via the 11S15 circuit out of Carmel Hill Substation. | 2025-12-31 | Notification | 2024-08-27
ES-24-G63 | 2024-07-30 | Greenskies Clean Energy LLC - Artillery Road Solar | Generator notification from Eversource Energy on behalf of Greenskies Clean Energy LLC for the installation of 2.75 MW Solar PV in Woodbury, CT and interconnecting to Artillery Road, Woodbury, CT via the 11S14 circuit out of Carmel Hill Substation. | 2024-12-31 | Notification | 2024-08-27
RMLD-24-G01 | 2024-07-30 | Keasarge Energy - 500 Riverpark Drive Battery | Generator notification from Reading Municipal Light Department on behalf of Keasarge Energy for the installation of 4.996 MW/11.182 MWh Battery in North Reading, MA and interconnecting to 500 Riverpark Drive, North Reading, MA via feeder 5W4 out of Station 5 Substation. | 2025-02-15 | Notification | 2024-08-27
MELD-24-G01 | 2024-07-18 | Middleton Electric Light Department - 105 South Main Street Natural Gas | Generator notification from Middleton Electric Department for the installation of a 2.5 MW natural gas generator in Middleton, MA and interconnecting to 105 South Main Street, Middleton, MA via M23-2 feeder out of Middleton Substation. | 2026-01-01 | Notification | 2024-08-27
RIE-24-G02 | 2024-07-30 | Green Development - 172 Beaver-River Road Solar | Generator notification from Rhode Island Energy on behalf of Green Development for the installation of 5.25 MW Solar PV in West Kingston, RI and interconnecting to 172 Beaver-River Road, West Kingston, Ri via the 68F1 circuit out of Kenyon Substation. | 2024-12-12 | Notification | 2024-08-27
RIE-24-G03 | 2024-07-30 | Oak Square Partners - 563 South Road Solar | Generator notification from Rhode Island Energy on behalf of Oak Square Partners for the installation of 4.42 MW Solar PV in East Greenwich, RI and interconnecting to 563 South Road, East Greenwich, RI via the 46F1 circuit out of Old Baptist Road Substation. | 2026-05-10 | Notification | 2024-08-27
RIE-24-G04 | 2024-07-30 | Nautilus Solar - 148 Mail Road Solar | Generator notification from Rhode Island Energy on behalf of Nautilus Solar for the installation of 4.990 MW Solar PV in Exeter, RI and interconnecting to 148 Mail Road, Exeter, RI via the 88F1 circuit out of Tower Hill Substation. | 2024-12-01 | Notification | 2024-08-27
RIE-24-G05 | 2024-07-30 | Nautilus Solar - 1590 Ten Road Road Solar | Generator notification from Rhode Island Energy on behalf of Nautilus Solar for the installation of 2.75 MW Solar PV in Exeter, RI and interconnecting to 590 Ten Rod Road, Exeter, RI via the 30F2 circuit out of Lafayette Substation. | 2024-12-01 | Notification | 2024-08-27
RIE-24-G06 | 2024-07-30 | Episcopal Diocese - 872 Reservoir Road Solar | Generator notification from Rhode Island Energy on behalf of Episcopal Diocese for the installation of 2.2 MW Solar PV in Chepachet, RI and interconnecting to 872 Reservoir Road, Chepachet, RI via the 34F2 circuit out of Chopmist Substation. | 2025-12-31 | Notification | 2024-08-27
RIE-24-G07 | 2024-07-30 | Revity Energy - 1935 Phenix Avenue Solar | Generator notification from Rhode Island Energy on behalf of Revity Energy for the installation of 6.25 MW Solar PV in Cranston, RI and interconnecting to 1935 Phenix Avenue, Cranston, RI via the 21F1 circuit out of West Cranston Substation. | 2025-12-31 | Notification | 2024-08-27
RIE-24-G08 | 2024-07-30 | Direct Energy Solar - 0 Victory Highway Solar | Generator notification from Rhode Island Energy on behalf of Direct Energy Solar for the installation of 3.5 MW Solar PV in Coventry, RI and interconnecting to 0 Victory Highway, Coventry, RI via the 63F3 circuit out of Hopkins Hill Substation. | 2025-09-01 | Notification | 2024-08-27
RIE-24-G09 | 2024-07-30 | Nexamp Solar - 689 Victory Highway Solar | Generator notification from Rhode Island Energy on behalf of Nexamp Solar for the installation of 4.0 MW Solar PV in West Greenwich, RI and interconnecting to 689 Victory Highway, West Greenwich, RI via the 3311 circuit out of Kent County Substation. | 2025-09-01 | Notification | 2024-08-27
RIE-24-G10 | 2024-07-30 | North Bridge Development - 214-215 James P Murphy Highway Solar | Generator notification from Rhode Island Energy on behalf of North Bridge Development for the installation of 3.6 MW Solar PV in West Warwick, RI and interconnecting to 214-215 James P Murphy Highway, West Warwick, RI via the 22F1 circuit out of Kent County Substation | 2025-09-01 | Notification | 2024-08-27
RIE-24-G11 | 2024-07-30 | Ameresco Inc. - 451 Arnold Road Solar | Generator notification from Rhode Island Energy on behalf of Ameresco Inc. for the installation of 4.975 MW Solar PV in Coventry, RI and interconnecting to 451 Arnold Road, Coventry, RI via the 22F1 circuit out of Kent County Substation. | 2024-12-01 | Notification | 2024-08-27
CMP-23-G25 | 2024-07-31 | Renesola Power Holdings, LLC - Athens Road Solar | Generator notification from Central Maine Power Company on behalf of Renesola Power Holdings, LLC for the installation of 1.992 MW Solar PV in Athens, ME and interconnecting to Athens Road, Athens, ME via Circuit 827D2 out of Athens Substation. (This was originally submitted as CMP-23-G28, but that PPA number had already been used.) | 2024-10-01 | Notification | 2024-08-27
ES-24-T06 | 2024-07-30 | Partial Rebuild of Line 362 | Transmisison notification from Eversource Energy for the partial rebuild of line 362 replacing 5.19-miles of existing structures and associated 954-kcmil ACSR and 1192-kcmil ACSR conductor with new structures and 1590-kcmil ACSS conductor. | 2025-12-31 | Withdrawn | 2024-09-17
ES-24-T07 | 2024-07-30 | Rebuild of Line 376 | Transmisison notification from Eversource Energy for the rebuild of line 376 replacing 4.99 miles of existing structures and associated 954-kcmil ACSR and 1192-kcmil ACSR conductor with new structures and 1590-kcmil ACSS conductor between Haddam Neck Substation and Scovill Rock Substation. | 2025-12-31 | Withdrawn | 2024-09-17
ES-24-T08 | 2024-07-30 | Partial Rebuild of Line 1772 | Transmisison notification from Eversource Energy for the partial rebuild of line 1772 replacing 6.66 miles of existing structures and associated 1192-kcmil ACSR and 1272-kcmil ACSR conductor with new structures and 1590-kcmil ACSS conductor. | 2025-12-31 | Notification | 2024-09-03
CMP-23-G01 Rev.1 | 2024-06-28 | Queue Position 1097 (QP 1097) Greene Apple Solar Project Rev.1 | Generation application from Central Maine Power on behalf of Swift Current Energy for the installation of a 178.59 MW solar facility connecting to a new three-breaker ring switching station located on Section 212 between Larrabee Road and Monmouth substations. | 2027-11-01 | Approved | 2024-07-30
CMP-23-T01 Rev.1 | 2024-06-28 | Queue Position 1097 (QP 1097) Greene Apple Solar Project Rev.1 | Transmission application from Central Maine Power for the installation of a new three-breaker ring bus switching station located on Section 212 between Larrabee Road and Monmouth substations. | 2027-05-01 | Approved | 2024-07-30
CMP-23-T02 Rev.1 | 2024-06-28 | Queue Position 1097 (QP 1097) Greene Apple Solar Project Rev.1 | Transmission application from Central Maine Power on behalf of Swift Current Energy for the installation of a 115/34.5/13.8 kV Main Power Transformer and a 100’ 115 kV generator lead line from the QP 1097 collector station to the new QP 1097 115 kV three breaker ring switching station. | 2027-05-01 | Approved | 2024-07-30
CMP-23-T03 Rev.1 | 2024-06-28 | Queue Position 1097 (QP 1097) Greene Apple Solar Project Rev.1 | Transmission application from Central Maine Power for the replacement of nine 115 kV circuit breakers at the Larrabee Road 115 kV substation. | 2027-05-01 | Approved | 2024-07-30
ES-24-G57 | 2024-07-01 | Eversource Energy Greater Boston Area Distributed Energy Resource (DER) Group Study Project - OnSite Renewables, LLC - 340 Pine Street Battery | Generator application from Eversource Energy on behalf of Onsite Renewables, LLC for the installation of a 4.9992 MW/18.432 MWh Battery facility in Canton, MA and interconnecting to the Canton Substation via the 470-H4 circuit. | 2025-01-01 | Approved | 2024-07-30
ES-24-G58 | 2024-07-01 | Eversource Energy Greater Boston Area Distributed Energy Resource (DER) Group Study Project - ZP Bettery Bevco LLC - 26 Pearl Street Battery | Generator application from Eversource Energy on behalf of ZP Battery Devco LLC for the installation of a 4.948 MW/19.792 MWh Battery facility in Bellingham, MA and interconnecting to the Medway Substation via the 65-H4 circuit. | 2025-01-01 | Approved | 2024-07-30
ES-24-G59 | 2024-07-01 | Eversource Energy Greater Boston Area Distributed Energy Resource (DER) Group Study Project - BWC Echo Lake, LLC - 0 Chestnut Street Solar and Battery | Generator application from Eversource Energy on behalf of BWC Echo Lake, LLC for the installation of a 3.9 MW Solar and 3.5 MW/7.0 MWh Battery facility in Hopkinton, MA and interconnecting to the Medway Substation via the 65-H7 circuit. | 2025-01-01 | Approved | 2024-07-30
ES-24-G60 | 2024-07-01 | Eversource Energy Greater Boston Area Distributed Energy Resource (DER) Group Study Project - Norfolk Road Solar, LLC - 6 Norfolk Road Solar and Battery | Generator application from Eversource Energy on behalf of Norfolk Road Solar, LLC for the installation of a 4.99 MW Solar and 4.99MW/10.6 MWh Battery facility in Millis, MA and interconnecting to the Walpole Substation via the 146-H10 circuit. | 2025-01-01 | Approved | 2024-07-30
CMP-22-G22 Rev.1 | 2024-06-28 | NextGrid Mahogany, LLC - 1043 Maine Street Solar | Generator notification from Central Maine Power on behalf of NextGrid Mahogany, LLC for the installation of 4.531 MW Solar PV in Lewiston, ME and interconnecting to 1043 Main Street, Lewiston, ME via Circuit 412D4 out of Deer Rips Substation. | 2024-12-31 | Notification | 2024-07-30
CMP-22-G33 Rev.1 | 2024-06-28 | NextGrid Bayberry, LLC - 497 Minot Road Solar | Generator notification from Central Maine Power on behalf of NextGrid Bayberry, LLC for the installation of 1.960 MW Solar PV in Minot, ME and interconnecting to 497 Minot Road, Minot, ME via Circuit 431D2 out of Mechanic Falls Substation. | 2024-12-31 | Notification | 2024-07-30
CMP-22-G43 Rev.1 | 2024-06-28 | Lewiston Solar II, LLC - 24 Ferry Road Solar | Generator notification from Central Maine Power on behalf of Lewiston Solar II, LLC for the installation of 1.975 MW Solar PV in Lewiston, ME and interconnecting to 24 Ferry Road, Lewiston, ME via Circuit 421D2 out of Challenger Drive Substation. | 2024-12-31 | Notification | 2024-07-30
ES-24-G56 | 2024-07-01 | Colony Honey LLC - 166 South Street Solar | Generator notification from Eversource Energy on behalf of Colony Honey LLC for the installation of 4.050 MW Solar PV in Morris, CT and interconnecting to 166 South Street, Morris, CT via 11S15 Circuit out of Carmel Hill 11S Substation. | 2025-12-31 | Notification | 2024-07-30
ES-24-G55 | 2024-07-02 | Greenskies Clean Energy LLC - 356 CT-2 Solar | Generator notification from Eversource Energy on behalf of Greenskies Clean Energy LLC for the installation of 2.75 MW Solar PV in Preston, CT and interconnecting to 356 CT-2, Preston, CT via Circuit 11B2 out of Gales Ferry Station. | 2025-06-30 | Notification | 2024-07-30
ES-19-G71 Rev.1 | 2024-07-02 | BE RE, LLC - 126 Ring Road Solar and Battery | Generator notification from Eversource Energy on behalf of BE RE, LLC for the installation of 2.0 MW Solar PV and 2.0 MW/13.5 MWh DC Coupled Battery in Plympton, MA and interconnecting to 126 Ring Road, Plympton, MA via Circuit 3-15-15 out of Kingston Substation. | 2024-08-15 | Notification | 2024-07-30
GTMLD-24-G01 | 2024-06-26 | Georgetown BESS 1 - 203 East Main Street Battery | Generator notification from Georgetown Municipal Light Department on behalf of Georgetown BESS 1 for the installation of a 3.0 MW/12.0 MWh Battery in Georgetown, MA and interconnecting to 203 East Main Street, Georgetown, MA via Feeder 2 out of Searle Street Substation. | 2025-06-01 | Notification | 2024-07-30
AGR-24-G01 | 2024-04-30 | Queue Position 1109 (QP 1109) | Generator application for the construction of a 1276.35MW offshore Wind farm comprising 134 wind turbine generators located on OCS-A 0534 south of Martha’s Vineyard and interconnecting to the Eversource transmission system at the West Barnstable 345kV Substation (921). | 2029-04-30 | Approved | 2024-07-02
AGR-24-T01 | 2024-04-30 | Queue Position 1109 (QP 1109) | Transmission application for the installation of a single offshore gas-insulated substation (“GIS”), containing 66kV switchgear, 220kV circuit breakers and three (3) 450MVA 220/66kV on-load tap-changing transformers. | 2029-04-20 | Approved | 2024-07-02
AGR-24-T02 | 2024-04-30 | Queue Position 1109 (QP 1109) | Transmission application for the installation of a combination of three (3) 1400mm² Cu, 3-core 220kV submarine cables and 1400mm² Cu single conductor 220kV terrestrial underground cable to transmit the power from the offshore substations approximately 63.6 miles to onshore substation. | 2029-04-30 | Approved | 2024-07-02
AGR-24-T03 | 2024-04-30 | Queue Position 1109 (QP 1109) | Transmission application for the installation of a single onshore substation containing three (3) 400MVA 345kV/220kV on-load tap-changing transformers, each separately connected to a 345kV straight bus and a 220kV straight bus. | 2029-04-30 | Approved | 2024-07-02
AGR-24-T04 | 2024-04-30 | Queue Position 1109 (QP 1109) | Transmission application for the installation of three (3) individual 345kV circuits providing separate onshore substation transformer interconnection to distinct West Barnstable 345kV station breaker positions through an approximately 3-mile underground circuit. | 2029-04-30 | Approved | 2024-07-02
AGR-24-T05 | 2024-04-30 | Queue Position 1109 (QP 1109) | Transmission application for the installation of three (3) +150MVAR/-150MVAR STATCOM’s connected directly to the 345kV bus. | 2029-04-30 | Approved | 2024-07-02
AGE-24-G02 | 2024-04-30 | Queue Position 1154 (QP 1154) | Generator application for the construction of an 857.25MW offshore Wind farm comprising 90 wind turbine generators located on OCS-A 0534 south of Martha’s Vineyard and interconnecting to the Eversource transmission system at the West Barnstable 345kV Substation (921). | 2029-05-01 | Approved | 2024-07-02
AGR-24-T06 | 2024-04-30 | Queue Position 1154 (QP 1154) | Transmission application for the installation of a single offshore gas-insulated substation (“GIS”), containing 66 kV switchgear, 220kV circuit breakers and two (2) 450MVA 220/66kV on-load tap-changing transformers. | 2028-03-12 | Approved | 2024-07-02
AGR-24-T07 | 2024-04-30 | Queue Position 1154 (QP 1154) | Transmission application for the installation of a combination of two (2) 1600mm² Cu, 3-core 220kV submarine cables and 1600mm² Cu single conductor 220kV terrestrial underground cable to transmit the power from the offshore substations approximately 59-miles to onshore substation. | 2028-03-12 | Approved | 2024-07-02
AGR-24-T08 | 2024-04-30 | Queue Position 1154 (QP 1154) | Transmission application for the installation of a single onshore substation containing two (2) 400MVA 345kV/220kV on-load tap-changing transformers, each separately connected to a 345kV straight bus and a 220kV straight bus | 2028-03-12 | Approved | 2024-07-02
AGR-24-T09 | 2024-04-30 | Queue Position 1154 (QP 1154) | Transmission application for the installation of two (2) individual 345kV circuits providing separate onshore substation transformer interconnection to distinct West Barnstable 345kV station breaker positions through an approximately 3-mile underground circuit. | 2028-03-12 | Approved | 2024-07-02
AGR-24-T10 | 2024-04-30 | Queue Position 1154 (QP 1154) | Transmission application for the installation of two (2) +150MVAR/-150MVAR STATCOM’s connected directly to the 345kV bus. | 2028-03-12 | Approved | 2024-07-02
ES-24-T21 | 2024-04-30 | Queue Position 1109 (QP 1109) and QP 1154 (QP1154) | Transmission application from Eversource Energy to install a new third 345 kV line (3997) connecting West Barnstable 345 kV and Bourne 345 kV Substations. The project constructs a new 345 kV circuit connecting the West Barnstable 345 kV and Bourne 345 kV substations along the 107/136/137 ROW. | 2029-04-30 | Approved | 2024-07-02
ES-24-T22 | 2024-04-30 | Queue Position 1109 (QP 1109) and QP 1154 (QP1154) | Transmission application from Eversource Energy to loop the existing Line 342 into the new Bourne 345 kV substation The project splits the existing 342 circuit between Canal and Jordan Tap into two circuits: 3420 from Bourne to Canal, and 342 from Bourne to Jordan Tap. | 2029-04-30 | Approved | 2024-07-02
ES-24-T23 | 2024-04-30 | Queue Position 1109 (QP 1109) and QP 1154 (QP1154) | Transmission application from Eversource Energy to upgrade the LTE rating of the 3992 circuit between Bourne and West Barnstable. | 2029-04-30 | Approved | 2024-07-02
ES-24-T24 | 2024-04-30 | Queue Position 1109 (QP 1109) and QP 1154 (QP1154) | Transmission application from Eversource Energy to upgrade the LTE rating of the 399 circuit between Bourne and Carver. | 2029-04-30 | Approved | 2024-07-02
ES-24-T25 | 2024-04-30 | Queue Position 1109 (QP 1109) and QP 1154 (QP1154) | Transmission application from Eversource Energy to upgrade the LTE rating of the 3991 circuit between Bourne and West Barnstable. | 2029-04-30 | Approved | 2024-07-02
ES-24-T26 | 2024-04-30 | Queue Position 1109 (QP 1109) and QP 1154 (QP1154) | Transmission application from Eversource Energy to add two bays with five breakers at the future Bourne 345 kV substation. | 2029-04-30 | Approved | 2024-07-02
ES-24-T27 | 2024-04-30 | Queue Position 1109 (QP 1109) and QP 1154 (QP1154) | Transmission application from Eversource Energy to add one bay and five breakers (three breakers for the new bay and two breakers added to the existing bays) to the future West Barnstable 345 kV substation. | 2029-04-30 | Approved | 2024-07-02
ES-24-T28 | 2024-04-30 | Queue Position 1109 (QP 1109) and QP 1154 (QP1154) | Transmission application from Eversource Energy to upgrade the protection systems for Eversource's West Barnstable 921 115 kV substation to meet the NPCC BPS design requirements. | 2029-04-30 | Approved | 2024-07-02
ES-20-T47 Rev.1 | 2024-04-30 | Queue Position 1109 (QP 1109) and QP 1154 (QP1154) | Transmission application from Eversource Energy to construct a new 345 kV breaker-and-a-half GIS Bourne substation in the vicinity of the existing 115 kV Bourne substation consisting of three bays and eight new breakers, looping in two existing transmission lines (Line 399 and Line 322) into the new 345 kV Bourne substation. | 2029-04-30 | Approved | 2024-07-02
ES-20-T48 Rev.1 | 2024-04-30 | Queue Position 1109 (QP 1109) and QP 1154 (QP1154) | Transmission application from Eversource Energy to upgrade the existing West Barnstable 345 kV substation as GIS breaker-and-a-half design with four bays and ten new breakers. | 2029-04-30 | Approved | 2024-07-02
ES-20-T49 Rev.1 | 2024-04-30 | Queue Position 1109 (QP 1109) and QP 1154 (QP1154) | Transmission application from Eversource Energy to install one 115 kV breaker at the existing 115 kV West Barnstable susbtation. | 2029-04-30 | Approved | 2024-07-02
ES-20-T50 Rev.1 | 2024-04-30 | Queue Position 1109 (QP 1109) and QP 1154 (QP1154) | Transmission application from Eversource Energy to install a second 345/115 kV transformer at the West Barnstable substation. | 2029-04-30 | Approved | 2024-07-02
ES-20-T51 Rev.1 | 2024-04-30 | Queue Position 1109 (QP 1109) and QP 1154 (QP1154) | Transmission application from Eversource Energy to convert the planned 115 kV Mid-Cape Line (RSP ID 1725 – Line 144: PPA ES-18-T11) to 345 kV terminating between the new 345 kV Bourne and the 345 kV West Barnstable substations. | 2029-04-30 | Approved | 2024-07-02
CMP-23-G06 Rev.1 | 2024-06-04 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Restudy Project - BD Solar Fryeburg LLC Rev.1 | Generator application from Central Maine Power (CMP) on behalf of BD Solar Fryeburg LLC for the installation a 2.45 MW PV facility in Fryeburg, ME and interconnecting to the Fryeburg substation via the 415D2 circuit. | 2029-09-30 | Approved | 2024-06-28
CMP-23-G12 Rev.1 | 2024-06-04 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Restudy Project - Naples Old County Solar 1 LLC Rev.1 | Generator application from Central Maine Power (CMP) on behalf of Naples Old County Solar 1 LLC for the installation a 2.295 MW PV facility in Naples, ME and interconnecting to the Bridgton 34 kV substation via the 406D4 circuit. | 2029-09-30 | Approved Withdrawn | 6/28/2024 2/13/2025
CMP-23-G14 Rev.1 | 2024-06-04 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Restudy Project - ISM Solar Bolster Mills, LLC Rev.1 | Generator application from Central Maine Power (CMP) on behalf of ISM Solar Bolster Mills, LLC for the installation a 2.0 MW PV facility in Harrison, ME and interconnecting to the Kimball Road substation via the 423D2 circuit. | 2029-09-30 | Approved Withdrawn | 6/28/2024 2/13/2025
CMP-23-G17 Rev.1 | 2024-06-04 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Restudy Project - Parsonfield Sokokis Solar 1 LLC - Rev.1 | Generator application from Central Maine Power (CMP) on behalf of Parsonfield Sokokis Solar 1 LLC for the installation a 4.073 MW PV facility in Parsonsfield, ME and interconnecting to the Hiram Tap substation via the 692D1 circuit. | 2029-12-31 | Approved Withdrawn | 6/28/2024 2/13/2025
CMP-23-G18 Rev.1 | 2024-06-04 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Restudy Project - NBD Solar Maine LLC - Rev.1 | Generator application from Central Maine Power (CMP) on behalf of NBD Solar Maine LLC for the installation a 2.45 MW PV facility in Limington, ME and interconnecting to the North Limington substation via the 638D1 circuit. | 2029-12-31 | Approved Withdrawn | 6/28/2024 2/13/2025
CMP-23-G19 Rev.1 | 2024-06-04 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Restudy Project - NBD Solar Maine LLC - Rev.1 | Generator application from Central Maine Power (CMP) on behalf of NBD Solar Maine LLC for the installation a 1.99 MW PV facility in Limington, ME and interconnecting to the North Limington substation via the 638D1 circuit. | 2029-12-31 | Approved Withdrawn | 6/28/2024 2/13/2025
CMP-23-G20 Rev.1 | 2024-06-04 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Restudy Project - 549 Doles Ridge Road Solar - Rev.1 | Generator application from Central Maine Power (CMP) on behalf of 549 Doles Ridge Road Solar LLC for the installation a 2.45 MW PV facility in Limerick, ME and interconnecting to the Limerick substation via the 632D1 circuit. | 2025-12-31 | Approved | 2024-06-28
CMP-23-G22 Rev.1 | 2024-06-04 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Restudy Project - Limerick East Range Solar 1 LLC - Rev.1 | Generator application from Central Maine Power (CMP) on behalf of Limerick East Range Solar 1 LLC for the installation a 1.999 MW PV facility in Limerick, ME and interconnecting to the Limerick substation via the 632D2 circuit. | 2025-12-31 | Approved Withdrawn | 6/28/2024 2/13/2025
BRP-24-G01 | 2024-06-05 | Queue Position 1138 (QP 1138) Substation and Solar Project | Generator Application from Brookfield Renewable Trading and Marketing LP on behalf of BPUS Generation Development LLC for a 51.105 MW PV facility interconnecting to Eversource line 1316 in Sterling, CT. | 2027-12-30 | Approved | 2024-06-28
BRP-24-T01 | 2024-06-05 | Queue Position 1138 (QP 1138) Substation and Solar Project | Transmission application from Brookfield Renewable Trading and Marketing LP on behalf of BPUS Generation Development LLC for the installation of a 115kV/34.5kV 56/74/93 MVA transformer. | 2027-09-30 | Approved | 2024-06-28
ES-24-T31 | 2024-06-10 | Queue Position 1138 (QP 1138) Substation and Solar Project | Transmission application from Eversource for the addition of a 115 kV 3-breaker ring-bus switchyard on the 1316 line between Canterbury substation and Tunnel substations. | 2027-09-30 | Approved | 2024-06-28
ES-24-G51 | 2024-06-10 | Pompeo Road Solar - Pompeo Rd Solar Project and VCP Realty, 1 Castle Rock Rd Solar Project | Generator application from Eversource on behalf of VCP Realty for the installation of a 3.0 MW solar facility in Woodstock, CT and interconnecting to the Tracy substation via the 14M9 circuit. | 2024-11-01 | Approved | 2024-06-28
ES-24-G52 | 2024-06-10 | Pompeo Road Solar - Pompeo Rd Solar Project and VCP Realty, 1 Castle Rock Rd Solar Project | Generator application from Eversource on behalf of Pompeo Road Solar for the installation of a 4.0 MW solar facility in Thompson, CT and interconnecting to the Tracy substation via the #2 Bus. | 2024-11-01 | Approved | 2024-06-28
VP-23-G02 Rev.1 | 2024-05-29 | Queue Position 1299 (QP 1299) Trenton Solar Project Rev.1 | Generator Application from Versant Power on behalf of Trenton Solar LLC for 70 MW PV facility interconnecting to a 115 kV bus in Trenton, ME. | 2026-09-25 | Approved | 2024-06-28
VP-23-T01 Rev.1 | 2024-05-29 | Queue Position 1299 (QP 1299) Trenton Solar Project Rev.1 | Transmission application from Versant Power for the installation of a new three-breaker ring bus switching station on Line 57 between Waltham and Trenton substation. | 2026-09-11 | Approved | 2024-06-28
VP-23-T02 Rev.1 | 2024-05-29 | Queue Position 1299 (QP 1299) Trenton Solar Project Rev.1 | Transmission Application from Versant Power on behalf of Trenton Solar LLC, for the installation of a 115kV/34.5kV 50/67/83 MVA transformer. | 2026-09-11 | Approved | 2024-06-28
AVRN-24-G01 | 2024-06-11 | Deerfield Wind Dynamic Control Change Project | Generator application from Avangrid Renewables to enable Voltage Control at Deerfield Wind in Searsburg, VT and interconnecting to the Putnam Road substation. | 2027-12-31 | Approved | 2024-06-28
NERP-24-X01 | 2024-06-11 | Fitchburg AVR Replacement Project | Generator application from Hartree Partners, NERP Fitchburg, LLC for the replacement of an AVR unit in Fitchburg, MA. | 2024-05-31 | Approved | 2024-06-18
CMP-21-G51 Rev.1 | 2024-05-30 | Vassalboro PV, LLC - 2579 Riverside Drive Solar | Generator notification from Central Maine Power on behalf of Vassalboro PV, LLC for the installation of 3.178 MW Solar PV in Vasslboro, ME and interconnecting to 2579 Riverside Drive, Vasslboro, ME via 861D8 circuit out of Vassalboro Substation. | 2024-10-01 | Notification | 2024-06-28
ES-24-G53 | 2024-05-14 | Kearsarge Energy - 0 Old Mill Road Solar | Generator notification from Eversource on behalf of Kearsarge Energy for the installation of 4.999 MW Solar PV in Stratford, NH and interconnecting to 0 Old Mill Road, Stratford, NH via 355X circuit out of Lost Nation Substation. | 2025-07-31 | Notification | 2024-06-28
ES-24-G54 | 2024-05-28 | Greenskies Clean Energy - 0 Spencer Hill Road Solar | Generator notification from Eversource on behalf of Greenskies Clean Energy for the installation of 3.74 MW Solar PV in Winchester, CT and interconnecting to 0 Spencer Hill Road, Winchester, CT via 33B7 circuit out of Winsted Substation. | 2024-07-01 | Notification | 2024-06-28
IELD-24-G01 | 2024-05-06 | Ipswich BESS 1 - 0 Town Farm Road Solar | Generator notification from Ipswich Electric Light Department on behalf of Ipswich BESS 1 for the installation of 4.99 MW/22.0 MWh Battery in Ipswich, MA and interconnecting to 0 Town Farm Road, Ipswich, MA via Ipswich Substation. | 2025-06-01 | Notification | 2024-06-28
LWL-24-G01 | 2024-05-14 | Convergent Energy and Power LP - 1533 St. Johnsbury Rd Solar | Generator notification from Littleton Water and Light on behalf of Convergent Energy and Power LP for the installation of 4.99 MW Solar PV in Grafton, NH and interconnecting to 1533 St. Johnsbury Rd, Grafton, NH via Line 30. | 2025-12-15 | Notification | 2024-06-28
PMLD-24-G01 | 2024-05-03 | Princeton BESS 1 - 168 Worcester Rd Solar | Generator notification from Princeton Municipal Light Department on behalf of Princeton BESS 1 for the installation of 2.0 MW/8.92 MWh Battery in Princeton, MA and interconnecting to 168 Worcester Rd, Princeton, MA via 1503 circuit out of Chocksett Substation. | 2025-06-01 | Notification | 2024-06-28
VPPSA-24-G01 | 2024-05-28 | Northfield BESS 1 - 138 King St Solar | Generator notification from Vermont Public Power Supply Authority on behalf of Northfield BESS 1 for the installation of 3.0 MW/12.0 MW Battery in Northfield, VT and interconnecting to 138 King St, Northfield, VT via 54G4 breaker at the Northfield King St. substation. | 2025-05-01 | Notification | 2024-06-28
ES-24-G20 Rev.1 | 2024-05-30 | Michaud Law Group LLC - 0 Oronoke Road Solar | Generator notification from Eversource on behalf of Michaud Law Group LLC for the installation of 4.125 MW Solar PV in New Haven, CT and interconnecting to 0 Oronoke Road, New Haven, CT via 13F62 circuit out of Baldwin Substation. | 2024-07-30 | Notification | 2024-06-28
CMP-23-G82 Rev.1 | 2024-06-04 | Damariscotta Solar 1 LLC - US Route 1 Solar | Generator notification from Central Maine Power on behalf of Damariscotta Solar 1 LLC for the installation of 4.7275 MW Solar PV in Damariscotta and interconnecting to US Rte 1, Damariscotta, ME via 219D1 circuit out of Damariscotta Mills substation. | 2024-12-30 | Notification Withdrawn | 6/28/2024 1/22/2025
CMP-23-G46 Rev.1 | 2024-06-05 | ME I Prospect Pond LLC - 1129 Bangor Road Solar | Generator notification from Central Maine Power on behalf of ME I Prospect Pond LLC for the installation of 4.984 MW Solar PV in Prospect, ME and interconnecting to 1129 Bangor Road, Prospect, ME via 846D1 circuit out of Prospect substation. | 2026-06-30 | Notification | 2024-06-28
CMP-23-G67 Rev.1 | 2024-06-05 | BD Solar Dexter LLC - 445 Corinna Road Solar | Generator notification from Central Maine Power on behalf of BD Solar Dexter LLC for the installation of 3.0 MW Solar PV in Dexter, ME and interconnecting to 445 Corinna Road, Dexter, ME via 813D1 circuit out of Dexter substation. | 2026-06-30 | Notification | 2024-06-28
ES-20-G64 Rev.1 | 2024-05-22 | NextGrid Red Cedar - 0 Middle Road Solar and Battery | Generator notification from Eversource on behalf of NextGrid Red Cedar LLC for the installation of 2.5 MW Solar PV and 1.35 MW/2.7 MWh DC Coupled Battery in Chatham, MA and interconnecting to 0 Middle Road, Chatham, MA via the 4-95A-95A circuit out of Harwich 968 Substation. | 2024-06-15 | Notification | 2024-06-28
NEP-20-G06-004 Rev.2 | 2024-06-03 | TJA Clean Energy - Blackstone Street Solar and Battery | Generator notification from New England Power on behalf of TJA Clean Energy for the installation of 4.56 MW Solar PV and 3.0 MW/6.672 MWh DC Coupled Battery in Blackstone, MA and interconnecting to the Mendon Substation via the 332W1 circuit. | 2024-09-01 | Notification | 2024-06-28
NEP-20-GNF27 Rev.1 | 2024-06-03 | TJA Clean Energy - Brook Street Solar | Generator notification from New England Power on behalf of TJA Clean Energy for the installation of 2.7 MW Solar PV and 1.75 MW/3.64 MWh DC Coupled Battery in Dighton, MA and interconnecting to the Dighton substation via the 19W74 feeder. | 2024-09-01 | Notification | 2024-06-28
ES-24-G02 Rev.1 | 2024-05-14 | Bluewave Storage Oringination - 305 Mount Parnassus Road Battery | Generator notification from Eversource on behalf of Bluewave Storage Origination for the installation of 4.99 MW/19.96 MWh Battery in East Haddam, CT and interconnecting to 305 Mount Parnassus Road, East Haddam, CT via the 11C13 circuit out of Haddam substation. | 2024-06-15 | Notification | 2024-06-28
NEP-24-GNF08 Rev.1 | 2024-06-03 | Onsite Renewables - 305 Mount Parnassus Road Battery | Generator notification from New England Power on behalf of Onsite Renewables for the installation of 4.9992 MW/18.432 MWh Battery in North Andover, MA and interconnecting to 334 Clark Street, North Andover, MA via the 56L4 circuit out of Woodchuck Hill substation. | 2026-02-15 | Notification | 2024-06-28
ES-24-G49 | 2024-04-24 | Queue Position 1192 (QP 1192) 100 MW (NET) Solar Project | Generation application from Eversource Energy on behalf of Solar Nursery, LLC for the installation of a 100 MW (net) solar facility in East Granby, CT and interconnecting to a new 345 kV, 3-breaker ring bus switchyard. | 2026-10-31 | Approved | 2024-05-28
ES-24-T29 | 2024-04-24 | Queue Position 1192 (QP 1192) 100 MW (NET) Solar Project | Transmission application from Eversource Energy for the installation of a new 345 kV, 3-breaker ring bus switchyard in East Granby, CT. | 2026-10-31 | Approved | 2024-05-28
ES-24-T30 | 2024-04-24 | Queue Position 1192 (QP 1192) 100 MW (NET) Solar Project | Transmission application from Eversource Energy for the installation of an 84/100/120 MVA, 345/34.5/13.8 kV generator step-up transformer. | 2026-10-31 | Approved | 2024-05-28
CMP-24-G01 | 2024-04-30 | Central Maine Power System Operator (ASO) Study Augusta 2 Area - 510 PV Project Development LLC - Puddledock Readfield Road Solar | Generator application from Central Maine Power on behalf of 510 PV Project Development LLC for the installation of a 1.99 MW PV facility in Manchester, ME and interconnecting to Puddledock Road substation via the 262D1 circuit. | 2028-06-30 | Approved | 2024-05-28
CMP-24-G03 | 2024-04-30 | Central Maine Power System Operator (ASO) Study Augusta 2 Area - ER Carlton Road Solar LLC - 35 Carlton Pond Road Solar | Generator application from Central Maine Power on behalf of ER Carlton Road Solar, LLC for the installation of a 1.999 MW PV facility in Winthrop, ME and interconnecting to Manchester substation via the 233D2 circuit. | 2025-09-19 | Approved | 2024-05-28
CMP-24-G04 | 2024-04-30 | Central Maine Power System Operator (ASO) Study Augusta 2 Area - Leighton Road Solar | Generator application from Central Maine Power on behalf of Syncarpha Solar LLC for the installation of a 4.95 MW PV facility in Augusta, ME and interconnecting to North Augusta substation via the 272D4 circuit. | 2024-12-01 | Approved Withdrawn | 5/28/2024 12/17/2024
CMP-24-G05 | 2024-04-30 | Central Maine Power System Operator (ASO) Study Augusta 2 Area - Puddledock Road LLC - Puddledock Road Solar | Generator application from Central Maine Power on behalf of Puddledock Road LLC for the installation of a 1.99 MW PV and 0.9 MW/2.196 MWh DC Coupled Battery facility in Manchester, ME and interconnecting to Puddledock Road substation via the 262D1 circuit. | 2024-11-04 | Approved Withdrawn | 5/28/2024 2/15/2025
CMP-24-G06 | 2024-04-30 | Central Maine Power System Operator (ASO) Study Augusta 2 Area - DG West River LLC - 654 West River Road Solar | Generator application from Central Maine Power on behalf of DG West River LLC for the installation of a 4.995 MW PV facility in Augusta, ME and interconnecting to Bond Brook substation via the 208D2 circuit. | 2025-12-31 | Approved | 2024-05-28
CMP-24-G07 | 2024-04-30 | Central Maine Power System Operator (ASO) Study Augusta 2 Area - West Gardiner PV LLC - 453 Lewiston Road Solar | Generator application from Central Maine Power on behalf of West Gardiner PV LLC for the installation of a 1.978 MW PV facility in West Gardiner, ME and interconnecting to West Street substation via the 255D2 circuit. | 2024-12-31 | Approved Withdrawn | 5/28/2024 1/22/2025
CMP-24-G08 | 2024-04-30 | Central Maine Power System Operator (ASO) Study Augusta 2 Area - New Gen Ventures LLC - Lajoie Street Solar | Generator application from Central Maine Power on behalf of New Gen Ventures LLC for the installation of a 1.9 MW PV facility in Augusta, ME and interconnecting to Augusta K5 substation via the 200D2 circuit. | 2024-12-31 | Approved | 2024-05-28
CMP-24-G09 | 2024-04-30 | Central Maine Power System Operator (ASO) Study Augusta 2 Area - BWC Togus Pond LLC - Cony Road Beech St Solar | Generator application from Central Maine Power on behalf of BWC Togus Pond LLC for the installation of a 2.72 MW PV facility in Chelsea, ME and interconnecting to Cony Road substation via the 216D2 circuit. | 2024-12-19 | Approved Withdrawn | 5/28/2024 3/18/2025
CMP-24-G10 | 2024-04-30 | Winslow-County Road-Lakewood 2 Area Distributed Energy Resource - BD Solar Holmes Farm LLC - Rice Rips County Rd Solar | Generator application from Central Maine Power on behalf of BD Solar Holmes Farm LLC for the installation of a 4.999 MW PV facility in Waterville, ME and interconnecting to County Road substation via the 873D2 circuit. | 2026-06-01 | Approved | 2024-05-28
CMP-24-G11 | 2024-04-30 | Winslow-County Road-Lakewood 2 Area Distributed Energy Resource - Oakland Solar II LLC - East Pond Road Solar | Generator application from Central Maine Power on behalf of Oakland Solar II LLC for the installation of a 1.99 MW PV facility in Oakland, ME and interconnecting to County Road substation via the 873D1 circuit. | 2024-12-01 | Approved Withdrawn | 5/28/2024 12/17/2024
GLE-24-G02 | 2024-05-03 | Queue Position 1086 (QP 1086) and Queue Position 1261 (QP 1261) Solar and Battery Project | Generation application from Glenvale LLC on behalf of Warren Meadow Solar Station LLC for the installation of 74.5 MW Solar PV and Battery facility in Highland, ME and interconnecting to Section 80 out of Highland substation. | Solar - 10/31/2025 Battery - 6/3/2026 | Approved | 2024-05-28
GLE-24-T02 | 2024-05-03 | Queue Position 1086 (QP 1086) and Queue Position 1261 (QP 1261) Solar and Battery Project | Transmission application from Glenvale LLC on behalf of Warren Meadow Solar Station LLC for the installation of a 57/75/95 MVA 115/345 kV transformer and a 0.0114 mile 115 kV generator lead line. | 2026-10-31 | Approved | 2024-05-28
CMP-22-T01 Rev.1 | 2024-05-03 | Queue Position 1086 (QP 1086) and Queue Position 1261 (QP 1261) Solar and Battery Project | Transmission application from Central Maine Power for the installation of a 115 kV three-breaker ring bus on CMP Section 80, approximately 2 miles from Highland substation. | 2025-05-01 | Approved | 2024-05-28
CMP-24-T02 | 2024-04-29 | Detroit T3 Transformer Addition Project | Transmission application from Central Maine Power for the installation of a new 115/34 kV transformer at Detroit substation with an LTE rating of 63 MVA. | 2026-09-30 | Approved | 2024-05-29
VP-22-G01 Rev.1 | 2024-05-03 | Queue Position 986 (QP 986) 19.7 MW Solar Project | Generation application from Versant Power on behalf of BD Solar Eddington LLC for the installation of a 19.7 MW (net) Solar PV facility interconnecting to a new switching station on 46 kV Line 5, approximately 5.1 miles from Graham substation. | 2024-11-18 | Approved | 2024-05-28
UES-24-G02 | 2024-03-26 | Phillips Exeter Academy - 0 Gilman Lane Solar | Generation notification from Unitil on behalf of Exeter Academy for the installation of 3.75 MW Solar PV in Exeter, NH and interconnecting to 0 Gilman Lane, Exeter, NH via the 3357 circuit out of Great Bay substation. | 2025-12-31 | Notification | 2024-05-28
UES-24-G03 | 2024-04-19 | Millside Solar LLC - 0 Merrill Corner Road Solar | Generation notification from Unitil on behalf of Millside Solar LLC for the installation of 4.0 MW Solar PV in Boscawen, NH and interconnecting to 0 Merrill Corner Road, Boscawen, NH via the 13W3 circuit out of Oak Hill substation. | 2026-06-30 | Notification | 2024-05-28
NEP-20-G06-002 Rev.1 | 2024-04-25 | Nexamp - 46 McQuade's Lane Solar and Battery | Generation notification from New England Power on behalf of Nexamp for the installation of 2.93 MW Solar PV and 2.49 MW/5.18 MWh DC Coupled Battery in Northbridge, MA and interconnecting to 46 McQuade’s Lane, Northbridge, MA via the 320W3 circuit out of Whitins Pond substation. | 2024-09-01 | Notification | 2024-05-28
PMLP-24-G01 | 2024-04-30 | Peabody BESS 1 LLC - 201 Warren Street Extension Battery | Generation notification from Peabody Municipal Lighting Plant on behalf of Peabody BESS 1 LLC for the insallation of 4.99 MW/22.0 MWh Battery in Peabody, MA and interconnecting to 201 Warren Street Extension, Peabody, MA via the 23 kV circuit out of Warren Street Switching Station. | 2025-06-01 | Notification | 2024-05-28
WMGLD-24-G01 | 2024-04-29 | Wakefield BESS 1 LLC - 23 Hemlock Road Battery | Generation notification from Wakefield Municipal Gas & Lighting on behalf of Wakefield BESS 1 LLC for the installation of a 4.99 MW/22.0 MWh Battery in Wakefield, MA and interconnecting to 23 Hemlock Road, Wakefield, MA via the 0012 circuit out of Beebe substation. | 2025-06-01 | Notification | 2024-05-28
CMP-21-G24 Rev.1 | 2024-03-29 | Queue Position 896 (QP 896) 19.3 MW Solar | Generator application from Central Maine Power on behalf of HEP USA SPV 3 Saco LLC for the installation of a 19.3 MW solar facility in Saco, ME and interconnecting to the Louden substation via a 34.5 kV circuit. | 2026-07-01 | Approved | 2024-04-30
ES-24-G02 | 2024-03-25 | Bluewave Storage Orinination LLC - 305 Mount Parnassus Road Battery Project | Generator application from Eversource on behalf of Bluewave Storage Original LLC for the installation of a 9.2 MW/40.0 MWh battery facility in East Haddam, CT and interconnecting to the Haddam substation via the 11C13 circuit. | 2024-06-15 | Approved | 2024-04-30
RIE-24-T05 | 2024-03-27 | New 115 kV Transmission Line from Woonsocket to Nasonville Project | Transmission application from Rhode Island Energy for the installation of a new 115 kV line from Woonsocket substation to Nasonville substation in Rhode Island. The new line will supply a new 55 MVA, 115/13.8 kV transformer at Nasonville substation. | 2027-12-31 | Approved | 2024-04-23
GLE-24-G01 | 2024-04-03 | Queue Position 935 (QP 935) West Baldwin Solar Project | Generator application from Glenvale LLC on behalf of West Baldwin Solar Station LLC for the installation of a 17.1 MW solar facility in Baldwin, ME and interconnecting to the 34.5 kV collector breaker tap on Section 91. | 2024-03-31 | Approved | 2024-04-30
VP-24-T01 | 2024-03-29 | Orrington Substation 80 MVAR Reactor Addition Project | Transmission application from Versant Power to add a dedicated 80 MVAR reactor to the Orrington T2 transformer and dedicate the existing two 40 MVAR reactors to the Orrington T1 transformer. | 2025-05-31 | Approved | 2024-04-23
GPS-23-G01 Rev.1 | 2024-04-04 | Generation Associated with QP 892/QP 940/ QP 1030/ QP 1247 Project | Generation application from Gravel Pit Solar, LLC for the installation of 145 MW (net) solar facility in East Windsor, CT and interconnecting to the Gravel Pit 35E substation. | 2025-11-01 | Approved | 2024-04-30
GPS-23-T01 Rev.1 | 2024-04-04 | Generation Associated with QP 892/QP 940/ QP 1030/ QP 1247 Project | Transmission application from Gravel Pit Solar, LLC for the installation of an 115/34.5/13.8 kV 51/68/85 MVA step-up transformer. | 2025-11-01 | Approved | 2024-04-30
ES-20-T34 Rev.2 | 2024-04-04 | Generation Associated with QP 892/QP 940/ QP 1030/ QP 1247 Project | Transmission application from Eversource Energy for the installation of a three-breaker ring bus tapped on the 115 kV Line 1200 between Barbour Hill and Windsor Locks substations. | 2024-09-19 | Approved | 2024-04-30
ES-24-G48 | 2024-03-12 | CTEC Solar LLC - 180 Leibert Road Solar | Generator notification from Eversource Energy on behalf of CTEC Solar LLC for the installation of 3.984 MW Solar PV in Hartford, CT and interconnecting to 180 Leibert Road, Hartford, CT via the 2N05 circuit out of Northwest Hartford substation. | 2025-12-31 | Notification | 2024-04-30
ES-24-G50 | 2024-04-01 | City of Bristol - 685 Lake Avenue Solar | Generator notification from Eversource Energy on behalf of City of Bristol for the installation of 1.875 MW Solar PV in Bristol, CT and interconnecting to 685 Lake Avenue, Bristol, CT via the 11K49 circuit out of Bristol substation. | 2025-12-31 | Notification | 2024-04-30
GMP-24-G01 | 2024-04-02 | MHG Solar LLC - 380 US Route 7 Solar | Generator notification from Green Mountain Power on behalf of MHG Solar LLC for the installation of 3.0 MW Solar PV in Rutland, VT and interconnecting to 380 US Route 7, Rutland, VT via the G34 circuit out of North Rutland substation. | 2025-12-31 | Notification | 2024-04-30
UES-21-G01 Rev.1 | 2024-03-25 | DG NH Seabrook, LLC - 27 South Access Road Solar | Generator notification from Unitil on behalf of DG NH Seabrook, LLC for the installation of 4.5 MW Solar PV in Seabrook, NH and interconnecting to 27 South Access Road, Seabrook, NH via the 3348 circuit out of Timber Swamp substation. | 2022-12-01 | Notification | 4/30/2024
UES-24-G01 | 2024-03-25 | Kearsage Energy, LLC - 77 Old Turnpike Road Solar | Generator notification from Unitil on behalf of Kearsage Energy, LLC for the installation of 4.999 MW Solar PV in Concord, NH and interconnecting to 77 Old Turnpike Road, Concord, NH via the 16X4 circuit out of Garvins substation. | 2025-05-01 | Notification | 2024-04-30
ES-24-G49 | 2024-04-04 | Kearsage Energy - 257 Jamestown Road Solar | Generator notification from Eversource Energy on behalf of Kearsage Energy for the installation of 4.99 MW Solar PV in Belmont, NH and interconnecting to 257 Jamestown Road, Belmont, NH via the 337 circuit out of Lanconia substation. | 2025-07-31 | Notification | 2024-04-30
NEP-24-GNF10 | 2024-04-02 | Onsite Renewables, LLC - 1753 Maine Street Battery | Generator notification from New England Power on behalf of Onsite Renewables, LLC for the installation of a 4.9992 MW/18.432 MWh Battery in Brockton, MA and interconnecting to 1753 Main Street, Brockton, MA via the 797W3 circuit out of East Bridgewater substation. | 2026-04-01 | Notification Withdrawn | 4/30/2024 4/16/2025
NEP-24-GNF13 | 2024-04-02 | Onsite Renewables, LLC - 1 Beaver Dam Road Battery | Generator notification from New England Power on behalf of Onsite Renewables, LLC for the installation of a 4.9992 MW/18.432 MWh Battery in Manchester, MA and interconnecting to 1 Beaver Dam Road, Manchester, MA via the 51T1 circuit out of East Beverly substation. | 2026-04-01 | Notification Withdrawn | 4/30/2024 12/17/2024
NEP-24-GNF14 | 2024-04-02 | Onsite Renewables, LLC - 152 Western Avenue Battery | Generator notification from New England Power on behalf of Onsite Renewables, LLC for the installation of a 4.9992 MW/18.432 MWh Battery in Essex, MA and interconnecting to 152 Western Avenue, Essex, MA via the 51T2 circuit out of East Beverly substation. | 2026-04-01 | Notification | 2024-04-30
NEP-24-GNF11 | 2024-04-02 | UGE USA, Inc - 720 High Street Solar and Battery | Generator notification from New England Power on behalf of UGE USA, Inc. for the installtion of 1.744 MW Solar PV and 0.55 MW/1.1 MWh DC Coupled Battery in Clinton, MA and interconnecting to 720 High Street, Clinton, MA via the 216W3 circuit out of Fitch Road substation. | 2026-04-01 | Notification | 2024-04-30
NEP-24-GNF12 | 2024-04-02 | NextGrid, Inc. - 262 Swansea Mall Drive Solar and Battery | Generator notification from New England Power on behalf of NextGrid, Inc. for the installation of 2.0 MW Solar PV and 2.0 MW/4.0 MWh DC Coupled Battery in Swansea, MA and interconnecting to 262 Swansea Mall Drive, Swansea, MA via the 11W85 circuit out of Swansea substation. | 2026-04-01 | Notification | 2024-04-30
FGE-19-G01 Rev.1 | 2024-03-25 | Fitchburg Renewables LLC - 239 Fisher Road Solar and Battery | Generator notification from Fitchburg Gas & Electric on behalf of Fitchburg Renewables LLC for the installation of 4.0 MW Solar PV and 2.023 MW/4.046 MWh AC Coupled Battery in Fitchburg, MA and interconnecting to 239 Fisher Road, Fitchburg, MA via the 35W36 circuit out of Beech Street substation. | 2024-05-01 | Notification | 2024-04-30
ES-23-T48 Rev.1 | 2024-03-20 | F190 Line Rebuild | Transmission notification from Eversource Energy for the rebuild of 0.02 miles of the F190 115 kV line between the tap on line B112 and the Eversource-Tamworth generator ownership border in NH with 1272 ACSS conductor. | 2024-12-31 | Notification | 2024-04-23
ES-24-T16 | 2024-03-29 | S136 Line Rebuild | Transmission notification from Eversource Energy for the rebuild of 27.03 miles of the S136 115 kV line between the Whitefield substation and Berlin substation with 1272 ACSS conductor. | 2026-12-31 | Notification | 2024-04-23
ES-24-T18 | 2024-04-01 | Partial Rebuild of Line 1556 | Transmission notification from Eversource Energy for the partial rebuild of Line 1556 replacing 0.43 miles of existing structures and associated 2-336-kcmil and 1272-kcmil ACSR conductor with 1590-kcmil ACSS conductor. | 2024-08-31 | Notification | 2024-04-23
ES-24-T19 | 2024-04-01 | Partial Rebuild of Line 1645 | Transmission notification from Eversource Energy for the partial rebuild of Line 1645 replacing 0.43 miles of existing structures and associated 1113-kcmil and 1272-kcmil ACSR conductor with 1590-kcmil ACSS conductor. | 2024-08-31 | Notification | 2024-04-23
ES-24-G14 | 2024-01-16 | Eversource Affected System Operator (ASO) Study Card Street-Mansfield Area Distributed Energy Resource (DER) Project - KCE CT 5, LLC - Village Hill Road Battery | Generation application from Eversource Energy on behalf of KCE CT 5, LLC for the installation of a 4.999 MW/30.272 MWh Battery facility in Willington, CT and interconnecting to the Mansfield substation via the 12J37 circuit. | 2025-07-27 | Approved | 2024-03-21
ES-24-G15 | 2024-01-16 | Eversource Affected System Operator (ASO) Study Card Street-Mansfield Area Distributed Energy Resource (DER) Project - Verogy - 931 Route 32 Solar | Generation application from Eversource Energy on behalf of Verogy for the installation of a 4.975 MW PV facility in North Franklin, CT and interconnecting to the Card substation via the 11F12 circuit. | 2024-12-31 | Approved | 2024-03-21
ES-24-G16 | 2024-01-16 | Eversource Affected System Operator (ASO) Study Card Street-Mansfield Area Distributed Energy Resource (DER) Project - Wildcat Renewables, LLC - Boulevard Road Solar | Generation application from Eversource Energy on behalf of Wildcat Renewables, LLC for the installation of a 15.0 MW PV facility in North Windham, CT and interconnecting to the Card substation via the 11F14 circuit. | 2024-06-30 | Approved | 2024-03-21
ES-24-G17 | 2024-01-16 | Eversource Affected System Operator (ASO) Study Card Street-Mansfield Area Distributed Energy Resource (DER) Project - VCP Realty, LLC - 221 Warrenville Road Solar | Generation application from Eversource Energy on behalf of VCP Realty, LLC for the installation of a 1.8 MW PV facility in Mansfield Center, CT and interconnecting to the Mansfield substation via the 12J5 circuit. | 2024-12-29 | Approved | 2024-03-21
ES-24-G18 | 2024-01-16 | Eversource Affected System Operator (ASO) Study Card Street-Mansfield Area Distributed Energy Resource (DER) Project - Verogy - 92 Upper Road Solar | Generation application from Eversource Energy on behalf of Verogy for the installation of a 4.0 MW PV facility in Stafford Springs, CT and interconnecting to the Mansfield substation via the 12J33 circuit. | 2024-12-29 | Approved | 2024-03-21
CMP-24-G22 | 2024-03-05 | Queue Position 1171 (QP 1171) 18.3 MW Wind Project | Generator application from Central Maine Power on behalf of Twin Energy LLC for the installation of an 18.3 MW wind facility in Roxbury, ME and interconnecting to the Roxbury substation via a 34.5 kV circuit. | 2025-10-17 | Approved | 2024-03-21
CMP-24-T01 | 2024-03-05 | Queue Position 1171 (QP 1171) 18.3 MW Wind Project | Transmission application from Central Maine Power to upgrade the Roxbury substation 115/34.5 kV transformer. | 2028-04-30 | Approved | 2024-03-21
VP-24-G01 | 2024-03-05 | Versant Power Affected System Operator (ASO) Study Penobscot-Hancock-Washington Area Distributed Energy Resource (DER) Project - UGE USA Inc. | Generation application from Versant Power on behalf of UGE USA Inc. for the installation of a 0.999 MW Solar PV facility in Bangor, ME and interconnecting to the Graham substation via the EB4 circuit. | 2025-06-01 | Withdrawn | 2024-05-14
VP-24-G02 | 2024-03-05 | Versant Power Affected System Operator (ASO) Study Penobscot-Hancock-Washington Area Distributed Energy Resource (DER) Project - BD Solar - 5 Old Coldbrook Road Solar | Generation application from Versant Power on behalf of BD Solar for the installation of a 2.625 MW Solar PV facility in Hampden, ME and interconnecting to the Graham substation via the HE3 circuit. | 2025-06-01 | Approved | 2024-03-21
VP-24-G03 | 2024-03-05 | Versant Power Affected System Operator (ASO) Study Penobscot-Hancock-Washington Area Distributed Energy Resource (DER) Project - UGE USA Inc. | Generation application from Versant Power on behalf of UGE USA Inc. for the installation of a 0.999 MW Solar PV facility in Corinth, ME and interconnecting to the Graham substation via the EC1 circuit. | 2025-06-01 | Withdrawn | 2024-05-14
VP-24-G04 | 2024-03-05 | Versant Power Affected System Operator (ASO) Study Penobscot-Hancock-Washington Area Distributed Energy Resource (DER) Project - Nexamp Solar LLC - Outback Lane Solar | Generation application from Versant Power on behalf of Nexamp Solar LLC for the installation of a 1.99 MW Solar PV facility in Brewer, ME and interconnecting to the Graham substation via the TS2 circuit. | 2025-12-31 | Approved | 2024-03-21
VP-24-G05 | 2024-03-05 | Versant Power Affected System Operator (ASO) Study Penobscot-Hancock-Washington Area Distributed Energy Resource (DER) Project - Acadia Energy LLC LLC - 90 Kelly Road Solar | Generation application from Versant Power on behalf of Acadia Energy LLC for the installation of a 1.99 MW Solar PV facility in Orono, ME and interconnecting to the Graham substation via the ON1 circuit. | 2025-06-01 | Approved | 2024-03-21
VP-24-G06 | 2024-03-05 | Versant Power Affected System Operator (ASO) Study Penobscot-Hancock-Washington Area Distributed Energy Resource (DER) Project - Nexamp LLC - 129 Hill Road Solar | Generation application from Versant Power on behalf of Nexamp LLC for the installation of a 1.99 MW Solar PV facility in Hampden, ME and interconnecting to the Graham substation via the HM4 circuit. | 2025-06-01 | Approved | 2024-03-21
VP-24-G07 | 2024-03-05 | Versant Power Affected System Operator (ASO) Study Penobscot-Hancock-Washington Area Distributed Energy Resource (DER) Project - NH Solar Garden - Arista Drive Solar | Generation application from Versant Power on behalf of NH Solar Garden for the installation of a 1.9 MW Solar PV facility in Brewer, ME and interconnecting to the Graham substation via the GP2 circuit. | 2025-06-01 | Approved | 2024-03-21
VP-24-G08 | 2024-03-05 | Versant Power Affected System Operator (ASO) Study Penobscot-Hancock-Washington Area Distributed Energy Resource (DER) Project - Wildcat Renewables LLC - Stillwater Avenue Solar | Generation application from Versant Power on behalf of Wildcat Renewables LLC for the installation of a 1.999 MW Solar PV facility in Orono, ME and interconnecting to the Graham substation via the ON3 circuit. | 2025-06-01 | Approved | 2024-03-21
VP-24-G09 | 2024-03-05 | Versant Power Affected System Operator (ASO) Study Penobscot-Hancock-Washington Area Distributed Energy Resource (DER) Project - Nexamp Solar LLC | Generation application from Versant Power on behalf of Nexamp Solar LLC for the installation of a 0.999 MW Solar PV facility in Hampden, ME and interconnecting to the Graham substation via the HM4 circuit. | 2025-12-31 | Withdrawn | 2024-05-14
VP-24-G10 | 2024-03-05 | Versant Power Affected System Operator (ASO) Study Penobscot-Hancock-Washington Area Distributed Energy Resource (DER) Project - Nexamp Solar LLC | Generation application from Versant Power on behalf of Nexamp Solar LLC for the installation of a 0.999 MW Solar PV facility in Franklin, ME and interconnecting to the Ellworth Falls substation via the FR1 circuit. | 2025-12-31 | Withdrawn | 2024-05-14
VP-24-G11 | 2024-03-05 | Versant Power Affected System Operator (ASO) Study Penobscot-Hancock-Washington Area Distributed Energy Resource (DER) Project - 510 PV Project Development LLC - N. Main Street Solar | Generation application from Versant Power on behalf of 510 PV Project Development LLC for the installation of a 1.99 MW Solar PV facility in Cherryfield, ME and interconnecting to the Deblois substation via the DB1 circuit. | 2025-06-01 | Approved | 2024-03-21
VP-24-G12 | 2024-03-05 | Versant Power Affected System Operator (ASO) Study Penobscot-Hancock-Washington Area Distributed Energy Resource (DER) Project - 510 PV Project Development LLC - Scotts Hill Road Solar | Generation application from Versant Power on behalf of 510 PV Project Development LLC for the installation of a 1.99 MW Solar PV facility in East Machias, ME and interconnecting to the WCS substation via the SH1 circuit. | 2025-06-01 | Approved | 2024-03-21
VP-24-G13 | 2024-03-05 | Versant Power Affected System Operator (ASO) Study Penobscot-Hancock-Washington Area Distributed Energy Resource (DER) Project - Nexamp Solar LLC - 131 County Road Solar | Generation application from Versant Power on behalf of Nexamp Solar LLC for the installation of a 1.99 MW Solar PV facility in Eastport, ME and interconnecting to the WCS substation via the EP2 circuit. | 2025-06-01 | Approved | 2024-03-21
ES-24-G21 | 2024-02-06 | Hunters Mountain 1 - Hunters Mountain Road Solar | Generator notification from Eversource Energy on behalf of Hunters Mountain 1 for the installation of 4.125 MW Solar PV in Naugatuck, CT and interconnecting to Hunters Mountain Road, Naugatuck, CT via the 21L3 circuit out of South Naugatuck substation. | 2024-07-31 | Notification | 2024-03-21
ES-24-G47 | 2024-02-29 | Mountain Laurel Farm Solar Pasture Garden LLC - 11 Village Corner Road Solar | Generator notification from Eversource Energy on behalf of Mountain Laurel Farm Solar Pasture Garden, LLC for the installation of 4.0 MW Solar PV in Wolfeboro, NH and interconnecting to 11 Village Corner Road, Wolfeboro, NH via the 346 circuit out of White Lake substation. | 2025-02-28 | Notification | 2024-03-21
RIE-24-G04 | 2024-03-05 | Ameresco Inc. - 300 Jenckes Hill Road Solar | Generator notification from Rhode Island Energy on behalf of Ameresco Inc. for the installation of 3.234 MW Solar PV in Smithfield, RI and interconnecting to 300 Jenckes Hill Road, Smithfield, RI via the 126W42 circuit out of Washington substation. | 2025-06-01 | Notification | 2024-03-21
RIE-24-G01 | 2024-03-05 | Revity Energy - 189 Weaver-Hill Road Solar | Generator notification from Rhode Island Energy on behalf of Revity Energy for the installation of 9.1 MW Solar PV in West Greenwich, RI and interconnecting to 189 Weaver-Hill Road, West Greenwich, RI via the 3310 circuit out of Kent County substation. | 2025-03-31 | Notification | 2024-03-21
HMLD-24-G01 | 2024-03-08 | Holden BESS 1 LLC - 21 Adams Road Battery | Generator notification from Holden Municipal Light Department on behalf of Holden BESS 1 LLC for the installation of a 4.99 MW/22.36 MWh Battery in Holden, MA and interconnecting to 21 Adams Road, Holden, MA via feeder 7 out of Chaffins substation. | 2024-07-27 | Notification | 2024-03-21
GELD-24-G01 | 2024-03-07 | Groton BESS 1 LLV - 440 Lowell Road Battery | Generator notification from Groton Electric Light Department on behalf of Groton BESS 1 LLC for the installation of a 2.0 MW/8.92 MWh Battery in Groton, MA and interconnecting to 440 Lowell Road, Groton, MA via feeder 5 out of Lowell Road substation. | 2024-07-06 | Notification | 2024-03-21
GELD-24-G02 | 2024-03-07 | Groton BESS 2 LLV - 342 Main Street Battery | Generator notification from Groton Electric Light Department on behalf of Groton BESS 2 LLC for the installation of a 2.0 MW/8.92 MWh Battery in Groton, MA and interconnecting to 342 Main Street, Groton, MA via feeder 6 out of Lowell Road substation. | 2024-08-12 | Notification | 2024-03-21
NEP-20-GNF29 Rev.3 | 2024-03-05 | BlueWave Solar, LLC - 903 Tremont Street Solar and Battery | Generation notification from New England Power on behalf of BlueWave Solar, LLC for the installation of a 2.0 MW Solar PV and 2.7 MW/8.1 MWh DC Coupled Battery in North Dighton, MA and interconnecting to 903 Tremont Street, North Dighton, MA via the 19W74 circuit out of Dighton substation | 2026-03-03 | Notification | 2024-03-21
NEP-24-GNF09 | 2024-03-06 | Northeast Energy Center, LLC - 304 Southbridge Road Natural Gas | Generation notification from New England Power on behalf of Northeast Energy Center, LLC for the installation of 4.0 MW Natural Gas in Charlton, MA and interconnecting to 304 Southbridge Road, Charlton, MA via the 413L4 circuit out of Snow Street substation. | 2025-03-01 | Notification | 2024-03-21
ES-24-T03 | 2024-02-09 | Partial Rebuild of Line 1000-1 | Transmission notification from Eversource Energy for the partial rebuild of Line 1000-1 replacing 1.2-miles of existing structures and associated 556-kcmil ACSR conductor with 1590-kcmil ACSS conductor. | 2025-12-31 | Notification | 2024-03-21
ES-24-T04 | 2024-02-09 | Partial Rebuild of Line 1090 | Transmission notification from Eversource Energy for the partial rebuild of Line 1090 replacing 1.2-miles of existing structures and associated 556-kcmil ACSR conductor with 1590-kcmil ACSS conductor. | 2025-12-31 | Notification | 2024-03-21
ES-24-T11 | 2024-03-05 | Replacement of Falls Village 5X Transformer | Transmission notification from Eversource Energy for the replacement of the existing 5X transformer at Falls Village substation with new transformer that has both 115 kV and 69 kV transmission taps, with initial operation at 69 kV. | 2026-12-31 | Notification | 2024-03-21
ES-24-T12 | 2024-03-05 | Replacement of Franklin Drive 4X Transformer | Transmission notification from Eversource Energy for the replacement of the 4X transformer at Franklin Drive substation with a new transformer. | 2025-12-31 | Notification | 2024-03-21
ES-24-T13 | 2024-03-05 | Replacement of Franklin Drive 5X Transformer | Transmission notification from Eversource Energy for the replacement of the 5X transformer at Franklin Drive substation with a new transformer. | 2025-12-31 | Notification | 2024-03-21
CMP-24-G14 | 2024-01-30 | Central Maine Power Affected System Operator (ASO) Study Louden-Biddeford-Portland Area Distributed Energy Resource (DER) Project - DG Maine CS LLC - 1069 Long Plains Road Solar | Generation application from Central Maine Power on behalf of DG Maine CS LLC for the installation of a 4.5 MW Solar PV facility in Buxton, ME and interconnecting to the Bar Mills substation via the 678D2 circuit. | 2024-06-30 | Approved Withdrawn | 2/22/2024 1/22/2025
CMP-24-G15 | 2024-01-30 | Central Maine Power Affected System Operator (ASO) Study Louden-Biddeford-Portland Area Distributed Energy Resource (DER) Project - BD Solar Biddeford - Drew Mills Road Solar | Generation application from Central Maine Power on behalf of BD Solar Biddeford LLC for the installation of a 4.969 MW Solar PV facility in Biddeford, ME and interconnecting to the May Street Side substation via the 634D1 circuit. | 2024-06-30 | Approved | 2024-02-22
CMP-24-G16 | 2024-01-30 | Central Maine Power Affected System Operator (ASO) Study Louden-Biddeford-Portland Area Distributed Energy Resource (DER) Project - 510 PV Project Development LLC - 720 US Route 1 Solar | Generation application from Central Maine Power on behalf of 510 PV Project Development LLC for the installation of a 1.99 MW Solar PV facility in Scarborough, ME and interconnecting to the Dunstan substation via the 617D2 circuit. | 2025-07-15 | Approved | 2024-02-22
CMP-24-G17 | 2024-01-30 | Central Maine Power Affected System Operator (ASO) Study Louden-Biddeford-Portland Area Distributed Energy Resource (DER) Project - Barrens Solar Partners LLC - 1 Green Road Solar | Generation application from Central Maine Power on behalf of Barrens Solar Partners LLC for the installation of a 4.979 MW Solar PV facility in Scarborough, ME and interconnecting to the Scarborough substation via the 693D1 circuit. | 2024-10-31 | Approved Withdrawn | 2/22/2024 3/18/2025
CMP-24-G18 | 2024-01-30 | Central Maine Power Affected System Operator (ASO) Study Louden-Biddeford-Portland Area Distributed Energy Resource (DER) Project - Rte 1 Freeport Solar LLC | Generation application from Central Maine Power on behalf of Rte 1 Freeport Solar LLC for the installation of a 4.973 MW Solar PV facility in Freeport, ME and interconnecting to the Freeport substation via the 225D4 circuit. | 2024-12-31 | Approved | 2024-02-22
CMP-24-G19 | 2024-01-30 | Central Maine Power Affected System Operator (ASO) Study Louden-Biddeford-Portland Area Distributed Energy Resource (DER) Project - ME White Plains Solar LLC - Lunt Drive Solar | Generation application from Central Maine Power on behalf of ME White Plains Solar LLC for the installation of a 1.25 MW Solar PV facility in Westbrook, ME and interconnecting to the Prides Corner substation via the 647D1 circuit. | 2024-12-31 | Approved Withdrawn | 2/22/2024 1/22/2025
CMP-24-G20 | 2024-01-30 | Central Maine Power Affected System Operator (ASO) Study Louden-Biddeford-Portland Area Distributed Energy Resource (DER) Project - C2 Energy Development LLC - 98 Eleanor Avenue Solar | Generation application from Central Maine Power on behalf of C2 Energy Development LLC for the installation of a 1.995 MW Solar PV facility in Westbrook, ME and interconnecting to the Westbrook substation via the 674D2 circuit. | 2024-09-30 | Approved Withdrawn | 2/22/2024 1/22/2025
CMP-24-G21 | 2024-01-30 | Central Maine Power Affected System Operator (ASO) Study Louden-Biddeford-Portland Area Distributed Energy Resource (DER) Project - Dichotomy Power LLC - 95 Olde Canal Way Hydro | Generation application from Central Maine Power on behalf of Dichotomy Power LLC for the installation of a 3.99 MW Hydro facility in Gorham, ME and interconnecting to the Moshers substation via the 635D2 circuit. | 2024-09-30 | Approved | 2024-02-22
ES-24-G19 | 2024-01-22 | Michaud Law Group LLC, New Haven Road Solar | Generation notification from Eversource on behalf of Michaud Law Group LLC for the installation of 2.999 MW Solar PV in Prospect, CT and interconnecting to New Haven Road, Prospect, CT via the 13F65 circuit out of Baldwin substation. | 2025-04-01 | Notification | 2024-02-22
ES-24-G20 | 2024-01-22 | Michaud Law Group LLC, Oronoke Road Solar | Generation notification from Eversource on behalf of Michaud Law Group LLC for the installation of 4.125 MW Solar PV in Waterbury, CT and interconnecting to Oronoke Road, Waterbury, CT via the 12B35 circuit out of Bunker Hill substation. | 2024-12-31 | Notification | 2024-02-22
ES-24-G01 | 2024-01-17 | Con Edison Development, 1 Vibert Road Battery | Generation notification from Eversource on behalf of Con Edison Development for the installation of a 1.285 MW/2.57 MWh Battery in South Windsor, CT and interconnecting to 1 Vibert Road, South Windsor, CT via the 14L5 circuit out of South Windsor substation. | 2024-06-17 | Notification | 2024-02-22
NEP-24-GNF05 | 2024-01-22 | Onsite Renewables, LLC, 30 L P Henderson Road Battery | Generation notification from New England Power on behalf of Onsite Renewables, LLC for the installation of a 4.9992 MW/18.432 MW Battery in Beverly, MA and interconnecting to 30 L P Henderson Road, Beverly, MA via the 18L1 circuit out of Beverly substation. | 2026-01-15 | Notification Withdrawn | 2/22/2024 9/17/2024
NEP-24-GNF06 | 2024-01-21 | Next Grid, Inc. - 80 Colon Street Battery | Generation notification from New England Power on behalf of Next Grid, Inc. for the installation of a 4.9992 MW/18.432 MW Battery in Beverly, MA and interconnecting to 80 Colon Street, Beverly, MA via the 51L2 circuit out of East Beverly substation. | 2026-01-15 | Notification Withdrawn | 2/22/2024 10/22/2024
NEP-24-GNF07 | 2024-01-26 | Onsite Renewables, LLC - 2022 Bridge Street Battery | Generation notification from New England Power on behalf of Onsite Renewables, LLC for the installation of a 4.9992 MW/18.432 MW Battery in Dracut, MA and interconnecting to 2022 Bridge Street, Dracut, MA via the 78L3 circuit out of North Dracut substation. | 2026-02-15 | Notification Withdrawn | 2/22/2024 9/17/2024
NEP-24-GNF08 | 2024-01-26 | Onsite Renewables, LLC - 334 Clark Street Battery | Generation notification from New England Power on behalf of Onsite Renewables, LLC for the installation of a 4.9992 MW/18.432 MW Battery in North Andover, MA and interconnecting to 334 Clark Street, North Andover, MA via the 56L2 circuit out of Woodchuck Hill substation. | 2026-02-15 | Notification | 2024-02-22
ES-17-G16 Rev.1 | 2024-01-08 | Hadley III Solar, LLC - 379 Russel Street Solar and Battery | Generation notification from Eversource on behalf of Hadley III Solar, LLC for the installation of 3.871 MW Solar PV and 2.0 MW/4.416 MWh AC Coupled Battery in Hadley, MA and interconnecting to 379 Russel Street, Hadley, MA via the 17K6 circuit out of Amherst substation. | 2024-03-01 | Notification | 2024-02-22
NEP-19-GNF37 Rev.3 | 2024-01-21 | Nexamp Solar, LLC - 60 Spring Street Solar and Battery | Generation notification from New England Power on behalf of Nexamp Solar, LLC for the installation of a 4.99 MW Solar PV and 3.0/6.0 MW DC Coupled Battery in Franklin, MA and interconnecting to 60 Spring Street, Franklin, MA via the 344W5 circuit out of Beaver Pond substation. | 2024-02-29 | Notification | 2024-02-22
NEP-21-G04 Rev.1 | 2024-01-25 | Next Grid - 5 Berry Street Solar and Battery | Generation notification from New England Power on behalf of Next Grid for the installation of a 4.107 MW Solar PV and 3.0/7.5 MWh DC Coupled Battery in Plainville, MA and interconnecting to 5 Berry Street, Plainville, MA via the 3451W3 circuit out of Plainville substation. | 2024-06-01 | Notification | 2024-02-22
RIE-24-T01 | 2024-01-19 | T-172N Woonsocket-Hartford Ave-West Farnum 115 kV Line Reconductoring | Transmission notification from Rhode Island Energy for the replacement of remaining wood poles with steel monopoles, replacement of existing hardware and insulators, and reconductoring of 1.3 miles of existing 1590 ACSR with 1590 ACSS between West Farnum and Woonsocket. | 2024-12-31 | Notification | 2024-02-14
RIE-24-T02 | 2024-01-19 | S-171N Woonsocket-Hartford Ave-West Farnum 115 kV Line Reconductoring | Transmission notification from Rhode Island Energy for the replacement of remaining wood poles with steel monopoles, replacement of existing hardware and insulators, and reconductoring of 1.3 miles of existing 1590 ACSR with 1590 ACSS between West Farnum and Woonsocket. | 2024-12-31 | Notification | 2024-02-14
RIE-24-T03 | 2024-01-19 | M13 Dexter-Border and EMI Tiverton-Tiverton Power 115 kV Line Rebuild | Transmission notification from Rhode Island Energy for the rebuild of approximately 9.2 miles of the M13 line with 1113 ACSS. | 2025-12-31 | Notification | 2024-02-14
RIE-24-T04 | 2024-01-19 | L14 Dexter-Border and EMI Tiverton-Tiverton Power 115 kV Line Rebuild | Transmission notification from Rhode Island Energy for the rebuild of approximately 9.2 miles of the L14 line with 1113 ACSS. | 2025-12-31 | Notification | 2024-02-14
NEP-24-T01 | 2024-01-30 | Bridgewater T161 Replacement | Transmission notification from New England Power for the replacement of the existing step-down 345/115 kV T161 transformer at the Bridgewater substation. | 2026-12-31 | Notification | 2024-02-14
ES-24-T02 | 2024-01-30 | U199 Line Rebuild | Transmission notification from Eversource for the replacement of 115 kV line U199 between the Littleton substation and Streeter Pond Tap in NH with 1272 ACSS conductor. | 2026-06-30 | Notification | 2024-02-14
SENA-21-T01 Rev.1 | 2024-01-02 | Queue Position 837 (QP 837) ETU Revision and Queue Position 1116 (QP 1116) Offshore Wind Project | Transmission application from Shell Energy North America on behalf of SouthCoast Wind LLC for the installation of a +/-320 kV 1,265 MVA Voltage Source Converter (VSC) HVDC system. | 2027-11-30 | Approved | 2024-01-29
SENA-21-T02 Rev.1 | 2024-01-02 | Queue Position 837 (QP 837) ETU Revision and Queue Position 1116 (QP 1116) Offshore Wind Project | Transmission application from Shell Energy North America on behalf of SouthCoast Wind LLC for the installation of a 0.47-mile 345 kV HVAC interconnection cable. | 2027-11-30 | Approved | 2024-01-29
NEP-21-T08 Rev.1 | 2024-01-02 | Queue Position 837 (QP 837) ETU Revision and Queue Position 1116 (QP 1116) Offshore Wind Project | Transmission application from New England Power to reconductor the E-183E and F-184S 115 kV lines from Brayton Point substation to Grand Army substation using 1113 ACSR conductor, upgrade switches and breakers, and replace bus 1 and associated conductors. | 2027-11-30 | Approved | 2024-01-29
NEP-21-T09 Rev.1 | 2024-01-02 | Queue Position 837 (QP 837) ETU Revision and Queue Position 1116 (QP 1116) Offshore Wind Project | Transmission application from New England Power to expand the 345 kV GIS substation to a three-bay breaker-and-a-half configuration and replace the two 115 kV breakers. | 2027-11-30 | Approved | 2024-01-29
SENA-23-G01 | 2024-01-02 | Queue Position 837 (QP 837) ETU Revision and Queue Position 1116 (QP 1116) Offshore Wind Project | Generation application from Shell Energy North America on behalf of SouthCoast Wind LLC for the installation of ninety 14.7 MVA (1,200 MW net) wind turbine generators and interconnecting to the Brayton Point 345 kV substation via an ETU (QP 837). | 2027-11-30 | Approved | 2024-01-29
ES-24-T01 | 2024-01-02 | Queue Position 837 (QP 837) ETU Revision and Queue Position 1116 (QP 1116) Offshore Wind Project | Transmission application from Eversource Energy to upgrade two breakers at the West Medway 345 kV substation. | 2027-11-30 | Approved | 2024-01-29
ES-24-G12 | 2023-12-20 | LSE Sagitta LLC - 290 West Hill Road Solar | Generator notification from Eversource Energy on behalf of LSE Sagitta LLC for the installation of 2.988 MW Solar PV in Torrington, CT and interconnecting to 290 West Hill Road, Torrington, CT via the SR5 circuit out of Canton substation. | 2024-08-31 | Notification | 2024-01-29
ES-24-G13 | 2023-12-21 | Greenskies Clean Energy, LLC, Fawn Meadow Lane Solar | Generator notification from Eversource Energy on behalf of Greenskies Clean Energy, LLC for the installation of 4.999 MW Solar PV in Woodbury, CT and interconnecting to Fawn Meadow Lane, Woodbury, CT via the 11S14 circuit out of Carmel Hill substation. | 2026-06-01 | Notification | 2024-01-29
RIE-24-GNF01 | 2024-01-05 | Econox Renewables - 1330 West Main Road Solar | Generator notification from Eversource Energy on behalf of Econox Renewables for the installation of 2.475 MW Solar PV in Portsmouth, RI and interconnecting to 1330 West Main Road, Portsmouth, RI via the 37W2 circuit out of Jepson substation. | 2024-12-02 | Notification | 2024-01-29
RIE-24-GNF02 | 2024-01-05 | Econox Renewables - 274 West Main Road Solar | Generator notification from Eversource Energy on behalf of Econox Renewables for the installation of 2.475 MW Solar PV in Portsmouth, RI and interconnecting to 274 West Main Road, Portsmouth, RI via the 37W2 circuit out of Jepson substation. | 2024-12-02 | Notification | 2024-01-29
RIE-24-GNF03 | 2024-01-05 | ECA Solar - Strawberry Field Road Solad | Generator notification from Eversource Energy on behalf of ECA Solar for the installation of 3.8 MW Solar PV in Portsmouth, RI and interconnecting to Strawberry Field Road, Warwick, RI via the 2222 circuit out of Drumrock substation. | 2024-12-02 | Notification | 2024-01-29
NEP-23-GNF10 | 2023-12-07 | Onsite Renewables, LLC - 118 Tewksbury Street Battery | Generator notification from New England Power on behalf of Onsite Renewables, LLC for the installation of a 4.9992 MW/18.432 MWh Battery in Andover, MA and interconnecting to 118 Tewksbury Street, Andover, MA via the 59L6 circuit out of East Tewksbury substation. | 2025-12-01 | Notification Withdrawn | 1/29/2024 1/22/2025
NEP-23-GNF11 | 2023-12-07 | Onsite Renewables, LLC - 23 Middlesex Road Battery | Generator notification from New England Power on behalf of Onsite Renewables, LLC for the installation of a 3.499 MW/13.824 MWh Battery in Tyngsboro, MA and interconnecting to 23 Middlesex Road, Tyngsboro, MA via the 2399 circuit out of North Chelmsford substation. | 2025-12-01 | Notification Withdrawn | 1/29/2024 9/17/2024
NEP-23-GNF12 | 2023-12-07 | Onsite Renewables, LLC - 616 Middlesex Turnpike Battery | Generator notification from New England Power on behalf of Onsite Renewables, LLC for the installation of a 4.9992 MW/18.432 MWh Battery in Billerica, MA and interconnecting to 616 Middlesex Turnpike, Billerica, MA via the 18L1 circuit out of South Billerica substation. | 2025-12-01 | Notification Withdrawn | 1/29/2024 9/17/2024
ES-24-G11 | 2023-12-14 | Bluewave Storage Origination, LLC - 973 Middlesex Turnpike Battery | Generator notification from Eversource Energy on behalf of Bluewave Storage Origination, LLC for the installation of a 4.99 MW/19.96 MWh Battery in Old Saybrook, CT and interconnecting to 973 Middlesex Turnpike, Old Saybrook, CT via the 15L12 circuit out of Bokum substation. | 2024-06-01 | Notification | 2024-01-29
NEP-24-GNF03 | 2023-12-20 | Onsite Renewables, LLC - 120 Mulberry Street Battery | Generator notification from New England Power on behalf of Onsite Renewables, LLC for the installation of a 4.9992 MW/18.432 MWh Battery in Brockton, MA and interconnecting to 120 Mulberry Street, Brockton, MA via the 911W57 circuit out of Ames substation. | 2025-12-01 | Notification Withdrawn | 1/29/2024 9/17/2024
NEP-24-GNF04 | 2023-12-21 | Onsite Renewables, LLC - 178 Highland Street Battery | Generator notification from New England Power on behalf of Onsite Renewables, LLC for the installation of a 4.9992 MW/18.432 MWh Battery in Brockton, MA and interconnecting to 178 Highland Street, Brockton, MA via the 911W13 circuit out of Ames substation. | 2025-12-01 | Notification Withdrawn | 1/29/2024 9/17/2024
ES-21-G85 Rev.1 | 2023-12-14 | Catalyze Holdings, LLC - 540R Main Street Solar and Battery | Generator notification from Eversource Energy on behalf of Catalyze Holdings, LLC for the installation of 2.66 MW Solar PV and 2.5 MW/10.0 MWh DC Coupled Battery in Acushnet, MA and interconnecting to 540R Main Street, Acushnet, MA via the 2-241-241 circuit out of Wing Lane substation. | 2026-12-01 | Notification | 2024-01-29
NEP-24-GNF01 | 2023-12-20 | Progeneration Energy - 152 Stedman Street Solar and Battery | Generator notification from New England Power on behalf of Progeneration Energy for the installation of 2.999 MW Solar PV and 2.0 MW/4.18 MWh AC Coupled Battery in Chelmsford, MA and interconnecting to 152 Stedman Street, Chelmsford, MA via the 16L4 circuit out of Meadowbrook substation. | 2025-12-01 | Notification | 2024-01-29
NEP-24-GNF02 | 2023-12-20 | Anawan Solar, LLC - 223 Winthrop Street Solar and Battery | Generator notification from New England Power on behalf of Anawan Solar, LLC for the installation of 0.938 MW Solar PV and 1.0 MW/3.0 MWh AC Coupled Battery in Rehoboth, MA and interconnecting to 233 Winthrop Street, Rehoboth, MA via the 7L4 circuit out of Mink Street substation. | 2025-12-01 | Notification | 2024-01-29
NEP-23-T10 | 2023-11-20 | Tewksbury #22 Transformer T3 Replacement Project | Transmission application from New England Power for the replacement of the existing 230/115/13.8 kV 3-13.8/18.4/23 MVA transformer T3 with a 230/115 kV 200/266.7/333 MVA transformer. | 2026-06-01 | Approved | 2023-12-19
NEP-23-T12 | 2023-12-04 | Prysmian Supply Tap From Brayton Point 115 kV Bus Project | Transmission application from New England Power to tap the Brayton Point 115 kV bus 1 to service Prysmian’s 115/13.8 kV substation by installing a 115 kV breaker and 115 kV, 1,200-foot underground cable. | 2025-11-30 | Approved Withdrawn | 12/19/2023 3/18/2025
NEP-23-G03 | 2023-12-04 | New England Power Affected System Operator (ASO) Study Hopedale West Distributed Energy Resource (DER) Project - BlueWave - 101 Blackstone Street Battery | Generator application from New England Power on behalf of BlueWave for the installation of a 4.99 MW/20.0 MWh Battery facility in Mendon, MA and interconnecting to Uxbridge substation via the 321W6 circuit. | 2025-12-01 | Approved Withdrawn | 12/21/2023 9/17/2024
NEP-23-G04 | 2023-12-04 | New England Power Affected System Operator (ASO) Study Hopedale West Distributed Energy Resource (DER) Project - Valta Energy - 140 Depot Street Solar and Battery | Generator application from New England Power on behalf of Valta Energy for the installation of a 1.5 MW PV and 0.528 MW/1.112 MWh AC Coupled Battery facility in Bellingham, MA and interconnecting to Depot Street substation via the 335W1 circuit. | 2025-12-01 | Approved Withdrawn | 12/21/2023 4/16/2025
NEP-23-G05 | 2023-12-04 | New England Power Affected System Operator (ASO) Study Hopedale West Distributed Energy Resource (DER) Project - Zero Point Development - 374 Hazel Street Battery | Generator application from New England Power on behalf of Zero Point Development for the installation of a 4.948 MW/20.0 MWh Battery facility in Uxbridge, MA and interconnecting to Whitins Pond substation via the 320W4 circuit. | 2025-12-01 | Approved | 2023-12-21
NEP-23-G06 | 2023-12-04 | New England Power Affected System Operator (ASO) Study Hopedale West Distributed Energy Resource (DER) Project - Zero Pond Development - 211 Whitins Road Battery | Generator application from New England Power on behalf of Zero Pond Development for the installation of a 4.948 MW/20.0 MWh Battery facility in Sutton, MA and interconnecting to Whitins Pond substation via the 320W5 circuit. | 2025-12-01 | Approved Withdrawn | 12/21/2023 9/17/2024
NEP-23-G07 | 2023-12-04 | New England Power Affected System Operator (ASO) Study Hopedale West Distributed Energy Resource (DER) Project - Zero Point Development - 404 Blackstone Street Battery | Generator application from New England Power on behalf of Zero Point Development for the installation of a 9.992 MW/40.0 MWh Battery facility in Uxbridge, MA and interconnecting to Uxbridge substation via the 321W6 circuit. | 2025-12-01 | Approved | 2023-12-21
CMP-23-G81 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Midcoast Area Distributed Energy Resource (DER) Project - Syncarpha Solar, LLC - Ridge Road Solar | Generator application from Central Maine Power on behalf of Syncarpha Solar, LLC for the installation of a 4.95 MW PV facility in Windsor, ME and interconnecting to Coopers Mills Road substation via the 230D1 circuit. | 2024-12-30 | Approved Withdrawn | 12/21/2023 1/22/2025
CMP-23-G82 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Midcoast Area Distributed Energy Resource (DER) Project - Damariscotta Solar 1 - US Route 1 Solar | Generator application from Central Maine Power on behalf of Damariscotta Solar 1, LLC for the installation of a 4.95 MW PV facility in Damariscotta, ME and interconnecting to Damariscotta Mills substation via the 219D1 circuit. | 2024-12-30 | Approved | 2023-12-21
CMP-23-G83 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Midcoast Area Distributed Energy Resource (DER) Project - South Thomaston PV LLC - 662 St. George Road Solar | Generator application from Central Maine Power on behalf of South Thomaston PV, LLC for the installation of a 1.998 MW PV facility in South Thomaston, ME and interconnecting to Thomaston Creek substation via the 246D1 circuit. | 2024-11-30 | Approved Withdrawn | 12/21/2023 1/22/2025
CMP-23-G84 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Midcoast Area Distributed Energy Resource (DER) Project - C2 Bristol 1, LLC - 0 Kelly Street Solar | Generator application from Central Maine Power on behalf of C2 Bristol 1, LLC for the installation of a 3.43 MW PV facility in Bristol, ME and interconnecting to Bristol substation via the 210D2 circuit. | 2024-12-31 | Approved | 2023-12-21
CMP-23-G85 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Midcoast Area Distributed Energy Resource (DER) Project - TPE Development, LLC - Old Portland Road Solar | Generator application from Central Maine Power on behalf of TPE Development, LLC for the installation of a 4.9251 MW PV facility in Brunswick, ME and interconnecting to Topsham Old substation via the 249D1 circuit. | 2024-12-31 | Approved Withdrawn | 12/21/2023 6/18/2024
CMP-23-G86 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Midcoast Area Distributed Energy Resource (DER) Project - C2 Bristol 11, LLC - 1829 Bristol Road Solar | Generator application from Central Maine Power on behalf of C2 Bristol 11, LLC for the installation of a 1.997 MW PV facility in Bristol, ME and interconnecting to Bristol substation via the 210D1 circuit. | 2024-08-30 | Approved | 2023-12-21
CMP-23-G87 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Midcoast Area Distributed Energy Resource (DER) Project - Topsham PV, LLC - Lovers Lane Solar | Generator application from Central Maine Power on behalf of Topsham PV, LLC for the installation of a 4.95 MW PV facility in Topsham, ME and interconnecting to Topsham Old substation via the 249D1 circuit. | 2024-11-30 | Approved Withdrawn | 12/21/2023 1/22/2025
CMP-23-G88 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Midcoast Area Distributed Energy Resource (DER) Project - Alna Community Solar, LLC - 1077 Alna Road Solar | Generator application from Central Maine Power on behalf of Alna Comunity Solar, LLC for the installation of a 2.875 MW PV facility in Alna, ME and interconnecting to Sheepscot substation via the 241D1 circuit. | 2024-03-01 | Approved | 2023-12-21
CMP-23-G89 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Midcoast Area Distributed Energy Resource (DER) Project - Wiscasset Gardiner Solar, LLC - 394 Gardiner Road Solar | Generator application from Central Maine Power on behalf of Wiscasset Gardiner Solar, LLC for the installation of a 1.75 MW MW PV facility in Wiscasset, ME and interconnecting to Messina substation via the 238D1 circuit. | 2024-03-01 | Approved Withdrawn | 12/21/2023 6/18/2024
CMP-23-G90 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Midcoast Area Distributed Energy Resource (DER) Project - Lincolnville PV, LLC - 51 Slab City Road Solar | Generator application from Central Maine Power on behalf of Lincolnville PV, LLC for the installation of a 1.998 MW PV facility in Lincolnville, ME and interconnecting to Lincolnville substation via the 800D1 circuit. | 2024-11-30 | Approved Withdrawn | 12/21/2023 1/22/2025
CMP-23-G91 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Midcoast Area Distributed Energy Resource (DER) Project - West Bath Tonal Solar, LLC - Tonal Lane Solar | Generator application from Central Maine Power on behalf of West Bath Tonal Solar, LLC for the installation of a 1.975 MW PV facility in West Bath, ME and interconnecting to Bath 34 substation via the 261D3 circuit. | 2024-03-01 | Approved Withdrawn | 12/21/2023 1/22/2025
CMP-23-G92 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Midcoast Area Distributed Energy Resource (DER) Project - Newcastle Route One Solar, LLC - Route 1 Solar | Generator application from Central Maine Power on behalf of Newcastle Route One Solar, LLC for the installation of a 1.9414 MW PV facility in Newcastle, ME and interconnecting to Damariscotta Mills substation via the 219D2 circuit. | 2024-03-01 | Approved Withdrawn | 12/21/2023 6/18/2024
CMP-23-G26 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Raymond Area Distributed Energy Resource (DER) Project - HEP Energy USA Project Development LLC - Wescott Road Solar | Generator application from Central Maine Power on behalf of HEP Energy USA Project Development LLC for the installation of a 4.87 MW PV facility in Gorham, ME and interconnecting to Fort Hill substation via the 624D2 circuit. | 2024-12-30 | Approved Withdrawn | 12/21/2023 2/15/2025
CMP-23-G27 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Raymond Area Distributed Energy Resource (DER) Project - 510 PV Project Development LLC - 464 Roosevelt Trail Solar | Generator application from Central Maine Power on behalf of 510 PV Project Development LLC for the installation of a 4.96 MW PV facility in Windham, ME and interconnecting to Swett Road substation via the 682D2 circuit. | 2024-12-31 | Approved | 2023-12-21
CMP-23-G28 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Raymond Area Distributed Energy Resource (DER) Project - ISM Solar Croocked River LLC - River Road Solar | Generator application from Central Maine Power on behalf of ISM Solar Croocked River LLC for the installation of a 4.999 MW PV facility in Naples, ME and interconnecting to Raymond substation via the 445D2 circuit. | 2024-12-31 | Approved Withdrawn | 12/21/2023 7/16/2024
CMP-23-G30 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Raymond Area Distributed Energy Resource (DER) Project - BWC Brandy Pond LLC - 281 Harrison Road Solar | Generator application from Central Maine Power on behalf of BWC Brandy Pond LLC for the installation of a 3.474 MW PV facility in Naples, ME and interconnecting to Naples Tap substation via the 469D1 circuit. | 2024-10-01 | Approved Withdrawn | 12/21/2023 2/15/2025
CMP-23-G31 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Raymond Area Distributed Energy Resource (DER) Project - Sabago Solar LLC - 91 Pipeline Road Solar | Generator application from Central Maine Power on behalf of Sabago Solar LLC for the installation of a 4.482 MW PV facility in Raymond, ME and interconnecting to Raymond substation via the 444D3 circuit. | 2024-10-31 | Approved Withdrawn | 12/21/2023 7/16/2024
CMP-23-G32 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Raymond Area Distributed Energy Resource (DER) Project - Casco A LLC - Roosevelt Trail Solar | Generator application from Central Maine Power on behalf of Casco A LLC for the installation of a 4.777 MW PV facility in Casco, ME and interconnecting to Sand Road Tap substation via the 470D1 circuit. | 2025-06-01 | Approved Withdrawn | 12/21/2023 2/15/2025
CMP-23-G33 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Raymond Area Distributed Energy Resource (DER) Project - Naples Roosevelt Trail Solar 1 LLC - Roosevelt Trail Solar | Generator application from Central Maine Power on behalf of Naples Roosevelt Trail Solar 1 LLC for the installation of a 2.4 MW PV facility in Naples, ME and interconnecting to Naples Tap substation via the 469D1 circuit. | 2024-12-01 | Approved Withdrawn | 12/21/2023 7/16/2024
CMP-23-G35 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Raymond Area Distributed Energy Resource (DER) Project - Casco PV LLC - 612 Meadow Road Solar | Generator application from Central Maine Power on behalf of Casco PV LLC for the installation of a 4.95 MW PV facility in Casco, ME and interconnecting to Raymond substation via the 445D2 circuit. | 2024-09-01 | Approved Withdrawn | 12/21/2023 7/16/2024
CMP-23-G36 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Raymond Area Distributed Energy Resource (DER) Project - BWC Lake Floria LLC - Damon Road Solar | Generator application from Central Maine Power on behalf of BWC Lake Floria LLC for the installation of a 4.99 MW PV facility in Raymond, ME and interconnecting to Raymond substation via the 445D1 circuit. | 2024-10-01 | Approved | 2023-12-21
CMP-23-G37 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Raymond Area Distributed Energy Resource (DER) Project - Maine White Pine Solar LLC - 9 Webb Road Solar | Generator application from Central Maine Power on behalf of Maine White Pine Solar LLC for the installation of a 1.995 MW PV facility in Windham, ME and interconnecting to Swett Road substation via the 682D1 circuit. | 2024-12-31 | Approved Withdrawn | 12/21/2023 7/16/2024
CMP-23-G38 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Raymond Area Distributed Energy Resource (DER) Project - Orchard Road Solar LLC - 3 Orchard Road Solar | Generator application from Central Maine Power on behalf of Orchard Road Solar LLC for the installation of a 1.999 MW PV facility in Standish, ME and interconnecting to Shaw Mills substation via the 660D2 circuit. | 2024-09-01 | Approved Withdrawn | 12/21/2023 2/15/2025
CMP-23-G74 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Sturtevant-Leeds-Livermore-Ludden-Riley Area Distributed Energy Resource (DER) Project - Leeds Route 106 Solar, LLC - 1053 Route 106 Solar | Generator application from Central Maine Power on behalf of Leeds Route 106 Solar, LLC for the installation of a 4.999 MW PV facility in Leeds, ME and interconnecting to Leeds substation via the 471D2 circuit. | 2024-09-01 | Approved | 2023-12-21
CMP-23-G75 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Sturtevant-Leeds-Livermore-Ludden-Riley Area Distributed Energy Resource (DER) Project - Clearwater Solar Partners, LLC - 414 Farmington Fall Road Solar | Generator application from Central Maine Power on behalf of Clearwater Solar Partners, LLC for the installation of a 4.99 MW PV facility in Farmington, ME and interconnecting to Sturtevant substation via the 858D1A circuit. | 2024-09-01 | Approved Withdrawn | 12/21/2023 3/18/2025
CMP-23-G76 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Sturtevant-Leeds-Livermore-Ludden-Riley Area Distributed Energy Resource (DER) Project - USS Maple Solar, LLC - Weld Road Solar | Generator application from Central Maine Power on behalf of USS Maple Solar, LLC for the installation of a 4.995 MW PV facility in Wilton, ME and interconnecting to Wilton substation via the 885D1 circuit. | 2024-12-31 | Approved Withdrawn | 12/21/2023 1/22/2025
CMP-23-G77 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Sturtevant-Leeds-Livermore-Ludden-Riley Area Distributed Energy Resource (DER) Project - Swan River Solar, LLC - 1312 Canton Point Road Solar | Generator application from Central Maine Power on behalf of Swan River Solar, LLC for the installation of a 1.999 MW PV facility in Dixfield, ME and interconnecting to Ludden Lane substation via the 461D1 circuit. | 2024-06-01 | Approved | 2023-12-21
CMP-23-G78 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Sturtevant-Leeds-Livermore-Ludden-Riley Area Distributed Energy Resource (DER) Project - NexGrid Huisache, LLC - 25 Strong Road Solar | Generator application from Central Maine Power on behalf of NexGrid Huisache, LLC for the installation of a 1.25 MW PV facility in Strong, ME and interconnecting to Phillips/Strong substation via the 841D1 circuit. | 2024-12-15 | Approved Withdrawn | 12/21/2023 1/22/2025
CMP-23-G79 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Sturtevant-Leeds-Livermore-Ludden-Riley Area Distributed Energy Resource (DER) Project - Wilton Route 2 Solar, LLC - Route 2 Solar | Generator application from Central Maine Power on behalf of Wilton Route 2 Solar, LLC for the installation of a 1.75 MW PV facility in Wilton, ME and interconnecting to East Wilton substation via the 816D1 circuit. | 2024-06-01 | Approved Withdrawn | 12/21/2023 1/22/2025
CMP-23-T20 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Sturtevant-Leeds-Livermore-Ludden-Riley Area Maine Distributed Energy Resource (DER) Project - Dogtown Shunt Capacitor Banks | Transmission application from Central Maine Power for the installation of a 10 MVAR shunt capacitor bank located at the Dogtown 115 kV substation in addition to three 10 MVAR shunt capacitor banks planned for interconnection of QP1028 and Detroit-Guilford-Belfast Cluster 6. | 2026-04-30 | Approved Withdrawn | 12/21/2023 3/18/2025
CMP-23-G80 | 2023-12-05 | Central Maine Power Affected System Operator (ASO) Study Western Maine Roxbury-Rumford-Woodstock Area Distributed Energy Resource (DER) Project - ER Hamlin Solar, LLC - 118 Ryerson Hill Road Solar | Generator application from Central Maine Power on behalf of ER Hamlin Solar, LLC for the installation of a 1.625 MW PV facility in Paris, ME and interconnecting to Paris Tap substation via the 409D1 circuit. | 2024-12-15 | Approved Withdrawn | 12/21/2023 1/22/2025
ES-23-G81 | 2023-11-29 | Greenskies Clean Energy LLC - 41 Middlefield Road Solar | Generation notification from Eversource Energy on behalf of Greenskies Clean Energy LLC for the installation of 3.035 MW Solar PV in Durham, CT and interconnecting to 41 Middlefield Road, Durham, CT via the 30K15 circuit out of Dooley substation. | 2024-05-01 | Notification | 2023-12-21
ES-23-G87 | 2023-11-29 | Rockingham County - 101 North Road Solar | Generation notification from Eversource Energy on behalf of Rockingham County for the installation of 3.25 MW Solar PV in Brentwood, NH and interconnecting to 101 North Road, Brentwood, NH via the 3103 circuit out of Brentwood substation. | 2024-12-31 | Notification | 2023-12-21
ES-23-G90 | 2023-11-29 | Encore Renewable Energy - 301 Poverty Plains Road Solar | Generation notification from Eversource Energy on behalf of Encore Renewable Energy for the installation of 4.999 MW Solar PV in Warner, NH and interconnecting to 301 Poverty Plains Road, Warner, NH via the 317 circuit out of Oak Hill substation. | 2024-05-01 | Notification | 2023-12-21
BELD-23-G01 | 2023-11-16 | Convergent Energy & Power - 119 Common Street Battery | Generation notification from Braintree Electric Light Department on behalf of Convergent Energy & Power for the installation of 4.99 MW Battery in Braintree, MA and interconnecting to 119 Common Street, Braintree, MA via the 13.8 kV circuit out of Curchil station. | 2025-01-31 | Notification | 2023-12-21
NEP-23-GNF08 | 2023-11-26 | Onsite Renewables, LLC - 333 Boston Road Battery | Generation notification from New England Power on behalf of Onsite Renewables, LLC for the installation of 4.9992 MW/18.432 MWh Battery in Billerica, MA and interconnecting to 333 Boston Road, Billerica, MA via the 70L2 circuit out of Billerica substation. | 2025-12-01 | Notification Withdrawn | 12/21/2023 10/22/2024
NEP-23-GNF09 | 2023-11-26 | Onsite Renewables, LLC - 210 Littleton Road Battery | Generation notification from New England Power on behalf of Onsite Renewables, LLC for the installation of 4.9992 MW/18.432 MWh Battery in Westford, MA and interconnecting to 210 Littleton Road, Westford, MA via the 58L3 circuit out of Boston Road substation. | 2025-12-01 | Notification Withdrawn | 12/21/2023 9/17/2024
VEC-23-G01 | 2023-11-13 | Green Mountain Power - 1 Veilleux Road Battery | Generator notification from Vermont Electric Cooperative on behalf of Green Mountain Power for the installation of a 3.0 MW/12.0MWh Battery in Troy, VT and interconnecting to 1 Veilleux Road, Troy, VT via the 13.2 kV circuit out of North Troy substation. | 2024-02-01 | Notification | 2023-12-21
DED-23-G01 | 2023-12-01 | Tangent Energy Solutions - 35 Ferncroft Road Battery | Generator notification from Danvers Electric Division on behalf of Tangent Energy Solutions for the installation of a 4.999 MW Battery in Danvers, MA and interconnecting to 35 Ferncroft Road, Danvers, MA via the 2393 circuit out of South Danvers substation. | 2024-05-31 | Notification | 2023-12-21
NEP-19-GNF37 Rev.2 | 2023-11-02 | Nexamp Solar - 60 Spring Street Solar and Battery | Generation notification from New England Power on behalf of Nexamp Solar for the installation of 4.98 MW Solar PV and 3.0 MW/6.0 MWh DC Coupled Battery in Franklin, MA and interconnecting to 60 Spring Street, Franklin, MA via the 13.8 kV circuit out of Beaver Pond substation. | 2021-09-03 | Notification | 2023-12-21
ES-23-G85 | 2023-11-29 | Central CT State University - 2004 Wells Street Fuel Cell | Generation notification from Eversource Energy on behalf of Central CT State University for the installation of a 2.0 MW Fuel Cell in New Britain, CT and interconnecting to 2004 Wells Street, New Britain, CT via the 7L88 out of East New Britain substation. | 2024-07-11 | Notification | 2023-12-21
GPS-21-G01 | 2023-11-03 | Generation Associated with QP 892/QP940/QP1030 | Generation application from Gravel Pit Solar, LLC for the installation of 120 MW (net) solar facility in East Windsor, CT and interconnecting to the Gravel Pit 35E substation. | 2024-05-15 | Approved | 2023-11-17
GPS-21-T01 | 2023-11-03 | Generation Associated with QP 892/QP940/QP1030 | Transmission application from Gravel Pit Solar, LLC for the installation of a 115/34.5/13.8 kV 51/68/85 MVA step-up transformer. | 2024-05-15 | Approved | 2023-11-17
ES-20-T34 Rev.1 | 2023-11-06 | Generation Associated with QP 892/QP940/QP1030 | Transmission application from Eversource Energy for the installation of a three-breakrer ring bus tapper on the 115 kV Line 1200 between Barbour Hill and Windsor Locks substations. | 2024-04-30 | Approved | 2023-11-17
NEP-23-T11 | 2023-10-30 | Reading Municipal Light Department (RMLD) Wilmington Station 6 Project | Transmission application from New England Power to loop approximately 0.1 miles of the T-146 115 kV line through a new 115 kV circuit breaker. | 2025-08-01 | Approved | 2023-11-17
RMLD-21-T01 | 2023-10-13 | Reading Municipal Light Department (RMLD) Wilmington Station 6 Project | Transmission application from Reading Municipal Lighting Department to construct the new Wilmington Station 6 substation with a new 115 kV circuit breaker and two 115/13.8 kV transformers. | 2025-08-01 | Approved | 2023-11-17
MDFA-21-T01 | 2023-11-01 | Hospital Road Substation - Replace Transformer 1 and Add Transformer 2 Project | Transmission application from Massachusetts Development Finance Agency to replace the existing 12/16/20 MVA 69/13.8 kV power transformer and 13.8 kV switchgear with two new 24/32/40 MVA 69/13.8 kV power transformers and new 13.8 kV two bus switchgear. | 2025-09-01 | Approved | 2023-11-15
ES-23-G52 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and CAPE Distributed Energy Resource (DER) Phase 2 Project - Ameresco Inc. - 50 Workshop Road Solar and Battery | Generation application from Eversource Energy on behalf of Ameresco Inc. for the installation of a 3.0 MW PV and 1.927 MW/3.854 MWh AC Coupled Battery facility in Yarmouth, MA and interconnecting to the Hyannis substation via the 4-92A-563 circuit. | 2024-02-15 | Approved Withdrawn | 11/17/2023 12/17/2024
ES-23-G53 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and CAPE Distributed Energy Resource (DER) Phase 2 Project - ASD Cape Cod Holdings LLC - 0 Boxberry Hill Road Solar and Battery | Generation application from Eversource Energy on behalf of ASD Cape Cod Holdings LLC for the installation of a 4.998 MW PV and 4.998 MW/25.364 MWh DC Coupled Battery facility in Falmouth, MA and interconnecting to the Hatchville substation via the 4-78-78 circuit. | 2024-02-15 | Approved | 2023-11-17
ES-23-G54 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and CAPE Distributed Energy Resource (DER) Phase 2 Project - ASD Cape Cod Holdings LLC - 41 Theatre Drive Solar and Battery | Generation application from Eversource Energy on behalf of ASD Cape Cod Holdings LLC for the installation of a 4.998 MW PV and 4.0 MW/11.824 MWh DC Coupled Battery facility in Falmouth, MA and interconnecting to the Hatchville substation via the 4-78-78 circuit. | 2024-11-30 | Approved | 2023-11-17
ES-23-G55 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and CAPE Distributed Energy Resource (DER) Phase 2 Project - ASD Cape Cod Holdings LLC - 48 Theatre Drive Solar and Battery | Generation application from Eversource Energy on behalf of ASD Cape Cod Holdings LLC for the installation of a 3.5 MW PV and 1.478 MW/2.956 MWh DC Coupled Battery facility in Falmouth, MA and interconnecting to the Hatchville substation via the 4-78-78 circuit. | 2024-11-30 | Approved | 2023-11-17
ES-23-G57 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and CAPE Distributed Energy Resource (DER) Phase 2 Project - Mashpee Public Schools - 500 Old Barnstable Road Solar and Battery | Generation application from Eversource Energy on behalf of Mashpee Public Schools for the installation of a 1.0 MW PV and 0.446 MW/0.892 MWh AC Coupled Battery facility in Mashpee, MA and interconnecting to the Mashpee substation via the 4-77B-454 circuit. | 2024-02-15 | Approved Withdrawn | 11/17/2023 12/17/2024
ES-23-G62 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and CAPE Distributed Energy Resource (DER) Phase 2 Project - Castletown Inc. - 1517 Freeman's Way Solar and Battery | Generation application from Eversource Energy on behalf of Castletown Inc. for the installation of a 4.999 MW PV and 4.999 MW/45.0 MWh DC Coupled Battery facility in Brewster, MA and interconnecting to the Orleans substation via the 9-95B-600 circuit. | 2024-02-16 | Approved | 2023-11-17
ES-23-G63 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and CAPE Distributed Energy Resource (DER) Phase 2 Project - NextGrid Basswood LLC - 0 Mid Cape Highway Solar and Battery | Generation application from Eversource Energy on behalf of NextGrid Basswood LLC for the installation of a 4.999 MW PV and 4.999 MW/19.62 MWh DC Coupled Battery facility in Brewster, MA and interconnecting to the Orleans substation via the 4-95B-95B circuit. | 2024-02-16 | Approved | 2023-11-17
ES-23-G64 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and CAPE Distributed Energy Resource (DER) Phase 2 Project - NextGrid Persimmon LLC - 420 Nathan Ellis Highway Solar and Battery | Generation application from Eversource Energy on behalf of NextGrid Persimmon LLC for the installation of a 4.99 MW PV and 4.0 MW/16.0 MWh DC Coupled Battery facility in Mashpee, MA and interconnecting to the Hatchville substation via the 4-77A-450 circuit. | 2024-02-16 | Approved | 2023-11-17
ES-23-G67 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and CAPE Distributed Energy Resource (DER) Phase 2 Project - Next Grid Inc. - 15 Atkins Road Solar and Battery | Generation application from Eversource Energy on behalf of Next Grid Inc. for the installation of a 4.6 MW PV and 4.2 MW/16.8 MWh DC Coupled Battery facility in East Sandwich, MA and interconnecting to the Sandwich substation via the 4-87A-471 circuit. | 2024-02-16 | Approved | 2023-11-17
ES-23-G68 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and CAPE Distributed Energy Resource (DER) Phase 2 Project - NextGrid Pecan LLC - 2 Sand Pipt Road Solar and Battery | Generation application from Eversource Energy on behalf of NextGrid Pecan LLC for the installation of a 4.107 MW PV and 2.4 MW/9.6 MWh DC Coupled Battery facility in Truro, MA and interconnecting to the Wellfleet substation via the 4-96-96 circuit. | 2024-02-16 | Approved | 2023-11-17
ES-23-G69 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and CAPE Distributed Energy Resource (DER) Phase 2 Project - NextGrid Torreya LLC - 590 Thomas B Landers Road Solar and Battery | Generation application from Eversource Energy on behalf of NextGrid Torreya LLC for the installation of a 3.5 MW PV and 2.5 MW/5.0 MWh DC Coupled Battery facility in Falmouth, MA and interconnecting to the Falmouth substation via the 4-98A-98A circuit. | 2024-02-16 | Approved | 2023-11-17
ES-23-G77 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and CAPE Distributed Energy Resource (DER) Phase 2 Project - Valta Solar LLC - 131 Great Western Road Solar and Battery | Generation application from Eversource Energy on behalf of Valta Solar LLC for the installation of a 2.15 MW PV and 1.8469 MW/3.6938 MWh AC Coupled Battery facility in Dennis, MA and interconnecting to the Harwich substation via the 4-92B-92B circuit. | 2024-02-17 | Approved | 2023-11-17
ES-23-G78 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and CAPE Distributed Energy Resource (DER) Phase 2 Project - Valta Solar LLC - 22 Hedges Pond Road Solar and Battery | Generation application from Eversource Energy on behalf of Valta Solar LLC for the installation of a 3.7 MW PV and 1.859 MW/3.836 MWh AC Coupled Battery facility in Plymouth, MA and interconnecting to the Valley substation via the 3-89-922 circuit. | 2024-02-17 | Approved | 2023-11-17
CMP-20-G94 Rev.1 | 2023-10-31 | ISM Solar Development, LLC - 24 Shepherds Acres Estate Solar | Generator notification from Central Maine Power on behalf of ISM Solar Development, LLC for the installation of 3.0 MW Solar PV in South Paris, ME and interconnecting to 24 Shepherds Acres Estate, South Paris, ME via the 409D1 circuit out of Paris Tap substation. | 2024-09-19 | Notification | 2023-11-17
ES-23-G80 | 2023-11-01 | Key Capture Energy LLC - 100 Salmon Brook Street Battery | Generator notification from Eversource Energy on behalf of Key Capture Energy LLC for the installation of 4.999 MW/30.024 MWh Battery in Granby, CT and interconnecting to 100 Salmon Brook Street, Granby, CT via the 43F circuit out of Simsbury substation. | 2026-08-04 | Notification | 2023-11-17
ES-20-G154 Rev.1 | 2023-10-30 | Clearway Energy - 160 Tihonet Road Solar and Battery | Generator notification from Eversource Energy on behalf of Clearway Energy for the installation of 4.999 MW Solar PV and 3.3 MW/6.884 MWh AC Coupled Battery in Wareham, MA and interconnecting to 160 Tihonet Road, Wareham, MA via Section 80 out of Wareham substation. | 2023-12-31 | Notification | 2023-11-17
ES-20-G155 Rev.1 | 2023-10-30 | Clearway Energy - 59 Federal Road Solar and Battery | Generator notification from Eversource Energy on behalf of Clearway Energy for the installation of 4.999 MW Solar PV and 4.999 MW/20.4547 MWh DC Coupled Battery in Carver, MA and interconnecting to 59 Federal Road, Carver, MA via Section 83 out of Wareham substation. | 2023-12-31 | Notification | 2023-11-17
ES-20-G156 Rev.1 | 2023-10-30 | Clearway Energy - 276 Federal Road Solar and Battery | Generator notification from Eversource Energy on behalf of Clearway Energy for the installation of 4.999 MW Solar PV and 3.3 MW/6.884 MWh AC Coupled Battery in Carver, MA and interconnecting to 276 Federal Road, Carver, MA via Section 83 out of Wareham substation. | 2023-12-31 | Notification | 2023-11-17
ES-20-G161 Rev.1 | 2023-10-30 | Clearway Energy - 0 Hammond Street Solar and Battery | Generator notification from Eversource Energy on behalf of Clearway Energy for the installation of 4.999 MW Solar PV and 4.999 MW/26.9888 MWh DC Coupled Battery in Carver, MA and interconnecting to 0 Hammond Street, Carver, MA via Section 83 out of Wareham substation. | 2023-12-31 | Notification | 2023-11-17
ES-21-G17 Rev.2 | 2023-10-30 | Sup Set Main Street Plympton Solar and Battery - 399 Main Street Solar and Battery | Generator notification from Eversource Energy on behalf of Sup Set Main Street Plympton Solar and Battery for the installation of 2.0 MW Solar PV and 1.65 MW/4.11 MWh AC Coupled Battery in Plympton, MA and interconnecting to 399 Main Street, Plympton, MA via the 3-51-901 circuit out of Brook Street substation. | 2025-01-31 | Notification | 2023-11-17
ES-23-G86 | 2023-10-30 | Davis Hill Development - 780 US-7 Solar and Battery | Generator notification from Eversource Energy on behalf of Davis Hill Development for the installation of 4.9992 MW Solar PV and 3.0 MW/6.0 MWh DC Coupled Battery in Gaylordsville, CT and interconnecting to 780 US-7, Gaylordsville, CT via the 11M3 circuit out of Bulls Bridge substation. | 2025-05-31 | Notification | 2023-11-17
ES-23-T61 | 2023-10-31 | Windsor Locks Substation Expansion | Transmission notification from Eversource Energy for the replacement of the existing 1T circuit breaker and installation of a second series breaker at the Windsor Locks 14K substation in Windsor Locks, CT. | 2026-12-31 | Notification | 2023-11-15
ES-23-T62 | 2023-10-31 | Enfield Substation Expansion | Transmission notification from Eversource Energy for the replacement of existing 1T circuit breaker and installation of a second series breaker at the Enfield 12C substation in Enfield, CT. | 2027-06-30 | Notification | 2023-11-15
NEP-23-T02 | 2023-10-13 | Ayer Substation Rebuild Project | Transmission notification from National Grid for the replacement of Ayer substation transformers T4 and T6 with two 115/69 kV 33.6/44.8/56 MVA autotransformers and two 115/13.8 kV 33/44/55 MVA two-winding transformers. | 2027-07-27 | Notification | 2023-11-15
ES-20-G124 Rev.2 | 2023-10-10 | Queue Position 781 (QP 781) Offshore Wind Second Modifications Project | Generator application from Eversource Energy for the installation of the 704 MW Revolution Wind 1 Offshore Wind Farm and interconnecting to Davisville 115 kV substation in Washington County, RI. | 2024-12-16 | Approved | 2023-10-30
ES-20-T20 Rev.2 | 2023-10-10 | Queue Position 781 (QP 781) Offshore Wind Second Modifications Project | Transmission application from Eversource Energy for the installation of a 175 MVAR onshore synchronous condenser at the Revolution Wind 275/115 kV substation. | 2024-06-01 | Approved | 2023-10-30
ES-20-T21 Rev.2 | 2023-10-10 | Queue Position 781 (QP 781) Offshore Wind Second Modifications Project | Transmission application from Eversource Energy for the 175 MVAR onshore synchronous condenser at the Revolution Wind 275/115 kV substation. | 2024-06-01 | Approved | 2023-10-30
ES-20-T22 Rev.2 | 2023-10-10 | Queue Position 781 (QP 781) Offshore Wind Second Modifications Project | Transmission application from Eversource Energy for the installation of two 275/115 kV onshore transformers at the Revolution Wind 275/115 kV substation. | 2024-06-01 | Approved | 2023-10-30
ES-20-T23 Rev.2 | 2023-10-10 | Queue Position 781 (QP 781) Offshore Wind Second Modifications Project | Transmission application from Eversource Energy for the installation of two 275 kV submarine and terrestrial cables at the Revolution Wind 275/115 kV substation. | 2024-06-01 | Approved | 2023-10-30
ES-20-T24 Rev.2 | 2023-10-10 | Queue Position 781 (QP 781) Offshore Wind Second Modifications Project | Transmission application from Eversource Energy for the installation of four 275/66 kV offshore transformers at the Revolution Wind 275/115 kV substation. | 2024-06-01 | Approved | 2023-10-30
ES-20-T25 Rev.2 | 2023-10-10 | Queue Position 781 (QP 781) Offshore Wind Second Modifications Project | Transmission application from Eversource Energy for the installation of two 115 kV circuits at the Revolution Wind 275/115 kV substation. | 2024-06-01 | Approved | 2023-10-30
ES-20-T26 Rev.2 | 2023-10-10 | Queue Position 781 (QP 781) Offshore Wind Second Modifications Project | Transmission application from Eversource Energy for the installation of a redundant 345 kV circuit breaker at Card 11F substation. | 2024-12-16 | Approved | 2023-10-30
RIE-23-T01 | 2023-10-10 | Queue Position 781 (QP 781) Offshore Wind Second Modifications Project | Transmission application from Rhode Island Energy for the rebuild of the existing 115/34.5 kV Davisville substation and conversion to a 6 breaker ring bus in North Kingstown, RI. | 2024-12-31 | Approved | 2023-10-30
RIE-23-T02 | 2023-10-10 | Queue Position 781 (QP 781) Offshore Wind Second Modifications Project | Transmission application from Rhode Island Energy for the reconductoring of the G-185N and K-189 Lines from Kent County substation to Drumrock substation. | 2024-12-31 | Approved | 2023-10-30
RIE-23-T03 | 2023-10-10 | Queue Position 781 (QP 781) Offshore Wind Second Modifications Project | Transmission application from Rhode Island Energy for the reconductoring of the G-185S and L-190 Lines from Kent County substation to Old Baptist Road substation to Davisville substation. | 2024-12-31 | Approved | 2023-10-30
RIE-23-T04 | 2023-10-10 | Queue Position 781 (QP 781) Offshore Wind Second Modifications Project | Transmission application from Rhode Island Energy for the Drumrock substation upgrades to upgrade the K-189 and G-185N limiting 115 kV equipment to 3000 A capacity and upgrade five 115 kV circuit breakers to 50 kA. | 2024-12-31 | Approved | 2023-10-30
UI-21-G04 Rev.1 | 2023-10-04 | Derby 14.4 MW Gross/14.0 MW Net Fuel Cell Project | Revision of Generator Application from United Illuminating on behalf of Derby Fuel Cell, LLC for the installation of a 14.4 MW gross/14.0 MW net Fuel Cell in Derby, CT and interconnecting to the Indian Wells substation via two express 13.8 kV distribution feeders to change from operating with voltage control to operating with unity power factor. | 2023-12-15 | Approved | 2023-10-30
NEM-23-X01 | 2023-10-10 | W.F. Wyman Station Unit AVR Replacement | Transmission application from NextEra Energy Marketing, LLC on behalf of FPL Energy Wyman IV LLC for the replacement of the existing General Electric AVR with a new Basler Electric DECS 450 (Dual Controllers) AVR at Wyman Station Unit 4 in Yarmouth, ME. | 2023-12-02 | Approved | 2023-10-30
CMP-20-T02 Rev.1 | 2023-10-10 | Larrabee Road Substation Reconfiguration Project | Transmission application from Central Maine Power to reconfigure the layout of the Larrabee Road substation for the interconnection of Queue Position 639 and to include a new 345 kV series breaker for the new 345/115 kV transformer T2. | 2025-12-31 | Approved | 2023-10-30
AR-23-G01 | 2023-10-12 | Queue Position 1112 (QP 1112) Battery Energy Storage Project | Generator application from Accelerate Renewables on behalf of Wendell Energy Storage LLC for the installation of a 99.9 MW/400 MWh battery energy storage system interconnecting to the National Grid transmission system on the 115 kV line B-128. | 2025-05-14 | Approved Withdrawn | 10/30/2023 7/3/2024
AR-23-T01 | 2023-10-12 | Queue Position 1112 (QP 1112) Battery Energy Storage Project | Transmission application from Accelerate Renewables on behalf of Wendell Energy Storage LLC to construct a new 115/34.5/0.66 kV transformer at the proposed QP 1112 site in Wendell, MA. | 2025-05-14 | Approved Withdrawn | 10/30/2023 7/3/2024
NEP-23-T09 | 2023-10-12 | Queue Position 1112 (QP 1112) Battery Energy Storage Project | Transmission application from New England Power for the installation of a three-breaker 115 kV ring bus substation at the proposed QP 1112 site in Wendell, MA. | 2025-05-14 | Approved Withdrawn | 10/30/2023 7/3/2024
GMP-23-G21 | 2023-09-12 | Boardman Hill Solar, LLC - 1352 Boardman Hill Road Solar | Generator notification from Green Mountain Power on behalf of Boardman Hill Solar, LLC for the installation of 2.2 MW Solar PV in West Rutland, VT and interconnecting to 1352 Boardman Hill Road, West Rutland, VT via the G47 circuit out of Rutland Gas Turbine substation. | 2024-07-01 | Notification | 2023-10-30
GMP-23-G22 | 2023-09-12 | ER Olde Farmhouse Road Solar LLC - Olde Farmhouse Road Solar | Generator notification from Green Mountain Power on behalf of ER Olde Farmhouse Road Solar LLC for the installation of 2.2 MW Solar PV in Danville, VT and interconnecting to Olde Farmhouse Road, Danville, VT via the G71 circuit out of Baker Avenue substation. | 2024-11-01 | Notification | 2023-10-30
GMP-23-G23 | 2023-09-20 | Williston E Chip Alley Solar LLC - 326 IBM Road Solar | Generator notification from Green Mountain Power on behalf of Williston E Chip Alley Solar LLC for the installation of 3.25 MW Solar PV in Williston, VT and interconnecting to 326 IBM Road, Williston, VT via the G1 circuit out of Williston substation. | 2024-09-01 | Notification | 2023-10-30
FGE-23-G03 | 2023-09-11 | Luminia - 0 Shea Street Solar | Generator notification from Unitil on behalf of Luminia for the installation of 4.999 MW Solar PV in Fitchburg, MA and interconnecting to 0 Shea Street, Fitchburg, MA via the 25W27 circuit out of River Street substation. | 2024-12-01 | Notification Withdrawn | 10/30/2023 3/18/2025
UES-23-G03 | 2023-09-11 | Merrimack County NH - 325 Daniel Webster Highway Solar | Generator notification from Unitil on behalf of Merrimack County NH for the installation of 3.375 MW Solar PV in Boscawen, MA and interconnecting to 325 Daniel Webster Highway, Boscawen, NH via the 13W3 circuit out of Oak Hill substation. | 2024-07-01 | Notification | 2023-10-30
UES-23-G04 | 2023-09-11 | LSE Ursa Minor LLC - 67 W Portsmouth Street Solar | Generator notification from Unitil on behalf of LSE Ursa Minor LLC for the installation of 4.98 MW Solar PV in Concord, NH and interconnecting to 67 W Portsmouth Street, Concord, NH via the 15W2 circuit out of Garvins substation. | 2024-12-31 | Notification | 2023-10-30
ES-23-G48 | 2023-09-28 | OnSite Renewables, LLC - 1208 VFW Parkway Battery | Generator notification from Eversource Energy on behalf of OnSite Renewables, LLC for the installation of a 4.9992 MW/18.432 MWh Battery in West Roxbury, MA and interconnecting to 1208 VFW Parkway, West Roxbury, MA via the 496-H3 circuit out of Hyde Park substation. | 2023-12-31 | Notification Withdrawn | 10/30/2023 7/16/2024
ES-23-G82 | 2023-09-13 | HQCA Energy Solutions, LLC - 40 Norwich Road Battery | Generator notification from Eversource Energy on behalf of HQCA Energy Solutions, LLC for the installation of a 4.0 MW/11.008 MWh Battery in Waterford, CT and interconnecting to 40 Norwich Road, Waterford, CT via the 9L09 circuit out of Williams Street substation. | 2025-06-30 | Notification | 2023-10-30
ES-23-G83 | 2023-09-13 | HQCA Energy Solutions, LLC - 0 State Pier Road Bettery | Generator notification from Eversource Energy on behalf of HQCA Energy Solutions, LLC for the installation of a 4.0 MW/11.008 MWh Battery in New London, CT and interconnecting to 0 State Pier Road, New London, CT via the 9L02 circuit out of Williams Street substation. | 2025-06-30 | Notification Withdrawn | 10/30/2023 7/16/2024
NEP-23-GNF07 | 2023-09-28 | Endurant Energy - 60 Commercial Street Battery | Generator notification from New England Power Company for the installation of a 2.937 MW/5.87 MWh Battery in Everett, MA and interconnecting to 60 Commercial Street, Everett, MA via the 23 kV circuit out of Thorndike Street substation. | 2025-10-01 | Notification | 2023-10-30
ES-23-G21 Rev.1 | 2023-10-20 | Clearway Energy - 77 Farm to Market Road Solar Battery | Generator notification from Eversource Energy on behalf of Clearway Energy for the installation of a 4.999 MW Solar PV and 2.31 MW/4.88809 MWh AC Coupled Battery in Wareham, MA and interconnecting to 77 Farm to Market Road, Wareham, MA via the 85 circuit out of Tremont substation. | 2023-11-30 | Notification | 2023-10-30
UI-23-G03 | 2023-10-10 | BT FC, LLC - 267 Grant Street Fuel Cell | Generator notification from United Illuminating on behalf of BT FC, LLC for the installation of a 2.0 MW Fuel Cell in Bridgeport, CT and interconnecting to 267 Grant Street, Bridgeport, CT via the 2644 circuit out of Baird substation. | 2024-01-02 | Notification | 2023-10-30
ES-23-T60 | 2023-09-21 | Replacement of Step-Down Transformer 3X at Montague Substation | Transmission notification from Eversource Energy for the replacement of the existing substation step-down transformer 3X at Montague substation and separation of bus relay from transformer relay to allow independent tripping. | 2024-05-31 | Notification | 2023-10-24
NEP-23-T05 | 2023-09-12 | Maplewood #16 Transformer T4 Replacement | Transmission notification from New England Power Company for the replacement of the existing load-serving transformer T4 at Maplewood substation. | 2025-07-01 | Notification | 2023-10-24
NEP-23-T08 | 2023-10-09 | West Andover #8 Transformer T10 and T20 Replacement | Transmission notification from New England Power Company for the replacement of the existing T10 and T20 30/40/40 MVA load-serving transformers at West Andover substation with 45/60/75 MVA units. | 2026-04-01 | Notification | 2023-10-24
NEP-18-T07 Rev.1 | 2023-10-10 | N12 and M13 Reconductoring and DCT Separation Project | Transmission notification from New England Power Company for the reconductoring of the 3.69-mile N12 and M13 115 kV lines and separation of the double-circuit towers between Pottersville substation and Bell Rock substation. | 2026-03-31 | Notification | 2023-10-24
ES-23-G56 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and Cape Distributed Energy Resource (DER) Phase 1 Project - Benson Brook Road Solar 2020, LLC | Generation application from Eversource Energy on behalf of Benson Brook Road Solar 2020, LLC for the installation of a 1.0 MW PV and 0.7714 MW/3.0856 MWh AC Coupled Battery facility in Marion, MA and interconnecting to the Crystal Spring substation via the 3-304-304 circuit. | 2024-02-15 | Approved Withdrawn | 9/20/2023 6/18/2024
ES-23-G58 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and Cape Distributed Energy Resource (DER) Phase 1 Project - 510 PV Project Development, LLC - 52 Morses Lane Solar and Battery | Generation application from Eversource Energy on behalf of 510 PV Project Development, LLC for the installation of a 4.99 MW PV and 4.99 MW/19.99 MWh DC Coupled Battery facility in Acushnet, MA and interconnecting to the Wing Lane substation via the 2-241-238 circuit. | 2024-02-15 | Approved | 2023-09-20
ES-23-G59 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and Cape Distributed Energy Resource (DER) Phase 1 Project - Galehead Development - 0 Commerce Way Solar | Generation application from Eversource Energy on behalf of Galehead Development for the installation of a 2.0 MW PV and 1.273 MW/2.546 MWh DC Coupled Battery facility in Marshfield, MA and interconnecting to the Duxbury substation via the 3-25-908 circuit. | 2024-02-15 | Approved | 2023-09-20
ES-23-G60 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and Cape Distributed Energy Resource (DER) Phase 1 Project - Kearsarge Solar LLC - 0 Amy Lot Solar and Battery | Generation application from Eversource Energy on behalf of Kearsarge Solar LLC for the installation of a 4.4 MW PV and 3.15 MW/6.3 MWh DC Coupled Battery facility in Freetown, MA and interconnecting to the Industrial Park substation via the 2-102-604 circuit. | 2024-02-15 | Approved | 2023-09-20
ES-23-G61 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and Cape Distributed Energy Resource (DER) Phase 1 Project - 510 PV Project Development, LLC - 73 Tremont Street Solar and Battery | Generation application from Eversource Energy on behalf of 510 PV Project Development, LLC for the installation of a 4.99 MW PV and 4.99 MW/20.0 MWh DC Coupled Battery facility in Carver, MA and interconnecting to the West Pond substation via the 3-11-11 circuit. | 2024-02-15 | Approved | 2023-09-20
ES-23-G65 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and Cape Distributed Energy Resource (DER) Phase 1 Project - Blueblossom Solar LLC - 715 Main Street Battery | Generation application from Eversource Energy on behalf of Blueblossom Solar LLC for the installation of a 4.782 MW/14.346 MWh Battery facility in Marshfield, MA and interconnecting to the Duxbury substation via the 3-24B-915 circuit. | 2024-02-16 | Approved | 2023-09-20
ES-23-G66 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and Cape Distributed Energy Resource (DER) Phase 1 Project - NextGrid Marshfield LLC - 23 Clay Pit Road Solar and Battery | Generation application from Eversource Energy on behalf of NextGrid Marshfield LLC for the installation of a 4.6 MW PV and 2.5 MW/12.099 MWh DC Coupled Battery facility in Marshfield, MA and interconnecting to the Marshfield substation via the 3-24A-24A circuit. | 2024-02-16 | Approved | 2023-09-20
ES-23-G70 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and Cape Distributed Energy Resource (DER) Phase 1 Project - Silo Electric LLC - 15 University Road Battery | Generation application from Eversource Energy on behalf of Silo Electric LLC for the installation of a 4.999 MW/11.008 MWh Battery facility in Canton, MA and interconnecting to the Canton substation via the 470-H1 circuit. | 2024-02-16 | Approved | 2023-09-20
ES-23-G71 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and Cape Distributed Energy Resource (DER) Phase 1 Project - Soland, LLC - 107 Wareham Street Solar and Battery | Generation application from Eversource Energy on behalf of Soland, LLC for the installation of a 4.996 MW PV and 3.1705 MW/12.682 MWh DC Coupled Battery facility in Carver, MA and interconnecting to the Tremont substation via the 3-86-86 circuit. | 2024-02-16 | Approved | 2023-09-20
ES-23-G72 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and Cape Distributed Energy Resource (DER) Phase 1 Project - SR Cross St Solar LLC - 11 Cross Street Solar and Battery | Generation application from Eversource Energy on behalf of SR Cross St Solar LLC for the installation of a 1.992 MW PV and 1.992 MW/2.0 MWh DC Coupled Battery facility in Carver, MA and interconnecting to the West Pond substation via the 3-10-10 circuit. | 2024-02-17 | Approved | 2023-09-20
ES-23-G73 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and Cape Distributed Energy Resource (DER) Phase 1 Project - SWEB Development USA LLC - Division Road Solar and Battery | Generation application from Eversource Energy on behalf of SWEB Development USA LLC for the installation of a 1.95 MW PV and 1.04 MW/2.3834 MWh DC Coupled Battery facility in Westport, MA and interconnecting to the Fisher Road substation via the 2-523-523 circuit. | 2024-02-17 | Approved | 2023-09-20
ES-23-G74 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and Cape Distributed Energy Resource (DER) Phase 1 Project - Syncarpha Solar LLC - 211 Middle Road Solar and Battery | Generation application from Eversource Energy on behalf of Syncarpha Solar LLC for the installation of a 4.98 MW PV and 4.0 MW/8.0 MWh AC Coupled Battery facility in Acushnet, MA and interconnecting to the Wing Lane substation via the 2-241-241 circuit. | 2024-02-17 | Approved | 2023-09-20
ES-23-G75 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and Cape Distributed Energy Resource (DER) Phase 1 Project - TJA Clean Energy - 67 Chace Road Solar and Battery | Generation application from Eversource Energy on behalf of TJA Clean Energy for the installation of a 4.99 MW PV and 3.75 MW/7.812 MWh DC Coupled Battery facility in Freetown, MA and interconnecting to the Industrial Park substation via the 2-108-108 circuit. | 2024-02-17 | Approved | 2023-09-20
ES-23-G76 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and Cape Distributed Energy Resource (DER) Phase 1 Project - TJA Clean Energy - 100 Parris Lane Solar and Battery | Generation application from Eversource Energy on behalf of TJA Clean Energy for the installation of a 4.99 MW PV and 2.5 MW/5.208 MWh DC Coupled Battery facility in Acushnet, MA and interconnecting to the Wing Lane substation via the 2-241-241 circuit. | 2024-02-17 | Approved | 2023-09-20
ES-23-T58 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and Cape Distributed Energy Resource (DER) Phase 1 Project - 115 kV underground cable Industrial Park - Assonet Substations and Upgrades | Transmission application from Eversource Energy for the installation of a new 10.8 miles, 115 kV underground cable between Industrial Park substation and Assonet substation and a new 15 MVAR reactor and breaker at the Assonet substation. | 2026-12-31 | Approved | 2023-09-20
ES-23-T59 | 2023-08-31 | Eversource Affected System Operator (ASO) Study Southeast Massachusetts (SEMA) and Cape Distributed Energy Resource (DER) Phase 1 Project - Second 115/13.2 kV Transformer and Breakers | Transmission application from Eversource Energy for the installation of a second 62.5 MVA 115/13.2 kV transformer and three new 115 kV breakers at the Assonet substation. | 2026-12-31 | Approved | 2023-09-20
ES-23-G16 | 2023-08-28 | University of Hartford Fuel Cell Project | Generator application from Eversource Energy on behalf of DESA Service, LLC for the installation of a 1.84 MW Fuel Cell facility in West Hartford, CT and interconnecting to the North Hartford substation via the 2N14 circuit. | 2023-10-31 | Approved | 2023-09-20
NEP-23-T06 | 2023-09-06 | Snake Hill Temporary and Permanent Substations Project | Transmission application from New England Power for the installation of a temporary 115/13.2 kV substation tapped from the W-123 line between Carpenter Hill substation and the tap to the Millennium generating plant using a 25 MVA mobile transformer and Modular Integrated Transportable Substation. | 2023-12-12 | Approved | 2023-09-20
NEP-23-T07 | 2023-09-06 | Snake Hill Temporary and Permanent Substations Project | Transmission application from New England Power for the installation of a new Snake Hill substation with a new 115/13.2 kV, 33/44/55 MVA transformer and associated distribution equipment on the 115 kV U-173 Line in Charlton, MA tapped between Carpenter Hill and Snow Street substations. | 2027-12-01 | Approved | 2023-09-20
CMP-23-G73 | 2023-09-05 | Queue Position 951 (QP 951) Andro Hydro Project | Generator application from Central Maine Power on behalf of Andro Hydro, LLC for the relocation of 26.63 MW of output from four separate generator groups comprising twenty-three hydroelectric generators that share existing 13.8 kV network and 115 kV transmission facilities for participation in the ISO New England wholesale markets. | 2023-12-13 | Approved | 2023-09-19
UES-23-G02 | 2023-08-23 | Unitil Energy Systems - 24 Towle Road Solar | Generator notification from Unitil Energy Systems for the installation of 4.875 MW Solar PV in Kingston, NH and interconnecting to 24 Towle Road, Kingston, NH via the 22X1 circuit out of Kingston substation. | 2024-12-01 | Notification | 2023-09-20
ES-23-G29 | 2023-08-22 | JPM Cheshire LLC - 354 Knotter Drive Battery | Generator notification from Eversource Energy on behalf of JPM Cheshire LLC for the installation of 4.9 MW/9.8 MWh Battery in Cheshire, CT and interconnecting to 354 Knotter Drive, Cheshire, CT via the 15Q4 circuit out of Canal Street substation. | 2024-12-31 | Notification | 2023-09-20
ES-23-G30 | 2023-08-22 | Acel International Holdings - 508A North Colony Road Battery | Generator notification from Eversource Energy on behalf of Accel International Holdings for the installation of 4.9 MW/9.8 MWh Battery in Meriden, CT and interconnecting to 508A North Colony Road, Meriden, CT via the 12F44 circuit out of Hanover Street substation. | 2024-12-31 | Notification | 2023-09-20
ES-23-G13 | 2023-08-31 | Davis Hill Development LLC - 344 Roosevelt Drive Battery | Generator notification from Eversource Energy on behalf of Davis Hill Development LLC for the installation of a 4.999 MW/20.3 MWh Battery in Monroe, CT and interconnecting to 344 Roosevelt Drive, Monroe, CT via the 14A53 circuit out of Stevenson substation. | 2024-12-31 | Notification | 2023-09-20
ES-23-G79 | 2023-08-31 | Davis Hill Development LLC - 781 Kent Road Battery | Generator notification from Eversource Energy on behalf of Davis Hill Development LLC for the installation of a 4.999 MW/20.3 MWh Battery in New Milford, CT and interconnecting to 781 Kent Road, New Milford, CT via the 11M61 circuit out of Bulls Bridge substation. | 2024-12-31 | Notification | 2023-09-20
RIE-23-GNF03 | 2023-09-05 | ECA Solar - 10 New Road Battery | Generator notification from Rhode Island Energy on behalf of ECA Solar for the installation of a 4.999 MW Battery in Rumford, RI and interconnecting to 10 New Road, Rumford, RI via the 20F1 circuit out of Phillipsdale substation. | 2024-12-01 | Notification | 2023-09-20
RIE-23-GNF07 | 2023-09-05 | Endurant Energy - 51 Fairlawn Avenue Battery | Generator notification from Rhode Island Energy on behalf of Endurant Energy for the installation of a 4.5 MW Battery in Pawtucket, RI and interconnecting to 51 Fairlawn Avenue, Pawtucket, RI via the 107W80 circuit out of Pawtucket substation. | 2024-12-01 | Notification | 2023-09-20
NEP-23-GNF06 | 2023-08-31 | NextGrid, LLC - 51 Lawrence Street Solar and Battery | Generation notification from New England Power on behalf of NextGrid, LLC for the installation of a 4.9992 MW Solar PV and 3.4 MW/10.2 MWh DC Coupled Battery in Pepperell, MA and interconnecting to 51 Lawrence Street, Pepperell, MA via the 226L1 circuit out of Groton Street substation. | 2025-12-01 | Notification | 2023-09-20
ES-23-T15 | 2023-09-01 | Partial Rebuild of Line 1142 | Transmission notification from Eversource Energy for the partial rebuild of Line 1142 replacing 7.3 miles of existing structures and associated 556-kcmil and 795-kcmil ACSR conductor with 1590-kcmil ACSS conductor. | 2025-12-31 | Notification | 2023-09-20
ES-23-T16 | 2023-09-01 | Rebuild of Line 1241 | Transmission notification from Eversource Energy for the rebuild of Line 1241 replacing 0.5 miles of existing structures and associated 795-kcmil ACSR conductor with 1590-kcmil ACSS conductor. | 2025-12-31 | Notification | 2023-09-20
ES-23-T17 | 2023-09-01 | Rebuild of Line 1319 | Transmission notification from Eversource Energy for the rebuild of Line 1319 replacing 4.6 miles of existing structures and associated 556-kcmil ACSR and 795-kcmil ACSS conductor with 1590-kcmil ACSS conductor. | 2025-12-31 | Notification | 2023-09-20
ES-23-T18 | 2023-09-01 | Partial Rebuild of Line 1403 | Transmission notification from Eversource Energy for the partial rebuild of Line 1403 replacing 1.3 miles of existing structures and associated 556-kcmil and 795-kcmil ACSS conductor with 1590-kcmil ACSS conductor. | 2025-12-31 | Notification | 2023-09-20
ES-23-T19 | 2023-09-01 | Rebuild of Line 1483 | Transmission notification from Eversource Energy for the rebuild of Line 1483 replacing 5.1 miles of existing structures and associated 795-kcmil ACSR conductor with 1590-kcmil ACSS conductor. | 2025-12-31 | Notification | 2023-09-20
ES-23-T20 | 2023-09-01 | Rebuild of Line 1545 | Transmission notification from Eversource Energy for the rebuild of Line 1545 replacing 4.5 miles of existing structures and associated 795-kcmil ACSR conductor with 1590-kcmil ACSS conductor. | 2025-12-31 | Notification | 2023-09-20
ES-23-T23 | 2023-09-01 | Rebuild of Line 1580 | Transmission notification from Eversource Energy for the rebuild of Line 1580 replacing 24 miles of existing structures and associated 4/0 Copper, 556-kcmil ACSR, and 795-kcmil ACSR conductor with 1590-kcmil ACSS conductor. | 2025-12-31 | Notification | 2023-09-20
ES-23-T24 | 2023-09-01 | Rebuild of Line 1808-1 | Transmission notification from Eversource Energy for the rebuild of Line 1808-1 replacing 14.2 miles of existing structures and associated 795-kcmil ACSR and ACSS conductor with 1590-kcmil ACSS conductor. | 2025-12-31 | Notification | 2023-09-20
ES-23-T55 | 2023-09-05 | F139 Line Rebuild | Transmission notification from Eversource Energy for the rebuild of the 115 kV F139 Line replacing 14.54 miles of existing conductor with 1272 ACSS conductor. | 2024-12-09 | Notification | 2023-09-20
ES-23-T57 | 2023-09-05 | W179-3 Line Rebuild | Transmission notification from Eversource Energy for the rebuild of the 115 kV W179-3 Line replacing 0.04 miles of existing conductor with 1272 ACSS conductor. | 2025-01-01 | Notification | 2023-09-20
CMP-23-G50 | 2023-08-24 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Phase 2 Project - C2 Parkman Solar LLC | Generator application from Central Maine Power (CMP) on behalf of C2 Parkman Solar LLC for the installation of a 14.0 MW PV facility in Guilford, ME and interconnecting to the Guilford substation via the 821D3 circuit. | 2024-11-15 | Approved Withdrawn | 8/31/2023 1/22/2025
CMP-23-G52 | 2023-08-24 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Phase 2 Project - Guilford High Street Solar LLC | Generator application from Central Maine Power (CMP) on behalf of Guilford High Street Solar LLC for the installation of a 3.0 MW PV facility in Guilford, ME and interconnecting to the Guilford substation via the 821D1 circuit. | 2024-11-21 | Approved Withdrawn | 8/31/2023 6/18/2024
CMP-23-G56 | 2023-08-24 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Phase 2 Project - Greenville CSG LLC | Generator application from Central Maine Power (CMP) on behalf of Greenville CSG LLC for the installation of a 4.25 MW PV facility in Monson, ME and interconnecting to the Monson substation via the 834D2 circuit. | 2024-01-23 | Approved | 2023-08-31
CMP-23-G59 | 2023-08-24 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Phase 2 Project - ME CDG 002 LLC | Generator application from Central Maine Power (CMP) on behalf of ME CDG 002 LLC for the installation of a 1.25 MW PV facility in Monson, ME and interconnecting to the Monson substation via the 834D1 circuit. | 2024-06-01 | Approved Withdrawn | 8/31/2023 6/18/2024
CMP-23-G60 | 2023-08-24 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Phase 2 Project - UGE USA INC | Generator application from Central Maine Power (CMP) on behalf of UGE USA INC for the installation of a 2.0 MW PV facility in Dover, ME and interconnecting to the Dover substation via the 815D2 circuit. | 2024-06-02 | Approved Withdrawn | 8/31/2023 2/13/2025
CMP-23-G61 | 2023-08-24 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Phase 2 Project - Piscataquis Valley Solar LLC | Generator application from Central Maine Power (CMP) on behalf of Piscataquis Valley Solar LLC for the installation of a 1.985 MW PV facility in Dover, ME and interconnecting to the Dover substation via the 815D1 circuit. | 2024-06-01 | Approved Withdrawn | 8/31/2023 1/22/2025
CMP-23-G62 | 2023-08-24 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Phase 2 Project - FFP Origination LLC | Generator application from Central Maine Power (CMP) on behalf of FFP Origination LLC for the installation of a 1.998 MW PV facility in Monson, ME and interconnecting to the Monson substation via the 834D2 circuit. | 2024-08-31 | Approved Withdrawn | 8/31/2023 6/18/2024
CMP-23-G66 | 2023-08-24 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Phase 2 Project - TPE Development LLC | Generator application from Central Maine Power (CMP) on behalf of TPE Development LLC for the installation of a 4.8 MW PV facility in Newport, ME and interconnecting to the Newport substation via the 837D2 circuit. | 2024-08-31 | Approved Withdrawn | 8/31/2023 6/18/2024
CMP-23-G67 | 2023-08-24 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Phase 2 Project - BD Solar Dexter LLC | Generator application from Central Maine Power (CMP) on behalf of BD Solar Dexter LLC for the installation of a 3.988 MW PV facility in Dexter, ME and interconnecting to the Dexter substation via the 813D1 circuit. | 2024-12-31 | Approved | 2023-08-31
CMP-23-G68 | 2023-08-24 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Phase 2 Project - Corrina Solar 1 LLC | Generator application from Central Maine Power (CMP) on behalf of Corrina Solar 1 LLC for the installation of a 4.925 MW PV facility in Corinna, ME and interconnecting to the Corinna substation via the 811D1 circuit. | 2024-09-01 | Approved | 2023-08-31
CMP-23-G69 | 2023-08-24 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Phase 2 Project - BD Solar Corinna LLC | Generator application from Central Maine Power (CMP) on behalf of BD Solar Corinna LLC for the installation of a 2.0 MW PV facility in Corinna, ME and interconnecting to the Corrina substation via the 811D1 circuit. | 2024-12-31 | Approved Withdrawn | 8/31/2023 1/22/2025
CMP-23-G70 | 2023-08-24 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Phase 2 Project - USS Blaine Solar LLC | Generator application from Central Maine Power (CMP) on behalf of USS Blaine Solar LLC for the installation of a 3.0 MW PV facility in Dexter, ME and interconnecting to the Dexter substation via the 813D1 circuit. | 2024-12-01 | Approved Withdrawn | 8/31/2023 3/18/2025
CMP-23-G71 | 2023-08-24 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Phase 2 Project - Pittsfield Solar 1 LLC | Generator application from Central Maine Power (CMP) on behalf of Pittsfield Solar 1 LLC for the installation of a 4.95 MW PV facility in Pittsfield, ME and interconnecting to the Pittsfield substation via the 842D1 circuit. | 2024-09-01 | Approved Withdrawn | 8/31/2023 1/22/2025
CMP-23-G72 | 2023-08-24 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Phase 2 Project - Snake Root Solar LLC | Generator application from Central Maine Power (CMP) on behalf of Snake Root Solar LLC for the installation of a 4.98 MW PV facility in Pittsfield, ME and interconnecting to the Burnham substation via the 807D1 circuit. | 2024-08-01 | Approved | 2023-08-31
CMP-23-T18 | 2023-08-24 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Phase 2 Project - Dogtown Capacitor | Transmission application from Central Maine Power (CMP) for the installation of a 20 MVAR capacitor bank at the Dogtown 115 kV SVC station. | 2025-10-31 | Approved | 2023-08-31
NEO-23-G01 | 2023-07-26 | Queue Position 944 (QP 944) Offshore Wind Project | Generator application from North East Offshore LLC for the installation of a 1,200 MW (net) offshore wind farm interconnecting to the Brayton Point 345 kV substation via a new 345 kV generator lead line. | 2026-05-31 | Approved | 2023-08-29
NEO-23-T01 | 2023-07-26 | Queue Position 944 (QP 944) Offshore Wind Project | Transmission application from North East Offshore LLC for the installation of a HVDC export system and 1,350 MVA, 345/365 kV transformer. | 2026-05-31 | Approved | 2023-08-29
NEO-23-T02 | 2023-07-26 | Queue Position 944 (QP 944) Offshore Wind Project | Transmission application from North East Offshore LLC for the installation of two 0.5-mile, 345 kV HVAC generator lead lines. | 2026-05-31 | Approved | 2023-08-29
NEO-23-T03 | 2023-07-26 | Queue Position 944 (QP 944) Offshore Wind Project | Transmission application from North East Offshore LLC for the installation of an offshore 330 kV substation and two 670 MVA, 330/66 kV transformers. | 2026-05-31 | Approved | 2023-08-29
NEP-23-T04 | 2023-07-20 | Queue Position 944 (QP 944) Offshore Wind Project | Transmission application from New England Power to expand the 345 kV GIS building and add a new 2-breaker bay to accommodate the generator lead lines. | 2027-05-31 | Approved | 2023-08-29
JUP-23-G02 | 2023-07-18 | Queue Position 1143 (QP 1143) 500 MW Singleton BESS Project | Generator application from Jupiter Power for the installation of a 500 MW/2,000 MWh battery energy storage system interconnecting to the Mystic 345 kV substation. | 2026-05-31 | Approved | 2023-08-29
JUP-23-T02 | 2023-07-18 | Queue Position 1143 (QP 1143) 500 MW Singleton BESS Project | Transmission application from Jupiter Power for the installation of two new 345/34.5/13.2 kV transformers at the Singleton project site and a 1.5-mile generator lead line. | 2026-05-31 | Approved | 2023-08-29
ES-23-T56 | 2023-07-19 | Queue Position 1143 (QP 1143) 500 MW Singleton BESS Project | Transmission application from Eversource Energy for the installation of a new duct bank, three termination stanchions, three lightning arrestors, disconnect switch, three CCVTs, and protection equipment at Mystic substation. | 2026-05-31 | Approved | 2023-08-29
VP-23-G02 | 2023-07-26 | Queue Position 1145 (QP 1145) 20.45 MW Solar Project | Generator application from Versant Power on behalf of Trenton Solar, LLC for the installation of a 20.45 MW (net) solar facility in Trenton, ME and interconnecting to the 115 kV switching station north of Trenton substation. | 2024-07-08 | Approved | 2023-08-29
VP-23-T01 | 2023-07-26 | Queue Position 1145 (QP 1145) 20.45 MW Solar Project | Transmission application from Versant Power for the installation of a new three-breaker ring bus switching station on Line 57 between Waltham and Trenton substation. | 2024-07-08 | Approved | 2023-08-29
VP-23-T02 | 2023-07-26 | Queue Position 1145 (QP 1145) 20.45 MW Solar Project | Transmission application from Versant Power for the installation of a 115/34.5/13.8 kV, 18 MVA interconnection transformer. | 2024-07-08 | Approved | 2023-08-29
CMP-23-G63 | 2023-07-19 | Queue Position 1146 (QP 1146) 40.355 MW Solar Project | Generator application from Central Maine Power (CMP) on behalf of Swain Solar, LLC for the installation of a 40.355 MW (net) solar facility interconnecting to a new 115 kV switching station. | 2024-07-09 | Approved Withdrawn | 8/29/2023 10/30/2024
CMP-23-T13 | 2023-07-19 | Queue Position 1146 (QP 1146) 40.355 MW Solar Project | Transmission application from Central Maine Power for the installation of a new 115 kV three-breaker ring bus switching station on Section 270 between Rumford substation and Roxbury substation. | 2024-07-09 | Approved Withdrawn | 8/29/2023 10/30/2024
CMP-23-T14 | 2023-07-19 | Queue Position 1146 (QP 1146) 40.355 MW Solar Project | Transmission application from Central Maine Power for the installation of a 115 kV/34.5/13.8 kV main power transformer and breaker. | 2024-07-09 | Approved Withdrawn | 8/29/2023 10/30/2024
CMP-23-G64 | 2023-07-19 | Queue Position 1169 (QP 1169) 1.999 MW Solar Project | Generator application from Central Maine Power (CMP) on behalf of Roxbury Solar Farm LLC for the installation of a 1.999 MW (net) solar facility interconnecting to the 12.47 kV circuit 447D1, approximately 7.46 miles from Rumford substation. | 2025-02-07 | Approved | 2023-08-29
CMP-23-G65 | 2023-07-19 | Queue Position 1190 (QP 1190) 33.1 MW Solar Project | Generator application from Central Maine Power (CMP) on behalf of Warren Meadow Solar Station LLC for the installation of a 33.1 MW (net) solar facility interconnecting to a modified QP 1086 switching station. | 2025-12-30 | Approved | 2023-08-29
CMP-23-T15 | 2023-07-19 | Queue Position 1190 (QP 1190) 33.1 MW Solar Project | Transmission application from Central Maine Power to modify the QP 1086 115 kV three-breaker ring bus switching station to a four-breaker ring bus. | 2025-12-30 | Approved | 2023-08-29
CMP-23-T16 | 2023-07-19 | Queue Position 1190 (QP 1190) 33.1 MW Solar Project | Transmission application from Central Maine Power for the installation of a 115 kV/34.5 kV main power transformer and breaker. | 2025-12-30 | Approved | 2023-08-29
CMP-23-T10 | 2023-07-26 | Upper Maine 2029 Solutions Project | Transmission application from Central Maine Power for the rebuild of Highland substation to a breaker-and-a-half scheme. | 2028-07-31 | Approved | 2023-08-29
CMP-23-T11 | 2023-07-26 | Upper Maine 2029 Solutions Project | Transmission application from Central Maine Power (CMP) for the installation of a +50/-25 MVAR synchronous condenser at Highland substation | 2028-07-31 | Approved | 2023-08-29
CMP-23-T12 | 2023-07-26 | Upper Maine 2029 Solutions Project | Transmission application from Central Maine Power for the installation of a 15 MVAR capacitor bank at Belfast substation. | 2028-07-31 | Approved | 2023-08-29
HMLP-23-T01 | 2023-07-31 | Hingham Municipal Lighting Plant (HMLP) New 115 kV Transmission Supply Project | Transmission application from Hingham Municipal Lighting Plant for the construction of a new 115 kV four-breaker ring bus station and installation of a 1,500-foot 115 kV underground tie cable between the new station and the existing Hobart station. | 2025-12-31 | Approved | 2023-08-21
HMLP-23-T02 | 2023-07-31 | Hingham Municipal Lighting Plant (HMLP) New 115 kV Transmission Supply Project | Transmission application from Hingham Municipal Lighting Plant for the installation of a radial 3.7-mile 115 kV underground cable from the new station to Eversource’s Broad Street station. | 2025-12-31 | Approved | 2023-08-21
ES-23-T53 | 2023-07-31 | Hingham Municipal Lighting Plant (HMLP) New 115 kV Transmission Supply Project | Transmission application from Eversource Energy for the construction of a new 115 kV three-breaker ring bus switching station in Weymouth, MA. | 2025-12-31 | Approved | 2023-08-21
ES-23-X02 | 2023-07-31 | Hingham Municipal Lighting Plant (HMLP) New 115 kV Transmission Supply Project | Transmission application from Eversource Energy to modify the Edgar station RAS to monitor line flows only on the four Edgar station to Holbrook station 115 kV lines and remove line open status utilization. | 2025-12-31 | Approved | 2023-08-21
ES-23-T49 | 2023-08-01 | Resistance Substation Retirement Project | Transmission application from Eversource Energy to retire 115 kV Resistance substation, retire the 115 kV T13 line between Schiller substation and Resistance substation, and remove the T130 breaker at the Schiller substation. The load at Resistance substation will be transferred to 115 kV Portsmouth substation. | 2024-03-31 | Approved | 2023-08-21
NEP-20-GNF06 Rev.2 | 2023-07-31 | Lodestar Energy, LLC - 1340 Lunenburg Road Solar | Generator notification from New England Power on behalf of Lodestar Energy, LLC for the installation of 3.875 MW Solar PV in Lancaster, MA and interconnecting to 1340 Lunenburg Road, Lancaster, MA via the 227W1 circuit out of Laurel Circle substation. | 2021-06-11 | Notification | 2023-08-29
GMP-23-G20 | 2023-07-13 | ER Kendall Hill Solar - 593 Kendall Hill Road Solar | Generator notification from Green Mountain Power on behalf of ER Kendall Hill Solar, LLC for the installation of 2.2 MW Solar PV in Pittsford, VT and interconnecting to 593 Kendall Hill Road, Pittsford, VT via the G10 circuit out of Pittsford Village substation. | 2023-12-31 | Notification | 2023-08-29
ES-23-G50 | 2023-07-31 | Glastonbury Solar One, LLC - 17 Wickham, Road Solar | Generator notification from Eversource Energy on behalf of behalf of Glastonbury Solar One, LLC for the installation of a 3.0 MW Solar PV in Glastonbury, CT and interconnecting to 17 Wickham Road, Glastonbury, CT via the 22R5 circuit out of Hopewell substation. | 2024-12-31 | Notification | 2023-08-29
NEP-23-GNF05 | 2023-07-31 | Bear Peak Power, LLC - 0 Christopher Columbus Drive Solar and Battery | Generator notification from New England Power on behalf of Bear Peak Power, LLC foe the installation of 1.25 MW Solar PV and 0.64 MW/1.362 MWh DC Coupled Battery in Berkshire, MA and interconnecting to 0 Christopher Columbus Drive, Berkshire, MA via the 1021W2 circuit out of Adams substation. | 2025-12-01 | Notification | 2023-08-29
NEP-20-GNF33 Rev.1 | 2023-07-31 | Rehoboth Renewables, LLC - 86 Pond Streer Solar and Battery | Generator notification from New England Power on behalf of Rehoboth Renewables, LLC for the installation of 3.06 MW Solar PV and 2.0 MW/5.18 MWh DC Coupled Battery in Rehoboth, MA and interconnecting to 86 Pond Street, Rehoboth, MA via the 7L4 circuit out of Mink Street substation. | 2025-12-01 | Notification | 2023-08-29
CMP-23-G45 | 2023-06-26 | ME I Stockton Springs McKenney 1.99 Solar Project | Generator application from Central Maine Power on behalf of ME I Stockton Springs McKenney LLC for the installation of a 1.99 MW solar facility in Stockton Springs, ME and interconnecting to the Searsport substation via the 850D1 circuit. | 2024-06-01 | Approved Withdrawn | 8/8/2023 6/18/2024
ES-23-G01 | 2023-06-29 | LSE Bootes 2.6 MW Solar Project | Generator application from Eversource Energy on behalf of Lodestar Energy LLC for the installation of a 2.6 MW solar facility in Enfield, CT and interconnecting to the Scitico substation via the 27H4 circuit. | 2023-12-31 | Approved | 2023-08-08
ES-23-G05 Rev.1 | 2023-06-26 | Lodestar Energy LLC, 191/181 Lovers Lane Solar | Generator notification from Eversource Energy on behalf of Lodestar Energy LLC for the installation of a 2.996 Solar PV in Torrington, CT and interconnecting to 191/181 Lovers Lane, Torrington, CT via the 1B12 circuit out of Franklin Drive substation. | 2024-05-31 | Notification | 2023-08-08
GMP-23-G19 | 2023-06-26 | Midway Ave Solar LLC, Midway Avenue Solar | Generator notification from Green Mountain Power on behalf of Midway Ave Solar LLC for the installation of a 2.2 MW Solar PV in Berlin, VT and interconnecting to Midway Avenue, Berlin, VT via the G5 circuit out of the Berlin substation. | 2024-08-04 | Notification | 2023-08-08
ES-22-G16 Rev.1 | 2023-06-28 | Greenskies Clean Energy LLC, Jeremy Hill Road Solar | Generator notification from Eversource Energy on behalf of Greenskies Clean Energy LLC for the installation of a 4.99875 MW Solar PV in Stonington, CT and interconnecting to Jeremy Hill Road, Stonington, CT via the 32P4 circuit out of Shunock substation. | 2023-08-31 | Notification | 2023-08-08
RIE-23-GNF02 | 2023-06-29 | MassAmerican Energy, 1193 Broad Street Solar | Generator notification from Rhode Island Energy on behalf of MassAmerican Energy for the installation of a 2.9 MW Solar PV in Central Falls, RI and interconnecting to 1193 Broad Street, Central Falls, RI via the 102W50 circuit out of Valley substation. | 2024-09-01 | Notification | 2023-08-08
UI-23-G02 | 2023-06-30 | North Haven One, LLC, 122 Mill Road Solar | Generator notification from United Illuminating on behalf of North Haven One, LLC for the installation of a 1.625 MW Solar PV in North Haven, CT and interconnecting to 122 Mill Road, North Haven, CT via the 1645 circuit out of Sackett substation. | 2023-10-01 | Notification | 2023-08-08
NEP-19-G30-018 Rev.1 | 2023-06-30 | BlueWave Solar, 3090 Palmer Street Solar | Generator notification from New England Power on behalf of BlueWave Solar for the installation of a 1.986 MW Solar PV in Palmer, MA and interconnecting via the 523L1 circuit out of the Thorndike substation. | 2023-12-02 | Notification | 2023-08-08
ES-23-G23 | 2023-06-20 | Key Capture Energy LLC, 44 Skinner Street Battery | Generator notification from Eversource Energy on behalf of Key Capture Energy LLC for the installation of a 4.9 MW/19.6 MWh Battery in East Hampton, CT and interconnecting to 44 Skinner Street, East Hampton, CT via the 21H9 circuit out of the Portland substation. | 2025-07-27 | Notification | 2023-08-08
ES-23-G49 | 2023-06-28 | Delorean Power LLC, 1111 Portland-Cobalt Road Battery | Generator notification from Eversource Energy on behalf of Delorean Power LLC for the installation of a 4.99 MW/25.4 MWh Battery in Portland, CT and interconnecting to 1111 Portland-Cobalt Road, Portland, CT via the 21H9 circuit out of Portland substation. | 2024-06-01 | Notification | 2023-08-08
NEP-23-GNF02 | 2023-06-30 | UGE USA, Inc., 21 Rockdale Street Battery | Generator notification from New England Power on behalf of UGE USA, Inc. for the installation of a 4.99 MW/19.96 MWh Battery in Worcester, MA and interconnecting to 21 Rockdale Street, Worcester, MA via the 24W4 circuit out of Greendale substation. | 2025-12-01 | Notification Withdrawn | 8/8/2023 3/19/2024
NEP-23-GNF03 | 2023-06-30 | UGE, USA, Inc., 3 Woburn Street Battery | Generator notification from New England Power on behalf of UGE USA, Inc. for the installation of a 4.0 MW/16.0 MWh Battery in Worcester, MA and interconnecting to 3 Woburn Street, Worcester, MA via the 24W4 circuit out of Greendale substation. | 2025-12-01 | Notification Withdrawn | 8/8/2023 3/19/2024
ES-21-G113 Rev.1 | 2023-06-27 | MCPF Needham, LLC, 89A Street Solar and Battery | Generator notification from Eversource Energy on behalf of MCPF Needham, LLC for the installation of a 1.3 MW Solar PV and 0.528 MW/1.112 MWh AC Coupled Battery in Needham, MA and interconnecting via the 292-H9 circuit out of Highlands substation. | 2023-07-31 | Notification | 2023-08-08
NEP-19-G30-036 Rev.2 | 2023-06-30 | BlueWave Solar, L22 Sykes Street Solar and Battery | Generator notification from New England Power on behalf of BlueWave Solar for the installation of a 4.93 MW Solar PV and 2.75 MW/11.0 MWh DC Coupled Battery in Palmer, MA and interconnecting via the 0504 circuit out of the Palmer substation. | 2023-11-23 | Notification | 2023-08-08
NEP-23-GNF04 | 2023-06-30 | Bloom Energy, 100 Research Drive Fuel Cell | Generator notification from New England Power on behalf of Bloom Energy for the installation of a 3.0 MW Fuel Cell in Worcester, MA and interconnecting to 100 Research Drive via the 27W3 circuit out of Bloomingdale substation. | 2025-12-01 | Notification | 2023-08-08
NEP-23-T03 | 2023-06-16 | Water Street Substation Transformer Replacement | Transmission notification from New England Power for the replacement of the existing load-serving transformer at Water Street substation due to asset condition issues. | 2028-05-19 | Notification | 2023-07-19
ES-23-G06 | 2023-05-26 | Eversource Enfield-Windsor Locks-Rockville Distributed Energy (DER) Group - Wildcat Renewables - Orcuttville Solar | Generator application from Eversource Energy (ES) on behalf of Wildcat Renewables for the installation of a 3.5 MW PV facility in Stafford, CT and interconnecting to the Blair substation via the 23.0 kV circuit. | 2023-12-31 | Approved Withdrawn | 6/30/2023 6/18/2024
ES-23-G40 | 2023-05-26 | Eversource Enfield-Windsor Locks-Rockville Distributed Energy (DER) Group - Wildcat Mountain Rd. | Generator application from Eversource Energy (ES) on behalf of Wildcat Renewables, LLC for the installation of a 2.0 MW PV facility in Suffield, CT and interconnecting to the Enfield substation via the 27.6 kV circuit. | 2023-12-31 | Approved Withdrawn | 6/30/2023 8/15/2023
ES-23-G41 | 2023-05-26 | Eversource Enfield-Windsor Locks-Rockville Distributed Energy (DER) Group - Wildcat N. Main St | Generator application from Eversource Energy (ES) on behalf of Wildcat Renewables, LLC for the installation of a 4.0 MW PV facility in Suffield, CT and interconnecting to the Enfield substation via the 27.6 kV circuit. | 2023-12-31 | Approved Withdrawn | 6/30/2023 8/15/2023
ES-23-G42 | 2023-05-26 | Eversource Enfield-Windsor Locks-Rockville Distributed Energy (DER) Group - Verogy Ella Grasso Turnpike | Generator application from Eversource Energy (ES) on behalf of Verogy for the installation of a 4.0 MW PV facility in Windsor Locks, CT and interconnecting to the Enfield substation via the 27.6 kV circuit. | 2024-12-31 | Approved Withdrawn | 6/30/2023 8/15/2023
ES-23-G43 | 2023-05-26 | Eversource Enfield-Windsor Locks-Rockville Distributed Energy (DER) Group - Windsor Locks | Generator application from Eversource Energy (ES) on behalf of Capture Energy LLC for the installation of a 5.02 MW/20.0 MWh Battery in Windsor, CT and interconnecting to the Windsor Locks substation via the 23.0 kV circuit. | 2025-07-27 | Approved | 2023-06-30
ES-23-G44 | 2023-05-26 | Eversource Enfield-Windsor Locks-Rockville Distributed Energy (DER) Group - VCP Windsor | Generator application from Eversource Energy (ES) on behalf of Verogy for the installation of a 3.75 MW PV facility in Windsor, CT and interconnecting to the Windsor Locks substation via the 23.0 kV circuit. | 2024-06-30 | Approved | 2023-06-30
ES-23-G32 | 2023-05-11 | ECA Solar, 415 Wilwood Avenue Solar | Generator notification from Eversource Energy (ES) on behalf of ECA Solar for the installation of a 1.68 MW Solar PV in Woburn, MA and interconnecting to 415 Wildwood Avenue, Woburn, MA via the 375-H3 circuit out of Woburn substation. | 2023-08-08 | Notification | 2023-06-30
ES-23-G47 | 2023-05-22 | Verogy, Creek Row Solar | Generator notification from Eversource Energy (ES) on behalf of Verogy for the installation of a 2.0 MW Solar PV in East Haddam, CT and interconnecting to Creek Row, East Haddam, CT via the 11C13 circuit out of Haddam substation. | 2024-12-31 | Approved Withdrawn | 6/30/2023 8/15/2023
GMP-23-G16 | 2023-05-19 | Stone Mill Solar LLC, 680 East Hubbardton Road Solar | Generator notification from Green Mountain Power on behalf of Stone Mill Solar LLC for the installation of a 2.2 MW Solar PV in Castleton, VT and interconnecting to 680 East Hubbardton Road, Castleton, VT via the G37 circuit out of Castleton substation. | 2023-12-04 | Notification | 2023-06-30
GMP-23-G17 | 2023-05-19 | Evergreen Road Solar LLC, Mahar Road Solar | Generator notification from Green Mountain Power on behalf of Evergreen Road Solar LLC for the installation of a 2.2 MW Solar PV in Fair Haven, VT and interconnecting to Mahar Road, Fair Haven, VT via the G24 circuit out of Hydeville substation. | 2023-12-31 | Notification | 2023-06-30
GMP-23-G18 | 2023-05-19 | Steinberg Road Solar LLC, Steinberg Road Solar | Generator notification from Green Mountain Power on behalf of Steinberg Road Solar LLC for the installation of a 2.2 MW Solar PV in Brandon, VT and interconnecting to Steinberg Road, Brandon, VT via the G70 circuit out of Brandon substation. | 2024-06-01 | Notification | 2023-06-30
ES-23-G31 | 2023-05-11 | Silo Electric LLC - 285 Medford Street Battery | Generator notification from Eversource Energy (ES) on behalf of Silo Electric LLC for the installation of a 4.999 MW/11.008 MWh Battery in Charlestown, MA and interconnecting to 285 Medford Street, Charlestown, MA via the 250-H3 circuit out of Mystic substation. | 2025-03-31 | Notification | 2023-06-30
ES-23-G36 | 2023-05-11 | Silver Street Energy Storage, LLC 404 Silver Street Battery | Generator notification from Eversource Energy (ES) on behalf of Silver Street Energy Storage, LLC for the installation of a 4.99 MW/19.96 MWh Battery in Agawam, MA and interconnecting to 404 Silver Street, Agawam, MA via the 30A6 circuit out of Silver substation. | 2025-12-21 | Notification | 2023-06-30
ES-23-G38 | 2023-05-11 | Baystate Medical Center Inc. 759 Chestbut Street Battery | Generator notification from Eversource Energy (ES) on behalf of Baystate Medical Center Inc. for the installation of a 2.0 MW/4.128 MWh Battery in Springfield, MA and interconnecting to 759 Chestnut Street, Springfield, MA via the 21S2 circuit out of Clinton substation. | 2025-12-31 | Notification | 2023-06-30
ES-23-G46 | 2023-05-23 | OnSite Renewables, LLC, 130 Worcester Road Battery | Generator notification from Eversource Energy (ES) on behalf of OnSite Renewables, LLC for the installation of a 4.9992 MW/18.432 MWh Battery in Framingham, MA and interconnecting to 130 Worcester Road, Framingham, MA via the 433-H11 circuit out of Speen Street substation. | 2023-10-01 | Notification | 2023-06-30
FGE-23-G02 | 2023-04-28 | OnSite Renewables, LLC, 99 Development Road Battery | Generator notification from Fitchburg Gas and Electric on behalf of OnSite Renewables, LLC for the installtion of a 4.9992 MW/18.432 MWh Battery in Fitchburg, MA and interconnecting to 99 Development Road, Fitchburg, MA via the 50W55 circuit out of Princeton Road substation. | 2023-10-01 | Notification | 2023-06-30
ES-23-G45 | 2023-05-25 | Endurant Energy, 400 Aircraft Road Battery | Generator notification from Eversource Energy (ES) on behalf of Endurant Energy for the installation of 2.992MW/6.0 MWh Battery in Middletown, CT and interconnecting to 400 Aircraft Road, Middletown, CT via the 13.8 kV circuit out of Middletown substation. | 2025-01-01 | Notification | 2023-06-30
NEP-23-GNF01 | 2023-05-26 | Onsite Renewables, LLC, 995 Andover Street Battery | Generator notification from New England Power on behalf of Onsite Renewables, LLC for the installation of a 4.9992 MW/18.432 MWh Battery in Tewksbury, MA and interconnecting to 995 Andover Street, Tewksbury, MA via the 75L2 circuit out of East Dracut substation. | 2025-07-01 | Notification | 2023-06-30
ES-23-G33 | 2023-05-11 | Nexamp - 149 Franklin Street Solar and Battery | Generator notification from Eversource Energy (ES) on behalf of Nexamp for the installation of a 1.5 MW Solar PV and 1.3651 MW/2.7302 MWh AC Coupled Battery in Stoneham, MA and interconnecting to 149 Franklin Street, Stoneham, MA via the 375-H8 circuit out of North Woburn substation. | 2024-06-03 | Notification | 2023-06-30
ES-23-G39 | 2023-05-11 | Summit Energy Group, 340 Pine Street Solar and Battery | Generator notification from Eversource Energy (ES) on behalf of Summit Energy Group for the installation of a 2.0 MW Solar PV and 1.0 MW/2.224 MWh DC Coupled Battery in Feeding Hills, MA and interconnecting to 340 Pine Street, Feeding Hills, MA via the 30A6 circuit out of Silver substation. | 2025-12-31 | Notification | 2023-06-30
NEP-20-G06-005 Rev.1 | 2023-05-26 | BlueWave Solar, LLC, 45 Oak Street Solar and Battery | Generator notification from New England Power on behalf of BlueWave Solar, LLC for the installation of a 2.0 MW Solar PV and 2.0 MW/8.1 MWh DC Coupled Battery in Douglas, MA and interconnecting to 45 Oak Street, Douglas, MA via the 320W5 circuit out of Whitins Pond substation. | 2025-07-01 | Notification | 2023-06-30
NEP-20-GNF29 Rev.2 | 2023-05-26 | BlueWave Solar, LLC, 903 Tremont Street Solar and Battery | Generator notification from New England Power on behalf of BlueWave Solar, LLC for the installationg of a 2.0 MW Solar PV and 2.0 MW/8.1 MWh DC Coupled Battery in North Dighton, MA and interconnecting to 903 Tremont Street, North Dighton, MA via the 19W74 circuit out of Dighton substation. | 2025-12-31 | Notification | 2023-06-30
ES-19-G32 Rev.3 | 2023-06-05 | TJA Solar, 17 Wilson Street Solar and Battery | Generator notification from Eversource Energy (ES) on behalf of TJA Solar for the installation of a 1.8 MW Solar PV and 1.25 MW/2.78 MWh DC Coupled Battery in Hopkinton, MA and interconnecting to 17 Wilson Street, Hopkinton, MA via the 455-H3 circuit out of Framingham substation. | 2023-08-31 | Notification | 2023-06-30
GMP-23-G14 | 2023-05-10 | Middlebury Resource Recovery Center, LLC 183 Industrial Avenue Biodigester | Generator notification from Green Mountain Power on behalf of Middlebury Resource Recovery Center, LLC for the installation of a 1.014 MW Biodigester in Middlebury, VT and interconnecting to 183 Industrial Avenue, Middlebury, VT via the G26 circuit out of Middlebury substation. | 2024-01-01 | Notification | 2023-06-30
GMP-23-G15 | 2023-05-10 | PurposeEnergy - St. Albans, LLC, Industrial Park Road Biodigester | Generator notification from Green Mountain Power on behalf of PurposeEnergy - St. Albans, LLC for the installation of a 1.014 MW Biodigester in Saint Albans, VT and interconnecting to Industrial Park Road, Saint Albans, VT via the G26 circuit out of Nason Street substation. | 2024-12-01 | Notification | 2023-06-30
UI-23-G01 | 2023-05-26 | SCEF1 Fuel Cell, LLC, 49 Coon Hollow Road Fuel Cell | Generator notification from the United Illuminating Company on behalf of SCEF1 Fuel Cell, LLC for the installation of a 2.8 MW Fuel Cell in Derby, CT and interconnecting to 49 Coon Hollow Road, Derby, CT via the 3674 circuit out of Ansonia substation. | 2023-11-15 | Notification | 2023-06-30
ES-23-T29 | 2023-05-22 | Installation of 4TA Circuit Breaker at Campville 14R | Transmission notification from Eversource Energy for the installation of a circuit breaker (4TA) in series with the existing 4T circuit breaker at Campville 14R substation. | 2024-06-30 | Notification | 2023-06-14
ES-23-T30 | 2023-05-24 | B112 Line Rebuild | Transmission notification from Eversource Energy for the rebuild of 22.88 miles of the B112 115 kV line between Beebe River substation and White Lake substation with 1272 ACSS conductor. | 2024-12-31 | Notification | 2023-06-14
ES-23-T48 | 2023-05-24 | F190 Line Rebuild | Transmission notification from Eversource Energy for the rebuild of 0.02 miles of the F190 115 kV line between the tap on line B112 and the Eversource-Tamworth generator ownership border in NH with 556 ACSR conductor. | 2024-07-01 | Notification | 2023-06-14
JUP-23-G01 | 2023-05-03 | 200 MW Buck Pond BESS Project (QP 1117) | Generator application from Jupiter Power for the installation of a 200 MW battery energy storage system in Westfield, MA and interconnecting to Eversource’s 115 kV Buck Pond substation. | 2026-05-31 | Approved | 2023-05-31
JUP-23-T01 | 2023-05-03 | 200 MW Buck Pond BESS Project (QP 1117) | Transmission application from Jupiter Power for the installation of a new 115/34.5/13.2 kV transformer at the Buck Pond project site and a 0.2 mile 115 kV generation lead line from the project site to the Buck Pond 115 kV substation. | 2026-02-28 | Approved | 2023-05-31
ES-23-T46 | 2023-03-31 | 200 MW Buck Pond BESS Project (QP 1117) | Transmission application from Eversource Energy for the conversion of Buck Pond substation to a four breaker ring bus and to increase the LTE rating of the Woodland – Pleasant 115 kV line. | 2026-02-28 | Approved | 2023-05-31
VP-21-G25 Rev.1 | 2023-04-28 | Three Rivers Solar Power Project (QP 833) | Generator application from Versant Power on behalf of Three Rivers Solar Power, LLC for the installation of a 100 MW solar facility in Northern Maine on the 115 kV Line 93 between Bull Hill and Deblois substations. | 2023-12-31 | Approved | 2023-05-31
VP-21-T05 Rev.1 | 2023-04-28 | Three Rivers Solar Power Project (QP 833) | Transmission application from Versant Power for the installation of a new QP833 collector substation and 85-foot 115 kV generation lead line from the transformer to the switching station. | 2023-12-31 | Approved | 2023-05-31
VP-21-T06 Rev.1 | 2023-04-28 | Three Rivers Solar Power Project (QP 833) | Transmission application from Versant Power for the installation of a new switching station on Line 93 between Bull Hill and Deblois substations. | 2023-12-31 | Approved | 2023-05-31
CMP-23-G39 | 2023-04-27 | Queue Position 1139 (QP 1139) Solar Project | Generator application from Central Maine Power on behalf of Turner Meadow Solar Station LLC for the installation of a 19.81 MW solar facility on CMP 34.5 kV Line Section 50, approximately 3.0-miles from the Turner substation. | 2024-12-31 | Approved | 2023-05-31
CMP-23-G41 | 2023-05-10 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Project - EDF Renewables | Generator application from Central Maine Power (CMP) on behalf of EDF Renewables for the installation a 4.999 MW PV facility in Belfast, ME and interconnecting to the Belfast substation via the 874D1 circuit. | 2024-06-01 | Approved | 2023-05-31
CMP-23-G42 | 2023-05-10 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Project - Belfast Solar 1 | Generator application from Central Maine Power (CMP) on behalf of Belfast Solar 1 LLC for the installation a 3.5 MW PV facility in Belfast, ME and interconnecting to the Belfast substation via the 803D3 circuit. | 2024-09-01 | Approved | 2023-05-31
CMP-23-G43 | 2023-05-10 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Project - Belfast PV LLC | Generator application from Central Maine Power (CMP) on behalf of Belfast PV LLC for the installation a 2.475 MW PV facility in Belfast, ME and interconnecting to the Belfast substation via the 803D6 circuit. | 2024-12-31 | Approved | 2023-05-31
CMP-23-G44 | 2023-05-10 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Project - Penobscot Narrows Solar 1 | Generator application from Central Maine Power (CMP) on behalf of Penobscot Narrows Solar 1, LLC for the installation a 4.98 MW PV facility in Bucksport, ME and interconnecting to the Bucksport substation via the 806D2 circuit. | 2024-01-15 | Approved | 2023-05-31
CMP-23-G46 | 2023-05-10 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Project - ME I Prospect Pond LLC | Generator application from Central Maine Power (CMP) on behalf of ME I Prospect Pond LLC for the installation a 4.974 MW PV facility in Prospect, ME and interconnecting to the Prospect substation via the 846D1 circuit. | 2024-07-07 | Approved | 2023-05-31
CMP-23-G47 | 2023-05-10 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Project - ER Brooks Solar, LLC | Generator application from Central Maine Power (CMP) on behalf of ER Brooks Solar, LLC for the installation a 4.0 MW PV facility in Brooks, ME and interconnecting to the Brooks substation via the 805D1 circuit. | 2024-09-01 | Approved | 2023-05-31
CMP-23-G48 | 2023-05-10 | Central Maine Power Detroit-Guilford-Belfast Area Distributed Energy Resource (DER) Group Study Project - 510 PV Project Development LLC | Generator application from Central Maine Power (CMP) on behalf of 510 PV Project Development LLC for the installation a 1.99 MW PV and 1.99 MW/13.0 MWh DC Coupled Battery facility in Bucksport, ME and interconnecting to the Bucksport substation via the 806D1 circuit. | 2024-12-15 | Approved | 2023-05-31
CMP-23-G40 | 2023-05-02 | Queue Position 905 (QP 905) Battery Energy Storage System Project | Generator application from Central Maine Power on behalf of South Portland ESS LLC for the installation of a 10 MW/20 MWh battery energy storage system interconnecting to the 636D2 34.5 kV circuit out of Mussey Road substation. | 2024-12-01 | Approved Withdrawn | 5/31/2023 6/18/2024
CMP-23-G49 | 2023-05-02 | Queue Position 1087 (QP 1087) Solar Project | Generator application from Central Maine Power on behalf of Fairfield Solar LLC for the installation of an 18.14 MW solar facility interconnecting to an express feeder out of the County Road substation. | 2023-06-30 | Approved | 2023-05-31
ES-23-G26 | 2023-05-02 | USS Vineyard Solar 4 MW Solar Project | Generator application from Eversource Energy on behalf of USS Somers Solar LLC for the installation of a 4.0 MW solar facility in Ellington, CT and interconnecting to the 27H1 circuit out of Scitico substation. | 2023-10-01 | Approved | 2023-05-31
UES-23-G01 | 2023-04-13 | Caspian Epsom Solar LLC, 0 Granny Howe Road Solar | Generator notification from Unitil on behalf of Caspian Epsom Solar LLC for the installation of a 2.5 MW Solar PV in Epsom, NH and interconnecting to 0 Granny Howe Road, Epsom, NH via the 34.5 kV circuit out of Hollis substation. | 2024-05-01 | Notification Withdrawn | 5/31/2023 8/13/2024
VELCO-23-GNF01 | 2023-04-21 | Gray Solar LLC, 1805 Cold River Road Solar | Generator notification from VELCO on behalf of Gray Solar LLC for the installation of a 2.192 MW Solar PV in Rutland, VT and interconnecting to 1805 Cold River Road, Rutland, VT via the G71 circuit out of South Rutland substation. | 2023-04-20 | Notification | 2023-05-31
GMP-23-G01 | 2023-04-28 | Green Mountain Power, 275 Lowery Road Solar | Generator notification from Green Mountain Power for the installation of a 4.999 MW Solar PV in Barre, VT and interconnecting to 275 Lowery Road, Barre, VT via the G3 circuit out of Websterville substation. | 2024-10-01 | Notification | 2023-05-31
GMP-23-G07 | 2023-04-06 | Rest Haven Road Solar, LLC, 370 Rest Haven Road Solar | Generator notification from Green Mountain Power on behalf of Rest Haven Road Solar, LLC for the installation of a 4.95 MW Solar PV in Londonderry, VT and interconnecting to 370 Rest Haven Road, Londonderry, VT via the G27 circuit out of Londonderry substation. | 2025-12-01 | Notification Withdrawn | 5/31/2023 4/17/2024
GMP-23-G08 | 2023-04-20 | Lake Road Solar, 2577 Lake Road Solar | Generator notification from Green Mountain Power on behalf of Lake Road Solar for the installation of a 4.975 MW Solar PV in Charlotte, VT and interconnecting to 2577 Lake Road, Charlotte, VT via the G1 circuit out of Charlotte substation. | 2024-12-31 | Notification | 2023-05-31
GMP-23-G09 | 2023-04-21 | Berlin Dog River Solar LLC, First Street Solar | Generator notification from Green Mountain Power on behalf of Berlin Dog River Solar LLC for the installation of a 2.2 MW Solar PV in Berlin, VT and interconnecting to First Street, Berlin, VT via the G7 circuit out of Mountain View substation. | 2024-03-01 | Notification | 2023-05-31
GMP-23-G10 | 2023-04-28 | Bristol Solar, LLC, 127 Cain Hill Road Solar | Generator notification from Green Mountain Power on behalf of Bristol Solar, LLC for the installation of a 2.2 MW Solar PV in Bristol, VT and interconnecting to 127 Cain Hill Road, Bristol, VT via the G38 circuit out of Hewitt Road substation. | 2023-12-01 | Notification | 2023-05-31
GMP-23-G11 | 2023-04-28 | Halladay Solar LLC, Middle Road South Solar | Generator notification from Green Mountain Power on behalf of Halladay Solar LLC for the installation of a 2.2 MW Solar PV in Middlebury, VT and interconnecting to Middle Road South, Middlebury, VT via the G75 circuit out of East Middlebury substation. | 2023-12-01 | Notification | 2023-05-31
NEP-19-GNF186 Rev.1 | 2023-05-02 | Green Street Power Partners, LLC, 1395 Commerce Way Solar | Generator notification from New England Power on behalf of Green Street Power Partners, LLC for the installation of a 1.08 MW Solar PV in Attleboro, MA and interconnecting to 1395 Commerce Way, Attleboro, MA via the 9L2 circuit out of Read Street substation. | 2023-03-31 | Notification | 2023-05-31
NEP-19-G30-003 Rev.3 | 2023-05-02 | Nexamp, 756 Barre Road Solar | Generator notification from New England Power on behalf of Nexamp for the installation of a 2.0 MW Solar PV in Oakham, MA and interconnecting to 756 Barre Road, Oakham, MA via the 604W2 circuit out of Barre substation. | 2021-04-20 | Notification | 2023-05-31
NEP-19-GNF135 Rev.1 | 2023-05-02 | Aquantum Solutions, LLC, 0 Lovers Lane Solar | Generator notification from New England Power on behalf of Aquantum Solutions, LLC for the installation of a 4.8 MW Solar PV in Haverhill, MA and interconnecting to 0 Lovers Lane, Haverhill, MA via the 76L1 circuit out of Whitter substation. | 2024-12-31 | Notification | 2023-05-31
GMP-23-G12 | 2023-05-02 | ER Waite Cemetery Solar, LLC, 44 Waite Cemetery Road Solar | Generator notification from Green Mountain Power on behalf ER Waite Cemetery Solar, LLC for the installation of a 2.2 MW Solar PV in Shaftsbury, VT and interconnecting to 44 Waite Cemetery Road, Shaftsbury, VT via the G20 circuit out of South Shaftsbury substation. | 2023-10-31 | Notification | 2023-05-31
GMP-23-G13 | 2023-05-03 | Trolley Tracks Solar LLC, York Street Ext Solar | Generator notification from Green Mountain Power on behalf Trolley Tracks Solar LLC for the installation of a 2.05 MW Solar PV in Poultney, VT and interconnecting to York Street Ext, Poultney, VT via the G27 circuit out of Poultney substation. | 2023-12-31 | Notification | 2023-05-31
ES-23-G14 | 2023-04-20 | O&G Industries Inc., Boardman Road Battery | Generator notification from Eversource Energy on behalf of O&G Industries Inc for the installation of a 1.287 MW/2.682 MWh Battery in New Milford, CT and interconnecting to Boardman Road, New Milford, CT via the 12Y9 circuit out of Rocky River substation. | 2024-05-01 | Notification | 2023-05-31
FGE-23-G01 | 2023-04-13 | UR-Silo Devco LLC, 485 Leominster Shirley Road Battery | Generator notification from Fitchburg Gas and Electric Light Company on behalf of UR-Silo Devco LLC for the installation of a 4.999 MW/10.369 MWh Battery in Lunenburg, MA and interconnecting to 485 Leominster Shirley Road, Lunenburg, MA via the 13.8 kV circuit out of Lunenburg substation. | 2024-04-13 | Notification | 2023-05-31
ES-23-G27 | 2023-05-01 | Silo Electric LLC, 30 Speen Street Battery | Generator notification from Eversource Energy on behalf of Silo Electric LLC for the installation of a 4.999 MW/11.008 MWh Battery in Framingham, MA and interconnecting to 30 Speen Street, Framingham, MA via the 433-H2 circuit out of Speen substation. | 2023-11-01 | Notification | 2023-05-31
ES-20-G40 Rev.1 | 2023-04-27 | Ameresco Solar Land Holdings, LLC, 129 French King Highway Solar and Battery | Generator notification from Eversource Energy on behalf of Ameresco Solar Land Holdings LLC for the installation of a 4.98 MW Solar PV and 2.49 MW/7.426 MWh DC Coupled Battery in Erving, MA and interconnecting to 129 French King Highway, Erving, MA via the 21C8 circuit out of the Montague substation. | 2023-09-30 | Notification | 2023-05-31
ES-23-G17 | 2023-04-28 | Frankland Road Solar LLC, 71 Frankland Road Solar and Battery | Generator notification from Eversource Energy on behalf of Frankland Road Solar LLC for the installation of a 4.475 MW Solar PV and 3.0 MW/6.75 MWh AC Coupled Battery in Hopkinton, MA and interconnecting to 71 Frankland Road, Hopkinton, MA via the 455-H8 circuit out of the West Framingham substation. | 2023-10-01 | Notification | 2023-05-31
ES-23-G24 | 2023-05-01 | Ameresco, 1215 Wilbraham Road Solar and Battery | Generator notification from Eversource Energy on behalf of Ameresco for the installation of a 1.2331 MW Solar PV and 1.0 MW/2.97 MWh AC Coupled Battery in Springfield, MA and interconnecting to 1215 Wilbraham Road, Springfield, MA via the 20A14 circuit out of the Breckwood substation. | 2025-12-31 | Notification | 2023-05-31
ES-23-G25 | 2023-05-01 | Ameresco, 1215 Wilbraham Road Solar and Battery | Generator notification from Eversource Energy on behalf of Ameresco for the installation of a 2.54999 MW Solar PV and 1.0 MW/2.97 MWh AC Coupled Battery in Springfield, MA and interconnecting to 1215 Wilbraham Road, Springfield, MA via the 20A33 circuit out of the Breckwood substation. | 2024-02-01 | Notification | 2023-05-31
ES-23-G28 | 2023-05-02 | Consolidated Energy Development, 333 Medford Street Solar and Battery | Generator notification from Eversource Energy on behalf of Consolidated Energy Development for the installation of a 3.3 MW Solar PV and 1.2846 MW/2.5696 MWh AC Coupled Battery in Charlestown, MA and interconnecting to 333 Medford Street, Charlestown, MA via the 250-H1 circuit out of the Mystic substation. | 2023-12-29 | Notification Withdrawn | 5/31/2023 7/16/2024
NEP-20-GNF24 Rev.1 | 2023-05-02 | NextSun Energy, LLC, 19 Fairlee Lane Solar and Battery | Generator notification from New England Power on behalf of NextSun Energy, LLC for the installation of a 2.0 MW Solar PV and 2.019 MW/12.116 MWh DC Coupled Battery in Norton, MA and interconnecting to 19 Fairlee Lane, Norton, MA via the 92W79 circuit out of Easton substation. | 2024-05-01 | Notification | 2023-05-31
CMP-23-G04 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - BWC Little River LLC | Generation application from Central Maine Power (CMP) on behalf of BWC Little River LLC for the installation a 4.925 MW PV facility in Buxton, ME and interconnecting to the Bonny Eagle substation via the 610D2 circuit. | 2028-06-01 | Approved Withdrawn | 4/27/2023 6/18/2024
CMP-23-G05 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - Standish Bonny Eagle Solar 1 LLC | Generation application from Central Maine Power (CMP) on behalf of Standish Bonny Eagle Solar 1 LLC for the installation a 2.49 MW PV facility in Standish, ME and interconnecting to the Bonny Eagle substation via the 610D2 circuit. | 2028-06-01 | Approved Withdrawn | 4/27/2023 2/13/2025
CMP-23-G06 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - BD Solar Fryeburg LLC | Generator application from Central Maine Power (CMP) on behalf of BD Solar Fryeburg LLC for the installation a 4.99 MW PV facility in Fryeburg, ME and interconnecting to the Fryeburg substation via the 415D2 circuit. | 2024-04-01 | Approved | 2023-04-27
CMP-23-G07 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - Naples PV LLC | Generation application from Central Maine Power (CMP) on behalf of Naples PV LLC for the installation a 4.95 MW PV facility in Naples, ME and interconnecting to the Bridgton 34 kV substation via the 406D4 circuit. | 2028-06-01 | Approved Withdrawn | 4/27/2023 6/18/2024
CMP-23-G08 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - Moose Solar, LLC | Generation application from Central Maine Power (CMP) on behalf of Moose Solar, LLC for the installation a 2.25 MW PV facility in Harrison, ME and interconnecting to the Kimball Road substation via the 423D1 circuit. | 2024-08-01 | Approved Withdrawn | 4/27/2023 9/19/2023
CMP-23-G09 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - ECA Solar LLC | Generation application from Central Maine Power (CMP) on behalf of ECA Solar LLC for the installation a 1.35 MW PV facility in Fryeburg, ME and interconnecting to the Fryeburg Tap substation via the 405D1 circuit. | 2023-08-01 | Approved Withdrawn | 4/27/2023 2/13/2025
CMP-23-G10 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - Limerick CSG LLC | Generation application from Central Maine Power (CMP) on behalf of Limerick CSG LLC for the installation a 4.0 MW PV facility in Limerick, ME and interconnecting to the Limerick substation via the 632D1 circuit. | 2028-06-01 | Approved Withdrawn | 4/27/2023 6/18/2024
CMP-23-G11 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - Walden Solar Maine VI LLC | Generation application from Central Maine Power (CMP) on behalf of Walden Solar Maine VI LLC for the installation a 4.95 MW PV facility in West Baldwin, ME and interconnecting to the Baldwin substation via the 691D1 circuit. | 2028-06-01 | Approved Withdrawn | 4/27/2023 9/19/2023
CMP-23-G12 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - Naples Old Country Solar 1 LLC | Generation application from Central Maine Power (CMP) on behalf of Naples Old County Solar 1 LLC for the installation a 4.192 MW PV facility in Naples, ME and interconnecting to the Bridgton substation via the 406D4 circuit. | 2028-06-01 | Approved | 2023-04-27
CMP-23-G13 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - Limington Sokokis Solar 1 LLC | Generator application from Central Maine Power (CMP) on behalf of Limington Sokokis Solar 1 LLC for the installation a 3.45 MW PV facility in Limington, ME and interconnecting to the North Limington substation via the 638D1 circuit. | 2028-06-01 | Approved Withdrawn | 4/27/2023 6/18/2024
CMP-23-G14 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - ISM Solar Bolster Mills, LLC | Generation application from Central Maine Power (CMP) on behalf of ISM Solar Bolster Mills, LLC for the installation a 3.25 MW PV facility in Harrison, ME and interconnecting to the Kimball Road substation via the 423D2 circuit. | 2024-08-01 | Approved | 2023-04-27
CMP-23-G15 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - Naples Solar 1 LLC | Generation application from Central Maine Power (CMP) on behalf of Naples Solar 1 LLC for the installation a 1.98 MW PV facility in Naples, ME and interconnecting to the Bridgton substation via the 406D4 circuit. | 2028-06-01 | Approved Withdrawn | 4/27/2023 9/19/2023
CMP-23-G16 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - Consolidated Edison Solutions LLC | Generation application from Central Maine Power (CMP) on behalf of Consolidated Edison Solutions LLC for the installation a 2.493 MW PV and 2.34 MW/6.078 MWh AC Coupled Battery facility in Denmark, ME and interconnecting to the Denmark substation via the 413D1 circuit. | 2028-06-01 | Approved Withdrawn | 4/27/2023 6/18/2024
CMP-23-G17 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - Parsonfield Sokokis Solar 1 LLC | Generation application from Central Maine Power (CMP) on behalf of Parsonfield Sokokis Solar 1 LLC for the installation a 4.074 MW PV facility in Parsonsfield, ME and interconnecting to the Hiram Tap substation via the 692D1 circuit. | 2028-06-01 | Approved | 2023-04-27
CMP-23-G18 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - NBD Solar Maine LLC | Generation application from Central Maine Power (CMP) on behalf of NBD Solar Maine LLC for the installation a 4.998 MW PV facility in Limington, ME and interconnecting to the North Limington substation via the 638D1 circuit. | 2028-06-01 | Approved | 2023-04-27
CMP-23-G19 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - NBD Solar Maine LLC | Generation application from Central Maine Power (CMP) on behalf of NBD Solar Maine LLC for the installation a 4.998 MW PV facility in Limington, ME and interconnecting to the North Limington substation via the 638D1 circuit. | 2023-06-01 | Approved | 2023-04-27
CMP-23-G20 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - 549 Doles Ridge Road Solar LLC | Generation application from Central Maine Power (CMP) on behalf of 549 Doles Ridge Road Solar LLC for the installation a 4.948 MW PV facility in Limerick, ME and interconnecting to the Limerick substation via the 632D1 circuit. | 2028-06-01 | Approved | 2023-04-27
CMP-23-G22 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - Limerick East Range Solar 1 LLC | Generation application from Central Maine Power (CMP) on behalf of Limerick East Range Solar 1 LLC for the installation a 2.5 MW PV facility in Limerick, ME and interconnecting to the Limerick substation via the 632D2 circuit. | 2028-06-01 | Approved | 2023-04-27
CMP-23-G23 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - Denmark PV LLC | Generation application from Central Maine Power (CMP) on behalf of Denmark PV LLC for the installation a 3.3 MW PV facility in Denmark, ME and interconnecting to the Denmark substation via the 413D2 circuit. | 2028-06-01 | Approved Withdrawn | 4/27/2023 6/18/2024
CMP-23-G24 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - 510 PV Project Development LLC | Generation application from Central Maine Power (CMP) on behalf of 510 PV Project Development LLC for the installation a 4.99 MW PV and 4.99 MW/26.0 MWh DC Coupled Battery facility in Bridgton, ME and interconnecting to the West Bridgton substation via the 458D1 circuit. | 2028-06-01 | Approved Withdrawn | 4/27/2023 6/18/2024
CMP-23-T08 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - North Bridgton Substation | Transmission application from Central Maine Power (CMP) for the installation of a new North Bridgton substation with a new 115/34.5 kV transformer, 115 kV line from Bridgton substation to Kimball substation, and a new 115 kV breaker at Kimball substation. | 2028-12-31 | Approved Withdrawn | 4/27/2023 6/18/2024
CMP-23-T09 | 2023-04-07 | Central Maine Power Kimball Area Distributed Energy Resource (DER) Group Study Project - Lovell Substation - New 115/34.5 kV Transformer | Transmission application from Central Maine Power (CMP) for the installation of a new 115/34.5 kV transformer and high-side breaker at Lovell substation. | 2028-12-31 | Approved Withdrawn | 4/27/2023 6/18/2024
NHT-22-T01 Rev.1 | 2023-04-07 | Line 363 Capacitor Banks Installation Project | Transmission application from New Hampshire Transmission to install two 50 MVAR 345 kV capacitor banks, converted to a C-Type Filter, on Line 363 adjacent to the existing Seabrook line termination yard in Seabrook, NH at a new Browns River station. | 2023-11-30 | Approved | 2023-04-20
VW-19-G01 Rev.2 | 2023-04-19 | Vineyard Wind Generation and Transmission Project | Generator application from Vineyard Wind for the construction of an 843.2 MW offshore wind farm comprising sixty-two 13.6 MW wind turbine generators located on OCS-A 501 south of Martha’s Vineyard and interconnecting to the Eversource transmission system at the Barnstable Switching Station. | 2024-05-27 | Approved | 2023-04-27
VW-19-T01 Rev.2 | 2023-04-20 | Vineyard Wind Generation and Transmission Project | Transmission application from Vineyard Wind for the installation of a single offshore gas-insulated substation (GIS) containing 66 kV switchgear, 220 kV circuit breakers and two 450 MVA 220/66 kV on-load tap-changing transformers. | 2023-06-01 | Approved | 2023-04-27
VW-19-T02 Rev.2 | 2023-04-21 | Vineyard Wind Generation and Transmission Project | Transmission application from Vineyard Wind for the installation of two 220 kV submarine cables from the offshore substation to onshore substation in Hyannis, MA. | 2023-06-01 | Approved | 2023-04-27
VW-19-T03 Rev.2 | 2023-04-22 | Vineyard Wind Generation and Transmission Project | Transmission application from Vineyard Wind for the installation of two 450 MVA 115/220/13.8 kV on-load tap-changing autotransformers, each with four 115 kV circuit breakers and three 220 kV circuit breakers. | 2023-06-01 | Approved | 2023-04-27
VW-19-T04 Rev.2 | 2023-04-23 | Vineyard Wind Generation and Transmission Project | Transmission application from Vineyard Wind for the installation of two 115 kV circuits providing separate Vineyard Wind onshore substation transformer interconnection to distinct Barnstable 115 kV station breaker positions. | 2023-06-01 | Approved | 2023-04-27
VW-19-T05 Rev.2 | 2023-04-24 | Vineyard Wind Generation and Transmission Project | Transmission application from Vineyard Wind for the installation of two +171/-133 MVAR synchronous condensers, each with a dedicated 175 MVA 11.5/115 kV substation transformer connected directly to the 115 kV bus. | 2023-06-01 | Approved | 2023-04-27
ES-19-T06 Rev.1 | 2023-04-25 | Vineyard Wind Generation and Transmission Project | Transmission application from Eversource Energy for the installation of two new 115 kV circuit breakers, relays, controls, and associated equipment at Barnstable Substation #958 in Barnstable, MA. | 2023-05-27 | Approved | 2023-04-27
ES-19-T07 Rev.1 | 2023-04-26 | Vineyard Wind Generation and Transmission Project | Transmission application from Eversource Energy to upgrade the protection systems for Eversource’s Tremont Substation #713 in Wareham, MA. | 2023-10-08 | Approved | 2023-04-27
IES-22-G01 Rev.1 | 2023-04-03 | South Wrentham Battery Energy Storage System Generation and Transmission Project (QP 877) | Generator application from ConnectGen for the installation of 55 3.16 MW inverters for a total of 173.8 MW (170 MW net output) of battery storage located in South Wrentham, MA and interconnecting to the South Wrentham 115 kV Substation. | 2023-12-31 | Approved | 2023-04-27
IES-22-T01 Rev.1 | 2023-04-03 | South Wrentham Battery Energy Storage System Generation and Transmission Project (QP 877) | Transmission application from ConnectGen for the installation of a 34.5/115 kV substation, 13.8/34.5/115 kV power transformer, and 115 kV generator lead line at the South Wrentham BESS project site in South Wrentham, MA. | 2023-12-31 | Approved | 2023-04-27
NEP-22-T05 Rev.1 | 2023-04-03 | South Wrentham Battery Energy Storage System Generation and Transmission Project (QP 877) | Transmission application from New England Power to upgrade the C-181N and D-128N 115 kV lines by increasing the clearances and operating temperatures for the existing bundled 636 AL conductor. | 2027-02-01 | Approved | 2023-04-27
NEP-22-T06 Rev.1 | 2023-04-03 | South Wrentham Battery Energy Storage System Generation and Transmission Project (QP 877) | Transmission application from New England Power for the conversion of South Wrentham substation into a five breaker ring bus and upgrades of terminal equipment and disconnect switches. | 2025-01-01 | Approved | 2023-04-27
NEP-23-G01 | 2023-04-03 | East Longmeadow Affected System Operator (ASO) Distributed Energy Resource (DER) Project - RPG Energy Group | Generator application from New England Power on behalf of RPG Energy Group, LLC for the installation of a 3.0 MW PV and 2.0 MW/4.5 MWh AC Coupled Battery facility in East Longmeadow, MA and interconnecting to the East Longmeadow 69 kV substation via the 508L2 13.2 kV circuit. | 2024-12-01 | Approved Withdrawn | 4/27/2023 9/17/2024
NEP-23-G02 | 2023-04-03 | East Longmeadow Affected System Operator (ASO) Distributed Energy Resource (DER) Project - OnSite Renewables, LLC | Generator application from New England Power on behalf of OnSite Renewables, LLC for the installation of a 4.99 MW/18.43 MWh Battery facility in East Longmeadow, MA and interconnecting to the East Longmeadow 69kV substation via the 508L4 13.2kV circuit. | 2024-12-01 | Approved Withdrawn | 4/27/2023 4/16/2025
CMP-23-G28 | 2023-04-03 | Queue Position 1369 Solar Project | Generator application from Central Maine Power on behalf of Renesola Power Holdings LLC for the installation of a 1.992 MW PV facility in Athens, ME and interconnecting to the Athens substation via the 827D2 circuit. (This PPA was was supposed to be numbered CMP-23-G25) | 2024-10-01 | Approved Withdrawn | 4/27/2023 8/13/2024
ES-23-T47 | 2023-04-04 | Monadnock Substation Rebuild Project | Transmission application from Eversource Energy to rebuild the Monadnock substation and convert it from a straight bus configuration to a five-breaker ring bus configuration and replace the two existing transformers with two 62.5 MVA 115/34.5 kV transformers. | 2024-12-31 | Approved | 2023-04-20
GRH-23-X01 | 2023-03-31 | Sherman U1 Generator AVR Replacement Project | Transmission application from Great River Hydro to replace the existing DC non-continuous acting analog automatic voltage regulator with a new digital automatic voltage regulator on an emergency basis. | 2023-05-09 | Approved | 2023-04-27
ES-21-G17 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - Sup Set | Generator application from Eversource Energy (ES) on behalf of Sup Set for the installation a 2.0 MW PV and 1.65 MW/4.11 MWh AC Coupled Battery facility in Plympton, MA and interconnecting to the Brook Street substation via the 3-51-901 circuit. | 2021-12-01 | Approved | 2023-04-27
ES-21-G56 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - Solar Carver 7 | Generator application from Eversource Energy (ES) on behalf of Solar Carver 7 for the installation a 3.0 MW PV and 3.0 MW/48.0 MWh DC Coupled Battery facility in Wareham, MA and interconnecting to the Tremont substation via the 3-81-81 circuit. | 2021-12-01 | Approved | 2023-04-27
ES-21-G57 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - Wareham County Rd A | Generator application from Eversource Energy (ES) on behalf of Wareham County Rd A for the installation a 4.075 MW PV and 4.075 MW/8.15 MWh DC Coupled Battery facility in Wareham, MA and interconnecting to the Tremont substation via the 3-85-85 circuit. | 2021-12-01 | Approved Withdrawn | 4/27/2023 6/18/2024
ES-21-G58 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - 1 N Carver Solar | Generator application from Eversource Energy (ES) on behalf of 1 N Carver Solar for the installation a 3.0 MW PV and 1.5 MW/3.336 MWh DC Coupled Battery facility in Wareham, MA and interconnecting to the Tremont substation via the 3-81-81 circuit. | 2022-04-01 | Approved Withdrawn | 4/27/2023 12/17/2024
ES-21-G60 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - Wareham County Road D | Generator application from Eversource Energy (ES) on behalf of Wareham County Road D for the installation a 4.98 MW PV and 4.98 MW/9.96 MWh DC Coupled Battery facility in Wareham, MA and interconnecting to the Tremont substation via the 3-85-85 circuit. | 2021-12-01 | Approved Withdrawn | 4/27/2023 6/18/2024
ES-21-G61 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - Ironwood Arwood | Generator application from Eversource Energy (ES) on behalf of Ironwood Atwood for the installation a 2.5 MW PV and 1.5 MW/6.0 MWh DC Coupled Battery facility in Carver, MA and interconnecting to the Tremont substation via the 3-81-950 circuit. | 2021-12-01 | Approved | 2023-04-27
ES-21-G64 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - Wareham Maple Springs Rd P2 | Generator application from Eversource Energy (ES) on behalf of Wareham Maple Springs Rd P2 for the installation a 4.89 MW PV and 4.89 MW/9.78 MWh DC Coupled Battery facility in Wareham, MA and interconnecting to the Wareham substation via the 3-82-82 circuit. | 2021-12-01 | Approved Withdrawn | 4/27/2023 6/18/2024
ES-21-G65 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - Wareham Charge Pond Rd P2 | Generator application from Eversource Energy (ES) on behalf of Wareham Charge Pond Rd P2 for the installation a 4.89 MW PV and 3.75 MW/7.5 MWh DC Coupled Battery facility in Wareham, MA and interconnecting to the Wareham substation via the 3-82-82 circuit. | 2021-06-01 | Approved Withdrawn | 4/27/2023 6/18/2024
ES-21-G66 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - Wankinco | Generator application from Eversource Energy (ES) on behalf of Wankinco for the installation a 4.99 MW PV facility in Carver, MA and interconnecting to the Wareham substation via the 3-83-83 circuit. | 2022-01-01 | Approved Withdrawn | 4/27/2023 11/19/2024
ES-21-G67 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - Old Orchard | Generator application from Eversource Energy (ES) on behalf of Old Orchard for the installation a 2.25 MW PV facility in Wareham, MA and interconnecting to the Wareham substation via the 3-83-83 circuit. | 2022-01-01 | Approved Withdrawn | 4/27/2023 7/16/2028
ES-21-G68 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - Frogfoot | Generator application from Eversource Energy (ES) on behalf of Frogfoot for the installation a 4.5 MW PV facility in Wareham, MA and interconnecting to the Wareham substation via the 3-83-83 circuit. | 2022-01-01 | Approved Withdrawn | 4/27/2023 7/16/2028
ES-21-G69 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - 140 Tihonet Road | Generator application from Eversource Energy (ES) on behalf of 140 Tihonet Road for the installation a 4.995 MW PV and 4.995 MW/30.0 MWh DC Coupled Battery facility in Wareham, MA and interconnecting to the Wareham substation via the 3-83-83 circuit. | 2021-12-01 | Approved | 2023-04-27
ES-21-G70 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - 150 Tihonet Road | Generator application from Eversource Energy (ES) on behalf of 150 Tihonet Road for the installation a 4.99 MW PV and 4.99 MW/25.0 MWh DC Coupled Battery facility in Wareham, MA and interconnecting to the Wareham substation via the 3-83-83 circuit. | 2021-12-01 | Approved | 2023-04-27
ES-21-G71 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - Wareham PV I | Generator application from Eversource Energy (ES) on behalf of Wareham PV I, LLC for the installation a 3.5 MW PV and 2.0 MW/4.0 MWh AC Coupled Battery facility in Wareham, MA and interconnecting to the Wareham substation via the 3-83-83 circuit. | 2021-12-27 | Approved | 2023-04-27
ES-21-G72 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - 27 Charge Pond Road | Generator application from Eversource Energy (ES) on behalf of 27 Charge Pond Road for the installation a 4.99 MW PV and 4.99 MW/30.0 MWh DC Coupled Battery facility in Wareham, MA and interconnecting to the Wareham substation via the 3-83-83 circuit. | 2021-12-01 | Approved | 2023-04-27
ES-21-G73 Rev.2 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - 0 Maple Springs Rd | Generator application from Eversource Energy (ES) on behalf of 0 Maple Springs Rd for the installation a 4.99 MW PV and 4.99 MW/26.0 MWh DC Coupled Battery facility in Wareham, MA and interconnecting to the Wareham substation via the 3-84-84 circuit. | 2022-04-08 | Approved | 2023-04-27
ES-21-G75 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - Fuller Rd, Carver | Generator application from Eversource Energy (ES) on behalf of Fuller Rd, Carver for the installation a 4.999 MW PV and 4.999 MW/11.128 MWh DC Coupled Battery facility in Carver, MA and interconnecting to the West Pond substation via the 3-10-10 circuit. | 2021-12-15 | Approved | 2023-04-27
ES-21-G76 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - 40 Grissom Road PV Project | Generator application from Eversource Energy (ES) on behalf of 40 Grissom Road PV Project for the installation a 1.8 MW PV and 1.0 MW/2.0 MWh AC Coupled Battery facility in Plymouth, MA and interconnecting to the West Pond substation via the 3-12-12 circuit. | 2021-09-01 | Approved | 2023-04-27
ES-21-G77 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - Johnson | Generator application from Eversource Energy (ES) on behalf of Johnson for the installation a 2.468 MW PV and 2.0 MW/22.26 MWh DC Coupled Battery facility in Carver, MA and interconnecting to the West Pond substation via the 3-10-930 circuit. | 2022-01-01 | Approved | 2023-04-27
ES-21-G78 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - 21 Ward Street | Generator application from Eversource Energy (ES) on behalf of 21 Ward Street for the installation a 3.0 MW PV and 3.0 MW/15.0 MWh DC Coupled Battery facility in Carver, MA and interconnecting to the West Pond substation via the 3-10-930 circuit. | 2021-12-01 | Approved | 2023-04-27
ES-21-G79 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - Old Orchard | Generator application from Eversource Energy (ES) on behalf of Old Orchard for the installation a 3.5 MW PV facility in Carver, MA and interconnecting to the West Pond substation via the 3-10-917 circuit. | 2022-01-01 | Approved Withdrawn | 4/27/2023 11/19/2024
ES-21-G80 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - CVE - Carver | Generator application from Eversource Energy (ES) on behalf of CVE - Carver for the installation a 1.625 MW PV Coupled Battery facility in Carver, MA and interconnecting to the West Pond substation via the 3-10-929 circuit. | 2021-12-01 | Approved | 2023-04-27
ES-21-G82 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - 0 Plymouth St, Carver | Generator application from Eversource Energy (ES) on behalf of 0 Plymouth St, Carver for the installation a 3.0 MW PV and 2.0 MW/4.24 MWh AC Coupled Battery facility in Carver, MA and interconnecting to the West Pond substation via the 3-10-10 circuit. | 2021-12-15 | Approved | 2023-04-27
ES-21-G83 Rev.1 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - 230 Plymouth Street | Generator application from Eversource Energy (ES) on behalf of 230 Plymouth Street for the installation a 3.0 MW PV and 2.0 MW/4.24 MWh AC Coupled Battery facility in Carver, MA and interconnecting to the West Pond substation via the 3-10-930 circuit. | 2021-12-15 | Approved | 2023-04-27
ES-23-G19 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - A. D. Makepeace Company | Generator application from Eversource Energy (ES) on behalf of A.D. Makepeace Company for the installation of a 3.6 MW PV facility in Wareham, MA and interconnecting to the Tremont substation via the 85 circuit. | 2023-05-01 | Approved Withdrawn | 4/27/2023 6/18/2024
ES-23-G20 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - Clearway Energy | Generator application from Eversource Energy (ES) on behalf of Clearway Energy for the installation of a 1.0 MW PV and 1.0 MW/5.204 MWh DC Coupled Battery facility in Wareham, MA and interconnecting to the Tremont substation via the 85 circuit. | 2023-05-01 | Approved | 2023-04-27
ES-23-G21 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - Clearway Energy | Generator application from Eversource Energy (ES) on behalf of Clearway Energy for the installation of a 5.0 MW PV and 2.31 MW/4.79 MWh AC Coupled Battery facility in Wareham, MA and interconnecting to the Tremont substation via the 85 circuit. | 2023-05-01 | Approved | 2023-04-27
ES-23-G22 | 2023-04-04 | Eversource Southeast Massachusetts (SEMA) and Cape Cod Affected System Operator (ASO) Distributed Energy Resource (DER) Project Revisions - Clearway Energy | Generator application from Eversource Energy (ES) on behalf of Clearway Energy for the installation of a 3.0 MW PV and 2.31 MW/4.79 MWh AC Coupled Battery facility in Wareham, MA and interconnecting to the Tremont substation via the 85 circuit. | 2023-05-01 | Approved | 2023-04-27
GMP-23-G05 | 2023-03-15 | Green Mountain Power - W. Salisbury Road Solar | Generator notification from Green Mountain Power for the installation of a 4.95 MW Solar PV in Salisbury, VT and interconnecting to W. Salisbury Road, Salisbury, VT via the G23 circuit out of the Salisbury substation. | 2024-05-07 | Notification | 2023-04-27
ES-23-G18 | 2023-03-06 | Silo Electric LLC - 425 Meadow St Battery | Generator notification from Eversource Energy on behalf of Silo Electric LLC for the installation of a 4.999 MW/11.008 MWh Battery in Chicopee, MA and interconnecting to 425 Meadow St, Chicopee, MA via the 21N7 circuit out of the Piper substation. | 2024-06-30 | Notification | 2023-04-27
ES-23-G12 | 2023-03-20 | ReNew Developers, LLC - 234 Riverside Ave Fuel Cell | Generator notification from Eversource Energy on behalf of ReNew Developers, LLC for the installation of a 4.0 MW Fuel Cell in Bristol, CT and interconnecting to 234 Riverside Ave, Bristol, CT via the 11K47 circuit out of the Bristol substation. | 2024-03-29 | Notification | 2023-04-27
GMP-23-G06 | 2023-03-29 | Green Mountain Power - 5033 Main Road Wind | Generator notification from Green Mountain Power for the installation of 2.2 MW Wind in Stamford, VT and interconnecting to 5033 Main Road, Stamford, VT via the G1 circuit out of the Stamford substation. | 2024-05-07 | Notification Withdrawn | 4/27/2023 3/19/2024
ES-23-T26 | 2023-03-24 | Partial Rebuild of Line 1637 | Transmission notification from Eversource Energy for the partial rebuild of Line 1637 to replace 4.5 miles of existing 556-kcmil ACSR conductor with 1590-kcmil ACSS conductor. | 2024-06-30 | Notification | 2023-04-20
ES-23-T27 | 2023-03-24 | Partial Rebuild of Line 1720 | Transmission notification from Eversource Energy for the partial rebuild of Line 1720 to replace 4.5 miles of existing 556-kcmil ACSR conductor with 1590-kcmil ACSS conductor. | 2024-06-30 | Notification | 2023-04-20
ES-23-T31 | 2023-03-24 | Partial Rebuild of Line 1355-1 | Transmission notification from Eversource Energy for the partial rebuild of Line 1355-1 to replace 1.7 miles of existing 556-kcmil ACSR conductor with 1272-kcmil ACSS conductor. | 2024-06-30 | Notification | 2023-04-20
ES-23-T32 | 2023-03-24 | Rebuild of Line 1355-2 | Transmission notification from Eversource Energy for the rebuild of Line 1355-2 to replace 0.7 miles of existing 4/0 copper conductor with 1272-kcmil ACSS conductor. | 2024-06-30 | Notification | 2023-04-20
ES-23-T33 | 2023-03-24 | Rebuild of Line 1355-3 | Transmission notification from Eversource Energy for the rebuild of Line 1355-3 to replace 4.6 miles of existing 556-kcmil ACSR conductor with 1272-kcmil ACSS conductor. | 2024-06-30 | Notification | 2023-04-20
ES-23-T34 | 2023-03-24 | Partial Rebuild of Line 1610-1 | Transmission notification from Eversource Energy for the partial rebuild of Line 1610-1 to replace 6.3 miles of existing 556-kcmil ACSR conductor with 1272-kcmil ACSS conductor. | 2024-06-30 | Notification | 2023-04-20
ES-23-T35 | 2023-03-24 | Rebuild of Line 1690 | Transmission notification from Eversource Energy for the rebuild of Line 1690 to replace 5.3 miles of existing 4/0 copper conductor and 795-kcmil ACSR conductor with 1272-kcmil ACSS conductor. | 2024-06-30 | Notification | 2023-04-20
ES-23-X01 | 2023-03-24 | Altresco SPS Retirement | Transmission notification from Eversource Energy for the retirement of the Altresco Special Protection Scheme as a result of an increase to the ratings of both Lines 1715 and 1816. | 2023-08-01 | Notification | 2023-04-20
ES-21-T38 Rev.2 | 2023-04-05 | Shunock 32P Synchronous Condenser and Ring Bus Expansion | Transmission notification from Eversource Energy for the installation of one +55/-29 MVAR synchronous condenser at Shunock (+50/-25 MVAR at POI) and expansion of the Shunock substation from a straight bus to a ring bus. Previous revisions of this PPA inadvertently provided impedances on a 50-MVA base instead of a 100-MVA base. | 2024-06-30 | Notification | 2023-04-20
VELCO-23-T01 | 2023-03-27 | Add One 115/13.2 kV Transformer at Tafts Corner | Transmission notification from VELCO to install a 115/13.2 kV transformer at the Tafts Corner substation to maintain service to the radial load during a 115/12.5 kV transformer outage. | 2024-12-15 | Notification | 2023-04-20
HMLD-23-T01 | 2023-04-06 | Chaffins Substation Transformer T1 Replacement | Transmission notification from Holden Municipal Light Department for the replacement of the T1 transformer at the Chaffins substation. | 2023-01-17 | Notification | 2023-04-20
HMLD-23-T02 | 2023-04-06 | Chaffins Substation Transformer T2 Replacement | Transmission notification from Holden Municipal Light Department for the replacement of the T2 transformer at the Chaffins substation. | 2022-10-19 | Notification | 2023-04-20
CMP-23-G01 | 2023-02-24 | Queue Position 1097 (QP 1097) Greene Apple Solar | Generation application from Central Maine Power on behalf of Swift Current Energy for the installation of a 178.59 MW solar facility connecting to a new three-breaker ring switching station located on Section 212 between Larrabee Road and Monmouth substations. | 2024-11-01 | Approved | 2023-03-16
CMP-23-T01 | 2023-02-24 | Queue Position 1097 (QP 1097) Greene Apple Solar | Transmission application from Central Maine Power for the installation of a new three-breaker ring bus switching station located on Section 212 between Larrabee Road and Monmouth substations. | 2024-11-01 | Approved | 2023-03-16
CMP-23-T02 | 2023-02-24 | Queue Position 1097 (QP 1097) Greene Apple Solar | Transmission application from Central Maine Power on behalf of Swift Current Energy for the installation of a 115/34.5/13.8 kV Main Power Transformer and a 100’ 115 kV generator lead line from the QP 1097 collector station to the new QP 1097 115 kV three breaker ring switching station. | 2024-11-01 | Approved | 2023-03-16
CMP-23-T03 | 2023-02-24 | Queue Position 1097 (QP 1097) Greene Apple Solar | Transmission application from Central Maine Power to replace eleven 115 kV circuit breakers at the Larrabee Road 115 kV substation. | 2024-11-01 | Approved | 2023-03-16
VP-23-G01 | 2023-02-27 | Queue Position 1165 (QP 1165) Solar Project | Generation application from Versant Power on behalf of SolAmerica Energy, LLC for the installation of a 1.97 MW solar facility in Trenton, ME and interconnecting to Ellsworth Falls substation via Line 28. | 2023-07-15 | Approved | 2023-03-16
ES-20-G27 Rev.1 | 2023-02-21 | Westfarms Mall, 500 Westfarms Mall Solar | Generation notification from Eversource Energy on behalf of Westfarms Mall for the installation of a 2.0328 MW Solar PV in Farmington, CT and interconnecting to 500 Westfarms Mall, Farmington, CT via the 1C03 circuit out of the Farmington substation. | 2023-04-01 | Notification | 2023-03-16
GMP-23-G03 | 2023-02-22 | Green Mountain Power - Hunt Road Solar | Generation notification from Green Mountain Power for the installation of a 3.8 MW Solar PV in Windsor, VT and interconnecting to Hunt Road, Windsor, VT via the G31 circuit out of the Windsor substation. | 2024-06-01 | Notification | 2023-03-16
GMP-23-G04 | 2023-02-22 | Green Mountain Power - Brandon Mountain Road Solar and Battery | Generation notification from Green Mountain Power for the installation of a 1.0 MW Solar PV and 2.0 MW/8.0 MWh AC Coupled Battery in Rochester, VT and interconnecting to Brandon Mountain Road, Rochester, VT via the G62 circuit out of Rochester substation. | 2024-04-01 | Notification | 2023-03-16
NEP-23-T01 | 2023-02-15 | Revere Substation Transformer Replacements | Transmission notification from New England Power to replace two existing load-service transformers at Revere Substation in Revere, MA. | 2025-06-04 | Notification | 2023-03-15
ES-23-T21 | 2023-02-24 | Rebuild of Line 1560-1 | Transmission notification from Eversource Energy for the rebuild of Line 1560-1 to replace 5.0 miles of existing structures and 795-kcmil ACSR conductor with 1590-kcmil ACSS conductor. | 2023-12-12 | Notification | 2023-03-15
ES-23-T22 | 2023-02-24 | Partial Rebuild of Line 1560-2 | Transmission notification from Eversource Energy for the rebuild of Line 1560-2 to replace 3.3 miles of existing structures and 795-kcmil ACSR conductor with 1590-kcmil ACSS conductor. | 2023-12-12 | Notification | 2023-03-15
ES-23-T25 | 2023-02-24 | Partial Rebuild of Line 1808-3 | Transmission notification from Eversource Energy for the rebuild of Line 1808-3 to replace 3.3 miles of existing structures and 795-kcmil ACSR conductor with 1590-kcmil ACSS conductor. | 2023-12-12 | Notification | 2023-03-15
ES-23-T38 | 2023-02-24 | Partial Rebuild of Line 500 | Transmission notification from Eversource Energy for the rebuild of Line 500 to replace 7.6 miles of existing 2/0 and 4/0 copper conductor with 1272-kcmil ACSS conductor. | 2023-06-30 | Notification | 2023-03-15
UI-23-T01 | 2023-02-28 | Rebuild Section 1560-3 | Transmission notification from United Illuminating Company for the rebuild of 3.958 miles of existing 4/0 copper conductor with 795 ACSR Drake conductor. | 2027-12-31 | Notification | 2023-03-15
UI-23-T02 | 2023-02-28 | Rebuild Section 1594 | Transmission notification from United Illuminating Company for the rebuild of 2.553 miles of existing 4/0 copper conductor with 795 ACSR Drake conductor. | 2027-12-31 | Notification | 2023-03-15
UI-23-T03 | 2023-02-28 | Rebuild of Section 1808-2 | Transmission notification from United Illuminating Company for the rebuild of 1.445 miles of existing 4/0 copper conductor with 795 ACSR Drake conductor. | 2027-12-31 | Notification | 2023-03-15
TMLP-23-G01 | 2023-03-06 | Fortistar Methane 3 LLC - 330 E Brittania Street Landfill Gas | Generation notification from Taunton Municipal Lighting Plant on behalf of Fortistar Methane 3 LLC for the installation of 1.63 MW Landfill Gas in Taunton, MA and interconnecting to 330 E Brittania Street, Taunton, MA via the 2014.5 circuit out of Station 20. | 1997-01-01 | Notification | 2023-03-16
TMLP-23-G02 | 2023-03-06 | Fortistar Methane 3 LLC - 330 E Brittania Street Landfill Gas | Generation notification from Taunton Municipal Lighting Plant on behalf of Fortistar Methane 3 LLC for the installation of 1.9 MW Landfill Gas in Taunton, MA and interconnecting to 330 E Brittania Street, Taunton, MA via the 2014.11 circuit out of Station 20. | 2009-01-01 | Notification | 2023-03-16
TMLP-23-G03 | 2023-03-06 | Cox Enterprises, Inc. - 123 Williams Street Solar | Generation notification from Taunton Municipal Lighting Plant on behalf of Cox Enterprises, Inc. for the installation of 3.0 MW Solar PV in Taunton, MA and interconnecting to 123 Williams Street, Taunton, MA via the 1614.12 circuit out of Station 16. | 2012-05-11 | Notification | 2023-03-16
TMLP-23-G04 | 2023-03-06 | GLC-(MA) Taunton, LLC - 32R Padelford Street Solar | Generation notification from Taunton Municipal Lighting Plant on behalf of GLC-(MA) Taunton, LLC for the installation of 3.0 MW Solar PV in Taunton, MA and interconnecting to 32R Padelford Street, Taunton, MA via the 1614.41 circuit out of Station 16. | 2012-05-11 | Notification | 2023-03-16
TMLP-23-G05 | 2023-03-06 | Berkley East Solar LLC - 2 Myricks Street Solar | Generation notification from Taunton Municipal Lighting Plant on behalf of Berkley East Solar LLC for the installation of 3.0 MW Solar PV in Taunton, MA and interconnecting to 2 Myricks Street, Taunton, MA via the 2014.42 circuit out of Cleary substation. | 2013-03-12 | Notification | 2023-03-16
TMLP-23-G06 | 2023-03-06 | Southern Sky Renewable Energy Berkley, LLC - 49 S Main Street Solar | Generation notification from Taunton Municipal Lighting Plant on behalf of Southern Sky Renewable Energy Berkley, LLC for the installation of 3.0 MW Solar PV in Taunton, MA and interconnecting to 49 S Main Street, Taunton, MA via the 1614.ET1 circuit out of Station 16. | 2013-12-27 | Notification | 2023-03-16
TMLP-23-G07 | 2023-03-06 | Captona Partnets Solar I Finco - Pole 253L2 - County Street Solar | Generation notification from Taunton Municipal Lighting Plant on behalf of Captona Partners Solar I Finco LLC for the installation of 3.0 MW Solar PV in Taunton, MA and interconnecting to Pole 253L2, County Street, Taunton, MA via the 2014.3 circuit out of Station 20. | 2016-08-23 | Notification | 2023-03-16
TMLP-23-G08 | 2023-03-06 | Taunton Municipal Lighting Plant - 500 W Water Street Distillate Fuel Oil | Generation notification from Taunton Municipal Lighting Plant for the installation of 2.495 MW Distillate Fuel Oil in Taunton, MA and interconnecting to 500 W Water Street, Taunton, MA via the 1614.DG-W circuit out of Station 16. | 2017-09-01 | Notification | 2023-03-16
TMLP-23-G09 | 2023-03-06 | Taunton Municipal Lighting Plant - 500 W Water Street Distillate Fuel Oil | Generation notification from Taunton Municipal Lighting Plant for the installation of 2.495 MW Distillate Fuel Oil in Taunton, MA and interconnecting to 500 W Water Street, Taunton, MA via the 1614.DG-W circuit out of Station 16. | 2017-09-01 | Notification | 2023-03-16
TMLP-23-G10 | 2023-03-06 | Taunton Municipal Lighting Plant - 500 W Water Street Distillate Fuel Oil | Generation notification from Taunton Municipal Lighting Plant for the installation of 2.495 MW Distillate Fuel Oil in Taunton, MA and interconnecting to 500 W Water Street, Taunton, MA via the 1614.DG-ET circuit out of Station 16. | 2017-09-01 | Notification | 2023-03-16
TMLP-23-G11 | 2023-03-06 | Taunton Municipal Lighting Plant - 500 W Water Street Distillate Fuel Oil | Generation notification from Taunton Municipal Lighting Plant for the installation of 2.495 MW Distillate Fuel Oil in Taunton, MA and interconnecting to 500 W Water Street, Taunton, MA via the 1614.DG-ET circuit out of Station 16. | 2017-09-01 | Notification | 2023-03-16
TMLP-23-G12 | 2023-03-06 | GSPP Raynham TMLP LLC (Green Street Power Partners) - Pole 30L2 - King Phillip Street Solar | Generation notification from Taunton Municipal Lighting Plant on behalf of GSPP Raynham TMLP LLC (Green Street Power Partners) for the installation of 2.28 MW Solar PV in Taunton, MA and interconnecting to Pole 30L2, King Phillip Street, Taunton, MA via the 2014.11 circuit out of Station 20. | 2019-06-09 | Notification | 2023-03-16
TMLP-23-G13 | 2023-03-06 | Taunton Municipal Lighting Plant - 1314 Somerset Avenue Battery | Generation notification from Taunton Municipal Lighting Plant for the installation of a 3.0 MW Battery in Taunton, MA and interconnecting to 1314 Somerset Avenue, Taunton, MA via the 1614.81 circuit out of Station 16. | 2020-03-02 | Notification | 2023-03-16
ES-23-G09 | 2023-02-03 | Queue Position 927 (QP 927) 1,200 MW (NET) Offshore Wind Project | Generation application from Eversource Energy on behalf of OCS-A 0522 LLC for the installation of a 1,276.35 MW (gross) offshore wind farm consisting of 134 turbines and interconnecting to the Montville 345 kV switchyard. | 2026-05-31 | Approved Withdrawn | 3/13/2023 8/7/2024
ES-23-T36 | 2023-02-03 | Queue Position 927 (QP 927) 1,200 MW (NET) Offshore Wind Project | Transmission application from Eversource Energy on behalf of OCS-A 0522 LLC for the installation of a 1,200 MW, +/-320 kV HVDC transmission system, a 1,320 MVA, 385/345 kV converter station transformer, and a 129.2 mile +/-320 kV submarine transmission line. | 2026-05-31 | Approved Withdrawn | 3/13/2023 8/7/2024
ES-23-T37 | 2023-02-03 | Queue Position 927 (QP 927) 1,200 MW (NET) Offshore Wind Project | Transmission application from Eversource Energy on behalf of OCS-A 0522 LLC for the installation of two 0.63 mile, 345 kV circuits from the onshore converter station to the Montville 345 kV switchyard. | 2026-05-31 | Approved Withdrawn | 3/13/2023 8/7/2024
ES-23-T04 | 2023-02-03 | Queue Position 927 (QP 927) 1,200 MW (NET) Offshore Wind Project | Transmission application from Eversource Energy for the installation of a 9 breaker, 3 bay breaker-and-a-half 345 kV GIS and associated switchyard upgrades at Montville 345 kV switchyard to accommodate two 345 kV circuits. | 2024-06-30 | Approved Withdrawn | 3/13/2023 8/7/2024
ES-23-G07 | 2023-01-25 | Aireline Renewables Providence Pike Solar Project | Generation application from Eversource Energy on behalf of AirLine Renewables for the installation of a 2.0 MW Solar PV facility in Putnam, CT and interconnecting to the Tracy substation. | 2023-03-31 | Approved Withdrawn | 3/13/2023 5/16/2023
MPC-23-X01 | 2023-01-24 | Millennium Power AVR Modification Project | Transmission application from Millennium Power for the replacement of the existing automatic voltage regulator (AVR) systems for the combustion turbine and steam turbine in Charlton, MA. | 2023-04-30 | Approved | 2023-03-13
WRD-23-G01 | 2023-01-27 | Queue Position 1098 (QP 1098) 50 MW Solar Project | Generation application from Walden Renewables on behalf of Goose Cove Solar, LLC for the installation of a 50 MW Solar PV facility in Trenton, ME and interconnecting to the Trenton substation. | 2024-12-31 | Approved Withdrawn | 3/13/2023 4/1/2024
CMP-23-G02 | 2023-01-31 | Queue Position 1151 (QP 1151) 1.968 MW Solar Project | Generation application from Central Maine Power on behalf of Felt Road Solar, LLC for the installation of a 1.968 MW Solar PV facility in Bryant Pond, ME and interconnecting to the Woodstock substation. | 2024-11-15 | Approved | 2023-03-13
CMP-23-G03 | 2023-01-31 | Queue Position 1080 (QP 1080) 65 MW Solar Project | Generation application from Central Maine Power on behalf of Canton Solar Energy Center, LLC for the installation of a 65 MW Solar PV facility in Canton, ME and interconnecting to the new 115 kV switching station on Section 280. | 2024-10-24 | Approved Withdrawn | 3/13/2023 10/18/2024
CMP-23-T04 | 2023-01-31 | Queue Position 1080 (QP 1080) 65 MW Solar Project | Transmission application from Central Maine Power on behalf of Canton Solar Energy Center, LLC for the installation of a 115/34.5 kV 60/80/100 MVA transformer and 115 kV breaker. | 2024-10-24 | Approved Withdrawn | 3/13/2023 10/18/2024
CMP-23-G05 | 2023-01-31 | Queue Position 1080 (QP 1080) 65 MW Solar Project | Transmission application from Central Maine Power for the installation of a new 115 kV three-breaker ring switching station on Section 280. | 2024-10-24 | Approved Withdrawn | 3/13/2023 10/18/2024
CMP-23-G06 | 2023-01-31 | Queue Position 1080 (QP 1080) 65 MW Solar Project | Transmission application from Central Maine Power for the uprate of 115 kV Section 280 to a minimum 236 MVA summer LTE rating. | 2024-10-24 | Approved Withdrawn | 3/13/2023 10/18/2024
ES-23-G03 | 2023-01-21 | Lodestar Energy LLC, 0 Brick Top Lane Solar | Generation notification from Eversource Energy on behalf of Lodestar Energy LLC for the installation of a 2.0 MW Solar PV in North Windham, CT and interconnecting to 0 Brick Top Lane, North Windham, CT via the 11F12 circuit out of Card Street substation. | 2023-09-15 | Notification Withdrawn | 3/13/2023 6/18/2024
ES-23-G04 | 2023-01-21 | FedEx, 1000 Middle Street PDSL Solar | Generation notification from Eversource Energy on behalf of FedEx for the installation of a 1.92 MW Solar PV in Middletown, CT and interconnecting to 1000 Middle Street PDSL, Middletown, CT via the 6A10 circuit out of Berlin substation. | 2023-06-01 | Notification | 2023-03-13
ES-23-G05 | 2023-01-19 | Lodestar Energy LLC, 191 Lovers Lane Solar | Generation notification from Eversource Energy on behalf of Lodestar Energy LLC for the installation of a 2.0 MW Solar PV in Torrington, CT and interconnecting to 191 Lovers Lane, Torrington, CT via the 1B12 circuit out of Franklin Drive substation. | 2023-12-29 | Notification | 2023-03-13
GMP-23-G02 | 2023-01-30 | Green Mountain Power, 904 Houghton Lane Solar | Generation notification from Green Mountain Power for the installation of a 3.5 MW Solar PV in Bennington, VT and interconnecting to 904 Houghton Lane, Bennington, VT via the G61 circuit out of the Lyons Street substation. | 2023-12-01 | Notification | 2023-03-13
ES-20-G175 Rev.1 | 2023-02-01 | Haddam Quarters Solar LLC, Haddam Quarter Road Solar | Generation notification from Eversource Energy on behalf of Haddam Quarters Solar LLC for the installation of a 1.95 MW Solar PV in Durham, CT and interconnecting to Haddam Quarter Road, Durham, CT via the 30K13 circuit out of the Dooley substation. | 2023-06-01 | Notification | 2023-03-13
WMLP-23-G01 | 2023-01-31 | Citizens Energy, 8 Municipal Way Battery | Generation notification from Wellesley Municipal Light Department on behalf of Citizens Energy for the installation of a 4.99 MW Battery in Wellesley, MA and interconnecting to 8 Municipal Way, Wellesley, MA via the 13.8 kV circuit out of Wellesley Hills substation. | 2024-04-30 | Notification | 2023-03-13
ES-19-G93 Rev.1 | 2023-01-18 | EDF Renewables Distributed Solutions, 28 Lawsbrook Road Solar and Battery | Generation notification from Eversource Energy on behalf of EDF Renewables Distributed Solutions for the installation of a 3.04 MW Solar PV and 2.0 MW/4.0 MWh AC Coupled Battery in Acton, MA and interconnecting to 28 Lawsbrook Road, Acton, MA via the 416-H8 circuit out of Maynard substation. | 2023-03-10 | Notification | 2023-03-13
ES-23-G10 | 2023-01-18 | Con Edison Battery Storage, 31 Pecks Lane Solar | Generation notification from Eversource Energy on behalf of Con Edison Battery Storage for the installation of a 0.8331 MW Solar PV and 1.5352 MW/6.0 MWh AC Coupled Battery in Newtown, CT and interconnecting to 31 Pecks Lane, Newtown, CT via the 12M3 circuit out of Newtown substation. | 2024-05-01 | Notification | 2023-03-13
NEP-19-GNF198 Rev.1 | 2023-01-30 | BlueWave, 1050 Hilldale Avenue Solar and Battery | Generation notification from New England Power on behalf of BlueWave for the installation of a 4.0 MW Solar PV and 4.0 MW/8.0 MWh DC Coupled Battery in Haverhill, MA and interconnecting to 1050 Hilldale Avenue, Haverhill, MA via the 13.2 kV circuit out of North Haverhill substation. | 2025-03-01 | Notification | 2023-03-13
ES-23-T02 | 2023-01-18 | Upgrade #1 Transformer at Kingston Substation #735 | Transmission notification from Eversource Energy to upgrade of #1 transformer at Kingston substation #735 from 12/16/20 MVA to 30/40/50 MVA. | 2023-08-02 | Notification | 2023-02-23
ES-23-T03 | 2023-01-18 | Upgrade #2 Transformer at Kingston Substation #735 | Transmission notification from Eversource Energy to upgrade of #2 transformer at Kingston substation #735 from 12/16/20 MVA to 30/40/50 MVA. | 2023-09-22 | Notification | 2023-02-23
ES-23-T08 | 2023-01-24 | Partial Rebuild of Line 1268 | Transmission notification from Eversource Energy for the rebuild of Line 1268 replacing 0.8 miles of existing 795-kcmil ACSS conductor with 1272-kcmil ACSS conductor. | 2026-12-31 | Notification | 2023-02-23
ES-23-T09 | 2023-01-24 | Partial Rebuild of Line 1485 | Transmission notification from Eversource Energy for the rebuild of Line 1485 replacing 5.8 miles of existing 4/0 copper and 795-kcmil ACSR conductor with 1272-kcmil ACSS conductor. | 2026-12-31 | Notification | 2023-02-23
ES-23-T10 | 2023-01-24 | Partial Rebuild of Line 1887-2 | Transmission notification from Eversource Energy for the rebuild of Line 1887-2 replacing 6.6 miles of existing 4/0 copper and 795-kcmil ACSR conductor with 1272-kcmil ACSS conductor. | 2026-12-31 | Notification | 2023-02-23
ES-23-T11 | 2023-01-24 | Partial Rebuild of Line 1163-1 | Transmission notification from Eversource Energy for the rebuild of Line 1163-1 replacing 3.3 miles of existing 795-kcmil ACSR conductor with 1272-kcmil ACSS conductor. | 2024-06-30 | Notification | 2023-02-23
ES-23-T12 | 2023-01-24 | Partial Rebuild of Line 1163-3 | Transmission notification from Eversource Energy for the rebuild of Line 1163-3 replacing 1.5 miles of existing 4/0 copper conductor with 1272-kcmil ACSS conductor. | 2024-06-30 | Notification | 2023-02-23
ES-23-T13 | 2023-01-24 | Partial Rebuild of Line 1550-1 | Transmission notification from Eversource Energy for the rebuild of Line 1550-1 replacing 3.3 miles of existing 795-kcmil ACSR conductor with 1272-kcmil ACSS conductor. | 2024-06-30 | Notification | 2023-02-23
ES-23-T14 | 2023-01-24 | Partial Rebuild of Line 1550-2 | Transmission notification from Eversource Energy for the rebuild of Line 1550-2 replacing 1.5 miles of existing 4/0 copper conductor with 1272-kcmil ACSS conductor. | 2024-06-30 | Notification | 2023-02-23
ES-23-T01 | 2023-01-03 | Replace 115 kV Cables 142 and 143 Project | Transmission application from Eversource Energy to replace two 115 kV underground cables that extend from Achusnet substation to Pine Street substation due to asset condition issues. | 2025-12-31 | Approved | 2023-01-19
NEP-21-T03 Rev.1 | 2023-01-04 | Tewksbury Statcom Project | Transmission application from New England Power for the installation of a 345 kV, +/- 167 MVAr Static Synchronous Compensator (STATCOM) at the Tewksbury 22A substation and the associated 150 MVA 345/38.4 kV transformer. In addition, a new bay will be added at the substation with two new 345 kV breakers. | 2023-05-26 | Approved | 2023-01-18
GMP-22-G16 | 2022-11-15 | Green Mountain Power - 1705 Route 14 Solar | Generator notification from Green Mountain Power for the installation of 4.125 MW Solar PV in Hartford, VT and interconnecting to the Wilder Substation via the G3 circuit. | 2023-07-01 | Notification Withdrawn | 1/19/2023 7/16/2024
GMP-22-G17 | 2022-11-16 | Green Mountain Power - Mill River Road Solar | Generator notification from Green Mountain Power for the installation of 4.95 MW Solar PV in St. Albans, VT and interconnecting to the Nason St. Substation via the G26 circuit. | 2024-03-01 | Notification | 2023-01-19
ES-22-G24 Rev.1 | 2022-12-21 | Verogy - 31 Thrall Road Solar | Generation notification from Eversource Energy on behalf of Verogy for the installation of 4.0 MW Solar PV in East Windsor, CT and interconnecting to 31 Thrall Road, East Windsor, CT via the 23J36 circuit out of Barbour Hill substation. | 2023-12-01 | Notification | 2023-01-19
VELCO-22-X01 | 2022-12-23 | Increase the Sand Bar Series Reactor Insertion | Transmission notification from VELCO for the increase of the Sand Bar Series Reactor insertion setting to 307 MVA to be above the winter LTE and increase of the time delay to one minute. | 2023-03-10 | Notification | 2023-01-19
CMEEC-23-T01 | 2022-12-23 | Addition of 115 kV Circuit Breaker 2T at the Buddington 16L Substation | Transmission notification from CMEEC for the addition of one 115 kV circuit breaker 2T at the Buddlington 16L substation in Groton, CT. | 2023-05-31 | Notification | 2023-01-19
ES-23-T05 | 2023-01-03 | Line 1222 Rebuild | Transmission notification from Eversource Energy for the rebuild of Line 1222 to replace 1.74 miles of 556-kcmil ACSR conductor with 1590-kcmil ACSS conductor. | 2024-05-31 | Notification | 2023-01-19
ES-23-T06 | 2023-01-03 | Line 1714 Rebuild | Transmission notification from Eversource Energy for the rebuild of Line 1714 to replace 9.4 miles of 556-kcmil ACSR conductor with 1590-kcmil ACSS conductor. | 2024-05-31 | Notification | 2023-01-19
ES-23-T07 | 2023-01-03 | Line 1720 Rebuild | Transmission notification from Eversource Energy for the rebuild of Line 1720 to replace 7.6 miles of 556-kcmil ACSR conductor with 1590-kcmil ACSS conductor. | 2024-05-31 | Notification | 2023-01-19
EDF-22-G01 | 2022-12-05 | Queue Position 1029 (QP 1029) Bradley Solar Project | Generation application from EDF Renewables for the installation of thirty-five (35) photovoltaic inverters totaling 120 MW in Chester, ME and interconnecting to a new three-breaker ring bus switching station on Versant Power’s 115 kV Line 97, 9.2 miles from Graham substation. | 2023-12-01 | Approved Withdrawn | 12/19/2022 2/6/2024
EDF-22-T01 | 2022-12-05 | Queue Position 1029 (QP 1029) Bradley Solar Project | Transmission application from EDF Renewables for the installation of a 115/34.5 kV main transformer, 115 kV generator lead line, and 115 kV circuit breaker in support of the 120 MW solar facility. | 2023-12-01 | Approved Withdrawn | 12/19/2022 2/6/2024
VP-22-T06 | 2022-12-05 | Queue Position 1029 (QP 1029) Bradley Solar Project | Transmission application from Versant Power for the installation of a three-breaker switching station on Versant Power’s 115 kV Line 97. | 2023-12-01 | Approved Withdrawn | 12/19/2022 2/6/2024
JUP-22-G05 | 2022-12-02 | 200 MW Milford BESS Project (QP 1089) | Generator application from Jupiter Power for the installation of a 200 MW battery energy storage system consisting of fifty-eight (58) inverters in Milford, CT and interconnecting to the 115 kV bus at the Devon 7R substation. | 2026-05-31 | Approved | 2022-12-19
JUP-22-T04 | 2022-12-02 | 200 MW Milford BESS Project (QP 1089) | Transmission application from Jupiter Power for the installation of two 115/34.5/13.2 kV 120 MVA main power transformers and a 0.3 mile 115 kV underground generator lead line from the project site to Devon 7R 115 kV substation. | 2026-05-31 | Approved | 2022-12-19
ES-22-T58 | 2022-12-02 | 200 MW Milford BESS Project (QP 1089) | Transmission application from Eversource Energy for the installation of associated bus work to connect QP 1089 at Devon 7R. | 2026-05-31 | Approved | 2022-12-19
NEP-22-T22 | 2022-11-28 | Moore/Fifteen Mile Falls Substation Rebuild Project | Transmission application from New England Power to rebuild the New England Power portion of the Moore #20 substation named Fifteen Mile Falls #3027 substation in Littleton, NH. | 2027-09-15 | Approved | 2022-12-14
GRH-22-T02 | 2022-11-30 | Moore/Fifteen Mile Falls Substation Rebuild Project | Transmission application from Great River Hydro to re-align the 230 kV interconnection facilities at the Moore #20 substation in Littleton, NH. | 2027-09-15 | Approved | 2022-12-14
ES-22-G41 | 2022-11-30 | Eversource Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Wildcat Renewables, LLC - 190 Fox Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Wildcat Renewables, LLC for the installation of a 4.99 MW PV and 2.74 MW/5.48 MWh DC Coupled Battery facility in Dalton, MA and interconnecting to the Berkshire substation via the 18C1 circuit. | 2022-12-31 | Approved Withdrawn | 12/14/2022 4/17/2024
ES-22-G42 | 2022-11-30 | Eversource Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Bluewave Capital - Pine Meadow Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Bluewave Capital for the installation of a 2.0 MW PV and 2.0 MW/8.0 MWh DC Coupled Battery facility in Northfield, MA and interconnecting to the French King substation via the 21B circuit. | 2022-12-30 | Approved | 2022-12-14
ES-22-G43 | 2022-11-30 | Eversource Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Nexamp Solar LLC - 99 Straits Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Nexamp Solar LLC for the installation of a 2.75 MW PV and 2.0 MW/4.0 MWh DC Coupled Battery facility in Hatfield, MA and interconnecting to the Podick substation via the 18G6 circuit. | 2022-12-30 | Approved Withdrawn | 12/14/2022 7/16/2024
ES-22-G44 | 2022-11-30 | Eversource Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Bluewave Capital - Upper Farm Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Bluewave Capital for the installation of a 2.9 MW PV and 3.0 MW/6.0 MWh DC Coupled Battery facility in Northfield, MA and interconnecting to the French King substation via a new circuit. | 2022-12-30 | Approved | 2022-12-14
ES-22-G45 | 2022-11-30 | Eversource Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Bluewave Capital - Upper Farm Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Bluewave Capital for the installation of a 2.0 MW PV and 1.5 MW/6.0 MWh DC Coupled Battery facility in Northfield, MA and interconnecting to the French King substation via a new circuit. | 2022-12-30 | Approved Withdrawn | 12/14/2022 7/16/2024
ES-22-G46 | 2022-11-30 | Eversource Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Bluewave Capital - Millers Falls Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Bluewave Capital for the installation of a 2.0 MW PV and 2.0 MW/8.0 MWh DC Coupled Battery facility in Northfield, MA and interconnecting to the French King substation via a new circuit. | 2022-12-30 | Approved | 2022-12-14
ES-22-G47 | 2022-11-30 | Eversource Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Bluewave Capital - 113 Brattleboro Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Bluewave Capital for the installation of a 2.0 MW PV and 2.0 MW/8.0 MWh DC Coupled Battery facility in Bernardston, MA and interconnecting to the Montague substation via a new circuit. | 2022-12-30 | Approved | 2022-12-19
ES-22-G48 | 2022-11-30 | Eversource Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Bluewave Capital - 543 Brattleboro Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Bluewave Capital for the installation of a 1.57 MW PV and 1.57 MW/6.0 MWh DC Coupled Battery facility in Bernardston, MA and interconnecting to the Montague substation via a new circuit. | 2022-12-30 | Approved Withdrawn | 12/19/2022 7/16/2024
ES-22-G49 | 2022-11-30 | Eversource Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Bluewave Capital - 100 Brattleboro Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Bluewave Capital for the installation of a 4.99 MW PV and 5.0 MW/20.0 MWh DC Coupled Battery facility in Bernardston, MA and interconnecting to the Montague substation via the 21C1 circuit. | 2022-12-30 | Approved | 2022-12-19
ES-22-G50 | 2022-11-30 | Eversource Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - ZP Battery DevCo LLC - Mt Warner Road Battery | Generator application from Eversource Energy (ES) on behalf of ZP Battery DevCo LLC for the installation of a 4.948 MW/20.0 MWh Battery facility in Hadley, MA and interconnecting to the Podick substation via the 18G4 circuit. | 2022-12-30 | Approved | 2022-12-19
ES-22-G51 | 2022-11-30 | Eversource Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Wildcat Renewables, LLC - 398 Deerfield Street Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Wildcat Renewables, LLC for the installation of a 4.99 MW PV and 4.99 MW/5.48 MWh DC Coupled Battery facility in Greenfield, MA and interconnecting to the Cumberland substation via the 22B2 circuit. | 2022-12-30 | Approved Withdrawn | 12/19/2022 7/16/2024
ES-22-G52 | 2022-11-30 | Eversource Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Bluewave Capital - Algerie Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Bluewave Capital for the installation of a 2.0 MW PV and 2.0 MW/8.0 MWh DC Coupled Battery facility in Becket, MA and interconnecting to the Blanford substation via the 19J3 circuit. | 2022-12-30 | Approved | 2022-12-19
ES-22-G53 | 2022-11-30 | Eversource Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Bluewave Capital - 509 Quarry Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Bluewave Capital for the installation of a 4.99 MW PV and 5.0 MW/20.0 MWh DC Coupled Battery facility in Becket, MA and interconnecting to the Blanford substation via the 19J3 circuit. | 2022-12-30 | Approved | 2022-12-19
ES-22-G54 | 2022-11-30 | Eversource Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Oak Leaf Solar XVII LLC - 832 Tamarack Road Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Oak Leaf Solar XVII LLC for the installation of a 2.49 MW PV and 1.5 MW/3.0 MWh DC Coupled Battery facility in Pittsfield, MA and interconnecting to the Oswald substation via the 30B3 circuit. | 2022-12-30 | Approved | 2022-12-19
ES-22-G55 | 2022-11-30 | Eversource Western Massachusetts Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Warren Farms Solar LLC - Warren Farms Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Warren Farms Solar LLC for the installation of a 2.66 MW PV and 2.0625 MW/4.125 MWh DC Coupled Battery facility in Dalton, MA and interconnecting to the Berkshire substation via the 18C1 circuit. | 2022-12-30 | Approved | 2022-12-19
ES-22-G62 | 2022-12-01 | Eversource Greater Boston Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Bluewave Solar - Chestnut Street Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Bluewave Solar for the installation of a 3.9 MW PV and 3.5 MW/7.0 MWh DC Coupled Battery facility in Hopkinton, MA and interconnecting to Hopkinton substation via the 126-H2 circuit. | 2025-12-31 | Approved Withdrawn | 12/19/2022 8/15/2023
ES-22-G63 | 2022-12-01 | Eversource Greater Boston Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - BPD Ventures LLC - 600 Central Street Battery | Generator application from Eversource Energy (ES) on behalf of BPD Ventures LLC for the installation of a 4.99 MW/20.0 MWh Battery facility in Holliston, MA and interconnecting to Holliston substation via the 130-H1 circuit. | 2025-12-31 | Approved | 2022-12-19
ES-22-G64 | 2022-12-01 | Eversource Greater Boston Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Nextgrid - 960 Main Street Solar and Battery | Generator application from Eversource Energy (ES) on behalf of NextGrid for the installation of a 4.999 MW PV and 3.74 MW/11.22 MWh DC Coupled Battery facility in Acton, MA and interconnecting to Maynard substation via the 416-H8 circuit. | 2025-12-31 | Approved | 2022-12-19
ES-22-G65 | 2022-12-01 | Eversource Greater Boston Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - Nextamp - 75 Spruce Street Solar and Battery | Generator application from Eversource Energy (ES) on behalf of Nexamp for the installation of a 1.125 MW PV and 1.0728 MW/2.1456 MWh AC Coupled Battery facility in Acton, MA and interconnecting to Maynard substation via the 416-H2 circuit. | 2025-12-31 | Approved | 2022-12-19
ES-22-G66 | 2022-12-01 | Eversource Greater Boston Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - NextGrid - 160 Maple Street Solar and Battery | Generator application from Eversource Energy (ES) on behalf of NextGrid for the installation of a 4.999 MW PV and 4.999 MW/25.0 MWh DC Coupled Battery facility in Bellingham, MA and interconnecting to Medway substation via the 65-H4 circuit. | 2025-12-31 | Approved | 2022-12-19
ES-22-G67 | 2022-12-01 | Eversource Greater Boston Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - NextGrid - 160 Maple Street Solar and Battery | Generator application from Eversource Energy (ES) on behalf of NextGrid for the installation of a 4.999 MW PV and 4.999 MW/25.0 MWh DC Coupled Battery facility in Bellingham, MA and interconnecting to Medway substation via the 65-H4 circuit. | 2025-12-31 | Approved | 2022-12-19
ES-22-G68 | 2022-12-01 | Eversource Greater Boston Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - NextGrid - 160 Maple Street Solar and Battery | Generator application from Eversource Energy (ES) on behalf of NextGrid for the installation of a 4.999 MW PV and 4.999 MW/25.0 MWh DC Coupled Battery facility in Bellingham, MA and interconnecting to Medway substation via the 65-H4 circuit. | 2025-12-31 | Approved | 2022-12-19
ES-22-G69 | 2022-12-01 | Eversource Greater Boston Affected System Operator (ASO) Distributed Energy Resource (DER) Group Study Project - SOL Customer Solutions - 0 Marshall Street Solar and Battery | Generator application from Eversource Energy (ES) on behalf of SOL Customer Solutions for the installation of a 2.5 MW PV and 1.32 MW/2.752 MWh DC Coupled Battery facility in Holliston, MA and interconnecting to Medway substation via the 65-H7 circuit. | 2025-12-31 | Approved | 2022-12-19
EIP-22-G01 Rev.1 | 2022-12-06 | Queue Position 939 (QP 939) Fuel Cell Project | Generator application from Eversource Energy on behalf of Generate NB Fuel Cells, LLC for the installation of a 20.1 MW Fuel Cell facility in New Britain, CT. | 2024-01-19 | Approved | 2022-12-19
ES-22-G39 | 2022-11-17 | The Nevar Company, South Main St. Solar | Generator notification from Eversource Energy on behalf of The Nevar Company for the installation of a 1.875 MW Solar PV in Middletown, CT and interconnecting to South Main St., Middletown, CT on the 13.2 kV circuit out of Dooley substation. | 2023-04-03 | Notification | 2022-12-19
ES-22-T57 | 2022-11-01 | Greggs Substation Rebuild Project | Transmission application from Eversource Energy to rebuild the Greggs substation and convert it from the dual straight bus configuration to a 4-bay breaker-and-a-half scheme in Goffstown, NH. | 2024-02-28 | Approved | 2022-11-16
BRP-22-G05 | 2022-10-31 | Rumford Battery Energy Storage Project (QP1113) | Generation application from Brookfield Renewable Trading & Marketing for the installation of an 8 MW battery system inside the Rumford Falls hydro station and interconnecting to the 11.5 kV system. | 2023-01-31 | Approved | 2022-12-05
GMP-22-G15 | 2022-10-03 | Green Mountain Power, 40 NCO Drive Solar | Generation notification from Green Mountain Power for the installation of a 2.1 MW Solar PV in South Burlington, VT and interconnecting to 40 NCO Drive, South Burlington, VT on the G1 circuit out of 79-Airport substation. | 2024-04-03 | Notification | 2022-12-05
ES-20-G43 Rev.1 | 2022-10-28 | ECOS Energy, 45 W. Fisk Road Solar | Generation notification from Eversource Energy on behalf of ECOS Energy for the installation of a 4.999 MW Solar PV in Hampton, CT and interconnecting to 45 W. Fisk Road, Hampton, CT on the 23 kV circuit out of Card Street 11F substation. | 2022-12-30 | Notification | 2022-12-05
ES-22-G60 | 2022-10-31 | Connecticut Department of Corrections, 176 Jarvis Street Solar | Generation notification from Eversource Energy on behalf of Connecticut Department of Corrections for the installation of a 3.9 MW Solar PV in Cheshire, CT and interconnecting to 176 Jarvis Street, Cheshire, CT on the 23 kV circuit out of Hanover Street 12F substation. | 2023-06-30 | Notification | 2022-12-05
ES-22-G61 | 2022-10-28 | Amazon, 1 Joseph Lane Solar | Generation notification from Eversource Energy on behalf of Amazon for the installation of a 4.98 MW Solar PV in Windsor, CT and interconnecting to 1 Joseph Lane, Windsor, CT on the 23 kV circuit out of Windsor Locks 14K substation. | 2021-12-31 | Notification | 2022-12-05
NEP-20-G04-036 Rev.1 | 2022-10-31 | Nautilus Solar LLC, 148 Mail Road Solar | Generator notification from New England Power on behalf of Nautilus Solar LLC for the installation of a 4.99 MW Solar PV in Exeter, RI and interconnecting to 148 Mail Road, Exeter, RI on the 12.47 kV circuit out of Tower Hill substation. | 2023-12-01 | Notification Withdrawn | 12/5/2022 8/13/2024
ES-22-G01 | 2022-10-31 | HAU Cheshire Project, LLC 5 McKee Place Solar and Battery | Generation notification from Eversource Energy on behalf of HAU Cheshire Project, LLC for the installation of a 0.9375 MW Solar PV and 0.25 MW/0.558 MWh AC Coupled Battery in Cheshire, CT and interconnecting to 5 McKee Place, Cheshire, CT on the 23 kV circuit out of Canal 15Q substation. | 2022-12-30 | Notification | 2022-12-05
ES-22-G37 | 2022-10-24 | Stamford Hospital, 110 Hillhurst Street Unit 123B123 Fuel Cell | Generation notification from Eversource Energy on behalf of Stamford Hospital for the installation of a 2.0 MW Fuel Cell in Stamford, CT and interconnecting to 110 Hillhurst Street Unit 123B123, Stamford, CT on the 13.2 kV circuit out of Waterside 22M substation. | 2022-12-31 | Notification | 2022-12-05
FL-22-T01 | 2022-11-02 | Replacement of Transformer 1X at Stevenson Substation | Transmission notification from FirstLight CT Housatonic LLC for the replacement of the three winding Stevenson 14A substation 1X transformer with a generator step-up transformer. | 2022-12-18 | Notification | 2022-12-05
ES-22-T50 | 2022-10-05 | Scobie Pond Series Reactor Project (QP 1101) | Transmission application from Eversource Energy for the installation of a 5.95 Ohm series reactor on the 363 line (Scobie Pond to Seabrook) at the 345 kV Scobie Pond substation. | 2023-12-31 | Approved | 2022-10-19
ES-22-G38 | 2022-09-08 | Hamilton Substrand PV Project | Generator application from Eversource Energy for the installation of a 2.0 MW PV facility in Windsor Locks, CT and interconnecting to the Windsor Locks substation. | 2023-04-01 | Approved | 2022-10-19
CMP-22-G04 | 2022-10-10 | Central Maine Power Sandford/Quaker Hill Distributes Energy Resources (DER) Cluster Study Update | Generator application from Central Maine Power on behalf of Con Edison Solutions LLC for the installation of a 3.486 MW PV and 2.34 MW/5.065 MWh AC Coupled Battery facility in Sanford, ME and interconnecting to the South Sanford substation via the 12.47 kV circuit. | 2024-12-31 | Approved Withdrawn | 10/19/2022 9/19/2023
ES-22-G59 | 2022-10-04 | Homestead Fuel Cell Project (QP 1168) | Generator application from Eversource Energy for the installation of an 8.7 MW Fuel Cell facility in Hartford, CT and interconnecting to the Northwest Hartford substation via a new feeder. | 2023-10-15 | Approved Withdrawn | 10/19/2022 6/18/2024
ES-22-T53 | 2022-10-04 | Partial Rebuild of Line 1231 and Line 1242 Project | Transmission application from Eversource Energy for the partial rebuild of Line 1231 to replace 25.8 miles of existing 2/0 copper conductor with 1272-kcmil ACSS conductor between Berkshire substation in Hinsdale, MA and Cumberland substation in Greenfield, MA. | 2024-11-30 | Approved | 2022-10-19
ES-22-T54 | 2022-10-04 | Partial Rebuild of Line 1231 and Line 1242 Project | Transmission application from Eversource Energy for the partial rebuild of Line 1242 to replace 28.6 miles of existing 2/0 copper conductor with 1272-kcmil ACSS conductor between Berkshire substation in Hinsdale, MA and Montague substation in Montague, MA. | 2024-11-30 | Approved | 2022-10-19
ES-22-G36 | 2022-09-23 | Hecate Energy Eastern Avenue Energy Center Project (QP 1115) | Generator application from Hecate Energy for the installation of a 250 MW storage facility consisting of seventy-four (74) inverters near Chelsea, MA and interconnecting to the 115 kV Chelsea substation. | 2025-10-01 | Approved | 2022-10-19
ES-22-T49 | 2022-09-23 | Hecate Energy Eastern Avenue Energy Center Project (QP 1115) | Transmission application from Hecate Energy for the installation of two 82/109/137 MVA 115/34.5/13.8 kV three winding station transformers and a 0.04 mile overhead generator lead line. | 2025-10-01 | Approved | 2022-10-19
ES-22-T39 | 2022-09-23 | Hecate Energy Eastern Avenue Energy Center Project (QP 1115) | Transmission application from Eversource Energy for the installation of one 115 kV Gas Insulated Circuit Breaker, two 115 kV breaker disconnect switches, a line disconnect/ground switch, surge arrester CCVTs, line terminal structure and underground risers, fiber, relays, control house expansion, and associated switching station equipment upgrades. | 2025-10-01 | Approved | 2022-10-19
GBCH-22-X01 | 2022-09-28 | Middletown Unit 4 AVR Replacement Project | Generator application from Generation Bridge Connecticut Holdings, LLC on behalf of Middletown Power LLC for the replacement of the Middletown Unit 4 Automatic Voltage Regulator (AVR) with a new unit. | 2022-11-13 | Approved | 2022-10-18
TPSC-22-X01 | 2022-10-10 | Berkshire Power Exciter Upgrade Project | Generator application from Tenaska Power Service Co. on behalf of Berkshire Power Company LLC to upgrade the exciter at Asset ID 1086 from Unitrol F to Unitrol 6080. | 2022-10-21 | Approved | 2022-10-18
GMP-22-G12 | 2022-08-12 | Green Mountain Power - Bullfrog Hollow Road | Generator notification from Green Mountain Power for the installation of 4.1 MW Solar PV in Wells, VT and interconnecting to Bullfrog Hollow Road, Wells, VT on the G20 circuit out of Pawlet substation. | 2023-07-01 | Notification | 2022-10-19
GMP-22-G13 | 2022-08-16 | Green Mountain Power - 640 South Furnace Road Solar | Generator notification from Green Mountain Power for the installation of 3.5 MW Solar PV in Pittsford, VT and interconnecting to 640 South Furnace Road, Pittsford, VT on the G11 circuit out of Pittsford Village substation. | 2023-11-30 | Notification | 2022-10-19
NEP-19-GNF162 Rev.2 | 2022-09-30 | Nexamp - 17 Griffin Road Solar | Generator notification from New England Power on behalf of 1.393 MW Solar PV in Charlton, MA and interconnecting to 17 Griffin Road, Charlton, MA on the 415L2 circuit out of West Charlton substation. | 2020-06-05 | Notification | 2022-10-19
ES-22-G57 | 2022-10-03 | Encore Renewables - Kendall Pond Road Solar | Generator notification from Eversource Energy on behalf of Encore Renewables for the installation of 2.25 MW Solar PV in Derry, NH and interconnecting to Scobie Pond Substation in Derry NH on the 12.47 kV circuit. | 2023-09-01 | Notification | 2022-10-19
ES-22-G58 | 2022-10-03 | Ameresco Inc - 15 Blackwater Road Solar | Generator notification from Eversource Energy on behalf of Ameresco Inc for the installation of 1.992 MW Solar PV in Strafford, NH and interconnecting to the Dover Substation on the 34.5 kV circuit. | 2023-04-03 | Notification | 2022-10-19
ES-22-G23 | 2022-10-04 | Bozzutos Inc. - 400 Industrial Avenue Solar and Fuel Cell | Generator notification from Eversource Energy on behalf of Bozzutos Inc. for the installation of a 1.0 MW Solar PV and 0.995 MW Fuel Cell in Cheshire, CT and interconnecting to 400 Industrial Avenue, Cheshire, CT on the 23 kV circuit out of Canal substation. | 2022-12-30 | Notification | 2022-10-19
NEP-22-GNF08 | 2022-09-30 | Distributed Solar Development - 27 Pond Street Solar and Battery | Generator notification from New England Power on behalf of Distributed Solar Development, LLC for the installation of a 0.875 MW Solar PV and 0.5 MW/1.112 MWh AC Coupled Battery in Attleboro, MA and interconnecting to 27 Pond Street, Attleboro, MA on the 23 kV circuit out of West Street substation. | 2025-10-01 | Notification Withdrawn | 10/19/2022 12/17/2024
GMP-22-G10 | 2022-08-08 | Green Mountain Power - 127 Kane Hill Road Battery | Generator notification from Green Mountain Power for the installation of a 2.95 MW/5.9 MWh Battery in Bristol, VT and interconnecting to 127 Kane Hill Road, Bristol, VT on the G38 circuit out of Hewlett Road substation. | 2023-02-08 | Notification | 2022-10-19
GMP-22-G11 | 2022-08-12 | Green Mountain Power - 150 Pilgrim Park Battery | Generator notification from Green Mountain Power for the installation of a 2.0 MW/4.0 MWh Battery in Waterbury, VT and interconnecting to 150 Pilgrim Park, Waterbury, VT on the G2 circuit out of Waterbury substation. | 2022-11-15 | Notification | 2022-10-19
GMP-22-G14 | 2022-09-30 | Green Mountain Power - Community Drive Battery | Generator notification from Green Mountain Power for the installation of a 4.99 MW/19.96 MWh Battery in South Burlington, VT and interconnecting to Community Drive, South Burlington, VT on the G1 circuit out of 43-Digital substation. | 2025-02-01 | Notification | 2022-10-19
CMP-22-T09 | 2022-10-03 | Detroit Transformer Replacement | Transmission notification from Central Maine Power for the replacement of the Detroit T1 43 MW LTE-rated transformer with a new 63 MW LTE-rated transformer. | 2022-12-31 | Notification | 2022-10-19
JUP-22-G03 | 2022-08-16 | Orrington II BESS Project (QP1015) | Generator application from Jupiter Power for the installation of a 100 MW battery energy storage system in Penobscot, ME and interconnecting to the 115 kV Orrington substation. | 2024-12-01 | Approved Withdrawn | 9/30/2022 8/22/2023
JUP-22-T03 | 2022-08-16 | Orrington II BESS Project (QP1015) | Transmission application from Jupiter Power for the installation of a new 115/34.5/13.2 kV transformer and 0.3 mile 115 kV generator lead line to the 115 kV Orrington substation. | 2024-12-01 | Approved Withdrawn | 9/30/2022 8/22/2023
VP-22-T05 | 2022-08-16 | Orrington II BESS Project (QP1015) | Transmission application from Versant Power for the installation of two 115 kV breakers, bus work, and related facilities to accommodate the 115 kV generator lead line. | 2024-12-01 | Approved Withdrawn | 9/30/2022 8/22/2023
WRD-22-G02 | 2022-08-22 | Queue Position 928 (QP 928) Solar Project | Generator application from Walden Renewables for the installation of a 20 MW PV facility in Madison, ME and interconnecting to the 34.5 kV Lakewood substation. | 2024-12-30 | Approved Withdrawn | 9/30/2022 11/27/2023
ES-22-T35 | 2022-08-24 | Holbrook Station #478 - Replace Existing 345/115 kV Autotransformer (345A) Project | Transmission application from Eversource Energy for the replacement of the existing 345/115 kV, 400 MVA Autotransformer at Holbrook Station #478 in Holbrook, MA. | 2023-06-01 | Approved | 2022-09-22
NEP-22-G05 | 2022-09-06 | Deer Meadow Solar Project (QP 1038) | Generator application from New England Power on behalf of Olive Wood Energy for the installation of a 76.25 MW PV facility in Hopkinton, NH and interconnecting to the QP 1038 substation. | 2025-10-31 | Approved | 2022-09-30
NEP-22-T23 | 2022-09-06 | Deer Meadow Solar Project (QP 1038) | Transmission application from New England Power for the installation of a three-breaker 230 kV ring bus substation, to be named later, at the proposed QP 1038 site in Hopkinton, NH. | 2027-08-30 | Approved | 2022-09-30
NEP-22-T24 | 2022-09-06 | Deer Meadow Solar Project (QP 1038) | Transmission application from New England Power on behalf of Olive Wood Energy for the installation of a 0.019 mile generator lead line for QP 1038. | 2025-10-31 | Approved | 2022-09-30
NEP-20-G01 Rev.1 | 2022-09-06 | Tiverton Brayton II & III Projects (QP 941 and QP 942) | Generator application from New England Power on behalf of Narragansett Electric and the Tiverton Brayton II, LLC for the installation of a 3.368 MW PV facility in Tiverton, RI and interconnecting to the Tiverton 2 substation via the 33F4 circuit. | 2022-11-01 | Approved | 2022-09-30
NEP-20-G02 Rev.1 | 2022-09-06 | Tiverton Brayton II & III Projects (QP 941 and QP 942) | Generator application from New England Power on behalf of Narragansett Electric and the Tiverton Brayton III, LLC for the installation of a 8.423 MW PV facility in Tiverton, RI and interconnecting to the Tiverton 2 substation via the 33F4 circuit. | 2022-11-01 | Approved | 2022-09-30
JUP-22-G04 | 2022-09-09 | Chester I BESS Project (QP 1019) | Generator application from Jupiter Power for the installation of a 20 MW battery energy storage system in Penobscot, ME and interconnecting to the 46 kV Chester substation. | 2024-04-01 | Approved Withdrawn | 9/30/2022 9/19/2023
CMP-22-G99 | 2022-09-09 | Queue Position 1028 (QP 1028) Wind Project | Generator application from Central Maine Power on behalf of Western Maine Renewables, LLC for the installation of fourteen 4.2 MVA wind turbines for a total of 58.8 MW in Moscow, ME and interconnecting to the new 115 kV substation. | 2024-12-01 | Approved | 2022-09-30
CMP-22-T06 | 2022-09-09 | Queue Position 1028 (QP 1028) Wind Project | Transmission application from Central Maine Power for the installation of a two-breaker tap bus on CMP Section 222 approximately 5.6 miles from the existing Wyman Hydro substation in Moscow, ME. | 2024-12-01 | Approved | 2022-09-30
CMP-22-T07 | 2022-09-09 | Queue Position 1028 (QP 1028) Wind Project | Transmission application from Central Maine Power for the installation of an 115/34.5/13.2 kV interconnection transformer, circuit switcher/breaker, and disconnect switch at the new 115 kV substation in Moscow, ME. | 2024-12-01 | Approved | 2022-09-30
CMP-22-T08 | 2022-09-09 | Queue Position 1028 (QP 1028) Wind Project | Transmission application from Central Maine Power for the installation of a 10 MVAR Capacitor Bank at the Dogtown 115 kV SVC station. | 2024-12-01 | Approved | 2022-09-30
UES-22-G02 | 2022-09-09 | DG NH Seabrook, LLC 626 Lafayette Road Solar | Generator notification from Unitil on behalf of DG NH Seabrook, LLC for the installation of a 2.75 Solar PV in Seabrook, NH and interconnecting to 626 Lafayette Road, Seabrook, NH on the 34.5 kV circuit out of Hampton substation. | 2023-11-01 | Notification Withdrawn | 9/30/2022 3/18/2025
ES-22-G32 | 2022-09-02 | Greenskies Clean Energy LLC, 320 Gospel Lane Solar | Generator notification from Eversource Energy on behalf of Greenskies Clean Energy LLC for the installation of a 1.99 MW Solar PV in Portland, CT and interconnecting to 320 Gospel Lane, Portland, CT on the 13.2 kV circuit out of Portland substation. | 2024-07-01 | Notification | 2022-09-30
ES-22-T42 | 2022-08-24 | Eagle TB154 Transformer Replacement | Transmission notification from Eversource Energy for the replacement of the 345/115 kV, 270 MVA transformer TB154 at Eagle substation in Merrimack, NH due to failure. | 2022-12-31 | Notification | 2022-09-22
ES-22-T43 | 2022-08-24 | Partial Rebuild of Line 1715 | Transmission notification from Eversource Energy for the partial rebuild of Line 1715 replacing 1.2 miles of existing structures and conductor with 1272-kcmil ACSS. | 2023-03-31 | Notification | 2022-09-22
ES-22-T44 | 2022-08-24 | Partial Rebuild of Line 1816 | Transmission notification from Eversource Energy for the partial rebuild of Line 1816 replacing 1.2 miles of existing structures and conductor with 1272-kcmil ACSS. | 2023-03-31 | Notification | 2022-09-22
ES-22-T45 | 2022-09-14 | Partial Rebuild of Line 1544 | Transmission notification from Eversource Energy for the partial rebuild of Line 1544 replacing 1.1 miles of existing HPFF conductor with 5000-kcmil XLPE. | 2027-08-31 | Notification | 2022-09-22
ES-22-T46 | 2022-09-14 | Partial Rebuild of Line 1755 | Transmission notification from Eversource Energy for the partial rebuild of Line 1755 replacing 1.1 miles of existing HPFF conductor with 5000-kcmil XLPE. | 2027-08-31 | Notification | 2022-09-22
ES-22-T47 | 2022-09-14 | Partial Rebuild of Line 1753 | Transmission notification from Eversource Energy for the partial rebuild of Line 1753 replacing 4.9 miles of existing HPFF conductor with 5000-kcmil XLPE. | 2025-12-31 | Notification | 2022-09-22
ES-22-T48 | 2022-09-14 | Partial Rebuild of Line 1792 | Transmission notification from Eversource Energy for the partial rebuild of Line 1792 replacing 4.8 miles of existing HPFF conductor with 5000-kcmil XLPE. | 2025-12-31 | Notification | 2022-09-22
JUP-22-G02 | 2022-07-19 | Chester II BESS Project (QP 1014) | Generator application from Jupiter Power for the installation of a 100 MW/200 MWh battery energy storage plant in Penobscot, ME and interconnecting to the Keene Road substation. | 2024-06-01 | Approved Withdrawn | 9/1/2022 8/22/2023
JUP-22-T02 | 2022-07-19 | Chester II BESS Project (QP 1014) | Transmission application from Jupiter Power for the installation of a new 115/34.5/13.2 kV transformer at the BES project site and new 0.5 mile 115 kV line from the project site to the Keene Road substation. | 2024-06-01 | Approved Withdrawn | 9/1/2022 8/22/2023
VP-22-T04 | 2022-07-22 | Chester II BESS Project (QP 1014) | Transmission application from Versant Power for the installation of two 115 kV breakers and associated bus work to accommodate the 115 kV lead line. | 2024-06-01 | Approved Withdrawn | 9/1/2022 8/22/2023
VP-22-G02 | 2022-07-22 | Versant Power Distributed Energy resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of BD Solar for the installation of a 4.99 MW PV facility in Hermon, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2022-07-21 | Approved | 2022-09-06
VP-22-G03 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of UGE USA Inc for the installation of a 2.0 MW PV facility in Bangor, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G04 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of Nexamp for the installation of a 2.5 MW PV facility in Mattawamkeag, ME and interconnecting to the Chester substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G05 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of Northern Lights Solar LLC for the installation of a 1.992 MW PV facility in Milford, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G06 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of EDF Renewables Distributed Solutions for the installation of a 1.999 MW PV facility in Bangor, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G07 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of Nexamp for the installation of a 1.99 MW PV facility in Chester, ME and interconnecting to the Chester substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G08 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of Kenduskeag Broadway LLC for the installation of a 1.999 MW PV facility in Kenduskeag, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G09 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of Cutler Solar LLC for the installation of a 1.75 MW PV facility in Cutler, ME and interconnecting to the Washington County substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G10 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of Loki Solar LLC for the installation of a 4.999 MW PV facility in Machias, ME and interconnecting to the Washington County substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G11 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of Summit Ridge Energy for the installation of a 4.95 MW PV facility in Brewer, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G12 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of Nexamp for the installation of a 3.25 MW PV facility in Pebmroke, ME and interconnecting to the Washington County substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G13 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of OneEnergy Development LLC for the installation of a 1.999 MW PV facility in Corinth, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G14 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of BD Solar Nicolin, LLC for the installation of a 3.3 MW PV facility in Ellsworth, ME and interconnecting to the Boggy substation via the 8.3 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G15 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of Walker Capital LLC for the installation of a 4.988 MW PV facility in Holden, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G16 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of ME I Corinth Main LLC for the installation of a 1.999 MW PV facility in Corinth, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G17 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of Trenton Solar Development LLC for the installation of a 1.875 MW PV facility in Trenton, ME and interconnecting to the Ellsworth Falls substation via the 34.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G18 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of Bomarc Road Solar LLC for the installation of a 4.98 MW PV facility in Bangor, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G19 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of SolAmerica Energy LLC for the installation of a 1.999 MW PV facility in Blue Hill, ME and interconnecting to the Boggy substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G20 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of GIRI Cherryfield Solar LLC for the installation of a 2.125 MW PV facility in Cherryfield, ME and interconnecting to the Harrington substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G21 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of Ameresco for the installation of a 1.992 MW PV facility in Ellsworth, ME and interconnecting to the Ellsworth Falls substation via the 34.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G22 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of Nexamp for the installation of a 4.99 MW PV facility in Greenfield, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G23 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of Nexamp for the installation of a 4.99 MW PV facility in Ellsworth, ME and interconnecting to the Ellsworth Falls substation via the 34.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G24 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of UGE USA Inc for the installation of a 2.0 MW PV facility in Veazie, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G25 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of OneEnergy Development LLC for the installation of a 1.999 MW PV facility in Holden, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2024-05-01 | Approved | 2022-09-06
VP-22-G26 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of BWC Jimmie Pond LLC for the installation of a 4.99 MW PV facility in Hampden, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2024-05-01 | Approved | 2022-09-06
VP-22-G27 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of BD Solar for the installation of a 4.999 MW PV facility in Millinocket, ME and interconnecting to the Chester substation via the 12.5 kV distribution circuit. | 2024-05-01 | Approved | 2022-09-06
VP-22-G28 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of OneEnergy Development LLC for the installation of a 1.99 MW PV facility in Eddington, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2024-05-01 | Approved | 2022-09-06
VP-22-G29 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of ME I Orrington Brewer Lake LLC for the installation of a 1.999 MW PV facility in Orrington, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2024-05-01 | Approved | 2022-09-06
VP-22-G30 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of BlueWave Solar MA LLC for the installation of a 4.0 MW PV facility in Orrington, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G31 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of Loki Solar LLC for the installation of a 1.999 MW PV facility in Whitneyville, ME and interconnecting to the Washington County substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G32 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of Hexagon Energy for the installation of a 1.99 MW PV facility in Brewer, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G33 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of Loki Solar LLC for the installation of a 1.999 MW PV facility in Machiasport, ME and interconnecting to the Washington County substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G34 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of MidCoast Solar LLC for the installation of a 1.99 MW PV facility in Bar Harbor, ME and interconnecting to the Trenton substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G35 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of OneEnergy Development LLC for the installation of a 1.999 MW PV facility in Hampden, ME and interconnecting to the Graham substation via the 12.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G36 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of GORO Jonesboro Solar LLC for the installation of a 1.99 MW PV facility in Jonesboro, ME and interconnecting to the Harrington substation via the 34.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G37 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of ReneSola Power Holdings LLC for the installation of a 1.999 MW PV facility in Cherryfield, ME and interconnecting to the Deblois substation via the 34.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
VP-22-G38 | 2022-07-22 | Versant Power Distributed Energy Resource (DER) Group Study Project | Generator application from Versant Power (VP) on behalf of Barren View Solar, LLC for the installation of a 1.99 MW PV facility in Jonesboro, ME and interconnecting to the Harrington substation via the 34.5 kV distribution circuit. | 2024-06-30 | Approved | 2022-09-06
ES-22-T34 | 2022-07-07 | K Street 103S Breaker Status Change Project | Transmission application from Eversource Energy to change the status of the 103S 345 kV breaker from normally closed to normally open at K Street substation in Boston, MA. | 2022-09-30 | Approved | 2022-08-19
ES-22-T32 | 2022-07-18 | Shifting Somerville Station 402 Load to be Normally Fed by Brighton Station 329 Project | Transmission application from Eversource Energy to change the normally open point at Somerville substation so that the load is normally fed by Brighton substation instead of Mystic substation. | 2022-08-29 | Approved Withdrawn | 8/19/2022 2/14/2024
ES-22-X01 | 2022-07-20 | 326 Line Remedial Action Scheme (RAS) Retirement Project | Transmission application from Eversource Energy for the retirement of the 326 Line RAS including steady state mode and stability mode. | 2022-12-31 | Approved | 2022-08-19
BRP-22-G04 | 2022-07-28 | Berlin Battery Energy Storage Project (QP 1103) | Generation application from Brookfield Renewable Trading & Marketing for the installation of a 14 MW battery system inside the Great Lakes Berlin hydro station and interconnecting to the 22 kV transmission system. | 2022-11-01 | Approved | 2022-09-01
CES-22-G01 | 2022-07-27 | Fore River Battery Energy Storage Project (QP 1111) | Generation application from Calpine Energy Services for the installation of a 20 MW/80 MWh Battery Energy Storage System (BESS) at Eversource’s 115 kV Edgar substation in Weymouth, MA. | 2026-03-01 | Approved Withdrawn | 9/1/2022 9/1/2023
CES-22-T01 | 2022-07-27 | Fore River Battery Energy Storage Project (QP 1111) | Transmission application from Calpine Energy Services for the installation of a main step-up transformer, 115 kV breaker, 115 kV disconnects, 115 kV generator lead line, and associated relaying and metering. | 2026-02-01 | Approved Withdrawn | 9/1/2022 9/1/2023
ES-22-T38 | 2022-07-28 | Fore River Battery Energy Storage Project (QP 1111) | Transmission application from Eversource Energy for the installation of a 115 kV gas insulated circuit breaker, two 115 kV breaker disconnect switches, a line disconnect/ground switch, surge arresters, CCVTs, line terminal potheads structure, bus supports, fiber, relays, and expanded control house and associated equipment. | 2026-03-01 | Approved Withdrawn | 9/1/2022 9/1/2023
ES-22-G24 | 2022-07-28 | Eversource Barbour Hill - Rockville Distributed Energy Resource (DER) Group Study Project | Generation application from Eversource Energy on behalf of Verogy for the installation of a 1.975 MW Solar PV facility in East Windsor, CT and interconnecting to 31 Thrall Road on the 23J36 circuit out of Barbour Hill substation. | 2023-12-01 | Approved | 2022-09-01
ES-22-G25 | 2022-07-28 | Eversource Barbour Hill - Rockville Distributed Energy Resource (DER) Group Study Project | Generation application from Eversource Energy on behalf of Verogy for the installation of a 2.0 MW Solar PV facility in Ellington, CT and interconnecting to 146 Tripp Road on the 14W7 circuit out of Rockville. | 2023-12-01 | Approved Withdrawn | 9/1/2022 6/18/2024
ES-22-G26 | 2022-07-28 | Eversource Barbour Hill - Rockville Distributed Energy Resource (DER) Group Study Project | Generation application from Eversource Energy on behalf of Community Power Group for the installation of a 4.0 MW Solar PV facility in Ellington, CT and interconnecting 24 Middle Road on the 14W7 circuit out of Rockville substation. | 2023-12-01 | Approved | 2022-09-01
ES-22-G27 | 2022-07-28 | Eversource Barbour Hill - Rockville Distributed Energy Resource (DER) Group Study Project | Generation application from Eversource Energy on behalf of CTEC Solar for the installation of a 1.875 MW Solar PV facility in South Windsor, CT and interconnecting to 186 Foster Street on the 23J33 circuit out of Barbour Hill substation. | 2023-12-01 | Approved | 2022-09-01
ES-22-T41 | 2022-08-02 | Montville 115/69/13.8 kV Autotransformer Project | Transmission application from Eversource Energy for the installation of a 115 kV circuit breaker and a 115/69/13.8 kV 40/53/67 MVA autotransformer at the Montville substation in Montville, CT. | 2023-02-18 | Approved | 2022-08-19
ES-22-G31 | 2022-07-14 | Dollar Tree Distribution Center, 99 International Drive Solar | Generator notification from Eversource Energy (ES) on behalf of Dollar Tree Distribution Center for the installaion of a 2.99 MW Solar PV in Windsor, CT and interconnecting to 99 International Drive on the 2A3 circuit out of North Bloomfield substation. | 2023-12-31 | Notification | 2022-09-01
GMP-22-G04 | 2022-07-11 | ER Danyow Road Solar, LLC, 200 Danyow Road Solar | Generator notification from Green Mountain Power on behalf of ER Danyow Road Solar, LLC for the installation of a 4.95 MW Solar PV in Enosburg Falls, VT and interconnecting to 200 Danyow Road on the G10 circuit out of the Sheldon substation. | 2023-08-25 | Notification | 2022-09-01
GMP-22-G05 | 2022-07-11 | ER Dunsmore LLC, 2642 Dusmore Road Solar | Generator notification from Green Mountain Power on behalf of ER Dunsmore, LLC for the installtion of a 4.95 MW Solar PV in Saint Albans, VT and interconnecting to 2642 Dunsmore Road on the G16 circuit out of the North Elm St. substation. | 2023-07-01 | Notification | 2022-09-01
GMP-22-G06 | 2022-07-11 | ER I Love Cows Solar, LLC Allen St Solar | Generator notification from Green Mountain Power on behalf of ER I Love Cows Solar, LLC for the installation of a 2.2 MW Solar PV in Barre, VT and interconnecting to Allen St on the 37G1 circuit out of Barre South End substation. | 2023-06-13 | Notification | 2022-09-01
GMP-22-G07 | 2022-07-11 | ER Nava Storage, LLC 1700 VT Rt 107 Solar | Generator notification from Green Mountain Power on behalf of ER Nava Storage, LLC for the installation of a 4.93 MW Solar PV in Royalton, VT and interconnecting to 1700 VT Rt 107 on the G29 circuit out of Bethel substation. | 2022-11-30 | Notification | 2022-09-01
GMP-22-G08 | 2022-07-11 | ER South Street Solar, LLC, 1432 South St Extension Solar | Generator notification from Green Mountain Power on behalf of ER South Street Solar, LLC for the installation of a 4.95 MW Solar PV in Middlebury, VT and interconnecting to 1342 South St Extension on the G23 circuit out of Middlebury substation. | 2022-11-14 | Notification | 2022-09-01
ES-22-G34 | 2022-07-29 | Airline Renewables, 254 Putnam Road Solar | Generator notification from Eversource Energy (ES) on behalf of Airline Renewables for the installation of a 1.968 MW Solar PV in Pomfret Center, CT and interconnecting to 254 Putnam Road on the 14M9 circuit out of Tracy substation. | 2022-12-01 | Notification | 2022-09-01
GMP-22-G09 | 2022-07-11 | ER South Street Storage, LLC 1342 South St Extension Battery | Generator notification from Green Mountain Power on behalf of ER South Street Storage, LLC for the installation of a 2.0 MW battery in Middlebury, VT and interconnecting to 1342 South St Extension on the G23 circuit out of Middlebury substation. | 2022-11-30 | Notification | 2022-09-01
NEP-19-GNF144 Rev.1 | 2022-08-01 | Syncarpha Solar, South Street Solar and Battery | Generation notification from New England Power (NEP) on behalf of Syncarpha Solar for the installation of a 4.2 MW Solar PV and 2.0 MW/4.0 MWh AC Coupled battery in Tewksbury, MA and interconnecting to South Street on the 59L3 circuit out of East Tewksbury substation. | 2022-02-18 | Notification | 2022-09-01
ES-22-G22 | 2022-07-13 | Americold, 24 Northwest Drive Natural Gas Unit | Generator notification from Eversource Energy (ES) on behalf of Americold for the installation of a 2.0 MW Natural Gas Unit in Plainville, CT and interconnecting to 24 Northwest Drive on the 4A10 circuit out of the Plainville substation. | 2022-09-07 | Notification | 2022-09-01
ES-22-T33 | 2022-07-14 | P145 Line Rebuild | Transmission notification from Eversource Energy (ES) for the replacement of 12.5-miles of the 115-kV line P145 between Merrimack substation and Farmwood substation with 1272 ACSS 54/19 conductor. | 2024-03-31 | Notification | 2022-08-19
ES-22-T40 | 2022-08-01 | Scotia Street Station #492 - Replace 115/14/4/14/4 kV Transformer 110B | Transmission notification from Eversource Energy (ES) for the replacement of existing 115/14.4/14.4 kV, 140 MVA transformer at Scotia Street substation with new 140 MVA transformer. | 2022-09-22 | Notification | 2022-08-19
NEP-22-T21 | 2022-07-13 | Franklin Square Transformer Replacements | Transmission notification from New England Power for the replacements of 40 MVA Franklin Square Transformers 1, 2, and 3 with 33/44/55 MVA transformers. | 2022-09-09 | Notification | 2022-08-19
MMWEC-22-G01 | 2022-07-05 | Ludlow Solar Surplus Interconnection Service Request | Generator application from MMWEC for the installation of a 6.9 MW Solar project in Ludlow, MA and interconnecting within the Stony Brook switching station. | 2022-08-01 | Approved | 2022-07-19
ES-20-G124 Rev.1 | 2022-07-06 | Queue Position 781 (QP 781) Offshore Wind Modifications Project Rev.1 | Generator application from Eversource Energy for the installation of the 704 MW Revolution Wind 1 Offshore Wind Farm and interconnecting to Davisville 115 kV substation in Washington County, RI. | 2024-12-16 | Approved | 2022-07-31
ES-20-T20 Rev.1 | 2022-07-06 | Queue Position 781 (QP 781) Offshore Wind Modifications Project Rev.1 | Transmission application from Eversource Energy for the installation of a 175 MVAR onshore synchronous condenser at the Revolution Wind 275/115 kV substation. | 2024-06-01 | Approved | 2022-07-31
ES-20-T21 Rev.1 | 2022-07-06 | Queue Position 781 (QP 781) Offshore Wind Modifications Project Rev.1 | Transmission application from Eversource Energy for the 300 MVAR onshore synchronous condenser at the Revolution Wind 275/115 kV substation. | 2024-06-01 | Approved | 2022-07-31
ES-20-T22 Rev.1 | 2022-07-06 | Queue Position 781 (QP 781) Offshore Wind Modifications Project Rev.1 | Transmission application from Eversource Energy for the installation of two 115/275 kV onshore transformers at the Revolution Wind 275/115 kV substation. | 2024-06-01 | Approved | 2022-07-31
ES-20-T23 Rev.1 | 2022-07-06 | Queue Position 781 (QP 781) Offshore Wind Modifications Project Rev.1 | Transmission application from Eversource Energy for the installation of two 275 kV submarine and terrestrial cables at the Revolution Wind 275/115 kV substation. | 2024-06-01 | Approved | 2022-07-31
ES-20-T24 Rev.1 | 2022-07-06 | Queue Position 781 (QP 781) Offshore Wind Modifications Project Rev.1 | Transmission application from Eversource Energy for the installation of four 275/66 kV offshore transformers at the Revolution Wind 275/115 kV substation. | 2024-06-01 | Approved | 2022-07-31
ES-20-T25 Rev.1 | 2022-07-06 | Queue Position 781 (QP 781) Offshore Wind Modifications Project Rev.1 | Transmission application from Eversource Energy for the installation of two 115 kV circuits at the Revolution Wind 275/115 kV substation. | 2024-06-01 | Approved | 2022-07-31
ES-20-T26 Rev.1 | 2022-07-01 | Queue Position 781 (QP 781) Offshore Wind Modifications Project Rev.1 | Transmission application from Eversource Energy for the installation of a redundant 345 kV circuit breaker at Card 11F substation. | 2023-01-31 | Approved | 2022-07-31
NEP-20-T06 Rev.1 | 2022-07-06 | Queue Position 781 (QP 781) Offshore Wind Modifications Project Rev.1 | Transmission application from New England Power for the rebuild of the existing 115/34.5 kV Davisville substation and conversion to a 6 breaker ring bus in North Kingstown, RI. | 2024-06-01 | Approved Withdrawn | 7/31/2022 10/24/2023
NEP-20-T07 Rev.1 | 2022-07-06 | Queue Position 781 (QP 781) Offshore Wind Modifications Project Rev.1 | Transmission application from New England Power for the reconductoring of the G-185N and K-189 Lines from Kent County substation to Drumrock substation. | 2024-06-01 | Approved Withdrawn | 7/31/2022 10/24/2023
NEP-20-T08 Rev.1 | 2022-07-06 | Queue Position 781 (QP 781) Offshore Wind Modifications Project Rev.1 | Transmission application from New England Power for the reconductoring of the G-185S and L-190 Lines from Kent County substation to Old Baptist Road substation to Davisville substation. | 2024-06-01 | Approved Withdrawn | 7/31/2022 10/24/2023
NEP-20-T32 Rev.1 | 2022-07-06 | Queue Position 781 (QP 781) Offshore Wind Modifications Project Rev.1 | Transmission application from New England Power for the Drumrock substation upgrades to upgrade the K-189 and G-185N limiting 115 kV equipment to 3000 A capacity. | 2024-06-01 | Approved Withdrawn | 7/31/2022 10/24/2023
CMP-22-G20 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - BD Solar, 445 Lewiston Junction Road Solar | Generation application from Central Maine Power (CMP) on behalf of BD Solar for the installation of a 4.99 MW PV facility in Auburn, ME and interconnecting to the Hotel Road substation via the 420D4 circuit. | 2022-11-08 | Approved | 2022-08-12
CMP-22-G21 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - BD Solar, 445 Lewiston Junction Road Solar | Generation application from Central Maine Power (CMP) on behalf of BD Solar for the installation of a 4.965 MW PV facility in Auburn, ME and interconnecting to the Hotel Road substation via the 420D4 circuit. | 2022-11-15 | Approved | 2022-08-12
CMP-22-G22 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - NextGrid, 1043 Main Street Solar | Generation application from Central Maine Power (CMP) on behalf of NextGrid for the installation of a 4.6 MW PV facility in Lewiston, ME and interconnecting to the Deer Rips substation via the 412D4 circuit. | 2023-12-31 | Approved | 2022-08-12
CMP-22-G23 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - Nexamp, 100 Penley Corner Road Solar and Battery | Generation application from Central Maine Power (CMP) on behalf of Nexamp for the installation of a 2.495 MW PV and 2.5 MW/10.0 MWh battery facility in Auburn, ME and interconnecting to the Great Falls substation via the 436D6 circuit. | 2023-06-30 | Approved Withdrawn | 8/12/2022 7/16/2024
CMP-22-G24 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - Borrego Solar, 1040 Perkins Ridge Road Solar and Battery | Generation application from Central Maine Power (CMP) on behalf of Borrego Solar for the installation of a 4.96 MW PV and 4.995 MW/26.0 MWh battery facility in Auburn, ME and interconnecting to the Hotel Road substation via the 420D2 circuit. | 2025-06-01 | Approved Withdrawn | 8/12/2022 7/16/2024
CMP-22-G25 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - Borrego Solar, Town Farm Road Solar | Generation application from Central Maine Power (CMP) on behalf of Borrego Solar for the installation of a 4.99 MW PV facility in Turner, ME and interconnecting to the Turner substation via the 454D1 circuit. | 2024-12-01 | Approved Withdrawn | 8/12/2022 9/19/2023
CMP-22-G26 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - 510 PV Project Development, 7 Springbrook Road Solar and Battery | Generation application from Central Maine Power (CMP) on behalf of 510 PV Project Development for the installation of a 4.99 MW PV and 4.99 MW/26.0 MWh battery facility in Turner, ME and interconnecting to the Turner Tap substation via the 467D1 circuit. | 2024-12-31 | Approved | 2022-08-12
CMP-22-G27 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - Turner CSG, 1393 Auburn Road Solar | Generation application from Central Maine Power (CMP) on behalf of Turner CSG for the installation of a 2.0 MW PV facility in Turner, ME and interconnecting to the Turner Tap substation via the 467D1 circuit. | 2023-03-31 | Approved Withdrawn | 8/12/2022 7/16/2024
CMP-22-G28 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - Turner CSG, 1393 Auburn Road Solar | Generation application from Central Maine Power (CMP) on behalf of Turner CSG for the installation of a 1.5 MW PV facility in Turner, ME and interconnecting to the Turner Tap substation via the 467D1 circuit. | 2023-03-31 | Approved Withdrawn | 8/12/2022 7/16/2024
CMP-22-G29 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - SRE Oringination 1, 308 Crowley Road Solar | Generation application from Central Maine Power (CMP) on behalf of SRE Origination 1 for the installation of a 2.0 MW PV facility in Sabattus, ME and interconnecting to the Crowleys substation via the 411D1 circuit. | 2023-06-01 | Approved | 2022-08-12
CMP-22-G30 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - Maine DG Holdings, 13 High Street Solar | Generation application from Central Maine Power (CMP) on behalf of Maine DG Holdings for the installation of a 4.851 MW PV facility in Paris, ME and interconnecting to the Norway substation via the 435D3 circuit. | 2023-12-31 | Approved | 2022-08-12
CMP-22-G31 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - Lisbon CSG, 47 Upland Road Solar | Generation application from Central Maine Power (CMP) on behalf of Lisbon CSG for the installation of a 3.125 MW PV facility in Lisbon, ME and interconnecting to the Lisbon substation via the 231D2 circuit. | 2023-03-13 | Approved Withdrawn | 8/12/2022 7/16/2024
CMP-22-G32 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - NextGrid Avocado, 0 South Main Street Solar | Generation application from Central Maine Power (CMP) on behalf of NextGrid Avocado for the installation of a 4.95 MW PV facility in Sabattus, ME and interconnecting to the Mechanic Falls substation via the 431D3 circuit. | 2023-12-31 | Approved Withdrawn | 8/12/2022 11/19/2024
CMP-22-G33 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - NextGrid Bayberry, 497 Minot Road Solar | Generation application from Central Maine Power (CMP) on behalf of NextGrid Bayberry for the installation of a 1.962 MW PV facility in Minot, ME and interconnecting to the Mechanic Falls substation via the 431D2 circuit. | 2023-12-31 | Approved | 2022-08-12
CMP-22-G34 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - TPE ME SB01, 121 Webster Corner Road Solar | Generation application from Central Maine Power (CMP) on behalf of TPE ME SB01 for the installation of a 4.876 MW PV facility in Sabattus, ME and interconnecting to the Crowleys substation via the 411D1 circuit. | 2023-03-31 | Approved | 2022-08-12
CMP-22-G35 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - ISM Solar Ryan Ranch, 0 Fore Street Solar | Generation application from Central Maine Power (CMP) on behalf of ISM Solar Ryan Ranch for the installation of a 3.0 MW PV facility in Oxford, ME and interconnecting to the Norway substation via the 435D1 circuit. | 2023-06-30 | Approved | 2022-08-12
CMP-22-G36 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - Taylor Hill Road Solar, 106 Taylor Hill Road Solar | Generation application from Central Maine Power (CMP) on behalf of Taylor Hill Road Solar for the installation of a 2.656 MW PV facility in Lewiston, ME and interconnecting to the Deep Rips substation via the 412D4 circuit. | 2023-05-01 | Approved Withdrawn | 8/12/2022 7/16/2024
CMP-22-G37 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - EDF Renewables, 268 Old Webster Road Solar | Generation application from Central Maine Power (CMP) on behalf of EDF Renewables for the installation of a 4.999 MW PV facility in Lewiston, ME and interconnecting to the Crowleys substation via the 411D2 circuit. | 2023-12-31 | Approved | 2022-08-12
CMP-22-G38 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - SRE Solar Origination 2, 27 Addi Drive Solar | Generation application from Central Maine Power (CMP) on behalf of SRE Solar Origination 2 for the installation of a 1.625 MW PV facility in Oxford, ME and interconnecting to the Oxford substation via the 437D1 circuit. | 2023-12-31 | Approved | 2022-08-12
CMP-22-G39 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - MEVS Pulk, 69 Lisbon Road Solar | Generation application from Central Maine Power (CMP) on behalf of MEVS Pulk for the installation of a 4.945 MW PV facility in Sabattus, ME and interconnecting to the Sabattus substation via the 450D1 circuit. | 2023-12-31 | Approved | 2022-08-12
CMP-22-G41 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - Solar Provider Group, 11 Forbes Road Solar | Generation application from Central Maine Power (CMP) on behalf of Solar Provider Group for the installation of a 1.875 MW PV facility in Lisbon, ME and interconnecting to the Lisbon Falls substation via the 232D1 circuit. | 2023-12-31 | Approved Withdrawn | 8/12/2022 9/19/2023
CMP-22-G42 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - 510 PV Project Development, 101 Frost Hill Avenue Solar and Battery | Generation application from Central Maine Power (CMP) on behalf of 510 PV Project Development for the installation of a 1.999 MW PV and 1.999 MW/10.5 MWh battery facility in Lisbon, ME and interconnecting to the Lisbon substation via the 231D1 circuit. | 2024-12-31 | Approved Withdrawn | 8/12/2022 7/16/2024
CMP-22-G43 | 2022-06-27 | Central Maine Power Lewiston Loop Distributed Energy Resources (DER) Cluster Study - Lewiston Solar II, 24 Ferry Road Solar | Generation application from Central Maine Power (CMP) on behalf of Lewiston Solar II for the installation of a 3.75 MW PV facility in Lewiston, ME and interconnecting to the Challenger 12 kV substation via the 421D2 circuit. | 2022-12-01 | Approved | 2022-08-12
NEP-22-T07 | 2022-07-01 | Vernon Station #13 Rebuild/Huntington #3026 Substation and 69 kV D-4 Line Protection Upgrade Project | Transmission application from New England Power to rebuild and rename the Vernon #13 substation to Huntington #3026 substation consisting of four 69 kV bays in a breaker and a half configuration. | 2025-12-12 | Approved | 2022-07-20
NEP-22-X01 | 2022-07-01 | Vernon Station #13 Rebuild/Huntington #3026 Substation and 69 kV D-4 Line Protection Upgrade Project | Transmission application from New England Power to upgrade the relay and communication systems at the Huntington and Deerfield substations. | 2027-02-28 | Approved | 2022-07-20
GRH-22-T01 | 2022-07-05 | Vernon Station #13 Rebuild/Huntington #3026 Substation and 69 kV D-4 Line Protection Upgrade Project | Transmission application from Great River Hydro for the rebuild of the Vernon 69 kV interconnection facility. | 2025-12-12 | Approved | 2022-07-20
WRD-22-G01 | 2022-07-05 | Mousam River Solar Project (QP 910) | Generator application from Walden Renewables for the installation of a 20 MW solar plant in Sanford, ME and interconnecting to the 34.5 kV circuit out of Sanford Substation. | 2024-12-30 | Approved | 2022-08-12
ES-22-G28 | 2022-07-06 | Mykiss Solar Project (QP 936) | Generator application from Eversource Energy on behalf of Mykiss Solar, LLC for the installation of a 45 MW solar plant in Dummer, NH and interconnecting to the 115 kV circuit out of Paris Switching Station. | 2022-11-07 | Approved Withdrawn | 8/12/2022 12/6/2023
ES-22-T36 | 2022-07-06 | Mykiss Solar Project (QP 936) | Transmission application from Eversource Energy for the installation of a new 10 MVAR Shunt Capacitor and 115 kV circuit breaker at the Lost Nation 115 kV substation in Northumberland, NH. | 2022-11-07 | Approved Withdrawn | 8/12/2022 12/6/2023
ES-22-T37 | 2022-07-06 | Mykiss Solar Project (QP 936) | Transmission application from Eversource Energy for the installation of a 115 kV tie line and 115 kV circuit breaker at the Paris substation in Dummer, NH. | 2022-11-07 | Approved Withdrawn | 8/12/2022 12/6/2023
CMP-22-G97 | 2022-07-01 | Topsham Meadow Solar Station Project (QP 1013) | Generator application from Central Maine Power on behalf of Topsham Meadow Solar Station LLC for the installation of 17.2 MW of solar inverters in Topsham, ME and interconnecting to Section 43 approximately three miles from Topsham substation. | 2022-09-30 | Approved | 2022-08-12
BRP-22-G03 | 2022-07-05 | Bonny Eagle Energy Storage Project (QP 1104) | Generator application from Brookfield Renewables Trading and Marketing for the installation of a 8.165 MW energy storage facility in Hollis, ME and interconnecting to the 34.5 kV circuit out of Bonny Eagle substation. | 2022-11-01 | Approved | 2022-08-12
ES-22-G19 | 2022-06-02 | ReVision Energy Inc, 0 Plain Road Solar | Generator notification from Eversource Energy (ES) on behalf of ReVision Energy Inc. for the installation of a 2.49 MW Solar PV in Hinsdale, NH and interconnecting to 0 Plain Road, Hinsdale, NH on the 34.5 kV circuit out of Chestnut Hill substation. | 2022-07-01 | Notification | 2022-08-01
ES-22-G20 | 2022-06-02 | NHSG, 909 W Swanzey Road Solar | Generator notification from Eversource Energy (ES) on behalf of NHSG for the installation of a 3.0 MW Solar PV in Swanzey, NH and interconnecting to 909 W Swanzey Road, Swanzey, NH on the 4.16 kV circuit out of Swanzey substation. | 2022-07-01 | Notification | 2022-08-01
ES-22-G21 | 2022-06-02 | NHSG, Industrial Park Drive Solar | Generator notification from Eversource Energy (ES) on behalf of NHSG for the installation of a 2.0 MW Solar PV in Franklin, NH and interconnecting to Industrial Park Drive, Franklin, NH on the 34.5 kV circuit out of Webster substation. | 2022-07-01 | Notification | 2022-08-01
ES-21-G106 Rev.1 | 2022-07-05 | Thompson Family Land Trust, Scitico Solar Rev.1 | Generator notification from Eversource Energy (ES) on behalf of Thompson Family Land Trust for the installation of a 6.0 MW Solar PV in Ellington, CT and interconnecting on the 27H9 circuit out of the Scitico substation. Revision to reflect the most recent inverter design. | 2022-06-30 | Notification | 2022-08-12
CMP-22-G96 | 2022-07-01 | TPE Development, OO01 Ross Road Solar | Generator notification from Central Maine Power (CMP) on behalf of TPE Development for the installation of a 4.7 MW Solar PV in Old Orchard Beach, ME and interconnecting to OO01 Ross Road, Old Orchard Beach, ME on circuit 630D4 out of Goosefare substation. | 2022-08-30 | Notification | 2022-08-12
NEP-19-GNF38 Rev.1 | 2022-07-01 | Nexamp Interconnections, West Street Solar and Battery | Generation notification from New England Power (NEP) on behalf of Nexamp Interconnections for the installation of a 4.98 MW Solar PV and 3.0 MW/6.0 MWh DC Coupled Battery in Douglas, MA and interconnecting to West Street, Douglas, MA on the 321W4 circuit out of Uxbridge substation. | 2023-03-18 | Notification | 2022-08-12
ES-22-G29 | 2022-07-01 | Delorean Power, 25 Fargo Road Battery | Generator notification from Eversource Energy (ES) on behalf of Delorean Power for the installation of a 4.99 MW/19.535 MWh Battery in Waterford, CT and interconnecting to 25 Fargo Road, Waterford, CT on the 23 kV circuit out of Waterford 36F substation. | 2024-06-01 | Notification | 2022-08-12
NEP-22-GNF07 | 2022-07-01 | Onsite Renewables, Kennedy Drive Battery | Generation notification from New England Power (NEP) on behalf of Onsite Renewables for the installation of a 4.999 MW/18.432 MWh Battery in Malden, MA and interconnecting to Kennedy Drive, Malden, MA on the 16W3 circuit out of Maplewood substation. | 2024-05-01 | Notification Withdrawn | 8/12/2022 9/17/2024
ES-22-T10 | 2022-06-20 | Partial Rebuild of Line 1327 | Transmission notification from Eversource Energy (ES) for the partial rebuild of 1.1-miles of Line 1327 with 1590-kcmil ACSS conductor. | 2022-12-31 | Notification | 2022-07-20
ES-22-T11 | 2022-06-20 | Partial Rebuild of Line 1428 | Transmission notification from Eversource Energy (ES) for the partial rebuild of 1.33-miles of Line 1428 with 1590-kcmil ACSS conductor. | 2022-12-31 | Notification | 2022-07-20
ES-22-T12 | 2022-06-20 | Partial Rebuild of Line 1447 | Transmission notification from Eversource Energy (ES) for the partial rebuild of 0.23-miles of Line 1447 with 1590-kcmil ACSS conductor. | 2022-12-31 | Notification | 2022-07-20
ES-22-T24 | 2022-06-17 | Replacement of Step-Down Transformer 1X at Beacon Falls Substation | Transmission notification from Eversource Energy (ES) for the replacement of existing step-down transformer 1X at Beacon Falls substation. | 2025-12-31 | Notification | 2022-07-20
ES-22-T25 | 2022-06-17 | Replacement of Step-Down Transformer 2X at Beacon Falls Substation | Transmission notification from Eversource Energy (ES) for the replacement of existing step-down transformer 2X at Beacon Falls substation. | 2025-12-31 | Notification | 2022-07-20
ES-22-T30 | 2022-06-17 | Replacement of Step-Down Transformer 2X at Hopewell Substation | Transmission notification from Eversource Energy (ES) for the replacement of existing step-down transformer 2X at Hopewell substation. | 2024-05-31 | Notification | 2022-07-20
ES-22-T31 | 2022-06-17 | Replacement of Step-Down Transformer 3X at Hopewell Substation | Transmission notification from Eversource Energy (ES) for the replacement of existing step-down transformer 3X at Hopewell substation. | 2024-05-31 | Notification | 2022-07-20
NEP-22-T19 | 2022-06-21 | Chartley Pond Transformer T1 Replacement | Transmission notification from New England Power for the replacement of existing 115/23 kV transformer T1 at Chartley Pond substation in Norton, MA. | 2021-11-11 | Notification | 2022-07-20
NEP-22-G03-001 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Kearsage Solar 0 Paxton Street Solar and Battery Project | Generation application from New England Power (NEP) on behalf of Kearsage Solar for the installation of a 5.0 MW PV and 20.0 MW/70 MWh battery facility in Leicester, MA and interconnecting to the Stafford Street substation via the 2236W2 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-002 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 1355 Main Street Battery Project | Generation application from New England Power (NEP) on behalf of Kearsage Solar for the installation of a 5.0 MW PV and 20.0 MW/70 MWh battery facility in Leicester, MA and interconnecting to the Stafford Street substation via the 2236W2 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-003 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 500 Bouthelier Road Solar and Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 4.95 MW PV and 3.364 MW/6.727 MWh battery facility in Leicester, MA and interconnecting to the Stafford Street substation via the 2236W3 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-004 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - SWEB Development 430 Rochdale Street Solar and Battery Project | Generation application from New England Power (NEP) on behalf of SWEB Development for the installation of a 4.75 MW PV and 2.5 MW/6.0 MWh battery facility in Auburn, MA and interconnecting to the Stafford Street substation via the 2236W4 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-005 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 0 Henshaw Street Solar and Battery | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 2.8 MW PV and 1.766 MW/3.523 MWh battery facility in Auburn, MA and interconnecting to the Stafford Street substation via the 2236W5 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-006 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 267 Brockelman Road Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 6.0 MW/40.0 MWh battery facility in Lancaster, MA and interconnecting to the Pratts Junction substation via the 225W3 circuit. | 2023-12-31 | Approved Withdrawn | 7/11/2022 6/18/2024
NEP-22-G03-007 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 0 Willard Street Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 5.0 MW/20.0 MWh battery facility in Leominster, MA and interconnecting to the Pratts Junction substation via the 225W4 circuit. | 2023-12-31 | Approved | 2022-07-11
NEP-22-G03-008 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 65 McGovern Boulevard Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 8.0 MW/32.0 MWh battery facility in Lancaster, MA and interconnecting to the Laurel Circle substation via the 227W1 circuit. | 2023-12-31 | Approved Withdrawn | 7/11/2022 6/18/2024
NEP-22-G03-009 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 55 Sycamore Street Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 10.0 MW/40.0 MWh battery facility in Millbury, MA and interconnecting to the Millbury substation via the 304W5 circuit. | 2023-12-31 | Approved Withdrawn | 7/11/2022 2/14/2024
NEP-22-G03-010 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - C-Tec Solar 161 Armsby Road Solar and Battery Project | Generation application from New England Power (NEP) on behalf of C-Tec Solar for the installation of a 1.75 MW PV and 1.0 MW/5.504 MWh battery facility in Sutton, MA and interconnecting to the Millbury substation via the 304W6 circuit. | 2023-12-31 | Approved Withdrawn | 7/11/2022 2/22/2023
NEP-22-G03-011 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 325 Worcester Road Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 8.0 MW/32.0 MWh battery facility in Charlton, MA and interconnecting to the North Oxford substation via the 406L1 circuit. | 2023-12-31 | Approved | 2022-07-11
NEP-22-G03-012 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Melink Solar 47 Fort Hill Road Solar and Battery Project | Generation application from New England Power (NEP) on behalf of Melink Solar for the installation of a 4.4 MW PV and 3.5 MW/7.0 MWh battery facility in Oxford, MA and interconnecting to the North Oxford substation via the 406L3 circuit. | 2023-12-31 | Approved | 2022-07-11
NEP-22-G03-013 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 27 Industrial Park Road Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 5.6 MW/32.0 MWh battery facility in Oxford, MA and interconnecting to the North Oxford substation via the 406L4 circuit. | 2023-12-31 | Approved | 2022-07-11
NEP-22-G03-014 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - SWEB Development 259 Worcester Street Solar and Battery Project | Generation application from New England Power (NEP) on behalf of SWEB Development for the installation of a 3.0 MW PV and 1.998 MW/4.292 MWh battery facility in Southbridge, MA and interconnecting to the Snow Street substation via the 413L4 circuit. | 2023-12-31 | Approved Withdrawn | 7/11/2022 2/14/2024
NEP-22-G03-015 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 294 Southbridge Road Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 5.0 MW/20.0 MWh battery facility in Charlton, MA and interconnecting to the Snow Street substation via the 413L4 circuit. | 2023-12-31 | Approved | 2022-07-11
NEP-22-G03-016 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 288 Southbridge Road Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Energy for the installation of a 5.0 MW/20.0 MWh battery facility in Charlton, MA and interconnecting to the Snow Street substation via the 413L4 circuit. | 2023-12-31 | Approved Withdrawn | 7/11/2022 2/14/2024
NEP-22-G03-017 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Developmetn 0 Dresser Hill Road Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 5.5 MW/40.0 MWh battery facility in Charlton, MA and interconnecting to the Snow Street substation via the 413L8 circuit. | 2023-12-31 | Approved Withdrawn | 7/11/2022 2/14/2024
NEP-22-G03-018 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 225 Dresser Hill Road Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 2.75 MW/20.0 MWh battery facility in Southbridge, MA and interconnecting to the Snow Street substation via the 413L8 circuit. | 2023-12-31 | Approved | 2022-07-11
NEP-22-G03-019 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 0 Griffin Road Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 2.5 MW/20.0 MWh battery facility in Charlton, MA and interconnecting to the West Charlton substation via the 415L1 circuit. | 2023-12-31 | Approved | 2022-07-11
NEP-22-G03-020 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 17 Griffin Road Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 5.0 MW/40.0 MWh battery facility in Charlton, MA and interconnecting to the West Charlton substation via the 415L1 circuit. | 2023-12-31 | Approved Withdrawn | 7/11/2022 2/14/2024
NEP-22-G03-021 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 0 Griffin Road Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 10.0 MW/40.0 MWh battery facility in Charlton, MA and interconnecting to the West Charlton substation via the 415L2 circuit. | 2023-12-31 | Approved | 2022-07-11
NEP-22-G03-022 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Melink Solar 45 Greenwich Plain Road Solar and Battery | Generation application from New England Power (NEP) on behalf of Melink Solar for the installation of a 2.2 MW PV and 2.5 MW/5.0 MWh battery facility in Ware, MA and interconnecting to the Ware substation via the 501L3 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-023 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Melink Solar 147 Greenwich Road Solar and Battery Project | Generation application from New England Power (NEP) on behalf of Melink Solar for the installation of a 3.3 MW PV and 2.5 MW/5.0 MWh battery facility in Ware, MA and interconnecting to the Ware substation via the 501L5 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-024 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Melink Solar 278 Osborne Road Solar and Battery Project | Generation application from New England Power (NEP) on behalf of Melink Solar for the installation of a 2.2 MW PV and 1.5 MW/3.0 MWh battery facility in Ware, MA and interconnecting to the Ware substation via the 501L5 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-025 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Melink Solar 198 Old Greenwich Plains Road Solar and Battery Project | Generation application from New England Power (NEP) on behalf of Melink Solar for the installation of a 3.3 MW PV and 2.5 MW/5.0 MWh battery facility in Ware, MA and interconnecting to the Ware substation via the 501L5 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-026 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Sunpin Solar 40 Sizer Drive Solar and Battery Project | Generation application from New England Power (NEP) on behalf of Sunpin Solar for the installation of a 3.0 MW PV and 1.0 MW/1.886 MWh battery facility in Wales, MA and interconnecting to the Little Rest Road substation via the 516L1 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-027 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 749 Reed Street Solar and Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 2.8 MW PV and 0.929 MW/1.859 MWh battery facility in Warren, MA and interconnecting to the Little Rest Road substation via the 516L3 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-028 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 68 South Maple Street Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 5.0 MW/0.712 MWh battery facility in Brookfield, MA and interconnecting to the Lashaway substation via the 525L2 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-029 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 175 East Main Street Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 10.0 MW/40.0 MWh battery facility in West Brookfield, MA and interconnecting to the Lashaway substation via the 525L3 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-030 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Melink Solar 223 1/2 Charlton Road Solar and Battery Project | Generation application from New England Power (NEP) on behalf of Melink Solar for the installation of a 4.4 MW PV and 4.5 MW/9.0 MWh battery facility in Spencer, MA and interconnecting to the Meadow Street substation via the 552L1 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-031 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Sunpin Solar 112 Draper Road Solar Project | Generation application from New England Power (NEP) on behalf of Sunpin Solar for the installation of a 4.999 MW PV facility in East Brookfield, MA and interconnecting to the Meadow Street substation via the 552L3 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-032 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Melink Solar 113 Ash Street Solar and Battery Project | Generation application from New England Power (NEP) on behalf of Melink Solar for the installation of a 4.4 MW PV and 4.0 MW/8.0 MWh battery facility in Spencer, MA and interconnecting to the Meadow Street substation via the 552L4 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-033 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 112 Pleasantdale Road Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 10.0 MW/40.0 MWh battery facility in Rutland, MA and interconnecting to the Treasure Valley substation via the 55W1 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-034 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 0 Cleveland Road Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 8.0 MW/32.0 MWh battery facility in Hardwick, MA and interconnecting to the Barre substation via the 604W5 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-035 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Kearsage Solar 2380 Barre Road Solar and Battery Project | Generation application from New England Power (NEP) on behalf of Kearsage Solar for the installation of a 4.4 MW PV and 3.15 MW/4.4 MWh battery facility in Hardwick, MA and interconnecting to the Barre substation via the 604W5 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-036 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 131 State Road Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 8.0 MW/32.0 MWh battery facility in Westminster, MA and interconnecting to the Crystal Lake substation via the 607W4 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-037 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - TJA Clean Energy 6 Village Inn Road Solar and Battery Project | Generation application from New England Power (NEP) on behalf of TJA Clean Energy for the installation of a 2.3 MW PV and 2.515 MW/5.504 MWh battery facility in Westminster, MA and interconnecting to the East Westminster substation via the 609W2 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-038 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 0 Murdock Avenue Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 9.4 MW/80.0 MWh battery facility in Winchendon, MA and interconnecting to the East Winchendon substation via the 612W1 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-039 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 0 Murdock Avenue Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 5.5 MW/40.0 MWh battery facility in Winchendon, MA and interconnecting to the East Winchendon substation via the 612W2 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-040 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Sunpin Solar 185 Baldwinville Road Solar Project | Generation application from New England Power (NEP) on behalf of Sunpin Solar for the installation of a 4.999 MW PV facility in Winchendon, MA and interconnecting to the East Winchendon substation via the 612W3 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-041 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Verogy 0 Town Dump Road Solar and Battery Project | Generation application from New England Power (NEP) on behalf of verogy for the installation of a 5.0 MW PV and 2.5 MW/5.246 MWh facility in Royalston, MA and interconnecting to the Royalston substation via the 701W1 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-042 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Nexamp Interconnections 0 Lockes Village Road Solar Project | Generation application from New England Power (NEP) on behalf of Nextamp Interconnections for the installation of a 2.791 MW PV facility in Wendell, MA and interconnecting to the Wendell Depot substation via the 705W1 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-043 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 25 Brookside Road Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 10.0 MW/40.0 MWh battery facility in Orange, MA and interconnecting to the Wendell Depot substation via the 705W3 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-044 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Zero Point Development 207 Daniel Shays highway Battery Project | Generation application from New England Power (NEP) on behalf of Zero Point Development for the installation of a 8.0 MW/32.0 MWh battery facility in Orange, MA and interconnecting to the Wendell Depot substation via the 705W4 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-045 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Sunpin Solar 0 New Athol Road Solar and Battery Project | Generation application from New England Power (NEP) on behalf of Sunpin Solar for the installation of a 3.0 MW PV and 2.0 MW/3.772 MWh battery facility in Petersham, MA and interconnecting to the Wendell Depot substation via the 705W4 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-G03-046 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Sunpin 0 Conant Road Solar and Battery Project | Generation application from New England Power (NEP) on behalf of Sunpin Solar for the installation of a 4.125 MW PV and 3.0 MW/5.658 MWh battery facility in Athol, MA and interconnecting to the Wendell Depot substation via the 705W4 circuit. | 2026-03-01 | Approved | 2022-07-11
NEP-22-T08 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - East Winchendon Transformer Replacement Project | Transmission application from New England Power (NEP) for the replacement of the existing 115/13.8 kV transformer with a 33/44/55 MVA unit in Winchendon, MA. | 2025-09-30 | Approved | 2022-07-11
NEP-22-T09 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Royalston Transformer Replacement Project | Transmission application from New England Power (NEP) for the replacement of the existing 69/4.16 kV transformer with a 69/13.8 kV transformer in Royalston, MA. | 2025-09-30 | Approved | 2022-07-11
NEP-22-T10 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Wendell Depot Transformer Addition and Replacement Project | Transmission application from New England Power (NEP) for the replacement of the existing transformer with a 33/44/55 MVA unit and addition of a second transformer of the same size in Wendell, MA. | 2025-09-30 | Approved | 2022-07-11
NEP-22-T11 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Barre Transformer Replacement Project | Transmission application from New England Power (NEP) for the replacement of the two existing transformers with 33/44/55 MVA units in Barre, MA. | 2025-09-30 | Approved | 2022-07-11
NEP-22-T12 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Meadow Street 69 kV Breaker and Transformer Addition Project | Transmission application from New England Power (NEP) for the installation of a new 69/13.2 kV transformer and new 69 kV circuit breaker at Meadow Street substation in Spencer, MA. | 2025-09-30 | Approved | 2022-07-11
NEP-22-T13 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Ware 69/13.2 kV Transformer Replacement Project | Transmission application from New England Power (NEP) for the installation of a new 69/13.2 kV transformer in Ware, MA. | 2025-09-30 | Approved | 2022-07-11
NEP-22-T14 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Lashaway 69 kV Transformer Replacements Project | Transmission application from New England Power (NEP) for the replacement of the two existing transformers with 24/32/40 MVA units and modification of associated distribution equipment in North Brookfield, MA. | 2025-09-30 | Approved | 2022-07-11
NEP-22-T15 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Leicester Substation Retirement Project | Transmission application from New England Power (NEP) for the retirement of the Leicester substation in Leicester, MA. | 2024-09-30 | Approved | 2022-07-11
NEP-22-T16 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study - Royalston 69 kV Breaker Additions Project | Transmission application from New England Power (NEP) for the installation of four new 69 kV breakers at Royalston substation in Royalston, MA. | 2027-09-30 | Approved | 2022-07-11
NEP-22-T17 | 2022-05-31 | Western Massachusetts Distributed Energy Resources (DER) Group 3 Cluster Study E-5/F-6 69 kV Reconductoring Project | Transmission application from New England Power (NEP) for the reconductoring of all sections of E-5 and F-6 69 kV lines with 795 ACSS conductor in Shelburne, MA. | 2030-01-31 | Approved | 2022-07-11
JUP-22-G01 | 2022-05-27 | Queue Position 1110 200 MW Battery Energy Storage Project | Generator application from Jupiter Power for the installation of a 200 MW Battery Energy Storage Project in Everett, Massachusetts and interconnecting to the Mystic substation. | 2025-05-31 | Approved | 2022-07-11
JUP-22-T01 | 2022-05-27 | Queue Position 1110 200 MW Battery Energy Storage Project | Transmission application from Jupiter Power for the installation of a 115/34.5/13.2 kV 138 MVA main power transformer and 1.5 mile 115 kV underground generator lead line from Mystic substation to the project site. | 2025-05-31 | Approved | 2022-07-11
ES-22-T21 | 2022-06-01 | Queue Position 1110 200 MW Battery Energy Storage Project | Transmission application from Eversource Energy for the installation of a new duct bank between the existing Mystic 9 Unit 93 terminal and the Mystic substation fence line, including new terminal equipment. | 2025-05-31 | Approved | 2022-07-11
ES-22-T27 | 2022-05-27 | Eversource New Hampshire (NH) 2029 Reliability Project - North Keene Synchronous Condenser | Transmission application from Eversource Energy for the installation of a +55/-32.2 MVAR Synchronous Condenser with a 115 kV breaker at North Keene 115 kV Substation in Keene, NH. | 2023-08-31 | Approved | 2022-06-15
ES-22-T28 | 2022-05-27 | Eversource New Hampshire (NH) 2029 Reliability Project - Huckins Hill Synchronous Condenser | Transmission application from Eversource Energy for the installation of a +55/-32.2 MVAR Synchronous Condenser with a 115 kV breaker at Huckins Hill 115 kV Substation in Holderness, NH. | 2023-08-31 | Approved | 2022-06-15
ES-22-T29 | 2022-05-27 | Eversource New Hampshire (NH) 2029 Reliability Project - Amherst Synchronous Condenser | Transmission application from Eversource Energy for the installation of a +127/-50 MVAR Synchronous Condenser with three 345 kV breakers at Amherst 345 kV Substation in Amherst, NH. | 2023-12-31 | Approved | 2022-06-15
CMP-22-G95 | 2022-05-27 | Queue Position 1021 Emery Meadow Solar Project | Generator application from Central Maine Power on behalf of Emery Meadow Solar Station LLC for the installation of a 16.425 MW Solar project in Buxton, Maine and interconnecting to line Section 182. | 2023-11-30 | Approved | 2022-07-11
CMP-22-G03 | 2022-06-01 | Central Maine Power Sanford/Quaker Hill Distributed Energy Resources Cluster Study - Lebanon CSG 429 West Lebanon Road Solar Project | Generation application from Central Maine Power (CMP) on behalf of Lebanon CSG, LLC for the installation of a 3.75 MW PV facility in Lebanon, ME and interconnecting to the Lebanon substation via the 695D2 circuit. | 2023-02-28 | Approved | 2022-06-27
CMP-22-G05 | 2022-06-01 | Central Maine Power Sanford/Quaker Hill Distributed Energy Resources Cluster Study - NBD Solar, LLC 83 Airport Road Solar Project | Generation application from Central Maine Power (CMP) on behalf of NBD Solar, LLC for the installation of a 4.998 MW PV facility in Sanford, ME and interconnecting to the Sanford Industrial Park substation via the 656D3 circuit. | 2022-09-15 | Approved | 2022-06-27
CMP-22-G06 | 2022-06-01 | Central Maine Power Sanford/Quaker Hill Distributed Energy Resources Cluster Study - Novel Energy Solutions, LLC 43 Sokokis Trail Solar Project | Generation application from Central Maine Power (CMP) on behalf of Novel Energy Solutions, LLC for the installation of a 4.998 MW PV facility in Waterboro, ME and interconnecting to the Waterboro substation via the 671D2 circuit. | 2022-12-31 | Approved | 2022-06-27
CMP-22-G07 | 2022-06-01 | Central Maine Power Sanford/Quaker Hill Distributed Energy Resources Cluster Study - South Berwick, LLC South Berwick Water Co Road Solar and Battery | Generation application from Central Maine Power (CMP) on behalf of South Berwick Solar, LLC for the installation of a 4.999 MW PV and 2.5 MW/5.56 MWh DC Coupled Battery facility in South Berwick, ME and interconnecting to the Bassett substation via the 602D2 circuit. | 2022-12-31 | Approved Withdrawn | 6/27/2022 10/18/2022
CMP-22-G08 | 2022-06-01 | Central Maine Power Sanford/Quaker Hill Distributed Energy Resources Cluster Study - EDF Renewable, LLC 14 Hazen Drive Solar Project | Generation application from Central Maine Power (CMP) on behalf of EDF Renewables, LLC for the installation of a 4.999 MW PV facility in Springvale, ME and interconnecting to the Butler’s Corner substation via the 612D1 circuit. | 2024-04-01 | Approved Withdrawn | 6/27/2022 11/19/2024
CMP-22-G09 | 2022-06-01 | Central Maine Power Sanford/Quaker Hill Distributed Energy Resources Cluster Study ReneSola Power Holdings, LLC 252 Lebanon Road Solar Project | Generation application from Central Maine Power (CMP) on behalf of ReneSola Power Holdings,LLC for the installation of a 1.994 MW PV facility in Lebanon, ME and interconnecting to the Lebanon substation via the 695D2 circuit. | 2023-06-15 | Approved | 2022-06-27
CMP-22-G10 | 2022-06-01 | Central Maine Power Sanford/Quaker Hill Distributed Energy Resources Cluster Study - BD Solar York, LLC 53 Major McIntire Road Solar Project | Generation application from Central Maine Power (CMP) on behalf of BD Solar York, LLC for the installation of a 4.949 MW PV facility in York, ME and interconnecting to the Bragdon Commons substation via the 689D1 circuit. | 2023-02-17 | Approved Withdrawn | 6/27/2022 9/19/2023
CMP-22-G11 | 2022-06-01 | Central Maine Power Sanford/Quaker Hill Distributed Energy Resources Cluster Study - Berwick Hubbard Solar 1, LLC 467 Hubbard Road Solar Project | Generation application from Central Maine Power (CMP) on behalf of Berwick Hubbard Solar 1, LLC for the installation of a 3.34 MW PV facility in Berwick, ME and interconnecting to the Berwick substation via the 603D2 circuit. | 2023-07-01 | Approved | 2022-06-27
CMP-22-G12 | 2022-06-01 | Central Maine Power Sanford/Quaker Hill Distributed Energy Resources Cluster Study - Lebanon West Lebanon Solar 1, LLC 429 West Lebanon Road Solar Project | Generation application from Central Maine Power (CMP) on behalf of Lebanon West Lebanon Solar 1, LLC for the installation of a 3.3 MW PV facility in Lebanon, ME and interconnecting to the Lebanon substation via the 695D1 circuit. | 2023-07-01 | Approved | 2022-06-27
CMP-22-G13 | 2022-06-01 | Central Maine Power Sanford/Quaker Hill Distributed Energy Resources Cluster Study - York Solar 1, LLC 74 Witchtrot Solar Project | Generation application from Central Maine Power (CMP) on behalf of York Solar 1, LLC for the installation of a 4.826 MW PV facility in York, ME and interconnecting to the South Berwick substation via the 663D2 circuit. | 2022-12-01 | Approved Withdrawn | 6/27/2022 9/19/2023
CMP-22-G14 | 2022-06-01 | Central Maine Power Sanford/Quaker Hill Distributed Energy Resources Cluster Study - MSD Sanford, LLC 5 Ledgewood Avenue Solar Project | Generation application from Central Maine Power (CMP) on behalf of MSD Sanford, LLC for the installation of a 4.875 MW PV facility in Sanford, ME and interconnecting to the Sanford Switch substation via the 657D4 circuit. | 2023-12-31 | Approved Withdrawn | 6/27/2022 9/19/2023
CMP-22-G15 | 2022-06-01 | Central Maine Power Sanford/Quaker Hill Distributed Energy Resources Cluster Study - MEVS Brown, LLC 987 Back Road Solar Project | Generation application from Central Maine Power (CMP) on behalf of MEVS Brown, LLC for the installation of a 4.98 MW PV facility in Shapleigh, ME and interconnecting to the Sanford Switch substation via the 657D3 circuit. | 2023-12-31 | Approved Withdrawn | 6/27/2022 1/18/2023
CMP-22-G16 | 2022-06-01 | Central Maine Power Sanford/Quaker Hill Distributed Energy Resources Cluster Study - BWC Bauneg Bed Pond, LLC 60 Pinewood Drive Solar Project | Generation application from Central Maine Power (CMP) on behalf of BWC Bauneg Beg Pond, LLC for the installation of a 4.915 MW PV facility in Sanford, ME and interconnecting to the Sanford Industrial Park substation via the 656D2 circuit. | 2023-07-26 | Approved Withdrawn | 6/27/2022 9/19/2023
CMP-22-G17 | 2022-06-01 | Central Maine Power Sanford/Quaker Hill Distributed Energy Resources Cluster Study - ReneSola Power Holdings, LLC Mount Hope Road Solar Project | Generation application from Central Maine Power (CMP) on behalf of ReneSola Power Holdings, LLC for the installation of a 1.995 MW PV facility in Sanford, ME and interconnecting to the High Street substation via the 626D5 circuit. | 2023-06-15 | Approved Withdrawn | 6/27/2022 11/19/2024
CMP-22-G18 | 2022-06-01 | Central Maine Power Sanford/Quaker Hill Distributed Energy Resources Cluster Study - ME I So Berwick Dow South Berwick Punkintown Road Solar | Generation application from Central Maine Power (CMP) on behalf of NESG SCF Maine 1 Holdco, LLC for the installation of a 1.999 MW PV facility in Berwick, ME and interconnecting to the South Berwick substation via the 663D2 circuit. | 2023-09-30 | Approved Withdrawn | 6/27/2022 1/18/2023
CMP-22-G19 | 2022-06-01 | Central Maine Power Sanford/Quaker Hill Distributed Energy Resources Cluster Study - ME I N. Berwick Valley LLC Oak Woods Road Solar Project | Generation application from Central Maine Power (CMP) on behalf of ME I N Berwick Valley, LLC for the installation of a 1.999 MW PV facility in Berwick, ME and interconnecting to the Pratt & Whitney substation via the 661D1 circuit. | 2023-09-30 | Approved Withdrawn | 6/27/2022 11/19/2024
ES-22-G11 Rev.1 | 2022-05-10 | US Solar LLC, Vista Drive Solar Rev.1 | Generator notification from Eversource Energy (ES) on behalf of US Solar LLC for the installation of a 2.0 Solar PV in Torrington, CT and interconnecting to Vista Drive, Torrington, CT on circuit 8A1 out of Torrington Terminal 8A substation. | 2023-12-31 | Notification | 2022-07-01
ES-22-T13 | 2022-05-06 | Replacement of Step-Down Transformer 2X at Ridgefield Substation | Replacement of existing Step-Down Transformer 2X at Ridgefield Substation in Ridgefield, CT. | 2023-05-31 | Notification | 2022-06-15
ES-22-T14 | 2022-05-06 | Replacement of Step-Down Transformer 3X at Ridgefield Substation | Replacement of existing Step-Down Transformer 3X at Ridgefield Substation in Ridgefield, CT. | 2023-12-31 | Notification | 2022-06-15
ES-22-T26 | 2022-05-30 | Replacement of Step-Down Transformer 1X at East Meriden Substation | Replacement of existing Step-Down Transformer 1X at East Meriden Substation in Meriden, CT. | 2022-07-15 | Notification | 2022-06-15
LRE-22-G01 | 2022-05-03 | Queue Position 670 (QP 670) Three Corners Solar Solar Project | Generation application from Three Corners Solar, LLC for the installation of thirty-nine 3.55 MVA inverters (138.45 MVA) and thirty-nine 645 V/34.5 kV step-up transformers in Somerset County, ME and interconnecting to the Albion Road 115 kV substation. | 2023-09-01 | Approved | 2022-06-08
LRE-22-T01 | 2022-05-03 | Queue Position 670 (QP 670) Three Corners Solar Solar Project | Transmission application from Three Corners Solar, LLC for the installation of approximately 5.28 miles of 115 kV transmission between the QP 670 collector substation and the Albion Road substation in Somerset County, ME. | 2023-07-03 | Approved | 2022-06-08
LRE-22-T02 | 2022-05-03 | Queue Position 670 (QP 670) Three Corners Solar Solar Project | Transmission application from Three Corners Solar, LLC for the installation of a 115 kV/34.5 kV/13.8 kV Main Power Transformer at the QP 670 collector substation in Somerset County, ME. | 2023-07-03 | Approved | 2022-06-08
CMP-22-T05 | 2022-05-03 | Queue Position 670 (QP 670) Three Corners Solar Solar Project | Transmission application from Central Maine Power for the installation of a 115 kV breaker and relocation of Section 257 to a new bay at Albion Road substation in Somerset County, ME. | 2023-07-03 | Approved | 2022-06-08
GBCTH-22-G01 | 2022-04-12 | Devon AVR Replacement Project | Generation application from Devon Power LLC for the replacement of existing AVRs at Devon Units 11, 12, 13, and 14 in Milford, CT. | 11 - 9/25/2022 12 - 10/2/2022 13 - 10/9/2022 14 - 10/16/2022 | Approved | 2022-06-08
NEP-20-G04-010 Rev.2 | 2022-05-02 | Western Rhode Island ASO Study #1 and #2 Revisions | Generation application from New England Power on behalf of Green Development LLC to remove the references to the withdrawn transmission Proposed Plan Applications NEP-20-T31 and NEP-21-T01. Project is for the installation of 2.0 MW of Solar PV in Exeter, RI and interconnecting to the Tower Hill substation. | 2021-07-15 | Approved | 2022-06-08
NEP-20-G04-030 Rev.2 | 2022-05-02 | Western Rhode Island ASO Study #1 and #2 Revisions | Generation application from New England Power on behalf of Green Development LLC to remove the references to the withdrawn transmission Proposed Plan Applications NEP-20-T31 and NEP-21-T01. Project is for the installation of 5.25 MW of Solar PV in West Kingston, RI and interconnecting to the Kenyon substation. | 2021-07-15 | Approved Withdrawn | 6/8/2022 8/13/2024
NEP-20-G04-034 Rev.1 | 2022-05-02 | Western Rhode Island ASO Study #1 and #2 Revisions | Generation application from New England Power on behalf of Green Development LLC to remove the references to the withdrawn transmission Proposed Plan Applications NEP-20-T31 and NEP-21-T01. Project is for the installation of 10.0 MW of Solar PV in West Greenwich, RI and interconnecting to the Kent County substation. | 2022-10-01 | Approved | 2022-06-08
NEP-20-G04-035 Rev.1 | 2022-05-02 | Western Rhode Island ASO Study #1 and #2 Revisions | Generation application from New England Power on behalf of Green Development LLC to remove the references to the withdrawn transmission Proposed Plan Applications NEP-20-T31 and NEP-21-T01. Project is for the installation of 10.0 MW of Solar PV in West Greenwich, RI and interconnecting to the Kent County substation. | 2022-10-01 | Approved | 2022-06-08
NEP-22-G02 | 2022-05-03 | Uxbridge Battery Energy Storage System Project | Generation application from New England Power on behalf of Uxbridge for the installation of a 4.948 MW Battery Energy Storage System in Uxbridge, MA and interconnecting to the Uxbridge substation. | 2024-12-31 | Approved | 2022-05-24
ES-22-T16 | 2022-05-03 | Install Mobile Transformer at Burlington Station 391 Project | Transmission application from Eversource Energy for the installation of a new 50 MVA 115/14.4 kV mobile transformer at Burlington Station 391 in Burlington, MA. | 2022-10-31 | Approved | 2022-05-24
GMP-22-G02 | 2022-04-13 | Green Mountain Power, Otter Creek Stark Solar | Generator notification from VELCO on behalf of Green Mountain Power for the installation of a 2.2 MW Solar PV in Bennington, VT and interconnecting to Rice Lane, Bennington, VT on the G59 circuit out of Silk Road substation. | 2023-12-31 | Notification | 2022-06-08
GMP-22-G03 | 2022-04-13 | Green Mountain Power, Otter Creek Warner Solar | Generator notification from VELCO on behalf of Green Mountain Power for the installation of a 2.2 MW Solar PV in Bennington, VT and interconnecting to Rice Lane, Bennington, VT on the G59 circuit out of Silk Road substation | 2023-12-31 | Notification | 2022-06-08
VELCO-22-GNF03 | 2022-04-19 | ER Sand Hill Solar LLC, 181 Sand Hill Road Solar | Generator notification from VELCO on behalf of ER Sand Hill Solar LLC for the installation of a 2.2 MW Solar PV in Castleton, VT and interconnecting to Sand Hill Road, Castleton, VT on the G37 circuit out of Castleton substation. | 2022-05-01 | Notification | 2022-06-08
VELCO-22-GNF04 | 2022-04-19 | ER Center Road Solar LLC, 340 Center Road Solar | Generator notification from VELCO on behalf of ER Center Road Solar LLC for the installation of a 2.1 MW Solar PV in Hardwick, VT and interconnecting to Center Road, Hardwick, VT on the 12.47 kV circuit out of Greensboro Bus #3. | 2022-03-28 | Notification | 2022-06-08
NEP-22-GNF06 | 2022-05-02 | Ameresco Solar LLC, Jenckes Hill Road Solar | Generator notification from New England Power on behalf of Ameresco Solar LLC for the installation of a 2.276 MW Solar PV in Lincoln, RI and interconnecting to Jenckes Hill Road on circuit 126W42 out of Washington substation. | 2023-06-01 | Notification | 2022-06-08
ES-22-G16 | 2022-04-26 | Greenskies, Jeremy Hill Rd Solar | Generator notification from Eversource Energy on behalf of Greenskies for the installation of a 4.999 MW Solar PV in Stonington, CT and interconnecting to Jeremy Hill Road, Stonington, CT on the A2 Bus out of Shunock substation. | 2022-09-01 | Notification | 2022-06-08
ES-22-G17 | 2022-05-03 | Ameresco Inc. Hickory Street Solar | Generator notification from Eversource Energy on behalf of Ameresco Inc for the installation of a 1.328 MW Solar PV in Suffield, CT and interconnecting to Hickory Street, Suffield, CT on the 30A2 circuit out of Silver 30A substation. | 2022-10-01 | Notification Withdrawn | 6/8/2022 8/13/2024
CMP-21-G22 Rev.1 | 2022-05-03 | Odiorne Lane Solar, LLC, 10 Odiorne Lane Solar | Generator notification from Central Maine Power on behalf of Odiorne Lane Solar, LLC for the installation of a 1.999 MW Solar PV in Eliot, ME and interconnecting to 10 Odiorne Lane, Eliot, ME on the 12.47 kV circuit out of Eliot substation. | 2023-03-31 | Notification | 2022-06-08
CMP-20-G97 Rev.1 | 2022-05-03 | ISM Solar Buttermilk Farm, LLC Dexter St. Solar | Generator notification from Central Maine Power on behalf of ISM Solar Buttermil Farm, LLC for the installation 4.999 MW Solar PV in Thomaston, ME and interconnecting to Dexter St., Thomaston, ME on the 12.47 kV circuit out of Park Street substation. | 2023-06-30 | Notification | 2022-06-08
ES-22-G14 | 2022-04-26 | NextGrid Tree of Heaven LLC, 1073 Main Street Solar and Battery | Generator notification from Eversource Energy on behalf of NextGrid Tree of Heaven LLC for the installation of a 2.15 MW Solar PV and 1.5 MW/6.0 MWh DC Coupled Battery in Mills, MA and interconnecting to 1073 Main Street, Mills, MA on the 14 kV circuit out of Walpole substation. | 2022-10-10 | Notification | 2022-06-08
ES-22-G15 | 2022-04-26 | Neponset Solar LLC, 455 South Street Solar and Battery | Generator notification from Eversource Energy on behalf of Neponset Solar LLC for the installation of a 2.0 MW Solar PV and 1.5 MW/6.0 MWh DC Coupled Battery in Walpole, MA and interconnecting to 455 South Street, Walpole, MA on the 14 kV circuit out of Walpole substation. | 2022-10-26 | Notification | 2022-06-08
VELCO-22-G01 | 2022-04-15 | NextSun Energy Rutland BESS LLC, 232 US Route 7 Battery | Generator notification from VELCO on behalf of NextSun Energy for the installation of a 4.97 MW BESS System in Rutland, VT and interconnecting to 232 US Route 1, Rutland, VT on the 12.0 kV circuit out of the North Rutland substation. | 2022-12-31 | Notification Withdrawn | 6/8/2022 4/17/2024
ES-22-T19 | 2022-04-26 | Replace the Existing 115/13.8 kV Transformer 110A at Medway Substation with a New Larger Unit | Replacement of the existing Medway Distribution Transformer 110A with a new, larger transformer. | 2023-08-31 | Notification | 2022-05-24
ES-22-T20 | 2022-04-26 | Replace Existing 115/13.8 kV Transformer 110B at Medway Substation with a New Larger Unit and Add One 115 kV Circuit Breaker | Replacement of the existing Medway Distribution Transformer 110B with a new, larger transformer and installing a 115 kV circuit breaker to match the existing breakers at Medway substation. | 2023-05-31 | Notification | 2022-05-24
CMP-22-T04 | 2022-05-05 | Rebuild 21.7 Miles of the 115 kV Line Section 80 Highland - Coopers Mills | Rebuild of 21.7 miles of the existing 115 kV line Section 80 between Highland and Coopers Mills substations with 1192.5 45/7 ACSR Bunting conductor. | 2027-12-31 | Notification | 2022-05-24
BRP-21-G01 | 2022-04-12 | Rumford Hydro Unit 2 Hydroelectric Gen AVR Replacement Project | Generation application from Brookfield Renewable Trading & Marketing for the replacement of the existing AVR at Rumford Lower Hydro Unit 2 with a new Basler DECS-250 digital AVR. | 2022-05-05 | Approved | 2022-05-06
ES-22-G09 | 2022-03-15 | Lodestar Energy Scorpious Solar PV Project | Generation application from Eversource Energy on behalf of Lodestar Energy for the installation of 1.999 MW of PV in Putnam, CT and interconnecting to the Tracy 14M Substation. | 2023-12-31 | Approved | 2022-05-06
ES-22-G04 | 2022-04-01 | Milford Spartan Solar | Generation application from Eversource Energy on behalf of Olivewood Energy for the installation of 16 MW of PV in Milford, NH and interconnecting to the South Milford Substation. | 2022-04-01 | Approved | 2022-05-06
IES-22-G01 | 2022-04-12 | South Wrentham Battery Energy Storage System Generation and Transmission Project | Generator application from ConnectGen for the installation of fifty-five (55) 3.16 MW inverters for a total of 173.8 MW (170 MW net output) of battery storage located in South Wrentham, MA and interconnecting to the South Wrentham 115 kV Substation. | 2023-12-31 | Approved | 2022-05-06
IES-22-T01 | 2022-04-12 | South Wrentham Battery Energy Storage System Generation and Transmission Project | Transmission application from ConnectGen for the installation of a 34.5/115 kV substation, 13.8/34.5/115 kV power transformer, and 115 kV generator lead line at the South Wrentham BESS project site in South Wrentham, MA. | 2023-10-28 | Approved | 2022-05-06
NEP-22-T05 | 2022-04-13 | South Wrentham Battery Energy Storage System Generation and Transmission Project | Transmission application from New England Power for the reconductoring of the C129S 115 kV line from South Wrentham to Union Street and C181N/D182N 115 kV lines from South Wrentham to Berry Street with 795 ACSR. | 2027-02-01 | Approved | 2022-05-06
NEP-22-T06 | 2022-04-13 | South Wrentham Battery Energy Storage System Generation and Transmission Project | Transmission application from New England Power for the conversion of South Wrentham substation into a five breaker ring bus and upgrades of terminal equipment. | 2025-01-01 | Approved | 2022-05-06
ES-22-G02 | 2022-03-10 | Greenskies Clean Energy LLC, 129 Bartholomew Hill RD Solar | Generator notification from Eversource Energy on behalf of Greenskies Clean Energy for the installation of a 4.0 MW Solar PV in Goshen, CT and interconnecting to 129 Bartholomew Hill Rd, Goshen, CT on the 27.6 kV circuit out of Campville 14R substation. | 2022-09-01 | Notification Withdrawn | 5/6/2022 6/18/2024
ES-22-G10 | 2022-03-24 | NESG Laconia 1 Solar, LLC, Endicott St East Solar | Generator notification from Eversource Energy on behalf of Laconia 1 Solar, LLC for the installation of a 2.85 MW Solar PV in Laconia, NH and interconnecting to Endicott St East, Laconia, NH on circuit 310 out of Laconia substation. | 2022-03-24 | Notification | 2022-05-06
ES-22-G11 | 2022-04-12 | US Solar, 105 Vista Drive Solar | Generator notification from Eversource Energy on behalf of US Solar for the installation of a 4.0 MW Solar PV in Torrington, CT and interconnecting to on circuit 8A1 out of Torrington Terminal 8A substation. | 2022-09-22 | Notification | 2022-05-06
ES-21-G109 Rev.1 | 2022-03-24 | Kearsage Energy LP, Dubarton Rd Solar | Generator notification from Eversource Energy on behalf of Kearsage Energy LP. The original proposal for 2.49 MW Solar PV in Manchester, NH and interconnecting to Dunbarton Rd, Manchester, NH on the 334R circuit out of Rimmon substation is revised to 2.656 MW. | 2022-06-01 | Notification | 2022-05-06
GMP-22-G01 | 2022-03-03 | Green Mountain Power, Alfrecha Road Solar | Generator notification from VELCO on behalf of Green Mountain Power for the installation of a 2.2 MW Solar PV in Clarendon, VT and interconnecting to Alrecha Road, Clarendon, VT on the circuit G72 out of South Rutland substation. | 2022-11-02 | Notification | 2022-05-06
NEP-21-GNF07 Rev.1 | 2022-04-12 | Sol Alliance, 300 Oak Street Solar | Generator notification from New England Power on behalf of Sol Alliance. The original proposal for 2.689 MW Solar PV in Pembroke, MA and interconnecting to 300 Oak Street, Pembroke, MA on the 910W51 circuit out of Water Street substation. Revision to decrease size to 2.559 MW. | 2021-03-01 | Notification | 2022-05-06
NEP-19-G30-036 Rev.1 | 2022-04-12 | BlueWave, L22 Sykes Street Solar and Battery | Generator notification from New England Power on behalf of BlueWave. The original proposal for 4.98 MW Solar PV in Palmer, MA and interconnecting to L22 Sykes Street, Palmer, MA on the 23 kV circuit out of Palmer substation. Revision to add a 4.0 MW/13.68 MWh DC Coupled Battery. | 2022-04-19 | Notification | 2022-05-06
NEP-19-G30-046 Rev.1 | 2022-04-12 | Tangent Energy, 0 Overlook Road Solar and Battery | Generator notification from New England Power on behalf of Tangent Energy. The original proposal for 4.98 MW Solar PV in Westminster, MA and interconnecting to 0 Overlook Road, Winchester, MA on the 610W3 circuit out of Park Street substation. Revision to add a 2.5 MW/5.0 MWh DC Coupled Battery. | 2023-01-12 | Notification | 2022-05-06
NEP-19-G30-057 Rev.3 | 2022-04-12 | Allco Renewable, 0 Spring Street Solar and Battery | Generator notification from New England Power on behalf of Allco Renewable. The original proposal for 3.9 MW Solar PV in Winchendon, MA and interconnecting to 0 Spring Street, Winchendon, MA on the 612W3 circuit out of East Winchendon substation. Revision to add a 1.017 MW/6.102 MWh DC Coupled Battery. | 2022-08-16 | Notification | 2022-05-06
NEP-19-GNF149 Rev.1 | 2022-04-12 | Beaumont Solar, 680 Centre Street Solar and Battery | Generator notification from New England Power on behalf of Beaumont Solar. The original proposal for 1.38 MW Solar PV in Brockton, MA and interconnecting to 680 Centre Street, Brockton, MA on the 91W46 circuit out of Dupont substation. Revision to add a 1.0 MW/4.0 MWh AC Coupled Battery. | 2022-12-28 | Notification | 2022-05-06
NEP-22-GNF03 Rev.1 | 2022-04-12 | Distributed Solar Development, 0 Stockwell Drive Solar and Battery | Generator notification from New England Power on behalf of Distributed Solar Development. The original proposal for 0.813 MW Solar PV and 0.25 MW/0.556 MWh DC Coupled Battery in Stoughton, MA and interconnecting to 0 Stockwell Drive, Stoughton, MA on the 75W1 circuit out of Harrison Blvd substation. Revision to update bus number. | 2024-05-01 | Notification | 2022-05-06
ES-22-G08 | 2022-03-04 | NBC Sports, 1 Blachley Rd Natural Gas Unit | Generator notification from Eversource Energy on behalf of NBC Sports for the interconnection of a 1.5 MW Natural Gas Unit in Stamford, CT and interconnecting to 1 Blachley Rd, Stamford, CT on the 13.2 kV circuit out of the Glenbrook 1K substation. | 2022-06-01 | Notification | 2022-05-03
HE-22-G01 | 2022-03-08 | Holyoke Gas & Electric, 28 Water Street Natural Gas Unit | Generator notification from Holyoke Gas & Electric for the installation of a 3.962 MW Natural Gas Unit in Holyoke, MA and interconnecting to 28 Water Street, Holyoke, MA on the 17L6 feeder out of Holyoke 17L substation. | 2022-04-01 | Notification | 2022-05-06
ES-22-T09 | 2022-03-11 | Replace Approximately 2,100’ Section of Lines 250-516/517 over the N. Washington Bridge in Boston, between Mystic Station and Hawkins St. Station | Transmission notification from Eversource Energy to replace approximately 2,100’ of Lines 250-516/517 over the N. Washington Bridge in Boston, between Mystic Station and Hawkins St. Station. | 2023-12-31 | Notification | 2022-04-28
DNC-GEN-2022-003 | 2022-02-25 | Millstone Power Station Units 3 Generator Upgrade Project | Generator application from Dominion Energy to upgrade Millstone Power Station Unit 3 in Waterford, CT to 1,260 MW net output. | 2022-05-15 | Approved | 2022-03-22
CMP-22-G02 | 2022-03-01 | Queue Position 1086 Generation and Transmission Project | Generator application from Central Maine Power for the installation of eighteen (18) 4.6 MVA (limited to 4.139 MW) inverters for a total of 74.5 MW. | 2024-11-30 | Approved Withdrawn | 3/22/2022 5/14/2024
CMP-22-T01 | 2022-03-01 | Queue Position 1086 Generation and Transmission Project | Transmission application from Central Maine Power to install a 115 kV three-breaker ring bus on CMP Section 80, approximately 2 miles from Highland Station. | 2024-11-30 | Approved | 2022-03-22
CMP-22-T02 | 2022-03-01 | Queue Position 1086 Generation and Transmission Project | Transmission application from Central Maine Power to install a 100-ft 115 kV generator lead line from the new three-breaker ring bus to the Warren Meadow Solar Station, LLC collector station and install a 115/34.5 kV transformer. | 2024-11-30 | Approved Withdrawn | 3/22/2022 5/14/2024
CMP-22-T03 | 2022-03-01 | Queue Position 1086 Generation and Transmission Project | Transmission application from Central Maine Power to increase the LTE rating of line Section 80 to 109 MVA by increasing the sag temperature and replacing two 115 kV structures. | 2024-11-30 | Approved Withdrawn | 3/22/2022 5/14/2024
UES-22-G01 | 2022-02-04 | Town of Exeter 10 Front Street Solar | Generator notification from Unitil on behalf of the Town of Exeter for the installation of a 1.5 MW Solar PV in Exeter, NH and interconnecting to 10 Front Street, Exeter, NH on circuit 43X1 out of Kingston substation. | 2022-12-20 | Notification | 2022-03-22
ES-22-G03 | 2022-02-09 | Pure Power Engineering 428 Bethmour Road Solar | Generator notification from Eversource on behalf of Pure Power Engineering for the installation of a 1.375 MW Solar PV in Bethany, CT and interconnecting to 428 Bethmour Road, Bethany, CT on circuit 11N81 out of Beacon Falls 11N substation. | 2022-09-01 | Notification Withdrawn | 3/22/2022 7/16/2024
ES-22-G05 | 2022-02-24 | Davis Hill Development River Road Solar | Generator notification from Eversource on behalf of Davis Hill Development for the installation of a 1.999 MW Solar PV in Southbury, CT and interconnecting to River Road, Southbury, CT on the 13.8 kV circuit out of Shepaug 13A substation. | 2023-12-29 | Notification | 2022-03-22
ES-22-G06 | 2022-02-24 | Cobb Road LLC 524 New London Road Solar | Generator notification from Eversource on behalf of Cobb Road LLC for the installation of a 3.984 MW Solar PV in Colchester, CT and interconnecting to 524 New London Road, Colchester, CT on the 23 kV bus at the Judd Brook 32R substation. | 2022-07-01 | Notification | 2022-03-22
ES-22-G07 | 2022-02-25 | Verogy Chamberlain Hill Road Solar | Generator notification from Eversource on behalf of Verogy for the installation of a 1.975 MW Solar PV in Middletown, CT and interconnecting to Chamberlain Hill Road, Middletown, CT at the A3 bus at the Haddam 11C substation. | 2023-12-29 | Notification Withdrawn | 3/22/2022 6/18/2024
NEP-22-GNF03 | 2022-02-28 | Distributed Solar Development 0 Stockwell Drive Solar and Battery | Generator notification from New England Power for the installation of a 0.813 MW Solar PV and 0.25 MW/0.556 MWh AC Coupled Battery in Stoughton, MA and interconnecting to 0 Stockwell Drive, Stoughton, MA on the 75W1 circuit out of Harrison Boulevard substation. | 2024-05-01 | Notification | 2022-03-22
VELCO-22-GNF01 | 2022-02-08 | Springfield BESS, LLC 116 Spoonerville Road Battery | Generator notification from VELCO for the installation of a 4.99 MW BES System in Waitsfield, VT and interconnecting to 116 Spoonerville Road on the NS-G63 circuit out of the North Springfield substation. | 2022-12-31 | Notification | 2022-03-22
VELCO-22-GNF02 | 2022-02-08 | Georgia BESS, LLC 980 Ballard Road Battery | Generator notification from VELCO for the installation of a 4.99 MW BES System in Georgia, VT and interconnecting to 980 Ballard Road on the 12.47 kV distribution circuit out of the GMP Georgia substation. | 2022-12-31 | Notification | 2022-03-22
NEP-22-T02 | 2022-02-25 | V-148S 115 kV Line Upgrade | Transmission notification from New England Power to rebuild the V-148S 115 kV Line (7.23 miles) between Washington and Read Street Substations by replacing the conductor and all structures. | 2023-04-30 | Notification | 2022-03-17
NEP-22-T03 | 2022-02-25 | Replace Q-143S & R-144 Underground Cables | Transmission notification from New England Power to replace the Q-143S and R-144 115 kV radial lines with two 115 kV high-voltage extruded dielectric (HVED) 1500 kcmil Cu underground cables. | 2022-06-30 | Notification | 2022-03-17
NEP-22-T04 | 2022-02-28 | E-157W 115 kV Line Partial Reconductoring | Transmission notification from New England Power to reconductor 0.36 miles of the E-157W line between Wyman Gordon and Centech substation due to asset condition issues. | 2022-06-30 | Notification | 2022-03-17
VELCO-22-T01 | 2022-02-04 | Rebuild the Highgate-Georgia K42 115 kV Line | Transmission notification from VELCO to rebuild the Highgate-Georgia K42 115 kV Line to Double-Bundle 1272 ACSR Delta reconfiguration. | 2025-12-31 | Notification | 2022-03-17
VP-22-T01 | 2022-01-27 | Versant Power Upper Maine Solutions Project | Transmission application from Versant Power to reconfigure reactors at Orrington Substation in Orrington, ME such that each reactor is connected to separate transformers. | 2023-12-31 | Approved Withdrawn | 2/16/2022 4/17/2024
VP-22-T02 | 2022-01-27 | Versant Power Upper Maine Solutions Project | Transmission application from Versant Power to install a breaker and related facilities to add a 10 MVAR reactor to the Keene Road 115 kV bus. | 2024-06-30 | Approved | 2022-02-16
VP-22-T03 | 2022-01-27 | Versant Power Upper Maine Solutions Project | Transmission application from Versant Power for the installation of a new breaker, 25 MVAR reactor, and +50/-25 MVAR synchronous condenser at the Boggy Brook 115 kV substation. | 2024-06-30 | Approved | 2022-02-16
VP-22-G01 | 2022-01-26 | BD Solar Eddington (QP 986) | Generator application from Versant Power on behalf of BD Solar Eddington LLC for the installation of 19.99 MW of solar generation located in Eddington, ME and interconnecting to a new switching station between Graham Substation and Old Town Substation. | 2024-11-18 | Approved | 2022-02-16
ES-22-T01 | 2022-02-01 | Reconfiguration of the Substation 9A Falls Village 69 kV Switchyard | Transmission application from Eversource Energy for the reconfiguration of the Substation 9A Falls Village 69 kV Switchyard in Salisbury, CT to an eight breaker ring bus. | 2024-06-30 | Approved | 2022-02-16
NEP-19-GNF185 Rev.1 | 2022-01-31 | AMP Solar Wallum Lake Road Solar and Battery | Generator notification from New England Power on behalf of AMP Solar Development, LLC. Original proposal for 4.998 MW Solar PV only in Douglas, MA and interconnecting to the 320W2 feeder at the Whitins Pond Substation is revised to add a 3.84 MW/12.88 MWh DC Coupled Battery. | 2022-01-24 | Notification | 2022-02-16
NEP-22-GNF01 | 2022-01-31 | Ameresco Solar Ranger Road Solar and Battery | Generator notification from New England Power on behalf of Ameresco Solar, LLC for the instalttation of a 0.938 MW solar PV and 0.5 MW/1.0 MWh AC Coupled Battery in Mathuen, MA and interconnecting to the 74L1 feeder at the East Methuen Substation. | 2024-03-31 | Notification Withdrawn | 2/16/2022 10/18/2022
NEP-22-GNF02 | 2022-01-31 | Next Grid Bedford Street Solar and Battery | Generator notification from New England Power on behalf of Next Grid, Inc. for the installation of a 3.0 MW solar PV and 2.07 MW/7.8 MWh DC Coupled Battery in Bridgewater, MA and interconnecting to the 797W1 feeder at the East Bridgewater Substation. | 2024-03-31 | Notification Withdrawn | 2/16/2022 9/17/2024
CMP-21-G54 | 2021-12-06 | Queue Position 953 Solar Generation Project | Generator application from Central Maine Power ("CMP") on behalf of BD Solar Church Hill LLC for the installation of eight 2,500 kW solar inverters (20 MW net output) located in Augusta, ME. | 2024-07-01 | Approved | 2022-01-27
NEP-22-G01 | 2022-01-03 | Douglas Pike PV Project (QP 1137) | Generator application from New England Power Company ("NEP") on behalf of RI Solar Renewables for the installation of 9.5 MW of PV in North Smithfield, RI and interconnecting to the 13.8 kV Nasonville Substation. | 2023-03-01 | Approved | 2022-01-27
NHT-22-T01 | 2022-01-10 | Line 363 Capacitor Banks Installation Project | Transmission application from New Hampshire Transmission ("NHT") for the installation of two 50 MVAR 345- kV capacitor banks on Line 363 adjacent to the existing Seabrook line termination yard in Seabrook, NH. | 2023-12-31 | Approved | 2022-01-19
NEP-19-G30-015 Rev.2 | 2022-01-03 | Borrego Solar Clark Street Solar and Battery Rev.2 | Generator notification from New England Power Company ("NEP") on behalf of Borrego Solar. Original proposal for 4.9 MW Solar PV only in Gardner, MA and interconnecting on the 607W5 feeder at the Crystal Lake Substation is revised to increase the PV size to 4.99 MW and add a 3.0MW/6.0MWh DC Coupled Battery. | 2020-12-31 | Approved | 2022-01-27
NEP-20-G03-113 Rev.2 | 2022-01-03 | Nexamp Union Road Solar and Battery Rev.2 | Generator notification from New England Power Company ("NEP") on behalf of Nexamp. Original proposal for 2.0 MW Solar PV only in Wales, MA and interconnecting on the 516L5 feeder at the Little Rest Road Substation is revised to add a 1.5MW/3.0MWh DC Coupled Battery. | 2020-08-26 | Approved | 2022-01-27
CMP-20-G31 Rev.1 | 2022-01-04 | MEVS Clark Wyman Hydro Nichols Hill Road | Generator notification from Central Maine Power ("CMP") on behalf of MEVS Clark, LLC. Hydro project revision to decrease output to 4.95 MW, down from 4.98 MW. Located in Bingham, ME and interconnecting to Circuit 872D1 at the Wyman Hydro Substation. | 2022-12-30 | Approved | 2022-01-27
NEP-22-T01 | 2022-01-03 | 517-532N & 517-533N 115 kV Underground Cables Replacement | Transmission notification from New England Power Company ("NEP") to replace the existing 517-532N & 517-533N underground cables in Quincy, MA. The new cables will be two 115 kV high voltage extruded dielectric 2000 kcmil Cu underground cables. | 2024-03-31 | Approved | 2022-01-19
ES-18-G63 Rev.1 | 2021-12-06 | Bay State Wind Generation Project (QP 846) Rev.1 | Generator application from Eversource Energy ("ES") on behalf of Bay State Wind for the installation of 80 11.0 MW off-shore wind turbines (40 MW increase from original project submission) located south of Martha’s Vineyard, MA. | 2026-05-31 | Approved Withdrawn | 12/17/2021 8/10/2022
ES-18-T26 Rev.1 | 2021-12-06 | Bay State Wind Generation Project (QP 846) Rev.1 | Transmission application from Eversource Energy (“ES”) for the installation of two 140 MVAr synchronous condensers connected via 345/24 kV transformers. | 2024-12-02 | Approved Withdrawn | 12/17/2021 8/10/2022
ES-18-T27 Rev.1 | 2021-12-06 | Bay State Wind Generation Project (QP 846) Rev.1 | Transmission application from Eversource Energy (“ES”) for the construction of a 345/275 kV on-shore substation comprising of two 345/275 kV autotransformers, six 345 kV switchgear bays, eight 275 kV switchgear bays, two 110-250 MVAr variable shunt reactors and two 275 kV harmonic filters. | 2024-12-02 | Approved Withdrawn | 12/17/2021 8/10/2022
ES-18-T28 Rev.1 | 2021-12-06 | Bay State Wind Generation Project (QP 846) Rev.1 | Transmission application from Eversource Energy (“ES”) for the installation and interconnection of two 275 kV submarine, landfall and land cable circuits with 180 MVAr shunt reactors at each end. | 2024-12-02 | Approved Withdrawn | 12/17/2021 8/10/2022
ES-18-T29 Rev.1 | 2021-12-06 | Bay State Wind Generation Project (QP 846) Rev.1 | Transmission application from Eversource Energy (“ES”) for the installation of two 275/66 kV off shore substations comprising each of two 280 MVA three winding transformers, four 275 kV switchgear bays, and 66 kV switchgear interconnecting array cables from the wind turbines. | 2024-12-02 | Approved Withdrawn | 12/17/2021 8/10/2022
ES-18-T30 Rev.1 | 2021-12-06 | Bay State Wind Generation Project (QP 846) Rev.1 | Transmission application from Eversource Energy (“ES”) for the installation and interconnection of two 345 kV buried land cable circuits interconnecting at the Brayton Point 345 kV and Bay State Wind 345/275 kV on-shore substation | 2024-12-02 | Approved Withdrawn | 12/17/2021 8/10/2022
AGIH-21-G03 | 2021-12-05 | Milford Grid Battery Energy Storage Generation and Transmission Project (QP 1017) | Generation application from Able Grid Infrastructure Holdings (“AGIH”) for the installation of a 200 MW/400 MWh battery storage facility in Milford, CT with 70 2.9 MVA power electronic inverters and 70 600V/34.5 kV two winding GDSU transformers. | 2023-10-01 | Approved Withdrawn | 12/17/2021 2/19/2025
AGIH-21-T03 | 2021-12-05 | Milford Grid Battery Energy Storage Generation and Transmission Project (QP 1017) | Transmission application Able Grid Infrastructure Holdings (“AGIH”) for the installation of a main station 345/34.5/13.8 kV load tap transformer and a generation tie line from the project site to the East Devon substation. | 2023-10-01 | Approved Withdrawn | 12/17/2021 2/19/2025
ES-21-T96 | 2021-11-30 | Milford Grid Battery Energy Storage Generation and Transmission Project (QP 1017) | Transmission application from Eversource Energy (“ES”) for the installation of a generator lead line from the East Devon 345 kV substation to the first structure on the generation side. Also install three 345 kV breakers, four 345 kV breaker disconnects, one line terminal structure, six capacitor coupled voltage transformers, three lightning arrestors and associated control and protection equipment. | 2023-05-31 | Approved Withdrawn | 12/17/2021 2/19/2025
UI-21-T02 | 2021-12-03 | Milford Grid Battery Energy Storage Generation and Transmission Project (QP 1017) | Transmission application from United Illuminating a.k.a Avangrid (“UI”) for the replacement of the East Shore 345/115 kV transformer 9X. | 2023-10-01 | Approved Withdrawn | 12/17/2021 2/19/2025
CMP-21-G32 | 2021-11-30 | Leeds Solar Generation Project (QP 923) | Generation application from Central Maine Power Company (“CMP”) on behalf of Walden Solar Maine for the installation 20.0 MW PV facility in Leeds, ME and interconnecting to the Leeds Substation via the 471D2 circuit. | 2022-12-31 | Approved | 2021-12-17
ES-21-G103 | 2021-11-30 | Glenvale River Road Putnam Solar Project | Generation application from Eversource Energy (“ES”) on behalf of Glenvale Solar for the installation of a 4.0 MW PV facility in Putnam, CT and interconnecting to the Tracy 14M Substation via the 14M29 23 kV circuit. | 2022-09-30 | Approved | 2021-12-17
CMP-21-G34 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - Delgrade PV Oakland Road Belgrade Solar | Generation application from Central Maine Power Company (“CMP”) on behalf of Belgrade PV for the installation 4.925 MW PV facility in Belgrade, ME and interconnecting to the County Road Substation via the 873D1 34.5 kV circuit. | 2022-10-01 | Approved Withdrawn | 12/17/2021 2/13/2025
CMP-21-G35 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - Sidney South Est River Road Sidney Solar | Generation application from Central Maine Power Company (“CMP”) on behalf of Sidney South for the installation 1.95 MW PV facility in Sidney, ME and interconnecting to the South Waterville Substation via the 855D2 12.47 kV circuit. | 2023-06-01 | Approved | 2021-12-17
CMP-21-G36 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - ER Oakland South Alpine Street Oakland Solar | Generation application from Central Maine Power Company (“CMP”) on behalf of ER Oakland South for the installation 2.375 MW PV facility in Oakland, ME and interconnecting to the Oakland Substation via the 839D1 12.47 kV circuit. | 2022-10-31 | Approved | 2021-12-17
CMP-21-G37 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - Cleantap Energy Eight Rod Road Waterville Solar and Battery | Generation application from Central Maine Power Company (“CMP”) on behalf of Cleantap Energy for the installation 3.5 MW PV and 1.75 MW/3.892 MWh battery facility in Waterville, ME and interconnecting to the South Waterville Substation via the 855D2 12.47 kV circuit. | 2022-10-31 | Approved | 2021-12-17
CMP-21-G38 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - MEVS Waterville Lefleur Road Waterville Solar | Generation application from Central Maine Power Company (“CMP”) on behalf of MEVS Waterville for the installation 4.95 MW PV facility in Waterville, ME and interconnecting to the West Waterville Substation via the 865D5 12.47 kV circuit. | 2022-12-31 | Approved | 2021-12-17
CMP-21-G39 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - MSD Galbraith Norridgewock Avenue Skowhegan Solar | Generation application from Central Maine Power Company (“CMP”) on behalf of MDS Galbraith for the installation 1.453 MW PV facility in Skowhegan, ME and interconnecting to the Skowhegan Tap Substation via the 864D1 12.47 kV circuit. | 2022-12-31 | Approved | 2021-12-17
CMP-21-G40 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - Skowhegan Solar Eaton Mountain Road Skowhegan Solar | Generation application from Central Maine Power Company (“CMP”) on behalf of Skowhegan Solar for the installation 4.925 MW PV facility in Skowhegan, ME and interconnecting to the Weston Substation via the 866D1 12.47 kV circuit. | 2022-12-31 | Approved | 2021-12-17
CMP-21-G41 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - Nexamp Solar Lakewood Road Madison Solar | Generation application from Central Maine Power Company (“CMP”) on behalf of Nexamp Solar for the installation 4.0 MW PV facility in Madison, ME and interconnecting to the Skowhegan North Side Substation via the 853D1 12.47 kV circuit. | 2022-12-01 | Approved | 2021-12-17
CMP-21-G42 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - Starks Holdings Anson Road Starks Solar | Generation application from Central Maine Power Company (“CMP”) on behalf of Starks Holdings for the installation 1.71 MW PV facility in Starks, ME and interconnecting to the Anson Substation via the 801D1 12.47 kV circuit. | 2023-06-01 | Approved | 2021-12-17
CMP-21-G43 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - BD Solar Valley Road North Anson Solar | Generation application from Central Maine Power Company (“CMP”) on behalf of BD Solar for the installation 2.0 MW PV facility in North Anson, ME and interconnecting to the North Anson Substation via the 838D2 12.47 kV circuit. | 2022-12-31 | Approved | 2021-12-17
CMP-21-G44 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - Norridgewock Martin Stream Smithfield Road Norridgewock Solar | Generation application from Central Maine Power Company (“CMP”) on behalf of Norridgewock Martin Stream for the installation 4.899 MW PV facility in Norridgewock, ME and interconnecting to the Skowhegan South Side Substation via the 854D1 12.47 kV circuit. | 2022-04-30 | Approved | 2021-12-17
CMP-21-G45 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - ER Dairy Farm River Road Anson Solar | Generation application from Central Maine Power Company (“CMP”) on behalf of ER Dairy Farm for the installation 4.0 MW PV facility in Anson, ME and interconnecting to the North Anson Substation via the 838D2 12.47 kV circuit. | 2022-10-31 | Approved | 2021-12-17
CMP-21-G46 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - Front Street Solar West Front Street Skowhegan Solar | Generation application from Central Maine Power Company (“CMP”) on behalf of Front Street Solar for the installation 3.199 MW PV facility in Skowhegan, ME and interconnecting to the Skowhegan South Side Substation via the 854D1 12.47 kV circuit. | 2022-08-01 | Approved | 2021-12-17
CMP-21-G47 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - BD Solar Winding Hill Road Norridgewock Solar | Generation application from Central Maine Power Company (“CMP”) on behalf of BD Solar for the installation 2.318 MW PV facility in Norridgewock, ME and interconnecting to the Skowhegan South Side Substation via the 854D1 12.47 kV circuit. | 2022-12-31 | Approved | 2021-12-17
CMP-21-G48 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - MSD Guimond Franklin Drive Fairfield Solar | Generation application from Central Maine Power Company (“CMP”) on behalf of MSD Guimond for the installation 4.98 MW PV facility in Fairfield, ME and interconnecting to the Fairfield Substation via the 817D1 12.47 kV circuit. | 2022-12-01 | Approved | 2021-12-17
CMP-21-G49 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - BWC Unity Pond Bangor Road Benton Solar | Generation application from Central Maine Power Company (“CMP”) on behalf of BWC Unity Pond for the installation 4.45 MW PV facility in Benton, ME and interconnecting to the Clinton Substation via the 810D1 12.47 kV circuit. | 2022-10-20 | Approved | 2021-12-17
CMP-21-G50 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - SunRaise Development Albion Road Benton Solar and Battery | Generation application from Central Maine Power Company (“CMP”) on behalf of SunRaise Development for the installation 0.873 MW PV and 0.875 MW/1.75 MWh battery facility in Benton, ME and interconnecting to the Winslow Substation via the 870D1 12.47 kV circuit. | 2022-12-01 | Approved | 2021-12-17
CMP-21-G51 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - Vassalboro PV Riverside Drive Vassalboro Solar | Generation application from Central Maine Power Company (“CMP”) on behalf of Vassalboro PV for the installation 4.45 MW PV facility in Vassalboro, ME and interconnecting to the Vassalboro Substation via the 861D8 12.47 kV circuit. | 2022-06-01 | Approved | 2021-12-17
CMP-21-G52 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - Winslow PV Riverside Drive Vassalboro Solar | Generation application from Central Maine Power Company (“CMP”) on behalf of Winslow PV for the installation 4.125 MW PV facility in Vassalboro, ME and interconnecting to the Vassalboro Substation via the 861D8 12.47 kV circuit. | 2022-06-01 | Approved | 2021-12-17
CMP-21-G53 | 2021-11-30 | Winslow and Lakewood Distributed Energy Resource (DER) Group Project - MEVS Richards Skowhegan Road Fairfield Solar | Generation application from Central Maine Power Company (“CMP”) on behalf of MEVS Richards for the installation 1.25 MW PV facility in Fairfield, ME and interconnecting to the Shawmut Substation via the 852D1 12.47 kV circuit. | 2022-12-31 | Approved Withdrawn | 12/17/2021 6/18/2024
ES-21-G116 | 2021-11-29 | ECA NEMA Brightfields I LLC 134 Commerce Way Woburn Solar | Generator notification from Eversource Energy ("ES") on behalf of ECA Nema Brightfields I LLC for the installation of a 2..451 MW Solar PV in Woburn, MA and interconnecting to 134 Commerce Way Woburn, MA on circuit 375-H9 out of N. Woburn 375 substation. | 2022-05-01 | Notification | 2021-12-17
VPPSA-21-GNF03 | 2021-11-02 | ER Lawrence Brook Solar, LLC 3780 Laporte Road Morristown Solar | Generator notification from Vermont Public Power Supply Authority on behalf of ER Lawrence Brook Solar, LLC for that installation of a 2.2 MW Solar PV in Morristown, VT and interconnecting to Substation 5 on circuit 3. | 2020-12-15 | Notification | 2021-12-17
NEP-21-GNF22 | 2021-11-29 | Revity Energy LLC 279 Jenckes-Hill Rd Lincoln Solar | Generator notification from New England Power Company ("NEP") on behalf of Revity Energy LLC for the installation of a 4.75 MW Solar PV in Lincoln, RI and interconnecting to the Washington Substation, 126W42. | 2023-03-01 | Notification | 2021-12-17
ES-21-G113 | 2021-11-30 | MCPF Needham, LLC 89A Needham Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of MCPF Needham, LLC for that installation of a 1.3 MW Solar PV and 0.528MW/1.112MWH DC Coupled AC/DC BATTERY LOCATED in Needham, MA and interconnecting to 89A Street Needham, MA on Circuit 292-H10 out of Newton Highlands 292 substation. | 2023-03-01 | Notification | 2021-12-17
ES-21-G114 | 2021-11-27 | Solect Energy Development, LLC 665 Cottage Street Springfield Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Solect Energy Development, LLC for that installation of a 0.7 MW Solar PV and 0.5575 MW/1.115 MWH DC Coupled AC/DC BATTERY LOCATED in Springfield, MA and interconnecting to 665 Cottage Street Springfield, MA on Circuit 5J13 out of East Springfield 5J substation. | 2023-02-01 | Notification | 2021-12-17
ES-21-G119 | 2021-11-30 | BWC Tillson Brook, LLC 172 South Lane Granville Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of BWC Tilllson Brook, LLC for the installation of a 2.0 MW Solar PV and 2.0 MW/ 8.0 MWH DC Coupled AC/DC BATTERY LOCATED in Granville, MA and interconnecting to 172 South Lane Granville MA on Eversource 23kV circuit 29A5 out of Southwick 29A substation. | 2021-12-31 | Notification | 2021-12-17
ES-21-G120 | 2021-11-30 | BWC Seymour Brook, LLC 274 South Lane Granville Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of BWC Seymour Brook, LLC for the installation of a 2.0 MW Solar PV and 2.0 MW/8.0 MWH DC Coupled AC/DC BATTERY LOCATED in Granville, MA and interconnecting to 274 South Lane Granville MA on Eversource 23kV circuit 29A5 out of Southwick 29A substation. | 2021-12-31 | Notification | 2021-12-17
ES-21-G121 | 2021-11-30 | BWC Trumble Brook, LLC 123 Barnard Rd Granville Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of BWC Trumble, LLC for the installation of a 4.99 MW Solar PV and 5.0MW/20.0MWH DC Coupled AC/DC battery located in Granville, MA and interconnecting to 123 Barnard Rd Granville, MA on Eversource 23kV circuit # 29A5 out of Southwick 29A substation. | 2021-12-31 | Notification | 2021-12-17
ES-21-G122 | 2021-11-30 | Southwick Solar, LLC 36 Hudson Dr Southwick Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of BWC Trumble, LLC for the installation of a 4.6 MW Solar PV and 2.0MW/8.0MWH DC Coupled AC/DC battery located in Southwick , MA and interconnecting to Eversource 13.8kV circuit #29A1 out of Southwick 29A. | 2021-12-31 | Notification | 2021-12-17
ES-21-G123 | 2021-11-30 | Syncarpha Solar, LLC 50 Independence Road Acton Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Syncarpha Solar, LLC for the installation of a 4.98 MW Solar PV and 4.0MW/8.0MWH DC Coupled AC/DC battery located in Acton, MA and interconnecting to 50 Independence Road Acton, MA on Circuit 416-H4 out of Maynard 416 substation. | 2022-06-01 | Notification | 2021-12-17
NEP-21-GNF21 | 2021-11-29 | ZeroPoint Energy Consultants 530 Glendale Road Hampden Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of ZeroPoint Energy Consultants for the installation of a 4.992 MW Solar PV and 3.0MW/6.672MWH DC Coupled AC/DC battery located in Hampden , MA and interconnecting to Wilbraham, 507L1, 13.2kV. | 2023-12-31 | Notification Withdrawn | 12/17/2021 12/17/2024
ES-21-G95 | 2021-11-30 | Jupiter Power LLC 215 Barber Hill Rd East Windsor Battery | Generator notification from Eversource Energy ("ES") on behalf of Jupiter Power LLC for the installation of a 2.2 MW/4.5 MWh DC Coupled AC/DC battery located in East Windsor, CT and interconnecting to 215 Barber Hill Rd East Windsor, CT on Circuit 23J36 out of Barbour Hill 23J station. | 2021-12-31 | Notification Withdrawn | 12/17/2021 1/18/2023
ES-21-G124 | 2021-11-30 | BWC Coles Brook Discovery Way Acton Battery | Generator notification from Eversource Energy ("ES") on behalf of BWC Coles Brook for the installation of two 2.5 MW/10.0 MWh DC Coupled AC/DC batteries (4.99 MW net output) located in Acton, MA and interconnecting to 416-H5 13.8 kV circuit out of the Maynard 416 substation. | 2022-06-01 | Notification | 2021-12-17
ES-21-G117 | 2021-11-29 | Cyxtera Communications, LLC 115 Second Ave Waltham | Generator notification from Eversource Energy ("ES") on behalf of Cyxtera Communications, LLC. Natural Gas Construction has a maximum net power injection at the point of interconnection of 0.0MW and will reduce load by 3.012 MW. Located in Waltham, MA and interconnecting to the 115 Second Ave, Waltham, MA Interconnect behind a 13.8kV primary customer with circuit 373-1360 and 531-1359H duplicate supply, both are off Trapelo Road Station #450. | 2021-12-31 | Notification | 2021-12-17
ES-21-G118 | 2021-11-29 | Cyxtera Communications, LLC 580 Winter St Waltham | Generator notification from Eversource Energy ("ES") on behalf of Cyxtera Communications, LLC. Natural Gas Construction has a maximum net power injection at the point of interconnection of 0.0MW and will reduce load by 1.994 MW. Located in Waltham, MA and interconnecting to the 580 Winter St Waltham, MA, Interconnect behind a 13.8kV primary customer with circuit 531-1359 and 526-1361H duplicate supply, both are off Trapelo Road Station #450. | 2021-12-31 | Notification | 2021-12-17
ES-21-T97 | 2021-09-20 | Clinton Substation 3X Transformer Replacement | Transmission notification from Eversource Energy ("ES") to replace the existing transformer at the Clinton Substation in Springfield, MA. The unit will be replaced with a 117/15.12 kV 37 MVA 3X step-down transformer. | 2022-12-31 | Notification | 2021-12-16
ES-21-T98 | 2021-09-20 | Franconia Substation 2X Transformer Replacement | Transmission notification from Eversource Energy ("ES") to replace the existing transformer at the Franconia Substation in Longmeadow, MA. The unit will be replaced with a 117/15.12 kV 37 MVA 3X step-down transformer. | 2022-11-30 | Notification | 2021-12-16
ES-21-T89 Rev.1 | 2021-12-01 | Berlin Substation TB 115 Transformer Replacement Rev.1 | Transmission notification from Eversource Energy ("ES"). Project revision is to update the name of the existing 115/34.5 kV 15 MVA transformer at the Berlin Substation in New Hampshire due to equipment failure. The transformer will be replaced with a 40 MVA unit and renamed TB 115. | 2/2022 | Notification | 2021-12-16
ES-21-T106 | 2021-11-08 | Partial Rebuild of 115 kV Line 1825 | Transmission notification from Eversource Energy ("ES") for the partial Partial rebuild of line 1825 replacing 2.8-miles of existing structures and associated 4/0 Copper conductor with 795-kcmil ACSS conductor from the Bristol substation to the Forestville substation. | 2022-03-31 | Notification | 2021-12-16
ES-21-T107 | 2021-11-29 | Partial Rebuild of 115 kV Line 1606 | Transmission notification from Eversource Energy ("ES") for the partial rebuild of the 115 kV line 1606 replacing 1.1-miles of existing structures and associated 4/0 Copper conductor with 1272-kcmil ACSS conductor from the Barbour Hill substation to the Rockville substation. | 2022-06-02 | Notification | 2021-12-16
ES-21-T108 | 2021-11-29 | Partial Rebuild of 115 kV Line 1724 | Transmission notification from Eversource Energy ("ES") for the partial rebuild of the 115 kV Line 1724 replacing 1.1-miles of existing structures and associated 4/0 Copper conductor with 1272-kcmil ACSS conductor Barbour Hill substation to the Rockville substation. | 2022-06-02 | Notification | 2021-12-16
CMP-21-T07 | 2021-10-29 | Elective Transmission Upgrade (ETU) Project (QP 889) | Transmission application from Central Maine Power Company (“CMP”) for the uprate to Surowiec South including installation of two (2) dynamic reactive devices (two ±300 MVA STATCOMs) to hold the Buxton 345 kV voltage at 351 kV (1.0174 pu). The 345 kV Section 3038 (Buxton – Surowiec) will re-terminate at the adjacent position, one STATCOM will interconnect in the current Section 3038 position, the other STATCOM will interconnect in the existing three-breaker bay shared with Section 385, and one new 345 kV breaker (IPT) will be installed in series with the existing K385-2 breaker at the Buxton 345 kV Substation. | 2023-12-13 | Approved | 2021-11-19
CMP-21-T08 | 2021-10-29 | Elective Transmission Upgrade (ETU) Project (QP 889) | Transmission application from Central Maine Power Company (“CMP”) to uprate the existing 115 kV Section 62 (Crowleys – Surowiec) by reconductoring the line from COOT 795 36/1 ACSR to Falcon 1590 54/19 ACSR to bring the line LTE rating to approximately 358 MVA. | 2023-12-13 | Approved | 2021-11-19
CMP-21-T09 | 2021-10-29 | Elective Transmission Upgrade (ETU) Project (QP 889) | Transmission application from Central Maine Power Company (“CMP”) to uprate the existing 115 kV Section 64 (Larrabee Road – Surowiec) by reconductoring approximately 13.64 miles of the existing line from COOT 795 36/1 ACSR to Bluejay 1113 45/7 ACSR to bring the line LTE rating to approximately 282 MVA. | 2023-12-13 | Approved | 2021-11-19
ES-21-T104 | 2021-11-02 | Elective Transmission Upgrade (ETU) Project (QP 889) | Transmission application from Eversource Energy (“ES”) to add a 345 kV circuit breaker (9126S) in series with circuit breaker 9126 at the Scobie Pond Substation. | 5/2023 | Approved | 2021-11-19
ES-21-T105 | 2021-11-02 | Elective Transmission Upgrade (ETU) Project (QP 889) | Transmission application from Eversource Energy (“ES”) to add a 345 kV circuit breaker (785S) in series with circuit breaker 785 at the Deerfield Substation. | 5/2023 | Approved | 2021-11-19
ES-21-G112 | 2021-10-28 | Dragway Solar Generation Project (QP 956) | Generation application from Eversource Energy ("ES") on behalf of Dragway Solar for the installation of a 10.0 MW net output PV facility in Epping, NH. | 2022-10-28 | Approved Withdrawn | 11/19/2021 5/1/2024
ES-21-G14 | 2021-10-29 | Eversource Affected System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project | Generation application from Eversource Energy (“ES”) on behalf of SunConnect Assonet for the installation of a 4.996 MW PV facility and a 4.0 MW/8.904 battery in Freetown, MA and interconnecting to the Bell Rock Substation via the 2-605-605 34.5 kV circuit. | 2021-12-31 | Approved | 2021-11-23
ES-21-G15 | 2021-10-29 | Eversource Affected System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project | Generation application from Eversource Energy (“ES”) on behalf of SunConnect Bryant Hill Farms for the installation of a 4.996 MW PV facility and a 4.0 MW/8.904 battery in Freetown, MA and interconnecting to the Bell Rock Substation via the 2-605-605 34.5 kV circuit. | 2021-12-31 | Approved | 2021-11-23
ES-21-G16 | 2021-10-29 | Eversource Affected System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project | Generation application from Eversource Energy (“ES”) on behalf of CVE Freetown Forge for the installation of a 2.0 MW PV facility and a 1.0 MW/2.224 battery in Assonet, MA and interconnecting to the Bell Rock Substation via the 2-605-605 34.5 kV circuit. | 2021-12-31 | Approved | 2021-11-23
ES-21-T52 | 2021-10-29 | Eversource Affected System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project | Transmission application from Eversource Energy (“ES”) for the installation of a 4.6 mile underground 115 kV 153 Cable between Bell Rock Substation and Assonet Substation along with the installation of a 15 MVAr shunt reactor at Assonet. | 7/2025 | Approved | 2021-11-23
ES-21-T54 | 2021-10-29 | Eversource Affected System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project | Transmission application from Eversource Energy (“ES”) for the construction of a new 115/13.2 kV Assonet Substation with one 62.5 MVA, 115/13.2 kV transformer and one 115 kV breaker in Freetown, MA. | 7/2025 | Approved | 2021-11-23
CMP-21-G26 | 2021-10-06 | Portsmouth Naval Shipyard Combined Heat and Power Combustion Turbine Generator and Battery Project | Generation application from Central Maine Power Company (“CMP”) on behalf of Portsmouth Naval Shipyard in Kittery, ME for the installation of a 6.8 MW Combined Heat and Power (CHP) combustion turbine generator (CTG3) that will continuously operate in parallel with one or both of the existing CTGs to exclusively serve electrical load at PNSY during normal operating conditions. New generation is a behind-the-meter load reducer. Controls will curtail CTG output as required to avoid export power to the grid. | 2022-01-15 | Approved | 2021-11-23
CMP-21-G27 | 2021-10-06 | Portsmouth Naval Shipyard Combined Heat and Power Combustion Turbine Generator and Battery Project | Generation application from Central Maine Power Company (“CMP”) on behalf of Portsmouth Naval Shipyard in Kittery, ME for the installation of a 1.016 MW lithium-ion BESS (with one or two hours of storage) for emergency operation only. The BESS would be technically capable of registering as an Alternative Technology Regulating Resource (ATRR) in ISO-NE market in the future, but PNSY is not seeking such registration at this time. | 2022-01-15 | Approved | 2021-11-23
NEP-21-G05 | 2021-10-29 | Shaker Road Solar and Battery Project | Generation application from New England Power Company (“NEP”) on behalf of NextEra Energy Resources for the installation 4.4 MW solar PV and 1.5 MW/6.0 MWh battery in East Longmeadow, MA and interconnecting to the Shaker Road Substation via the 522L4 13.2 circuit. | 2023-06-01 | Approved Withdrawn | 11/23/2021 8/15/2023
UI-21-G04 | 2021-10-28 | Derby Fuel Cell Energy Project (QP 1055) | Generation application from Avangrid aka United Illuminating (“UI”) on behalf of Fuel Cell Energy for the installation 14.4 MW fuel cell generator in Derby, CT and interconnecting to the Indian Wells Substation via the 13.8 circuit. | 2022-04-18 | Approved | 2021-11-23
CMP-21-G31 | 2021-11-01 | Nestle Waters Hollis Solar Generation Project | Generation application from Central Maine Power Company (“CMP”) on behalf of Nestle Waters North America for the installation 10.0 MW PV facility in Hollis, ME and interconnecting to the Perrier Substation via the 698D1 34.5 kV circuit. | 2022-12-08 | Approved | 2021-11-23
VELCO-21-GNF02 | 2021-10-11 | Golden Solar Portland Street St. Johnsbury Solar | Generator notification from VELCO on behalf of Golden Solar for the installation of a 2.2 MW solar PV in St. Johnsbury, VT and interconnecting to the Bay Street Substation via the G4 12.5 kV circuit. | 2021-10-30 | Notification | 2021-11-23
ES-21-G111 | 2021-10-19 | Greenskies Boombridge Road Stonington Solar | Generator notification from Eversource Energy (“ES”) on behalf of Greenskies for the installation of a 4.999 MW solar PV in Stonington, CT and interconnecting to the Shunock Substation via the 32P1 13.8 kV circuit. | 2021-11-30 | Notification | 2021-11-23
UES-21-G01 | 2021-10-25 | DG NH Seabrook Lafayette Seabrook Solar | Generator notification from Unitil on behalf of DG NH Seabrook for the instalaltion of a 4.5 MW solar PV in Seabrook, NH and interconnecting to the Timber Swamp Substation via the 3359 34.5 kV circuit. | 2022-12-01 | Notification | 2021-11-23
CMP-21-G29 | 2021-11-01 | Louth Callan Renewables US 1 Kittery Solar | Generation notification from Central Maine Power Company (“CMP”) on behalf of Louth Callan Renewables for the installation of a 1.5 MW solar PV in Kittery, ME and interconnecting to the Kittery Substation via the 668D1 12.47 kV circuit. | 2022-12-30 | Notification | 2021-11-23
CMP-21-G33 | 2021-11-01 | Dynamic Energy Pond Wales Solar | Generation notification from Central Maine Power Company (“CMP”) on behalf of Revision Energy for the installation of a 4.99 MW solar PV in Wales, ME and interconnecting to the Monmouth Substation via the 457D1 34.5 kV circuit. | 2022-12-31 | Notification | 2021-11-23
NEP-19-GNF162 Rev.1 | 2021-10-29 | Nexamp Griffin Road Charlton Solar and Battery Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Nexamp for the installation of a 1.393 MW solar PV and 1.0 MW/2.726 MWh battery in Charlton, MA and interconnecting to the West Charlton Substation via the 415L2 13.2 kV circuit. Proposed in-service date of the PV was June 5, 2020. The project is being revised to add an AC coupled battery. The max output of the 1.393 MW (AC) facility has not changed. | 2022-10-01 | Notification | 2021-11-23
NEP-20-G08 Rev.1 | 2021-10-29 | Renewable Energy International Meadowbrook Road Amesbury Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Renewable Energy International for the installation of a 4.99 MW solar PV and 4.128 MW/8.256 MWh battery in Amesbury, MA and interconnecting to the West Amesbury Substation via the 275L2 13.2 kV circuit. The project is being revised to modify the original DC coupled battery size to 4,128kW/8,256kWh. The max output of the 4.99 MW (AC) facility has not changed. | 2023-05-01 | Notification | 2021-11-23
ES-21-T89 | 2021-10-13 | Berlin Substation TB 115 Transformer Replacement | Transmission notification from Eversource Energy (“ES”) to replace the existing 115/34.5 kV 15 MVA TB 115 transformer at the Berlin Substation in New Hampshire due to equipment failure. The transformer will be replaced with a 40 MVA unit and renamed TX 115. | 2/2022 | Notification | 2021-11-17
ES-21-T44 Rev.1 | 2021-10-23 | Rebuild 115 kV Line E-115 Rev.1 | Transmission notification from Eversource Energy (“ES”) to rebuild the 115 kV Line E-115 from Huckins, NH to Pemigewasset, NH. PPA has been revised to update the normal rating of E-115-2 to 159 MVA instead of 241 MVA. | 12/2023 | Notification | 2021-11-17
ES-21-T51 Rev.1 | 2021-10-29 | Reconductor 115 kV Line 191 Rev.1 | Transmission notification from Eversource Energy (“ES”) to reconductor the 15.3 mile overhead 115kV Line 191 with 1590 kcmil from Auburn Street to Kingston Substation. | 7/2025 | Notification | 2021-11-23
VP-21-G25 | 2021-09-03 | Three Rivers Solar and Generation and Transmission Project | Generator application from Versant Power ("VP") on behalf of Three Rivers Solar Power, for the installation of 35 2.857 MW (100 MWs net output) solar array. | 12/2023 | Approved | 2021-11-08
VP-21-T05 | 2021-09-03 | Three Rivers Solar and Generation and Transmission Project | Transmission application from Versant Power (“VP”) on behalf of Three Rivers Solar Power, for the installation of a new collector substation. | 9/2023 | Approved | 2021-11-08
VP-21-T06 | 2021-09-03 | Three Rivers Solar and Generation and Transmission Project | Transmission application from Versant Power (“VP”) on behalf of Three Rivers Solar Power, for the installation of a new switching station in L 93 between Bull Hill and Deblois 115 kV. | 9/2023 | Approved | 2021-11-08
VP-21-T07 | 2021-09-03 | Three Rivers Solar and Generation and Transmission Project | Transmission application from Versant Power (“VP”) on behalf of Three Rivers Solar Power, to add a 50 MVA synchronous condenser at the Boggy Brook substation and construct associated 115 kV breaker-and-a-half rung with two new 40 kA breakers and related protection systems. | 9/2023 | Approved Withdrawn | 11/8/2021 2/15/2022
IES-21-G01 | 2021-10-07 | Cross Road Battery Energy Storage Generation and Transmission Project (QP 876) | Generator application from Interconnect Energy Storage (“IES”) for the installation of 246 MW/492 MWh Battery Energy Storage System (BESS) in Dartmouth, MA along with 74 34.5 kV GSU transformers. | 2024-12-31 | Approved Withdrawn | 11/8/2021 12/20/2021
IES-21-T01 | 2021-10-07 | Cross Road Battery Energy Storage Generation and Transmission Project (QP 876) | Transmission application from Interconnect Energy Storage (“IES”) for the construction of a new 34.5/115 kV substation at the Cross Road BESS project site. The substation will have two main power transformers rated at 13.8/34.5/115 kV each with a maximum rating of 130 MVA. A new 0.189 mile 115 kV interconnection transmission line will also be installed to the third terminal position at the new Cross Road three breaker ring bus. | 2024-10-28 | Approved Withdrawn | 11/8/2021 12/20/2021
ES-21-T83 | 2021-10-06 | Cross Road Battery Energy Storage Generation and Transmission Project (QP 876) | Transmission application from Eversource Energy (“ES”) to reconductor High Hill to Cross Road Line 109 to at least 280 MVA and increase the LTE line rating on the same line to at least 306.6 MVA. | 2024-12-31 | Approved Withdrawn | 11/8/2021 12/20/2021
ES-21-T85 | 2021-10-06 | Cross Road Battery Energy Storage Generation and Transmission Project (QP 876) | Transmission application from Eversource Energy (“ES”) to reconductor High Hill to Industrial Park Line 111 to at least 315.4 MVA. | 2024-10-28 | Approved Withdrawn | 11/8/2021 12/20/2021
ES-21-T86 | 2021-10-06 | Cross Road Battery Energy Storage Generation and Transmission Project (QP 876) | Transmission application from Eversource Energy (“ES”) to reconductor Industrial Park Tap to Industrial Park Line 112 to at least 342.3. | 2024-10-28 | Approved Withdrawn | 11/8/2021 12/20/2021
ES-21-T87 | 2021-10-06 | Cross Road Battery Energy Storage Generation and Transmission Project (QP 876) | Transmission application from Eversource Energy (“ES”) for the construction of a new Cross Road 3-breaker ring-bus that will require the installation of three 115kV circuit breakers, six capacitor voltage transformers (CVTs), six 115kV disconnect switches, station service transformers, and a new 115kV control house which will contain the relays and associated equipment. | 2024-10-28 | Approved Withdrawn | 11/8/2021 12/20/2021
NEP-21-T11 | 2021-09-27 | Cross Road Battery Energy Storage Generation and Transmission Project (QP 876) | Transmission application from New England Power Company (“NEP”) to upgrade the W4S and X3S 115 kV Lines from Grand Army to Hathaway Tap. | 2024-12-31 | Approved Withdrawn | 11/8/2021 12/20/2021
ES-21-T90 | 2021-09-20 | Bokum Substation Reconfiguration Project | Transmission application from Eversource Energy (“ES”) for the installation of six 115 kV circuit breakers, three new 115/23 kV distribution transformers, and six 115 kV disconnection switches at the Bokum 15L substation in Old Saybrook, CT. The project is to address local system reliability. | 2023-12-31 | Approved | 2021-10-27
ES-21-T101 | 2021-10-04 | Sandy Hook Substation 37F 2X Transformer | Transmission application from Eversource Energy (“ES”) for the installation of a new 115/23 kV distribution transformer and a high-side PASSM0 double-tie circuit breaker at the Sandy Hook Substation in Newtown, CT for system reliability. | 5/2023 | Approved | 2021-10-27
ES-21-T38 Rev.1 | 2021-09-30 | Eastern Connecticut Project Update - Shunock Substation Upgrades Rev.1 | Transmission application from Eversource Energy ("ES") for the installation of a +55/-29 MVAR synchronous condenser (+50/-25 MVAR at POI) at Shunock Substation and expand the substation from a straight bus configuration to a 115 kV ring bus configuration. | 6/2024 | Approved | 2021-10-27
CMP-21-G25 | 2021-09-30 | Solar Generation Project (QP 929) | Generation application from Central Maine Power Company (“CMP”) on behalf of Greeskies Clean Energy for the installation of a 19.0 MWs net output PV facility in Saco, ME and interconnecting to the Louden Substation via the 34.5 kV circuit. | 2023-07-31 | Approved | 2021-11-08
NRG-21-X01 | 2021-10-05 | Montville 5 Generator Automatic Voltage Regulator (AVR) Replacement Project | Transmission application from NRG Power Marketing (“NRG”) for the replacement of the Montville 5 generator AVR with Basler’s DECS 2020 unit due end of their service life. | 2021-11-05 | Approved | 2021-11-08
ES-21-G98 Rev.1 | 2021-09-30 | Greenskies Miller Road East Windsor Solar Rev.1 | Generator notification from Eversource Energy (“ES”) on behalf of Greenskies for the installation of a 4.99 MW solar PV in East Windsor, CT and interconnecting to the Barbour Hill Substation via the 23J36 105W50 23 kV circuit. | 2022-09-01 | Notification | 2021-11-08
CMP-21-G28 | 2021-10-04 | MEVS West Beech Road Scarborough Solar | Generator application from Central Maine Power Company (“CMP”) on behalf of MEVS for the installation of a 4.95 MW solar PV in Scarborough, ME and interconnecting to the Dunstan Substation via the 617D3 12.47 kV circuit. | 2022-12-30 | Notification | 2021-11-08
NEP-19-GNF114 Rev.1 | 2021-10-04 | TJA Solar Federal Street Blackstone Solar and Battery 1 Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of TJA Solar for the installation of a 4.2 MW solar PV and 3.0 MW/6.389 MWh battery in Blackstone, MA and interconnecting to the Riverside Substation via the 108W60 13.8 kV circuit. | 2022-06-02 | Notification | 2021-11-08
NEP-19-GNF126 Rev.2 | 2021-10-04 | TJA Solar Federal Street Blackstone Solar and Battery 2 Rev.2 | Generator notification from New England Power Company ("NEP") on behalf of TJA Solar for the installation of a 3.6 MW solar PV and 2.5 MW/5.48 MWh battery in Blackstone, MA and interconnecting to the Riverside Substation via the 108W60 13.8 kV circuit. | 2022-04-07 | Notification | 2021-11-08
NEP-21-GNF20 | 2021-10-04 | BlueWave Solar Plain Street Rehoboth Battery | Generator notification from New England Power Company ("NEP") on behalf of BlueWave Solar for the installation of a 4.99 MW/20.0 MWh battery in Rehoboth, MA and interconnecting to the Mink Street Substation via the 7L5 13.2 kV circuit. | 2023-04-01 | Notification Withdrawn | 11/8/2021 8/15/2023
ES-21-T100 | 2021-09-28 | Franconia Substation Step-Down Transformer 3X Replacement | Transmission notification from Eversource Energy (“ES”) to replace the existing 117/15.12 kV step-down transformer 3X at the Franconia Substation. | 2021-06-30 | Notification | 2021-10-27
ES-21-T99 | 2021-09-27 | Clinton Substation Step-Down Transformer 2X Replacement | Transmission notification from Eversource Energy (“ES”) to replace the existing 117/15.12 kV step-down transformer 2X at the Clinton Substation. | 2021-06-30 | Notification | 2021-10-27
ES-21-T93 | 2021-09-17 | Doreen Substation Step-Down Transformer 1X Replacement | Transmission notification from Eversource Energy (“ES”) to replace the existing 115/23.0 kV step-down transformer 1X at the Doreen Substation. | 2022-02-28 | Notification | 2021-10-27
ES-21-T94 | 2021-09-17 | Breckwood Substation Step-Down Transformer 1X Replacement | Transmission notification from Eversource Energy (“ES”) to replace the existing 117/15.12 kV step-down transformer 1X at the Breckwood Substation. | 2022-12-31 | Notification | 2021-10-27
ES-21-T95 | 2021-09-17 | Breckwood Substation Step-Down Transformer 2X Replacement | Transmission notification from Eversource Energy (“ES”) to replace the existing 117/15.12 kV step-down transformer 2X at the Breckwood Substation. | 2022-02-28 | Notification | 2021-10-27
CMP-21-G24 | 2021-09-08 | Solar Generation Project (QP 896) | Generation application from Central Maine Power Company ("CMP") on behalf of HEP USA SPV 3 Saco for the installation of 14 1.56 MWs (19.6 MWs net output) PV facility in Saco, ME and interconnecting to the Louden Substation via the 34.5 kV circuit. | 2023-12-31 | Approved | 2021-10-18
PES-21-X01 | 2021-08-17 | Androscoggin Automatic Voltage Regulators (AVR) Replacement Project | Transmission application from Pixelle Energy Services (PES) for the replacement of three analog Brush MVAR units with new digital Brush PRISMIC A3100 AVR units at the Androscoggin Co-Generation facility. | AVR 3 - 10/14/2021 AVR 2 - 10/17/2021 AVR 1 - 10/20/2021 | Approved | 2021-10-18
ES-21-G45 | 2021-08-10 | Air Line Renewables Soap Street Danielson Solar | Generator notification from Eversource Energy ("ES") on behalf of Air Line Renewables for the installation of a 4.0 MW solar PV in Danielson, CT and interconnecting to the Tracy Substation via the 14M24 23 kV circuit. | 2021-12-31 | Notification Withdrawn | 10/18/2021 6/18/2024
ES-21-G101 | 2021-08-10 | Air Line Renewables Alexander Parkway Dayville Solar | Generator notification from Eversource Energy ("ES") on behalf of Air Line Renewables for the installation of a 4.0 MW solar PV in Dayville, CT and interconnecting to the Tracy Substation via the 14M 23 kV circuit. | 2021-12-31 | Notification Withdrawn | 10/18/2021 5/16/2023
ES-21-G46 | 2021-08-10 | Air Line Renewables Lake Road Dayville Solar | Generator notification from Eversource Energy ("ES") on behalf of Air Line Renewables for the installation of a 2.0 MW solar PV in Dayville, CT and interconnecting to the Tracy Substation via the 14M 23 kV circuit. | 2021-12-31 | Notification Withdrawn | 10/18/2021 5/16/2023
ES-21-G47 | 2021-08-10 | Air Line Renewables Wrights Crossing Road Pomfret Center Solar | Generator notification from Eversource Energy ("ES") on behalf of Air Line Renewables for the installation of a 2.0 MW solar PV in Pomfret Center, CT and interconnecting to the Tracy Substation via the 14M 23 kV circuit. | 2021-12-31 | Notification Withdrawn | 10/18/2021 5/16/2023
ES-21-G48 | 2021-08-10 | Air Line Renewables Providence Pike Putnam Solar | Generator notification from Eversource Energy ("ES") on behalf of Air Line Renewables for the installation of a 2.0 MW solar PV in Putnam, CT and interconnecting to the Tracy Substation via the 14M 23 kV circuit. | 2021-12-31 | Notification Withdrawn | 10/18/2021 8/17/2022
ES-21-G109 | 2021-08-10 | Kearsarge Energy Dunbarton Road Manchester Solar | Generator notification from Eversource Energy ("ES") on behalf of Kearsarge Energy for the installation of a 2.49 MW solar PV in Manchester, NH and interconnecting to the Rimmon Substation via the 334R 34.5 kV circuit. | 2021-12-31 | Notification | 2021-10-18
ES-21-G110 | 2021-09-02 | ReVision Energy Pickering Road Rochester Solar | Generator notification from Eversource Energy ("ES") on behalf of ReVision Energy for the instalaltion of a 3.3 MW solar PV in Rochester, NH and interconnecting to the Dover Substation via the 371D 34.5 kV circuit. | 2022-12-01 | Notification Withdrawn | 10/18/2021 8/17/2022
NEP-20-G04-005 Rev.1 | 2021-09-03 | ECA Solar Strawberry Field Road Warwick Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of ECA Solar for the installation of a 3.0 MW solar PV in Warwick, RI and interconnecting to the Drumrock Substation via the 2222 23 kV circuit. | 2022-01-10 | Notification Withdrawn | 10/18/2021 1/16/2024
ES-21-G108 | 2021-09-03 | Niagara Bottling Woodland Avenue Bloomfiend Solar | Generator notification from Eversource Energy ("ES") on behalf of Niagara Bottling for the installation of a 2.82 MW solar PV in Bloomfield, CT and interconnecting to the North Bloomfield Substation via the 2A2 23 kV circuit. | 2022-01-10 | Notification | 2021-10-18
VELCO-21-GNF01 | 2021-08-02 | MacKinnon Solar Cold River Road Rutland Solar | Generator notification from VELCO on behalf of MacKinnon Solar for the installation of a 2.192 MW solar PV in Rutland, VT and interconnecting to the South Rutland via the G71 12.47 kV circuit. | 2021-08-26 | Notification | 2021-10-18
ES-21-G26 Rev.1 | 2021-09-07 | Eversource ASO Study Interconnections in SEMA and Cape Cod Generation and Transmission Project – Westport Stone & Sand Westport Solar Rev.1 | Generator notification from Eversource Energy ("ES") for a minor revision to a 4.95 MW solar PV in Westport, MA and interconnecting to the Fisher Road Substation via the 2-522-522 13.2 kV circuit. | 2021-09-30 | Notification | 2021-10-18
NEP-21-GNF16 | 2021-09-03 | Agilitas Energy Fall River Avenue Seekonk Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Agilitas Energy for the installation of a 4.99 MW solar PV and 3.0 MW/9.0 MWh battery in Seekonk, MA and interconnecting to the Mink Street Substation via the 7L5 13.2 kV circuit. | 2023-05-01 | Notification Withdrawn | 10/18/2021 1/22/2025
ES-21-G73 Rev.1 | 2021-09-07 | Eversource ASO Study Interconnections in SEMA and Cape Cod Generation and Transmission Project – Maple Springs Road Wareham Solar and Battery Rev.1 | Generator notification from Eversource Energy ("ES") for a minor revision to a 4.99 MW solar PV and 4.99 MW/26 MWh battery in Wareham, MA and interconnecting to the Wareham #714 Substation via the 3-84-84 23 kV circuit. | 2022-04-08 | Notification | 2021-10-18
ES-21-G24 Rev.1 | 2021-09-07 | Eversource ASO Study Interconnections in SEMA and Cape Cod Generation and Transmission Project – Pine Hill Road Westport Solar and Battery Rev.1 | Generator notification from Eversource Energy ("ES") for a minor revision to a 3.25 MW solar PV and 3.25 MW/6.75 MWh battery in Wareham, MA and interconnecting to the Fisher Road Substation via the 2-522-522 13.2 kV circuit. | 2021-12-01 | Notification | 2021-10-18
VELCO-21-T01 | 2021-08-23 | Florence Substation Transformer Replacement | Transmission notification from VELCO to replace the 56 MVA 115/46 kV transformer at the Florence substation. | 12/2022 | Notification | 2021-09-22
ES-21-T50 | 2021-08-30 | Line G192 Conductor Replacement | Transmission notification from Eversource Energy ("ES") to replace the 1.29 miles for Line G192 from structure 2 to structure 17 with 795 ACSR 16/7 conductors between Bridge Street substation in Nashua, NH and Power Street substation in Hudson, NH. | 12/2021 | Notification | 2021-09-22
NEP-21-X02 | 2021-08-19 | GE Lynn (Riverworks) Source Transfer System (STS) Automatic Control Scheme | Transmission notification from New England Power Company ("NEP") to implement a utility source transfer system (STS) at their Lynn (Riverworks) facility’s 115 kV substation. For planned outages, the STS will manage closed-transition transfer between National Grid (NGRID) utility source lines A-179 and Q-169, without interruption to GE facility load. Upon manual initiation, the STS will perform automated closed-transition transfer from the active to the alternate source line. For unplanned outages, the STS will provide open-transition transfer to the alternate line, with minimal interruption to GE load. This open-transition transfer will be fully automated by the STS upon detecting loss of voltage at the active source line. | 12/2021 | Notification | 2021-09-22
ES-21-T88 | 2021-08-26 | Line D108 115 kV Rebuild | Transmission notification from Eversource Energy ("ES") to replace the 1.28-miles of the 115-kV line D108 between North Keene substation and Keene substation with 1272 ACSS 54/19 conductors. | 12/2021 | Notification | 2021-09-22
ES-21-T62 Rev.1 | 2021-09-07 | Eversource ASO Study Interconnections in SEMA and Cape Cod Generation and Transmission Project – Upgrade Wareham Substation to Six-Breaker Ring Bus Configuration Rev.1 | Transmission notification from Eversource Energy ("ES") for a minor revision to upgrade the Wareham Substation to a six-breaker 115 kV ring bus configuration. | 1/2026 | Notification Withdrawn | 10/18/2021 4/18/2023
ES-21-T63 Rev.1 | 2021-09-07 | Eversource ASO Study Interconnections in SEMA and Cape Cod Generation and Transmission Project – Replace Wareham Substation Transformer #1 Rev.1 | Transmission notification from Eversource Energy ("ES") for a minor revision to replace the Wareham Substation transformer #1 with a new 45/60/75 MVA 115/23 kV transformer. | 1/2026 | Notification | 2021-10-18
ES-21-T64 Rev.1 | 2021-09-07 | Eversource ASO Study Interconnections in SEMA and Cape Cod Generation and Transmission Project – Replace Wareham Substation Transformer #3 Rev.1 | Transmission notification from Eversource Energy ("ES") for a minor revision to replace the Wareham Substation transformer #3 with a new 45/60/75 MVA 115/23 kV transformer. | 1/2026 | Notification Withdrawn | 10/18/2021 4/18/2023
ES-21-T65 Rev.1 | 2021-09-07 | Eversource ASO Study Interconnections in SEMA and Cape Cod Generation and Transmission Project – Reconductor 115 kV Rev.1 | Transmission notification from Eversource Energy ("ES") for a minor revision to reconductor the 115 kV 132 Line between Brook Street Station and West Pond Substation. | 1/2026 | Notification | 2021-10-18
ES-21-T66 Rev.1 | 2021-09-07 | Eversource ASO Study Interconnections in SEMA and Cape Cod Generation and Transmission Project – Upgrade West Pond Substation Rev.1 | Transmission notification from Eversource Energy ("ES") for a minor revision to upgrade the West Pond Substation to a six-breaker 115 kV ring bus configuration. | 1/2026 | Notification | 2021-10-18
ES-21-T67 Rev.1 | 2021-09-07 | Eversource ASO Study Interconnections in SEMA and Cape Cod Generation and Transmission Project – Replace West Pond Substation Transformer #1 Rev.1 | Transmission notification from Eversource Energy ("ES") for a minor revision to replace the West Pond Substation transformer #1 with a new 45/60/75 MVA 115/23 kV transformer. | 1/2026 | Notification | 2021-10-18
ES-21-T68 Rev.1 | 2021-09-07 | Eversource ASO Study Interconnections in SEMA and Cape Cod Generation and Transmission Project – Replace West Pond Substation Transformer #2 Rev.1 | Transmission notification from Eversource Energy ("ES") for a minor revision to replace the West Pond Substation transformer #2 with a new 45/60/75 MVA 115/23 kV transformer. | 1/2026 | Notification | 2021-10-18
ES-21-T69 Rev.1 | 2021-09-07 | Eversource ASO Study Interconnections in SEMA and Cape Cod Generation and Transmission Project – Replace West Pond Substation Transformer #3 Rev.1 | Transmission notification from Eversource Energy ("ES") for a minor revision to replace the West Pond Substation transformer #3 with a new 45/60/75 MVA 115/23 kV transformer. | 1/2026 | Notification | 2021-10-18
ES-21-T73 Rev.1 | 2021-09-07 | Eversource ASO Study Interconnections in SEMA and Cape Cod Generation and Transmission Project – Replace Tremont Substation Transformer #1 Rev.1 | Transmission notification from Eversource Energy ("ES") for a minor revision to replace the Tremont Substation transformer #1 with a new 45/60/75 MVA 115/23 kV transformer. | 1/2026 | Notification | 2021-10-18
ES-21-T74 Rev.1 | 2021-09-07 | Eversource ASO Study Interconnections in SEMA and Cape Cod Generation and Transmission Project – Replace Tremont Substation Transformer #2 Rev.1 | Transmission notification from Eversource Energy ("ES") for a minor revision to replace the Tremont Substation transformer #2 with a new 45/60/75 MVA 115/23 kV transformer. | 1/2026 | Notification | 2021-10-18
ES-21-T75 Rev.1 | 2021-09-07 | Eversource ASO Study Interconnections in SEMA and Cape Cod Generation and Transmission Project – Replace Tremont Substation Transformer #3 Rev.1 | Transmission notification from Eversource Energy ("ES") for a minor revision to replace the Tremont Substation transformer #3 with a new 45/60/75 MVA 115/23 kV transformer. | 1/2026 | Notification | 2021-10-18
ES-21-T80 Rev.1 | 2021-09-07 | Eversource ASO Study Interconnections in SEMA and Cape Cod Generation and Transmission Project – Replace Fisher Road Substation Transformer #1 Rev.1 | Transmission notification from Eversource Energy ("ES") for a minor revision to replace the Fisher Road Substation transformer #1 with a new 37/50/62.5 MVA 115/13.2 kV transformer. | 7/2025 | Notification | 2021-10-18
ES-21-T81 Rev.1 | 2021-09-07 | Eversource ASO Study Interconnections in SEMA and Cape Cod Generation and Transmission Project – Replace Fisher Road Substation Transformer #2 Rev.1 | Transmission notification from Eversource Energy ("ES") for a minor revision to replace the Fisher Road Substation transformer #2 with a new 37/50/62.5 MVA 115/13.2 kV transformer. | 7/2025 | Notification | 2021-10-18
AGIH-21-G02 | 2021-08-05 | Medway Battery Energy Storage Generator and Transmission Project (QP 844) | Generation application from Able Grid Infrastructure Holdings (“AGIH”) for construction of a 250 MW/500 MWh battery storage system with 131 2.5 MVA 0.55/34.5 kV generator step up transformers in Medway, MA. | 2023-05-31 | Approved | 2021-09-03
AGIH-21-T02 | 2021-08-05 | Medway Battery Energy Storage Generator and Transmission Project (QP 844) | Transmission application from Able Grid Infrastructure Holdings (“AIGH”) for the installation of a 345/34.5/13.8 kV load tap changing power transformer and a generation tie line from the project site to the West Medway Substation. | 2023-05-31 | Approved | 2021-09-03
ES-21-T49 | 2021-08-05 | Medway Battery Energy Storage Generator and Transmission Project (QP 844) | Transmission application from Eversource Energy (“ES”) for the installation of a generator lead line from West Medway Substation to the first structure on the generation side. Also install one 345 kV breaker, two 345 kV breaker disconnects, one line terminal structure, three Capacitor Coupled Voltage Transformers (CCVTs), three lightning arrestors and associated protection and control systems. | 2023-05-31 | Approved | 2021-09-03
VW-21-G01 | 2021-07-23 | Vineyard Wind Generation and Transmission Project (QP 792) | Generation application from Vineyard Wind (“VW”) for construction of 92 9.5 MW MHI-Vestas offshore wind turbines (limited to 9.375 MWs each for 862.5 MW total output) south of Martha’s Vineyard, MA. | 2023-05-31 | Approved Withdrawn | 9/3/2021 1/13/2022
VW-21-T01 | 2021-07-23 | Vineyard Wind Generation and Transmission Project (QP 792) | Transmission application from Vineyard Wind (“VW”) for the installation of a single offshore gas-insulated substation (“GIS”), containing 66 kV switchgear, 220 kV circuit breakers and two (2) 450 MVA 220/66 kV on-load tap-changing transformers. | 2023-05-31 | Approved Withdrawn | 9/3/2021 1/13/2022
VW-21-T02 | 2021-07-23 | Vineyard Wind Generation and Transmission Project (QP 792) | Transmission application from Vineyard Wind (“VW”) for the installation of a combination of two 1600mm² Cu, 3-core 220kV submarine cables and 1600mm² Cu single conductor 220kV terrestrial underground cable to transmit the power from the offshore substations approximately 93-miles to onshore substation. The offshore cable system will also consist of an offshore, midpoint shunt reactor platform, one 220 kV, 200 MVAR fixed shunt reactor connected to each of the two cable circuits. | 2023-05-31 | Approved Withdrawn | 9/3/2021 1/13/2022
VW-21-T03 | 2021-07-23 | Vineyard Wind Generation and Transmission Project (QP 792) | Transmission application from Vineyard Wind (“VW”) for the installation of a single onshore substation containing two 400 MVA 345kV/220kV on-load tap changing transformers, each separately connected to a 345 kV straight bus and a 220 kV straight bus. Each 345 kV bus will have five 345 kV circuit breakers. | 2023-05-31 | Approved Withdrawn | 9/3/2021 1/13/2022
VW-21-T04 | 2021-07-23 | Vineyard Wind Generation and Transmission Project (QP 792) | Transmission application from Vineyard Wind (“VW”) for the installation of two individual 345kV circuits providing separate Vineyard Wind onshore substation transformer interconnection to distinct Montville 345kV station breaker positions through an approximately 1.6-mile underground circuit. | 2023-05-31 | Approved Withdrawn | 9/3/2021 1/13/2022
VW-21-T05 | 2021-07-23 | Vineyard Wind Generation and Transmission Project (QP 792) | Transmission application from Vineyard Wind (“VW”) for the installation of two +150MVAR/-150MVAR STATCOM’s for dynamic voltage support provision will interconnect at each Vineyard Wind onshore substation 345 kV bus (subject of PPA VW-21-T03) regulating the Eversource 345kV Montville bus (subject of PPA ES-21-T82). | 2023-05-31 | Approved Withdrawn | 9/3/2021 1/13/2022
ES-21-T82 | 2021-08-04 | Vineyard Wind Generation and Transmission Project (QP 792) | Transmission application from Eversource Energy ("ES") for a reconfiguration of the existing substation 4J Montville 345 kV switchyard into a breaker-and-a-half design with all transmission lines and autotransformers terminated in a bay position. | 4/1//2023 | Approved Withdrawn | 9/3/2021 1/13/2022
ES-21-G12 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Arsene Street Solar | Generator application from Eversource Energy (“ES”) for construction of a 5.0 MW PV facility in Mattapoisett, MA and interconnecting to the Arsene Street substation via the 2-221-221 13.2 kV circuit. | 2021-12-01 | Approved Withdrawn | 9/23/2021 1/18/2023
ES-21-G13 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Fairhaven 1 Charity Stevens Lane Fairhaven Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 2.0 MW PV and 2.0 MW/4 MWh battery facility in Fairhaven, MA and interconnecting to the Arsene Street substation via the 2-221-221 13.2 kV circuit. | 2021-12-30 | Approved | 2021-09-23
ES-21-G17 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Sup Set Main Street Plympton Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 2.0 MW PV and 1.65 MW/4.11 MWh battery facility in Plympton, MA and interconnecting to the Brook Street substation via the 3-51-901 23.0 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G18 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Sharon Mountain Landfill Mountain Street Sharon Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 5.0 MW PV and 5.0 MW/10.0 MWh battery facility in Sharon, MA and interconnecting to the Brook Street substation via the 470-H12 13.8 kV circuit. | 2022-03-18 | Approved | 2021-09-23
ES-21-G19 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - route 88 Solar 1 Route 88 Westport Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.0 MW PV and 1.2645 MW/2.529 MWh battery facility in Westport, MA and interconnecting to the Cross Road substation via the 2-532-532 13.2 kV circuit. | 2021-10-15 | Approved | 2021-09-23
ES-21-G20 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Dartmouth Solar and Energy Storage Cross Road North Dartmouth Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 3.0 MW PV and 2.0 MW/8.0 MWh battery facility in North Dartmouth, MA and interconnecting to the Cross Road substation via the 2-532-532 13.2 kV circuit. | 2021-11-30 | Approved Withdrawn | 9/23/2021 7/16/2024
ES-21-G21 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Randal Lane Mattapoisett Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.999 MW PV and 3.0 MW/6.36 MWh battery facility in Mattapoisett, MA and interconnecting to the Crystal Spring substation via the 2-301-301 13.2 kV circuit. | 2022-12-15 | Approved | 2021-09-23
ES-21-G22 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Blacksmith Shop Road Falmouth Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.99 MW PV and 3.0 MW/12.0 MWh battery facility in Falmouth, MA and interconnecting to the Falmouth substation via the 4-98A-98A 23.0 kV circuit. | 2021-12-31 | Approved | 2021-09-23
ES-21-G23 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Blacksmith Shop Solar South Locustfield Road East Falmouth Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 3.0 MW PV and 2.5 MW/10.0 MWh battery facility in East Falmouth, MA and interconnecting to the Falmouth substation via the 4-98A-98A 23.0 kV circuit. | 2021-12-01 | Approved Withdrawn | 9/29/2021 6/18/2024
ES-21-G24 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Pine Hill Road Westport Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 3.25 MW PV and 3.25 MW/6.75 MWh battery facility in Westport, MA and interconnecting to the Fisher Road substation via the 2-522-522 13.2 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G25 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - CVE Westport Tootell Drift Road Westport Solar | Generator application from Eversource Energy (“ES”) for construction of a 2.0 MW PV facility in Westport, MA and interconnecting to the Fisher Road substation via the 2-523-523 13.2 kV circuit. | 2021-12-01 | Approved Withdrawn | 9/23/2021 7/16/2024
ES-21-G26 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Westport Stone and Sand Old County Road Bristol Solar | Generator application from Eversource Energy (“ES”) for construction of a 4.95 MW PV facility in Bristol, MA and interconnecting to the Fisher Road substation via the 2-522-522 13.2 kV circuit. | 2021-09-30 | Approved | 2021-09-23
ES-21-G27 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Ironwood Gadus Horseneck Road Westport Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.0 MW PV and 2.5 MW/10.0 MWh battery facility in Westport, MA and interconnecting to the Fisher Road substation via the 2-523-523 13.2 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G28 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - CVE Westport Soules Way Westport Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.0 MW PV and 2.0 MW/4.448 MWh battery facility in Westport, MA and interconnecting to the Fisher Road substation via the 2-523-523 13.2 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G29 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Next Grid Depot Road Harwich Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 3.15 MW PV and 1.5 MW/6.094 MWh battery facility in Harwich, MA and interconnecting to the Harwich substation via the 4-95A-95A 23.0 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G30 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Park Drive Acushnet Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.999 MW PV and 4.0 MW/8.0 MWh battery facility in Acushnet, MA and interconnecting to the Industrial Park substation via the 2-106-106 13.2 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G31 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Scrimshaw Solar Acushnet Avenue Acushnet Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 2.0 MW PV and 1.0 MW/2.224 MWh battery facility in Acushnet, MA and interconnecting to the Industrial Park substation via the 2-106-106 13.2 kV circuit. | 2021-11-30 | Approved Withdrawn | 9/23/2021 6/18/2024
ES-21-G32 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - TJA Clean Energy Chace Road Freetown Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.99 MW PV and 3.75 MW/7.812 MWh battery facility in Freetown, MA and interconnecting to the Industrial Park substation via the 2-108-108 13.2 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G33 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Braley Road Freetown Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 3.3 MW PV and 2.0 MW/2.0 MWh battery facility in Freetown, MA and interconnecting to the Industrial Park substation via the 2-108-108 13.2 kV circuit. | 2022-12-01 | Approved | 2021-09-23
ES-21-G34 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Quanapoag Road Freetown Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.995 MW PV and 4.995 MW/30.0 MWh battery facility in Freetown, MA and interconnecting to the Industrial Park substation via the 2-102-102 13.2 kV circuit. | 2022-04-01 | Approved | 2021-09-23
ES-21-G35 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Ironwood Costa Braley Road Freetown Solar | Generator application from Eversource Energy (“ES”) for construction of a 5.0 MW PV facility in Freetown, MA and interconnecting to the Industrial Park substation via the 2-102-604 13.2 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G36 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - CVE Freetown Clermont Way Freetown Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 2.0 MW PV and 1.0 MW/2.224 MWh battery facility in Freetown, MA and interconnecting to the Industrial Park substation via the 2-102-608 13.2 kV circuit. | 2021-12-31 | Approved Withdrawn | 9/23/2021 6/18/2024
ES-21-G38 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Cushman Road Solar | Generator application from Eversource Energy (“ES”) for construction of a 3.0 MW PV and 2.0 MW/4.24 MWh battery facility in Rochestor, MA and interconnecting to the Rochester substation via the 3-703-703 13.2 kV circuit. | 2022-12-15 | Approved | 2021-09-23
ES-21-G39 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Snipatuit Pauline’s Way Rochester Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.0 MW PV and 3.0 MW/6.36 MWh battery facility in Rochester, MA and interconnecting to the Rochester substation via the 3-703-703 13.2 kV circuit. | 2022-12-15 | Approved | 2021-10-01
ES-21-G40 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Braley Hill South Rochester Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.999 MW PV and 4.999 MW/11.686 MWh battery facility in Rochester, MA and interconnecting to the Rochester substation via the 3-703-703 13.2 kV circuit. | 2022-12-15 | Approved | 2021-09-23
ES-21-G41 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Featherbed Lane South Rochester Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 2.0 MW PV and 2.0 MW/4.24 MWh battery facility in Rochester, MA and interconnecting to the Rochester substation via the 3-703-703 13.2 kV circuit. | 2022-12-15 | Approved Withdrawn | 9/23/2021 11/14/2023
ES-21-G42 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - CVE Rochester Neck Road Rochester Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 2.0 MW PV and 1.0 MW/2.224 MWh battery facility in Rochester, MA and interconnecting to the Rochester substation via the 3-703-703 13.2 kV circuit. | 2021-12-31 | Approved Withdrawn | 9/23/2021 6/18/2024
ES-21-G43 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Cape Crossing Pimlico Pond Sandwich Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.998 MW PV and 2.0 MW/4.0 MWh battery facility in Sandwich, MA and interconnecting to the Sandwich substation via the 4-81B-443 23.0 kV circuit. | 2021-09-01 | Approved Withdrawn | 9/23/2021 12/17/2024
ES-21-G44 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Autumnwood Discovery Hill Road Sandwich Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 6.25 MW PV and 6.25 MW/12.5 MWh battery facility in Sandwich, MA and interconnecting to the Sandwich substation via the 4-81B-81B 23.0 kV circuit. | 2021-10-01 | Approved Withdrawn | 9/23/2021 12/17/2024
ES-21-G56 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Solar Carver North Carver Road Wareham Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 3.0 MW PV and 3.0 MW/48.0 MWh battery facility in Wareham, MA and interconnecting to the Tremont substation via the 3-81-81 23.0 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G57 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Wareham County Road Wareham Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.075 MW PV and 4.075 MW/8.15 MWh battery facility in Wareham, MA and interconnecting to the Tremont substation via the 3-85-85 23.0 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G58 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - 1 North Carver Road Wareham Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 3.0 MW PV and 1.5 MW/3.336 MWh battery facility in Wareham, MA and interconnecting to the Tremont substation via the 3-81-81 23.0 kV circuit. | 2022-04-01 | Approved | 2021-09-23
ES-21-G60 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Wareham County Road Wareham Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.98 MW PV and 4.98 MW/9.96 MWh battery facility in Wareham, MA and interconnecting to the Tremont substation via the 3-85-85 23.0 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G61 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Ironwood Atewood Cobblestone Lane Carver Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 2.5 MW PV and 1.5 MW/6.0 MWh battery facility in Carver, MA and interconnecting to the Tremont substation via the 3-81-950 23.0 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G62 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - NextGrid Scenic Highway Bourne Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.999 MW PV and 4.999 MW/31.0 MWh battery facility in Bourne, MA and interconnecting to the Valley substation via the 3-88-923 23.0 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G63 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - NextGrid Ernist Valeri Bourne Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.999 MW PV and 4.999 MW/48.4 MWh battery facility in Bourne, MA and interconnecting to the Valley substation via the 3-88-923 23.0 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G64 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Wareham Maple Spring Road Wareham Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.98 MW PV and 4.98 MW/9.78 MWh battery facility in Wareham, MA and interconnecting to the Wareham substation via the 3-82-82 23.0 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G65 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Wareham Charge Pond Road Wareham Solar and Battery P2 | Generator application from Eversource Energy (“ES”) for construction of a 4.89 MW PV and 3.75 MW/7.5 MWh battery facility in Wareham, MA and interconnecting to the Wareham substation via the 3-82-82 23.0 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G66 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Wankinco Federal Road Carver Solar | Generator application from Eversource Energy (“ES”) for construction of a 4.99 MW PV facility in Carver, MA and interconnecting to the Wareham substation via the 3-83-83 23.0 kV circuit. | 2022-01-01 | Approved | 2021-09-23
ES-21-G67 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Old Orchard Tihonet Road Wareham Solar | Generator application from Eversource Energy (“ES”) for construction of a 2.25 MW PV facility in Wareham, MA and interconnecting to the Wareham substation via the 3-83-83 23.0 kV circuit. | 2022-01-01 | Approved | 2021-09-23
ES-21-G68 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Frogfoot Tihonet Road Wareham Solar | Generator application from Eversource Energy (“ES”) for construction of a 4.5 MW PV facility in Wareham, MA and interconnecting to the Wareham substation via the 3-83-83 23.0 kV circuit. | 2022-01-01 | Approved | 2021-09-23
ES-21-G69 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - 140 Tihonet Road Wareham Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.995 MW PV and 4.995 MW/30.0 MWh battery facility in Wareham, MA and interconnecting to the Wareham substation via the 3-83-83 23.0 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G70 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - 150 Tihonet Road Wareham Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.99 MW PV and 4.99 MW/25.0 MWh battery facility in Wareham, MA and interconnecting to the Wareham substation via the 3-83-83 23.0 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G71 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Wareham PV Charge Pond Road Wareham Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 3.5 MW PV and 2.0 MW/4.0 MWh battery facility in Wareham, MA and interconnecting to the Wareham substation via the 3-83-83 23.0 kV circuit. | 2021-12-27 | Approved | 2021-09-23
ES-21-G72 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - 27 Charge Pond Road Wareham Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.99 MW PV and 4.99 MW/30.0 MWh battery facility in Wareham, MA and interconnecting to the Wareham substation via the 3-83-83 23.0 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G73 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Maple Springs Road Wareham Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.99 MW PV and 4.99 MW/26.0 MWh battery facility in Wareham, MA and interconnecting to the Wareham substation via the 3-84-84 23.0 kV circuit. | 2022-04-08 | Approved | 2021-09-23
ES-21-G74 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - 104 Tremont Street Carver Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.98 MW PV and 4.0 MW/8.48 MWh battery facility in Carver, MA and interconnecting to the West Pond substation via the 3-11-11 23.0 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G75 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project -Fuller Road Carver Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.999 MW PV and 4.999 MW/11.128 MWh battery facility in Carver, MA and interconnecting to the West Pond substation via the 3-10-10 23.0 kV circuit. | 2022-12-15 | Approved | 2021-09-23
ES-21-G76 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Grissom Road Plymouth Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 1.8 MW PV and 1.09 MW/2.0 MWh battery facility in Plymouth, MA and interconnecting to the West Pond substation via the 3-12-12 23.0 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G77 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Johnson Purchase Street Carver Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 2.468 MW PV and 2.0 MW/22.26 MWh battery facility in Carver, MA and interconnecting to the West Pond substation via the 3-10-930 23.0 kV circuit. | 2022-01-01 | Approved | 2021-09-23
ES-21-G78 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Ward Street Carver Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 3.0 MW PV and 3.0 MW/15.0 MWh battery facility in Carver, MA and interconnecting to the West Pond substation via the 3-10-930 23.0 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G79 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Plymouth Street Franklin Marsh Carver Solar | Generator application from Eversource Energy (“ES”) for construction of a 3.5 MW PV facility in Carver, MA and interconnecting to the West Pond substation via the 3-10-917 23.0 kV circuit. | 2022-01-01 | Approved | 2021-09-23
ES-21-G80 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - CVE Wrenham Road Carver Solar | Generator application from Eversource Energy (“ES”) for construction of a 1.625 MW PV facility in Carver, MA and interconnecting to the West Pond substation via the 3-10-929 23.0 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-G82 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Plymouth Street Carver Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 3.0 MW PV and 2.0 MW/4.24 MWh battery facility in Carver, MA and interconnecting to the West Pond substation via the 3-10-930 23.0 kV circuit. | 2022-12-15 | Approved | 2021-09-23
ES-21-G83 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - 230 Plymouth Street Carver Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 3.0 MW PV and 2.0 MW/4.24 MWh battery facility in Carver, MA and interconnecting to the West Pond substation via the 3-10-10 23.0 kV circuit. | 2022-12-15 | Approved | 2021-09-23
ES-21-G84 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Mendall Road Acushnet Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.995 MW PV and 3.3 MW/19.8 MWh battery facility in Acushnet, MA and interconnecting to the Wing Lane substation via the 2-241-241 13.2 kV circuit. | 2022-04-01 | Approved | 2021-09-23
ES-21-G85 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - TJA Clean Energy Main Street Acushnet Solar and Battery | Generator application from Eversource Energy (“ES”) for construction of a 4.99 MW PV and 3.75 MW/7.812 MWh battery facility in Acushnet, MA and interconnecting to the Wing Lane substation via the 2-241-241 13.2 kV circuit. | 2021-12-01 | Approved | 2021-09-23
ES-21-T51 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Reconductor the 191 Line | Transmission application from Eversource Energy (“ES”) to reconductor the 15.3 miles of the overhead 191 115 kV Line from between Auburn St. and Kingston will be reconductored with 954 ACSS. | 7/2025 | Approved | 2021-09-23
ES-21-T52 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - 153 Cable | Transmission application from Eversource Energy (“ES”) to install the new 4.6 mile 115 kV underground cable 153 between Bell Rock and Assonet and a 10 MVAr shunt reactor at the Bell Rock substation. | 7/2025 | Approved | 2021-09-23
ES-21-T53 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - 154 Cable | Transmission application from Eversource Energy (“ES”) to install the new 4.6 mile 115 kV underground cable 154 between Bell Rock and Assonet and a 10 MVAr shunt reactor at Bell Rock substation. | 7/2025 | Approved | 2021-09-23
ES-21-T54 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Assonet Station | Transmission application from Eversource Energy (“ES”) to construct a new 115/13.2 kV Assonet station with six-breaker ring configuration. | 7/2025 | Approved | 2021-09-23
ES-21-T55 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Assonet Station 1X | Transmission application from Eversource Energy (“ES”) to install a new 115/13.2 kV transformer #1 at the Assonet station. | 7/2025 | Approved | 2021-09-23
ES-21-T56 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Assonet Station 2X | Transmission application from Eversource Energy (“ES”) to Install a new 115/13.2 kV transformer #2 at the Assonet station. | 7/2025 | Approved | 2021-09-23
ES-21-T57 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Assonet Station 3X | Transmission application from Eversource Energy (“ES”) to install a new 115/13.2 kV transformer #3 at the Assonet station. | 7/2025 | Approved | 2021-09-23
ES-21-T58 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Industrial Park | Transmission application from Eversource Energy (“ES”) to construct a ring bus substation at the Industrial Park 115 kV station. | 1/2026 | Approved | 2021-09-23
ES-21-T59 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Industrial Park T1 | Transmission application from Eversource Energy (“ES”) to replace the 115/13.2 kV transformer T1 at the Industrial Park station. | 1/2026 | Approved | 2021-09-23
ES-21-T60 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Industrial Park T2 | Transmission application from Eversource Energy (“ES”) to replace the 115/13.2 kV transformer T2 at the Industrial Park station. | 1/2026 | Approved | 2021-09-23
ES-21-T61 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Industrial Park T3 | Transmission application from Eversource Energy (“ES”) to install a new 115/13.2 kV transformer T3 at the Industrial Park station. | 1/2026 | Approved | 2021-09-23
ES-21-T62 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Wareham Station | Transmission application from Eversource Energy (“ES”) to upgrade the Wareham substation to a six breaker 115 kV ring bus configuration. | 1/2026 | Approved | 2021-09-23
ES-21-T63 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Wareham Station T1 | Transmission application from Eversource Energy (“ES”) to replace the Wareham substation transformer #1 with a new 45/60/75 MVA 115/23 kV transformer. | 1/2026 | Approved | 2021-09-23
ES-21-T64 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Wareham Station T3 | Transmission application from Eversource Energy (“ES”) to install a new 45/60/75 MVA 115/23 kV transformer #3 at the Wareham substation. | 1/2026 | Approved | 2021-09-23
ES-21-T65 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - 132 Line | Transmission application from Eversource Energy (“ES”) to reconductor the existing 115-kV #132 circuit from Eversource’s Brook Street Station to Eversource’s West Pond Substation. | 1/2026 | Approved | 2021-09-23
ES-21-T66 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - West Pond Station | Transmission application from Eversource Energy (“ES”) to upgrade the West Pond substation to a six breaker ring bus configuration. | 1/2026 | Approved | 2021-09-23
ES-21-T67 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - West Pond Station T1 | Transmission application from Eversource Energy (“ES”) to replace the West Pond substation transformer #1 with a new 45/60/75 MVA 115/23 kV transformer. | 1/2026 | Approved | 2021-09-23
ES-21-T68 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - West Pond Station T2 | Transmission application from Eversource Energy (“ES”) to replace the West Pond substation transformer #2 with a new 45/60/75 MVA 115/23 kV transformer. | 1/2026 | Approved | 2021-09-23
ES-21-T69 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - West Pond Station T3 | Transmission application from Eversource Energy (“ES”) to replace the West Pond substation transformer #3 with a new 45/60/75 MVA 115/23 kV transformer. | 1/2026 | Approved | 2021-09-23
ES-21-T70 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Extend 112 Line | Transmission application from Eversource Energy (“ES”) to extend the 115kV Line 112 from Crystal Spring Junction to Crystal Spring station. The conductor design includes 3 miles of 795 ACSS. | 12/2024 | Approved | 2021-09-23
ES-21-T71 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Crystal Spring Station T1 | Transmission application from Eversource Energy (“ES”) to replace the Crystal Spring 646 transformer #1 with a 37/50/62.5 MVA 115/13.2 kV transformer. | 12/2024 | Approved | 2021-09-23
ES-21-T72 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Crystal Spring Station T2 | Transmission application from Eversource Energy (“ES”) to install a new 37/50/62.5 MVA 115/13.2 kV transformer at the Crystal Spring substation. | 12/2024 | Approved | 2021-09-23
ES-21-T73 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Tremont Station T1 | Transmission application from Eversource Energy (“ES”) to replace the Tremont substation transformer #1 with a new 45/60/75 MVA 115/23 kV transformer. | 1/2026 | Approved | 2021-09-23
ES-21-T74 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Tremont Station T2 | Transmission application from Eversource Energy (“ES”) to replace the Tremont substation transformer #2 with a new 45/60/75 MVA 115/23 kV transformer. | 1/2026 | Approved | 2021-09-23
ES-21-T75 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Tremont Station T3 | Transmission application from Eversource Energy (“ES”) to replace the Tremont substation transformer #3 with a new 45/60/75 MVA 115/23 kV transformer. | 1/2026 | Approved | 2021-09-23
ES-21-T76 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Rochester Station T1 | Transmission application from Eversource Energy (“ES”) to replace the Rochester substation transformer #1 with a new 37/50/62.5 MVA 115/13.2 kV transformer. | 12/2024 | Approved | 2021-09-23
ES-21-T77 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Rochester Station T2 | Transmission application from Eversource Energy (“ES”) to replace the Rochester substation transformer #2 with a new 37/50/62.5 MVA 115/13.2 kV transformer. | 12/2024 | Approved | 2021-09-23
ES-21-T78 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Wing Lane Station T1 | Transmission application from Eversource Energy (“ES”) to replace the Wing Lane substation transformer #1 with a new 37/50/62.5 MVA 115/13.2 kV transformer. | 12/2024 | Approved | 2021-09-23
ES-21-T79 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Wing Lane Station T2 | Transmission application from Eversource Energy (“ES”) to replace the Wing Lane substation transformer #2 with a new 37/50/62.5 MVA 115/13.2 kV transformer. | 12/2024 | Approved | 2021-09-23
ES-21-T80 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Fisher Road Station T1 | Transmission application from Eversource Energy (“ES”) to replace the Fisher Road substation transformer #1 with a new 37/50/62.5 MVA 115/13.2 kV transformer. | 7/2025 | Approved | 2021-09-23
ES-21-T81 | 2021-08-03 | Eversource Affescted System Operator (ASO) Study Interconnections in SEMA and Cape Cod Generation and Transmission Project - Fisher Road Station T2 | Transmission application from Eversource Energy (“ES”) to replace the Fisher Road substation transformer #2 with a new 37/50/62.5 MVA 115/13.2 kV transformer. | 7/2025 | Approved | 2021-09-23
ES-21-G106 | 2021-07-26 | Scitico Ellington Solar Project (QP 1033) | Generation application from Eversource Energy (“ES”) on behalf of Scitico Solar for the installation of a 6 MW PV facility in Ellington, CT and interconnecting to the Scitico Substation via the 27H9 23.0 kV circuit. | 2022-06-30 | Approved | 2021-09-03
GRH-21-X01 | 2021-08-03 | Harriman U1, U2, U3 Generator AVR Replacement Project | Transmission application from Great River Hydro (“GRH”) for the replacement of the existing 1990 vintage Westinghouse, Type MGR analog automatic voltage regulators (AVR) with new Basler Model DECS-250N AVR units on our Harriman Hydro Units 1-3 at Harriman Station, located in Readsboro, VT. The proposed in-service date for U1 AVR is TBD in 2022, for U2 AVR is TBD 2022, and U3 AVR is September 17, 2021. | U1 - TBD 2022 U2 - TBD 2022 U3 - 9/17/2021 | Approved | 2021-09-03
VPPSA-21-GNF01 | 2021-08-09 | ER Billings Road Hardwick Solar | Generator notification from Vermont Public Power Supply Authority on behalf of ER Billings Road Solar for the installation of a 1.62 MW solar PV in Hardwick, VT and interconnecting to the Berlin Substation via the 12.47 kV circuit. | 2021-09-15 | Notification | 2021-09-03
VPPSA-21-GNF02 | 2021-08-09 | ER Bone Hill East Roxbury Road Northfield Solar | Generator notification from Vermont Public Power Supply Authority on behalf of ER Bone Hill East Roxbury Road Northfield Solar for the installation of a 1.25 MW solar PV in Northfield, VT and interconnecting to the King Street Substation via the 54G4 12.47 kV circuit. | 2021-09-15 | Notification | 2021-09-03
ES-21-G98 | 2021-07-22 | Greenskies Miller Road East Windsor Solar | Generation notification from Eversource Energy (“ES”) on behalf of Greenskies for the installation of a 4.0 MW solar PV in East Windsor, CT and interconnecting to the Barbour Hill Substation via the 23J36 23 kV circuit. | 2022-09-01 | Notification | 2021-09-03
CMP-21-G23 | 2021-08-03 | MEVS Hanson Salmon Falls Road Hollis Solar | Generator notification from Central Maine Power Company (“CMP”) on behalf of MEVS Hanson for the installation of a 4.95 MW solar PV in Hollis, ME and interconnecting to the Bar Mills Substation via the 678D1 12.47 kV circuit. | 2022-08-31 | Notification | 2021-09-03
CMP-20-G110 Rev.1 | 2021-08-03 | BD Solar Sidney Fields Road Sidney Solar Rev.1 | Generator notification from Central Maine Power Company (“CMP”) on behalf of BD Solar Sidney for the installation of a 1.5 MW solar PV in Sidney, ME and interconnecting to the Sidney Substation via the 242D1 12.47 kV circuit. | 2021-12-31 | Notification | 2021-09-03
NEP-20-G05-002 Rev.1 | 2021-08-02 | Aquantum Solutions East Broadway Haverhill Solar and Battery Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Aquantum Solutions for the installation of a 2.75 MW solar PV and 1.265 MW/2.529 MWh battery in Haverhill, MA and interconnecting to the West Newbury Substation via the 47L1 13.2 kV circuit. | 2023-08-01 | Notification Withdrawn | 9/3/2021 11/19/2024
NEP-21-GNF11 | 2021-08-02 | Zero Point Development Ware Road Belchertown Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Zero Point Development for the installation of a 2.8 MW solar PV and 1.859 MW/3.718 MWh battery in Belchertown, MA and interconnecting to the Belchertown Substation via the 509L1 13.2 kV circuit. | 2023-08-01 | Notification | 2021-09-23
NEP-19-G30-003 Rev.2 | 2021-08-02 | Nexamp Barre Road Oakham Solar and Battery Rev.2 | Generator notification from New England Power Company ("NEP") on behalf of Nexamp for the installation of a 2.0 MW solar PV and 1.363 MW/2.726 MWh battery in Oakham, MA and interconnecting to the Barre Substation via the 604W2 13.8 kV circuit. | 2021-04-21 | Notification | 2021-09-23
ES-21-G107 | 2021-07-29 | Lawrence and Memorial Hospital Montauk New London Gas Generator | Generation notification from Eversource Energy (“ES”) on behalf of Lawrence and Memorial Hospital for the installation of a 1.838 MW gas generator in New London CT and interconnecting to the Williams Street Substation via the 9L06/9L07 13.2 kV circuit. | 2022-08-01 | Notification | 2021-09-03
ES-21-T84 | 2021-07-22 | Reconductor 282-520 and 282-521 115 kV Underground Cables | Reconductor the 282-520 and 282-521 cables between the Waltham and Electric Ave 115 kV stations. | 12/2023 | Notification | 2021-08-23
SENA-21-T01 | 2021-06-25 | Mayflower Wind HVDC ETU Transmission Project (QP 837) | Transmission application from Shell Energy North America (“SENA”) on behalf of Mayflower Wind for the installation of a 95 mile +/- 400 kV 1200 MW submarine HVDC transmission cable from the offshore HVDC converter station to the onshore HVDC converter station. | 8/2023 | Approved | 2021-07-15
SENA-21-T02 | 2021-06-25 | Mayflower Wind HVDC ETU Transmission Project (QP 837) | Transmission application from Shell Energy North America (“SENA”) on behalf of Mayflower Wind for the installation of a 2.6 mile 345 kV underground cable from the Brayton Point 345 kV substation to the onshore HVDC converter station. | 8/2023 | Approved | 2021-07-15
NEP-21-T08 | 2021-06-28 | Mayflower Wind HVDC ETU Transmission Project (QP 837) | Transmission application from New England Power Company (“NEP”) for the reconductor of the 1.5 mile overhead transmission 115 kV E-183E/F-184S Lines from Brayton Point Substation to Grand Army Substation in Somerset, MA using 1113 ACSR. Also upgrade the existing 183-1 and 183-2 switches with 3000 amp switches and existing 20T, 2084, an F184 breakers with 3000 amp SF6 breakers. | 8/2023 | Approved | 2021-07-15
NEP-21-T09 | 2021-06-28 | Mayflower Wind HVDC ETU Transmission Project (QP 837) | Transmission application from New England Power Company (“NEP”) to expand the Brayton Point Substation and install new 2-breaker bay for QP 837 interconnection. Install new 345 kV 32 MVAr oil filled shunt reactor and associated equipment. Also, install associated open-air equipment from interconnecting cable riser structure and new 345 kV reactor to GIS building. In addition, replace existing 30 and 30T 115 kV breakers with 4000A SF6 breakers. | 8/2023 | Approved | 2021-07-15
ES-21-T40 | 2021-06-23 | Eversource New Hampshire Transmission Lines Rebuild Project | Transmission application from Eversource Energy (“ES”) for the replacement of 18.09 miles of overhead transmission on the D142 115 kV Line with 1272 MCM ACSS conductor along with new structures between Whitefield Substation and the Lost Nation Substation in New Hampshire. | 12/2023 | Approved | 2021-07-15
ES-21-T41 | 2021-06-23 | Eversource New Hampshire Transmission Lines Rebuild Project | Transmission application from Eversource Energy (“ES”) for the replacement of 12.65 miles of overhead transmission on the O154 115 kV Line with 1272 MCM ACSS conductor along with new structures between the Lost Nation Substation and Paris Switching Station in New Hampshire. | 12/2023 | Approved | 2021-07-15
ES-21-T42 | 2021-06-23 | Eversource New Hampshire Transmission Lines Rebuild Project | Transmission application from Eversource Energy (“ES”) for the replacement of 13.87 miles of overhead transmission on the W179-1 115 kV Line and 1.46 miles of overhead transmission on the W179-2 115 kV Line with 1272 MCM ACSS conductor along with new structures between the Berlin Substation and the Pontook Tap, and between the Pontook Tap and the Paris Switching Station in New Hampshire. | 12/2023 | Approved | 2021-07-15
ES-21-T43 | 2021-06-23 | Eversource New Hampshire Transmission Lines Rebuild Project | Transmission application from Eversource Energy (“ES”) for the replacement of 3.39 miles of overhead transmission on the Z180 115 kV Line with 1272 MCM ACSS conductor along with new structures between the Beebe River Substation and Huckins Hill Switching Station in New Hampshire. | 12/2023 | Approved | 2021-07-15
ES-21-T44 | 2021-06-23 | Eversource New Hampshire Transmission Lines Rebuild Project | Transmission application from Eversource Energy (“ES”) for the replacement of 6.87 miles of overhead transmission on the E115-1 115 kV Line and 8.07 miles of overhead transmission on the E115-2 115 kV Line, and 0.53 miles of overhead transmission on the E115-3 115 kV Line with 1272 MCM ACSS conductor along with new structures between the Huckins Hill Switching Station and the Ashland Tap, and between the Ashland Tap and the Pemigewasset Substation, and between the Ashland Tap and the Ashland Substation in New Hampshire. | 12/2023 | Approved | 2021-07-15
ES-21-T45 | 2021-06-23 | Eversource New Hampshire Transmission Lines Rebuild Project | Transmission application from Eversource Energy (“ES”) for the replacement of 10.61 miles of overhead transmission on the A111 115 kV Line with 1272 MCM ACSS conductor along with new structures between the Pemigewasset Substation and Webster Substation in New Hampshire. | 12/2023 | Approved | 2021-07-15
CMP-21-G19 | 2021-06-28 | Walden Renewables Solar Generation and Transmission Project (QP 911) | Generator application from Central Maine Power Company (“CMP”) on behalf of Walden Renewables for the installation of fourteen 2.75 MW solar PV (35 MW total output) in Sweden, ME. | 2022-12-31 | Approved Withdrawn | 7/15/2021 7/5/2022
CMP-21-T05 | 2021-06-28 | Walden Renewables Solar Generation and Transmission Project (QP 911) | Transmission application from Central Maine Power Company (“CMP”) for the installation of a second 115/34.5 kV transformer equivalent to the existing 40/45/57 MVA 115/34.5 kV transformer in a new bay (straight bus configuration) at the Lovell Substation in Sweden, ME. | 2022-12-31 | Approved Withdrawn | 7/15/2021 7/5/2022
CMEEC-21-T01 | 2021-06-28 | New London Submarine Base Gas Generation | Generator application from Connecticut Municipal Electric Energy Cooperative (“CMEEC”) on behalf of the Groton Utilities for the installation of two 5.4 MW gas generators (10.8 MW total output) in Groton, CT and interconnecting to the SUBASE Substation via the M3N and M5N 33 kV circuits. | 2022-10-15 | Approved | 2021-07-15
ES-21-G86 | 2021-06-24 | Cape Cod Provincetown Battery Storage Project | Generator application from Eversource Energy (“ES”) for the installation of 24.9/-15 MW/38 MWh battery storage generator in Provincetown, MA and interconnecting to the Wellfleet Substation via the 96 23 kV circuit. | 2021-09-01 | Approved | 2021-07-15
NEP-18-G12 Rev.1 | 2021-06-25 | University Solar Victory Highway West Greenwich Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of University Solar for the installation of a 4.0 MW solar PV in West Greenwich, RI and interconnecting to the Kent County Substation via the 3311 34.5 kV circuit. Project is downsizing from 7.34 MWs to 4.0 MWs. | 2021-05-27 | Notification | 2021-07-15
BED-21-G01 | 2021-06-14 | South Forty Solar Sunset Cliff Road Burlington Solar | Generator notification from Burlington Electric Department ("BED") for the installation of a 2.5 MW solar PV in Burlington, VT and interconnecting to the McNeil Substation via the 1L113.8 kV circuit. | 2021-12-27 | Notification | 2021-07-15
ES-19-G88 Rev.1 | 2021-06-17 | Verogy East Road East Windsor Solar Rev.1 | Generation notification from Eversource Energy ("ES") on behalf of Verogy for the installation of a 4.975 MW solar PV in East Windsor, CT and interconnecting to the Barbour Hill 23J Substation via the 23J36 23 kV circuit. | 2021-09-15 | Notification | 2021-07-15
CMP-21-G20 | 2021-06-28 | NextGrid Franklin Road Jay Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of NextGrid for the installation of a 4.2 MW solar PV in Jay, ME and interconnecting to the Livermore Falls Substation via the 428D1 12.47 kV circuit. | 2021-12-31 | Notification | 2021-07-15
CMP-21-G22 | 2021-06-28 | Odiorne Lane Eliot Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of Odiorne Lane Solar for the installtion of a 4.999 MW solar PV in Eliot, ME and interconnecting to the Eliot Substation via the 687D1 12.47 kV circuit. | 2021-09-30 | Notification | 2021-07-15
NEP-21-GNF12 | 2021-06-25 | NextGrid Washington Street Wrentham Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of NextGrid for the installation of a 2.738 MW solar PV and 2.0 MW/6.0 MWh battery in Wrentham, MA and interconnecting to the Crocker Pond Substation via the 3424W1 13.8 kV circuit. | 2022-10-01 | Notification | 2021-07-15
NEP-21-GNF13 | 2021-06-25 | Western Mass Cluster Study Part 2 - Amp Solar Development Leverett Road Shutesbury Solar and Battery 1 | Generator notification from New England Power Company ("NEP") on behalf of Amp Solar Development for the installation of a 2.0 MW solar PV and 2.0 MW/5.04 MWh battery in Shutesbury, MA and interconnecting to the Shutesbury Substation via the 704W1 13.8 kV circuit. | 2022-10-01 | Notification | 2021-07-15
NEP-20-G03-069 Rev.1 | 2021-06-25 | Western Mass Cluster Study Part 2 - Amp Solar Development Pratt Corner Road Shutesbury Solar and Battery 2 Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Amp Solar Development for the installation of a 2.998 MW solar PV and 3.0 MW/10.08 MWh battery in Shutesbury, MA and interconnecting to the Shutesbury Substation via the 704W1 13.8 kV circuit. Project is downsizing from 4.998 MWs to 2.998 MWs. | 2022-10-01 | Notification | 2021-07-15
NEP-20-G03-070 Rev.1 | 2021-06-25 | Western Mass Cluster Study Part 2 - Amp Solar Development Pratt Corner Road Shutesbury Solar and Battery 3 Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Amp Solar Development for the installation of a 4.998 MW solar PV and 9.0 MW/40.32 MWh battery in Shutesbury, MA and interconnecting to the Shutesbury Substation via the 704W1 13.8 kV circuit. Project is revised to reflect new interconnection feeder. | 2022-10-01 | Notification | 2021-07-15
FGE-21-G01 | 2021-06-07 | Northeast Solar Development Alpine Road Fitchburg Solar and Battery | Generator notification from Fitchburg Gas and Electric ("FGE") on behlaf of Northeast Solar Development for the installation of a 2.738 MW solar PV and 2.7 MW battery in Fitchburg, MA and interconnecting to the Flagg Pond Substation via the 22W10 13.8 kV circuit. | 2022-06-01 | Notification | 2021-07-15
FGE-21-G02 | 2021-06-07 | Northeast Solar Development Oak Hill Road Fitchburg Solar and Battery | Generator notification from Fitchburg Gas and Electric ("FGE") on behlaf of Northeast Solar Development for the installation of a 2.738 MW solar PV and 2.7 MW battery in Fitchburg, MA and interconnecting to the Flagg Pond Substation via the 22W10 13.8 kV circuit. | 2022-06-01 | Notification Withdrawn | 7/15/2021 10/18/2022
CMP-21-G21 | 2021-06-28 | Dixfield Solar Wilton Road Dixfield Solar and Battery | Generator notification from Central Maine Power Company ("CMP") on behalf of Dixfield Solar for the installation of a 2.5 MW solar PV and 2.0 MW/8 MWh battery in Dixfield, ME and interconnecting to the Ludden Lane Substation via the 461D1 34.5 kV circuit. | 2021-12-01 | Notification | 2021-07-15
NEP-21-T07 | 2021-06-21 | C-203 and D-204 230 kV Line Reconductoring | Transmission notification from New England Power Company ("NEP") to reconductor 0.2 miles of overhead transmission of the C-203 and C-204 230 kV Lines between Moore Substation and Littleton Tap due to asset conditions. | 12/2021 | Notification | 2021-07-15
ES-21-T48 | 2021-06-22 | Partial Rebuild of the 690 115 kV Line | Transmission notification from Eversource Energy ("ES") for a partial rebuild of 1.75 miles of overhead transmission on the 690 115 kV Line to replace existing structures and associated copper conductor with 556 kcmil ACSS conductor from Salisbury Substation to the CT/NY border. | 2021-12-17 | Notification | 2021-07-15
UI-21-T01 | 2021-06-22 | 115 kV Pequonnock Substation Rebuild Topology Change | Transmission notification from United Illuminating ("UI") to reorder the line/transformer terminations. In addition, the numbering scheme for the breakers has been changed to start at 11T as part of constructability benefits. | 9/2024 | Notification | 2021-07-15
VP-21-G24 | 2021-06-03 | Downeast Wind Generation and Transmission Project (QP 760) | Generation application from Versant Power ("VP") on behalf of Downeast Wind, to install thirty 4.2 MW (126 MWs total output) wind turbines in Columbia, Maine. | 2023-12-20 | Approved | 2021-07-01
VP-21-T01 | 2021-06-03 | Downeast Wind Generation and Transmission Project (QP 760) | Transmission application from Versant Power (“VP”) for the construction of a new switching station in L52 between Deblois and Epping that will break the 115kV Line 52 approximately 4.03 miles west of Epping with a three breaker ring bus to accommodate the new interconnection for the QP760 wind project. | 2023-09-01 | Approved | 2021-07-01
VP-21-T02 | 2021-06-03 | Downeast Wind Generation and Transmission Project (QP 760) | Transmission application from Versant Power (“VP”) to reconductor 3.23 miles of the existing 115 kV 59 Line between the Epping Switching Station and the Columbia Tap with 795 ACSR to match the rest of the Downeast Loop and meet project thermal requirements | 2023-09-01 | Approved | 2021-07-01
VP-21-T03 | 2021-06-03 | Downeast Wind Generation and Transmission Project (QP 760) | Transmission application from Versant Power (“VP”) to install a 150 MVA STATCOM between the T1 transformer and 59 Line at the Tunk Lake substation in support of QP 760. | 2023-09-01 | Approved | 2021-07-01
VP-21-T04 | 2021-06-03 | Downeast Wind Generation and Transmission Project (QP 760) | Transmission application from Versant Power (“VP”) to construct a new Downeast Wind Collector Substation with a 13.8/34.5/115 kV 80/106/133 MVA transformer and install four 34.5 breakers and a 40 MVA synchronous condenser. | 2023-09-01 | Approved | 2021-07-01
ES-21-T25 | 2021-06-01 | Eastern Connecticut 2029 Transmission Reliability Project | Transmission application from Eversource Energy ("ES") to convert Line 100 (Gales Ferry to Montville) to 115 kV and rebuild with 1272 MCM ACSS (1.1 miles) and 1590 MCM ACSS (0.9 miles) conductors. | 6/2024 | Approved | 2021-06-17
ES-21-T26 | 2021-06-01 | Eastern Connecticut 2029 Transmission Reliability Project | Transmission application from Eversource Energy ("ES") to re-terminate Line 100 (into the Montville 115 kV bus between the new 4T and 5T circuit breakers. | 6/2024 | Approved | 2021-06-17
ES-21-T27 | 2021-06-01 | Eastern Connecticut 2029 Transmission Reliability Project | Transmission application from Eversource Energy ("ES") to convert Line 400-1 (Tunnel to Ledyard Junction) to 115 kV and rebuild with 1272 ACSS (8.6 miles) conductors. | 6/2024 | Approved | 2021-06-17
ES-21-T28 | 2021-06-01 | Eastern Connecticut 2029 Transmission Reliability Project | Transmission application from Eversource Energy ("ES") to add one 115 kV circuit breaker and re-terminate the 400-1 Line section into the Tunnel 115 kV bus. | 6/2024 | Approved | 2021-06-17
ES-21-T29 | 2021-06-01 | Eastern Connecticut 2029 Transmission Reliability Project | Transmission application from Eversource Energy ("ES") to convert Line 400-2 (Ledyard Junction to CMEEC Border Bus) to 115 kV with the existing 556 ACSR conductor (2.94 miles). | 6/2024 | Approved | 2021-06-17
ES-21-T30 | 2021-06-01 | Eastern Connecticut 2029 Transmission Reliability Project | Transmission application from Eversource Energy ("ES") to convert Line 400-3 (Gales Ferry to Ledyard Junction) to 115 kV and rebuild with 1272 ACSS (1.61 miles) conductors. | 6/2024 | Approved | 2021-06-17
ES-21-T31 | 2021-06-01 | Eastern Connecticut 2029 Transmission Reliability Project | Transmission application from Eversource Energy ("ES") to install a 345/115 kV autotransformer 4X and control enclosure at the Card substation. | 6/2024 | Approved | 2021-06-17
ES-21-T32 | 2021-06-01 | Eastern Connecticut 2029 Transmission Reliability Project | Transmission application from Eversource Energy ("ES") to install one 115 kV series circuit breaker 14TA at the Card substation. | 6/2024 | Approved | 2021-06-17
ES-21-T33 | 2021-06-01 | Eastern Connecticut 2029 Transmission Reliability Project | Transmission application from Eversource Energy ("ES") to convert the Gales Ferry substation to 115 kV (distribution). | 6/2024 | Approved | 2021-06-17
ES-21-T34 | 2021-06-01 | Eastern Connecticut 2029 Transmission Reliability Project | Transmission application from Eversource Energy ("ES") to convert the Gales Ferry substation to 115 kV (transmission) and re-terminate the 100 Line. | 6/2024 | Approved | 2021-06-17
ES-21-T35 | 2021-06-01 | Eastern Connecticut 2029 Transmission Reliability Project | Transmission application from Eversource Energy ("ES") to install a 25.2 MVAR capacitor bank and one capacitor breaker at the Killingly 115 kV A1 bus. | 6/2024 | Approved | 2021-06-17
ES-21-T36 | 2021-06-01 | Eastern Connecticut 2029 Transmission Reliability Project | Transmission application from Eversource Energy ("ES") to install a 345 kV series circuit breaker 1TA in series with Montville 345 kV breaker 1T. | 6/2024 | Approved | 2021-06-17
ES-21-T37 | 2021-06-01 | Eastern Connecticut 2029 Transmission Reliability Project | Transmission application from Eversource Energy ("ES") to install a 115 kV series reactor on the 1465 Line terminal at Mystic with a bypass switch normally open. | 6/2024 | Approved | 2021-06-17
ES-21-T38 | 2021-06-01 | Eastern Connecticut 2029 Transmission Reliability Project | Transmission application from Eversource Energy ("ES") to install one +50/-25 MVAR synchronous condenser at Shunock and expand the Shunock from a straight bus to a ring bus. | 6/2024 | Approved | 2021-06-17
ES-21-T39 | 2021-06-01 | Eastern Connecticut 2029 Transmission Reliability Project | Transmission application from Eversource Energy ("ES") to upgrade the Card substation to Bulk Power System (BPS) standard. | 6/2024 | Approved | 2021-06-17
NEP-21-T05 | 2021-05-28 | Eastern Connecticut 2029 Transmission Reliability Project | Transmission application from New England Power Company ("NEP") to reconductor the 115 L190-4 Line from West Kingston substation to Tower Hill substation to 795 MCM ACSS. Also reconductor the 115 L190-5 Line from Tower Hill substation to Davisville Tap to 795 MCM ACSS. | 10/2025 | Approved | 2021-06-17
CMEEC-21-T01 | 2021-05-28 | Eastern Connecticut 2029 Transmission Reliability Project | Transmission application from Connecticut Municipal Electric Energy Co-Op. ("CMEEC") to add one 115-kV circuit breaker and re-terminate the 400 Line from Buddington CMEEC/ES border into the Buddington115-kV bus (CMEEC Project) and reconnecting the Buddington 1X transformer to 115 kV. | 6/2024 | Approved | 2021-06-17
CMEEC-21-T02 | 2021-05-28 | Eastern Connecticut 2029 Transmission Reliability Project | Transmission application from Connecticut Municipal Electric Energy Co-Op. ("CMEEC") to convert 400 Line (Buddington to CMEEC/ES Border) to 115 kV. | 6/2024 | Approved | 2021-06-17
AGIH-21-G01 | 2021-06-01 | Ballston Battery Energy Storage Generation and Transmission Project (QP 984) | Generation application from Able Grid Infrastructure Holdings (“AGIH”) for the construction of a 152.16 MW/300 MWh battery storage facility in Billerica, MA. | 2023-09-30 | Approved | 2021-07-01
AGIH-21-T01 | 2021-06-01 | Ballston Battery Energy Storage Generation and Transmission Project (QP 984) | Transmission application from Able Grid Infrastructure Holdings (“AGIH”) for the construction of a new 115/34.5/13.8 kV transformer at the new four breaker ring bus in Billerica, MA. | 2023-05-31 | Approved | 2021-07-01
NEP-21-T06 | 2021-06-01 | Ballston Battery Energy Storage Generation and Transmission Project (QP 984) | Transmission application from New England Power Company (“NEP”) for the construction of a new four breaker ring bus substation in Billerica, MA and a two mile 115 kV line to interconnect the Ballston Battery project. | 2023-09-20 | Approved | 2021-07-01
EIP-21-G01 | 2021-05-21 | NB Fuel Cell Generation and Transmission Project (QP 939) | Generation application from EIP Investment (“EIP”) for the construction of a 20.24 MW fuel cell generation project in New Britain, CT. | 2022-09-01 | Approved | 2021-07-01
ES-21-T46 | 2021-05-29 | NB Fuel Cell Generation and Transmission Project (QP 939) | Transmission application from Eversource Energy (“ES”) to upgrade the 115/69 kV autotransformer at the Black Rock 11H Substation in support of the NB Fuel Cell Project. | 2022-08-01 | Approved | 2021-07-01
NRG-21-G01 | 2021-05-26 | Middletown 5 Generation Repowering and Transmission Project (QP 894) | Generation application from NRG Power Marketing (“NRG”) to interconnect a new 378 MW combustion turbine generation facility at the existing Middletown 5A Station in Middletown, CT. This is being considered as a repowering of the Middletown Units 2 and 3. | 2025-05-31 | Approved Withdrawn | 7/1/2021 12/02/2021
NRG-21-T01 | 2021-05-26 | Middletown 5 Generation Repowering and Transmission Project (QP 894) | Transmission application from NRG Power Marketing (“NRG”) to install a 308/410/512 MVA 115/26 kV generator step-up (GSU) transformer and generator lead from the Middletown 5 GSU to the Middletown 115 kV Substation Bus B between breakers 5T and 7T. | 2024-10-01 | Approved Withdrawn | 7/1/2021 12/02/2021
ES-21-T22 | 2021-05-07 | Middletown 5 Generation Repowering and Transmission Project (QP 894) | Transmission application from Eversource Energy (“ES”) to upgrade the 1766 Line from Dooley to West Side to increase the summer LTE rating from 177 MVA to a minimum of 181 MVA. | 2024-03-01 | Approved Withdrawn | 7/1/2021 12/02/2021
ES-21-T23 | 2021-05-07 | Middletown 5 Generation Repowering and Transmission Project (QP 894) | Transmission application from Eversource Energy (“ES”) to upgrade the 1443 Line from Middletown to Portland to increase the summer LTE rating from 223 MVA to a minimum of 230 MVA. | 2024-03-01 | Approved Withdrawn | 7/1/2021 12/02/2021
ES-21-T24 | 2021-05-07 | Middletown 5 Generation Repowering and Transmission Project (QP 894) | Transmission application from Eversource Energy (“ES”) to upgrade the Middletown 5A Station Bus A to increase the summer LTE rating from 325 MVA to a minimum of 399 MVA. | 2024-03-01 | Approved Withdrawn | 7/1/2021 12/02/2021
ES-21-G169 Rev.2 | 2021-05-31 | Gravel Pit Solar III Generation Project Rev.2 (QP 1030) | Generation application from Eversource Energy (ES) on behalf of Gravel Pit Solar for a 45 MW increase in output power to 120 MWs in East Windsor, CT and interconnecting to the 115 kV Line between the Barbour Hill 23J Substation and the Windsor Locks 14K Substation. | 2022-11-01 | Approved | 2021-07-01
ES-18-G33 Rev.1 | 2021-05-27 | Ameresco Candlewood Mountain Road New Milford Solar Rev.1 | Generator notification from Eversource Energy ("ES") on behalf of Ameresco for the installation of 3.984 MW solar PV in New Milford, CT and interconnecting to the Rocky River 12Y Substation via the 12Y9 1540 13.8 kV circuit. | 2022-07-01 | Notification | 2021-07-01
NEP-21-GNF08 | 2021-05-28 | SunPower Milestone Road Nantucket Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of SunPower for the installation of a 2.85 MW solar PV and 1.287 MW/2.529 MWh battery (3.4 MW max net injection) in Nantucket, MA and interconnecting to the Candle Street Substation via the 101L7 13.2 kV circuit. | 2022-08-01 | Notification Withdrawn | 7/1/2021 6/18/2024
NEP-21-GNF10 | 2021-05-28 | Ecogy Solar Radcliff Road Tewksbury Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Ecogy Solar for the installation of a 1.238 MW solar PV and 0.305 MW/1.22 MWh battery in Tewksbury, MA and interconnecting to the Tewksbury Substation via the 20L1 13.2 kV circuit. | 2022-09-01 | Notification Withdrawn | 7/1/2021 9/19/2023
ES-21-T47 | 2021-05-28 | Partial Rebuild of 115 kV 1588 Line | Transmission notification from Eversource Energy ("ES") for the partial rebuild of 2.6 miles of the 115 kV 1588 Line from Colony Substation to North Wallingford Substation to replace existing structures and associated 4/0 copper conductor with 1272-kcmil ACSS conductor. | 2021-12-31 | Notification | 2021-06-17
UI-21-X0 | 2021-05-19 | Retirement of the Bridgeport Harbor #3 Runback SPS/RAS #25 | Transmission notification from United Illuminating ("UI") for the retirement of the Bridgeport Harbor #3 Runback SPS/RAS #25 due to the retirement of the Bridgeport Harbor 3 generator effective June 1, 2021. | 2021-12-31 | Notification | 2021-06-17
CMP-21-T04 | 2021-06-01 | Replacement of T1 Transformer at Spring Street Substation | Transmission notification from Central Maine Power Company ("CMP") for the replacement of 115/37 kV 25/42 MVA transformer T1 at Spring St 115/34.5 kV substation with an AVANGRID standard 120/36 kV 30/50 MVA transformer due to poor asset condition of the existing transformer. | 2021-03-31 | Notification | 2021-06-17
ES-21-T15 | 2021-05-03 | Boston Area Optimized Solution (BAOS) Transmission Project | Transmission application from Eversource Energy (“ES”) for the installation of a 11.9 ohm series reactor with a bypass breaker on Line 346 at the North Cambridge Substation. | 6/2023 | Approved | 2021-05-21
ES-21-T16 | 2021-05-03 | Boston Area Optimized Solution (BAOS) Transmission Project | Transmission application from Eversource Energy (“ES”) for the installation of a 11.9 ohm series reactor with a bypass breaker on Line 365 at the North Cambridge Substation. | 6/2023 | Approved | 2021-05-21
NEP-21-T03 | 2021-04-30 | Boston Area Optimized Solution (BAOS) Transmission Project | Transmission application from New England Power Company (“NEP”) for the installation of a 345 kV, +/- 167 MVAr Static Synchronous Compensator (STATCOM) at the Tewksbury 22A substation. In addition, a new bay will be added at the substation with two new 345 kV breakers and four disconnect switches and installing a 150 MVA 345/38.4 kV transformer. | 10/2023 | Approved | 2021-05-21
NEP-21-X01 | 2021-04-30 | Boston Area Optimized Solution (BAOS) Transmission Project | Transmission application from New England Power Company (“NEP”) for the installation of a Direct Transfer Trip (DTT) automatic control scheme to open the 345 kV 2T345 breaker at West Amesbury when both the 394 and 4T-94 breakers at Ward Hill are open or when the 394-3 Line switch at Ward Hill is open. This will mitigate the 394 line-end open contingency at Ward Hill. | 1/2023 | Approved | 2021-05-21
VP-21-G01 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - BD Solar Brewer Lambert Road Brewer Solar | Generation application from Versant Power (“VP”) on behalf of BD Solar Brewer for the installation of a 4.99 MW solar array in Brewer, ME and interconnecting to the Graham substation via the 12.5 kV EA4 feeder. | 2021-03-31 | Approved | 2021-06-01
VP-21-G02 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - HEP Energy USA Airline Road Clifton Solar | Generation application from Versant Power (“VP”) on behalf of HEP Energy USA for the installation of a 4.875 MW solar array in Clifton, ME and interconnecting to the Graham substation via the 12.5 kV GS1 feeder. | 2021-03-31 | Approved | 2021-06-01
VP-21-G03 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - Dynamic Energy Solutions Broadway Glenburn Solar | Generation application from Versant Power (“VP”) on behalf of Dynamic Energy Solutions for the installation of a 4.999 MW solar array in Glenburn, ME and interconnecting to the Graham substation via the 12.5 kV EB3 feeder. | 2020-12-31 | Approved | 2021-06-01
VP-21-G04 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - CEB Development A Gilman Road Bangor Solar | Generation application from Versant Power (“VP”) on behalf of CEB Development A for the installation of a 4.875 MW solar array in Bangor, ME and interconnecting to the Graham substation via the 12.5 kV HR3 feeder. | 2021-05-01 | Approved | 2021-06-01
VP-21-G05 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - CEB Development B Gilman Road Bangor Solar | Generation application from Versant Power (“VP”) on behalf of CEB Development A for the installation of a 4.875 MW solar array in Bangor, ME and interconnecting to the Graham substation via the 12.5 kV HR3 feeder. | 2021-05-01 | Approved | 2021-06-01
VP-21-G06 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - Dynamic Energy Solutions Mills Road Exeter Solar | Generation application from Versant Power (“VP”) on behalf of Dynamic Energy Solutions for the installation of a 4.0 MW solar array in Exeter, ME and interconnecting to the Graham substation via the 13.2 kV EC3 feeder. | 2020-12-31 | Approved | 2021-06-01
VP-21-G07 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - Dynamic Energy Solutions Hammett Road Enfield Solar | Generation application from Versant Power (“VP”) on behalf of Dynamic Energy Solutions for the installation of a 4.999 MW solar array in Enfield, ME and interconnecting to the Chester substation via the 12.5 kV EN1 feeder. | 2020-12-31 | Approved | 2021-06-01
VP-21-G08 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - Sunraise Mariaville West Mariaville Road Ellsworth Solar | Generation application from Versant Power (“VP”) on behalf of Sunraise Mariaville West for the installation of a 1.625 MW solar array in Ellsworth, ME and interconnecting to the Ellsworth Falls substation via the 12.5 kV ML3 feeder. | 2020-11-30 | Approved | 2021-06-01
VP-21-G09 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - CEB Development A Bedford Farm Road Lincoln Solar | Generation application from Versant Power (“VP”) on behalf of CEB Development A for the installation of a 4.875 MW solar array in Lincoln, ME and interconnecting to the Chester substation via the 12.5 kV LC2 feeder. | 2021-05-01 | Approved | 2021-06-01
VP-21-G10 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - CEB Development B Bedford Farm Road Lincoln Solar | Generation application from Versant Power (“VP”) on behalf of CEB Development A for the installation of a 2.0 MW solar array in Lincoln, ME and interconnecting to the Chester substation via the 12.5 kV LC2 feeder. | 2021-05-01 | Approved | 2021-06-01
VP-21-G11 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - CEB Development B Hog Bay Road Franklin Solar | Generation application from Versant Power (“VP”) on behalf of CEB Development B for the installation of a 4.995 MW solar array in Franklin, ME and interconnecting to the Ellsworth Falls substation via the 12.5 kV FR1 feeder. | 2021-10-01 | Approved | 2021-06-01
VP-21-G12 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - Revision Energy Route 193 Deblois Solar | Generation application from Versant Power (“VP”) on behalf of Revision Energy for the installation of a 4.95 MW solar array in Deblois, ME and interconnecting to the Deblois substation via the 34.5 kV DB1 feeder. | 2021-09-30 | Approved | 2021-06-01
VP-21-G13 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - CEB Development A Bucksport Road Ellsworth Solar | Generation application from Versant Power (“VP”) on behalf of CEB Development A for the installation of a 4.875 MW solar array in Ellsworth, ME and interconnecting to the Ellsworth Falls substation via the 34.5 kV EH4 feeder. | 2021-05-01 | Approved | 2021-06-01
VP-21-G14 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - CEB Development A Cards Crossing Road Franklin Solar | Generation application from Versant Power (“VP”) on behalf of CEB Development A for the installation of a 2.5 MW solar array in Franklin, ME and interconnecting to the Ellsworth Falls substation via the 12.5 kV FR1 feeder. | 2021-05-01 | Approved | 2021-06-01
VP-21-G15 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - SRE Solar Origination Northfield Road Marshfield Solar | Generation application from Versant Power (“VP”) on behalf of SRE Solar Origination for the installation of a 2.0 MW solar array in Marshfield, ME and interconnecting to the Washington County substation via the 12.5 kV SH2 feeder. | 2020-12-31 | Approved | 2021-06-01
VP-21-G16 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - Renewable Energy Development Bar Harbor Road Trenton Solar | Generation application from Versant Power (“VP”) on behalf of Renewable Energy Development for the installation of a 4.975 MW solar array in Trenton, ME and interconnecting to the Ellsworth Falls substation via the 34.5 kV L28 feeder. | 2020-09-30 | Approved | 2021-06-01
VP-21-G17 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - 510 PV Project Development Hog Bay Road Franklin Solar | Generation application from Versant Power (“VP”) on behalf of 510 PV Project Development for the installation of a 2.0 MW solar array in Franklin, ME and interconnecting to the Ellsworth Falls substation via the 12.5 kV FR2 feeder. | 2021-05-01 | Approved | 2021-06-01
VP-21-G18 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - CEB Development A South Chester Road Chester Solar | Generation application from Versant Power (“VP”) on behalf of CEB Development A for the installation of a 4.975 MW solar array in Chester, ME and interconnecting to the Chester substation via the 12.5 kV KB1 feeder. | 2021-05-01 | Approved | 2021-06-01
VP-21-G19 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - | Generation application from Versant Power (“VP”) on behalf of SRE Solar Origination for the installation of a 2.0 MW solar array in Bangor, ME and interconnecting to the Graham substation via the 12.5 kV BA3 feeder. | 2020-12-31 | Approved | 2021-06-01
VP-21-G20 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - Gateway Solar Medway Road Medway Solar | Generation application from Versant Power (“VP”) on behalf of Gateway Solar for the installation of a 4.0 MW solar array in Medway, ME and interconnecting to the Chester substation via the 12.5 kV EK2 feeder. | 2021-05-01 | Approved | 2021-06-01
VP-21-G21 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - Melink Milo Solar West Main Road Milo Solar | Generation application from Versant Power (“VP”) on behalf of Melink Milo Solar for the installation of a 1.992 MW solar array in Milo, ME and interconnecting to the Chester substation via the 13.2 kV MI2 feeder. | 2021-04-01 | Approved | 2021-06-01
VP-21-G22 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - Melink Holden Solar Main Road Holden Solar | Generation application from Versant Power (“VP”) on behalf of Melink Holden Solar for the installation of a 2.375 MW solar array in Holden, ME and interconnecting to the Graham substation via the 12.5 kV LU2 feeder. | 2021-07-01 | Approved | 2021-06-01
VP-21-G23 | 2021-04-30 | Versant Power Distributed Generation Cluster Project - CEB Development C Route 200 Franklin Solar | Generation application from Versant Power (“VP”) on behalf of CEB Development C for the installation of a 1.5 MW solar array in Franklin, ME and interconnecting to the Ellsworth Falls substation via the 12.5 kV FR1 feeder. | 2022-05-01 | Approved | 2021-06-01
CMP-21-T02 | 2021-05-04 | Bowman Street Substation | Transmission application from Central Maine Power Company (“CMP”) to reconfigure the Bowman Street substation to install a 115 kV bus-tie breaker and install a third 115/34.5 kV 20/37 MVA transformer. | 2021-05-31 | Approved | 2021-05-20
UI-21-G03 | 2021-05-11 | CP NB Solar I Forest Road Northford Solar | Generator notification from United Illuminating ("UI") on behalf of CP NB Solar I for the installation of a 2.0 MW solar PV in Northford, CT and interconnecting to the Quinnipac Substation via the 1540 13.8 kV circuit. | 2021-12-31 | Notification | 2021-06-01
CMP-21-15 | 2021-05-04 | ER Pleasant Street Pleasant Street Wilton Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of ER Pleasant Street Solar for the instalaltion of a 3.0 MW solar PV in Wilton, ME and interconnecting to the East Wilton Substation via the 816D1 12.47 kV circuit. | 2021-09-30 | Notification | 2021-06-01
CMP-21-16 | 2021-05-04 | Solar Provider Group Glenn Harris Road New Sharon Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of Solar Provider Group for the installation fo a 3.60 MW solar PV in New Sharon, ME and interconnecting to the Farmington Falls Substation via the 818D1 34.5 kV circuit. | 2021-09-30 | Notification | 2021-06-01
NEP-19-G21 Rev.1 | 2021-05-03 | Green Development Iron Mine Hill Road 1 North Smithfield Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Green Development for the installation of a 9.6 MW solar PV in North Smithfield, RI and interconnecting to the proposed Iron Mine Hill Substation via the 34.5 kV circuit. | 2021-12-15 | Notification | 2021-06-01
NEP-19-G22 Rev.1 | 2021-05-03 | Green Development Iron Mine Hill Road 2 North Smithfield Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Green Development for the installation of a 9.6 MW solar PV in North Smithfield, RI and interconnecting to the proposed Iron Mine Hill Substation via the 34.5 kV circuit. | 2021-12-15 | Notification | 2021-06-01
NEP-19-G23 Rev.1 | 2021-05-03 | Green Development Iron Mine Hill Road 3 North Smithfield Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Green Development for the installation of a 9.6 MW solar PV in North Smithfield, RI and interconnecting to the proposed Iron Mine Hill Substation via the 34.5 kV circuit. | 2021-12-15 | Notification | 2021-06-01
NEP-19-G24 Rev.1 | 2021-05-03 | Green Development Iron Mine Hill Road 4 North Smithfield Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Green Development for the installation of a 9.6 MW solar PV in North Smithfield, RI and interconnecting to the proposed Iron Mine Hill Substation via the 34.5 kV circuit. | 2021-12-15 | Notification | 2021-06-01
NEP-20-G03-113 Rev.1 | 2021-05-03 | Nexamp Union Road Wales Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Nexamp for the installation of a 2.0 MW solar PV in Wales, MA and interconnecting to the Little Rest Road Substation via the 516L5 13.2 kV circuit. Application revised to correct bus number. | 2020-11-09 | Notification | 2021-06-01
UI-21-G02 | 2021-05-10 | 2019 ESA Project Company Crescent Street New Haven Fuel Cell and Solar | Generator notification from United Illuminating ("UI") on behalf of 2019 ESA Project Company for the installation of a 1.35 MW fuel cell and 2.31 solar PV in New Haven, CT and interconnecting to the Broadway Substation via the 1906 13.8 kV circuit. | 2021-06-01 | Notification | 2021-06-01
ES-21-T19 | 2021-04-21 | West Roxbury Station Transformer Replacement | Transmission notification from Eversource Energy ("ES") to replace the existing 90 MVA load-service transformer 110B at the West Roxbury Station with a new 110/24 kV unit due to unit failure. | 2021-03-30 | Notification | 2021-05-20
CMP-21-T03 | 2021-05-04 | Ludden Lane Substation Transformer and Circuit Breaker Addition | Transmission notification from Central Maine Power ("CMP") to reconfigure the Ludden Lane Substation to install a 115/34.5 kV 12/22 MVA transformer with a fourth 115 kV ring-bus circuit breaker. | 2021-02-26 | Notification | 2021-05-20
ESR-21-G02 | 2021-04-01 | Cross Town Energy Battery Energy Storage System Generation (QP 874) | Generation application from Energy Storage Resources ("ESR") for the installation of a 175 MW/350 MWh battery energy storage plant in Gorham, ME. The project will interconnect to the 115 kV Moshers Substation. There will also be transmission work associated with this project. | 2023-04-01 | Approved | 2021-04-16
ESR-21-T02 | 2021-04-01 | Cross Town Energy Battery Energy Storage System Generation (QP 874) | Transmission application from Energy Storage Resources ("ESR") for the construction of a new 115/34.5 12.8 kV Transformer at the Moshers 115 kV Substation along with a 0.15 generation lead from the generation project to the substation. | 2022-12-01 | Approved | 2021-04-16
CMP-21-T01 | 2021-04-01 | Cross Town Energy Battery Energy Storage System Generation (QP 874) | Transmission application from Central Maine Power ("CMP") for the installation of one 115 kV breaker at the Moshers Substation Bus #2 to facilitate interconnection of the Cross Town Energy Battery Storage Project. | 2022-12-01 | Approved | 2021-04-16
DMT-21-X01 | 2021-03-31 | Lake Road Unit #1, Unit #2, Unit #3 Automatic Voltage Regulator (AVR) Replacement Project | Transmission application from Dynegy Marketing & Trade ("DMT") for the AVR upgrades to Units #1, #2 & #3 that are required to replace the existing ABB Unitrol F Excitation control systems with ABB Unitrol 6080 with the latest firmware. The ABB Unitrol F has “reach end of life” status and support both software and parts will be limited affecting unit reliability. The proposed in service date is for Units #1 and #3 is April 30, 2021. The proposed in service date for Unit #2 is May 7, 2021. | 2021-05-07 | Approved | 2021-04-16
ES-21-G97 | 2021-03-31 | Nellie Solar Project | Generator application from Eversource Energy ("ES") on behalf of Nellie Solar for the installation of a 15 MW solar array in Newport , NH and interconnecting to the North Road Substation via the 3410 34.5 kV feeder. | 2022-10-01 | Approved | 2021-04-16
ES-21-G96 | 2021-03-31 | Pembroke Solar Project | Generator application from Eversource Energy ("ES") on behalf of Pembroke Solar for the installation of a 17.5 MW solar array in Bow, NH and interconnecting to the Garvins Substation via the 334G 34.5 kV feeder. | 2022-10-01 | Approved | 2021-04-16
NEP-21-G04 | 2021-03-29 | Next Grid Berry Street Plainville, MA Solar and Battery DER Project | Generator application from New England Power ("NEP") on behalf of Next Grid for the installation of a 4.99 MW solar array and 4.0 MW/15.84 MWh battery in Plainville, MA and interconnecting to the Plainville Substation via the 3451W3 13.8 kV feeder. | 2023-07-01 | Approved | 2021-04-16
BRP-21-X01 | 2021-03-25 | Pontook Hydroelectric Unit #3 Automatic Voltage Regulator (AVR) Replacement Project | Generator application from Brookfield Renewable Trading and Marketing ("BRP") to replace the existing Pontook Unit 3 is a 3.58MW variable pitch propeller turbine, with an existing Siemens type EX-1 analog automatic voltage regulator (AVR) that is original equipment installed in 1986 and now obsolete. This plan will replace the existing AVR and will allow the installation of the new Basler DECS-400 digital AVR. | Q2 2021 | Approved | 2021-04-16
ES-21-T17 | 2021-03-26 | Replacement of Two +/- 75 MVAR Statcoms at Glenbrook Substation Project | Transmission application from Eversource Energy ("ES") for the replacement of two +/- 75 MVAR STATCOMs due to asset condition issues at the Glenbrook Substation located in Stamford, CT. | 2021-04-18 | Approved | 2021-04-14
ES-21-T18 | 2021-03-30 | Bunker Hill Substation Expansion Project | Transmission application from Eversource Energy ("ES") for the expansion of the Bunker Hill Substation in Waterbury, CT with the installation of three new 115-kV, 3000 Amps, 40kA SF6 circuit breakers, seven vertical disconnect switches, relocation of the 3X terminal and reconnect to the bus between the new 4T and existing 3T circuit breakers. Relocation of the 1789 Line terminal and reconnect to the bus section between the new 6T and existing 1T circuit breakers, and relocation of the 1029 Line terminal and reconnect to the bus section between new 4T and 5T circuit breakers. | 2022-09-01 | Approved | 2021-04-15
CMP-21-G13 | 2021-03-30 | Yarmouth Road Gray Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of Gray Yarmouth Road Solar for the installation of a 4.994 MW solar PV in Gray, ME and interconnecting to the Gray Substation via the 416D1 12.47 kV circuit. | 2021-09-30 | Notification | 2021-04-16
ES-21-G94 | 2021-03-15 | Louth Callan Renewables Rattlesnake Ledge Road Salem Solar | Generator notification from Eversource Energy ("ES") on behalf of Louth Callan Renewables for the installation of a 4.0 MW solar PV in Salem, CT and interconnecting to the Judd Brook 32R Substation via the 32R1 23J36 23 kV circuit. | 2022-06-01 | Notification Withdrawn | 4/16/2021 7/19/2022
ES-21-G93 | 2021-03-15 | Louth Callan Renewables Randolph Road Middletown Solar | Generator notification from Eversource Energy ("ES") on behalf of Louth Callan Renewables for the installation of a 2.5 MW solar PV in Middletown, CT and interconnecting to the Dooley 30K Substation via the 30K16 13.2 kV circuit. | 2022-06-01 | Notification Withdrawn | 4/16/2021 9/20/2022
ES-19-G30 Rev.2 | 2021-03-26 | Engie Partridge Road Lanesborough Solar and Battery Rev.2 | Generator notification from Eversource Energy ("ES") on behalf of Engie for the installation of a 4.536 MW solar PV project with 3.0 MW/6.672 MWh battery in Lanesborough, MA and interconnecting to the Partridge 15E Substation via the 15E 23 kV feeder. | 2021-09-15 | Notification | 2021-04-16
ES-19-G31 Rev.2 | 2021-03-26 | Engie Saddleback Solar North Main Street Lanesborough Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Engie for the installation of a 3.6 MW solar PV project with 2.50 MW/5.56 MWh battery in Lanesborough, MA and interconnecting to the Partridge 15E Substation via the 15E 23 kV feeder. | 2021-09-15 | Notification | 2021-04-16
ES-20-G51 Rev.1 | 2021-03-26 | Engie Skyline Solar South Main Street Lanesborough Solar and Battery Rev.1 | Generator notification from Eversource Energy ("ES") on behalf of Engie for the installation of a 4.536 MW solar PV project with 3.0 MW/6.672 MWh battery in Lanesborough, MA and interconnecting to the Partridge 15E Substation via the 15E 23 kV feeder. | 2021-09-15 | Notification | 2021-04-16
NEP-21-GNF04 | 2021-03-29 | Arcor Summit Street Halifax Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Arcor for the installation of a 1.75 MW solar PV project with a 0.75 MW/1.644 MWh battery in Halifax, MA and interconnecting to the Mill Street Substation via the 912W75 13.8 kV feeder. | 2022-07-01 | Notification | 2021-04-16
NEP-21-T04 | 2021-04-01 | Billerica Transformer T2 Replacement | Transmission notification from New England Power Company ("NEP") to replace the failed existing 30/40/50 MVA load-service transformer T2 at the Billerica Substation with a new 33/44/55 MVA unit. | 6/2021 | Notification | 2021-04-15
ES-21-T13 | 2021-02-24 | Rood Avenue Substation Transformer Addition Project | Transmission application from Eversource Energy ("ES") for the addition of a 37.5/50/62.5 MVA, 115 kV/23 kV transformer (24J-3X) at the Rood Avenue Substation in Windsor, CT. | 2023-05-31 | Approved | 2021-03-18
ES-20-G169 Rev.1 | 2021-01-26 | Gravel Pit Solar Generation and Transmission Project Rev.1 | Generator application from Eversource Energy ("ES") for a 25 MW increase in output power to 75 MWs in East Windsor, CT and interconnecting to the 115 kV Line between the Barbour Hill 23J Substation and the Windsor Locks 14K Substation. | 2022-11-01 | Approved Withdrawn | 3/30/2021 11/14/2023
NEP-21-G03-001 | 2021-02-26 | Western Massachusetts Generation Cluster Group 1 Project - Dynamic Energy Solutions Adams Street East Brookfield Solar and Battery | Generator application from New England Power Company ("NEP") on behalf of Dynamic Energy Solutions for the installation of a 4.98 MW solar PV project with 3.0 MW/6.3 MWh battery in East Brookfield, MA and interconnecting to the Meadow Street Substation via the 552L3 13.2 kV feeder. | 2021-04-02 | Approved | 2021-03-30
NEP-21-G03-002 | 2021-02-26 | Western Massachusetts Generation Cluster Group 1 Project - Seaboard Solar Leicester Street Auburn Solar and Battery | Generator application from New England Power Company "(NEP") on behalf of Seaboard Solar for the installation of a 4.875 MW solar PV project with 4.875 MW/12.714 MWh battery in Auburn, MA and interconnecting to the Pondville Substation via the 26W1 13.8 kV feeder. | 2022-05-19 | Approved | 2021-03-30
NEP-21-G03-003 | 2021-02-26 | Western Massachusetts Generation Cluster Group 1 Project - Syncarpha Mulberry Street Leicester Solar and Battery | Generator application from New England Power Company ("NEP") on behalf of Syncarpha for the installation of a 2.592 MW solar PV project with 2.0 MW/4.0 MWh battery in Leicester, MA and interconnecting to the Leicester Substation via the 21W1 13.8 kV feeder. | 2021-03-31 | Approved | 2021-03-30
ES-21-G92 | 2021-02-11 | Solar Mattern Farm Route 2 Preston Solar | Generator notification from Eversource Energy ("ES") on behalf of Solar Mattern Farm for the installation of a 4.0 MW solar PV in Preston, CT and interconnecting to the Gales Ferry 11B Substation via the 11B2 13.8 kV circuit. | 2021-07-21 | Notification | 2021-03-30
CMP-21-G01 | 2021-03-01 | NextGrid South Street Biddeford Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of NextGrid for the installation of a 4.99 MW solar PV in Biddeford, ME and interconnecting to the Biddeford Pump Substation via the 605D1 12.47 kV circuit. | 2021-09-30 | Notification | 2021-03-30
CMP-21-G03 | 2021-03-01 | TPE Development Ross Road Olad Orchard Beach Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of TPE Development for the installation of a 4.7 MW solar PV in Old Orchard Beach, ME and interconnecting to the Factory Substation via the 621D1 12.47 kV circuit. | 2021-09-30 | Notification Withdrawn | 3/30/2021 7/19/2022
CMP-21-G08 | 2021-03-01 | Waldoboro Solar Controversy Lane Waldoboro Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of Waldoboro Solar for the installation of a 4.925 MW solar PV in Waldoboro, ME and interconnecting to the Waldoboro Substation via the 252D2 12.47 kV circuit. | 2021-09-30 | Notification | 2021-03-30
CMP-21-G09 | 2021-03-01 | NexAmp Solar St. George Road South Thomaston Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of NexAmp Solar for the installation of a 4.0 MW solar PV in South Thomaston, ME and interconnecting to the Thomaston Creek Substation via the 246D1 34.5 kV circuit. | 2021-09-30 | Notification | 2021-03-30
CMP-21-G10 | 2021-03-01 | Knights Pond Solar Junction Road South Berwick Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of Knights Pond Solar for the installation of a 3.88 MW solar PV in South Berwick, ME and interconnecting to the Bassett Substation via the 602D3 12.47 kV circuit. | 2021-09-30 | Notification | 2021-03-30
CMP-21-G11 | 2021-03-01 | CEC Development Appleton Road Union Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of CEC Development for the installation of a 2.0 MW solar PV in Union, ME and interconnecting to the Union Substation via the 251D1 12.47 kV circuit. | 2021-09-30 | Notification | 2021-03-30
NEP-19-G30-057 Rev.2 | 2021-02-26 | Allco Renewable Energy Spring Street Winchendon Solar Rev.2 | Generator notification from New England Power Company ("NEP") on behalf of Allco Renewable Energy for the installation of a 3.9 MW solar PV in Winchendon, MA and interconnecting to the East Winchendon Substation via the 612W3 13.8 kV feeder. | 2022-08-31 | Notification | 2021-03-30
NEP-19-G30-032 Rev.2 | 2021-02-26 | Sunpin Solar North Brookfield Road Spencer Solar Rev.2 | Generator notification from New England Power Company ("NEP") on behalf of Sunpin Solar for the installation of a 2.2 MW solar PV in Spencer, MA and interconnecting to the Meadow Street Substation via the 552L1 13.2 kV feeder. | 2021-04-02 | Notification | 2021-03-30
NEP-13-GNF20 Rev.1 | 2021-02-26 | Borrego Solar Wilson Street Spencer Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Borrego Solar for the installation of a 2.0 MW solar PV in Spencer, MA and interconnecting to the Leicester Substation via the 21W1 13.8 kV feeder. | 2013-08-07 | Notification | 2021-03-30
NEP-19-G30-024 Rev.2 | 2021-02-26 | Clearway Energy Group Belchertown Road Ware Solar Rev.2 | Generator notification from New England Power Company ("NEP") on behalf of Clearway Energy Group for the installation of a 1.452 MW solar PV in Ware, MA and interconnecting to the Ware Substation via the 501L2 13.2 kV feeder. | 2021-04-01 | Notification | 2021-03-30
NEP-20-GNF28 Rev.1 | 2021-03-01 | Kearsarge Solar Brook Street Bellingham Solar and Battery Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Kearsarge Solar for the installation of a 4.99 MW solar PV project with 2.64 MW/9.6 MWh battery in Bellingham, MA and interconnecting to the Depot Street Substation via the 335W1 13.8 kV feeder. PPA revision reflects a MW change in the battery from 2.25/9.0 MWh to 2.64/9.6 MWh. | 2021-07-22 | Notification | 2021-03-30
NEP-20-G03-025 Rev.1 | 2021-02-26 | Ameresco Solar Indian Road Dudley Solar and Battery Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Ameresco Solar for the installation of a 1.25 MW solar PV project with 0.5 MW/1.112 MWh battery in Dudley, MA and interconnecting to the East Webster Substation via the 412L4 13.2 kV feeder. PPA revision reflects a MW change in the solar from 1.32 MWs to 1.25 MWs and adds a battery to the project. | 2022-10-01 | Notification | 2021-03-30
NEP-19-G30-054 Rev.2 | 2021-02-26 | Zero Point Dresser Hill Road Southbridge Solar and Battery Rev.2 | Generator notification from New England Power Company ("NEP") on behalf of Zero Point for the installation of a 7.1 MW solar PV project with 5.4 MW/10.799 MWh battery in Southbridge, MA and interconnecting to the Snow Street Substation via the 413L8 13.2 kV feeder. PPA revision reflects a MW change in the solar from 7.5 MWs to 7.1 MWs. | 2021-04-01 | Notification | 2021-03-30
NEP-19-G30-034 Rev.2 | 2021-02-26 | AES Distributed Energy Ward Street North Brookfield Solar and Battery Rev. 2 | Generator notification from New England Power Company ("NEP") on behalf of AES Distributed Enerdy for the installation of a 5.8 MW solar PV project with 6.0 MW/16.62 MWh battery in North Brookfield, MA and interconnecting to the Lashaway Substation via the 0012 23 kV feeder. | 2021-04-01 | Notification | 2021-03-30
NEP-19-G30-030 Rev.2 | 2021-02-26 | Dynamic Energy Solutions Palmer Road Ware Solar and Battery Rev.2 | Generator notification from New England Power Company ("NEP") on behalf of Dynamic Energy Solutions for the installation of a 3.0 MW solar PV project with 1.92 MW/4.5 MWh battery in Ware, MA and interconnecting to the Ware Substation via the 501L2 13.2 kV feeder. | 2021-03-31 | Notification | 2021-03-30
CMP-21-G12 | 2021-03-02 | Sunraise Development Augusta Road Bowdoin Solar and Battery | Generator notification from Central Maine Power Company ("CMP") on behalf of Sunraise Development for the installation of a 2.49 MW solar PV project with 2.5 MW/6.25 MWh battery in Bowdoin, ME and interconnecting to the Topsham Substation via the 250D1 12.47 kV feeder. | 2021-06-30 | Notification | 2021-03-30
ES-21-G91 | 2021-02-11 | Saint Mary's Hospital Franklin Street Waterbury Gas Generator | Generation notification from Eversource Energy ("ES") on behalf of Saint Mary's Hospital for the installation of a 1.5 MW natural gas generator in Waterbury, CT and interconnecting to the Freight Street 11W Substation via the 11W43 13.8 kV feeder. | 2021-11-15 | Notification | 2021-03-30
UI-21-G01 | 2021-02-26 | 2019 ESA Project Company Wintergreen Avenue New Haven Solar and Fuel Cell | Generator notification from Avangrid/United Illuminating (“UI”) on behalf of 2019 ESA Project Company for the installation of a 1.59 MW solar and fuel cell generator (0.956 MW PV/0.6 MW fuel cell) in New Haven, CT and interconnecting to the Broadway Substation via the 1906 13.8 kV feeder. | 2021-06-01 | Notification | 2021-03-30
VELCO-21-X01 | 2021-03-01 | Remove PV 20 Line Trip Scheme | Transmission notification from VELCO to remove the PV 20 Line Trip Scheme as it is no longer needed as a fully redundant protection system is currently in place. | 2021-07-01 | Notification | 2021-03-18
ES-21-G90 | 2021-02-02 | QP 726 Battery and Transmission Project | Generator application from Eversource Energy ("ES") on behalf of Cranberry Point Energy Storage for the construction of a 150 MW battery energy storage system interconnecting to the Eversource transmission system at the Carver 115 kV station. | 2023-05-31 | Approved Withdrawn | 3/3/2021 1/22/2025
ES-21-T10 | 2021-02-02 | QP 726 Battery and Transmission Project | Transmission application from Eversource Energy ("ES") to construct a new 115 kV 3 breaker ring bus station at the Carver 115 kV Substation. The station will split Line 127 between Carver and Semass into two circuits, LN 127 from Carver to QP 726 Point of Interconnection and LN 152 from QP 726 to SEMASS in support of the QP 726 Battery Project. | 2023-02-01 | Approved | 2021-03-03
ES-21-T14 | 2021-02-02 | QP 726 Battery and Transmission Project | Transmission application from Eversource Energy ("ES") on behalf of Cranberry Point Energy Storage to construct a new 115/34.5 kV step-up transformer at the Carver 115 kV Substation in support of the QP 726 Battery Project. | 2023-02-01 | Approved Withdrawn | 3/3/2021 1/22/2025
ES-21-G10 | 2021-02-04 | Lahey Hospital and Medical Center Burlington Solar and Battery Project | Generator application from Eversource Energy ("ES") on behalf of Lahey Hospital and Medical Center for the installation of a 3.5 MW solar array and a 2.651 MWS/10.461 MWh battery (5 MW max output) in Burlington, MA and interconnecting to the Burlington 391 Substation via the 391-H5 13.8 kV circuit. | 2022-03-01 | Approved Withdrawn | 3/3/2021 6/18/2024
NEP-21-G02-001 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - EDP Noose Neck Hill Road Hopkinton Solar | Generator application from New England Power ("NEP") on behalf of EDP for the installation of a 4.95 MW solar array in Hopkinton, RI and interconnecting to the Chase Hill Substation via the 155F8 12.47 kV feeder. | 2025-06-30 | Approved Withdrawn | 3/3/2021 7/13/2021
NEP-21-G02-002 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Revity Energy Seven Mile Road Cranston Solar | Generator application from New England Power ("NEP") on behalf of Revity Energy for the installation of a 1.56 MW solar array in Cranston, RI and interconnecting to the West Cranston Substation via the 21F2 12.47 kV feeder. | 2022-04-01 | Approved Withdrawn | 3/3/2021 5/18/2021
NEP-21-G02-003 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Direct Energy Solar Victory Highway Covington Solar | Generator application from New England Power ("NEP") on behalf of Direct Energy Solar for the installation of a 3.5 MW solar array in Covington, RI and interconnecting to the Hopkins Hill Substation via the 63F3 12.47 kV feeder. | 2022-04-01 | Approved Withdrawn | 3/3/2021 8/13/204
NEP-21-G02-004 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - EDP Skunk Hill Road Hopkinton Solar | Generator application from New England Power ("NEP") on behalf of EDP for the installation of a 20.0 MW solar array in Hopkinton, RI and interconnecting to the Wood River Substation via the 85T2 34.5 kV feeder. | 2025-06-30 | Approved Withdrawn | 3/3/2021 7/13/2021
NEP-21-G02-005 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - ISM Solar Development Log Road Smithfield Solar | Generator application from New England Power ("NEP") on behalf of ISM Solar Development for the installation of an 8.0 MW solar array in Smithfield, RI and interconnecting to the Farnum Pike Substation via the 23F3 12.47 kV feeder. | 2022-04-01 | Approved | 2021-03-03
NEP-21-G02-006 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - EDP Weaver Hill Road West Greenwich Solar | Generator application from New England Power ("NEP") on behalf of EDP for the installation of a 10.0 MW solar array in West Greenwich, RI and interconnecting to the Kent County Substation via the 3310 34.5 kV feeder. | 2022-04-01 | Approved Withdrawn | 3/3/2021 3/19/2024
NEP-21-G02-007 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - ISM Solar Development Centerville Road Log Road Smithfeld Solar | Generator application from New England Power ("NEP") on behalf of ISM Solar Development for the installation of a 4.975 MW solar array in Warwick, RI and interconnecting to the Drumrock Substation via the 14F4 12.47 kV feeder. | 2022-04-01 | Approved Withdrawn | 3/3/2021 5/14/2024
NEP-21-G02-008 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Blue Wave Solar Kingstown Road Richmond Solar | Generator application from New England Power ("NEP") on behalf of Blue Wave Solar for the installation of a 19.6 MW solar array in Richmond, RI and interconnecting to the Wood River Substation via the 85T2 34.5 kV feeder. | 2025-06-30 | Approved Withdrawn | 3/3/2021 7/13/2021
NEP-21-G02-009 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Nexamp Solar Victory highway West Greenwich Solar | Generator application from New England Power ("NEP") on behalf of Nexamp Solar for the installation of a 4.0 MW solar array in West Greenwich, RI and interconnecting to the Kent County Substation via the 3311 34.5 kV feeder. | 2022-04-01 | Approved Withdrawn | 3/3/2021 8/13/204
NEP-21-G02-010 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Direct Energy Solar Boom Bridge Road Westerly Solar | Generator application from New England Power ("NEP") on behalf of Direct Energy Solar for the installation of a 4.875 MW solar array in Westerly, RI and interconnecting to the Westerly Substation via the 16F2 12.47 kV feeder. | 2025-06-30 | Approved Withdrawn | 3/3/2021 7/13/2021
NEP-21-G02-011 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Northbridge Development JP Murphy Highway West Warwick Solar | Generator application from New England Power ("NEP") on behalf of North Bridge Development for the installation of a 3.6 MW solar array in West Warwick, RI and interconnecting to the Kent County Substation via the 22F112.47 kV feeder. | 2022-04-01 | Approved Withdrawn | 3/3/2021 8/13/204
NEP-21-G02-012 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Revity Energy Weaver Hill Road West Greenwich Solar | Generator application from New England Power ("NEP") on behalf of Revity Energy for the installation of a 40.7 MW solar array in West Greenwich, RI and interconnecting to the Kent County Substation via the 3309 34.5 kV feeder. | 2022-04-01 | Approved | 2021-03-03
NEP-21-G02-013 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Revity Energy Shore Drive Johnston Solar | Generator application from New England Power ("NEP") on behalf of Revity Energy for the installation of a 4.875 MW solar array in Johnston, RI and interconnecting to the Johnston Substation via the 18F6 12.47 kV feeder. | 2022-04-01 | Approved | 2021-03-03
NEP-21-G02-014 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Kearsarge Solar Oak Hill Road North Kingstown Solar | Generator application from New England Power ("NEP") on behalf of Kearsarge Solar for the installation of a 3.060 MW solar array in North Kingstown, RI and interconnecting to the Tower Hill Substation via the 88F7 12.47 kV feeder. | 2025-06-30 | Approved Withdrawn | 3/3/2021 7/13/2021
NEP-21-G02-015 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Revity Energy Frontier Road Hopkinton Solar | Generator application from New England Power ("NEP") on behalf of Revity Energy for the installation of a 15.125 MW solar array in Hopkinton, RI and interconnecting to the Wood River Substation via the 85T2 34.5 kV feeder. | 2025-06-30 | Approved Withdrawn | 3/3/2021 7/13/2021
NEP-21-G02-016 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Direct Energy Solar Quarry Road Westerly Solar | Generator application from New England Power ("NEP") on behalf of Direct Energy Solar for the installation of a 2.375 MW solar array in Westerly, RI and interconnecting to the Chase Hill Substation via the 155F2 12.47 kV feeder. | 2025-06-30 | Approved Withdrawn | 3/3/2021 7/13/2021
NEP-21-G02-017 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - InFEWSion Frenchtown Road North Kingstown Solar | Generator application from New England Power ("NEP") on behalf of InFEWSion for the installation of a 4.0 MW solar array in North Kingstown, RI and interconnecting to the Old Baptist Road Substation via the 46F3 12.47 kV feeder. | 2022-04-01 | Approved Withdrawn | 3/3/2021 8/17/2021
NEP-21-G02-018 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - ISM Solar Arnold Road Coventry Solar | Generator application from New England Power ("NEP") on behalf of ISM Solar Development for the installation of a 4.975 MW solar array in Coventry, RI and interconnecting to the Kent County Substation via the 22F1 12.47 kV feeder. | 2022-04-01 | Approved Withdrawn | 3/3/2021 8/13/204
NEP-21-G02-019 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Revity Energy Colvintown Road Coventry Solar | Generator application from New England Power ("NEP") on behalf of Revity Energy for the installation of a 4.875 MW solar array in Coventry, RI and interconnecting to the New London Substation via the 150F4 12.47 kV feeder. | 2022-04-01 | Approved Withdrawn | 3/3/2021 6/15/2021
NEP-20-G04-021 Rev.1 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Green Development Ten Rod Road Exeter Solar Rev.1 | Generator application from New England Power ("NEP") on behalf of Green Development for the installation of a 2.64 MW solar array in Exeter, RI and interconnecting to the Wickford Junction 89T2 34.5 kV feeder. | 2023-06-30 | Approved Withdrawn | 3/3/2021 1/19/2022
NEP-20-G04-022 Rev.1 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Green Development Tripps Corner Road Exeter Solar Rev.1 | Generator application from New England Power ("NEP") on behalf of Green Development for the installation of a 7.04 MW solar array in Exeter, RI and interconnecting to the Wickford Junction 89T2 34.5 kV feeder. | 2023-06-30 | Approved Withdrawn | 3/3/2021 1/19/2022
NEP-20-G04-023 Rev.1 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Green Development Stamp Place Exeter Solar Rev.1 | Generator application from New England Power ("NEP") on behalf of Green Development for the installation of a 7.04 MW solar array in Exeter, RI and interconnecting to the Wickford Junction 89T2 34.5 kV feeder. | 2023-06-30 | Approved Withdrawn | 3/3/2021 1/19/2022
NEP-20-G04-024 Rev.1 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Green Development Ten Rod Road Exeter Solar Rev.1 | Generator application from New England Power ("NEP") on behalf of Green Development for the installation of a 9.68 MW solar array in Exeter, RI and interconnecting to the Wickford Junction 89T2 34.5 kV feeder. | 2023-06-30 | Approved Withdrawn | 3/3/2021 1/19/2022
NEP-20-G04-025 Rev.1 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Green Development Ten Rod Road Exeter Solar Rev.1 | Generator application from New England Power ("NEP") on behalf of Green Development for the installation of a 8.8 MW solar array in Exeter, RI and interconnecting to the Wickford Junction 89T2 34.5 kV feeder. | 2023-06-30 | Approved Withdrawn | 3/3/2021 1/19/2022
NEP-20-G04-026 Rev.1 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Green Development Ten Rod Road Exeter Solar Rev.1 | Generator application from New England Power ("NEP") on behalf of Green Development for the installation of a 4.4 MW solar array in Exeter, RI and interconnecting to the Wickford Junction 89T2 34.5 kV feeder. | 2023-06-30 | Approved Withdrawn | 3/3/2021 1/19/2022
NEP-20-G04-027 Rev.1 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Green Development Ten Rod Road Exeter Solar Rev.1 | Generator application from New England Power ("NEP") on behalf of Green Development for the installation of a 7.04 MW solar array in Exeter, RI and interconnecting to the Wickford Junction 89T2 34.5 kV feeder. | 2023-06-30 | Approved Withdrawn | 3/3/2021 1/19/2022
NEP-20-G04-028 Rev.1 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Green Development Tripps Corner Road Exeter Solar Rev.1 | Generator application from New England Power ("NEP") on behalf of Green Development for the installation of a 7.04 MW solar array in Exeter, RI and interconnecting to the Wickford Junction 89T2 34.5 kV feeder. | 2023-06-30 | Approved Withdrawn | 3/3/2021 1/19/2022
NEP-20-G04-029 Rev.1 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project - Green Development Stamp Place Exeter Solar Rev.1 | Generator application from New England Power ("NEP") on behalf of Green Development for the installation of a 4.4 MW solar array in Exeter, RI and interconnecting to the Wickford Junction 89T2 34.5 kV feeder. | 2023-06-30 | Approved Withdrawn | 3/3/2021 1/19/2022
NEP-21-T01 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project | Transmission application from New England Power ("NEP") on behalf of Narragansett Electric for the addition of two 115 kV circuit breakers to convert the West Kingston Substation into a 4-breaker ring bus configuration in support of the Western RI ASO #2 DER Cluster and Transmission Project. | 2023-06-30 | Approved Withdrawn | 3/3/2021 4/27/2022
NEP-21-T02 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project | Transmission application from New England Power ("NEP") on behalf of Narragansett Electric for the installation of a new 25 MVA (+25/-12.5 MVAR) synchronous condenser, a 115/13.8 kV transformer and in line circuit breaker at the Tower Hill Substation in support of the Western RI ASO #2 DER Cluster and Transmission Project. | 2025-06-30 | Approved Withdrawn | 3/3/2021 7/13/2021
NEP-20-T25 Rev.1 | 2021-02-02 | Western Rhode Island Affected System Operator (ASO) #2 DER Cluster and Transmission Project Rev.1 | Transmission application from New England Power ("NEP") on behalf of Narragansett Electric to change the 115/34.5 kV transformer impedances at the Wickford Junction Substation in support of the Western RI ASO #2 DER Cluster and Transmission Project. | 2021-07-15 | Approved | 2021-03-03
ES-21-G89 | 2021-01-15 | C-TEC Solar Pompeo Road North Grosvenordale Solar | Generator notification from Eversource Energy ("ES") on behalf of C-Tec Solar for the installation of a 2.973 MW solar PV in North Grosvenordale, CT and interconnecting to the Tracy Substation via 14M22 415L3 23 kV circuit. | 2022-06-30 | Notification | 2021-02-25
ES-21-G88 | 2021-01-15 | Mayland Energy Point of Rocks Road Falls Village Solar | Generator notification from Eversource Energy ("ES") on behalf of Mayland Energy for the installation of a 1.5 MW solar PV in Falls Village, CT and interconnecting to the Falls Village 4L Substation via 4L08 13.2 kV circuit. | 2021-06-25 | Notification Withdrawn | 2/25/2021 3/19/2024
NEP-21-GNF07 | 2021-01-29 | Sol Alliance Oak Street Pembroke Solar | Generator notification from New England Power ("NEP") on behalf of Sol Alliance for the installation of a 2.689 MW solar PV in Pembroke, MA and interconnecting to the Water Street Substation via 910W51 13.8 kV circuit. | 2022-02-26 | Notification | 2021-02-25
CMP-21-G02 | 2021-01-06 | Dynamic Energy Solutions Leeds Junction Road Wales Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of Dynamic Energy Solutions for the installation of a 4.5 MW solar PV in Wales, ME and interconnecting to the Monmouth Substation via the 457D1 34.5 kV circuit. | 2021-12-31 | Notification | 2021-02-25
CMP-21-G05 | 2021-01-06 | Renesola Power Holdings Ridge Road Athens Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of Renesola Power Holdings for the installation of a 2.749 MW solar PV in Athens, ME and interconnecting to the Athens Substation via the 827D1 12.47 kV circuit. | 2021-12-31 | Notification | 2021-02-25
CMP-21-G06 | 2021-01-06 | Revision Energy River Road Gardiner Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of 3.852 MW solar PV in Gardiner, ME and interconnecting to the Browns Crossing Substation via the 211D1 12.47 kV circuit. | 2021-12-31 | Notification | 2021-02-25
CMP-21-G07 | 2021-01-06 | PWH Properties Plesant Street Canton Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of PWH Properties for the installation of a 3.0 MW solar PV in Canton, ME and interconnecting to the Rumford IP Substation via the 466D1 34.5 kV circuit. | 2021-12-31 | Notification | 2021-02-25
NEP-19-G30-035 Rev.1 | 2021-01-29 | Zero Point Engineering Coy Hill Road Warren Solar and Battery Rev.1 | Generator notification from New England Power ("NEP") on behalf of Zero Point Engineering for the installation of a 4.0 MW solar PV project with 2.475 MW/4.96 MWh battery in Warren, MA and interconnecting to the Little Rest Road 516L3 13.2 kV feeder. PPA revision reflect a MW change from 4.95 MWs to 4.0 MWs. | 2021-02-12 | Notification | 2021-02-25
ES-21-G87 | 2021-01-06 | Eastern CT State University High Street Willimantic Fuel Cell | Generator notification from Eversource Energy ("ES") on behalf of Eastern CT State University for the installation of a 1.59 MW natural gas fuel cell in Willimantic, CT and interconnecting to the Card 11F Substation via the 11F9 23 kV feeder. | 2021-01-29 | Notification | 2021-02-25
ES-21-T08 | 2021-01-12 | Partridge Substation 1X Step-Down Transformer Replacement | Transmission notification from Eversource Energy ("ES") for the replacement of the 37.5 MVA 115/23 kV 1X step-down transformer at the Partridge Substation in Pittsfield, MA. | 2021-08-14 | Notification | 2021-02-26
ES-21-T09 | 2021-01-21 | Canton Substation 2X Step-Down Transformer Replacement | Transmission notification from Eversource Energy ("ES") for the replacement of the 37.5 MVA 115/23 kV 2X step-down transformer at the Canton Substation in Canton, CT due to failed equipment. | 2020-12-14 | Notification | 2021-02-26
ES-21-T11 | 2021-01-22 | Newington Substation 1X Step-Down Transformer Replacement | Transmission notification from Eversource Energy ("ES") for the replacement of the 37.5 MVA 115/23 kV 1X step-down transformer at the Newington Substation in Newington, CT. | 2021-02-28 | Notification | 2021-02-26
ES-21-T12 | 2021-01-22 | Newington Substation 3X Step-Down Transformer Replacement | Transmission notification from Eversource Energy ("ES") for the replacement of the 37.5 MVA 115/23 kV 3X step-down transformer at the Newington Substation in Newington, CT. | 2021-05-17 | Notification | 2021-02-26
ES-21-G05 | 2021-01-07 | Eversource Western Mass Generation and Transmission Cluster Project - Otis Solar and Battery Project | Generator application from Eversource Energy ("ES") for the installation of a 4.998 MW solar array and 2.25 MW/4.62 MWh battery in Otis, MA and interconnecting to the Blandford 19J Substation via the 23 kV express feeder. | 2021-12-01 | Approved Withdrawn | 1/25/2021 7/16/2024
ES-21-G06 | 2021-01-07 | Eversource Western Mass Generation and Transmission Cluster Project - Rolling Potato Blandford Solar and Battery Project | Generator application from Eversource Energy ("ES") for the installation of a 5.0 MW solar array and 5.0 MW/12.0 MWh battery in Blandford, MA and interconnecting to the Blandford 19J Substation via the 23 kV express feeder. | 2021-11-30 | Approved Withdrawn | 1/25/2021 7/16/2024
ES-21-G07 | 2021-01-07 | Eversource Western Mass Generation and Transmission Cluster Project - Russel Solar and Battery Project | Generator application from Eversource Energy ("ES") for the installation of a 2.75 MW solar array and 1.5 MW/3.0 MWh battery in Russel, MA and interconnecting to the Blandford 19J Substation via the 23 kV express feeder. | 2022-06-01 | Approved | 2021-01-25
ES-21-G08 | 2021-01-07 | Eversource Western Mass Generation and Transmission Cluster Project - Lanesborough Solar and Battery Project | Generator application from Eversource Energy ("ES") for the installation of a 4.99 MW solar array and 3.0 MW/6.672 MWh battery in Lanesborough, MA and interconnecting to the Partridge 15E Substation via the 23 kV express feeder. | 2021-06-01 | Approved Withdrawn | 1/25/2021 7/16/2024
ES-21-G09 | 2021-01-07 | Eversource Western Mass Generation and Transmission Cluster Project - South Deerfield Solar and Battery Project | Generator application from Eversource Energy ("ES") for the installation of a 2.25 MW solar array and 1.257 MW/2.514 MWh battery in South Deerfield, MA and interconnecting to the Cumberland 22B Substation via the 13.8 kV express feeder. | 2022-06-01 | Approved | 2021-01-25
ES-21-T03 | 2021-01-05 | Eversource Western Mass Generation and Transmission Cluster Project - Blandford Substation 1X Step-Down Transformer Replacement Project | Transmission application from Eversource Energy ("ES") for the replacement of the 115/23 kV, 37.5 MVA 1X step-down transformer at the Blandford 19J substation in Blandford, MA. | 2022-06-01 | Approved | 2021-01-25
ES-21-T04 | 2021-01-05 | Eversource Western Mass Generation and Transmission Cluster Project - Blandford Substation 2X Step-Down Transformer Replacement Project | Transmission application from Eversource Energy ("ES") for the replacement of the 115/23 kV, 37.5 MVA 2X step-down transformer at the Blandford 19J substation in Blandford, MA. | 2022-06-01 | Approved | 2021-01-25
NEM-20-G08 | 2021-01-07 | Montville Energy Center Solar Generation and Transmission Project | Generator application from NextEra Energy Resources ("NEM") for the installation of a 19.9 MW solar array at the Montville Energy Center in Uncasville, CT. | 2023-12-31 | Approved Withdrawn | 1/25/2021 9/9/2022
NEM-20-T08 | 2021-01-07 | Montville Energy Center Solar Generation and Transmission Project | Transmission application from NextEra Energy Resources ("NEM") for the interconnection of the 19.9 MW solar array from the Montville Solar facility to the 69/35.5 kV 24 MVA transformer at the Montville 69 kV Substation in Uncasville, CT. | 2023-12-31 | Approved | 2021-01-25
ES-20-T45 | 2020-12-18 | Montville Energy Center Solar Generation and Transmission Project | Transmission application from Eversource Energy ("ES") for the installation of a 69 kV circuit breaker at the Montville 4J Substation. This will support of the 19.9 MW solar array at the Montville Solar facility in Uncasville, CT. | 2023-06-30 | Approved | 2021-01-25
ES-20-T46 | 2020-12-18 | Montville Energy Center Solar Generation and Transmission Project | Transmission application from Eversource Energy ("ES") for the installation of a 1.7 mile overhead/0.152 mile underground 69 kV transmission line from the Montville Solar facility to the Montville 4J Substation in Uncasville, CT. | 2023-06-30 | Approved | 2021-01-25
NEP-21-G01 | 2021-01-04 | TPE Development School House Road Warren Solar Project | Generator application from New England Power Company ("NEP") on behalf of TPE Development for the installation of a 6.93 MW solar array in Warren, RI and interconnecting to the Warren Substation via the 12.47 kV 5F2 circuit. | 2022-05-19 | Approved | 2021-01-25
KCE-21-G01 | 2021-01-07 | Killingly Battery Storage Generator and Substation Project | Generator application from Key Capture Energy ("KCE") for the installation of a new 200 MW/400 MWh battery storage project, consisting of 96-2.5 MVA SMA Sunny Central Storage 2500-EV-US inverters located in Putnam, CT and supporting transmission work interconnecting to the Killingly Substation. | 2024-05-01 | Approved Withdrawn | 1/25/2021 3/16/2021
ES-21-T05 | 2021-01-07 | Killingly Battery Storage Generator and Substation Project | Transmission application from Eversource Energy ("ES") for the installation of two new 345-kV circuit breakers (1T and 2T) at Killingly 345-kV substation and expand the 345-kV bus into a 4-breaker ring bus, install a 345-kV Motor Operated Disconnect (MOD) in the generator line position created by the new 345-kV 1T and 2T circuit breakers, and modify/upgrade the LTC controls of the existing Killingly 2X autotransformer for potential reverse power flow contingency condition. | 2024-03-01 | Approved Withdrawn | 1/25/2021 3/16/2021
ES-21-T06 | 2021-01-07 | Killingly Battery Storage Generator and Substation Project | Transmission application from Eversource Energy ("ES") for the installation of approximately 2500 feet of a 345-kV Overhead/Underground gen-tie line. The underground portion will install an approximately 1000 feet of 345-kV underground cable with 3500 kcmil bare copper, 345-kV XLPE cables, with two cables per phase from Killingly S/S to Killingly UG/OH Transition structure. The overheard portion will install an approximately 1500 feet of 345-kV Line from Killingly UG/OH Transition structure to QP831 with 2 x 1590 kcmil ACSS conductor. | 2024-03-01 | Approved Withdrawn | 1/25/2021 3/16/2021
ES-21-T07 | 2021-01-07 | Killingly Battery Storage Generator and Substation Project | Transmission application from Eversource Energy ("ES") for the rebuild of the 69-kV 400-1 Line (Ledyard Junction to Tunnel OH/UG Transition structure) with 8.516 miles of 1272 kcmil ACSS conductor. Also install approximately 200 feet of underground cable with 5000 kcmil enameled/oxidized copper, XLPE cable, one cable per phase from Tunnel OH/UG Transition structure to Tunnel S/S. | 2024-03-01 | Approved Withdrawn | 1/25/2021 3/16/2021
ES-21-T01 | 2021-01-04 | Carmel Hill Substation Expansion Project | Transmission application from Eversource Energy ("ES") for the modification of the Carmel Hill Substation to connect a second Eversource bulk distribution transformer (2X). Based on Eversource’s standard substation design, the substation needs to include two 115-kV tie breakers to accommodate the new configuration. There will be one new bulk distribution transformer, 11S-2X (115/23-kV, 62.5-MVA), and two new 115-kV circuit breakers, 11S-2T and 2TA – between 11S-2X (new) and 11S-3X, and two new disconnect switches, 11S-2X1-2 and 11S-3X1-2. | 2023-12-31 | Approved | 2021-01-22
NEP-19-G30-041 Rev.1 | 2021-01-04 | Sunpin Solar Sturbridge Road Charlton Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Sunpin Solar for the installation of a 4.999 MW solar PV in Charlton, MA and interconnecting to the West Charlton Substation via 415L3 13.2 kV circuit. | 2022-10-01 | Notification | 2021-01-25
NEP-19-GNF30-045 Rev.1 | 2021-01-04 | Energy Development Brookfield Road Charlton Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Energy Development for the installation of a 2.64 MW solar PV in Charlton, MA and interconnecting to the West Charlton Substation via 415L3 13.2 kV circuit. | 2022-10-01 | Notification Withdrawn | 1/25/2021 11/16/2021
NEP-21-GNF03 | 2021-01-04 | Sun Power River Street Dunstable Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Sun Power for the installation of a 4.89 MW solar PV project with 3.5 MW/7.0 MWh battery in Dunstable, MA and interconnecting to the New Groton Substation via the 226L1 13.2 kV feeder. | 2022-05-01 | Notification Withdrawn | 1/25/2021 9/21/2021
NEP-21-GNF02 | 2021-01-04 | Saint Gobain Abrasives New Bond Street Worcester Gas Generator | Generator notification from New England Power Company ("NEP") on behalf of Saint Gobain Abrasives for the installation of a 4.9 MW natural gas generator in Worcester, MA and interconnecting to the Greendale Substation via 24W2 13.8 kV circuit. | 2022-05-01 | Notification | 2021-01-25
ES-21-T02 | 2021-01-04 | Cumberland Substation 2X Step-Down Transformer Replacement | Transmission notification from Eversource Energy ("ES") for the replacement of the 117/15.12 kV 37 MVA 2X step-down transformer at the Cumberland Substation in Greenfield, MA. | 2021-06-22 | Notification | 2021-01-22
VW-20-G01 | 2020-11-03 | Vineyard Wind Offshore Wind Generation and Transmission Project (QP 700) | Generator application from Vineyard Wind for the construction of an 838.2MW offshore Wind farm comprising 88 wind turbine generators located on OCS-A 501 south of Martha’s Vineyard and interconnecting to the Eversource transmission system at the West Barnstable 345kV Substation (921). | 2024-05-01 | Approved Withdrawn | 1/4/2021 6/18/2024
VW-20-T01 | 2020-11-03 | Vineyard Wind Offshore Wind Generation and Transmission Project (QP 700) | Transmission application for Vineyard Wind for the installation of a single offshore gas-insulated substation (“GIS”), containing 66 kV switchgear, 220 kV circuit breakers and two (2) 450 MVA 220/66 kV on-load tap-changing transformers. | 2024-05-01 | Approved Withdrawn | 1/4/2021 6/18/2024
VW-20-T02 | 2020-11-03 | Vineyard Wind Offshore Wind Generation and Transmission Project (QP 700) | Transmission application from Vineyard Wind for the installation of a combination of two (2) 1600mm² Cu, 3-core 220kV submarine cables and 1600mm² Cu single conductor 220kV terrestrial underground cable to transmit the power from the offshore substations approximately 59-miles to onshore substation. | 2024-05-01 | Approved Withdrawn | 1/4/2021 6/18/2024
VW-20-T03 | 2020-11-03 | Vineyard Wind Offshore Wind Generation and Transmission Project (QP 700) | Transmission application from Vineyard Wind for the installation of a single onshore substation containing two (2) 400 MVA 345kV/220kV on-load tap-changing transformers, each separately connected to a 345 kV straight bus and a 220 kV straight bus. Each 345 kV bus will have five 345 kV circuit breakers. | 2024-05-01 | Approved Withdrawn | 1/4/2021 6/18/2024
VW-20-T04 | 2020-11-03 | Vineyard Wind Offshore Wind Generation and Transmission Project (QP 700) | Transmission application from Vineyard Wind for the installation of two (2) individual 345kV circuits providing separate Vineyard Wind onshore substation transformer interconnection to distinct Barnstable 345kV station breaker positions through an approximately.3-mile underground circuit, see Eversource PPA ES-20-T48. | 2024-05-01 | Approved Withdrawn | 1/4/2021 6/18/2024
VW-20-T05 | 2020-11-03 | Vineyard Wind Offshore Wind Generation and Transmission Project (QP 700) | Transmission application for Vineyard Wind for the installation of two +150MVAR/-150MVAR STATCOM’s connected directly to the 345kV bus. | 2024-05-01 | Approved Withdrawn | 1/4/2021 6/18/2024
ES-20-T47 | 2020-11-03 | Vineyard Wind Offshore Wind Generation and Transmission Project (QP 700) | Transmission application from Eversource Energy for the construction of a new 345 kV Bourne Substation. The proposed project constructs a new 345 kV breaker-and-a-half GIS Bourne substation in the vicinity of the existing 115 kV Bourne substation consisting of three bays and eight new breakers, looping in two existing transmission lines (Line 399 and Line 322) into the new 345 kV Bourne substation. | 2024-05-01 | Approved | 2021-01-04
ES-20-T48 | 2020-11-03 | Vineyard Wind Offshore Wind Generation and Transmission Project (QP 700) | Transmission application from Eversource Energy for the upgrade of the existing 345 kV West Barnstable Substation. The proposed project upgrades the existing West Barnstable 345 kV substation as GIS breaker-and-a-half design with four bays and nine new breakers. | 2024-05-01 | Approved | 2021-01-04
ES-20-T49 | 2020-11-03 | Vineyard Wind Offshore Wind Generation and Transmission Project (QP 700) | Transmission application from Eversource Energy for the upgrade of the existing 115 kV West Barnstable Substation. The proposed project installs two 115 kV breakers at the existing 115 kV West Barnstable substation. | 2024-05-01 | Approved | 2021-01-04
ES-20-T50 | 2020-11-03 | Vineyard Wind Offshore Wind Generation and Transmission Project (QP 700) | Transmission application from Eversource Energy for the installation of a second 345/115 kV Transformer at the West Barnstable Substation. The proposed project installs a second 345/115 kV transformer at the West Barnstable substation. | 2024-05-01 | Approved | 2021-01-04
ES-20-T51 | 2020-11-03 | Vineyard Wind Offshore Wind Generation and Transmission Project (QP 700) | Transmission application from Eversource Energy to convert the planned 115 kV Mid-Cape Line (Line #144) to 345 kV. The proposed project converts the planned 115 kV Mid-Cape Line (RSP ID 1725 – Line 144: PPA ES-18-T11) to 345 kV terminating between the new 345 kV Bourne and the 345 kV West Barnstable substations. | 2024-05-01 | Approved | 2021-01-04
CMP-20-G100 | 2020-11-03 | Augusta Area Solar and Battery Generation Cluster Project | Generator application from Central Maine Power Company ("CMP") on behalf of Redfield Solar I for the installation of a 4.95 MW solar array and 4.99 MW/25 MWh battery at 368 Main Street Lane in Redfield, ME and interconnecting to the Puddledock Road substation via the 262D1 circuit. | 2021-12-31 | Approved | 2021-01-04
CMP-20-G101 | 2020-11-03 | Augusta Area Solar and Battery Generation Cluster Project | Generator application from Central Maine Power Company ("CMP") on behalf of 510 PV Project Development for the installation of a 4.5 MW solar array and 4.99 MW/25 MWh battery at 16 Treasure Lane in Manchester, ME and interconnecting to the Manchester substation via the 233D1 circuit. | 2021-12-31 | Approved | 2021-01-04
CMP-20-G102 | 2020-11-03 | Augusta Area Solar and Battery Generation Cluster Project | Generator application from Central Maine Power Company ("CMP") on behalf of Pinegate Winthrop for the installation of a 2.425 MW solar array in at Maranacook Road in Winthrop, MW and interconnecting to the Winthrop substation via the 256D3 circuit. | 2021-09-30 | Approved | 2021-01-04
CMP-20-G103 | 2020-11-03 | Augusta Area Solar and Battery Generation Cluster Project | Generator application from Central Maine Power Company ("CMP") on behalf of Sunraise Development for the installation of a 3.75 MW solar array and 2.0 MW/4.448 MWh battery at 823 Church Hill Road in Augusta, ME and interconnecting to the Blair Road substation via the 207D2 circuit. | 2020-12-31 | Approved | 2021-01-04
CMP-20-G104 | 2020-11-03 | Augusta Area Solar and Battery Generation Cluster Project | Generator application from Central Maine Power Company ("CMP") on behalf of Sunraise Development for the installation of a 4.4775 MW solar array and 2.25 MW/5.004 MWh battery at Route 3 Belfast Road in China, ME and interconnecting to the South China substation via the 244D2 circuit. | 2020-12-31 | Approved | 2021-01-04
CMP-20-G105 | 2020-11-03 | Augusta Area Solar and Battery Generation Cluster Project | Generator application from Central Maine Power Company ("CMP") on behalf of 510 PV Project Development for the installation of a 4.99 MW solar array and 4.99 MW/26.0 MWh battery at Water Street in Randolph, ME and interconnecting to the Bowman Street substation via the 263D1 circuit. | 2021-12-31 | Approved | 2021-01-04
CMP-20-G106 | 2020-11-03 | Augusta Area Solar and Battery Generation Cluster Project | Generator application from Central Maine Power Company ("CMP") on behalf of Sunraise Development for the installation of a 3.25 MW solar array at 47 Market Street in Gardiner, ME and interconnecting to the Gardiner substation via the 226D2 circuit. | 2020-12-31 | Approved | 2021-01-04
CMP-20-G107 | 2020-11-03 | Augusta Area Solar and Battery Generation Cluster Project | Generator application from Central Maine Power Company ("CMP") on behalf of Consolidated Edison Solutions for the installation of a 4.975 MW solar array and 2.34 MW/5.065 MWh battery at Central Street in Hallowell, ME and interconnecting to the Manchester substation via the 233D2 circuit. | 2021-06-30 | Approved Withdrawn | 1/4/2021 8/17/2021
CMP-20-G108 | 2020-11-03 | Augusta Area Solar and Battery Generation Cluster Project | Generator application from Central Maine Power Company ("CMP") on behalf of Revision Energy for the installation of a 2.0 MW solar array at 45 Shepherd Road in Sidney, ME and interconnecting to the Sidney substation via the 242D1 circuit. | 2021-12-31 | Approved | 2021-01-04
CMP-20-G109 | 2020-11-03 | Augusta Area Solar and Battery Generation Cluster Project | Generator application from Central Maine Power Company ("CMP") on behalf of ISM Solar Development for the installation of a 4.999 MW solar array at 351 Hallowell Road in Chelsea, ME and interconnecting to the Cony Road substation via the 216D2 circuit. | 2021-09-30 | Approved | 2021-01-04
CMP-20-G110 | 2020-11-03 | Augusta Area Solar and Battery Generation Cluster Project | Generator application from Central Maine Power Company ("CMP") on behalf of BD Sidney for the installation of a 2.0 MW solar array at Fields Road in Sidney, ME and interconnecting to the Sidney substation via the 242D1 circuit. | 2021-12-31 | Approved | 2021-01-04
CMP-20-G111 | 2020-11-03 | Augusta Area Solar and Battery Generation Cluster Project | Generator application from Central Maine Power Company ("CMP") on behalf of Revision Energy for the installation of a 4.95 MW solar array at 415 Kelley Road in Pittston, ME and interconnecting to the Bowman Street substation via the 263D1 circuit. | 2021-09-30 | Approved | 2021-01-04
CMP-20-G112 | 2020-11-03 | Augusta Area Solar and Battery Generation Cluster Project | Generator application from Central Maine Power Company ("CMP") on behalf of Maine DOT Environmental Office for the installation of a 4.875 MW solar array at 25 Bond Brook Road in Augusta, ME and interconnecting to the Bond Brook substation via the 208D1 circuit. | 2021-12-31 | Approved | 2021-01-04
CMP-20-G113 | 2020-11-03 | Augusta Area Solar and Battery Generation Cluster Project | Generator application from Central Maine Power Company ("CMP") on behalf of Maine DOT Environmental Office for the installation of a 1.703 MW solar array at Western Avenue in Augusta, ME and interconnecting to the Capital Street substation via the 215D3 circuit. | 2021-12-31 | Approved | 2021-01-04
CMP-20-G114 | 2020-11-03 | Augusta Area Solar and Battery Generation Cluster Project | Generator application from Central Maine Power Company ("CMP") on behalf of Renesola Power Holdings for the installation of a 1.75 MW solar array at Lincoln Street in Richmond, ME and interconnecting to the Richmond substation via the 240D1 circuit. | 2021-12-31 | Approved | 2021-01-04
CMP-20-G115 | 2020-11-03 | Augusta Area Solar and Battery Generation Cluster Project | Generator application from Central Maine Power Company ("CMP") on behalf of Consolidated Edison Solutions for the installation of a 4.0 MW solar array at Highland Avenue in Gardiner, ME and interconnecting to the West Street substation via the 255D1 circuit. | 2021-06-30 | Approved | 2021-01-04
CMP-20-G116 | 2020-11-03 | Augusta Area Solar and Battery Generation Cluster Project | Generator application from Central Maine Power Company ("CMP") on behalf of Revision Energy for the installation of a 2.0 MW solar array at 485 North Belfast Avenue in Augusta, ME and interconnecting to the Augusta K5 substation via the 200D2 circuit. | 2022-06-30 | Approved | 2021-01-04
CMP-20-G117 | 2020-11-03 | Augusta Area Solar and Battery Generation Cluster Project | Generator application from Central Maine Power Company ("CMP") on behalf of USS Togus Solar for the installation of a 4.999 MW solar array at Smith Road in Chelsea, ME and interconnecting to the Cony Road substation via the 216D1 circuit. | 2021-12-31 | Approved | 2021-01-04
NEP-20-G08 | 2020-11-30 | Renweable Energy International eadowbrook Road West Amesbury Solar and Battery Project | Generator application from New England Power Company ("NEP") on behalf of Renewable Energy International for the installation of a 4.99 MW solar array with a 2.5 MW/5.66 MWh battery interconnecting at the West Amesbury Substation via the 275L2 13.2 kV feeder. | 2022-04-20 | Approved | 2021-01-04
ES-20-G175 | 2020-11-05 | Haddam Quarters Solar LLC Haddam Quarters Road Durham Solar | Generator notification from Eversource Energy ("ES") on behalf of Haddam Quarters Solar LLC for the installation of a 2.375 MW solar PV in Durham, CT and interconnecting to the Dooley 30K Station via circuit 30K13. | 2021-03-01 | Notification | 2021-01-04
ES-20-G176 | 2020-11-05 | Mayland Energy Greenwoods Road East Norfolk Solar | Generator notification from Eversource Energy ("ES") on behalf of Mayland Energy for the installation of a 4.0 MW solar PV in Norfolk, CT and interconnecting to the Canton 5R Substation via Circuit 5R80 at 599 Greenwoods Road East in Norfolk, Connecticut. | 2021-12-31 | Notification | 2021-01-04
NEP-20-GNF12 Rev.1 | 2020-11-30 | Altus Power America Mill River Southfield Road New Marlborough Rev.1 | Original proposal for a 2.0MW solar PV project in New Marlborough Massachusetts on the 13.8 kV 1109W1 feeder out of Pleasant Street Substation is revised to add a 2MW / 2.224MWh DC coupled battery. | 2021-04-16 | Notification | 2021-01-04
NEP-20-GNF053 | 2020-11-30 | River Street Associates River Street Halifax Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of River Street Associates, LLC for the installation of a 1.5 MW solar PV and 1.5 MW/3 MWh battery in Halifax, Massachusetts interconnecting to the 912W75 feeder from the Mill Street Substation. | 2022-01-01 | Notification | 2021-01-04
NEP-20-T11 Rev.1 | 2020-11-20 | Otter River Substation Winchendon 69 kV Ring Bus Addition and DVAR | Revision to previously approved one-line diagram with no change to analysis. Additional bays are proposed for the station to enable the station to be built as an open-air station as opposed to a Gas Insulated Substation (GIS) as orginally opposed. | 9/2027 | Notification Withdrawn | 1/4/2021 3/16/2021
ES-20-T67 | 2020-11-30 | Breckwood Substation Springfield Replacement of Step-Down Transformer 3X | Replacement of an existing 37 MVA 117/15.12kV substation step-down transformer. | 2020-12-20 | Notification | 2020-12-24
ES-20-T68 | 2020-11-30 | Gunn Substation Easthampton Replacement of Step-Down Transformer 1X | Replacement of an existing 37.5MVA 115/23kV substation step-down transformer. | 2021-01-21 | Notification | 2020-12-24
CMP-20-G99 | 2020-11-02 | Roxbury Solar Generation and Transmission Project | Generator application from Central Maine Power Company (CMP) on behalf of Roxbury Solar for the installation of a 55.0 MW solar array and interconnecting to the Roxbury substation. | 2022-10-03 | Approved | 2020-12-14
CMP-20-T08 | 2020-11-02 | Roxbury Solar Generation and Transmission Project | Transmission application from Central Maine Power Company (CMP) for the installation of a 115 kV circuit breaker at the Roxbury substation bus #1 adjacent to the KGT1-1 breaker. | 2022-10-03 | Approved | 2020-12-14
CMP-20-T09 | 2020-11-02 | Roxbury Solar Generation and Transmission Project | Transmission application from Central Maine Power Company (CMP) for the installation one 115 kV/34.5 kV/13.8 kV Power Transformer and construct a 400 foot 115 kV transmission generator tie-line breaker at the Roxbury Substation Bus #1 (straight bus configuration) adjacent to the KGT1-1 breaker. | 2022-10-03 | Approved | 2020-12-14
ES-20-T40 | 2020-11-03 | Line 111 Cross Road to Fisher Road 115 kV Line Extension Project | Transmission application from Eversource Energy (ES) for the construction of a new 5.45-mile, radial 115 kV overhead transmission line along an existing Eversource right-of-way between the Cross Road Substation and Fisher Road Substation, both located in the Town of Dartmouth, Massachusetts. | 6/2021 | Approved | 2020-12-11
NEP-20-GNF40 | 2020-11-02 | Verogy Great Road North Smithfield Solar | Generator notification from New England Power Company ("NEP") on behalf of Verogy Great Road Woonsocket Solar for the installation of a 2.125 MW solar PV in North Smithfield, RI and interconnecting to the Woonsocket Substation via the 26W5 13.8 kV feeder. | 2021-09-01 | Notification Withdrawn | 12/14/2020 10/19/2021
NEP-20-GNF52 | 2020-11-02 | Nippawus Solar Renewables West Main Road Portsmouth Solar II | Generator notification from New England Power Company ("NEP") on behalf of Nippawus Solar for the installation of a 1.74 MW solar PV in North Kingston, RI and interconnecting to the Old Baptist Road Substation via the 46F3 12.47 kV feeder. | 2017-12-29 | Notification | 2020-12-14
NEP-19-G30-040 Rev.2 | 2020-11-02 | Energy Development Winchendon Road Royalston Solar Rev.2 | Generator notification from New England Power Company ("NEP") on behalf of Energy Development for the installation of a 2.5 MW solar PV in Royalston, MA and interconnecting to the Royalston Substation via the original 701J1 4.16 kV feeder. | 2022-04-26 | Notification | 2020-12-14
CMP-20-G118 | 2020-11-04 | BD Solar County Road Westbrook Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of BD Solar for the installation of a 4.99 MW solar PV in Westbrook, ME and interconnecting to the Spring Street Substation via the 668D5 12.47 kV feeder. | 2021-12-31 | Notification | 2020-12-14
NEM-20-G05 | 2020-09-23 | Wallingford Solar | Generator notification from NextEra Energy Resources on behalf of Wallingford Renewable Energy for the installation of a 4.99 MW solar array in Wallingford, CT and interconnecting to the Wallingford substation via the 13.8 kV feeder, POI C. | 2020-12-31 | Notification | 2020-12-14
NEM-20-G06 | 2020-09-23 | Wallingford Solar | Generator notification from NextEra Energy Resources on behalf of Wallingford Renewable Energy for the installation of a 4.99 MW solar array in Wallingford, CT and interconnecting to the Wallingford substation via the 13.8 kV feeder, POI A. | 2020-12-31 | Notification | 2020-12-14
NEM-20-G07 | 2020-09-23 | Wallingford Solar | Generator notification from NextEra Energy Resources on behalf of Wallingford Renewable Energy for the installation of a 4.99 MW solar array in Wallingford, CT and interconnecting to the Wallingford substation via the 13.8 kV feeder, POI B. | 2020-12-31 | Notification | 2020-12-14
NEP-20-G03-047 Rev.1 | 2020-11-02 | Zero Point Development Henshaw Street Auburn Solar and Battery Rev.1 | Output decrease to 2.8 MW solar PV and 3.245 MW/6.502 MWh battery in Auburn, MA and interconnecting to the Stafford Street Substation via the original 2236W5 13.8 kV feeder. | 2022-10-01 | Notification Withdrawn | 12/14/2020 2/16/2021
NEP-20-G03-089 Rev.1 | 2020-11-02 | Industrial Engineering George Hill Road Grafton Solar and Battery | Output decrease to 4.3 MW solar PV and 0.615 MW/1.229 MWh battery in Grafton, MA and interconnecting to the Millbury Substation via the original 304W2 13.8 kV feeder. | 2021-11-01 | Notification | 2020-12-14
GMP-20-G01 | 2020-11-04 | CVI Renewables Pitman Road Barre Battery | Generator notification from Green Mountain Power on behalf of CVI Renewables for the installation of a 4.99 MW/14.45 MWh battery in Barre, VT and interconnecting to the Websterville Substation via the 61G2 12.47 kV kV feeder. | 2021-04-21 | Notification | 2020-12-14
NEP-20-T35 | 2020-11-03 | S-145/T146 115 kV Line Reconductoring - North Reading Substation to Wallace Substation | Transmission notification for reconductoring approximately 4.6 miles of the S-145 and T-146 115 kV lines between North Reading Substation and Wallace Substation due to asset condition issues. | 6/2022 | Notification | 2020-12-11
NEP-20-T34 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Treasure Valley 115 kV Breaker and Transformer Addition | Transmission application from New England Power Company ("NEP") to loop the B-128 line through a new in-line circuit breaker and associated equipment, sectionalizing the existing line into Stafford Street – Treasure Valley (B-128) and Treasure Valley– Harriman (B-128N). Also add new 115/13.8 kV, 24/32/40 MVA transformer with associated distribution equipment. | 9/2023 | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-T10 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - East Winchendon Transformer Addition Rev.1 | Transmission application from New England Power Company ("NEP") Replace T1 (115/13.8 kV) with 33/44/55 MVA unit; replace airbreak with circuit switcher. | 9/2023 | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-T20 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Little Rest Road 115 kV Breaker and Transformer Addition | Transmission application from New England Power Company ("NEP") for the installation of a 115 kV breaker at Little Rest Road substation, in-line with the W-175 line. The in-line breaker will sectionalize the existing line into Palmer – Little Rest Road (W-175W) and Little Rest Road – Carpenter Hill (W-175E). Also upgrade the existing 115/13.8 kV transformer to 33/44/55 MVA and add one new 115/13.8 kV transformer to 33/44/55 MVA with associated distribution equipment. | 9/2023 | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-19-G08 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Independence Solar - McCormick Road PV | Generator application from New England Power, on behalf of Independence Solar LLC, for the installation of a 7.94 MW solar array in Spencer, MA and interconnecting to the Meadow Street Substation via the 552L5 13.2 kV feeder. | 2020-12-31 | Approved | 2020-11-09
NEP-19-G30-001 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Seaboard Solar - Ellis Road PV | Generator application from New England Power Company ("NEP"), on behalf of Seaboard Solar for the installation of a 4.875 MW solar PV array interconnecting to the Westminster substation via the 602W3, 13.8 kV feeder in Westminster, MA. | 2020-12-23 | Approved | 2020-11-09
NEP-19-G30-013 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Standard Solar Inc. - Orange Road PV | Generator application from New England Power Company ("NEP"), on behalf of Standard Solar Inc., for the installation of a 4.980 MW solar PV array interconnecting to the Wendell Depot substation via the 705W2, 13.8 kV feeder in Orange, MA. | 2021-06-01 | Approved | 2020-11-09
NEP-19-G30-015 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Borrego Solar - Clark Street PV | Generator application from New England Power Company ("NEP"), on behalf of Borrego Solar, for the installation of a 4.9 MW solar PV array interconnecting to the Crystal Lake substation via the 607W5, 13.8 kV feeder in Gardner, MA. | 2020-11-15 | Approved | 2020-11-09
NEP-19-G30-024 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Clearway Energy Group - Belchertown Road PV | Generator application from New England Power Company ("NEP"), on behalf of Clearway Energy Group, for the installation of a 1.452 MW solar PV array interconnecting to the Ware substation via the 501L3, 13.2 kV feeder in Ware, MA. | 2021-04-01 | Approved | 2020-11-09
NEP-19-G30-030 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Dynamic Energy - Palmer Road PV and Battery | Generator application from New England Power Company ("NEP"), on behalf of Dynamic Energy, for the installation of a 3.000 MW solar PV array and battery interconnecting to the Ware substation via the 501L3, 13.2 kV feeder in Ware, MA. | 2021-02-04 | Approved | 2020-11-09
NEP-19-G30-032 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sunpin Solar Development LLC - Brookfield Road PV | nerator application from New England Power Company ("NEP"), on behalf of Sunpin Solar Development LLC, for the installation of a 2.200 MW solar PV array interconnecting to the Meadow Street substation via the 552L2, 13.2 kV feeder in Spencer, MA. | 2021-01-29 | Approved | 2020-11-09
NEP-19-G30-034 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - AES Distributed Energy, Inc. - Ward Street PV and Battery | Generator application from New England Power Company ("NEP"), on behalf of AES Distributed Energy, Inc., for the installation of a 5.800 MW solar PV array and battery interconnecting to the Lashaway substation via the 525L5, 13.2 kVfeeder in North Brookfield, MA. | 2020-11-20 | Approved | 2020-11-09
NEP-19-G30-040 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Energy Development Group - Winchendon Road PV | Generator application from New England Power Company ("NEP"), on behalf of Energy Development Group, for the installation of a 2.4998 MW solar PV array interconnecting to the Royalston substation via the 701W1, 13.8 kV feeder in Royalston, MA. | 2022-04-26 | Approved | 2020-11-09
NEP-19-G30-057 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Allco Renewable Energy Ltd - Spring Street PV | Generator application from New England Power Company ("NEP"), on behalf of Allco Renewable Energy Ltd, for the installation of a 3.900 MW solar PV array interconnecting to the East Winchendon substation via the 612W4, 13.8 kV feeder in Winchendon, MA. | 2021-03-19 | Approved | 2020-11-09
NEP-20-G03-002 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Princeton Repower LLC - Keyes Road PV | Generator application from New England Power Company ("NEP"), on behalf of Princeton Repower LLC for the installation of a 4.99 MW solar PV array interconnecting to the Crystal Lake substation via the 607W6, 13.8 kV feeder in Gardner, MA. | 2022-10-01 | Approved Withdrawn | 11/9/2020 1/20/2021
NEP-20-G03-011 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - Bouthelier Road PV and BESS | Generator application from New England Power Company ("NEP"), on behalf of Zero Point Development for the installation of a 4.95 MW solar PV array and 3.245MW/6.502MWh battery interconnecting to the Stafford Street substation via the 2236W3, 13.8 kV feeder in Leicester, MA. | 2022-10-01 | Approved Withdrawn | 11/9/2020 2/16/2021
NEP-20-G03-019 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Melink Solar Development - Greenwich Plain Road PV and BESS | Generator application from New England Power Company ("NEP"), on behalf of Melink Solar Development for the installation of a 2.2 MW solar PV array and 2.5MW/5.0MWh battery interconnecting to the Ware substation via the 501L3, 13.2 kV feeder in Ware, MA. | 2022-10-01 | Approved Withdrawn | 11/9/2020 2/16/2021
NEP-20-G03-020 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Melink Solar Development - Ash Street PV and BESS | Generator application from New England Power Company ("NEP"), on behalf of Melink Solar Development for the installation of a 4.4 MW solar PV array and 4.0MW/8.0MWh battery interconnecting to the Meadow Street substation via the 552L4, 13.2 kV feeder in Spencer, MA. | 2021-06-01 | Approved Withdrawn | 11/9/2020 2/16/2021
NEP-20-G03-024 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sunpin Solar Development - Baldwinville Road PV | Generator application from New England Power Company ("NEP"), on behalf of Sunpin Solar Development for the installation of a 4.99 MW solar PV array interconnecting to the East Winchendon substation via the 612W4, 13.8 kV feeder in Winchendon, MA. | 2021-06-01 | Approved Withdrawn | 11/9/2020 2/16/2021
NEP-20-G03-044 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sunpin Solar Development - Draper Road PV | Generator application from New England Power Company ("NEP"), on behalf of Sunpin Solar Development for the installation of a 4.99 MW solar PV array interconnecting to the Meadow Street substation via the 552L3, 13.2 kv feeder in East Brookfield, MA. | 2021-06-01 | Approved Withdrawn | 11/9/2020 2/16/2021
NEP-20-G03-048 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - Ware Road PV and BESS | Generator application from New England Power Company ("NEP"), on behalf of Zero Point Development for the installation of a 4.95 MW solar PV array and 2.45MW/4.8MWh battery interconnecting to the Belchertown substation via the 509L1, 13.2 kV feeder in Belchertown, MA. | 2021-06-01 | Approved Withdrawn | 11/9/2020 2/16/2021
NEP-20-G03-052 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Cypress Creek Renewables - Bemis Road PV and BESS | Generator application from New England Power Company ("NEP"), on behalf of Cypress Creek Renewables for the installation of a 2.5 MW solar PV array and 1.5MW/3.0MWh battery interconnecting to the East Winchendon 612W4, 13.8 kV feeder in Winchendon, MA. | 2022-10-01 | Approved Withdrawn | 11/9/2020 1/20/2021
NEP-20-G03-055 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Heartwood Group - Kinzer Drive and BESS | Generator application from New England Power Company ("NEP"), on behalf of Heartwood Group for the installation of a 2.0 MW solar PV array and 1.5MW/3.0MWh battery interconnecting to the Crystal Lake 607W1, 13.8 kV feeder in Gardner, MA. | 2022-10-01 | Approved Withdrawn | 11/9/2020 2/16/2021
NEP-20-G03-063 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Allco Renewable Energy Ltd - Spring Street PV | Generator application from New England Power Company ("NEP"), on behalf of Allco Renewable Energy Ltd, for the installation of a 4.99 MW solar PV array interconnecting to the East Winchendon substation via the 612W3, 13.8 kV feeder in Winchendon, MA. | 2021-06-01 | Approved Withdrawn | 11/9/2020 2/16/2021
NEP-20-G03-064 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Allco Renewable Energy Ltd - Teel Road PV | Generator application from New England Power Company ("NEP"), on behalf of Allco Renewable Energy Ltd, for the installation of a 4.99 MW solar PV array interconnecting to the East Winchendon substation via the 612W3, 13.8 kV feeder in Winchendon, MA. | 2022-10-01 | Approved Withdrawn | 11/9/2020 2/16/2021
NEP-20-G03-086 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sunpin Solar Development - Sizer Drive PV and BESS | Generator application from New England Power Company ("NEP"), on behalf of Sunpin Solar Development for the installation of a 3.0 MW solar PV array and 1.0MW/1.886MWh battery interconnecting to the Little Rest Road substation via the 516L5, 13.2 kV feeder in Wales, MA. | 2021-06-01 | Approved | 2020-11-09
NEP-20-G03-096 Rev.1 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - UGT - Keyes Road PV3 | Generator application from New England Power Company ("NEP"), on behalf of UGT for the installation of a 4.99 MW solar PV array interconnecting to the Crystal Lake substation via the 607W1, 13.8 kV feeder in Gardner, MA. | 2022-10-01 | Approved Withdrawn | 11/9/2020 1/20/2021
NEP-20-G03-097 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sunpin Solar - Conant Road PV and BESS | Generator application from New England Power Company ("NEP"), on behalf of Sunpin Solar for the installation of a 4.2 MW solar PV array and 3.0MW/5.658MWh battery interconnecting to the Wendell Depot substation via the 705W4, 13.8 kV feeder in Athol, MA. | 2022-10-01 | Approved Withdrawn | 11/9/2020 2/16/2021
NEP-20-G03-098 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Kearsarge Solar LLC - Barre Road PV and BESS | Generator application from New England Power Company ("NEP"), on behalf of Kearsarge Solar LLC for the installation of a 4.4 MW solar PV array and 3.15MW/12MWh battery interconnecting to the Barre substation via the 604W2, 13.8 kV feeder in Hardwick, MA. | 2022-10-01 | Approved Withdrawn | 11/9/2020 2/16/2021
NEP-20-G03-099 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Cypress Creek Renewables - Coldbrook Road PV and BESS | Generator application from New England Power Company ("NEP"), on behalf of Cypress Creek Renewables for the installation of a 4.0 MW solar PV array and 3.0MW/6.0MWh battery interconnecting to the Barre substation via the 604W2, 13.8 kV feeder in Oakham, MA. | 2022-10-01 | Approved Withdrawn | 11/9/2020 2/16/2021
NEP-20-G03-100 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Williamsville Road Solar - Williamsville Road PV and BESS | Generator application from New England Power Company ("NEP"), on behalf of Williamsville Road Solar for the installation of a 3.0 MW solar PV array and 1.5MW/2.5MWh battery interconnecting to the Barre substation via the 604W4, 13.8 kV feeder in Hubbardston, MA. | 2022-10-01 | Approved Withdrawn | 11/9/2020 2/16/2021
NEP-20-G03-101 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project -Green Street Power Partners - Simplex Drive PV | Generator application from New England Power Company ("NEP"), on behalf of Green Street Power Partners for the installation of a 3.78 MW solar PV array interconnecting to the Ashburnham substation via the 610W3, 13.8 kV feeder in Westminster, MA. | 2022-10-01 | Approved Withdrawn | 11/9/2020 1/20/2021
NEP-20-G03-102 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sunpin Solar - New Athol Road PV and BESS | Generator application from New England Power Company ("NEP"), on behalf of Sunpin Solar for the installation of a 3.0 MW solar PV array and 2.0MW/5.998MWh battery interconnecting to the Wendell Depot substation via the 705W4, 13.8 kV feeder in Petersham, MA. | 2022-10-01 | Approved Withdrawn | 11/9/2020 2/16/2021
NEP-20-G03-103 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sol Systems - Maple Avenue PV and BESS | Generator application from New England Power Company ("NEP"), on behalf of Sol Systems for the installation of a 4.998 MW solar PV array and 3.5MW/7.672MWh battery interconnecting to the Treasure Valley substation via the 55W1, 13.8 kV feeder in Rutland, MA. | 2022-10-01 | Approved Withdrawn | 11/9/2020 2/16/2021
NEP-20-G03-104 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sol Systems - Wheeler Road PV and BESS | Generator application from New England Power Company ("NEP"), on behalf of Sol Systems for the installation of a 4.998 MW solar PV array and 3.5MW/7.672MWh battery interconnecting to the Treasure Valley substation via the 55W1, 13.8 kV feeder in Rutland, MA. | 2022-10-01 | Approved Withdrawn | 11/9/2020 2/16/2021
NEP-20-G03-105 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Ameresco - Otter River Road PV | Generator application from New England Power Company ("NEP"), on behalf of Ameresco for the installation of a 2.5 MW solar PV array interconnecting to the Crystal Lake substation via the 607W5, 13.8 kV feeder in Gardner, MA. | In-service | Approved | 2020-11-09
NEP-20-G03-106 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Borrego Solar - Happy Hollow Road PV and Battery | Generator application from New England Power Company ("NEP"), on behalf of Borrego Solar for the installation of a 4.95 MW solar PV array and 3.3MW/6.4MWh battery interconnecting to the Crystal Lake substation via the 607W5, 13.8 kV feeder in Winchendon, MA. | In-service | Approved | 2020-11-09
NEP-20-G03-107 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Nexamp - Pitcherville Road PV | Generator application from New England Power Company ("NEP"), on behalf of Nexamp for the installation of a 2.8 MW solar PV array interconnecting to the Crystal Lake substation via the 607W2, 13.8 kV feeder in Hubbardston, MA. | In-service | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-G03-108 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Borrego Solar - West Livermore Hill Road PV and BESS | Generator application from New England Power Company ("NEP"), on behalf of Borrego Solar for the installation of a 4.99 MW solar PV array and 2.31MW/4.62MWh battery interconnecting to the Crystal Lake substation via the 607W4, 13.8 kV feeder in Westminster, MA. | In-service | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-G03-109 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Borrego Solar - Gardner Road PV | Generator application from New England Power Company ("NEP"), on behalf of Borrego Solar for the installation of a 1.92 MW solar PV array interconnecting to the Crystal Lake substation via the 607W2, 13.8 kV feeder in Hubbardston, MA. | In-service | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-G03-110 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Dynamic Energy Solutions - Lincoln Avenue PV | Generator application from New England Power Company ("NEP"), on behalf of Dynamic Energy Solutions for the installation of a 8.04 MW solar PV array interconnecting to the East Winchendon substation via the 612W2, 13.8 kV feeder in Winchendon, MA. | In-service | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-G03-111 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Dynamic Energy Solutions - Boston Post Road PV | Generator application from New England Power Company ("NEP"), on behalf of Dynamic Energy Solutions for the installation of a 4.5 MW solar PV array interconnecting to the Lashaway substation via the 525L4, 13.2 kV feeder in West Brookfield, MA. | In-service | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-G03-112 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Dynamic Energy Solutions - Adams Street PV and BESS | Generator application from New England Power Company ("NEP"), on behalf of Dynamic Energy Solutions for the installation of a 4.98 MW solar PV array and 3.0MW/6.30MWh battery interconnecting to the Lashaway substation via the 525L3, 13.2 kV feeder in East Brookfield, MA. | 2020-11-19 | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-G03-113 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Nexamp - Union Road PV | Generator application from New England Power Company ("NEP"), on behalf of Nexamp for the installation of a 2.0 MW solar PV array interconnecting to the Little Rest Road substation via the 516L5, 13.2 feeder in Wales, MA. | In-service | Approved | 2020-11-09
NEP-20-G03-114 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Spencer Landfill Solar, LLC - PV | Generator application from New England Power Company ("NEP"), on behalf of Spencer Landfill Solar LLC for the installation of a 2.45 MW solar PV array interconnecting to the Meadow Street substation via the 552L1, 13.2 kV feeder in Spencer, MA. | In-service | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-G03-115 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - Wilson Road PV and BESS | Generator application from New England Power Company ("NEP"), on behalf of Zero Point Development for the installation of a 2.0 MW solar PV array and 0.98MW/1.96MWh battery interconnecting to the Meadow Street substation via the 552L4, 13.2 kV feeder in Spencer, MA. | In-service | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-G03-116 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Navisun - Old Webster Road PV | Generator application from New England Power Company ("NEP"), on behalf of Navisun for the installation of a 1.74 MW solar PV array interconnecting to the North Oxford substation via the 406L5, 13.2 kV feeder in Oxford, MA. | In-service | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-G03-117 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Oxford Community Solar LLC - PV | Generator application from New England Power Company ("NEP"), on behalf of Oxford Community Solar LLC for the installation of a 4.0 MW solar PV array interconnecting to the North Oxford substation via the 406L5, 13.2 kV feeder in Oxford, MA. | In-service | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-G03-118 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - Boutilier Street PV | Generator application from New England Power Company ("NEP"), on behalf of Zero Point Development for the installation of a 2.886 MW solar PV array interconnectiong to the Stafford Street substation via the 2236W3, 13.8 kV feeder in Leicester, MA. | In-service | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-G03-119 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - GLC (MA) Wilson, LLC - Wilson Street PV | Generator application from New England Power Company ("NEP"), on behalf of GLC (MA) Wilson, LLC for the installation of a 2.0 MW solar PV array interconnecting to the Stafford Street substation via the 2236W3, 13.8 kV feeder in Spencer, MA. | In-service | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-G03-120 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Mass PV 7 LLC - Auburn Street PV | Generator application from New England Power Company ("NEP"), on behalf of Mass PV 7 LLC for the installation of a 4.833 MW solar PV array interconnecting to the Stafford Street substation via the 2236W2, 13.8 kV feeder in Leicestr, MA. | In-service | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-G03-121 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - Paxton Road PV | Generator application from New England Power Company ("NEP"), on behalf of Zero Point Development for the installation of a 2.0 MW solar PV array interconnecting to the Stafford Street substation via the 2236W3, 13.8 kV feeder in Spencer, MA. | In-service | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-G03-122 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Borrego Solar - Auburn Street PV | Generator application from New England Power Company ("NEP"), on behalf of Borrego Solar for the installation of a 4.92 MW solar PV array interconnecting to the Stafford Street substation via the 2236W4, 13.8 feeder in Leicester, MA. | In-service | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-G03-123 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Seaboard Solar - Leicester Street PV and BESS | Generator application from New England Power Company ("NEP"), on behalf of Seaboard Solar for the installation of a 4.875 MW solar PV array and 4.875MW/12.714MWh battery interconnecting to the Stafford Street substation via the 2236W5, 13.8 kV feeder in Auburn, MA. | 2022-01-07 | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-G03-124 | 2020-10-06 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Syncarpha - Mulberry Street PV and BESS | Generator application from New England Power Company ("NEP"), on behalf of Syncarpha for the installation of a 2.592 MW solar PV array and 2.0MW/4.0MWh battery interconnecting to the Stafford Street substation via the 2236W2, 13.8 kV feeder in Leicester, MA. | 2021-03-30 | Approved Withdrawn | 11/9/2020 3/16/2021
NEP-20-T33 | 2020-10-06 | North Marlborough Substation Transformer Addition | Transmission application from New England Power Company (NEP) for the addition of a 40 MVA 115/13.8 kV transformer at the North Marlborough substation. | 6/2020 | Approved | 2020-11-10
NEP-20-GNF49 | 2020-10-05 | Econox Renewables West Main Road Portsmouth Solar | Generator notification from New England Power Company ("NEP"), on behalf of Econox Renewables for the installation of a 2.52 MW solar PV in Portsmouth, RI and interconnecting to the Dexter Substation via the 36W42 13.8 kV feeder. | 2021-12-01 | Notification Withdrawn | 11/9/2020 1/16/2024
NEP-20-GNF50 | 2020-10-05 | Econox Renewables West Main Road Portsmouth Solar | Generator notification from New England Power Company ("NEP"), on behalf of Econox Renewables for the installation of a 2.52 MW solar PV in Portsmouth, RI and interconnecting to the Dexter Substation via the 37W42 13.8 kV feeder. | 2021-12-01 | Notification Withdrawn | 11/9/2020 1/16/2024
NEP-20-GNF51 | 2020-10-05 | Kearsarge Solar West Shore Road Porstmouth Solar | Generator notification from New England Power Company ("NEP"), on behalf of Kearsarge Solar West Shore Road Portsmouth Solar for the installation of a 4.875 MW solar PV in Portsmouth, RI and interconnecting to the Dexter Substation via the 36W42 13.8 kV feeder. | 2021-12-01 | Notification | 2020-11-09
VELCO-20-GNF01 | 2020-09-03 | VEPP ER Salvage Yard Laporte Road Morristown Solar | Generator notification from from VELCO, on behalf of VEPP for the installation of a 2.1 MW solar PV in Morristown, VT and interconnecting to the Morrisville Substation via the S22 12.5 kV feeder. | 2020-12-01 | Notification | 2020-11-09
ES-20-G173 | 2020-09-24 | Mayland Energy Lime Rock Road Lakeville Solar | Generator notification from Eversource Energy ("ES") on behalf of Mayland Energy for the installation of a 1.5 MW solar PV in Lakeville, CT and interconnecting to the Falls Village Substation via the 4L09 13.2 kV feeder. | 2021-12-31 | Notification Withdrawn | 11/9/2020 9/20/2022
CMP-20-G95 | 2020-10-06 | Wyman Hill Solar Wyman Hill Road Rumford Solar | Generator notification from Central Maine Power ("CMP") on behalf of Wyman Hill Solar for the installation of a 3.984 MW solar PV in Rumford, ME and interconnecting to the Rumford Substation via the 447D2 12.47 kV feeder. | 2021-09-30 | Notification | 2020-11-09
CMP-20-G88 | 2020-10-06 | Jay Field Solar Main Street Jay Solar | Generator notification from Central Maine Power ("CMP") on behalf of Jay Field Solar for the installation of a 3.54 MW solar PV in Jay, ME and interconnecting to the Riley Substation via the 449D2 12.47 kV feeder. | 2022-04-01 | Notification Withdrawn | 11/9/2020 8/17/2021
CMP-20-G86 | 2020-10-06 | Revision Energy Souther Road Livermore Falls Solar | Generator notification from Central Maine Power ("CMP") on behalf of Revision Energy for the installation of a 3.892 MW solar PV in Livermore Falls, ME and interconnecting to the Livermore Falls Substation via the 428D3 12.47 kV feeder. | 2021-09-01 | Notification | 2020-11-09
VPPSA-20-G01 | 2020-10-12 | CF North Haven Rimmon Road North Haven Solar | Generator notification from Vermont Public Power Supply Authority on behalf of CF North Haven for the installation of a 4.98 MW solar PV in North Haven, CT and interconnecting to the Quinnipiac Substation via the 1542 13.8 kV feeder. | 2020-11-06 | Notification | 2020-11-09
CMP-20-G52 Rev.1 | 2020-10-06 | Nutting Ridge Solar Oxford Road Otisfield Solar and Battery Rev.1 | Generator notification from Central Maine Power ("CMP") on behalf of Nutting Ridge Solar for the installation of a 3.88 MW solar PV and 4.0MW/16.0MWh battery addition in Otisfield, ME and interconnecting to the Casco Tap Substation via the 463D1 12.47 kV feeder. | 2021-06-30 | Notification | 2020-11-09
CMP-20-G92 | 2020-10-06 | Clean Tap Energy Portland Road Gray Solar and Battery | Generator notification from Central Maine Power ("CMP") on behalf of Clean Tap Energy for the installation of a 2.0 MW solar PV and 1.0MW/2.224MWh battery addition in Gray, ME and interconnecting to the Gray Substation via the 416D3 12.47 kV feeder. | 2021-09-01 | Notification | 2020-11-09
ES-20-T28 | 2020-10-01 | Line 1768 Rebuild | Transmission notification from Eversource Energy ("ES") to partially rebuild the 11.35 overhead 115 kV Line 1768 from East Granby Junction to the CT/MA border | 6/2021 | Notification | 2020-11-06
ES-20-T29 | 2020-09-10 | Horton Cove Line 100 Structure Rebuild | Transmission notification from Eversource Energy ("ES") to rebuild the 0.85 miles of Line 100 in Montville and over Horton Cove from 556-kcmil ACSR to 1590-kcmil ACSS. | 9/2021 | Notification | 2020-11-06
ES-20-T30 | 2020-09-10 | Horton Cove Line 1080 Structure Rebuild | Transmission notification from Eversource Energy ("ES") to rebuild the 0.6-miles of Line 1080 in Montville and over Horton Cove from 1272-kcmil ACSR to 1590-kcmil ACSS. | 9/2021 | Notification | 2020-11-06
ES-20-T31 | 2020-09-10 | Horton Cove Line 1280 Structure Rebuild | Transmission notification from Eversource Energy ("ES") to rebuild the 0.6-miles of Line 1280 in Montville and over Horton Cove from 1272-kcmil ACSR to 1590-kcmil ACSS. | 9/2021 | Notification | 2020-11-06
ES-20-T32 | 2020-09-10 | Horton Cove Line 1410 Structure Rebuild | Transmission notification from Eversource Energy ("ES") to rebuild the 0.85-miles of Line 1410 in Montville and over Horton Cove from 556-kcmil ACSR to 1590-kcmil ACSS. | 9/2021 | Notification | 2020-11-06
NRG-20-X01 | 2020-09-11 | Middletown 10 AVR Replacement | Generator application from NRG Power Marketing ("NRG") for the replacement of the Middletown 10 AVR unit with a new Basler DECS250 static exciter. | 2022-10-11 | Approved | 2020-10-05
ES-16-T07 Rev.1 | 2020-09-10 | Sudbury Substation to Hudson Light and Power Substation 115 kV Underground Cable Rev.1 | Transmission application from Eversource Energy ("ES") for the installation of a new 115 kV line (384-501) 9.1 mile underground cable from Eversource’s Sudbury Substation to Hudson Light & Power’s Hudson Substation and adding one 115kV breaker (#7) at Sudbury Substation. | 12/2023 | Approved | 2020-10-05
NEP-19-G30-003 Rev.1 | 2020-09-08 | Nexamp Solar Barre Road Oakham Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Nexamp Solar for the instalation of a 2.0 MW solar PV (reduced from 2.2 MWs) and removal of battery in Oakham, MA and interconnecting to the Barre Substation via the 604W2 13.8 kV feeder. | 2020-10-05 | Notification | 2020-10-05
NEP-20-G04-010 Rev.1 | 2020-09-08 | Green Development Exeter Road Exeter Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Green Development for the installation of a 2.0 MW solar PV in Exeter, RI and interconnecting to the Tower Hill Substation via the 88F1, 12.47kV feeder. | 2021-07-15 | Notification | 2020-10-05
NEP-20-G04-011 Rev.1 | 2020-09-08 | ISM Solar Development Stilson Road Richmond Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of ISM Solar Development for the installation of a 3.5 MW solar PV in Richmond, RI and interconnecting to the Kenyon Substation via the 68F4, 12.47kV feeder. | 2021-07-15 | Notification | 2020-10-05
NEP-20-G04-021 Rev.1 | 2020-09-08 | GD Exeter Ten Rod II Ten Rod Road Exeter Solar Rev. 1 | Generator notification from New England Power Company ("NEP") on behalf of GD Exeter Ten Road II for the installation of a 2.6 MW solar PV in Exeter, RI and interconnecting to the Wickford Junction Substation via the 34.5kV feeder. | 2021-07-15 | Notification | 2020-10-05
NEP-20-G04-030 Rev.1 | 2020-09-08 | Richmond Beaver River I Beaver River Road West Kingston Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of GD Richmond Beaver River I for the installation of a 5.3 MW solar PV in West Kingston, RI and interconnecting to the Kenyon Substation via the 68F1 12.47kV feeder. | 2021-07-15 | Notification | 2020-10-05
NEP-20-G04-033 Rev.1 | 2020-09-08 | TPE Development Bates Trail West Greenwich Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of TPE development for the installation of a 9.8 MW solar PV in West Greenwich, RI and interconnecting to the Kent County Substation via the 3311 34.5kV feeder. | 2021-07-15 | Notification Withdrawn | 10/5/2020 1/19/2022
NEP-20-G04-037 Rev.1 | 2020-09-08 | Ameresco Springbrook Road Westerly Solar | Generator notification from New England Power Company ("NEP") on behalf of Ameresco for the installation of a 6.5 MW solar PV in Westerly, RI and interconnecting to the Wood River Substation via the 85T2 34.5kV feeder. | 2021-07-15 | Notification | 2020-10-05
NEP-20-G04-023 Rev.1 | 2020-09-08 | Green Development Stamp Place Exeter Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Green Development for the installation of a 7.04 MW solar PV in Exeter, RI and interconnecting to the Wickford Junction Substation via the 89T2 34.5kV feeder. | 2021-07-15 | Notification | 2020-10-05
CMP-20-G82 | 2020-09-09 | MSD Wiscassett Chewonki Neck Road Wiscassett Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of MSD Wiscassett for the installation of a 4.95 MW solar PV in Wiscassett, ME and interconnecting to the Maine Yankee Substation via the 274D1 12.47kV feeder. | 2021-09-30 | Notification | 2020-10-05
CMP-20-G83 | 2020-09-09 | ISM Pratt and Whitney High Street North Berwick Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of ISM Solar Pratt and Whitney for the installation of a 4.999 MW solar PV in North Berwick, ME and interconnecting to the CMP Pratt and Whitney Substation via the 661D1 12.47kV feeder. | 2021-09-30 | Notification | 2020-10-05
CMP-20-G84 | 2020-09-09 | Dimension ME 1 Briggs Street West Paris Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of Dimension ME 1 for the installation of a 2.5 MW solar PV in West Paris, ME and interconnecting to the CMP Trapp Corner Substation via the 453D1 12.47kV feeder. | 2021-12-31 | Notification | 2020-10-05
CMP-20-G85 | 2020-09-09 | Maine DG Holdings Longroad Athens Route 150 Harmony Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of Maine DG Holdings for the installation of a 4.91 MW solar PV in Harmony, ME and interconnecting to the Athens Substation via the 827D2 12.47kV feeder. | 2021-12-31 | Notification | 2020-10-05
CMP-20-G94 | 2020-09-09 | ISM Solar Development Sheperds Acres Estate South Paris Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of ISM Solar Development for the installation of a 2.91 MW solar PV in South Paris, ME and interconnecting to the CMP Paris Tap Substation via the 409D1 12.47kV feeder. | 2021-09-30 | Notification | 2020-10-05
CMP-20-G98 | 2020-09-09 | Revision Energy Highland Avenue South Portland Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of Revision Energy for the installation of a 2.5 MW solar PV in South Portland, ME and interconnecting to the Pleasant Hill Substation via the 644D2 12.47kV feeder. | 2021-09-30 | Notification | 2020-10-05
CMP-20-G58 | 2020-09-09 | TPE Development Waldoboro Road Washington Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of TPE Development for the installation of a 4.0 MW solar PV in Washington, ME and interconnecting to the Stickney’s Corner Substation via the 245D1 12.47kV feeder. | 2021-09-30 | Notification | 2020-10-05
CMP-20-G87 | 2020-09-09 | NBD Solar Main Street Waterboro Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of NBD Solar for the installation of a 4.998 MW solar PV in Waterboro, ME and interconnecting to the CMP Waterboro Substation via the 671D2 12.47kV feeder. | 2021-06-30 | Notification | 2020-10-05
CMP-20-G93 | 2020-09-09 | Carrabassett Solar I Route 16 Carrabassett Valley Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of Carrabassett Solar I for the installation of a 4.995 MW solar PV in Carrabassett Valley, ME and interconnecting to the Bigelow Substation via the 882D1 34.5kV feeder. | 2021-07-31 | Notification | 2020-10-05
CMP-20-G91 | 2020-09-09 | Sol CES Projects Harpswell Road Brunswick Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of Sol CES Projects for the installation of a 4.999 MW solar PV in Brunswick, ME and interconnecting to the Brunswick West Side Substation via the 213D1 12.47kV feeder. | 2021-09-01 | Notification | 2020-10-05
CMP-20-G97 | 2020-09-09 | ISM Solar Buttermilk Lane Thomaston Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of ISM Solar for the installation of a 4.999 MW solar PV in Thomaston, ME and interconnecting to the CMP Park Street Substation via the 293D7 12.47kV feeder. | 2021-09-30 | Notification | 2020-10-05
NEP-19-GNF37 Rev.1 | 2020-09-06 | Nexamp Solar Spring Street Ranklin Solar and Battery Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Nexamp Solar for the installation of a 4.99 MW solar PV and 3.0 MW/6.0 MWh battery addition in Franklin, MA and interconnecting to the Beaver Pond Substation via the 344W5 13.8 kV feeder. | 2021-09-03 | Notification | 2020-10-05
NEP-19-GNF67 Rev.1 | 2020-09-06 | Astrum Solar Hobomock Street Pembroke Solar and Battery Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Astrum Solar for the installation of a 3.2 MW solar PV and 1.5 MW/4.637 MWh battery addition in Pembroke, MA and interconnecting to the Beaver Pond Substation via the 910W25 13.8 kV feeder. | 2021-09-01 | Notification | 2020-10-05
NEP-20-GNF02 Rev.1 | 2020-09-06 | CEC Development River Road Williamsburg Solar and Battery Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of CEC Development for the installation of a 3.9 MW solar PV (reduced from 4.675 MWs) and 4.0 MW/8.0 MWh battery in Williamsburg, MA and interconnecting to the Florence Junction Substation via the 909W1 13.8 kV feeder. | 2022-09-29 | Notification Withdrawn | 10/8/2020 5/17/2022
NEP-20-GNF19 | 2020-09-06 | Kearsarge Solar Cabot Street Beverly Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Kearsarge Solar for the installation of a 1.342 MW solar PV and 0.5 MW/2.224 MWh battery in Beverly, MA and interconnecting to the Beverly Substation via the 12L4 13.2 kV feeder. | 2021-09-01 | Notification Withdrawn | 10/5/2020 5/17/2022
NEP-19-G30-002 Rev.1 | 2020-09-08 | Seaboard Solar Leicester Street Auburn Solar and Battery Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Seaboard Solar for the installation of a 4.875 MW solar PV and 4.875 MW/12.714 MWh battery addition in Auburn, MA and interconnecting to the Pondville Substation via the 26W1 13.8kV feeder. | 2022-01-07 | Notification Withdrawn | 10/5/2020 10/20/2020
NEP-20-G06-004 Rev.1 | 2020-09-08 | TJA Clean Energy Blackstone Street Blackstone Solar and Battery Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of TJA Clean Energy for the installation of a 4.99 MW solar PV and 3.0 MW/6.672 MWh battery addition in Blackstone, MA and interconnecting to the Mendon Substation via the 332W1 13.8kV feeder. | 2022-01-10 | Notification | 2020-10-05
CMP-20-G90 | 2020-09-09 | 510 PV Project Development Acadia Highway Orland Solar and Battery | Generator notification from Central Maine Power Company ("CMP") on behalf of 510 PV Project Development for the installation of a 4.99 MW solar PV and 4.99 MW/20 MWh battery in Orland, ME and interconnecting to the Bucksport Substation via the 806D2 34.5kV feeder. | 2021-10-01 | Notification | 2020-10-05
CMP-20-G96 | 2020-09-09 | 510 PV Project Development Brackett Road Gorham Solar and Battery | Generator notification from Central Maine Power Company ("CMP") on behalf of 510 PV Project Development for the installation of a 4.99 MW solar PV and 4.99 MW/26 MWh battery in Gorham, ME and interconnecting to the Westbrook Substation via the 674D2 12.47kV feeder. | 2022-02-01 | Notification | 2020-10-05
NEP-20-GNF48 | 2020-09-06 | Renew PC 10 Equipment Chelmsford Street Lowell Combined Heat and Power (CHP) Generator and Battery | Generator notification from New England Power Company ("NEP") on behalf of TJA Renew PC 10 Equipment for the installation of a 3.279 MW CHP Generator and .630 MW/1.554 MWh battery in Lowell, MA and interconnecting to the Quebec Street Substation via the 319 23kV feeder. | 2021-11-01 | Notification | 2020-10-05
ES-20-T37 | 2020-08-20 | Partial Rebuild of Line 1191 | Transmission noticiation from Eversource Energy ("ES") to partially rebuild Line 1191 replacing existing structures and associated 2/0 copper and 556-kcmil ACSR conductor with 1272-kcmil ACSS conductor. | 2022-03-31 | Notification | 2020-10-05
NRG-20-G50 | 2020-07-28 | ESPN Natural Gas Generator Project | Generator application from NRG Curtailment Solutions (NRG) on behalf of ESPN for the installation of a 9.876 natural gas generator in Bristol, CT. | 2020-09-04 | Approved | 2020-08-28
VP-20-G18 | 2020-07-09 | Nine Dragons Old Town Mill Steam Generator Project | Generator application from Versant Power ("VP") on behalf of ND OTM, for the installation of a 15.92 steam generator connecting to the Graham substation via the 44 kV Line 5 in Old Town, ME. | 2020-09-15 | Approved | 2020-08-28
CMP-20-G73 | 2020-08-04 | BWC Maces Pond Rockland Road Rockport Solar | Generator notification from Central Maine Power ("CMP") on behalf of BWC Maces Pond for the installation of a 3.55 MW solar PV in Rockport, ME and interconnecting to the Meadow Road Substation via the 270D2 12.47 kV feeder. | 2020-12-30 | Notification | 2020-08-31
ES-20-G171 | 2020-07-28 | Citrine Power Main Street Portland Solar | Generator notification from Eversource Energy (ES) on behalf of Citrine Power for the installation of a 1.975 MW solar PV in Portland, CT and interconnecting to the Portland 21H Substation via the 21H14 12.47 kV feeder. | 2021-12-31 | Notification Withdrawn | 8/31/2020 4/17/2024
CMP-20-G75 | 2020-08-04 | BD Solar Rangeley Pressure Ridge Road Rangeley Solar | Generator notification from Central Maine Power ("CMP") on behalf of BD Solar Rangeley for the installation of a 2.985 MW solar PV in Rangeley, ME and interconnecting to the Rangeley Substation via the 875D2 12.47 kV feeder. | 2021-07-01 | Notification | 2020-08-31
CMP-20-G78 | 2020-08-04 | Edgecomb Solar I Dodge Road Edgecomb Solar | Generator notification from Central Maine Power ("CMP") on behalf of Edgecomb Solar I for the installation of a 4.901 MW solar PV in Edgecomb, ME and interconnecting to the Edgecomb Substation via the 223D1 12.47 kV feeder. | 2021-01-31 | Notification | 2020-08-31
CMP-20-G77 | 2020-08-04 | NRS Bethel Solar Walkers Mill Road Bethel Solar | Generator notification from Central Maine Power ("CMP") on behalf of NRS Bethel Solar for the installation of a 2.007 MW solar PV in Bethel, ME and interconnecting to the Lockes Mill Substation via the 429D1V circuit. | 2021-07-30 | Notification | 2020-08-31
CMP-20-G79 | 2020-08-04 | NESG SCF Maine 1 Holdco Route 236 Berwick Solar | Generator notification from Central Maine Power ("CMP") on behalf of NESG SCF Maine 1 Holdco for the installation of a 1.75 MW solar PV in Berwick, ME and interconnecting to the Berwick Substation via the 603D2 12.47 kV circuit. | 2020-12-31 | Notification | 2020-08-31
CMP-20-G56 | 2020-08-04 | NextGrid Roderick Road Winslow Solar | Generator notification from Central Maine Power ("CMP") on behalf of NextGrid for the installation of a 4.6 MW solar PV in Winslow, ME and interconnecting to the Winslow Substation via the 870D2 12.47 kV circuit. | 2020-12-30 | Notification | 2020-08-31
CMP-20-G72 | 2020-08-04 | Wiscasset Solar I Lowelltown Road Wiscasset Solar | Generator notification from Central Maine Power ("CMP") on behalf of Wiscasset Solar I for the installation of a 4.925 MW solar PV in Wiscasset, ME and interconnecting to the Messina Substation via the 238D1 12.47 kV circuit. | 2021-01-31 | Notification | 2020-08-31
CMP-20-G15 Rev.1 | 2020-08-04 | BWC Swan Pond Creek South Street Dayton Solar Rev.1 | Generator notification from Central Maine Power ("CMP") on behalf of BWC Swan Pond Creek for the installation of a 4.99 MW solar PV in Dayton, ME and interconnecting to the Biddeford Pumping Substation via the 605D1 12.47 kV feeder. | 2020-12-30 | Notification | 2020-08-31
NEP-20-GNF41 | 2020-08-03 | Ecos Energy Housantonic Street Lenox Solar | Generator application from New England Power Company (“NEP”) on behalf of Ecos Energy for the installation of a 4.99 MW solar PV in Lenox, MA and interconnecting to the Lenox Depot Substation via the 1130W1 13.8 kV circuit. | 2021-09-01 | Notification | 2020-08-31
NEP-20-G04-007 Rev.1 | 2020-08-03 | Direct Energy Solar Chase Hill Road Ashway Solar Rev.1 | Generator application from New England Power Company (“NEP”) on behalf of Direct Energy Solar for the installation of a 2.25 MW solar PV (down from 2.464 MWs) in Ashaway, RI and interconnecting to the Chase Hill Substation via the 155F4 12.47 kV circuit. | 2021-07-15 | Notification Withdrawn | 8/31/2020 1/20/2021
ES-20-G120 | 2020-07-17 | Tuckernuck Industries Loomis Road Bolton Solar | Generator notification from Eversource Energy ("ES") on behalf of Tuckernuck Industries for the installation of a 1.86 MW solar PV in Bolton, CT and interconnecting to the Manchester Substation via the 3A03 23 kV circuit. | 2021-05-28 | Notification Withdrawn | 8/31/2020 9/20/2022
ES-20-G170 | 2020-07-24 | Verogy Platt Road Waterwon Solar | Generator notification from Eversource Energy ("ES") on behalf of Verogy for the installation of a 1.975 MW MW solar PV in Watertown, CT and interconnecting to the Shaws Hill Substation via the 24H6 13.8 kV circuit. | 2020-12-31 | Notification | 2020-08-31
CMP-20-G76 | 2020-08-04 | Arctaris Saddleback Solar Rangeley Road Dallas Plantation Solar and Battery | Generator notification from Central Maine Power ("CMP") on behalf of Arctaris Saddleback Solar for the installation of a 4.885 MW MW solar PV and 3.0 MW/16.0 MWh battery in Dallas Plantation, ME and interconnecting to the Saddleback Substation via the 876D1 34.5 kV feeder. | 2021-09-15 | Notification | 2020-08-31
CMP-20-G74 | 2020-08-04 | Borrego Solar Phillips Strong Norton Hill Road Strong Solar and Battery | Generator notification from Central Maine Power ("CMP") on behalf of 510 PV Project Development for the installation of a 4.878 MW solar PV and 4.99 MW/25.0 MWh battery in Strong, ME and interconnecting to the Phillips/Strong Substation via the 841D1 34.5 kV feeder. | 2021-09-15 | Notification | 2020-08-31
CMP-20-G80 | 2020-08-04 | Sunraise Development Searsmont Road Lincolnville Solar and Battery 1 | Generator notification from Central Maine Power ("CMP") on behalf of Sunraise Development for the installation of a 4.0 MW solar PV and 4.0 MW/4.448 MWh battery in Lincolnville, ME and interconnecting to the Lincolnville Substation via the 800D1 34.5 kV feeder. | 2021-08-15 | Notification | 2020-08-31
CMP-20-G66 | 2020-08-04 | Sunraise Development Augusta Road Bowdoin Solar and Battery 1 | Generator notification from Central Maine Power ("CMP") on behalf of Sunraise Development for the installation of a 3.638 MW solar PV and 2.5 MW/4.448 MWh battery in Bowdoin, ME and interconnecting to the Topsham Substation via the 250D1 12.47 kV feeder. | 2021-06-15 | Notification | 2020-08-31
NEP-20-GNF42 | 2020-08-03 | Valta Energy Forge Parkway Franklin Solar and Battery | Generator application from New England Power Company (“NEP”) on behalf of Valta Energy for the installation of a 1.828 MW solar PV and 0.528 MW/1.112 MWh battery in Franklin, MA and interconnecting to the Beaver Pond Substation via the 344W2 13.8 kV feeder. | 2021-09-01 | Notification | 2020-08-31
NEP-20-GNF44 | 2020-08-03 | Valta Energy Fort Pond Lancaster Solar and Battery | Generator application from New England Power Company (“NEP”) on behalf of Valta Energy for the installation of a 4.98 MW solar PV and 2.5 MW/5.246 MWh battery in Lancaster, MA and interconnecting to the Laurel Circle Substation via the 227W1 13.8 kV feeder. | 2020-11-23 | Notification | 2020-08-31
NEP-20-G03-015 Rev.1 | 2020-08-03 | Syncarpha Solar Lombard Road Hubbardston Solar and Battery Rev.1 | Generator application from New England Power Company (“NEP”) on behalf of Syncarpha Solar for the installation of a 3.396 MW solar PV (down from 4.98 MWs) and 3.0 MW/6.0 MWh battery in Hubbardston, MA and interconnecting to the East Westminster Substation via the 609W1 13.8 kV feeder. | 2022-10-01 | Notification Withdrawn | 8/31/2020 11/18/2020
NEP-20-G03-083 Rev.1 | 2020-08-03 | C-Tec Solar Armsby Road Sutton Solar and Battery Rev.1 | Generator application from New England Power Company (“NEP”) on behalf of C-Tec Solar for the installation of a 2.05 MW solar PV (down from 3.142 MWs) and 1.02 MW/4.08 MWh battery in Sutton, MA and interconnecting to the Millbury Substation via the 314W6 13.8 kV feeder. | 2021-06-01 | Approved Withdrawn | 8/31/2020 1/20/2021
NEP-20-G03-008 Rev.1 | 2020-08-03 | Nexamp Bemis Road Warren Solar and Battery Rev.1 | Generator application from New England Power Company (“NEP”) on behalf of Nexamp for the installation of a 4.99 MW solar PV and the addition of a 3.0 MW/6.0 MWh battery in Hubbardston, MA and interconnecting to the Little Rest Road Substation via the 516L2 13.2 kV feeder. | 2021-06-01 | Notification Withdrawn | 8/31/2020 2/16/2021
NEP-20-GNF006 Rev.1 | 2020-08-03 | Lodestar Energy Lunenburg Road Lancaster Solar and Battery Rev. 1 | Generator application from New England Power Company (“NEP”) on behalf of Lodestar Energy for the installation of a 3.875 MW solar PV and the addition of a 2.0 MW/4.24 MWh battery in Lancaster, MA and interconnecting to the Laurel Circle Substation via the 227W1 13.8 kV feeder. | 2021-01-01 | Notification | 2020-08-31
ES-20-G90 Rev.1 | 2020-05-08 | BWC Pine Meadow Brook Pine Mwadow Road Northfield Solar and Battery Rev.1 | Generator application from New England Power Company (“NEP”) on behalf of BWC Pine Meadow Brook for the installation of a 3.0 MW solar PV and 3.0 MW/12.0 MWh battery in Northfield, MA and interconnecting to the French King 21B Substation via the 21B8 feeder. | 2020-08-31 | Notification | 2020-08-31
ES-20-G91 | 2020-05-08 | BWC Pine Meadow Brook Pine Meadow Road Northfield Solar and Battery Rev.1 | Generator application from New England Power Company (“NEP”) on behalf of BWC Pine Meadow Brook for the installation of a 2.0 MW solar PV and 2.0 MW/8.0 MWh battery in Northfield, MA and interconnecting to the French King 21B Substation via the 21B8 feeder. | 2020-08-31 | Notification | 2020-08-31
ES-20-G166 | 2020-07-08 | Bradley Energy Center Schoephoester Road Windsor Locks Gas Generator | Generator notification from Eversource Energy ("ES") on behalf of Bradley Energy Center for the installation of a 3.37 MW gas generator in Windsor Locks, CT and interconnecting to the Windsor Locks 14K Substation via the 147K feeder. | 2010-08-01 | Notification | 2020-08-31
ES-19-T17 Rev.1 | 2020-08-04 | Rebuild of Line 667 Rev.1 | Transmission notification from Eversource Energy ("ES") to change the Normal, LTE and STE Summer MVA ratings on the 69 kV 667 Line. | 2023-12-31 | Notification | 2020-08-28
ES-20-T38 | 2020-08-04 | Partial Rebuild of Line 1618 | Transmission notification from Eversource Energy ("ES") to partially rebuild Line 1618 by replacing structures and associated 336 kcmil ASCR conductor with 556 kcmil ACSS conductor. | 2023-12-31 | Notification | 2020-08-28
ES-20-X01 | 2020-08-04 | Tillson SPS Retirement | Transmission notification from Eversource Energy ("ES") for the retirement of the Tillson Special Protection System (SPS) due to the completion of ES-20-T08, ES-20-T09, ES-20-T10, ES-20-T11 and ES-20-T36. The SPS was designed to balance the loading of the in-service transmission lines between Montague Substation and Fairmont Switching Station following a contingency event since the existing phase conductors have very restricted ratings | 12/2023 | Notification | 2020-08-28
ES-20-G167 | 2020-06-23 | SR Litchfield Solar Project | Generator application from Eversource Energy ("ES") for the installation of a 19.8 MW solar array interconnecting to the Campville 14R substation in Harwinton, CT. | 2021-03-30 | Approved | 2020-07-27
CMP-20-G40 | 2020-07-06 | BD Solar Winslow II Solar Project | Generator application from Central Maine Power Company ("CMP") on behalf of BD Solar Winslow II for the installation of a 6.999 MW solar array interconnecting to the Winslow Substation via the 12.47 kV 870D2 circuit. | 2020-12-31 | Approved | 2020-07-27
ES-20-T33 | 2020-07-06 | Wareham Transformer #2 Addition Project | Transmission application from Eversource Energy ("ES") to “double end” the existing single ended Wareham station with a 45/60/75 MVA 115/23 kV transformer #2 and associated equipment, including a 115 kV circuit switcher, 23 kV bus section, and a 23 kV 4.8 MVAR capacitor bank. | 7/2021 | Approved | 2020-07-31
ES-20-G168 | 2020-07-06 | SR Stonington Solar Project | Generator application from Eversource Energy ("ES") for the installation of a 10.0 MW solar array in North Stonington, CT and interconnecting to the Shunock 32P Substation via the 13.8 32P2 circuit. | 2021-06-30 | Approved | 2020-07-27
ES-20-G169 | 2020-07-10 | Gravel Pit Solar Generation and Transmission Project | Generator application from Eversource Energy ("ES"), on behalf of Gravel Pit Solar for a 50 MW solar array, each with its own 630V/34.5 kV GSU. The proposed project’s Point of Interconnection (POI) is a tap on the 115 kV Connecticut Light & Power Company line between Barbour Hill 23J Substation and Windsor Locks 14K Substation. | 2022-11-30 | Approved | 2020-07-27
ES-20-T34 | 2020-07-10 | Gravel Pit Solar Generation and Transmission Project | Transmission application from Eversource Energy ("ES") for the installation of a three-breaker ring bus tapped on the 115 kV Eversource Line 1200 between Barbour Hill 23J Substation and Windsor Locks 14K Substation. | 2022-10-30 | Approved | 2020-07-27
ES-20-T35 | 2020-07-10 | Gravel Pit Solar Generation and Transmission Project | Transmission application from Eversource Energy ("ES") for the installation of a 115/34.5 kV step-up transformer. | 2022-10-30 | Approved Withdrawn | 7/27/2020 11/14/2023
VW-19-G01 Rev.1 | 2020-07-07 | Vineyard Wind Project Revisions | Generator application revision from Vineyard Wind ("VW") to replace 99 offshore Siemens SWT 8.0-154 (8.4 MW) wind turbines to 84 offshore MHI Vestas V164-9.5 (10MW) (840 MWs total output) wind turbines. The project will interconnect to the Eversource transmission system at the Barnstable Switch Station. | 2023-10-05 | Approved | 2020-07-27
VW-19-T01 Rev.1 | 2020-07-07 | Vineyard Wind Project Revisions | Transmission application revision from Vineyard Wind ("VW") for the installation of a single offshore gas-insulated substation (“GIS”), containing 66 kV switchgear, 220 kV circuit breakers and two (2) 450 MVA 220/66 kV on-load tap-changing transformers. | 2022-08-01 | Approved | 2020-07-27
VW-19-T02 Rev.1 | 2020-07-07 | Vineyard Wind Project Revisions | Transmission application revision updating cable length and impedances from Vineyard Wind (VW) for the installation of a combination of two (2) 1200mm² and 1400mm² Cu, 3-core 220kV submarine cables and 2500mm² Al single conductor 220kV terrestrial underground cable to transmit the power from the offshore substations approximately 50-miles to onshore substation. | 2022-08-01 | Approved | 2020-07-27
VW-19-T03 Rev.1 | 2020-07-07 | Vineyard Wind Project Revisions | Transmission application revision from Vineyard Wind ("VW") for the installation of two (2) 450 MVA 115kV/220kV/13.8kV on-load tap-changing autotransformers with 13.8kV tertiary winding, each with four (4) 115 kV circuit breakers and three (3) 220 kV circuit breakers, both in single-bus arrangements. | 2022-08-01 | Approved | 2020-07-27
VW-19-T04 Rev.1 | 2020-07-07 | Vineyard Wind Project Revisions | Transmission application revision from Vineyard Wind ("VW") for the installation of two separate 115kV terrestrial cable circuits providing separate Vineyard Wind onshore substation transformer interconnection to distinct Barnstable 115kV station breaker positions through an approximately .14-mile underground circuit. | 2022-08-01 | Approved | 2020-07-27
VW-19-T05 Rev.1 | 2020-07-07 | Vineyard Wind Project Revisions | Transmission application revision from Vineyard Wind ("VW") for the installation of two (2) 16.5 kV Synchronous Condensers has been revised to connect to the on-shore 115 kV buses instead of tertiary windings of 220/115kV transformers. | 2022-08-01 | Approved | 2020-07-27
CMP-20-G54 | 2020-07-06 | Etna ME 2 Stage Road Etna Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of Etna ME 2 for the installation of a 2.0 MW solar PV in Etna, ME and interconnecting to the Carmel Substation via the 808D1 12.47 kV feeder. | 2021-03-31 | Notification Withdrawn | 7/30/2020 11/18/2020
CMP-20-G68 | 2020-07-06 | CEC Development Nonesuch Road Gorham Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of CEC Development for the installation of a 4.826 MW solar PV in Gorham, ME and interconnecting to the Spring Street Substation via the 668D5 12.47 kV feeder. | 2021-03-31 | Notification | 2020-07-30
CMP-20-G71 | 2020-07-06 | EDF Renewables Kennebec River Road Embden Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of EDF renewables for the installation of a 4.999 MW solar PV in Embden, ME and interconnecting to the Embden Substation via the 868D1 12.47 kV feeder. | 2021-09-30 | Notification | 2020-07-30
CMP-20-G69 | 2020-07-06 | EDF Renewables Christian Hill Road Bristol Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of EDF renewables for the installation of a 4.899 MW solar PV in Bristol, ME and interconnecting to the Bristol Substation via the 210D2 12.47 kV feeder. | 2021-09-30 | Notification | 2020-07-30
CMP-20-G70 | 2020-07-06 | Longroad North Augusta Civic Center Drive Augusta Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of Maine DG Holdings for the installation of a 2.475 MW solar PV in Augusta, ME and interconnecting to the North Augusta Substation via the 272D6 34.5 kV circuit. | 2021-12-03 | Notification | 2020-07-30
CMP-20-G67 | 2020-07-06 | Revision Energy Curra Road Knox Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of Revision Energy for the installation of a 1.462 MW solar PV in Knox, ME and interconnecting to the Unity Substation via the 860D2 12.47 kV circuit. | 2020-12-31 | Notification | 2020-07-30
CMP-20-G42 | 2020-07-06 | Walden Solar Maine II route 9B Landfill Wells Solar | Generator notification from Central Maine Power Company ("CMP") on behalf of Walden Solar Maine II for the installation of a 4.9 MW solar PV in Wells, ME and interconnecting to the Pratt & Whitney Substation via the 661D2 12.47 kV circuit. | 2021-04-30 | Notification | 2020-07-30
ES-19-G65 Rev.1 | 2020-06-03 | Ecos Energy Bilton Road Somers Solar Rev.1 | Generator notification from Eversource Energy ("ES") on behalf of Ecos Energy for the installation of a 2.99 MW solar PV in Somers, CT and interconnecting to the Scitico 27H Substation via the 27H7 23 kV circuit. | 2019-09-11 | Notification | 2020-07-30
ES-20-G43 | 2020-07-06 | Ecos Fisk Road Hampton Solar | Generator notification from Eversource Energy ("ES") on behalf of Ecos Fisk Road for the installation of a 4.0 MW solar PV in Hampton, CT and interconnecting to the Card Street Substation via the 11F14 23 kV circuit | 2022-03-02 | Notification | 2020-07-30
ES-19-G66 Rev.1 | 2020-06-03 | Sayles Avenue Putnam Solar Rev.1 | Generator notification from Eversource Energy ("ES") on behalf of Sayles Ave Solar for the installation of a 1.98 MW solar PV in Putnam, CT and interconnecting to the Tracy 14M Substation via the 14M28 23 kV circuit. | 2019-07-01 | Notification Withdrawn | 7/30/2020 8/17/2021
NEP-20-GNF17 | 2020-07-06 | Econox Renewables Log Road Burrillville Solar | Generator notification from New England Power Company (“NEP”) on behalf of Econox Renewables for the installation of a 3.9 MW solar PV in Burrillville, RI and interconnecting to the Nasonville Substation via the 127W40 13.2 kV feeder. | 2021-09-01 | Notification | 2020-07-30
NEP-20-GNF37 | 2020-06-01 | Enel X Cherry Hill Drive Beverly Solar | Generator notification from New England Power Company (“NEP”) on behalf of Enel X for the installation of a 1.95 MW solar PV in Beverly, MA and interconnecting to the Balch Street Substation via the 72L1 13.2 kV feeder. | 2021-08-01 | Notification | 2020-07-30
ES-20-G61 Rev.1 | 2020-06-03 | 510 PV project Development Blacksmith Shop Road Falmouth Solar and Battery Rev.1 | Generator notification from Eversource Energy ("ES") on behalf of 510 PV Project Development for the installation of a 3.3 MW solar PV and 3.3 MW/4.73 MWh battery in Falmouth, MA and interconnecting to the Falmouth Substation via the 4-98A-98A 23 kV feeder. | 2021-06-08 | Notification Withdrawn | 7/30/2020 12/17/2024
ES-19-G36 Rev.1 | 2020-06-03 | Borrego Solar South Main Street Freetown Solar and Battery Rev.1 | Generator notification from Eversource Energy ("ES") on behalf of Borrego Solar for the installation of a 4.999 MW solar PV and 5.0 MW/10.0 MWh battery in Freetown, MA and interconnecting to the Bell Rock Road Substation via the 2-635-635 13.2 kV feeder. | 2020-05-01 | Notification | 2020-07-30
ES-20-G51 | 2020-06-12 | TJA Clean Energy South Main Street Lanesborough Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of TJA Clean Energy for the installation of a 4.99 MW solar PV and 3.0 MW/6.576 MWh battery in Lanesborough, MA and interconnecting to the Partridge 15E Substation via the 15E1 23 kV feeder. | 2020-12-12 | Notification | 2020-07-30
ES-20-G22 Rev.1 | 2020-06-03 | Sunraise Development Lake Street Plympton Solar and Battery Rev.1 | Generator notification from Eversource Energy ("ES") on behalf of Sunraise Development for the installation of a 4.998 MW solar PV and 4.25 MW/9.452 MWh battery in Plympton, MA and interconnecting to the Kingston Substation via the 3-15-906 23 kV feeder. | 2020-12-01 | Notification | 2020-08-07
ES-20-G71 Rev.1 | 2020-06-03 | BE RE Ring Road Plympton Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Sunraise Development for the installation ot a 4.999 MW solar PV and 4.999 MW/96 MWh battery in Plympton, MA and interconnecting to the Kingston Substation via the 3-15-15 23 kV feeder. | 2020-09-01 | Notification | 2020-08-07
CMP-20-G66 | 2020-07-06 | Sunraise Topsham Augusta Road Bowdoin Solar and Battery | Generator notification from Central Maine Power Company ("CMP") on behalf of Sunraise Development for the installation of a 3.638 MW solar PV and 2.5 MW/4.448 MWh battery in Bowdoin, ME and interconnecting to the Topsham Substation via the 250D112.47 kV feeder. | 2021-06-15 | Notification | 2020-07-30
ES-19-G46 Rev.1 | 2020-06-03 | Marthas Vineyard Battery Edgartown Vineyard Haven Road Oak Bluff Battery | Generator notification from Eversource Energy ("ES") on behalf of Marthas Vineyard Battery for the installation of a 4.9 MW/9.8 MWh battery in Oak Bluff, MA and interconnecting to the Falmouth Bulk Station via the 4-75-75 13.8 kV feeder. | 2020-12-01 | Notification Withdrawn | 7/30/2020 8/17/2021
HGE-20-G01 | 2020-06-16 | Citizens Energy Water Street Holyoke Battery | Generator notification from Holyoke Gas and Electric on behalf of Citizens Energy for the installation of a 4.99 MW/10.0 MWh battery in Holyoke, MA and interconnecting to the North Canal Substation via the 44P5 13.8 kV feeder. | 4/31/2021 | Notification | 2020-07-30
HMLP-20-G01 | 2020-07-13 | KEI Mass Energy Storage Bare Cove Park Hingham Battery | Generator notification from Hingham Municipal Lighting Plant/Energy New England on behalf of KEI Mass Energy Storage for the installation of a 2.0 MW/6.0 MWh battery in Hingham, MA and interconnecting to the Hobart Substation via the 478-503 13.8 kV feeder. | 2020-12-18 | Notification | 2020-07-30
PUD-20-G01 | 2020-07-02 | Ocean State BTM Davis Drive Pascoag Battery | Generator notification from Pascoag Utility District on behalf of Ocean State BTM for the installation of a 3.0 MW/9.0 MWh battery in Pascoag, RI and interconnecting to the Pascoag Substation via the 188170 13.8 kV feeder. | 2021-06-01 | Notification | 2020-07-30
NEP-20-X01 | 2020-06-30 | South Wrentham Transformer Circuit Switcher Failure DDT Addition | Transmission notification from New England Power Company (“NEP”) to add a circuit switcher failure direct transfer trip protection to the 115 kV 1T115 and 2T115 circuit switchers at South Wrentham. | 6/2021 | Notification | 2020-07-31
CMP-20-T01 | 2020-06-03 | New England Clean Energy Connect (NECEC) HVDC Transmission Project | Transmission application from Central Maine Power Company (CMP) for the construction of 27 miles of new 345 kV transmission line (on-existing right-of-way) between the Coopers Mills Substation in Windsor, ME and Maine Yankee Substation in Wiscasset, ME. The existing 345kV Section 392 shall be repositioned on adjacent existing lattice steel structures in order to make way for the proposed 345 kV circuit interconnection into the existing Maine Yankee Substation. The proposed 345 kV circuit shall utilize existing lattice steel structures (prior Section 392 position) for approximately three (3) miles at the interconnection into the existing Maine Yankee Substation. Install one 345 kV breaker at the Coopers Mills Substation, re-terminate Section 392 and Section 3025, and terminate the proposed new line to Maine Yankee. Install three 345 kV breakers to expand the Maine Yankee Substation to a nine-breaker, breaker-and-a-half configuration. Terminate the proposed new line to Coopers Mills and re-terminate Section 377 and Section 392. | 2022-11-01 | Approved | 2020-07-09
CMP-20-T02 | 2020-06-03 | New England Clean Energy Connect (NECEC) HVDC Transmission Project | Transmission application from Central Maine Power Company (CMP) for the installation of a second Larrabee Road 345/115 kV transformer equivalent in Normal, LTE, STE summer thermal ratings, and impedance to the existing 345/115 kV transformer. Install three 345 kV breakers at the 345 kV Larrabee Road Substation for termination of the new line from Merrill Road and a second 345/115 kV transformer; these three 345 kV breakers shall be able to be operated with independent pole tripping. Install two 115 kV breakers at the 115 kV Larrabee Road Substation for termination of a second 345/115 kV transformer in a new two breaker bay. | 2022-11-01 | Approved | 2020-07-09
CMP-20-T03 | 2020-06-03 | New England Clean Energy Connect (NECEC) HVDC Transmission Project | Transmission application from Central Maine Power Company (CMP) for the installation of one 50 MVAR reactor bank on Bus #1 of the Buxton 345 kV Substation. | 2022-11-01 | Approved | 2020-07-09
CMP-20-T04 | 2020-06-03 | New England Clean Energy Connect (NECEC) HVDC Transmission Project | Transmission application from Central Maine Power Company (CMP) for the construction of 207 miles of new 320 kV symmetrical monopole HVDC transmission line from Appalaches Substation in Saint-Adrien-d’Irlande, Quebec to Merrill Road Substation in Lewiston, ME. | 2022-11-01 | Approved | 2020-07-09
CMP-20-T05 | 2020-06-03 | New England Clean Energy Connect (NECEC) HVDC Transmission Project | Transmission application from Central Maine Power Company (CMP) for the construction of a new HVDC Converter Terminal at Merrill Road Substation. | 2022-11-01 | Approved | 2020-07-09
CMP-20-T06 | 2020-06-03 | New England Clean Energy Connect (NECEC) HVDC Transmission Project | Transmission application from Central Maine Power Company (CMP) for the construction of 1.6 miles of new 345 kV AC transmission line from Merrill Road 345 kV substation to Larrabee Road 345 kV substation. | 2022-11-01 | Approved | 2020-07-09
ES-20-T27 | 2020-06-01 | New England Clean Energy Connect (NECEC) HVDC Transmission Project | Transmission application from Eversource Energy (ES) for the thermal uprate of the 22.88 mile B112 115 kV transmission line from Beebe River in Campton, NH to Tamworth F190 Tap in Tamworth, NH. | 6/2022 | Approved Withdrawn | 7/9/2020 3/18/2025
NEP-20-G05-001 | 2020-05-29 | King Street Comprehensive Solar Cluster Project - Power Factor Amesbury Line Road Haverhill Solar | Generator application from New England Power Company (“NEP”) on behalf of Power Factor LLC for the installation of a 2 MW solar array interconnecting to the MECO distribution system in Haverhill, MA via the 47L1 feeder out of the West Newbury substation. | 10/2021 | Approved | 2020-07-14
NEP-20-G05-002 | 2020-05-29 | King Street Comprehensive Solar Cluster Project - Aquantum Solutions East Broadway Haverhill Solar | Generator application from New England Power Company (“NEP”) on behalf of Aquantum Solutions for the installation of a 4.98 MW solar array interconnecting to the MECO distribution system in Haverhill, MA via the 47L1 feeder out of the West Newbury substation. | 9/2021 | Approved | 2020-07-14
NEP-20-G05-003 | 2020-05-29 | King Street Comprehensive Solar Cluster Project - Nexamp Aaron Drive Topsfield Solar | Generator application from New England Power Company (“NEP”) on behalf of Nexamp for the interconnection of a 4.0 MW solar array interconnecting to the MECO distribution system in Topsfield, MA via the 26L1 feeder out of the Topsfield substation. | 10/2021 | Approved Withdrawn | 7/14/2020 12/14/2021
NEP-20-G06-001 | 2020-06-01 | ASO South Comprehensive Cluster Project - Bluewave Solar Hartford Avenue Mendon Solar and Battery | Generator application from New England Power Company (“NEP”) on behalf of Bluewave Solar for the interconnection of a 2.6 MW solar PV and 1.5 MW/3.51 MWh battery in Mendon, MA and interconnecting to the Uxbridge 2 substation via S321W6 13.8 kV circuit. | 2020-12-01 | Approved Withdrawn | 7/14/2020 6/15/2021
NEP-20-G06-002 | 2020-06-01 | ASO South Comprehensive Cluster Project - Nexamp McQuade's Lane Northbridge Solar and Battery | Generator application from New England Power Company (“NEP”) on behalf of Nexamp for the interconnection of a 2.93MW solar PV and 2.0 MW/4.0 MWh battery in Northbridge, MA and interconnecting to the Whitens Pond substation via 320W3 13.8 kV circuit. | 2020-08-07 | Approved | 2020-07-14
NEP-20-G06-003 | 2020-06-01 | ASO South Comprehensive Cluster Project - EDF Renewables Milk Street Blackstone Solar and Battery | Generator application from New England Power Company (“NEP”) on behalf of EDF Renewables for the interconnection of a 2.46 MW solar PV and 1.17 MW/3.0 MWh battery in Blackstone, MA and interconnecting to the Uxbridge 2 substation via 321W6 13.8 kV circuit. | 2021-04-05 | Approved | 2020-07-14
NEP-20-G06-004 | 2020-06-01 | ASO South Comprehensive Cluster Project - TJA Clean Energy Blackstone Street Blackstone Solar | Generator application from New England Power Company (“NEP”) on behalf of TJA Clean Energy for the interconnection of a 4.99 MW solar PV in Blackstone, MA and interconnecting to the Menden substation via the 332W1 13.8 kV circuit. | 2022-01-10 | Approved | 2020-07-14
NEP-20-G06-005 | 2020-06-01 | ASO South Comprehensive Cluster Project - Bluewave Solar Oak Street Douglas Solar and Battery | Generator application from New England Power Company (“NEP”) on behalf of Bluewave Solar for the interconnection of a 3.574 MW solar PV and 1.75 MW/7.0 MWh battery in Blackstone, MA and interconnecting to the Whitins Pond substation via 320W5 13.8 kV circuit. | 2020-12-01 | Approved | 2020-07-14
ES-20-G161 | 2020-06-02 | Wareham Cluster Solar and Battery Project - Hammond Street Carver Solar and Battery | Generator application from Eversource Energy ("ES") on behalf of Clearwater Energy for the installation of a 5.0 MW solar PV and 5.0 MW/26.642 MWh battery in Carver, MA and interconnecting to the Wareham Substation via Section 83. | 2021-10-01 | Approved | 2020-07-14
ES-20-G154 | 2020-06-02 | Wareham Cluster Solar and Battery Project - Tihonet Road Wareham Solar and Battery | Generator application from Eversource Energy ("ES") on behalf of Clearwater Energy for the installation of a 5.0 MW solar PV and 3.0 MW/6.658 MWh battery in Wareham, MA and interconnecting to the Wareham substation via Section 80. | 2021-10-01 | Approved | 2020-07-14
ES-20-G158 | 2020-06-02 | Wareham Cluster Solar and Battery Project - Tremont Street Carver Solar and Battery | Generator application from Eversource Energy (“ES”) on behalf of Clearwater Energy for the installation of a 1.5 MW solar PV and 1.5 MW/7.5 MWh battery in Carver, MA and interconnecting to the Wareham substation via Section 83. | 2021-10-01 | Approved | 2020-07-14
ES-20-G159 | 2020-06-02 | Wareham Cluster Solar and Battery Project - 77 Farm to Market Wareham Solar and Battery | Generator application from Eversource Energy (“ES”) on behalf of Clearwater Energy for the installation of a 5.0 MW solar PV and 2,31 MW/4.79 MWh battery in Wareham, MA and interconnecting to the Wareham substation via Section 80. | 2021-10-01 | Approved | 2020-07-14
ES-20-G156 | 2020-06-02 | Wareham Cluster Solar and Battery Project - 276 Federal Road Carver Solar and Battery | Generator application from Eversource Energy (“ES”) on behalf of Clearwater Energy for the installation of a 5.0 MW solar PV and 3.3 MW/6.6 MWh battery in Carver, MA and interconnecting to the Wareham substation via Section 83. | 2021-10-01 | Approved | 2020-07-14
ES-20-G160 | 2020-06-02 | Wareham Cluster Solar and Battery Project - 299 Farm to Market Road Wareham Solar and Battery | Generator application from Eversource Energy (“ES”) on behalf of Clearwater Energy for the installation of a 3.0 MW solar PV and 2.31 MW/4.79 MWh battery in Wareham, MA and interconnecting to the Wareham substation via Section 80. | 2021-10-01 | Approved | 2020-07-14
ES-20-G155 | 2020-06-02 | Wareham Cluster Solar and Battery Project - 59 Federal Road Carver Solar and Battery | Generator application from Eversource Energy (“ES”) on behalf of Clearwater Energy for the installation of a 5.0 MW solar PV and 5.0 MW/26.37 MWh battery in Carver, MA and interconnecting to the Wareham substation via Section 83. | 2021-10-01 | Approved | 2020-07-14
ES-20-G157 | 2020-06-02 | Wareham Cluster Solar and Battery Project - Clearway Energy Charlotte Furnace Road Wareham Solar and Battery | Generator application from Eversource Energy (“ES”) on behalf of Clearwater Energy for the installation of a 1.0 MW solar PV and 1.0 MW/5.204 MWh battery in Wareham, MA and interconnecting to the Wareham substation via Section 80. | 2021-10-01 | Approved | 2020-07-14
EM-20-G08 | 2020-06-02 | Versant Power Cluster Solar Project - NextGrid Boradway Street Bangor Solar | Generator application from Emera Maine (“EM”) on behalf of NextGrid for the installation of a 4.6 MW solar array in Bangor, ME and interconnecting to the East Bangor Substation via 12.5 kV circuit. | 2021-12-31 | Approved | 2020-07-14
EM-20-G09 | 2020-06-02 | Versant Power Cluster Solar Project - Nexamp Phillips Way Dedham Solar and Battery | Generator application from Emera Maine (“EM”) on behalf of Nexamp Solar for the installation of a 4.99 MW solar PV and 4.0 MW/16.0 MWh battery in Dedham, ME and interconnecting to the Lucerne Substation via 12.5 kV circuit. | 2021-12-31 | Approved | 2020-07-14
EM-20-G10 | 2020-06-02 | Versant Power Cluster Solar Project - Walker Capital Dirigo Way Old Town Solar | Generator application from Emera Maine (“EM”) on behalf of Walker Capital for the installation of a 4.5 MW solar array in Old Town, ME and interconnecting to the Milford Substation via 12.5 kV circuit. | 2021-12-31 | Approved | 2020-07-14
EM-20-G11 | 2020-06-02 | Versant Power Cluster Solar Project - BD Solar Ellsworth Thorson Road Hancock Solar | Generator application from Emera Maine (“EM”) on behalf of BD Solar Ellsworth for the installation of a 7.0 MW solar array in Hancock, ME and interconnecting to the Hancock Substation via 12.5 kV circuit. | 2021-03-31 | Approved | 2020-07-14
EM-20-G12 | 2020-06-02 | Versant Power Cluster Solar Project - BD Solar Hancock Washington Junction Road Hancock Solar | Generator application from Emera Maine (“EM”) on behalf of BD Solar Hancock for the installation of a 7.0 MW solar array in Hancock, ME and interconnecting to the Hancock Substation via 12.5 kV circuit. | 2021-03-31 | Approved | 2020-07-14
EM-20-G13 | 2020-06-02 | Versant Power Cluster Solar Project - Sunraise Development Mariaville Ellsworth Solar and Battery | Generator application from Emera Maine (“EM”) on behalf of Sunraise Development for the installation of a 1.875 MW solar PV and 1.0 MW/2.224 MWh battery in Ellsworth, ME and interconnecting to the Mill Street Substation via 12.5 kV circuit. | 2020-11-30 | Approved | 2020-07-14
EM-20-G14 | 2020-06-02 | Versant Power Cluster Solar Project - Wishcamper Companies Meadow Road Hampden Solar | Generator application from Emera Maine (“EM”) on behalf of Wishcamper Companies for the installation of a 4.95 MW solar array in Hampden, ME and interconnecting to the Hampden Substation via 12.5 kV circuit. | 2021-03-31 | Approved | 2020-07-14
EM-20-G15 | 2020-06-02 | Versant Power Cluster Solar Project - Dimension ME 1 West Main Street Milo Solar | Generator application from Emera Maine (“EM”) on behalf of Dimension ME 1 for the installation of a 4.5 MW solar array in Milo, ME and interconnecting to the Milo substation via 12.5 kV circuit. | 2020-10-30 | Approved | 2020-07-14
EM-20-G16 | 2020-06-02 | Versant Power Cluster Solar Project - 510 PV Project Development Route 172 Surry Solar and Battery | Generator application from Emera Maine (“EM”) on behalf of 510 PV Project Development for the installation of a 4.99 MW solar PV and 4.99 MW/20.0 MWh battery in Surry, ME and interconnecting to the Surry Substation via 12.5 kV circuit. | 2021-04-30 | Approved | 2020-07-14
EM-20-G17 | 2020-06-02 | Versant Power Cluster Solar Project - 510 PV Project Development Somerset Street Millinocket Solar and Battery | Generator application from Emera Maine (“EM”) on behalf of 510 PV Project Development for the installation of a 4.99 MW solar PV and 4.99 MW/25.0 MWh battery in Millinocket, ME and interconnecting to the Millinocket Substation via 12.5 kV circuit. | 2021-04-30 | Approved | 2020-07-14
GRH-20-X01 | 2020-06-02 | Great River Hydro AVR Replacement and Digital Governor Retrofit Project | Transmission application from Great River Hydro (“GRH”) for the replacement existing U1-4 Westinghouse Type MGR analog automatic voltage regulators (AVRs) with four new Basler DECS-250N digital automatic voltage regulators. In addition, on U2-4, the existing Woodward governors with 501 control will be replaced with a PLC based digital governor control. Proposed in-service date for the U-1 AVR is July 25, 2020, U-2 AVR is August 7, 2020, U-3 AVR is August 22, 2020, and U-4 AVR is September 4, 2020. The proposed in service date for the U-2 Governor is October 31, 2020, U-3 Governor is November 7, 2020, and the U-4 Governor is November 14, 2020. | 2020-11-14 | Approved | 2020-07-09
ES-20-G162 | 2020-06-02 | Highland Avenue Dartmouth Cluster Solar and Battery Project | Generator application from Eversource Energy (“ES”) for the installation of a 4.999 MW solar PV and 4.999 MW/25.0 MWh battery in Dartmouth, MA and interconnecting to the Cross Road substation via Circuit 532. | 2020-12-02 | Approved | 2020-07-14
UI-20-G03 | 2020-06-08 | Bridgeport Fuel Cell Project | Generator application from Avangrid/United Illuminating (“UI”) for the installation of a 9.66 MW fuel cell generator interconnection proposed and owned by NuPower Generator Bridgeport LLC located in Bridgeport, CT connected to UI’s Congress Street substation through two 13.8kV distribution circuits. | 2021-12-01 | Approved | 2020-07-14
CMEEC-20-G01 | 2020-06-03 | CMEEC New London Navy Fuel Cell Project | Generator application from CMEEC for the installation of two 3.7 MW (7.4 MW net output) fuel cell generators and interconnected to Bus 3 via the M14N circuit at the Subase 33/13.8 kV substation. | 2020-07-30 | Approved | 2020-07-14
ES-20-G165 | 2020-06-03 | Waterford Solar Project | Generator application from Eversource Energy (“ES”) for the installation of a 16 MW solar array and interconnected to the 23.0 kV Bus A2 at Eversource’s Waterford 36F 115/23-kV Substation. | 2021-04-01 | Approved | 2020-07-14
CMP-20-G49 | 2020-05-30 | 510 PV Project Development 278 Main Street Ocford Solar | Generator notification from Central Maine Power ("CMP") on behalf of 510 PV Project Development for the installation of a 4.29 MW solar PV in Oxford, ME and interconnecting to the Oxford Substation via the 437D1 12.47 kV feeder. | 2021-05-03 | Notification | 2020-07-14
CMP-20-G45 | 2020-05-30 | BWC Bluewave MA Johnson Road Scarborough Solar | Generator notification from Central Maine Power ("CMP") on behalf of BWC Bluewave MA for the installation of a 4.955 MW solar PV in Scarborough, ME and interconnecting to the Scarborough Substation via the 639D1 12.47 kV feeder. | 2020-12-30 | Notification | 2020-07-14
CMP-20-G59 | 2020-06-01 | Union ME 2 Appleton Road Union Solar | Generator notification from Central Maine Power ("CMP") on behalf of Union ME 2 for the installation of a 4.875 MW solar PV in Union, ME and interconnecting to the Scarborough Substation via the 251D1 12.47 kV feeder. | 2020-12-18 | Notification | 2020-07-14
CMP-20-G46 | 2020-05-30 | CQA Development Main Street | Generator notification from Central Maine Power ("CMP") on behalf of CQA Development for the installation of a 4.95 MW solar PV in Jay, ME and interconnecting to the Riley Substation via the 449D2 12.47 kV feeder. | 2020-11-01 | Notification | 2020-07-14
CMP-20-G48 | 2020-06-01 | EDF Renewables Nequasset Road Woolwich Solar | Generator notification from Central Maine Power ("CMP") on behalf of EDF Renewables for the installation of a 4.999 MW solar PV in Woolwich, ME and interconnecting to the Woolwich Substation via the 258D1 12.47 kV feeder. | 2021-08-30 | Notification | 2020-07-14
CMP-20-G64 | 2020-06-01 | BD Solar North Bridgton Chadbourne Hill Road Bridgton Solar | Generator notification from Central Maine Power ("CMP") on behalf of BD Solar North Bridgton for the installation of a 4.965 MW solar PV in Bridgton, ME and interconnecting to the Bridgton Substation via the 406D1 12.47 kV circuit. | 2020-09-03 | Notification | 2020-07-14
CMP-20-G57 | 2020-05-30 | Energy Management Industrial Park Road Rumford Solar | Generator notification from Central Maine Power ("CMP") on behalf of Energy Management for the installation of a 4.998 MW solar PV in Rumford, ME and interconnecting to the Rumford IP Substation via the 466D1 34.5kV circuit. | 2021-01-15 | Notification | 2020-07-14
CMP-20-G53 | 2020-05-30 | Maine DG Holdings ME 113 West Baldwin Solar | Generator notification from Central Maine Power ("CMP") on behalf of Maine DG Holdings for the installation of a 4.95 MW solar PV in West Baldwin, ME and interconnecting to the Baldwin Substation via the 691D1 34.5kV circuit. | 2022-01-28 | Notification | 2020-07-14
CMP-20-G62 | 2020-06-01 | Nexamp Solar Great Falls Riverside Drive Auburn Solar | Generator notification from Central Maine Power ("CMP") on behalf of Nexamp Solar Great Falls for the installation of a 4.965 MW solar PV in Auburn, ME and interconnecting to the Great Falls Substation via the 436D6 12.47kV circuit. | 2021-04-30 | Notification | 2020-07-14
CMP-20-G44 | 2020-05-30 | Soltage H Road Action Solar | Generator notification from Central Maine Power ("CMP") on behalf of Soltage for the installation of a 3.398 MW solar PV in Acton, ME and interconnecting to the Butler’s Corner Substation via the 612D2 12.47kV circuit. | 2020-12-31 | Notification | 2020-07-14
CMP-20-G51 | 2020-06-01 | Soltage Casco Road Route 11 Naples Solar | Generator notification from Central Maine Power ("CMP") on behalf of Soltage for the installation of a 2.0 MW solar PV in Naples, ME and interconnecting to the Raymond Substation via the 445D2 34.5kV circuit. | 2021-03-01 | Notification | 2020-07-14
CMP-20-G60 | 2020-06-01 | SRE Solar Origination 1 Maxcys Mill Road Windsor Solar | Generator notification from Central Maine Power ("CMP") on behalf of SRE Solar Origination 1 for the installation of a 2.0 MW solar PV in Windsor, ME and interconnecting to the Cooper Mills Road Substation via the 818D2 12.47kV circuit. | 2021-03-01 | Notification | 2020-07-14
CMP-20-G43 | 2020-05-30 | TPE Development Coffin Road North Berwick Solar | Generator notification from Central Maine Power ("CMP") on behalf of TPE Development for the installation of a 4.95 MW solar PV and in North Berwick, ME and interconnecting to the Bassett Substation via the 602D3 12.47 kV circuit. | 2021-07-31 | Notification | 2020-07-14
CMP-20-G55 | 2020-05-30 | TPE Development Bowman Street Farmingdale Solar | Generator notification from Central Maine Power ("CMP") on behalf of TPE Development for the installation of a 4.85 MW solar PV and in North Berwick, ME and interconnecting to the Browns Crossing Substation via the 211D2 12.47 kV circuit. | 2020-07-31 | Notification | 2020-07-14
CMP-20-G04 | 2020-05-30 | NextGrid Mastic Webb Road Waterville Solar | Generator notification from Central Maine Power ("CMP") on behalf of NextGrid Mastic for the installation of a 4.6 MW solar PV and in Waterville, ME and interconnecting to the Oakland Substation via the 839D1 12.47 kV circuit. | 2020-10-31 | Notification | 2020-07-14
ES-20-G163 | 2020-06-02 | Allco Renewable Energy Limited Voluntown Road Griswold Solar | Generator notification from Eversource Energy ("ES") on behalf of Allco Renewable Energy Limited for the installation of a 2.99 MW solar PV in Griswold, CT and interconnecting to the Frybrook Substation via the 13B25 23 kV circuit. | 2020-09-03 | Notification | 2020-07-14
ES-20-G164 | 2020-05-20 | Windham Solar Volutown Road Griswold Solar | Generator notification from Eversource Energy ("ES") on behalf of Windham Solar for the installation of a 2.0 MW solar PV in Griswold, CT and interconnecting to the Frybrook Substation via the 13B25 23 kV circuit. | 2020-11-30 | Notification | 2020-07-14
ES-19-G54 Rev.1 | 2020-06-02 | ECA SEMA CAN 2 Draper Lane Canton Solar | Generator notification from Eversource Energy ("ES") on behalf of ECA SEMA CAN 2 for the installation of a 1.359 MW solar PV in Canton, MA and interconnecting to the Canton Substation via the 470H6 4 kV feeder. Notification revision is to reduce previously approved capacity. | 2020-12-01 | Notification | 2020-07-14
NEP-19-GNF35 Rev.1 | 2020-06-01 | Attleboro Landfill Solar Peckham Street Attleboro Solar | Generator notification from New England Power Company ("NEP") on behalf of Heartwood Group Inc. for the installation of a 1.7 MW solar PV in Attleboro, MA and interconnecting to the Chartley Pond Substation via the 8L1 13.2 kV feeder. Resource capacity is being reduced from 2.0 MWs to 1.7 MWs. | 2021-06-01 | Notification | 2020-07-14
NEP-19-GNF126 Rev.1 | 2020-06-01 | TJA Solar Blackstone Street Blackstone Solar | Generator notification from New England Power Company ("NEP") on behalf of TJA Solar for the installation of a 3.96 MW solar PV in Blackstone, MA and interconnecting to the Riverside Substation via the 108W60 13.8 kV feeder. Revision is to correct the substation name. | 2021-02-18 | Notification | 2020-07-14
NEP-20-GNF36 | 2020-06-01 | Enter Solar Douglass Street Uxbridge Solar | Generator notification from New England Power Company ("NEP") on behalf of Enter Solar for the installation of a 4.966 MW solar PV in Uxbridge, MA and interconnecting to the Uxbridge 1 Substation via the 321W113.8 kV circuit. | 2021-06-01 | Notification | 2020-07-14
NEP-19-G30-008 Rev.1 | 2020-06-01 | Nexamp Barre Cut Off Road New Braintree Solar | Generator notification from New England Power Company ("NEP") on behalf of Nexamp for the installation of a 5.477 MW solar PV in New Braintree, MA and interconnecting to the Barre Substation via the 604W3 13.8 kV circuit. Revision is for the reduction in output from 5.96 MWs to 5.477 MWs. | 2021-02-26 | Notification | 2020-07-14
EM-20-G02 | 2020-05-08 | Herman Solar Route 2 Herman Solar | Generator notification from Emera Maine (“EM”) on behalf of Herman Solar for the installation of a 4.98 MW solar PV in Herman, ME and interconnecting to the Herman Substation via the 2.5 kV circuit. | 2020-11-01 | Notification | 2020-07-14
EM-20-G03 | 2020-05-08 | NextGrid Pushaw Solar Pushaw Road Bangor Solar | Generator notification from Emera Maine (“EM”) on behalf of NextGrid Pushaw Solar for the installation of a 4.6 MW solar PV in Bangor, ME and interconnecting to the East Bangor Substation via the 12.5 kV circuit. | 2020-12-31 | Notification | 2020-07-14
EM-20-G04 | 2020-05-08 | NextGrid Water Street Howland Solar | Generator notification from Emera Maine (“EM”) on behalf of NextGrid for the installation of a 4.6 MW solar PV in Howland, ME and interconnecting to the Stanford Substation via the 12.5 kV circuit. | 2020-12-31 | Notification | 2020-07-14
EM-20-G05 | 2020-05-08 | Dynamic Solar Main Street Corinth Solar | Generator notification from Emera Maine (“EM”) on behalf of Dynamic Solar for the installation of a 4.999 MW solar PV in Corinth, ME and interconnecting to the East Corinth via the 12.5 kV circuit. | 2020-12-31 | Notification | 2020-07-14
EM-20-G06 | 2020-05-08 | Pine Gate Renewables Route 1 Harrington Solar | Generator notification from Emera Maine (“EM”) on behalf of Pine Gate Renewables for the installation of a 2.25 MW solar PV in Harrington, ME and interconnecting to the Harrington Substation via the 12.5 kV circuit. | 2020-12-31 | Notification | 2020-07-14
EM-20-G07 | 2020-05-08 | 510 PV Project Development Caterpillar Hill Road Sedgewick Solar | Generator notification from Emera Maine (“EM”) on behalf of 510 PV Project Development for the installation of a 4.99 MW solar PV in Sedgewick, ME and interconnecting to the Brooksville Substation via the 12.5 kV circuit. | 2021-04-01 | Notification | 2020-07-14
CMP-20-G50 | 2020-06-01 | Nexamp Solar Fort Hill Road Gorham Solar and Battery | Generator notification from Central Maine Power ("CMP") on behalf of Nexamp Solar for the installation of a 4.99 MW solar PV and 3.0 MW/12.0 MWh battery in Gorham, ME and interconnecting to the Fort Hill Substation via the 642D1 12.47 kV circuit. | 2021-04-30 | Notification | 2020-07-14
CMP-20-G52 | 2020-06-01 | Nutting Ridge Solar Oxford Road Otisfield Solar and Battery | Generator notification from Central Maine Power ("CMP") on behalf of Nutting Ridge Solar for the installation of a 3.395 MW solar PV and 4.0 MW/16.0 MWh battery in Otisfield, ME and interconnecting to the Casco Tap Substation via the 663D1 12.47 kV circuit. | 2021-06-30 | Notification | 2020-07-14
CMP-20-G63 | 2020-05-30 | Sunraise Development Pequawket Trail Baldwin Solar and Battery | Generator notification from Central Maine Power ("CMP") on behalf of Sunraise Development for the installation of a 4.875 MW solar PV and 2.5 MW/5.56 MWh battery in Baldwin, ME and interconnecting to the Hiram Tap Substation via the 692D1 34.5 kV circuit. | 2020-11-15 | Notification | 2020-07-14
NEP-20-GNF29 Rev.1 | 2020-06-01 | Bluewave Solar Tremont Street North Dighton Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Bluewave Solar for the installation of a 2.4 MW solar PV and 2.4 MW/9.6 MWh battery in North Dighton, MA and interconnecting to the Dighton Substation via the 19W74 13.8 kV circuit. Revision is to add a battery to the previously approved solar project. | 2021-07-19 | Notification | 2020-07-14
NEP-20-G03-065 Rev.1 | 2020-06-01 | Western Massachusetts Group 2 Cluster - AMP Solar Coy Hill Road Warren Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of AMP Solar for the installation of a 4.98 MW solar PV and 7.0 MW/35.0 MWh battery in Warren, MA and interconnecting to the Little Rest Road Substation via the 516L3 13.2 kV circuit. Revision is to add a battery to the previously approved solar project. | 2021-06-01 | Notification Withdrawn | 8/11/2020 9/23/2020
NEP-20-G03-053 Rev.1 | 2020-06-01 | Western Massachusetts Group 2 Cluster - Clean Energy Collective East Road Orange Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Clean Energy Collective for the installation of a 3.0 MW solar PV and 3.0 MW/6.576 MWh battery in Orange, MA and interconnecting to the Wendell Depot Substation via the 705W3 13.8 kV circuit. Revision is to add a battery to the previously approved solar project. | 2021-06-01 | Notification Withdrawn | 8/11/2020 2/16/2021
NEP-20-G03-066 Rev.1 | 2020-06-01 | Western Massachusetts Group 2 Cluster - AMP Solar Coy Hill Road Warren Solar and Battery 2 | Generator notification from New England Power Company ("NEP") on behalf of AMP Solar for the installation of a 4.98 MW solar PV and 7.0 MW/35 MWh battery in Warren, MA and interconnecting to the Little Rest Road Substation via the 516L3 13.2 kV circuit. Revision is to add a battery to the previously approved solar project. | 2021-06-01 | Notification Withdrawn | 8/11/2020 9/23/2020
NEP-20-GNF34 | 2020-06-01 | Pro-Tech Energy Old Union Turnpike Lancaster Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Pro-Tech Energy for the installation of a 4.95 MW solar PV and 2.475 MW/4.96 MWh battery in Fall River, MA and interconnecting to the Hathaway Street Substation via the 106W46 13.8 kV circuit. | 2020-08-16 | Notification | 2020-07-14
NEP-20-GNF35 | 2020-06-01 | NextGrid New Street Fall River Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of NextGrid for the installation of a 4.2 MW solar PV and 4.0 MW/16.0 MWh battery in Fall River, MA and interconnecting to the Hathaway Street Substation via the 106W46 13.8 kV circuit. | 2021-06-01 | Notification Withdrawn | 7/14/2020 6/15/2021
ES-20-G146 | 2020-06-02 | US Coast Guard Finance Riverside Heights New London Generator and Solar | Generator notification from Eversource Energy ("ES") on behalf of Coast Guard Finance for the installation of a 1.42 MW gas generator and solar PV in New London, CT and interconnecting to the Williams Street Substation via the 9L01 13.2 kV circuit. | 2020-08-01 | Notification | 2020-07-14
CMP-20-G41 | 2020-05-31 | Sanford EES Cyro Drive Sanford Battery | Generator notification from Central Maine Power ("CMP") on behalf of Sanford EES for the installation of a 4.99 MW battery in Sanford, ME and interconnecting to the Sanford IP Substation via the 656D3 12.47 kV circuit. | 2021-12-31 | Notification | 2020-07-14
NEP-20-G03-001 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sunpin Solar - Conant Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Sunpin Solar for the installation of a 4.2 MW solar PV generator and 3 MW/5.658 MWh batteries in Athol, MA interconnecting to the 13.8 kV 1193W1 feeder out of the Lost Town substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 10/20/2020
NEP-20-G03-002 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Princeton Repower, LLC - Keyes Road PV | Generator application from New England Power Company ("NEP") on behalf of Princeton Repower, LLC for the installation of a 4.99 MW solar PV generator in Gardner, MA interconnecting to the 13.8 kV 607W8 feeder out of the Crystal Lake substation. | 2022-10-01 | Approved | 2020-07-08
NEP-20-G03-003 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sunraise Development - Hunt Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Sunraise Development for the installation of a 2.5 MW solar PV generator and 1.75 MW/3.892 MWh batteries in Oakham, MA interconnecting to the 34.5 kV 1194T1 feeder out of the Powder Mill substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-004 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sunraise Development - Edison Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Sunraise Development for the installation of a 4.4 MW solar PV generator and 6.25 MW/13.7 MWh batteries in Oakham, MA interconnecting to the 34.5 kV 1194T1 feeder out of the Powder Mill substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-005 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Kearsarge Solar, LLC - Barre Road PV | Generator application from New England Power Company ("NEP") on behalf of Kearsarge Solar, LLC for the installation of a 4.4 MW solar PV generator in Hardwick, MA interconnecting to the 34.5 kV 1194T1 feeder out of the Powder Mill substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 10/202020
NEP-20-G03-006 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - Main Street PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Zero Point Development for the installation of a 2.0 MW solar PV generator and 1.0 MW and 2.0 MWh batteries in Spencer, MA interconnecting to the 13.8 kV 2236W3 feeder out of the Stafford Street substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-007 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Nexamp - Lockes Village Road PV | Generator application from New England Power Company ("NEP") on behalf of Nexamp for the installation of a 2.791 MW solar PV generator in Wendall, MA interconnecting to the 13.8 kV 705W1 feeder out of the Wendell Depot substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 2/16/2021
NEP-20-G03-008 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Nexamp - Bemis Road PV | Generator application from New England Power Company ("NEP") on behalf of Nexamp for the installation of a 4.99 MW solar PV generator in Warren, MA interconnecting to the 13.2 kV 516L2 feeder out of the Little Rest Road substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-009 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Cypress Creek Renewables - Lower Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Cypress Creek Renewables for the installation of a 4.99 MW solar PV generator and 3.5 MW/7 MWh batteries in Gilbertville-Hardwick, MA interconnecting to the 13.2 kV 501L2 feeder out of the Ware substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 2/16/2021
NEP-20-G03-010 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Forefront Power, LLC - Robbins Road PV | Generator application from New England Power Company ("NEP") on behalf of Forefront Power, LLC for the installation of a 1.92 MW solar PV generator in Ware, MA interconnection to the 13.2 kV 501L1 feeder out of the Ware substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 1/20/2021
NEP-20-G03-011 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - Bouthelier Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Zero Point Development for the installation of a 4.95 MW solar PV generator and 3.245 MW/ 6.502 MWh batteries in Leicester, MA interconnecting to the 13.8 kV 2236W7 feeder out of the Stafford Street substation. | 2022-10-01 | Approved | 2020-07-08
NEP-20-G03-012 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Borrego Solar - Gardner Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Borrego Solar for the installation of a 4.99 MW solar PV generator and 2.64 MW/ 5.28 MWh batteries in Winchendon, MA interconnecting to the 34.5 kV 1616T2 feeder out of the Whitmanville substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 11/18/2020
NEP-20-G03-013 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Prometheus Power Group - Russell Farm Road PV | Generator application from New England Power Company ("NEP") on behalf of Prometheus Power Group for the installation of a 2.64 MW solar PV generator in Winchendon, MA interconnecting to the 34.5 kV 612T2 feeder out of the East Winchendon substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-014 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - SWEB Development UAS - Rochdale Street PV | Generator application from New England Power Company ("NEP") on behalf of SWEB Development USA for the installation of a 4.875 MW solar PV generator in Auburn, MA interconnecting to the 13.8 kV 2236W4 feeder out of the Stafford Street substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 2/16/2021
NEP-20-G03-015 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Syncarpha Solar, LLC - Lombard Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Syncarpha Solar, LLC for the installation of a 4.98 MW solar PV generator and 3.3 MW/ 6.0 MWh batteries in Hubbardston, MA interconnecting to the 13.8 kV 609W1 feeder out of the East Westminster substation. | 2022-10-01 | Approved | 2020-07-08
NEP-20-G03-016 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Syncarpha Solar, LLC - Prentiss Hill Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Syncarpha Solar, LLC for the installation of a 4.98 MW solar PV generator and 4.4 MW/ 8 MWh batteries in Hubbardston, MA interconnecting to the 13.8 kV 609W1 feeder out of the East Westminster substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-017 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - UGT - Keyes Road PV1 | Generator application from New England Power Company ("NEP") on behalf of UGT for the installation of a 4.99 MW solar PV generator in Gardner, MA interconnecting to the 13.8 kV 607W6 feeder out of the Crystal Lake substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 1/20/2021
NEP-20-G03-018 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - UGT - Keyes Road PV2 | Generator application from New England Power Company ("NEP") on behalf of UGT for the installation of a 9.98 MW solar PV generator in Gardner, MA interconnecting to the 13.8 kV 607W7 feeder out of the Crystal Lake substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 1/20/2021
NEP-20-G03-019 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Melink Solar Development - Greenwich Plain Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Melink Solar Development for the installation of a 4.4 MW solar PV generator and 2.5 MW/ 5.0 MWh batteries in Ware, MA interconnecting to the 13.2 kV 501L2 feeder out of the Ware substation. | 2022-10-01 | Approved | 2020-07-08
NEP-20-G03-020 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Melink Solar Development - Ash Street PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Melink Solar Development for the installation of a 4.4 MW solar PV generator and 2.5 MW/ 5.0 MWh batteries in Spencer, MA interconnecting to the 13.2 kV 552L1 feeder out of the Meadow Street substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-021 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Borrego Solar - Franklin Street PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Borrego Solar for the installation of a 4.971 MW solar PV generator and 3.3 MW/6.0 MWh batteries in Belchertown, MA interconnecting to the 13.2 kV 523L2 feeder out of the Thorndike substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 2/16/2021
NEP-20-G03-022 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - SEP Solar, LLC - Oxford Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of SEP Solar, LLC for the installation of a 3.63 MW solar PV generator and 2.0 MW/ 4.0 MWh batteries in Dudley, MA interconnecting to the 13.2 kV 412L4 feeder out of the East Webster substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-023 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - Barre Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Zero Point Development for the installation of a 2.5 MW solar PV generator and 1.622 MW and 3.251 MWh batteries in New Braintree, MA interconnecting to the 34.5 kV 1194T1 feeder out of the Power Mill substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-024 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sunpin Solar Development - Baldwinville Road PV | Generator application from New England Power Company ("NEP") on behalf of Sunpin Solar Development for the installation of a 4.99 MW solar PV generator in Winchendon, MA interconnecting to the 34.5 kV 612T2 feeder out of the East Winchendon substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-025 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Ameresco Solar - Indian Road PV | Generator application from New England Power Company ("NEP") on behalf of Ameresco Solar for the installation of a 1.32 MW solar PV generator in Dudley, MA interconnecting to the 13.2 kV 412L4 feeder out of the East Webster substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-026 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - AMP Solar Development - Cronin Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of AMP Solar Development for the installation of a 4.998 MW solar PV generator and 4.0 MW/ 12.0 MWh batteries in Warren, MA interconnecting to the 13.2 kV 408L2 feeder out of the Fiskdale substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-027 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Melink Solar Development - Fort Hill Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Melink Solar Development for the installation of a 4.4 MW solar PV generator and 2.5 MW/ 5.0 MWh batteries in Oxford, MA interconnecting to the 13.2 kV 406L4 feeder out of the North Oxford substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 2/16/2021
NEP-20-G03-028 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Melink Solar Development - Old W Brookfield Road PV1 and BESS | Generator application from New England Power Company ("NEP") on behalf of Melink Solar Development for the installation of a 4.4 MW solar PV generator and 2.5 MW/ 5.0 MWh batteries in Warren, MA interconnecting to the 13.2 kV 516L3 feeder out of the Little Rest Road substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-029 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Melink Solar Development - Old W Brookfield Road PV2 and BESS | Generator application from New England Power Company ("NEP") on behalf of Melink Solar Development for the installation of a 4.4 MW solar PV generator and 2.5 MW/ 5.0 MWh batteries in Warren, MA interconnecting to the 13.2 kV 516L3 feeder out of the Little Rest Road substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-030 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Nexamp - Pitcherville Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Nexamp for the installation of a 2.51 MW solar PV generator and 1.0 MW/ 2.0 MWh batteries in Hubbardston, MA interconnecting to the 13.8 kV 607W2 feeder out of the Crystal Lake substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 2/16/2021
NEP-20-G03-031 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Lake Street Development - State Road PV | Generator application from New England Power Company ("NEP") on behalf of Lake Street Development for the installation of a 1.875 MW solar PV generator in Westminster, MA interconnecting to the 13.8 kV 609W1 feeder out of the East Westminster substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-032 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - AMP Solar Development - Glenwood Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of AMP Solar Development for the installation of a 4.3 MW solar PV generator and 3.0 MW/12.0 MWh batteries in Rutland, MA interconnecting to the 13.8 kV 55W3 feeder out of the Treasure Valley substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 8/17/2021
NEP-20-G03-033 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - County Road PV1 and BESS | Generator application from New England Power Company ("NEP") on behalf of Zero Point Development for the installation of a 1.5 MW solar PV generator and 0.75 MW/ 1.5 MWh batteries in Rutland, MA interconnecting to the 34.5 kV 1194T3 feeder out of the Powder Mill substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-034 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - Glenwood Road PV1 and BESS | Generator application from New England Power Company ("NEP") on behalf of Zero Point Development for the installation of a 4.95 MW solar PV generator and 2.45 MW/ 4.9 MWh batteries in Rutland, MA interconnecting to the 34.5 kV 1194T3 feeder out of the Powder Mill substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-035 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - Glenwood Road PV2 and BESS | Generator application from New England Power Company ("NEP") on behalf of Zero Point Development for the installation of a 2.5 MW solar PV generator and 1.575 MW/ 3.15 MWh batteries in Rutland, MA interconnecting to the 34.5 kV 1194T3 feeder out of the Powder Mill substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-036 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - Campbell Street PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Zero Point Development for the installation of a 3.5 MW solar PV generator and 2.2 MW/ 4.41 MWh batteries in Rutland, MA interconnecting to the 34.5 kV 1194T3 feeder out of the Powder Mill substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-037 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - Bushy Lane PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Zero Point Development for the installation of a 1.5 MW solar PV generator and 0.75 MW/ 1.47 MWh batteries in Rutland, MA interconnecting to the 34.5 kV 1194T3 feeder out of the Powder Mill substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-038 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - Glenwood Road PV3 and BESS | Generator application from New England Power Company ("NEP") on behalf of Zero Point Development for the installation of a 2.5 MW solar PV generator and 1.225 MW/ 2.45 MWh batteries Rutland, MA interconnecting to the 34.5 kV 1194T3 feeder out of the Powder Mill substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-039 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - County Road PV2 and BESS | Generator application from New England Power Company ("NEP") on behalf of Zero Point Development for the installation of a 2.0 MW solar PV generator and 0.98 MW and 1.96 MWh batteries in Rutland, MA interconnecting to the 34.5 kV 1194T3 feeder out of the Powder Mill substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-040 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Glenwood Road PV4 and BESS | Generator application from New England Power Company ("NEP") on behalf of Zero Point Development for the installation of a 3.5 MW solar PV generator and 1.98 MW/ 3.78 MWh batteries in Rutland, MA interconnecting to the 34.5 kV 1194T3 feeder out of the Powder Mill substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-041 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - OYA Solar MA - Mountain Road PV1 | Generator application from New England Power Company ("NEP") on behalf of OYA Solar MA for the installation of a 4.99 MW solar PV generator in Erving, MA interconnecting to the 13.8 kV 705W3 feeder out of the Wendell Depot substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-042 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sunpin Solar Development - Norcross Road PV | Generator application from New England Power Company ("NEP") on behalf of Sunpin Solar Development for the installation of a 4.99 MW solar PV generator in Spencer, MA interconnecting to the 13.2 kV 525L1 feeder out of the Lashaway substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 2/16/2021
NEP-20-G03-043 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Cypress Creek Renewables - North Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Cypress Creek Renewables for the installation of a 4.998 MW solar PV generator and 4.2 MW/16.8 MWh in Monrow, MA interconnecting to the 13.8 kV 1019W1 feeder out of the Bear Swamp Upper Yard substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 11/18/2020
NEP-20-G03-044 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sunpin Solar Development - Draper Road PV | Generator application from New England Power Company ("NEP") on behalf of Sunpin Solar Development for the installation of a 4.999 MW solar PV generator in East Brookfield, MA interconnecting to the 13.2 kV 552L2 feeder out of the Meadow Street substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-045 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sunpin Solar Development - Brookfield Road PV | Generator application from New England Power Company ("NEP") on behalf of Sunpin Solar Development for the installation of a 3.0 MW solar PV generator in Warren, MA interconnecting to the 13.2 kV 408L2 feeder out of the Fiskdale substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 5/17/2022
NEP-20-G03-046 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Nextera Energy Resources - Dunhamtown Palmer Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Nextera Energy Resources for the installation of a 3.0 MW solar PV generator and 2.0 MW/8.0 MWh batteries in Drimfield, MA interconnecting to the 13.2 kV 503L4 feeder out of the Palmer substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 9/21/2021
NEP-20-G03-047 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - Henshaw Street PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Zero Point Development for the installation of a 3.0 MW solar PV generator and 3.245 MW/ 6.502 MWh batteries in Aubrun, MA interconnecting to the 13.8 kV 2236W5 feeder out of the Strafford Street substation. | 2022-10-01 | Approved | 2020-07-08
NEP-20-G03-048 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - Ware Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Zero Point Development for the installation of a 4.95 MW solar PV generator and 2.45 MW/ 4.8 MWh batteries in Belchertown, MA interconnecting to the 13.2 kV 509L2 feeder out of the Belchertown substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-049 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - EDF Renewables Distributed Solutions - Old Webster Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of EDF Renewables Distributed Solutions for the installation of a 4.0 MW solar PV generator and 2.0 MW/ 4.2 MWh batteries in Oxford, MA interconnecting to the 13.2 kV 406L5 feeder out of the North Oxford substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 2/16/2021
NEP-20-G03-050 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - South Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Zero Point Development for the installation of a 2.5 MW solar PV generator and 1.225 MW/ 2.45 MWh batteries in Oakham, MA interconnecting to the 34.5 kV 1194T1 feeder out of the Powder Mill substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-051 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Pro-Tech Energy Solutions, LLC - Rochdale Street PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Pro-Tech Energy Solutions, LLC for the installation of a 4.95 MW solar PV generator and 3.0MW/ 6.0 MWh batteries in Auburn, MA interconnecting to the 13.8 kV 2236W5 feeder out of the Stafford Street substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-052 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Cypress Creek Renewables - Bemis Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Cypress Creek Renewables for the installation of a 2.5 MW solar PV generator and 4.2 MW/ 16.8 MWh batteries in Winchendon, MA interconnecting to the 34.5 kV 612T2 feeder out of the East Winchendon substation. | 2022-10-01 | Approved | 2020-07-08
NEP-20-G03-053 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Clean Energy Collective - East Road PV | Generator application from New England Power Company ("NEP") on behalf of Clean Energy Collective for the installation of a 3.0 MW solar PV generator in Orange, MA interconnecting to the 13.8 kV 705W3 feeder out of the Wendell Depot substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-054 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Zero Point Development - Coldbrook Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Zero Point Development for the installation of a 4.95 MW solar PV generator and 3.15 MW/ 6.3 MWh batteries in Oakham, MA interconnecting to the 34.5 kV 1194T1 feeder out of the Powder Mill substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-055 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Heartwood Group - Kinzer Drive PV | Generator application from New England Power Company ("NEP") on behalf of Heartwood Group for the installation of a 2.5 MW solar PV generator in Gardner, MA interconnecting to the 13.8 kV 607W6 feeder out of the Crystal Lake substation. | 2022-10-01 | Approved | 2020-07-08
NEP-20-G03-056 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Cypress Creek Renewables - Hovey Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Cypress Creek Renewables for the installation of a 2.0 MW solar PV generator and 1.5MW/ 3.0 MWh batteries in Monson, MA interconnecting to the 13.2 kV 503L1 feeder out of the Palmer substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-057 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - OYA Solar MA - Mountain Road PV2 | Generator application from New England Power Company ("NEP") on behalf of OYA Solar MA for the installation of a 4.99 MW solar PV generator in Erving, MA interconnecting to the 13.8 kV 705W3 feeder out of the Wendell Depot substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-058 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - OYA Solar MA - Hale Street PV | Generator application from New England Power Company ("NEP") on behalf of OYA Solar MA for the installation of a 4.99 MW solar PV generator in Winchendon, MA interconnecting to the 34.5 kV 612T2 feeder out of the East Winchendon substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-059 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - OYA Solar MA - Athol Road PV | Generator application from New England Power Company ("NEP") on behalf of OYA Solar MA for the installation of a 4.99 MW solar PV generator in Royalston, MA interconnecting to the 4.16 kV 701J1 feeder out of the Royalston substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-060 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - OYA Solar MA - Old Turnpike Road PV | Generator application from New England Power Company ("NEP") on behalf of OYA Solar MA for the installation of a 4.99 MW solar PV generator in Oakham, MA interconnecting to the 34.5 kV 1194T1 feeder out of the Powder Mill substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-061 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Nexamp - Griffin Street PV | Generator application from New England Power Company ("NEP") on behalf of Nexamp for the installation of a 2.5 MW solar PV generator in Palmer, MA interconnecting to the 13.2 kV 525L2 feeder out of the Thorndike substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-062 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - unraise Development - School Street PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Sunraise Development for the installation of a 5.65 MW solar PV generator and 5.25 MW/12.5 MWh batteries in Granby, MA interconnecting to the 13.2 kV 527L1 feeder out of the Five Corners substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-063 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Allco Renewable Energy Limited - Spring Street PV | Generator application from New England Power Company ("NEP") on behalf of Allco Renewable Energy Limited for the installation of a 4.99 MW solar PV generator in Winchendon, MA interconnecting to the 34.5 kV 612T2 feeder out of the East Winchendon substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-064 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Allco Renewable Energy Limited - Teel Road PV | Generator application from New England Power Company ("NEP") on behalf of Allco Renewable Energy Limited for the installation of a 4.99 MW solar PV generator in Winchendon, MA interconnecting to the 34.5 kV 612T2 feeder out of the East Winchendon substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-065 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - AMP Solar Development - Coy Hill Road PV1 and BESS | Generator application from New England Power Company ("NEP") on behalf of AMP Solar Development for the installation of a 4.98 MW solar PV generator in Warren, MA interconnecting to the 13.2 kV 516L3 feeder out of the Little Rest Road substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-066 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Coy Hill Road PV2 and BESS | Generator application from New England Power Company ("NEP") on behalf of AMP Solar Development for the installation of a 4.98 MW solar PV generator in Warren, MA interconnecting to the 13.2 kV 516L3 feeder out of the Little Rest Road substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-067 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - SWEB Development USA - Palmer Road PV | Generator application from New England Power Company ("NEP") on behalf of SWEB Development USA for the installation of a 1.875 MW solar PV generator in Brimfield, MA interconnecting to the 13.2 kV 503L4 feeder out of the Palmer substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-068 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - AMP Solar Development - Pratt Corner Road PV1 and BESS | Generator application from New England Power Company ("NEP") on behalf of AMP Solar Development for the installation of a 4.998 MW solar PV generator and 6.0 MW/ 30 MWh batteries in Shutesbury, MA interconnecting to the 13.8 kV 704W1 feeder out of the Shutesbury substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-069 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - AMP Solar Development - Pratt Corner Road PV2 and BESS | Generator application from New England Power Company ("NEP") on behalf of AMP Solar Development for the installation of a 4.998 MW solar PV generator and 6.0 MW/ 30 MWh batteries in Shutesbury, MA interconnecting to the 13.8 kV 704W1 feeder out of the Shutesbury substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-070 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - AMP Solar Development - Baker Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of AMP Solar Development for the installation of a 4.998 MW solar PV generator and 6.0 MW/ 30 MWh batteries in Shutesbury, MA interconnecting to the 13.8 kV 704W1 feeder out of the Shutesbury substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-071 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - AMP Solar Development - Montague Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of AMP Solar Development for the installation of a 4.998 MW solar PV generator and 6.0 MW/ 30 MWh batteries in Shutesbury, MA interconnecting to the 13.8 kV 704W1 feeder out of the Shutesbury substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-072 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Clean Focus Renewables - Hillsville Road PV | Generator application from New England Power Company ("NEP") on behalf of Clean Focus Renewables for the installation of a 1.8 MW solar PV generator in North Brookfield, MA interconnecting to the 13.2 kV 525L1 feeder out of the Lashaway substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-073 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Clean Focus Renewables - White Pond Road PV | Generator application from New England Power Company ("NEP") on behalf of Clean Focus Renewables for the installation of a 2.0 MW solar PV generator in Athol, MA interconnecting to the 13.8 kV 1193W1 feeder out of the Lost Town substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-074 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Omni-Lumens Holdings 3 - Willey Road PV | Generator application from New England Power Company ("NEP") on behalf of Omni- Lumens Holdings 3 for the installation of a 4.98 MW solar PV generator in Monroe, MA interconnecting to the 13.8 kV 1019W1 feeder out of the Bear Swamp Upper Yard substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 11/18/2020
NEP-20-G03-075 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Omni-Lumens Holdings 3 - Main Road PV | Generator application from New England Power Company ("NEP") on behalf of Omni- Lumens Holdings 3 for the installation of a 4.98 MW solar PV generator in Monroe, MA interconnecting to the 13.8 kV 1019W1 feeder out of the Bear Swamp Upper Yard substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 11/18/2020
NEP-20-G03-076 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Omni-Lumens Holdings 3 - Mohawk Trail PV | Generator application from New England Power Company ("NEP") on behalf of Omni- Lumens Holdings 3 for the installation of a 4.648 MW solar PV generator in Florida, MA interconnecting to the 13.8 kV 1015W1 feeder out of the Walker Street substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 11/18/2020
NEP-20-G03-077 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Cypress Creek Renewables - Lyons HillRoad PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Cypress Creek Renewables for the installation of a 4.99 MW solar PV generator and 3.5 MW/7 MWh batteries in Athol, MA interconnecting to the 13.8 kV 1193W3 feeder out of the Lost Town substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-078 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Pro-Tech Energy Solutions, LLC - Bragg Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Pro-Tech Energy Solutions, LLC for the installation of a 2.8 MW solar PV generator and 2.45 MW/ 4.9 MWh batteries in Warren, MA interconnecting to the 13.2 kV 516L2 feeder out of the Little Rest Road substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-079 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Cypress Creek Renewables - Coldbrook Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Cypress Creek Renewables for the installation of a 4.99 MW solar PV generator and 4.2 MW/ 16.8 MWh batteries in Oakham, MA interconnecting to the 34.5 kV 1194T1 feeder out of the Powder Mill substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 10/20/2020
NEP-20-G03-080 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - General Electric International - Bliss Road PV | Generator application from New England Power Company ("NEP") on behalf of General Electric International for the installation of a 4.625 MW solar PV generator in Florida, MA interconnecting to the 13.8 kV 1015W1 feeder out of the Walker Street substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-081 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - C-Tec Solar - Chapel Street PV and BESS | Generator application from New England Power Company ("NEP") on behalf of C-Tec Solar for the installation of a 4.998 MW solar PV generator and 2.5 MW/5.0 MWh batteries in Leicester, MA interconnecting to the 13.8 kV 2236W2 feeder out of the Stafford Street substation. | 2022-10-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-082 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sunpin Solar Development - Brimfield Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Sunpin Solar Development for the installation of a 4.999 MW solar PV generator and 3.0 MW/ 5.998 MWh batteries in Warren, MW interconnecting to the 13.2 kV 516L1 feeder out of the Little Rest Road substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 2/16/2021
NEP-20-G03-083 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - C-Tec Solar - Armsby Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of C-Tec Solar for the installation of a 3.142 MW solar PV generator and 1.0 MW/ 4.0 MWh batteries in Sutton, MA interconnecting to the 13.8 kV 304W6 feeder out of the Millbury substation. | 2021-06-01 | Approved | 2020-07-08
NEP-20-G03-084 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Omni-Lumens Holdings 3 - Quabbin Boulevard PV | Generator application from New England Power Company ("NEP") on behalf of Omni-Lumens Holdings 3 for the installation of a 1.518 MW solar PV generator in Orange, MA interconnecting to the 13.8 kV 705W2 feeder out of the Wendell Depot substation. | 2021-06-01 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G03-085 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Williamsville Road Solar - Williamsville Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Williamsville Road Solar for the installation of a 3.0 MW solar PV generator and 1.5 MW/2.5 MWh batteries in Hubbardston, MA interconnecting to the 34.5 kV 1194T3 feeder out of the Power Mill substation. | 2022-10-01 | Approved Withdrawn | 6/2/2020 10/20/2020
NEP-20-G03-086 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sunpin Solar Development - Sizer Drive PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Sunpin Solar Development for the installation of a 3.0 MW solar PV generator and 1.0 MW/1.885 MWh batteries in Wales, MA interconnecting to the 13.2 kV 516L1 feeder out of the Little Rest Road substation. | 2021-06-01 | Approved Withdrawn | 6/2/2020 2/16/2021
NEP-20-G03-087 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sunpin Solar Development - Wachusett Street PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Sunpin Solar Development for the installation of a 4.99 MW solar PV generator and 3.0 MW/5.998 MWh batteries in Leominster, MA interconnecting to the 13.8 kV 207W6 feeder out of the Litchfield Street substation. | 2021-06-01 | Approved Withdrawn | 6/2/2020 11/16/2021
NEP-20-G03-088 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Green Street Power Partners - Simplex Drive PV | Generator application from New England Power Company ("NEP") on behalf of Green Street Power Partners for the installation of a 3.78 MW solar PV generator in Westminster, MA interconnecting to the 34.5 kV 1616T2 feeder out of the Whitmanville substation. | 2022-10-01 | Approved Withdrawn | 6/2/2020 10/20/2020
NEP-20-G03-089 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Industria Engineering - George Hill Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Industria Engineering for the installation of a 4.56 MW solar PV generator and 3.5 MW/8.456 MWh batteries in Grafton, MA interconnecting to the 13.8 kV 304W2 feeder out of the Millbury substation. | 2021-06-01 | Approved | 2020-06-02
NEP-20-G03-090 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Carbon Finance Strategies - Maine Street PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Carbon Finance Strategies for the installation of a 3.3 MW solar PV generator and 1.5 MW/3.0 MWh batteries in Wilbraham, MA interconnecting to the 13.2 kV 507L2 feeder out of the Wilbraham substation. | 2021-06-01 | Approved Withdrawn | 6/2/2020 2/16/2021
NEP-20-G03-091 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Borrego Solar - Carpenter Hill Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Borrego Solar for the installation of a 3.5 MW solar PV generator and 1.98 MW/3.96 MWh batteries in West Charlton, MA interconnecting to the 13.2 kV 415L2 feeder out of the West Charlton substation. | 2021-06-01 | Approved Withdrawn | 6/2/2020 3/16/2021
NEP-20-G03-092 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sunpin Solar Development - New Athol Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Sunpin Solar Development for the installation of a 3.0 solar PV generator and 3.0 MW/5.998 MWh batteries in Petersham, MA interconnecting to the 13.8 kV 1193W3 feeder out of the Lost Town substation. | 2022-10-01 | Approved Withdrawn | 6/2/2020 10/20/2020
NEP-20-G03-093 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Clean Energy Collective - Clemence Hill Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Clean Energy Collective for the installation of a 1.32 MW solar PV generator and 1.5 MW/3.288 MWh batteries in Southbridge, MA interconnecting to the 13.2 kV 413L2 feeder out of the Snow Street substation. | 2021-06-01 | Approved Withdrawn | 6/2/2020 5/16/2023
NEP-20-G03-094 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sol Systems - Maple Avenue PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Sol Systems for the installation of a 4.998 MW solar PV generator and 3.5 MW/7.672 MWh batteries in Rutland, MA interconnecting to the 34.5 kV 1194T3 feeder out of the Powder Mill substation. | 2022-10-01 | Approved Withdrawn | 6/2/2020 10/20/2020
NEP-20-G03-095 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Sol Systems - Wheeler Road PV and BESS | Generator application from New England Power Company ("NEP") on behalf of Sol Systems for the installation of a 4.998 MW solar PV generator and 3.5 MW/7.672 MWh batteries in Rutland, MA interconnecting to the 34.5 kV 1194T3 feeder out of the Powder Mill substation. | 2022-10-01 | Approved Withdrawn | 6/2/2020 10/20/2020
NEP-20-G03-096 | 2020-05-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - UGT - Keyes Road PV 3 | Generator application from New England Power Company ("NEP") on behalf of UGT for the installation of a 4.99 MW solar PV generator in Gardner, MA interconnecting to the 13.8 kV 607W8 feeder out of the Crystal Lake substation. | 2022-10-01 | Approved | 2020-06-02
NEP-20-T09 | 2020-04-20 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Whitmanville 115/34/13.8 kV Substation | Transmission application from New England Power Company ("NEP") to install a new substation Whitmanville on the 115 kV I-135 line in Westminster, MA with an in-line breaker that will sectionalize the existing line into I-135 (Chinook - Whitmanville) and I-I135E (Whitmanville - Flagg Pond) with three distribution transformers. | 9/2023 | Approved Withdrawn | 6/2/2020 10/20/2020
NEP-20-T10 | 2020-04-20 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - East Winchendon Transformer Addition | Transmission application from New England Power Company ("NEP") to replace the T1 distribution transformer and replace the airbreak with a circuit switcher. Add a T2 distribution transformer and associated distribution equipment. | 9/2023 | Approved | 2020-06-02
NEP-20-T11 | 2020-04-20 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Otter River 69 kV Ring Bus Addition and Dvar | Transmission application from New England Power Company ("NEP") to convert the 69 kV Otter River substation to a three bay breaker and a half scheme and add two 69 kV DVAr (16 MVAr each) off each main bus. | 9/2027 | Approved | 2020-06-02
NEP-20-T12 | 2020-04-20 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Wendell Depot Transformer Addition | Transmission application from New England Power Company ("NEP") to replace the T1 distribution transformer and associated equipment and add a T2 distribution transformer and associated distribution equipment. | 9/2023 | Approved Withdrawn | 6/2/2020 3/16/2021
NEP-20-T13 | 2020-04-20 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Lost Town 115/13.8 kV Substation | Transmission application from New England Power Company ("NEP") to install a new substation, Lost Town, on the 115 kV A-127 line in Wendell, MA with an in-line breaker that will sectionalize the existing line into A-127 (Stafford Street - Lost Town) and A-127X (Lost Town - Erving) and add a new distribution transformer with associated distribution equipment. | 9/2023 | Approved Withdrawn | 6/2/2020 10/20/2020
NEP-20-T14 | 2020-04-20 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Barre Transformer Replacements | Transmission application from New England Power Company ("NEP") to replace the T1 and T2 distribution transformers at the Barre substation. | 9/2023 | Approved Withdrawn | 6/2/2020 3/16/2021
NEP-20-T15 | 2020-04-20 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Powder Mill 115/34.5 kV Substation | Transmission application from New England Power Company ("NEP") to install a new substation, Powder Mill, on the 115 kV A-127 line in Barre, MA that will tap the A-127 line between the Paxton and Barre substations. Add a new distribution transformer with associated distribution equipment. | 9/2023 | Approved Withdrawn | 6/2/2020 10/20/2020
NEP-20-T16 | 2020-04-20 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Stafford Street 115/13.8 kV Substation | Transmission application from New England Power Company ("NEP") to install a new substation, Stafford Street, in Leicester, MA that connects the A-127, B-128, and Z-126 line together via a three bay, 115 breaker and a half arrangement. Retire and remove the tower 510 airbreak switches and add two distribution transformers with associated distribution equipment. | 9/2023 | Approved | 2020-06-02
NEP-20-T17 | 2020-04-20 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Meadow Street 69 kV Breaker and Transformer Addition | Transmission application from New England Power Company ("NEP") to add a new distribution transformer with associated distribution equipment at the Meadow Street substation with a new 69 kV circuit breaker. | 9/2023 | Approved Withdrawn | 6/2/2020 3/16/2021
NEP-20-T18 | 2020-04-20 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Ware 69/13.2 kV Transformer Addition | Transmission application from New England Power Company ("NEP") to add a new distribution transformer with associated distribution equipment at the Ware substation. | 9/2023 | Approved Withdrawn | 6/2/2020 3/16/2021
NEP-20-T19 | 2020-04-20 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Lashaway 69 kV Transformer Replacement | Transmission application from New England Power Company ("NEP") to replace the T1 and T2 distribution transformers and replace the 69 kV transformer airbreaks with circuit switchers. Modify associated distribution equipment to convert modular feeders to standard switch and a half configuration. | 9/2023 | Approved Withdrawn | 6/2/2020 3/16/2021
NEP-20-T20 | 2020-04-20 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Little Rest Road 115 kV Breaker and Transformer Additions | Transmission application from New England Power Company ("NEP") to install a 115 kV breaker at Little Red Road substation, in-line with the W-175 line. The in-line breaker will sectionalize the existing line into W-175W (Palmer - Little Rest Road) and W-175E (Little Rest Road - Carpenter Hill). Add two distribution transformers with associated distribution equipment. | 9/2023 | Approved | 2020-06-02
NEP-20-T21 | 2020-04-20 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Thorndike 115 kV Breaker and Transformer Additions | Transmission application from New England Power Company ("NEP") to loop the X-176 line through a new in-line circuit breaker and associated equipment, sectionalizing the existing line into X-176E (Palmer - Thorndike) and X-176W (Thorndike - Ludlow). Remove the 115 kV disconnect switch 7617. Add a new distribution transformer with associated distribution equipment. | 9/2023 | Approved Withdrawn | 6/2/2020 10/20/2020
NEP-20-T22 | 2020-04-20 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Palmer 115 kV Transformer Addition and Replacement | Transmission application from New England Power Company ("NEP") to add one distribution transformer with associated distribution equipment, replace the T2 distribution transformer with associated distribution equipment, and move the existing T7 distribution transformer from bus 1 to bus 2 at the Palmer substation. | 9/2023 | Approved Withdrawn | 6/2/2020 10/20/2020
NEP-20-T23 | 2020-04-20 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Westminster Substation Retirement | Transmission application from New England Power Company ("NEP") to retire the Westminster substation after the installation of the Whitmanville substation. Remove the 69 kV taps from lines A-1/B-2 to station, remove the distribution transformer and the Westminster switch tower and tap and in-line switches. | 9/2023 | Approved Withdrawn | 6/2/2020 10/20/2020
NEP-20-T24 | 2020-04-20 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Leicester Substation Retirement | Transmission application from New England Power Company ("NEP") to retire the Leicester substation after installation of Stafford Street substation and remove the 69 kV taps from lines E-5E/F6-E to station and remove the distribution transformers. | 9/2023 | Approved Withdrawn | 6/2/2020 3/16/2021
NEP-14-T07 Rev.2 | 2020-04-20 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - North Oxford Breaker and Transformer Addition | Transmission application from New England Power Company ("NEP") to loop the V-174 line through a new in-line circuit breaker and associated equioment, sectionalizing the existing line into V174E (Millbury - N Oxford) and V-174W (N Oxford - Carpenter Hill). Add a new distribution transformer with associated distribution equipment. | 9/2023 | Approved Withdrawn | 6/2/2020 3/16/2021
NEP-20-T26 | 2020-04-20 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - Ware 69 kV Breaker Addition | Transmission application from New England Power Company ("NEP") to install a new 69 kV circuit breaker for lin O-15N, completing the third 69 kV bay at the Ware substation. | 9/2023 | Approved | 2020-06-02
NEP-20-T27 | 2020-04-22 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 2) Generation and Transmission Project - A-1/B-2 69 kV Reconductoring | Transmission application from New England Power Company ("NEP") to reconductor all sections of the A-1 and B-2 69 kV main lines from Pratts Junction substation to Vernon substation (including Athol and Gardner taplines) with 795 ACSS conductor. | 1/2027 | Approved | 2020-06-02
NEP-20-G04-001 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - Econox Renewables - Howard Avenue PV | Generator application from New England Power Company ("NEP") on behalf of Econox Renewables for the installation of a 3.12 MW solar PV generator in North Scituate, RI interconnecting to the 12.47 kV 38F1 feeder out of the Putnam Pike substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-002 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - Episcopal Diocese of Rhode Island - Reservoir Road PV | Generator application from New England Power Company ("NEP") on behalf of the Episcopal Diocese of Rhode Island for the installation of a 2.2 MW solar PV generator in Chepacket, RI interconnecting to the 12.47 kV 34F2 feeder out of the Chopmist substation. | 2021-07-15 | Approved Withdrawn | 7/8/2020 8/13/2024
NEP-20-G04-003 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - Green Development - Scituare Avenue | Generator application from New England Power Company ("NEP") on behalf of Green Development for the installation of a 4.25 MW solar PV generator in Johnston, RI interconnecting to the 12.47 kV 18F11 feeder out of the Johnston substaiton. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-004 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - Nexamp Solar - Putnam Pike PV | Generator application from New England Power Company ("NEP") on behalf of Nexamp Solar for the installation of a 2.5 MW solar PV generator in Chapachet, RI interconnecting to the 12.47 kV 38F1 feeder out of the Putnam Pike substation. | 2021-07-15 | Approved Withdrawn | 7/8/2020 8/18/2020
NEP-20-G04-005 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - ECA Solar - Strawberry Field Road PV | Generator application from New England Power Company ("NEP") on behalf of ECA Solar for the installation of a 3.85 MW solar PV generator in Warwick, RI interconnecting to the 23 kV 2222 feeder out of the Drumrock substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-006 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - Freepoint Solar - Burdick Road PV | Generator application from New England Power Company ("NEP") on behalf of Freepoint Solar for the installation of a 3.34 MW solar PV generator in Charlestown, RI interconnecting to the 34.5 kV 85T3 feeder out of the Wood River substation. | 2021-07-15 | Approved Withdrawn | 7/8/2020 11/18/2020
NEP-20-G04-007 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - Direct Energy Solar - Chase Hill Road PV | Generator application from New England Power Company ("NEP") on behalf of Direct Energy Solar for the installation of a 2.464 MW solar PV generator in Ashaway, RI interconnecting to the 12.47 kV 155F4 feeder out of the Chase Hill substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-008 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - Freepoint Solar - Gardner Road PV | Generator application from New England Power Company ("NEP") on behalf of Freepoint Solar for the installation of a 4.5 MW solar PV generator in Charlestown, RI interconnecting to the 34.5 kV 85T3 feeder out of the Wood River substation. | 2020-07-21 | Approved Withdrawn | 7/8/2020 11/18/2020
NEP-20-G04-009 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - Green Development - Main St PV | Generator application from New England Power Company ("NEP") on behalf of Green Development for the installation of a 3.875 MW solar PV generator in Hopkinton, RI interconnecting to the 12.47 kV 155F8 feeder out of the Chase Hill substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-010 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - Green Development - Exeter Road PV | Generator application from New England Power Company ("NEP") on behalf of Green Development for the installation of a 2.0 MW solar PV generator in Exeter, RI interconnecting to the 12.47 kV 88F1 feeder out of the Tower Hill substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-011 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - ISM Solar Development | Generator application from New England Power Company ("NEP") on behalf of ISM Solar Development for the installation of a 3.5 MW solar PV generator in Richmond, RI interconnecting to the 12.47 kV 68F1 feeder out of the Kenyon substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-012 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - Oak Square Partners - South Road PV | Generator application from New England Power Company ("NEP") on behalf of Oak Square Partners for the installation of a 4.422 MW solar PV generator in East Greenwich, RI interconnecting to the 12.47 kV 46F1 feeder out of the Old Baptist substation. | 2021-07-15 | Approved Withdrawn | 7/8/2020 8/13/2024
NEP-20-G04-013 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - Direct Energy Solar - Arnold Place PV | Generator application from New England Power Company ("NEP") on behalf of Direct Energy Solar for the installation of a 3.8 MW solar PV generator in Exeter, RI interconnecting to the 12.47 kV 30F1 feeder out of the Lafayette substation. | 2021-07-15 | Approved Withdrawn | 7/8/2020 8/18/2020
NEP-20-G04-014 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - Nautilus Solar Energy - Ten Rod Road PV | Generator application from New England Power Company ("NEP") on behalf of Nautilus Solar Energy for the installation of a 2.75 MW solar PV generator in Exeter, RI interconnecting to the 12.47 kV 30F2 feeder out of the Lafayette substation. | 2021-07-15 | Approved Withdrawn | 7/8/2020 8/13/2024
NEP-20-G04-015 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - DuTemple Solar - Ten Rod Road PV | Generator application from New England Power Company ("NEP") on behalf of DuTemple Solar for the installation of a 1.4 MW solar PV generator in Exeter, RI interconnecting to the 12.47 kV 30F2 feeder out of the Lafayette substation. | 2021-07-15 | Approved Withdrawn | 7/8/2020 8/18/2020
NEP-20-G04-016 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - Dry Bridge 1 | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 10 MW solar PV geerator in North Kingstown, RI interconnecting to the 34.5 kV 89T1 feeder out of the Wickford Junction substaiton. | 2021-07-15 | Approved Withdrawn | 7/8/2020 12/17/2024
NEP-20-G04-017 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - Dry Bridge 2 | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 10 MW solar PV geerator in North Kingstown, RI interconnecting to the 34.5 kV 89T1 feeder out of the Wickford Junction substaiton. | 2021-07-15 | Approved Withdrawn | 7/8/2020 12/17/2024
NEP-20-G04-018 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - Dry Bridge 3 | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 10 MW solar PV geerator in North Kingstown, RI interconnecting to the 34.5 kV 89T1 feeder out of the Wickford Junction substaiton. | 2021-07-15 | Approved Withdrawn | 7/8/2020 12/17/2024
NEP-20-G04-019 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - Dry Bridge 4 | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 10 MW solar PV geerator in North Kingstown, RI interconnecting to the 34.5 kV 89T1 feeder out of the Wickford Junction substaiton. | 2021-07-15 | Approved Withdrawn | 7/8/2020 12/17/2024
NEP-20-G04-020 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - Exeter Renewables 1 | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 10 MW solar PV geerator in Exeter, RI interconnecting to the 34.5 kV 89T1 feeder out of the Wickford Junction substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-021 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - GD Exeter Ten Rod II | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 2.64 MW solar PV generator in Exeter, RI interconnecting to the 34.5 kV 89T2 feeder out of the Wickford Junction substaiton. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-022 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - Exeter Tripps II | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 7.04 MW solar PV generator in Exeter, RI interconnecting to the 34.5 kV 89T2 feeder out of the Wickford Junction substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-023 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - Stamp Array I | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 7.04 MW solar PV generator in Exeter, RI interconnecting to the 34.5 kV 89T2 feeder out of the Wickford Junction substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-024 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - WED Ridge Solar II | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 9.68 MW solar PV generator in Exeter, RI interconnecting to the 34.5 kV 89T2 feeder out of the Wickford Junction substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-025 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - WED Ridge Solar III | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 8.8 MW solar PV generator in Exeter, RI interconnecting to the 34.5 kV 89T2 feeder out of the Wickford Junction substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-026 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - GD Exeter Ten Rod I | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 4.4 MW solar PV generator in Exeter, RI interconnecting to the 34.5 kV 89T2 feeder out of the Wickford Junction substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-027 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - GD Exeter Queens I | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 7.04 MW solar PV generator in Exeter, RI interconnecting to the 34.5 kV 89T2 feeder out of the Wickford Junction substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-028 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - GD Exeter Tripps I | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 7.04 MW solar PV generator in Exeter, RI interconnecting to the 34.5 kV 89T2 feeder out of the Wickford Junction substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-029 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - GD Exeter Queens II | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 4.4 MW solar PV generator in Exeter, RI interconnecting to the 34.5 kV 89T2 feeder out of the Wickford Junction substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-030 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - GD Richmond Beaver River I | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 5.28 MW solar PV generator in West Kingston, RI interconnecting to the 12.47 kV 68F1 feeder out of the Kenyon substation. | 2021-07-15 | Approved Withdrawn | 7/8/2020 8/13/2024
NEP-20-G04-031 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - Nautilus Solar | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 8.0 MW solar PV generator in Ashaway, RI interconnecting to the 34.5 kV 85T1 feeder out of the Wood River substation. | 2021-07-15 | Approved Withdrawn | 7/8/2020 9/23/2020
NEP-20-G04-032 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - Revity Energy | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 6.25 MW solar PV generator in Cranston, RI interconnecting to the 12.47 kV 21F1 feeder out of the West Cranston substation. | 2021-07-15 | Approved Withdrawn | 7/8/2020 8/13/2024
NEP-20-G04-033 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - TPE Development | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 9.8 MW solar PV generator in West Greenwich, RI interconnecting to the 12.47 kV 3311 feeder out of the Kent County substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-034 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - GD West Greenwich Nooseneck I | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 10.0 MW solar PV generator in West Greenwich, RI interconnecting to the 34.5 kV 3310 feeder out of the Kent County substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-035 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - GD West Greenwich Nooseneck II | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 10.0 MW solar PV generator in West Greenwich, RI interconnecting to the 34.5 kV 3310 feeder out of the Kent County substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-036 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - Nautilus Solar | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 6.75 MW solar PV generator in Exeter, RI interconnecting to the 12.47 kV 88F1 feeder out of the Tower Hill substation. | 2021-07-15 | Approved Withdrawn | 7/8/2020 8/13/2024
NEP-20-G04-037 | 2020-05-08 | Western Rhode Island Distributed Energy Resource Cluster - Ameresco | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 6.474 MW solar PV generator in Westerly, RI interconnecting to the 34.5 kV 85T2 feeder out of the Wood River substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-038 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - GD Hopkinton Main I Project 1 | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 2.625 MW solar PV generator in Hopkinton, RI interconnecting to the 12.47 kV 155F6 feeder out of the Chase Hill substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-G04-039 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - Chase Hill Substation | Generator application from New England Power Company ("NEP") on behalf of Narragansett Electric for the installation of a 4.125 MW solar PV generator in Hopkinton, RI interconnecting to the 12.47 kV 155F6 feeder out of the Chase Hill substation. | 2021-07-15 | Approved | 2020-07-08
NEP-20-T25 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - Wickford Junction Substation | Transmission application from New England Power Company ("NEP") on behalf of Narragansett Electric to loop the L-190 line into a new four breaker ring bus at the new Wickford Junction Substation, sectionalizing the existing line into the L-190S (Wickford Junction - Tower Hill - West Kingston) and L-190N (Wickford Junction - Davisville Tap - Kent County). Add two new distribution transformers with associated distribution equipment. | 2021-07-15 | Approved | 2020-06-02
NEP-20-T31 | 2020-04-24 | Western Rhode Island Distributed Energy Resource Cluster - G-185N and K-189 Uprate | Transmission application from New England Power Company ("NEP") on behalf of Narragansett Electric to reconductor the G-185N and replace conductor hardware on the K-189 line to increase the ratings. | 2020-07-15 | Approved Withdrawn | 6/2/2020 4/27/2022
ES-20-G137 | 2020-05-05 | Industrial Park Distributed Energy Resource Cluster - Industrial Park - Duchaine Boulevard | Generator application from Eversource Energy ("ES") for the installation of a 1.384 MW solar PV generator in New Bedford, MA interconnecting to the 13.2 kV 152 feeder out of the Industrial Park substation. | 2020-12-31 | Approved | 2020-06-26
ES-20-G138 | 2020-05-05 | Industrial Park Distributed Energy Resource Cluster - Kearsarge - New Bedford | Generator application from Eversource Energy ("ES") for the installation of a 4.99 MW solar PV generator in New Bedford, MA interconnecting to the 13.2 kV 2-103-103 feeder out of the Industrial Park substation. | 2020-09-08 | Approved | 2020-06-26
ES-20-G143 | 2020-05-05 | Industrial Park Distributed Energy Resource Cluster - Freetown Solar - Bullock Road | Generator application from Eversource Energy ("ES") for the installation of a 4.99 MW solar PV generator and 4.99 MW/ 26.3 MWh batteries in Freetown, MA interconnecting to the 13.2 kV 102 feeder out of the Industrial Park substation. | 2020-07-01 | Approved | 2020-06-26
ES-20-G139 | 2020-05-05 | Mattapoisset/Achusnet Area Distributed Energy Resource Cluster - Acushnet Solar - Main Street | Generator application from Eversource Energy ("ES") for the installation of a 1.0 MW solar PV generator in Acushnet, MA interconnecting to the 13.2 kV 241 line out of the Wing Lane substation. | 2021-03-31 | Approved | 2020-06-26
ES-20-G140 | 2020-05-05 | Mattapoisset/Achusnet Area Distributed Energy Resource Cluster - Acushnet Solar - Robinson Road | Generator application from Eversource Energy ("ES") for the installation of a 1.0 MW solar PV generator in Acushnet, MA interconnecting to the 13.2 kV 241 line out of the Wing Lane substation. | 2021-03-31 | Approved | 2020-06-26
ES-20-G141 | 2020-05-05 | Mattapoisset/Achusnet Area Distributed Energy Resource Cluster - Acushnet Solar - Cushing Road | Generator application from Eversource Energy ("ES") for the installation of a 2.0 MW solar PV generator in Acushnet, MA interconnecting to the 13.2 kV 241 line out of the Wing Lane substation. | 2021-03-31 | Approved | 2020-06-26
ES-20-G142 | 2020-05-05 | Mattapoisset/Achusnet Area Distributed Energy Resource Cluster - Acushnet Solar - Main Street | Generator application from Eversource Energy ("ES") for the installation of a 1.0 MW solar PV generator in Acushnet, MA interconnecting to the 13.2 kV 241 line out of the Wing Lane substation. | 2021-03-31 | Approved | 2020-06-26
ES-20-G149 | 2020-05-06 | Mattapoisset/Achusnet Area Distributed Energy Resource Cluster - BWC Acushnet River, LLC | Generator application from Eversource Energy ("ES") on behalf of BWC Acushnet, LLC for the installation of a 4.6 MW solar PV generator and 2.75 MW/ 5.5 MWh batteries in Mattapoisett, MA interconnecting to the 13.2 kV 301 line out of the Crystal Spring substation. | 2021-04-15 | Approved Withdrawn | 6/26/2020 4/18/2023
ES-20-G150 | 2020-05-06 | Mattapoisset/Achusnet Area Distributed Energy Resource Cluster - BWC Mill Pond, LLC | Generator application from Eversource Energy ("ES") on behalf of BWC Mill Pond, LLC for the installation of a 4.98 MW solar PV generator and 2.8 MW/ 5.6 MWh batteries in Mattapoisett, MA interconnecting to the 13.2 kV 301 line out of the Crystal Spring substation. | 2021-04-14 | Approved Withdrawn | 6/26/2020 4/18/2023
ES-20-G151 | 2020-05-06 | Mattapoisset/Achusnet Area Distributed Energy Resource Cluster - BWC Nyes Cove, LLC | Generator application from Eversource Energy ("ES") on behalf of BWC Nyes Cove, LLC for the installation of a 4.98 MW solar PV generator and 2.8 MW/ 5.6 MWh batteries in Mattapoisett, MA interconnecting to the 13.2 kV 302 line out of the Crystal Spring substation. | 2021-04-14 | Approved Withdrawn | 6/26/2020 3/16/2021
ES-20-G152 | 2020-05-06 | Mattapoisset/Achusnet Area Distributed Energy Resource Cluster - BlueWave Solar | Generator application from Eversource Energy ("ES") on behalf of BlueWave Solar for the installation of a 2.6 MW solar PV generator and 1.5 MW/ 3.0 MWh batteries in Mattapoisett, MA interconnecting to the 13.2 kV 302 line out of the Crystal Spring substation. | 2021-04-14 | Approved Withdrawn | 6/26/2020 3/16/2021
ES-20-G153 | 2020-05-05 | Mattapoisset/Achusnet Area Distributed Energy Resource Cluster - BWC Pine Island Pond, LLC | Generator application from Eversource Energy ("ES") on behalf of BWC Pine Island Pond, LLC for the installation of a 3.3 MW solar PV generator and 2.0 MW/ 4.0 MWh batteries in Mattapoisett, MA interconnecting to the 13.2 kV 302 line out of the Crystal Spring substation. | 2021-04-14 | Approved Withdrawn | 6/26/2020 3/16/2021
BRP-20-G01 | 2020-04-10 | Great Lakes Hydro America Millinocket - Powersville Battery Project | Generator application from Brookfield Renewable Trading and Marketing on behalf of Great Lakes Hydro America (GLHA) for the installation of two 10.5 MW battery systems at the existing GLHA generation facility located in Millinocket, ME interconnecting to the 34.5 kV Millinocket substation and the 34.5 kV Powersville substation in Medway, ME. | 2020-06-01 | Approved | 2020-06-02
ES-20-G124 | 2020-05-08 | Revolution Wind I Offshore Wind Farm | Generator application from Eversource Energy ("ES") on behalf of DDW Rev I, LLC for the installation of a 704 MW offshore wind farm, in Washington County, RI interconnecting near the Davisville substation. | 2023-12-01 | Approved | 2020-06-02
ES-20-T20 | 2020-05-08 | Revolution Wind I Offshore Wind Farm | Transmission application from Eversource Energy ("ES") on behalf of DDW Rev I, LLC for the installation of a +175/-78.5 MVAr synchronous condenser in Washington County, RI interconnecting to the Revolution Wind substation. | 2023-01-31 | Approved | 2020-06-02
ES-20-T21 | 2020-05-08 | Revolution Wind I Offshore Wind Farm | Transmission application from Eversource Energy ("ES") on behalf of DDW Rev I, LLC for the installation of a +300/-100 MVAr synchronous condenser in Washington County, RI interconnecting to the Revolution Wind substation. | 2023-01-31 | Approved | 2020-06-02
ES-20-T22 | 2020-05-08 | Revolution Wind I Offshore Wind Farm | Transmission application from Eversource Energy ("ES") on behalf of DDW Rev I, LLC for the installation of two 275/115 kV transformers in Washington County, RI interconnecting to the Revolution Wind substation. | 2023-01-31 | Approved | 2020-06-02
ES-20-T23 | 2020-05-08 | Revolution Wind I Offshore Wind Farm | Transmission application from Eversource Energy ("ES") on behalf of DDW Rev I, LLC for the installation of three-core submarine and single-core underground cables in Washington County, RI interconnecting from the Revolution Wind 275/66 kV off-shore substation to the Revolution Wind 275/115 kV on-shore substation. | 2023-01-31 | Approved | 2020-06-02
ES-20-T24 | 2020-05-08 | Revolution Wind I Offshore Wind Farm | Transmission application from Eversource Energy ("ES") on behalf of DDW Rev I, LLC for the installation of four 275/66 kV transformers in Washington County, RI interconnecting to the Revolution Wind substation. | 2023-01-31 | Approved | 2020-06-02
ES-20-T25 | 2020-05-08 | Revolution Wind I Offshore Wind Farm | Transmission application from Eversource Energy ("ES") on behalf of DDW Rev I, LLC for the installation of a Cu cable, single core in Washington County, RI interconnecting the Revolution Wind substation to the Davisville substation. | 2023-01-31 | Approved | 2020-06-02
ES-20-T26 | 2020-04-06 | Revolution Wind I Offshore Wind Farm | Transmission application from Eversource Energy ("ES") for the installation of a redundant circuit breaker for the 345 kV 3T breaker at the Card substation in Connecticut. | 2023-01-31 | Approved | 2020-06-26
NEP-20-T06 | 2020-05-14 | Revolution Wind I Offshore Wind Farm | Transmission application from New England Power Company ("NEP") on behalf of Naragansett Electric to rebuild of the Davisville substation located in North Kingstown, RI to a six breaker ring bus substation. | 2023-01-31 | Approved | 2020-06-02
NEP-20-T07 | 2020-05-14 | Revolution Wind I Offshore Wind Farm | Transmission application from New England Power Company ("NEP") on behalf of Naragansett Electric to reconductor the G-185N and K-189 lines from Kent County to Drumrock. | 2023-01-31 | Approved | 2020-06-02
NEP-20-T08 | 2020-05-14 | Revolution Wind I Offshore Wind Farm | Transmission application from New England Power Company ("NEP") on behalf of Naragansett Electric to reconductor the G-185S and L-190 lines. The G-185S will be reconductored from Kent County to Davisville Tap to Old Baptist to Davisville. The L-190 will be reconductored from Kent County to Davisville Tap to Old Baptist to Davisville and Tower Hill to Davisville Tap. | 2023-01-31 | Approved | 2020-06-02
NEP-20-T32 | 2020-05-14 | Revolution Wind I Offshore Wind Farm | Transmission application from New England Power Company ("NEP") on behalf of Naragansett Electric to upgrade the K-189 and G185N limiting 115 kV equipment and five circuit breakers at the Drumrock substation. | 2023-01-31 | Approved | 2020-06-02
CMP-20-G25 | 2020-05-05 | Longroad Development Ridge Road Monmouth Solar Project | Generator notification Central Maine Power ("CMP") on behalf of Longroad Development Company, LLC for the installation of a 4.95 MW solar PV generator in Monmouth Maine interconnecting to the 475D1 34,5kV distribution circuit from CMP Monmouth Substation. | 2021-09-30 | Approved | 2020-06-25
CMP-20-G26 | 2020-05-05 | Cianbro Detroit Somerset Avenue Pittsfield Solar Project | Generator notification Central Maine Power ("CMP") on behalf of Cianbro Development Company for the installation of a 4.98 MW solar PV generator in Pittsfield Maine interconnecting to 812D1 12.47kV distribution circuit from CMP Detroit Substation. | 2021-12-31 | Approved | 2020-06-25
CMP-20-G27 | 2020-05-05 | Dynamic Energy Solutions River Road Norridgewock Solar Project | Generator notification Central Maine Power ("CMP") on behalf of Dynamic Energy Solutions, LLC for the installation of a 4.999 MW solar PV generator in Norridgewock Maine interconnecting to 864D1 12.47kV distribution circuit from CMP Skowhegan Tap Substation. | 2020-12-31 | Approved | 2020-06-25
CMP-20-G28 | 2020-05-05 | BD Solar Fairfield Street Oakland Solar Project | Generator notification Central Maine Power ("CMP") on behalf of BD Solar Oakland, LLC for the installation of a 4.99 MW solar PV generator in Oakland Maine interconnecting to 873D1 34.5 kV distribution circuit from CMP County Road Substation. | 2021-05-15 | Approved | 2020-06-25
CMP-20-G31 | 2020-05-05 | MEVS Clark Wyman Hydro Nichols Hill Road Bingham Solar Project | Generator notification Central Maine Power ("CMP") on behalf of MEVS Clark, LLC for the installation of a 4.98 MW solar PV generator in Bingham, ME and interconnecting to the 872D1 distribution circuit from Wyman Hydro Substation. | 2021-09-30 | Approved | 2020-06-25
CMP-20-G32 | 2020-05-05 | MEVS Old Ferry Road Chewanki Neck Road Wiscasset Solar Project | Generator notification Central Maine Power ("CMP") on behalf of MEVS Wiscasset, LLC for the installation of a 4.98 MW solar PV generator in Wiscasset Maine interconnecting to 274D1 12.47kV distribution circuit from CMP Maine Yankee Substation. | 2021-09-30 | Approved Withdrawn | 6/25/2020 8/17/2021
CMP-20-G33 | 2020-05-05 | Berwick Solar, LLC Route 236 Berwick Solar Project | Generator notification Central Maine Power ("CMP") on behalf of Berwick Solar, LLC for the installation of a 3.545 MW solar PV generator in Berwick Maine interconnecting to 603D2 12.47kV distribution circuit from CMP Berwick Substation. | 2021-01-15 | Approved | 2020-06-25
CMP-20-G34 | 2020-05-05 | TPE Harmony Road Athens Solar Project | Generator notification Central Maine Power ("CMP") on behalf of TPE Development, LLC for the installation of a 4.4 MW solar PV generator in Athens Maine interconnecting to 827D2 12.47kV distribution circuit from CMP Athens Substation. | 2021-07-31 | Approved | 2020-06-25
CMP-20-G36 | 2020-05-05 | HEP Energy McLucas Road Waldoboro Solar Project | Generator notification Central Maine Power ("CMP") on behalf of HEP Energy USA Project Development, LLC for the installation of a 4.875 MW solar PV generator in Waldoboro Maine interconnecting to the Waldoboro Substation through 671D1 12.47kV distribution circuit. | 2021-12-01 | Approved | 2020-06-25
CMP-20-G37 | 2020-05-05 | Nexamp Solar Wyman Hill Road Rumford Solar Project | Generator notification Central Maine Power ("CMP") on behalf of Nexamp Solar, LLC for the installation of a 4.99 MW solar PV generator in Rumford Maine interconnecting to 447D2 12.47kV distribution circuit from CMP Rumford Substation. | 2021-04-01 | Approved | 2020-06-25
CMP-20-G38 | 2020-05-05 | Dimension Livermore Falls CSG Turmel Road Jay Solar Project | Generator notification Central Maine Power ("CMP") on behalf of Livermore Falls CSG for the installation of a 3.25 MW solar PV generator in Jay, ME and interconnecting to 428D1 12.47kV distribution circuit from Livermore Falls. | 2021-02-28 | Approved | 2020-06-25
CMP-20-G39 | 2020-05-05 | SRE Farmington Falls Whitter Road Farmington Solar Project | Generator notification Central Maine Power ("CMP") on behalf of SRE Solar Origination 1, LLC for the installation of a 1.96 MW solar PV generator in Farmington Maine interconnecting to 818D2 12.47kV distribution circuit from CMP Farmington Falls Substation. | 2020-12-31 | Approved | 2020-06-25
ES-19-G73 Rev.1 | 2020-05-05 | Greenskies Renewables Taugwonk Spur Road North Stonington Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Greenskies Renewable Energy to increase the capacitcy from 2.5 MW to 4.98 MW. | 2022-06-30 | Approved | 2020-06-25
ES-20-G08 | 2020-04-30 | Renewable Energy Development Partners Swan Holt Pond Road Carver Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Renewable Energy Development Partners for the installation of a 2.98 MW solar PV generator in Carver, MA interconnecting to Line 10 out of West Pond Station #737. | 2020-11-20 | Approved | 2020-06-25
ES-20-G14 | 2020-05-05 | Pinegates Orchard Avenue Woodbury Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Tamarack Solar, LLC for the installation of a 4.0 MW solar PV generator in Woodbury, CT interconnecting to Carmel Hills 115kV Substation through Eversource 11S14 23kV distribution feeder. | 2021-04-01 | Approved Withdrawn | 6/25/2020 7/21/2020
ES-20-G54 | 2020-05-05 | BQ Energy Waterbury Mark Lane Waterbury Solar Project | Generator notification from Eversource Energy ("ES") on behalf of BQ Energy Waterbury for the installation of a 2.35 MW olar PV generator in Waterbury CT interconnecting to the Nera Substation through Eversource 13H99 13.8kV distribution feeder. | 2021-07-15 | Approved Withdrawn | 6/25/2020 9/20/2022
ES-20-G102 | 2020-04-30 | Citrine Power, LLC Skinner Street East Hampton Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Citrine Power, LLC for the installation of a 2.0 MW solar PV generator in East Hampton CT interconnecting to Portland 115-kV Substation through Eversource 21 H9 23kV distribution feeder. | 2022-06-30 | Approved | 2020-06-25
ES-20-G126 | 2020-04-23 | Cobb Road Durham Road Madison Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Cobb Road, LLC for the installation of a 1.99 MW solar PV generator in Madison, and interconnecting to Green Hill 115-kV Substation through the 30R10 23 kV distribution feeder. | 2021-06-25 | Approved | 2020-06-25
ES-20-G133 | 2020-04-23 | Cobb Road Route 9 Old Saybrook Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Cobb Road, LLC for the installation of a 1.98 MW solar PV generator in Old Saybrook, CT, and interconnecting to Bokum 115-kV Substation through the 15L6 13.8 kV distribution feeder. | 2021-06-25 | Approved Withdrawn | 6/25/2020 9/20/2022
ES-20-G134 | 2020-05-08 | Verogy North Street Enfield Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Verogy for the installation of a 4.975 MW solar PV generator in Enfield, CT, and interconnecting to Scitico 27H Substation through the #2 bus. | 2022-06-30 | Approved | 2020-06-25
ES-20-G135 | 2020-05-08 | Verogy Perkins Street Bristol Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Verogy for the installation of a 2.0 MW solar PV generator in Bristol, CT, and interconnecting to Chippen Hill 15U Substation through the B1 bus. | 2022-06-30 | Approved Withdrawn | 6/25/2020 9/20/2022
ES-20-G136 | 2020-05-08 | Verogy Tripp Road Ellington Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Verogy for the installation of a 2.0 MW solar PV generator in Ellington, CT, and interconnecting to Barbour Hill 23J Substation through the A2 bus. | 2022-06-30 | Approved Withdrawn | 6/25/2020 7/13/2021
ES-20-G144 | 2020-04-24 | Standard Solar, LLC Gate Street Carver Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Standard Solar, LLC for the installation of a 2.5 MW solar PV generator in Carver, MA interconnecting to the 3-10-10 Circuit out of West Pond Station #737. | 2020-09-14 | Approved | 2020-06-25
ES-20-G145 | 2020-04-23 | C-Tec Solar West Main Street North Canaan Solar Project | Generator notification from Eversource Energy ("ES") on behalf of C-Tec Solar for the installation of a 1.4 MW solar PV generator in North Canaan, CT and interconnecting to North Canaan Substation through the 5L02 13.2 kV distribution circuit. | 2022-06-30 | Approved | 2020-06-25
ES-20-G147 | 2020-04-23 | Sperry Solar, LLC Providence - New London Turnpike North Stonington Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Sperry Solar, LLC for the installation on a 1.001 MW solar PV generator in North Stonington, CT interconnecting to Shunock Substation through Eversource 32 P 4 13.8kV distribution feeder. | 2022-06-30 | Approved Withdrawn | 6/25/2020 9/20/2022
ES-20-G148 | 2020-04-23 | Independence Solar New Britain Avenue Farmington Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Independence Solar for the installation of a 1.98 MW solar PV generator in Farmington, CT and interconnecting to Farmington Substation through the 1C08 23 kV distribution circuit. | 2021-06-25 | Approved Withdrawn | 6/25/2020 6/18/2024
CMP-20-G29 | 2020-05-05 | Sunraise Route 32 China Solar and Battery Project | Generator notification from Central Maine Power ("CMP") on behalf of Route 32 China Solar Project, LLC for the installation of a 4.875 MW solar PV generator and 2.5 MW/ 5.48 MWh batteries in China Maine interconnecting to 244D1 12.47kV distribution circuit from CMP South China Substation. | 2021-02-15 | Approved | 2020-06-25
CMP-20-G30 | 2020-05-05 | Sunraise Perkins Road Belfast Solar and Battery Project | Generator notification from Central Maine Power ("CMP") on behalf of Sunraise Development, LLC for the installation of a 4.75 MW solar PV generator and 2.5 MW/ 5.48 MWh batteries in Belfast Maine interconnecting to 893D5 12.47kV distribution circuit from CMP Belfast West Side Substation. | 2021-02-15 | Approved | 2020-06-25
CMP-20-G35 | 2020-05-05 | Sunraise North Nobleboro Road Waldoboro Solar and Battery Project | Generator notification from Central Maine Power ("CMP") on behalf of Sunraise Development, LLC for the installation of a 2.5 MW solar PV generator and 1.25 MW/ 2.74 MWh batteries in Waldoboro, Maine interconnecting to 252D2 12.47kV distribution circuit from the CMP Waldoboro Substation. | 2021-02-25 | Approved | 2020-06-25
FGE-20-G01 | 2020-04-28 | Nexamp Solar West Meadow Road Townsend Solar and Battery Project | Generator notification from Fitchburg Gas and Electric on behalf of Nexamp Solar for the installation of a 1.99 MW solar PV generator and 1.0 MW/ 4.0 MWh battery in Townsend, MA interconnecting to West Townsend Substation via the 39W18 115 kV circuit. | 2021-02-28 | Approved Withdrawn | 6/25/2020 1/20/2021
ES-20-G130 | 2020-04-15 | Otis ANG Reilly Street Buzzards Bay Solar and Battery Project | Generator notification from Eversource Energy ("ES") on behalf of Otis ANG for the installation of a 4.832 MW solar PV generator and 4.832 MW/ 9.664 MWh batteries in Buzzards Bay, MA and interconnecting to 79 line from the Otis 915 Substation. | 2021-06-30 | Approved Withdrawn | 6/25/2020 6/18/2024
NEP-19-G30-027 Rev.1 | 2020-05-01 | Blue Wave Solar Shore Road Solar and Battery Project | Generator notification from New England Power Company ("NEP"), on behalf of BlueWave Solar to reduce the PV generator to 4.2 MW and add 1.118 MW/ 2.76 MWh batteries. | 2020-08-07 | Approved | 2020-06-25
UI-20-G01 | 2020-05-06 | Covidian McDermott Road North Haven Fuel Cell Project | Generator notification from United Illuminating ("UI") for a 2.0 MW fuel cell that replaces the existing 1.959 MW cogeneration unit in North Haven, CT interconnecting to 13.8kV Circuit 1701 East Shore Substation. | 2020-06-15 | Approved | 2020-05-19
UI-20-G02 | 2020-05-06 | Covidian Middletown Avenue North Haven Fueld Cell Project | Generator notification from United Illuminating ("UI") for a 2.0 MW fuel cell that replaces the existing 2.97 MW cogeneration unit in North Haven, CT interconnecting to 13.8kV Circuit 1550 Quinnipiac Substation. | 2020-06-15 | Approved | 2020-05-19
GB-20-G01 | 2020-04-09 | Engie Moultonborough Neck Road Moultonborough Energy Storage Project | Generator notification from Genbright on behalf of Engie Load Reduction Company, LLC for the installation of a 2.41 MW energy storage project interconnecting to NHEC Moultonborough Tie Line fed from LD Ashland 34.5kV Substation. | 2020-12-25 | Approved | 2020-06-25
ES-20-G122 | 2020-04-01 | Bloom Energy Fueld Cell Old Amston Road | Generator application from Eversource Energy ("ES") for the installation of a 10 MW fuel cell interconnecting to the 23kV bus of the Eversource Judd Brook 32R 27.6/23.0kV Substation. | 2020-12-01 | Approved | 2020-05-06
NEM-20-G04 | 2020-04-06 | Keay Brook Energy Center | Generator application from NextEra Energy Resources for the installation of a 20 MW solar facility in York County Maine interconnecting to the Avangrid Lebanon-Sanford 34.5kV Line supplied by Lebanon Substation. | 2023-12-31 | Approved Withdrawn | 5/6/2020 11/27/2024
NEP-19-G30-006 Rev.1 | 2020-04-01 | Blue Wave Solar Upper Gore Road Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Blue Wave Solar for the installation of a 4.98 MW solar PV generator and 3 MW/6 MWh batteries in Webster, MA interconnecting to the 13.2kV 412L1 Feeder out of the East Webster Substation. Revision is to add battery storage. | 2021-01-12 | Notification Withdrawn | 5/6/2020 3/16/2021
NEP-20-GNF22 | 2020-04-01 | BQ Energy Brayton Point Road Somerset Solar Project | Generator notification from New England Power Company ("NEP") on behalf of BQ Energy for the installation of a 3.05 MW solar PV generator in Somerset, MA interconnecting to the 13.8 11W84 Feeder out of Swansea Substation. | 2020-07-31 | Notification Withdrawn | 5/6/2020 10/20/2020
ES-20-T17 | 2020-03-16 | Reconductor the 110-510 and 110-511 115 kV Underground Cables | Transmission notification from Eversource ("ES") to reconductor the 110-510 and 110-511 115 kV underground cables between the Baker St, Colburn St, and Brighton substations (17.6 miles) in Boston, MA. | 6/2022 | Notification | 2020-04-29
ES-20-T03 Rev.1 | 2020-04-09 | Rebuild of the 1355-1 Line | Transmission notification from Eversource ("ES") to rebuild the 1355-1 line (1.49 miles) from Schwab substation to Wallingford's Colony substation. Revised PPA corrects line length and impedance. | 2020-05-31 | Notification | 2020-04-29
NEP-20-T01 Rev.1 | 2020-03-13 | East Tewksbury Substation Transformers Replacement | Transmission notification from New England Power Company ("NEP") to replace existing 115/13.8kV 24/32/40 MVA transformers T1 and T2 with 115/13.8kV 33/44/55 MVA transformers. Revised PPA corrects the seciondary voltages to 13.2 kV. | 2/2022 | Notification | 2020-04-29
NEP-20-GNF14 | 2020-04-01 | Independence Main Street Bolton Solar Project | Generator notification from New England Power Company ("NEP") on behalf of Independence Solar for the installation of a 1.56 MW solar PV generator in Bolton, MA interconnecting to the 13.8kV 216W6 Feeder out of the Fitch Road Substation. | 2021-10-01 | Notification Withdrawn | 4/28/2020 5/18/2021
NEP-20-GNF23 | 2020-04-01 | USI Depot Street Bellingham Solar Project | Generator notification from New England Power Company ("NEP") on behalf of USI 150 Depot, LLC for the installation of a 1.652 MW solar PV generator in Bellingham, MA interconnecting to the 13.8kV 335W1 Feeder out of Depot Street Substation. | 2020-09-02 | Notification Withdrawn | 4/28/2020 8/18/2020
NEP-20-GNF24 | 2020-04-01 | NextSun Energy Fairlee Lane Solar and Battery Project | Generator notification from New England Power Company ("NEP") on behalf of NextSun Energy for the installation of a 4.0 MW solar PV generator and 4.5 MW/2.7 MWh batteries in Norton, MA interconnecting to the 13.8kV 92W79 Feeder out of the Easton Substation. | 2020-07-31 | Notification | 2020-04-28
NEP-20-GNF25 | 2020-04-01 | TJA Clean Energy Auburn Street Bridgewater Solar Project | Generator notification from New England Power Company ("NEP") on behalf of TJA Clean Energy, LLC for the installation of a 4.99 MW solar PV generator in Bridgewater, MA interconnecting to the 13.8kV 912W55 Feeder out of Mill Street Substation. | 2020-07-15 | Notification Withdrawn | 4/28/2020 615/2021
NEP-20-GNF26 | 2020-04-01 | Southern Sky Renewable Energy Cedar Street Solar and Battery Project | Generator notification from New England Power Company ("NEP") on behalf of Southern Sky Renewable Energy Rhode Island, LLC for the installation of a 3.469 MW solar PV generator and 0.56MW/ 1.02MWh batteries in Attleboro, MA interconnecting to the 23kV 2274 Feeder out of West Street Substation. | 2020-04-24 | Notification | 2020-04-28
NEP-20-GNF27 | 2020-04-01 | TJA Clean Energy Brook Street Solar and Battery Project | Generator notification from New England Power Company ("NEP") on behalf of TJA Clean Energy, LLC for the installation of a 2.97 MW solar PV generator and 1.75 MW/3.83 MWh batteries in Dighton, MA interconnecting to the 13.8kV 19W74 Feeder out of Dighton Substation. | 2020-07-31 | Notification | 2020-04-28
NEP-20-GNF28 | 2020-04-01 | Kearsarge Solar Brook Street Solar and Battery Project | Generator notification from New England Power Company ("NEP") on behalf of Kearsarge Solar, LLC for the installation of a 4.99 MW solar PV generator and 2.25 MW/9 MWh batteries in Bellingham, MA interconnecting to the 13.8kV 335W1 Feeder to Depot Street Substation. | 2021-04-10 | Notification | 2020-04-28
NEP-20-GNF29 | 2020-04-01 | Blue Wave Tremont Street Solar Project | Generator notification from New England Power Company ("NEP") on behalf of Bluewave Solar for the installation of a 2.40 MW solar PV generator in North Dighton, MA interconnecting to the 13.8 kV 19W74 Feeder Dighton Substation. | 2021-07-19 | Notification | 4/28/20230
NEP-20-GNF30 | 2020-04-01 | Gramercy Propoety Group Marley Street Solar and Battery Project | Generator notification from New England Power Company ("NEP") on behalf of Gramercy Property Group for the installation of a 2.40 MW solar PV generator and 1.0 MW/2.345 MWh batteries in West Bridgewater, MA interconnecting to the 13.8kV 98W44 Feeder out of Belmont Substation. | 2020-04-30 | Notification | 2020-04-28
NEP-20-GNF31 | 2020-04-01 | Pacifico Energy Richardson Avenue Solar and Battery Project | Generator notification from New England Power Company ("NEP") on behalf of Pacifico Energy for the installation of a 4.50 MW solar PV generator and 7MW/35MWh batteries in Attleboro, MA interconnecting to the 13.2kV 8L3 Feeder out of the Charley Pond Substation. | 2020-12-02 | Notification | 2020-04-28
NEP-20-GNF32 | 2020-04-01 | Atlantic Design Green Street Solar Project | Generator notification from New England Power Company ("NEP") on behalf of Atlantic Design for the installation of a 1.5 MW solar PV generator in Wrentham, MA interconnecting to the 13.8kV 3422W1 Feeder out of the South Wrentham Substation. | 2021-03-15 | Notification Withdrawn | 4/28/2020 4/13/2021
NEP-20-GNF33 | 2020-04-01 | Nexamp Pond Street Solar and Battery Project | Generator notification from New England Power Company ("NEP") on behalf of Nexamp Solar, LLC for the installation of a 4.45 MW solar PV generator and 1.0 MW/2.0 MWh batteries in Rehobeth, MA interconnecting to the 13.2kV 7L4 Feeder out of the Mink Street Substation. | 2021-08-30 | Notification | 2020-04-28
NEP-20-GNF39 | 2020-04-06 | Green Development, LLC Old Smithfield Road Solar Project | Generator notification from New England Power Company ("NEP") on behalf of Green Development, LLC for the installation of a 2.0 MW solar PV generator in North Smithfield, Rhode Island interconnecting to the 13.8kV 26W3 Feeder out of Woonsocket Substation. | 2021-06-04 | Notification | 2020-04-28
NEP-20-GNF10 Rev.1 | 2020-04-01 | Clean Energy Collective Hewins Street Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Clean Energy Collective for the installation of a 2.125 MW solar PV generator and 3 MW/6 MWh batteries in Sheffield, MA interconnecting to the 13.8kV 1108W2 Feeder out of Sheffield Substation. Revision is to add battery storage. | 2020-11-02 | Notification | 2020-04-28
ES-20-G17 | 2020-04-07 | IGS Solar 10 Cranberry Road Kingston Solar Project | Generator notification from Eversource Energy ("ES") on behalf of IGS Solar, LLC for the installation of a 1.8 MW solar PV generator in Kingston, Massachusetts interconnecting to the Eversource Kingston Substation #735 through 23kV Feeder #3-17-17. | 2020-05-31 | Notification | 2020-04-28
ES-20-G23 | 2020-04-07 | Pinegates North Stonington Solar Project | Generator notification from Eversource Energy ("ES") on behalf Pinegates for the installation of a 2.0 MW solar PV generator in North Stonington, Connecticut interconnecting to the Shunock 115kV Substation through Eversource 32P1 13.8kV distribution Feeder. | 2021-01-05 | Notification Withdrawn | 4/28/2020 6/18/2024
ES-20-G49 | 2020-04-07 | Lodestar 81 East Main Street Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Lodestar Energy, LLC for the installation of a 2.0 MW solar PV generator in North Canaan, Connecticut interconnecting to the North Canaan Substation through Eversource 5L04 13.2kV distribution Feeder. | 2020-08-01 | Notification | 2020-04-28
ES-20-G69 | 2020-04-06 | Greenskies Renewable Energy Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Greenskies Renewable Energy for the installation of a 4.99 MW solar PV generator in East Windsor, Connecticut interconnecting to the A2 bus in the Barbour Hill Substation. | 2022-06-30 | Notification | 2020-04-28
ES-20-G123 | 2020-04-07 | Lodestar Platt Hill Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Lodestar Energy, LLC for the installation of a 2.003 MW solar PV generator in Winsted, Connecticut interconnecting to the Burrville Substation through Eversource 2951 23kV distribution Feeder. | 2020-10-01 | Notification | 2020-04-28
ES-20-G125 | 2020-04-07 | Green Street Power Mystic Road Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Green Street Power Partners for the installation of a 4.999 MW solar PV generator in North Stonington, Connecticut interconnecting to Shunock Substation through Eversource 32P4 13.8kV distribution Feeder. | 2020-12-31 | Notification Withdrawn | 4/28/2020 7/13/2021
ES-20-G127 | 2020-04-06 | Verogy Hill Street Bristol Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Verogy, LLC for the installation of a 3.25 MW solar PV generator in Bristol, Connecticut interconnecting to Chippen Hill Substation through Eversource 15U2 13.8kV distribution Feeder. | 2020-12-20 | Notification | 2020-04-28
ES-20-G128 | 2020-04-06 | Verogy Prospect Street Burlington Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Verogy, LLC for the installation of a 3.5 MW solar PV generator in Burlington, Connecticut interconnecting to the Canton Substation through Eversource 5R7 23kV distribution Feeder. | 2020-12-31 | Notification | 2020-04-28
ES-20-G129 | 2020-04-06 | Verogy East Pearl Road Torrington Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Verogy, LLC for the installation of a 1.975 MW solar PV generator in Torrington, Connecticut interconnecting to the 23 44J3 Feeder fed by the 27.6kV 2453 Feeder from the Campville 14R Substation. | 2020-12-20 | Notification | 2020-04-28
ES-20-G131 | 2020-04-08 | Green Street Power Pine Street Columbia Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Green Street Power Partners for the installation of a 4.999 MW solar PV generator in Columbia, Connecticut interconnecting to the Columbia 20Y Substation through the 13.8kV 20Y distribution Feeder. | 2021-12-31 | Notification Withdrawn | 4/28/2020 7/21/2020
ES-20-G132 | 2020-04-08 | Citrine Power Meriden Road Middlefield Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Citrine Power, LLC for the installation of a 2.0 MW solar PV generator in Middlefield, Connecticut connecting to the Westside 7A Substation through Eversource 13.2kV 7A77 Feeder. | 2019-12-27 | Notification | 2020-04-28
ES-19-G30 Rev.1 | 2020-03-09 | TJA Solar Partridge Road Solar and Battery Project | Generator notification from Eversource Energy ("ES") on behalf of TJA Solar for the installation of a 4.99 MW solar PV generator and 3.0 MW/6.576 MWh batteries in Lanesborough, Massachusetts interconnecting to the 15E2 Feeder through the Partridge 15E Substation. Revision adds battery storage without changing the generation output. | 2020-09-01 | Notification | 2020-04-28
ES-19-G31 Rev.1 | 2020-03-09 | TJA Solar North Main Street Solar and Battery Project | Generator notification from Eversource Energy ("ES") on behalf of TJA Solar for the installation of a 3.96 MW solar PV generator with 2.5 MW/5.48 MWh batteries in Lanesborough, Massachusetts interconnecting to the 15E1 Feeder through the Partridge 15E Substation. Revision adds battery storage without changing the generation output. | 2020-09-01 | Notification | 2020-04-28
ES-20-G05 | 2020-03-07 | SunRaise Development Mayflower Road Solar and Battery Project | Generator notification from Eversource Energy ("ES") on behalf of SunRaise Development, LLC for the installation of a 4.998 MW solar PV generator with 4 MW/8 MWh batteries and total project output limited to 4.998MW in Plympton, MA interconnecting to the Brook Street Substation #727 through the 23kV Feeder #3-51-901. | 2020-10-01 | Notification | 2020-04-28
ES-20-G18 Rev.1 | 2020-03-18 | DG Massachusetts Solar George Millard Road Solar and Battery Project | Generator notification from Eversource Energy ("ES") on behalf of DG Massachusetts Solar, LLC for the installation of a 3.75 MW solar PV generator with 3 MW/12 MWh batteries in Blandford, MA interconnecting to the Blandford 19J 115-kV Substation through the 19J2 23kV Feeder. | 2020-12-11 | Notification | 2020-04-28
ES-20-G65 Rev.1 | 2020-03-18 | CEC Development Cypress Point Solar and Battery Project | Generator notification from Eversource Energy ("ES") on behalf of CEC Developmet, LLC for the installation of a 4.875 MW solar PV generator and 9.75 MW/21.37 MWh batteries and total output of 4.875MW in Harwich, MA interconnecting to the 22.8 kV Circuit 4-95A-599 out of the Harwich 968 Station. | 2020-11-30 | Notification Withdrawn | 4/28/2020 7/16/2024
ES-20-G19 Rev.1 | 2020-03-18 | PVH Energy Storage Onota Street Pittsfield Solar and Battery Project | Generator notification from Eversource Energy ("ES") on behalf PVH Energy. Revision to the approved application to remove the batteries and to reduce the generator output from 2.108 MW to 1.38 MW. | 2020-08-01 | Notification | 2020-04-28
CMP-20-G07 | 2020-03-05 | Dynamic Energy Solutions Skowhegan North Side Solar Project | Generator notification Central Maine Power ("CMP") on behalf of Dynamic Energy Solutions, LLC for the installation of a 4.999 MW solar PV generator in Madison, Maine interconnecting to the 12.47kV 853D1 distribution circuit from the CMP Skowhegan North Side Substation. | 2020-12-31 | Notification | 2020-04-28
CMP-20-G08 | 2020-03-09 | Dirt Solar Skowhegan East Ridge Road Solar Project | Generator notification Central Maine Power ("CMP") on behalf of Dirt Solar, LLC for the installation of a 2.625 MW solar PV generator in Skowhegan, Maine interconnecting to the 12.47kV 866 D1 distribution circuit from the CMP Weston Hydro Solon MFG Substation. | 2020-08-01 | Notification | 2020-04-28
CMP-20-G09 | 2020-03-17 | Walden Solar Gravel Pit Solar Project | Generator notification Central Maine Power ("CMP") on behalf of Walden Solar Maine II, LLC for the installation of a 4.752 MW solar PV generator in Wells, Maine interconnecting to the 12.47kV 661D2 circuit from the CMP Pratt & Whitney Substation. | 2020-12-30 | Notification | 2020-04-28
CMP-20-G10 | 2020-03-17 | Pine Gates Renewables Solar Project | Generator notification Central Maine Power ("CMP") on behalf of Pine Gates Renewables, LLC for the installation of a 2.125 MW solar PV generator in Rockport, Maine interconnecting to the 12.47kV 270D1 distribution circuit from the CMP Meadow Road Substation. | 2021-04-01 | Notification | 2020-04-28
CMP-20-G11 | 2020-03-18 | ECA Solar West Bethel Solar Project | Generator notification Central Maine Power ("CMP") on behalf of ECA Maine BET, LLC for the installation of 4.8 MW solar PV generator in Bethel, Maine interconnecting to the 12.47kV 403D1 distribution circuit from the CMP Bethel Substation. | 2020-12-15 | Notification | 2020-04-28
CMP-20-G12 | 2020-03-19 | SRE Solar Waldoboro Road Washington Solar Project | Generator notification Central Maine Power ("CMP") on behalf of SRE Solar Origination 1, LLC for the installation of a 2.0 MW solar PV generator in Washington, Maine interconnecting to the 12.47kV 245D2 distribution circuit from the CMP Stickney’s Corner Substation. | 2021-03-01 | Notification | 2020-04-28
CMP-20-G13 | 2020-03-27 | BD Solar Standish Solar Project | Generator notification Central Maine Power ("CMP") on behalf of BD Solar Standish, LLC for the installation of a 4.99 MW solar PV generator in Standish, Maine interconnecting to the 12.47kV 660D1 distribution circuit from the CMP Shaw Mills Road Substation. | 2021-10-01 | Notification | 2020-04-28
CMP-20-G14 | 2020-03-27 | ISM Solar Shaker Solar Project | Generator notification Central Maine Power ("CMP") on behalf of ISM Solar Development, LLC for the installation of a 4.915 MW solar PV generator in Gray, Maine interconnecting to the 12.47kV 41621 distribution circuit from the CMP Gray Substation. | 2020-12-31 | Notification | 2020-04-28
CMP-20-G15 | 2020-03-07 | BWC Blue Wave South Street | Generator notification Central Maine Power ("CMP") on behalf of BWC Blue Wave MA, LLC for the installation og a 4.99 MW solar PV generator with 4.2 MW/8.4 MWh batteries in Dayton Maine interconnecting to the 12.47kV 605D1 distribution circuit from the CMP Biddeford Pumping Substation. | 2020-12-30 | Notification | 2020-04-28
CMP-20-G16 | 2020-03-27 | BWC Blue Wave New County Road Louden Solar and Battery Project | Generator notification Central Maine Power ("CMP") on behalf of BWC Blue Wave Solar MA, LLC for the installation of a 4.8 MW solar PV generator in Saco, Maine interconnecting to the 12.47kV 633D1 distribution circuit from the CMP Louden Substation. | 2020-12-30 | Notification | 2020-04-28
CMP-20-G17 | 2020-04-07 | Shaw Brothers Construction Bar Mills Solar Project | Generator notification Central Maine Power ("CMP") on behalf of Shaw Brothers Construction Inc. for the installation of a 2.4 MW solar PV generator in Buxton, Maine interconnecting to the 12.47kV 678D2 distribution circuit from the CMP Bar Mills Substation. | 2020-08-01 | Notification | 2020-04-28
CMP-20-G18 | 2020-04-07 | Borrego Solar Middlesex Road Solar and Battery Project | Generator notification Central Maine Power ("CMP") on behalf of 510PV Development, LLC for the installation of a 4.99 MW solar PV generator with 4.99 MW/25 MWh batteries in Topsham Maine interconnecting to the 12.47kV 250D2 distribution circuit from the CMP Topsham Substation. | 2021-06-07 | Notification | 2020-04-28
CMP-20-G19 | 2020-04-07 | Borrego Solar Turnpike Road Solar and Battery Project | Generator notification Central Maine Power ("CMP") on behalf of 510PV Development, LLC for the installation of a 4.99 MW solar PV generator with 4.99 MW/25 MWh batteries in Searsport Maine interconnecting to the 12.47kV 850D1 distribution circuit from the CMP Searsport Substation. | 2021-07-20 | Notification | 2020-04-28
CMP-20-G20 | 2020-04-07 | Riverside Solar Project | Generator notification Central Maine Power ("CMP") on behalf of Riverside Solar, LLC for the installation of a 4.9875 MW solar PV generator in Augusta, Maine interconnecting to the 12.47kV 200D3 distribution circuit from the CMP Augusta KS Substation. | 2021-01-31 | Notification | 2020-04-28
CMP-20-G21 | 2020-04-07 | CGA Solar South Sanford Solar Project | Generator notification Central Maine Power ("CMP") on behalf of CGA Solar for the installation of a 4.95 MW solar PV generator in Sanford Maine interconnecting to the 12.47kV distribution circuit from the CMP Sanford Substation. | 2020-12-31 | Notification | 2020-04-28
CMP-20-G22 | 2020-04-08 | Borrego Solar Center Road Solar and Battery | Generator notification Central Maine Power ("CMP") on behalf of 510PV Development, LLC for the installation of a 4.99 MW solar PV generator with 4.99 MW/20 MWh batteries in Winthrop Maine and total output limited to 4.99MWinterconnecting to the Winthrop Substation over Circuit 256D. | 2021-06-15 | Notification | 2020-04-28
CMP-20-G23 | 2020-04-08 | Borrego Solar Front Ridge Road Solar and Battery Project | Generator notification Central Maine Power ("CMP") on behalf of 510PV Development, LLC for the installation of a 4.99 MW solar PV generator with 4.99 MW/26 MWh batteries in Orland Maine interconnecting to the 12.47kV distribution Circuit 802D2 out of CMP Bucksport Substation. | 2021-07-19 | Notification | 2020-04-28
CMP-20-G24 | 2020-04-08 | Walden Solar Fryeburg Tap Solar Project | Generator notification Central Maine Power ("CMP") on behalf of Walden Solar Maine IV, LLC for the installation of a 4.875 MW solar PV generator in Fryeburg, Maine interconnecting to the Fryeburg Tap Substation through 12.47kV Circuit 45D2. | 2020-12-31 | Notification | 2020-04-28
NEM-20-G01 | 2020-03-03 | Chinook Solar | Generator application from NextEra Energy Resources on behalf of Chinook Solar, LLC for the installation of a 30 MW solar PV generator in Fitzwilliam, NH. | 2021-11-01 | Approved Withdrawn | 4/17/2020 10/31/2021
NEM-20-T01 | 2020-03-03 | Chinook Solar | Transmission application from NextEra Energy Resources on behalf of Chinook Solar, LLC for the installation of a 21/28/35 MVA step up transformer. | 2021-10-01 | Approved Withdrawn | 4/17/2020 10/31/2021
NEP-20-T05 | 2020-03-03 | Chinook Solar | Transmission application from New England Power Company ("NEP") to install a new three-breaker 115 kV ring bus substation, to be named later, at the proposed Chinook Solar PV sire in Fitzwilliam, NH. | 2021-11-01 | Approved Withdrawn | 4/17/2020 10/31/2021
NEM-20-G02 | 2020-03-03 | Tilton Heights Solar | Generator application from NextEra Energy Resources on behalf of Tilton Heights Energy Center, LLC for the installation of a 20 MW solar PV generator in Tilton, NH interconnecting to a tap on Eversource’s 34.5kV Line #3216 supplied by the Webster/Daniel Substation. | 2023-12-31 | Approved Withdrawn | 4/17/2020 11/27/2024
NEM-20-G03 | 2020-03-03 | Black Hill Point Energy Center | Generator application from NextEra Energy Resources on behalf of Chinook Solar, LLC for the installation of a 19.9 MW solar PV generator in Canterbury, CT interconnecting to the Eversource Killingly - Tunnel 115 kV line L-1607. | 2023-12-31 | Approved Withdrawn | 4/17/2020 11/27/2024
NEM-20-T03 | 2020-03-03 | Black Hill Point Energy Center | Transmission application from NextEra Energy Resources on behalf of Chinook Solar, LLC for the installation of a 18/24 MVA step up transformer. | 2023-12-31 | Approved Withdrawn | 4/17/2020 11/27/2024
ES-20-T19 | 2020-03-05 | Black Hill Point Energy Center | Transmission application from Eversource Energy ("ES") to install a 115 kV breaker to the existing three-breaker ring bus at Canterbury 67F. | 2023-12-01 | Approved Withdrawn | 4/17/2020 11/27/2024
NEP-20-G01 | 2020-03-05 | Tiverton Brayton II | Generator application from New England Power Company ("NEP") to install a 5.9 MW solar PV generator in Tiverton, RI interconnecting to the 33F4 12.47 kV feeder into the Tiverton 2 substation. | 2020-09-14 | Approved | 2020-04-17
NEP-20-G02 | 2020-03-05 | Tiverton Brayton III | Generator application from New England Power Company ("NEP") to install a 5.9 MW solar PV generator in Tiverton, RI interconnecting to the 33F4 12.47 kV feeder into the Tiverton 2 substation. | 2020-09-14 | Approved | 2020-04-17
ES-20-G82 | 2020-03-10 | 510 Project Development Mechanic Street Hopkinton Solar | Generator notification from Eversource Energy ("ES") on behalf of 510 Project Development for the installation of a 4.0 MW solar PV generator and 2.31 MW/4.73 MWh batteries in Hopkinton, MA interconnecting to Circuit 126-H4 out of the Hopkinton 126 Station. | 2021-06-20 | Notification Withdrawn | 4/16/2020 4/27/2022
ES-20-G75 | 2020-02-24 | Sandwich Public Schools Quaker Meeting Road Sandwich | Generator notification from Eversource Energy ("ES") on behalf of Sandwich Public Schools for the installation of a 2.563 MW solar PV generator and 0.892 MW/1.784 MWh batteries total output limited to 2.563MW in Sandwich, MA interconnecting to Circuit 4-81B-81B out of Sandwich 916 Station. | 2020-03-01 | Notification Withdrawn | 4/16/2020 12/17/2024
ES-20-G86 | 2020-02-18 | ASD Shutesbury Road Amherst Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of ASD Shutesbury, MA for the installation of a 4.4 MW solar PV generator and 6 MW/36 MWh batteries in Amherst, MA interconnecting to the 17K7 feeder fed from Amherst 17K Substation. | 2020-11-30 | Notification | 2020-04-16
ES-20-G97 | 2020-02-19 | Montague Road Amherst Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Montague Road Solar, LLC for the installation of a 3 MW solar PV generator and 2.0 MW/4.0 MWh batteries total output limited to 3.0MW in Amherst, MA interconnecting to the 18G7 feeder out of Podick 18G Substation. | 2020-11-30 | Notification | 2020-04-16
NEP-20-GNF21 | 2020-03-02 | Bloom Energy Alexander Road Billerica Gas Project | Generator notification from New England Power Company ("NEP") on behalf of Bloom Energy for the installation of a 2.5 MW gas-fired facility in Billerica, MA interconnecting to New England Power’s 92L4 feeder out of the Pinehurst Substation. | 2022-02-01 | Notification | 2020-04-10
NEP-20-GNF20 | 2020-03-02 | SunPower Corporation Boylston Street Worcester Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of SunPower Corp. for the installation of a 1.887 MW solar PV generator and batteries in Worcester, MA interconnecting to Greendale Substation, 24W5 13.8kV. | 2020-09-24 | Notification Withdrawn | 4/10/2020 5/19/2020
NEP-20-GNF18 | 2020-03-02 | Direct Energy Higginson Avenue Lincoln Solar | Generator notification from New England Power Company ("NEP") on behalf of Direct Energy Solar for the installation of 2.9 MW solar PV generator in Lincoln, Rhode Island interconnecting to the 102W51 13.8kV Valley Substation. | 2021-01-29 | Notification | 2020-04-10
NEP-19-G30-004 Rev.1 | 2020-03-02 | Syncarpha Mulberry Street Leicester Solar and Battery | Generator notification from New England Power Company ("NEP") for the installation of a 2.952 MW solar PV generator and 2.0 MW/4.0 MWh batteries in Leicester, MA interconnecting to the 21W1 13.8kV feeder Leicester Substation. Revision to the previously approved PV-only project approved at the November 2019 RC Meeting is to add the batteries. | 2021-01-12 | Notification Withdrawn | 4/10/2020 10/20/2020
CMP-20-G06 | 2020-03-03 | Rumford ESS LLC IP Industrial Park Drive Rumford BESS Project | Generator notification from Central Maine Power ("CMP") on behalf of Rumford ESS for the installation of a 4.99 MW energy storage only project in Rumford, ME interconnecting to the 466D1 34.5kV distribution circuit from the CMP Rumford IP Substation. | 2021-03-01 | Notification | 2020-04-10
CMP-20-G05 | 2020-03-03 | HEP Energy Checkline Drive Parkman Solar | Generator notification from Central Maine Power ("CMP") on behalf of HEP Energy USA Project Development, LLC for the installation of a 4.875 solar PV generator in Parkman, ME interconnecting to the 821D1 12.47kV distribution circuit from the CMP Guilford Substation. | 2022-01-01 | Notification | 2020-04-10
ES-20-G121 | 2020-03-02 | CoreSite Somerville Inner Belt Road Somerville Project | Generator notification from Eversource Energy ("ES") on behalf of 2017 Fuel Operating Company I, LLC for the installation of a 4.2 MW (2.4 MW, 1.2 MW, and 0.6 MW) fuel cell in Somerville, MA interconnecting behind customer station #387 and #98 supplied by a 13.8kV DSS Line 30=179XYH, 387-148H and 98-158 off Mystic Substation #250. | 2020-06-15 | Notification | 2020-04-10
ES-20-G110 | 2020-02-26 | Sunspire Ice House Canopy Medfield Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Sunspire Solar, LLC for the instalaltion of a 0.720 MW solar PV generator and 0.56 MW/2.088 MWh batteries with a total output of 1.28 MW in Medfield, MA interconnecting to 13.8kV 3PH Feeder #456-H3 into Dover 456 Substation. | 2020-12-18 | Notification Withdrawn | 4/10/2020 6/18/2024
ES-20-G111 | 2020-02-26 | Sunspire Ice House Roof Medfield Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Sunspire Solar, LLC for the installation of a 0.767 MW solar PV generator and 0.56 MW/2.088 MWh batteries with a total output of 1.327 MW in Medfield, MA interconnecting to 13.8kV 3PH Feeder #456-H3 into Dover 456 Substation. | 2020-10-02 | Notification | 2020-04-10
ES-20-G112 | 2020-02-26 | Marshall Street Holliston Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Marshall Street Solar, LLC for the installation of a 5.0 MW solar PV generator and 4.0 MW/8.48 MWh batteries with total output limited to 4.999 MW in Holliston, MA interconnecting to the13.8 kV 3PH Feeder #130-H1 into Holliston #130 Substation. | 2021-02-01 | Notification | 2020-04-10
ES-20-G113 | 2020-02-27 | CVEC Parcel E Workshop Road South Yarmouth Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Yarmouth DPW for the installation of a 1.0 MW solar generator and 0.56 MW/1.115 MWh batteries with a total output of 1.56 MW in South Yarmouth, MA interconnecting to the 24kV Circuit 4-92B-560 into Hyannis #961 Substation. | 2020-08-01 | Notification | 2020-04-10
ES-20-G114 | 2020-02-27 | Forefront Power St. Pius Wood Road South Yarmouth Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Forefront Power, LLC for the installation of a 0.756 MW solar PV generator and 0.50 MW/1.096 MWh batteries with a total output of 1.256 MW in South Yarmouth, MA interconnecting to the 24kV Circuit 4-92B-560 into Hyannis #961 Substation. | 2020-08-28 | Notification | 2020-04-10
ES-20-G115 | 2020-03-02 | Hanscom Military Northbridge Road Hanscom Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Hanscom Storage Provider, LLC for the installation of a 1.645 MW solar PV generator and 1.5 MW/4.50 MWh batteries with a total output of 3.139 MW in Hanscom AFB, MA interconnecting to the 13.8kV Circuit 319-1378 into Lexington #320 Substation. | 2020-11-30 | Notification | 2020-04-10
ES-20-G116 | 2020-03-02 | Lincoln Public Schools Ballfield Road Lincoln Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Lincoln Public Schools for the installation of a 1.331 MW solar PV generation and 0.5 MW/1.0 MWh batteries with total output of 1.831 MW in Lincoln, MA interconnecting to 13.8kV Circuit 320-H3 into Lexington #320 Substation. | 2020-10-25 | Notification | 2020-04-10
ES-20-G118 | 2020-03-02 | CVEC Golf Lots Freemans Way Brewster Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Freemans Way Solar Project 2019, LLC for the installation of a 1.0 MW solar PV generation and 0.49 MW/0.892 MWh batteries with total output of 1.490 MW in Brewster, MA interconnecting to Orleans Station #975 Bus 2. | 2020-08-01 | Notification | 2020-04-10
ES-20-G103 | 2020-02-07 | Altus Power America Inc. Cherry Hill Road Rockfall Solar | Generator notification from Eversource Energy ("ES") on behalf of Altus Power America Inc. for the installation of a 1.5 MW solar PV generator in Rockfall, CT interconnecting to the Dooley 115kV Substation through the Eversource Energy 30K11 13.2kV distribution feeder. | 2021-12-31 | Notification | 2020-04-10
ES-20-G104 | 2020-02-07 | C-TEC Solar Berlin Landfill Deming Street Berlin Solar | Generator notification from Eversource Energy ("ES") on behalf of C-TEC for the installation of a 1.3 MW solar PV generator in Berlin, CT interconnecting to the Berlin 115 kV substation through the Eversource Energy 6A5 13.8 kV distribution feeder. | 2022-06-30 | Notification | 2020-04-10
ES-20-G106 | 2020-02-26 | Brightfields Development Dan Road Canton Solar | Generator notification from Eversource Energy ("ES") on behalf of Brightfields Development, LLC for the installation of a 1.1 MW solar PV generator interconnecting to 13.8 kV feeder #470-H8 into Canton 470 Substation. | 2020-08-28 | Notification | 2020-04-10
ES-20-G101 | 2020-02-18 | TJA South Main Street Lanesborough Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of TJA Clean Energy for the installation of a 4.99 MW solar PV generator and 3.0MW/6.58MWh batteries in Lanesborough, MA interconnecting to the 15E1 feeder out of Partridge 15E Substation. | 2020-08-07 | Notification | 2020-04-10
ES-20-G99 | 2020-02-18 | Roy Morrison and Associates Organic Growers II Greenfield Road Colrain Solar | Generator notification from Eversource Energy ("ES") on behalf of Roy Morrison and Associates for the installation of a 1.98 MW solar PV generator in Colrain, MA interconnecting to the 29R2 feeder out of Shelburne 29R Substation. | 8/2020 | Notification Withdrawn | 4/10/2020 8/17/2022
ES-20-G98 | 2020-02-18 | Kearsarge Greenfield Road Colrain Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Kearsarge Solar, LLC for the installation of a 3.3 MW solar PV generator and 2.5 MW/10 MWh batteries in Colrain, MA interconnecting to the 29R2 feeder out of Shelburne 29R Substation. | 8/2020 | Notification Withdrawn | 4/10/2020 11/18/2020
ES-20-G100 | 2020-02-18 | CES Tuckahoe Turf Farm South West Main Street Agawam Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Agawam Tuckahoe Solar, LLC for the installation of a 4.975 MW solar PV generator and 2.3 MW/4.64 MWh batteries in Agawam, MA interconnecting to the 30A1 feeder out of Silver 30A Substation. | 6/2020 | Notification | 2020-04-10
ES-20-G94 | 2020-02-18 | Pacifico Energy Bernardston Road Greenfield Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Pacifico Energy North America Inc. for the installation of a 4.5 MW solar PV generator and 3.0MW/6.5MWh batteries in Greenfield, MA interconnecting to the 21C feeder out of Montague 21C Substation. | 8/2020 | Notification | 2020-04-10
ES-20-G93 | 2020-02-18 | CPV Red Rock Solar LLC Lyon Street - Ludlow Solar | Generator notification from Eversource Energy ("ES") on behalf of CPV Red Rock Solar, LLC for the installation of a 4.4 MW solar PV generator in Ludlow, MA interconnecting to the 19S3 feeder out of Ludlow 19S Substation. | 8/2020 | Notification Withdrawn | 4/10/2020 11/18/2020
ES-20-G95 | 2020-02-18 | Charterhouse Development Corp. Barker Road Pittsfield Solar | Generator notification from Eversource Energy ("ES") on behalf of Charterhouse Development Corp. for the installation of 2.574 MW solar PV generator in Pittsfield, MA interconnecting to 30B2 feeder out of Oswald 30B Substation. | 8/2020 | Notification Withdrawn | 4/10/2020 3/16/2021
ES-20-G90 | 2020-02-18 | BWC Pine Meadow Brook Pine Meadow Road Northfield Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Pine Meadow Brook, LLC for the installation of a 4.98 MW solar PV generator and 3 MW/6 MWh batteries in Northfield, MA interconnecting to the 21B8 feeder into French King 21B Substation. | 8/2020 | Notification | 2020-04-10
ES-20-G92 | 2020-02-18 | Nexamp East Street Ludlow Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Nexamp Solar, LLC for the installation of a 2.8 MW solar PV generator and 1.5 MW/3 MWh batteries in Ludlow, MA interconnecting to the 19S1 feeder into Ludlow 19S Substation. | 8/2020 | Notification | 2020-04-10
ES-20-G88 | 2020-02-18 | Roy Morrison and Associates Coates Road Leyden Solar | Generator notification from Eversource Energy ("ES") on behalf of Roy Morrison and Associates for the installation of a 4.98 MW solar PV generator in Leyden, MA interconnecting to the 22B7 feeder out of the Cumberland 22B Substation. | 8/2020 | Notification Withdrawn | 4/10/2020 8/17/2022
ES-20-G89 | 2020-02-18 | Northfield Mt. Hermon Schoole Lamplighter Way Gill Solar | Generator notification from Eversource Energy ("ES") on behalf of TES NMH1Solar23, LLC for the installation of a 2.31 MW solar PV generator in Gill, MA interconnecting to a new express feeder into French King 21B Substation. | 8/2020 | Notification Withdrawn | 4/10/2020 11/18/2020
ES-20-G83 | 2020-02-21 | Frankland Road Solar Farm Hopkinton Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Frankland Road Solar, LLC for the installation of 4.475 MW solar PV generator and 3.51 MW/9 MWh batteries with total output limited to 4.475 MW in Hopkinton, MA interconnecting to Circuit 126-H2 out of the Hopkinton 126 Substation. | 2021-04-01 | Notification Withdrawn | 4/10/2020 4/18/2023
ES-20-G84 | 2020-02-18 | Town of Amherst Belchertown Road Amherst Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Town of Amherst Solar, LLC for the installation of a 2.5 MW solar PV generator and 2.0 MW/12 MWh batteries in Amherst, MA interconnecting to the 17K2 feeder fed from the Amherst 17K Substation. | 8/2020 | Notification | 2020-04-10
ES-20-G85 | 2020-02-18 | ASD Tower Road Pelham Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of ASD Tower MA Solar, LLC for the installation of a 4.4 MW solar PV generator and 6 MW/36 MWh batteries in Pelham, MA interconnecting to the 17K2 feeder fed from Amherst 17K Substation. | 2021-01-01 | Notification | 2020-04-10
ES-20-G87 | 2020-02-18 | Treehouse Hawley Road Ashfield Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Treehouse Solar, LLC for installation of a 4.998 MW solar PV generator and 4.0 MW/12 MWh batteries in Ashfield, MA interconnecting to the 38A1 feeder out of the Ashfield 38A Substation. | 9/2020 | Notification Withdrawn | 4/10/2020 11/18/2020
ES-20-G81 | 2020-03-02 | ConEd Development Rotary Circle South Bourne Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of ConEdison Development for the installation of a 4.975 MW solar PV generator and 4.68 MW/10.13 MWh batteries with project output limited to 4.975 MW in Bourne, MA interconnecting to Circuit 4-86-402 out of Otis 915 Station. | 2020-11-01 | Notification Withdrawn | 4/10/2020 2/22/2023
ES-20-G80 | 2020-02-25 | ECA SEMA Fox LLC Washington Street Foxborough Solar | Generator notification from Eversource Energy ("ES") on behalf of ECA SEMA Fox, LLC for the installation of a 3.90 MW solar PV generator in Foxborough, MA interconnecting to Circuit 146-H3 out of the Walpole 146 Station. | 2021-01-21 | Notification Withdrawn | 4/10/2020 6/18/2024
ES-20-G77 | 2020-03-10 | CEC Development Fearing Hill Road Wareham Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of CEC Development, LLC for the installation of a 2.99 MW solar PV generator and 2.25 MW/4.93 MWh batteries in Wareham, MA interconnecting to Circuit 3-85-85 out of Tremont 713 Station. | 2020-10-30 | Notification | 2020-04-10
ES-20-G78 | 2020-03-10 | 510 Project Development Old Tuck Bug Road Rochester Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of 510 Project Development for the installation of a 3.0 MW solar PV generator and 3.0 MW/15 MWh batteries in Rochester, MA interconnecting to Circuit 3-85-85 out of Tremont 713 Station. | 2021-01-31 | Notification Withdrawn | 4/10/2020 12/17/2024
ES-20-G79 | 2020-03-10 | NextGrid Hawthorn Pond Road Norfolk Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of NextGrid Hawthorn, LLC for the installation of a 4.99 MW solar PV generator and 2.0 MW/4.0 MWh batteries in Norfolk, MA interconnecting to Circuit 146-H3 out of the Walpole 146 Substation. | 2021-05-30 | Notification | 2020-04-10
ES-20-G74 | 2020-02-21 | CGN LLC Camp Good News Mass Route 130 Forestdale Solar | Generator notification from Eversource Energy ("ES") on behalf of CGN, LLC for the installation of a 4.99 MW solar PV generator in Forestdale, MA interconnecting to Circuit 4-81B-443 out of Sandwich 916 Substation. | 2020-12-01 | Notification | 2020-04-10
ES-20-G63 | 2020-03-02 | Forefront Power Our Lady Grace Meetinghouse Road Chatham Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Forefront Power, LLC for the installation of a 2.56 MW solar PV generator and 1.0 MW/2.192 MWh batteries with total project output of 2.56MW in Chatham, MA interconnecting to Circuit 4-95A-95A out of the Harwich 968 Substation. | 2020-11-01 | Notification | 2020-04-10
ES-20-G64 | 2020-03-10 | Nextgrid Red Cedar LLC Sand Pit Middle Road Chatham Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Nextgrid Red Cedar, LLC for the installation of a 2.5 MW solar PV generator and 1.5 MW/6 MWh batteries in Chatham, MA interconnecting to Circuit 4095A-95A out of the Harwich 968 Substation. | 2020-10-01 | Notification | 2020-04-10
ES-20-G65 | 2020-03-02 | CEC Development LLC Cypress Point Harwich Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of CEC Development, LLC for the installation of a 4.875 MW solar PV generator and 9.75 MW/21.37 MWh batteries in Harwich, MA interconnecting to Circuit 4-95A-599 out of Harwich 968 Station. | 2020-11-30 | Notification | 2020-04-10
ES-20-G66 | 2020-02-24 | SCS Barnstable West Nathan-Ellis Highway Falmouth Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of SCS Nathan Ellis 011282 Falmouth West, LLC for the installation of a 4.0 MW solar PV generator and 2.25 MW/4.94 MWh batteries in Falmouth, MA interconnecting to Circuit 4-77A-450 out of the Hatchville 936 Station. | 2021-06-02 | Notification | 2020-04-10
ES-20-G67 | 2020-02-24 | SCS Barnstable East Nathan-Ellis Highway Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of SCS Nathan Ellis 011282 Falmouth West, LLC for the installation of a 0.999 MW solar PV generator and 0.75 MW/1.644 MWh batteries in Falmouth interconnecting to Circuit 4-77A-450 out of the Hatchville 936 Station. | 2021-06-02 | Notification | 2020-04-10
ES-20-G68 | 2020-03-02 | ASD Sandwich Road Falmouth Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of ASD Sandwich Solar, LLC for the installation of a 4.89 MW solar PV generator and 4.0 MW/12.0 MWh batteries in Falmouth, MA interconnecting to Circuit 4-98B-448 out of the Hatchville 936 Station. | 2020-12-31 | Notification Withdrawn | 4/10/2020 6/18/2024
ES-20-G70 | 2020-03-10 | TJA Clean Energy Wakeby Road Barnstable Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of TJA Clean Energy for the installation of a 4.99 MW solar PV generator and 3 MW/6.576 MWh batteries in Barnstable, MA interconnecting to Circuit 4-88-88 out of the Mashpee 946 Station. | 10/12021 | Notification | 2020-04-10
ES-20-G71 | 2020-02-22 | 510 Project Development Acton-Boxboro High School Charter Road Acton | Generator notification from Eversource Energy ("ES") on behalf of 510 Solar Project Development for the installation of a 2.1 MW/4.17 6MWh energy storage only project in Acton, MA interconnecting to Circuit 416-H4 out of the Maynard 416 Station. | 2020-09-01 | Notification | 2020-04-10
ES-20-G72 | 2020-03-10 | NextGrid Jamaica Caper Brewster Sand Pit Freemans Way Brewster Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of NextGrid Jamaica Caper, LLC for the installation of 2.5 MW solar PV generator and 1.75 MW/7 MWh batteries in Brewster, MA interconnecting to Circuit 4-95B-600 out of Orleans 975 Station. | 2019-11-15 | Notification | 2020-04-10
ES-20-G73 | 2020-02-21 | Lodestar Energy Victory Drive Sandwich Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Lodestar Energy, LLC for the installation of a 2.125 MW solar PV generator and 1.0 MW/2.192 MWh batteries in Sandwich, MA interconnecting to Circuit 4-81B-443 out of the Sandwich 916 Substation. | 2020-09-01 | Notification | 2020-04-10
ES-20-G59 | 2020-02-22 | Freetown East PVI LLV Locust Street Freetown Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Freetown East PVI LLC for the installation of a 4.498 MW solar PV generator and 2.50 MW/5.48 MWh batteries in Freetown, MA interconnecting to Circuit 2-605-605 out of the Bell Rock 661 Substation. | 2020-12-01 | Notification | 2020-04-10
ES-20-G60 | 2020-03-10 | EIP Will Drive Canton Solar | Generator notification from Eversource Energy ("ES") on behalf of EIP Will Drive Solar, LLC for the installation of a 3.24 MW solar PV generator in Canton, MA interconnecting to Circuit 269-1321H into Station 470 Canton. | 2020-12-04 | Notification | 2020-04-10
ES-20-G61 | 2020-03-02 | 510 Project Development Blacksmith Shop Road Falmouth Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of 510 PV Project Development for the installation of a 3.3 MW solar PV generator and 3.3 MW/4.73 MWh batteries in Falmouth, MA interconnecting to Circuit 4-98A out of Falmouth 933 Station. | 2021-06-08 | Notification | 2020-04-10
ES-20-G62 | 2020-03-10 | 510 Project Development Depot Road Harwich Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of 510 Project Development for the installation of a 3.75 MW solar PV generator and 2.31 MW/4.62 MWh batteries in Harwich, MA with total project output limited to 3.75 MW interconnecting to Circuit 4-95A-95A out of Harwich 968 Station. | 2021-06-20 | Notification Withdrawn | 4/10/2020 4/22/2020
ES-20-G55 | 2020-01-31 | Nexamp Dalton Bridle Road Dalton Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Nexamp Solar LLC for the installation of a 4.4 MW solar PV generator and 2.0 MW/4.0 MWh batteries in Dalton, MA interconnecting to the 18C1 feeder through the Berkshire 18C Substation. | 6/2020 | Notification | 2020-04-10
ES-20-G56 | 2020-02-12 | Nexamp Solar Poland Road Conway Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Nexamp Solar LLC for the installation of a 4.4 MW solar PV generator and 2.0 MW/4.0 MWh batteries in Conway, MA interconnecting to the 38A1 feeder through the Ashfield 38A Substation. | 8/1/2020 | Notification | 2020-04-10
ES-20-G57 | 2020-03-20 | 510 Project Development Copicut Road Freetown Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of 510 Project Development for the installation of a 4.99 MW solar PV generator and 5.0 MW/26.431 MWh batteries in Freetown, MA interconnecting to Circuit 2-605-605 out of Bell Rock 661 Station. | 2021-02-21 | Notification | 2020-04-10
ES-20-G58 | 2020-03-10 | SWEB Development Route 24 Freetown Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of SWEB Development USA LLC for the installation of a 4.875 MW solar PV generator and 2.438 MW/5.421 MWh batteries in Freetown, MA interconnecting to Circuit 2-605-605 out of Bell Rock 661 Station. | 2022-09-01 | Notification | 2020-04-10
ES-20-G53 | 2020-03-03 | Brigham Womens Hospital Energy Storage System No. 1 | Generator notification from Eversource Energy ("ES") on behalf of Brigham Womens Hospital for the installation of a 1.6 MW energy storage only project in Boston, MA interconnecting to the 14kV customer owned Station #335 supplied by 14kV DSS Line 335-1031 and 335-1141 off the 115kV/14kV Colburn Station. | 3/2020 | Notification | 2020-04-20
ES-20-G48 | 2020-03-10 | Churchill Solar Farm LLC Churchill Street Pittsfield Solar | Generator notification from Eversource Energy ("ES") on behalf of Churchill Solar Farm, LLC for the installation of 3.25 MW solar PV generation in Pittsfield, MA interconnecting to the 30B5 feeder through the Oswald 30B Substation. | 10/2020 | Notification Withdrawn | 4/10/2020 5/18/2021
ES-20-G37 | 2020-02-12 | CEC Development LLC Fox Hill Road Bernardston Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of CEC Development for the installation of 2.0 MW solar PV generator and 2.0 MW/4.0 MWh batteries in Bernardston, MA interconnecting to the 21C1 feeder through the Montague 21C Substation. | 2020-06-01 | Notification | 2020-04-10
ES-20-G35 | 2020-02-12 | Kearsarge West Street Ludlow Solar | Generator notification from Eversource Energy ("ES") on behalf of Kearsarge Solar, LLC for the installation of 3.3 MW solar PV generation in Ludlow, MA interconnecting to the 27A5 feeder through the Orchard 27A Substation. | 7/2020 | Notification | 2020-04-10
ES-20-G03 | 2020-02-25 | Solect Energy Development LLC MIT Lincoln Lab Wood Street Lexington Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Solect Energy Development, LLC for the installation of 0.24MW solar PV generation and 0.26 MW/.0522 MWh and 1.0 MW/2.19 MWh batteries in Lexington, MA interconnecting to customer station #115 supplied by 13.8kV DSS 115-1387, 115-1388, 115-1389 off the 115kV/14kV Hartwell Ave Station #533. | 2020-06-30 | Notification | 2020-04-10
ES-20-G15 | 2019-12-13 | Camp White Fuller Street Ludlow Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Camp White Solar, LLC for the installation of 4.998 MW solar PV generator and (4.2 MW/16.8 MWh) batteries in Ludlow, MA interconnecting to the 19S3 feeder through the Ludlow 19S Substation. | 5/2020 | Notification | 2020-04-10
ES-20-G19 | 2019-12-20 | PVH Energy Storage Onota Street Pittsfield Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of PVH Energy for the installation of 2.108 MW solar PV generation and (0.728 MW/ 2.72MWh) batteries in Pittsfield MA interconnecting to the 30B5 feeder through the Oswald 30B Substation. | 5/2020 | Notification | 2020-04-10
ES-20-G21 | 2019-12-24 | Revere Solar LLC Cape Street Lee Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Revere Solar, LLC for the installation of 4.998 MW solar PV generation and (4.2 MW/16.8MWh) batteries in Lee, MA interconnecting to the 1681 feeder through the Pleasant 16B Substation. | 5/2020 | Notification Withdrawn | 4/10/2020 6/18/2024
ES-20-G22 | 2019-12-24 | LTI Smartglass Inc. Federico Drive Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of LTI Smartglass Inc. for the installation of 1.45 MW solar PV generation and (0.5 MW/ 1.016 MWh) batteries in Pittsfield, MA interconnecting to the 19A5 feeder through the Doreen 19A Substation. | 5/2020 | Notification | 2020-04-10
ES-19-G32 Rev.2 | 2020-03-10 | TJA Solar Wilson Street Hopkinton Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of TJA Solar for the installation of 2.77 MW solar PV generation and 1.75 MW/3.892 MWh batteries with net output of 2.77MW in Hopkinton, MA interconnecting to the 13.8kV 455-H3 Circuit off West Framingham Station #455 115kV/14kV/ 110A. | 11/2020 | Notification | 2020-04-10
ES-16-G59 Rev.1 | 2020-02-25 | Plainfield Solar LLC Union Street Plainfield Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Plainfield Solar, LLC for the installation of 1.99 MW solar PV generation and 1.07 MW/2.14 MWh batteries with total output limited to 1.99MW in Plainfield, MA interconnecting to the Plainfield 18K Substation. | 8/2020 | Notification | 2020-04-10
ES-20-T18 | 2020-02-26 | Wing Land Substation Emergency Replacement of Failed Transformer with Spare | Transmission notification from Eversource Energy (“ES”) to replace a failed 21/28/35[39] MVA 115/13.2kV transformer with a spare 12/16/20[22] MVA 115/13.2kV transformer at Wing Lane Substation #624. | 2020-05-01 | Notification | 2020-03-27
NEP-20-T04 | 2020-03-05 | Golden Hills Shunt Reactor Addition | Transmission application from New England Power Company ("NEP") to tap a 160 MVAr shunt reactor off the 345 kV #349 Wakefield Junction – Mystic Line at Golden Hills Substation. | 9/2021 | Approved | 2020-03-27
ES-20-T12 | 2020-02-25 | Pemigewasset Transformer TB88 Replacement | Transmission application from Eversource Energy (“ES”) for the replacement of the 115-34.5kV 20MVA transformer TB88 with a 62.5 MVA unit with an impedance of approximately half that of the existing transformer. | 10/2020 | Approved | 2020-03-27
ES-20-G26 | 2020-03-09 | Granville I Hayes Road Granville Solar | Generator notification from Eversource Energy ("ES") on behalf of Granville I Solar, LLC for the installation of a 4.5 MW solar PV generation in Granville, MA interconnecting to the 29A5 feeder through the Southwick 29A Substation. | 5/2020 | Notification | 2020-03-26
TFRM-20-X01 | 2020-01-30 | Sheffield Wind AVR Project | Implement Automatic Voltage Regulator (AVR) at the 40MW Vermont Wind LLC / Sheffield Wind facility through updated software. | 2020-09-01 | Approved | 2020-03-24
KGE-20-G01 | 2020-02-05 | Kendall Station Upgrade | Generator application from Kendall Green Energy for upgrades to Kendall Station to increase capacity by 36 MW. Prime mover and rotor upgrade, and H2 pressure increase. | 2022-06-01 | Approved Withdrawn | 3/24/2020 3/4/2025
KGE-20-G02 | 2020-02-05 | Kendall Station Upgrade | Generator application from Kendall Green Energy for capacity restoration project to reutilize capacity and uprate asset 1672. | 2022-06-01 | Approved | 2020-03-24
VELCO-20-T01 | 2020-01-30 | Freepoint Commodities LLC - FPS Panton Solar Project | Expand bus work and add a 115-kV breaker to connect QP807 Solar PV project to the Vergennes 115-kV Substation. | 2023-06-01 | Approved | 2020-03-24
FPS-20-G01 | 2020-02-05 | Freepoint Commodities LLC - FPS Panton Solar Project | Generator application from Freepoint Commodities LLC for FPS Panton Solar Project a 50 MW solar PV generation project consisting of 23 2.5MVA inverters with an aggregate rating of 50MW interconnecting to the 115-kV Vergennes Substation in Panton, VT. | 2024-01-01 | Approved | 2020-03-24
EM-20-G01 | 2020-01-24 | BD Solar 1 - Milo Solar PV Project | Generator application from Emera Maine on behalf of BD Solar 1, LLC for Milo Solar PV Project (Milo Solar Units 1-8) a 20MW solar array interconnecting to a tap line on the Emera Maine 46kV Line 74 adjacent to the Milo Substation. The project consists of: (i) eight 2.5 MW solar inverters (each rated at 2.5MW +/- 1.145MVAR; (ii) one 46kV, 600A, 250kV BIL pole mounted recloser; eight 0.55/46kV GSU transformers; (iii) eight collector strings to be operated at 0.55 kV nominal. | 8/2020 | Approved | 2020-03-24
NEP-20-T02 | 2020-02-03 | N-192 Cable Replacement and Beverly Substation Transformer Addition | Replacement of the N-192 Cable and addition of a transformer in the Beverly Substation. | 5/2023 | Approved | 2020-03-24
ES-20-T04 | 2020-01-30 | Undergrounding of 0.178 miles of 1440 Glenbrook - Waterside Line | Transmission notification from Eversource Energy (“ES”) to underground 0.178 mile of the 115-kV 1440 Line between Glenbrook and Waterside Substations in Stamford, CT. Replace underground portion of existing conductor to address line clearance requirements. | 2020-04-30 | Notification | 2020-03-05
ES-20-T05 | 2020-01-30 | Undergrounding of 0.178 miles of 1750-2 South End Substation - Tomac Tap Line | Transmission notification from Eversource Energy (“ES”) to underground of 0.178 miles of the 115-kV 1750-2 Line from South End Substation to Tomac Tap in Stamford, CT. Replace a portion of the 115-kV 1750-2 Line in Stamford and Grenwich, CT with 0.178 miles of 5000-kcmil underground cable to address line clearance requirements. | 2020-04-30 | Notification | 2020-03-05
ES-20-T06 | 2020-01-30 | Asset Condition Rebuild of 1655 Branford 11J - North Haven 10A Line (Structures Only) | Transmission notification from Eversource Energy (“ES”) for the Asset Condition rebuild of the 11.45 mile 115-kV 1655 Line between Bradford 11J and North Haven 10A Substations (Structure Replacements Only). The project consists of the replacement of wood structures on the 115-kV 1655 overhead line between Branford 11J Substation in Branford, CT and Avangrid’s New Haven 10A Substation in Wallingford, CT. The existing conductor will not be replaced or upgraded but the impedance and line length will be corrected and the summer LTE will increase from 239MVA to 252 MVA due to terminal equioment rating correction. Other summer ratings remain unchanged. | 2020-01-20 | Notification | 2020-03-05
ES-20-T08 | 2020-01-22 | Rebuild Line 1632 Montague - Podick | Transmission notification from Eversource Energy (“ES”) to rebuild line 1632 from Montague to Podick. Replace the existing 14.9 miles of conductor with 795-kcmil ACSS phase conductor rated at 123/145/148 Summer. | 12/2023 | Notification | 2020-03-05
ES-20-T09 | 2020-01-22 | Rebuild Line 1044 Montague - Amherst | Transmission notification from Eversource Energy (“ES”) to rebuild line 1044 from Montague to Amherst. Replace 15.9 miles of existing conductor from Montague to Tillson Tap with 795kcmil ACSS phase conductor rated at 159/159/159 Summer (Normal, LTE, STE) and replace 1.6 miles of existing conductor from Tillson Tap to Amherst with 795kcmil ACSS phase conductor rated at 159/159/159 Summer (Normal, LTE, STE). | 12/2023 | Notification | 2020-03-05
ES-20-T10 | 2020-01-22 | Rebuild Line 1113 Podick - Fairmount | Transmission notification from Eversource Energy (“ES”) to rebuild line 1113 from Podick to Fairmont. Replace 3.4 miles of existing conductor from Podick to Tillson Tap with 795kcmil ACSS phase conductor rated at 189/202/249 Summer (Normal, LTE, STE). Replace 10.2 miles of existing conductor from Tillson Tap to Five Corners Tap with 795kcmil ACSS phase conductor rated at 283/352/386 Summer (Normal, LTE, STE). Replace 4.9 miles of existing conductor with 795kcmil ACSS phase conductor rated at 235/251/316 Summer (Normal, LTE, STE). | 12/2023 | Notification | 2020-03-05
ES-20-T11 | 2020-01-22 | Rebuild 1134 Amherst - Fairmount | Transmission notification from Eversource Energy (“ES”) to rebuild line 1134 from Amherst to Fairmont. Replace 8.5 miles of existing conductor with 795kcmil ACSS phase conductor rated at 91/106/107 Summer (Normal, LTE, STE). Replace 4.9 miles of existing conductor with 795kcmil ACSS phase conductor rated at 235/251/316 Summer (Normal, LTE, STE). | 12/2023 | Notification | 2020-03-05
NEP-20-T01 | 2020-02-03 | East Tewksbury Substation Transformer Replacements | Transmission notification from New England Power Company ("NEP") to replace existing 115/13.8kV 24/32/40 MVA transformers T1 and T2 with 115/13.8kV 33/44/55 MVA transformers. | 2/2022 | Notification | 2020-03-05
CMP-20-G01 | 2020-02-05 | NextGrid Mangrove LLC Merrill Road Lewiston Solar | Generator notification from Central Maine Power ("CMP") on behalf of NextGrid Mangrove LLC for the installation of a 4.9 MW solar PV generator in Lewiston, ME interconnecting to Central Maine Power, Deer Rips Substation, Circuit 412D4 Pole #P9. | 2020-09-30 | Notification | 2020-02-28
CMP-20-G02 | 2020-02-05 | NextGrid Cliffrose LLC Lisbon Street Lewiston Solar | Generator notification from Central Maine Power ("CMP") on behalf of NextGrid Cliffrose LLC for the installation of a 2.0 MW solar PV generator in Lewiston, ME interconnecting to Central Maine Power, Crowleys Substation, Circuit 411D1 Pole #P10. | 2020-10-01 | Notification | 2020-02-28
ES-19-G32 Rev.1 | 2020-02-03 | TJA Solar Wilson Street Hopkinton Solar | Generator notification from Eversource Energy ("ES") on behalf of TJA Solar for the installation of a 2.772 MW solar PV generator in Hopkinton, MA interconnecting to the 13.8Kv 455-H3 circuit off West Framingham Station #445 115kV/14kV 110A. | 11/2020 | Notification | 2020-02-28
ES-19-G58 Rev.1 | 2020-02-03 | GSSG New Hampshire Shannon Road Franklin Solar | Generator notification from Eversource Energy ("ES") on behalf of GSSG New Hampshire LLC for the installation of a 2.0 MW solar PV generator in Franklin, NH interconnecting to Eversource NH-337X6 Circuit fed from the 3548 Line out of the Eversource NH-Daniel Substation. | 2020-02-03 | Notification | 2020-02-28
ES-20-G31 | 2020-01-27 | Verogy Bucks Hill Road Waterbury Solar | Generator notification from Eversource Energy ("ES") on behalf of Verogy for the installation of a 2.0 MW solar PV generator in Waterbury, CT interconnecting to Noera 13H Substation through Eversource Energy 13H99 13.8kV distribution feeder. | 2022-06-30 | Notification Withdrawn | 2/28/2020 7/16/2024
ES-20-G32 | 2020-01-27 | Buck Solar LLC Pine Gates Pequot Trail Stonington Solar | Generator notification from Eversource Energy ("ES") on behalf of Buck Solar LLC for the installation of a 2.0 MW solar PV generator in Stonington, CT interconnecting to the Mystic 115kV Substation through Eversource Energy 13K1 13.8kV distribution feeder. | 2020-12-31 | Notification Withdrawn | 2/28/2020 9/20/2022
ES-20-G38 | 2020-01-17 | Old Frontier Solar III, LLV Settright Road Deerfield Solar | Generator notification from Eversource Energy ("ES") on behalf of Old Frontier Solar III, LLC for the installation of a 2.0 MW solar PV generator in Deerfield, MA interconnecting to the 22B3 Feeder through the Cumberland 22B Substation. | 2020-05-31 | Notification | 2020-02-28
ES-20-G40 | 2020-02-10 | Ameresco Solar Land Holdings LLC French King Highway | Generator notification from Eversource Energy ("ES") on behalf of Ameresco Solar Land Holdings LLC for the installation of a 4.98 MW solar PV generator in Erving, MA interconnecting to the 21C9 feeder through the Montague 21C substation. | 6/2020 | Notification | 2020-02-28
ES-20-G41 | 2020-01-17 | Power America Inc., Old Dalton Road Hinsdale Solar | Generator notification from Eversource Energy ("ES") on behalf of Power America Inc. for the insallation of a 3.0 MW solar PV generator in Hinsdale, MA interconnecting to the 18C2 Feeder through the Berkshire 18C Substation. | 2020-07-01 | Notification | 2020-02-28
NEP-20-GNF16 | 2020-02-03 | Forefront Power - Main Street Uxbridge Solar | Generator notification from New England Power Company ("NEP") on behalf of Forefront Power LLC for the installation of a 4.0 MW solar PV generator in Uxbridge, MA interconnected to the 321W9 13.8kV distribution feeder to the Uxbridge Substation. | 2020-07-14 | Notification | 2020-02-28
NEP-17-GNF44 Rev.1 | 2020-02-03 | 510 Project Development - Main Street Newbury Solar | Generator notification from New England Power Company ("NEP") on behalf of 510 Project Development for the installation of a 2.0 MW solar PV generator located in Newbury, MA interconnected to the 2405 23kV distribution feeder to the King Street Substation. The revision is to reduce the original system size of 4.4 MW to 2.0 MW. | 2020-10-15 | Notification | 2020-02-28
NEP-19-GNF172 Rev.1 | 2020-02-03 | Blue Wave Solar - Beebe Road Wilbraham Solar | Generator notification from New England Power Company ("NEP") on behalf of Blue Wave Solar for the installation of a 4.0 MW solar PV generator in Wilbraham, MA interconnected to the 507L1 13.2kV distribution feeder to the Wilbraham Substation. The revision consists of a reduction from the original system size from 4.4 MW to 4.0MW. | 2020-02-21 | Notification | 2020-02-28
CMP-20-G03 | 2020-02-05 | 510 PV Project LLC Development Borrego Kimball Road Harrison Solar and Battery | Generator notification from Central Maine Power ("CMP") on behalf of 510 PV Project Development, LLC for the installation of a 4.99 MW solar PV generator and 4.99/26MWh battery in Harrison, ME interconnecting to Central Maine Power, Kimball Road Substation, Circuit 423D1 Pole #75. | 2020-12-31 | Notification | 2020-02-28
ES-20-G01 | 2020-02-10 | Kearsarge Norfolk LLC North Street Walpole Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Kearsarge Solar LLC for the installation of a 4.99 MW solar PV generator and 2.4 MW/4.8 MWh battery in Walpole, Massachusetts interconnecting to the 13.8kV circuit 456-H1 off 115/14kV Dover Substation. | 2020-07-31 | Notification | 2020-02-28
ES-20-G07 | 2020-01-15 | Kearsarge Solar Rear Turnpike Road Montague Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Kearsarge Solar LLC for the installation of a 3.77 MW solar PV generator and battery in Montague, MA interconnecting to the 21C2 feeder through the Montague 21C Substation. | 4/2020 | Notification | 2020-02-28
ES-20-G18 | 2020-01-27 | DG Massachusetts Solar LLC George Millard Road Blandford Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of DG Massachusetts Solar LLC for the installation of a 4.45 MW solar PV generator and battery in Blandford, MA interconnecting to Blandford Substation through Eversource Energy 19J2 23kV distribution feeder. | 5/2020 | Notification | 2020-02-28
ES-20-G39 | 2020-02-10 | Beacon Solar LLC Florence Road Easthampton Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Beacon Solar, LLC for the installation of a 4.998 MW solar PV generator and battery in Easthampton, MA interconnecting to the 15A3 Eversource feeder, which is served from Gunn 15A Substation. | 2020-05-31 | Notification | 2020-02-28
NEP-20-GNF15 | 2020-02-03 | Zero Point - Providence Street Uxbridge Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of ZPT Energy Solutions for the installation of a 2.0 MW solar PV generator and battery in Uxbridge, MA interconnecting through the 321W9 13.8kV distribution feeder to the Uxbridge Substation. | 2020-05-01 | Notification | 2020-02-28
CMP-19-G10 | 2019-12-18 | Hep Energy Curtis Street Pittsfield Solar | Generator notification from Central Maine Power ("CMP") on behalf of HEP Energy USA Project Development, LLC for the installation of 4.875 MW solar PV in Pittsfield, ME interconnecting to Central Maine Power, Detroit Substation, Circuit 812D1 Pole P-#4. | 2020-07-01 | Notification | 2020-02-26
CMP-19-G11 | 2019-12-18 | NextGrid Peppertree Lewiston Junction Road Poland Solar | Generator notification from Central Maine Power ("CMP") on behalf of NextGrid, Inc. for the installation of 4.875 MW solar PV in Poland, ME interconnecting to Central Maine Power, Hotel Road Substation, Circuit 420D4 Pole #020. | 2020-09-09 | Notification | 2020-02-26
CMP-19-G12 | 2019-12-23 | BD Solar Palmyra US Route Palmyra Solar | Generator notification from Central Maine Power ("CMP") on behalf of 4.99 MW solar PV in Palmyra, ME interconnecting on the 12.47MW 837D1 distribution circuit from CMP’s Newport Substation. | 2021-06-30 | Notification | 2020-02-26
ES-20-G47 | 2020-01-09 | O & G Industries, Inc. Southbury Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of O & G Industries, Inc. for the installation of 1.24 MW solar PV generator and battery in Southbury Connecticut interconnecting to the Bates Rock substation through the Eversource Energy 21K2 13.8kV distribution feeder. | 2020-02-14 | Notification | 2020-02-26
ES-20-G42 | 2020-01-07 | Osborne Correctional Bilton Road Somers Solar | Generator notification from Eversource Energy ("ES") on behalf of CT Department of Corrections for the installation of 2.0 MW solar PV in Somers, CT interconnecting to the Scitico substation through the Eversource Energy 27H6 23KV distribution feeder. | 2020-06-01 | Notification | 2020-02-26
ES-20-G34 | 2020-01-03 | Sunjet Hill Street Bristol Solar | Generator notification from Eversource Energy ("ES") on behalf of Sunjet Energy, LLC for the installation of 1.998 MW solar PV in Bristol, CT interconnecting to the 13.8kV bus in the Eversource Chippen Hill 115-kV Substation through the Eversource 15U4 13.8kV distribution feeder. | 2022-06-30 | Notification Withdrawn | 2/26/2020 9/20/2022
ES-20-G33 | 2020-01-03 | Pinegates Garnet Solar Monahan Road Uncasville Solar | Generator notification from Eversource Energy ("ES") on behalf of Pinegates Renewables for the installation of 2.0 MW solar PV in Uncasville, CT interconnecting to the Eversource Judd Brook 115-kV Substation through the Eversource 32R1 23-kV distribution feeder. | 2020-10-01 | Notification Withdrawn | 2/26/2020 9/20/2022
ES-20-G29 | 2019-12-27 | Altus Power America Mt. Herman Station Road Northfield Solar | Generator notification from Eversource Energy ("ES") on behalf of Altus Power America Inc. for the installation of 4.5 MW solar PV in Northfield, MA interconnecting to the Eversource French King 21B substation. | 5/2020 | Notification Withdrawn | 2/26/2020 3/17/2020
ES-20-G27 | 2019-12-24 | Westfarms Associates Westfarms Mall Farmington Solar | Generator notification from Eversource Energy ("ES") on behalf of Westfarms Associates for the installation of 2.6307 MW solar PV in Farmington, CT interconnecting to the Eversource Farmington Substation through the Eversource 1CO3 23kV distribution feeder. | 2020-01-03 | Notification | 2020-02-26
ES-20-G25 | 2020-01-07 | Charles Garrity Paul Drive Lee Solar | Generator notification from Eversource Energy ("ES") on behalf of ZPTII Energy Solutions, LLC for the installation of 2.0 MW solar PV generator in Lee, MA interconnecting to Eversource Woodland 17G 115kV substation through the Eversource 17G3 23kV distribution feeder. | 5/2020 | Notification Withdrawn | 2/26/2020 8/17/2022
ES-20-G24 | 2019-12-24 | Caps Solar New London Road Colchester Solar | Generator notification from Eversource Energy ("ES") on behalf of Caps Solar, LLC for the installation of 1.0014 MW solar PV in Colchester, CT interconnecting to the Eversource Judd Brook Substation through the Eversource 32R1 23kV distribution feeder. | 2020-06-01 | Notification Withdrawn | 2/26/2020 9/20/2022
ES-20-G20 | 2019-12-20 | Mass RE 12 Railroad Yard Deerfield Solar | Generator notification from Eversource Energy ("ES") on behalf of Mass RE 12 for the installation of 2.2 MW solar PV in Deerfield, MA interconnecting to the 22B4 feeder through the Cumberland 22B substation. | 5/2020 | Notification Withdrawn | 2/26/2020 8/17/2022
ES-20-G16 | 2019-12-12 | CSW Energy Fitch Hill Road Uncasville Solar | Generator notification from Eversource Energy ("ES") on behalf of CSW Energy for the installation of1.968 MW solar PV in Uncasville, CT interconnecting to the Uncasville 115KV substation through the Eversource Energy 1Q01 13.2KV distribution feeder. | 5/2020 | Notification | 2020-02-26
ES-20-G13 | 2019-12-13 | Energy Development Group Hathaway Road Westhampton Solar | Generator notification from Eversource Energy ("ES") on behalf of Energy Development Group, LLC for the installation of 2.5 MW solar PV in Westhampton, MA interconnecting to the 15A3 feeder through the Gunn 15A substation. | 2021-04-01 | Notification Withdrawn | 2/26/2020 8/17/2022
ES-20-G12 | 2019-12-13 | Soltage Park Street Easthampton Solar | Generator notification from Eversource Energy ("ES") on behalf of Soltage, LLC for the installation of 2.457 MW solar PV in Easthampton, MA interconnecting the 15A2 Feeder into Gunn 15A substation. | 2020-06-08 | Notification | 2020-02-26
ES-20-G06 | 2020-01-07 | Sysco Corporation Inwood Road Rocky Hill Solar | Generator notification from Eversource Energy ("ES") on behalf of Sysco Corporation for the installation of 1.8 MW solar PV in Hartford, CT interconnecting to the Eversource Rocky Hill 3R Substation through the Eversource 3R12 23kV distribution feeder. | 2020-10-30 | Notification Withdrawn | 2/26/2020 6/18/2024
ES-19-G22 Rev.1 | 2020-01-09 | SunRaise Development Lake Street Plympton Solar and Battery Rev.1 | Generator notification from Eversource Energy ("ES") on behalf of SunRaise Development, LLC for the installation of 3.247 MW solar PV and 2.0MW/4.448MWH battery in Plympton, MA interconnecting to the Eversource Kingston Substation #735 transformer#2 23kV feeder 3-15-906. The proposed in-service date is 12/1/2020.This application was previously approved as a 4.998MW PV generator and battery at the November 2019 RC meeting. | 2020-12-01 | Notification | 2020-02-26
NEP-20-GNF13 | 2020-01-07 | Altus Power America Clayton Road Sheffield Solar | Generator notification from New England Power Company ("NEP") on behalf of Altus Power America for the installation of 2.20 MW solar PV in Sheffield, MA interconnecting to NEP’s 1108W2 feeder out of its Pleasant Street substation. | 2020-03-20 | Notification | 2020-02-26
NEP-20-GNF12 | 2020-01-07 | Altus Power America Mill River Southfield Road New Malborough | Generator notification from New England Power Company ("NEP") on behalf of Altus Power America for the installation of 2.0 MW solar PV in New Marlborough, MA interconnecting to NEP’s 1109W1 feeder out of its Pleasant Street substation. | 2020-04-29 | Notification | 2020-02-26
NEP-20-GNF11 | 2020-01-07 | Lodestar Energy Stockbridge Road Great Barrington Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Lodestar Energy, LLC for the installation of 2.0 MW solar PV with 1000kW/2256kWh of DC coupled battery in Great Barrington, MA interconnecting to NEP’s 1102W1 feeder out of its Pleasant Street substation. | 2021-02-09 | Notification Withdrawn | 2/26/2020 9/13/2022
NEP-20-GNF10 | 2020-01-07 | Clean Energy Collective Hewins Street Sheffield Solar | Generator notification from New England Power Company ("NEP") on behalf of Clean Energy Collective for the installation of 2.13 MW solar PV in Sheffield, MA interconnecting to NEP’s 1108W2 feeder out of its Pleasant Street substation. | 2020-11-02 | Notification | 2020-02-26
NEP-20-GNF09 | 2020-01-07 | Navisun Home Road Sheffield Solar | Generator notification from New England Power Company ("NEP") on behalf of Navisun, LLC fot the installation of 1.98 MW solar PV in Sheffield, MA interconnecting to NEP’s 1109W1 feeder out of its Pleasant Street substation. | 2020-04-08 | Notification | 2020-02-26
NEP-20-GNF07 | 2020-01-07 | Zero Point Randall Road Berlin Solar | Generator notification from New England Power Company ("NEP") on behalf of Zero Point Development, Inc. for the installation of 4.95 MW solar PV in Berlin, MA interconnecting to NEP’s 318W3 feeder out of its North Marlboro substation. | 2020-06-01 | Notification | 2020-02-26
NEP-20-GNF06 | 2020-01-07 | Lodestar Energy Lunenburg Road Lancaster Solar | Generator notification from New England Power Company ("NEP") on behalf of Lodestar Energy, LLC for the installation of 3.90 MW solar PV in Lancaster, MA interconnecting to NEP’s 227W1 feeder out of its Laurel Circle substation. | 2020-03-26 | Notification | 2020-02-26
NEP-20-GNF05 | 2020-01-07 | Pro-Tech Energy Old Union Turnpike Lancaster Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of 4.95 MW solar PV with 2475kW/4960kWh of DC coupled battery in Southbridge, MA interconnecting to NEP’s 227W1 feeder out of its Laurel Circle substation. | 2020-08-16 | Notification Withdrawn | 2/26/2020 6/16/2020
NEP-20-GNF04 | 2020-01-07 | Zero Point Development Main Street Williamsburg Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Zero Point Development, Inc. for the installation of 4.95 MWsolar PV with 3245kW/6502kWh of decoupled battery in Williamsburg, MA interconnecting to NEP’s 909W3n feeder out of its Florence Junction substation. | 2020-11-27 | Notification | 2020-02-26
NEP-20-GNF03 | 2020-01-07 | Direct Energy Solar River Road northampton Solar | Generator notification from New England Power Company ("NEP") on behalf of Direct Energy Solar for the installation of 4.0 MW solar PV in Northampton, MA interconnecting to NEP’s 9-09W3 feeder out of its Florence Junction substation. | 2021-11-01 | Notification Withdrawn | 2/26/2020 5/19/2020
NEP-20-GNF02 | 2020-01-07 | CEC Development River Road Williamsburg Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Clean Energy Collective for the installation of 4.68 MW solar PV with 100kW/2000kWh of DC coupled battery in Williamsburg, MA on NEP’s 909W1 feeder out of its Florence Junction substation. | 2022-09-29 | Notification | 2020-02-26
NEP-20-GNF01 | 2020-01-07 | Syncarpha Solar LLC Glendale Road Northampton Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Syncarpha Solar, LLC for the installation of 4.99 MW solar PV with 2000kW/4000kWh of AC coupled battery in Northampton, MA interconnecting to NEP’s 909W4 feeder out of its Florence Junction substation. | 2021-03-11 | Notification | 2020-02-26
NEP-19-GNF68 Rev.1 | 2020-01-07 | Heron Crossing Solar Shuman Avenue Stoughton Solar and Battery Rev.1 | Previously approved 2 MW solar PV generator in Stoughton Massachusetts interconnecting to NEP’s 94W42 feeder out of its Parkview Substation is modified to add 2000kW/2192 kWh of DC coupled battery. | 2020-05-14 | Notification | 2020-02-21
ES-20-G30 | 2020-01-03 | Pinegates Narwhal Gildersleeve Road Portland Solar | Generator notification from Eversource Energy ("ES") on behalf of Pinegates Renewables for the installation of 4.0 MW solar PV in Portland, CT interconnecting to the Eversource Portland 115-kV Substation through the Eversource 21H12 23-kV distribution feeder. | 2021-06-01 | Notification Withdrawn | 2/21/2020 9/20/2022
ES-20-T03 | 2020-01-09 | 1355-1 Line Rebuild Project | Transmission notification from Eversource Energy (“ES”) to rebuild 1.3 miles of 115-kV PTF line from Schwab Junction to Colony Substation (owned by Wallingford Utility) in Wallingford, CT. The rebuild is to replace the existing bundled 4/O copper (built in 1927) conductor with 556 ACSS conductor due to asset condition. | 2020-05-31 | Notification | 2020-02-21
ES-20-T02 | 2020-01-08 | Mansfield (12J) 69-kV Substation | Transmission notification from Eversource Energy (“ES”) that the Mansfield (12J) Substation in Mansfield Connecticut is installing two step-down distribution transformers two 69kV circuit breakers, and four 69-Kv circuit switchers to replace an existing step-down transformer. The Project is needed to address local load reliability. | 2022-12-31 | Notification | 2020-02-21
ES-20-T01 | 2019-12-30 | Replacement of Mystic 115 kV Breaker | Transmission notification from Eversource Energy (“ES”) that Mystic Station is replacing 115kV breaker #4 at Mystic Station #250 with a double breaker. The Mystic Sta. #250, Double Breaker #4 Installation Project was identified as part of the Boston 2028 Needs Assessment. The Project is needed to mitigate high transmission system voltages. | 6/2021 | Notification | 2020-02-21
ES-20-G09 | 2019-12-13 | CVE North America Montague Road Westhampton Solar | Generator notification from Eversource Energy ("ES") on behalf of CVE North America, Inc. for the installation of 4.98 MW solar PV in Westhampton, MA interconnecting to the Eversource 15A3 Feeder through the Gunn 15A substation. | 5/2020 | Notification | 2020-02-10
ES-20-G10 | 2019-12-13 | CVE North America Blandford Road Russell Solar | Generator notification from Eversource Energy ("ES") on behalf of CVE North America, Inc. for the installation of 2.988 MW solar PV in Russell, MA interconnecting to the 19J2 Feeder through the Blandford 19J substation. | 5/2020 | Notification | 2020-02-10
ES-20-G11 | 2019-12-31 | CVE North America West Main Road Peru Solar | Generator notification from Eversource Energy ("ES") on behalf of CVE North America, Inc. for the installation of 3.32 MW solar PV in Peru, MA interconnecting to the 18C2 Feeder through the Berkshire 18C substation. | 5/2020 | Notification | 2020-02-10
NEP-20-GNF08 | 2020-01-07 | CVE North America Knight Road New Marlboro Solar | Generator notification from New England Power Company ("NEP") on behalf of CVE North America, Inc. fior the installation of 4.98 MW solar PV in New Marlboro, MA interconnecting to NEP’s 1109W1 feeder out of its Pleasant Street substation. | 2020-05-04 | Notification | 2020-02-10
NEP-19-GNF13 | 2019-12-01 | Kearsarge Solar Old Groveland Road Haverhill Solar Project | Generator notification from New England Power Company ("NEP") on behalf of Kearsarge Solar, LLC for the installation of 4.8 MW solar PV in Haverhill, MA and interconnecting to the King Street Substation via the 2329 23 kV feeder. | 2020-06-01 | Notification | 2019-12-30
NEP-19-GNF135 | 2019-12-01 | Aquantum Solutions Lovers Lane Haverhill Solar Project | Generator notification from New England Power Company ("NEP") on behalf of Aquantum Solutions, Inc. for the installation of 4.98 MW solar PV in Haverhill, MA and interconnecting to the Whittier Substation via the 76L1 13.2 kV feeder. | 2020-05-01 | Notification | 2019-12-30
NEP-19-GNF184 | 2019-12-01 | UPS Brick Kiln Road Chelmsford Solar Project | Generator notification from New England Power Company ("NEP") on behalf of UPS for the installation of 1.992 MW solar PV in Chelmsford, MA and interconnecting to the Meadowbrook Substation via the 2384 23 kV feeder. | 2020-08-07 | Notification | 2019-12-30
NEP-19-GNF188 | 2019-12-01 | Lodestar Energy Lafayette Road Salisbury Solar Project | Generator notification from New England Power Company ("NEP") on behalf of Lodestar Energy for the installation of 4.0 MW solar PV in Salisbury, MA and interconnecting to the Beach Road Substation via the 7L4 13.2 kV feeder. | 2021-02-25 | Notification Withdrawn | 12/30/2019 9/23/2020
NEP-19-GNF196 | 2019-12-01 | Kearsarge Solar Dexter Road East Providence Solar Project | Generator notification from New England Power Company ("NEP") on behalf of Kearsarge Solar, LLC for the installation of 2.0 MW solar PV in East Providence, RI and interconnecting to the Wampanoag Substation via the 48F6 12.47 kV feeder. | 2021-02-05 | Notification | 2019-12-30
NEP-19-GNF199 | 2019-12-01 | Independence Solar Town Farm Lane North Billerica Solar Project | Generator notification from New England Power Company ("NEP") on behalf of Independence Solar for the installation of 1.95 MW solar PV in North Billerica, MA and interconnecting to the Billerica Substation via the 70L1 13.2 kV feeder. | 2020-11-17 | Notification Withdrawn | 12/30/2019 4/22/2020
NEP-19-GNF141 | 2019-12-01 | Cabot Corporation Conord Road Billerica Solar and Battery Project | Generator notification from New England Power Company ("NEP") on behalf of Cabot Corporation for the installation of 1.491 MW solar PV and battery in Billerica, MA and interconnecting to the Billerica Substation via the 70L2 13.2 kV feeder. | 2021-06-06 | Notification Withdrawn | 12/30/2019 2/19/2020
NEP-19-GNF181 | 2019-12-01 | Kearsarge Solar South Martin Road Amesbury Solar and Battery Project | Generator notification from New England Power Company ("NEP") on behalf of Kearsarge Solar, LLC for the installation of 4.89 MW solar PV and battery in Amesbury, MA and interconnecting to the West Amesbury Substation via the 275L4 13.2 kV feeder. | 2019-12-31 | Notification | 2019-12-30
NEP-19-GNF183 | 2019-12-01 | BlueWave Crow Lane Newburyport Solar and Battery Project | Generator notification from New England Power Company ("NEP") on behalf of BlueWave Solar for the installation of 1.65 MW solar PV and battery in Newburyport, MA and interconnecting to the Newburyport Substation via the 36L2 13.2 kV feeder. | 2020-03-06 | Notification Withdrawn | 12/30/2019 4/27/2022
NEP-19-GNF198 | 2019-12-01 | BlueWave Crow Hilldale Avenue Haverhill Solar and Battery Project | Generator notification from New England Power Company ("NEP") on behalf of BlueWave Solar for the installation of 4.0 MW solar PV and battery in Haverhill, MA and interconnecting to the North Haverhill Substation via the 48L1 13.2 kV feeder. | 2021-06-20 | Notification | 2019-12-30
NEP-19-G30-014 | 2019-12-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Zero Point Engineering Couburn Road Charlton Solar and Battery Project | Generator application from New England Power Company (“NEP”), on behalf of Zero Point Engineering, for the installation of a 2.0 MW solar array and battery in Charlton, MA which will interconnect to the North Oxford Substation via the 406L3 13.2 kV feeder. | 2020-02-01 | Approved | 2019-12-30
NEP-19-G30-022 Rev.1 | 2019-12-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Zero Point Development - Dresser Road Snow Street Solar Project | Generator application from New England Power Company (“NEP”), on behalf of Zero Point Engineering, for the installation of a 2.5 MW solar array which will interconnect to the Snow Street Substation via the 413L1 13.2 kV feeder. | 2021-05-03 | Approved | 2019-12-30
NEP-19-G30-026 Rev.1 | 2019-12-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Zero Point Development - Dresser Hill Road Snow Street Solar and Battery Project | Generator application from New England Power Company (“NEP”), on behalf of Zero Point Engineering, for the installation of a 2.0 MW solar array and battery which will interconnect to the Snow Street Substation via the 413L8 13.2 kV feeder. | 2021-05-03 | Approved | 2019-12-30
NEP-19-G30-037 | 2019-12-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - ZECOS Energy Pease Road East Longmeadow Solar Project | Generator application from New England Power Company (“NEP”), on behalf of ECOS Energy, for the installation of a 4.0 MW solar array in East Longmeadow, MA which will interconnect to the East Longmeadow Substation via the 508L4 13.2 kV feeder. | 2020-09-25 | Approved | 2019-12-30
NEP-19-G30-054 Rev.1 | 2019-12-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Zero Point Development - Dresser Hill Road Snow Street Solar and Battery Project | Generator application from New England Power Company (“NEP”), on behalf of Zero Point Engineering, for the installation of a 7.75 MW solar array and battery which will interconnect to the Snow Street Substation via the 413L8 13.2 kV feeder. | 2020-11-19 | Approved | 2019-12-30
ES-19-G84 | 2019-12-03 | Greenskies Renewable Elmridge Road Pawcatuck Solar | Generator notification from Eversource Energy ("ES") on behalf of Greenskies Renewable Energy for the installation of 3.0 MW solar PV in Pawcatuck CT, and interconnecting to the Shunock Substation via the 32P3 13.8 kV feeder. | 2022-06-30 | Notification Withdrawn | 12/30/2019 9/20/2022
ES-19-G57 | 2019-11-18 | GSSG New Hampshire Loudon Road Pittsfield Solar | Generator notification from Eversource Energy ("ES") on behalf of GSSG New Hampshire, LLC for the installation of 2.0 MW solar PV in Pittsfield, NH and interconnecting to the Oak Hill Substation via the 319 34.5 kV feeder. | 2019-12-31 | Notification | 2019-12-30
CMP-19-G09 | 2019-12-04 | Hep Energy Wilton Road Farmington Solar | Generator notification from Central Maine Power ("CMP") on behalf of Hep Energy USA Project Development, LLC for the installation of 4.875 MW solar PV in Farmington, ME and interconnecting to the Sturtevant Substation via the 858D3 12.47 kV feeder. | 2021-03-31 | Notification | 2019-12-30
CMP-19-G05 | 2019-12-04 | Walden Solar Rushton Street Sanford Solar | Generator notification from Central Maine Power ("CMP") on behalf of Walden Solar NE LLC for the installation of 4.95 MW solar PV in Sanford, ME and interconnecting to the High Street Substation via the 626D1 12.47 kV feeder. | 2020-12-31 | Notification | 2019-12-30
ES-19-G75 | 2019-12-02 | Borrego Solar Brookwood Drive Westport Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Borrego Solar for the installation of 4.99 MW solar PV and battery in Westport, MA and interconnecting to the Fisher Road Substation via the 2-523-523 13.2 kV feeder. | 2021-08-25 | Notification | 2019-12-30
CPV-19-G01 | 2019-11-25 | CPV Towantic Generator and Transmission Project | Generator application from CPV Towantic (“CPV”) to increase the summer net rating of the CPV Towantic generation 45 MWs for a total net output of 795.5 MWs. | 2020-03-01 | Approved | 2019-12-30
ES-19-T29 | 2019-12-05 | CPV Towantic Generator and Transmission Project | Transmission application from Eversource Energy (“ES”) to upgrade the 3 mile of overhead 115 kV 1029-2 Line from Bunker Hill to Baldwin Tap with 795 kcmil ACSS in support of the Towantic Generator Uprate Project. | 2020-12-31 | Approved | 2019-12-30
JP-19-G01 | 2019-12-03 | Ocean State Power Generator Uprate Project | Generator application from Jericho Power (“JP”) for the uprate of the Ocean State Power generators I and II to 668.9 MW (net output) interconnecting to the Sherman Road Substation in Harrisville, RI. | 2022-05-31 | Approved | 2019-12-30
ROX-19-G01 | 2019-11-25 | RoxWind Generator Wind Project | Generator application from RoxWind LLC. (“ROX”) for the construction of a new 15.3 MW wind farm in Roxbury, ME and interconnecting to the Roxbury Substation. Project will also install one new 34.5 kV breaker at the Roxbury Substation to terminate a dedicated feeder from the wind farm. | 2020-10-15 | Approved | 2019-12-30
NEM-19-G08 | 2019-12-04 | West Portsmouth Solar Generator Project | Generator application from NextEra Energy Resources (“NEM”) for the installation of a 11.25 MW solar array in Concord, NH which will interconnect via a 0.06 mile 34.5 kV feed from the Unitil West Portsmouth Substation. | 2021-11-01 | Approved Withdrawn | 12/30/2019 3/11/2021
NEP-19-G30-001 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Seaboard Solar - Ellis Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Seaboard Solar, for the installation of a 4.875 MW solar PV array interconnecting to the Westminster substation via the 602W3, 13.8 kV feeder in Westminster, MA. | 2020-08-05 | Approved | 2019-12-10
NEP-19-G30-002 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Seaboard Solar - Leicester Street Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Seaboard Solar, for the installation of a 4.875 MW solar PV array interconnecting to the Pondville substation via the 26W1, 13.8 kV feeder in Auburn, MA. | 2021-08-08 | Approved | 2019-12-10
NEP-19-G30-003 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Nexamp Inc. - Barre Road PV and Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Nexamp Inc., for the installation of a 2.200 MW solar PV array and battery interconnecting to the Barre substation via the 604W2, 13.8 kV feeder in Oakham, MA. | 2020-05-11 | Approved | 2019-12-10
NEP-19-G30-004 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Syncarpha Solar LLC - Mulberry Street Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Syncarpha Solar LLC, for the installation of a 2.580 MW solar PV array interconnecting to the Leicester substation via the 21W1, 13.8 kV feeder in Leicester, MA. | 2020-09-30 | Approved | 2019-12-10
NEP-19-G30-005 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Granby Solar - East Street Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Nexamp Inc., for the installation of a 3.000 MW solar PV array and battery interconnecting to the Five Corners substation via the 527L1, 13.2 kV feeder in Granby, MA. | 2020-06-03 | Approved | 2019-12-10
NEP-19-G30-006 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - BlueWave Solar - Upper-Gore Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of BlueWave Solar, for the installation of a 4.980 MW solar PV array interconnecting to the East Webster substation via the 412L1, 13.2 kV feeder in Webster, MA. | 2021-01-29 | Approved | 2019-12-10
NEP-19-G30-007 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Borrego Solar - East Harbor Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Borrego Solar, for the installation of a 1.980 MW solar PV array interconnecting to the Adams substation via the 1021W1, 13.8 kV feeder in Cheshire, MA. | 2020-02-12 | Approved | 2019-12-09
NEP-19-G30-008 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Nexamp Inc. - Barre Cut Off Road Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Nexamp Inc., for the installation of a 5.969 MW solar PV array and battery interconnecting to the Barre substation via the 604W3, 13.8 kV feeder in New Braintree, MA. | 2021-02-26 | Approved | 2019-12-09
NEP-19-G30-009 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Navisun LLC - Turner Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Navisun LLC, for the installation of a 1.980 MW solar PV array interconnecting to the North Oxford substation via the 406L3, 13.2 kV feeder in Charlton, MA. | 2020-05-20 | Approved | 2019-12-09
NEP-19-G30-010 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Navisun LLC - Old Webster Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Navisun LLC, for the installation of a 1.740 MW solar PV array interconnecting to the North Oxford substation via the 406L3, 13.2 kV feeder in Oxford, MA. | 2019-12-20 | Approved | 2019-12-09
NEP-19-G30-011 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Allco Renewable Energy Ltd. - Monson Turnpike Road Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Allco Renewable Energy Ltd, for the installation of an 8.000 MW solar PV array and battery interconnecting to the Belchertown substation via the 509L2, 13.2 kV feeder in Ware, MA. | 2021-02-28 | Approved | 2019-12-10
NEP-19-G30-012 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Borrego Solar - Carpenter Hill Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Borrego Solar, for the installation of a 3.500 MW solar PV array interconnecting to the West Charlton substation via the 415L2, 13.2 kV feeder in Charlton, MA. | 2020-03-31 | Approved | 2019-12-10
NEP-19-G30-013 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Standard Solar Inc. - Orange Road Solar PV | Generator application from New England Power Company ("NEP"), on behalf of Standard Solar Inc., for the installation of a 4.980 MW solar PV array interconnecting to the Wendell Depot substation via the 705W4, 13.8 kV feeder in Orange, MA. | 2020-04-20 | Approved | 2019-12-10
NEP-19-G30-015 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Borrego Solar - Clark Street Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Borrego Solar, for the installation of a 4.990 MW solar PV array interconnecting to the Crystal Lake substation via the 607W1, 13.8 kV feeder in Gardner, MA. | 2020-06-03 | Approved | 2019-12-10
NEP-19-G30-016 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Zero Point Development - Wilson Road Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Zero Point Development, for the installation of a 2.000 MW solar PV array and battery interconnecting to the Meadow Street substation via the 552L1, 13.2 kV feeder in Spencer, MA. | 2020-02-13 | Approved | 2019-12-10
NEP-19-G30-017 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Syncarpha Solar LLC - Little Rest Road Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Syncarpha Solar LLC, for the installation of a 4.980 MW solar PV array and battery interconnecting to the Little Rest Road substation via the 516L2, 13.2 kV feeder in Warren, MA. | 2021-03-19 | Approved Withdrawn | 12/10/2019 11/18/2020
NEP-19-G30-018 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - BlueWave Solar - Palmer Street Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of BlueWave Solar, for the installation of a 4.980 MW solar PV array interconnecting to the Thorndike substation via the 523L1, 13.2 kV feeder in Palmer, MA. | 2020-05-27 | Approved | 2019-12-10
NEP-19-G30-019 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - BlueWave - Daniels Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of BlueWave Solar, for the installation of a 3.330 MW solar PV array interconnecting to the Walker Street substation via the 1015W2, 13.8 kV feeder in Clarksburg, MA. | 2020-09-07 | Approved Withdrawn | 12/10/2019 6/16/2020
NEP-19-G30-020 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Syncarpha Solar LLC - Potato Hill Road Solar PV and Battery | Generator application from New England Power Company ("NEP"), on behalf of Syncarpha Westminster, LLC, for the installation of a 4.980 MW solar PV array and battery interconnecting to the East Westminster substation via the 609W1, 13.8 kV feeder in Westminster, MA. | 2021-01-19 | Approved | 2019-12-10
NEP-19-G30-021 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Zero Point Development - Ravine Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Zero Point Development, for the installation of a 2.000 MW solar PV array interconnecting to the Barre substation via the 604W3, 13.8 kV feeder in New Braintree, MA. | 2021-10-29 | Approved Withdrawn | 12/10/2019 4/13/2021
NEP-19-G30-022 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Zero Point Development - Dresser Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Zero Point Development, for the installation of a 1.500 MW solar PV array interconnecting to the Snow Street substation via the 413L1, 13.2 kV feeder in Southbridge, MA. | 2021-05-03 | Approved | 2019-12-10
NEP-19-G30-023 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Seaboard Solar - Beaman Road Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Seaboard Solar, for the installation of an 8.820 MW solar PV array and battery interconnecting to the Ware substation via the 501L1, 13.2 kV feeder in West Brookfield, MA. | 2021-06-15 | Approved | 2019-12-10
NEP-19-G30-024 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Clearway Energy Group - Belchertown Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Clearway Energy Group, for the installation of a 1.320 MW solar PV array interconnecting to the Ware substation via the 501L2, 13.2 kV feeder in Ware, MA. | 2020-01-25 | Approved | 2019-12-10
NEP-19-G30-025 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - BlueWave Solar - Estabrook Street Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of BlueWave Solar, for the installation of a 1.760 MW solar PV array and battery interconnecting to the Millbury substation via the 304W1, 13.8 kV feeder in Grafton, MA. | 2020-08-07 | Approved | 2019-12-10
NEP-19-G30-026 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Zero Point Development - Dresser Hill Road Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Zero Point Development, for the installation of a 2.000 MW solar PV array and battery interconnecting to the Snow Street substation via the 413L3, 13.2 kV feeder in Southbridge, MA. | 2021-05-03 | Approved | 2019-12-10
NEP-19-G30-027 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - BlueWave Solar - Shore Road Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of BlueWave Solar, for the installation of a 4.980 MW solar PV array and battery interconnecting to the Meadow Street substation via the 552L3, 13.2 kV feeder in North Brookfield, MA. | 2020-02-25 | Approved | 2019-12-10
NEP-19-G30-028 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - BlueWave Solar - Hospital Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of BlueWave Solar, for the installation of a 2.490 MW solar PV array interconnecting to the Palmer substation via the 507, 23 kV feeder in Monson, MA. | 2021-02-26 | Approved Withdrawn | 12/10/2019 2/19/2020
NEP-19-G30-029 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Borrego Solar - Breckenridge Street Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Borrego Solar, for the installation of a 4.950 MW solar PV array and battery interconnecting to the Palmer substation via the 503L1, 13.2 kV feeder in Palmer, MA. | 2019-11-25 | Approved | 2019-12-10
NEP-19-G30-030 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Dynamic Energy - Palmer Road PV Solar Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Dynamic Energy, for the installation of a 3.000 MW solar PV array and battery interconnecting to the Ware substation via the 501L2, 13.2 kV feeder in Ware, MA. | 2020-12-31 | Approved | 2019-12-10
NEP-19-G30-031 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Dynamic Energy - Adams Street Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Dynamic Energy, for the installation of a 4.980 MW solar PV array and battery interconnecting to the Meadow Street substation via the 552L3, 13.2 kV feeder in East Brookfield, MA. | 2020-04-30 | Approved Withdrawn | 12/10/2019 10/20/2020
NEP-19-G30-032 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Sunpin Solar Development LLC - Brookfield Road Solar PV Array | nerator application from New England Power Company ("NEP"), on behalf of Sunpin Solar Development LLC, for the installation of a 2.200 MW solar PV array interconnecting to the Meadow Street substation via the 552L1, 13.2 kV feeder in Spencer, MA. | 2020-05-16 | Approved | 2019-12-10
NEP-19-G30-033 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - AES Distributed Energy, Inc. - Orange Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of AES Distributed Energy, Inc., for the installation of a 9.990 MW solar PV array interconnecting to the Wendell Depot substation via the 705W3, 13.8 kV feeder in Orange, MA. | 2020-02-10 | Approved | 2019-12-10
NEP-19-G30-034 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - AES Distributed Energy, Inc. - Ward Street Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of AES Distributed Energy, Inc., for the installation of a 5.800 MW solar PV array and battery interconnecting to the Lashaway substation via the 0012, 23 kV feeder in North Brookfield, MA. | 2020-02-25 | Approved | 2019-12-10
NEP-19-G30-035 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Zero Point Development - Coy Hill Road Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Zero Point Development, for the installation of a 4.950 MW solar PV array and battery interconnecting to the Little Rest Road substation via the 516L3, 13.2 kV feeder in Warren, MA. | 2020-02-15 | Approved | 2019-12-10
NEP-19-G30-036 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - BlueWave Solar - Sykes Street Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of BlueWave Solar, for the installation of a 4.980 MW solar PV array interconnecting to the Palmer substation via the 504, 23 kV feeder in Palmer, MA. | 2020-01-22 | Approved | 2019-12-10
NEP-19-G30-038 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Zero Point Development - Reed Street Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Zero Point Development, for the installation of a 3.500 MW solar PV array interconnecting to the Little Rest Road substation via the 516L3, 13.2 kV feeder in Warren, MA. | 2020-06-10 | Approved Withdrawn | 12/10/2019 2/19/2020
NEP-19-G30-039 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - BlueWave Solar - Gulf Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of BlueWave Solar, for the installation of a 4.980 MW solar PV array interconnecting to the Belchertown substation via the 509L2, 13.2 kV feeder in Belchertown, MA. | 2020-12-21 | Approved Withdrawn | 12/10/2019 5/18/2021
NEP-19-G30-040 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Energy Development Group - Winchendon Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Energy Development Group, for the installation of a 2.496 MW solar PV array interconnecting to the Royalston substation via the 701J1, 4.16 kV feeder in Royalston, MA. | 2020-06-20 | Approved Withdrawn | 12/10/2019 3/16/2021
NEP-19-G30-041 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Sunpin Solar Development LLC - Sturbridge Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Sunpin Solar Development LLC, for the installation of a 4.990 MW solar PV array interconnecting to the West Charlton substation via the 415L1, 13.2 kV feeder in Charlton, MA. | 2020-11-22 | Approved | 2019-12-10
NEP-19-G30-042 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Sunraise Development LLC - Grove Street Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Sunraise Development LLC, for the installation of a 4.990 MW solar PV array and battery interconnecting to the Adams substation via the 1021W2, 13.8 kV feeder in Adams, MA. | 2020-11-09 | Approved | 2019-12-10
NEP-19-G30-043 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - AMP Solar Development - Three Rivers Road Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of AMP Solar Development, for the installation of a 4.000 MW solar PV array and battery interconnecting to the Thorndike substation via the 523L1, 13.2 kV feeder in Wilbraham, MA. | 2020-08-14 | Approved | 2019-12-10
NEP-19-G30-044 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Clean Energy Collective - Ingalls Road Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Clean Energy Collective, for the installation of a 4.375 MW solar PV array and battery interconnecting to the Adams substation via the 1021W2, 13.8 kV feeder in Cheshire, MA. | 2021-08-18 | Approved Withdrawn | 12/10/2019 11/18/2020
NEP-19-G30-045 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Energy Development Group - Brookfield Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Energy Development Group, for the installation of a 2.640 MW solar PV array interconnecting to the West Charlton substation via the 415L3, 13.2 kV feeder in Charlton, MA. | 2021-02-26 | Approved | 2019-12-10
NEP-19-G30-046 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Tangent Energy Solutions Inc. - Overlook Road PV Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Tangent Energy Solutions Inc., for the installation of a 4.980 MW solar PV array interconnecting to the Ashburnham substation via the 610W3, 13.8 kV feeder in Westminster, MA. | 2021-03-05 | Approved | 2019-12-10
NEP-19-G30-047 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - SWEB Development USA, LLC - Mitchell Hill Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of SWEB Development USA, LLC, for the installation of a 3.375 MW solar PV array interconnecting to the Lashaway substation via the 525L2, 13.2 kV feeder in Brookfield, MA. | 2021-04-12 | Approved | 2019-12-10
NEP-19-G30-048 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Borrego Solar - Somers Road Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Borrego Solar, for the installation of a 3.875 MW solar PV array and battery interconnecting to the West Hampden substation via the 139L1, 13.2 kV feeder in Hampden, MA. | 2020-03-03 | Approved | 2019-12-10
NEP-19-G30-049 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Nextera Energy Resources - Dunhamtown Palmer Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Nextera Energy Resources, for the installation of a 3.000 MW solar PV array interconnecting to the Palmer substation via the 503L4, 13.2 kV feeder in Brimfield, MA. | 2021-06-15 | Approved Withdrawn | 12/10/2019 11/18/2020
NEP-19-G30-050 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Clearway Energy Group - Dresser Hill Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Clearway Energy Group, for the installation of a 3.744 MW solar PV array interconnecting to the Snow Street substation via the 413L3, 13.2 kV feeder in Southbridge, MA. | 2020-04-20 | Approved | 2019-12-10
NEP-19-G30-051 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Syncarpha Solar LLC - Main Street Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Syncarpha Solar LLC, for the installation of a 4.980 MW solar PV array and battery interconnecting to the Millbury substation via the 304W5, 13.8 kV feeder in Millbury, MA. | 2021-03-12 | Approved | 2019-12-10
NEP-19-G30-052 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Zero Point Development - Doric Road Solar PV PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Zero Point Development, for the installation of a 4.950 MW solar PV array and battery interconnecting to the West Charlton substation via the 415L1, 13.2 kV feeder in Charlton, MA. | 2022-04-22 | Approved Withdrawn | 12/10/2019 8/18/2020
NEP-19-G30-053 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Clean Energy Collective - Thresher Road Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Clean Energy Collective, for the installation of a 2.500 MW solar PV array and battery interconnecting to the West Hampden substation via the 139L1, 13.2 kV feeder in Hampden, MA. | 2020-09-30 | Approved Withdrawn | 12/10/2019 8/18/2020
NEP-19-G30-054 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Zero Point Development - Dresser Hill Road Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Zero Point Development, for the installation of a 7.750 MW solar PV array and battery interconnecting to the Snow Street substation via the 413L3, 13.2 kV feeder in Southbridge, MA. | 2021-11-19 | Approved | 2019-12-10
NEP-19-G30-055 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Zero Point Development - Spencer Road Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Zero Point Development, for the installation of a 2.000 MW solar PV array and battery interconnecting to the Treasure Valley substation via the 55K11,24.9 kV feeder in Spencer, MA. | 2020-07-15 | Approved Withdrawn | 12/10/2019 2/16/2021
NEP-19-G30-056 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Ameresco Solar - Cross Road Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Ameresco Solar, for the installation of a 3.818 MW solar PV array and battery interconnecting to the West Hampden substation via the 139L1, 13.2 kV feeder in Hampden, MA. | 2021-05-07 | Approved | 2019-12-10
NEP-19-G30-057 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Allco Renewable Energy Ltd - Spring Street Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Allco Renewable Energy Ltd, for the installation of a 3.900 MW solar PV array interconnecting to the East Winchendon substation via the 612W3, 13.8 kV feeder in Winchendon, MA. | 2021-03-19 | Approved | 2019-12-10
NEP-19-G30-058 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Zero Point Development - Old Union Turnpike Solar PV Array and Battery | Generator application from New England Power Company ("NEP"), on behalf of Zero Point Development, for the installation of a 4.950 MW solar PV array and battery interconnecting to the Litchfield substation via the 207W3, 13.8 kV feeder in Lancaster, MA. | 2021-01-06 | Approved | 2019-12-10
NEP-19-G30-059 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project - Next Grid Inc. - Colton Road Solar PV Array | Generator application from New England Power Company ("NEP"), on behalf of Next Grid Inc., for the installation of a 3.400 MW solar PV array interconnecting to the Millbury substation via the 304W4, 13.8 kV feeder in Millbury, MA. | 2021-06-15 | Approved | 2019-12-10
NEP-19-X01 | 2019-11-01 | Western Massachusetts Distributed Energy Resource Additions Cluster (Group 1) Generation and Transmission Project | Transmission application from New England Power Company ("NEP"), on behalf of Syncarpha Westminster, LLC, for the installation of Direct Transfer Trip (DTT) protection from Pratts Junction to Crystal Lake 69 kV substation that trips the entire B-2S line following the B2 breaker open contingency at Pratts Junction. This application is associated with NEP-19-G30-020. | 2021-05-31 | Approved Withdrawn | 12/10/2019 6/15/2021
FPS-19-G05 | 2019-11-05 | FPS Peterborough Solar Project | Generator application from Freepoint Solar LLC (“FPS”) for the installation 20 MW solar array in Peterborough, NH, to be interconnect with a line tap on the Eversource 34.5 kV Line 313 between South Peterborough and Monadnock substation. The project will consist of nine 2.5 MVA solar inverters. | 12/2022 | Approved Withdrawn | 12/13/2019 1/26/2021
FPS-19-G06 | 2019-11-06 | FPS Thornton Solar Project | Generator application from Freepoint Solar LLC (“FPS”) for the installation 20 MW solar array in Thornton, NH, to be interconnect with a line tap on the Eversource NH 34.5 kV Line 342B 4.5 miles north of the Beebe River substation. The project will consist of nine 2.5 MVA solar inverters. | 12/2022 | Approved Withdrawn | 12/13/2019 1/26/2021
NEP-19-GNF94 | 2019-11-01 | Energy Development Partners Sanford Road Westport Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Energy Development Partners for the installation of 3.3 MW solar PV and battery in Westport, MA and interconnecting to the Bates Street Substation via the 115W52 13.8 kV feeder. | 2020-01-01 | Notification Withdrawn | 12/13/2019 1/20/2021
NEP-19-GNF193 | 2019-11-01 | Kearsarge Solar Sohier Road Beverly Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Kearsarge Solar, LLC for the installation of 3.886 MW solar PV and battery in Beverly, MA and interconnecting to the Beverly Substation via the 12L4 13.2 kV feeder. | 2021-10-28 | Notification | 2019-12-13
NEP-19-GNF127 | 2019-11-01 | Syncarpha Solar Providence Road Northbridge Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Syncarpha Solar LLC for the installation of 4.98 MW solar PV and battery in Northbridge, MA and interconnecting to the Uxbridge Substation via the 321W5 13.8 kV feeder. | 2020-04-02 | Notification | 2019-12-13
NEP-19-GNF175 | 2019-11-01 | ECA South One Mansfield Avenue Norton Solar | Generator notification from New England Power Company ("NEP") on behalf of ECA South One, LLC for the installation of 3.33 MW solar PV in Norton, MA and interconnecting to the Chartley Pond Substation via the 4L2 13.2 kV feeder. | 2020-03-15 | Notification | 2019-12-13
NEP-19-GNF173 | 2019-11-01 | Next Grid Partners Plain Street Norton Solar | Generator notification from New England Power Company ("NEP") on behalf of Next Grid Partners, LLC for the installation of 1.5 MW solar PV in Norton, MA and interconnecting to the Chartley Pond Substation via the 4L1 13.2 kV feeder. | 2020-07-07 | Notification | 2019-12-13
NEP-19-GNF92 | 2019-11-01 | Omni Navitas Holdings Spring Street Franklin Solar | Generator notification from New England Power Company ("NEP") on behalf of Omni Navitas Holdings, LLC for the installation of 1.98 MW solar PV in Franklin, MA and interconnecting to the Union Street Substation via the 348W7 13.8 kV feeder. | 2020-07-31 | Notification Withdrawn | 12/13/2019 6/16/2020
NEP-19-T09 | 2019-10-30 | Static Synchronous Series Compensator (SSSC) at Fitch Road Substation on W-23 Line Project | Transmission application from New England Power Company (“NEP”) for the installation of a power flow control device, which is a modular, Static Synchronous Series Compensator (SSSC), to inject a leading or lagging voltage in quadrature with the line current, providing the functionality of a series capacitor or a series reactor respectively on 69 kV W-23 circuit at the Fitch Road substation in Clinton, MA. The device operates in conjunction with a module which provides rapid protection during fault conditions for the SSSC and enables operators to manually bypass the SSSC under normal operation. | 3/2020 | Approved | 2019-12-10
ES-19-G101 | 2019-10-24 | Allco Renewable Energy Voluntown Road Griswold Solar | Generator notification from Eversource Energy ("ES") on behalf of Allco Renewable Energy for the installation of 3.996 MW solar PV in Griswold, CT and interconnecting to the Frybrook Substation via the 13B25 115 kV feeder. | 2019-11-12 | Notification | 2019-12-13
VELCO-19-GNF02 | 2019-11-04 | Wallingford Solar Creek Road Wallingford Solar | Generator notification from VELCO on behalf of Wallingford Solar for the installation of 2.2 MW solar PV in Wallingford, VT and interconnecting to the Wallingford Substation via the WF-G23 12.47 kV circuit. | 2019-12-13 | Notification | 2019-12-13
NEP-19-GNF195 | 2019-11-01 | Green Development Fields Point Drive Providence Wind | Generator notification from New England Power Company ("NEP") on behalf of Green Development for the installation of 1.5 MW wind facility in Providence, RI and interconnecting to the Point Street Substation via the 76F7 12.47 kV feeder. | 2020-12-30 | Notification | 2019-12-13
NEP-19-GNF194 | 2019-11-01 | Green Development Harborside Boulevard Providence Wind | Generator notification from New England Power Company ("NEP") on behalf of Green Development for the installation of 3.0 MW wind facility in Providence, RI and interconnecting to the Point Street Substation via the 76F7 12.47 kV feeder. | 2020-12-30 | Notification | 2019-12-13
NEP-19-GNF203 | 2019-11-01 | Invest Green Narragansett Park Drive Pawtucket Solar | Generator notification from New England Power Company ("NEP") on behalf of Invest Green for the installation of 1.03 MW solar PV in Pawtucket, RI and interconnecting to the Pawtucket Substation via the 107W53 13.8 kV feeder. | 2020-08-07 | Notification | 2019-12-13
NEP-19-GNF109 | 2019-11-01 | Ameresco Solar Manville Hill Road Cumberland Solar | Generator notification from New England Power Company ("NEP") on behalf of Ameresco Solar for the installation of 4.482 MW solar PV in Cumberland, RI and interconnecting to the Staples Substation via the 112W41 13.8 kV feeder. | 2020-04-03 | Notification | 2019-12-13
NEP-19-GNF105 | 2019-11-01 | Ameresco Solar Crandall Road Tiverton Solar | Generator notification from New England Power Company ("NEP") on behalf of Ameresco Solar for the installation of 1.66 MW solar PV in Tiverton, RI and interconnecting to the Tiverton Substation via the 33F4 12.47 kV feeder. | 2020-02-08 | Notification | 2019-12-13
NEP-19-GNF116 | 2019-11-01 | Ameresco Solar Crandall Road Tiverton 2 | Generator notification from New England Power Company ("NEP") on behalf of Ameresco Solar for the installation of 1.826 MW solar PV in Tiverton, RI and interconnecting to the Tiverton Substation via the 33F4 12.47 kV feeder. | 2020-04-30 | Notification | 2019-12-13
NEP-19-GNF74 | 2019-11-01 | Melville Solar Power Davis Street Portsmouth Solar | Generator notification from New England Power Company ("NEP") on behalf of Melville Solar Power for the installation of 3.00 MW solar PV in Portsmouth, RI and interconnecting to the Dexter Substation via the 36W44 13.8 kV feeder. | 2020-03-31 | Notification | 2019-12-13
NEP-19-GNF69 | 2019-11-01 | Heartwood Group Maine Road Tiverton Solar | Generator notification from New England Power Company ("NEP") on behalf of Heartwood Group Inc. for the installation of 2.44 MW solar PV in Tiverton, RI and interconnecting to the Tiverton Substation via the 33F3 12.47 kV feeder. | 2020-02-20 | Notification | 2019-12-13
NEP-19-GNF71 | 2019-11-01 | Green Development Birch Swamp Road Warren Solar | Generator notification from New England Power Company ("NEP") on behalf of Green Development for the installation of 1.60 MW solar PV in Warren, RI and interconnecting to the Warren Substation via the 5F2 12.47 kV feeder. | 2020-03-30 | Notification | 2019-12-13
NEP-19-GNF46 | 2019-11-01 | Energy Development Partners Touisset Road Warren Solar | Generator notification from New England Power Company ("NEP") on behalf of Energy Development Partners for the installation of 3.75 MW solar PV in Warren, RI and interconnecting to the Warren Substation via the 5F2 12.47 kV feeder. | 2020-06-22 | Notification | 2019-12-13
ES-19-G102 | 2019-11-05 | Old Middleboro Road Rochester Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Old Middleboro Road Solar for the installation of 4.975 MW solar PV and battery in Rochester, MA and interconnecting to the Rochester Substation via the 703 13.2kV feeder. | 2020-12-31 | Notification | 2019-12-13
ES-19-G71 | 2019-10-30 | BE RE Ring Road Plympton Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of BE RE LLC for the installation of 4.999 MW solar PV and battery in Plympton, MA and interconnecting to the Kingston Substation via the 3-15-15 23 kV feeder. | 2020-09-01 | Notification | 2019-12-13
ES-19-G94 | 2019-10-17 | ECA Solar South Gages Way Dennis Solar | Generator notification from Eversource Energy ("ES") on behalf of ECA Solar for the installation of 4.95 MW solar PV in Dennis, MA and interconnecting to the Harwich Substation via the 4-92B-92B 23 kV feeder. | 2020-06-01 | Notification Withdrawn | 12/13/2019 6/18/2024
CMP-19-G04 | 2019-11-11 | Hep Energy Fuller Corner Road Hartland Solar | Generator notification from Central Maine Power Company (“CMP”) on behalf of Hep Energy USA Project Development, LLC for the installation of 4.0 MW solar PV in Hartland, ME and interconnecting to the Hartland Substation via the 824D2 12.47 kV circuit. | 2020-10-15 | Notification | 2019-12-13
CMP-19-G06 | 2019-11-11 | Hep Energy Chesley Drive Waterville Solar | Generator notification from Central Maine Power Company (“CMP”) on behalf of Hep Energy USA Project Development, LLC for the installation of 4.92 MW solar PV in Waterville, ME and interconnecting to the South Waterville Substation via the 855D2 12.47 kV circuit. | 2020-10-15 | Notification | 2019-12-13
CMP-19-G08 | 2019-11-11 | Hep Energy Albion Road Unity Solar | Generator notification from Central Maine Power Company (“CMP”) on behalf of Hep Energy USA Project Development, LLC for the installation of 4.98 MW solar PV in Unity, ME and interconnecting to the South Unity Substation via the 860D1 12.47 kV circuit. | 2020-12-15 | Notification | 2019-12-13
ES-19-G93 | 2019-10-28 | Acton Water Solar Lawsbrook Street Action Solar | Generator notification from Eversource Energy ("ES") on behalf of Acton Water Solar for the installation of 3.04 MW solar PV in Acton, MA and interconnecting to the Maynard Substation via the 416-H8 13.8 kV feeder. | 2020-06-30 | Notification | 2019-12-13
CMP-14-T01 Rev.1 | 2019-11-08 | County Road Substation Rev.1 | Transmission notification from Central Maine Power Company (“CMP”). The original proposed topology associated with the County Road Substation PPA (CMP-14-T01) included construction of 6.5 miles of new 115 kV (1192 kcmil 45/7 ACSR) conductor from the Section 241A tap point (Structure 91) to the new County Road Substation. Due to real estate restrictions on the northern side of Section 241A tap point uncovered during detailed engineering, the 1192 kcmil 45/7 ACSR conductor will be tied into the County Road to Heywood Road segment instead of tying into the line segment from County Road to Lakewood as originally planned. | 5/2020 | Notification | 2019-12-10
ES-19-T33 | 2019-11-08 | Replacement of 1608-2 Line 115 kV Underground Cable | Transmission notification from Eversource Energy ("ES") for the replacement of the 115 kV underground cable section on Line 1608-2. The section is in Norwalk, CT from the Norwalk Harbor Substation to Ely Avenue Junction. The Project is needed to address asset condition and system reliability issues. The section is 1.48 miles and the replacement cable will be 2500 kcmil HPFF. | 2019-09-08 | Notification | 2019-12-10
ES-19-T34 | 2019-11-08 | Replacement of 1880-1 Line 115 kV Underground Cable Section | Transmission notification from Eversource Energy ("ES") for the replacement of a section of the 115 kV underground cable on Line 1880-1. The section is in Norwalk, CT from the Manhole #14 (near Norwalk Harbor Substation) to Ely Avenue Junction. The Project is needed to address asset condition and system reliability issues. The section is 0.91 miles and the replacement cable will be 2500 kcmil HPFF. | 2019-02-01 | Notification | 2019-12-10
NEM-19-G07 | 2019-11-01 | Lone Pine Solar Generation and Transmission Project | Generator application from NextEra Energy Resources (“NEM”) for the Lone Pine Solar Generator Project for the installation of a 150 MW solar array in York County Maine and interconnecting to the 3183 345 kV Line 27.7 miles from the Buxton Substation. | 2022-12-31 | Approved Withdrawn | 12/13/2019 8/12/2021
NEM-19-T07 | 2019-11-01 | Lone Pine Solar Generation and Transmission Project | Transmission application from NextEra Energy Resources (“NEM”) for the installation of a station transformer at the Lone Pine Collector Substation. | 2022-12-01 | Approved | 2019-12-13
CMP-19-T02 | 2019-11-01 | Lone Pine Solar Generation and Transmission Project | Transmission application from Central Maine Power Company (“CMP”) for the construction of a new three-breaker 345 kV ring bus configured substation to accommodate the interconnection of the Lone Pine Solar project on the existing Section 391 between Buxton Substation and Scobie Pond Substation. | 2022-12-31 | Approved | 2019-12-13
ES-19-G22 | 2019-10-10 | SunRaise Development Lake Street Plympton Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of SunRaise Development for the installation of 4.998 MW solar PV and battery in Plympton, MA and interconnecting to the Kingston Substation via the 3-15-906 23 kV feeder. | 2020-12-01 | Notification | 2019-11-12
ES-19-G82 | 2019-10-01 | Borrego Solar Division Road Westport Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Borrego Solar for the installation of 3.0 MW solar PV and battery in Westport, MA and interconnecting to the Fisher Road Substation via the 2-523-523 13.2 kV feeder. | 2021-01-27 | Notification Withdrawn | 11/12/2019 3/14/2023
ES-19-G37 | 2019-10-01 | Borrego Solar Blacksmith Shop Road Falmouth Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Borrego Solar for the installation of 4.95 MW solar PV and battery in Falmouth, MA and interconnecting to the Falmouth Substation via the 4-98A-98A 23 kV feeder. | 2020-08-12 | Notification | 2019-11-12
ES-19-G34 | 2019-10-01 | Borrego/510 PV Project Development Brook Street Plympton Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Borrego/510 PV Project Development for the installation of 3.0 MW solar PV and battery in Plympton, MA and interconnecting to the Brook Street Substation via the 3-51-51 23 kV feeder. | 2019-10-31 | Notification | 2019-11-12
ES-19-G91 | 2019-10-08 | Lumens Holdings South River Street Marshfield Solar | Generator notification from Eversource Energy ("ES") on behalf of Lumens Holdings for the installation of 2.112 MW solar PV in Marshfield, MA and interconnecting to the Marshfield Substation via the 3-24A-24A 23 kV feeder. | 2020-03-01 | Notification | 2019-11-12
ES-19-G27 | 2019-10-08 | BE RE Tremont Street Carver Solar | Generator notification from Eversource Energy ("ES") on behalf of BE RC LLC for the installation of 2.0 MW MW solar PV in Carver, MA and interconnecting to the Tremont Street Substation via the 3-81-81 23 kV feeder. | 2019-10-31 | Notification | 2019-11-12
ES-19-G90 | 2019-10-07 | Connecticut College Reservoir Street New London Fuel Cell | Generator notification from Eversource Energy ("ES") on behalf of Connecticut College for the installation of a 1.26 MW fuel cell in New London, CT and interconnecting to the Williams Street Substation via the 9L09 13.2 kV feeder. | 10/2019 | Notification | 2019-11-12
ES-19-G86 | 2019-10-07 | Verogy East Street Southington Solar | Generator notification from Eversource Energy ("ES") on behalf of Verogy for the installation of 4.0 MW solar PV in Southington, CT and interconnecting to the Southington Substation via the 4C19 13.8 kV feeder. | 2020-12-31 | Notification | 2019-11-12
ES-19-G88 | 2019-10-07 | Verogy East Road East Windsor Solar | Generator notification from Eversource Energy ("ES") on behalf of Verogy for the installation of 4.0 MW solar PV in East Windsor, CT and interconnecting to the Rockville Substation via the 14W7 13.8 kV feeder. | 2020-12-31 | Notification | 2019-11-12
ES-19-G87 | 2019-10-08 | Lodestar Energy Sand Road Canaan Solar | Generator notification from Eversource Energy ("ES") on behalf of Lodestar Energy for the installation of 2.0 MW solar PV in Canaan, CT and interconnecting to the North Canaan Substation via the 5L02 13.2 kV feeder. | 7/31/201 | Notification | 2019-11-12
ES-19-G73 | 2019-10-03 | Greenskies Renewables Taugwonk Spur Road Stonington Solar | Generator notification from Eversource Energy ("ES") on behalf of Greenskies Renewables for the installation of 2.5 MW solar PV in Stonington, CT and interconnecting to the Mystic Substation via the 13K8 13.8 kV feeder. | 2022-06-30 | Notification | 2019-11-12
ES-19-G85 | 2019-10-08 | Connecticut State Colleges and Universities Cedar Street Newington Solar | Generator notification from Eversource Energy ("ES") on behalf of Connecticut State Colleges and Universities for the installation of 2.0 MW solar PV in Newington, CT and interconnecting to the East New Britain Substation via the 7L82 13.8 kV feeder. | 2021-04-02 | Notification Withdrawn | 11/12/2019 6/18/2024
ES-19-G46 | 2019-09-24 | Martha's Vineyard Oaks Bluffs Battery | Generator notification from Eversource Energy ("ES") for the installation of a 4.9 MW battery in Oaks Bluffs, MA and interconnecting to the Falmouth Substation via the 4-75-75 23 kV feeder. | 12/2020 | Notification | 2019-11-12
ES-19-G54 | 2019-10-01 | ECA SEMA CAN Draper Lane Canton Solar | Generator notification from Eversource Energy ("ES") on behalf of ECA SEMA CAN for the installation of 2.485 MW solar PV in Canton, MA and interconnecting to the Canton Substation via the 470-H6 14 kV feeder. | 10/2019 | Notification | 2019-11-12
VEC-19-G05 | 2019-09-16 | Jericho Gravel Ethan Allen Road Jericho Solar | Generator notification from Vermont Electric CoOp on behalf of Jericho Gravel for the installation of 1.5 MW solar PV in Jericho, VT and interconnecting to the VEC Substation via the 10-3A 12.47 kV feeder. | 2019-11-30 | Notification | 2019-11-12
VEC-19-G06 | 2019-09-16 | Jericho Landfill Browns Trace Road Jericho Solar | Generator notification from Vermont Electric CoOp on behalf of Jericho Landfill for the installation of 1.65 MW solar PV in Jericho, VT and interconnecting to the VEC Substation via the 08-1A 12.47 kV feeder. | 2019-11-30 | Notification | 2019-11-12
NEM-19-G06 | 2019-10-02 | Davenport Solar Generation Project | Generator application from NextEra Energy Resources (“NEM”) for the installation of a 15 MW inverter-based solar generation project to Green Mountain Power’s (“GMP’s”) 46 kV line between Florence and Middlebury substations, approximately four miles from the Florence Substation in Brandon, Vermont. | 2021-12-01 | Approved Withdrawn | 11/12/2019 6/14/2022
NEP-19-G21 | 2019-10-09 | Iron Mine Hill Road Solar Generation and Transmission Project | Generator application from New England Power Company (“NEP”) for the installation of 3.84 MW solar array connecting to the 34.5 kV distribution feeder from theproposed Iron Mine Hill Road Substation in North Smithfield, Rhode Island. | 2020-11-30 | Approved | 2019-11-12
NEP-19-G22 | 2019-10-09 | Iron Mine Hill Road Solar Generation and Transmission Project | Generator application from New England Power Company (“NEP”) for the installation of 4.608 MW solar array connecting to the 34.5 kV distribution feeder from the proposed Iron Mine Hill Road Substation in North Smithfield, Rhode Island. | 2020-11-30 | Approved | 2019-11-12
NEP-19-G23 | 2019-10-09 | Iron Mine Hill Road Solar Generation and Transmission Project | Generator application from New England Power Company (“NEP”) for the installation of 2.304 MW solar array connecting to the 34.5 kV distribution feeder from the proposed Iron Mine Hill Road Substation in North Smithfield, Rhode Island. | 2020-11-30 | Approved | 2019-11-12
NEP-19-G24 | 2019-10-09 | Iron Mine Hill Road Solar Generation and Transmission Project | Generator application from New England Power Company (“NEP”) for the installation of 6.912 MW solar array connecting to the 34.5 kV distribution feeder from the proposed Iron Mine Hill Road Substation in North Smithfield, Rhode Island. | 2020-11-30 | Approved | 2019-11-12
NEP-19-G25 | 2019-10-09 | Iron Mine Hill Road Solar Generation and Transmission Project | Generator application from New England Power Company (“NEP”) for the installation of 2.304 MW solar array connecting to the 34.5 kV distribution feeder from the proposed Iron Mine Hill Road Substation in North Smithfield, Rhode Island. | 2020-11-30 | Approved Withdrawn | 11/12/2019 5/18/2021
NEP-19-G26 | 2019-10-09 | Iron Mine Hill Road Solar Generation and Transmission Project | Generator application from New England Power Company (“NEP”) for the installation of 2.304 MW solar array connecting to the 34.5 kV distribution feeder from the proposed Iron Mine Hill Road Substation in North Smithfield, Rhode Island. | 2020-11-30 | Approved Withdrawn | 11/12/2019 5/18/2021
NEP-19-G27 | 2019-10-09 | Iron Mine Hill Road Solar Generation and Transmission Project | Generator application from New England Power Company (“NEP”) for the installation of 6.144 MW solar array connecting to the 34.5 kV distribution feeder from the proposed Iron Mine Hill Road Substation in North Smithfield, Rhode Island. | 2020-11-30 | Approved Withdrawn | 11/12/2019 5/18/2021
NEP-19-G28 | 2019-10-09 | Iron Mine Hill Road Solar Generation and Transmission Project | Generator application from New England Power Company (“NEP”) for the installation of 6.144 MW solar array connecting to the 34.5 kV distribution feeder from the proposed Iron Mine Hill Road Substation in North Smithfield, Rhode Island. | 2020-11-30 | Approved Withdrawn | 11/12/2019 5/18/2021
NEP-19-G29 | 2019-10-09 | Iron Mine Hill Road Solar Generation and Transmission Project | Generator application from New England Power Company (“NEP”) for the installation of 3.84 MW solar array connecting to the 34.5 kV distribution feeder from the proposed Iron Mine Hill Road Substation in North Smithfield, Rhode Island. | 2020-11-30 | Approved Withdrawn | 11/12/2019 5/18/2021
NEP-19-T08 | 2019-10-09 | Iron Mine Hill Road Solar Generation and Transmission Project | Transmission application from New England Power Company (“NEP”) for the construction of a new 115/34.5 kV Iron Mine Hill Road Substation connecting to the 115 kV H17 Line in North Smithfield, Rhode Island to interconnect the Iron Mine Hill Road Solar Project. | 2020-11-30 | Approved | 2019-11-12
NEP-19-G19 | 2019-10-08 | King Solar 1 & 2 Solar Generator Project | Generator application from New England Power Company (“NEP”) for the installation of 6.22 MW solar array connecting to the 26W1 13.8 kV distribution feeder from the Woonsocket Substation in Rhode Island. | 2020-10-30 | Approved | 2019-11-12
NEP-19-G20 | 2019-10-08 | King Solar 1 & 2 Solar Generator Project | Generator application from New England Power Company (“NEP”) for the installation of 6.22 MW solar array connecting to the 26W7 13.8 kV distribution feeder from the Woonsocket Substation in Rhode Island. | 2020-10-30 | Approved | 11/12/219
ES-19-T25 | 2019-09-13 | Upgrade Wellfleet Substation Transformer #1 | Transmission notification from Eversource Energy (“ES”) to upgrade transformer #1 from 16/21/26 MVA to 30/40/50 MVA at the Wellfleet Substation in Wellfleet, MA. | 2020-11-25 | Notification | 2019-11-05
ES-19-T26 | 2019-09-13 | Upgrade Wellfleet Substation Transformer #2 | Transmission notification from Eversource Energy (“ES”) to upgrade transformer #2 from 16/21/26 MVA to 30/40/50 MVA at the Wellfleet Substation in Wellfleet, MA. | 2020-04-29 | Notification | 2019-11-05
ES-19-T22 | 2019-09-27 | Putnam Station Transformer Addition | Transmission notification from Eversource Energy (“ES”) for the installation of a 4th 115/13/8 kV transformer at the Putnam Substation in Cambridge, MA. | 6/2020 | Notification | 2019-11-05
ES-19-T27 | 2019-10-04 | Scitico Substation Circuit Breaker and Transformer Addition | Transmission application from Eversource Energy (“ES”) for the addition of one new 62.5 MVA 115/23-kV distribution transformer, one 115-kV circuit breaker, and two circuit switchers at the existing Scitico 27H Substation in Enfield, Connecticut. The project is needed to address local load serving reliability and forecasted load increase at the Scitico Substation by 2021. | 2019-12-31 | Approved | 2019-11-05
ES-19-T31 | 2019-10-11 | Stepstone 35L-1X Transformer Re-Rate | Transmission notification from Eversource Energy (“ES”) to re-rate the existing Stepstone 35L-1X at the Stepstone 35L Substation, located in Guilford, Connecticut due to a change in Eversource’s transformer rating methodology. | 2019-12-31 | Notification | 2019-11-05
ES-19-T04 | 2019-09-25 | Andrew Square to Dewar Street Station 115 kV Cable installation Project | Transmission application from Eversource Energy (“ES”) for the installation of a new 2.2 mile 115 kV cable between Andrew Square Station #106 and Dewar Street Station #483. The Project includes the installation of two new 115 kV circuit breakers at Andrew Square Station and the installation of two new 115 kV circuit breakers at Dewar Street Station. | 12/2022 | Approved | 2019-11-05
NEP-19-GNF45 | 2019-09-11 | Founders Homestead Farm Portsmouth Solar | Generator notification from New England Power Company ("NEP") on behalf of Founders Homestead Farm for the installation of 4.5 MW solar PV in Portsmouth, RI and interconnecting to the Dexter 36 Substation via the 36W44 13.8 kV feeder. | 2019-07-29 | Notification | 2019-10-09
NEP-19-GNF57 | 2019-09-11 | Freepoint Solar Woodvile Road Richmond Solar | Generator notification from New England Power Company ("NEP") on behalf of Freepoint Solar for the installation of 4.5 MW solar PV in Richmond, RI and interconnecting to the Wood River Substation via the 85T1 34.5 kV feeder. | 2020-01-31 | Notification | 2019-10-09
NEP-19-GNF49 | 2019-09-11 | Ameresco Solar Hamilton Allenton Road North Kingstown Solar | Generator notification from New England Power Company ("NEP") on behalf of Ameresco Solar for the installation of 1.9 MW solar PV in North Kingstown, RI and interconnecting to the Tower Hill Substation via the 88F5 12.47 kV feeder. | 2019-10-01 | Notification | 2019-10-09
NEP-19-GNF48 | 2019-09-11 | Kearsarge Solar Kenyon Woods Way Wakefield Solar | Generator notification from New England Power Company ("NEP") on behalf of Kearsarge Solar for the installation of 3.168 MW solar PV in Wakefield, RI and interconnecting to the Kenyon Substation via the 68F2 12.47 kV feeder. | 2019-09-19 | Notification | 2019-10-09
NEP-19-GNF190 | 2019-09-11 | Nugen Capital Briggs Drive East Greenwich Solar | Generator notification from New England Power Company ("NEP") on behalf of Nugen Capital for the installation of 4.98 MW solar PV in East Greenwich, RI and interconnecting to the Old Baptist Road Substation via the 46F1 12.47 kV feeder. | 2019-12-01 | Notification | 2019-10-09
NEP-19-GNF58 | 2019-09-11 | Devonshire Energy Salem Street Smithfield Solar | Generator notification from New England Power Company ("NEP") on behalf of Devonshire Energy for the installation of 2.64 MW solar PV in Smithfield, RI and interconnecting to the Farnum Pike Substation via the 23F5 12.47 kV feeder. | 2019-12-18 | Notification | 2019-10-09
NEP-19-GNF42 | 2019-09-11 | NextPath Fiance Hartfod Pike Foster Solar | Generator notification from New England Power Company ("NEP") on behalf of NextPath Finance for the installation of 2.59 MW solar PV in Foster, RI and interconnecting to the Chopmist Substation via the 34F 12.47 kV feeder. | 2019-12-16 | Notification | 2019-10-09
NEP-19-GNF43 | 2019-09-11 | NextPath Fiance Hartfod Pike Foster Solar II | Generator notification from New England Power Company ("NEP") on behalf of NextPath Finance for the installation of 2.0 MW solar PV in Foster, RI and interconnecting to the Chopmist Substation via the 34F 12.47 kV feeder. | 2020-01-10 | Notification | 2019-10-09
NEP-19-GNF77 | 2019-09-11 | ISM Solar Development Cowesett Road Warwick Solar II | Generator notification from New England Power Company ("NEP") on behalf of ISM Solar Development for the installation of 4.78 MW solar PV in Warwick, RI and interconnecting to the Kent County Substation via the 22F4 12.47 kV feeder. | 2020-06-01 | Notification | 2019-10-09
NEP-19-GNF189 | 2019-09-11 | ISM Solar Development Cowesett Road Warwick Solar | Generator notification from New England Power Company ("NEP") on behalf of ISM Solar Development for the installation of 4.78 MW solar PV in Warwick, RI and interconnecting to the Kent County Substation via the 22F3 12.47 kV feeder. | 2019-10-02 | Notification | 2019-10-09
NEP-19-GNF186 | 2019-09-11 | GSSP Commerce Way Attleboro Solar | Generator notification from New England Power Company ("NEP") on behalf of GSSP for the installation of 1.5 MW solar PV in Attleboro, MA and interconnecting to the Reed Street Substation via the 9L2 13.2 kV feeder. | 2020-04-06 | Notification | 2019-10-09
NEP-19-GNF185 | 2019-09-11 | AMP Solar Wallum Lake Road Douglas Solar | Generator notification from New England Power Company ("NEP") on behalf of AMP Solar for the installation of 4.99 MW solar PV in Douglas, MA and interconnecting to the Whitins Pond Substation via the 320W2 13.8 kV feeder. | 2020-03-23 | Notification | 2019-10-09
NEP-19-GNF149 | 2019-09-11 | Beaumont Solar Brockton Centre Street Solar | Generator notification from New England Power Company ("NEP") on behalf of Beaumont Solar for the installation of 1.38 MW solar PV in Brockton, MA and interconnecting to the Dupont Substation via the 91W46 13.8 kV feeder. | 2020-06-01 | Notification | 2019-10-09
NEP-19-GNF86 | 2019-09-11 | Forefront Power Williams Street Dighton Solar | Generator notification from New England Power Company ("NEP") on behalf of Forefront Power for the installation of 3.75 MW solar PV in Dighton, MA and interconnecting to the East Dighton Substation via the 19W74 13.8 kV feeder. | 2019-09-19 | Notification | 2019-10-09
ES-19-G66 | 2019-09-04 | Sales Avenue Solar Putnam Solar | Generator notification from Eversource Energy ("ES") on behalf of Sales Avenue Solar for the installation of 1.98 MW solar PV in Putnam, CT and interconnecting to the Tracy Substation via the 14M28 23 kV feeder. | 2019-07-01 | Notification | 2019-10-09
ES-19-G50 | 2019-09-05 | NE Solar Garden Route 11B Laconia Solar | Generator notification from Eversource Energy ("ES") on behalf of NE Solar Garden for the installation of 4.0 MW solar PV in Laconia, NH and interconnecting to the Laconia Substation via the 310 34.5 kV feeder. | 2019-12-31 | Notification Withdrawn | 10/9/2019 2/16/2021
ES-19-G58 | 2019-09-28 | GSSG New Hampshire Shannon Road Franklin Solar | Generator notification from Eversource Energy ("ES") on behalf of GSSG New Hampshire for the installation of 3.0 MW solar PV in Franklin, NH and interconnecting to the Daniel Substation via the 337X6. | 2019-12-31 | Notification | 2019-10-09
ES-19-G65 | 2019-09-04 | Ecos Energy Bilton Road Somers Solar | Generator notification from Eversource Energy ("ES") on behalf of Ecos Energy for the installation of 2.99 MW solar PV in Somers, CT and interconnecting to the Scitico Substation via the 27H7 23 kV feeder. | 2019-09-11 | Notification | 2019-10-09
ES-19-G53 | 2019-09-04 | Borrego Solar Maple Street Bellingham Solar | Generator notification from Eversource Energy ("ES") on behalf of Borrego Solar for the installation of 4.0 solar PV in Bellingham, MA and interconnecting to the Medway Substation via the 65H4 14 kV feeder. | 2019-08-27 | Notification | 2019-10-09
NEP-16-G16 | 2019-09-11 | Solar Breaker Tank Farm Project | Generator application from New England Power Company (“NEP”) on behalf of Narragansett Electric for the Solar Breaker Tank Farm #4 project for the installation of a 9.9 MW solar array and interconnecting between the Jepson and Gate substation via the 37K33 23 kV feeder in Middletown, RI. | 6/2020 | Approved | 2019-10-09
NEP-16-G17 | 2019-09-11 | Solar Breaker Tank Farm Project | Generator application from New England Power Company (“NEP”) on behalf of Narragansett Electric for the Solar Breaker Tank Farm #5 project for the installation of a 9.9 MW solar array and interconnecting between the Jepson and Gate substation via the 37K33 23 kV feeder in Middletown, RI. | 6/2020 | Approved | 2019-10-09
NEP-16-G18 | 2019-09-11 | Solar Breaker Tank Farm Project | Generator application from New England Power Company (“NEP”) on behalf of Narragansett Electric for the Solar Breaker Landfill Solar project for the installation of a 1.0 MW solar array and interconnecting between the Jepson and Gate substation via the 37K33 23 kV feeder in Middletown, RI. | 6/2020 | Approved | 2019-10-09
NEP-19-G15 | 2019-09-10 | Navy Generator CHP Project | Generator application from New England Power Company (“NEP”) on behalf of Narragansett Electric for the Navy Generator CHP project for the installation of a 7.74 MW gas turbine combined heat and power and interconnecting to the Navy 69/13.8 kV substation in Middletown, RI. | 6/2021 | Approved | 2019-10-09
CED-18-G01 Rev.1 | 2019-08-26 | CED Northampton Solar Ryan Road Northampton Solar and Battery | Generator notificationfrom ConEd Development ("CED") on behalf of CED Northampton Solar for the installation of 4.3 MW MW solar PV and battery in Northampton, MA and interconnecting to the Florence Junction Substation via the 09-909W4 13.8 kV feeder. | 2019-10-31 | Notification | 2019-10-09
CEE-19-X01 | 2019-09-17 | Merrimack AVR Replacement Project | Transmission application from Con Edison Energy Development (“CEE”) for the replacement of the Merrimack 1 AVR with a new Basler DECS 2100 digital voltage regulator system. | 2019-11-30 | Approved | 2019-10-09
EXE-19-X01 | 2019-09-11 | Mystic 8 & 9 AVR Replacement Project | Transmission application from Exelon Generation Co. (“EXE”) for the replacement of the excitation controllers and AVRs at the Mystic 8 Station. The upgrade will install new ABB UNITROL Static Excitation System at generator, which will provide excitation current to the exciters and replace the existing AVRs. | 10/2019 | Approved | 2019-10-09
EXE-19-X02 | 2019-09-11 | Mystic 8 & 9 AVR Replacement Project | Transmission application from Exelon Generation Co. (“EXE”) for the replacement of the excitation controllers and AVRs at the Mystic 9 Station. The upgrade will install new ABB UNITROL Static Excitation System at generator, which will provide excitation current to the exciters and replace the existing AVRs. | 10/2019 | Approved | 2019-10-09
FGE-19-G05 | 2019-08-09 | Settlers Solar Northfield Road Lunenburg Solar | Generator notification from Fitchburg Gas & Electric ("FG&E") on behalf of Settlers Solar for the installation of 4.99 MW solar PV in Lunenburg, MA and interconnecting to the Pleasant Street Substation via the 31W37 13.8 kV feeder. | 2019-12-01 | Notification | 2019-10-09
ES-19-T18 | 2019-08-30 | Gunn 15A-1X 115/23 kV Distribution Transformer Replacement | Transmission notification from Eversource Energy (“ES”) to replacement of the existing 15A-1X, 115/23-kV distribution transformer at the Gunn 15A substation, located in East Hampton Massachusetts. The existing 15A-1X transformer is being replaced to address asset local load serving system reliability issues. | 6/2020 | Notification | 2019-10-07
ES-19-T24 | 2019-09-09 | Northeast Simsbury Distribution Transformer Addition | Transmission application from Eversource Energy (“ES”) for the Northeast Simsbury Distribution Transformer Addition Project to install a 115/23 kV 62.5 MVA transformer at the Simsbury Substation in Simsbury, CT to address local load serving reliability issues. | 2019-12-31 | Approved | 2019-10-07
ES-19-T23 | 2019-08-28 | Partial reconductoring of the Holbrook to East Holbrook 398-537 line | Transmission notification from Eversource Energy (“ES”) to reconductor 0.39 miles of the 115kV 398-537 Line from Holbrook Station 478 to the border with National Grid outside East Holbrook Station 398. The existing 350 Cu conductor will be replaced with 795 ACSR. | 10/2019 | Notification | 2019-10-07
ES-19-T19 | 2019-08-29 | Stepstone 35L-2X Transformer Addition | Transmission notification from Eversource Energy (“ES”) for the addition of a second 115/23-kV, 62.5 MVA bulk distribution transformer 35L-2X with associated switchgear at the Stepstone 35L Substation located in Guilford, Connecticut. | 2019-12-31 | Notification | 2019-10-07
ES-19-T21 | 2019-08-20 | 349 X and Y 345 kV Cable Reconductoring | Transmission notification from Eversource Energy (“ES”) to reconductor 349X&Y 345 kV underground cables between the Golden Hills substation in Saugus, MA and the Mystic substation in Charlestown, MA. The existing 2000 kcmil High Pressure Fluid Filled pipe type Cable will be replaced with the 2500 kcmil cable of the same type. | 4/2021 | Notification | 2019-10-07
CMP-19-G02 | 2019-08-09 | BD Solar Augusta Solar Project | Generator application from Central Maine Power Company (“CMP”) for the BD Solar Augusta Solar Project to install a 7.2 MW solar array in Augusta, ME and interconnecting to the Blair Road Substation via the 270D2 12.47 kV feeder. | 2020-09-01 | Approved | 2019-08-26
CMP-19-G01 | 2019-08-09 | BD Solar Oxford Solar Project | Generator application from Central Maine Power Company (“CMP”) for the BD Solar Oxford Solar Project to install a 9.2 MW solar array in Norway, ME and interconnecting to the Oxford Substation via the 437D1 and 437D2 12.47 kV feeders. | 2020-09-01 | Approved | 2019-08-26
NEM-19-G03 | 2019-07-23 | Dawn Land Solar Generation and Transmission Project | Generator application from NextEra Energy Resources (“NEM”) for the Dawn Land Solar Generation and Transmission Project to install a 75 MW solar array in Washington County, ME. | 2022-05-31 | Approved Withdrawn | 8/26/2019 8/12/2020
NEM-19-T03 | 2019-07-23 | Dawn Land Solar Generation and Transmission Project | Transmission application from NextEra Energy Resources (“NEM”) for the Dawn Land Solar Generation and Transmission Project to install a 51/68/85 MVA 115/34.5 kV station transformer at the Deblois Substation to interconnect the solar array. | 2022-05-31 | Approved Withdrawn | 8/26/2019 8/12/2020
EM-19-T02 | 2019-07-23 | Dawn Land Solar Generation and Transmission Project | Transmission application from Emera Maine (“EM”) for the Dawn Land Solar Generation and Transmission Project to construct a new 115 kV substation and expand the Deblois Substation. Project will add one 115 kV breaker at the new substation and 4 115 kV breakers at the Deblois substation. Install 13.4 miles of 115 kV transmission line from the new substation to the Deblois substation. Install a new 115/34.5/13.8 kV transformer. Install three 34.5 kV breakers at the new substation and other associated transmission work. | 2022-05-31 | Approved Withdrawn | 8/26/2019 8/12/2020
CEE-19-X01 | 2019-07-30 | Schiller CT 1AVR Replacement Project | Transmission application from ConEdison Energy (“CEE”) for the Schiller CT 1 AVR Replacement Project to replace the existing AVR on Schiller CT 1 with a Basler DECS-250 digital Pilot Exciter. | 9/2019 | Approved | 2019-08-27
NEM-19-G05 | 2019-08-05 | Randolph Center Solar Project | Generator application from NextEra Energy Resources (“NEM”) for the Randolph Center Solar Project to install a 20 MW solar array in Randolph, VT and interconnecting to the Randolph Center 46 kV Substation. | 2021-11-01 | Approved Withdrawn | 8/26/2019 8/12/2020
SWEB-19-G01 | 2019-08-06 | Silver Maple Wind Generation and Transmission Project | Generator application from SWEB Development (“SWEB”) for the Silver Maple Wind Generation and Transmission Project to install a 20 MW wind farm in Penobscot County, ME and interconnecting to the Randolph Center 46 kV Substation. | 2020-12-16 | Approved | 2019-08-26
SWEB-19-T01 | 2019-08-06 | Silver Maple Wind Generation and Transmission Project | Transmission application from SWEB Development (“SWEB”) for the Silver Maple Wind Project to interconnect the 20 MW wind farm in Penobscot County, MEto the Silver Maple four breaker ring bus substation. | 2020-12-16 | Approved | 2019-08-26
EM-19-T03 | 2019-08-09 | Silver Maple Wind Generation and Transmission Project | Transmission application from Emera Maine (“EM”) for the Silver Maple Wind Generation and Transmission Project to install a four breaker ring bus substation in Penobscot County, ME. | 2020-10-01 | Approved | 2019-08-26
NEM-19-G04 | 2019-08-05 | Chariot Solar Generation and Transmission Project | Generator application from NextEra Energy Resources (“NEM”) for the Chariot Solar Generation and Transmission Project to install a 50 MW solar facility in Hinsdale, NH and interconnecting to the 115 kV line between the Vernon Road Tap and Vernon Road Substation | 2023-11-01 | Approved Withdrawn | 8/26/2019 1/13/2025
NEM-19-T04 | 2019-08-05 | Chariot Solar Generation and Transmission Project | Transmission application from NextEra Energy Resources (“NEM”) for the Chariot Solar Generation and Transmission Project to install a 115/34.5 kV station transformer that interconnects to the new 115 kV three-breaker ring bus substation in Hinsdale, NH. | 2023-09-27 | Approved Withdrawn | 8/26/2019 1/13/2025
NEP-19-T07 | 2019-08-12 | Chariot Solar Generation and Transmission Project | Transmission application from New England Power Company (“NEP”) for the Chariot Solar Generation and Transmission Project to construct a new 115 kV three-breaker ring bus substation in Hinsdale, NH to interconnect the solar project. | 2021-10-01 | Approved Withdrawn | 8/26/2019 1/13/2025
VELCO-19-GNF01 | 2019-08-01 | Otter Creek Solar Rice Lane Bennington Solar | Generator notification from VELCO for the installation of 2.16 MW solar PV in Bennington, VT and interconnecting to the GMP Silk Road Substation via the G59 12.47 kV feeder. | 2019-10-15 | Notification | 2019-08-27
NEP-19-GNF100 | 2019-08-01 | Tangent Energy Solutions Fitchburg Road Westminster Solar | Generator notification from New England Power Company ("NEP") on behalf of Tangent Energy Solutions for the installation of 3.0 MW solar PV in Westminster, MA and interconnecting to the East Westminster Substation via the 609W2 13.8 kV feeder. | 2019-09-15 | Notification | 2019-08-28
NEP-17-GNF35 Rev.1 | 2019-08-01 | GSPP AJAX 2 United Drive West Bridgewater Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of 4.728 MW solar PV in West Bridgewater, MA and interconnecting to the Easton Substation via the 92W54 13.8 kV feeder. | 2019-10-04 | Notification | 2019-08-28
NEP-19-GNF84 | 2019-08-01 | Renewable Energy Smith Street Attleboro Solar | Generator notification from New England Power Company ("NEP") on behalf of Renewable Energy for the installation of 4.268 MW solar PV in Attleboro, MA and interconnecting to the Chartley Pond Substation via the 8L4 13.2 kV feeder. | 2020-06-16 | Notification | 2019-08-28
NEP-19-GNF72 Rev.1 | 2019-08-01 | Green Development White Oak Lane Glocester Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Green Development for the installation of 1.8 MW solar PV in Glocester, RI and interconnecting to the Wolf Hill Substation via the 2221 23 kV feeder. | 2020-03-31 | Notification | 2019-08-28
NEP-19-GNF131 | 2019-08-01 | Borrego Solar Cummings Road Tyngsboro Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Borrego Solar for the installation of 4.999 MW solar PV and battery in Tyngsboro, MA and interconnecting to the Tyngsboro Substation via the 211L1 13.2 kV feeder. | 2020-06-06 | Notification | 2019-08-28
NEP-19-GNF129 | 2019-08-01 | Borrego Solar Cronin Road Warren Solar Battery | Generator notification from New England Power Company ("NEP") on behalf of Borrego Solar for the installation of 1.5 MW solar PV and battery in Warren, MA and interconnecting to the Fiskdale Substation via the 408L2 13.2 kV feeder. | 2019-11-19 | Notification | 2019-08-28
NEP-19-GNF130 | 2019-08-01 | Borrego Solar Pleasant Street Dunstable Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Ameresco for the installation of 4.5 MW solar PV and battery in Dunstable, MA and interconnecting to the Dunstable Substation via the 210L1 13.2 kV feeder. | 2020-04-01 | Notification | 2019-08-28
NEP-19-GNF132 | 2019-08-01 | NPS Bloom Energy Patriot Place Foxborough Solar | Generator notification from New England Power Company ("NEP") on behalf of NPS for the installation of 2.085 MW solar PV in Foxborough, MA and interconnecting to the Crocker Pond Substation via the 3424W3 13.8 kV feeder. | 2020-09-01 | Notification | 2019-08-28
NEP-19-GNF134 | 2019-08-01 | GSPP Millbrook Street Worcester Solar | Generator notification from New England Power Company ("NEP") on behalf of GSPP for the installation of 1.53 MW solar PV in Worcester, MA and interconnecting to the Nashua Street Substation via the HT48 13.8 kV feeder. | 2020-09-08 | Notification Withdrawn | 8/28/2019 9/25/2019
NEP-19-GNF142 | 2019-08-01 | ISM Solar Dighton Hart Street Dighton Solar | Generator notification from New England Power Company ("NEP") on behalf of ISM Solar Dighton for the installation of 2.8 MW solar PV in Dighton, MA and interconnecting to the Dighton Substation via the 19W72 13.8 kV feeder. | 2019-09-02 | Notification | 2019-08-28
NEP-19-GNF166 | 2019-08-01 | Borrego Solar West Livermore Hill Westminster Solar | Generator notification from New England Power Company ("NEP") on behalf of Borrego Solar for the installation of 4.99 MW solar PV in Westminster, MA and interconnecting to the Ashburnham Substation via the 610W3 13.8 kV feeder. | 2019-09-02 | Notification | 2019-08-28
NEP-19-GNF169 | 2019-08-01 | Borrego Solar West Street Gardner Solar | Generator notification from New England Power Company ("NEP") on behalf of Borrego Solar for the installation of 4.95 MW solar PV in Gardner, MA and interconnecting to the Crystal Lake Substation via the 607W1 13.8 kV feeder. | 2019-12-09 | Notification | 2019-08-28
NEP-19-GNF172 | 2019-08-01 | Bluewave Solar Beebe Road Wilbraham Solar | Generator notification from New England Power Company ("NEP") on behalf of Bluewave Solar for the installation of 4.4 MW solar PV in Wilbraham, MA and interconnecting to the Wilbraham Substation via the 507L1 13.2 kV feeder. | 2020-02-21 | Notification | 2019-08-28
NEP-19-GNF155 | 2019-08-01 | Borrego Solar Happy Hollow Road Winchendon Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Borrego Solar for the installation of 4.95 MW solar PV and battery in Winchendon, MA and interconnecting to the Crystal Lake Substation via the 607W1 13.8 kV feeder. | 2019-09-22 | Notification | 2019-08-28
NEP-19-GNF156 | 2019-08-01 | Williams College Main Street Williamstown Solar and Diesel Generator | Generator notification from New England Power Company ("NEP") on behalf of Williams College for the installation of 4.98 MW solar PV and diesel generator in Williamstown, MA and interconnecting to the Williamstown Substation via the 1003W1 13.8 kV feeder. | 2019-09-25 | Notification | 2019-08-28
NEP-19-GNF157 | 2019-08-01 | Borrego Solar Williamstown Road Hubbardston Solar | Generator notification from New England Power Company ("NEP") on behalf of Borrego Solar for the installation of 4.901 MW solar PV in Hubbardston, MA and interconnecting to the Barre Substation via the 604W4 13.8 kV feeder. | 2019-09-30 | Notification | 2019-08-28
NEP-19-GNF158 | 2019-08-01 | Dynamic Energy Solutions Boston Post Road West Brookfield | Generator notification from New England Power Company ("NEP") on behalf of Dynamic Energy Solutions for the installation 4.5 MW solar PV in West Brookfield, MA and interconnecting to the Lashaway Substation via the 525L2 13.2 kV feeder. | 2019-10-31 | Notification | 2019-08-28
NEP-19-GNF159 | 2019-08-01 | Nexamp Solar Breckenridge Street Palmer Solar and Energy | Generator notification from New England Power Company ("NEP") on behalf of Nexamp Solar for the installation of 4.4 MW solar PV and battery in Palmer, MA and interconnecting to the Palmer Substation via the 503L1 13.2 kV feeder. | 2019-10-15 | Notification | 2019-08-28
NEP-19-GNF144 | 2019-08-01 | Syncarpha Solar Laite Road Tewksbury Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Syncarpha Solar for the installation of 4.58 MW solar PV and battery in Tewksbury, MA and interconnecting to the East Tewksbury Substation via the 59L3 13.2 kV feeder. | 2020-03-15 | Notification | 2019-09-04
NEP-19-GNF153 | 2019-08-01 | Borrego Solar Partridgeville Road Athol Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Borrego Solar for the installation of 1.98 MW solar PV and battery in Athol, MA and interconnecting to the Chestnut Hill Substation via the 702W3 13.8 kV feeder. | 2019-09-17 | Notification | 2019-08-28
NEP-19-GNF154 | 2019-08-01 | Borrego Solar Homestead Road Charlton Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Borrego Solar for the installation of 2.98 MW solar PV and battery in Charlton, MA and interconnecting to the North Oxford Substation via the 406L1 13.2 kV feeder. | 2019-09-16 | Notification | 2019-08-29
NEP-19-GNF161 | 2019-08-01 | Zero Point Engineering Osgood Road Charlton Solar | Generator notification from New England Power Company ("NEP") on behalf of Zero Point Engineering for the installation of 4.5 MW solar PV in Charlton, MA and interconnecting to the West Charlton Substation via the 415L1 13.2 kV feeder. | 2019-11-21 | Notification | 2019-08-29
NEP-19-GNF162 | 2019-08-01 | Nexamp Griffin Road Charlton Solar | Generator notification from New England Power Company ("NEP") on behalf of Nexamp Solar for the installation of 1.393 MW solar PV in Charlton, MA and interconnecting to the West Charlton Substation via the 415L2 13.2 kV feeder. | 2019-10-11 | Notification | 2019-08-29
NEP-19-GNF163 | 2019-08-01 | Nexamp Union Road Wales Solar | Generator notification from New England Power Company ("NEP") on behalf of Nexamp Solar for the installation of 2.0 MW solar PV in Wales, MA and interconnecting to the Little Rest Road Substation via the 516L1 13.2 kV feeder. | 2019-10-19 | Notification | 2019-08-29
NEP-19-GNF165 | 2019-08-01 | Altus Power Mill Road Hampden Solar | Generator notification from New England Power Company ("NEP") on behalf of Altus Power for the installation of 2.0 MW solar PV in Hampden, MA and interconnecting to the West Hampden Substation via the 139L1 13.2 kV feeder. | 2019-12-18 | Notification | 2019-08-29
ES-19-G60 | 2019-08-09 | ECA NE MA HOL Lowloand Street Holliston Solar | Generator notification from Eversource Energy ("ES") on behalf of ECA NE MA HOL for the installation of 1.509 MW solar PV in Holliston, MA and interconnecting to the Sherborn Substation via the 274-H3 14 kV feeder. | 2019-12-31 | Notification | 2019-08-27
ES-19-T15 | 2019-07-16 | Breckwood 20A-3X 115/13.8 kV Transformer Replacement | Transmission notification from Eversource Energy ("ES") for the replacement of the existing Breckwood 20A-3X, 115/13.8-kV distribution transformer at the Breckwood 20A Substation, located in Springfield, Massachusetts. The existing 20A-3X transformer is being replaced due to asset conditions | 2019-12-31 | Notification | 2019-08-29
ES-19-G67 | 2019-07-29 | Blue Planet Funding Cocheco Road Farmington Solar | Generator notification from Eversource Energy ("ES") on behalf of Blue Planet Funding for the installation of 4.0 MW solar PV in Farmington, NH and interconnecting to the Rochester Substation via the 362 34.5 kV feeder. | 2019-12-31 | Notification Withdrawn | 8/27/2019 2/16/2021
ES-19-G49 | 2019-07-19 | GSSG New Hampshire Goffstown Solar | Generator notification from Eversource Energy ("ES") on behalf of GSSG New Hampshire for the installation of 4.99 MW solar PV in Goffstown, NH and interconnecting to the Rimmon Substation via the 328X1 34.5 kV feeder. | 2019-12-31 | Notification | 2019-08-27
ES-19-G59 | 2019-07-10 | Granby Public Schools Wells Road Granby Solar | Generator notification from Eversource Energy ("ES") on behalf of Town of Granby Public Schools for the installation of 1.6286 MW solar PV in Granby, CT and interconnecting to the Southwick Substation via the 29A3 23 kV feeder. | 2020-04-01 | Notification Withdrawn | 8/27/2019 9/20/2022
ES-19-G48 | 2019-07-19 | GSSG New Hampshire Hinsdale Road Winchester Solar | Generator notification from Eversource Energy ("ES") on behalf of GSSG New Hampshire for the installation of 4.99 MW solar PV in Winchester, NH and interconnecting to the Chestnut Hill Substation via the 3178X4 34.5 kV feeder. | 2019-12-31 | Notification Withdrawn | 8/27/2019 1/22/2020
ES-19-G47 | 2019-07-19 | GSSG New Hampshire Issac Buswell Road Ossipee Solar | Generator notification from Eversource Energy ("ES") on behalf of GSSG New Hampshire for the installation of 3.0 MW solar PV in Ossipee, NH and interconnecting to the Center Ossipee Substation via the 19W1 34.5 kV feeder. | 2019-12-31 | Notification Withdrawn | 8/27/2019 2/16/2021
ES-19-G57 | 2019-07-19 | GSSG New Hampshire Loudon Road Pittsfield Solar | Generator notification from Eversource Energy ("ES") on behalf of GSSG New Hampshire for the installation of 4.0 MW solar PV in Pittsfield, NH and interconnecting to the Oak Hill Substation via the 319 34.5 kV feeder. | 2019-12-31 | Notification | 2019-08-27
ES-19-G56 | 2019-07-19 | GSSG New Hampshire Petticoat Lane Haverhill Solar | Generator notification from Eversource Energy ("ES") on behalf of GSSG New Hampshire for the installation of 4.99 MW solar PV in Haverhill, NH and interconnecting to the Green Mountain Power Newbury Substation via the 12W1 12.47 kV feeder. | 2019-12-31 | Notification Withdrawn | 8/27/2019 1/22/2020
ES-19-G69 | 2019-07-30 | UMASS Tillson Farm Road Amherst Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of UMASS for the installation of 4.052 MW solar PV and battery in Amherst, MA and interconnecting to the 13.8 kV Tillson Substation. | 2019-12-31 | Notification | 2019-08-27
ES-19-G21 | 2019-07-31 | SunRaise Development Old Pine Hill Road Westport Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of SunRaise Development for the installation of 3.125 MW solar PV and battery in Westport, MA and interconnecting to the Fisher Road Substation via the 2-522-522 13.2 kV feeder. | 2019-12-01 | Notification Withdrawn | 8/27/2019 6/18/2024
ES-19-G68 | 2019-07-29 | Blue Planet Funding Commerce Way Franklin Solar | Generator notification from Eversource Energy ("ES") on behalf of Blue Planet Funding for the installation of 3.0 MW solar PV in Franklin, NH and interconnecting to the Daniel Substation via the 1X4 34.5 kV feeder. | 2019-12-31 | Notification Withdrawn | 8/27/2019 2/16/2021
ES-19-G52 | 2019-07-08 | Copper Technologies Raboth Road Kingston Solar | Generator notification from Eversource Energy ("ES") on behalf of Copper Technologies for the installation of 3.51 MW solar PV in Kingston, MA and interconnecting to the Kingston Substation via the 3-17-17 23 kV feeder. | 2019-12-31 | Notification | 2019-08-27
ES-19-G20 | 2019-07-31 | CVE North America Drift Road Westport Solar | Generator notification from Eversource Energy ("ES") on behalf of CVE North America, Inc. for the installation of 2.40 MW solar PV in Westport, MA and interconnecting to the Fisher Road Substation via the 2-523-523 13.2 kV feeder. | 2019-09-30 | Notification | 2019-08-27
ES-19-G35 | 2019-07-09 | Kearsarge Middle Road Acushnet Solar | Generator notification from Eversource Energy ("ES") on behalf of Kearsarge for the installation of 1.904 MW solar PV in Acushnet, MA and interconnecting to the Wing Lane Substation via the 2-241-241 13.2 kV feeder. | 2019-10-31 | Notification | 2019-08-27
ES-19-G23 | 2019-07-26 | SunRaise Development Old Falmouth Road Barnstable Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of SunRaise Development for the installation of 4.998 MW solar PV and battery in Barnstable, MA and interconnecting to the Mashpee Substation via the 4-88-88 23 kV feeder. | 2019-12-01 | Notification | 2019-08-27
ES-19-G39 | 2019-07-09 | ASD Cotuit MA Solar Cotuit Road Sandwich Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of ASD Cotuit MA for the installation of 3.11 MW solar PV and battery in Sandwich, MA and interconnecting to the Sandwich Substation #916 via the 4-81B-443 23 kV feeder. | 8/2020 | Notification | 2019-08-27
ES-19-G24 | 2019-07-26 | BE RE Flag Swamp Road Dartmouth Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of BE RE LLC for the installation of 2.0 MW solar PV and battery in Dartmouth, MA and interconnecting to the Cross Road Substation #651 via the 2-541-541 13.2 kV feeder. | 2019-08-30 | Notification Withdrawn | 8/27/2019 3/14/2023
FGE-19-G01 | 2019-08-09 | Fitchburg Renewables Fisher Road Fitchburg Solar | Generator notification from Fitchburg Gas & Electric ("FG&E") on behalf of Fitchburg Renewables for the installation of 4.0 MW solar PV in Fitchburg, MA and interconnecting to the Beech Street Substation via the 35W36 13.8 kV feeder. | 2019-12-01 | Notification | 2019-08-26
FGE-19-G02 | 2019-08-09 | NESG Solar Holding Fisher Road Fitchburg Solar | Generator notification from Fitchburg Gas & Electric ("FG&E") on behalf of NESG Solar Holding for the installation of 3.204 MW solar PV in Fitchburg, MA and interconnecting to the Pleasant Street Substation via the 31W37 13.8 kV feeder. | 2020-02-01 | Notification | 2019-08-26
FGE-19-G03 | 2019-08-09 | NH Solar Garden Alpine Road Fitchburg Solar | Generator notification from Fitchburg Gas & Electric ("FG&E") on behalf of NH Solar Garden for the installation of 4.4 MW solar PV in Fitchburg, MA and interconnecting to the River Street Substation via the 25W28 13.8 kV feeder. | 2021-02-01 | Notification Withdrawn | 8/27/2019 9/25/2019
FGE-19-G04 | 2019-08-09 | North Branch Energy Ashburnham Street Fitchburg Solar | Generator notification from Fitchburg Gas & Electric ("FG&E") on behalf of North Branch Energy for the installation of 4.885 MW solar PV in Fitchburg, MA and interconnecting to the River Street Substation via the 25W28 13.8 kV feeder. | 2021-02-01 | Notification | 2019-08-27
NEP-19-GNF151 | 2019-08-01 | Nexamp Wachusetts Road Rutland Solar | Generator notification from New England Power Company ("NEP") on behalf of Nexamp Solar for the installation of 2.0 MW solar PV in Rutland, MA and interconnecting to the Treasure Valley Substation via the 55W1 13.8 kV feeder. | 2019-09-19 | Notification | 2019-08-22
NEP-19-GNF152 | 2019-08-01 | Western Mass Electric Mill Road Hampden Solar | Generator notification from New England Power Company ("NEP") on behalf of Western Mass Electric for the installation of 3.48 MW solar PV in Hampden, MA and interconnecting to the West Hampden Substation via the 139L1 13.2 kV feeder. | 2019-09-05 | Notification | 2019-08-22
NEP-19-GNF150 | 2019-08-01 | Borrego Solar River Street Palmer Solar | Generator notification from New England Power Company ("NEP") on behalf of Borrego Solar for the installation of 3.468 MW solar PV in Palmer, MA and interconnecting to the Thorndike Substation via the 523L4 13.2 kV feeder. | 2019-10-30 | Notification | 2019-08-22
ES-19-X01 | 2019-06-24 | Andrew Square Substation Upgrade Project | Transmission application from Eversource Energy (“ES”) for the installation of two independent current differential high speed protection groups on the K Street to Andrew Square 115 kV cables (106-526, 106-527) to provide the selectivity to differentiate between a line fault and a transformer fault. The project will provide protection system fault clearing selectivity and design in compliance with NPCC Directory 4 BPS protection system design criteria | 11/2019 | Approved | 2019-07-25
ES-19-X02 | 2019-06-24 | Dewar Street Substation Upgrade Project | Transmission application from Eversource Energy (“ES”) for the installation of two independent current differential high speed protection groups on the K Street to Dewar 115 kV cables (483-524, 483-525) to provide the selectivity to differentiate between a line fault and a transformer fault. The project will provide protection system fault clearing selectivity and design in compliance with NPCC Directory 4 BPS protection system design criteria. | 11/2019 | Approved | 2019-07-25
ES-19-T17 | 2019-07-03 | Portsmouth Substation Upgrade Project | Transmission application from Eversource Energy (“ES”) for the replacement of an existing 115-34kV, 44.8 MVA transformer with a 62.5 MVA rated unit, addition of a second 115/34kV 62.5 MVA transformer, installation of one new 115kV bus tie circuit breaker, installation of two new 115kV circuit breaker disconnect switches. Also install one new 115kV circuit switcher for high-side transformer protection and addition of two 7.2 MVAR capacitor banks, one on each 34.5 kV bus and add a 34.5 kV Portsmouth bus tie circuit breaker, which will be normally open, with an automatic close function upon loss of a Portsmouth transformer. | 2020-06-01 | Approved | 2019-07-25
FPS-19-G01 | 2019-06-13 | FPS Plainfield Solar Project | Generator application from Freepoint Commodities LLC (“FPS”) for the installation of ten 2.0 MW (solar arrays (20 MWs total net output) in Plainfield, CT and interconnecting to the 23 kV bus at the Fry Brook Substation. | 12/2022 | Approved | 2019-07-25
FPS-19-G02 | 2019-06-17 | FPS Fair Haven Solar Project | Generator application from Freepoint Commodities LLC (“FPS”) for the installation of ten 2.0 MW solar arrays (20 MWs total net output) in Fair Haven, VT and interconnecting to the 46 kV line between the GMP Fair Haven and Carver Falls Substations. | 2022-07-01 | Approved | 2019-07-25
FPS-19-G03 | 2019-06-17 | FPS Claremont Solar Project | Generator application from Freepoint Commodities LLC (“FPS”) for the installation of ten 2.0 MW solar arrays (20 MWs total net output) in Claremont, NH and interconnecting to the 46 kV line between the GMP Claremont Tap and High Bridge Substation | 2022-07-01 | Approved Withdrawn | 7/25/2019 10/5/2021
FPS-19-G04 | 2019-06-17 | FPS Shaftsbury Solar Project | Generator application from Freepoint Commodities LLC (“FPS”) for the installation of ten 2.0 MW solar arrays (20 MWs total net output) in Shaftsbury, VT and interconnecting to the 46 kV line between the GMP South Shaftsbury Tap and East Arlington Substation. | 2022-07-01 | Approved | 2019-07-25
ES-19-G40 | 2019-06-13 | Borrego Solar Hedges Pond Road Plymouth Solar | Generator notification from Eversource Energy ("ES") on behalf of Borrego Solar Systems for the installation of 3.75 MW solar PV in Plymouth, MA and interconnecting to the Valley Substation via the 3-89-89 23 kV feeder. | 2019-12-31 | Notification | 2019-07-25
ES-19-G36 | 2019-06-12 | Borrego Solar South Main Street Freetown Solar | Generator notification from Eversource Energy ("ES") on behalf of Borrego Solar Systems for the installation of 4.999 MW solar PV in Freetown, MA and interconnecting to the Bell Rock Substation via the 2-635-635 34.5 kV feeder. | 2020-05-01 | Notification | 2019-07-25
ES-19-G25 | 2019-07-09 | CVE North America Wing Lane Acushnet Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of CVE North America for the installation of 2.5 MW solar PV and 1.262 MW battery in Acushnet, MA and interconnecting to the Wing Lane Substation via the 2-240-240 13.2 kV feeder. | 2019-10-31 | Notification | 2019-07-25
ES-19-G19 | 2019-06-13 | SunRaise Development Cranberry Highway Wareham Solar | Generator notification from Eversource on behalf of SunRaise Development LLC for the installation of a 2.5 MW PV array with 2.0 MW of DC coupled battery storage, inverter limited to 2.5 MWAC at the PCC, located at 2382 Cranberry Highway in Wareham, Massachusetts. | 2019-12-01 | Notification | 2019-07-25
ES-19-G33 | 2019-06-10 | Syncarpha Chester Road Blandford Solar and Battery | Generator notification from Eversource Energy ("ES") on behalf of Syncarpha Blandford for the installation of 4.99 MW solar PV and 4 MW battery in Blandford, MA and interconnecting to the Blandford Substation via the 19J2 feeder. | 2019-11-18 | Notification | 2019-07-25
NEP-19-GNF04 | 2019-06-27 | Ameresco Otter River Road Gardner Solar | Generator notification from New England Power Company ("NEP") on behalf of Ameresco for the installation of 2.5 MW solar PV in Gardner, MA and interconnecting to the Crystal Lake Substation via the 607W1 13.8 kV feeder. | 2020-09-01 | Notification | 2019-07-25
NEP-19-GNF61 | 2019-06-27 | NSTAR Electric Denslow Road East Longmeadow Solar | Generator notification from New England Power Company ("NEP") on behalf of NSTAR Electric for the installation of 4.99 MW solar PV in East Longmeadow, MA and interconnecting to the East Longmeadow Substation via the 508L5 13.2 kV feeder. | 2020-11-15 | Notification | 2019-07-25
NEBS-19-G01 | 2019-06-26 | Madison Business Park BESS | Generator notification from New England Battery Storage ("NEBS") for the installation of a 1.5 MW battery energy storage facility in Madison, ME and interconnecting to the Jones Street Substation via the 12.47 kV feeder. | 2020-01-01 | Notification | 2019-07-25
NEP-16-T02 Rev.1 | 2019-07-01 | Wakefield - Woburn Underground Cable Rev. 1 | Transmission notification from New England Power Company (“NEP”) for the installation for a new 345 kV underground line (#3136) from Wakefield Junction substation to company border with Eversource at the Wakefield/Stoneham, MA town line; two new circuit breaker at Wakefield Junction substation; new 345 kV variable shunt reactor (reference Eversource PPA ES-16-T06). Revision is to update the summer normal and revised winter line ratings reflecting current cable design. | 5/2021 | Notification | 2019-07-25
ES-16-T06 Rev.1 | 2019-07-02 | Wakefield - Woburn Underground Cable Rev. 1 | Transmission notification from Eversource Energy ("ES") for the installation of a new approximately 8 mile 345 kV underground cable circuit from Eversource’s Woburn Substation, in Woburn, MA to National Grid’s Wakefield Junction Substation, in Wakefield, MA with 160 Mvar variable shunt reactors at each terminal. Expand the 345 kV switchyard at Woburn Substation to be a breaker-and-a-half substation with four bays. NEP-16-T02 covers the National Grid portion of the project. Revision is to update the summer normal and revised winter line ratings reflecting current cable design. | 5/2021 | Notification | 2019-07-25
ES-19-T16 | 2019-06-27 | Line 667 Asset Condition | Transmission notification from Eversource Energy ("ES") for the rebuild of the existing 69-kV 667 Line from Salisbury Substation in Salisbury, CT to Falls Village Substation, in Falls Village due to asset conditions, with 556 ACSS conductor. | 2019-12-31 | Notification | 2019-07-25
NEP-19-G09 | 2019-05-08 | Syncarpha Puddon I & II Solar and Battery Energy Storage Facility | Generator application from New England Power Company (“NEP”) for the Syncarpha Puddon I & II Solar and Battery Energy Storage Facility to install a 9.96 MW solar array and battery energy storage system in Northbridge, MA and interconnecting to the Whitins Pond Substation via the 320W1 feeder. | 11/2019 | Approved | 2019-07-09
NEP-19-G14 | 2019-06-20 | Vernon Solar Generation and Transmission Project | Generator application from New England Power Company (“NEP”), on behalf of Freepoint Solar (“FPS”), for the construction of a 20 MW solar array in Vernon, VT. | 12/2022 | Approved Withdrawn | 7/9/2019 9/10/2020
NEP-19-T04 | 2019-06-20 | Vernon Solar Generation and Transmission Project | Transmission application from New England Power Company (“NEP”), on behalf of Freepoint Solar (“FPS”), for the installation of a new 16.2/21.6/27 MVA step-up transformer and transmission lead from tap on D-4 Vernon Solar Substation to FPS Vernon collector. | 12/2022 | Approved Withdrawn | 7/9/2019 9/10/2020
NEP-19-T05 | 2019-06-20 | Vernon Solar Generation and Transmission Project | Transmission application from New England Power Company (“NEP”) for the construction of a new three-breaker 69 kV ring-bus Vernon Solar Substation. | 12/2022 | Approved Withdrawn | 7/9/2019 9/10/2020
ES-19-T05 | 2019-05-24 | Eastport Substation Circuit Breaker Addition Project | Transmission application from Eversource Energy (“ES”) for the addition of four 115 kV circuit breakers and modification of a straight bus to a ring bus at the Eastport Substation in Rochester, New Hampshire. | 6/2020 | Approved | 2019-07-09
NEP-19-T06 | 2019-06-06 | Reynolds Avenue Substation Project | Transmission application from New England Power Company (“NEP”) for the construction of a new 115/13.2kV substation in Rehoboth, Massachusetts. The new station will be built in a company owned parcel next to Reynolds Avenue in Rehoboth, MA. Construction will consist of two 55 MVA transformers, breaker-and-a-half metal-clad switchgear, two 7.2 MVAR station capacitor banks, and five feeder positions. The station will be supplied from the C-181S (between Brayton Point and Chartley Pond) and D-182S (between Brayton Point and Mansfield) lines. | 1/2022 | Approved | 2019-07-09
ES-19-G42 | 2019-05-31 | ECA NEMA WOB Cabot Road Woburn Solar | Generator notification from Eversource Energy ("ES") on behalf of ECA NEMA WOB LLC for the installation of 1.31 MW solar PV in Woburn, MA and interconnecting to the North Woburn Substation via the 375-H1 14 kV feeder. | 2019-08-01 | Notification | 2019-07-09
NEP-19-GNF27 Rev.1 | 2019-06-06 | Syncarpha Solar Franklin Street Halifax Solar Rev.1 | Generator notification from New England Power Company ("NEP") on behalf of Syncarpha Solar for the installation of 3.668 MW solar PV in Halifax, MA and interconnecting to the Mill Street Substation via the 912W75 13.8 kV feeder. | 2019-06-15 | Notification | 2019-07-09
NEP-19-GNF68 | 2019-06-06 | Heron Crossing Shuman Avenue Stoughton Solar | Generator notification from New England Power Company ("NEP") on behalf of Heron Crossing Solar for the installation of 2.0 MW solar PV in Stoughton, MA and interconnecting to the Park View Substation via the 94W42 13.8 kV feeder. | 2019-12-04 | Notification | 2019-07-09
NEP-19-GNF108 | 6/62019 | Omni Navitas Holdings West Central Street Franklin Solar | Generator notification from New England Power Company ("NEP") on behalf of Omni Navitas Holdings for the installation of 1.248 MW solar PV in Franklin, MA and interconnecting to the Beaver Pond Substation via the 344W6 13.8 kV feeder. | 2020-01-28 | Notification Withdrawn | 7/9/2019 6/15/2021
NEP-19-GNF128 | 2019-06-06 | CEC Development Mohawk Trail Charlemont Solar | Generator notification from New England Power Company ("NEP") on behalf of CEC Development for the installation of 2.5 MW solar PV in Charlemont, MA and interconnecting to the Bear Swamp Substation via the 1019W1 13.8 kV feeder. | 2020-06-23 | Notification | 2019-07-09
NEP-19-GNF114 | 2019-06-06 | TJA Solar Federal Street Blackstone Solar | Generator notification from New England Power Company ("NEP") on behalf of TJA Solar for the installation of 4.95 MW solar PV in Blackstone, MA and interconnecting to the Riverside Substation via the 108W60 13.8 kV feeder. | 2020-09-01 | Notification | 2019-07-09
NEP-19-GNF123 | 2019-05-13 | Nimali Power Union Street Portsmouth Solar | Generator notification from New England Power Company ("NEP") on behalf of Nimali Power RI LLC for the installation of 1.3 MW MW solar PV in Portsmouth, RI and interconnecting to the Jepson Substation via the 37W41 13.8 kV feeder. | 2020-01-15 | Notification | 2019-07-09
ES-19-G51 | 2019-06-03 | Bloomfield CT 1 Generator | Generator notification from Eversource Energy ("ES") on behalf of Bloomfield CT 1 LLC for the installation of 1.62 MW combustion turbine in Bloomfield, CT and interconnecting to the Bloomfield 3B Substation via the 3B11 23 kV feeder. | 2019-06-28 | Notification | 2019-07-09
ES-19-T13 | 2019-05-21 | Eddy Substation Circuit Breaker Addition | Transmission notification from Eversource Energy ("ES") for the addition of a 115 kV circuit breaker at the Eddy Substation, located in Manchester, New Hampshire. The circuit breaker is proposed to be installed as a normally open line tie breaker between Lines D121 (to Merrimack substation) and P106 (to Rimmon substation). The line tie circuit breaker would only be closed for maintenance and construction activities. When the line tie circuit breaker is closed, protection will remain for both Line D121 and Line P106 regardless of which line breaker is out-of-service. | 6/2020 | Notification | 2019-07-09
ES-19-T12 | 2019-05-24 | Emerald Street Substation Circuit Breaker Addition | Transmission notification from Eversource Energy ("ES") for the addition of three 115 kV circuit breakers at the Emerald St. substation, located in Keene, New Hampshire. It is proposed to install two bus tie circuit breakers, without the breaker logic enabled and effectively being used as SCADA controlled switches. The bus tie circuit breakers would only be opened to support maintenance and construction activities. A third circuit breaker is proposed to be installed as a normally open line tie breaker between Lines A152 and D108. | 6/2020 | Notification | 2019-07-09
NEP-19-GNF98 | 2019-06-06 | Zero Point Development Wilbraham Road Monson Solar | Generator notification from New England Power Company ("NEP") on behalf of Zero Point Development for the installation of 2.0 MW solar PV in Monson, MA and interconnecting to the Wilbraham Substation via the 507L1 13.2 kV feeder. | 2019-09-01 | Notification | 2019-06-28
EM-19-G01 | 2019-06-21 | Old Town Mill Generator Project | Generator application from Emera Maine (“EM”) on behalf of Old Town Mill to restart the existing 10.625 MW steam generator in Old Town Maine. The generator will run behind the meter and will not export power to the grid but will be able to support system voltage and frequency. | 2019-07-01 | Approved | 2019-06-28
NEP-19-G13 | 2019-05-14 | MacDill Solar Generation and Transmission Project | Generator application from New England Power Company (“NEP”) for the installation of a 19.98 MW solar array in Lanesborough, MA | 9/2020 | Approved Withdrawn | 6/10/2019 4/22/2020
NEP-19-T02 | 2019-05-14 | MacDill Solar Generation and Transmission Project | Transmission application from New England Power Company (“NEP”) for the installation of a new 115/34.5/13.2 kV 15/20/25 MVA generator step-up transformer (GSU) at the new interconnection substation. | 9/2020 | Approved Withdrawn | 6/10/2019 4/22/2020
NEP-19-T03 | 2019-05-14 | MacDill Solar Generation and Transmission Project | Transmission application from New England Power Company (“NEP”) for the construction of a new three-breaker 115 kV ring bus substation on the F-132 Line at the proposed McDill PV site. | 9/2020 | Approved Withdrawn | 6/10/2019 4/22/2020
WED-19-G01 | 2019-05-22 | Wallingford Solar Project | Generator application from The Town of Wallingford Public Utilities Electric Division for the installation of a 4.99 MW solar array interconnecting to the Wallingford 13M substation via the 13.8 kV distribution system. | 2019-12-31 | Approved | 2019-06-10
WED-19-G02 | 2019-05-22 | Wallingford Solar Project | Generator application from The Town of Wallingford Public Utilities Electric Division for the installation of a 4.99 MW solar array interconnecting to the Wallingford 13M substation via the 13.8 kV distribution system. | 2019-12-31 | Approved | 2019-06-10
WED-19-G03 | 2019-05-22 | Wallingford Solar Project | Generator application from The Town of Wallingford Public Utilities Electric Division for the installation of a 10.0 MW solar array interconnecting to the Wallingford 13M substation via the 13.8 kV distribution system | 2019-12-31 | Approved | 2019-06-10
NEP-19-G10 | 2019-05-22 | Encore Casino Generation Project | Generator application from New England Power Company (“NEP”) for the Encore Casino Solar Project to install a 0.69 MW solar array in Everett, MA interconnecting to the Hendersonville Substation via the 593W4 feeder. | 12/2020 | Approved | 2019-06-10
NEP-19-G11 | 2019-05-14 | Encore Casino Generation Project | Generator application from New England Power Company (“NEP”) for the Encore Casino Battery Energy Storage System to install a 4.0 MW battery in Everett, MA interconnecting to the Hendersonville Substation via the 593W1 and 593W4 feeders. | 12/2020 | Approved | 2019-06-10
NEP-19-G12 | 2019-05-14 | Encore Casino Generation Project | Generator application from New England Power Company (“NEP”) for the Encore Casino CoGen/CHP generator to install a 3.12 MW CoGen/CHP generator in Everett, MA interconnecting to the Hendersonville Substation via the 593W1 and 593W4 feeders. | 12/2020 | Approved | 2019-06-10
NEP-19-GNF118 | 2019-05-13 | South Essex Sewerage Salem Solar | Generator notification from New England Power Company ("NEP") on behalf of South Essex Sewerage PV for the installation of 1.56 MW solar PV in Salem, MA and interconnecting to the Salem Substation via the 2321 23 kV feeder. | 2019-05-31 | Notification | 2019-06-10
NEP-19-GNF119 | 2019-05-13 | Bluewave Capital Brimball Avenue Beverly Solar | Generator notification from New England Power Company ("NEP") on behalf of Bluewave Capital for the installation of 3.5 MW solar PV in Beverly, MA and interconnecting to the East Beverly Substation via the 51L1 13.2 kV feeder. | 2019-09-05 | Notification | 2019-06-10
NEP-19-GNF120 | 2019-05-13 | Renewable Energy Commander Shea Blvd Quincy Solar | Generator notification from New England Power Company ("NEP") on behalf of Renewable Energy for the installation of 1.01 MW solar PV in Quincy, MA and interconnecting to the North Quincy Substation via the 11W3 13.8 kV feeder. | 2020-02-03 | Notification | 2019-06-10
NEP-19-GNF121 | 2019-05-13 | Nexamp Ayers Village Road Methuen Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Nexamp for the installation of 2.09 MW solar PV and battery in Methuen, MA and interconnecting to the East Methuen Substation via the 74L1, 13.2 kV feeder. | 2021-05-13 | Notification Withdrawn | 6/10/2019 5/18/2021
NEP-19-GNF122 | 2019-05-13 | Ameresco Aegean Drive Methuen Solar | Generator notification from New England Power Company ("NEP") on behalf of Ameresco for the installation of 1.75 MW solar PV in Methuen, MA and interconnecting to the West Methuen Substation via the 63L2 13.2 kV feeder. | 2021-02-17 | Notification | 2019-06-10
NEP-19-GNF124 | 2019-05-13 | GSPP Millbrook Street Worcester Solar | Generator notification from New England Power Company ("NEP") on behalf of GSPP for the installation of 1.71 MW solar PV in Worcester, MA and interconnecting to the Nashua Street Substation via the HT48 13.8 kV feeder. | 2019-07-01 | Notification | 2019-06-10
NEP-19-GNF82 | 2019-05-13 | ISM Solar Bronco Highway Burrillville Solar | Generator notification from New England Power Company ("NEP") on behalf of ISM Solar for the installation of 2.54 MW solar PV in Burrillville, RI and interconnecting to the Nasonville Substation via the 127W42 13.8 kV feeder. | 2019-06-20 | Notification | 2019-06-10
NEP-19-GNF125 | 2019-05-13 | Oak Square Walling Road Burrillville Solar | Generator notification from New England Power Company ("NEP") on behalf of Oak Square for the installation of 1.82 MW solar PV in Burrillville, RI and interconnecting to the Nasonville Substation via the 127W40 13.8 kV feeder. | 2020-01-15 | Notification | 2019-06-10
NEP-19-GNF72 | 2019-05-13 | Green Development White Oak Lane Glocester Solar | Generator notification from New England Power Company ("NEP") on behalf of Green Development for the installation of 3.0 MW solar PV in Glocester, RI and interconnecting to the Wolf Hill Substation via the 2221 23 kV feeder. | 2020-03-31 | Notification | 2019-06-10
NEP-19-GNF126 | 2019-05-13 | TJA Solar Blackstone Street Blackstone Solar | Generator notification from New England Power Company ("NEP") on behalf of TJA Solar for the installation 3.96 MW solar PV in Blackstone, MA and interconnecting to the South Bellingham Substation via the 108W60 13.8 kV feeder. | 2019-10-10 | Notification | 2019-06-10
NEP-19-GNF07 | 2019-05-13 | Turning Point Development West Greenwich Solar | Generator notification from New England Power Company ("NEP") on behalf of Turning Point Development for the installation of 3.34 MW solar PV in West Greenwich, RI and interconnecting to the Hopkins Hill Substation via the 63F2 12.47 kV feeder. | 2019-12-31 | Notification | 2019-06-10
NEP-19-GNF11 | 2019-05-13 | Cypress Creek Bridgewater Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Cypress Creek for the installation of 4.99 MW solar PV and battery in Bridgewater, MA and interconnecting to the Mill Street Substation via the 912W55 13.8 kV feeder. | 2020-03-15 | Notification Withdrawn | 6/10/2019 10/20/2020
NEP-19-GNF14 | 2019-05-13 | Astrum Solar Crandall Lane Hopkinton Solar | Generator notification from New England Power Company ("NEP") on behalf of Astrum Solar for the installation of 3.1 MW solar PV in Hopkinton, RI and interconnecting to the Wood River Substation via the 85T3 34.5 kV feeder. | 2020-01-01 | Notification | 2019-06-10
NEP-19-GNF19 | 2019-05-13 | Hopeful Solar Snake Hill Road Burrillville Solar | Generator notification from New England Power Company ("NEP") on behalf of Hopeful Solar for the installation of 4.0 MW solar PV in Burrillville, RI and interconnecting to the Nasonville Substation via the 127W41 13.8 kV feeder. | 2020-01-15 | Notification | 2019-06-10
NEP-19-GNF21 | 2019-05-13 | Direct Energy Solar Chase Hill Road Hopkinton Solar | Generator notification from New England Power Company ("NEP") on behalf of Direct Energy Solar for the installation of 2.9 MW solar PV in Hopkinton, RI and interconnecting to the Chase Hill Substation via the 155F4 12.47 kV feeder. | 2019-12-15 | Notification | 2019-06-10
NEP-19-GNF22 | 2019-05-13 | Kearsarge Solar Quarry Road Bradford Solar | Generator notification from New England Power Company ("NEP") on behalf of Kearsarge Solar for the installation of 4.08 MW solar PV in Westerly, RI and interconnecting to the Chase Hill Substation via the 155F2 12.47 kV feeder. | 2019-12-15 | Notification | 2019-06-10
NEP-19-GNF23 | 2019-05-13 | Tangent Energy Street Trust Whitman Solar | Generator notification from New England Power Company ("NEP") on behalf of Tangent Energy Solutions for the installation of 2.18 MW solar PV in Whitman, MA and interconnecting to the Uxbridge Substation via the 321W9 13.8 kV feeder. | 2020-03-15 | Notification Withdrawn | 6/10/2019 6/16/2020
NEP-19-GNF24 | 2019-05-13 | Solsource Sharps Lot Road Swansea Solar | Generator notification from New England Power Company ("NEP") on behalf of Solsource LLC for the installation of 1.5 MW solar PV in Swansea, MA and interconnecting to the Dighton Substation via the 19W73 13.8 kV feeder. | 2020-06-15 | Notification | 2019-06-10
NEP-19-GNF26 | 2019-05-13 | Cypress Creek Rocky Hill Road Road Rehoboth Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Cypress Creek for the installation of 4.99 MW solar PV and battery in Rehoboth, MA and interconnecting to the Chartley Pond Substation via the 8L4 13.2 kV feeder. | 2020-03-15 | Notification | 2019-06-11
NEP-19-GNF27 | 2019-05-13 | Syncarpha Solar Franklin Street Halifax Solar | Generator notification from New England Power Company ("NEP") on behalf of Syncarpha Solar for the installation of 1.67 MW solar PV in Halifax, MA and interconnecting to the Mill Street Substation via the 912W75 13.8 kV feeder. | 2019-06-15 | Notification | 2019-06-11
NEP-19-GNF28 | 2019-05-13 | Borrego Solar Woodland Avenue Seekonk Colar | Generator notification from New England Power Company ("NEP") on behalf of Borrego Solar for the installation of 4.98 MW solar PV in Seekonk, MA and interconnecting to the West Street Substation via the 2248 23 kV feeder. | 2019-06-15 | Notification | 2019-06-10
NEP-19-GNF29 | 2019-05-13 | Halifax Solar River Street Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Halifax Solar for the installation fo 4.95 MW solar PV and battery in Halifax, MA and interconnecting to the Mill Street Substation via the 912W75 13.8 kV feeder. | 2019-10-10 | Notification | 2019-06-10
NEP-19-GNF30 | 2019-05-13 | Mass Electric Northbridge Solar | Generator notification from New England Power Company ("NEP") on behalf of Mass Electric for the installation of 4.97 MW solar PV in Northbridge, MA and interconnecting to the Whitins Pond Substation via the 320W5 13.8 kV feeder. | 2019-09-15 | Notification | 2019-06-10
NEP-19-GNF33 | 2019-05-13 | Syncarpha Solar Linwood Avenue Northbridge Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Syncarpha Solar for the installation of 4.98 MW solar PV and battery in Northbridge, MA and interconnecting to the Whitins Pond Substation via the 320W3 13.8 kV feeder. | 2019-10-18 | Notification | 2019-06-10
NEP-19-GNF34 | 2019-05-13 | Syncarpha Solar Douglas Street Uxbridge Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Syncarpha Solar for the installation of 4.28 MW solar PV and battery in Uxbridge, MA and interconnecting to the Uxbridge Substation via the 321W1 13.8 kV feeder. | 2019-10-04 | Notification Withdrawn | 6/10/2019 6/16/2020
NEP-19-GNF35 | 2019-05-13 | Attleboro Landfill Solar | Generator notification from New England Power Company ("NEP") on behalf of Attleboro Landfill Solar for the installation of 2.0 MW solar PV in Attleboro, MA and interconnecting to the Chartley Pond Substation via the 8L4 13.2 kV feeder. | 2019-06-28 | Notification | 2019-06-10
NEP-19-GNF36 | 2019-05-13 | Kearsarge Solar Franklin Solar and Battery | Generator notification from New England Power Company ("NEP") on behalf of Kearsarge Solar for the installation of 1.82 MW solar PV and battery in Franklin, MA and interconnecting to the South Wrentham Substation via the 2284 23 kV feeder. | 2020-04-01 | Notification | 2019-06-10
NEP-19-GNF37 | 2019-05-13 | Nexamp Solar Spring Street Franklin Solar | Generator notification from New England Power Company ("NEP") on behalf of Nexamp Solar for the installation of 4.98 MW solar PV in Franklin, MA and interconnecting to the Beaver Pond Substation via the 344W5 13.8 kV feeder. | 2020-07-01 | Notification | 2019-06-10
NEP-19-GNF38 | 2019-05-13 | Nexamp Solar West Street Douglas Solar | Generator notification from New England Power Company ("NEP") on behalf of Nexamp Solar for the installation of 4.98 MW solar PV in Douglas, MA and interconnecting to the Whitins Pond T1 Substation via the 321W4 13.8 kV feeder. | 2020-07-01 | Notification | 2019-06-10
NEP-19-GNF39 | 2019-05-13 | Turning Point Solar Hopkins Hill Road West Greenwich Solar | Generator notification from New England Power Company ("NEP") on behalf of Turning Point Solar for the installation of 3.34 MW solar PV in West Greenwich, RI and interconnecting to the Hopkins Hill Substation via the 63F2 12.47 kV feeder. | 2019-12-15 | Notification | 2019-06-10
ES-19-G32 | 2019-05-07 | TJA Solar Wilson Street Hopkinton Solar | Generator notification from Eversource Energy ("ES") on behalf of TJA solar for the installation of 2.772 MW solar PV in Hopkinton, MA and interconnecting to the West Framingham Substation via the 455H3 13.8 kV feeder. | 9/2019 | Notification | 2019-06-10
NEP-19-GNF67 | 2019-03-25 | Astrum Hobomock Stret Pembroke Solar | Generator notification from New England Power ("NEP") on behalf of Astrum Solar for the installation of 3.2 MW solar PV in Pembroke, MA and interconnecting to the Water Street Substation via the 910W5 13.8 kV feeder. | 2019-04-03 | Notification | 2019-05-01
NEP-19-GNF91 | 2019-03-25 | Ameresco County Road Hanson Solar | Generator notification from New England Power ("NEP") on behalf of Ameresco for the installation of 1.328 MW solar PV in Hanson, MA and interconnecting to the Plymouth Street Substation via the 93W43 13.8 kV feeder. | 2020-07-31 | Notification Withdrawn | 5/1/2019 11/18/2020
NEP-19-GNF83 | 2019-03-25 | Bartletts Ocean View Farm Nantucket Solar | Generator notification from New England Power ("NEP") on behalf of Bartletts Ocean View Farm for the installation of 1.0 MW solar PV in Nantucket, MA and interconnecting to the Candle Street Substation via the 101L5 13.2 kV feeder. | 2019-10-28 | Notification | 2019-05-01
NEP-19-GNF81 | 2019-03-25 | ISM Solar Development Cranston Solar | Generator notification from New England Power ("NEP") on behalf of ISM Solar Development for the installation of 2.375 MW solar PV in Cranston, RI and interconnecting to the Pontiac Substation via the 27F5 12.47 kV feeder. | 2019-12-20 | Notification | 2019-05-01
NEP-19-GNF73 | 2019-03-25 | Nugen Capital Management Bristol Solar | Generator notification from New England Power ("NEP") on behalf of Nugen Capital Management for the installation of 4.98 MW solar PV in Bristol, MA and interconnecting to the Bristol Substation via the 51F1 12.47 kV feeder. | 2020-01-04 | Notification | 2019-05-01
ES-19-G08 | 2019-03-14 | CEC Mill Road Fairhaven Solar | Generator notification from Eversource Energy ("ES") on behalf of Clean Energy Collective for the installation of 2.0 MW solar PV in Fairhaven, MA and interconnecting to the Arsene Street Substation via the 2-221-221 13.2 kV feeder. | 2019-04-01 | Notification | 2019-05-01
ES-19-G07 | 2019-03-14 | CEC Wareham Solar | Generator notification from Eversource Energy ("ES") on behalf of Clean Energy Collective for the installation of 2.0 MW solar PV in Wareham, MA and interconnecting to the Tremont Substation via the 3-85-85 23 kV feeder. | 2019-02-01 | Notification | 2019-05-01
ES-19-G09 | 2019-04-01 | CEC Yankee Lane Fairhaven Solar | Generator notification from Eversource Energy ("ES") on behalf of Clean Energy Collective for the installation of 2.875 MW solar PV in Fairhaven, MA and interconnecting to the Arsene Street Substation via the 2-221-221 13.2 kV feeder. | 2019-04-01 | Notification | 2019-05-01
ES-19-G05 | 2019-03-14 | Nextamp Solar Dartmouth Solar | Generator notification from Eversource Energy ("ES") on behalf of Nextamp Solar for the installation of 2.3 MW solar PV in Dartmouth, MA and interconnecting to the Cross Road Substation via the 2-543-543 13.2 kV feeder. | 2019-01-01 | Notification | 2019-05-01
ES-19-G04 | 2019-03-14 | REDP Carver Solar | Generator notification from Eversource Energy ("ES") on behalf of Renewable Energy Development Partners (REDP) for the installation of 2.5 MW solar PV in Carver, MA and interconnecting to the West Pond Substation via the 3-10-10 23 kV feeder. | 2019-03-01 | Notification | 2019-05-01
ES-19-G16 | 2019-04-04 | Falmouth Landfill Solar | Generator notification from Eversource Energy ("ES") on behalf of Falmouth Landfill Solar for the installation of 1.5 MW solar PV in Falmouth, MA and interconnecting to the Falmouth Substation via the 98A 23 kV feeder. | 10/2019 | Notification | 2019-05-01
ES-19-G06 | 2019-03-14 | Borrego Acushnet Titleist New Nedford Battery Energy Storage System | Generator notification from Eversource Energy ("ES") on behalf of Borrego Solar Systems for the installation of a 1.5 MW MW Battery Energy Storage System in New Bedford, MA and interconnecting to the Industrial Park Substation via the 45G1 2-107-107 13.2 kV feeder. | 2019-04-14 | Notification | 2019-05-01
ES-19-G10 | 2019-03-14 | LSE Dolphinus Enfield Solar | Generator notification from Eversource Energy ("ES") on behalf of LSE Delphinus for the installation fo 1.992 MW solar PV in Enfield, CT and interconnecting to the Scitico Substation via the 27H8 23 kV feeder. | 2019-03-01 | Notification | 2019-05-01
ES-19-G17 | 2019-03-19 | TGC III Westwood Solar | Generator notification from Eversource Energy ("ES") on behalf of TGC III MA Portfolio Operating for the installation of 1.2 MW solar PV in Westwood, MA and interconnecting to the Hyde Park Substation via the 344-1412H1 14 kV feeder. | 2019-09-01 | Notification Withdrawn | 5/1/2019 6/18/2024
ES-19-G29 | 2019-04-02 | Ashland Solar | Generator notification from Eversource Energy ("ES") on behalf of Ashland Solar for the installation of 4.36 MW solar PV in Ashland, MA and interconnecting to the Sherborn Substation via the 274-1429H1 13.8 kV feeder. | 4/2019 | Notification | 2019-05-01
ES-19-31 | 2019-04-09 | TJA North Maine Street Lanesborough Solar | Generator notification from Eversource Energy ("ES") on behalf of TJA Solar for the installation of 3.96 MW solar PV in Lanesborough, MA and interconnecting to the Partridge Substation via the 15E1 feeder. | 2019-12-31 | Notification | 2019-05-01
ES-19-G30 | 2019-04-09 | TJA Partridge Road Lanesborough Solar | Generator notification from Eversource Energy ("ES") on behalf of TJA Solar for the installation of 4.99 MW solar PV in Lanesborough, MA and interconnecting to the Partridge Substation via the 15E2 feeder. | 2019-12-31 | Notification | 2019-05-01
VEC-18-G03 Rev.1 | 2019-03-15 | Alburgh Solar Rev.1 | Generator notification from Vermont Electric CoOp on behalf of SoCore VT Alburgh for the installation of 1.0 MW solar PV in Alburgh, VT and interconnecting to the VEC Substation via the 28-1A 12.47 kV feeder. Application revised to reflect the installed under frequency protection. | 2016-12-31 | Notification | 2019-05-01
VEC-18-G02 Rev.1 | 2019-03-15 | BDE Grand Isle Solar Rev.1 | Generator notification from Vermont Electric CoOp on behalf of BDE Grand Isle for the installation of 4.978 MW solar PV in Grand Isle, VT and interconnecting to the VEC Substation via the 29-1A 12.47 kV feeder. Application revised to reflect the installed under frequency protection. | 12/2018 | Notification | 2019-05-01
VEC-18-G01 Rev.1 | 2019-03-15 | Maggie Hill Hinesburg Solar Rev.1 | Generator notification from Vermont Electric CoOp on behalf of SoCore VT Maggie Hill LLC for the installation of 1.26 MW solar PV in Hinesburg, VT and interconnecting to the Hinesburg Substation via the 19-1A feeder. Application revised to reflect the installed under frequency protection. | 2017-11-21 | Notification | 2019-05-01
CMP-19-G03 | 2019-03-07 | BD Fairfield Solar | Generator notification from Avangrid on behalf of BD Fairfield Solar for the installation of 4.99 MW solar PV in Fairfield, ME and interconnecting to the Shawmut Substation via the 852D1 115 kV feeder. | 2019-10-01 | Notification | 2019-05-01
EM-19-T01 | 2019-04-09 | Boggy Brook T1 Transformer Replacement | Transmission application for replacement of the 28 MVA 115/46 kV T1 transformer at the Boggy Brook Substation due to asset conditions. | 2019-04-09 | Notification | 2019-05-01
NETC-19-G01 | 2019-04-10 | Killingly Energy Center Generation and Transmission Project | Generator application from NTE Energy (NTEC) for the construction of a 671 MW (Summer Net Output) 693 MW (Winter Net Output) combined cycle dual-fuel generator in Killington, CT interconnecting to a new Eversource switching station and then to the 345 kV 3271 Line. | 2022-03-21 | Approved Withdrawn | 5/1/2019 8/31/2023
NETC-19-T01 | 2019-04-10 | Killingly Energy Center Generation and Transmission Project | Transmission application from NTE Energy (NTEC) for the construction of on 345/23.5 kV and one 345/16 kV generator GSU transformers in Killington, CT. | 2021-05-18 | Approved Withdrawn | 5/1/2019 8/31/2023
ES-19-T09 | 2019-04-10 | Killingly Energy Center Generation and Transmission Project | Transmission application from Eversource Energy (ES) for the construction of a new three-breaker, 345-kV ring bus Cotton Bridge Substation in Killingly, CT and tapping the 3271 Line between Eversource’s Lake Road and Card Street Substations into the new Cotton Bridge 345-kV Substation. A 345-kV generator lead will also be constructed from the Cotton Bridge 345-kV Substation to the generator collector bus. The proposed project is required to connect the Killingly Energy Center project. | 2020-07-01 | Approved Withdrawn | 5/1/2019 8/31/2023
NEP-19-G08 | 2019-04-05 | Independence Solar Generator Project | Generator application from New England Power, on behalf of Independence Solar LLC, for the installation of a 8.125 MW solar array in Spencer, MA and interconnecting to the Meadow Street Substation via the 552L5 13.2 kV feeder. | 2020-05-01 | Approved | 2019-05-01
NEM-19-G02 | 2019-04-10 | Farmington Solar Generation and Transmission Project | Generator application from NextEra Energy Marketing (NEM), on behalf of Farmington Solar LLC, for the installation of a 78.4 MW (net output) solar array in Franklin County, ME. | 2020-07-01 | Approved | 2019-05-01
NEM-19-T02 | 2019-04-10 | Farmington Solar Generation and Transmission Project | Transmission application from NextEra Energy Marketing (NEM), on behalf of Farmington Solar LLC, for the installation of a 54/72/90 MVA 115/34.5 kV transformer along with a +/- 20 MVAR Superconductor DVAR with its own GSU on the low side of the interconnecting transformer at the new substation being constructed by CMP. | 2020-07-01 | Approved | 2019-05-01
CMP-19-T01 | 2019-04-10 | Farmington Solar Generation and Transmission Project | Transmission application from Avangrid, on behalf of Central Maine Power Company (CMP), to construct a new ring bus configured substation to accommodate the interconnection of Farmington Solar on the existing Section 278 115 kV Line between Livermore Substation and Sturtevant Substation. | 2020-07-01 | Approved | 2019-05-01
NEP-19-T01 | 2019-03-14 | First Street Transformer Addition Project | Transmission application from New England Power Company, on behalf of Narragansett Electric, for the construction of the 115/12.47 kV First Street Substation in East Providence, RI. Transformer rating will be 24/32/40 MVA, four feeder positions and a 7.2 MVAR station capacitor bank. | 3/2022 | Approved | 2019-05-01
GMP-19-G01 | 2019-03-05 | GMP Milton Battery Energy Storage System | Generator notification from Green Mountain Power (“GMP”) on behalf of GMP Microgrid Milton LLC for the installation of a 2.0 MW Battery Energy Storage System in Milton, VT and interconnecting to the Ferrisburgh Substation via the 45G1 12.47 kV feeder. | 2019-07-03 | Notification | 2019-04-02
GMP-19-G02 | 2019-03-05 | GMP Ferrisburgh Battery Energy Storage System | Generator notification from Green Mountain Power (“GMP”) on behalf of GMP Microgrid Ferrisburgh LLC for the installation of a 2.0 MW Battery Energy Storage System in Milton, VT and interconnecting to the Ferrisburgh Substation via the 45G1 12.47 kV feeder. | 2019-07-01 | Notification | 2019-04-02
GMP-19-G03 | 2019-03-05 | GMP Essex Battery Energy Storage System | Generator notification from Green Mountain Power (“GMP”) on behalf of GMP Microgrid Essex LLC for the installation of a 2.0 MW Battery Energy Storage System in Milton, VT and interconnecting to the Essex Substation via the 33Y4 34.5 kV feeder. | 2019-07-01 | Notification | 2019-04-02
NEP-19-G05 | 2019-02-28 | Encore Casino Generation Project | Generator application from New England Power Company (“NEP”) for the Encore Casino Solar Project to install a 0.69 MW solar array in Everett, MA interconnecting to the Norman Street Substation via the 8W1 feeder. | 5/2019 | Approved | 2019-04-02
NEP-19-G06 | 2019-02-28 | Encore Casino Generation Project | Generator application from New England Power Company (“NEP”) for the Encore Casino Battery Energy Storage System to install a 4.0 MW battery in Everett, MA interconnecting to the Norman Street Substation via the 8W1 feeder. | 5/2019 | Approved | 2019-04-02
NEP-19-G07 | 2019-02-28 | Encore Casino Generation Project | Generator application from New England Power Company (“NEP”) for the Encore Casino CoGen/CHP generator to install a 3.12 MW CoGen/CHP generator in Everett, MA interconnecting to the Norman Street Substation via the 8W1 feeder. | 5/2019 | Approved | 2019-04-02
MMWEC-19-X01 | 2019-03-07 | Stony Brook Automatic Voltage Regulator (AVR) Replacement Project | Transmission application from Massachusetts Municipal Wholesale Electric Company (“MMWEC”) for the replacement of the exciter controller / AVR for the Stony Brook Unit 1 steam turbine generator as well as the five gas turbine generators. The upgrade will install a new Basler DECS 400 excitation control system, which will provide excitation current to the exciters and replace the existing AVRs. | 2019-04-13 | Approved | 2019-04-02
NEP-19-G01 | 2019-02-22 | Hope Farm and Scituate Solar Generator Project | Generator application from New England Power Company (“NEP”) for the Hope Farm Solar Generator Project to install a 10 MW solar array in Cranston,RI interconnecting to the Hope Substation via the 2228 23 kV feeder. | 2019-05-01 | Approved | 2019-04-02
NEP-19-G02 | 2019-02-22 | Hope Farm and Scituate Solar Generator Project | Generator application from New England Power Company (“NEP”) for the Scituate Solar Generator Project to install a 10 MW solar array in Scituate,RI and interconnecting to the Hope Substation via the 2228 23 kV feeder. | 2019-09-01 | Approved Withdrawn | 4/2/2019 2/16/2021
VW-19-G01 | 2019-03-06 | Vineyard Wind Generator and Transmission Project | Generator application from Vineyard Wind (“VW”) for the installation of 99 8.4 MW off-shore Siemens wind turbine generators (831 MWs total output). | 2021-05-01 | Approved | 2019-04-02
VW-19-T01 | 2019-03-06 | Vineyard Wind Generator and Transmission Project | Transmission application from Vineyard Wind (“VW”) for the installation of four off-shore 220/66 kV 225 MVA load tap changing autotransformers.In addition, construct 66kV switchgear bays connecting the array cable and 220kV switchgear bays connecting to the two export cables. | 2021-05-01 | Approved | 2019-04-02
VW-19-T02 | 2019-03-06 | Vineyard Wind Generator and Transmission Project | Transmission application from Vineyard Wind (“VW”) for the installation of two 220 kV submarine export cables and one 170 MVAR reactor and one 180 MVAR reactor. | 2021-05-01 | Approved | 2019-04-02
VW-19-T03 | 2019-03-06 | Vineyard Wind Generator and Transmission Project | Transmission application from Vineyard Wind (“VW”) for the construction of a 220/115 kV on-shore substation with 220 kV and 115 kV switchgear. Install two 450 MVA 115/220/33 kV tap changing autotransformers. Install two -200/+267 MVAR synchronous condensers each connected to the tertiary windings of the autotransformers. Install two variable shunt reactors (-50 to -160 MVAr and -60 to -180 MVAR). Also install two harmonic filters and associated fixed shunt reactors. | 2021-05-01 | Approved | 2019-04-02
VW-19-T04 | 2019-03-06 | Vineyard Wind Generator and Transmission Project | Transmission application from Vineyard Wind (“VW”) for the installation of two 220 kV terrestrial circuits buried in duct bank connecting offshore submarine cable circuits to VW onshore substation. Install two 115kV terrestrial cable bundle circuits buried in duct bank connecting VW onshore substation to existing bays at the 115kV Barnstable Switch Station. | 2021-05-01 | Approved | 2019-04-02
VW-19-T05 | 2019-03-06 | Vineyard Wind Generator and Transmission Project | Transmission application from Vineyard Wind (“VW”) for the installation of two +267/-200 MVAR synchronous condensers at each Vineyard Wind onshore substation transformer 33 kV winding terminal. | 2021-05-01 | Approved | 2019-04-02
ES-19-T06 | 2019-03-04 | Vineyard Wind Generator and Transmission Project | Transmission application from Eversource Energy (“ES”) for the installation of two new 115 kV circuit breakers, relays, controls and associated equipment at the Barnstable substation #958 in Barnstable, MA. | 2021-05-01 | Approved | 2019-04-02
ES-19-T07 | 2019-03-04 | Vineyard Wind Generator and Transmission Project | Transmission application from Eversource Energy (“ES”) to upgrade the protection systems at the Tremont Substation #713 in Wareham, MA to meet the NPCC BPS design requirements. | 2021-05-01 | Approved | 2019-04-02
ES-19-T08 | 2019-02-05 | North Bloomfield 2A-3X 115/23 kV Distribution Transformer Replacement | Transmission notification from Eversource Energy ("ES") for the replacement of the 2A-3X 115/23 kV distribution transformer at the North Bloomfield substation due to equipment failure. | 4/2019 | Notification | 2019-04-02
NRG-19-G01 | 2019-03-04 | Middletown 5 Generator Repowering Project | Generator application from NRG to interconnect a new combustion turbine facility with a maximum summer net power output of 376.0 MW (90˚F) and with a maximum winter net power output of 378.0 MW (20°F). The project consists of one combustion turbine to be connected at the existing Middletown 115 kV substation in Middletown, CT. QP647 is being considered as a repowering of Middletown Unit 2 and Unit 3. | 5/2022 | Approved Withdrawn | 4/2/2019 6/11/2020
NRG-19-T01 | 2019-03-04 | Middletown 5 Generator Repowering Project | Transmission application from NRG to interconnect the Middletown 5 GSU to the Middletown 115 kV substation Bus B between breakers 5T and 7T. | 2021-10-01 | Approved | 2019-04-02
MMWEC-19-G01 | 2019-03-05 | Berkshire Wind Expansion | Generator notification from MMWEC on behalf of Berkshire Wind for the installation of two 2.3 MW (4.6 MW total output) wind turbine additions in Lanesborough, MA and interconnecting to the Partridge 15E Substation via the 15E4 feeder which increase the total facility output to 19.6 MWs. | 2019-07-01 | Notification | 2019-04-02
ES-18-G14 | 2019-03-04 | SunJet Energy Bethlehem Solar | Generator notification from Eversource Energy (“ES”) on behalf of SunJET Energy LLC for the installation of 1.998 MW solar PV in Bethlehem, CT and interconnecting to the Carmel Hill Substation via the 11S15 23 kV feeder. | 2019-11-29 | Notification | 2019-04-02
VELCO-19-T01 | 2019-02-22 | Ascutney SVC Circuit Switcher Installation | Transmission notification from Vermont Electric Power Company ("VELCO") for the installation of a circuit switcher (fault current interrupter) on the 115 kV side of the Ascutney SVC 115/18 kV transformer at the SVC-10 switch location. | 6/2019 | Notification | 2019-04-02
NEP-19-GNF31 | 2019-03-01 | Cypress Creek South Street Douglas Solar | Generator notification from New England Power ("NEP") on behalf of Cypress Creek Renewables LLC for the installation of 4.99 MW solar PV in Douglas, MA and interconnecting to the Whitins Pond Substation via the 320W2 13.8 kV feeder. | 2020-04-11 | Notification | 2019-04-02
NEP-19-GNF06 | 2019-03-01 | Richmond Solar Power Solar | Generator notification from New England Power ("NEP") on behalf of Richmond Solar Power for the installation of 4.7 MW solar PV in Richmond, RI and interconnecting to the Wood River Substation via the 85T1 34.5 kV feeder. | 2019-01-29 | Notification | 2019-04-02
NEP-19-GNF03 | 2019-02-11 | Hopkinton Industrial Park Ashaway Solar | Generator notification from New England Power ("NEP") on behalf of Hopkinton Industrial Park for the installation of 2.5 MW solar PV in Ashaway, RI and interconnecting to the Chase Hill Substation via the 155F6 12.47 kV feeder. | 2019-08-28 | Notification | 2019-04-02
NEP-19-GNF02 | 2019-03-01 | Burrillville Solar | Generator notification from New England Power ("NEP") on behalf of Burrillville Solar LLC for the installation of 2.34 MW solar PV in Burrillville, RI and interconnecting to the Nasonville Substation via the 127W42 13.8 kV feeder. | 2019-04-30 | Notification | 2019-04-02
NEP-18-GNF25 Rev.1 | 2019-03-01 | 510 PV Project Development Plainville Solar and Battery Rev.1 | Generator notification from New England Power ("NEP") on behalf of 510 PV Project Development for the installation of 4.95 MW solar PV in Plainville, MA and interconnecting to the Plainville Substation via the 3451W3 13.8 kV feeder. The project is now adding a battery to the facility. | 2019-01-07 | Notification | 2019-04-02
NEP-19-GNF09 | 2019-03-01 | Green Development Victory Highway West Greenwich Solar | Generator notification from New England Power ("NEP") on behalf of Islander Solar for the installation of Green Development for the installation of 1.75 MW solar PV in West Greenwich, RI and interconnecting to the Hopkins Hill Substation via the 63F6 12.47 kV feeder. | 2019-07-03 | Notification | 2019-04-02
NEP-19-GNF15 | 2019-03-01 | Islander Iron Mine Hill Road North Smithfield Solar | Generator notification from New England Power ("NEP") on behalf of Islander Solar for the installation of 2.5 MW solar PV in North Smithfield, RI and interconnecting to the Woonsocket Substation via the 26W3 13.8 kV feeder. | 2020-01-01 | Notification | 2019-04-02
NEP-19-GNF20 | 2019-02-28 | Astrum Shipyard Street Providence Solar | Generator notification from New England Power ("NEP") on behalf of Astrum Solar for the installation of 2.77 MW solar PV in Providence, RI and interconnecting to the Point Street Substation via the 76F7 12.47 kV feeder. | 2020-01-15 | Notification | 2019-04-02
NEP-19-GNF01 | 2019-03-01 | Forbes Street East Providence Solar | Generator notification from New England Power ("NEP") on behalf of Forbes Street Solar LLC for the installation of 2.9 MW solar PV in East Providence, RI and interconnecting to the Wampanoag Substation via the 48F3 12.47 kV feeder. | 2019-03-01 | Notification | 2019-04-02
NEP-19-GNF10 | 2019-03-01 | Lighthouse Solar Ridge Road Smithfield Solar | Generator notification from New England Power ("NEP") on behalf of Lighthouse Solar for the installation of 2.0 MW solar PV in Smithfield, RI and interconnecting to the Farnum Pike Substation via the 23F6 12.47 kV feeder. | 2020-01-15 | Notification | 2019-04-02
NEP-19-GNF12 | 2019-03-01 | Green Development Buttonwoods Road Richmond Solar | Generator notification from New England Power ("NEP") on behalf of Green Development for the installation of 1.25 MW solar PV in Richmond, RI and interconnecting to the West Kenyon Substation via the 68F4 12.47 kV feeder. | 2019-07-03 | Notification | 2019-04-02
NEP-19-GNF17 | 2019-02-28 | Global Resources Michelle Way Johnston Solar | Generator notification from New England Power ("NEP") on behalf of Global Resources for the installation of 4.99 MW solar PV in Johnston, RI and interconnecting to the West Cranston Substation via the 18F6 12.47 kV feeder. | 2020-01-01 | Notification | 2019-04-02
NEP-19-GNF18 | 2019-02-28 | Infewsion Peck Hill Road Johnston Solar | Generator notification from New England Power ("NEP") on behalf of Infewsion LLC for the installation of 2.57 MW solar PV in Johnston, RI and interconnecting to the Johnston T4 Substation via the 21F2 12.47 kV feeder. | 2020-01-01 | Notification | 2019-04-02
NEP-19-GNF16 | 2019-03-01 | Cypress Creek Summer Street Franklin Solar | Generator notification from New England Power ("NEP") on behalf of Cypress Creek Summer Street PV for the installation of 2.5 MW solar PV in Franklin, MA and interconnecting to the East Union Street Substation via the 348W5 13.8 kV feeder. | 2020-03-15 | Notification | 2019-04-02
NEP-19-GNF08 | 2019-03-01 | Socore West Street Winchendon Solar | Generator notification from New England Power ("NEP") on behalf of West St. Solar LLC for the installation of 1.97 MW solar PV in Winchendon, MA and interconnecting to the East Winchendon Substation via the 612W1 13.8 kV feeder. | 2019-08-09 | Notification | 2019-04-02
ES-19-G03 | 2019-01-24 | Otis ANG Barnstable Battery Storage | Generator notification from Eversource Energy ("ES") on behalf of South Energy Investments for the installation of a 1.6 MW battery storage system in Barnstable, MA and interconnecting to the Otis Substation via the 79 23 kV feeder. | 2019-04-01 | Notification | 2019-02-21
ES-19-G15 | 2019-01-24 | Cambridge Solar | Generator notification from Eversource Energy ("ES") on behalf of the City of Cambridge for the installation of 1.1 MW solar PV in Cambridge, MA and interconnecting to the East Cambridge Substation via the 875-1312 and 875-1317 14kV kV feeder. | 2019-10-01 | Notification | 2019-02-20
NEP-19-G03 | 2019-01-29 | Nantucket Combustion Turbine Generator | Generator application from New England Power Company (“NEP”) for the installation of a 15 MW combustion turbine generator in Nantucket, MA and interconnecting to the Nantucket Electric distribution system in Nantucket, MA at the 13.2 kV Bunker Rd substation. | 5/2019 | Approved | 2019-02-20
NEP-19-G04 | 2019-01-29 | Nantucket Battery Energy Storage System | Generator application from New England Power Company (“NEP”) for the installation of a 6 mw/48 MWh battery energy storage system in Nantucket, MA and interconnecting to the Nantucket Electric distribution system in Nantucket, MA at the 13.2 kV Bunker Rd substation. | 5/2019 | Approved | 2019-02-20
ES-19-G13 | 2019-01-10 | Beluga Colchester Solar | Generator notification from Eversource Energy ("ES") on behalf of Beluga Solar LLC for the installation of 1.0014 MW solar PV in Colchester, CT and interconnecting to the Judd Brook 32R Substation via the 32R3 23 kV feeder. | 2020-06-01 | Notification Withdrawn | 2/20/2019 6/18/2024
ES-19-G02 | 2019-01-24 | OTIS ANG Barnstable Wind Turbine | Generator notification from Eversource Energy ("ES") on behalf of AFCEE for the installation of a 1.5 MW wind turbine in Barnstable, MA and interconnecting to the Otis Substation via the 79 23 kV feeder. | 2019-04-01 | Notification | 2019-02-20
ES-19-T02 | 2019-01-30 | Neutral Grounding Reactor Installation at Mystic | Transmission application from Eversource Energy (ES) for the installation of a neutral grounding reactor on the Mystic Station autotransformers 345A and 345B. Reactor Rating is 7 ohm, 34.5 kV, 200 kV BIL. | 2019-06-01 | Notification | 2019-02-13
ES-19-T03 | 2019-01-30 | Neutral Grounding Reactor Installation at K Street | Transmission application from Eversource Energy (ES) for the installation of a neutral grounding reactor on the K Street Station autotransformers 345A and 345B. Reactor Rating is 7 ohm, 34.5 kV, 200 kV BIL. | 2019-06-01 | Notification | 2019-02-13
ES-19-G12 | 2018-12-04 | Independence Old Lyme Solar | Generator notification from Eversource Energy ("ES") on behalf of Independence Solar for the installation of 1.995 MW solar PV in Old Lyme, CT and interconnecting to the Flanders 11Y 115 kV Substation via the 11Y7 23 kV feeder. | 2019-03-29 | Notification | 2019-01-28
ES-19-G11 | 2019-01-02 | South Energy Investments South Windsor Generator | Generator notification from Eversource Energy ("ES") on behalf of South Energy Investments for the installation of a 4.99 MW natural gas generator in South Windsor, CT and interconnecting to the South Windsor 14L 115 kV Substation via the 14L5 13.8 kV feeder. | 2019-03-31 | Notification | 2019-01-28
NEM-19-G01 | 2019-01-07 | Constitution Solar Generator Project | Generator application from NextEra Energy Resources (“NEM”) for the construction of a 20 MW (net output) solar array located in Plainfield, CT and interconnecting to the Frybrook 23 kV Substation. | 2019-11-01 | Approved Withdrawn | 1/28/2019 2/15/2023
UI-19-01 | 2019-01-08 | Railroad Corridor Transmission Line Rebuild | Transmission notification from Avangrid/United Illuminating (“UI”) for the rebuild of the 8809A-2 line (Pequonnock - Congress) with 1590 kcmil ACSS. | 2025-01-31 | Notification | 2019-01-28
UI-19-02 | 2019-01-08 | Railroad Corridor Transmission Line Rebuild | Transmission notification from Avangrid/United Illuminating (“UI”) for the rebuild of the 8909B-2 line (Pequonnock - Congress) with 1590 kcmil ACSS. | 2025-01-31 | Notification | 2019-01-28
UI-19-03 | 2019-01-08 | Railroad Corridor Transmission Line Rebuild | Transmission notification from Avangrid/United Illuminating (“UI”) to rebuild a portion of the 1130 line (Pequonnock - UI Str. B737) with 1590 kcmil ACSS. | 2028-04-30 | Notification | 2019-01-28
UI-19-04 | 2019-01-08 | Railroad Corridor Transmission Line Rebuild | Transmission notification from Avangrid/United Illuminating (“UI”) for the rebuild of the 1430 line (Ash Creek - ESE Str. B648) with 1590 kcmil ACSS. | 2028-04-30 | Notification | 2019-01-28
UI-19-05 | 2019-01-08 | Railroad Corridor Transmission Line Rebuild | Transmission notification from Avangrid/United Illuminating (“UI”) for the rebuild of the 91001-1 line (Pequonnock - Bridgeport Resco) and the 91001-2 line (Bridgeport Resco - Ash Creek) with 1590 kcmil ACSS. | 2026-08-31 | Notification | 2019-01-28
UI-19-06 | 2019-01-08 | Railroad Corridor Transmission Line Rebuild | Transmission notification from Avangrid/United Illuminating (“UI”) for the rebuild of the 88005A-1 line (Milvon - Woodmont) with 1590 kcmil ACSS. | 2028-05-31 | Notification | 2019-01-28
UI-19-07 | 2019-01-08 | Railroad Corridor Transmission Line Rebuild | Transmission notification from Avangrid/United Illuminating (“UI”) for the rebuild of the 89005B-1 line (Milvon - Woodmont) with 1590 kcmil ACSS. | 2028-05-31 | Notification | 2019-01-28
UI-19-08 | 2019-01-08 | Railroad Corridor Transmission Line Rebuild | Transmission notification from Avangrid/United Illuminating (“UI”) for the rebuild of the 8804A line (Woodmont - Allings Crossing) with 1590 kcmil ACSS. | 2026-04-30 | Notification | 2019-01-28
UI-19-09 | 2019-01-08 | Railroad Corridor Transmission Line Rebuild | Transmission notification from Avangrid/United Illuminating (“UI”) for the rebuild of the 8904B line (Woodmont - Allings Crossing) with 1590 kcmil ACSS. | 2026-04-30 | Notification | 2019-01-28
UI-19-10 | 2019-01-08 | Railroad Corridor Transmission Line Rebuild | Transmission notification from Avangrid/United Illuminating (“UI”) for the rebuild of the 88003A-3 line (Allings Crossing - Elmwest) with 1590 kcmil ACSS. | 2024-01-31 | Notification | 2019-01-28
UI-19-11 | 2019-01-08 | Railroad Corridor Transmission Line Rebuild | Transmission notification from Avangrid/United Illuminating (“UI”) for the rebuild of the 89003B-3 line (Allings Crossing - Elmwest) with 1590 kcmil ACSS. | 2024-01-31 | Notification | 2019-01-28
UI-19-12 | 2019-01-08 | Railroad Corridor Transmission Line Rebuild | Transmission notification from Avangrid/United Illuminating (“UI”) for the rebuild of the 88003A-2 line (Elmwest - West River) with 1590 kcmil ACSS. | 2024-10-31 | Notification | 2019-01-28
UI-19-13 | 2019-01-08 | Railroad Corridor Transmission Line Rebuild | Transmission notification from Avangrid/United Illuminating (“UI”) for the rebuild of the 89003B-2 line (Elmwest - West River) with 1590 kcmil ACSS. | 2024-10-31 | Notification | 2019-01-28
ES-19-T01 | 2019-01-02 | Southington 115 kV Circuit Breaker Installation | Transmission notification from Eversource Energy ("ES") for the installation of a 115 kV circuit breaker located between the high side of the 115/13.8kV 6X transformer and the ring bus R1 at Southington 4C Substation. The Project is designed to provide the isolation of 4C-6X when the transformer fails and prevent bus interruption and tripping of the bus tie reactor as a result of a bulk transformer fault. | 2019-12-31 | Notification | 2019-01-28
ES-19-01 | 2018-12-17 | Hanscom Bedford CHP Generator Project | Generator application from Eversource Energy (“ES”) for the construction of a 5.177 MW (gross output) Combined Heat and Power (CHP) generator in Bedford, MA and interconnecting to the 115/14 kV Lexington Substation via the 319-1377H and 319-1379H feeders. | 1/2019 | Approved | 2019-01-28
NEP-18-GNF24 Rev.1 | 2018-12-04 | Clean Footprint Winchendon Solar Rev.1 | Generator notification from New England Power ("NEP") on behalf of Clean Footprint LLC for the installation of a 3.1 MW solar PV in Winchendon, MA and interconnecting to the East Winchendon Substation via the 13.8 kV 612W1 feeder. | 2018-10-22 | Notification | 2018-12-20
NEP-18-GNF33 | 2018-11-02 | Blackstone River Road Worcester Solar | Generator notification from New England Power (“NEP”) on behalf of Solect Energy Development for the installation of 1.992 MW solar PV in Worcester, MA and interconnecting to the Vernon Hill Substation via the 13.8 kV 8W2 feeder. | 2018-11-14 | Notification | 2018-12-20
NEP-18-GNF32 | 2018-11-02 | Oxford Community Solar | Generator notification from New England Power (“NEP”) on behalf of Oxford Community Solar for the installation of 4.0 MW solar PV in Oxford, MA and interconnecting to the North Oxford Substation via the 13.2 kV 406L4 feeder. | 2019-03-31 | Notification | 2018-12-20
NEP-18-GNF31 | 2018-11-02 | Spencer Landfill Solar | Generator notification from New England Power (“NEP”) on behalf of Spencer Landfill Solar for the installation of 2.95 MW solar PV in Spencer, MA and interconnecting to the Meadow Street Substation via the 13.2 kV 552L3 feeder. | 2019-01-08 | Notification | 2018-12-20
NEP-18-T25 | 2018-12-03 | Golden Rock/Rockingham Substation Phase II Project | Transmission application from New England Power Company (“NEP”) for the construction of two new 115 kV tap circuits off the G-133W and G-133 circuits from the Golden Rock substation to the NG/LU border in Salem, NH. | 6/2021 | Approved | 2018-12-20
LU-18-T01 | 2018-12-03 | Golden Rock/Rockingham Substation Phase II Project | Transmission application from Liberty Utilities (“LU”) for the construction of a new 115/13.2 kV Rockingham Substation with eight 13.2 kV feeders and 115 kV tap circuits off NEP’s extension of the 115 kV G-133 and G-133W Lines. | 6/2021 | Approved | 2018-12-20
ES-18-G95 | 2018-12-05 | Pawcatuck Solar Generator Project | Generator application from Eversource Energy ("ES") on behalf of Pawcatuck Solar LLC for the construction of a 15 MW solar array located in North Stonington, CT and interconnecting via a 13.8 kV feeder to the 115 kV Shunock Substation. | 2019-09-30 | Approved | 2018-12-20
ES-18-G93 | 2018-11-21 | UMass Amherst Battery Storage | Generator notification from Eversource Energy ("ES") for the installation of a 1.2 MW battery storage facility in Amherst, MA and interconnecting to the Tilson Substation via the 13.8 kV A2 feeder. | 2019-02-01 | Notification | 2018-12-20
ES-17-T03 Rev.1 | 2018-11-20 | Line 108-4 Reconductor Bourne to Valley Rev.1 | Reconductor of the existing 2.6 mile overhead 115 kV Line 108-4 from Bourne Substation in Bourne, MA to Valley Substation in Plymouth, MA with 795 ACSS. Proposed in service date of the project is November, 2018. This revision to the previously approved PPA is to describe a change of scope of the proposed project such that the reconductoring does not include the crossing of the Cape Cod Canal. | 2018-11-01 | Notification | 2018-12-20
NEP-18-T01 Rev.1 | 2018-12-04 | Bell Rock Substation Expansion Rev.1 | The Bell Rock substation expansion is part of the 2026 Southeast Massachusetts and Rhode Island (SEMA/RI) Reliability Solution projects. The previously approved PPA has been revised to reflect change in position of 115/34.5 kV distribution transformer #E from the 115 kV bus to the L14 line due to constructability reasons. | 11/2020 | Notification | 2018-12-20
ES-18-G24 | 2018-10-26 | BlueWave Capital Wareham Solar Generator Project | Generator application from Eversource Energy (“ES”) on behalf of BlueWave Capital Wareham for the installation of a 1.495 MW (net output) solar array in Wareham, MA and interconnecting to the Wareham Station #714 substation via a new 23 kV feeder. | 2018-12-15 | Approved | 2018-11-21
ES-18-G25 | 2018-10-26 | BlueWave Capital Wareham Solar Generator Project | Generator application from Eversource Energy (“ES”) on behalf of BlueWave Capital Wareham for the installation of a 0.995 MW (net output) solar array in Wareham, MA and interconnecting to the Wareham Station #714 substation via a new 23 kV feeder. | 2018-12-15 | Approved | 2018-11-21
ES-18-G26 | 2018-10-26 | BlueWave Capital Wareham Solar Generator Project | Generator application from Eversource Energy (“ES”) on behalf of BlueWave Capital Wareham for the installation of a 1.495 MW (net output) solar array in Wareham, MA and interconnecting to the Wareham Station #714 substation via a new 23 kV feeder. | 2018-12-15 | Approved | 2018-11-21
ES-18-G27 | 2018-10-26 | BlueWave Capital Wareham Solar Generator Project | Generator application from Eversource Energy (“ES”) on behalf of BlueWave Capital Wareham for the installation of a 3.995 MW (net output) solar array in Wareham, MA and interconnecting to the Wareham Station #714 substation via a new 23 kV feeder. | 2018-12-20 | Approved | 2018-11-21
ES-18-G83 | 2018-10-18 | Harvard Boston CHP Generator | Generator notiofication from Eversource ("ES") on behalf of Harvard University for the installation of a 2.39 MW CHP generator in Boston, MA and interconnecting to the Thornton Substation via the 14 kV 144-122H and 144-138H feeder. | 8/2019 | Notification | 2018-11-21
CED-18-G01 | 2018-10-12 | CED Northampton Solar | Generator notificationfrom ConEd Development ("CED") for the installation of 4.3 MW solar PV in Northampton, MA and interconnecting to the Florence Junction substation via the 13.8 kV 09-909-W4 feeder. | 2018-12-31 | Notification | 2018-11-21
NEP-18-T24 | 2018-10-19 | Salem Harbor Transformer Replacement | Transmission notification from New England Power ("NEP") for the replacement of two 115/23 kV transformers rated at 45/60/75 MVA at the Salem Harbor Substation in Salem, MA. | 2021-08-01 | Notification | 2018-11-21
ES-18-T36 | 2018-10-19 | Montague 21C-4X 115/13.8 kV Transformer Replacement | Transmission notifcation from Eversource Energy ("ES") for the replacement of the 21C-4X 115/13.8 kV transformer rated at 65.5/81.1/98.2 MVA at the Montague Substation in Montague, MA. | 2019-05-31 | Notification | 2018-11-21
ES-18-T38 | 2018-10-19 | Gunn 15A 115/23 kV Transformer Replacement | Transmission notifcation from Eversource Energy ("ES") for the replacement of the 15A 115/23 kV transformer rated at 62.5/69.6/93.8 MVA at the Gunn Substation in Easthampton, MA. | 12/2018 | Notification | 2018-11-21
NEP-18-GNF29 | 2018-10-02 | Amazon Innovation Way Fall River Solar | Generator notification from New England Power Company (“NEP”) on behalf of Amazon for the installation of 2.1 MW solar PV in Fall River, MA and interconnecting to the Sykes Road Substation via the 13.8 28W50 feeder. | 2018-12-01 | Notification | 2018-11-21
NEP-18-GNF27 | 2018-10-02 | Dynamic Energy Goshen Solar | Generator notification from New England Power Company (“NEP”) on behalf of Dynamic Energy Solutions LLC for the installation of 3.995 MW solar PV in Goshen, MA and interconnecting to the Florence Junction Substation via the 13.8 909W3 feeder. | 2019-03-04 | Notification | 2018-11-21
NEP-18-GNF34 | 2018-11-02 | Housatonic Johnston Solar | Generator notification from New England Power Company (“NEP”) on behalf of Housatonic Solar LLC for the installation of 3.0 solar PV in Johnston, RI and interconnecting to the Johnston Substation via the 12.47 18F6 feeder. | 2018-11-17 | Notification | 2018-11-21
NEP-18-GNF30 | 2018-11-02 | LDSP 12 Shutesbury Solar | Generator notification from New England Power Company (“NEP”) on behalf of Direct Energy for the installation of 4.5 MW solar PV in Shutesbury, MA and interconnecting to the Shutesbury Substation via the 13.8 kV 704W1 feeder. | 2019-02-05 | Notification | 2018-11-21
NEBS-18-G01 | 2018-09-28 | New England Battery Storage Madison Battery | Generator notification from New England Battery Storage ("NEBS") for the installation of a 4.99 MW battery in Madison, ME and interconnecting to the Jones Street Substation 34.5 kV feeder. | 2019-04-01 | Notification | 2018-10-24
NEP-18-GNF26 | 2018-10-02 | Direct Energy Hopkinton Solar | Generator notification from New England Power Company (“NEP”) on behalf of Direct Energy for the installation of 1.165 MW solar PV in Hopkinton, MA and interconnecting to the Chace Hill Substation via the 12.47 155F6 feeder. | 2018-11-21 | Notification | 2018-10-24
NEP-18-GNF28 | 2018-10-02 | Southern Sky A Street Johnston Solar | Generator notification from New England Power Company (“NEP”) on behalf of Southern Sky for the installation of 3.22 MW solar PV in Johnston, RI and interconnecting to the Johnston Substation via the 12.47 18F11 feeder. | 2018-11-14 | Notification | 2018-10-24
VEC-18-G04 | 2018-09-13 | VESI VEC Hinesburg Battery | Generator notification from Vermont Electric CoOp on behalf of VESI VEC, LLC for the installation of a 1.9 MW battery in Hinesburg, VT and interconnecting to the Hinesburg Substation via the 19-3A feeder. | 2019-06-30 | Notification | 2018-10-24
NEM-18-G01 | 2018-09-11 | Quinebaug Solar Generator and Transmission Project | Generator application from NextEra Energy Resources (“NEM”) on behalf of Quinebaug Solar, LLC for the installation of a 49.9 MW solar array in Brooklyn and Canterbury, CT and interconnecting to the new Canterbury 67F switching station. | 2020-07-01 | Approved | 2018-10-24
NEM-18-T01 | 2018-09-11 | Quinebaug Solar Generator and Transmission Project | Transmission application from NextEra Energy Resources (“NEM”) on behalf of Quinebaug Solar, LLC for the installation of a 115/34.5/13.8 kV 33/44/55 MVA GSU transformer at the new Canterbury 67F switching station. | 2020-07-01 | Approved | 2018-10-24
ES-18-T53 | 2018-09-11 | Quinebaug Solar Generator and Transmission Project | Transmission application from Eversource Energy (“ES”) for the addition of three 115-kV circuit breakers and bus work to create a three-breaker ring bus design substation Canterbury 115-kV. The bifurcation of the existing 115-kV 1607-4 Line between Killingly Substation in Killingly and Exeter Tap in Plainfield, CT to create the 1607-4N Line between Killingly Substation in Killingly, CT and Canterbury Substation in Canterbury, CT and the installation of protective relays. | 2020-07-01 | Approved | 2018-10-24
ES-18-T34 | 2018-09-11 | Quinebaug Solar Generator and Transmission Project | Transmission application from Eversource Energy (“ES”) for rebuilding the approximately 0.5-mile long transmission section from the Montville 115 kV substation to the Bean Hill substation (Line 1000) and the Tunnel 115 kV substation (1080 Line), where the 1000 and 1080 115-kV lines share common towers such that each line will have separate towers. The project is required to eliminate adverse impact that resulted from the proposed queued generator project QP588. Conductor type, thermal ratings, and protection relaying for the 1000 and 1080 115-kV lines will not change as a result of the project. | 2020-07-01 | Approved | 2018-10-24
ES-18-G82 | 2018-09-20 | Fidelity Merrimack Solar | Generator notification from Eversource Energy ("ES") on behalf of Devonshire Energy for the installation of 2.4 MW in Merrimack, NH and interconnecting to the Thornton Substation via the 34.5 kV 3241X feeder. | 2018-12-31 | Notification | 2018-10-24
NEP-18-G13 | 2018-08-23 | Dynamic Energy Solar Project | Generator application from New England Power Company (“NEP”) on behalf of Dynamic Energy Solutions LLC for the Winchendon Ash Street Solar Project for the installation of a 5.97 MW solar array in Winchendon, MA and interconnecting to the East Winchendon substation via the 13.8 kV 612W1 feeder. | 2018-12-31 | Approved | 2018-10-11
NEP-18-G14 | 2018-08-23 | Dynamic Energy Solar Project | Generator application from New England Power Company (“NEP”) on behalf of Dynamic Energy Solutions LLC for the Winchendon Lincoln Avenue Solar Project for the installation of an 8.04 MW solar array in Winchendon, MA and interconnecting to the East Winchendon substation via the 13.8 kV 612W3 feeder. | 2018-12-31 | Approved | 2018-10-11
NEP-18-G09 | 2018-08-31 | University Solar Generator Project | Generator application from New England Power Company (“NEP”) on behalf of University Solar LLC for the installation of an 8 MW solar array in West Greenwich, RI and interconnecting to the Kent County #22 substation via the 34.5 kV 3311 feeder. | 5/2019 | Approved | 2018-10-11
NEP-18-G10 | 2018-08-31 | University Solar Generator Project | Generator application from New England Power Company (“NEP”) on behalf of University Solar LLC for the installation of an 8 MW solar array in West Greenwich, RI and interconnecting to the Kent County #22 substation via the 34.5 kV 3311 feeder. | 5/2019 | Approved | 2018-10-11
NEP-18-G11 | 2018-08-31 | University Solar Generator Project | Generator application from New England Power Company (“NEP”) on behalf of University Solar LLC for the installation of an 8 MW solar array in West Greenwich, RI and interconnecting to the Kent County #22 substation via the 34.5 kV 3311 feeder. | 5/2019 | Approved | 2018-10-11
NEP-18-G12 | 2018-08-31 | University Solar Generator Project | Generator application from New England Power Company (“NEP”) on behalf of University Solar LLC for the installation of a 7.34 MW solar array in West Greenwich, RI and interconnecting to the Kent County #22 substation via the 34.5 kV 3311 feeder. | 5/2019 | Approved | 2018-10-11
NEP-18-G07 | 2018-08-31 | Turning Point Solar Generator Project | Generator application from New England Power Company (“NEP”) on behalf of Turning Point Energy LLC for the installation of a 7 MW solar array in North Kingstown, RI and interconnecting to the Tower Hill #88 substation via the 12.47 kV 88F3 feeder. | 4/2019 | Approved Withdrawn | 10/11/2018 11/16/2021
NEP-18-G08 | 2018-08-31 | Turning Point Solar Generator Project | Generator application from New England Power Company (“NEP”) on behalf of Turning Point Energy LLC for the installation of a 6.12 MW solar array in North Kingstown, RI and interconnecting to the Tower Hill #88 substation via the 12.47 kV 88F3 feeder. | 4/2019 | Approved Withdrawn | 10/11/2018 11/16/2021
NEP-18-T23 | 2018-09-10 | West Cranston Transformer Replacement | Transmission notification from New England Power ("NEP") to replace the existing 115/13.2 kV 12/16/20 MVA West Cranston Substation transformer in Cranston, RI with a new, larger unit rated at 24/32/40 MVA. | 11/2018 | Notification | 2018-10-11
EM-18-G01 | 2018-09-14 | Cutler Navy Backup Generator | Generator notification from Emera Maine ("EM") on behalf of NAVFAC MIDLANT for the installation of a 3.0 MW diesel generator in Cutler, ME and interconnecting to the Bucks Harbor Substation via the 21 feeder. | 2018-10-01 | Notification | 2018-10-11
ES-19-G63 | 2018-07-31 | Bay State Wind Generation and Transmission Project | Generator application from Eversource Energy (“ES”) on behalf of Bay State Wind LLC for the installation of a 105 8 MW off-shore wind turbine generators (840 MW net output) in Massachusetts and interconnecting to the 345 kV Brayton Point Substation in Somerset, MA. | 2023-05-31 | Approved Withdrawn | 10/11/2018 8/10/2022
ES-18-T26 | 2018-07-31 | Bay State Wind Generation and Transmission Project | Transmission application from Eversource Energy (“ES”) for the installation of two 140 MVAR STATCOMs at the Bay State Wind 345kV/275kV substation, in Somerset, MA. | 2021-01-31 | Approved Withdrawn | 10/11/2018 8/10/2022
ES-18-T27 | 2018-07-31 | Bay State Wind Generation and Transmission Project | Transmission application from Eversource (“ES”) Energy for the installation of a two 345/275 kV transformers at the Bay State Wind 345kV/275kV substation, in Somerset, MA. | 2021-01-31 | Approved Withdrawn | 10/11/2018 8/10/2022
ES-18-T28 | 2018-07-31 | Bay State Wind Generation and Transmission Project | Transmission application from Eversource Energy (“ES”) for the installation of two 59 mile 275 kV submarine cables from the Bay State Wind 275kV/66kV substation, off-shore to the Bay State Wind 345kV/275kV substation in Somerset, MA. | 2021-01-31 | Approved Withdrawn | 10/11/2018 8/10/2022
ES-18-T29 | 2018-07-31 | Bay State Wind Generation and Transmission Project | Transmission application from Eversource Energy (“ES”) for the installation of two 275/66 kV transformers at the Bay State Wind off shore substation. | 2018-01-31 | Approved Withdrawn | 10/11/2018 8/10/2022
ES-18-T30 | 2018-07-31 | Bay State Wind Generation and Transmission Project | Transmission application from Eversource Energy (“ES”) for the installation of a two .52 mile underground 3500 kcmil CU XLPE 345 kV line from Brayton Point Substation to Bay State Wind 1 345/275 kV. | 2018-01-31 | Approved Withdrawn | 10/11/2018 8/10/2022
NEP-18-T22 | 2018-07-25 | Bay State Wind Generation and Transmission Project | Transmission application from New England Power Company (“NEP”) for the expansion and upgrade of the Brayton Point Substation from the present ring bus configuration to a breaker and a half configuration and install four new 345 kV breakers in support of the Bay State Wind project. | 2018-01-31 | Approved Withdrawn | 10/11/2018 8/10/2022
ES-18-G28 | 2018-09-04 | Borrego Plympton Solar | Generator notification from Eversource Energy ("ES") on behalf of Borrego Solar for the installation of 4.95 MW solar PV in Plympton, MA and interconnecting to the Brook Street #727 Substation via the 23 kV 3-51-901 feeder. | 2018-10-01 | Notification | 2018-10-11
ES-18-T32 | 2018-07-16 | Brighton Substation Transformer Replacement | Transmission notifcation from Eversource Energy ("ES") for the in-kind replacement of the existing 100MVA 110B transformer bank vintage 1955 at Brighton Substation #329 in Brighton, MA. The transformer will be replaced by a new HICO 90 MVA ,117/14 kV bank. | 11/2018 | Notification | 2018-10-11
VELCO-18-GNF01 | 2018-09-17 | Martin Brook Williamstown Solar | Generator notification from Vermont Electric Power Company ("VELCO") on behalf Martin Brook PV, LLC for the installation of 1.485 MW solar PV in Williamstown, VT and interconnecting to the Websterville Substation via the GMP 3305 feeder. | 2018-10-31 | Notification | 2018-10-11
NEP-14-GNF12 Rev.1 | 2018-09-17 | SunEdison Origination Reboth Solar | Generator notification from New England Power ("NEP") on behalf of SunEdison Origination for the installation of 4.0 MW solar PV revision in Reboth, MA and changing the interconnecting to the South Wrentham Substation via the 23 kV 2248 feeder. | 2014-06-30 | Notification | 2018-10-11
NEP-18-GNF25 | 2018-09-18 | 510 Project Development Plainville Solar | Generator notification from New England Power ("NEP") on behalf of 510 Project Development for the installation of 4.95 MW solar PV in Plainville, MA and interconnecting to the Plainville Substation via the 13.8 kV 3451W2 feeder. | 2019-01-07 | Notification | 2018-10-11
NEP-18-GNF24 | 2018-09-18 | Clean Footprint Winchendon Solar | Generator notification from New England Power ("NEP") on behalf of Clean Footprint for the installation of 2.7 MW solar PV in Winchendon, MA and interconnecting to the East Winchendon Substation via the 13.8 kV 612W1 feeder. | 2018-10-22 | Notification | 2018-10-11
NEP-18-GNF23 | 2018-09-18 | Nextamp Ashburnham 1 & 2 Westminster Solar | Generator notification from New England Power ("NEP") on behalf of Nextamp for the installation of 1.449 MW solar PV in Westminster, MA and interconnecting to the Ashburnham Substation via the 13.8 kV 610W3 feeder. | 2018-11-11 | Notification | 2018-10-11
NEP-18-GNF22 | 2018-09-18 | Green Development Flat River Road Coventry Solar | Generator notification from New England Power ("NEP") on behalf of Green Development, LLC for the installation of 3.0 MW solar PV in Coventry, RI and interconnecting to the Coventry Substation via the 12.47 kV 54F1 feeder. | 2018-12-18 | Notification | 2018-10-11
NEP-18-GNF21 | 2018-09-18 | Southern Sky Kilvert Street Warwick Solar | Generator notification from New England Power ("NEP") on behalf of Southern Sky for the installation of 4.992 MW solar PV in Warwick, RI and interconnecting to the Kilvert Street Substation via the 12.47 kV 87F2 feeder. | 2018-11-19 | Notification | 2018-10-11
NEP-18-GNF20 | 2018-09-19 | Southern Sky Plainfield Place North Providence Solar | Generator notification from New England Power ("NEP") on behalf of Southern Sky for the installation of 4.116 MW solar PV in North Providence, RI and interconnecting to the West Cranston Substation via the 12.47 kV 23F6 feeder. | 2018-10-31 | Notification | 2018-10-11
NEP-18-GNF19 | 2018-09-18 | Green Development George Washington Highway Lincoln Solar | Generator notification from New England Power ("NEP") on behalf of Green Development, LLC for the installation of 3.0 MW solar PV in Lincoln, RI and interconnecting to the Washington Substation via the 13.8 kV 126W42 feeder. | 2018-11-01 | Notification | 2018-10-11
NEP-18-GNF18 | 2018-09-18 | Southern Sky Plainfield Place Johnston Solar | Generator notification from New England Power ("NEP") on behalf of Southern Sky for the installation of 2.01 MW solar PV in Johnston, RI and interconnecting to the West Cranston Substation via the 21F2 feeder. | 2018-11-14 | Notification | 2018-10-11
NEP-18-GNF17 | 2018-09-17 | Green Development West Main Middletown Solar | Generator notification from New England Power ("NEP") on behalf of Green Development, LLC for the installation of 2.5 MW solar PV in Middletown, RI and interconnecting to the Jepson Substation via the 23 kV 37K33 feeder. | 2018-11-14 | Notification | 2018-10-11
CMP-18-G01 | 2018-08-31 | Barefoot Fairfield Solar | Generator notification from Avangrid on behalf of USA SPV 1 Barefoot LLC for the installation of 4.32 MW solar PV in Fairfield, ME and interconnecting to the Fairfield 34.5 kV Substation via the 817D3 feeder. | 2018-12-15 | Notification | 2018-10-11
ES-18-G72 | 2018-09-06 | Amazon DEDC Windsor Solar | Generator notification from Eversource Energy ("ES") on behalf of Amazon DEDC for the installation of 1.488 MW solar PV in Windsor, CT and interconnecting to the Bloomfield 3B Substation via the 3B02 23 kV feeder. | 2018-09-30 | Notification | 2018-10-11
ES-18-G43 | 2018-08-01 | Applied Golf Hickory Ridge Amherst Solar | Generator notification from Eversource Energy ("ES") on behalf of Applied Golf Hickory Ridge for the installation of 4.98 MW solar PV in Tolland, MA and interconnecting to the Amherst 17 K via the 17K8 feeder. | 2019-04-01 | Notification | 2018-10-11
ES-18-G42 | 2018-07-24 | BWC Crystal Springs Road Mattapoisett Solar Project | Generator application from Eversource Energy ("ES") on behalf of BWC Origination LLC for the installation of 4.75 MW photovoltaic generator in Mattapoisett, MA and interconnecting to the Crystal Springs Substation #636 via the new express 13.2 kV feeder to be constructed. | 2018-09-01 | Approved | 2018-08-30
ES-18-G60 | 2018-07-26 | Roberts Brothers Lumber Ashfield Biomass Generator | Generator notification from Eversource Energy (“ES”) on behalf of Roberts Brothers Lumber Co. for the installation of a 2.0 MW biomass generator in Ashfield, MA and interconnecting to the Ashfield 38A Substation via the 38A1 feeder. | 2019-07-01 | Notification Withdrawn | 8/30/2018 8/15/2023
ES-18-G58 | 2018-07-18 | Trinity College Hartford Generator | Generator notification from Eversource Energy (“ES”) on behalf of Broad Street Fuel Cell for the installation of a 1.38 MW natural gas generator in Hartford, CT and interconnecting to the South Meadow 1A Substation via the 147 feeder. | 2018-09-14 | Notification | 2018-08-30
ES-18-G37 | 2018-07-27 | Greenfield Solar | Generator notification from Eversource Energy (“ES”) on behalf of the City of Greenfield for the installation of 1.2 MW solar PV in Greenfield, MA and interconnecting to the Montague 21C Substation via the 21C1 feeder. | 2019-01-01 | Notification | 2018-08-30
ES-18-G30 | 2018-07-18 | Rocky Hill Solar | Generator notification from Eversource Energy (“ES”) on behalf of the Town of Rocky Hill for the installation of 3.0 MW solar PV in Rocky Hill, CT and interconnecting to the Rocky Hill 3R Substation via the 3R02 feeder. | 2018-09-14 | Notification | 2018-08-30
ES-18-G45 | 2018-07-06 | CVE North America Tolland Solar | Generator notification from Eversource Energy (“ES”) on behalf of CVE North America, Inc. for the installation of 4.98 MW solar PV in Tolland, MA and interconnecting to the Blandford 19J Substation via the 19J4 feeder. | 2019-07-01 | Notification | 2018-08-30
ES-18-G48 | 2018-07-06 | Citizens Oak Street Springfield Solar | Generator notification from Eversource Energy (“ES”) on behalf of Citizens Oak Street Solar for the installation of 3.5 MW solar PV in Springfield, MA and interconnecting to the Orchard 27A Substation via the 27A13 feeder. | 2019-07-01 | Notification | 2018-08-30
ES-18-G32 | 2018-07-18 | Becton Dickinson North Canaan Solar | Generator notification from Eversource Energy (“ES”) on behalf of Beckton Dickinson & Co for the installation of 1.98 MW solar PV in North Canaan, CT and interconnecting to the North Canaan 5L 69 kV Substation via the 13,2 kV feeder. | 2018-09-14 | Notification | 2018-08-30
NEP-18-G04 | 2018-07-27 | Southern Sky Solar Generation Project | Generation application from New England Power ("NEP") for the Southern Sky 5 MW PV Project (RI-23731163) at Hopkinton, RI. The generating facility will include forty SUNGROW SG125HV, 600 V, 125 kW/kVA inverters and associated customer owned equipment. The plant will connect to the Narragansett Electric distribution system in Hopkinton, RI on the 34.5kV feeder 85T1 out of the Wood River #85 station | 2/2019 | Approved | 2018-08-30
NEP-18-G05 | 2018-07-27 | Southern Sky Solar Generation Project | Generation application from New England Power ("NEP") for the Southern Sky 3.875 MW PV Project (RI-23731212) at Hopkinton, RI. The generating facility will include thirty one SUNGROW SG125HV, 600 V, 125 kW/kVA inverters and associated customer owned equipment. The plant will connect to the Narragansett Electric distribution system in Hopkinton, RI on the 34.5kV feeder 85T1 out of the Wood River #85 station. | 2/2019 | Approved | 2018-08-30
NEP-18-G06 | 2018-07-27 | Southern Sky Solar Generation Project | Generation application from New England Power ("NEP") for the Southern Sky 5 MW PV Project (RI-23731230) at Hopkinton, RI. The generating facility will include forty SUNGROW SG125HV, 600 V, 125 kW/kVA inverters and associated customer owned equipment. The plant will connect to the Narragansett Electric distribution system in Hopkinton, RI on the 34.5kV feeder 85T1 out of the Wood River #85 station. | 2/2019 | Approved | 2018-08-30
ES-18-G61 | 2018-07-16 | FedEx Ground Package System Middletown Generator | Generator notification from Eversource Energy (“ES”) on behalf of FedEx Ground Package System, Inc for the installation of a 1.05 MW natural gas generator in Middletown, CT and interconnecting to the Berlin 6A Substation via the 6A10 feeder. | 2018-09-14 | Notification | 2018-08-30
ES-18-G59 | 2018-07-16 | GSPP Zac Leverett Solar | Generator notification from Eversource Energy (“ES”) on behalf of GSPP Zac LLC for the installation of 3.12 MW solar PV in Leverett, MA and interconnecting to the Podick 18G Substation via the 18G7 feeder. | 2019-08-01 | Notification Withdrawn | 8/30/2018 8/15/2023
ES-18-G53 | 2018-07-12 | LSE Draco/LSE Dorado Southwick Solar | Generator notification from Eversource Energy (“ES”) on behalf of LSE Draco LLC for the installation of 4.0 MW solar PV in Southwick, MA and interconnecting to the Southwick 29A Substation via the 29A3 feeder. | 2018-10-01 | Notification | 2018-08-30
NEP-18-GNF15 | 2018-07-25 | Kearsarge Rose Hill Road South Kingstown Solar | Generator notification from New England Power (“NEP”) on behalf of Kearsarge Solar LLC for the installation of 3.78 MW solar PV in West Kingstown, MA and interconnecting to the West Kingston Substation via the 3308 feeder. | 2018-08-14 | Notification | 2018-08-30
NEP-18-GNF16 | 2018-07-25 | Kearsarge Plains Road West Kingstown Solar | Generator notification from New England Power (“NEP”) on behalf of Kearsarge Solar LLC for the installation of 3.11 MW solar PV in West Kingstown, MA and interconnecting to the West Kingston Substation via the 3307 feeder. | 2018-08-14 | Notification | 2018-08-30
ES-18-T25 | 2018-06-25 | Removal of Temporary 115/23 kV 20 MVA Mobile Transformer at Valley Substation | Transmission notification from Eversource Energy (“ES”) for the removal of the temporary 115/23 kV 20 MVA mobile transformer used to carry substation load and permit ongoing upgrades of the Valley Substation to two permanent (2) 30/40/50 MVA transformer banks, plus ancillary station upgrades. These permanent station upgrades were previously approved by ISO-NE under ES-15-T52 (for upgrade of the Valley #2 transformer bank) and under ES-16-T49 (for upgrade of the Valley #1 transformer bank). | 2018-06-28 | Notification | 2018-07-25
ES-18-G50 | 2018-06-20 | CEC Development Carver Solar | Generator notification from Eversource Energy (“ES”) on behalf of CEC Development LLC for the installation of 2.0 MW solar PV in Carver, MA and interconnecting to the West Pond Substation via the 23 kV 3-10-10 feeder. | 2018-07-20 | Notification | 2018-07-25
ES-18-G51 | 2018-06-25 | Borrego Rochester Solar | Generator notification from Eversource Energy (“ES”) on behalf of Borrego Solar for the installation of 2.706 MW solar PV in Rochester, MA and interconnecting to the Rochester 745 Substation via the 13.2 kV 707 feeder. | 2018-10-01 | Notification | 2018-07-25
ES-18-G52 | 2018-06-21 | Hopkinton MA 1 Solar | Generator notification from Eversource Energy (“ES”) on behalf of Hopkinton MA 1 for the installation of 2.0 MW solar PV in Hopkinton, MA and interconnecting to the Hopkinton Substation via the 14 kV feeder. | 2018-07-20 | Notification | 2018-07-25
ES-18-T21 | 2018-06-28 | Bloomfield 3B-2X Distribution Transformer Replacement | Transmission notification from Eversource Energy (“ES”) for the replacement of the existing 3B-2X, 115/23-kV distribution transformer at the Bloomfield 2B Substation, located in Bloomfield Connecticut. The existing 3B-2X transformer is being proactively replaced due to its age, past operating and maintenance issues. | 2018-12-31 | Notification | 2018-07-25
ES-15-T11 Rev.1 | 2018-06-25 | Installation of New 115 kV Hybrid Line and Series Reactor Between Newington and Southwest Hartford Substations | PPA revision to Eversource PPA ES-15-T11, which was approved on April 16, 2015. The project consists of a new, approximately 3.7-mile, 115-kilovolt (kV) hybrid transmission line (underground and overhead combinations) between the Newington Substation to the Southwest Hartford Substation, as well as associated upgrades to the two substations and addition of a 1.4% series reactor to Southwest Hartford end of the line. The new 115-kV line will link the two substations, which are not presently connected. As proposed in 2015, the new 115-kV line was to be an all-underground circuit buried primarily beneath local and state road rights-of-way (ROWs) through densely-developed suburban/urban areas. Subsequent consultations with Connecticut DOT and Amtrak revealed that 65% of the new 115-kV line can effectively be accommodated, in an overhead line design, within an Amtrak railroad corridor resulting in significant cost savings. | 12/2019 | Notification | 2018-07-25
ES-18-G38 | 2018-06-21 | Montague Road Amherst Solar | Generator notification from Eversource Energy (“ES”) on behalf of Montague Road Solar LLC for the installation of 3.12 MW solar PV in Amherst, MA and interconnecting to the Podick 18G Substation via 18G4 feeder. | 2019-03-01 | Notification | 2018-07-25
ES-18-G39 | 2018-06-21 | Soltage Easthampton Solar | Generator notification from Eversource Energy (“ES”) on behalf of Soltage LLC for the installation of 1.85 MW solar PV in Easthampton, MA and interconnecting to the Gunn 15A Substation via 15A2 feeder. | 2019-01-01 | Notification Withdrawn | 7/25/2018 7/18/2023
ES-18-G17 | 2018-06-22 | TJA Agawam Solar | Generator notification from Eversource Energy (“ES”) on behalf of TJA Solar for the installation for 4.989 MW solar PV in Agawam, MA and interconnecting to the Silver 30A Substation via 30A3 feeder. | 2018-12-01 | Notification | 2018-07-25
ES-18-G41 | 2018-06-22 | ForeFront Power Easthampton Solar | Generator notification from Eversource Energy (“ES”) on behalf of ForeFront Power LLC for the installation of 1.095 MW solar PV in Easthampton, MA and interconnecting to the Gunn 15A Substation via the 15A5 feeder. | 2018-10-01 | Notification Withdrawn | 7/25/2018 7/18/2023
ES-18-G44 | 2018-06-20 | BVD East Street Pittsfield Solar | Generator notification from Eversource Energy (“ES”) on behalf of BVD LLC for the installation of 1.998 MW solar PV in Pittsfield, MA and interconnecting to the Doreen 19A Substation via the 19A4 feeder. | 2019-02-01 | Notification | 2018-07-25
ES-18-G18 | 2018-05-30 | Pulpit Hill Amherst Solar | Generator notification from Eversource ("ES") on behalf of LSE Fornax LLC for the installation of 4.98 MW solar PV in Amherst, MA and interconnecting to the Podick 18G Substation via 18G7 feeder. | 2018-07-01 | Notification | 2018-06-22
ES-18-G07 | 2018-05-30 | Sunpin Solar Blandford Solar | Generator notification from Eversource ("ES") on behalf of Sunpin Solar Development for the installation of 4.7 MW solar PV in Blandford, MA and interconnecting to the Blandford Substation via 19J4 feeder. | 2018-06-13 | Notification | 2018-06-22
ES-18-G03 | 2018-05-30 | 510 PV Project Development Becket Solar | Generator notification from Eversource ("ES") on behalf of Borrego Solar for the installation of 4.95 MW solar PV in Becket, MA and interconnecting to the Pleasant Street Substation via the 23 kV 16B1 feeder. | 2018-09-01 | Notification | 2018-06-22
ES-18-T22 | 2018-05-25 | Greggs Transformer Retirement Project | Transmission application from Eversource Energy (“ES”) for the retirement of the 115/34.5 kV TB 17 transformer at the Greggs Substation located in Goffstown, NH. Upon the transformer retirement, the load will be supplied from the Weare Substation. | 12/2018 | Approved | 2018-06-22
ES-18-T23 | 2018-06-06 | Upgrade 398 Line from Connecticut-New York Border to Long Mountain Substation | Reconductor a segment of the existing 345-kV, 398 Line. This segment is 5.45 miles long and is located between transmission structure #8001 Dover, NY (near NY-CT border) and transmission structure #8044 New Milford, CT (near Long Mountain Substation). Eversource would replace the existing 2156 kcmil ACSR conductor with 2156 kcmil ACSS conductor. Eversource will also replace the existing overhead shield wire on the same segment with OPGW for relay communications. The impedance of the 398 Line will remain unchanged. The existing summer normal, LTE and, STE ratings are 1,226, 1,428, 1,735 and would be increased to 1,428, 1,880, 2,328, respectively, as a result of the project. | 2019-05-19 | Notification | 2018-06-22
NEP-18-GNF12 | 2018-05-29 | Compass Circle Solar North Kingstown Solar | Generator notification from New England Power ("NEP") on behalf of Compass Circle Solar for the installation of 2.0 MW solar PV in North Kingstown, RI and interconnecting to the Old Baptist Road Substation via the 12.47 kV 46F4 feeder. | 2018-07-20 | Notification | 2018-06-22
NEP-18-GNF13 | 2018-05-29 | BWC Blossom Road Westport Solar | Generator notification from New England Power ("NEP") on behalf of BWC Blossom Road for the installation of 4.5 MW solar PV in Westport, MA and interconnecting to the Bates Street Substation via the 13.8 kV 115W52 feeder. | 2018-07-20 | Notification | 2018-06-22
NEP-18-GNF14 | 2018-05-29 | BWC Adirondack Lane Westport Solar | Generator notification from New England Power ("NEP") on behalf of BWC Adirondack Lane for the installation of 4.998 MW solar PV in Westport, MA and interconnecting to the Bates Street Substation via the 13.8 kV 115W52 feeder. | 2018-07-20 | Notification | 2018-06-22
ES-18-G12 | 2018-04-25 | Feeding Hills Road Southwick Solar | Generator notification from Eversource (“ES”) for the installation of 4.98 MW solar PV in Southwick, MA and interconnecting to the Southwick 29A Substation via the 29A1 feeder. | 2018-07-01 | Notification | 2018-05-30
ES-18-G16 | 2018-04-27 | Roosevelt Avenue Springfield Solar | Generator notification from Eversource (“ES”) for the installation of 4.0 MW solar PV in Springfield, MA and interconnecting to the East Springfield Substation via the 05J18 feeder. | 2018-05-21 | Notification | 2018-05-30
ES-18-G10 | 2018-04-25 | Miller Falls Road Montauge Solar | Generator notification from Eversource (“ES”) for the installation of 4.08 MW solar PV in Montague, MA and interconnecting to the Montague Substation via the 21C8 feeder. | 2018-05-16 | Notification | 2018-05-30
ES-18-G06 | 2018-04-27 | Chapin Street Ludlow Solar | Generator notification from Eversource (“ES”) for the installation of 1.86 MW solar PV in Ludlow, MA and interconnecting to the Ludlow 19S Substation via the 19S1 feeder. | 2018-09-01 | Notification | 2018-05-30
ES-18-G15 | 2018-04-27 | Plain Road Hatfield Solar | Generator notification from Eversource (“ES”) for the installation of 3.6 MW solar PV in Hatfield, MA and interconnecting to the Podick 18G Substation via the 18G5 feeder. | 2018-07-01 | Notification | 2018-05-30
ES-18-G11 | 2018-04-18 | Amherst Road Sunderland Solar | Generator notification from Eversource (“ES”) for the installation of 1.084 MW solar PV in Sunderland, MA and interconnecting to the Podick 18G Substation via the 18G3 feeder. | 2018-10-01 | Notification | 2018-05-30
NEP-18-GNF11 | 2018-05-09 | Umass Memorial Hospital Worcester CHP Generator | Generator notification from New England Power (“NEP”) on behalf of UMass Memorial Hospital for the installation of a 2.649 MW CHP generator in Worcester, MA and interconnecting to the Bloomingdale Substation via the 13.8 kV HT55 feeder. | 2018-06-15 | Notification | 2018-05-30
NEP-18-GNF10 | 2018-05-09 | Zero Point Engineering Charlton Solar | Generator notification from New England Power (“NEP”) on behalf of Zero Point Engineering for the installation of 2.499 MW solar PV in Charlton, MA and interconnecting to the West Charlton Substation via the 13.2 kV 415L1 feeder. | 2018-06-01 | Notification | 2018-05-30
NEP-18-GNF08 | 2018-05-09 | Shirley Solar | Generator notification from New England Power (“NEP”) on behalf of Massachusetts Electric for the installation of 2.0 MW solar PV in Shirley, MA and interconnecting to the Ayer Substation via the 13.8 kV 201W1 feeder. | 2018-06-01 | Notification | 2018-05-30
HE-18-G01 | 2018-04-30 | Mt. Tom Battery Energy Storage System | Generator notification from Holyoke Gas & Electric for the installation of a 3.0 MW battery storage system in Holyoke, MA and interconnecting to the Holyoke 17L Substation via the 36H1 feeder. | 2018-05-31 | Notification | 2018-05-30
ES-18-G34 | 2018-05-02 | Simsbury Solar Generation Project | Generator application from Eversource Energy on behalf of Deepwater Wind Solar II for the installation of two 13.2 MW (26.4 MW net output) photovoltaic generator in Simsbury, CT and interconnecting to the 23 kV bus at the Northeast Simsbury 43F Substation. | 5/2019 | Approved | 2018-05-30
ES-18-G33 | 2018-05-02 | Candlewood New Milford Solar Generation Project | Generator application from Eversource Energy on behalf of Candlewood Solar for the installation of a 20 MW photovoltaic generator in New Milford, CT and interconnecting to the 13.8 kV bus at the Rocky River 12Y Substation. | 2018-12-31 | Approved | 2018-05-30
NEP-18-G03 | 2018-04-11 | Johnston Landfill Wind Generator Project | Generator application from New England Power (“NEP”) on behalf of Green Energy Development for the construction of seven 3.0 MW (21 MWs net output) wind turbine generators located in Johnston, RI. The project will interconnect to the Narragansett Electric’s Johnson Substation via a 23 kV #2227 feeder. | 12/2018 | Approved | 2018-05-16
KGE-18-X01 | 2018-04-11 | Kendall AVR Installation Project | Transmission application from Kendall Green Energy (“KGE”) for the installation of a GE EX2100e Automatic Voltage Regulator (AVR)/Exciter and Power System Stabilizer (PSS) for the Kendall 4 generator. | 5/2018 | Approved | 2018-05-16
NEP-18-G02 | 2018-04-11 | Southern Sky West Cranston Solar Project | Generator application from New England Power (“NEP”) on behalf of Southern Sky Renewable Energy for the construction of an 7.75 MW solar array located in Cranston, RI. The project will interconnect to the Narragansett Electric’s 12.47 kV #21F1 feeder out of the West Cranston Substation. | 2019-01-15 | Approved | 2018-05-16
NEP-18-G01 | 2018-04-11 | Southern Sky Rhode Island Solar Project | Generator application from New England Power (“NEP”) on behalf of Southern Sky Renewable Energy for the construction of an 8.5 MW solar array located in between the Johnson Substation and Drumrock Substation in RI. The project will interconnect to the Narragansett Electric’s 23 kV #2228 feeder. | 2018-11-15 | Approved | 2018-05-16
NEP-18-T20 | 2018-04-11 | Woonsocket Substation Modification and Admiral Street Substation Transformer Addition Project | Transmission application from New England Power (“NEP”) for the addition of two breaker and a half bays feeding four line positions. The new configuration will consist of 12 115 kV circuit breakers arranges in four breaker and a half bays. The Q-143S and R-144 lines that presently tieinto the main 115 kV bus will be terminated in their own bay positions. | 12/2021 | Approved | 2018-05-16
NEP-18-T21 | 2018-04-11 | Woonsocket Substation Modification and Admiral Street Substation Transformer Addition Project | Transmission application from New England Power (“NEP”) for the construction of a new 115/12.47 kV Admiral Street Substation in Providence, RI. The substation will consist of two 40 MVA transformers supplied from the Q-143 and R-144 cables from the Franklin Square Substation and Q-143 and R-144 overhead lines from the Woonsocket Substation. | 2023 | Approved | 2018-05-16
ES-18-T20 | 2018-04-10 | North Road Substation Circuit Breaker Addition Project | Transmission application from Eversource Energy (“ES”) for the addition of two 115 kV line circuit breakers and the replacement of an existing 115 kV circuit switcher at the North Road Substation in Sunapee, NH. | 12/2018 | Approved | 2018-05-16
UI-18-X01 | 2018-04-02 | Ansonia 1570 Line SPS Retirement | Transmission application from Avangrid/United Illuminating (“UI”) for the retirement of the existing Ansonia Substation 1570 line NPCC Type III SPS. The SPS was designed to relieve the post-contingent overload on line 1570 from Derby Junction to Indian Well Substation. With the Pootatuck Reconfiguration Project in service, the SPS action is no longer required. | 7/2018 | Approved | 2018-05-16
WGE-18-G02 | 2018-04-13 | GSPP Terawatt Westfield Solar | Generator notification from Westfield Gas and Electric (“WG&E”) on behalf of GSPP Terawatt Westfield LLC for the installation of 3.6 MW solar PV in Westfield, MA and interconnecting to the Buck Pond Substation via the 23 kV 34B feeder. | 2018-07-31 | Notification | 2018-05-16
VEC-18-G03 | 2018-03-07 | SCORE VT Arburgh Solar | Generator notification from Vermont Electric CoOp on behalf of SCORE VT Alburgh, LLC for the installation of 1.0 MW solar PV in Arburgh, VT and interconnecting to the VEC Substation 28-1A via the 12.47 kV 62B feeder. | 2016-12-31 | Notification | 2018-05-16
NEP-18-GNF07 | 2018-04-09 | Kearsarge Hartford Avenue Uxbridge Solar | Generator notification from New England Power (“NEP”) on behalf of Kearsarge Uxbridge for the installation of 1.872 MW solar PV in Uxbridge, MA and interconnecting to the Uxbridge Substation via the 13.8 kV 321W6 feeder. | 2018-10-01 | Notification | 2018-05-16
NEP-18-GNF06 | 2018-04-09 | Zero Point Boutilier Street Leicester Solar | Generator notification from New England Power (“NEP”) on behalf of Zero Point Engineering for the installation of 2.886 MW solar PV in Leicester, MA and interconnecting to the Leicester Substation via the 13.8 kV 21W2 feeder. | 2018-06-11 | Notification | 2018-05-16
NEP-18-GNF05 | 2018-04-09 | SunE Sunset Winchendon Solar | Generator notification from New England Power (“NEP”) on behalf of SunE Sunsets Holdings for the installation of 2.0 MW solar PV in Winchendon, MA and interconnecting to the East Winchendon Substation via the 13.8 kV 612W1 feeder. | 2018-06-11 | Notification | 2018-05-16
NEP-18-GNF09 | 2018-04-09 | SA LLC II CHP Southbridge Generator | Generator notification from New England Power (“NEP”) on behalf of SA LLC II for the installation of 1.126 MW CHP generator in Southbridge, MA and interconnecting to the Snow Street Substation via the 13.2 kV 413L6 feeder. | 2018-05-01 | Notification | 2018-05-16
NU-13-T32 Rev.2 | 2018-04-11 | Greenwich 115/13.2 kV Substation Project | Transmission Application revision from Northeast Utilities (a.k.a Eversource Energy) (“ES”) to change to an air-insulated substation, add two 115/13.2 kV 60 MVA bulk power transformers, a one 115 kV circuit breaker and two new 115 kV 3500 kcmil XPLE underground cables from the Cos Cob Substation to the Greenwich Substation (aprox. 2.3 miles each). | 12/2019 | Notification | 2018-05-16
ES-18-T13 | 2018-04-11 | Montville 16X 115/69 kV Autotransformer Replacement | Transmission Application from Eversource Energy (“ES”) for the replacement of the Montville 16X 115/69 kV Autotransformer. | 6/2019 | Notification | 2018-05-16
ES-18-T14 | 2018-04-11 | Card 5X 345/115 kV Autotransformer Replacement | Transmission Application from Eversource Energy (“ES”) for the replacement of the Card 5X 345/115 kV Autotransformer. | 12/2018 | Notification | 2018-05-16
NEP-18-T13 | 2018-03-29 | Clear River Energy Center Upgrades | Transmission Application from New England Power (“NEP”) for the reconductoring of the 0.17 mile 115 kV S171N Tap from West Farnum Substation to West Farnum S-171N Line Tap associated with the Clear River Energy Center Project. | 2020-12-01 | Notification Withdrawn | 5/16/2018 12/18/2018
NEP-18-T14 | 2018-03-29 | Clear River Energy Center Upgrades | Transmission Application from New England Power (“NEP”) for the uprate of the 0.99 mile 115 kV K189 Line from Kent County Substation to Drumrock Substation associated with the Clear River Energy Center Project. | 2020-12-01 | Notification Withdrawn | 5/16/2018 12/18/2018
NEP-18-T15 | 2018-03-29 | Clear River Energy Center Upgrades | Transmission Application from New England Power (“NEP”) for the reconductoring of the 0.99 mile 115 kV G-185N Line from Kent County Substation to Drumrock Substation associated with the Clear River Energy Center Project. | 2020-12-01 | Notification Withdrawn | 5/16/2018 12/18/2018
NEP-18-T16 | 2018-03-29 | Clear River Energy Center Upgrades | Transmission Application from New England Power (“NEP”) for the reconductoring of the 3.60 mile 115 kV H17 Line from Farnum Substation to Riverside Substation associated with the Clear River Energy Center Project. | 2020-12-01 | Notification Withdrawn | 5/16/2018 12/18/2018
NEP-18-T17 | 2018-03-29 | Clear River Energy Center Upgrades | Transmission Application from New England Power (“NEP”) for the reconductoring of the 10.04 mile 115 kV R9 Line from Riverside Substation to Valley Substation associated with the Clear River Energy Center Project. | 2020-12-01 | Notification Withdrawn | 5/16/2018 12/18/2018
NEP-18-T18 | 2018-03-29 | Clear River Energy Center Upgrades | Transmission Application from New England Power (“NEP”) for the replacement of the 345/115 kV 174T and 175T Transformers at the West Farnum Substation associated with the Clear River Energy Center Project. | 2020-12-01 | Notification Withdrawn | 5/16/2018 12/18/2018
NEP-18-T19 | 2018-03-29 | Clear River Energy Center Upgrades | Transmission Application from New England Power (“NEP”) for the reconductoring of the 0.17 mile 115 kV T-172N Tap from the West Farnum Substation to the West Farnum T-172N Line Tap. | 2020-12-01 | Notification Withdrawn | 5/16/2018 12/18/2018
ES-18-G13 | 2018-03-30 | Windsor Road Hinsdale Solar | Generator notification from Eversource (“ES”) for the installation of 2.0 MW solar PV in Hinsdale, MA and interconnecting to the Berkshire 18C Substation via the 18C2feeder. | 2018-04-30 | Notification | 2018-05-16
ES-18-G02 | 2018-03-30 | Churchill Solar Pittsfield Solar | Generator notification from Eversource (“ES”) on behalf of Churchill Solar LLC for the installation of 1.996 MW solar PV in Pittsfield, MA and interconnecting to the Oswald Substation via the 30B5 feeder. | 2018-04-30 | Notification | 2018-05-16
ES-18-G14 | 2018-03-30 | Cadwell Drive East Springfield Solar | Generator notification from Eversource (“ES”) for the installation of 1.68 MW solar PV in East Springfield, MA and interconnecting to the East Springfield 5A Substation via the 5J11A feeder. | 2018-07-01 | Notification | 2018-05-16
NEP-18-T01 | 2018-03-23 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from New England Power (“NEP”) for the construction of a new Grand Army Substation with a 115 kV 4-bay breaker and a half GIS Switching Station in Somerset, MA to loop the E-183E, F-184, X3 and W4 lines. Equipment will be rated for a 3000 A and circuit breakers will be 63 kA. Protection upgrades will be performed at remote terminals as needed to accommodate proposed relaying for lines terminating at the new Grand Army Substation. | 11/2020 | Approved | 2018-05-01
NEP-18-T02 | 2018-03-23 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from New England Power (“NEP”) for the addition of a new 345/115/24 kV 268/358/448 MVA transformer, 115 kV breaker at the Brayton Point Substation. Also reconfigure the 115 kV termination of transformers 3A and 3B and upgrade E-183E and F-184S limiting 115 kV equipment to 3000 A capacity and operate the 115 kV 30T breaker as normally open. | 6/2020 | Approved | 2018-05-01
NEP-18-T03 | 2018-03-23 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from New England Power (“NEP”) to increase the clearances on the 115 kV E-183E and F-184S lines between Brayton Point and Grand Army Substation. Protection schemes at line terminals will be upgraded to accommodate increased thermal ratings. | 11/2019 | Approved | 2018-05-01
NEP-18-T04 | 2018-03-23 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from New England Power (“NEP”) to reconductor the X3S and W4S lines between Somerset (Pottersville) and Grand Army Substations with 2-439 ACCC conductor and separate X3S/W4S double circuit towers. Also move the Y2 and Z1 from Somerset Switchyard and tap from new W4S and X3S lines. | 11/2019 | Approved | 2018-05-01
NEP-18-T05 | 2018-03-23 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from New England Power (“NEP”) to add a new 115 kV circuit breaker and move the 115 kV Q10 line to a new terminal position at the Robinson Avenue Substation. The new circuit breaker will be 3000 A and 40 kA. | 11/2019 | Approved | 2018-05-01
NEP-18-T06 | 2018-03-23 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from New England Power (“NEP”) to install a new 115 kV 45 MVAr capacitor and a new 115 kV circuit breaker at the Berry Street Substation. The new circuit breaker will be 3000 A and 63 kA. Also install dual pilot protection schemes on C-181N and D-182N lines. | 12/2020 | Approved Withdrawn | 5/1/2018 3/16/2021
NEP-18-T07 | 2018-03-23 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from New England Power (“NEP”) to separate the N12 and M13 lines double circuit towers and reconductor N12 and M134N lines between Somerset (Pottersville) and Bell Rock Substations. | 12/2021 | Approved | 2018-05-01
NEP-18-T08 | 2018-03-23 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from New England Power (“NEP”) to expand the 115 kV Bell Rock Substation to a 3-bay breaker and a half station with a series breaker between the N12 and D21 tie breaker. All equipment will be rated for 3000 A with the circuit breakers rated at 63 kA. | 12/2021 | Approved | 2018-05-01
NEP-18-T09 | 2018-03-23 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from New England Power (“NEP”) to extend the 115 kV Line 114 from the Eversource/NGrid border at Dartmouth town line to Bell Rock Substation (4.2 miles) Overhead conductor will be 1590 ACSS. Also install a new 3000 A, 63 kA bus breaker to terminate Line 114 at expanded Bell Rock Substation. Also install a new 37.5 MVAr capacitor at Bell Rock Substation. | 12/2021 | Approved | 2018-05-01
NEP-18-T10 | 2018-03-23 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from New England Power (“NEP”) to replace the T3 345/115 kV transformer at the Kent County Substation with a new 330/440/550 MVA transformer. | 11/2020 | Approved | 2018-05-01
NEP-18-T11 | 2018-03-23 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from New England Power (“NEP”) to rebuild the 115 kV Somerset Substation as a new substation called Pottersville Substation. Equipment will be rated for 3000 A and the circuit breakers will be 63 kA. | 11/2020 | Approved | 2018-05-01
NEP-18-T12 | 2018-03-23 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from New England Power (“NEP”) to increase the clearances on the 115 kV J16S line between Highland Drive and Staples Substations. Protection schemes at line terminals will be upgrade to accommodate increased thermal ratings as required. Expected upgraded ratings will be 144/156/160 MVA. | 12/2020 | Approved | 2018-05-01
ES-18-T05 | 2018-04-13 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from Eversource Energy (“ES”) for the addition of a 115 kV 35.3 MVAR capacitor bank and associated circuit breaker at the High Hill Substation. | 2021-12-31 | Approved | 2018-05-01
ES-18-T06 | 2018-04-13 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from Eversource Energy (“ES”) for the addition of a 115 kV 35.3 MVAR capacitor bank and associated circuit breaker at the Wing Lane Substation. | 2021-12-31 | Approved | 2018-05-01
ES-18-T07 | 2018-04-13 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from Eversource Energy (“ES”) for the looping of the existing 115-kV circuit 201-502 (C-129N) into Eversource’s Medway Substation, in Medway, MA. The project will expand the 115-kV switchyard at Medway Substation with an additional breaker-and-a-half bay and re-terminate some existing lines in order to accommodate the preliminarily named C-129N and C-129W circuits. Dual pilot protection schemes will be installed as part of the NPCC Directory 1 implementation plan. | 12/2021 | Approved | 2018-05-01
ES-18-T08 | 2018-04-13 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from Eversource Energy (“ES”) for the construction of a new 8 mile 115 kV circuit extension from Eversource’s Industrial Park Tap, in New Bedford, MA to the ownership border with National Grid on the way to their Bell Rock Substation, in Fall River, MA. | 2021-12-31 | Approved | 2018-05-01
ES-18-T09 | 2018-04-13 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from Eversource Energy (“ES”) for the construction of a replacement Eversource 115-kV Bourne switching station in Bourne, MA to replace the existing switching station. The existing station is a straight-bus design with line circuit breakers while the new station will be a breaker-and-half design. | 12/31/2020 | Approved | 2018-05-01
ES-18-T10 | 2018-04-13 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from Eversource Energy (“ES”) for the construction of a replacement Eversource 115-kV Kingston substation in Kingston, MA to replace the existing substation. The existing station is a straight-bus design with a single bus-tie circuit breaker while the new station will be a breaker-and-half design. | 2021-12-31 | Approved | 2018-05-01
ES-18-T11 | 2018-04-13 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from Eversource Energy (“ES”) for the construction of a new 115-kV circuit from Eversource’s Bourne Switching Station, in Bourne, MA to Eversource’s West Barnstable Substation, in Barnstable, MA. A third bay with two circuit breakers will be constructed at West Barnstable and a circuit breaker (#9) will be added at Bourne for protection. | 2021-12-31 | Approved | 2018-05-01
ES-18-T12 | 2018-04-13 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from Eversource Energy (“ES”) for the construction of a new 115-kV circuit from Eversource’s Carver Substation, in Carver, MA to Eversource’s Kingston Substation, in Kingston, MA. A new circuit breaker will be required at each end (#4 at Kingston and #952 at Carver) for protection. | 2021-12-31 | Approved | 2018-05-01
ES-18-T15 | 2018-04-13 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from Eversource Energy (“ES”) for the upgrading or replacement of eight 345 kV circuit breakers with 3000 amp, 63 kA interrupting circuit breakers at Eversource’s West Medway Substation in Medway, MA in order to have a higher fault current interrupting capability. | 2021-12-31 | Approved | 2018-05-01
ES-18-T16 | 2018-04-13 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from Eversource Energy (“ES”) for the replacement of five 115 kV circuit breakers with 3000 amp, 63 kA interrupting circuit breakers at Eversource’s Medway Substation in Medway, MA in order to have a higher fault current interrupting capability. | 12/2021 | Approved | 2018-05-01
ES-18-T17 | 2018-04-13 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from Eversource Energy (“ES”) for the upgrading of the protection system for the 345 kV bus at Eversource’s West Barnstable Substation in Barnstable, MA in order to meet NPCC BPS design requirements. | 12/2021 | Approved | 2018-05-01
ES-18-T18 | 2018-04-13 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from Eversource Energy (“ES”) for the upgrading of the protection system for the 115 kV bus at Eversource’s Bourne Substation in Bourne, MA in order to meet NPCC BPS design requirements. | 2021-12-31 | Approved | 2018-05-01
ES-18-T19 | 2018-04-13 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from Eversource Energy (“ES”) for the upgrading of the protection system for the 115 kV bus at Eversource’s Medway Substation in Medway, MA in order to meet NPCC BPS design requirements. | 12/2021 | Approved | 2018-05-01
MGED-18-T01 | 2018-04-06 | SEMA/RI 2026 Reliability Solution Transmission Project | Transmission application from Middleborough Gas & Electric Department (“MGED”) for the replacement of the existing conductor on the Middleborough Gas & Electric Department portion of the E1 line with 795-kcmil ACSS. | 12/2019 | Approved | 2018-05-01
EM-18-G01 | 2018-02-02 | Weaver Wind Generation Project | Generator application from Emera Maine (“EM”) on behalf Weaver Wind LLC for the installation of 22 3.3 MW wind turbine generators (72.6 MW total net output) in Hancock County, Maine and interconnecting to the Bull Hill substation via the new collector substation and LRE generator lead. | 2019-10-31 | Approved | 2018-03-26
EM-18-T01 | 2018-02-02 | Weaver Wind Generation Project | Transmission application from Emera Maine (“EM”) on behalf Weaver Wind LLC for the construction of a 115/34.5 kV 75/100 MVA collector substation to interconnect the Weaver Wind Generation Project. Project will also include a 36 MVAR D-VAR with two second 3X overload. | 2019-10-31 | Approved | 2018-03-26
MATEP-18-X01 | 2018-02-27 | MATEP Exciter Replacement Project | Transmission application from MATEP (“MATEP”) for the replacement of the excitation systems associated with the GE steam turbine electric generators MATEP STG-2 and STG-3. The new Exciter model is a GE EX2100e SCT/PPT (Saturable Current Transformer/Power Potential Transformer), model ST4B and it is a digital voltage regulator intended to be a direct replacement for the existing electro-mechanical system: a GE model GEK-33507B SCT/PPT Static System. The reason for the replacement is obsolesce, as GE is no longer supporting the existing exciter models. There will be no change in unit ratings. | 2018-09-01 | Approved | 2018-03-26
NEP-18-GNF03 | 2018-02-26 | Barre Solar | Generator notification from New England Power (“NEP”) on behalf of Barre Solar Road for the installation of 1.92 MW solar PV in Barre, MA and interconnecting to the Barre Substation via the 13.8 kV 604W4 feeder. | 2018-03-20 | Notification | 2018-03-26
NEP-18-GNF04 | 2018-02-26 | Asahi America Lawrence Solar | Generator notification from New England Power (“NEP”) on behalf of Asahi America for this installation of 1.139 MW solar PV in Lawrence, MA and interconnecting to the West Andover Substation via the 34.5 kV 8T2 feeder. | 2018-03-20 | Notification | 2018-03-26
ES-18-G19 | 2018-02-14 | Durham Manufacturing Solar | Generator notification from Eversource (“ES”) on behalf of Durham Manufacturing for the installation of 1.215 MW solar PV in Durham, CT and interconnecting to the West Dooley Substation via the 13.2 kV 30K14 feeder. | 2018-06-01 | Notification | 2018-03-26
ES-18-G09 | 2018-02-20 | Lee Site 31 Solar | Generator notification from Eversource (“ES”) on behalf of Lee Site 31 for the installation of 1.86 MW solar PV in Lee, MA and interconnecting to the Pleasant 16B Substation via the 16B1 feeder. | 2018-03-23 | Notification | 2018-03-26
ES-18-G08 | 2018-02-20 | Pittsfield Site 44 Solar | Generator notification from Eversource (“ES”) on behalf of Pittsfield Site 44 for the installation of 1.16 MW solar PV in Pittsfield, MA and interconnecting to the Partridge 15E Substation via the 15E2 feeder. | 2018-03-28 | Notification | 2018-03-26
ES-18-G04 | 2018-02-07 | Tobey Road Wareham Solar | Generator notification from Eversource (“ES”) for the installation of 3.3 MW solar PV in Wareham, MA and interconnecting to the Tremont Substation via the 23 kV 3-85-92815E2 feeder. | 2018-07-01 | Notification | 2018-03-26
ES-18-G20 | 2018-02-08 | Plymouth Service Center Solar | Generator notification from Eversource (“ES”) for the installation of 1.116 MW solar PV in Plymouth, MA and interconnecting to the West Pond Substation via the 23 kV 12 feeder. | 2018-03-01 | Notification | 2018-03-26
ES-18-G05 | 2018-02-14 | Manchester Community College Solar | Generator notification from Eversource (“ES”) on behalf of General Electric for the installation of 2.0 MW solar PV in Manchester, CT and interconnecting to the Manchester Substation via the 23 kV 3A09 feeder. | 2018-04-27 | Notification | 2018-03-26
GMP-18-G01 | 2018-02-20 | SB VT South Burlington Solar | Generator notification from VELCO on behalf of Green Mountain Power (“GMP”) for the installation of 1.548 MW solar PV in South Burlington, VT and interconnecting to the Dorset Street Substation via the 12.47 kV 78G1 feeder. | 2017-10-11 | Notification | 2018-03-26
GMP-18-G02 | 2018-02-20 | Elizabeth Mine Strafford Solar | Generator notification from VELCO on behalf of Green Mountain Power (“GMP”) for the installation of 4.998 MW solar PV in Strafford, VT and interconnecting to the Sharon Substation via the 12.47 kV 7SH-G35 feeder. | 2017-11-09 | Notification | 2018-03-26
ES-18-G29 | 2018-02-27 | Parallel Products New Bedford Solar | Generator notification from Eversource (“ES”) on behalf of Parallel Products of New England for the installation of 1.196 MW solar PV in New Bedford, MA and interconnecting to the Industrial Park Substation via the 13.2 kV 2-151-151 feeder. | 2018-04-01 | Notification | 2018-03-26
GMP-18-G03 | 2018-03-02 | Saint Albans Solar | Generator notification from Green Mountain Power (“GMP”) on behalf of Saint Albans Solar for the installation of 4.896 MW solar PV in Saint Albans, VT and interconnecting to the Nason Street Substation via the 12.47 kV NA-G26 feeder. | 2018-06-30 | Notification | 2018-03-26
GMP-18-G04 | 2018-03-02 | Brattleboro Landfill Solar | Generator notification from Green Mountain Power (“GMP”) on behalf of PSVTF1, LLC for the installation of 4.98 MW solar PV in Brattleboro, VT and interconnecting to the Brudies Road Substation via the 12.47 kV BU-G48 feeder. | 2018-06-01 | Notification | 2018-03-26
GMP-18-G05 | 2018-03-02 | Gilman Renewable Lunenburg Solar | Generator notification from Green Mountain Power (“GMP”) on behalf of Gilman Renewable Solar for the installation of 2.1 MW solar PV in Lunenburg, VT and interconnecting to the Gilman Substation via the 12.47 kV GM-G62 feeder. | 2018-06-01 | Notification | 2018-03-26
WGE-18-G01 | 2018-03-05 | Green Meadow Lumber Westfield Solar | Generator notification from Westfield Gas and Electric (“WG&E”) on behalf of Green Meadow Lumber for the installation of 1.98 MW solar PV in Westfield, MA and interconnecting to the Elm Substation via the 23 kV 22G6 feeder. | 2018-06-01 | Notification | 2018-03-26
ES-18-G01 | 2018-01-30 | Ice River Springs Pittsfield Solar | Generator notification from Eversource Energy (“ES”) on behalf of APE Berkshires for the installation of 1.59 MW solar PV in Pittsfield, MA, and interconnecting to the Oswald 115 kV Substation via the 30B7 feeder. | 2018-02-28 | Notification | 2018-02-21
COV-18-X01 | 2018-02-06 | Bristol Refuse AVR Replacement Project | Transmission application from Covanta Energy Marketing (“COV”) for the replacement of the AVRs at the Forestville Station. The upgrade will install a new Basler DECS 250 excitation system, which will provide excitation current to the exciters and replace the existing AVRs. | 2018-02-27 | Approved | 2018-02-21
ES-18-T04 | 2018-01-10 | Holliston Station Mobile Transformer Replacement | Replace the existing 50 MVA, 115/14 kV mobile transformer with a new 20 MVA, 117/15.12 kV mobile transformer. Other equipment details remain largely the same. A 123 kV, 1,200 amp continuous rated circuit switcher will remain in place. A 115 kV, 1,200 amp line disconnect is being added between the mobile station circuit switcher and the tap at 115 kV line 274-509. A mobile circuit breaker trailer with 2 - 1,200 amp, 15 kV vacuum circuit breakers is being added at the station. The existing 15 kV, 600 amp, pole-top feed reclosers are being moved to the street. The tie into the existing 13.8 kV distribution circuit infrastructure at ROW 7-1 and Fiske St. will remain. | 5/2018 | Notification | 2018-02-21
NEP-18-GNF02 | 2018-01-31 | Kingston Road Richmond Solar | Generator notification from New England (“NEP”) on behalf of Green Development for the installation of 4.5 MW solar PV in Richmond, Rhode Island and interconnecting to the Kenyon Substation via the 12.47 kV 68F4 feeder. | 2018-01-19 | Notification | 2018-02-21
NEP-18-GNF01 | 2018-01-31 | Stilson Road Richmond Solar | Generator notification from New England (“NEP”) on behalf of Green Development for the installation of 2.0 MW solar PV in Richmond, Rhode Island and interconnecting to the Kenyon Substation via the 12.47 kV 68F4 feeder. | 2018-01-19 | Notification | 2018-02-21
VEC-18-G01 | 2018-01-23 | Magee Hill Hiensburg Solar | Generator notification from Vermont Electric CoOp on behalf of SoCor VT Magee Hill LLC for the installation of 1.26 MW solar PV in Hinesburg, Vermont and interconnecting to the Hinesburg Substation via the 19-1A feeder. | 2017-11-21 | Notification | 2018-02-21
VEC-18-G02 | 2018-01-29 | BDE Grand Island Solar | Generator notification from Vermont Electric CoOp on behalf of BDE Grand Isle Solar LLC for the installation 4.98 MW solar PV in Grand Isle, Vermont and interconnecting to the VEC Substation via the 12.47 kV 29-1A feeder. | 12/2017 | Notification | 2018-02-21
ES-18-T03 | 2018-01-02 | Lost Nation Circuit Breaker Replacement and Transformer Additions | Transmission application from Eversource Energy (“ES”) for the addition of a 115 kV line circuit breaker and a second 115/34.5 kV transformer to the Lost Nation Substation in Northumberland, New Hampshire. | 6/2018 | Approved | 2018-01-29
ES-18-T01 | 2018-01-02 | Deerfield Substation 345/115 kV Autotransformer TB 14 Replacement | Transmission notification from Eversource Energy (“ES”) for the replacement of the existing 270/360/450 MVA 345/115 kV autotransformers at the Deerfield Substation in Deerfield, New Hampshire. | 2018-07-01 | Notification | 2018-01-29
ES-18-T02 | 2018-01-02 | Littleton Substation 230/115 kV Autotransformer TB 41 Replacement | Transmission notification from Eversource Energy (“ES”) for the replacement of the existing 210/280/350 MVA 230/115 kV autotransformer at the Littleton Substation in Littleton, New Hampshire. | 2018-07-01 | Notification | 2018-01-29
NEP-17-GNF63 | 2017-12-08 | Wendell Solar | Generator notification from New England Power (“NEP”) on behalf of the Town of Wendell for the installation of 1.76 MW solar PV in Clinton, MA, and interconnecting to the Fitch Road Substation via the 13.8 kV 216W3 feeder. | 2017-12-30 | Notification | 2017-12-27
NEP-17-GNF64 | 2017-12-08 | Blue Wave Capital Mendon Solar | Generator notification from New England (“NEP”) on behalf of Blue Wave Capital for the installation of 2.603 MW solar PV in Mendon, MA, and interconnecting to the Depot Street Substation via the 13.8 kV 335W1 feeder. | 2017-12-30 | Notification | 2017-12-27
NEP-17-GNF43 Rev.1 | 2017-12-08 | Northampton Solar Rev.1 | Generator notification from New England (“NEP”) on behalf of the City of Northampton for the installation of 2.335 MW solar PV in Northampton, MA (revised from 1.867 MWs) and interconnecting to the Florence Junction Substation via the 13.8 kV 909W4 feeder. | 2017-12-30 | Notification | 2017-12-27
NEP-17-GNF23 | 2017-12-08 | Monson Solar | Generator notification from New England (“NEP”) on behalf of Monson Solar for the installation of 2.0 MW solar PV in Monson, MA and interconnecting to the Palmer Substation via the 13.2 kV 503L2 feeder. | 2017-12-30 | Notification | 2017-12-27
ES-17-G25 | 2017-12-01 | CEC Rochester MA 2 Solar | Generator notification from Eversource Energy (“ES”) on behalf of CCEC Rochester MA 2 LLC for the installation of 1.002 MW solar PV in Rochester, MA and interconnecting to the Rochester Substation via the 13.2 kV 702 feeder. | 2018-01-01 | Notification | 2017-12-27
NEP-17-T14 | 2017-11-22 | Evertt Substation 115/23 kV Transformer Replacement | Transmission notification from New England Power (“NEP”) for the replacement of three 115/23 kV with two 115/23 kV transformers at the Everett Substation in Everett, MA due to asset conditions and reliability concerns. | 12/2018 | Notification | 2017-12-27
ES-17-T35 | 2017-12-06 | East Springfield 5J Substation 115/13.8 kV Transformer Replacement | Transmission notification from Eversource Energy (“ES”) for the replacement of the 115/13.8 kV East Springfield 6X transformer at the East Springfield 5J Substation in East Springfield, MA due to a short in the secondary wiring. | 2017-12-31 | Notification | 2017-12-27
CMP-17-G02 | 2017-11-06 | Georges River Biomass Generator Project | Generator application from Central Maine Power Company (“CMP”) on behalf Georges River Energy, LLC for the installation of an 8.5 MW (7.5 MW net output) biomass generator in Searsmont, ME and interconnecting to the 34.5 kV distribution circuit at the Belfast substation. | 2018-06-01 | Approved | 2017-12-06
NEP-17-GNF62 | 2017-10-04 | ISM Solar Dighton 2 Dighton Solar | Generator application from New England Power (“NEP”) on behalf of ISM Solar Dighton 2 LLC for the installation of 2.0 MW solar PV in Dighton, MA, and interconnecting to the Dighton Substation via the 13.8 kV 19W73 feeder. | 2017-11-30 | Notification | 2017-12-06
NEP-17-GNF48 | 2017-11-02 | GR Lawrence Sanitary Distribution CHP Generator | Generator application from New England Power (“NEP”) on behalf of GR Lawrence Sanitary Distribution for the installation of a 3.2 MW (net output) CHP generator in North Andover, MA, interconnecting to the Ward Hill Substation via the 23 kV 2358 feeder. | 2017-11-30 | Notification | 2017-12-06
NEP-17-GNF58 | 2017-11-02 | Clark University Worcester CHP Generator | Generator application from New England Power (“NEP”) on behalf of Clark University for the installation of a 1.0 MW (net output) CHP generator in Worcester, MA, interconnecting to the Webster Street Substation via the 13.8 kV HT41feeder. | 2017-11-30 | Notification | 2017-12-06
NEP-17-GNF60 | 2017-11-02 | UMass Health Alliance Leominster CHP Generator | Generator application from New England Power (“NEP”) on behalf of UMass Health Alliance for the installation of a 1.837 MW (net output) CHP generator in Leominster, MA, interconnecting to the Prospect Street Substation via the 13.8 kV 219W6 feeder. | 2017-11-30 | Notification | 2017-12-06
VELCO-17-GNF03 | 2017-11-07 | Next Generation Solar Farm New Haven Solar | Generator application from VELCO on behalf of Next Generation Solar Farm, LLC for the installation of 2.2 MW solar PV in New Haven, Vermont and interconnecting to the GMP Weybridge Substation via the 12.47 kV WY-G81 feeder. | 2017-12-15 | Notification | 2017-12-06
ES-17-G40 | 2017-11-07 | Borrego Solar Freetown Solar | Generator application from Eversource Energy (“ES”) for the installation of 1.98 MW solar PV in Freetown, MA and interconnecting to the Eversource Industrial Park Substation via the 13.2 kV 102 feeder. | 2018-02-06 | Notification | 2017-12-06
ES-17-G27 | 2017-10-27 | Holiday Hill Community Wind Russell Wind | Generator application from Eversource Energy (“ES”) on behalf of Holiday Hill Community Wind for the installation of a 4.98 MW (net output) wind turbine generator in Russell, MA, interconnecting to the Blandford Substation via the 23 kV 19J1 feeder. | 2018-08-01 | Notification | 2017-12-06
ES-17-T28 | 2017-10-17 | Emerald Street Substation Transformer Addition | Transmission notification from Eversource Energy (“ES”) for the addition of a 3rd 30 MVA 115 kV transformer at the Emerald Street Substation in Keene, NH and addition of a 2nd 115 kV bus differential protection. | 12/2018 | Notification | 2017-12-06
ES-17-T33 | 2017-10-31 | Baldwin 3X 115/13.8 kV Transformer Replacement | Transmission notification from Eversource Energy (“ES”) for the replacement of the Baldwin 3X 115/13.8 kV transformer at the Baldwin 13F Substation in Waterbury, CT due to equipment failure. | 2017-11-30 | Notification | 2017-12-06
ES-17-T34 | 2017-10-31 | Portland 21H-2X 115/23 kV Transformer Replacement | Transmission notification from Eversource Energy (“ES”) for the replacement of the Portland 21H-2X 115/23 kV transformer at the Portland 21H Substation in Portland, CT due to equipment failure. | 2017-12-31 | Notification | 2017-12-06
EXE-17-X01 | 2017-11-06 | West Medway 1,2, & 3 AVR Replacement Project | Transmission application from Exelon Generation Company (“EXE”) for the replacement of the excitation controller and AVRs at the West Medway Station (Jets 1, 2 and 3). The upgrade will install a new Allen Bradley Combination Generation Control Module at each jet, which will provide excitation current to the exciters and replace the existing AVRs. | 11/2017 | Approved | 2017-12-06
NEP-16-T12 Rev.1 | 2017-10-27 | Hendersonville Substation Project Rev.1 | PPA revision for the 115/13.8 kV Hendersonville Substation. Initial application inadvertently omitted a detail in the documentation about the P-168 underground cable relocation which was modeled in the study. The underground to overhead transition riser structure on the NEP-owned section of the 115 kV P-168 circuit between Mystic and Chelsea is being relocated by 0.17 mile for the new Wynn Casino in Everett, MA (expected ISD - Nov 2017). The location of the riser structure on the NEP-owned section of the 115 kV O-167 circuit between Mystic and Everett remains unchanged. | 11/2017 | Notification | 2017-12-06
ES-17-G39 | 2017-11-08 | Woods Hill Solar Project | Generator application from Eversource Energy (“ES”) on behalf of Woods Hill Solar LLC for the installation of a 20.0 MW solar array in Pomfret, CT and interconnected via a 23 kV 6.1 mile express feeder to the Tracy Substation. | 2017-12-31 | Approved | 2017-11-17
NEP-17-GNF57 | 2017-10-04 | Belchertown Renewables Franklin Street Belchertown Solar | Generator application from New England Power (“NEP”) on behalf of Belchertown Renewables LLC for the installation of 2.0 MW solar PV in Belchertown, MA, interconnecting to the Thorndike Substation via the 13.2 kV 523L2 feeder. | 2017-10-30 | Notification | 2017-10-31
NEP-17-GNF56 | 2017-10-04 | Belchertown Renewables North Liberty Street Belchertown Solar | Generator application from New England Power (“NEP”) on behalf of Belchertown Renewables LLC for the installation of 2.0 MW solar PV in Belchertown, MA, interconnecting to the Thorndike Substation via the 13.2 kV 523L2 feeder. | 2017-10-30 | Notification | 2017-10-31
NEP-17-GNF55 | 2017-09-29 | Zero Point Engineering Spencer Solar | Generator application from New England Power (“NEP”) on behalf of Zero Point Engineering for the installation of 2.0 MW solar PV in Spencer, MA, interconnecting to the Leicester Substation via the 13.8 kV 21W1 feeder. | 2017-10-30 | Notification | 2017-10-31
NEP-17-GNF54 | 2017-09-29 | Griffin Road Solar I Charlton Solar | Generator application from New England Power (“NEP”) on behalf of Griffin Road Solar I for the installation of 2.0 MW solar PV in Charlton, MA, interconnecting to the West Charlton Substation via the 13.2 kV 415L2 feeder. | 2017-10-30 | Notification | 2017-10-31
NEP-17-GNF53 | 2017-09-29 | Dudley River Solar Southbridge Solar | Generator application from New England Power (“NEP”) on behalf of Dudley River Solar LLC for the installation of 3.0 MW solar PV in Southbridge, MA, interconnecting to the Snow Street Substation via the 13.2 kV 413L3feeder. | 2017-10-30 | Notification | 2017-10-31
FGE-17-G01 | 2017-09-27 | LSE Cassiopeia Ashby Solar | Generator application from Fitchburg Gas & Electric Light Company (“FG&E”) on behalf of LSE Cassiopeia LLC for the installation of 1.85 MW solar PV in Ashby, MA, interconnecting to the West Townsend Substation via the 13.8 kV 39W19 feeder. | 2017-10-04 | Notification | 2017-10-31
ES-17-G32 | 2017-09-13 | Solar Star Massachusetts Framingham Solar | Generator application from Eversource Energy (“ES”) on behalf of Solar Star Massachusetts II LLC for the installation of 1.608 MW solar PV in Framingham, MA, interconnecting to the West Framingham Substation via the 14 kV 455-H7 feeder. | 2017-10-31 | Notification | 2017-10-31
ES-17-G29 | 2017-10-05 | Newington VA Hospital Generator | Generator application from Eversource Energy (“ES”) on behalf of Newington VA Hospital for the installation of a 1.16 MW combustion generator in Newington, CT, interconnecting to the Newington 4A Substation via the 23 kV 4A12 feeder. | 2017-11-01 | Notification | 2017-10-31
ES-17-G35 | 2017-09-29 | Doosan Fuel Cell America Waterbury Fuel Cell | Generator application from Eversource Energy (“ES”) on behalf of Doosan Fuel Cell America for the installation of a 1.32 MW fuel cell in Waterbury, CT, interconnecting to the Baldwin 13F Substation via the 13.8 kV 13F61 feeder. | 2017-11-17 | Notification | 2017-10-31
ES-17-T30 | 2017-10-05 | Maine Power Express Transmission Project | Transmission application from Eversource Energy (“ES”) on behalf of Maine Power Express for an Elective Transmission Upgrade (ETU) for the installation of a 1,050 MVA, ±320 kV 315 mile underground/sub-sea HVDC transmission line from Haynesville, ME to Massport Conley Terminal Boston, MA. | 12/2022 | Approved | 2017-10-31
ES-17-T31 | 2017-10-05 | Maine Power Express Transmission Project | Transmission application from Eversource Energy (“ES”) on behalf of Maine Power Express for an Elective Transmission Upgrade (ETU) for the installation of two 345 kV AC underground lines from Massport Conley Terminal Boston, MA to K Street Substation, Boston MA. | 12/2022 | Approved | 2017-10-31
ES-17-T32 | 2017-10-05 | Maine Power Express Transmission Project | Transmission application from Eversource Energy (“ES”) for an Elective Transmission Upgrade (ETU) for the installation of four 345 kV GIS breakers at the K Street Substation and relocate the 3162 and 3163 345 kV lines to support the breaker configuration. | 12/2022 | Approved | 2017-10-31
CMP-17-G01 | 2017-10-05 | Pittsfield Maine Solar Generator Project | Generator application from Central Maine Power Company (“CMP”) for the installation of a 9.9 MW solar array interconnected to the Hartland substation on line section 82. | 2017-12-01 | Approved | 2017-10-31
NEP-17-GNF52 | 2017-09-06 | Onyx Renewable Partners Pembroke Solar | Generator application from Eversource Energy (“ES”) on behalf of Onyx Renewable Partners for the installation of 2.4 MW solar PV in Pembroke, MA, interconnecting to the Water Street Substation via the 13.8 kV 910W25 feeder. | 2017-09-30 | Notification | 2017-09-27
NEP-17-GNF50 | 2017-09-06 | Palumbo Solar Uxbridge Solar | Generator application from New England Power (“NEP”) on behalf of Palumbo Solar LLC for the installation of 3.0 MW solar PV in Uxbridge, MA, interconnecting to the Uxbridge Substation via the 13.8 kV 321W2 feeder. | 2017-09-30 | Notification | 2017-09-27
NEP-17-GNF47 | 2017-09-06 | Solten Randolph Solar | Generator application from New England Power (“NEP”) on behalf of Solten Randolph 4500 LLC for the installation of 3.78 MW solar PV in Randolph, MA, interconnecting to the South Randolph Substation via the 13.8 kV 97W2 feeder. | 2017-09-30 | Notification | 2017-09-27
NEP-17-GNF51 | 2017-09-06 | Preferred Freezer Everett Solar | Generator application from New England Power (“NEP”) on behalf of Preferred Freezer for the installation of 1.327 solar PV in Everett, MA, interconnecting to the Thorndike Substation via the 23 kV 2401 feeder. | 2017-09-30 | Notification | 2017-09-27
NEP-17-GNF49 | 2017-09-06 | Williamstown Solar | Generator application from New England Power (“NEP”) on behalf of the Town of Williamstown for the installation of 1.5 MW solar PV in Northampton, MA, interconnecting to the Williamstown Substation via the 13.8 kV 1003W1 feeder. | 2017-09-30 | Notification | 2017-09-27
NEP-17-GNF46 | 2017-09-06 | 510 PV Project Development Leicester Solar | Generator application from New England Power (“NEP”) on behalf of 510 PV Project Development LLC for the installation of 4.929 MW solar PV in Leicester, MA, interconnecting to the North Oxford Substation via the 13.2 kV 406L1 feeder. | 2017-09-30 | Notification | 2017-09-27
ES-17-G34 | 2017-09-06 | Borrego Solar Carver Solar | Generator application from Eversource Energy (“ES”) on behalf of Borrego Solar for the installation of 1.98 MW solar PV in Carver, MA, interconnecting to the West Pond Substation via the 23 kV 3-10-929 feeder. | 2018-02-01 | Notification | 2017-09-27
ES-17-G33 | 2017-09-07 | LSE Coma Berenices and LSE Canes East Windsor Solar | Generator application from Eversource Energy (“ES”) on behalf of LSE Coma Berenices and LSE Canes Venatici for the installation of 3.96 MW solar PV in East Windsor, CT and interconnecting to the 115 kV Barbour Hill Substation via the 23J36 feeder. | 2017-10-29 | Notification | 2017-09-27
ES-17-G26 | 2017-07-11 | Brass Mill Center Solar Waterbury Solar | Generator application from Eversource Energy (“ES”) on behalf of Brass Mill Center Solar LLC for the installation of 2.1784 MW solar PV in Waterbury, CT, interconnecting to the Baldwin 13F Substation via the 13.8 kV 13F63 and 13F66 feeders. | 2017-12-20 | Notification | 2017-09-27
CED-17-G01 | 2017-09-11 | CED Foster Solar | Generator application from Con Edison Development Inc. (“CED”) on behalf of CED Foster Solar for the installation of 1.98 MW solar PV in Foster, RI, interconnecting to the Wolf Hill Substation via the 34F1 feeder. | 2017-11-01 | Notification | 2017-09-27
ES-17-X03 | 2017-09-11 | 326 SPS Thermal Mode Set Point Change | Transmission notification from Eversource Energy (“ES”) for the set point change to the 326 SPS to change the SPS winter thermal mode to avoid the possibility of SPS action when not required due to a set point that is below the thermal limit of the line. | 3/2018 | Notification | 2017-09-27
NEP-17-GNF40 | 2017-08-09 | Tufts University Medford CHP Generator | Generator application from New England Power (“NEP”) on behalf of Tufts University for the installation of a 3.815 MW CHP Generator in Medford, MA and interconnecting to the Everett Substation via the 23 kV 2344 feeder. | 2017-09-30 | Notification | 2017-09-07
NEP-17-GNF45 | 2017-08-09 | Solar MA Project Management Dudley Solar | Generator application from New England Power (“NEP”) on behalf of Solar MA Project Management Dudley Solar for the installation of 2.997 MW solar PV in Dudley, MA, interconnecting to the Snow Street Substation via the 13.2 kV 413L3 feeder. | 2017-09-15 | Notification | 2017-09-07
NEP-17-GNF44 | 2017-08-09 | 510 PV Project Development Newbury Solar | Generator application from New England Power (“NEP”) on behalf of 510 PV Project Development, LLC for the installation of 4.4 MW solar PV in Newbury, MA, interconnecting to the King Street Substation via the 23 kV 2367 feeder. | 2017-09-15 | Notification | 2017-09-07
NEP-17-GNF43 | 2017-08-09 | Northampton Solar | Generator application from New England Power (“NEP”) on behalf of City of Northampton for the installation of 1.867 MW solar PV in Northampton, MA, interconnecting to the Florence Junction Substation via the 13.8 kV 909W4 feeder. | 2017-09-15 | Notification | 2017-09-07
NEP-17-GNF42 | 2017-08-09 | JH Solar/Ledeaux Solar North Brookfield Solar | Generator application from New England Power (“NEP”) on behalf of JH Solar LLC and Ledeaux Solar LLC for the installation of 2.0 MW solar PV in North Brookfield, MA, interconnecting to the Lashaway Substation via the 13.2 kV 525L2 feeder. | 2017-09-15 | Notification | 2017-09-07
NEP-17-GNF41 | 2017-08-09 | Soltage Plainville Solar | Generator application from New England Power (“NEP”) on behalf of Soltage, LLC for the installation of 4.89 MW solar PV in Plainville, MA, interconnecting to the West Street Substation via the 23 kV 2286 feeder. | 2017-09-15 | Notification | 2017-09-07
ES-17-G31 | 2017-07-28 | CEC Solar Millis Solar | Generator application from Eversource Energy (“ES”) on behalf of CEC Solar LLC for the installation of 1.002 solar PV in Millis, MA, interconnecting to the Medway #65 Substation via the 13.8 kV 65H3 feeder. | 2017-09-13 | Notification | 2017-09-07
ES-17-G28 | 2017-07-10 | CEFIA Holdings Barrette Thompson Solar | Generator application from Eversource Energy (“ES”) on behalf of CEFIA Holdings LLC for the installation of 2.96 solar PV in Thompson, CT, interconnecting to the Tracy Substation via the 23 kV 14M8 feeder. | 2017-08-31 | Notification | 2017-09-07
ES-17-G30 | 2017-08-02 | Windham Solar Lebanon Solar | Generator application from Eversource Energy (“ES”) on behalf of Windham Solar LLC for the installation of 4.998 solar PV in Lebanon, CT, interconnecting to the Card 11F Substation via the 23 kV 11F12 feeder. | 2017-08-31 | Notification | 2017-09-07
NN-17-G01 | 2017-08-17 | Number Nine Wind Farm Generation and Transmission Project | Generator application from Number Nine Wind Farm (“NN”) for the installation of 102 2.1 MW Gamesa wind turbine generators (214.2 net output) with a constant reactive power mode injecting 0.267 MVAR per turbine located in Aroostook County, ME. | 2019-12-30 | Approved | 2017-09-07
NN-17-G02 | 2017-08-17 | Number Nine Wind Farm Generation and Transmission Project | Generator application from Number Nine Wind Farm (“NN”) for the installation of 17 2.0 MW Gamesa wind turbine generators (34.0 net output) with a constant reactive power mode injecting 0.255 MVAR per turbine located in Aroostook County, ME. | 2019-12-30 | Approved | 2017-09-07
NN-17-T01 | 2017-08-17 | Number Nine Wind Farm Generation and Transmission Project | Transmission application from Number Nine Wind Farm (“NN”) for the construction of a 162 mile generator lead line from the 345 kV Number Nine Collector Substation to the new 345 kV Pittsfield Substation. Also install a 345/34.5 kV transformer rated at 288 MVA. | 2019-11-30 | Approved | 2017-09-07
NN-17-T02 | 2017-08-17 | Number Nine Wind Farm Generation and Transmission Project | Transmission application from Number Nine Wind Farm (“NN”) for the construction of a 345 kV Collector Substation with twelve 34.5 kV breakers and four 345 kV breakers in addition to the 104 MVAR DVAR and two 42.5 MVAR reactors and a 345/34.5 kV transformer. | 2019-11-30 | Approved | 2017-09-07
NN-17-T03 | 2017-08-17 | Number Nine Wind Farm Generation and Transmission Project | Transmission application from Number Nine Wind Farm (“NN”) for the installation of two 42.5 MVAR Reactors mechanically switched and controlled by the AMSC DVAR at the 345 kV Number Nine Collector Substation. | 2019-11-30 | Approved | 2017-09-07
NN-17-T04 | 2017-08-17 | Number Nine Wind Farm Generation and Transmission Project | Transmission application from Number Nine Wind Farm (“NN”) for the installation of two 42.5 MVAR Reactors at the Pittsfield 345 kV Substation to be SCADA controlled by CMP. | 2019-11-30 | Approved | 2017-09-07
NN-17-X01 | 2017-08-17 | Number Nine Wind Farm Generation and Transmission Project | Transmission application from Number Nine Wind Farm (“NN”) for the installation of a 104 MVAR American Superconductor DVAR at the 345 kV Number Nine Collector Substation with 300% overload capability. | 2019-11-30 | Approved | 2017-09-07
CMP-17-T02 | 2014-08-14 | Number Nine Wind Farm Generation and Transmission Project | Transmission application from Central Maine Power Company (“CMP”) for the construction of a three breaker ring bus substation (Pittsfield) to accommodate the interconnection of Number Nine Wind Farm on the existing Section 3023 between Albion Road and Orrington Substations. Additionally two 42.5 MVAR 345 kV reactors shall be connected to the Pittsfield station end of the generator lead. | 2019-12-30 | Approved | 2017-09-07
NEP-17-T13 | 2017-07-07 | I-35 69 kV Line Removal | Transmission notification from New England Power (“NEP”) for the removal of the 69 kV I-35 Line due to the decommissioning of the Shrewsbury #306 Substation. Project will include removal of all parts of the I-35 Line to include structures and conductors between Millbury and Shrewsbury including all taps connecting to the 69 kV X-24 Line and switches at the North Grafton Switch Tower. | 5/2017 | Notification | 2017-09-07
NEP-17-GNF36 | 2017-06-27 | Solar MA Project Management Ware Solar | Generator notification from New England Power (“NEP”) on behalf of Solar MA Project Management for the installation of 4.592 MW solar PV in Ware, MA, interconnecting to the Ware Substation via the 13.2 kV 501L4 feeder. | 2017-07-30 | Notification | 2017-07-27
NEP-17-GNF37 | 2017-06-27 | SunEdison Origination 1 Brockton Solar | Generator notification from New England Power (“NEP”) on behalf of SunEdison Origination 1, LLC for the installation of 3.72 MW solar PV solar PV in Brockton, MA, interconnecting to the Dupont Substation via the 13.8 kV 91W41 feeder. | 2017-07-30 | Notification | 2017-07-27
NEP-17-GNF38 | 2017-06-27 | Old Sturbridge Solar | Generator notification from New England Power (“NEP”) on behalf of Old Sturbridge Inc. for the installation of 1.5 MW solar PV in Sturbridge, MA, interconnecting to the Fiskdale (Snow Street T1) Substation via the 13.2 kV 408L1feeder. | 2017-07-30 | Notification | 2017-07-27
NEP-17-GNF39 | 2017-06-27 | Nippawus Solar North Kingstown Solar | Generator notification from New England Power (“NEP”) on behalf of Nippawus Solar, LLC for the installation of 1.74 MW solar PV in North Kingston, RI, interconnecting to the Davisville Substation via the 34.5 kV 84T3 feeder. | 2017-07-30 | Notification | 2017-07-27
ES-17-G19 | 2017-06-30 | Naugatuck Waste Water Treatment Plant Fuel Cell | Generator notification from Eversource Energy (“ES”) on behalf of Doosan Fuel Cell America for the installation of a 1.38 MW fuel cell generator in Naugatuck, CT and interconnecting to the South Naugatuck Substation via the 13.8 kV 21L4 feeder. | 2017-07-20 | Notification | 2017-07-27
ES-17-G24 | 2017-05-18 | Danbury TRS Fuel Cell | Generator notification from Eversource Energy (“ES”) on behalf of TRS Fuels Cell, LLC for the installation of a 3.79 MW fuel cell generator in Danbury, CT and interconnecting to the Triangle Street Substation via the 13.8 kV 11A57-2 feeder. | 2017-09-01 | Notification | 2017-07-17
ES-17-G21 | 2017-05-15 | Baystate Medical CHP Generator Project | Generator application from Eversource Energy (“ES”) for the installation of a 5.4 MW CHP generator located in Springfield, MA and interconnecting to the Clinton Substation via the 13.8 kV line. | 2017-12-31 | Approved | 2017-07-17
ES-17-G01 | 2017-06-07 | MIT Combustion Turbine Generator Project | Generator application from Eversource Energy (“ES”) for the installation of two 21.0 MW (42.0 MW net output) combustion turbine generators interconnected to the Putnam 115 kV substation on the Eversource 14 kV distribution system. | Q1 2019 | Approved | 2017-07-17
GRH-17-G01 | 2017-04-28 | Moore Hydro Generator Addition Project | Generator application from Great River Hydro (“GRH”) for the installation of a 4.6 MW hydro generator connected to the 13.8 kV Moore Substation in Littleton, NH. The project will not change the existing generators, generator step-up transformers, or interconnection configuration at the 13.8 kV Moore Substation. | 2021-05-31 | Approved | 2017-07-17
TMLP-17-T02 | 2017-05-18 | Taunton County Street Substation | Transmission application from Taunton Municipal Light Plant (“TMLP”), for the construction of a new County Street Substation in Taunton, MA comprising of two 115/13.8 kV 50 MVA transformers tapping off the 115 kV U6 and S8 lines. | 7/2020 | Approved | 2017-07-17
NEP-17-GNF35 | 2017-06-02 | Green Street Power Partners West Bridgewater Solar | Generator notification from New England Power (“NEP”) on behalf of Green Street Power Partners West Bridgewater Solar for the installation of 3.6 MW solar PV in West Bridgewater, MA, interconnecting to the Easton Substation via the 13.8 kV 92W54 feeder. | 2017-06-30 | Notification | 2017-07-17
NEP-17-GNF33 | 2017-06-02 | Renewable Generation Palmer Solar | Generator notification from New England Power (“NEP”) on behalf of Renewable Generation, LLC for the installation of 1.08 MW solar PV in Palmer, MA, interconnecting to the Palmer Substation via the 13.2 kV 503L4 feeder. | 2017-06-30 | Notification | 2017-07-17
NEP-14-GNF17-Rev.1 | 2017-06-02 | Solar MA Project Management Clinton Solar Rev.1 | Generator notification from New England Power (“NEP”) on behalf of Solar MA Project Management Clinton Solar for the installation of 2.196 MW solar PV in Clinton, MA, interconnecting to the Fitch Road Substation via the 13.8 kV 216W5 feeder. Project revised to increase MW output from 2.0 MWs to 2.196 MWs. | 2017-06-30 | Notification | 2017-07-17
NEP-17-GNF34 | 2017-06-02 | 515 Main Saugus Solar | Generator notification from New England Power (“NEP”) on behalf of 515 Main Saugus, LLC for the installation of 1.296 MW solar PV in Saugus, MA, interconnecting to the Melrose Substation via the 13.8 kV 25W1 feeder. | 2017-06-30 | Notification | 2017-07-17
NEP-17-GNF32 | 2017-06-02 | 510 PV Project Development Hubbardston | Generator notification from New England Power (“NEP”) on behalf of 510 PV Project Development for the installation of 1.92 MW solar PV in Hubbardston, MA, interconnecting to the Westminster Substation via the 13.8 kV 602W2 feeder. | 2017-06-10 | Notification | 2017-07-17
NEM-17-G02 | 2017-06-02 | Sanford Airport Solar Generation and Transmission Project | Generator application from NextEra Energy Resources (“NEM”) for the installation of a 50 MW solar array located in Sanford, ME and interconnecting to the 115 kV Section 237 from Sanford to Maguire Road. | 8/2019 | Approved | 2017-07-17
NEM-17-T02 | 2017-06-02 | Sanford Airport Solar Generation and Transmission Project | Transmission application from NextEra Energy Resources (“NEM”) for the installation of a 115/34.5/13.8 kV transformer with fixed taps. | 8/2019 | Approved | 2017-07-17
CMP-17-T01 | 2017-06-02 | Sanford Airport Solar Generation and Transmission Project | Transmission application from Central Maine Power Company (“CMP”) for the construction of a new ring bus configured substation to accommodate the interconnectionof Sanford Solar on the existing Section 237 115 kV transmission line between Maguire Road and Sanford Substation. | 8/2019 | Approved | 2017-07-17
ES-17-T07 | 2017-05-05 | Alps to Berkshire Transmission Project | Transmission application from Eversource Energy (“ES”) for the rebuild of the 26.2 mile overhead 115 kV 1231 Line from Berkshire to Plainfield Tap, Plainfield Tap to the Ashfield Tap, and Ashfield Tap to the Cumberland Substation using 556 MCM ACSS. | 8/2019 | Approved Withdrawn | 7/10/2017 12/18/2018
ES-17-T08 | 2017-05-05 | Alps to Berkshire Transmission Project | Transmission application from Eversource Energy (“ES”) for the rebuild of the 28.7 mile overhead 115 kV 1242 Line from Berkshire to Plainfield Tap, Plainfield Tap to the Ashfield Tap, and Ashfield Tap to the Montague Substation using 556 MCM ACSS. | 8/2019 | Approved Withdrawn | 7/10/2017 12/18/2018
ES-17-T09 | 2017-05-05 | Alps to Berkshire Transmission Project | Transmission application from Eversource Energy (“ES”) for the rebuild of the 7.8 mile overhead 115 kV 1211 Line from Doreen Substation to North Tap and North Tap to Oswald Substation using 556 MCM ACSS. | 8/2019 | Approved Withdrawn | 7/10/2017 12/18/2018
ES-17-T10 | 2017-05-05 | Alps to Berkshire Transmission Project | Transmission application from Eversource Energy (“ES”) for the replacement of the 345/115 kV 2X autotransformer at the Berkshire 18C Substation with a new 600 MVA transformer. The Berkshire Substation will be modified to a six circuit breaker ring bus and the new autotransformer will have isolation devices on the primary and secondary side of the autotransformer. | 8/2019 | Approved Withdrawn | 7/10/2017 12/18/2018
ES-17-T11 | 2017-05-05 | Alps to Berkshire Transmission Project | Transmission application from Eversource Energy (“ES”) for the addition of a 600 MW HVDC Converter at the Berkshire Substation. | 8/2019 | Approved Withdrawn | 7/10/2017 12/18/2018
ES-17-T12 | 2017-05-05 | Alps to Berkshire Transmission Project | Transmission application from Eversource Energy (“ES”) for the installation of a 23.3 mile overhead 345 kV transmission line from Berkshire 18C Substation to Alps Substation in New York using 2-954 MCM ACSS. | 8/2019 | Approved Withdrawn | 7/10/2017 12/18/2018
ES-17-T13 | 2017-05-05 | Alps to Berkshire Transmission Project | Transmission application from Eversource Energy (“ES”) for the upgrades of the Cumberland 22B 115 kV Substation to include replacement of one 800A wave trap with one 1200A wave trap as well as changes to relay settings. | 8/2019 | Approved Withdrawn | 7/10/2017 12/18/2018
ES-17-T14 | 2017-05-05 | Alps to Berkshire Transmission Project | Transmission application from Eversource Energy (“ES”) for the upgrades of the Montague 21C 115 kV Substation to include replacement of one 800A wave trap with one 1200A wave trap as well as upgrade the substation conductor to 1590 MCM ACSR. | 8/2019 | Approved Withdrawn | 7/10/2017 12/18/2018
VELCO-17-T02 | 2017-05-01 | Alps to Berkshire Transmission Project | Transmission notification from Vermont Electric Power Company (“VELCO”) for the installation of one 20 MVAR capacitor bank at the Bennington 115 kV substation in support of the Alps to Berkshire transmission project. | 8/2019 | Approved Withdrawn | 7/10/2017 12/18/2018
BRP-17-G01 | 2017-05-11 | Bear Swamp Uprate Project | Generator application from Brookfield Renewable (“BRP”),for the installation of new pump-turbine runners, new runner and stationary seal rings, allow synchronous condenser operation, new pump-turbine wicket gates, stay vane and stay ring modification, new wicket gate bushings, shaft seal modifications, motor-generator stator rewind, rotor replacement. These upgrades will uprate the generating capability of the two units from 600 MW to 666 MW (333 MW each unit) and will also uprate the pumping capability of the two units from 600 MW to 666 MW (333 MW each unit). | 6/2020 | Approved | 2017-06-02
NEP-17-T03 | 2017-04-26 | Bear Swamp Uprate Project | Transmission application from New England Power Company (“NEP”), for the installation of a 2nd 115 kV capacitor bank (63 MVAR) and increasing the size of the 1st 115 kV capacitor bank from 50 MVAR to 63 MVAR to address negative impact on Bear Swamp area voltages during pumping conditions. | 6/2020 | Approved | 2017-06-02
NEM-17-G01 | 2017-05-01 | Coolidge Solar I Generator and Transmission Project | Generator application from NextEra Energy Resources (“NEM”) on behalf of Coolidge Solar I LLC, for the installation of a 19.9 MW net output solar array located in Ludlow, VT. | 2018-09-01 | Approved | 2017-06-02
NEM-17-T01 | 2017-05-01 | Coolidge Solar I Generator and Transmission Project | Transmission application from NextEra Energy Resources (“NEM”) on behalf of Coolidge Solar I LLC, for the installation of a 115/34.5 kV 13/17/22 MVA GSU Transformer in support of the Coolidge Solar Project. | 2018-09-01 | Approved | 2017-06-02
VELCO-17-T01 | 2017-05-01 | Coolidge Solar I Generator and Transmission Project | Transmission application from Vermont Electric Power Company (“VELCO”) for the interconnection of the Coolidge Solar Project to the Coolidge | 2018-09-01 | Approved | 2017-06-02
ES-17-T17 | 2017-05-12 | Curtisville Switching Station Phase II Project | Transmission application from Eversource Energy (“ES”) for the Phase II of the Curtisville Switching Station Project for the addition of two synchronous condensers of 25 MVA each at the Farmwood 115 kV Switching Station and remove the 30 MW loading limitation at the Broken Ground Substation. | 6/2018 | Approved | 2017-06-02
VELCO-17-GNF02 | 2017-05-16 | Otter Valley Pittsford Solar | Generator notification from VELCO on behalf of Otter Valley Solar Farm LLC for the installation of 2.178 MW solar PV in Pittsford, VT and interconnecting to the GMP Pittsford Village Substation via the 12.47 kV AP 10 distribution circuit. | 2017-08-15 | Notification | 2017-06-02
ES-17-T18 | 2017-05-09 | Interconnection of a Temporary 20 MVA Mobile Substation at Valley Substation #715 | Notification from Eversource (“ES”) for the interconnection of a temporary 20 MVA mobile substation to replace removed #113 bank at Valley Substation #715 in Plymouth, MA. | 2017-06-01 | Notification | 2017-06-02
ES-17-G13 | 2017-05-16 | Alternate Power and Energy Wareham Solar | Generator notification from Eversource ("ES") on behalf of Alternate Power and Energy for the installation of 1.7 MW solar PV in Wareham, MA, interconnecting to the Tremont Substation via the 23 kV 85 feeder. | 2017-04-18 | Notification | 2017-06-02
ES-17-G18 | 2017-04-19 | LSDP II Deerfield Solar | Generator notification from Eversource ("ES") on behalf of LSDP II, LLC for the installation of 4.45 MW solar PV in Deerfield, MA and interconnecting to the Cumberland Substation via the 13.8 kV 22B4 feeder. | 2017-06-30 | Notification | 2017-06-02
ES-17-G20 | 2017-04-19 | Deerfield AD1 Deerfield Biomass | Generator notification from Eversource ("ES") on behalf of Deerfield AD I for the installation of 1.0 MW biomass generator in Deerfield, MA and interconnecting to the Cumberland Substation via the 13.8 kV 22B1 feeder. | 2017-05-31 | Notification | 2017-06-02
ES-17-G21 | 2017-05-04 | Energy Price Management Hinsdale Solar | Generator notification from Eversource ("ES") on behalf of Energy Price Management Group, LLC for the installation of 1.99 MW solar PV in Hinsdale, MA and interconnecting to the Berkshire Substation via the 23 kV 18C2 distribution circuit. | 2017-05-31 | Notification | 2017-06-02
NEP-17-GNF30 | 2017-05-03 | Upton Solar LLC | Generator notification from New England Power ("NEP") on behalf of Upton Solar, LLC for the installation of 2.0 solar PV in Upton, MA, interconnecting to the Depot Street Substation via the 13.8 kV 335W3 feeder. | 2017-06-01 | Notification | 2017-06-02
NEP-17-GNF28 | 2017-05-03 | 510 PV Project Development Fall River Solar | Generator notification from New England Power ("NEP") on behalf of 510 PV Project Development, LLC for the installation of 1.992 MW solar PV in Fall River, MA, interconnecting to the Bates Street Substation via the 13.8 kV 115W52 feeder. | 2017-06-01 | Notification | 2017-06-02
NEP-17-GNF31 | 2017-05-08 | Orbit Energy Johnston Biomass | Generator notification from New England Power ("NEP") on behalf of Orbit Energy RI, LLC for the installation of 3.2 MW biomass generator in Johnston, RI and interconnecting to the Johnston Substation via the 23 kV 2227 feeder. | 2017-06-01 | Notification | 2017-06-02
NEP-17-GNF29 | 2017-05-03 | Garden Hill Solar Rutland Solar | Generator notification from New England Power ("NEP") on behalf of Garden Hill Solar for the installation of 4.68 MW solar PV in Rutland, MA, interconnecting to the Treasure Valley 55 Substation via the 13.8 kV 55W1feeder. | 2017-06-01 | Notification | 2017-06-02
NEP-17-GNF27 | 2017-05-03 | CEC Solar North Adams | Generator notification from New England Power ("NEP") on behalf of CEC Solar #1079 and #1080 for the installation of 1.98 MW solar PV in North Adams, MA, interconnecting to the Adams Substation via the 13.8 kV 1021W2 feeder. | 2017-06-01 | Notification | 2017-06-02
ES-17-T20 | 2017-05-16 | Scobie Pond TB30 Transformer Replacement and Shunt Reactor Installation Project | Transmission application from Eversource Energy to replace the existing TB30 345/115/13.8 kV autotransformer with a three phase two-winding spare transformer (TB150) at the Scobie Pond 345 kV Substation. | 6/2017 | Approved | 2017-05-24
ES-17-T21 | 2017-05-16 | Scobie Pond TB30 Transformer Replacement and Shunt Reactor Installation Project | Transmission application from Eversource Energy for the addition of two 40 MVAR fixed shunt reactors at the Scobie Pond 115 kV substation due to the failure of the Scobie Pond TB30 Autotransformer. | 12/2017 | Approved | 2017-05-24
NEP17-GNF24 | 2017-04-05 | North Smithfield POW 1 Solar | Generator notification from New England Power ("NEP") on behalf of North Smithfield Solar POW 1 LLC for the installation of 2.2 MW solar PV in North Smithfield, RI and interconnecting to the Woonsocket Substation via the 13.8 kV 26W1feeder. | 2017-05-01 | Notification | 2017-05-04
ES-17-G11 | 2017-03-21 | CG Savoy Energy Development Savoy Solar | Generator notification from Eversource Energy ("ES") on behalf of Savoy Energy Development, LLC for the installation of 2.0 MW solar PV in Savoy, MA and interconnecting to the Berkshire Substation via the 23 kV 18C1 feeder. | 2017-05-31 | Notification | 2017-05-04
ES-17-T06 | 2017-03-31 | Scitico 14W 115/23 kV Distribution Transformer Replacement | Transmission notification from Eversource Energy ("ES") to replace the Scitico 14W 115/23 kV distribution transformer due to asset conditions. | 2017-05-31 | Notification | 2017-05-04
ES-17-X01 | 2017-03-24 | Barnstable SPS Retirement | Transmission notification from Eversource Energy ("ES") to retire Barnstable SPS as a result of separating Line 122 and Line 135. | 12/2017 | Notification | 2017-05-04
ES-17-T04 | 2017-03-24 | Circuit Separation of Line 122 and Line 135 | Transmission notification from Eversource Energy ("ES") to separate the existing 3.25 mile overhead 115 kV Line 122 from Barnstable Substation in Barnstable MA to Oak Street Substation in Barnstable, MA and the 115 kV Line 135 from Barnstable Substation in Barnstable MA to West Barnstable Substation in Barnstable, MA so they do not share common structures. | 12/2017 | Notification | 2017-05-04
ES-17-T05 | 2017-03-24 | Circuit Separation of Line 325 and Line 344 | Transmission notification from Eversource Energy ("ES") to separate the existing 8.9 mile overhead 345 kV Line 325 from West Medway Substation in Medway, MA to West Walpole Substation in Walpole, MA and the 345 kV Line 344 from West Medway Substation in Medway, MA to Bridgewater Substation in Bridgewater, MA so they do not share common structures. | 12/2017 | Notification | 2017-05-04
ES-17-T03 | 2017-03-24 | Line 108-4 Reconductor Bourne to Valley | Transmission notification from Eversource Energy ("ES") to reconductor the existing 2.6 mile overhead 115 kV Line 108-4 from Bourne Substation in Bourne, MA to Valley Substation in Plymouth, MA with 795 ACSS. | 12/2017 | Notification | 2017-05-04
ES-17-T02 | 2017-03-24 | Line 112 Reconductor Tremont to Industrial Park Tap | Transmission notification from Eversource Energy ("ES") to reconductor the existing 10.3 mile overhead 115 kV Line 112 from Tremont Substation in Wareham, MA to Industrial Park Tap in Acushnet, MA with 795 ACSS. | 12/2017 | Notification | 2017-05-04
ES-17-X02 | 2017-03-23 | Y-151 SPS Setpoint Change | Transmission notification from Eversource Energy ("ES") to change the Y-151 SPS setpoint from 112 MVA to 386 MVA as a result of upgrading the Y-151 conductor. The SPS trips the Y-151circuit at the Power Street Substation in Hudson, NH to prevent equipment damage when the loading exceeds the STE rating. | 2017-03-25 | Notification | 2017-05-04
HE-17-T01 | 2017-03-28 | Holyoke 17L Substation Asset Replacement | Transmission notification from Holyoke Gas and Electric ("HG+E") to replace one in-line 115 kV circuit breaker, terminate the two existing 115 kV lines and supply two 115/13.8 kV power transformers at the Holyoke 17L Substation in Holyoke, MA. | 11/2019 | Notification | 2017-05-04
NEP-17-T12 | 2017-04-03 | M13/L14 115 kV Line Reconductor Bell Rock Road to Bates Street Tap | Transmission notification from New England Power ("NEP") to reconductor the 8.3 mile overhead 115 kV M13/L14 Line from Bell Rock Road to Bates Street Tap. | 4/2021 | Notification Withdrawn | 5/4/2017 3/16/2021
ES-17-G15 | 2017-03-30 | Otis Wind | Generator notification from Eversource Energy ("ES") on behalf of The Town of Otis for the installation of a 1.5 MW wind turbine generator in Otis, MA and interconnecting to the Blandford Substation via the 23 kV 19J3 feeder. | 2017-04-28 | Notification | 2017-05-04
ES-17-G14 | 2017-04-07 | Lower Village Hydro Claremont Generator | Generator notification from Eversource Energy ("ES") on behalf of Sugar River Power, LLC for the installation of a 1.4 MW hydro generator in Claremont, NH and interconnecting to the Lafayette Street Substation via the 12.5 kV 109214 feeder. | 3/2017 | Notification | 2017-05-04
ES-17-G02 | 2017-03-21 | Lone Plain Solar Whately Solar | Generator notification from Eversource Energy ("ES") on behalf of Lone Plain Solar for the installation of 1.99 MW solar PV in Whately, MA and interconnecting to the Podick Substation via the 13.8 kV 18G8 feeder. | 2017-10-01 | Notification | 2017-05-04
ES-17-G17 | 2017-03-30 | Kearsarge Solar Montague Solar | Generator notification from Eversource Energy ("ES") on behalf of Kearsarge Solar, LLC for the installation of 4.18 MW solar PV in Montague, MA and interconnecting to the Montague Substation via the 13.8 kV 21C3 feeder. | 2017-04-28 | Notification | 2017-05-04
ES-17-G16 | 2017-03-24 | Hadley III Solar | Generator notification from Eversource Energy ("ES") on behalf of Hadley III Solar, LLC for the installation of 3.99 MW solar PV in Hadley, MA and interconnecting to the Amherst Substation via the 13.8 kV 17K6 feeder. | 2017-04-28 | Notification | 2017-05-04
ES-17-G10 | 2017-03-21 | CG Greenfield Energy Development Greenfield Solar | Generator notification from Eversource Energy ("ES") on behalf of Greenfield Energy Development, LLC for the installation of 2.0 MW solar PV in Greenfield, MA and interconnecting to the Montague Substation via the 13.8 kV 21C1 feeder. | 2017-05-31 | Notification | 2017-05-04
ES-17-G12 | 2017-03-21 | CG Southampton Energy Development Southampton Solar | Generator notification from Eversource Energy ("ES") on behalf of Southampton Energy Development, LLC for the installation of 2.0 MW solar PV in Southampton, MA and interconnecting to the Gunn Substation via the 23 kV 15A1 feeder. | 2017-05-31 | Notification | 2017-05-04
ES-17-G08 | 2017-03-21 | ALDI South Windsor Solar | Generator notification from Eversource Energy ("ES") on behalf of ALDI, Inc for the installation of 1.665 MW solar PV in South Windsor, CT and interconnecting to the South Windsor Substation via the 13.8 kV 14L4 feeder. | 2017-06-30 | Notification | 2017-05-04
NEP17-GNF26 | 2017-04-05 | Soltage East Bridgewater Solar | Generator notification from New England Power ("NEP") on behalf of Soltage LLC for the installation of 4.9 MW solar PV in East Bridgewater, MA and interconnecting to the Dupont Substation via the 13.8 kV 91W41 feeder. | 2017-05-01 | Notification | 2017-05-04
NEP17-GNF25 | 2017-04-05 | BWC Bassriver Westport Solar | Generator notification from New England Power ("NEP") on behalf of BWC Bassriver LLC for the installation of 2.0 MW solar PV in Westport, MA and interconnecting to the Bates Street Substation via the 13.8 kV 115W52 feeder. | 2017-05-01 | Notification | 2017-05-04
NEP-17-GNF22 | 2017-04-05 | Housatonic Solar 1 West Stockbridge | Generator notification from New England Power ("NEP") on behalf of Housatonic Solar 1 LLC for the installation of 2.0 MW solar PV in West Stockbridge, MA and interconnecting to the Risingdale Substation via the 13.8 kV 1109W3 feeder. | 2017-05-01 | Notification | 2017-05-04
NEP-17-GNF21 | 2017-04-04 | Stonehill College North Easton Solar | Generator notification from New England Power ("NEP") on behalf of Stone Hill College for the installation of 2.166 MW solar PV in North Easton, MA, interconnecting to the Belmont Street Substation via the 13.8 kV 98W48 feeder. | 2017-05-01 | Notification | 2017-05-04
NEP-17-T02 | 2017-03-08 | Aquidneck Island Reliability Project | Transmission application from New England Power Company (“NEP”) for the conversion of the Jepson substation from 69 kV to 115 kV. Removal of the existing 69 kV equipment and 115-69 kV transformers at the Dexter substation and converting 69 kV lines 61 and 62 to 115 kV. Also construction of a 69/13.8 kV Substation in Newport, RI. | 12/2019 | Approved | 2017-03-31
NEP-17-GNF20 | 2017-03-04 | Aspen Aerogels East Providence Generator Project | Generator notification from New England Power (“NEP”) on behalf of Aspen Aerogels Inc., for the installation of a 1.51 MW internal combustion synchronous generator in East Providence, RI and interconnecting to the Wampanoag Substation via the 12.47 kV 48F6 feeder. | 2017-01-28 | Notification | 2017-03-31
NEP-17-GNF10-Rev.1 | 2017-03-04 | Syncarpha Bondsville Palmer Solar Project | Generator notification from New England Power (“NEP”) on behalf of Syncarpha Bondsville LLC for the installation of 4.4 MW solar PV in Palmer, MA and interconnecting to the Wampanoag Substation via the 13.2 kV 523L4 feeder. Project is increasing the previously approved 4.0 MW output to 4.4 MWs. | 2017-04-01 | Notification | 2017-03-31
NEP-17-GNF19 | 2017-03-04 | SunEdison Foxboro Solar Project | Generator notification from New England Power (“NEP”) on behalf of SunEdison Organization 1 LLC for the installation of 1.2 MW solar PV in Foxboro MA, interconnecting to the Foxboro 2 Substation via the 13.8 kV 3432W2 feeder. | 2017-04-01 | Notification | 2017-03-31
NEP-17-GNF18 | 2017-03-04 | ISM Partners Dighton Solar Project | Generator notification from New England Power (“NEP”) on behalf of ISM Partners LLC for the installation of 3.5 MW solar PV in Dighton MA, interconnecting to the Dighton Substation via the 13.8 kV 19W72 feeder. | 2017-04-01 | Notification | 2017-03-31
NEP-17-GNF17 | 2017-03-04 | Sampson Road Charlton Solar Project | Generator notification from New England Power (“NEP”) on behalf of Sampson Road Solar for the installation of 2.0 MW solar PV in Charlton, MA, interconnecting to the West Charlton Substation via the 13.2 kV 415L2 feeder. | 2017-04-15 | Notification | 2017-03-31
NEP-17-GNF16 | 2017-03-03 | Incom Charlton Solar Project | Generator notification from New England Power (“NEP”) on behalf of Incom Inc. for the installation of 2.5 MW solar PV in Charlton, MA, interconnecting to the Snow Street Substation via the 13.2 kV 413L4 feeder. | 2017-04-15 | Notification | 2017-03-31
NEP-17-GNF15 | 2017-03-03 | 510 Project Development Leicester Solar Project | Generator notification from New England Power (“NEP”) on behalf of 510 PV Project Development LLC for the installation of 2.0 MW solar PV in Leicester, MA, interconnecting to the North Oxford Substation via the 13.2 kV 406L1 feeder. | 2017-04-01 | Notification | 2017-03-31
NEP-17-GNF14 | 2017-03-03 | Quality Drive Lincoln Solar Project | Generator notification from New England Power (“NEP”) on behalf of Quality Drive LLC for the installation of 1.16 MW solar PV in Lincoln, RI, interconnecting to the Washington Substation via the 126W42 feeder. | 2017-04-01 | Notification | 2017-03-31
NEP-17-GNF13 | 2017-03-03 | Hewlett Packard Andover Solar Project | Generator notification from New England Power (“NEP”) on behalf of Hewlett Packard for the installation of 1.8 MW solar PV in Andover, MA, interconnecting to the East Tewksbury Substation via the 13.2 kV 59L5 feeder. | 2017-04-01 | Notification | 2017-03-31
NEP-17-GNF12 | 2017-03-03 | Iron Horse 4 Billerica Solar Project | Generator notification from New England Power (“NEP”) on behalf of Iron Horse 4 LLC for the installation of 4.999 MW solar PV in Billerica, MA, interconnecting to the Billerica Substation via the 23 kV 2385 feeder. | 2017-04-01 | Notification | 2017-03-31
EM-17-X01 | 2017-02-14 | Keene Road 345 kV Cross Trip Control Removal | Transmission notification from Emera Maine (“EM”) to remove the cross trip at Keene Road. Presently Keene Rd control scheme is set up to trip the Chester SVC line 3015 by opening the normally open KT1H-2 whenever both breakers KT1H-1 and K3001-5 are open, which potentially left the SVC radial to the T1 Auto transformer (if KT1H-2 were closed) and the Emera Maine 115kV system. This system is redundant to normal operating conditions with KT1H-2 operated normally open. The removal of this cross trip is just a cleanup item to simplify the local control scheme. | 6/2017 | Notification | 2017-03-31
TMLP-17-T01 | 2017-02-03 | Cleary Flood Substation Ring Bus Replacement Project | Transmission notification from Taunton Municipal Light Plant (“TMLP”) for the replacement of the Cleary Flood Substation 115 kV ring bus with a new 115 kV breaker and one half substation. The new substation will terminate two 115 kV lines connecting Cleary to the NGrid S8 and V5 lines, two 115 kV lines supplying radial TLMP distribution load, and one short 115 kV tie line to the Cleary Flood Generation plant. | 11/2019 | Notification | 2017-03-31
ES-17-G07 | 2017-03-02 | Shagbark Lumber East Hassam Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of RER Energy Group for the installation of 1.316 MW solar PV in East Haddam CT, interconnecting to the Haddam 11C Substation via the 23 kV 11C13 feeder. | 2017-04-23 | Notification | 2017-03-31
KES-17-T01 | 2017-01-27 | Kleen Energy AVR Replacement and Enable PSS Project | Transmission application from Kleen Energy Systems LLC (“KES”) for the replacement of the station Automatic Voltage Regulator (AVR) for Kleen CT 1, CT 2, and ST1 generators and enable the Power System Stabilizer (PSS). | 2017-04-01 | Approved | 2017-02-24
TCPM-17-X01 | 2017-01-27 | McIndoes Units 1-4 AVR Replacement Project | Transmission application from TransCanada Northeast Hydro (“TCPM”) for the replacement of the station Automatic Voltage Regulator (AVR) for McIndoes Units 1 – 4 generators. | 2017-05-31 | Approved | 2017-02-24
AWE-17-G01 | 2017-01-26 | Antrim Wind Generation and Transmission Project | Generator application from Antrim Wind Energy LLC (“AWE”) for the installation of nine 3.2 MW wind turbine generators (28.2 MW net output) in Antrim, New Hampshire. | 2018-12-31 | Approved | 2017-02-24
ES-17-T01 | 2017-01-26 | Antrim Wind Generation and Transmission Project | Transmission application from Eversource Energy (”ES”) for the construction of the Tuttle Hill 115 kV Switching Station with a three 115 kV circuit breaker ring bus in Antrim, New Hampshire . In addition, the L163 Line from North Keene to Jackman will be split to connect the new switching station. | 12/2018 | Approved | 2017-02-24
ES-17-G06 | 2017-01-30 | Rumford Avenue Newton Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Rumford Avenue Solar LLC for the installation of a 1.671 MW solar array located in Newton, MA and interconnecting via the 13.8 kV distribution circuit 33-H3 out of the 115/14 kV Waltham Station #282. | 2017-04-01 | Notification | 2017-02-24
ES-17-G05 | 2017-01-18 | Boston Medical Center CHP Generator Project | Generator notification from Eversource Energy (“ES”) on behalf Boston Medical Center for the installation of a 2.0 MW CHP generator and interconnecting behind 13.8 kV primary customer station #376, supplied by two 13.8 kV Lines 376-90 and 376-104 off Andrew Square Station #106 in Boston, MA. | 2017-03-31 | Notification | 2017-02-24
ES-17-G03 | 2017-01-30 | Quantum Biopower Southington Generator Project | Generator notification from Eversource Energy (“ES”) on behalf of Quantum Biopower LLC for the installation of a 1.15 MW biogas fuel combustion generator located in Southington, CT and interconnecting via the 13.8 kV distribution circuit 12A6 out of the 115 kV Forestville #12A substation. | 2017-03-01 | Notification | 2017-02-24
ES-17-G09 | 2017-02-08 | Lodestar Canis Major Hartford Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Lodestar Energy LLC for the installation of a 2.0 MW solar array located in Hartford, CT and interconnecting via the 13.8 kV distribution circuit 30A2 out of the 115 kV Silver 30A substation. | 2017-03-15 | Notification | 2017-02-24
NEP-17-GNF09 | 2017-02-01 | Syncarpha Still River Bolton Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Syncarpha Still River LLC for the installation of a 2.4 MW solar array located in Bolton, MA and interconnecting via the 13.8 kV distribution circuit 216W4 out of the Fitch Road #216 substation. | 2017-02-28 | Notification | 2017-02-24
NEP-17-GNF10 | 2017-02-01 | Syncarpha Bondsville Palmer Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Syncarpha Bondsville LLC for the installation of a 4.0 MW solar array located in Palmer, MA and interconnecting via the 13.2 kV distribution circuit 523L4 out of the Thorndike #523 substation. | 2017-02-28 | Notification | 2017-02-24
NEP-17-GNF08 | 2017-02-01 | Osgood Solar North Andover Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Osgood Solar LLC for the installation of a 4.77 MW solar array located in North Andover, MA and interconnecting via the 13.8 kV distribution circuit 2358 out of the Ward Hill substation. | 2017-02-28 | Notification | 2017-02-24
NEP-17-GNF07 | 2017-02-01 | 510 PV Project Development Newbury Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of 510 PV Project Development LLC for the installation of a 2.98 MW solar array located in Newbury, MA and interconnecting via the 13.8 kV distribution circuit 2367 out of the King Street substation. | 2017-02-28 | Notification | 2017-02-24
NEP-17-GNF05 | 2017-01-26 | CEC Solar West Bridgewater Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of CEC Solar for the installation of a 1.656 MW solar array located in West Bridgewater, MA and interconnecting via the 13.8 kV distribution circuit 98W44 out of the Belmont substation. | 2017-02-28 | Notification | 2017-02-24
NEP-17-GNF06 | 2017-02-02 | Bradford Holdings Haverhill Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Bradford Holdings LLC for the installation of a 4.968 MW solar array located in Haverhill, MA and interconnecting via the 23 kV distribution circuit 2356 out of the Ward Hill substation. | 2017-02-28 | Notification | 2017-02-24
NEP-17-GNF04 | 2017-02-02 | BJ's Distribution Center Uxbridge Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of BJ’s Distribution Center #800 for the installation of a 1.001 MW solar array located in Uxbridge, MA and interconnecting via the 13.8 kV distribution circuit 321W2 out of the Uxbridge substation. | 2017-02-28 | Notification | 2017-02-24
NEP-17-GNF03 | 2017-02-02 | Worcester Landfill Solar I Project | Generator notification from New England Power Company (“NEP”) on behalf of City of Worcester Landfill for the installation of a 2.1 MW solar array located in Worcester, MA and interconnecting via the 13.8 kV distribution circuit 8W1 out of the Vernon Hill substation. | 2017-02-28 | Notification | 2017-02-24
NEP-17-GNF11 | 2017-02-02 | Worcester Landfill Solar II Project | Generator notification from New England Power Company (“NEP”) on behalf of City of Worcester Landfill for the installation of a 4.4 MW solar array located in Worcester, MA and interconnecting via the 13.8 kV distribution circuit 8W2 out of the Vernon Hill substation. | 2017-02-28 | Notification | 2017-02-24
NEP-17-X01 | 2017-02-07 | Carpenter Hill W-175 Overload SPS Retirement Project | Transmission notification from New England Power Company (“NEP”) on for the retirement of the Carpenter Hill W-175 Overload SPS. | 3/2017 | Notification | 2017-02-24
NEP-17-X02 | 2017-01-27 | Brayton Point LOLA SPS Retirement Project | Transmission notification from New England Power Company (“NEP”) on for the retirement of the Brayton Point LOLA SPS. | 2017-06-30 | Notification | 2017-02-24
NEP-17-GNF01 | 2017-01-03 | ECA Solar Leominster Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of ECA Solar LLC, for the installation of a 2.8 MW solar array in Leominster, MA and interconnecting to the Pratts Junction #225 substation via feeder #225W2. | 2017-01-31 | Notification | 2017-01-31
NEP-17-GNF02 | 2017-01-03 | GE Lynn Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of GE Lynn, for the installation of a 1.52 MW solar array in Lynn, MA and interconnecting to the GE Riverworks substation via the Line O-169. | 2017-01-01 | Notification | 2017-01-31
GMP-16-G02 | 2016-12-20 | GMP Williston Solar Project | Generator notification from Vermont Electric Power Company (“VELCO”) on behalf of Green Mountain Power Company for the installation of a 4.685 MW solar array located in Williston, VT and interconnecting to the Essex 12.47 kV circuit 19G3. | 2016-11-08 | Notification | 2017-01-31
GMP-16-G03 | 2016-12-20 | GMP Richmond Solar Project | Generator notification from Vermont Electric Power Company (“VELCO”) on behalf of Green Mountain Power Company for the installation of a 1.999 MW solar array located in Richmond, VT and interconnecting to the Richmond 12.47 kV circuit 51G1. | 2016-09-08 | Notification | 2017-01-31
GMP-16-G04 | 2016-12-20 | GMP Panton Solar Project | Generator notification from Vermont Electric Power Company (“VELCO”) on behalf of Green Mountain Power Company for the installation of a 4.896 MW solar array located in Panton, VT and interconnecting to the Vergennes 12.47 kV circuit 9G2. | 2016-12-31 | Notification | 2017-01-31
GMP-16-G05 | 2016-12-20 | GMP Williamstown Solar Project | Generator notification from Vermont Electric Power Company (“VELCO”) on behalf of Green Mountain Power Company for the installation of a 4.992 MW solar array located in Williamstown, VT and interconnecting to the Websterville 12.47 kV circuit 61G1. | 2016-12-31 | Notification | 2017-01-31
GMP-16-G06 | 2016-12-20 | GMP Hartford Solar Project | Generator notification from Vermont Electric Power Company (“VELCO”) on behalf of Green Mountain Power Company for the installation of a 4.992 MW solar array located in Hartford, VT and interconnecting to the Quechee 12.47 kV circuit G17. | 2016-12-14 | Notification | 2017-01-31
GMP-16-G07 | 2016-12-20 | GMP Bondville Solar Project | Generator notification from Vermont Electric Power Company (“VELCO”) on behalf of Green Mountain Power Company for the installation of a 2.16 MW solar array located in Bondville, VT and interconnecting to the Stratton 12.47 kV circuit G33. | 2016-02-19 | Notification | 2017-01-31
GMP-16-G08 | 2016-12-20 | GMP Westminster National Guard Solar Project | Generator notification from Vermont Electric Power Company (“VELCO”) on behalf of Green Mountain Power Company for the installation of a 1.793 MW solar array located in Westminster, VT and interconnecting to the Westminster 12.47 kV circuit 74G2. | 2016-12-31 | Notification | 2017-01-31
GMP-16-G09 | 2016-12-20 | GMP Cold River Road Rutland Solar Project | Generator notification from Vermont Electric Power Company (“VELCO”) on behalf of Green Mountain Power Company for the installation of a 2.34 MW solar array located in Rutland, VT and interconnecting to the South Rutland 12.47 kV circuit G71. | 2016-12-31 | Notification | 2017-01-31
VELCO-17-GNF01 | 2017-01-04 | VEEP Pownal Park Solar Project | Generator notification from Vermont Electric Power Company (“VELCO”) on behalf of Pownal Solar Park LLC for the installation of a 2.2 MW solar array located in Pownal, VT and interconnecting to the GMP Pownal substation at the 12.47 kV circuit G35. | 2016-12-26 | Notification | 2017-01-31
CMEEC-16-G03 | 2016-12-22 | Solar City Mountain Ash Farm Norwich Battery Storage | Generator notification from Connecticut Municipal Eversource Energy Cooperative (“CMEEC”) on behalf of Solar City Corporation for the installation of a 0.750 MW battery storage unit to be used in conjunction with the existing 3.5 MW solar array (4.25 MW total net output) located in Norwich, CT and interconnecting via the circuit 913 fed from Bean Hill Substation. | 2017-02-01 | Notification | 2017-01-31
CMEEC-16-G07 | 2016-12-27 | Solar City Lafayette Drive Groton Solar Project | Generator notification from Connecticut Municipal Eversource Energy Cooperative (“CMEEC”) on behalf of Solar City Corporation for the installation of a 4.25 MW solar array located in Groton, CT and interconnecting via the circuit 323 fed from Pleasant Valley Substation. | 2017-02-17 | Notification | 2017-01-31
CMEEC-16-G06 | 2016-12-29 | Solar City Trident Park Groton Solar Project | Generator notification from Connecticut Municipal Eversource Energy Cooperative (“CMEEC”) on behalf of Solar City Corporation for the installation of a 1.008 MW solar array located in Groton, CT and interconnecting via the circuit 13-1-2 fed from Pleasant Valley Substation. | 2017-01-20 | Notification | 2017-01-31
NEP-17-T01 | 2017-01-04 | Golden Rock Substation Transformer Addition Project | Transmission application from New England Power Company (“NEP”) for the removal of the Golden Rock tap to the G-133W Line, loop the G-133W Line in and out of the Golden Rock Substation, and install a 115/13.2 kV 33/44/55 MVA transformer and a 115 kV in line breaker at the Golden Rock Substation #19. The line designation from W. Methuen to Golden Rock will remain as G-133W. The line from Golden Rock to E. Methuen will become G-133. | 6/2018 | Approved | 2017-01-31
ES-17-G04 | 2017-01-05 | Speen Street Fragmingham Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Altus Power America for the installation of a 1.25 MW solar array located in Framingham, MAand interconnecting via the 13.8 kV circuit 203-1348H3 off of the Speen Street Substation #433. | 1/2017 | Notification | 2017-01-31
VELCO-16-T14 | 2016-10-28 | Vermont Green Line HVDC ETU Project | Transmission application from Vermont Electric Power Company (“VELCO”) on behalf of Vermont Green Line Devco, LLC for the addition of the QP498 HVDC Terminal. | 12/2019 | Approved Withdrawn | 12/28/2016 2/2/2018
VELCO-16-T15 | 2016-10-28 | Vermont Green Line HVDC ETU Project | Transmission application from Vermont Electric Power Company (“VELCO”) on behalf of Vermont Green Line Devco LLC for the addition of the 150 kV DC cable from the New York/Vermont Border to the New Haven Converter. | 8/2019 | Approved Withdrawn | 12/28/2016 2/2/2018
VELCO-16-T16 | 2016-10-28 | Vermont Green Line HVDC ETU Project | Transmission application from Vermont Electric Power Company (“VELCO”) on behalf of Vermont Green Line Devco LLC for the addition of the 345 kV cable circuit tie from the New Haven 345 kV substation to the Vermont Green Line New Haven Converter. | 8/2019 | Approved Withdrawn | 12/28/2016 2/2/2018
VELCO-16-T17 | 2016-10-28 | Vermont Green Line HVDC ETU Project | Transmission application from Vermont Electric Power Company (“VELCO”) for the modification of the New Haven 345 kV substation to interconnect QP498 includes adding two 345 kV breakers and closing the New Haven 345 kV ring substation. | 12/2019 | Approved Withdrawn | 12/28/2016 2/2/2018
VELCO-16-T18 | 2016-10-28 | Vermont Green Line HVDC ETU Project | Transmission application from Vermont Electric Power Company (“VELCO”) for the reconductoring of the K43, 115 kV transmission line (New Haven-Williston 115 kV). | 12/2019 | Approved Withdrawn | 12/28/2016 2/2/2018
TCPM-16-G01 | 2016-10-28 | Ocean State Generator Addition and Transmission Project | Generator application from TransCanada Power Marketing (“TCPM”) for the installation of a 238 MW (net output) combustion turbine generator at the existing Ocean StatePower facility and interconnecting to the existing Ocean State Power 345 kV Substation at Sherman Farm Road in Burrillville, RI. | 2020-06-01 | Approved Withdrawn | 12/28/2016 10/3/2017
TCPM-16-T01 | 2016-10-28 | Ocean State Generator Addition and Transmission Project | Transmission application from TransCanada Power Marketing (“TCPM”) for the addition and interconnection of a 195/340 MVA 345 kV generator step-up transformer (GSU) at the Ocean State Power 345 kV bus. | 2019-07-01 | Approved Withdrawn | 12/28/2016 10/3/2017
TCPM-16-T02 | 2016-10-28 | Ocean State Generator Addition and Transmission Project | Transmission application from TransCanada Power Marketing (“TCPM”) for the replacement of breakers B1 through B6 with breakers rated for 50kA. This work will be done in conjunction with switchyard modifications to connect Ocean State Power III. | 2018-07-01 | Approved Withdrawn | 12/28/2016 10/3/2017
UI-16-T03 | 2016-12-02 | Pequonnock Substation Reconfiguration Project | Transmission application from The United Illuminating Company (“UI”) for the reconfiguration of UI’s Pequonnock 115 kV substation to a 5-bay breaker-and-a-half Gas Insulated Substation. | 12/2020 | Approved | 2016-12-28
ES-16-G34 | 2016-11-09 | Mattapoisett Solar Cluster Project | Generation application from Eversource Energy (“ES”) on behalf of BWC Origination LLC for the installation of 2 MW of solar photovoltaic generation in Mattapoisett, MA interconnecting at the Crystal Spring #646 substation switchyard via a new express 13.2 kV feeder. | 9/2018 | Notification | 2016-12-28
ES-16-G33 | 2016-11-09 | Mattapoisett Solar Cluster Project | Generation application from Eversource Energy (“ES”) on behalf of BWC Origination LLC for the installation of 5 MW of solar photovoltaic generation in Mattapoisett, MA interconnecting at the Crystal Spring #646 substation switchyard via a new express 13.2 kV feeder. | 9/2018 | Approved | 2016-12-28
ES-16-G55 | 2016-11-21 | Syncarpha Hancock Solar I | Generator notification from Eversource Energy (“ES”) on behalf of Syncarpha Hancock I, LLC for the installation of a 2 MW solar array located in Hancock, MA and interconnecting to the Oswald 30B 115 kV substation via the 23 kV 30B7 distribution feeder. | 10/2017 | Notification | 2016-12-28
ES-16-G56 | 2016-11-21 | Syncarpha Hancock Solar II | Generator notification from Eversource Energy (“ES”) on behalf of Syncarpha Hancock II, LLC for the installation of a 2 MW solar array located in Hancock, MA and interconnecting to the Oswald 30B 115 kV substation via the 23 kV 30B7 distribution feeder. | 10/2017 | Notification | 2016-12-28
ES-16-G57 | 2016-11-21 | Syncarpha Hancock Solar III | Generator notification from Eversource Energy (“ES”) on behalf of Syncarpha Hancock III, LLC for the installation of a 1 MW solar array located in Pittsfield, MA and interconnecting to the Oswald 30B 115 kV substation via the 23 kV 30B7 distribution feeder. | 10/2017 | Notification | 2016-12-28
ES-16-G58 | 2016-11-21 | Whately Renewables Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Whately Renewables, LLC for the installation of a 1 MW solar array located in Whately, MA and interconnecting to the Podick 18G 115 kV substation via the 13.8 kV 18G8 distribution feeder. | 8/2017 | Notification | 2016-12-28
ES-16-G60 | 2016-11-22 | University of Massachusetts Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of the University of Massachusetts for the installation of a 4.158 MW solar array located in Amherst, MA and interconnecting to the Tillson 10P 115 kV Substation via the 13.8 kV A1 and A2 bus. | 2016-11-15 | Notification | 2016-12-28
ES-16-G59 | 2016-11-08 | Plainfield Solar West Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Plainfield Solar, LLC for the installation of a 1.99 MW solar array interconnecting via the 23 kV distribution circuit 18K2 at the Plainfield substation located in Plainfield, MA. | 11/2018 | Notification | 2016-12-28
ES-15-T59-Rev.1 | 2016-12-01 | 211-503/504 Line Reconductor Project | Transmission notification from Eversource Energy (“ES”) to reconductor 4.68 miles of overhead on the 211-503/504 Lines from North Woburn Tap to the NSTAR/National Grid board at Burlington/Billerica, MA. The revision changes the conductor from 1590 ACSR to 954 ACSS. Proposed in service date of the project is December 2016 for the 211-503 Line reconductor and May 2017 for the 211-504 Line reconductor. | 5/2017 | Notification | 2016-12-28
NEP-16-GNF24 | 2016-12-01 | BWC Wading River Mendon Solar Project | Generator notification from New England Power (“NEP”) on behalf of BWC Wading River LLC for the installation of a 3 MW solar array located in Mendon, MA and interconnecting to the 13.8 kV, Feeder # 332W1 to the Mendon #332 substation. | 2016-12-31 | Notification | 2016-12-28
NEP-16-GNF23 | 2016-12-01 | Theodore Drive Westminster Solar Project | Generator notification from New England Power (“NEP”) on behalf of Theodore Drive Solar LLC for the installation of a 1.497 MW solar array located in Westminster, MA and interconnecting to the East Westminster #609 substation via Feeder #609W1. | 2016-12-31 | Notification | 2016-12-28
NEP-16-GNF22 | 2016-12-01 | 510 PV Project Development Southbridge Solar | Generation notification from New England Power (“NEP”) on behalf of 510 PV Project Development LLC for the installation of a 1.44 MW solar array located in Southbridge, MA and interconnecting to the Snow Street Substation via Feeder #413L4. | 2016-12-31 | Notification | 2016-12-28
ES-16-T64 | 2016-12-01 | 1670-1 Line Reconductor Project | Transmission notification from Eversource Energy (“ES”) to reconductor 5.21 miles of overhead on the 1670, 115 kV transmission line from Southington Substation to Reservoir Junction. The existing 556 ACSR conductor will be replaced with 556 ACSS conductor. | 12/2018 | Notification | 2016-12-28
NEP-16-T12 | 2016-11-17 | Hendersonville Substation Project | Transmission application from New England Power (“NEP”) for the addition of the new Hendersonville 115/13.8 kV substation in Everett, MA. Supply to the new substation will be provided from taps of the overhead portion of NEP’s 115 kV O-167 (Eversource's 423-515) and P-168 (Eversource's 488-518) lines. The new substation will have two 115/13.8 kV 24/32/40 MVA transformers, each supplied from a different 115 kV line. Circuit breakers will be added on the high side of each transformer. | 12/2020 | Approved | 2016-12-28
HE-16-G01 | 2016-12-09 | Mt. Tom Solar Project | Generator notification from Holyoke Gas & Electric (“HGE”) for the installation of a 4.612 MW solar array located in Holyoke, MA and interconnecting to the 13.8 kV, Feeder #36H1 to the Highland 36H substation. | 2016-12-21 | Notification | 2016-12-28
CMEEC-16-G04 | 2016-11-04 | Groton Fuel Cell Project | Generator application from Connecticut Municipal Electric Energy Cooperative (“CMEEC”) for the installation of two 2.8 MW fuel cell generators (5.6 MW net output) interconnecting to the 34.5 kV Groton Utilities distribution system at the Shennecossett Road Substation located in Groton, CT. | 2016-09-01 | Approved | 2016-12-16
GDF-16-G01 | 2016-10-13 | Milford, MA Generator Uprate and Transmission Project | Generator application from GDF Suez (“GDF”) to increase the Network Resource Capability of the existing 149 MW, one-on-one combined cycle generator interconnected at the Milford 115 kV Substation in Milford, MA by incorporation of combustion turbine peak firing and duct burner addition to the heat recovery steam generator inlet. The new net output for the plant will be 216 MWs at 50 degrees, 222.7 MWs at 20 degrees. | 10/2016 | Approved | 2016-12-16
GDF-16-X01 | 2016-10-13 | Milford, MA Generator Uprate and Transmission Project | Transmission application from GDF Suez (“GDF”) for the replacement of the existing distance protection scheme on Line D-130 terminal at the Milford Power Substation with a pilot protection Scheme. | 10/2016 | Approved | 2016-12-16
ES-16-X06 | 2016-11-02 | Milford, MA Generator Uprate and Transmission Project | Transmission application from Eversource Energy (“ES”) to replace one Step Distance protection scheme on the 201-501 115 kV Line terminal at Medway Substation #65, with a High Speed protections scheme as required by QP527. | 10/2016 | Approved | 2016-12-16
NEP-16-X01 | 2016-10-20 | Milford, MA Generator Uprate and Transmission Project | Transmission application from New England Power Company (“NEP”) for the installation of a pilot protection scheme for the D-130 transmission line relaying at the Millbury #2 terminal. | 10/2016 | Approved | 2016-12-16
DYN-16-G01 | 2016-11-07 | Milford, CT Generator Uprate Project | Generator application from Dynegy Marketing and Trade (“DYN”) on behalf of Milford Power for the increase of the net output of the Milford, CT plant units 1 & 2 by anadditional 47 MWs at 0 degrees (318.5 MWs net output per unit) and an additional 33.2 MWs at 50 degrees (293.00 MWs net output per unit) at the Milford Power combined cycle generator interconnected to the East Devon substation in Milford, CT. | 2017-05-01 | Approved | 2016-12-16
DYN-16-G02 | 2016-11-08 | Lake Road Generator Uprate Project | Generator application from Dynegy Marketing and Trade (“DYN”) on behalf of Lake Road Generating Company, to increase the net output of the Lake Road generating facility Units 1, 2, & 3 by approximately 28 MWs at 90 degrees (284.33 MWs net output per unit) and 32 MWs at 50 degrees (294.00 MWs net output per unit), and 36 MWs at 0/20 degrees (311.33 MWs net output per unit). | 2017-10-31 | Approved | 2016-12-16
CPV-16-G01-Rev.1 | 2016-11-07 | Towantic Generator Uprate Project - Rev.1 | Generator application from Competitive Power Ventures (“CPV”) for the increase of the net output of the Towantic 2 x1 combined cycle generator plant units CT1, CT2 & ST3 by an additional 55.5 MWs 50 degrees (800.5 MWs net output @ 50 degrees and 830.5 MWs at 0 degrees) interconnected at a new 115 kV substation south of Baldwin Junction and north of the Oxford substation. | 2018-06-01 | Approved | 2016-12-16
ES-16-T56 | 2016-10-31 | 1555 115 kV Line Rebuild Project | Transmission notification from Eversource Energy (“ES”) for the rebuild of the 6.7 mile overhead 1555 115 kV Line from Rocky River to Bulls Bridge. | 2017-12-31 | Notification | 2016-12-16
ES-16-G47 | 2016-09-28 | Borrego Solar Freetown Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Borrego Solar for the installation of a 3.984 MW solar array located in Freetown, MA and interconnecting via the 13.2V, Feeder #111 at the Eversource Industrial Park #636 Substation. | 2016-12-30 | Notification | 2016-12-16
ES-16-G14 | 2016-09-28 | Borrego Solar Plympton Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Borrego Solar for the installation of a 4.95 MW solar array located in Plympton, MA and interconnecting via the 23 kV, Feeder #51 at the Brook Street #727 Substation. | 2016-12-30 | Notification | 2016-12-16
ES-16-G31 | 2016-10-31 | CEC Solar Fairhaven Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of CEC Solar, LLC for the installation of a 1.692 MW solar array located in Fairhaven, MA and interconnecting via the 13.2 kV, Feeder #221 at the Arsene Street #654 Substation. | 2016-11-14 | Notification | 2016-12-16
ES-16-G41 | 2016-11-01 | Borrego Solar Bourne Road Plymouth Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Borrego Solar for the installation of a 3.912 MW solar array located in Plymouth, MA and interconnecting to the 23 kV feeder, Circuit #924 to the Valley Substation #715. | 2017-11-15 | Notification | 2016-12-16
ES-16-T52 | 2016-10-27 | Garvins 115 kV Substation Circuit Switcher Addition Project | Transmission notification from Eversource Energy (“ES”) for the addition of two 115 kV circuit switchers (J39 and J51) that will open when either of the transformer primary or secondary protection systems operate. The circuit switchers will have Circuit Switcher Failure Relay and a Lockout Relay. | 9/2017 | Notification | 2016-12-16
ES-16-G53 | 2016-10-27 | Foxwoods CHP Generator Addition Project | Generator notification from Eversource Energy (“ES”) on behalf of Foxwoods Resort and Casino for the installation of a 3.15 MW CHP generating unit to their existing Foxwoods CoGen unit located in Mashantucket, CT and interconnecting to the Tunnel 12S3, 12S5 23 kV circuits and Mystic 13K, 34.5 kV circuit. | 2016-11-30 | Notification | 2016-12-16
ES-16-G52 | 2016-10-28 | Smith and Wesson Springfield Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Smith and Wesson for the installation of a 1.985 MW solar array located in Springfield, MA and interconnecting to the 13.8 kV 5J18A distribution circuit to the East Springfield 115 kV substation. | 2017-01-31 | Notification | 2016-12-16
ES-16-G51 | 2016-10-28 | East Acres Solar Pittsfield Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of East Acres Solar, LLC for the installation of a 3.3 MW solar array located in Pittsfield, MA and interconnecting to the 23 kV 15E1 distribution circuit to the Partridge 115 kV substation. | 1/31/2017 | Notification | 2016-12-16
ES-16-T63 | 2016-11-01 | Line 1211 Structure Replacement Project | Transmission notification from Eversource Energy (“ES”) for the replacement of 44 wood H-Frame structures on the 7.79 mile 1211 115 kV Line from the Doreen Substation in Pittsfield, MA to the Oswald Substation in Pittsfield, MA. | 1/2017 | Notification | 2016-12-16
ES-16-G54 | 2016-11-01 | Borrego Andrew Square Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Borrego Solar for the installation of a 2.28 MW solar array located in South Boston, MA and interconnecting via the 13.8 kV, Feeder #106 at the Andrew Square Substation #106. | 12/31/2016 | Notification | 2016-12-16
ES-16-G44 | 2016-01-11 | Certain Teed Landfill Walpole Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Certain Teed Corp. for the installation of a 1.95 MW solar array located in Walpole, MA and interconnecting via the 13.8 kV, Feeder #146-H6 at the Walpole Station #146. | 2017-01-13 | Notification | 2016-12-16
DEM-16-T01 | 2016-06-30 | Millstone 2 Open Phase Protection System Installation Project | Transmission notification from Dominion Energy Marketing (“DEM”) for the installation of an Open Phase Detection/Protection system on Millstone Unit 2 GSU and Reserve Station Service Transformers. The system will isolate plant auxiliary loads from the affected transformer which would include tripping the generator switchyard breakers in the event of an Open Phase condition on the GSU. | Spring 2017 | Notification Withdrawn | 12/16/2016 8/18/2020
NEP-16-G02-Rev.1 | 2016-11-01 | Bluewave Capital French River Solar Project - Rev.1 | Generator notification from New England Power Company (“NEP”) on behalf of BlueWave Capital for the revision to the installation of a 12 MW solar array located in Oxford, MA and approved at the July 12, 2016 Reliability Committee meeting. The project is being revised to show a zero reactive power capability for the resource consistent with the project System Impact Study. | 2016-09-15 | Notification | 2016-12-16
NEP-16-GNF21 | 2016-11-01 | Kearsarge Energy Granby Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Kearsarge Energy, LLC for the installation of a 2.25 MW solar array located in Granby, MA and interconnecting via Feeder #527L1 out of the Five Corners #527 substation. | 2017-05-02 | Notification | 2016-12-16
CEL-16-G02 | 2016-10-31 | CED Chicopee Solar Westover Solar Project | Generator notification from Chicopee Electric Light Department (“CEL”) on behalf of CED Chicopee Solar, LLC for the installation of a 3.0 MW solar array located in Chicopee, MA and interconnecting via Feeder #7P6 out of the Memorial #7P substation. | 2017-01-07 | Notification | 2016-12-16
MMWEC-16-G01 | 2016-11-18 | Waters River Generator and Transmission Project | Generator application from Massachusetts Municipal Wholesale Electric Company (“MMWEC”) for the installation of 61.816 MW (net output at 50 degrees) simple cycle gas turbine generator in Peabody, MA and interconnecting to the NEP C-155S 115 kV Line at Peabody Municipal’s Waters River Substation. | 6/2020 | Approved | 2016-12-14
MMWEC-16-T01 | 2016-11-18 | Waters River Generator and Transmission Project | Transmission application from Massachusetts Municipal Wholesale Electric Company (“MMWEC”) for the installation of 115 kV generator step-up transformer (GSU) at the Waters River Substation. | 6/2020 | Approved | 2016-12-14
FPL-16-G01 | 2016-10-27 | Casco Bay Energy Storage Project | Generator application from FPL Energy Wyman, LLC (“FPL”) for the installation of a 16.2 MW (net output) battery storage unit located at the Wyman generator station located in Yarmouth, ME to provide frequency regulation and VAR service. | 2016-11-30 | Approved | 2016-11-17
ES-16-G32 | 2016-09-13 | Beacon Falls Fuel Cell Generator and Transmission Project | Generator application from Eversource Energy (“ES”) on behalf of Beacon Falls Energy Park, LLC for the installation of a 63.3 MW (net output) fuel cell generator located in Beacon Fall, CT. | 5/2019 | Approved Withdrawn | 11/8/2016 2/4/2020
ES-16-T53 | 2016-09-13 | Beacon Falls Fuel Cell Generator and Transmission Project | Transmission application from Eversource Energy (“ES”) for the addition of two 115 kV circuit breakers, bus work and protection relays to complete a ring bus design at the Beacon Falls 115 kV Substation to interconnect the Beacon Falls Fuel Cell generator. | 5/2019 | Approved Withdrawn | 11/8/2016 2/4/2020
ES-16-T57 | 2016-09-29 | Beacon Falls Fuel Cell Generator and Transmission Project | Transmission application from Eversource Energy (“ES”) on behalf of Beacon Falls Energy, LLC for the installation of two 13.8/115 kV generator step up transformers at the Beacon Falls Energy Park. | 5/2019 | Approved Withdrawn | 11/8/2016 2/4/2020
ES-16-G46 | 2016-10-07 | Enfield Solar Generator and Transmission Project | Generator application from Eversource Energy (“ES”) on behalf of Ranger Solar, LLC for the installation of a 20 MW solar array located in Enfield, CT and interconnecting to the Scitico substation. | 2018-07-15 | Approved | 2016-11-08
ES-16-T55 | 2016-10-07 | Enfield Solar Generator and Transmission Project | Transmission application from Eversource Energy (“ES”) for the addition of two new 115-kV circuit breakers and converting the existing straight-bus to a ring bus at the Eversource Scitico 115 kV substation in Enfield, CT. Additionally, a generator step-up transformer will be connected to the 115-kV bus between the two new circuit breakers. | 2018-07-15 | Approved | 2016-11-08
ES-16-T62 | 2016-10-07 | Enfield Solar Generator and Transmission Project | Transmission application from Eversource Energy (“ES”) for the addition of a generator step up transformer with a high side circuit breaker connected to the 115 kV bus at the Scitico substation. | 2018-07-15 | Approved | 2016-11-08
ES-16-G42 | 2016-09-28 | Marathon Solar Hopkinton Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Marathon Solar, LLC for the installation of a 3.06 MW solar array located in Hopkinton, MA and interconnecting via the 13.8 kV, circuit 126-H4 at the Hopkinton #126 substation. | 2016-10-30 | Notification | 2016-11-08
ES-16-G43 | 2016-09-28 | Solar City Lexington Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Solar City Corp. for the installation of a 1.624 MW solar array located in Lexington, MA and interconnecting via the 13.8 kV, circuit 533-H2 at the Hartwell Avenue #533 substation. | 2016-10-28 | Notification | 2016-11-08
ES-16-T54 | 2016-09-30 | Brighton Substation Transformer Replacement Project | Transmission notification from Eversource Energy (“ES”) for the replacement in kind of the existing 100 MVA 110C transformer bank at the Brighton Substation #329 in Brighton, MA. The transformer will be replaced by a new HICO 90 MVA, 115/14 kV bank. | 5/2017 | Notification | 2016-11-08
ES-16-G45 | 2016-09-28 | Solar Blue Framingham Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Solar Blue ADESA Framingham Solar Project 1 for the installation of a 3.06 MW solar array located in Framingham, MA and interconnecting via the 13.8 kV, circuit 274-H4 at the Sherborn #274 substation. | 2016-11-01 | Notification | 2016-11-08
ES-16-G05 | 2016-09-28 | Bird Machine Walpole Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Bird Machine Solar Farm, LLC for the installation of a 3.45 MW solar array located in Walpole, MA and interconnecting via the 13.8 kV, circuit 146-H3 and circuit 146-H1 at the Walpole #146 substation. | 2016-11-01 | Notification | 2016-11-08
CEL-16-G01 | 2016-09-19 | Southern Sky Renewable Chicopee Solar Project | Generator notification from Chicopee Electric Light Department (“CEL”) on behalf of Southern Sky Renewable Energy Chicopee, LLC for the installation of a 2.0 MW solar array located in Chicopee, MA and interconnecting via the 13.8 kV, circuit 18L21 at the Chicopee #18L substation. | 2016-12-31 | Notification | 2016-11-08
UI-15-T01-Rev.1 | 2016-08-31 | Bridgeport Harbor Circuit Breaker Addition Project - Rev.1 | Transmission notification from United Illuminating Company (“UI”) for the installation of an additional third 345 kV GIS circuit breaker at the PSEG’s Bridgeport Harbor Combined Cycle 345 kV GIS substation. | 5/2018 | Notification | 2016-11-08
GMP-16-G01 | 2016-09-30 | Huntington Falls Hydro Generator Uprate Project | Transmission application from Green Mountain Power Company (“GMP”) for the 1.1 MW capacity increase (6.6 MW total net output) to the Huntington Falls Hydro Generator Plant. The plant consists of three units connected via a 4.16/46 kV GSU to a radial 46 kV line supplied from the VELCO Florence 115/46 kV substation. | 2017-02-01 | Approved | 2016-11-08
NEP-16-T10 | 2016-10-03 | Sandy Pond Substation Transformer Replacement Project | Transmission notification from New England Power Company (“NEP”) for the installation of a new 115/23 kV 33.44.55 MVA transformer at the Sandy Pond Substation #237 located in Ayer, MA. | 12/2020 | Notification | 2016-11-08
VELCO-16-T01 | 2016-10-10 | New England Clean Power Link ETU Project | Transmission notification from TDI New England (“TDI”) for the addition of the QP501 HVDC Converter Terminal. | 1/2019 | Approved | 2016-11-01
VELCO-16-T02 | 2016-10-10 | New England Clean Power Link ETU Project | Transmission notification from TDI New England (“TDI”) for the addition of the +/-320 kV DC transmission line from the Québec/Vermont border to the QP501 HVDC Converter Terminal. | 1/2019 | Approved | 2016-11-01
VELCO-16-T03 | 2016-10-10 | New England Clean Power Link ETU Project | Transmission notification from TDI New England (“TDI”) for the addition of the 345 kV AC transmission line from the QP501 HVDC Converter Terminal to the VELCO Coolidge 345 kV substation. | 1/2019 | Approved | 2016-11-01
VELCO-16-T04 | 2016-10-10 | New England Clean Power Link ETU Project | Transmission notification from Vermont Electric Power Company (“VELCO”) to modify the Coolidge 345 kV substation to interconnect the QP501 ETU project. Modifications include adding a new 345 kV breaker and replacing the Coolidge 345/115 kV autotransformer. | 1/2019 | Approved | 2016-11-01
VELCO-16-T05 | 2016-10-10 | New England Clean Power Link ETU Project | Transmission notification from Vermont Electric Power Company (“VELCO”) to replace the Newfane 115/46 kV transformer. | 1/2019 | Approved | 2016-11-01
VELCO-16-T06 | 2016-10-10 | New England Clean Power Link ETU Project | Transmission notification from Vermont Electric Power Company (“VELCO”) to replace the West Rutland 115/46 kV transformer. | 1/2019 | Approved | 2016-11-01
VELCO-16-T07 | 2016-10-10 | New England Clean Power Link ETU Project | Transmission notification from Vermont Electric Power Company (“VELCO”) to replace a relay for the Middlebury 115/46 kV transformer. | 1/2019 | Approved | 2016-11-01
VELCO-16-T08 | 2016-10-10 | New England Clean Power Link ETU Project | Transmission notification from Vermont Electric Power Company (“VELCO”) to replace the Irasburg 115/46 kV transformer. | 1/2019 | Approved | 2016-11-01
VELCO-16-T09 | 2016-10-10 | New England Clean Power Link ETU Project | Transmission notification from Vermont Electric Power Company (“VELCO”) to reconductor the VELCO portion of the 381 line (Vernon-Border 345 kV). | 1/2019 | Approved | 2016-11-01
VELCO-16-T10 | 2016-10-10 | New England Clean Power Link ETU Project | Transmission notification from Vermont Electric Power Company (“VELCO”) to Reconductor the K32 line (Coolidge-Cold River 115 kV). | 1/2019 | Approved | 2016-11-01
VELCO-16-T11 | 2016-10-10 | New England Clean Power Link ETU Project | Transmission notification from Vermont Electric Power Company (“VELCO”) to Reconductor the K30 line (West Rutland-Florence-Middlebury 115 kV). | 1/2019 | Approved | 2016-11-01
VELCO-16-T12 | 2016-10-10 | New England Clean Power Link ETU Project | Transmission notification from Vermont Electric Power Company (“VELCO”) to Reconductor the K43 line (New Haven-Williston 115 kV). | 1/2019 | Approved | 2016-11-01
VELCO-16-T13 | 2016-10-10 | New England Clean Power Link ETU Project | Transmission notification from Vermont Electric Power Company (“VELCO”) to Reconductor the K27 line (Williston-Tafts Corner 115 kV). | 1/2019 | Approved | 2016-11-01
ES-16-T58 | 2016-10-13 | New England Clean Power Link ETU Project | Transmission notification from Eversource Energy (“ES”) for the upgrade of the 115 kV N186 Line to achieve the required thermal ratings identified in the System Impact Study. | 1/2019 | Approved | 2016-11-01
ES-16-T59 | 2016-10-13 | New England Clean Power Link ETU Project | Transmission notification from Eversource Energy (“ES”) for the upgrade of the 115 kV A152 Line to achieve the required thermal ratings identified in the System Impact Study. | 1/2019 | Approved | 2016-11-01
ES-16-T60 | 2016-10-13 | New England Clean Power Link ETU Project | Transmission notification from Eversource Energy (“ES”) for the reconductoring of the 345 kV 381 Line to achieve the required thermal ratings identified in the System Impact Study. | 1/2019 | Approved | 2016-11-01
ES-16-T61 | 2016-10-13 | New England Clean Power Link ETU Project | Transmission notification from Eversource Energy (“ES”) for the upgrade of the 345 kV 398 Line to achieve the required thermal ratings identified in the System Impact Study. | 1/2019 | Approved | 2016-11-01
INV-16-G01 | 2016-07-06 | Clear River Energy Center Generation and Transmission Project | Generator application from Invenergy Energy (INV) for the installation of two combustion turbines and two steam turbines operating as two combined cycle units to be directly connected to the 345 kV Sherman Rd substation. The maximum rated summer gross is 1050 MW and the maximum rated winter gross output is 1100 MW (at temp ≥ 0˚F). The Project will be interconnected to the 345 kV Sherman Rd substation with a dedicated 345 kV line. | 2019-06-01 | Approved Withdrawn | 10/21/2016 11/26/2019
INV-16-T01 | 2016-07-06 | Clear River Energy Center Generation and Transmission Project | Transmission notification from Invenergy (INV) for the installation of a new 23.5 kV/345 kV generator step-up transformer rated at 380 MVA. | 2019-06-01 | Approved Withdrawn | 10/21/2016 11/26/2019
NEP-16-T07 | 2016-07-06 | Clear River Energy Center Generation and Transmission Project | Transmission notification from New England Power Company (“NEP”) for the construction of a new 6.5 mile overhead 345 kV transmission line from the Sherman Road Substation in Burrillville, RI to the Clear River Energy Center. | 2019-06-01 | Approved Withdrawn | 10/21/2016 11/26/2019
NEP-16-T08 | 2016-07-06 | Clear River Energy Center Generation and Transmission Project | Transmission notification from New England Power Company (“NEP”) for the construction of a new 345 kV two breaker bay and addition of a tie breaker at the Sherman Road Substation to interconnect to the Clear River Energy Center. | 2019-06-01 | Approved Withdrawn | 10/21/2016 11/26/2019
ES-16-T42 | 2016-07-05 | Clear River Energy Center Generation and Transmission Project | Transmission notification from Eversource Energy (ES) for the 10.6 mile reconductoring of Line 3361 from the Blackstone Station in Blackstone, MA to the Line 3361 border of MA/RI. | 2019-06-01 | Approved Withdrawn | 10/21/2016 11/26/2019
ES-16-T49 | 2016-08-22 | Valley Substation #715 Transformer Replacement Project | Transmission notification from Eversource Energy (“ES”) for the in-kind replacement of the existing 12/16/20 MVA #1 transformer bank at Valley Substation #715 in Plymouth, MA. The transformer will be upgraded to a new 30/40/50 MVA, 115/23kV bank. Replacement of the secondary bus and breaker with a 2000 Amp secondary breaker and metalclad switchgear for four 23kV feeders and a 4.8 MVAR switched capacitor bank. | 2017-06-01 | Notification | 2016-10-21
ES-16-T50 | 2016-08-22 | Tremont Substation #713 Transformer Replacement Project | Transmission notification from Eversource Energy (“ES”) for the in-kind replacement of the 12/16/20 MVA #1 transformer bank at Tremont Substation #713 in Wareham, MA. The transformer will be upgraded to a 15/20/25 MVA 115/23kV bank. | 2017-06-01 | Notification | 2016-10-21
ES-16-G26 | 2016-09-08 | Borrego Spring Street Plympton Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Borrego Solar for the installation of a 1.86 MW solar array located in Plympton, MA and interconnecting via the 23 kV, circuit 980 at the Brook Street Substation #727. | 2016-11-11 | Notification | 2016-10-21
ES-16-T45 | 2016-09-01 | Hopkinton Station 126 Distribution Transformer Addition Project | Transmission application from Eversource Energy (“ES”) for the installation of a 3rd 117/15.12 kV, 30/50/64.5 MVA transformer, a 115 kV “Pass Mo” prefabricated breaker - bus combination line-up, a 3rd section of 14 kV switchgear equipped with 8 feeder positions and 2 5.4 MVAR, 13.8 kV shunt capacitor banks. | 2017-06-01 | Approved | 2016-10-21
ES-16-G38 | 2016-08-20 | US Light Energy Pittsfield Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of US Light Energy LLC for the installation of a 1.497 MW solar array located in Pittsfield, MA and interconnecting via the 23 kV, circuit 30 B7 at the Oswald 115 kV Substation. | 2017-04-01 | Notification | 2016-10-21
ES-16-G30 | 2016-07-21 | Solutia Indian Orchard Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of ESMA-44 LLC for the installation of a 1.931 MW solar array located in Springfield, MA and interconnecting via the 13.8 kV, circuit 27A12 at the Orchard 115 kV Substation. | 2016-12-31 | Notification | 2016-10-21
ES-16-G21 | 2016-09-02 | Pepperidge Farms Fuel Cell Unit 2 Project | Generator notification from Eversource Energy (“ES”) on behalf of Pepperidge Farms for the installation of a 1.4 MW fuel cell located in Bloomfield, CT and interconnecting via the 23 kV, circuit 3B03 at the Bloomfield 115 kV Substation. | 2016-09-30 | Notification | 2016-10-21
ES-16-G35 | 2016-08-31 | 510 Project Development Ludlow Solar Projects A, B, & C | Generator notification from Eversource Energy (“ES”) on behalf of Borrego Solar for the installation of a 2.988 MW solar array located in Ludlow, MA and interconnecting via the 13.8 kV, circuit 19S2 at the Ludlow 115 kV Substation. | 2017-05-01 | Notification | 2016-10-21
ES-16-G23 | 2016-07-12 | ACE Woburn Solar | Generator notification from Eversource Energy (“ES”) on behalf of ACE Woburn Solar, LLC for the installation of a 2.64 MW solar array located in Woburn, MA and interconnecting via the 13.8 kV, circuit 375-H6 at the North Woburn Station #375. | 2016-09-01 | Notification | 2016-10-21
ES-15-T25-Rev.1 | 2016-08-30 | 1779 115 kV Line Rebuild/Asset Conditions Project Rev.1 | Transmission notification from Eversource Energy (“ES”) for the rebuilding of portions of 1779 115-kV Line from South Meadow Substation in Hartford, CT to South Windsor Junction in South Windsor, CT due to asset conditions. This revision is required because of the change of conductor from the approved 556 ACSS to 795 ACSS and 636 ACSR conductors. The overall ratings of the 1779 Line remains the same, and the line constants did not change significantly as a result of a change in conductor types. | 12/2017 | Notification | 2016-10-21
SPL-16-G01 | 2016-08-31 | Hemphill Generator Capacity Increase Project | Generator notification from Springfield Power (“SPL”) to increase the capacity rating of the Hemphill generator located in Springfield, MA from 16.14 MWs to 19.5 MWs (net output) based on improvements made to the turbine. | 2016-10-01 | Notification | 2016-10-21
NEP-16-GNF17 | 2016-09-08 | Sutton Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Sutton Solar LLC for the installation of a 1.95 MW solar array located in Sutton, MA and interconnecting via the 320W5 feeder at the Whitins Pond Substation #320. | 2016-10-01 | Notification | 2016-10-21
NEP-16-GNF16 | 2016-09-08 | SunEdison Franklin Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of SunEdison Origination LLC for the installation of a 1.05 MW solar array located in Franklin, MA and interconnecting via the 344W3 feeder at the Beaver Pond Substation #344. | 2015-05-22 | Notification Withdrawn | 10/21/2016 10/22/2024
NEP-16-GNF19 | 2016-09-08 | Iron Horse Billerica Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Iron Horse Solar I LLC for the installation of a 3.5 MW solar array located in Billerica, MA and interconnecting via the 2385 feeder at the Billerica Substation. | 2016-12-31 | Notification | 2016-10-21
NEP-16-GNF20 | 2016-09-08 | Hunt Road Amesbury Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Hunt Road Solar LLC for the installation of a 4.5 MW solar array located in Amesbury, MA and interconnecting via the 275L4 feeder at the West Amesbury Substation #275. | 2016-10-01 | Notification | 2016-10-21
NEP-16-GNF18 | 2016-09-08 | Horner Millwork Somerset Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Horner Millwork Corp. for the installation of a 1.143 MW solar array located in Somerset, MA and interconnecting via the 11W82 feeder at the Swansea Substation #11. | 2016-12-31 | Notification | 2016-10-21
ES-16-X05 | 2016-08-30 | Lost Nation AVR Replacement Project | Transmission application from Eversource Energy (“ES”) for the upgrade of the existing General Electric Model 3S7501FS140 exciter and voltage regulator on the Lost Nation combustion turbine (17.9 MWs WSCC, 13.9 MWs SSCC) to a General Electric EX2100e. | 2016-10-17 | Approved | 2016-10-21
ES-16-T47 | 2016-08-16 | South Milford Transformer Replacement Project | Transmission notification from Eversource Energy (“ES”) for the replacement of the TB86 (44.8 MVA), with a new 44.8 MVA 115 – 34.5 kV transformer at the South Milford Substation. | 12/2016 | Notification | 2016-10-21
ES-16-T48 | 2016-09-01 | Tracy Ring Bus and Transformer Project | Transmission notification from Eversource Energy (“ES”) to expand the existing Tracy 14M 115-kV bus into a full ring bus arrangement. Install two 115-kV circuit breakers and associated substation equipment and add a new 115/13.8-kV 3X transformer (47 MVA). | 5/2017 | Notification | 2016-10-21
NHT-16-T02 | 2016-09-27 | Seabrook 345 kV Substation Coupling Capacitor Voltage Transformer Replacements with Voltage Transformers (Protection Measurement Transformers) | Transmission notification from New Hampshire Transmission (“NHT”) for the replacement three CCVTs (“363‐CCVT”) connected to the 345kV Seabrook‐Scobie Pond 363 line terminal equipment with three new VTs (“363‐VT”). The decision to retire the 363‐CCVTs at this time is based on an asset condition assessment of the equipment and a determination that this equipment has reached or exceeded its expected end‐of‐life. | 2016-11-11 | Notification | 2016-10-21
ES-16-G36 | 2016-08-20 | Hampshire College Field K Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Solar City Corporation for the installation of a 2.077 MW solar array located in Hadley, MA and interconnecting via the 13.8 kV, circuit 19B15 at the Midway 115 kV Substation. | 2017-01-01 | Notification | 2017-10-14
ES-16-G37 | 2016-08-20 | Hampshire College Field I Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Solar City Corporation for the installation of a 2.047 MW solar array located in Amherst, MA and interconnecting via the 13.8 kV, circuit 19B16 at the Midway 115 kV Substation. | 2017-01-01 | Notification | 2017-10-14
ES-16-G39 | 2016-08-20 | BVD Cloverdale Pittsfield Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of BVD, LLC for the installation of a 1.484 MW solar array located in Pittsfield, MA and interconnecting via the 23 kV, circuit 30B7 at the Oswald 115 kV Substation. | 2017-04-01 | Notification | 2016-10-14
ES-16-G40 | 2016-08-30 | BVD Churchill Pittsfield Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of BVD, LLC for the installation of a 1.98 MW solar array located in Pittsfield, MA and interconnecting via the 23 kV, circuit 30B7 at the Oswald 115 kV Substation. | 2017-04-01 | Notification | 2016-10-14
ES-16-T51 | 2016-09-06 | Curtisville Switching Station and Broken Ground Substation Project | Transmission application from Eversource Energy (“ES”) for Phase I of the Curtisville 115 kV Switching Station and the Broken Ground 115 – 34.5 kV Substation located in Concord, NH. The Curtisville Switching Station work will consist of splitting the 115 kV Line C189 (Farmwood to Garvins) to connect a new Curtisville Switching Station. The Curtisville Switching Station will be a five circuit breaker ring bus. Two 115-kV circuits are to be built from Curtisville to the Broken Ground Substation at approximately 250 feet each. The 115 kV Curtisville Switching Station will be constructed, owned and operated by Eversource Energy. The Broken Ground Substation work will consist of installing two 60 MVA, 115/34.5 kV transformers and two 115 kV circuit breakers and associated 34.5 kV bus work and circuit breakers. The Broken Ground Substation and be constructed, owned and operated by Unitil Energy Systems (UES). | 6/2017 | Approved | 2016-10-13
ES-16-X02 | 2016-09-06 | Schiller AVR Replacement Project | Transmission application from Eversource Energy (“ES”) for the replacement of the Schiller Unit G4 steam turbine generator excitation system with Basler DECS 2100 digital excitation systems. | 2017-10-30 | Approved | 2016-10-13
ES-16-X03 | 2016-09-06 | Schiller AVR Replacement Project | Transmission application from Eversource Energy (“ES”) for the replacement of the Schiller Unit G5 steam turbine generator excitation system with Basler DECS 2100 digital excitation systems. | 2017-04-30 | Approved | 2016-10-13
ES-16-X04 | 2016-09-06 | Schiller AVR Replacement Project | Transmission application from Eversource Energy (“ES”) for the replacement of the Schiller Unit G6 steam turbine generator excitation system with Basler DECS 2100 digital excitation systems. | 2017-10-30 | Approved | 2016-10-13
ES-16-G24 | 2016-07-12 | Astra Zeneca Waltham CHP Project | Generator notification from Eversource Energy (“ES”) on behalf of Astra Zeneca for the installation of a 1.2 MW CHP located in Waltham, MA and interconnecting Interconnect behind a 13.8kV primary customer station #373 with circuit 373-1358 normal supply, 373-1360 duplicate supply, both are off Trapelo Road Station #450. | 2016-08-24 | Notification | 2016-08-23
ES-16-G27 | 2016-07-26 | 510 Project Development Solar Gill | Generator notification from Eversource Energy (“ES”) on behalf of 510 Project Development Solar Gill for the installation of a 1.992 MW solar array located in Gill, MA and interconnecting to the French King 115 kV substation through the 21B8 13.8 kV circuit. | 2016-12-31 | Notification | 2016-08-23
ES-16-G28 | 2016-07-26 | Hatfield Solar Project | Generator notification from Eversource Energy (“ES”) onbehalf of Hatfield Renewables, LLC for the installation of a 1.89 MW solar array located in Hatfield, MA and interconnecting to the Podick 115 kV substation through the 18G6 13.8 kV circuit. | 2017-06-01 | Notification | 2016-08-23
ES-16-TCA-13 | 2016-07-22 | X176 Line Rebuild Project | Transmission notification from Eversource Energy (“ES”) for 2.96 miles of overhead structure replacements on the 115 kV X176 Line from Ludlow Substation to the Eversource/NGrid border. | 1/2017 | Notification | 2016-08-23
BE-16-X01 | 2016-07-26 | Bridgeport Energy PSS Installation Project | Transmission application from Emera Energy Service Subsidiary #5 on behalf of Bridgeport Energy (“BE”) for to enable a Power System Stabilizer to the existing Bridgeport Energy combined cycle generator units BE ST10, CT 11 and CT 12. | 9/2016 | Approved | 2016-08-23
NEP-16-G03 | 2016-07-28 | Solterra Spencer Solar Project | Generator application from New England Power Company (“NEP”) for the installation of a 14.682 MW solar array comprised of seven 1000kW, one 393 kW, one 331 kW, one 298 kW, three 860 kW, one 1400 kW, one 930 kW and two 875 kW photovoltaic (PV) inverters. The inverters will be connected to the 23 kV distribution network through the 480V/23.9kV step up transformers. The facilities will be located in Paxton, MA and will be interconnected to the Treasure Valley 115 kV Substation of National Grid via a new 23 kV distribution circuit 55K11 and a 115 /24 kV transformer rated 20/26.6/33 MVA. | 2016-09-08 | Approved | 2016-08-23
NEP-16-T09 | 2016-07-28 | Solterra Spencer Solar Project | Transmission application from New England Power Company (“NEP”) for the installation of a 115/24 kV transformer rated 20/26.6/33 MVA at the Treasure Valley Substation in Spencer, MA to connect the Solterra Spencer Solar Project. | 2016-09-08 | Approved | 2016-08-23
CMP-16-G01 | 2016-08-02 | Athens Energy LLC | Generator application from Central Maine Power Company (“CMP”) on behalf of Athens Energy LLC for the installation of a 8.5 MW (Gross MWs) biomass generator and interconnecting via a 12.47 distribution circuit to the 115 kV Athens Substation in Athens, Maine. | 2016-07-30 | Approved | 2016-08-17
ES-16-G25 | 2016-06-28 | Clean Energy Collective Carver Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Clean Energy Collective LLC for the installation of a 2.00 MW solar array located in Carver, MA and interconnecting via the 23 kV, feeder #51 at the Brook Street Substation #727. | 2016-08-05 | Notification | 2016-07-19
ES-16-T44 | 2016-06-29 | Webster Transformer Replacement Project | Transmission notification from Eversource Energy (“ES”) for the replacement of three 115/34.5 kV transformers (20 MVA, 20MVA, 16 MVA) with two new 44.8 MVA 115/34.5 kV transformers at the Webster Substation in Franklin, NH. | 11/2017 | Notification | 2016-07-19
ES-16-G17 | 2016-06-14 | Falmouth Landfill Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of The Townof Falmouth for the installation of a 3.0 MW solar array located in Falmouth, MA and interconnecting via the 23 kV, feeder #98A at the Falmouth Substation. | 2016-09-01 | Notification | 2016-07-19
ES-16-G09 | 2016-06-15 | NRG Freeman Sandwich Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of NRG Renew Canal I LLC for the installation of a 1.476 MW solar array located in Sandwich, MA and interconnecting via the 23 kV, feeder #81 at the Otis Substation. | 2016-11-29 | Notification | 2016-07-19
ES-16-G11 | 2016-06-15 | Westport 1 Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Westport Power Associates for the installation of a 2.0 MW solar array located in Westport, MA and interconnecting via the 13.2 kV, feeder #532 at the Cross Road Substation. | 2016-11-01 | Notification | 2016-07-19
NEP-16-GNF15 | 2016-06-27 | WED Portsmouth I Wind Project | Generator notification from New England Power Company (“NEP”) for the installation of a 1.5 MW wind turbine generator located in Portsmouth, RI and interconnecting via the 13.8 kV, circuit 36W41 at the Dexter 36 Substation. | 2016-07-01 | Notification | 2016-07-19
NEP-15-GNF17 Rev.1 | 2016-06-27 | Nextamp Peak Hancock Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 2.0 MW solar array located in Hancock, MA and interconnecting via the 23 kV, circuit 1018K1 at the Partridge 15E Substation. Project revisions include a change and increase in plant size from 1.75 to 2 MW and equipment associated with the plant. | 2016-12-14 | Notification | 2016-07-19
ES-16-G20 | 2016-06-21 | Citizens Agawam Landfill Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Citizen’s Enterprises Corp. for the installation of a 1.936 MW solar array located in Agawam, MA and interconnecting via the 13.8 kV, circuit 16C12 at the Agawam 16C Substation. | 2016-10-31 | Notification | 2016-07-19
ES-16-G18 | 2016-06-20 | Big Y Foods Southwick Solar Project | Generator notification from Eversource Energy (“ES”) for the installation of a 1.316 MW solar array located in Southwick, MA and interconnecting via the 23 kV,circuit 29A5 at the Southwick 29A Substation. | 2016-10-31 | Notification | 2016-07-19
UI-16-T02 | 2016-06-16 | East Shore 345 kV Circuit Switcher Replacement Project | Transmission notification from United Illuminating (“UI”) for the replacement of the 345 kV circuit switchers at the East Shore Substation in New Haven, CT. | 12/2018 | Notification | 2016-07-19
ES-16-G19 | 2016-06-17 | LSE Centaurus Ashland Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of LSE Centaurus LLC for the installation of a 2.412 MW solar array located in Ashland, MA and interconnecting via the 13.8 kV, 274-H1 circuit off Western Ave. Sherborn Station #274. | 2016-07-31 | Notification | 2016-07-19
KGE-16-G01 | 2016-06-23 | Kendall 3 Steam Generator AVR Replacement and Steam Turbine Upgrade Project | Generator application from Kendall Green Energy (“KGE”) for the installation of a new GE EX2100e AVR. The Project also includes installing a Back Pressure Steam Turbine (BPST) prime mover for Kendall 3. | 2016-07-12 | Approved | 2016-07-19
TCPM-16-X01 | 2016-06-14 | Moore Hydro Excitation System Upgrade and PSS Addition Project | Transmission application from TransCanada Power Marketing (“TCPM”) for the upgrade of the existing rotating exciters on the Moore hydro units 1 thru 4 at Moore Station in Littleton, NH with new ABB Unitrol 6080 Static Excitation Systems. A power system stabilizer (PSS) will be added to each Moore unit as part of this upgrade. | 2016-11-30 | Approved | 2016-07-19
UI-16-G02 | 2016-06-20 | Yale University Generator Project | Generator application from United Illuminating Company (“UI”) on behalf of Yale University for the installation of two gas turbine generators (7.2 MWs summer net output each. 14.4 MWs total output) located in New Haven, CT and interconnecting to the 13.8 distribution system at Broadway 115/13.8 kV substation. | 5/2016 | Approved | 2016-07-19
NEP-16-G02 | 2016-06-27 | Bluewave Capital French River Oxford Solar Project | Generator application from New England Power Company (“NEP”) on behalf of Bluewave Capital for the installation of a 12 MW solar array located in Oxford, MA and interconnecting to the 13.2 kV feeders 406L2 and 406L4 out of the North Oxford Substation. | 2016-09-15 | Approved | 2016-07-19
ES-16-T43 | 2016-06-29 | Seafood Way Substation Project | Transmission application from Eversource Energy (“ES”) for the construction of a new twelve-breaker, 115 kV substation (Seafood Way Substation) in Boston, MA connecting both to Chatham Substation and to the K St. Substation via the 250-516/517 115 kV underground cable circuits. The new substation includes three 115/14 kV distribution transformers. | 12/2018 | Approved | 2016-07-19
ES-16-T31 | 2016-07-06 | Northern Pass Transmission Project | Transmission application from Eversource Energy (“ES”) for the installation of a new HVDC Converter Terminal in Franklin, NH. The HVDC system will have a nominal rating of ± 320 kV, 1100 MW. It will be constructed and operated as a symmetrical monopole system. The HVDC system will deliver 1090 MW nominal to the 345-kV Deerfield Substation, its Point-of-Interconnection. The HVDC voltage source converter system has the feature to operate as a STATCOM and can independently operate within its full reactive power capability and will regulate the 345-kV Franklin ac terminal to 1.030 per unit voltage. A 345-kV, 15 MVAR ac harmonic filter is included. The Franklin HVDC terminal will interconnect to Canada at the 735/230-kV Des Cantons substation in Quebec, Canada via a ± 320-kV dc transmission line from Des Cantons to Franklin and then to the United tates transmission system at the Public Service of New Hampshire’s 345-kV Deerfield substation (POI), located in Deerfield, New Hampshire, via a 345-kV ac overhead transmission line. | 2019-05-31 | Approved Withdrawn | 7/19/2016 8/14/2019
ES-16-T32 | 2016-07-06 | Northern Pass Transmission Project | Transmission application from Eversource Energy (“ES”) for the installation of a new +/- 320 kV HVDC transmission line (97.8 miles overhead, 60.55 miles underground) from Franklin to Des Cantons Substations. The U.S. portion of the HVDC line will run for a total of 158.3 miles from the US/Canadian international border in Pittsburgh, New Hampshire to Franklin, New Hampshire. | 2019-05-31 | Approved Withdrawn | 7/19/2016 8/14/2019
ES-16-T33 | 2016-07-06 | Northern Pass Transmission Project | Transmission application from Eversource Energy (“ES”) for the installation of a new 345-kV ac transmission line from the new Franklin HVDC Converter Terminal to the 345-kV Deerfield Substation. Fiber optic cable will be installed on the new transmission line. To accommodate termination of the new Franklin to Deerfield ac transmission line at the Deerfield Substation, and to prevent transmission line crossings, the existing 345-kV Deerfield – Scobie 373 transmission line will be re-positioned at the 345-kV Deerfield Substation to its own new bay position. The new 345-kV Franklin to Deerfield 3132 AC transmission line will be constructed with two 1590 ACSR, 45/7 stranding, conductors per phase. The transmission towers will be a combination of H-frame, delta, and vertical structures. | 2019-05-31 | Approved Withdrawn | 7/19/2016 8/14/2019
ES-16-T34 | 2016-07-06 | Northern Pass Transmission Project | Transmission application from Eversource Energy (“ES”) for the for upgrades to the Deerfield Substation in Deerfield, NH. To accommodate termination of the new 345-kV line from Franklin Station to Deerfield Substation, and to prevent transmission line crossings, the existing 373 transmission line (Deerfield Substation to Scobie Pond Substation) will be re-positioned to a new bay position. The new 345-kV transmission line will terminate at the vacated 373 Line terminal position. The existing bus protection scheme will be retained and reconfigured to accommodate the new line terminations. Two 345-kV shunt connected, mechanically switched capacitor (MSC) banks, each rated 75 Mvar(2x75 MVAR), will be installed with each bank having its own dedicated circuit breaker. The two capacitor banks with their respective circuit breaker will interconnect to the 345-kV bus via an additional single 345-kV circuit breaker. The capacitor banks are to be controlled by the proposed Deerfield SVC when the SVC is in-service. The existing 345-kV transmission Line 391 that currently connects the Central Maine Power Buxton Substation to the Eversource Energy Scobie Pond Substation will be looped into and terminated at the 345-kV Deerfield Substation, in Deerfield, NH. Terminating Line 391 at Deerfield substation creates two separate, independent circuits; 391N Buxton to Deerfield, 391S Deerfield to Scobie Pond. The 391S line will terminate between existing circuit-breakers 7332 and 3220, which are currently in series with each other. The 391N Line will terminate in its own new bay position with two new 345-kV circuit breakers. A new Static VAR Compensator (SVC), rated -160/+375 MVAR will be interconnected, at 345-kV, in a newly created terminal position. The SVC will operate in voltage control and utilize its inherent MVAR capacity rating to controlthe 345-kV Deerfield bus voltage to the lower set-point of 352.3 kV and maintain the bus voltage in the range of 352.3 to 360 kV. | 2019-05-31 | Approved Withdrawn | 7/19/2016 8/14/2019
ES-16-T35 | 2016-07-06 | Northern Pass Transmission Project | Transmission application from Eversource Energy (“ESM”) for the upgrades at the 345 kV Scobie Pond Substation. Install a 275 MVAR of 345-kV shunt connected capacitor banks at the 345-kV Scobie Pond Substation. The 275 MVAR of capacitors will be divided into four separate capacitor banks each with its own circuit breaker; two 87.5 MVAR capacitor banks (2 x 87.5 MVAR) and two 50MVAR capacitor bank (2 x 50 MVAR). The four capacitors banks will interconnect to the 345-kV Scobie Pond Bus #2 via a single 345-kV circuit breaker. In addition to the capacitor bank installation, two 345-kV, 50 kA circuit breakers will be installed. One circuit breaker is to be installed in series with existing circuit-breaker #9126, and the other circuit breaker will be installed in series with circuit-breaker #262. | 2019-05-31 | Approved Withdrawn | 7/19/2016 8/14/2019
ES-16-T36 | 2016-07-06 | Northern Pass Transmission Project | Transmission application from Eversource Energy (“ESM”) for the upgrade of the 345 kV Deerfield to Scobie Line 373 to a 1580 MVA summer Long Time Emergency thermal rating. | 2019-05-31 | Approved Withdrawn | 7/19/2016 8/14/2019
ES-16-T37 | 2016-07-06 | Northern Pass Transmission Project | Transmission application from Eversource Energy (“ESM”) for the looping of the 345 kV Buxton to Scobie 391 Line into Deerfield Substation and upgrade a new section of the 345 kV Deerfield to Scobie 391S Line. The plan is to loop-in and terminate the existing 345-kV Buxton – Scobie 391 transmission line at the 345-kV Deerfield Substation. Terminating 345-kV Buxton – Scobie 391 transmission line at the 345-kV Deerfield Substation creates two separate, independent 345-kV transmission line circuits; line 391N from 345-kV Buxton Substation to 345-kV Deerfield Substation, and line 391S from 345-kV Deerfield Substation to 345-kV Scobie Pond Substation. The 391N line will terminate in a new bay position at the 345-kV Deerfield Substation. The 391S line will terminate between the existing circuit-breakers #7332 and #3220, which are currently in series. New primary and backup transmission line protection schemes will be installed for both the 391N and 391S transmission lines. In addition to terminating the 345-kV 391 transmission line at the 345-kV Deerfield Substation, the NPT Project requires that the new 391S line be upgraded to a 1580 MVA summer Long Time Emergency thermal rating. The existing 345-kV 391 transmission line, Buxton Substation to Scobie Pond Substation, is approximately 68 miles long (Buxton to ME/NH border ~31 miles and ME/NH border to Scobie Pond ~37 miles). The proposed 345-kV 391N transmission line, 345-kV Buxton Substation to 345-kV Deerfield Substation, will be approximately 50 miles long (Buxton to ME/NH border ~31 miles and ME/NH border to Deerfield ~19 miles). The proposed 345-kV 391Stransmission line, 345-kV Deerfield Substation to 345-kV Scobie Pond Substation, will be approximately 19 miles long. | 2019-05-31 | Approved Withdrawn | 7/19/2016 8/14/2019
UI-16-G01 | 2016-05-26 | Woodbridge Fuel Cell Project | Generator notification from United Illuminating (“UI”) for the installation of a 2.8 MW fuel cell located in Woodbridge, CT and interconnecting via the 13.8 kV, feeder 1605 at the June Street Substation. | 2016-12-01 | Notification | 2016-06-30
CMEEC-16-G03 | 2016-05-23 | Solar City Stott Avenue Norwich Solar Project | Generator notification from Connecticut Municipal Electric Energy Cooperative (“CMEEC”) on behalf of Solar City Corporation for the installation of a 3.5 MW solar array located in Norwich, CT and interconnecting via the 13.8 kV, 913 feeder at the Bean Hill Substation. | 2016-06-30 | Notification | 2016-06-30
CMEEC-16-G02 | 2016-05-27 | Rogers Road Norwich Solar Project | Generator notification from Connecticut Municipal Electric Energy Cooperative (“CMEEC”) on behalf of Solar City Corporation for the installation of a 2.5 MW solar array located in Norwich, CT and interconnecting via the 13.8 kV distribution system at the Bean Hill Substation. | 2016-06-30 | Notification | 2016-06-30
NEP-16-GNF14 | 2016-06-01 | Norton Landfill Solar Project | Generation notification from New England Power Company for the installation of a 2.25 MW solar array located in Norton, MA and interconnecting via the 13.2 kV, 4L1 feeder to the Norton 4 Substation. | 2016-12-31 | Notification | 2016-06-30
NEP-16-GNF13 | 2016-06-01 | Tyngsborough Solar Project | Generation notification from New England Power Company for the installation of a 1.656 MW solar array located in Tyngsborough, MA and interconnecting via the 13.2 kV, 210L1 feeder to the Dunstable 210 Substation. | 2016-12-31 | Notification | 2016-06-30
ES-16-G10 | 2016-05-12 | Borrego Marie's Way Freetown Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Borrego Solar for the installation of a 3.96 MW solar array located in Freetown, MA and interconnecting via the 13.2 kV, 108 feeder at the Industrial Park Substation #636. | 2016-09-08 | Notification | 2016-06-30
ES-16-G04 | 2016-05-25 | Stafford Middle School Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Town of Stafford for the installation of a 2.0 MW solar array located in Stafford, CT and interconnecting via the 23 kV, Blair 15M2 fed from Rockville 14W. | 2016-07-01 | Notification | 2016-06-30
ES-16-G16 | 2016-05-27 | Downing Parkway Pittsfield Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Downing Parkway Solar LLC for the installation of a 2.34 MW solar array located in Pittsfield, MA and interconnecting via the 23 kV, circuit 19A3 at the Doreen 19A Substation. | 2016-10-31 | Notification | 2016-06-30
ES-16-G03 | 2016-05-25 | Corbin Russwin Berlin Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Sol Systems LLC for the installation of a 1.78 MW solar array located in Berlin, CT and interconnecting via the 13.8 kV, circuit 6A6 at the Berlin 6A Substation. | 2016-07-01 | Notification | 2016-06-30
ES-16-G08 | 2016-05-12 | CEC Old Country Westport Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of CEC Solar for the installation of a 2.55 MW solar array located in Westport, MA and interconnecting via the 13.2 kV, 522 feeder at the Fisher Road Substation #657. | 2016-08-01 | Notification | 2016-06-30
ES-16-G07 | 2016-05-11 | 510 Development Hyde Park Boston Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of 510 Development for the installation of a 3.0 MW solar array located in Boston, MA and interconnecting via the 13.8 kV, 496-H2 circuit off Hyde Park Station. | 2016-11-30 | Notification | 2016-06-30
ES-16-T41 | 2016-05-26 | Electric Avenue Substation Project | Transmission notification from Eversource Energy (“ES”) for the construction of a new twelve-breaker, 115 kV substation (Electric Ave. Substation) in Brighton, MA connecting both to Eversource’s Waltham Substation and to Eversource’s Brighton Substation via the 282-520/521 115 kV underground cable circuits. The new substation includes three 115/14 kV distribution transformers. | December 2018 | Approved | 2016-06-30
EE-16-G01 | 2016-05-04 | Tiverton Power Generation Uprate Project - QP 525 | Generator application from Emera Energy (“EE”) on behalf of Tiverton Power LLC for the uprate of existing Tiverton Power combined cycle generation facility to 292MW and 287.5MW at 50F (for a plant output increase of approximately 21.5MW). Power System Stabilizers for the two machines will be set and enabled as part of this uprate project. | 2016-09-30 | Approved | 2016-06-30
EE-16-X01 | 2016-05-04 | Tiverton Power Generation Uprate Project - QP 525 | Generator application from Emera Energy (“EE”) on behalf of Tiverton Power LLC for the retirement of the Tiverton L14/M13 Type III SPS. National Grid was able to determine that the L14/M13 tap lines can be operated at a higher temperature. QP#525 SIS concluded that the tap lines had ratings adequate for the total project (including the uprate) output and will not require the SPS to prevent thermal overloads. | 2016-10-01 | Approved | 2016-06-30
EM-16-G01 | 2016-05-19 | Downeast Wind Generation and Transmission Project - QP #400 | Generator application from Emera Maine (“EM”) on behalf of Downeast Wind LLC for the installation of 30 3.0 MW (90 MW Net Output) wind turbine generators in Washington County, ME and interconnecting to Emera Maine Epping 115kV switching station by means of a new collector substation and generator lead. | 2018-12-31 | Approved Withdrawn | 6/30/2016 4/19/2018
EM-16-T01 | 2016-05-19 | Downeast Wind Generation and Transmission Project - QP #400 | Transmission application from Emera Maine (“EM”) on behalf of Downeast Wind LLC for the Epping switching station reconfiguration and breaker addition for the project generator lead. | 2018-12-31 | Approved Withdrawn | 6/30/2016 4/19/2018
EM-16-T02 | 2016-05-19 | Downeast Wind Generation and Transmission Project - QP #400 | Transmission application from Emera Maine (“EM”) on behalf of Downeast Wind LLC for the collector substation 115/34.5kV new main power transformer and associated breakers and protection associated with QP#400. Also construct a new five mile 115kV generator lead from Epping switching station to the project collector substation. | 2018-12-31 | Approved Withdrawn | 6/30/2016 4/19/2018
ES-16-T05 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the installation of a new 25 mile long 345 kV overhead line from Eversource’s Scobie Pond Substation, in Londonderry, NH to National Grid’s Tewksbury 22A Substation, in Tewksbury, MA. The Eversource portion of the new line is 9.8 miles. A new 345 kV bay connected to the existing breaker-and-half bus arrangement will be constructed at Scobie Pond Substation with a circuit breaker on either side of the new circuit. | December 2017 | Approved | 2016-06-09
ES-16-T06 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the installation of a new 8 mile 345 kV underground cable circuit from Eversource’s Woburn Substation, in Woburn, MA to National Grid’s Wakefield Junction Substation, in Wakefield, MA with 160 MVAr variable shunt reactors at each terminal. Expand the 345 kV switchyard at Woburn Substation to be a breaker-and-a-half substation with four bays. NEP-16-T02 covers the National Grid portion of the project. | December 2018 | Approved | 2016-06-09
ES-16-T07 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the addition of a new 115 kV overhead line from Eversource’s Sudbury Substation to Hudson Light & Power’s Forest Avenue Substation and adding one 115kV breaker (#7) at Sudbury Substation. HLPD-16-T01 covers the Hudson Light & Power Department portion of the project. | December 2018 | Approved | 2016-06-09
ES-16-T08 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the addition of a new 345 kV shunt reactor and converting the existing straight-bus to a ring-bus at Eversource’s K Street Substation in Boston, MA by adding breakers #109, #110, and #111. | December 2018 | Approved | 2016-06-09
ES-16-T09 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the construction of a new Eversource 115 kV switching station in Sharon, MA tobreak up the existing West Walpole to Holbrook 115 kV circuits 447-508 and 447-509 and the new West Walpole to Holbrook circuit (partially the existing 447-502) into two circuits each. | December 2018 | Approved | 2016-06-09
ES-16-T10 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the addition of a new Eversource 115 kV 14 mile overhead line from Eversource’s Walpole Substation, through a new Sharon Switching Station, continuing to Eversource’s Holbrook Substation. At Holbrook, a new 115 kV circuit breaker will be added to accommodate this new circuit. | December 2018 | Approved | 2016-06-09
ES-16-T11 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the addition of a new 115 kV 36.7 MVAr shunt capacitor bank at Eversource’s Hartwell Ave Substation. | December 2018 | Approved | 2016-06-09
ES-16-T12 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the construction of a new Eversource 115 kV 4.7 mile (total) underground cable circuits from Eversource’s Mystic Substation to Eversource’s Chelsea Substation (via new East Eagle Substation). | December 2018 | Approved | 2016-06-09
ES-16-T13 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the construction of a new six-breaker, 115 kV ring bus substation (East Eagle Substation) in East Boston, MA connecting both to Eversource’s Mystic Substation and to Eversource’s Chelsea Substation via new 115 kV underground cable circuits. The new substation includes two 115/14 kV distribution transformers. | December 2018 | Approved | 2016-06-09
ES-16-T14 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for splitting the overhead DCT for approx. 1.5 miles from Baker St substation to a point on the ROW at existing common structure locations. Then a new underground cable section, which will be part of the 110-522 line, will go from that point on the ROW for approx. 2.36 miles where it will terminate at the Needham Substation. | December 2018 | Approved | 2016-06-09
ES-16-T15 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the retirement of the Mystic 9 SPS. | December 2018 | Approved | 2016-06-09
ES-16-T16 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the retirement of the Y-151 SPS, an NPCC Type III SPS, designed to trip breakers at Power Street Substation to eliminate overloads on the Y-151 line between Power Street and Pelham substations. This SPS is no longer needed and procedures for approval of its removal will be initiated following PPA approval. | December 2018 | Approved | 2016-06-09
ES-16-T17 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the reconductoring of the 3.7 mile overhead 115 kV Y-151 line from Power St Substation to the border with National Grid. See NEP-16-T03 for reconductoring the 115 kV Y-151 and Y-151S lines from the Eversource / National Grid border to Pelham Substation and from Pelham Substation to Dracut Jct. | December 2018 | Approved | 2016-06-09
ES-16-T18 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the installation of series breakers #29S and #103S and installing a bus tie breaker #33 at K Street. Additionally, existing circuit breakers #29 (to be #29P), and #103 (to be #103P) at K Street as well as circuit breaker #7 at Mystic will be changed to be operated normally-closed as opposed to their current normally-open status. | December 2018 | Approved | 2016-06-09
ES-16-T19 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the upgrade of the existing 7.96 mile 115 kV 211-514 underground circuit from Eversource’s Woburn Substation, in Woburn, MA to Eversource’s Mystic Substation, in Everett/Boston, MA by paralleling the existing 115 kV underground cable with a new 115 kV underground cable and operating in a bifurcated manner. A new 115kV series reactor will be installed with the new cable. | December 2018 | Approved | 2016-06-09
ES-16-T20 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the installation of a second 345/115 kV autotransformer and a new 345 kV circuit breaker at Eversource’s Mystic Substation in Charlestown/Everett, MA. | December 2018 | Approved | 2016-06-09
ES-16-T21 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the replacement of existing Woburn autotransformer with a new larger unit. The Project also adds four new 345 kV circuit breakers and relocates the termination for the 345 kV 338 line from Tewksbury – Woburn and the 345 kV 346 line from North Cambridge to Woburn. | December 2018 | Approved | 2016-06-09
ES-16-T22 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the completion of upgrades at the Kingston Substation in Boston, MA to create a second normally closed 115 kV bus tie and associated circuit breakers. Additionally, reconfigure the 345 kV switchyard by opening 345 kV breakers #101 and #103. | December 2018 | Approved | 2016-06-09
ES-16-T23 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the opening of the existing 329-510/511 lines at Somerville Substation in Somerville, MA and the 250-516/517 115 kV lines at Chatham St. Substation in Boston, MA, including line switchers and associated equipment at both Somerville Substation and Chatham St. Substation. | December 2018 | Approved | 2016-06-09
ES-16-T24 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the addition of a 36.7 MVAR capacitor bank at Sudbury Station. | December 2018 | Approved | 2016-06-09
ES-16-T25 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the reconfiguration of the Waltham Substation, including relocating terminations for phase shifters and the 282-507 line and adding three new circuit breakers. | December 2018 | Approved | 2016-06-09
ES-16-T26 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for operating the 115 kV bus tie breaker #13 at Brighton Substation as normally closed. | December 2018 | Approved | 2016-06-09
ES-16-T27 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Eversource Energy ("ES") for the installation of a 115 kV, 54 Mvar shunt capacitor bank at Newton Highlands Substation in Newton, MA. | December 2018 | Approved | 2016-06-09
NEP-16-T01 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from New England Power Company ("NEP") for the addition of a new 345 kV line from the Eversource border in Hudson, NH to the Tewksbury 22A Substation owned by NEP. Additionally, two new 345 kV circuitbreakers will be installed in an existing indoor GIS at Tewksbury 22A. | December 2017 | Approved | 2016-06-09
NEP-16-T02 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from New England Power Company ("NEP") for the installation of two new 345 kV, 50 kA, 4000 A circuit breakers in an existing GIS 3-bay breaker-and-third configuration at Wakefield Junction substation, 4000 A terminal equipment for the new proposed 345 kV UG cable (from Wakefield Junction substation to Woburn substation) and a new 345 kV, 160 MVAr variable shunt reactor bank (70 MVAr fixed and 90 MVAr variable). Also, operate one of the existing Wakefield Junction Autotransformers in a normally open configuration. | December 2018 | Approved | 2016-06-09
NEP-16-T03 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from New England Power Company ("NEP") for the reconductoring of the 5.22 mile overhead Y-151N 115 kV Line from Pelham Substation in Pelham, NH to the PSNH border in Hudson, NH and the 4.10 mile overhead Y-151 115 kV Line from Pelham Substation in Pelham, NH to Dracut Junction in Dracut, MA. | Y-151N - Apr. 2017 Y-151 - Sept. 2017 | Approved | 2016-06-09
HLPD-16-T01 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Hudson Light and Power Department ("HLPD") for the expansion of the existing Forest Avenue Substation into a 6 position 115 kV ring bus to allow for termination of the new Sudbury – Hudson 115 kV line to be installed by Eversource Energy. | December 2018 | Approved | 2016-06-09
CMP-16-T01 | 2016-04-06 | Greater Boston Transmission Project | Transmission notification from Central Maine Power Company ("CMP") for the installation of a +/- 200 MVAr STATCOM at the 345 kV bus of the Coopers MillsSubstation in Windsor, ME. | December 2018 | Approved | 2016-06-09
UI-16-T01 | 2016-04-13 | North Haven Transformer Replacement Project | Transmission notification from United Illuminating Company (“UI”) for the replacement of the existing 115/13.8 kV 30/40/50 MVA non-load tap changing transformers at North Haven Substation in North Haven, Connecticut. They will be replaced with 115/13.8 kV 30/40/50 MVA Load Tap Changing (LTC) transformers. The replacement LTC transformers address the Connecticut Public Utilities Regulatory Authority voltage regulation requirements for customers supplied by North Haven Substation. To accommodate the new transformers, the 115 kV transformer disconnect switches will also be replaced. | June 2016 | Approved | 2016-05-23
CED-16-G01 | 2016-04-21 | Con Edison Westfield Solar Project | Generator notification from Con Edison Development (“CED”) for the installation of a 2.0 MW solar array located in Westfield, MA and interconnecting at the Buck Pond Substation via the 23.0 kV 34B123 feeder. | 2016-09-01 | Notification | 2016-05-23
NEP-16-GNF12 | 2016-05-04 | Hilltop Charlton Solar Project | Generator notification from New England Power Company (“NEP) for the installation of a 1.98 MW solar array located in Charlton, MA and interconnecting via the 13.2 kV, 415L1 feeder at the West Charlton Substation. | 2016-06-01 | Notification | 2016-05-23
NEP-16-GNF11 | 2016-05-04 | BWC Salmon Brook Grafton Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 3.0 MW solar array located in Grafton, MA and interconnecting via the 13.8 kV, 304W2 feeder to the Millbury 304 Substation. | 2016-06-15 | Notification | 2016-05-23
NEP-16-G01 | 2016-04-04 | West Coventry Wind Project | Generator notification from New England Power Company (“NEP”) on behalf of Narragansett Electric Company for the installation of ten 1.5 MW wind turbine generators (15 MWs Gross Output) located in Coventry, RI and interconnecting via the Narragansett Electric 2232 23 kV line between Drumrock and Hope Substations. The Hope Substation is fed from the Johnston Substation through the 2228 23 kV Line. | June 2016 | Approved | 2016-05-19
ES-16-T28 | 2016-04-01 | Pochassic 115 kV Switching Station Project | Transmission notification from Eversource Energy (“ES”) for the construction of a 115 kV three breaker ring bus switching station at or adjacent to Pochassic 37R Substation, and loop the existing line 1512 (Granville Jct. to Elm) into the new switching station by building two single circuit lines approximately 950 feet in length from the 1512 tap point to the switching station using 1272 kcmil ACSS conductor. Also terminate new line 1293 (Buck Pond to Pochassic Switching Station) into the new switching station and add the necessary terminal equipment, protection, SCADA Controls, and communication equipment. | December 2019 | Approved | 2016-05-05
ES-16-T29 | 2016-04-01 | Pochassic 115 kV Switching Station Project | Transmission notification from Eversource Energy (“ES”) for the installation of a new 115-kV Circuit Breaker at Buck Pond 34B Substation, connect the new 115-kV line 1293 (Buck Pond to Pochassic Switching Station) to the straight bus, and reconnect 115-kV lines 1657 and 1302 into new positions. Also reconnect distribution transformer 2X into a new 115-kV position. Add / modify the necessary terminal equipment, protection, SCADA Controls and communication equipment. | December 2019 | Approved | 2016-05-05
ES-16-T30 | 2016-04-01 | Pochassic 115 kV Switching Station Project | Transmission notification from Eversource Energy (“ES”) for the Construction of a new 115-kV line 1293 from Buck Pond 34B Substation to Pochassic Switching Station by installing 1272 kcmil ACSS conductor on the vacant side of the existing double-circuit structures that also carry115-kV line 1302 (Buck Pond to Pochassic tap) on the other side. | December 2019 | Approved | 2016-05-05
NEP-16-T06 | 2016-03-18 | Crystal Lake 69 kV Substation Project | Transmission notification from New England Power Company (“NEP") for the retirement of the Park Street 69 kV Substation in Gardner, MA and replaced with a new Crystal Lake 69 kV Substation to address asset condition issues associated with the existing Park St substation. The project will shorten the Gardner 69 kV tap lines (and consequently the B-2N and B-2S 69 kV transmission lines) by approximately ½ mile each. | October 2016 | Approved | 2016-05-05
NEP-16-GNF08 | 2016-04-06 | Nextsun Energy Shirley Solar Project | Generator notification from New England Power Company (“NEP") for the installation of a 2.0 MW solar array located in Shirley, MA and interconnecting at the Ayer 201 Substation via the 13.8 kV 201W1 feeder. | 2016-04-30 | Notification | 2016-05-05
NEP-16-GNF09 | 2016-04-06 | SL MA Shirley Solar Project | Generator notification from New England Power Company (“NEP") for the installation of a 1.5 MW solar array located in Shirley, MA and interconnecting at the Laurel Circle 227 Substation via the 13.8 kV 227W1 feeder. | 2016-06-01 | Notification | 2016-05-05
NEP-16-GNF10 | 2016-04-06 | Mass Solar East Longmeadow Solar Project | Generator notification from New England Power Company (“NEP") for the installation of a 1.696 MW solar array located in East Longmeadow, MA and interconnecting at the Shaker Road 522 Substation via the 13.2 kV 522L4 feeder. | 2016-05-06 | Notification | 2016-05-05
CMEEC-16-G01 | 2016-04-13 | Solar City Brush Hill Bozrah Solar Project | Generator notification from Connecticut Municipal Electric Energy Cooperative (“CMEEC”) on behalf of Solar City Corp. for the installation of a 2.5 MW solar array located in Bozrah, CT and interconnecting via the 13.8 kV 34W2 feeder from the Stockhouse Road Substation 34W. | 2016-09-30 | Notification | 2016-05-05
VELCO-16-GNF02 | 2016-03-11 | Sudbury Solar Project | Generator notification from Vermont Electric Power Company ("VELCO") on behalf of Sudbury Solar LLC for the installation of a 2.0 MW solar array located in Sudbury, VT and interconnecting via Line 5 Pole 70-3 on the GMP Leicester Substation Circuit #LJ13. | 2016-04-06 | Notification | 2016-04-01
ES-16-G06 | 2016-03-08 | EMC Bellingham Solar Project | Generator notification from Eversource Energy ("ES") on behalf of EMC for the installation of a 1.44 MW solar array located in Bellingham, MA and interconnecting via the 13.2 kV 65-H4 circuit to the 552L1 feeder to the Medway Station #65. | March 2016 | Notification | 2016-04-01
NEP-16-GNF07 | 2016-03-09 | Foster Solar North Scituare Solar Project | Generator notification from New England Power Company ("NEP") for the installation of a 1.17 MW solar array located in North Scituate, RI and interconnecting via the 12.47 kV 34F3 feeder to the Chopmist 34 substation. | 2016-04-30 | Notification | 2016-04-01
NEP-16-GNF06 | 2016-03-09 | Blair Enterprise Rutland Solar Project | Generator notification from New England Power Company ("NEP") for the installation of a 1.98 MW solar array located in Rutland, MA and interconnecting via the 13.2 kV 552L1 feeder to the Meadow St. 552 substation. | 2016-04-06 | Notification | 2016-04-01
NEP-16-GNF05 | 2016-03-09 | SunEdison Origination 1 Foxboro Solar Project | Generator notification from New England Power Company ("NEP") for the installation of a 2 MW solar array located in Foxboro, MA and interconnecting via the 13.8 kV 3432W2 feeder to the Foxboro 3432 substation. | 2016-04-08 | Notification | 2016-04-01
NEP-16-T04 | 2016-02-05 | Replacement of 345-115 kV Autotransformer at Carpenter Hill Substation | Transmission notification from New England Power Company ("NEP") for the replacement of the 345/115 kV Autotransformer (268/358/448 MVA) at the Carpenter Hill Substation in Charlton, MA. | June 2016 | Approved | 2016-02-23
NEP-15-T13 | 2016-01-21 | South Street Substation and T1, T2, T3 115 kV Supply Rebuild | Transmission notification from New England Power Company ("NEP") on behalf of Narragansett Electric to replace the existing 115 kV overhead transmission lines (T1, T2, T3) from Franklin Square to the South Street Substation with three new 2000 kcmil Cu XLPE insulated underground cables, 0.3 miles each. | May/June 2019 | Approved | 2016-02-23
NHT-16-T01 | 2016-01-22 | Seabrook 345kV Substation Breaker Removal and Bus Upgrade Project | Transmission notification from New Hampshire Transmission ("NHT") to perform Bus upgrades and breaker removals at the Seabrook Switchyard. Project will consist of two phases. Phase I will remove the 345kV GIS Breaker 22. Bus 4 becomes part of Bus 2 and Remove Bus 4 CCVTs since removal of Bus 4 eliminates need for Bus 4 CCVTs. Upgrade remainder of Bus 2 from 1981 ITE 3000A GIB to new 4000A CGIT GIB. Phase II will remove the old 345kV GIS Breaker 11 that is no longer a functioning breaker and instead has been locked closed and converted to a Gas Zone. Upgrade remainder of Bus 1 from 1981vintage GIB to new 4000A CGIT GIB. | Phase 1 - Nov. 2016 Phase 2 - Nov. 2017 | Notification | 2016-02-23
NEP-16-GNF01 | 2016-02-08 | Twin Rivers Quincy Gas Generator Project | Generator notification from New England Power Company ("NEP") on behalf of Twin River Technologies for the installation of a 2.052 MW natural gas synchronous generator located in Quincy, MA and interconnecting to the Field Street Substation via the 1202 & 1203 13.8 kV Feeders | 2015-12-14 | Notification | 2016-02-23
NEP-16-GNF02 | 2016-02-08 | Peterson Road Palmer Solar Project | Generator notification from New England Power Company ("NEP") for the installation of a 2.55 MW solar array located in Palmer, MA and interconnecting to the Palmer 503 Substation via the 13.2 kV 503L1 feeder. | 2016-02-17 | Notification | 2016-02-23
NEP-16-GNF03 | 2016-02-08 | Solar City Andover Solar Project | Generator notification from New England Power Company ("NEP") for the installation of a 1.71 MW solar array located in Andover, MA and interconnecting to the East Tewksbury 59 Substation via the 13.2 kV 59L5 feeder. | 2016-03-01 | Notification | 2016-02-23
NEP-16-GNF04 | 2016-02-08 | Brookfield Wire West Brookfield Solar Project | Generator notification from New England Power Company ("NEP") for the installation of a 1.612 MW solar array located in West Brookfield, MA and interconnecting to the Lashway 525 Substation via the 13.2 kV 525L2 feeder. | 2016-03-15 | Notification | 2016-02-23
NEP-07-T47 Rev.2 | 2016-02-01 | Upgrade Auburn Street Substation Rev.2 | Transmission notification from New England Power Company ("NEP") to revise the Auburn Street Substation Project to match the "as built" transformer positions. | May 2013 | Notification | 2016-02-23
VELCO-16-GNF01 | 2016-02-04 | Ball Mountain Jamaica Hydro Project | Generator notification from Vermont Electric Power Company (“VELCO”) on behalf of Blue Heron Hydro, LLC for the installation of a 2.196 MW run-of-river hydro generator located in Jamaica, VT and interconnecting at the GMP Line 5052, Pole 29. | 2016-02-05 | Notification | 2016-02-23
ES-16-T02 | 2016-01-07 | Pittsfield/Greenfield Area - Group II Transmission Upgrades Project | Transmission notification from Eversource Energy ("ES") for the installation of the 7T circuit breaker at Northfield Mountain 345-kV Substation and connect a new 75-150 MVAR Variable Shunt Reactor into the 7T/8T position using a live tank circuit breaker. | December 2017 | Approved | 2016-01-26
ES-16-T03 | 2016-01-07 | Pittsfield/Greenfield Area - Group II Transmission Upgrades Project | Transmission notification from Eversource Energy ("ES") for the installation of a new 75-150 MVAR Variable Shunt Reactor and connect it to the 345-kV Bus 3B using a circuit breaker at the Ludlow 19S Substation. | December 2017 | Approved | 2016-01-26
ES-16-T04 | 2016-01-07 | Pittsfield/Greenfield Area - Group II Transmission Upgrades Project | Transmission notification from Eversource Energy ("ES") for the installation of a 115-kV 20.6 MVAR Capacitor Bank and connect it into the 3T/4T ring-bus position using a 115-kV synchronous closing circuit breaker. Also the Doreen 13T circuit breaker will be operated normally open. | December 2017 | Approved | 2016-01-26
NU-12-T35-Rev.1 | 2016-01-07 | Pittsfield/Greenfield Area - Group II Transmission Upgrades Project | Transmission notification revision from Eversource Energy ("ES") for the rebuild of the 1361/1242 double-circuit tower line from Montague 21C Substation to Cumberland 22B Substation using 556 kcmil ACSS conductor for each circuit. The remainder of the 1242 line from Cumberland 22B Substation to Berkshire 18C Substation will not change. | December 2016 | Approved | 2016-01-26
NEP-16-T01 | 2016-01-06 | Medway Substation BPS Upgrade Project | Transmission notification from Eversource Energy ("ES") to upgrade the Medway Substation #65 to NPCC Bulk Power System (BPS) standards to include the construction of a new control house and installation of relaying and redundant control wiring. | June 2019 | Notification | 2016-01-26
PSEG-15-G01-Rev.1 | 2015-11-03 | PSEG Bridgeport Harbor Generator Modification Project | Generator notification from PSEG Power Connecticut LLC ("PSEG") to modify the previously approved Bridgeport Harbor combined cycle generator output from 547.5 MWs to 532.6 MWs due to a change from a larger model generator size to a smaller model generator size. | 2019-05-31 | Approved | 2015-12-28
PSEG-15-T01-Rev.1 | 2015-11-03 | PSEG Bridgeport Harbor Generator Modification Project | Transmission notification from PSEG Power Connecticut LLC ("PSEG") for the installation of a 264 MVA transformer (GSU-1) for the Bridgeport Harbor combined cycle generator | 2019-05-31 | Approved | 2015-12-28
PSEG-15-T02-Rev.1 | 2015-11-03 | PSEG Bridgeport Harbor Generator Modification Project | Transmission notification from PSEG Power Connecticut LLC ("PSEG") for the installation of a 138 MVA transformer (GSU-2) for the Bridgeport Harbor combined cycle generator. Proposed in service date of the project is May 31, 2019. | 2019-05-31 | Approved | 2015-12-28
BE-15-G02 | 2015-11-16 | Bridgeport Energy Capacity Increase Project | Generator notification from Emera Energy Service Subsidiary #5 on behalf of Bridgeport Energy ("BE") to increase the capacity of the Bridgeport Energy combined cycle generator located in Bridgeport, CT by 18MWs at 50 deg. F. | 4th Quarter of 2017 | Approved Withdrawn | 12/28/2015 9/14/2017
NEP-15-GNF27 | 2015-12-04 | 510 PV Project Development Southbridge Solar Project | Generator notification from New England Power Company ("NEP") on behalf of Massachusetts Electric Company for the installation of a 1.92 MW solar array located in Barre, MA and interconnecting via the 604W1 feeder out of the Barre Substation #604. | 2015-12-31 | Notification | 2015-12-28
NEP-15-GNF28 | 2015-12-04 | 510 PV Project Development Southbridge Solar Project | Generator notification from New England Power Company ("NEP") on behalf of Massachusetts Electric Company for the installation of a 1.92 MW solar array located in Southbridge, MA and interconnecting via the 413L4 feeder out of the Snow Street Substation #413. | 2016-01-18 | Notification | 2015-12-28
WED-15-T02 | 2015-12-01 | Wallingford Transmission Upgrade Project | Transmission notification from Wallingford Department of Public Utilities Electric Division ("WED") for the installation of a 0.1 mile overhead 115 kV line from Wallingford 13M – 1305 Line to Wallingford Energy 6G – 1305 Line to connect the new fourth transformer at Wallingford Energy 6G to 13M. | May 2018 | Notification | 2015-12-28
WED-15-T03 | 2015-12-01 | Wallingford Transmission Upgrade Project | Transmission notification from Wallingford Department of Public Utilities Electric Division ("WED") for the replacement of four existing 115 kV 25 kA circuit switchers, one on the high voltage side of each existing 115/13.8 kV power transformers at 13M, with 40 kA circuit switchers. | May 2018 | Notification | 2015-12-28
WED-15-T04 | 2015-12-01 | Wallingford Transmission Upgrade Project | Transmission notification from Wallingford Department of Public Utilities Electric Division ("WED") for revision of the 115 kV bus work to change the point where the existing 1640 Line attaches to the 13M ring bus. A new 115 kV/40 kA SF 6 circuit breaker will be installed between the existing 13M 2T and 13M 3T circuit breakers. This work addresses the contingency of any single breaker failure causing the loss of more than one 115 kV line out of 13M. | May 2018 | Notification | 2015-12-28
WED-15-T05 | 2015-12-01 | Wallingford Transmission Upgrade Project | Transmission notification from Wallingford Department of Public Utilities Electric Division ("WED") for the installation of seven new 115 kV poles and install and/or transfer 3000 feet of three phase line. This will place the 1630 and 1640 Lines from Wallingford 13M to the Pent Road Junction on separate structures. This address a double circuit contingency that limits the firm N-1 output of generation connected to 13M. | May 2018 | Notification | 2015-12-28
ES-15-G08 | 2015-11-19 | Southern Sky Renewable Energy Carver Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Southern Sky Renewable Energy Carver LLC for the installation of a 1.5 MW solar array located in Carver, MA and interconnecting via the #10 feeder out of the .Eversource West Pond Substation #737. | 2015-11-15 | Notification | 2015-12-28
ES-15-G23 | 2015-11-30 | Willow Hill Road Solar Project | Generator notification from Eversource Energy ("ES") on behalf of Willow Hill Road Solar for the installation of a 1.904 MW solar array located in Lee, MA and interconnecting via the #17G7 feeder out of the Woodland 17G Substation. | April 2016 | Notification | 2015-12-28
ES-15-G13 | 2015-10-30 | Fusion Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Fusion Solar Center, LLC for the installation of a 20.0 MW solar array located in Sprague, CT and interconnected to the 23 kV distribution feeder to Tunnel 12S Substation in Preston, CT. | 2016-12-31 | Approved | 2015-12-01
NEP-15-T08 | 2015-11-04 | Kent County Substation Transformer Addition Project | Transmission notification from New England Power Company (“NEP”) for the installation of a new 115/13.2 kV, 24/32/40 MVA transformer T5 tapped off the G-185S line at the Kent County Substation #22. | January 2017 | Approved | 2015-12-01
EXE-15-X01 | 2015-11-05 | Mystic 7 AVR Replacement Project | Transmission notification from Exelon Generation Co. (“EXE”) for the replacement and installation of the Mystic 7 Automatic Voltage Regulator (AVR) with a new EX2100 voltage regulator for the GE Alterrex exciter. The module will also update the governor controller. | 2015-11-25 | Approved | 2015-12-01
ES-15-T94 | 2015-10-27 | Glenbrook 1K-3X Distribution Transformer Replacement Project | Transmission notification from Eversource Energy (“ES”) for the replacement of the Glenbrook 1K-3X 115/13.8 kV Distribution Transformer in Stamford, CT. The transformer rating is 36/48/670 MVA. | 2015-11-30 | Notification | 2015-12-01
NEP-15-GNF19 | 2015-11-06 | Erving Paper Mills Generator | Generator notification from New England Power Company (“NEP”) for the installation of a 3.3 MW synchronous generator located in Erving, MA and interconnecting at the Wendell Depot Substation #705 via the 13.8 kV 705W1 feeder. | 2015-11-20 | Notification | 2015-12-01
NEP-15-GNF20 | 2015-11-06 | Hollingsworth & Vose West Groton Generator | Generator notification from New England Power Company (“NEP”) for the installation of a 3.5 MW synchronous generator located in West Groton, MA and interconnecting at the Ayer Substation #201 via the 13.8 kV 201W4 feeder. | 2015-11-20 | Notification | 2015-12-01
NEP-15-GNF21 | 2015-11-06 | Ken’s Food Marlborough Generator | Generator notification from New England Power Company (“NEP”) for the installation of a 1.2 MW synchronous generator located in Marlborough, MA and interconnecting at the Northboro Road Substation #317 via the 13.8 kV 317W1 feeder. | 2015-11-20 | Notification | 2015-12-01
NEP-15-GNF22 | 2015-11-06 | WA MA West Warren Solar | Generator notification from New England Power Company (“NEP”) for the installation of a 2.0 MW solar array located in West Warren, MA and interconnecting at the Little Rest Road Substation #516 via the 13.2 kV 516L3 feeder. | 2015-12-07 | Notification | 2015-12-01
NEP-15-GNF23 | 2015-11-06 | Kearsarge Bellingham Solar | Generator notification from New England Power Company (“NEP”) for the installation of a 3.108 MW solar array located in Bellingham, MA and interconnecting at the Beaver Pond Substation #344 via the 13.8 kV 344W4 feeder. | 2015-12-14 | Notification | 2015-12-01
NEP-15-GNF24 | 2015-11-06 | Bluewave Capital Rehoboth Solar | Generator notification from New England Power Company (“NEP”) for the installation of a 1.67 MW solar array located in Rehoboth, MA and interconnecting at the Mink Street Substation #7 via the 13.2 kV 7L5 feeder. | 2015-12-15 | Notification | 2015-12-01
NEP-15-GNF25 | 2015-11-06 | Syncarpha Palmer Solar | Generator notification from New England Power Company (“NEP”) for the installation of a 4.995 MW solar array located in Palmer, MA and interconnecting at the Thorndike Substation #523 via the 13.2 kV 523L4 feeder. | 2015-12-21 | Notification | 2015-12-01
NEP-15-GNF26 | 2015-11-06 | RT MA Housatonic Solar | Generator notification from New England Power Company (“NEP”) for the installation of a 2.0 MW solar array located in Housatonic, MA and interconnecting at the Risingdale Substation #1109 via the 13.8 kV 1109W3 feeder. | 2015-12-31 | Notification | 2015-12-01
ES-15-G22 | 2015-11-04 | Church Street Weston Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Church Street Solar LLC for the installation of a 1.795 MW solar array located in Weston, MA and interconnecting to the Trapelo Road Waltham Station #450 13.8 kV circuit #450-H7. | 2015-12-15 | Notification | 2015-12-02
ES-15-T95 | 2015-10-31 | Speen Street Station #433 115 kV Line Disconnects | Transmission notification from Eversource Energy (“ES”) for the installation of two air break, motor-operated, 123 kV, 550 kV BIL and 2,000 amp continuous rated line disconnects at Speen St. Station 433 located in Framingham, MA. | 2016-03-01 | Notification | 2015-12-01
ES-15-G21 | 2015-11-05 | Brigham & Women’s Faulkner Hospital Generator Project | Generator notification from Eversource Energy (“ES”) on behalf of Brigham & Women’s Faulkner Hospital for the installation of two 800 kW CHP Synchronous Generators (1.6 MW Net Output) located in Jamaica Plain, MA and interconnecting to Hyde Park Station 496, 14 kV Bus Section(s) 3 and 4 via 14 kV lines 13-1416XY, 13-1417, 13-1418 and 13-1419. | 2016-02-01 | Notification | 2015-12-01
VELCO-15-GNF07 | 2015-11-09 | Waterhouse Hyde Park Solar Project | Generator notification from Vermont Electric Power Company ("VELCO") on behalf of Village of Hyde Park Electric Department for the installation of 1.0 MW solar array located in Hyde Park, VT and interconnecting to the Hyde Park Substation. | 2016-05-31 | Notification | 2015-12-01
ES-15-T82 | 2015-10-07 | Carver Street Breaker Addition Project | Transmission notification from Eversource Energy (“ES”) for the installation of six new 115 kV circuit breakers at Carver St. Station #71. Also install two high speed protection groups on 115 kV cables 329-512/513 between Carver St and Brighton Stations and 514/-512/513 cables between Carver St and Kingston Station. | Fall 2016 | Approved | 2015-11-05
ES-15-T75 | 2015-10-01 | Canal 15Q Substation Breaker and 115/23 kV Transformer Addition Project | Transmission notification from Eversource Energy (“ES”) for the installation of a new 115 kV circuit breaker and a second 36/48/60 MVA step down transformer at the Canal 15Q Substation in Southington, CT | May 2016 | Approved | 2015-11-05
ES-15-T84 | 2015-10-01 | North Keene Substation Project | Transmission notification from Eversource Energy (“ES”) for the construction of the North Keene 115 kV Substation. Loop in the 115-kV Line L163, utilizing two 115-kV circuit breakers. Also install one 115/12.47-kV 30 MVA transformer at North Keene Substation and modify the existing Keene Substation by replacing four of the five existing transformers at with one 115/12.47-kV 30 MVA transformer and replace the existing 12.47 kV switchgear. | June 2016 | Approved | 2015-11-05
NRG-15-G01 | 2015-10-09 | Canal Generator Addition and Transmission Project | Generator notification from NRG Energy Inc. (“NRG”) for the installation and interconnection of a 336 MW simple cycle combustion generator interconnected to the Canal 345 kV substation. | 2019-05-31 | Approved | 2015-11-05
NRG-15-T01 | 2015-10-09 | Canal Generator Addition and Transmission Project | Transmission notification from NRG Energy Inc. (“NRG”) for the installation of a 0.3 mile overhead 345 kV line from the Canal CT generator to the Canal Substation between breakers 812P and 812S. | 2019-05-31 | Approved | 2015-11-05
ES-15-T77 | 2015-10-07 | Canal Generator Addition and Transmission Project | Transmission notification from Eversource Energy (“ES”) for the installation of a 345 kV disconnect switch at the Canal 345 kV Substation and connection of Canal 3 to the Canal 345 kV Substation at the existing bus position between breakers 812P and 812S. | May 2019 | Approved | 2015-11-05
ES-15-T83 | 2015-10-01 | Rimmon Substation Project | Transmission notification from Eversource Energy (“ES”) for the construction of a new Rimmon substation and relocate the existing Rimmon Substation equipment to the new site. Add a second Rimmon 115/34.5-kV, 44.8 MVA transformer and associated equipment. Add two 115-kV terminals with two circuit breakers, associated disconnect switches, and protection and controls. Loop 115-kV Line J114 in and out of the Rimmon Substation. Also add new 115-kV capacitor banks (2x13.3 Mvar) and add a series 115-kV circuit breaker to the Greggs bus tie breaker BT30. | June 2016 | Approved | 2015-11-05
GDF-15-G01 | 2015-10-08 | Bethlehem Generator Replacement Project | Generator notification from GDF Suez Energy Marketing NA (“GDF”) for the installation of a replacement 17.1 MW synchronous generator located in Bethlehem, NH. | 2015-12-08 | Approved | 2015-11-05
ES-15-T80 | 2015-09-10 | Manchester 3A-2X 115/23 kV Distribution Transformer Replacement Project | Transmission notification from Eversource Energy (“ES”) for the replacement of the existing 3A-3X 115/23 kV distribution transformer due to asset conditions. | December 2016 | Notification | 2015-11-05
ES-15-G17 | 2015-10-05 | Solar City Needham Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Solar City Corporation for the installation of a 3.12 MW solar array located in Needham, MA and interconnecting at the Needham Station #148, 13.8 kV circuit 148-H1. | 2015-11-30 | Notification | 2015-11-05
ES-15-G18 | 2015-10-01 | Sunpin Pittsfield Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Sunpin Solar Development LLC for the installation of a 3.3 MW solar array located in Pittsfield, MA and interconnecting at the Partridge 15E 115 kV Substation via the Eversource 15E2 23 kV distribution circuit. | 2015-10-25 | Notification | 2015-11-05
VELCO-15-GNF06 | 2015-10-06 | Nebraska Valley Solar Project | Generator notification from Vermont Electric Company (“VELCO”) on behalf of Stowe Electric Department for the installation of a 1.0 MW solar array located in Stowe, VT and interconnecting at the 7.2/12.47 kV circuit #2 originating at the Stowe Wilkens Substation. | 2016-05-31 | Notification | 2015-11-05
NEP-15-GNF15 | 2015-10-05 | WGL Energy Systems Marlborough Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of WGL Energy Systems LLC for the installation of a 1.073 MW solar array located in Marlborough, MA and interconnecting at the Marlborough 311 Substation via the #311W6 13.8 kV feeder. | 2015-11-01 | Notification | 2015-11-05
NEP-15-GNF16 | 2015-10-05 | Solar MA Project Management North Oxford Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Solar MA Project Management LLC for the installation of a 1.5 MW solar array located in Oxford, MA and interconnecting at the North Oxford 406 Substation via the #406L3 13.2 kV feeder. | 2015-11-23 | Notification | 2015-11-05
NEP-15-GNF17 | 2015-10-05 | Nextamp Peak Hancock Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Nextamp Peak LLC for the installation of a 1.75 MW solar array located in Hancock, MA and interconnecting at the Partridge 15E Substation via the #1018K1 23 kV feeder. | 2015-11-01 | Notification | 2015-11-05
NEP-15-GNF18 | 2015-10-05 | Altus Power America Great Barrington Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Altus Power America, Inc. for the installation of a 2.5 MW solar array located in Great Barrington, MA and interconnecting at the Risingdale 1109 Substation via the #1109W1 13.8 kV feeder. | 2015-12-01 | Notification | 2015-11-05
NU-14-G08-Rev.1 | 2015-10-09 | Nextamp Capital Dartmouth Solar Project Rev.1 | Generator notification from Eversource Energy (“ES”) for the revision to the Nextamp Capital Dartmouth Solar Project downsizing the size of the project from 4.68 MWs to 2.25 MWs. The solar array will interconnect to the #543 13.2 kV distribution circuit out of the Cross Road Substation #651 off of the #111 transformer. | January 2016 | Notification | 2015-11-05
ES-15-T81 | 2015-10-05 | K Street Substation Breaker Addition Project | Transmission notification from Eversource Energy for the installation of a normally open 115 kV 63 kA IC 3000 amp breaker #33 between the existing breakers #12 and #15 at the K Street Substation in Boston, MA. | December 2016 | Notification | 2015-11-05
CMP-15-T03 | 2015-09-01 | New Gloucester Substation Project | Transmission notification from Central Maine Power Company (“CMP”) for the construction of a new 115/34.5 kV New Gloucester Substation that sectionalizes Section 208 by adding four 115 kV circuit breakers in a ring bus configuration with the installation of a new 115/34.5 kV 30/56 MVA transformer at a new green field site, construction of roughly 8 miles of new 115 kV (1192 kcmil 45/7 ACSR) conductor (Section 282) from the Surowiec Substation to the New Gloucester Substation,add a 115 kV circuit breaker and relocate Sections 166 and 69 into a different bay position at the Surowiec Substation, and partially re-build existing Section 208 to accommodate the new Section 282 in the ROW. | December 2021 | Approved | 2015-10-01
EP-15-G01 | 2015-09-03 | Newington Generator Uprate Project | Generator notification from Essential Power (“ES”) to install an Advanced Hot Gas Path Upgrade on Gas Turbines 1 & 2 at the Newington Station to increase summer incremental net capacity uprate of +27.9 MW (at ≥ 50° F). The combustion turbine generators (CTG1 and CTG2) will both be upgraded by 13.1 MW, and the steam turbine (STG) is being downgraded by 0.1 MW. The station service load has also reduced by 1.8 MW. The combined plant summer rated net output is 596.1 MW (at ≥ 50° F). The winter incremental net capacity uprate is 39.1 MW providing a net plant output of 634.9 MW (at ≥ 0°F).and improved efficiency. | September 2015 | Approved | 2015-10-01
ES-15-T61 | 2015-08-27 | North Cambridge Substation 115 kV Terminal Swaps Project | Transmission notification from Eversource Energy (“ES”) to swap the 115kV board positions for the Blair Pond-North Cambridge 115kV line 509-530 and the Alewife Station #828 Transformer #1 and the Brighton-North Cambridge 115kV line 329-531 and the Alewife Station #828 Transformer #4 at North Cambridge. The project addresses overloads for the loss of one of the North Cambridge 345/115kV Autotransformers followed by a stuck breaker of either the North Cambridge 115kV breakers #5 or #10. | December 2016 | Approved | 2015-10-01
ES-15-G12 | 2015-09-01 | Harvard DG Interconnection Project | Generator notification from Eversource Energy (“ES”) on behalf of President and Fellows of Harvard College for the installation of a 8 MW Combustion Turbine Generator located in Cambridge, MA and interconnected via the NSTAR owned 14 kV distribution lines 831-1111 and 831-1113 to Putnam Station 831. Both distribution lines will operate in parallel at Putnam Station 831 and the Harvard owned station. The connection to the transmission system will be through the NSTAR Electric and Gas Corp. owned 117.5/14.4 kV, 62.5 MVA distribution station transformers 110A and 110B located at Putnam Station 831. | 2015-10-01 | Approved | 2015-10-01
ES-15-X01 | 2015-09-02 | Line 326 SPS Setpoint Change Project | Transmission notification from Eversource Energy (“ES”) for the set point change to the 326 Line SPS (special protection system) installed on the 345-kV Line 326, at the Scobie Pond Substation. This SPS has three modes of operation ‘Disabled’, ‘Thermal’ (summer/winter), and ‘Stability’ and is classified as a NPCC Type I SPS. This change affects the thermal mode of the SPS and involves increasing the summer MVA set point from 1429 MVA to 1749 MVA and increasing the winter MVA set point from 1697 MVA to 1793 MVA. | March 2016 | Notification | 2015-10-01
ES-15-G14 | 2015-08-21 | Brass Mill Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of Brass Mill Solar Center LLC for the installation of a 1.16 MW solar array located in Waterbury, CT and interconnecting at the 13F63 & 13F66 13.8 kV feeders from Eversouce CTs Baldwin 13F substation. | 2015-11-13 | Notification | 2015-10-01
IBR-15-G01 | 2015-08-04 | Deerfield Wind Generator Project | Generator notification from Iberdrola Renewables LLC (“IBR”) on behalf of Deerfield Wind LLC for the installation of 15 wind turbine generator rated at 2 MWs each (30 MWs net output) located in Bennington County, Vermont. | 2017-12-31 | Approved | 2015-08-25
IBR-15-T01 | 2015-08-04 | Deerfield Wind Generator Project | Transmission notification from Iberdrola Renewables LLC (“IBR”) on behalf of Deerfield Wind LLC for the installation of a 18/24/30 MVA 34.5/69 kV transformer at the to be constructed Putnam Road 69 kV Substation in Searsburg, VT. | 2017-10-01 | Approved | 2015-08-25
VELCO-15-T05 | 2015-07-27 | Deerfield Wind Generator Project | Transmission notification from Vermont Electric Power Company (“VELCO”) on behalf of Green Mountain Power for the construction of a new Putnam Road 3-breaker ring substation connecting to the Y-25 line, 0.5 mi west of route 8, between the Bennington 69 kV station and the Sleepy Hollow/Searsburg Wind tap. The substation will be the point of interconnection of a proposed wind generation project. | 2017-12-31 | Approved | 2015-08-25
NEP-15-T12 | 2015-08-05 | Deerfield Wind Generator Project | Transmission notification from New England Power Company (“NEP”) for the reconductoring of the seven mile overhead 69 kV J-10 line (Adams - Deerfield 5) with 477 ACSR to address the impact of interconnecting the 30 MW QP477 Deerfield Wind project as specified in IBR-15-G01. | 2017-10-01 | Approved | 2015-08-25
EXE-15-G01 | 2015-07-07 | Medway Generator and Transmission Project | Generator notification from Exelon West Medway II, LLC (“EXE”) for the installation of two 103.5 MW combustion turbine generators (207.0 MW net output) at the West Medway Generator Station in Medway, MA. | 2018-04-01 | Approved | 2015-08-25
EXE-15-T01 | 2015-07-07 | Medway Generator and Transmission Project | Transmission notification from Exelon West Medway II, LLC (“EXE”) for the installation of a three winding 13.8/13.8/115 kV Generator Step Up transformer (GSU) at the West Medway II Station to support the two new generators at Medway. This will be interconnected via a 0.25 mile, 1272 kcmil, 115 kV overhead line from the West Medway II Station to the Medway 115 kV Substation in Medway, MA. | April 2018 | Approved | 2015-08-25
ES-15-G11 | 2015-07-13 | CEC Kingston Solar Project | Generation notification from Eversource Energy (“ES”) on behalf of CEC Solar #1040 LLC and CEC Solar #1041 for the installation of a 1.57 MW solar array located in Kingston, MA and interconnecting to the Eversource Kingston Substation #735, #2 transformer, #909 23 kV circuit. | October 2015 | Notification | 2015-08-25
ES-15-G06 | 2015-07-14 | Ahold Stop & Shop Warehouse CoGen Project | Generation notification from Eversource Energy (“ES”) on behalf of Ahold for the installation of a 1.137 MW biodigester-fired cogeneration unit located in Freetown, MA and interconnecting #606 13.2 kV feeder out of the Assonet Substation #647, fed by the #635 34.5 kV line out of the Bell Rock Substation #661. | 2015-12-01 | Notification | 2015-08-25
NU-14-T11-Rev.1 | 2015-08-06 | Transmission Elements Upgrade due to CPV Towantic Generator | Transmission notification revision from Eversource Energy (formally “NU”) to rebuild the 6 mile overhead 15 kV 1585N Line from Towantic 115 kV Substation in Oxford, CT to the 115 kV Bunker Hill Substation in Waterbury, CT. | 2018-06-01 | Notification | 2015-08-25
NU-14-T12-Rev.1 | 2015-08-06 | Transmission Elements Upgrade due to CPV Towantic Generator | Transmission notification revision from Eversource Energy (“ES”) to reconductor the 1.2 mile overhead 115 kV 1575S Line from Towantic 115 kV Substation in Oxford, CT to the Oxford 115 kV Substation in Oxford, CT. | 2018-06-01 | Notification | 2015-08-25
ES-15-T72 | 2015-08-06 | Transmission Elements Upgrade due to CPV Towantic Generator | Transmission notification revision from Eversource Energy (“ES”) to rebuild the 3 mile overhead 115 kV 1575N-1 Line from Towantic 115 kV Substation in Oxford, CT to the 115 kV Baldwin Tap in Waterbury, CT. | 2018-06-01 | Notification | 2015-08-25
ES-15-T73 | 2015-08-06 | Transmission Elements Upgrade due to CPV Towantic Generator | Transmission notification revision from Eversource Energy (“ES”) to rebuild/reconductor the 4.4 mile overhead 115 kV 1710 Line from Devon 115 kV Substation in Milford, CT to the Trumbull Junction, CT. | 2018-06-01 | Notification | 2015-08-25
ES-15-T74 | 2015-08-06 | Transmission Elements Upgrade due to CPV Towantic Generator | Transmission notification revision from Eversource Energy (“ES”) to rebuild the 4.5 mile overhead 115 kV 1730 Line from Devon 115 kV Substation in Milford, CT to the UI Border/Trumbull 115 kV Substation in Trumbull, CT. | 2018-06-01 | Notification | 2015-08-25
WEII-15-G01 | 2015-06-29 | Wallingford Generator and Transmission Project | Generator notification from Wallingford Energy II, LLC (“WEII”) for the installation of two (Units 6 & 7) 50 MW natural gas turbine generators (100 MWs net output) located in Wallingford CT. | 2018-03-30 | Approved | 2015-07-23
WEII-15-T01 | 2015-06-29 | Wallingford Generator and Transmission Project | Transmission notification from Wallingford Energy II, LLC (“WEII”) for the installation of a 66 MVA 115/13.8 kV Generator Step Up Transformer interconnecting Unit #7 13.8 kV Bus to the Wallingford 115 kV Switchyard. | 2018-03-30 | Approved | 2015-07-23
WED-15-T01 | 2015-06-29 | Wallingford Generator and Transmission Project | Transmission notification from Town of Wallingford, Department of Public Utilities (“WED”) for the replacement of the 795 kcml ACSR 115 kV transmission line from the Wallingford 13M 1305 Line to the Wallingford Energy 6G 1305 Line with 1590 kcml ACSR. | 2018-05-01 | Approved | 2015-07-23
NEP-12-G09-Rev.1 | 2015-06-22 | Harrington Street Vuelta Solar and Harrington Street Old Wardour Solar Generation and Transmission Project | Generator notifications from New England Power Company (“NEP”) on behalf of Vuelta Solar LLC and Old Wardour LLC for the installation of two 4.875 MW solar arrays (9.75 MW net output) located in East Brookfield, MA. | 2015-10-31 | Approved | 2015-07-23
NEP-15-G10 | 2015-06-22 | Harrington Street Vuelta Solar and Harrington Street Old Wardour Solar Generation and Transmission Project | Generator notifications from New England Power Company (“NEP”) on behalf of Vuelta Solar LLC and Old Wardour LLC for the installation of two 4.875 MW solar arrays (9.75 MW net output) located in East Brookfield, MA. | 2015-10-31 | Approved | 2015-07-23
NEP-15-G09 | 2015-06-22 | Harrington Street Vuelta Solar and Harrington Street Old Wardour Solar Generation and Transmission Project | Transmission notification from New England Power Company (“NEP”) for the installation of a 69/13.2 kV transformer rated 12/16/20 MVA and required switchgear at the proposed Harrington St PV Collector Substation to connect the Vuelta Solar and Old Wardour PV projects on the 69 kV E-5 line. | 2015-10-31 | Approved | 2015-07-23
ES-15-T76 | 2015-06-26 | Sudbury Substation Autotransformer and Ring Bus Installation Project | Transmission notification from Eversource Energy (“ES”) for the installation of a 230/115 kV Autotransformer and 230 kV Ring Bus at the Sudbury Substation located in Sudbury, MA. Also, an existing 230 kV line, 282-602, that currently runs between West Medway and Waltham, will be looped in and out of the new 230 kV ring at Sudbury. In addition, the termination of the existing 115 kV line, 342-507, will be relocated to a new breaker position at Sudbury, as a part of the Project. | 2015-12-01 | Approved | 2015-07-23
VELCO-15-GNF04 | 2015-06-12 | Bridport West Solar Project | Generator notification from Vermont Electric Company (VELCO) on behalf of VEEP Inc. for the installation of a 2.0 MW solar array located in Bridport, VT and interconnecting via the 12.47 kV feeder GMP line 36 on Circuit #WY81. | 2015-07-01 | Notification | 2015-07-23
VELCO-15-GNF05 | 2015-06-12 | Champlain Valley Solar Project | Generator notification from Vermont Electric Company (VELCO) on behalf of VEEP Inc. for the installation of a 2.0 MW solar array located in Middlebury, VT and interconnecting via the 12.47 kV feeder GMP line EM75 Extension on Pole #26.3 | 2015-07-01 | Notification | 2015-07-23
NEP-15-GNF08 | 2015-07-01 | Kent County Substation Transformer Addition Project | Transmission notification from New England Power Company (“NEP”) for the installation of a new 115/13.2 kV, 24/32/40 MVAR transformer T5 at the Kent County Substation #22 and tapped of the G-185S line. | 2017-01-01 | Notification
CMP-15-X01 | 2015-06-19 | Maine Capacitor Control Settings Project | Transmission notification from Central Maine Power Company (“CMP”) for changes to increase the overvoltage trip settings to the Orrington, Mason, Surowiec and South Gorham 115 kV connected capacitors to enhance system performance during power swing events through the Maine 345 kV transmission corridor. | 2015-06-15 | Notification | 2015-07-23
NEP-15-GNF13 | 2015-07-02 | BWC Fivemile River Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of BWC Fivemile River LLC for the installation of a 1.5 MW solar array located in Oxford, MA and interconnecting by the 406L1 Feeder out of the North Oxford Substation #406. | 2015-08-31 | Notification | 2015-07-23
NEP-15-GNF14 | 2015-07-02 | Halifax Solar NG Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Halifax Solar NG LLC for the installation of a 2.5 MW solar array located in Halifax, MA and interconnecting by the 912W75 Feeder out of the Mill Street Substation #912. | 2015-08-13 | Notification | 2015-07-23
ES-15-T79 | 2015-07-02 | Orchard 27A Substation 3rd Distribution Transformer Project | Transmission notification from Eversource Energy (“ES”) for the installation of a 3rd 115/13.8 kV distribution transformer at the Orchard 27A Substation | 2015-10-31 | Notification | 2015-07-23
NEP-14-T07-Rev.1 | 2015-07-02 | North Oxford Substation Breaker and Transformer Addition Project | Transmission notification from New England Power Company (“NEP”) for the installation of an in-line breaker (V174) at the North Oxford Substation which will sectionalize the existing V-174 line into V-174W (Carpenter Hill – North Oxford) and V174 (North Oxford – Millbury 2). Also add a new 2nd 115/13.2 kV, 24/32/40 MVA transformer at the North Oxford Substation in Oxford, MA. | 2018-06-01 | Notification | 2015-07-23
CES-15-G01 | 2015-05-22 | Pioneer Valley Electric Center (PVEC) Generation and Transmission Uprate Project | Generator notification from Calpine Energy Services (“CES”) for the installation of 1 x 1 combined cycle generator (CTG - 292.2 MWs net output winter 20 deg F) (STG – 144.3 MWs net output winter 20 deg F) located in Westfield, MA. | 2018-06-01 | Approved Withdrawn | 7/9/2015 4/26/2016
CES-15-T01 | 2015-05-22 | Pioneer Valley Electric Center (PVEC) Generation and Transmission Uprate Project | Transmission notification from Calpine Energy Services (“CES”) for the installation of a combustion turbine 115 kV generator step up transformer rated at 180/300 MVA. | 2018-03-01 | Approved Withdrawn | 7/9/2015 4/26/2016
CES-15-T02 | 2015-05-22 | Pioneer Valley Electric Center (PVEC) Generation and Transmission Uprate Project | Transmission notification from Calpine Energy Services (“CES”) for the installation of a combustion turbine 115 kV generator step up transformer rated at 102/170 MVA. | 2018-03-01 | Approved Withdrawn | 7/9/2015 4/26/2016
ES-15-T57 | 2015-05-22 | Pioneer Valley Electric Center (PVEC) Generation and Transmission Uprate Project | Transmission notification from Eversource Energy (“ES”) for the construction of a new 115-kV switching station in Westfield, MA in a ring bus configuration consisting of four (4) 115-kV circuit breakers with a minimum 40-kA short-circuit interrupting capability, associated breaker disconnects, control house, and protection and controls. Loop the existing line 1302 (between Buck Pond and Pochassic tap) into the new switching station and terminate to establish new lines from Buck Pond 34B Substation to PVEC Switching Station (length approximately 1.0 mile) and from Pochassic Substation tap to PVEC Switching Station (length approximately 2.12 miles). Also, terminate the leads for the steam turbine generator step-up transformer and the gas turbine generator step-up transformer into the new switching station. | 2018-03-01 | Approved Withdrawn | 7/9/2015 2/29/2016
ES-15-T58 | 2015-05-22 | Pioneer Valley Electric Center (PVEC) Generation and Transmission Uprate Project | Transmission notification from Eversource Energy (“ES”) for reconductoring of the 1657-3 line section (approximately 160 feet) from Southampton Junction to the Eversource / HG&E border using 795 kcmil ACSS conductor to match or exceed the ratings of the HG&E line section from the Eversource / HG&E border to Ingleside. | 2018-03-01 | Approved Withdrawn | 7/9/2015 2/29/2016
ES-15-T70 | 2015-05-22 | Pioneer Valley Electric Center (PVEC) Generation and Transmission Uprate Project | Transmission notification from Eversource Energy (“ES”) to upgrade the necessary terminal equipment at Agawam 16C Substation to match or exceed the 1302 line conductor ratings. | 2018-03-01 | Approved Withdrawn | 7/9/2015 2/29/2016
SE-15-G01 | 2015-05-27 | Hancock Wind Generation and Transmission Project | Generator notification from Emera Maine on behalf of Hancock Wind LLC for the installation of seventeen 3.0 MW wind turbine generators (51 MWs net output) located in Hancock County, ME. | 2016-12-31 | Approved | 2015-07-07
SE-15-T01 | 2015-05-27 | Hancock Wind Generation and Transmission Project | Transmission notification from Emera Maine on behalf of Hancock Wind LLC for the installation of the 115/34.5 kV Hancock Collector Substation new main power transformer, 16MVAR D-Var and associated breakers and protection. | 2015-12-31 | Approved | 2015-07-07
ES-15-G01 | 2015-05-28 | Acushnet Ball Plant CoGen Project | Generation notification from Eversource Energy (“ES”) on behalf of Acushnet Ball Plant #3 for the installation of a 2.001 MW natural gas cogeneration unit located in New Bedford, MA and interconnecting to the Industrial Park Substation #636 via 13.2 kV feeders #101 (normal) and #103 (Alternate). | 2015-08-01 | Notification | 2015-07-09
NEP-15-GNF11 | 2015-06-02 | Bluewave Capital Webster Solar Project | Generation notification from New England Power Company (“NEP”) on behalf of Bluewave Capital LLC for the installation of a 1.38 MW solar array located in Webster, MA and interconnecting via feeder #412L3 out of the East Webster Substation #412. | 2015-09-15 | Notification | 2015-07-09
NEP-15-GNF12 | 2015-06-02 | Castle Neck River Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of BWC Castle Neck River LLC for the installation of 3.0 MW solar array located in Haverhill, MA and interconnecting via feeder 48L1 out of the North Haverhill Substation #48. | 2015-08-21 | Notification | 2015-07-09
ES-15-G02 | 2015-06-02 | SunEdison Plympton Solar Project | Generator notification from Eversource Energy (“ES”) on behalf of SunEdison LLC for the installation of a 4.0 MW solar array in Plympton, MA fed by the Brook Street Substation #727 23 kV feeder #51. | 2016-10-01 | Notification Withdrawn | 7/9/2015 8/27/2015
UI-15-G01 | 2015-05-14 | UIL Glastonbury Fuel Cell Project | Generator notification from United Illuminating Company (“UI”) on behalf of UIL Distributed Resources LLC for the installation of a 3.67 MW fuel cell generator in Glastonbury, CT and fed by the Hopewell Substation 22R5 feeder. | 2015-07-15 | Notification | 2015-07-09
ES-15-G07 | 2015-04-30 | Brigham & Woman’s Hospital CHP Synchronous Generator Project | Transmission notification from Eversource Energy (ES) to relocate termination for existing 36.7 MVAR 115kV Capacitor Bank at Chelsea Station #488 in Chelsea, MA. | 2015-06-01 | Approved | 2015-05-26
ES-15-G05 | 2015-03-17 | Hadley 2 Solar Project | Generation notification from Eversource Energy (“ES”) on behalf of Hadley 2 Solar for the installation of a 1.95 MW solar array located in Hadley, MA and interconnecting via the 115 kV Amherst 17K substation through the 17K1 feeder at 13.8 kV. | 2015-04-30 | Approved | 2015-05-26
VELCO-15-X01 | 2015-04-24 | Disable Highgate HVDC Converter Runback Project | Transmission notification from Vermont Electric Power Company (“VELCO”) to permanently disable the Highgate HVDC Converter Runback schemes associated with the outage of PV 20, K21 or the K22 line. The Highgate runback schemes have been disabled since the refurbishment of the converter in November 2012 and the establishment of the export interface in October 2012 | 2015-04-24 | Notification | 2015-05-26
NEP-15-GNF18 | 2015-05-11 | NextAmp Capital Rutland Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of NextAmp Capital LLC for the installation of a 4.999 MW solar array in Rutland, MA and customer fed by Feeder #55W3 out of the Treasure Valley Substation #55. | 2015-07-11 | Notification | 2015-05-26
NEP-11-T04-Rev.1 | 2015-05-08 | Chase Hill Substation Project – Rev.1 | Transmission notification from New England Power Company (“NEP”) for the revision to the Chase Hill Substation Project located in Hopkinton, RI. The initial scope of work included the installation of two (2) 24/32/40 MVA rated 115-13.2 kV transformers to serve the local distribution system in the Southern Rhode Island area; an in-line 2000A continuous, 40 kA interrupting circuit breaker to provide the necessary protection, and splitting the existing 1870S line into 1870S line from Wood River (National Grid) to Hopkinton (National Grid) and 1814 line from Hopkinton (National Grid) to Shunock (Northeast Utilities) substations. Since the initial project determination of “no adverse impacts” on June 7, 2011, the scope and name of the substation have changed and the in-line breaker and second transformer have been dropped | 2015-05-08 | Approved | 2015-05-26
NEP-15-GNF10 | 2015-05-08 | SunEdison Rutland Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of SunEdison Origination 1 LLC for the installation of a 2.0 MW solar array in Rutland, MA and customer fed by Feeder #55W1 out of the Treasure Valley Substation #55 | 2015-08-26 | Notification | 2015-05-26
NEP-15-GNF09 | 2015-05-08 | West Brookfield Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of West Brookfield Solar LLC for the installation of a 1.4 MW solar array in West Brookfield, MA and customer fed by Feeder #525L2 out of the Lashway Substation #525. | 2015-08-06 | Notification | 2015-05-26
ES-15-T66 | 2015-03-27 | Chelsea Capacitor Bank Relocation Project | Transmission notification from Eversource Energy (ES) to relocate termination for existing 36.7 MVAR 115kV Capacitor Bank at Chelsea Station #488 in Chelsea, MA | 2015-12-31 | Approved | 2015-05-01
MIRA-15-X01 | 2015-04-02 | MIRA Exciter and Automatic Voltage Regulator Upgrade Project | Transmission notification from Materials Innovation Recycling Authority (MIRA) for the upgrade to the excitation and automatic voltage regulator (AVR) to existing generator #5 (Asset ID# 580) interconnected at the South Meadows 1A Substation with a GE EX2100E exciter. | 2015-05-07 | Approved | 2015-05-01
ES-15-T59 | 2015-03-17 | 211-503/504 Reconductor Project | Transmission notification from Eversource Energy (ES) to reconductor 2.08 miles of overhead 211-503/504 Lines from the North Woburn Tap to NSTAR/National Grid border at Burlington/Billerica. | 2017-05-01 | Notification | 2015-05-01
ES-15-T62 | 2015-03-27 | Greater Boston Circuit Breaker Project | Transmission notification from Eversource Energy (ES) for the installation of a 345kV 50 kA IC 3000 amp breaker in series with existing 345 kV breaker 104 at Stoughton Substation #330 in Stoughton, MA | 2016-12-01 | Notification | 2015-05-01
ES-15-T63 | 2015-03-27 | Greater Boston Circuit Breaker Project | Transmission notification from Eversource Energy (ES) for the installation of a new normally open 115kV 63 kA IC 3000 amp breaker in series with the existing normally open 115 kV breaker 29 at K St. Substation #385 in Boston, MA. | 2015-12-01 | Notification | 2015-05-01
ES-15-T64 | 2015-03-27 | Greater Boston Circuit Breaker Project | Transmission notification from Eversource Energy (ES) for the installation of a 345kV 50 kA IC 3000 amp breaker in series with the existing 345 kV breaker 104 at Woburn Substation #211 in Woburn, MA | 2016-12-01 | Notification | 2015-05-01
ES-15-T65 | 2015-03-27 | Greater Boston Circuit Breaker Project | Transmission notification from Eversource Energy (ES) for the installation of a new 115kV 63 kA IC 3000 amp breaker at Framingham Substation #240 in Framingham | 2017-06-01 | Notification | 2015-05-01
NEP-15-T03 | 2015-03-19 | Greater Boston Reconductor Project | Transmission notification from New England Power (NEP) to reconductor M-139/ N- 140 115 kV transmission lines, a total of 13.31 miles of overhead line. Proposed in-service dates: December 2016 for M-139 from Tewksbury Substation to Billerica Tap; December 2016 for M-139 from Billerica Tap to Pinehurst Tap; May 2017 for M-139 from Pinehurst Tap to Border; December 2016 for N-140 from Tewksbury Substation to Pinehurst Tap and; May 2017 for N-140 from Pinehurst Tap to Border. | 12/1/2016, 5/1/2017, 12/1/2016, 5/1/2017 | Notification | 2015-05-01
NEP-15-T04 | 2015-03-19 | Greater Boston Reconductor Project | Transmission notification from New England Power (NEP) to reconductor F-158N 115 kV overhead transmission line from Golden Hills Substation in Saugus, MA to Maplewood Substation in Malden, MA (4.28 miles), and separate F-158N and Q-169 lines (existing Double Circuit Tower (DCT) structures) between Golden Hills Substation and Maplewood Substation, into independent single circuit structures. Proposed in-service dates: June 2016 for reconductor of F-158N transmission line and December 2015 for the F-158N/Q-169 DCT separation. | 6/1/2016, 12/1/2015 | Notification | 2015-05-01
NEP-15-T05 | 2015-03-19 | Greater Boston Reconductor Project | Transmission notification from New England Power (NEP) to reconductor F-158S 115 kV overhead transmission line from Maplewood Substation in Malden, MA to Everett Substation in Everett, MA (2.48 miles). | 2016-06-01 | Notification | 2015-05-01
NEP-15-T06 | 2015-03-19 | Greater Boston Reconductor Project | Transmission notification from New England Power (NEP) to reconductor W-23W 69 kV overhead transmission line from Northborough Road Substation in Southborough, MA to Woodside Substation in Northborough, MA (3.67 miles). | 2016-06-01 | Notification | 2015-05-01
NEP-15-T07 | 2015-03-19 | Greater Boston Reconductor Project | Transmission notification from New England Power (NEP) to eliminate Double Circuit Tower structures on E-157 115 kV and X-24W 69 kV transmission lines. | 2015-12-01 | Notification | 2015-05-01
NEP-15-GNF07 | 2015-04-10 | SunE Solar New England I LLC Project | Generator notification from New England Power (NEP) on behalf of SunE Solar New England I LLC to interconnect a 3 MW solar generating system to National Grid’s 13.8 kV distribution system in Bridgewater, MA on the company’s 912W55 feeder out of the Mill Street Substation #912. | 2015-04-24 | Notification | 2015-05-01
NEP-15-GNF08 | 2015-04-10 | HA MA Solar LLC Project | Generator notification from New England Power (NEP) on behalf of HA MA Solar LLC to interconnect a 3.5 MW solar generating system to National Grid’s 13.2 kV distribution system in Hampden, MA on the company’s 139L1 feeder out of the West Hampden Substation #139. | 2015-07-16 | Notification | 2015-05-01
ES-15-T67 | 2015-04-01 | Bulls Bridge Substation Transformer Replacement Project | Transmission notification from Eversource Energy (ES) for replacement of 115/27.6 kV transformer with a rating of 28/37.3/46.7 MVA at the Bulls Bridge Substation in New Milford, CT. | 2015-03-01 | Notification | 2015-05-01
ES-15-G04 | 2015-03-31 | Holliston Solar Project | Generator notification from Eversource Energy (ES) on behalf of Marina Energy for the installation of a 1.3 MW PV facility in Holliston, MA and interconnecting on circuit 65-H7 via Medway Station #65, Bus Section #2. | 2015-05-01 | Notification | 2015-05-01
ES-15-T71 | 2015-04-21 | Manchester Substation Transformer Replacement Project | Transmission notification from Eversource Energy (ES) for replacement of Manchester 3A-2X 115/23 kV transformer with a rating of 36/48/60 MVA at the Manchester Substation in Manchester, CT. | 2015-12-01 | Notification | 2015-05-01
ES-15-T69 | 2015-03-30 | Line 372 Reconductor Project | Transmission notification from Eversource Energy (ES) to reconductor 4.2 miles of 345 kV underground cable Line 372 from Mystic to Kingston Street in Boston, MA. | 2015-12-01 | Notification | 2015-05-01
NU-13-T32-Rev.1 | 2015-04-08 | Greenwich 115/13.2 kV Substation Project | Transmission notification from Connecticut Light and Power d.b.a. Eversource Energy (ES) of revisions to previously approved PPA NU-13-T32 that reflects changes to the radial circuits between existing Cos Cob Substation and previously approved Greenwich Substation and its configuration. | 2017-06-01 | Notification | 2015-05-01
GMP-15-G01 | 2015-04-08 | Proctor Hydroelectric Station Project | Generator notification from VELCO on behalf of Green Mountain Power Company for improvements to increase plant capacity from 6.65 MW to 10.2 MW which consists of five units connected via a 4.16/46 kV GSU to a radial 46 kV line supplied from VELCO Florence 115/46 kV Substation | 2015-05-03 | Notification | 2015-05-01
ES-15-T30 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for the rebuild of the Bunker Hill Substation in Waterbury, CT by adding a new three bay, nine breaker/breaker and a half substation. | 2017-12-31 | Approved Withdrawn | 4/16/2015 5/23/2017
ES-15-T31 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for the looping the 115-kV 1990 Line in and out of Bunker Hill Substation in Waterbury, CT via termination on two new line terminal positions. This will create two lines, 1990N between Frost Bridge and Bunker Hill Substations and 1990S between Bunker Hill Substation, Baldwin Junction Substation, and Q384 Towantic Substation. | 2017-12-31 | Approved Withdrawn | 4/16/2015 5/23/2017
ES-15-T32 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for the replacement of 556 ACSR conductor with 556 ACSS conductor between Bunker Hill Substation in Waterbury, CT to Baldwin Junction in Middlebury CT. | 2017-12-31 | Approved | 2015-04-16
ES-15-T33 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for closing the normally open 115-kV 2T circuit breaker at Baldwin 115-kV Substation in Waterbury, CT. | 2017-12-31 | Approved | 2015-04-16
ES-15-T34 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for installation of a new 115-kV line from Plumtree Substation in Bethel, CT to Brookfield Junction in Brookfield, CT. | 2017-12-31 | Approved | 2015-04-16
ES-15-T35 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for reconfiguring the 1887 line into a 3-terminal line between Plumtree, West Brookfield, and Shepaug Substations. The 1770 line will be reconfigured into a two 2-terminal lines so that 1770W Line will be from Plumtree Substation to Stony Hill Substation and 1770E Line will be from Stony Hill Substation to Bates Rock Substation. | 2017-12-31 | Approved | 2015-04-16
ES-15-T36 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for reconductoring the 1887 line from 336 ACSR to 556 ACSS between West Brookfield Substation in Brookfield, CT and West Brookfield Junction in Brookfield, CT. | 2017-12-31 | Approved | 2015-04-16
ES-15-T37 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for relocating the 22K 115-kV capacitor bank (37.8 MVAr) to the 1770E Line terminal at Stony Hill Substation in Brookfield, CT. Also install a synchronous condenser (+25/-12.5 MVAr) at Stony Hill Substation. | 2017-12-31 | Approved | 2015-04-16
ES-15-T38 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for installation of a 115-kV circuit breaker in series with the existing 29T breaker. Also relocate the existing 37.8 MVAr capacitor bank from 115-kV “B” bus to “A” bus at Plumtree | 2017-12-31 | Approved | 2015-04-16
ES-15-T39 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for installing two 14.4 MVAr capacitor banks and associated 115 kV circuit breakers at West Brookfield Substation in Brookfield, CT. | 2017-12-31 | Approved | 2015-04-16
ES-15-T40 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for reducing the 25.2 MVAr capacitor at Rocky River 115-kV Substation in New Milford, CT to 14.4 MVAr. | 2017-12-31 | Approved | 2015-04-16
ES-15-T41 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for replacing two Freight Substation 115-kV circuit breakers in Waterbury, CT. The circuit breaker replacements are required if ISO-NE Queue position #384 project is completed. | 2017-12-31 | Approved | 2015-04-16
ES-15-T42 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for installing a 25.2 MVAr 115 kV capacitor bank at Oxford Substation, in Oxford, CT. | 2017-12-31 | Approved | 2015-04-16
ES-15-T43 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for rebuilding a portion of 115-kV 1682 line from Wilton 115-kV Substation in Wilton, CT to Norwalk 115-kV Substationin Norwalk, CT and upgrading Wilton Substation terminal equipment. | 2017-12-31 | Approved | 2015-04-16
ES-15-T44 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for reconductoring the 115-kV 1470-1 and 1470-3 lines from Wilton 115-kV Substation in Wilton, CT to Ridgefield Junction in Ridgefield, CT and from Ridgefield Junction to Peaceable 115-kV Substation in Redding, CT | 2017-12-31 | Approved | 2015-04-16
ES-15-T45 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for looping the 1570 line in and out of the United Illuminating Pootatuck 115-kV Substation in Shelton, CT. | 2017-12-31 | Approved | 2015-04-16
ES-15-T46 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for separating the 3827 Line and the 1610 Line between Cook Hill Junction in Cheshire, CT and the Cheshire Hamden town line. | 2017-12-31 | Approved Withdrawn | 4/16/2015 5/23/2017
ES-15-T47 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for retirement of the two +/- 8 MVAr Stony Hill DVARs as part of the Southwest Connecticut (SWCT) Solutions. | 2017-12-31 | Approved | 2015-04-16
ES-15-T48 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from Eversource Energy (“ES”) for retirement of the +/- 8 MVAr Bates Rock DVAR and a 13.8-kV capacitor bank as part of the Southwest Connecticut (SWCT) Solutions. | 2017-12-31 | Approved | 2015-04-16
UI-12-T15-Rev.1 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from United Illuminating Company (“UI”) for the installation of a 115 kV series reactor (7.5 ohm) at Mix Avenue Substation in Hamden, CT located on the 1610-2 terminal. | 2017-12-31 | Approved | 2015-04-16
UI-15-T02 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from United Illuminating Company (“UI”) for the re-conductor/rebuild the 2.26 mile overhead 88006A 115kV line to 1590 kcmil ACSS (or equivalent rated) from the Baird 115 kV Substation in Stratford, CT to the Devon Tie 115 kV Switching Station in Milford CT. | 2017-12-31 | Approved | 2015-04-16
UI-15-T03 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from United Illuminating Company (“UI”) for the re-conductor/rebuild the 2.26 mile overhead 89006B 115kV line to 1590 kcmil ACSS (or equivalent rated) from the Baird 115 kV Substation in Stratford, CT to the Devon Tie 115 kV Switching Station in Milford CT. | 2017-12-31 | Approved | 2015-04-16
UI-15-T04 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from United Illuminating Company (“UI”) for reconfiguring the Pootatuck 115 kV Substation in Shelton, CT into a 4 breaker ring bus and the addition of 115 kV capacitor bank (30 MVAR). | 2017-12-31 | Approved | 2015-04-16
UI-15-T05 | 2015-02-17 | Southwest Connecticut – Greater Hartford/Central Connecticut Transmission Project | Transmission notification from United Illuminating Company (“UI”) for the installation of two 25 MVAr 115 kV capacitor banks at the Ansonia Substation in Ansonia, CT (1 on 1560 terminal, 1 on 1594 terminal). | 2017-12-31 | Approved | 2015-04-16
ES-15-T01 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for adding a new 345/115-kV autotransformer at Barbour Hill Substation in South Windsor, CT. The project requires reconfiguration of the existing substation and consists of installing one 345-kV to be designated 2T at the Barbour Hill 345-kV Substation and re-terminate the 3557 Line between the Barbour Hill 2T and 3T 345-kV circuit breakers. Install two 115-kV circuit breakers designated as the 2X3-A1 and 2X3-B1 at the Barbour Hill 115-kV Substation. Also add a second 345/115-kV autotransformer at the Barbour Hill Substation. The second 345/115-kV autotransformer at the Barbour Hill Substation shall have the same electrical impedances (R, X, and B) on a 100-MVA base as the existing Barbour Hill 1X autotransformer. | 2017-12-31 | Approved | 2015-04-16
ES-15-T02 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for installation of a new 345-kV 24TA circuit breaker in series with the existing 345-kV 24T circuit breaker at Manchester Substation in Manchester, CT. | 2017-12-31 | Approved | 2015-04-16
ES-15-T03 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for reconductoring the 115-kV 1763 Line between Manchester 115-kV Substation in Manchester, CT and CT Barbour Hill 115-kV Substation in South Windsor, CT with a 795 ACSS conductor. | 2017-12-31 | Approved | 2015-04-16
ES-15-T04 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for constructing a new 115-kV line between Frost Bridge Substation in Watertown, CT and Campville Substation in Harwinton, CT. In addition to the proposed 115-kV line, there are substation modifications that are required to accommodate the new line and eliminate specific stuck breaker contingencies. These modifications are installation of three 115 kV circuit breakers (BTA, BT and 3TA) at Campville Substation and terminate the proposed line between the new BT and 3TA circuit breakers. Install the 2TA 115-kV circuit breaker in series with the 2T circuit breaker at Campville Substation. Install the AT 115-kV circuit breaker and terminate the proposed line in the bus section between the existing 24T circuit breaker and the proposed AT circuit breaker at Frost Bridge. | 2017-12-31 | Approved | 2015-04-16
ES-15-T05 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for separating the 115-kV double circuit tower (DCT) configuration corresponding to the 115-kV1191 Line from Frost Bridge Substation in Watertown, CT to Campville Substation inHarwinton, CT and the 1921 Line from Thomaston Substation in Thomaston, CT toCampville Substation. | 2017-12-31 | Approved | 2015-04-16
ES-15-T06 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for reconductoring the 115-kV 1810-1 Line from Southington Substation in Southington, CT to Lake Avenue Junction in Bristol, CT with 795 ACSS conductor | 2017-12-31 | Approved | 2015-04-16
ES-15-T07 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for replacing the existing 115-kV 3% series reactors on the 1910 and 1950 Lines with 5% seriesreactors at Southington 115-kV Substation in Southington, CT | 2017-12-31 | Approved | 2015-04-16
ES-15-T08 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for replacing the normally open 115-kV 19T circuit breaker with a 115-kV 3% series reactor at Southington Substation in Southington, CT. The 19T circuit breaker will be relocated to Ring Bus #1 and the proposed 21TA 115-kV circuit breaker will also be installed on Ring Bus #1 to establish the terminal position for the proposed series reactor. Additionally, the proposed 5TA 345-kV circuit breaker will be installed in series with the existing 5T circuit breaker in the Southington 345-kV Substation. | 2017-12-31 | Approved | 2015-04-16
ES-15-T09 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for converting the Newington 115-kV Substation in Newington, CT into a ring bus. The project consists of installing two 115-kV circuit breakers AT and BT. Reterminating the 1785 Line into the terminal position between the existing 2T and proposed AT circuit breakers. Also reterminating the 1783 Line into position between the existing 1T and 2T circuit breakers. | 2017-12-31 | Approved | 2015-04-16
ES-15-T10 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for reconductoring the 115-kV 1783-2 Line from Newington 115-kV Substation in Newington, CT to Newington Tap in Newington, CT, with 1590 ACSS conductor. 1783 line relocated to the ring bus position between the existing 1T and 2T breakers. | 2017-12-31 | Approved | 2015-04-16
ES-15-T11 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for installing a new 5000 kcmil XLPE 115-kV underground cable between Newington 115-kV Substation in Newington, CT and Southwest Hartford Substation in Hartford, CT. The line will be terminated at Newington Substation to the position between the existing 2T and the proposed AT 115-kV circuit breakers. The line will connect to a new 2% series reactor with a parallel bypass switch. The series reactor and bypass switch will terminate between the new AT and BT circuit breakers at Southwest Harford Substation. Also installing two 115-kV, 63-kA, 3000A circuit breakers (AT and BT) at the Southwest Hartford Substation. | 2017-12-31 | Approved | 2015-04-16
ES-15-T12 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for installing the two 115-kV circuit breaker (AT and BT) at the Southwest Hartford Substation and converting the Southwest Hartford Substation into a ring bus. | 2017-12-31 | Approved | 2015-04-16
ES-15-T13 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for installing a 26 TA 115-kV circuit breaker in series with the existing 26T circuit breaker at the Berlin Substation in Berlin CT. Also relocate the existing 115 kV 50.5 MVAR capacitor bank from 115 kV B bus to the 115 kV A bus. | 2017-12-31 | Approved | 2015-04-16
ES-15-T14 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for installing a 115-kV 3% series reactor in series with the 1704 Line at Southwest Hartford 115-kV Substation in Hartford, CT | 2017-12-31 | Approved | 2015-04-16
ES-15-T15 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for reconfiguring the 115-kV Rood Avenue 115-kV Substation in Windsor, CT to a ring bus by installing four new 115-kV circuit breakers in the AT, BT, CT and DT positions. Also loop the 115-kV 1779 Line in and out of Rood Avenue 115-kV Substation to create two 2-terminal lines between South Meadow 115-kV Substation in Hartford, CT to Rood Avenue Substation and Rood Avenue Substation to Bloomfield Substation in Bloomfield, CT. | 2017-12-31 | Approved | 2015-04-16
ES-15-T16 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for upgrading the1779 line between Rood Avenue 115-kV Substation in Windsor, CT and Bloomfield 115-kV Substation in Bloomfield, CT and separating the 1777/1779 DCT. In addition, the proposed 2TA 115-kV circuit breaker will be installed at Bloomfield Substation in Bloomfield, CT. The reconfigured 1779 Line will be terminated between the proposed 2TA and existing 3T circuit breakers at Bloomfield Substation. | 2017-12-31 | Approved | 2015-04-16
ES-15-T17 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for separating the 1751/1777 DCT between Bloomfield 115-kV Substation in Bloomfield, CT and Bloomfield Junction in Bloomfield, CT and installing the 13TA 115-kV circuit breaker in series with the existing 13T circuit breaker at North Bloomfield 115-kV Substation in Bloomfield, CT. | 2017-12-31 | Approved | 2015-04-16
ES-15-T18 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for installing three new single phase 200-MVA rated 345/115-kV autotransformers at Haddam 11C Substation in Haddam, CT with same electrical impedances (R, X, and B), ratings (Normal, STE, LTE) and the same LTC tap size and range as the existing Haddam autotransformer. Install four 345 kV circuit breaker and reconfigure the Haddam 345‐kV Substation into a breaker-and-half configuration. Also split the 345 kV 348 Line into two 2‐terminal lines 348E ‐ Millstone to Haddam, and 348W - Haddam to Beseck. Reconfigure the Haddam Substation. | 2017-12-31 | Approved | 2015-04-16
ES-15-T19 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for installing six new 115-kV circuit breakers in Green Hill Substation in Madison, CT, and reconfiguring the substation into a ring bus, and installing two 25.2 MVAr capacitor banks. | 2017-12-31 | Approved | 2015-04-16
ES-15-T20 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for adding one 115-kV circuit breaker and installing one 37.8 MVAr capacitor bank at the Hopewell Substation in Glastonbury, CT. | 2017-12-31 | Approved | 2015-04-16
ES-15-T21 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for installing one 25.2 MVAr capacitor bank and 115-kV circuit breaker on the 1766 line terminal at the West Side Substation in Middletown, CT | 2017-12-31 | Approved | 2015-04-16
ES-15-T22 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for separating the existing 1572-1620 DCT configuration between Middletown and Pratt and Whitney Substations between Middletown and Haddam Substations. | 2017-12-31 | Approved | 2015-04-16
ES-15-T23 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for separating the existing 1537-1655 DCT configuration between Branford and Branford Railroad Substations and between Branford and North Haven Substations. It also consists of installing one new 115-kV circuit breaker adjacent to the 2T circuit breaker at the Branford 115-kV Substation in Branford, CT. | 2017-12-31 | Approved | 2015-04-16
ES-15-T24 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | Transmission notification from Eversource Energy (“ES”) for increasing the 37.8 MVAr capacitor at Branford 115-kV Substation in Branford, CT to 50.4 MVAr. | 2017-12-31 | Approved | 2015-04-16
NU-08-T61-Rev.1 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | PPA Withdrawal Notification from Eversource Energy (formally NU) for the Frost Bridge 18R Substation expansion by adding a 345/115 kV autotransformer. | 2017-12-31 | Withdrawn | 2015-04-16
NU-12-T15 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | PPA Withdrawal Notification from Eversource Energy (formally NU) for the North Bloomfield 2A Substation expansion. | 2017-12-31 | Approved | 2015-04-16
NU-12-T16-Rev.1 | 2015-02-17 | Greater Hartford/Central Connecticut (GHCC) Transmission Project | PPA Withdrawal Notification from Eversource Energy (formally NU) for the addition of a 2nd Beseck 9F Substation variable shunt reactor (75-150 MVAr). | 2017-12-31 | Approved | 2015-04-16
ES-15-T53 | 2015-02-25 | Blair Pond Substation Project | Transmission notification from Eversource Energy (“ES”) for the construction of a new Blair Pond 115/13.8 kV substation in Belmont, MA. The substation will have a 115 kV ring bus and will be supplied by existing 329-530115 kV line between the North Cambridge and Brighton substations (to be re-numbered as 509-530). | 2016-06-30 | Approved | 2015-04-16
VELCO-15-T01 | 2015-02-27 | Connecticut River Corridor Transmission Project | Transmission application from Vermont Electric Power Company (“VELCO”) to upgrade the existing K31 Coolidge to Ascutney 115 kV Line with 1351 ACSS conductor. | 2017-10-30 | Approved | 2015-04-16
VELCO-15-T02 | 2015-02-27 | Connecticut River Corridor Transmission Project | Transmission Application from Vermont Electric Power Company (“VELCO”) to install a 50/-25 MVAr Static VAR Compensator (SVC) at the Ascutney Substation and add a third bay to the Ascutney Substation. | 2017-10-30 | Approved | 2015-04-16
VELCO-15-T03 | 2015-02-27 | Connecticut River Corridor Transmission Project | Transmission Application from Vermont Electric Power Company (“VELCO”) to split the Harford 25 MVAr capacitor bank into two 12.5 MVAr capacitor banks. | 2017-10-30 | Approved | 2015-04-16
VELCO-15-T04 | 2015-02-27 | Connecticut River Corridor Transmission Project | Transmission Application from Vermont Electric Power Company (“VELCO”) to reconfigure the Chelsea 115 kV Substation from a straight bus to a 3 breaker ring substation. | 2017-10-30 | Approved | 2015-04-16
NEP-15-T02 | 2015-03-06 | Ipswich River/Peabody Substation Project | Transmission notification from New England Power Company “NEP”) for the removal of the existing single transformer Ipswich River 115–23 kV substation currently tapped from B-154N line and installation of a new two transformer Ipswich River 115–23 kV substation which will tap both the B-154N and the C-155N lines. | 2016-05-30 | Approved | 2015-04-16
NEP-15-G01 | 2015-03-03 | Spruce Ridge Wind Generation and Transmission Project | Generator notification from New England Power Company (“NEP”) on behalf of Spruce Ridge Wind Farm LLC for the installation of 28 1.815 Vestas V1000 wind turbine generators (50.82 MWs net output) located in Groton, NH. Construction of two 34.5 kV collector circuits with 14 wind turbines per circuit. Also install a 230/34.5/13.8 kV main transformer with 40/53/66 MVA rating and switchgear to interconnect the wind power facility. | 2017-09-15 | Approved Withdrawn | 4/16/2015 4/10/2017
NEP-15-T01 | 2015-03-03 | Spruce Ridge Wind Generation and Transmission Project | Transmission notification from New England Power Company (“NEP”) for the construction of a 230 kV interconnection substation in Groton, NH, which includes three 230kV, 3000A, 40kA, non-IPT breakers and nine (9) 230kV, 3000A three phase motor operated disconnects. Construct a 0.05 mile long, 230 kV tap line connecting the interconnection substation to the 230 kV A-201 transmission line. Connect the interconnection substation to the proposed wind power facility as specified in NEP-15-G01. | 2017-09-15 | Approved Withdrawn | 4/16/2015 4/10/2017
ES-15-T55 | 2015-03-03 | Spruce Ridge Wind Generation and Transmission Project | Transmission notification from Eversource Energy (“ES”) for the thermal upgrade of the 11 mile 115 kV A111 Line from Webster Substation in Webster, NH to Pemigewassett Substation in Littleton, NH from 135 MVA to 138 MVA in support of the Spruce Ridge Wind Generator Project. | 2017-09-15 | Approved Withdrawn | 4/16/2015 4/10/2017
ES-15-T56 | 2015-03-03 | Spruce Ridge Wind Generation and Transmission Project | Transmission notification from Eversource Energy (“ES”) for the thermal upgrade of the 8 mile 115 kV E115-2 Line from Ashland Tap in Ashland, NH to the Pemigewassett Substation in Littleton, NH from 135 MVA to 138 MVA in support of the Spruce Ridge Wind Project. | 2017-09-15 | Approved Withdrawn | 4/16/2015 4/10/2017
GRE-15-G01 | 2015-03-10 | Granite Ridge Generator Uprate Project | Generator notification from Granite Ridge Energy LLC (“GRE”) for the summer incremental net capacity uprate of +40 MW (at ≥ 50° F) of an existing 2x1 combined cycle facility. The steam turbine generator (STG) will be connected at PSNH’s 115 kV Watts Brook station and the combustion turbine generators (CTG1 and CTG2) will be connected at National Grid’s 230 kV North Litchfield station. CTG1 and CTG2 will both be upgraded by approximately 17.5 MW, and STG will be upgraded by 5 MW (at ≥ 50° F). The combined plant summer rated net output is 761 MW (at ≥ 50° F). The winter incremental net capacity uprate is +8 MW for a combined net plant output of 814 MW (at ≥ 0° F). | 2015-03-17 | Approved | 2015-04-16
VELCO-15-GNF03 | 2015-02-20 | Stafford Hill Solar Project | Generation notification from Vermont Electric Power Company (“VELCO”) for the installation of a 2.0 MW solar array interconnecting at the East Rutland Substation via the 12.47 kV Circuit #51, Line 222, Pole 2-5 in Rutland, VT. | 2015-04-30 | Notification | 2015-04-16
ES-15-T60 | 2015-03-02 | 533-508 Line Upgrade Project | Transmission notification from Eversource Energy (“ES”) for upgrading the 533-508 Line from Hartwell Avenue Substation in Lexington, MA to Lexington Substation in Lexington, MA by removing sag limitation, replacing cable risers and control and protection changes including installing new meter and CTs. Once the upgrade is complete, the line will be rated to the full conductor rating of 282/359/400 MVA Summer. Existing ratings are 279/279/279 MVA Summer | 2015-05-30 | Notification | 2015-04-16
NEP-15-GNF06 | 2015-03-06 | TJA Bridgewater Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of TJA Solar LLC, PV Project for the installation of a 2.967 MW solar array in Bridgewater, MA and customer fed by Feeder #797W1 out of the East Bridgewater Substation #797. | 2015-05-22 | Notification | 2015-04-16
NEP-15-GNF05 | 2015-03-06 | Bluewave Capital Sturbridge Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Bluewave Capital LLC, PV Project for the installation of a 2 MW solar array in Sturbridge, MA and customer fed by Feeder #415L3 out of the West Charlton Substation #415. | 2015-05-24 | Notification | 2015-04-16
ES-15-G03 | 2015-03-03 | Wind Colebrook South Project | Generator notification from Eversource Energy (“ES”) on behalf of Wind Colebrook South LLC for the installation of a 4.98 MW wind turbine generator located in Colebrook, CT and interconnecting to the 27 kV Canton 5R Substation circuit 5R80. | 2015-06-01 | Notification | 2015-04-16
NEP-15-GNF04 | 2015-01-30 | Johnston Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Johnston Solar I LLC for the installation of a 1.375 MW solar array located in Johnston, RI and interconnecting via the Feeder #21F2 out of the West Cranston Substation #21 | 2015-04-01 | Notification | 2015-02-25
NEP-15-GNF03 | 2015-01-30 | Synacarpha Leominster Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Syncarpha Massachusetts LLC for the installation of a 2.0 MW solar array located in Leominster, MA and interconnecting via the Feeder #219W2 out of the Prospect Street Substation #219. | 2015-02-28 | Notification | 2015-02-25
NEP-15-GNF02 | 2015-01-30 | Solar City Swansea Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Solar City Corporation for the installation of a 2.0 MW solar array located in Swansea, MA and interconnecting via the Feeder #11W84 out of the Swansea Substation #11. | 2015-04-24 | Notification | 2015-02-25
NEP-15-GNF01 | 2015-01-30 | North Adams Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 2.25 MW solar array located in North Adams, MA and interconnecting via the Feeder #1015W01 out of the Walker Street Substation #1015. | 2015-04-06 | Notification | 2015-02-25
ES-15-T52 | 2015-01-29 | Valley Substation Transformer Replacement Project | Transmission notification from Eversource Energy Service Company (“ES”) for the replacement of the Valley #2 15/20/25 MVA Transformer bank with a new 30/40/50 MVA 115/23kV transformer bank, 23kV secondary breaker, and 23kV breaker disconnect switches located in Plymouth, MA. | 2015-06-01 | Approved | 2015-02-25
NMLD-15-T01 | 2015-01-21 | Norwood Line 447-508 and 447-509 Line Rehabilitation Project | Transmission notification from Norwood Municipal Light Department (“NMLD”) for the rehabilitation of 115 kV lines 447-508 and 447-509 from the NSTAR tap in Sharon to the Dean St. #495 substation in Norwood, MA. | 2016-11-30 | Approved | 2015-02-25
UI-15-G01 | 2015-01-20 | University of Bridgeport Fuel Cell Project | Generator notification from United Illuminating Company (“UI) on behalf of UB Fuel Cell for the installation of a 1.389 MW (net output) fuel cell generator in Bridgeport, CT and interconnecting to the Pequonnock Substation Feeder #2507. | 2015-02-11 | Approved | 2015-02-25
ES-15-T25 | 2015-02-10 | 1779 Line Upgrade Project | Transmission notification from Eversource Energy Service Company (“ES”) for the rebuilding of 1779 115-kV Line from South Meadow Substation to Bloomfield Substation in Bloomfield, CT due to asset conditions. | 2017-12-31 | Approved | 2015-02-25
FW-15-G01 | 2015-01-01 | Blue Sky Wind Generation and Transmission Project | Generation notification from First Wind Energy Marketing (“FW”) on behalf of Blue Sky West LLC for the construction of 56 Vestas 3.3 MW wind turbine generators (184.8 MWs net output) and a 60 MVA synchronous condenser and an associated collector system, located in Piscataquis County, ME. | 2016-12-31 | Approved | 2015-03-02
FW-15-T01 | 2015-01-01 | Blue Sky Wind Generation and Transmission Project | Transmission notification from First Wind Energy Marketing (“FW”) on behalf of Blue Sky West LLC for the construction of a new 34.5/115 kV Substation (Blue Sky West Substation) located in Bingham, ME, and 17 miles of overhead 795 KCM ACSR 2 conductor, bundle 115 kV transmission line between the Blue Sky West Substation and the Guilford Substation. | 2016-12-31 | Approved | 2015-03-02
CMP-15-T01 | 2015-01-01 | Blue Sky Wind Generation and Transmission Project | Transmission notification from Central Maine Power Company (“CMP”) for the installation of a 0/+70 MVAR SVC at the Detroit Substation located in Detroit, ME, in association with the Blue Sky West Wind Farm. | 2017-05-01 | Approved | 2015-03-02
CMP-15-T02 | 2015-01-01 | Blue Sky Wind Generation and Transmission Project | Transmission notification from Central Maine Power Company (“CMP”) for the rerate of Section 85 115 kV line from Detroit to Guilford Substations and add a three breaker ring bus to the Guilford Substation located in Parkman, ME, in association with the Blue Sky West Wind Farm. | 2016-08-01 | Approved | 2015-03-02
EM-15-T01 | 2015-01-01 | Blue Sky Wind Generation and Transmission Project | Transmission notification from Emera Maine (“EM”) for the reinstallation of the existing Orrington series capacitor (originally S388, now S3023 due to a line reconfiguration change), reducing its size from 25 ohms to 22.32 ohms. Also install a second series capacitor in S388 to compensate 42% of the Orrington toCoopers Mills line section. | 2016-12-31 | Approved | 2015-03-02
PSEG-15-G01 (Revision available) | 2015-01-07 | Bridgeport Harbor Combined Cycle Generator and Transmission Project | Generator notification from PSEG Energy Resources & Trade LLC (“PSEG”) for the construction of a 517.5 MW (Summer Net Output)/542.5 MW (Winter Net Output) 1x1 Combined Cycle Gas & Steam Turbine generator located in Bridgeport, CT. | 2018-05-31 | Approved | 2015-02-10
PSEG-15-T01 (Revision available) | 2015-01-07 | Bridgeport Harbor Combined Cycle Generator and Transmission Project | Transmission notification from PSEG Energy Resources & Trade LLC (“PSEG”) for the installation of a 430 MVA transformer for the CT GSU-1 interconnecting the Bridgeport Harbor CCGT generator at the Singer 345 kV Substation. | 2018-05-31 | Approved | 2015-02-10
PSEG-15-T02 (Revision available) | 2015-01-07 | Bridgeport Harbor Combined Cycle Generator and Transmission Project | Transmission notification from PSEG Energy Resources & Trade LLC (“PSEG”) for the installation of a 430 MVA transformer for the ST GSU-2 interconnecting the Bridgeport Harbor CCGT generator at the Singer 345 kV Substation. | 2018-05-31 | Approved | 2015-02-10
UI-15-T01 | 2015-01-07 | Bridgeport Harbor Combined Cycle Generator and Transmission Project | Transmission notification from United Illuminating Company (“UI”) to terminate and connect the 345 kV underground line from the Bridgeport Harbor Combined Cycle Generator to the Singer 345 kV Substation. | 2018-05-31 | Approved | 2015-02-10
BE-15-G01 | 2015-01-02 | Bridgeport Energy Generator Uprate | Generator notification from Emera Energy Service Subsidiary #5/Bridgeport Energy (“BE”) to increase the net output of the Bridgeport Energy combined cycle generator (BE ST10, CT 11, CT 12) located in Bridgeport, CT by 47.8 MWs at 50 degrees. | 2015-03-01 | Approved | 2015-02-10
NU-14-G11 | 2015-01-09 | TJA Carver Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of TJA Solar Inc. for the installation of a 4.99 MW solar array located in Carver, MA and interconnecting to the NU Brook Street Substation #727, 23 kV feeder #51, 23 kV circuit #980. | 2015-03-01 | Notification Withdrawn | 2/10/2015 7/12/2016
VELCO-15-GNF01 | 2015-01-05 | Whitcomb Solar Project | Generator notification from Vermont Electric Power Company (“VELCO) on behalf of Chester Power Partners for the installation of a 2.175 MW solar array and interconnecting to the 19G5 feeder to the Essex Substation in Essex Junction, VT. | 2014-10-30 | Notification | 2015-02-10
VELCO-15-GNF02 | 2015-01-05 | Chester Solar Project | Generator notification from Vermont Electric Power Company (“VELCO) on behalf of ER WR Whitcomb Farm Solar, LLC for the installation of a 2.2 MW solar array and interconnecting Substation #11, Circuit #03, Poll 1-3-2 in Chester, VT. | 2014-11-03 | Notification | 2015-02-10
EXE-14-X01 | 2014-12-11 | Framingham and Mystic AVR Replacement Project | Transmission notification from Exelon Generation Company LLC (“EXE”) for the replacement of the excitation controller and AVRs at Framingham Station (Jets 1, 2 and 3). The upgrade will install a new Allen Bradley Combination Generation Control Module with Series Boost Unit at each jet, which will provide excitation current to the existing brushless exciters and replace the existing AVRs. | 2014-12-19 | Approved | 2014-12-29
EXE-14-X02 | 2014-12-11 | Framingham and Mystic AVR Replacement Project | Transmission notification from Exelon Generation Company LLC (“EXE”) for the replacement of the excitation controller and AVR at the Mystic Jet. The upgrade will install a new Allen Bradley Combination Generation Control Module with Series Boost Unit, which will provide excitation current to the existing brushless exciter and replace the existing AVR. | 2014-12-19 | Approved | 2014-12-29
VELCO-14-GNF10 | 2014-11-14 | Barton Solar Project | Generator notification from Vermont Electric Company (“VELCO”) on behalf of Barton Solar. LLC for the installation of a 1.89 MW solar array located in Barton, VT and interconnecting to the 3A feeder origination from the Burton Hill Substation via the 3A5 pad-mounted recloser located at the Barton Solar project. | 2014-11-14 | Notification | 2015-01-13
NEP-14-GNF21 | 2014-12-05 | SEC CRSD Solar One Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of SEC CRSD Solar One, LLC for the installation of a 2.89 MW solar array located in Hardwick, MA and interconnecting via Feeder #501L2 out of the Ware Substation #501. | 2014-12-31 | Notification | 2015-01-13
NEP-14-GNF22 | 2014-12-05 | Solar City Williamsburg Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Solar City Corp. for the installation of a 2.266 MW solar array located in Williamsburg, MA and interconnecting via Feeder #909W3 out of the Florence Junction Substation #909. | 2014-12-22 | Notification | 2015-01-13
CMP-14-X01 | 2014-12-11 | Eliminate 3rd Path of Section 396 SPS Project | Transmission notification from Central Maine Power Company (“CMP”) for the elimination of the 3rd Path of Section 396 SPS because of over-redundancy. | 2015-01-01 | Notification | 2015-01-13
WBLTN-14-G01 | 2014-10-03 | Borrego West Boylston Solar | Generator notification from West Boylston Municipal Lighting Plant (“WBLTN”) on behalf of Borrego Solar Systems Inc. for the installation of a 3.0 MW solar array located in West Boylston, MA and interconnecting to the 13.8 kV Hartwell Street feeder via the West Boylston Substation P142W. | 2014-12-01 | Notification | 2015-01-14
PWF-14-G01 | 2014-06-06 | Passadumkeag Wind Restudy Project | Wind Generation project with total output 39.975MW, connecting to Emera Maine Line 64 by means of a new collector substation | Q4 2015 | Approved | 2014-09-09
PWF-14-T01 | 2014-06-06 | Passadumkeag Wind Restudy Project | Q357 Collector substation 115/34.5 kV under load tap changing transformer located at the collector substation and point of interconnection with Emera Maine. | Q4 2015 | Approved | 2014-09-09
EM-14-T02 | 2014-06-06 | Passadumkeag Wind Restudy Project | Ring bus tap of existing Line 64 and renumber of southern portion of that line | Q4 2015 | Approved | 2014-09-09
DEM-14-G01 | 2014-11-05 | Manchester Street Generator Uprate Project | Generator notification from Dominion Energy, Manchester St, Inc. (“DEM”) for the increased MW output of Manchester St generators 9/9A, 10/10A, and 11/11A based on upgrades performed to the combustion turbines. As a result, the station’s summer NCR will increase from 483 MWs to 510 MWs and the CNRC will increase from 447 MWs to 477 MWs. | 2015-03-02 | Approved | 2014-12-01
NU-14-T21 | 2014-10-01 | Sudbury Station 115 kV Shunt Reactor Installation Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the installation of two new 115 kV, 20 MVAR shunt reactors at Sudbury Substation. The new reactors are needed to lower transmission voltages in the Sudbury - Maynard load area under light load conditions. The main project components consist of the 115 kV, 20 MVAR reactors and associated 115 kV circuit breakers with a synchronous switching controller. | 2014-12-01 | Approved | 2014-11-20
NU-13-T31-Rev.1 | 2014-11-06 | Peaslee Substation Modification Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the Peaslee Substation project to alleviate breaker failure contingencies through a change in the line termination points at the Peaslee Substation | 2016-06-01 | Approved | 2014-12-01
NEP-14-GNF17 | 2014-11-07 | Clinton Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Solar MA Project Management LLC for the installation of a 2.0 MW solar array located in Clinton, MA and interconnecting to the Fitch Road 216 Substation via the 13.8 kV 216W5 feeder. | 2014-12-01 | Notification | 2014-12-01
NEP-14-GNF18 | 2014-11-07 | RIN Logistics Fall River Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of RIN Logistics Inc. for the installation of a 1.5 MW solar array located in Fall River, MA and interconnecting to the Sykes Road 28 Substation via the 13.8 kV 28W51 feeder. | 2014-11-15 | Notification | 2014-12-01
NEP-14-GNF19 | 2014-11-07 | Independence Stoughton Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Independence Solar VII LLC for the installation of a 1.725 MW solar array located in Stoughton, MA and interconnecting to the Parkview 94 Substation via the 13.8 kV 94W42 feeder. | 2014-11-14 | Notification | 2014-12-01
NEP-14-GNF20 | 2014-11-07 | Sune Solar Norton Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Sune Solar Norton 1 LLC for the installation of a 3.0 MW solar array located in Norton, MA and interconnecting to the Easton 92 Substation via the 13.8 kV 92W79 feeder. | 2014-12-31 | Notification | 2014-12-01
NEP-14-T12 | 2014-11-07 | Webster Street Tap #1 Reconductor Project | Transmission notification from New England Power Company (“NEP”) for the reconductor of 2.2 miles of overhead transmission of the 115 kV A-127 line. | 2017-05-01 | Notification | 2014-12-01
NU-12-T44-Rev.1 | 2014-10-29 | Littleton Substation Autotransformer Revision Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the installation of a 230 kV circuit breaker versus the initial design of a circuit switcher on the second 230/115 kV Littleton Autotransformer TB138 located in Littleton, NH to enable future improvements in area fault isolation. | 2014-11-04 | Notification | 2014-12-01
NU-14-G02 | 2014-10-23 | Novartis Synchronous Generator Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of Novartis for the installation of two 1.4 MW synchronous generators in Cambridge, MA. Generator one will interconnect to the Putnam Station #831, Bus Section A via 14 kV distribution line 831-1301. Generator 2 will interconnect to the Putnam Station #831, Bus Section B via 14 kV distribution line 831-1324. | 2014-12-31 | Notification | 2014-12-01
VELCO-14-GNF09 | 2014-11-05 | GMP Park Street Rutland Solar Project | Generator notification from Vermont Electric Company (“VELCO”) on behalf of Park Street Solar for the installation of a 1.833 MW solar array located in Rutland, VT and interconnecting to the South Rutland Substation 12.47 kV circuit 70. | 2014-11-30 | Notification | 2014-12-01
VELCO-14-GNF08 | 2014-11-05 | Route 7 Rutland Solar Project | Generator notification from Vermont Electric Company (“VELCO”) on behalf of NextSun Energy Rutland for the installation of a 1.5 MW solar array located in Rutland, VT and interconnecting to the North Rutland Substation 12.47 kV circuit 34. | 2014-11-30 | Notification | 2014-12-01
BRP-14-X01 | 2014-10-08 | Cataract Hydro AVR Replacement Project | Transmission notification from Brookfield Renewable Energy (“BRP”) for the replacement of the Automatic Voltage Regulator (“AVR”) at the Cataract Hydro Unit 1 located near the Louden 115 kV Substation. | 2015-10-16 | Approved | 2014-11-20
BRP-14-G01 | 2014-10-03 | Wyman Hydro Upgrade Project | Generator notification from Brookfield Renewable Power (BRP) for the upgrade of the Wyman Hydro Units 1 & 3. Unit 1 will perform a turbine runner replacement, GSU transformer replacement and excitation system replacement. Unit 3 will perform a turbine runner replacement, stator rewinding and excitation system replacement. Upgrades will result in a 7.1 MW net output increase for the units to 30 MWs (total net output) and increased reactive capability. | 2015-03-31 | Approved | 2014-11-20
BELD-14-G01 | 2014-10-06 | Watson 3 (Potter Repowering) Generator Project | Generator notification from Braintree Electric Light Department (“BELD”) for the installation of a combustion turbine generator with a maximum summer net output of 63.3 MW (at 50° F and higher). The Project will be interconnected at the same point as the existing Potter II combined cycle plant. The existing Potter II plant and associated generator step-up transformer (GSU) will be retired prior to QP438 being placed into service. The Project will result in a MW capacity reduction of approximately 22 MW (summer, ≥ 50° F) and 32 MW (winter, ≥ 0° F) at the Potter 115kV station. | 2018-11-22 | Approved Withdrawn | 11/20/2014 5/31/2017
BELD-14-T01 | 2014-10-06 | Watson 3 (Potter Repowering) Generator Project | Transmission notification from Braintree Electric Light Department (“BELD”) for the interconnection of the Watson 3 generator to the 115 kV Switchyard Station 16 via a 636 KCMIL Aluminum 0.03 mile overhead 115 kV line. | 2018-11-22 | Approved Withdrawn | 11/20/2014 5/31/2017
NU-14-G09 | 2014-10-07 | Freetown Braley 2 Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) On behalf of Braley Rd II LLC, c/o Rockland Capital for the installation of a 2.948 MW solar array located in East Freetown, MA and interconnecting to the NU Industrial Park Substation #636 via the 13.2 kV feeder #108. | 2014-10-01 | Notification | 2014-11-20
NU-14-G10 | 2014-10-07 | Freetown Chace Road Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of Braley Rd II LLC, c/o Rockland Capital for the installation of a 4.5 MW solar array located in East Freetown, MA and interconnecting to the NU Industrial Park Substation #636 via the 13.2 kV feeder #108. | 2014-10-01 | Notification | 2014-11-20
NU-14-G08 (Revision available) | 2014-10-07 | NextAmp Dartmouth Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of NextAmp Capital, LLC for the installation of a 4.68 MW solar array located in Dartmouth, MA and interconnecting to the NU Cross Road Substation #651 via the 13.2 kV feeder #543. | 2016-01-01 | Notification | 2014-11-20
NU-14-T71 | 2014-10-07 | Bloomfield 3X 115/23 kV Distribution Transformer Replacement Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the replacement of the existing Bloomfield 3X 115/23 kV distribution transformer at the Bloomfield 3B 115/23 kV substation in Bloomfield CT. The new transformer will be rated at 60MVA, 115/23 kV. | 2014-11-30 | Notification | 2014-11-20
WGE-14-G01 | 2014-10-08 | Twiss Street Solar Project | Generator notification from Westfield Gas & Electric Department (“WGE”) for the installation of a 1.5 MW solar array in Westfield, MA and interconnecting to the WGE Buck Pond 34B substation via the 23 kV Feeder #34B7. | 2014-12-31 | Notification | 2014-11-20
VELCO-14-GNF07 | 2014-09-29 | Boltonville Hydro Project | Generator notification from Vermont Electric Power Company (“VELCO”) for the interconnection of a 1.318 MW run of river hydro generator in Boltonville, VT and interconnecting to the Ryegate Power Substation #85 via the 85G2 circuit. Proposed in service date of the project will be upon completion of the project interconnection agreement if required. | 2014-09-26 | Notification | 2014-11-20
NU-14-G16 | 2014-09-02 | Jericho Wind Farm Expansion Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of Queue Position #437 for the installation of two 2.85 MW wind turbine generators at the Jericho Wind Farm. Project will interconnect to the PSNH Jericho Road 34/.5 kV Substation in Berlin, NH. Unit name plate capability is 5.7 MWs but due to distribution system limitations, the combined total output of the project and QP #415 will be limited by a wind farm controller 10 12.05 MWs, a 3.5 MW increase from the original QP #415 project | 2014-11-01 | Approved | 2014-10-21
NEP-14-T10 | 2014-09-02 | Southeast Substation Project | Transmission notification from New England Power Company (“NEP”) for the construction of a new Southeast Substation located in Pawtucket, RI. Project will consist of two 115/13.8 kV 33/44/55 MVA LTC transformer supplied via taps off the X3 and T7 Lines. In addition, at Pawtucket No. 1 substation, move the T74 115/13.8 kV transformer to the T71 transformer position and retire existing T71 115/13.8 kV transformer and associated 13.8 kV indoor bus. | 2014-12-01 | Approved | 2014-10-21
NU-14-G17 | 2014-09-09 | Brewster Landfill Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of CF CVEC Owner One LLC the installation of a 1.083 MW solar array located in Brewster, MA and interconnecting to the NU Harwich Substation #968, #118 transformer via the 23 kV feeder #89A. | 2014-09-05 | Notification | 2014-10-21
NEP-14-T11 | 2014-09-09 | Ward Hill Transformer Replacement Project | Transmission notification from New England Power Company (“NEP”) for the replacement of the existing 48/64/80 MVA 115/24 kV T1 transformer with a new 45/60/75 MVA 115/24 kV transformer due to unit conditions at the Ward Hill substation located in Haverhill, MA. | 2014-06-01 | Notification | 2014-10-21
NEP-14-T05 | 2014-08-25 | East Beverly Substation Transformer Replacement Project | Transmission notification from New England Power Company (“NEP”) for the replacement of two existing 115/34.5 kV 24/32/40 MVA transformers with115/34.5 kV 33/44/55 MVA transformers at the East Beverly Substation located in Beverly, MA. | 2016-11-01 | Notification | 2014-10-21
UI-14-G03 | 2014-08-28 | UI Seaside Renewable Solar Project | Generator notification from United Illuminating Company (“UI”) for the installation of a 2.2 MW solar array fuel cell generator located in Bridgeport CT and interconnecting to the Pequonnock 115/13.8 KV Substation 13.8 kV bus #1, position #8, circuit #2501. | 2015-07-01 | Notification | 2014-10-21
VELCO-14-T01 | 2014-07-14 | PV 20 Cable Line Replacement Project | Transmission notification from Vermont Electric Company (“VELCO”) for replacement of the submarine cables along the PV 20 115 kV line connecting Plattsburgh, NY substation and the Sand Bar VT substation. | 2017-12-01 | Notification | 2014-10-21
VELCO-14-GNF03 | 2014-07-14 | Coventry Solar Project | Generator notification from Vermont Electric Company (“VELCO”) on behalf of Coventry Photovoltaic LLC for the construction of a 2.2 MW solar array located in Coventry, VT and interconnecting to the H17 45 kV line out of the Irasburg substation. | 2014-07-09 | Notification | 2014-10-21
VELCO-14-GNF04 | 2014-07-14 | North Clarendon Solar Project | Generator notification from Vermont Electric Company (“VELCO”) on behalf of Clarendon Solar Farm LLC for the construction of a 2.0 MW solar array located in North Clarendon, VT and interconnecting to the 12.5 kV feeder out of North Brattleboro supplied from the Vernon Road substation. | 2014-08-01 | Notification | 2014-10-21
VELCO-14-GNF05 | 2014-07-14 | Technology Drive Solar Project | Generator notification from Vermont Electric Company (“VELCO”) on behalf of WE 90 Technology Drive, LLC for the construction of a 2.0 MW solar array located in Brattleboro, VT and interconnecting to the 12.5 kV feeder out of South Rutland supplied from the Cold River substation. | 2014-07-01 | Notification | 2014-10-21
VELCO-14-GNF06 | 2014-07-14 | Charlotte Solar Project | Generator notification from Vermont Electric Company (“VELCO”) on behalf of Charlotte Solar, LLC for the installation of a 2.0 MW solar array located in Charlotte, VT and interconnecting to the Green Mountain Power pole #129 to a 12.47 kV distribution circuit. | 6/2014 | Notification | 2014-10-21
PWF-14-G01 | 2014-06-06 | Passadumkeag Wind Generation and Transmission Project | Generator notification from Passadumkeag Windpark LLC (“PWF”) for the installation of thirteen 3.075MW wind turbine generators (39.975 MW net output) located in Passadumkeag, ME and interconnecting to the Emera Maine Line 64 by means of a new collector substation. | 2015-12-31 | Approved | 2014-09-09
PWF-14-T01 | 2014-06-06 | Passadumkeag Wind Generation and Transmission Project | Transmission notification from Passadumkeag Windpark LLC (“PWF”) for the construction of a new 115/34.5 kV collector substation under load tap changing transformer located at the collector substation and point of interconnection with Emera Maine | 2015-12-31 | Approved | 2014-09-09
EM-14-T02 | 2014-06-06 | Passadumkeag Wind Generation and Transmission Project | Transmission notification from Emera Maine (“EM”) for a ring bus tap of the existing Line 64 aprox. 22.5 miles north of Graham and aprox. 10 miles south of Enfield and renumber of the southern portion of the line | 2015-12-31 | Approved | 2014-09-09
NU-14-G12 | 2014-07-29 | Borrego Federal Road Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) for the installation of a 4.5 MW solar array located in Carver, MA and interconnecting via the NU #83 23 kV distribution feeder out of the Wareham Substation #714 | 2014-12-31 | Notification | 2014-09-09
NU-14-G07 | 2014-07-29 | Mattapoisett Crystal Spring Road Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of BlueWave Capital, LLC for the installation of a 4.5 MW solar array located in Mattapoisett, MA and interconnecting via the NU #302 13.2 kV distribution feeder out of the Crystal Spring Substation #646. | 2015-03-01 | Notification | 2014-09-09
NU-14-G15 | 2014-07-29 | Plymouth Cedarville Phase II Solar | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of Renewable Energy Development Partners, LLC for the installation of a 2.0 MW solar array located in Plymouth, MA and interconnecting via the NU #89 23 kV distribution feeder out of the Valley Substation #715. | 2014-10-01 | Notification | 2014-09-09
NU-14-G13 | 2014-07-29 | Tihonet Park East Solar | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of 510 PV Project Development, LLC for the installation of a 2.0 MW solar array located in Wareham, MA and interconnecting via the NU #83 23 kV distribution feeder out of the Wareham Substation #714. | 2014-12-31 | Notification | 2014-09-09
NU-14-G14 | 2014-07-29 | Onset Water District Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of 510 PV Project Development, LLC for the installation of a 2.0 MW solar array located in Wareham, MA and interconnecting via the NU #84 23 kV distribution feeder and #961 23 kV distribution circuit out of the Wareham Substation #714 | 2014-12-31 | Notification | 2014-09-09
NEP-14-GNF14 | 2014-08-01 | SunEdison Origination I Fall River Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of SunEdison Origination I, LLC for the installation of a 2.0 MW solar array located in Fall River, MA and interconnecting via the 28W50 13.8 kV distribution feeder to the Sykes Road Substation #28. | 2016-10-24 | Notification | 2014-09-09
NEP-14-GNF15 | 2014-08-01 | SunEdison Origination I Grafton Solar | Generator notification from New England Power Company (“NEP”) on behalf of SunEdison Origination I, LLC for the installation of a 2.0 MW solar array located in Grafton, MA and interconnecting via the 304W1 13.8 kV distribution feeder to the Millbury Substation #304. | 2014-11-01 | Notification | 2014-09-09
NEP-14-GNF16 | 2014-08-01 | Bluewave Capital Palmer Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Bluewave Capital, LLC for the installation of a 3.8 MW solar array located in Palmer, MA and interconnecting via the 0504 23 kV distribution feeder to the Palmer Substation #514. | 2016-12-06 | Notification | 2014-09-09
NEP-14-T09 | 2014-07-24 | V-148N 115 kV Line Reconductoring | Transmission notification from New England Power Company (“NEP”) on behalf of Narragansett Electric for the reconductoring of the 4.2 mile overhead V-148N 115 kV transmission line from Woonsocket Substation, RI to Washington Substation, RI. | 2017-06-01 | Notification | 2014-09-09
UI-14-T03 | 2014-07-29 | Old Town 115/13.8 kV Substation Rebuild Project | Transmission notification from United Illuminating Company (“UI”) for the reconstruction of the Old Town Substation located in Bridgeport, CT. Project will consist of installation of nine new monopoles to allow for re-routing of the 1222 and 1710 115 kV lines in and out of the substation, including the addition of a new 115 kV gas circuit breaker and disconnect switches and modification of the 115 kV bus. The installation of two new 30/40/50 MVA, 118/14.9 kV power transformers, with load tap changers(LTCs). The installation of a new Power Delivery Center (PDC) for interconnecting the existing distribution circuits and the removal of the existing distribution substation | 2017-12-01 | Notification | 2014-09-09
UI-14-T04 | 2014-07-29 | Baird 115/13.8 kV Substation Rebuild Project | Transmission notification from United Illuminating Company (“UI”) for the reconstruction of the Baird Substation located in Stratford, CT. Project will consist of the installation of two new monopoles to allow for re-routing of the 88006A and 89006B 115 kV line taps into the substation, including the addition of two new 115 kV gas circuit breakers, associated disconnect switches and modification of the 115 kV bus. The installation of two new 30/40/50 MVA, 118/14.9 kV power transformers, with load tap changers (LTCs. The installation of a new Power Delivery Center (PDC) for interconnecting the existing distribution circuits and the removal of the existing distribution substation. | 2018-12-31 | Notification | 2014-09-09
UI-14-G01 | 2014-07-30 | East Shore Renewable Fuel Cell Project | Generator notification from United Illuminating Company (“UI”) for the installation of a 2.8 MW fuel cell generator located in New Haven, CT and interconnecting to the East Shore 115/13.8 kV Substation 13.8 kV bus #2, position #26. | 2015-01-15 | Notification | 2014-09-09
UI-14-G02 | 2014-07-30 | Seaside Renewable Fuel Cell Project | Generator notification from United Illuminating Company (“UI”) for the installation of a 2.8 MW fuel cell generator located in Bridgeport, CT and interconnecting to the Pequonnock 115/13.8 kV Substation 13.8 kV bus #1, position #8, circuit #2501. | 2015-04-15 | Notification | 2014-09-09
NU-14-T19 | 2014-07-28 | Summerville Substation Transformer Replacement Project | Transmission notification from Northeast Utilities Service Company (“NU”) to upgrade the Somerville Station #402 in Somerville, Massachusetts to replace Transformer 110A and its associated circuit switcher. The new transformer will be rated 117/15kV 37/50/65.4 MVA. Relays will be upgraded but relay schemes will not be changed | 2015-06-01 | Notification | 2014-09-09
NU-14-T20 | 2014-07-28 | Wing Lane Substation Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the upgrades to the Wing Lane Substation #624 in Acushnet, Massachusetts. Replace three automatic sectionalizing switches for primary / alternate supply from 115kV lines #112 and #114 to Wing Lane and Arsene substations with a two-breaker switching module; install a 115/13.2 kV, 24/32/40 MVA transformer and associated equipment to double end the substation; install line metering on the 112 and 114 lines to enhance system operations. | 2015-08-01 | Notification | 2014-09-09
NU-14-T17 | 2014-06-25 | K Street to Dewar & Andrew Square Cable Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the installation of two 115 kV HPFF 2250 kcmil CU cables from K St Substation to a wye-splice manhole on Day Blvd for a distance of approximately 5,000’. Split the wye-splices on the 483-524/525 lines and reconnect the sections to Andrew Sq creating circuits 106-526/527. Connect these new circuits to K St bus positions formerly connected to generators. At K St install a new circuit breaker in the west 115 kV bus to create separate positions for autotransformer 345A and line 483-525. | 2015-06-01 | Approved | 2014-08-08
NEP-14-T07 | 2014-07-16 | North Oxford Substation Project | Transmission notification from New England Power Company (“NEP”) for the installation of 115 kV inline breaker and a new 2nd 24/32/40 MVA, 115/13.2 kV transformer at the North Oxford Substation located in Oxford, MA. Proposed in service | 2018-06-01 | Approved | 2014-08-08
NEP-14-T06 | 2004-06-30 | North Grafton Substation Project | Transmission notification from New England Power Company (“NEP”) for the replacement of the existing 69/4.16 kV, 3.75MVA transformer with a 69/13.8 kV, 24/32/40 MVA transformer at the North Grafton Substation #328 located in North Grafton, MA. | 2016-06-01 | Approved | 2014-08-08
CPV-14-G01 | 2014-06-05 | Towantic Combined Cycle Generator and Transmission Project | Generator notification from CPV Towantic LLC (“CVP”) for the construction of a 745MW (net output) (CT1 265 MWs net, CT2 265 MWs net, ST1 245 MWs net), 2 x 1 combined-cycle generation plant in Oxford, CT. | 2018-06-01 | Approved | 2014-08-08
CPV-14-T01 | 2014-06-05 | Towantic Combined Cycle Generator and Transmission Project | Transmission notification from CPV Towantic LLC (“CVP”) for the installation of two 200/330 MVAR transformers for CTs 1 & 2. | 2018-06-01 | Approved | 2014-08-08
CPV-14-T02 | 2014-06-05 | Towantic Combined Cycle Generator and Transmission Project | Transmission notification from CPV Towantic LLC (“CVP”) for the installation of a 200/330 MVA transformers for ST 1. | 2018-06-01 | Approved | 2014-08-08
NU-14-T10 | 2014-06-05 | Towantic Combined Cycle Generator and Transmission Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the construction of Towantic 115-kV Substation and Termination of 1575, 1585, and 1990 115-kV Lines into Towantic 115-kV Substation | 2018-06-01 | Approved | 2014-08-08
NU-14-T11 (Revision available) | 2014-06-05 | Towantic Combined Cycle Generator and Transmission Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the upgrade of the 115-kV 1585N Line section between Towantic and Bunker Hill Substations. | 2018-06-01 | Approved | 2014-08-08
NU-14-T12 (Revision available) | 2014-06-05 | Towantic Combined Cycle Generator and Transmission Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the For the upgrade 115-kV 1575S Line section between Towantic and Oxford Substations | 2018-06-01 | Approved | 2014-08-08
NEP-14-T08 | 2014-07-16 | East Webster Substation Project | Transmission notification from New England Power Company (“NEP”) for the replacement of the existing 69/13.2kV 30MVA transformer T1 with a 24/32/40 MVA 69/13.2kV transformer | 2018-06-01 | Notification | 2014-08-08
NU-14-T18 | 2014-08-11 | Montville Autotransformer Replacement Project | Transmission notification from Northeast Utilities service Company (“NU”) for the replacement of existing 18x and 19x 345/115-kV Autotransformers at Montville Substation with similar rated transformers. | 2014-12-31 | Notification | 2014-08-08
EM-14-X01 | 2014-07-09 | New Brunswick Direct Path Logic Special Protection System Modification | Transmission notification from Emera Maine (“EM”) on behalf of the New Brunswick Power System Operator for the modification of the New Brunswick Direct Path Logic (DPL) Special Protection System (SPS – NPCC SPP #176) to include the Madawaska HVDC facility. | 2014-07-17 | Notification | 2014-07-18
NU-14-T15 | 2014-06-02 | Acushnet/Pine Street Cable Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the Relocation of two 115 kV pipe-type cables from the present Acushnet River crossing to a new river crossing. Reconfiguration of the Acushnet #612 substation to effectively parallel underground cables #112 and #114 (to be renamed #142 and #143); installation of a series breaker with Acushnet breaker #EW22. At Pine St Substation # 611 install series breakers with circuit breaker 11212 and 11412; Remove two former GSU transformers from service. Also install two 10 MVAr switched shunt reactors with isolation circuit breakers. Make condition based upgrades to miscellaneous equipment at both substation as well as upgrade relays and control equipment. | 2016-06-01 | Approved | 2014-07-18
NEP-14-T03 | 2014-05-28 | Pelham Transformer and Breaker Project | Transmission notification from New England Power Company (“NEP”) for the installation of an in-line 115 kV circuit breaker. Loop the 115 kV Y-151 line through the substation via a section of new 115 kV overhead line. Replace the existing 115/13.2, 12/16/20 MVA transformer with a 115/13.2 kV, 24/32/40 MVA transformer. Install a second 115/13.2 kV, 24/32/40 MVA transformer. | 2017-06-01 | Approved | 2014-07-18
CPV-14-G01 | 2014-03-28 | Towantic Combined Cycle Generator Project | Generator notification from CPV Towantic LLC (“CVP”) for the construction of a 745MW (net output) (CT1 265 MWs net, CT2 265 MWs net, ST1 245 MWs net), 2 x 1 combined-cycle generation plant in Oxford, CT. | 2018-06-01 | Approved | 2014-08-08
CPV-14-T01 | 2014-03-28 | Towantic Combined Cycle Generator Project | Transmission notification from CPV Towantic LLC (“CVP”) for the installation of two 200/330 MVAR transformers for CTs 1 & 2. | 2018-06-01 | Approved | 2014-08-08
CPV-14-T02 | 2014-03-28 | Towantic Combined Cycle Generator Project | Transmission notification from CPV Towantic LLC (“CVP”) for the installation of a 200/330 MVA transformers for ST 1. | 2018-06-01 | Approved | 2014-08-08
NU-14-T10 | 2014-03-28 | Towantic Combined Cycle Generator Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the construction of Towantic 115-kV Substation and Termination of 1575, 1585, and 1990 115-kV Lines into Towantic 115-kV Substation. | 2018-06-01 | Approved | 2014-08-08
NU-14-T11 | 2014-03-28 | Towantic Combined Cycle Generator Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the upgrade of the 115-kV 1585N Line section between Towantic and Bunker Hill Substations. | 2018-06-01 | Approved | 2014-08-08
NU-14-T12 | 2014-03-28 | Towantic Combined Cycle Generator Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the For the upgrade 115-kV 1575S Line section between Towantic and Oxford Substations | 2018-06-01 | Approved | 2014-08-08
FGE-14-G01 | 2014-05-29 | Chase Road Solar Project | Generator notification from Unitil-Fitchburg Gas & Electric Company (“FGE”) for the installation of a 2.49 MW solar array located in Lunenburg, MA and interconnecting via the 13.8 kV 30W31 circuit to the Lunenburg substation #30. | 2014-06-30 | Notification | 2014-07-18
UI-14-T01 | 2014-05-29 | Housatonic River Crossing 115 kV Line Rebuild Project | Transmission notification from United Illuminating Company (“UI”) for the 0.47 mile overhead 88006A 115 kV Line Rebuild, Milford-Stratford, Connecticut. | 2015-12-01 | Notification | 2014-07-18
UI-14-T02 | 2014-05-29 | Housatonic River Crossing 115 kV Line Rebuild Project | Transmission notification from United Illuminating Company (“UI”) for the 0.47 mile overhead 89006B 115 kV Line Rebuild, Milford-Stratford, Connecticut. | 2015-12-01 | Notification | 2014-07-18
NU-14-T16 | 2014-06-12 | Barnstable/Harwich Tap 115 kV Line Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the construction of a 7.8 mile 115 kV overhead transmission line from the Barnstable 115 kV Substation to Harwich Tap. This new line will mitigate the loss of load resulting from the simultaneous loss of double circuit tower (DCT) lines 118 and 119. | 2018-06-01 | Notification | 2014-07-18
NU-14-X02 | 2014-06-12 | Barnstable/Harwich Tap 115 kV Line Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the modification of the existing Barnstable Type 1 SPS. The modification is needed in order to keep the function of the existing SPS unchanged after the completion of the project. | 2018-06-01 | Notification | 2014-07-18
NU-14-T06-Rev.1 and NU-14-X01-Rev.1 | 2014-05-13 | UMA Tillson Substation Project Rev.1 | Transmission notifications from Northeast Utilities Service Company (“NU”) for the revision to the UMA Tillson Substation Project to document the correction in the Winter STE rating of line 1113 from the Five Corners Substation tap point to the UMA Tillson Substation in Amherst, MA tap point from 90 MVA to 91 MVA. | 2015-09-01 | Notification | 2014-07-18
NEP-14-GNF13 | 2014-06-06 | NexAmp Belchertown Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of NexAmp Belchertown Solar LLC for the construction of a 1.3 MW solar array located in Belchertown, MA and interconnecting to the National Grid 13.2 kV distribution system on the 509L2 feeder out of the Belchertown 509 substation. | 2014-06-17 | Notification | 2014-07-18
NEP-14-T04 | 2014-06-05 | Tewksbury 22A 345 kV GIS Substation Rebuild Project | Transmission notification from New England Power Company (“NEP”) in kind replacement of the Tewksbury 22A GIS Substation Rebuild Project due to asset conditions, reliability and environment issues. | 2014-12-01 | Notification | 2014-07-18
CEL-14-G02 | 2014-06-05 | CRBP Solar Project | Generator notification from Chicopee Electric Light Department on behalf of Chicopee Granby Road Solar LLC for the construction of a 1.6 MW solar array located in Chicopee, MA and interconnecting via the 18L13 feeder out of the Chicopee 18L substation. | 2014-12-01 | Notification | 2014-07-18
CEL-14-G01 | 2014-06-05 | CRBP Solar Project | Generator notification from Chicopee Electric Light Department on behalf of Chicopee River Business Park Solar LLC for the construction of a 2.0 MW solar array located in Chicopee, MA and interconnecting via the 18L12 feeder out of the Chicopee 18L substation. | 2014-12-01 | Notification | 2014-07-18
FW-12-T02-Rev.2 | 2014-05-01 | Oakfield Wind Project Rev.2 | Transmission notification revision from First Wind Energy Marketing (“FW”) on behalf of Evergreen Wind Power II LLC for the Addition of a new Keene Rd 115/345kV autotransformer dedicated to the project, two 115kV 25MVAR capacitor banks, associated circuit breakers and switchgear, 115kV transmission line between Keene Rd and the new Oakfield collector substation, 115/34.5/12.5kV three winding transformer located at the collector substation, and one 60MVA synchronous condenser located on collector substation transformer tertiary winding. The change that is reflected in Rev. 2 is going from two transformers in the collector substation to a single larger transformer with the same effective impedance as the original configuration. | 2015-12-01 | Approved | 2014-05-29
FW-12-G02-Rev.2 | 2014-05-01 | Oakfield Wind Project Rev.2 | Generator notification revision from First Wind Energy Marketing (“FW”) on behalf of Evergreen Wind Power II LLC for the modification of the 147.6 MW Oakfield Wind Farm collector substation to show updated 34.5 kV breaker arrangement, transformer changes and turbine count installation interconnecting to the Emera Maine Keene Road 345 kV | 2015-12-01 | Approved | 2014-05-29
NEP-14-GNF10 | 2014-05-09 | UGT Renewable Energy 7 Billerica Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of UGT Renewable Energy 7 LLC for the installation of a 4.99 MW solar array located in Billrica, MA and interconnecting to the 13.2 kV 70L8 feeder out of the Billerica Substation #70. | 2014-06-01 | Notification | 2014-05-29
NEP-14-GNF11 | 2014-05-09 | Bluewave Capital Uxbridge Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of BlueWave Capital LLC for the installation of a 3.0 MW solar array located in Uxbridge, MA and interconnecting to the 13.8 kV 321W9 feeder out of the Uxbridge Substation #321. | 2014-06-01 | Notification | 2014-05-29
NEP-14-GNF12 | 2014-05-09 | SunEdison Origination 3 Rehoboth Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of SunEdison Origination 3 LLC for the installation of a 4.0 MW solar array located in Rehoboth, MA and interconnecting to the 23 kV 2284 feeder out of the West Street Substation. | 2014-06-01 | Notification | 2014-05-29
NU-14-G06 | 2014-04-14 | Norwalk Hospital Gas Generator Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of Norwalk Hospital for the installation of a 3.0 MW gas turbine generator located in Norwalk, CT and interconnecting to the 9S4 feeder out of the Norwalk Substation. | 2014-05-30 | Notification | 2014-05-29
NEP-14-G03 | 2014-03-21 | Block Island Wind Farm Project | Generator notification from New England Power Company (“NEP”) on behalf of Deep Water Wind, LLC for the installation of five 6.0 MW wind turbine generators (30 MW net output) located on a off shore wind farm 3 miles SE of Block Island, RI and interconnecting to a new 34.5 kV substation in the town of New Shoreham in Block Island, RI. The project will be connected to Narragansett’s 34.5kV sub-transmission system at Wakefield substation via the to-be-constructed Block Island Transmission System (BITS) which includes two new 34.5 kV substations, one on Block Island and the other on the main land in Narragansett, RI, and 34.5 kV sub-submarine, underground and overhead lines | 2016-06-01 | Approved | 2014-04-28
NU-14-T06 | 2013-03-17 | UMA Tillson Substation Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the construction of a 115/13.8 kV substation located in Amherst, MA. to serve the increased load at the University of Massachusetts (UMA). The new Tillson substation will be connected to the WMECO transmission system by tapping existing lines 1113 and 1044, and building two single circuit lines from the tap points to the substation. A 115-kV bus tie-breaker with 40-kA interrupting capability will be installed at Tillson substation and operated normally open (N.O.). Also, 115-kV line circuit switchers with 40 kA interrupting capability will be installed on the two lines (1044 and 1113) coming into the substation and on the 1044 line at Amherst substation.Two (2) 115/13.8 kV distribution transformers will be installed at Tillson substation, each with a high-side (115-kV) circuit switcher. The capacity of existing lines 1113 and 1044 will be upgraded as follows: • Increase clearances on the 1113 line from the Five Corners substation tap point to the UMA Tillson substation tap point to obtain summer ratings of at least 68/68/68/73 MVA (normal/LTE/STE/DAL), and winter ratings of at least 91/91/90/99 MVA. • Increase clearances on the 1113 line from Fairmont 16H Substation to the Five Corners substation tap point to obtain summer ratings of at least 76/76/76/86 MVA (normal/LTE/STE/DAL), and winter ratings of at least 120/120/121/139 MVA. • Increase clearances on the 1044 line from Montague 21G Substation to the Tillson/Amherst tap point to obtain summer ratings of at least 58/58/58/62 MVA (normal/LTE/STE/DAL), and winter ratings of at least 84/84/84/91 MVA. | 2015-09-01 | Approved | 2014-04-28
NU-14-X01 | 2013-03-17 | UMA Tillson Substation Project | Transmission notification from Northeast Utilities Service Company (“NU”)to install a Type 3 Special Protection System (SPS) to avoid loading lines 1113 and 1044 above the STE/DAL ratings during switching operations necessary for load transfers at Tillson, Podick and Amherst substations following the 1113, 1044, 1632 and 1134 line outages. The SPS will be facilitated by communication links between the area substations | 2015-09-01 | Approved | 2014-04-28
NU-14-T09 | 2014-03-21 | Mill Pond Substation Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the construction of a new 115/12.5 kV Mill Pond substation located in Portsmouth, NH.The transformer loadings at Jackson, Lafayette and ISLG 559 distribution 34.5 kV and 12.5kV substations in the Portsmouth area of New Hampshire are projected to exceed their emergency limits in 2015. These distribution substations are fed from the 115-kV transmission system out of the Resistance and Ocean Road substations. The new substation will be fed from a new half mile radial 115-kV line. The new line will be tapping the existing 115-kV U181 Line from Ocean Road to Schiller Substation. | 6/1/20105 | Approved | 2014-04-28
NU-14-G05 | 2014-03-26 | SunDurance CFS I Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of SunDurance-CFS I, LLC for the installation of a two 1.67 MW solar arrays (3.30 MW net output) in Southwick, MA and interconnecting to the Southwick 29A 115 kV substation via the WMECO 29A1 13.8 kV distribution circuit. | 2014-05-30 | Notification | 2014-04-28
NEP-14-GNF05 | 2014-04-04 | UGT Renewable Energy 13 Oxford Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of UGT Renewable Energy 13 LLC for the installation of a 2.75 MW solar array located in Oxford, MA and interconnecting to the 406L4 feeder out of the North Oxford Substation #406. | 2014-06-01 | Notification | 2014-04-28
NEP-14-GNF06 | 2014-04-04 | CES Massachusetts Easton Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of CES Massachusetts Solar LLC for the installation of a 2 MW solar array located in Easton, MA and interconnecting to the 98W46 feeder out of the Belmont St. Substation #98. | 2014-06-01 | Notification | 2014-04-28
NEP-14-GNF07 | 2014-04-04 | Bluewave Capital Haverhill Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of BlueWave Capital LLC for the installation of a 1.43 MW solar array located in Haverhill, MA and interconnecting to the 47L1 feeder out of the West Newbury Substation #47. | 2014-06-01 | Notification | 2014-04-28
NEP-14-GNF08 | 2014-04-04 | Mass PV 7 Leicester Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Mass PV 7 LLC for the installation of a 4.833 MW solar array located in Leicester, MA and interconnecting to the 21W2 feeder out of the Leicester Substation #21. | 2014-06-01 | Notification | 2014-04-28
NEP-14-GNF09 | 2014-04-04 | 205 Sturbridge Solar Brimfield Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of 205 Sturbridge Solar, LLC for the installation of a 2.0 MW solar array located in Brimfield, MA and interconnecting to the 516L1 feeder out of the Little Rest Road Substation. | 2014-04-15 | Notification | 2014-04-28
NU-13-T04 | 2014-03-03 | Mashpee Substation Upgrade Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the addition of a second 30/40/50 MVA 115/23 kV transformer and 23kV bus section, and provide for two additional 23kV feeders and a 4.8 MVAR station capacitor bank. As part of the project to increase station capacity, a 2-breaker 115kV breaker arrangement with associated equipment will be installed at Mashpee Substation in #136 Falmouth Tap to Barnstable 115kV line. | 2015-12-31 | Approved | 2014-03-20
EP-14-G01 | 2014-03-10 | Newington Generator Uprate Project | Generator notification from Essential Power Newington, LLC (“EP”) for the uprate of the Newington Energy combined cycle generator located in Newington, NH from 561.5 MWs to 594.8 MWs net output degrees F and 547.5 MWs to 568.2 MWs net output at 50 degrees F as a result of an air permitting correction that allows supplementary firing of the plant’s heat recovery steam generator duct burners during temperatures below 60 degrees F. | 2014-03-01 | Approved | 2014-03-20
NU-14-G03 | 2014-02-12 | Jericho Mountain Wind Project | Generator notification from Northeast Utilities Service Company (“NU”) for the construction of three 2.85 MW (8.55 MWs net output) in Berlin, NH and interconnect to the Jericho Road 34.5 kV substation also in Berlin, NH. | 2014-10-01 | Approved | 2014-03-20
CMP-14-T01 | 2014-03-03 | County Road Substation Project | Transmission notification from Central Maine Power Company (“CMP”) for the construction of a new County Road (Rice Rips) substation that sectionalizes Section 241 by adding four 115 kV circuit breakers in a ring bus configuration and install two 115/34.5 kV 30/56 MVA transformers at a new green field site. The new substation will replace the existing Rice Rips substation. Also construct 6.5 miles of new 115 kV (1192 kcmil 45/7 ACSR) conductor from the Section 241A tap point to the new Country Road Substation | 2017-09-01 | Approved | 2014-03-20
NU-14-T07 | 2014-03-18 | Saxonville Temporary Mobile Station #278 Project | Transmission notification from Northeast Utilities Service Company (“NU”) to establish a new temporary 115/14 kV at the retired 14/4 kV Station #278 located in Framingham, MA. Tap 115 kV line 342-507. Install mobile station equipment including a 20 MVA, 117/15.12 kV transformer, a 123 kV, 1,200 amp, 31.5 kAmp interrupting rated circuit switcher and 2 - 1,200 amp, 15 kV vacuum circuit breakers. Tie into existing 13.8 kV distribution circuit infrastructure at ROW 8-1 and Lake Rd. The new temporary station provides additional distribution system supply in time for summer peak 2014. | 2014-06-01 | Notification | 2014-03-20
NU-14-G04 | 2014-02-28 | Hartford Hospital Fuel Cell Project | Generator notification from Northeast Utilities Service Company (“NU”) for the installation of a 1.5 MW fuel cell in Hartford, CT and interconnecting to South Meadows Feeder 109 and Feeder 151. | 2014-03-21 | Notification | 2014-03-20
VELCO-14-GNF02 | 2014-02-28 | WMA Chester Solar I Project | Generator notification from Vermont Electric Company (“VELCO”) on behalf of Vermont Public Power Supply Authority for the construction of a 4.8 MW solar array located in Chester, MA and interconnecting to the Blandford 19J 115 kV substation via WMECO’s 19J3 23kV distribution circuit via the Town of Chester Municipal Electric Light Department’s “extension of the WMECO 19J3” 23 kV distribution circuit. | 2014-03-19 | Notification | 2014-03-20
UI-09-T01-Rev.1 | 2014-03-10 | Shelton Substation Name Change to Pootatuck Substation | Transmission notification from United Illuminating Company (“UI”) to change the name of the existing Shelton 115/13.8 kV substation located in Shelton, CT to Pootatuck 115/13.8 kV substation. | 2014-03-18 | Notification | 2014-03-20
UI-12-T20-Rev.1 | 2014-01-28 | Hawthorne 115 kV Capacitor Bank Addition Project Rev.1 | Transmission notification from United Illuminating Company (“UI”) for the reduction of the previously proposed two capacitor banks from 30 MVAR each to 20 MVAR each (40 MVAR total) located at the Hawthorne 115 kV Substation in Fairfield, CT | 2015-12-01 | Approved | 2014-02-27
FW-14-G01 | 2014-01-15 | Bowers Wind Generation and Transmission Project | Generation notification from First Wind Energy Marketing (“FW”) on behalf of Champlain Wind LLC for the construction of sixteen 3 MW wind turbine generators (total output 48 MWs) located in Penobscot and Washington Counties, ME. | 2015-08-31 | Approved Withdrawn | 2/24/2014 2/17/2015
FW-14-T01 | 2014-01-15 | Bowers Wind Generation and Transmission Project | Transmission Notification from First Wind Energy Marketing (“FW”) on behalf of Champlain Wind LLC for the construction of a new 115/34.5 kV substation in Penobscot County, ME. Install two 34.5 kV circuit breaker and a new 115/34.5 kV interconnection transformer (30/40/50 MVA). | 2015-08-31 | Approved Withdrawn | 2/24/2014 2/17/2015
EM-14-T01 | 2014-01-15 | Bowers Wind Generation and Transmission Project | Transmission notification from Emera Maine (“EM”) for the installation of a 20 MVAR DVAR at the Chester 115 kV Substation located in Chester, ME to mitigate voltage performance issues. | 2015-08-31 | Approved Withdrawn | 2/24/2014 2/17/2015
FW-12-G02-Rev.1 | 2013-12-16 | Oakfield Wind Generation and Transmission Project Rev.1 | Generator notification revision from First Wind Energy Marketing (“FW”) on behalf of Evergreen Wind Power II LLC for the removal of the normally open bus tie breaker and the elimination of the 40.5 MVAR variable capacitor bank as part of the 147.6 MW Oakfield Wind Farm. | 2014-08-31 | Approved | 2014-02-24
FW-12-T02-Rev.1 | 2013-12-16 | Oakfield Wind Generation and Transmission Project Rev.1 | Transmission notification revision from First Wind Energy Marketing (“FW”) on behalf of Evergreen Wind Power II LLC for the addition of a 60 MVA synchronous condenser and related transformer changes at the Oakfield collector substation. | 2015-12-31 | Approved | 2014-02-24
NEP-14-T01 | 2014-01-24 | Mid-Weymouth Substation Transformer Project | Transmission notification from New England Power Company (“NEP”) for the addition of a 115 kV transformer at the Mid-Weymouth Substation located in Weymouth, MA to mitigate anticipated load growth in the area. | 2015-06-01 | Notification | 2014-02-27
NEP-14-GNF02 | 2014-02-07 | 205 Sturbridge Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of 205 Sturbridge Solar LLC for the installation of a 3 MW solar array located in Brimfield, MA and interconnect to the NGrid 13.2 kV distribution system on the 516L1 feeder out of the Little Rest Road #516 substation. | 2014-04-15 | Notification | 2014-02-27
NEP-14-GNF03 | 2014-02-07 | Bluewave Capital Grafton Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Bluewave Capital LLC for the installation of a 2 MW solar array located in Grafton, MA and interconnecting to the NGrid 13.8 kV distribution system on the 304W1 feeder out of the Millbury 4 substation. | 2014-04-14 | Notification | 2014-02-27
NEP-14-GNF04 | 2014-02-07 | Bluewave Capital Berlin Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Bluewave Capital LLC for the installation of a 3 MW solar array located in Berlin, MA and interconnecting to the NGrid 13.8 kV distribution system on the 318W3 feeder out of the North Marlborough substation. | 2014-05-30 | Notification | 2014-02-27
NEP-13-GNF44-Rev.1 | 2014-02-07 | Gardner Solar 1 Project Revision | Generator notification revision from New England Power Company (“NEP”) on behalf of Massachusetts Electric Company for the Gardner Solar I Project to change the size of the solar array to 1.98 MWs and interconnect to the NGrid 13.8 kV distribution system in Gardner, MA on the 601W1 feeder out of the Park St. 601 substation. | 2014-02-14 | Notification | 2014-02-27
NU-13-T24-Rev.1 | 2014-01-15 | Northern Pass – Scobie Pond Substation Project Revision | Transmission notification revision from Northeast Utilities Service Company (“NU”) for revisions to the Scobie Pond Substation drawing to reflect the addition of the 802S circuit breaker. | 2017-06-01 | Notification Withdrawn | 2/27/2014 3/29/2016
NU-14-T02 | 2014-01-29 | Norwalk Substation 115/13.8 kV Transformer Addition Project | Transmission notification revision from Northeast Utilities Service Company (“NU”) for installation of a 115/13.8 kV transformer and one 115 kV circuit breaker at the Norwalk Substation located in Norwalk, CT. | 2014-06-01 | Notification | 2014-02-27
NEP-13-G04 | 2014-01-10 | Toray Plastics Gas Generator Project | Generator notification from New England Power Company (“NEP”) for two gas fired generator (12.5 MWs total net output) located in Davisville, MA and interconnecting to the NGrid 84T4 34.5 kV feeder out of the Davisville substation. | 2013-12-01 | Approved | 2014-02-24
NEP-12-G04-Rev.1 | 2014-01-09 | Warren Solar Project Revision | Generator notification revision from New England Power Company (“NEP”) on behalf of First Wind for the construction of a 14 MW solar generator located in Warren, MA and interconnecting via the NGrid 516L4 13.2 kV feeder out of the Little Rest Road substation. Project revisions include a change to the previous owner (Mass PV 3 LLC) to First Wind, station capacity change from 9 MWs to 14 MWs and the SMA inverter models were included, as documented in the supporting revised study report. | 2014-03-01 | Approved | 2014-02-11
EMI-05-G01-Rev.1 | 2014-01-15 | Cape Wind Project Revisions | Generator notification revision from Energy Management Inc. for the installation of 130 wind turbines each rated at 3.6 MWs (454 MWs total net output, 468 MWs total gross output) located in Nantucket Sound, MA and interconnecting to the NSTAR 115 kV Barnstable Substation. Application revised to reflect a change to the wind turbine type from GE 3.6 MW Type 3 to Seimens SWT-4.0-107 (firmware limited to 3.6 MWs) wind turbines. | 2016-12-01 | Approved Withdrawn | 2/11/2014 1/12/2017
EMI-14-T01 | 2014-01-15 | Cape Wind Project Revisions | Transmission notification from Energy Management Inc. for the construction of two 115kV submarine/underground cable circuits and a 33:115kV offshore electric service platform (ESP) connecting the offshore wind farm to the 115kV Barnstable Substation. The electric service platform will consist of three 114/152/190MVA 33:115kV transformers and a five breaker GIS ring bus. Each cable circuit will be 18.4 miles in length and consist of two 800 mm solid dielectric cables with 12.6 miles being submarine cable and 5.8 miles being underground upland cable. | 2016-05-01 | Approved Withdrawn | 2/11/2014 1/12/2017
NU-14-T04 | 2014-01-15 | Cape Wind Project Revisions | Transmission notification from Northeast Utilities Service Company (“NU”) for the expansion of the Barnstable 115 kV substation to include a circuit breaker in the fourth bay and a circuit breaker in the fifth bay. Due to modifications at the Barnstable 115 kV substation since the approval of the NSTAR-05-T07 PPA, the requirement to expand the Barnstable 115 kV substation to include a fifth bay with two circuit breakers and add a third circuit breaker in the planned fourth bay has been reduced. Installation of four 35 MVAR shunt reactors at the Barnstable 115 kV substation to compensate for 115 kV and 33 kV cable charging. Each shunt reactor shall have a dedicated synchronous closing circuit breaker in order to avoid any transient over-voltages during switching. The modification to this requirement from the original NSTAR-05-T07 PPA is the change in location of two of the four 35 MVAR shunt reactors from the Cape Wind Electric Service Platform to the Barnstable 115 kV substation. Installation of a redundant circuit breaker in series with the existing #312 circuit breaker at the Canal 345 kV substation. Replacement of the Bourne 115 kV #12272 circuit breakers with breakers having independent poletripping (IPT). Addition of two harmonic filter banks to the Barnstable 115 kV substation with each having 35 MVAR of net charging. Each filter bank shall have a dedicated closing circuit breaker. The need for the filter capacitor banks was determined through detailed design studies of the Cape Wind project. The compensation of the net charging from these additional filter capacitor banks resulted in the following two required upgrades: Modification of the Barnstable SVC to result in having a net inductive operating capability of 70.5 MVAR and the addition of a 40 MVAR shunt reactor at the West Barnstable 115 kV substation that shall have a dedicated closing circuit breaker. | 2016-05-01 | Approved Withdrawn | 2/11/2014 1/12/2017
NU-13-G28 | 2014-01-09 | Barnstable Airport Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) for the installation of a 4.5 MW solar array located in Barnstable, MA and interconnecting to the Hyannis Junction Substation #961 via the NU #92A 23 kV distribution feeder. | 2014-06-01 | Notification | 2014-02-24
NU-14-T01 | 2014-01-06 | Dover Transformer Replacement Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the replacement of the 110/13.8 kV, 18/24 MVA transformer 110B at Dover Station #456. The existing transformer is vintage 1953, and has reached the end of its useful life. The outdated transformer is in poor condition and limits the capacity of the station to levels below the 2014 forecasted load. | 2014-06-01 | Notification | 2014-02-24
NU-13-T34 | 2013-12-18 | Harwich Tap Reconductoring Project | Transmission notification from Northeast Utilities Service Company (“NU”) to reconductor the 4.4 mile Harwich #119 Tap line from Harwich Tap (Dennis, MA) to Harwich Bulk (Harwich, MA) from 4/0 ACSR 6/1 to 795 ACSS 54/7. This line section will also be brought up to present state code and hardened with the installation of steel structure at line angles. | 2014-03-01 | Notification | 2014-02-24
NU-14-G01 | 2014-01-09 | Lahey Clinic Hospital CHP Generator Project | Generator notification from Northeast Utilities Service Company (“NU”) for the construction of a load reducing 2.93 MW (net output) CHP synchronous generatorm in Burlington, MA and interconnecting to the NSTAR Burlington #391 substation via the 541-1377H feeder. | 2014-01-01 | Notification | 2014-02-24
NU-13-G27 | 2014-01-13 | New Bedford Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of TJA Solar, LLC for the construction of a 3 MW solar array located in New Bedford, MA and interconnecting to the Northeast Utilities Industrial Park Substation #636 via the 13.2 kV feeder #103. | 2014-03-01 | Notification Withdrawn | 1/21/2014 6/12/2014
VELCO-13-GNF06 | 2014-01-07 | Sheldon Springs Solar Project | Generator notification from Vermont Electric Company (“VELCO”) for the construction of a 2.2 MW solar array located in Sheldon, VT and interconnecting via the VEC Sheldon Springs Hydro 46 kV supplied by the Highgate 15 kV substation. | 2013-08-11 | Notification | 2014-02-24
VELCO-13-GNF07 | 2014-01-07 | St. Albans Solar Project | Generator notification from Vermont Electric Company (“VELCO”) for the construction of a 2.0 MW solar array located in St. Albans, VT and interconnecting via the 12.5 kV #52 circuit at the GMP East St. Albans 34.5 kV substation. | 2013-11-07 | Notification | 2014-02-24
VELCO-13-GNF08 | 2014-01-07 | Cross Pollination Solar Project | Generator notification from Vermont Electric Company (“VELCO”) for the construction of a 1.96 MW solar array in New Haven, VT and interconnecting via the 9G4 12.5 kV circuit at the Vergennes 34.5 kV substation. | 2013-09-04 | Notification | 2014-02-24
VELCO-14-GNF01 | 2014-01-07 | Limerick Solar Project | Generator notification from Vermont Electric Company (“VELCO”) for the construction of a installation of a 2.12 MW solar array located in Shelburne, VT and interconnecting via the GMP 53G1 12.47 kV circuit at the Shelburne substation. | 2014-01-17 | Notification | 2014-02-24
NEP-14-GNF01 | 2014-01-10 | North Brookfield Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of North Brookfield Solar LLC for the installation of a 3.0 MW solar array located in North Brookfield, MA and interconnecting via the #525L1 feeder out of the Lashaway substation #525. | 2014-03-17 | Notification | 2014-02-24
NU-13-T20 | 2013-12-01 | Northern Pass Transmission Project | Transmission notification from Northeast Utilities Service Company (“NU”) on behalf of Northern Pass Transmission LLC. for the construction of a 345 kV air insulated substation with a eight circuit breaker ring bus. in Franklin, NH, a 1200 MW bi-directional, bi-polar, and a HVDC line commutated converter station 0/100 Mvar Static VAR Compensator (SVC). The 345-kV Franklin substation will interconnect to Public Service of New Hampshire’s 345-kV Deerfield substation (POI), located in Deerfield, New Hampshire, via a 345-kV ac overhead transmission line, and to the Des Canton substation in Quebec, Canada, via an HVDC link. The HVDC link will be a 1200 MW bi-directional HVdc line commutated converter, operating at ±300 kV. The Franklin HVdc link will have two 600 MW, 12-pulse line commutated converters with the following reactive compensation: 400 Mvar (2x100 Mvar per pole) of harmonic filters; 350 Mvar (175 Mvar per pole) of thyristor switched capacitors (1x25 Mvar TSC brank, 1x50 Mvar TSC branch, and 1x100 Mvar TSC branch);120 Mvar (2x60 Mvar) of mechanically switched reactors (MSR). | 2017-12-01 | Approved Withdrawn | 12/31/2013 3/29/2016
NU-13-T21 | 2013-12-01 | Northern Pass Transmission Project | Transmission notification from Northeast Utilities Service Company (“NU”) on behalf of Northern Pass Transmission LLC. for the construction of a 153 mile dc transmission line, which includes 8 miles of underground cable, from the Franklin Converter Terminal Substation located in Franklin, New Hampshire, to the US / Canadian border. The distance from the US / Canadian border in Quebec to the Des Canton Substation, which is where the dc line will terminate, is approximately 48 miles. The proposed dc transmission line is a bipolar, ± 300-kV, constructed of 2x2933 AAAC conductors per pole. A dedicated metallic return circuit will be of a single 2933 AAAC conductor. The underground portion of the dc line will be constructed of 2000 (mm)2 copper conductor. | 2017-12-01 | Approved Withdrawn | 12/31/2013 3/29/2016
NU-13-T22 | 2013-12-01 | Northern Pass Transmission Project | Transmission notification from Northeast Utilities Service Company (“NU”) on behalf of Northern Pass Transmission LLC. for the construction of a new 345-kV ac transmission line, 3132, will be constructed from the Franklin Converter Terminal Substation to the Deerfield 345-kV Substation. Fiber optic cable will be installed on the new transmission line. To accommodate termination of line 3132 at Deerfield, and to prevent transmission line crossings, the existing 345-kV Line 373 (Deerfield Substation to Scobie Pond Substation) will be re-positioned at the 345-kV Deerfield Substation to its own new bay position. Line 3132 will be constructed with two (2) 1590 ACSR, 45/7 stranding, conductors per phase having 18 inch conductor spacers. The transmission towers will be a combination of H-frame, delta, and vertical structures. | 2017-12-01 | Approved Withdrawn | 12/31/2013 3/29/2016
NU-13-T23 | 2013-12-01 | Northern Pass Transmission Project | Transmission notification from Northeast Utilities Service Company (“NU”) on behalf of Northern Pass Transmission LLC. for the construction of the 345-kV Deerfield Substation. The Deerfield 345-kV Substation will be reconfigured to accommodate the new Northern Pass Transmission Project ac transmission line 3132 interconnection, the re-termination of the 345-kV Buxton to Scobie Pond transmission line 391, and the addition of shunt capacitor banks. Four 345-kV shunt capacitor banks, 50 Mvar each, will be installed with four new 345-kV existing Deerfield 345-kV series circuit breakers, (7310 & 7310S, and 851 & 851S), will remain in place. To accommodate termination of the new 345-kV Franklin to Deerfield line, and to prevent transmission line crossings, the existing 373 line (Deerfield Substation to Scobie Pond Substation) will be re-positioned to its own new bay position. The new transmission line 3132 will terminate at the vacated 373 line position. The existing bus protection scheme will be retained and reconfigured to accommodatethe new line terminations. | 2017-12-01 | Approved Withdrawn | 12/31/2013 3/29/2016
NU-13-T24 (Revision available) | 2013-12-01 | Northern Pass Transmission Project | Transmission notification from Northeast Utilities Service Company (“NU”) on behalf of Northern Pass Transmission LLC. for the installation of a 210 Mvar of 345-kV capacitor banks at the 345-kV Scobie Pond Substation. The capacitor banks will be connected to 345-kV Scobie Pond Bus #2 via a five 345-kV, 50 kA circuit breaker. The capacitor banks will be divided into four separate banks, three (3) 60 Mvar banks and one (1) 30 Mvar bank with each bank having its own dedicated circuit breaker. The capacitor banks will be equipped with voltage protection. In addition to the capacitor banks, two 345-kV, 50 kA circuit breakers will be installed. One circuit breaker is to be installed in series with the existing 9126 circuit breaker, and the other circuit breaker installed in series with the 262 circuit breaker. | 2017-12-01 | Approved Withdrawn | 12/31/2013 3/29/2016
NU-13-T25 | 2013-12-01 | Northern Pass Transmission Project | Transmission notification from Northeast Utilities Service Company (“NU”) on behalf of Northern Pass Transmission LLC. for the termination of the 345-kV ac transmission line 391, 345-kV Buxton Substation to 345-kV Scobie Pond Substation at the 345-kV Deerfield Substation. Terminating line 391 at the 345-kV Deerfield Substation creates two separate transmission line circuits; line 391N from 345-kV Buxton Substation to 345-kV Deerfield Substation, and line 391S from 345-kV Deerfield Substation to 345-kVScobie Pond Substation. The 391N line will terminate in its own new bay position at the 345-kV Deerfield Substation. The 391S line will terminate between the existing series circuit breakers 7332 and 3220. New primary and backup transmission line protection schemes will be installed for line 391N and line 391S. In addition to terminating transmission line 391 at the 345-kV Deerfield Substation, the Project requires that the new 391S line section be upgraded to a minimum Long Time Emergency thermal rating of 1470 MVA. To achieve this thermal rating, conductor sag limitations will be removed and the line’s connecting hardware will be replaced so that the line can be operated to 140 degrees C. The existing 345-kw transmission line 391, Buxton Substation to Scobie Pond Substation, is approximately 68 mileslong, (Buxton to ME/NH border ~31 miles, ME/NH border to Scobie Pond ~37 miles). The proposed 345-kV transmission line 391N, 345-kV Buxton Substation to 345-kV Deerfield Substation, will be approximately 50 miles long, (Buxton to ME/NH border ~31 miles, ME/NH border to Deerfield ~19 miles). The proposed 345-kv transmission line 391S, 345-kV Deerfield Substation to 345-kV Scobie Pond Substation, will be approximately 19 miles long. | 2017-12-01 | Approved Withdrawn | 12/31/2013 3/29/2016
NU-13-T26 | 2013-12-01 | Northern Pass Transmission Project | Transmission notification from Northeast Utilities Service Company (“NU”) on behalf of Northern Pass Transmission LLC. for the 345-kV ac transmission line 373, 345-kV Deerfield Substation to 345-kV Scobie Pond Substation, be thermally up-rated to a minimum Long Time Emergency thermal rating of 1435 MVA. To achieve this thermal rating, conductor sag limitations will be removed and the line’s connecting hardware will be replaced so that the line can be operated to 140 degrees C | 2017-12-01 | Approved Withdrawn | 12/31/2013 3/29/2016
NU-13-X03 | 2013-12-01 | Northern Pass Transmission Project | Transmission notification from Northeast Utilities Service Company (“NU”) on behalf of Northern Pass Transmission LLC to increase the 326 Line SPS summer thermal mode setpoint to 1515 MVA. The 326 Line SPS is a NPCC #26 Type 1 SPS. The 326 line summer thermal rating, N/LTE/STE, will be 1358/1515/1515 MVA. The Northern Pass Transmission (NPT) Project SIS determined that the Northeast Utilities’ portion of the 345-kV ac transmission line 326, 345-kV Scobie Pond Substation to the PSNH/NEP border, be thermally upgraded to a minimum summer Long Time Emergency (LTE) thermal rating of 1515 MVA. To achieve this thermal rating, conductor sag limitations would be removed and the conductor’s connecting hardware would be replaced, from the 345-kV Scobie Pond Substation through to the New Hampshire (PSNH)/Massachusetts (NEP) border, so that the line can be operated to 140 degrees C. The 326 Line SPS would require a thermal mode setpoint change from 1430 MVA to 1515 MVA. The 326 transmission line has been upgraded as part of the New Hampshire / Vermont 10 Year Study Plan while the NPT study was nearingcompletion. The present 326 transmission line summer thermal rating (N/LTE/STE) is 1358/1429/1429 MVA. The 326 line’s summer thermal LTE rating is limited by the 326 Line SPS thermal mode set point of 1429 MVA. The present 326 transmission line conductor summer thermal rating, N/LTE/STE, is 1358/1747/1906 MVA. The 345-kV 326 transmissionline distances are Scobie Pond to Lawrence Road ~11 miles and Lawrence to New Hampshire/Massachusetts Border ~7 miles. | 2017-12-01 | Approved Withdrawn | 12/31/2013 3/29/2016
FP-13-G01 | 2013-12-11 | Footprint Generator and Salem Harbor Transmission Project | Generator notification from Footprint Power Salem Harbor Development LP (“FP”) for the construction of two combined cycle (1 gas turbine, one steam turbine) generating units, each with a combined net output of 337.0 MWs (647.0 MWs total net output) at the existing Salem Harbor generation site located in Salem, MA. | 2016-05-31 | Approved | 2014-02-03
NEP-13-T12 | 2013-12-11 | Footprint Generator and Salem Harbor Transmission Project | Transmission notification from New England Power Company (“NEP”)for the construction of a single new 115 kV bay with two circuit breakers at the existing Salem Harbor Substation in support of the Footprint Generator project. | 2016-05-31 | Approved | 2014-02-03
NU-13-T17 | 2013-11-13 | Newtown Substation Circuit Breaker Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the installation of a new 115 kV circuit breaker at the Newtown Substation located in Newtown, CT. splitting the 1760 and 1876 lines into two independent line to provide optimization of the line relay settings for the most reliable operation. Also, tripping and reclosing selectivity will be improved. | 2014-12-31 | Approved | 2014-02-11
NU-13-T31 | 2013-12-03 | Peaslee Substation/Kingston Substation Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the construction of the 115 kV Peaslee Switching Station consisting of a five circuit breakers in a ring bus configuration (PTF). Construction of a 115-kV overhead circuit, approximately 5.5 miles (PTF). Protection and Control additionsand changes at remote terminals, including Scobie Pond, Chester (Pulpit Rock), Brentwood, Great Bay, Kingston (PTF and Non-PTF). Construction of two 115-kV radial overhead circuits, each approximately 1500 feet, to supply a new Unitil 115/34.5-kV Substation (Non-PTF). | 2016-06-01 | Approved | 2014-02-11
UES-13-T01 | 2013-12-03 | Peaslee Substation/Kingston Substation Project | Transmission notification from Unitil Energy Systems (“UES”) for the construction of the 115kV – 34.5kV Kingston distribution stepdown substation, consisting of a two 60MVA stepdown transformers, 115kV circuit breakers, 34.5kV capacitor banks and 34.5kV circuit breakers for transformer and distribution line protection (non-PTF) along with protection and control additions/changes at Kingston (Non-PTF). | 2016-06-01 | Approved | 2014-02-11
NU-13-G33 | 2013-11-12 | Sudbury Landfill Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of Solar Sudbury One LF, LLC for a 1.33 MW solar array located in Sudbury MA and interconnect to the Sudbury Station #342, transformer 110A via the 14 kV distribution circuit 342-H3. | 2014-12-01 | Notification | 2014-02-11
NSTAR-11-T08-Rev.1 | 2013-12-06 | West Barnstable Substation Project Revision | Transmission notification from Northeast Utilities Service Company (“NU”) for the construction of an Construct an eight circuit breaker 115 kV substation at the West Barnstable location and install a new nominally 550 MVA 345/115kV auto-transformer at the new substation. The high side of the auto-transformer will be supplied with a 345 kV line from Carver 345 kV. Also, Line #115 will be brought in and out of the new substation. The name of the substation has been changed from Service Road to West Barnstable and the number of circuit breakers has been increased from 6 to 8. | 2013-09-01 | Notification | 2014-02-11
NSTAR-11-X01-Rev.1 | 2013-12-06 | West Barnstable Substation Project Revision | Transmission notification from Northeast Utilities Service Company (“NU”) to disable the existing Special Protection System (SPS) at the Barnstable 115 kV Substation will be disabled. The SPS will be enabled whenever the new 345 kV line from Carver to the West Barnstable Substation is out of service. Also updating the station name from Service Road to West Barnstable and update the one line diagrams to reflect the additional circuit breakers. | 2012-06-01 | Notification | 2014-02-11
NEP-13-GNF58 | 2013-12-09 | 100 Dupont Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 1.225 MW solar array located in Providence, RI and interconnecting to the Elmwood Substation via the 23 kV, 2228 Feeder. | 2014-01-15 | Notification | 2014-02-11
NEP-13-GNF59 | 2013-12-09 | Synagro Woonsocket Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 2.0 MW solar array located in Woonsocket, RI and interconnecting to the Riverside 108 Substation via the 13.8 kV, 108W55 Feeder. | 2013-11-15 | Notification | 2014-02-11
PLMP-13-13-G01 | 2013-12-04 | Waters River Jet Capacity Revision Project | Generator notification from Massachusetts Municipal Wholesale Electric Company on behalf of Peabody Municipal Light Plant (“PMLP”) for the generation true up of the Waters River Jet generator located in Peabody, MA. Revised unit rating is 47.050 MWs net output. | 2013-12-31 | Notification | 2014-02-11
NU-13-T33 | 2013-12-05 | Holbrook Autotransformer Project | Transmission notification from Northeast Utilities Service Company (“NU”) to replace the existing 345/115 kV, 490 MVA autotransformer at Holbrook Station #478. The existing autotransformer was installed in June 2013 (NU-13-T08). The autotransformer was taken out of service in November 2013 due to high noise and vibration believed to be caused by high harmonics on the 345 kV system. NSTAR plansto temporarily reinstall the “old” Holbrook autotransformer. The temporary replacementautotransformer is rated 400 MVA Summer Normal. | 2013-12-31 | Notification | 2014-02-11
NU-13-G34 | 2013-11-14 | Waltham High School Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) to install a 1.1 MW solar array located in Waltham, MA and interconnecting to the Waltham Station #450, transformer 110A via the 14 kV distribution circuit 363-1369YH1. | 2012-10-18 | Notification | 2014-02-11
NEP-13-T11 | 2013-12-09 | Salem Harbor Cable Replacement Project | Transmission notification from New England Power Company (“NEP”) for the replacement of the S-145E/T-146E underground cables from Salem Harbor to Canal Street with 5000 kcmil Cu. The expected summer LTE rating is 400 MVA per circuit. | 2016-06-01 | Notification | 2014-02-11
NU-13-T32 | 2013-12-03 | Greenwich 115/13.2 kV Substation Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the construction of a new 115/13.2 kV substation located in Greenwich, CT. The GIS substation will include two 115/13.2-kV 60-MVA bulk power transformers, two 115-kV circuit breakers. Two new 115-kV 5000 kcmil XPLE Underground cables from Greenwich to Cos Cob Substation approximately 3.0 miles each. In addition, supporting modifications will be made to the Cos Cob substation will include one new 115 kV circuit breaker and repositioning of the 1750 line termination | 2017-06-01 | Notification | 2014-02-11
NU-13-G35 | 2013-12-12 | Acton Landfill Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) for the construction of a 1.5 MW solar array located in Acton, MA and interconnecting to Maynard Station #416, Bus Section 1 via a 14 kV distribution circuit 416-H4. | 2013-12-18 | Notification | 2014-02-11
MATEP-13-G01 | 2013-10-21 | MATEP Generator Addition Project | Generator notification from MATEP LLC for the installation of a third gas turbine (14.9 MW net output) at the existing MATEP generating plant in Boston, MA. The generator will interconnect through the existing MATEP interconnection with NSTAR via three 13.8 kV tie lines from the NStar Brighton Station #329. | 2017-06-01 | Approved | 2014-01-09
NU-13-G30 | 2013-11-01 | Antares Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) for the installation of a 4.0 MW solar array located in East Lyme, CT and interconnecting to the Flanders 11Y Substation, 23 kV feeder 11Y1-2. | 2013-12-30 | Notification | 2014-01-09
NU-13-G24 | 2013-11-05 | Bluewave Dartmouth Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of Bluewave Capital LLC for the installation of a 3.5 MW solar array in Dartmouth, MA and interconnecting to the NU Industrial Park Substation #636, #112 Transformer 13.2 kV feeder #103. | 2013-11-05 | Notification | 2014-01-09
NU-13-G23 | 2013-11-05 | Bluewave Mattapoisett Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of Bluewave Capital LLC for the installation of a 1.5 MW solar array in Mattapoisett, MA and interconnecting to the NU Crystal Springs Substation #646, 13.2 kV feeder #301. | 2014-03-01 | Notification | 2014-01-09
NU-13-G22 | 2013-11-05 | Bluewave Plymouth Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of Bluewave Capital LLC for the installation of a 4.26 MW solar array in Plymouth, MA and interconnecting to the Manomet Substation #721, 23 kV feeder #71. | 2014-03-01 | Notification | 2014-01-09
NU-13-G18 | 2013-11-05 | Bluewave Holliston Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of Bluewave Capital LLC for the installation of a 3.0 MW solar array in Holliston, MA and interconnecting to the Medway Station 65, 13.8 kV circuit 65-H6. | 2014-06-30 | Notification | 2014-01-09
NU-13-T18 | 2013-11-01 | Torrington Autotransformer Replacement Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the replacement of the 40/53/67 MVA 115/69kV Autotransformer at the Torrington Terminal Substation located in Torrington, CT. | 2013-12-01 | Notification | 2014-01-09
NU-13-G29 | 2013-11-13 | Southern Sky Ravenbrook Landfill Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) for the installation of a 5.0 MW solar array in Carver, MA and interconnecting to the Northeast Utilities #10 23 kV distribution supply line and #930 23 kV distribution circuit out of the West Pond Substation #737. | 2013-12-30 | Notification | 2013-12-10
CED-13-G04 | 2013-10-10 | Merrimack Solar Project | Generator notification from Con Edison Development (“CED”) on behalf of Merrimac Solar, LLC for the installation of a 1.5 MW solar array located in Merrimac, MA and interconnecting to the Mill Street Substation via the 13.8 kV distribution feeder #3. | 2013-12-01 | Notification | 2014-01-09
NEP-13-GNF38 | 2013-11-08 | Smith College Steam Turbine Project | Generator notification from New England Power Company (“NEP”) for the installation of a 3.5 MW gas fueled steam turbine generator located in Northampton, MA and interconnecting to the West Street #901 Substation via the 13.8 kV S100feeder. | 2013-10-15 | Notification | 2014-01-09
NEP-13-GNF48 | 2013-11-08 | Forbes Street Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 3 MW solar array located in East Providence, RI and interconnecting to the Mink Street #7 Substation via the 23 kV 2267feeder. | 2013-11-22 | Notification | 2013-11-21
NEP-13-GNF49 | 2013-11-08 | Solventerra Palmer Project | Generator notification from New England Power Company (“NEP”) for the installation of a 3.5 MW solar array located in Palmer, MA and interconnecting to the Thorndike #523 Substation via the 13.2 kV 523L2feeder. | 2013-12-01 | Notification | 2014-01-09
NEP-13-GNF50 | 2013-11-08 | Solventerra Warren Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 3 MW solar array located in Warren, MA and interconnecting to the Little Rest Road #516 Substation via the 13.2 kV 516L3feeder. | 2013-12-05 | Notification | 2014-01-09
NEP-13-GNF51 | 2013-11-08 | Lowell Landfill Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 1.333 MW solar array located in Lowell, MA and interconnectingto the North Chelmsford #2 Substation via the 13.2 kV 2L4feeder. | 2013-12-27 | Notification | 2014-01-09
NEP-13-GNF52 | 2013-11-08 | EPG Solar Barre I Project | Generator notification from New England Power Company (“NEP”) for the installation of a 2 MW solar array located in Barre, MA and interconnecting to the Barre #604 Substation via the 13.8 kV 604W1feeder. Marvelous | 2013-12-31 | Notification | 2014-01-09
NEP-13-GNF53 | 2013-11-08 | EPG Solar Barre II Project | Generator notification from New England Power Company (“NEP”) for the installation of a 1.5MW solar array located in Barre, MA and interconnecting to the Barre #604 Substation via the 13.8 kV 604W3feeder. | 2013-12-31 | Notification | 2014-01-09
NEP-13-GNF54 | 2013-11-08 | Cabot Beverly Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 2 MW solar array located in Beverly, MA and interconnecting to the North Beverly #18 Substation via the 23 kV 2365feeder. | 2013-12-31 | Notification | 2014-01-09
NEP-13-GNF55 | 2013-11-08 | UGT Renewable Energy Lancaster I Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 2.5 MW solar array located in Lancaster, MA and interconnecting to the Laurel Circle #227 Substation via the 13.8 kV 227W1feeder. | 2013-12-31 | Notification | 2014-01-09
NEP-13-GNF56 | 2013-11-08 | UGT Renewable Energy Lancaster II Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 2.499 MW solar array located in Lancaster, MA and interconnecting to the Laurel Circle #227 Substation via the 13.8 kV 227W3feeder. | 2013-12-31 | Notification | 2014-01-09
NEP-13-GNF57 | 2013-11-08 | Old Wardour Holdings Spencer Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 4 MW solar array located in Spencer, MA and interconnecting to the E5 transmission line via the 69 kV E5feeder. | 2013-12-01 | Notification | 2014-01-09
NEP-13-T10 | 2013-11-12 | East Longmeadow Transformer Replacement | Transmission notification from New England Power Company (“NEP”) for the replacement of the existing T1 69/13.2 kV 6.25 MVA transformer with a 69/13.2 kV 24/32/40 MVA transformer at the East Longmeadow Substation in East Longmeadow, MA. | 2015-02-01 | Notification | 2014-01-09
CMEEC-13-G01 | 2013-09-30 | Backus Hospital Diesel Generator Project | Generator notification from Connecticut Municipal Electric Energy Cooperative (“CMEEC”) for the installation of four 2.49 MW (9.96 MW total net output) diesel generators located in Norwich, CT and interconnecting to the 13.8 kV Dudley Street Substation. | 2014-06-01 | Approved | 2013-10-23
NU-13-G16 | 2013-10-01 | Dartmouth Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) for the installation of two solar farms with two separate points of interconnection to one 13.2kV distribution feeder, with a combined output of 6.75 MW located in Dartmouth, MA. The project will interconnect to the NU Utilities’ #541 13.2kV distribution feeder out of Cross Road Substation #651. | 2013-06-01 | Approved | 2013-10-23
NU-13-G19 | 2013-10-01 | Plymouth Wind Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of Future Generation Wind, LLC for the installation of three 2 MW wind turbines (5.927 MW net output) located in Buzzard’s Bay, MA. Project will interconnect to a new 22.8 kV feeder that will connect to Bus #2 at the Valley Substation #715. | 2014-04-01 | Approved Withdrawn | 10/23/2013 1/16/2024
GMP-11-G01-Rev.1 | 2013-10-01 | Kingdom Wind/Jay Tap Synchronous Condenser Project | Generator notification revision from Green Mountain Power Company (“GMP”) for a wind farm power plant controller (“PPC”) that manages wind farm turbines’ collective reactive capability to control the wind farm’s 46kV collector bus voltage has been introduced to replace the need for the 34.5kV collector-installed +/-2MVAr STATCOM and reduce the Jay Tap 46kV station-installed dynamic reactive requirement from +35MVAr to +25MVAr. | 2013-11-01 | Approved | 2013-10-23
BRE-13-X01 | 2013-10-05 | Fife Brook AVR Project | Transmission notification from Brookfield Renewable Energy Group (“BRE”) for the replacement of the existing Automatic Voltage Regulator (AVR) with a Basler DECS-250 model to the Fife Brook Generator (Asset ID#413). The upgrade will not change the voltage capability of the generation output of the unit. | 2013-11-01 | Approved | 2013-10-23
NU-13-G21 | 2013-10-07 | Pave Paws Wind Project | Generator notification from Northeast Utilities Service Company (“NU”) for the installation of two 1.5 MW (3 MWs net output) wind turbine generators located in Bourne, MA. The units will interconnect to a privately-owned 115/23kV distribution substation owned by the U.S. Air Force, which is interconnected to NU's #122 115kV transmission line between Bourne Switching Station #917 and Sandwich Substation #916. The interconnection of the two new 1.6 MW wind turbines bring the total connected generation at this point of interconnection to 6.2 MW, above the 5 MW threshold in PP5-1 whereby a Level 2 PPA is required. | 2013-10-21 | Approved | 2013-10-23
NEP-13-T09 | 2013-09-12 | Cooks Pond Transformer Replacement Project | Transmission notification from New England Power Company (“NEP”) for the replacement of the T1 and T2 69/13.8 kV 10/12.5 MVA transformers with 69/13.8 24/32/40 MVA transformers and replace the 1T54 and 2T53 69 kV airbreaks with 1200A 69 kV circuit switchers at the Cooks Pond #23 Substation located in Worcester, MA. | 2013-09-01 | Notification | 2013-10-23
NEP-13-GNF24 | 2013-10-04 | NextSun Energy Douglas Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 3.0 MW solar array in Douglas, MA and interconnecting to the Uxbridge #321 Substation via the 13.8 kV 321W1 feeder. | 2013-10-01 | Notification | 2013-10-23
NEP-13-GNF39 | 2013-10-04 | Solventerra North Brookfield Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 2.0 MW solar array located in North Brookfield, MA and interconnecting to the Lashway #525 Substation via the 23 kV 0012 feeder | 2013-10-29 | Notification | 2013-10-23
NEP-13-GNF40 | 2013-10-04 | NextAmp Hubbardson Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 2.8 MW solar array located in Hubbardson, MA and interconnecting to the Westminster #602 Substation via the 13.8 kV 602W2 feeder. | 2013-12-01 | Notification | 2013-10-23
NEP-13-GNF41 | 2013-10-04 | Syncarpha Bolton Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 4.95 MW solar array located in Bolton, MA and interconnecting to the Pratt’s Junction #225 Substation via the 13.8 kV 225W1 feeder. | 2013-12-27 | Notification | 2013-10-23
NEP-13-GNF42 | 2013-10-04 | NextAmp Winchendon Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 1.9 MW solar array located in Winchendon, MA and interconnecting to the East Winchendon #612 Substation via the 13.8 kV 612W3 feeder. | 2013-12-27 | Notification | 2013-10-23
NEP-13-GNF43 | 2013-10-04 | NextAmp Ayers Village Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of 2.0 MW solar array located in Methuen, MA and interconnecting to the Ward Hill #43 Substation via the 23 kV 2376 feeder. | 2013-12-27 | Notification | 2013-10-23
NEP-13-GNF44 | 2013-10-04 | Gardner Solar I Project | Generator notification from New England Power Company (“NEP”) for the installation of a 2.0 MW solar array located in Gardner, MA and interconnecting to the Park Street #601 Substation via the 13.8 kV 601W1feeder. | 2013-12-01 | Notification | 2013-10-23
NEP-13-GNF45 | 2013-10-04 | Fall River Innovation Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 2.85 MW solar array located in Fall River, MA and interconnecting to the Sykes Road #28 Substation via the 13.8 kV 28W50 feeder. | 2013-12-27 | Notification | 2013-10-23
NEP-13-GNF46 | 2013-10-04 | Geospeak Energy Charlton I Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 2.0 MW solar array located in Charlton, MA and interconnecting to the West Charlton #415 Substation via the 13.2 kV 415L1 feeder. | 2013-12-01 | Notification | 2013-10-23
NEP-13-GNF47 | 2013-10-04 | Geospeak Energy Charlton II Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 2.0 MW solar array located in Charlton, MA and interconnecting to the West Charlton #415 Substation via the 13.2 kV 415L2 feeder. | 2013-12-01 | Notification | 2013-10-23
NU-13-G26 | 2013-09-30 | Cottage Street Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of Western Massachusetts Electric Company for the for the installation of a 3.25 MW solar array located in Springfield, MA and interconnecting to the East Springfield 5J Substation via the 13.8 kV 5J13 feeder. | 2013-10-16 | Notification | 2013-10-23
NU-13-T15 | 2013-09-03 | Newtown Substation Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the expansion of the 12 M 115/13.8 kV Newtown Substation located in Newtown, CT to support added load growth in the area. | 2012-05-01 | Notification | 2013-10-23
NU-13-G25 | 2013-09-23 | Hudson Energy Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) on ehalf of Hudson Energy Solar Corp. for the installation of three 500 kW solar arrays (1.5 MWs net output) in Southwick, MA and interconnecting to the Southwick 29A 115 kV Substation via the WEMECO 29A1 13.8 distribution circuit. | 2014-03-01 | Notification | 2013-10-23
CMP-13-T01 | 2013-09-09 | Kimball Road Transformer Project | Transmission notification from Central Maine Power Company (”CMP”) For the installation of a second 120/36 kV 30/56 MVA transformer at the Kimball Road Substation and relocate one of the 115 kV 30 MVAR capacitor banks from Bus 4 to Bus 3. | 2014-12-01 | Approved Withdrawn | 10/2/2013 8/17/2021
NU-13-T16 | 2013-08-06 | Reeds Ferry 115 kV Circuit Breaker Addition Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the installation of a 115 kV circuit breaker at the Reeds Ferry Substation located in Merrimack, NH | 2014-01-01 | Approved | 2013-10-02
AMLP-13-G01 | 2013-08-20 | Ashburnham Solar Project | Generator notification from Massachusetts Municipal Wholesale Electric Company (MMWEC) on behalf of Ashburnham Municipal Light Plant for the installation of a 3 MW solar project located in Ashburnham, MA and interconnecting to Ashburnham Substation 610 via circuit feeder W2. | 2013-10-01 | Notification | 2013-10-02
NU-13-G20 | 2014-09-18 | Future Generation Wind Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of Future Generation Wind LLC for the installation of a 1.976 net MW solar project located in Buzzard’s Bay, MA and interconnecting to the Valley Substation #715 via the 22.8 kV distribution feeder circuit #88. | 2014-04-01 | Notification Withdrawn | 10/23/2013 1/16/2024
CMP-13-T02 | 2014-09-18 | Section 242 Line Rebuild Project | Transmission notification from Central Maine Power Company (“CMP”) for the 1.1 mile rebuild of the 115 kV transmission line Section 242 from 477 ACSR to single pole 1192 ACSR conductor from Haywood Road Substion in Benton, ME to Winslow Substation in Winslow, ME. | 2014-12-01 | Notification | 2013-10-02
NU-13-G04 | 2014-09-09 | Sullivan Ledge New Bedford Solar Project | Generator notification from NSTAR Electric & Gas Company (“NSTAR) on behalf of Blueware Capital and RGS Energy for the installation of a 1.75 MW solar array located in New Bedford, MA and interconnecting to the Highland Avenue Substation #688 via the 13.2 kV distribution feeder #403 | 2014-04-01 | Notification | 2013-10-02
NEP-13-GNF32 | 2014-09-09 | Integrys Lancaster Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Integrys MA Solar LLC for the installation of a 3 MW solar array located in Lancaster, MA and fed by feeder #225W3 out of the Pratt’s Junction Substation #225 | 2013-10-10 | Notification | 2013-10-02
NEP-13-GNF33 | 2014-09-09 | NextSun Energy Rockland Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of NextSun Energy Rockland LLC for the installation of a 2 MW solar array located in Rockland, MA and fed by feeder #93W40 out of the Plymouth Street Substation #90. | 2013-12-04 | Notification | 2013-10-02
NEP-13-GNF34 | 2014-09-09 | Millbury Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Millbury Solar LLC for the installation of a 3 MW solar array located in Millbury, MA and fed by feeder #304W5 out of the Millbury Substation #304. | 2013-12-27 | Notification | 2013-10-02
NEP-13-GNF35 | 2014-09-09 | A Plus International Westborough Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of A Plus International for the installation of a 1.82 MW solar array located in Westborough, MA and fed by feeder #312W4 out of the Westborough Substation #312. | 2013-10-08 | Notification | 2013-10-02
NEP-13-GNF36 | 2013-09-09 | Outland Renewable Energy Spencer Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Outland Renewable Energy LLC for the installation of a 3 MW solar array located in Spencer, MA and fed by feeder #552L1 out of the Meadow Street Substation #552. | 2013-11-13 | Notification | 2013-10-02
NEP-13-GNF37 | 2013-09-09 | Tecta Solar West Bridgewater Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Tecta Solar West Bridgewater LLC for the installation of a 1.5 MW solar array located in West Bridgewater, MA and fed by feeder #797W19 out of the East Bridgewater Substation #797. | 2013-08-15 | Notification | 2013-10-02
NU-13-T14 | 2013-09-12 | Line Z177 Circuit Breaker Addition Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the installation of a 115 kV Circuit Breaker on Line Z177with disconnect switches at the Berlin Substation in Berlin, NH. | 2013-09-01 | Notification | 2013-10-02
NU-13-T13 | 2013-08-09 | Pochassic Transformer Replacement Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the replacement of 115/69 kV transformer at the Pochassic 37R Substation in Westfield, MA. | 2013-09-01 | Approved | 2013-08-28
ERM-13-G01 | 2013-08-09 | Dighton Power Uprate and AVR Project | Generator notification from EquiPower Resources Management (“ERM”) for the capacity increase of Dighton Power from 185.0MWs to 195.0 MWs (Winter Net) and 160.0 MWs to 167.0 MWs (Summer Net). | 2013-10-01 | Approved | 2013-08-28
ERM-13-X01 | 2013-08-09 | Dighton Power Uprate and AVR Project | Transmission notification from EquiPower Resources Management (“ERM”) for the replacement of the existing Dighton Power Automatic Voltage Regulator with newer model. | 2013-10-01 | Approved | 2013-08-28
NEP-13-T08 | 2013-07-31 | Reed Street Transformer Replacement Project | Transmission notification revision from New England Power Company (“NEP”) to replace the existing T4 115-13.2 kV 12/16/20 MVA transformer with one 115-13.2 kV 24/32/40 MVA transformer, replace the 148T4- 115 kV airbreak with one 1200A 115 kV circuit switcher. | 5/2015 | Notification | 2013-08-28
NEP-13-GNF18 | 2013-08-09 | NextAmp Capital Rutland Solar Project | Generator notification from New England Power Company (“NEP) for the installation of a of a 4.999 MW solar generator and interconnecting to the National Grid 13.8 kV distribution system in Rutland, MA via the 55W1 feeder out of the Treasure Valley 55 substation. | 12/2013 | Notification | 2013-08-28
NEP-13-GNF26 | 2013-08-09 | Citizens Enterprises Rehoboth Solar Project | Generator notification from New England Power Company (“NEP) for the installation of a of a 2.0 MW solar array in Rehoboth, MA and interconnecting to the National Grid 13.2 kV distribution system in Rehoboth via the 8L4 feeder out of the Chartley Pond 8 substation. | 12/2013 | Notification | 2013-08-28
NEP-13-GNF27 | 2013-08-09 | Soltas Energy Franklin Solar Project | Generator notification from New England Power Company (“NEP) for the installation of a of a 1.725 MW solar array in Franklin, MA and interconnecting to the National Grid 13.8 kV distribution system in Franklin via the 344W3feeder out of the Beaver Pond 344 substation. | 2013-07-03 | Notification | 2013-08-28
NEP-13-GNF28 | 2013-08-09 | One United West Bridgewater Solar Project | Generator notification from New England Power Company (“NEP) for the installation of a of a 1.75 MW solar array in West Bridgewater, MA and interconnecting to the National Grid 13.8 kV distribution system in West Bridgewater via the 98W44 feeder out of the Belmont St. 98 substation | 2013-10-15 | Notification | 2013-08-28
NEP-13-GNF29 | 2013-08-09 | NextAmp Capital North Kingstown Solar Project | Generator notification from New England Power Company (“NEP) for the installation of a of a 2.0 MW solar array in North Kingstown, RI and interconnecting to the National Grid 12.47 kV distribution system in North Kingstown via the 46F4 feeder out of the Old Baptist Rd. 46 Substation | 2014-01-03 | Notification | 2013-08-28
NEP-13-GNF30 | 2013-08-09 | GLC Development South Easton Solar Project | Generator notification from New England Power Company (“NEP) for the installation of a of a 1.5 MW solar array in South Easton, MA and interconnecting to the National Grid 13.8 kV distribution system in South Easton via the 92W54 feeder out of the Easton 92 substation. | 2013-10-22 | Notification | 2013-08-28
VELCO-13-GNF01 | 2013-07-24 | Williamstown Solar Project | Generator notification from Vermont Electric Company (“VELCO”) on behalf of Gasna 14P, LLC for the installation of a 2.0 MW solar generator and interconnecting to the GMP 70 G4 Circuit in White River Junction, VT. | 2012-12-01 | Notification | 2013-08-28
VELCO-13-GNF02 | 2013-07-24 | South Burlington Solar Project | Generator notification from Vermont Electric Company (“VELCO”) on behalf of SunGen Sharon I, LLC for the installation of a 1.805 MW solar generator and interconnecting to the Line 2904 Pole 1-2 PT in Sharon, VT. | 2012-08-01 | Notification | 2013-08-28
VELCO-13-GNF03 | 2013-07-24 | SunGen Solar I Project | Generator notification from Vermont Electric Company (“VELCO”) on behalf of SunGen Sharon I, LLC for the installation of a 1.805 MW solar generator and interconnecting to the Line 2904 Pole 1-2 PT in Sharon, VT. | 2012-08-01 | Notification | 2013-08-28
VELCO-13-GNF04 | 2013-07-24 | White River Junction Solar Project | Generator notification from Vermont Electric Company (“VELCO”) on behalf of CRL Solar, LLC for the installation of a 2.166 MW solar generator and interconnecting to the GMP 70 G4 Circuit in White River Junction, VT. | 2012-10-19 | Notification | 2013-08-28
VELCO-13-GNF05 | 2013-07-24 | Southern Vermont Energy Park Solar Project | Generator notification from Vermont Electric Company (“VELCO”) on behalf of SVEP Solar Project Company, LLC for the installation of a 2.0 MW solar generator and interconnecting at the Washington Electric Cooperative/Jackson Corners Circuit 3 in Williamstown, VT. | 2012-12-01 | Notification | 2013-08-28
NEP-13-GNF25 | 2013-06-01 | Cornerstone Power Monson Solar Project | Generator notification from New England Power Company (NEP) for the installation of a 3.0 MW solar array in Monson, MA and interconnecting to the Palmer #503 substation via the 13.2 kV 503L2 feeder. | 2013-10-31 | Notification | 2013-08-07
NEP-13-GNF23 | 2013-07-12 | Kearsarge Grafton Solar Project | Generator Notification from New England Power Company (“NEP”) for the installation of a 1.5 MW solar array in Grafton, MA and interconnecting to the Millbury #304 substation via the 13.8 kV 304W6 feeder. | 2013-10-02 | Notification | 2013-08-07
NEP-13-GNF22 | 2013-07-12 | Palmer Solar Project | Generator Notification from New England Power Company (“NEP”) for the installation of a 2.0 MW solar array in Palmer, MA and interconnecting to the Shearers Corner #514 substation via the 13.2 kV 514L1 feeder. | 2013-08-01 | Notification | 2013-08-07
NU-13-G09 | 2013-07-03 | Little Quittacas System Solar Project | Generator Notification from Northeast Utilities Service Company (“NU”) for the installation of a 1.5 MW solar array in Rochester, MA and interconnecting to the NSTAR Industrial Park Substation #636, 13.2 kV feeder #102. | 10/2013 | Notification | 2013-08-07
NU-13-G10 | 2013-07-03 | Little Quittacas System Solar Project | Generator Notification from Northeast Utilities Service Company (“NU”) for the installation of a 2.0 MW solar array located in Rochester, MA and interconnecting to the NSTAR Industrial Park Substation #636, 13.2 kV feeder #102. | 10/2013 | Notification | 2013-08-07
NU-13-T10 | 2013-06-03 | Holliston Temporary Transformer Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the installation of a 115/14.4 kV mobile station transformer and two distribution circuits to establish a new supply in the Western region of NSTAR. The need for this installation is driven by the high annual load growth rate at Purchase Street Station #126. The Project will establish a temporary distribution system supply at transmission ROW 7 and Fiske Street in Holliston. The transformer will be connected to 115 kV line 274-509 which extends from Medway Station 65 to Sherborn Station 274. The temporary transformer will be connected to the 115 kV line with a circuit switcher. | 2013-06-01 | Approved | 2013-07-25
CPEM-12-X01 | 2013-06-06 | Rumford Power System Stabilizer (PSS) Project | System Stabilizer (PSS) Project – Level III (Vote) CPEM-12-X01 – Transmission Notification from CP Energy Marketing (“CPEM”) topermanently install the previously commissioned Power System Stabilizer EX2000 software at the Rumford Power facility. This equipment is currently installed at the Rumford Facility pursuant to a Proposed Plan Application for the temporary installation of the PSS during transmission construction. The PPA for temporary construction was approved by ISO New England on March 30, 2012. Under PPA#CPEM -12-X01, the PSS entered into service in November 2012. This application provides for the permanent installation of the PSS upon the completion of certain area transmission construction in May 2014. | 2014-05-01 | Approved | 2013-07-25
CMP-12-X01-Rev.1 | 2013-06-05 | Rumford Area Temporary SPS Modification Project | Transmission notification from Central Maine Power Company (“CMP”) for the installation of a temporary Rumford Area SPS (NPCC Type III SPS) to reject generation at Rumford Power Associates (RPA) for faults on Sections: 210, 211, 217, 221, 228, 243, 229, various Rumford Area buses, and breaker failure conditions at Kimball Road during the construction of Section 243A as part of the Maine Power Reliability Program (MPRP). This change is required to maintain system stability during the construction period. (This modification adds a fault on the 229 line as a trigger of SPS action). | 2013-09-29 | Approved | 2013-07-25
NEP-13-T05 | 2013-05-10 | Wakefield Substation Project | Transmission notification from New England Power Company (“NEP”) for the construction of a new 115/13.8 kV substation to be named Wallace Substation in Wakefield, MA supplied via taps off of the S-145 & T-146 lines from Tewksbury 22 to Wakefield Junction. | 2014-06-01 | Approved | 2013-07-25
NEP-13-T06 | 2013-05-10 | Wakefield Substation Project | Transmission notification from New England Power Company (“NEP”) for the reconductoring of the 115 kV lines S-145 & T-146 between Wakefield Junctionand the new Wallace Substation in Wakefield, MA. | 2014-06-01 | Approved | 2013-07-25
NU-13-T08 | 2013-06-03 | Holbrook Autotransformer Replacement Project | Transmission notification from Northeast Utilities Service Company (“NU”) to replace the existing 345/115 kV, 400 MVA Autotransformer at Holbrook Station #478.The existing autotransformer is being replaced based on age and operating condition issues. The new autotransformer is rated 490 MVA Summer Normal. | 2013-06-01 | Approved | 2013-06-18
NU-12-T14-Rev.1 | 2013-05-29 | Beseck Substation Variable Shunt Reactor Project | Transmission notification revision from Northeast Utilities Service Company (“NU”) due to a change in the reactor connection at the existing Beseck 9F Substation as part of the GSRP project. Connect a variable 75-150 MVAR shunt reactor to Bus B with a 500-kV 63 kA live tank circuit breaker at Beseck 9F 345-kV switching station | 2013-12-01 | Notification | 2013-07-25
NU-12-T16-Rev.1 | 2013-05-29 | Beseck Substation Variable Shunt Reactor Project | Transmission notification revision from Northeast Utilities Service Company (“NU”) due to a change in the reactor connection at the existing Beseck 9F Substation as part of the NEEWS/CCRP project. Connect a second variable 75-150 MVAR shunt reactor to Bus A with a 500-kV 63 kA live tank circuit breaker at the Beseck 9F 345-kV switching station. | 2017-12-01 | Notification | 2013-07-25
PMLP-13-T01 | 2013-05-09 | Peabody Bus Links Project | Transmission notification from Peabody Municipal Light Plant (“PMLP”) for the installation of a permanent set of bus links into the CS3 115 kV circuit switcher at the Waters River Substation. Installation will allow the Waters River Jet 2 generation asset to be connected to the B154 South 115 kV transmission Line. | 2013-06-20 | Notification | 2013-07-25
NU-13-G17 | 2013-06-03 | Somers Solar Center Project | Generator notification from Northeast Utilities Service Company (“NU”) for the installation of a 4.99 MW solar array in Somers, CT and interconnecting at the Scitico 27H Substation 23 kV distribution feeder on South Rd. Somers, CT. | 2013-09-30 | Notification | 2013-07-25
NU-13-T09 | 2013-05-31 | Somersville Substation Transformer Replacement Project | Transmission notification from Northeast Utilities Service Company (“NU”) to replace the existing 115/14 kV, 65 MVA transformer at Somerville Station #402. The existing transformer failed on May 6, 2013 after experiencing an internal fault. A new 65 MVA transformer was installed and placed in-service May 31, 2013. | 2013-05-31 | Notification | 2014-09-09
NEP-13-GNF16 | 2013-06-07 | Berkeley Real Estate Solar Project | Generator notification from New England Power Company (“NEP) on behalf of Berkeley Real Estate Management LLC for the installation of a 2 MW solar generator and interconnecting to the National Grid 13.2 distribution system in Methuen, MA via the 63L2 feeder out of the West Methuen 63 substation. | 2013-10-01 | Notification | 2013-07-25
NEP-13-GNF17 | 2013-06-07 | OSG Solar Project | Generator notification from New England Power Company (“NEP) On behalf of OSG Solar I-III LLC for the installation of a 2.5 MW solar generator and Interconnecting to the National Grid 13.8 kV distribution system in Orange, MA via the 702W2 feeder out of the Chestnut Hill 702 substation. | 2012-07-06 | Notification | 2013-07-25
NEP-13-GNF19 | 2013-06-07 | Sungen Orange Solar Project | Generator notification from New England Power Company (“NEP) on behalf of SunGen Orange LLC for the installation of a 2 MW solar generator and interconnecting to the National Grid 705W2 feeder via the Wendell Depot 705 substation | 2013-06-07 | Notification | 2013-07-25
NEP-13-GNF20 | 2013-06-07 | Wilson Ground Mount Solar Generator Project | Generator notification from New England Power Company (“NEP) on behalf of GLC-(MA) Wilson LLC for the installation of a 2 MW solar generator and interconnecting to the National Grid 13.2 kV distribution system in Spencer, MA via the 552L1 feeder out of the Meadow St. 552 substation. | 2013-06-20 | Notification | 2013-07-25
NEP-13-GNF21 | 2013-06-07 | Scituate Wind Project | Generator notification from New England Power Company (“NEP)on behalf of Scituate Wind LLC for the installation of a 1.5 MW wind turbine generator and interconnecting to the National Grid 13.8 distribution system in Scituate, MA via the 915W36 feeder out of the Scituate 915 substation. | 2013-03-29 | Notification | 2013-07-25
MMWEC-12-G01-Rev.1 | 2013-06-06 | Chicopee Citizens Enterprise Solar Project | Generation notification revision from Massachusetts Municipal Wholesale Electric Company (“MMWEC”) for the increase in output power from 2.5 MW to 3.0 MWs for the solar array generator located in Chicopee, MA. Project will interconnect to the 24B1 Feeder out of Prospect Street Substation. | 2013-12-01 | Notification | 2013-07-25
UI-13-G01 | 2013-05-07 | Bridgeport Fuel Cell Project | Generator notification from United Illuminating Company (“UI”) on behalf of Bridgeport Fuel Cell Park, LLC for the installation of two 2.8 MW (5.6 MWs net output) fuel cells in Bridgeport, CT and a 13.8 kV interconnection to the Ash Creek Substation. | 2013-12-24 | Approved | 2013-07-02
UI-13-G02 | 2013-05-07 | Bridgeport Fuel Cell Project | Generator notification from United Illuminating Company (“UI”) on behalf of Bridgeport Fuel Cell Park, LLC for the installation of two 2.8 MW (5.6 MWs net output) fuel cells in Bridgeport, CT and a 13.8 kV interconnection to the New Congress I Substation | 2013-12-24 | Approved | 2013-07-02
UI-13-G03 | 2013-05-07 | Bridgeport Fuel Cell Project | Generator notification from United Illuminating Company (“UI”) on behalf of Bridgeport Fuel Cell Park, LLC for the installation of one 2.8 MW fuel cell and one 1.35 MW induction generator in Bridgeport, CT and a 13.8 kV interconnection to the New Congress II Substation. | 2013-12-24 | Approved | 2013-07-02
NU-13-T07 | 2013-05-07 | Haddam Neck 345 kV Variable Shunt Reactor Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the installation of one 75-150 MVAr 345 kV variable shunt reactor at the Haddam Neck 14B Switching Station. Also install a 345-kV circuit breaker (14B-3T-2) at the Haddam Neck 14B Switching Station in the existing spare position between the 14B-2T-2 and 14B-4T-2 circuit breakers, and replace the existing 345-kV circuit breaker (14B-4T-2). | 2014-06-01 | Approved | 2013-07-02
NU-13-G15 | 2013-05-07 | Acushnet RGHRT Braley 1 Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) for the installation of a 1.5 MW solar array in Freetown, MA and interconnecting at 13.3 kV to the #604 distribution circuit and the #102 13.2 kV feeder out of the Industrial Park Substation #636. | 2012-06-15 | Notification | 2013-07-25
NU-13-G12 | 2013-05-07 | Plymouth Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) for the installation of a 4.75 MW solar array in Plymouth, MA and interconnecting at the #73 23 kV distribution feeder out of the Manomet Substation #721. | 2013-05-01 | Notification | 2013-07-02
NU-13-G11 | 2013-05-07 | Plympton Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) for the installation of a 4.0 MW solar array in Plympton, MA and interconnecting at the #51 23kV distribution supply line out of the Brook Street Substation #727. Brook Street Substation #727 is a new 115/23kV bulk distribution station that is currently under construction, with an expected in-service date of June 2013. The new substation was approved under I.3.9 application NSTAR-12-T02. The PV array will not be permitted to interconnect until the new substation is in-service. | 2013-06-01 | Notification | 2013-07-02
NEP-13-GNF07 | 2013-05-10 | Boston Scientific Quincy Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Boston Scientific for the installation of a 1.1 MW solar generator located in Quincy, MA and interconnecting to the #11W3 feeder out of the North Quincy Substation #11. | 2013-11-01 | Notification | 2013-07-02
NEP-13-GNF08 | 2013-05-10 | Narragansett Bay Commission Wind Project | Generator notification from New England Power Company (“NEP”) on behalf of Narragansett Bay Commission for the installation of a 4.5 MW wind turbine generator located in Providence, RI and interconnecting to the #76F8 feeder out of the Point Street Substation #76. | 2012-10-16 | Notification | 2013-07-02
NEP-13-GNF10 | 2013-05-10 | Soltas Athol Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Soltas Athol for the installation of a 3.0 MW solar generator located in Athol, MA and interconnecting to the #702W1 feeder out of the Chestnut Hill Substation # 702. | 2013-07-01 | Notification | 2013-07-02
NEP-13-GNF09 | 2013-05-10 | Soltas Orange Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Soltas Orange for the installation of a 3.0 MW solar generator located in Orange, MA and interconnecting to the #702W3 feeder out of the Chestnut Hill Substation # 702. | 2013-07-01 | Notification | 2013-07-02
NEP-13-GNF11 | 2013-05-10 | Scituate Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of the Town of Scituate for the installation of a 3.0 MW solar generator located in Scituate, MA and interconnecting to the #915W36 feeder out of the Scituate Substation # 915. | 2013-11-01 | Notification | 2013-07-02
NEP-13-GNF12 | 2013-05-10 | Winchendon Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Town of Winchendon for the installation of a 2.0 MW solar generator located in Winchendon, MA and interconnecting to the #612W1 feeder out of the East Winchendon Substation # 612. | 2013-12-01 | Notification Withdrawn | 7/2/2013 11//19/2013
NEP-13-GNF13 | 2013-05-10 | Kearsarge Franklin Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Kearsarge Franklin LLC for the installation of a 3.0 MW solar generator located in Franklin, MA and interconnecting to the #3422W1 feeder out of the South Wrentham Substation # 3422. | 2013-08-01 | Notification | 2013-07-02
NEP-13-GNF15 | 2013-05-10 | Hubbardston Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Hubbardson Solar LLC for the installation of a 2.0 MW solar generator located in Hubbardson, MA and interconnecting to the #604W4 feeder out of the Barre Substation # 604. | 2013-08-01 | Notification | 2013-07-02
NEP-13-GNF14 | 2013-05-10 | KS Solar Five Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of KS Solar Five LLC for the installation of a 4.0 MW solar generator located in Franklin, MA and interconnecting to the #2284 feeder out of the South Wrentham Substation # 2284. | 2013-12-01 | Notification | 2013-07-02
CED-13-G02 | 2013-05-10 | West Greenwich Solar Project | Generator notification from Con Edison Development (“CED”) for the installation of a 1.75 MW solar array in West Greenwich, RI and interconnecting to the Hopkins Hill Substation via the Narragansett 63F6 12.47 kV distribution circuit. | 2013-05-27 | Notification | 2013-07-02
NEP-13-G02 | 2013-04-11 | Monson Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of ten 0.5 MW (5 MWs net output) solar plant in Monson, MA and install a 69/13.2 kV, 5 MVA transformer and switchgear interconnecting to the plant. | 2014-06-01 | Approved Withdrawn | 5/14/2013 10/28/2014
NEP-13-G03 | 2013-04-11 | Monson Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of ten 0.5 MW (5 MWs net output) solar plant in Monson, MA and install a 69/13.2 kV, 5 MVA transformer and switchgear interconnecting to the plant. | 2014-06-01 | Approved Withdrawn | 5/14/2013 10/28/2014
NEP-13-T07 | 2013-04-11 | Monson Solar Project | Transmission notification from New England Power Company (“NEP”) for the construction of a new interconnection substation with a single (1) 69 kV, 2000A, 31.5kA breaker and two (2) 2000A load-break switches in Monson, MA. Construct a 0.1 mile long, 69 kV tap line connecting the interconnection substation to the 69 kV N-14 transmission line. Connect the interconnection substation to the proposed PV plants as specified in NEP-13-G02 and NEP-13-G03. | 2014-06-01 | Approved Withdrawn | 5/14/2013 10/28/2014
NU-13-G13 | 2013-04-08 | Velcro Generator Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of Velcro USA, Inc for the construction of a 5.3 MW gas turbine generator and interconnecting to the PSNH 370X2 circuit that taps into the 370X line which is fed by the 3142 circuit out of PSNH’s Bedford Substation. | 2013-05-31 | Approved | 2013-05-14
NU-13-X01 | 2013-03-19 | Lake Road Type III SPS Generation Rejection Retirement Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the Lake Road Type III SPS Generation Rejection Retirement. In 2016, the Interstate Reliability Project of the New England East-West Solution will be installed. This project includes a second Card to Lake Road transmission line and a Lake Road to West Farnum. The NEEWS 2012 Proposed Plan Application (PPA) studies included delta P calculations for the Lake Road plant. These calculations indicated that with these additional system modifications that under all lines in-service that potential excessive shaft torques was no longer a concern. This was the sole need for the Type III SPS. The other power flow, short circuit and stability simulations performed as part of the NEEWS PPA did not indicate any other need for this SPS. | 121/2016 | Notification | 2013-05-14
NU-13-G14 | 2013-04-10 | NextAmp Hadley Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) for the installation of five 0.50 MW (2.5 MWs net output) solar generator on Hadley, MA and interconnecting to the Amherst 17K 115 kV substation via the WEMECO 17K1 13.8 kV distribution circuit. | 2013-09-01 | Notification | 2013-05-14
NEP-13-GNF01 | 2013-04-10 | Berkshire School Solar Project | Generator Notification from New England Power Company (“NEP”) for the installation of a 1.75 MW solar generator in Sheffield, MA and interconnecting to the 1108W1 feeder out of the Sheffield #8 substation. | 2011-12-10 | Notification | 2013-05-14
NEP-13-GNF02 | 2013-04-10 | Douglas Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 2.0 MW solar generator in Douglas, MA and interconnecting to the 320W2 feeder out of the Whitins Pond Substation #320 in Northbridge, MA | 2012-12-28 | Notification | 2013-05-14
NEP-13-GNF03 | 2013-04-10 | NCCI Gardner Prison Wind Project | Generator notification from New England Power Company (“NEP”) for the installation of a 3.3 MW wind turbine generator in Gardner, MA and interconnecting to the 601W4 feeder out of the Park Street substation # 601. | 2013-04-03 | Notification | 2013-05-14
NEP-13_GNF04 | 2013-04-10 | Sungen Uxbridge Solar Project | Generator notification from New England Power Company (“NEP”) for the ninstallation of a 2.85 MW solar generator in Uxbridge, MA and interconnecting to the 321W4 feeder out of the Uxbridge substation #321. | 2013-05-01 | Notification | 2013-05-14
NEP-13-GNF05 | 2013-04-10 | Sungen Mark Andover Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 2.85 MW solar generator in Andover, MA and interconnecting to the 59L1 feeder out of the East Tewksbury Substation #59 | 2013-05-01 | Notification | 2013-05-14
NEP-13-GNF06 | 2013-04-10 | East Bridgewater Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of a 2.0 MW solar generator in East Bridgewater, MA and interconnecting to the 797W42 feeder out of the East Bridgewater substation #797. | 2013-05-01 | Notification | 2013-05-14
CED-13-G01 | 2013-04-10 | UMass Amherst Solar Project | Generator notification from Con Edison Development Inc. (“CED”) for the installation of four 0.50 MW (2.0 MWs net output) solar generator located in Hadley, MA and interconnecting to the Podick 18G 115 kV substation via WEMECO 18G4 13.8 distribution circuit. | 2013-05-01 | Notification | 2013-05-14
NEP-13-T02 | 2013-03-06 | Mt. Support/Slayton Hill/Michael Ave. Substation Project | Transmission notification from New England Power Company (“NEP”) to loop the 115 kV W-149N line into the Mount Support Substation in Lebanon, NH by building a 2.1-mile tap line from Wilder Switching Junction to Mount Support. Install one 115 kV, 40 kA in-line breaker at Mount Support, creating two separate lines, W-149N between Wilder and Mount Support and W-149 between Mount Support and Slayton Hill. Install equipment for one high speed protection system on W-149N between Wilder and Mount Support and one high speed protection system on resulting W-149 between Mount Support and Slayton Hill. Install a 2nd 24/30/40 MVA, 115/13.8 kV transformer. | 2017-06-01 | Approved | 2013-04-04
NEP-13-T03 | 2013-03-06 | Mt. Support/Slayton Hill/Michael Ave. Substation Project | Transmission notification from New England Power Company (“NEP”) to replace the existing 12/16/20 MVA, 115/13.8 kV transformer T1 at the Slayton Hill Substation in Lebanon, NH with a 33/44/55 MVA unit. Install equipment for one high speed protection system on the W-149 line between Mount Support and Slayton Hill. | 2017-06-01 | Approved | 2013-04-04
NEP-13-T04 | 2013-03-06 | Mt. Support/Slayton Hill/Michael Ave. Substation Project | Transmission notification from New England Power Company (“NEP”) to construct a new Michael Ave Substation in Charlestown, NH by tapping the W-149S line. Install one 15/20/25 MVA, 115/13.2 kV transformer at Michael Ave Substation. | 2013-06-01 | Approved | 2013-04-04
NU-13-G06 | 2013-03-11 | Barnstable Landfill Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of American Capital Energy for the installation of a 1.416 MW PV array, consisting of a AE Solaron 250 kW and a AE Solaron 500 kW inverter interconnected to a 750 kVA 480Y/277 volt to 23kV padmount step-up transformer, and two AE Solaron 333 kW inverters connected to a 2nd 750 kVA 480Y/277 volt to 23kV padmount stepup transformer. Both padmount step-up transformers will connect via 23kV 1/0 AL URD cable through a recloser to NSTAR’s #88 23kV feeder out of Mashpee Substation #946. | 2013-04-01 | Notification | 2013-04-15
NU-13-G07 | 2013-03-11 | Barnstable Landfill Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of American Capital Energy for the installation of a2.0 MW PV array, consisting four (4) AE Solaron 500 kW inverters interconnected to a 2000 kVA 480Y/277 volt to 23kV padmount stepup transformer. The padmount step-up transformer will connect via 23kV 1/0 AL URD cable through a recloser to NSTAR’s #80A 23kV feeder out of Oak Street. | 2013-04-01 | Notification | 2013-04-15
NU-13-T05 | 2013-02-15 | Canton Transformer Replacement Project | Transmission notification from Northeast Utilities Service Company (“NU”) to replace the existing transformer 110B at Canton Station 470 with a new 117/15.12, 37/50/62.5 MVA, OA/FA/FA LTC unit. | 2013-06-01 | Notification | 2013-04-04
NU-13-T06 | 2013-02-15 | Canton Transformer Replacement Project | Transmission notification from Northeast Utilities Service Company (“NU”) to replace the existing transformer 110A at Canton Station 470 with a new 117/15.12, 37/50/62.5 MVA, OA/FA/FA LTC unit. | 2013-06-01 | Notification | 2013-04-04
NU-13-G03 | 2013-03-11 | Dennis Landfill Solar Project | Generator notification from NSTAR Electric and Gas Company (“NSTAR”) on behalf of American Capital Energy for the installation of two (2) separate PV array interconnections of 1.25 MW each, with each 1.25 MW array consisting of two 500 kW Solaron Inverters connected through 500 kVA 480V to 23kV padmount step-up transformers, and a 250 kW Solaron Inverter connected through a 250 kVA 480V to 23kV padmount step-up transformer. Interconnection will be made to the NSTAR’s #92B 23kV distribution feeder out of NSTAR’s Harwich Substation #968. | 2013-03-01 | Notification | 2013-04-15
BHE-13-T01 | 2013-03-05 | Keene Road Transformer Project | Transmission notification from Bangor Hydro Electric Company (“BHE”) for the installation of a new load serving transformer and related facilities at Keene Rd 115kV substation. Transformer is intended to operate in parallel with existing transformer(s) serving the BHE 46kV subtransmission system. | 2014-07-01 | Notification | 2013-04-15
NU-08-T13-Rev. | 2013-02-06 | NEEWS/GSRP Project Revisions | Transmission notification revision from Northeast Utilities Service Company (“NU”) for the Breckwood 115-kV circuit 1322 Reactor Bypass and Open Breckwood Substation 1T Breaker and Maintain Breaker in the Normally Open Position. | 2013-12-01 | Notification | 2013-04-04
NU-08-T35-Rev.1 | 2013-02-06 | NEEWS/GSRP Project Revisions | Transmission notification revision from Northeast Utilities Service Company (“NU”) to add a 2nd High Speed Protection System to the 115 kV Line 1311, Agawam to West Springfield. | 2013-12-01 | Notification | 2013-04-04
NU-08-T36-Rev.1 | 2013-02-06 | NEEWS/GSRP Project Revisions | Transmission notification revision from Northeast Utilities Service Company (“NU”) to add a 2nd High Speed Protection System to the 115 kV Line 1412, Agawam to West Springfield. | 2013-12-01 | Notification | 2013-04-04
NU-13-T01 | 2013-02-26 | Scotia Street Circuit Breaker Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the installation of three new indoor 115 kV gas insulated circuit breakers at the Scotia Street Substation #492 in Boston, MA. One of the new circuit breakers will replace 115/14 kV transformer 110B circuit switcher CS770. The second new breaker will replace 115 kV switch S790 on Brighton Station #329 side of cable 329-513. The third breaker will be added on the Kingston Street Station #514 side of cable 329-513. The Scotia Street 110B transformer protection will be tied into the new 115 kV transformer breaker. The two new circuit breakers on cable 329-513 will initially be used to provide sectionalizing capability and will not be part of 329-513 transmission line protection. A proposed future project will split line 329-513 into two independently relayed lines. | 2013-05-01 | Notification | 2013-04-04
NU-13-G02 | 2013-03-11 | Mashpee Landfill Solar Project | Generator notification from NSTAR Electric and Gas Company (“NSTAR”) on behalf of American Capital Energy for the interconnection of three (3) AE Solaron 500 kW inverters, all connected to a common 1500 kVA 480Y/277 Volt to 23kV padmount step-up transformer. The padmount transformer connects back via 23kV 1/0 AL URD cable and overhead tap through recloser to an existing NSTAR overhead 23kV distribution circuit on Asher’s Path. The point of interconnection will be made to NSTAR’s #88 23kV distribution supply line and #455 circuit out of NSTAR’s Mashpee Substation #946. | 2013-03-01 | Notification | 2013-04-15
NU-13-G08 | 2013-03-01 | Tolland Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) for the installation of seven 500 kW solar generators (3.5 MW net output) located in Tolland, MA and interconnecting to the Blanford 19J 115 kV Substation via WEMECO’s 9J4 23 kV distribution circuit. | 2013-03-26 | Notification | 2013-04-12
FPLE-13-G01 | 2013-01-29 | Weston Hydro Upgrade Project | Generator notification from NextEra Energy Resources (“NextEra”) for the change in net station output at the Weston Hydro Electric Station. Project will uprate Unit 4 by installing a new runner and rehabilitate the generator components. A new AVR will be installed on all 4 units. A new generator step up transformer will be installed and changed to a Wye configuration on the system side (34.5 kV). The units will be connected to the CMP Weston Hydro Solon Substation #5, 34.5 kV. The result of the project upgrade will increase the current claimed capability from 13.2 MWs to 14.8 MWs. | 2014-12-01 | Notification | 2013-04-12
NU-12-T23 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to eliminate the conductor clearance limitations on the 18 mile 345 kV overhead line from Scobie Pond to Lawrence Road NH/MA border. | 2016-12-01 | Approved | 2013-03-07
NU-12-T44 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to install a 2nd 230/115 kV autotransformer at the Littleton Substation. Tap the existing National Grid 230-kV Comerford- Moore C203 line into the Littleton Substation. Build a new 1/2 mile 230-kV transmission line between the C203 tap point and the Littleton Substation and connect it to the new 230/115-kV autotransformer. Install a 230-kV circuit switcher and two 115-kV circuit breakers at Littleton Substation. | 2016-12-01 | Approved | 3/7/2013 12/1/14
NU-12-T45 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to install two +25/-12.5 MVAR 115-kV dynamic devices and two 115-kV circuit breaker at the Saco Valley Substation. Two 115/13.8-kV transformers will also be installed to accommodate the dynamic devices. | 2016-12-01 | Approved | 2013-03-07
NU-12-T46 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to install four 26.6 MVAR 115-kV capacitor banks and two 115-kV circuit breakers at the Webster Substation. | 2016-12-01 | Approved | 2013-03-07
NU-12-T47 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to tap the existing 345-kV Scobie Pond to Amherst 380 line and build a new three circuit breaker 345-kV ring bus. Install a single 345/115-kV autotransformer at the Eagle Substation. Install four 115-kV circuit breakers and four 26.6 MVAR capacitor banks at the Eagle Substation. | 2016-12-01 | Approved | 2013-03-07
NU-12-T48 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to install a new 345-kV series circuit breaker next to the existing 802 circuit breaker for the 380E line at the Scobie Pond Substation | 2016-12-01 | Approved | 2013-03-07
NU-12-T49 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to build a new 6 mile 115-kV transmission line between the Scobie Pond and Huse Road Substations in parallel to the existing I158 Line. Install two 115-kV circuit breakers at the Huse Rd Substation and one circuit breaker at the Scobie Pond Substation. | 2016-12-01 | Approved | 2013-03-07
NU-12-T50 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to eliminate terminal equipment and conductor clearance limitations on the 18 mile 115-kV Deerfield to Garvins G146 line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T51 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to eliminate terminal equipment and conductor clearance limitations on the 12 mile 115-kV Merrimack to Oak Hill P145 line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T52 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to rebuild the existing 15 mile 115-kV Deerfield to Pine Hill D118 line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T53 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to rebuild the existing 3 mile 115-kV Merrimack to Garvins H137 line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T54 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU” to eliminate terminal equipment and conductor clearance limitations on the existing 115-kV Greggs-Rimmon-Eddy J114 line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T55 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to tap the existing 115-kV Garvins-Webster V182 line into the Oak Hill Substation and build a new six 115-kV circuit breaker substation in a “breaker & half” configuration. | 2016-12-01 | Approved | 2013-03-07
NU-12-T56 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to relocate the existing two 36.7 MVAR 115-kV capacitor banks from Bus 2, installing one bank on Bus 1 and the other bank on Bus 3 at the Merrimack Substation. Replace the existing Q171 circuit breaker at the Merrimack Substation. | 2016-12-01 | Approved | 2013-03-07
NU-12-T57 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to rebuild the existing 5 mile 115-kV Eagle – Bridge Street – Power Street K165 Line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T58 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to build a new 13 mile 115-kV transmission line between the Madbury and Portsmouth Substations. Install one 115-kV circuit breaker at both the Madbury and Portsmouth Substations. | 2016-12-01 | Approved | 2013-03-07
NU-12-T59 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to build a new 6 mile 115-kV transmission line between the Scobie Pond and Chester Substations. Build a new five 115-kV circuit breaker substation in a “breaker & half” configuration at the Chester Substation and install one 115-kV circuit breaker at the Scobie Pond Substation. | 2016-12-01 | Approved | 2013-03-07
NU-12-T60 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to install six 13.3 MVAR capacitor banks and two 115-kV circuit breakers at the Schiller Substation. Install a new 115-kV circuit breaker in series with the existing BT10 circuit breaker. Relocate the existing 115-kV Schiller – Portsmouth Z156 line from Bus A to Bus B. | 2016-12-01 | Approved | 2013-03-07
NU-12-T61 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to eliminate terminal equipment and conductor clearance limitations on the 19 mile 115-kV Chester to Great Bay H141 line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T62 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to eliminate terminal equipment and conductor clearance limitations on the 11 mile portion of the 115-kV Scobie Pond to Kingston Tap R193 line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T63 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to install a new 115-kV circuit breaker in series with the R1690 circuit breaker at the Three Rivers Switching Station. | 2016-12-01 | Approved | 2013-03-07
NU-12-T64 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to build a new 2 mile 115-kV transmission line between the Fitzwilliam and Monadnock Substations. Install two 115-kV circuit breakers at the Fitzwilliam Substation and one 115-kV circuit breaker at the Monadnock Substation. | 2016-12-01 | Approved | 2013-03-07
NU-12-T65 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission Notification from Northeast Utilities Service Company (“NU”) to install two 345-kV 26.6 MVAR capacitor banks and one 345-kV circuit breaker at the Amherst Substation. | 2016-12-01 | Approved Withdrawn | 3/7/2013 11/15/2017
NU-12-T66 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to eliminate terminal equipment and conductor clearance limitations on the 11 mile 115-kV Keene to Monadnock T198 line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T67 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to install two 115-kV 13.3 MVAR capacitor banks and one 115-kV circuit breaker at the Weare Substation. | 2016-12-01 | Approved | 2013-03-07
NU-12-T68 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to rebuild the existing 13 mile 115-kV Chestnut Hill to Westport to Swanzey A152 Line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T69 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to rebuild the existing 1 mile 115-kV Chestnut Hill to NH/VT border N186 Line. | 2016-12-01 | Approved | 2013-03-07
NU-12-X02 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to retire the Saco Valley Under Voltage Load Shedding (UVLS) scheme. | 2016-12-01 | Approved | 2013-03-07
NU-12-X03 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to retire the Beebe River Under Voltage Load Shedding (UVLS) scheme. | 2016-12-01 | Approved | 2013-03-07
NU-13-T02 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to upgrade the Power Street Substation in Hudson, NH to NPCC BPS standards. | 2016-12-01 | Approved | 2013-03-07
NEP-12-T19 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission Notification from New England Power Company (“NEP”) to reconductor the 345 kV 326 line section between Sandy Pond in Ayer, MA and MA/NH state border with 2-1113 ACSR. Replace five (5) 345 kV 2000A disconnects with 3000A disconnects. | 2016-12-01 | Approved Withdrawn | 3/7/2013 1/13/2015
NEP-12-T20 | 2013-01-31 | New Hampshire Transmission Upgrades Project | Transmission notification from New England Power Company (“NEP”) to build a new 0.2-mile 230 kV C-203 tap line into the Littleton Substation (NU). | 2016-12-01 | Approved | 2013-03-07
NEP-13-T01 | 2013-01-02 | Shrewsbury Centech Substation Project | Transmission notification from New England Power Company (“NEP”) on behalf of Shrewsbury Electric and Cable Operations (“SELCO”) for the construction of a new 115/13.8 kV substation to be named “Centech” supplied via a loop of the NEP Line E-157 which will contain an inline circuit breaker to sectionalize the existing E-157 line into E-157W (Millbury – Centech) and E-157 (Centech – E Main St), with one transformer on each resulting line. (The third section of E-157 from E Main St to Northboro Rd will be renamed E-157E as part of a separate, previously processed application). | 2014-06-01 | Approved | 2013-03-07
SELCO-13-T01 | 2013-01-02 | Shrewsbury Centech Substation Project | Transmission notification from Shrewsbury Electric and Cable Operations (“SELCO”) for the construction of a new 115/13.8 kV distribution substation with its 115 kV In-line breaker as a looped interconnection into the existing NGRID circuit E-157 which NGRID will split with one segment terminating at the Millbury Substation being designated as 157W, and the segment terminating at the N. Main Street Substation will retain the prior E-157 designation. | 2014-06-01 | Approved | 2013-03-07
NU-13-T02 | 2013-02-04 | Doubling Carver Breaker 862 Project | Transmission notification from NSTAR Electric and Gas Company (“NSTAR”) for the installation of a circuit breaker in series with the Carver 345 kV circuit breaker #862 at the Carver 345 kV Substation. | 2013-12-01 | Notification | 2013-03-07
NEP-11-T07-Rev.1 | 2013-01-22 | Reconductor S-145/T-147 Line Project | Transmission notification revision from New England Power Company (“NEP”) for the reconductor S-145/T-146 115 kV transmission lines from Tewksbury #22 Substation to North Reading Tap. | 2014-06-01 | Notification | 2013-03-07
NU-12-T23 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to eliminate the conductor clearance limitations on the 18 mile 345 kV overhead line from Scobie Pond to Lawrence Road NH/MA border. | 2016-12-01 | Approved | 2013-03-07
NU-12-T44 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to install a 2nd 230/115 kV autotransformer at the Littleton Substation. Tap the existing National Grid 230-kV Comerford- Moore C203 line into the Littleton Substation. Build a new 1/2 mile 230-kV transmission line between the C203 tap point and the Littleton Substation and connect it to the new 230/115-kV autotransformer. Install a 230-kV circuit switcher and two 115-kV circuit breakers at Littleton Substation. | 2016-12-01 | Approved | 2013-03-07
NU-12-T45 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to install two +25/-12.5 MVAR 115-kV dynamic devices and two 115-kV circuit breaker at the Saco Valley Substation. Two 115/13.8-kV transformers will also be installed to accommodate the dynamic devices. | 2016-12-01 | Approved | 2013-03-07
NU-12-T46 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to install four 26.6 MVAR 115-kV capacitor banks and two 115-kV circuit breakers at the Webster Substation. | 2016-12-01 | Approved | 2013-03-07
NU-12-T47 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to tap the existing 345-kV Scobie Pond to Amherst 380 line and build a new three circuit breaker 345-kV ring bus. Install a single 345/115-kV autotransformer at the Eagle Substation. Install four 115-kV circuit breakers and four 26.6 MVAR capacitor banks at the Eagle Substation. | 2016-12-01 | Approved | 2013-03-07
NU-12-T48 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to install a new 345-kV series circuit breaker next to the existing 802 circuit breaker for the 380E line at the Scobie Pond Substation. | 2016-12-01 | Approved | 2013-03-07
NU-12-T49 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to build a new 6 mile 115-kV transmission line between the Scobie Pond and Huse Road Substations in parallel to the existing I158 Line. Install two 115-kV circuit breakers at the Huse Rd Substation and one circuit breaker at the Scobie Pond Substation. | 2016-12-01 | Approved | 2013-03-07
NU-12-T50 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to eliminate terminal equipment and conductor clearance limitations on the 18 mile 115-kV Deerfield to Garvins G146 line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T51 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to eliminate terminal equipment and conductor clearance limitations on the 12 mile 115-kV Merrimack to Oak Hill P145 line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T52 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to rebuild the existing 15 mile 115-kV Deerfield to Pine Hill D118 line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T53 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to rebuild the existing 3 mile 115-kV Merrimack to Garvins H137 line | 2016-12-01 | Approved | 2013-03-07
NU-12-T54 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to eliminate terminal equipment and conductor clearance limitations on the existing 115-kV Greggs-Rimmon-Eddy J114 line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T55 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to tap the existing 115-kV Garvins-Webster V182 line into the Oak Hill Substation and build a new six 115-kV circuit breaker substation in a “breaker & half” configuration. | 2016-12-01 | Approved | 2013-03-07
NU-12-T56 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to relocate the existing two 36.7 MVAR 115-kV capacitor banks from Bus 2, installing one bank on Bus 1 and the other bank on Bus 3 at the Merrimack Substation. Replace the existing Q171 circuit breaker at the Merrimack Substation. | 2016-12-01 | Approved | 2013-03-07
NU-12-T57 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to rebuild the existing 5 mile 115-kV Eagle – Bridge Street – Power Street K165 Line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T58 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to build a new 13 mile 115-kV transmission line between the Madbury and Portsmouth Substations. Install one 115-kV circuit breaker at both the Madbury and Portsmouth Substations | 2016-12-01 | Approved | 2013-03-07
NU-12-T59 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to build a new 6 mile 115-kV transmission line between the Scobie Pond and Chester Substations. Build a new five 115-kV circuit breaker substation in a “breaker & half” configuration at the Chester Substation and install one 115-kV circuit breaker at the Scobie Pond Substation. | 2016-12-01 | Approved | 2013-03-07
NU-12-T60 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to install six 13.3 MVAR capacitor banks and two 115-kV circuit breakers at the Schiller Substation. Install a new 115-kV circuit breaker in series with the existing BT10 circuit breaker. Relocate the existing 115-kV Schiller – Portsmouth Z156 line from Bus A to Bus B. | 2016-12-01 | Approved | 2013-03-07
NU-12-T61 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to eliminate terminal equipment and conductor clearance limitations on the 19 mile 115-kV Chester to Great Bay H141 line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T62 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to eliminate terminal equipment and conductor clearance limitations on the 11 mile portion of the 115-kV Scobie Pond to Kingston Tap R193 line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T63 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to install a new 115-kV circuit breaker in series with the R1690 circuit breaker at the Three Rivers Switching Station. | 2016-12-01 | Approved | 2013-03-07
NU-12-T64 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to build a new 2 mile 115-kV transmission line between the Fitzwilliam and Monadnock Substations. Install two 115-kV circuit breakers at the Fitzwilliam Substation and one 115-kV circuit breaker at the Monadnock Substation. | 2016-12-01 | Approved | 2013-03-07
NU-12-T65 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to install two 345-kV 26.6 MVAR capacitor banks and one 345-kV circuit breaker at the Amherst Substation. | 2016-12-01 | Approved | 2013-03-07
NU-12-T66 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to eliminate terminal equipment and conductor clearance limitations on the 11 mile 115-kV Keene to Monadnock T198 line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T67 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to install two 115-kV 13.3 MVAR capacitor banks and one 115-kV circuit breaker at the Weare Substation. | 2016-12-01 | Approved | 2013-03-07
NU-12-T68 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to rebuild the existing 13 mile 115-kV Chestnut Hill to Westport to Swanzey A152 Line. | 2016-12-01 | Approved | 2013-03-07
NU-12-T69 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to rebuild the existing 1 mile 115-kV Chestnut Hill to NH/VT border N186 Line. | 2016-12-01 | Approved | 2013-03-07
NU-12-X02 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to retire the Saco Valley Under Voltage Load Shedding (UVLS) scheme. | 2016-12-01 | Approved | 2013-03-07
NU-12-X03 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from Northeast Utilities Service Company (“NU”) to retire the Beebe River Under Voltage Load Shedding (UVLS) scheme. | 2016-12-01 | Approved | 2013-03-07
NEP-12-T19 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from New England Power Company (“NEP”) to reconductor the 345 kV 326 line section between Sandy Pond in Ayer, MA and MA/NH state border with 2-1113 ACSR. Replace five (5) 345 kV 2000A disconnects with 3000A disconnectsat the Sandy Pond Substation. | 2016-12-01 | Approved | 2013-03-07
NEP-12-T20 | 2012-11-30 | New Hampshire Transmission Upgrades Project | Transmission notification from New England Power Company (“NEP”) to build a new 0.2-mile 230 kV C-203 tap line into the Littleton Substation (NU). | 2016-06-15 | Approved | 2013-03-07
NU-13-G01 | 2013-01-04 | UMass/Dartmouth Gas Turbine Project | Generator notification from Northeast Utilities Service Company (“NU”) for the construction of a 2.015 MW gas turbine synchronous generator in Dartmouth, MA and interconnecting at the 13.2 kV distribution level to NSTAR #531 13.2 kV feeder out of the Cross Road Substation #651 and under N-1 conditions for loss of that feeder, after actuation of an autothrowover scheme, to the #525 feeder out of Fisher Road Substation #657. | 2013-01-15 | Notification | 2013-01-18
NU-12-T42 | 2012-11-28 | 1990 Line Structure Replacement Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the 20 mile overhead modifications to the 1990 line relaying from Frost Bridge 115 kV Substation in Watertown, CT to Baldwin 115 kV in Waterbury, CT and Stevenson 115 kV Substation in Monroe, CT in order to account for the proposed conductor changes. OPGW fiber will be added between all 3 terminals, the backup relay scheme will be changed to line current differential and the relay settings will be changed. | 2014-12-01 | Approved | 2013-01-18
NU-12-G03 | 2012-12-03 | Antrim Wind Generator and Transmission Project | Generator Notification from Northeast Utilities Service Company (“NU”) on behalf of Antrim Wind Energy, LLC for the construction of eleven 3 MW wind turbine generators (33 MWs total) located in Antrim, NH | 2013-12-01 | Approved Withdrawn | 1/18/2013 8/15/2013
NU-12-T43 | 2012-12-03 | Antrim Wind Generator and Transmission Project | Transmission Notification from Northeast Utilities Service Company (“NU”) on behalf of Antrim Wind Energy, LLC for the construction of a new 115-kV switching station in Antrim, New Hampshire in a ring bus configuration consisting of three 115-kV circuit breakers, associated breaker disconnects, control house, and protection and controls. Split 115 kV Line L163 (between Jackman and Keene Substations) into the new switching station to establish new lines from Jackman Substation to the new Tuttle Hill Switching Station (Line X104, approximate length of 6.5 miles) and from Keene Substation to the new Tuttle Hill Switching Station (Line L163, approximate length of 19.4 miles). | 2013-12-01 | Approved Withdrawn | 1/18/2013 8/15/2013
NEP-12-T15 | 2012-12-05 | Highland Drive Substation Project | Transmission notification from New England Power Company (“NEP”) for the construction of a new Highland Drive 115/13.8kV substation with a single (1) breaker and two (2) 115/13.8kV, 33/44/55 MVA transformers in Cumberland, RI. Loop the new substation into the J16 line by constructing two new 115kV taps each 0.045 miles in length. Reconductor approximately 2.24 miles of the J16 overhead line between Riverside and the new Highland Drive substation. Upgrade the relaying for the J16 at Riverside substation and J16 at Staples substation. | 2014-06-01 | Approved | 2013-01-18
NEP-12-T16 | 2012-12-05 | Highland Drive Substation Project | Transmission notification from New England Power Company (“NEP”) for the upgrade of the 344 and 333 oil circuit breakers to SF6 insulated breakers, aluminum bus conductor and all associated equipment for the V-148S circuit at Robinson Ave. Reconductor the V-148S overhead conductor (approximately 0.02 miles) between the bus and the V-148 tap. | 2014-06-01 | Approved | 2013-01-18
NEP-12-G04 | 2012-11-29 | Little Rest Road Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Mass PV3 LLC for the construction of eighteen 0.5 solar arrays (9 MWs total) located in Warren, MA and interconnecting to the 516L4 13.2 kV feeder out of the Little Rest Road Substation. | 2012-12-01 | Approved | 2013-01-18
NU-12-G06 | 2012-12-03 | Timbertop Wind Project | Generator Notification from Northeast Utilities Service Company (“NU”) on behalf of Timbertop Wind I, LLC for construction and interconnection of seven 2.3 MW wind turbine generators (16.1 MWs net output) located in New Ipswich and Temple Township, NH and interconnecting via a 8.5 mile overhead 34.5 feeder at the project bus on the PSNH 3235 Line and terminating at the Monadnock 34.5 kV Substation | 2014-10-01 | Approved Withdrawn | 1/18/2013 8/15/2013
CPN-12-G01 | 2012-12-04 | Westbrook Energy Center Uprate Project | Generator notification from Calpine Corporation (“CPN”) for a 10 MW uprate at the Westbrook Energy Center turbine generator from 528 MWs to 538 MWs (net output). | 2012-10-20 | Approved | 2013-01-18
UI-12-T01-Rev.1 | 2012-12-06 | 8300 Line Reconfiguration Project | Transmission notification from United Illuminating Company (“UI”) for the reconfiguration of the overhead 115 kV lines, Quinnipiac – Grand Avenue 8300 and Mill River - Grand Avenue 9550 will not be terminated at the Grand Avenue 115 kV Switching Station as proposed in Figure 1: 8300 Line Reconfiguration Project - Grand Avenue Switching Station Configuration as proposed in UI-12-T01. Instead, due to physical construction reasons, the 8300 and 9505 115 kV lines will have their terminations at Grand Avenue Switching Station swapped. | 2012-11-28 | Notification | 2013-01-18
UI-12-T02-Rev.1 | 2012-12-06 | 8300 Line Reconfiguration Project | Transmission notification from United Illuminating Company (“UI”) for the reconfiguration the overhead 115 kV lines, Quinnipiac – Grand Avenue8300 and Mill River - Grand Avenue 9550 will not be terminated at the Grand Avenue 115 kV Switching Station as proposed in Figure 1: 8300 Line Reconfiguration Project –Grand Avenue Switching Station Configuration as proposed in UI-12-T02. Instead, due to physical construction reasons, the 8300 and 9505 115 kV lines will have their terminations at Grand Avenue Switching Station swapped. | 2012-11-28 | Notification | 2013-01-18
UI-12-T03-Rev.1 | 2012-12-06 | 8300 Line Reconfiguration Project | Transmission notification from United Illuminating Company (“UI”) for the reconfiguration the overhead 115 kV lines, Quinnipiac – Grand Avenue 8300 and Mill River - Grand Avenue 9550 will not be terminated at the Grand Avenue 115 kV Switching Station as proposed in Figure 1: 8300 Line Reconfiguration Project –Grand Avenue Switching Station Configuration as proposed in UI-12-T03. Instead, due to physical construction reasons, the 8300 and 9505 115 kV lines will have their terminations at Grand Avenue Switching Station swapped. | 2012-11-28 | Notification | 2013-01-18
NEP-12-GNF08 | 2012-11-29 | Westford Solar Project | Generator notification from New England Power Company (“NEP”) for the construction of four (4) photovoltaic generator units, rated with a total of 4 MW, is proposed to be interconnected into National Grid’s 23 kV distribution system through 23 kV Feeder #2387 in Chelmsford, MA. National Grid’s 23 kV Feeder #2387 is supplied from National Grid North Chelmsford No. 2 Substation located in Chelmsford, MA. The generator will export onto the 23kV distribution system. | 2012-04-05 | Notification | 2013-01-18
NEP-12-GNF13 | 2012-11-13 | 433 Purchase Solar Project | Purchase Solar NG, LLC (NuGen capital Management LLC) for the construction and interconnection of a photovoltaic generating facility, rated 2.5 MW, to National Grid’s distribution system by a single phase lateral off the 19W73 feeder. The 19W73 feeder is a 13.8 kV, 3 phase, 4 wire multi grounded wye circuit supplied by the Dighton substation located in Dighton, MA. | 2012-11-17 | Notification | 2013-01-18
NEP-12-GNF14 | 2012-11-19 | South Barre Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of South Barre Solar LLC for the construction and interconnection of a 1.6 MW photovoltaic generating facility at a ‘greenfield’ stand-alone site at 750 South Barre Rd (Rt 32), Barre, MA. The area where the generator is situated is supplied by the 13.2kV 604W3 feeder from the nearby Barre substation approximately 1,600 circuit feet away. | 2012-11-29 | Notification | 2013-01-18
NEP-12-GNF15 | 2012-11-19 | EPG Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of EPG Solar LLC for the construction and interconnection of a 3 MW PV generation system located near 236 Blackmer Road Southbridge MA. The proposed area for the PV system is served by National Grid’s 13.2kV three-phase, grounded radial feeder 413L3 from Snow Street Substation. | 2012-12-06 | Notification | 2013-01-18
NEP-12-GNF16 | 2012-11-29 | Equity Industrial Wind Project | Generator notification from New England Power Company (“NEP”) on behalf of Equity Industrial Turbines LLC for the construction and interconnection of two wind turbine generator units each rated at 2 MW for a total of 4 MW to National Grid’s 23 kV subtransmission system onto the Company’s #2364 feeder out of the Gloucester Substation. | 2012-12-18 | Notification | 2013-01-18
NEP-12-GNF11 | 2012-12-05 | Constellation Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Constellation Energy for the construction and interconnection of a 2 MW solar array in Uxbridge, MA and customer fed through two 1000 KVA transformers fed by Feeder 321W2 out of the Uxbridge Substation #321. | 2012-08-06 | Notification | 2013-01-18
NEP-12-GNF17 | 2012-12-05 | Wind Energy Development Wind Turbine Project | Generator notification from New England Power Company (“NEP”) on behalf of Wind Energy Development for construction and interconnection of a 1.5 MW wind turbine generator located in North Kingstown, RI and customer fed through NGRID’s 12.47 KV feeder out of the Lafayette Substation #30. | 2012-11-26 | Notification | 2013-01-18
NU-12-G04 | 2012-12-03 | Ludlow Landfill Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) for the construction of four 0.5 MW solar arrays (2 MWs total) located in Ludlow, MA and interconnecting to the Orchard 27A 115 kV Substation via WMECO 27A5 distribution circuit. | 2013-03-01 | Notification | 2013-01-18
NU-12-G05 | 2012-12-03 | NextAmp Capital Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) for the construction of a 2MW solar array located in Whately, MA and interconnecting to the Podick 18G 115 kV Substation via the WMECO 18G8 13.8 distribution circuit. | 2013-05-01 | Notification | 2013-01-18
NSTAR-12-G15 | 2012-12-06 | No Fossil Fuel II Solar Project | Generator notification from NSTAR Electric and Gas Company (“NSTAR”) for the construction of a 4.56 MW solar array located in Dartmouth, MA and interconnecting to the Fisher Road Substation #657 13.2 kV circuit #525. | 2012-12-01 | Notification | 2013-01-18
BHE-08-T08 Rev.1 | 2012-12-05 | Line 66 Rerate Revision Project | Transmission notification revision from Bangor Hydro Electric Company (“BHE”) to rerate the 25 mile overhead 115 kV Line 66 between Rebel Hill Switching Station and the Deblois Switching Station due to an impedance change created by a conductor replacement. | 2013-12-01 | Notification | 2013-01-18
NEP-12-T13 | 2012-10-26 | Pittsfield/Greenfield Area Upgrade Project | Transmission notification from New England Power Company (“NEP”) at the Harriman Substation to install a 115 kV tie breaker and reconductor both 115 kV main busses. Upgrade the 115 kV terminal equipment for E-131 circuit and replace five 115 kV breakers at the substation due to asset condition. Also construct a new 115 kV control house in the 115 kV yard and migrate the 115 kV controls and protection from the existing power house to the new control house. | 2017-06-01 | Approved | 2012-12-07
NEP-12-T14 | 2012-10-26 | Pittsfield/Greenfield Area Upgrade Project | Transmission notification from New England Power Company (“NEP”) to Reconductor the A-127 115 kV line with 2-477 ACCR between the new substation in Erving, MA and Montague Tap. Swap the existing tap to Montague from B-128 Line to the A-127 Line. Reconductor A-127 Tap to Montague with 1590 ACSS. Separate the A-127 and Y-177 lines (existing Double Circuit Tower structures) between Montague and Montague Tap onto independent single circuit structures. | 2017-06-01 | Approved | 2012-12-07
NU-12-T29 | 2012-10-26 | Pittsfield/Greenfield Area Upgrade Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the installation of a 14.4 MVAR 115 kV capacitor bank and 115 kV circuit breaker at the Podick 18G substation located in Amherst, MA | 2016-06-01 | Approved | 2012-12-07
NU-12-T30 | 2012-10-26 | Pittsfield/Greenfield Area Upgrade Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the installation of a 14.4 MVAR 115 kV capacitor bank and 115 kV circuit breaker at the Amherst 17K substation located in Amherst, MA | 2016-06-01 | Approved | 2012-12-07
NU-12-T31 | 2012-10-26 | Pittsfield/Greenfield Area Upgrade Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the installation of a 14.4 MVAR 115 kV capacitor bank and 115 kV circuit breaker at the Cumberland 22B substation located in Greenfield, MA. | 2016-06-01 | Approved | 2012-12-07
NU-12-T32 | 2012-10-26 | Pittsfield/Greenfield Area Upgrade Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the expansion of the Northfield Mountain 16R substation into a breaker-and-a-half arrangement. The 345-kV 6T circuit breaker will be added to complete the existing partial breaker-and-a-half bay, and four additional 345-kV circuit breakers will be installed to form two new bays (one on the east side of the substation and one on the west side). A 345/115-kV autotransformer rated 632/730/862 MVA (normal/LTE/STE) will be installed with a new 115-kV circuit breaker on the low-side. Lines 354, 312 and 381 will be re-terminated into different bay positions. The five new 345-kV circuit breakers will have a nameplate rating of 3000 A and an interrupting capability of 50 kA. The new 115-kV circuit breaker will have a nameplate rating of 4000 A and an interrupting capability of at least 40 kA. | 2016-06-01 | Approved | 2012-12-07
NU-12-T33 | 2012-10-26 | Pittsfield/Greenfield Area Upgrade Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the construction of a new 115-kV station name Erving 38F Switching Station located in Erving, MA, in a ring bus configuration consisting of three (3) 115-kV circuit breakers with a nameplate rating of 3000A and a short-circuit interrupting capability of at least 40 kA. Loop the existing A127 line into the new Erving switching station. | 2016-06-01 | Approved | 2012-12-07
NU-12-T34 | 2012-10-26 | Pittsfield/Greenfield Area Upgrade Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the construction of a new 115-kV line 1604 from Northfield Mountain Substation to the new Erving Switching Station located in Erving, MA. | 2016-06-01 | Approved | 2012-12-07
NU-12-T35 (Revision available) | 2012-10-26 | Pittsfield/Greenfield Area Upgrade Project | Transmission notification from Northeast Utilities Service Company (“NU”) to rebuild the 1361 line from Montague 21C substation to Cumberland 22B substation on separate single-circuit structures. | 2016-06-01 | Approved | 2012-12-07
NU-12-T36 | 2012-10-26 | Pittsfield/Greenfield Area Upgrade Project | Transmission notification from Northeast Utilities Service Company (“NU”) to disconnect the Montague 5T circuit breaker for line Y177 from the 11T/4T position and reconnect it into the 3T/4T position via a 115-kV underground cable. Install a 115-kV 40 kA circuit switcher on the high side of distribution transformer 3X. Provide high speed primary protection for the A127W line (Harriman-Montague-Erving). | 2016-06-01 | Approved | 2012-12-07
NU-12-T37 | 2012-10-26 | Pittsfield/Greenfield Area Upgrade Project | Transmission notification from Northeast Utilities Service Company (“NU”) to remove the sag limitation on the 1512 line from Blandford 19J substation to Granville Junction. | 2016-06-01 | Approved | 2012-12-07
NU-12-T38 | 2012-10-26 | Pittsfield/Greenfield Area Upgrade Project | Transmission notification from Northeast Utilities Service Company (“NU”) to remove the sag limitation on the 1421 line from Pleasant 16B substation to Blandford 19J substation. | 2016-06-01 | Approved | 2012-12-07
NU-12-T39 | 2012-10-26 | Pittsfield/Greenfield Area Upgrade Project | Transmission notification from Northeast Utilities Service Company (“NU”) to reconductor the 1371 line from Woodland 17G substation to Pleasant 16B substation. | 2016-06-01 | Approved Withdrawn | 12/7/2012 1/7/2016
NU-12-T41 | 2012-10-26 | Pittsfield/Greenfield Area Upgrade Project | Transmission notification from Northeast Utilities Service Company (“NU”) to upgrade the thermal rating of the 345 kV Line 381 from the MA/NH border to NH/VT border. The upgrade will result in summer thermal ratings of at least 1358/1626/1760 MVA (normal/LTE/STE). The upgrade is to be achieved by increasing the maximum allowable conductor temperature to 140°C, which involves replacing connectors and raising structures. | 2016-06-01 | Approved | 2012-12-07
NU-12-T27 | 2012-10-25 | South Norwalk Substation Project | Transmission notification from Northeast Utility Service Company (“NU”) to split the 1890E Line from South Norwalk 115 kV Substation to the Sherwood 115 kV Substation and the 1890W Line from South Norwalk 115 kV Substation to the Ely Avenue 115 kV Junction as required to interconnect the CTMEEC South Norwalk 115/13.8 kV Substation Project (CTMEEC-11-T01). | 2013-06-01 | Approved | 2012-12-07
CTMEEC-11-T01 Rev.1 | 2012-10-25 | South Norwalk Substation Project | CTMEEC-11-T01-Rev.1 – Transmission Notification from Connecticut Transmission Municipal Electric Energy Cooperative (“CTMEEC”) on behalf of South Norwalk Electric and Water District for the construction of a new 115/13.8-kV substation located in South Norwalk, CT and NU will interconnect the project to the existing 115-kV system via the 1890 line between CL&P’s Sherwood Substation and the Ely Avenue Tap. | 2013-06-01 | Approved | 1/17/2012 12/7/2012
TERM-12-G01 | 2012-10-16 | Wallingford Capacity Increase Project | Generator notification from Twin Eagle Resource Management (“TERM”) for a 2.7 MW increase in the capacity rating for each of the Wallingford 1-5 gas generators (13.5 MW net increase) located in Wallingford, CT. | 2012-12-31 | Approved | 2012-12-07
NSTAR-12-T16 | 2012-10-16 | 107 Line Reconductor Project | Transmission notification from NSTAR Electric and Gas Company (“NSTAR”) to Reconductor 5.2 miles of overhead 115 kV transmission Line 107 from 4/0 ACSR conductor to 795 kcmil ACSS 54/7 Condor conductor and rebuild/replace ~ 35 wood H- Frame tangent structures, increasing height as necessary for adequate ground clearance and rebuild/replace ~ 11 wood angle or Dead-End structures with three-pole steel structures. | 2013-12-31 | Notification | 2012-12-07
NSTAR-12-T14 | 2012-10-15 | Baker Street/Newton Oil Line and Substation Upgrade Project | Transmission notification from NSTAR Electric and Gas Company (“NSTAR”) for the addition of a dielectric fluid (“oil”) circulation underground pipe for the Baker Street – Newton 292-522 and 292-523 115kV cables with heat exchangers at both Baker St and Newton Highlands substations; At Newton Highland Substation- Install two new 115kV breakers to complete the 115kV ring bus and replace the existing 115/14kV transformers 110A, 110B and 110C with three new 117/15.12kV 37/50/62.5 MVA transformers (75 MVA LTE). | 2013-12-31 | Notification | 2012-12-07
NSTAR-12-T17 | 2012-11-02 | Line 115 Upgrade Project | Transmission notification from NSTAR Electric and Gas Company (“NSTAR”) to upgrade 3.7 miles of existing 115 kV Line #115 from Oak Street area to Barnstable 115 kV substation. to 1113 ACSS conductor resulting in a new LTE rating of 448 MVA. The upgrade is required to mitigate an overload of the Line #115 section following the loss of the 122/120 DCT lines. This upgrade will allow the de-activation of the Barnstable SPS in 2013 following the completion of the Long Term Lower SEMA project. | 2013-12-31 | Notification | 2012-12-07
NSTAR-12-G16 | 2012-11-05 | No Fossil Fuel Solar Project | Generator notification from NSTAR Electric and Gas Company (“NSTAR”) on behalf of No Fossil Fuel for the installation of a 3.04 MW solar array in Marshfield, MA and interconnecting at the 23 kV distribution level to the #21 23 kV feeder out of the NSTAR Marshfield Substation #739 | 2012-11-01 | Notification | 2012-12-07
NSTAR-12-T18 | 2012-10-23 | Hyannis Junction Substation Transformer Project | Transmission notification from NSTAR Electric and Gas Company (“NSTAR”) for the installation of a 3rd 30/40/50 MVA transformer bank at Hyannis Junction, with two 115kV ABB Pass MO circuit breakers with an auto-throw-over scheme. It is further proposed to eliminate the capacity constraint on the #123 line by reconductoring one-mile of 4/0 ACSR with 795 ACSS conductor. | 2014-06-30 | Notification | 2012-12-07
NSTAR-12-T19 | 2012-10-23 | Putnam Station #831 Bus Improvement Project | Transmission notification from NSTAR Electric and Gas Company (“NSTAR”) for replacement of 115 kV load break switch LBS6A at Putnam Station #831 with a normally closed breaker and the swapping the bus positions between the 831-540 line and transformer 110B. | 2013-05-31 | Notification | 2012-12-07
NSTAR-12-T13 | 2012-11-08 | Crystal Springs Substation Transformer Replacement Project | Transmission notification from NSTAR Electric and Gas Company (“NSTAR”) for replacement of an existing 12/16/20 MVA 115/13.2kV bulk distribution transformer with a larger spare 24/32/40 MVA 117/14.4kV bank at Crystal Spring Substation #646. The transformer replacement is required to resolve all facilities in (N-0) capacity | 2012-12-31 | Notification | 2012-12-07
NEP-07-T26-Rev.1 | 2012-10-25 | Adams Substation Project | Transmission notification revision from New England Power Company (“NEP”) for the installation of two new 115 kV, 3000 A, 40 kA breakers to complete the 4-breaker ring bus configuration at the Adams substation. Relocate the E-131 and Q-117 115 kV line terminations at Adams. Swap the positions of the 115/69 kV autotransformer T3 and the 115/23 kV transformer T4. | 2014-12-31 | Notification | 2012-12-07
NEP-12-GNF12 | 2012-10-08 | Varian Semiconductor Wind Project | Generator notification from New England Power Company (“NEP”) on behalf of Varian Semiconductor Equipment Associates for the construction of a 2.5 MW wind turbine generator located in Gloucester, MA and interconnecting to the NGRID 23 kV Feeder #2364 supplied from Gloucester #24 substation. | 2012-11-19 | Notification | 2012-12-07
VELCO-12-T09 | 2012-10-31 | Bennington Line Change Project | Transmission notification from Vermont Electric Company (“VELCO”) to increase the transmission length of the overhead 115 kV K4 Line from Bennington to Adams by approximately one mile (19.51 miles total length). Project is associated with the Bennington Substation relocation (VELCO-10-T06). | 2013-10-31 | Notification | 2012-12-07
VELCO-12-T10 | 2012-10-31 | Bennington Line Change Project | Transmission notification from Vermont Electric Company (“VELCO”) to increase the transmission length of the overhead 115 kV K6 Line from Bennington to Hoosick by approximately one half mile (27.76 miles total length). Project is associated with the Bennington Substation relocation (VELCO-10-T06). | 2013-10-31 | Notification | 2012-12-07
VELCO-12-T11 | 2012-10-31 | Bennington Line Change Project | Transmission notification from Vermont Electric Company (“VELCO”) to reduce the transmission length of the overhead 115 kV Y25 Line from Bennington to Deerfield by approximately one mile (10.19 miles total length). Project is associated with the Bennington Substation relocation (VELCO-10-T06). | 2013-10-31 | Notification | 2012-12-07
NU-12-T40 | 2012-10-25 | East Devon Substation Circuit Breaker Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the installation of a 345 kV circuit breaker at the East Devon 345 kV substation located in Milford, CT. | 2014-06-01 | Notification | 2012-12-07
NU-12-G02 | 2012-10-17 | Hatfield Solar Project | Generator notification from Northeast Utilities Service Company (“NU”) on behalf of Western Massachusetts Electric Company for the construction of four 0.50 MW solar array (2.0 MWs new output) located in Hatfield, MA and interconnecting to the Podick 18G 115 kV substation via the WMECO 18G6 13.8 kV distribution circuit. | 2012-12-01 | Notification | 2012-12-07
NU-12-X01 | 2012-10-04 | Merrimack AVR Replacement Project | Transmission notification from Northeast Utilities Service Company (“NU”) to retrofit the existing Automatic Voltage Regulators (AVR) at the Merrimack Generating Station CT1 and CT2 with identical Basler DECS-200 digital excitation controllers. | 2012-11-01 | Approved | 2012-11-08
UI-12-T21 | 2012-10-04 | Pequonnock Substation | Transmission notification from United Illuminating Company (“UI”) for the control house rebuild at the Pequonnock 115 kV Substation to allow for relay upgrades and the addition of a one cycle protection clearing time delay. | 2015-12-01 | Approved Withdrawn | 11/8/12 9/25/2014
UI-12-T14 | 2012-10-04 | 115 kV Phase Angle Regulator Removal and Mix Avenue Series Reactor Addition Project | Transmission notification from United Illuminating Company (“UI”) for the Sacket 115 kV Phase Angle Regulator (PAR) removal from the Sackett 115 kV Substation in North Haven, CT. | 2015-12-01 | Approved | 2012-11-08
UI-12-T15 | 2012-10-04 | 115 kV Phase Angle Regulator Removal and Mix Avenue Series Reactor Addition Project | Transmission notification from United Illuminating Company (“UI”) for the Mix Avenue 115 kV Series Reactor Addition located at the Mix Avenue 115 kV Substation in Hamden, CT | 2015-12-01 | Approved | 2012-11-08
NEP-12-T06 | 2012-10-04 | Shun Pike Substation Project | Transmission notification from New England Power Company (“NEP”) on behalf of Narragansett Electric Company for the construction of a new Shun Pike Substation that will tap the T-172S line to supply local area load requirements with one dedicated 12/16/20 MVA-rated 115/13.2 kV transformer, and use a 40 kA-rated circuit switcher for transformer protection. In addition, Shun Pike substation will be built to enable future expansion for two115/12.47 kV transformers and an in-line 115 kV circuit breaker. | 2013-12-01 | Approved | 2012-11-08
NEP-12-T07 | 2012-10-04 | Wamesit Substation Project | Transmission notification from New England Power Company (“NEP”) for the construction of a new Wamesit Substation #20 with two 115/13.2 kV 33/44/55 MVA transformers on existing National Grid owned land in Tewksbury, build 115 kV tap lines to the K-137E and J-162 lines and install SCADA-capable, in-line disconnect switches, one on each line, for sectionalizing the 115 kV lines. Primary protection for all transmission line elements, including the tap lines, will be the circuit breakers at remote substations. Circuit switchers rated for 40 kA will be used for local transformer protection. | 2016-12-01 | Approved | 2012-11-08
VELCO-12-T05 | 2012-10-03 | Ascutney Line Change Project | Transmission notification from Vermont Electric Company (“VELCO”) to increase the length of the overhead 115 kV K15 Line from Ascutney to Windsor by one mile increasing total line length to 7.93 miles. Project is associated with the Ascutney Substation Relocation project. | 2013-03-01 | Notification | 2012-11-08
VELCO-12-T06 | 2012-10-03 | Ascutney Line Change Project | Transmission notification from Vermont Electric Company (“VELCO”) to increase the length of the overhead 115 kV K31 Line from Ascutney to Coolidge by one mile increasing total line length to 13.92 miles. Project is associated with the Ascutney Substation Relocation project. | 2013-03-01 | Notification | 2012-11-08
VELCO-12-T07 | 2012-10-03 | Ascutney Line Change Project | Transmission notification from Vermont Electric Company (“VELCO”) to reduce the length of the overhead tap into the 115 kV K149 Line from Bellows Falls to Slayton Hill by one mile reducing total line length to 38.39 miles. Project is associated with the Ascutney Substation Relocation project. | 2013-03-01 | Notification | 2012-11-08
VELCO-12-T08 | 2012-10-03 | Ascutney Line Change Project | Transmission notification from Vermont Electric Company (“VELCO”) to reduce the length of the overhead tap into the 115 kV K174 Line from Ascutney to Webster by one mile reducing total line length to 17.18 miles. Project is associated with the Ascutney Substation Relocation project. | 2013-03-01 | Notification | 2012-11-08
NSTAR-12-G14 | 2012-10-03 | Farmview Estates Solar Project | Generator notification from NSTAR Electric and Gas Company (“NSTAR”) for the installation of a 3.5 MW solar array in Sandwich, MA. Generator will interconnect at the 23 kV distribution level to the #443 distribution circuit and the #81B 23 kV feeder out of the NSATR Sandwich Substation # 916. | 2012-11-30 | Notification | 2012-11-08
NSTAR-12-G12 | 2012-10-03 | Tisbury Landfill Solar Project | Generator notification from NSTAR Electric and Gas Company (“NSTAR”) for the installation of a 1.083 MW solar array in Tisbury, MA. Generator will interconnect at the 23 kV distribution level to the #228 distribution circuit and the #97 23 kV feeder out of the NSTAR Falmouth Substation # 933. | 2013-06-01 | Notification | 2012-11-08
NEP-12-T12 | 2012-10-04 | Line L-164 Derate Project | Transmission notification from New England Power Company (“NEP”) To de-rate the 115 kV L-164 Line sections at the East Dracut Tap (Tewksbury Jct. to East Dracut – 1.9 miles overhead) and North Dracut Tap (East Dracut to North Dracut- 3.8 miles overhead). | 2012-11-05 | Notification | 2012-11-08
VELCO-12-T04 | 2012-09-07 | Bennington 115 kV Capacitor Addition Project | Transmission notification from Vermont Electric Company (“VELCO”) for the installation of two 12.5 MVAR capacitor banks at the Bennington 115 kV Substation located in Bennington, VT. | 2013-10-01 | Approved | 2012-10-09
UI-12-T16 | 2012-08-29 | Bridgeport/New Haven Area Voltage Upgrade Project | Transmission notification from United Illuminating Company (“UI”) for the installation of two 20 MVAR 115 kV capacitor banks at the Mix Avenue 115 kV Substation located in Hamden, CT. | 2015-12-01 | Approved | 2012-10-05
UI-12-T17 | 2012-08-29 | Bridgeport/New Haven Area Voltage Upgrade Project | Transmission Notification from United Illuminating Company (“UI”) for the installation of a 42 MVAR 115 kV capacitor bank at the Grand Avenue 115 kV Substation located in New Haven, CT. | 2015-12-01 | Approved Withdrawn | 10/5/2012 3/6/2014
UI-12-T18 | 2012-08-29 | Bridgeport/New Haven Area Voltage Upgrade Project | Transmission notification from United Illuminating Company (“UI”) for the removal of a 42 MVAR 115 kV capacitor bank at the Sackett 115 kV Substation in North Haven, CT. | 2015-12-01 | Approved | 2012-10-05
UI-12-T19 | 2012-08-29 | Bridgeport/New Haven Area Voltage Upgrade Project | Transmission Notification from United Illuminating Company (“UI”) for the installation of a 20 MVAR 115 kV capacitor bank at the Sackett 115 kV Substation in North Haven, CT. | 2015-12-01 | Approved Withdrawn | 10/5/2012 3/6/2014
UI-12-T20 | 2012-08-29 | Bridgeport/New Haven Area Voltage Upgrade Project | Transmission notification from United Illuminating Company (“UI”) for the installation of two 30 MVAR 115 kV capacitor banks at the Hawthorne115 kV Substation located in Fairfield, CT. | 2015-12-01 | Approved | 2012-10-05
BRP-12-G02 | 2012-09-06 | Granite Reliable Wind Control System Revision Project | Generation notification from Brookfield Renewable Energy Group (“BRP”) on behalf of Granite Reliable Power, LLC for the change in unit leading MVAr capability from 0.0 MVAr to -0.301 MVAr for each of the 33 Granite Reliable Wind Park turbines located in Coos County, NH. in order to improve unit performance and minimize voltage stability concerns. | 2012-12-01 | Approved | 2012-10-09
BRP-12-X01 | 2012-09-06 | Granite Reliable Wind Control System Revision Project | Transmission notification from Brookfield Renewable Energy Group (“BRP”) on behalf of Granite Reliable Power, LLC for the addition of a Power Plant Controller (PPC) to allow the reactive output of the Granite Reliable Wind Farm to respond and control voltage by varying real and reactive power output, frequency and voltage for each of the wind turbine generators. | 2012-12-01 | Approved | 2012-10-09
NU-12-T28 | 2012-09-07 | Memorial Drive 115 kV Cable Project | Transmission notification from Northeast Utilities Service Company (“NU”) on behalf of Chicopee Electric Light Department for the installation of a 0.08 mile underground cable for a section of each of the two circuits (1638 and 1904) to Memorial Drive substation to avoid crossing overhead lines 1702, 1803 and 1601. | 2013-12-01 | Approved | 2012-10-09
CEL-12-T01 | 2012-09-07 | Memorial Drive 115 kV Cable Project | Transmission notification from Chicopee Electric Light (“CEL”) for the construction of a new Chicopee Memorial Drive 115/13.8 kV Substation fed from a loop of planned 115 kV Line No. 1904 (Piper to new Fairmont Substation) and the construction of 0.75 mile of overhead 115kV line for a section of each of the two circuits (1638 and 1904). | 2013-12-01 | Approved | 2012-10-09
NSTAR-12-G09 | 2012-09-05 | Harwich Landfill Solar Project | Generator notification from NSTAR Electric and Gas Company (“NSTAR”) on behalf of American Capital Energy Inc. for the installation of two 2 MW solar arrays (4.0 MWs net output) located in Harwich, MA and interconnecting to the NSTAR Harwich Substation #968, 23 kV feeder #89A. | 2013-06-01 | Notification | 2012-10-09
NSTAR-12-G10 | 2012-09-05 | Chatham Landfill Solar Project | Generator notification from NSTAR Electric and Gas Company (“NSTAR”) on behalf of American Capital Energy Inc. for the installation of a 1.5 MW solar array located in Chatham, MA and interconnecting to the NSTAR 23 kV distribution circuit #606, fed by #95B 23 kV distribution supply feeder from Orleans Substation #975. | 2013-06-01 | Notification | 2012-10-09
NSTAR-12-G11 | 2012-09-05 | Katama Farm Solar Project | Generator notification from NSTAR Electric and Gas Company (“NSTAR”) on behalf of American Capital Energy Inc. for the installation of a 1.083 MW solar array located in Edgartown, MA and interconnecting to the NSTAR Falmouth Substation #933, 23 kV distribution supply feeder #97. | 2013-06-01 | Notification | 2012-10-09
NSTAR-12-T10 | 2012-09-05 | Mashpee Substation Transformer Replacement Project | Transmission notification from NSTAR Electric and Gas Company (“NSTAR”) for the replacement of the existing 20/26/33 MVA 115/23 kV distribution transformer with a new 30/40/50 MVA transformer at the Mashpee Substation #946 located in Mashpee, MA. | 2013-06-01 | Notification | 2012-10-09
NEP-12-G09 | 2012-07-26 | East Brookfield Solar Project | Generator notification from New England Power Company (“NEP”) for the installation of twelve 0.5 MW photovoltaic generators (6.0 MWs net output) and installation of a 69/13.2 kV, 7.5 MVA transformer and switchgear interconnecting to the photovoltaic plant located in East Brookfield, MA. | 2012-12-01 | Approved | 2012-08-27
NEP-12-T09 | 2012-07-26 | East Brookfield Solar Project | Transmission notification from New England Power Company for the construction and interconnection of a new substation with a 69 kV, 2000A, 31.5 kA breaker and two 2000 A load break switches located in East Brookfield, MA. Also construct a new 69 kV tap line connecting the substation to the 69 kV E-5 transmission line and interconnect the substation to the East Brookfield photovoltaic plant. | 2012-12-01 | Approved | 2012-08-27
NEP-12-T05 | 2012-07-25 | Kilvert Street Substation Transformer Installation Project | Transmission notification from New England Power Company (“NEP”) for the installation of a new 115/12.47 kV 33/44/55 MVA transformer at the Kilvert Street Substation located in Warwick, RI. Also install a new circuit switcher inside the substation for T1 protection and a new load break disconnect switch on J-188 Line, to sectionalize the radial line during outages. | 2014-12-01 | Notification | 2012-08-27
NEP-12-T10 | 2012-07-25 | Reconductor L-164 115 kV Line Project | Transmission notification from New England Power Company (“NEP) for the reconductoring of Line L-164 from Tewksbury Junction to West Andover, MA to relieve potential line loading under contingency conditions. | 2012-12-31 | Notification | 2012-08-27
UI-12-T05 | 2012-07-11 | New Haven/Bridgeport Area Thermal Upgrades Project | Transmission notification from United Illuminating Company (“UI”) for the Reconductor/Rebuild of the 2.4 mile overhead 8809A 115 kV Line from the Baird 115 kV Substation in Stratford, CT to the Congress 115 kV Substation in Bridgeport, CT. | 2015-12-01 | Notification | 2012-08-27
UI-12-T06 | 2012-07-11 | New Haven/Bridgeport Area Thermal Upgrades Project | Transmission notification from United Illuminating Company (“UI”) for the Reconductor/Rebuild of the 2.4 mile overhead 8909B 115 kV Line from the Baird 115 kV Substation in Stratford, CT to the Congress 115 kV Substation in Bridgeport, CT. | 2015-12-01 | Notification | 2012-08-27
UI-12-T07 | 2012-07-11 | New Haven/Bridgeport Area Thermal Upgrades Project | Transmission notification from United Illuminating Company (“UI”) for the Baird 115 kV A & B Bus Upgrade at the Baird 115 kV Substation in Stratford, CT. | 2015-12-01 | Notification | 2012-08-27
UI-12-T08 | 2012-07-11 | New Haven/Bridgeport Area Thermal Upgrades Project | Transmission notification from United Illuminating Company (“UI”) for the Reconductor/Rebuild of the 2.9 mile overhead 1610-2 115 kV Line from Glen Lake junction 115 kV in Woodbridge, CT to the Mix Avenue 115 kV Substation in Hamden, CT. | 2015-12-01 | Notification Withdrawn | 2012-08-27
UI-12-T09 | 2012-07-11 | New Haven/Bridgeport Area Thermal Upgrades Project | Transmission notification from United Illuminating Company (“UI”) for the upgrade of the 1685 and 1610 115 kV relaying at the June Street 115 kV substation in Woodbridge, CT. | 2015-12-01 | Notification | 2012-08-27
UI-12-T10 | 2012-07-11 | New Haven/Bridgeport Area Thermal Upgrades Project | Transmission notification from United Illuminating Company (“UI”) for the upgrade of the 1630-3 115 kV relaying at the North Haven 115 kV substation in North Haven, CT. | 2015-12-01 | Notification | 2012-08-27
UI-12-T11 | 2012-07-11 | New Haven/Bridgeport Area Thermal Upgrades Project | Transmission notification from United Illuminating Company (“UI”) for the Reconductor/Rebuild of the 1.67 mile overhead 1630-3 115 kV Line from the North Haven 115 kV substation in North Haven, CT to the Walrec 115 kV substation in Wallingford, CT | 2015-12-01 | Notification Withdrawn | 8/27/2012 3/6/2014
UI-12-T12 | 2012-07-11 | New Haven/Bridgeport Area Thermal Upgrades Project | Transmission notification from United Illuminating Company (“UI”) for the Reconductor/Rebuild of the 1.4 mile overhead 88005A 115 kV Line from the Milvon 115 kV substation in Milford, CT to the Devon Tie 115 kV Switching Station in Milford, CT. | 2015-12-01 | Notification | 2012-08-27
UI-12-T13 | 2012-07-11 | New Haven/Bridgeport Area Thermal Upgrades Project | Transmission notification from United Illuminating Company (“UI”) for the Reconductor/Rebuild of the 1.4 mile overhead 89005B 115 kV Line from the Milvon 115 kV substation in Milford, CT to the Devon Tie 115 kV Switching Station in Milford, CT. | 2015-12-01 | Notification | 2012-08-27
BRP-12-G01 | 2012-07-03 | Granite Reliable Wind Farm Revisions | Generator notification from Brookfield Renewable Power Inc. (“BRP”) to revise the limit of the leading MVar capability of the Granite Reliable Wind Farm for each turbine from 0.0875 MVar to 0.0 MVar for an overall reduction of 28.9 MVar change to the generating resource. The 99 MW Granite Reliable Wind farm is interconnected to the PSNH Coos 115 kV transmission loop located in Drummer, NH | 2012-07-20 | Approved | 2012-07-25
NSTAR-12-T06 | 2012-06-04 | Hartwell 115 kV Shunt Capacitor Installation Project | Transmission notification from NSTAR Electric and Gas Company (“NSTAR”) for the installation of a new 115 kV, 36.7 MVAR shunt capacitor at Hartwell Substation. The new capacitor bank is needed to support sagging transmission voltages in the Burlington - Hartwell load area for contingencies that result in the loss of 115 kV line 533-508 between Lexington and Hartwell. The main project components consist of the 115 kV, 36.7 MVAR mobile capacitor and a 115 kV circuit breaker with a Synchronous Switching Controller. | 2012-11-01 | Approved | 2012-08-06
BHE-12-G01 | 2012-05-29 | Pisgah Wind Farm Generation and Transmission Project | Generation notification from Bangor Hydro Electric Company (“BHE”) for the construction of five 1.815 MW wind turbine generators (9.075 MWs net) on Pisgah Mountain, Clifton, ME and interconnecting via the BHE 115 kV Line 66 as a tap. | 2013-07-01 | Approved | 2012-08-06
BHE-12-T04 | 2012-05-29 | Pisgah Wind Farm Generation and Transmission Project | Transmission notification from Bangor Hydro Electric Company (“BHE”) To interconnect the Pisgah Wind Farm via a 0.04 mile overhead tap to Line 66 to the Pisgah collector substation high side breaker. | 2013-09-01 | Approved | 2012-08-06
NSTAR-12-G07 | 2012-07-06 | Canton Landfill Solar Project | Generator notification from NSTAR Electric and Gas Company (“NSTAR”) for the construction of three 1 MW (3 MWs net) solar generators interconnecting to the Canton Station #470, Transformer 110A via distribution circuit 470-H4 located in Canton, MA. | 2012-07-18 | Notification | 2012-08-06
NSTAR-12-G08 | 2012-07-06 | Canton Landfill Solar Project | Generator notification from NSTAR Electric and Gas Company (“NSTAR”) for the construction of two 1 MW (2 MWs net) solar generators interconnecting to the Canton Station #470, Transformer 110C via distribution circuit 470-H8 located in Canton, MA. | 2012-07-18 | Notification | 2012-08-06
MMWEC-12-G03 | 2012-06-14 | Ipswich Wind II Project | Generator notification from Massachusetts Municipal Wholesale Electric Company (“MMWEC”) for the construction of a 2.0 MW wind turbine generator located in Ipswich, MA and interconnecting to the Fowlers Lane Substation #5 supplied from the High Street Substation #4 supplied by a 23 kV Line 2372 or Line 2394 feed from the National Grid 115 kV King Street Substation in Groveland, MA. | 2012-09-30 | Notification | 2012-08-06
FPLE-12-G01 | 2012-07-05 | Skelton Hydro Capacity Increase Project | Generator notification from FPL Maine Hydro (“FPLE”) for 2.4 MW capacity increase to the Skelton Hydro generating station (Asset #569) by replacement of the two generator turbines, control switchgear, and station service wiring. The units will be interconnected to the CMP Louden Substation 34.5 kV bus in York County, ME through a 34.5 kV generator lead. | 8/12/2013 12/26/2013 | Notification | 2012-08-06
FW-12-G02 | 2012-06-18 | Oakfield Wind Farm and Transmission Project | Generator notification from First Wind (“FW”) on behalf of Evergreen Wind Power II, LLC for construction of forty eight 3.075 MW wind turbine generators (147.6 MWs Net) located in Oakfield, ME. And interconnecting to the BHE Keene Road 345 kV Substation. | 2014-08-31 | Approved | 2012-07-17
FW-12-T02 | 2012-06-18 | Oakfield Wind Farm and Transmission Project | Transmission notification from First Wind (“FW”) on behalf of Evergreen Wind Power II, LLC for the construction of a Oakfield collector substation, Keene Rd 115/345kV new autotransformer , 59 mile overhead 115 kV transmission line between Keene Rd and the new Oakfield collector substation, two 115 kV 25 MVAR capacitor banks, associated circuit breakers and switchgear, and two 115/34.5 kV under load tap changing transformers located at the collector substation. | 2014-08-31 | Approved | 2012-07-17
BHE-12-T03 | 2012-06-18 | Oakfield Wind Farm and Transmission Project | Transmission notification from Bangor Hydro Electric Company (“BHE”) for bus expansion, protection updates and new 345 kV breaker to accommodate new generator transformer and lead interconnection | 2014-08-31 | Approved | 2012-07-17
NU-12-T25 | 2012-06-04 | South End 115 kV Cable Project | Transmission notification from Northeast Utilities Service Company for the installation of a 1.5 mile underground 115 kV cable from the Glenbrook 115 kV substation to the South End 115 kV substation located in Stamford, CT. | 2014-12-31 | Approved | 2012-07-17
CTMEEC-12-T01 | 2012-06-13 | Fitch Street Substation Project | Transmission notification from Connecticut Transmission Municipal Electric Energy Cooperative (“CTMEEC”) for the construction of a new 115 kV to 27.6 kV Substation on behalf of Third Taxing District (TTD) Electric Department. The substation will be energized via the CL&P 1416 Line between Compo and Darien 115 kV Substations. The new substation will include two 115/27.6 kV transformers along with protective devices and systems. | 2013-12-31 | Approved | 2012-07-17
NU-12-T26 | 2012-06-13 | Fitch Street Substation Project | Transmission notification from Northeast Utilities Service Company (“NU”) modification to the exiting 115-kV 1416 line between CL&P’s Darien and Compo Substations. The modification is in support of the Connecticut Transmission Municipal Electric Energy Cooperative (dba TRANSCO), proposed installation of a new 115/27.6 kV substation that TRANSCO is proposing on behalf of the Third Taxing District (TTD) in Norwalk, CT. | 2013-12-31 | Approved | 2012-07-17
MMED-03-T01-Rev.1 | 2012-06-05 | East Mansfield Substation and Transformer Project Revision 1 | Transmission notification from Mansfield Municipal Electric Department (“MMED”) for the construction of a new 115/13.8 kV substation located in Mansfield, MA. The station was to consist of one 115/13.8 kV, 24/32/40 MVA transformer. The substation transformer was to be connected to the 115 kV system via a circuit switcher to a single circuit extension of Line E1. The design has been modified to incorporate two 115/13.8 kV, 24/32/40 MVA transformers. Also the single phase line extension to the East Mansfield substation from Easton Station #92 is now labeled as the A24 Line. | 2012-07-01 | Notification | 2012-07-17
NSTAR-12-T09 | 2012-05-21 | Reconductor 211-508 115 kV Line Project | Transmission notification from NSTAR Electric and Gas Company (“NSTAR”) for the reconductoring of the 211-508 115 kV Line from Woburn to Burlington. | 2013-01-31 | Notification | 2012-07-17
VELCO-12-T03 | 2012-05-30 | Vernon Road Breaker Addition Project | Transmission notification from Vermont Electric Company (“VELCO”) on behalf of Central Vermont Public Service for the installation of three new 115 kV circuit breakers at the Vernon Road Substation | 2013-06-01 | Notification | 2012-07-17
NSTAR-12-T08 | 2012-06-04 | West Medway Breaker Addition | Transmission notification from NSTAR Electric and Gas Company (“NSTAR”) for the addition of a new 345 kV 63 kA IC 3000 amp breaker in series with the existing 345 kV breaker #106 at West Medway. | 2012-07-17 | Notification | 2012-07-17
VELCO-12-G01 | 2012-04-18 | Grandpa’s Knob Wind Farm and Transmission Project | Generator notification from Vermont Electric Power Company (“VELCO”) on behalf of Grandpa’s Knob Windpark, LLC,for construction of twenty 2.5 MW Nordex N100 wind turbine generators (50 MWs Net) located in West Rutland, VT and interconnecting to the West Rutland 115 kV Substation. | 2013-12-31 | Approved Withdrawn | 5/29/2012 5/23/2014
VELCO-12-T01 | 2012-04-18 | Grandpa’s Knob Wind Farm and Transmission Project | Transmission notification from Vermont Electric Power Company (“VELCO”) for the construction of two miles of overhead 115 kV line from the Grandpa’s Knob wind farm to the West Rutland Substation. | 2013-12-31 | Approved Withdrawn | 5/29/2012 5/23/2014
VELCO-12-T02 | 2012-04-18 | Grandpa’s Knob Wind Farm and Transmission Project | Transmission notification from Vermont Electric Power Company (“VELCO”) for the construction of a new 115 kV substation connecting the Grandpa’s nob wind farm to the 115 kV system via a 115/34.5 kV step up transformer. | 2013-12-31 | Approved Withdrawn | 5/29/2012 5/23/2014
NEP-07-T23 Rev.1 | 2012-04-25 | A-127W 115 kV Line Reconductor Rev. 1 | Transmission notification from New England Power Company (“NEP”) to reconductor portions of the A-127W line with 477 ACCR conductor (instead of 795 ACSS as in the original application) for 7 miles from Tower 510 to Paxton and 10 miles from Wendell Depot to the Cabot Taps. Additionally, due to the reconductoring on both the A-127W and B-128W lines as described in NEP-11-T01 the proposed swapping of the Cabot/Montague tap from the B-128 Line to the A-127 Line is no longer required, and switch 2713 will be replaced with a 2000A switch rather than being removed from the A-127W line. | 2014-11-01 | Approved | 2012-05-30
MMWEC-12-T01 | 2012-04-10 | Denton-Lovell Substation Project | Transmission notification from Massachusetts Municipal Wholesale Electric Company (“MMWEC”) to upgrade the Denton-Lovell Substation by replacing the existing 15 kV distribution switchgear with new 15 kV switchgear. Replacement of both power transformers (115 kV/13.8 kV with new units rated at 24/32/40 MVA. Removal of the existing 115 kV bus tie disconnect switches and replacement of the existing circuit switchers with new 115 kV disconnect switches and circuit breakers | 2012-12-01 | Notification | 2012-05-29
MMWEC-12-G01 | 2012-04-10 | Chicopee Citizens Enterprise Solar Project | Generation notification from Massachusetts Municipal Wholesale Electric Company (“MMWEC”) for the construction of a 2.5 MW solar array generator located in Chicopee, MA. Project will interconnect to the 24B1 Feeder out of Prospect Street Substation. | 2012-05-01 | Notification | 2012-05-30
MMWEC-12-G02 | 2012-04-10 | Shrewsbury-Cherry Street Solar Project | Generation notification from Massachusetts Municipal Wholesale Electric Company (“MMWEC”) for the construction of a 2.5 MW solar array generator located in Shrewsbury, MA. Project will interconnect to the SELCO Feeder Circuit R13-1 from Rolf Avenue Substation connected to the NGrid P142 line. | 2012-07-01 | Notification | 2012-05-30
MMED-03-T01-Rev.1 | 2012-05-07 | East Mansfield Substation and Transformer Project Revision 1 | Transmission notification from Mansfield Municipal Electric Department (“MMED”) for the construction of a new 115/13.8 kV substation located in Mansfield, MA. The station was to consist of one 115/13.8 kV, 24/32/40 MVA transformer. The substation transformer was to be connected to the 115 kV system via a circuit switcher to a single circuit extension of Line E1. The design has been modified to incorporate two 115/13.8 kV, 24/32/40 MVA transformers. Also the single phase line extension to the East Mansfield substation from Easton Station #92 is now labeled as the A24 Line. | 2012-07-01 | Notification | 2012-07-17
NSTAR-12-T05 | 2012-04-25 | Scotia Street Station 115 kV Upgrade Project | Transmission notification from NSTAR Electric and Gas Company (“NSTAR”) for the installation of three new indoor 115 kV gas insulated circuit breakers at Scotia Street substation #492 in Boston MA. The project is presently under construction due to the need to repair station damage resulting from the Scotia Street station fire that occurred on 3/13/2012. One of the new circuit breakers will replace 115/14 kV transformer 110A circuit switcher CS771. The second new breaker will replace 115 kV switch S791on Brighton Station #329 side of cable 329-512. The third breaker will be added on the Kingston Street Station #514 side of cable 329-512. The Scotia Street 110A transformer protection will be tied into the new 115 kV transformer breaker. The two new circuit breakers on cable 329-512 will initially be used to provide sectionalizing capability and will not be part of 329-512 transmission line protection. A proposed future project will split line 329-512 into two independently relayed lines. The main project component is the Gas Insulated Switchgear consisting of three 115 kV breakers and associated vdisconnects and grounding switches. | 2012-06-01 | Notification | 2012-05-30
NEP-08-T44-Rev.1 | 2012-04-03 | NEEWS Interstate Analysis Project | Transmission notification from New England Power Company (“NEP”) to install a new 341 West Farnum to Connecticut/Rhode Island Border 345 kV Line. PPA | 2015-12-01 | Approved | 2012-05-04
NEP-08-T45-Rev.1 | 2012-04-03 | NEEWS Interstate Analysis Project | Transmission notification from New England Power Company (“NEP”) to install a new 366 Millbury to West Farnum 345 kV Line. | 2015-12-01 | Approved | 2012-05-04
NEP-08-T48-Rev.1 | 2012-04-03 | NEEWS Interstate Analysis Project | Transmission notification from New England Power Company (“NEP”) to expand, reconfigure and upgrade the 345 kV Millbury Substation and upgrade the 1402, 302 and 314 breakers with new 4000A 50 kA breakers. | 2015-12-01 | Approved | 2012-05-04
NEP-12-T01 | 2012-04-03 | NEEWS Interstate Analysis Project | Transmission notification from New England Power Company (“NEP”) to rebuild and reconductor the 345 kV 328 Line from Sherman Road Switching Station in Burrillville, RI to West Farnum Substation in Smithfield, RI. | 2015-12-01 | Approved | 2012-05-04
NEP-12-T02 | 2012-04-03 | NEEWS Interstate Analysis Project | Transmission notification from New England Power Company (“NEP”) to construct a new Sherman Road Air Insulated Substation and replace the existing ring bus with a new two bay breaker and half open air switching station with a double tie breaker in one of the bays, with breakers rated at 4000A continuous and 50kA interrupting capability. This construction is required as Sherman Road requires substantial upgrades due to changes in the thermal loadings, short circuit fault duty duties. | 2015-12-01 | Approved | 2012-05-04
NEP-12-T03 | 2012-04-03 | NEEWS Interstate Analysis Project | Transmission notification from New England Power Company (“NEP”) to upgrade the West Farnum 115 kV Substation and double the 1713 tie breaker and upgrade the 115kV station to comply with current BPS standards. The addition of this new breaker constitutes “significant work” and therefore will require the station be brought to current BPS standards. | 2015-12-01 | Approved | 2012-05-04
NEP-08-T52-Rev.1 | 2012-04-03 | Rhode Island Reliability Projects | Transmission notification from New England Power Company (“NEP”) to expand and reconfigure the 345 kV West Farnum Substation. This includes the expansion required for all three of the new 345 kV lines terminating at the substation. Revision is due to change in final configuration of 345kV station changed to facilitate line crossings and entry points. | 2012-05-20 | Approved | 2012-05-04
NEP-08-T53-Rev.1 | 2012-04-03 | Rhode Island Reliability Projects | Transmission notification from New England Power Company (“NEP”) to install a third 345/115kV auto transformer at Kent County and expand and reconfigure 345/115 kV Substation and build to BPS standards. Transformer nameplate rating 269/358/448 MVA, make new 345 kV breakers 3000A, 50 kA breakers and new 115 kV breakers 3000A, 63 kA breakers. Revision is due to additional 115kV breaker added on 115kV side of existing T3 transformer to mitigate an N-1-1 contingency voltage concern. | 2011-11-20 | Approved | 2012-05-04
NEP-08-T56-Rev.1 | 2012-04-03 | Rhode Island Reliability Projects | Transmission notification from New England Power Company (“NEP”) to upgrade 115 kV Franklin Square terminal equipment. Discussions with breaker manufacturer revealed that by adding breaker capacitors at various locations on the bus work the breaker short circuit capacity would be increased from 40kA to 50 kA instead of the original plan of upgrading the 115 kV Franklin Square terminal equipment (including all 115 kV breakers to 3000A, 63 kA). | 2012-05-20 | Approved | 2012-05-04
NU-08-T11-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to rebuild the 115-kV Line 1230 from Agawam 16C Substation to Piper 21N Substation. Revision is because the conductor is being revised from 1590 kcmil ACSR to 1272 kcmil ACSS based on the new NU standard. The ratings of both conductors are comparable. | 2013-12-01 | Approved | 2012-05-04
NU-08-T12-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to rebuild the 115-kV Line 1314 from Agawam 16C Substation to Chicopee 18L Substation. Revision is because the conductor is being revised from 1272 kcmil ACSR to 1272 kcmil ACSS based on the new NU standard. | 2013-12-01 | Approved | 2012-05-04
NU-08-T13-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the 115-kV circuit 1322 from East Springfield 5J Substation to Breckwood 20A Substation to have the existing series reactors bypassed. Revision is the bypass switch will be a circuit switcher. | 2013-12-01 | Approved | 2012-05-04
NU-08-T14-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to rebuild the 115-kV Line 1426 from Cadwell 50F Switching Station to Orchard 27A Substation. Revision is because the conductor is being revised from 1272 kcmil ACSR to 1272 kcmil ACSS based on the new NU standard. | 2013-12-01 | Approved | 2012-05-04
NU-08-T15-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to reconductor / rebuild the 115-kV Line 1481 from Ludlow19S Substation to Cadwell 50F Switching Station. Revision is because the conductor is being revised from 2x795 kcmil ACSR to 1590 kcmil ACSS to allow existing structures to be used. The two conductor sizes have comparable ratings. | 2013-12-01 | Approved | 2012-05-04
NU-08-T16-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to reconductor the 115-kV Line 1552 from Ludlow 19S Substation to Orchard 27A Substation. Revision is because the conductor is being revised from 1590 kcmil ACSR to 1272 kcmil ACSS based on the new NU standard. The ratings of both conductors are comparable and the ACSS conductor can be placed on the existing structures. | 2013-12-01 | Approved | 2012-05-04
NU-08-T17-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to separate the 115-kV three terminal line 1723 (Fairmont-Piper-East Springfield), and rebuild/construct a two terminal line #1904, from Fairmont 16H switching station to Piper 21N substation. Revision is because the conductor is being revised from 1590 kcmil ACSR to 1272 kcmil ACSS based on the new NU standard. The ratings of both conductors are comparable. Also, the line number changed from 1601 to 1904. | 2013-12-01 | Approved | 2012-05-04
NU-08-T18-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to separate the 115-kV three terminal line 1254 (Fairmont-Chicopee-Shawinigan), and rebuild/construct a two terminal line #1702 from Fairmont 16H switching station to Chicopee 18L substation. Revision is because the conductor is being revised from 1272 kcmil ACSR to 1272 kcmil ACSS based on the new NU standard. Also, the line number changed from 1602 to 1702. | 2013-12-01 | Approved | 2012-05-04
NU-08-T19-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to separate the 115-kV three terminal line 1723 (Fairmont-Piper-East Springfield), and rebuild/construct a two terminal line #1803 from Fairmont 16H switching station to Cadwell 50F switching station. Revision is because the conductor is being revised from 2x1272 kcmil ACSR to 2x1272 kcmil ACSS based on the new NU standard. The stability requirement for the 2nd high speed protection scheme has been eliminated since both Fairmont and Cadwell switching stations are not BPS facilities. Also, the line number changed from 1603 to1803. | 2013-12-01 | Approved | 2012-05-04
NU-08-T20-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to separate the 115-kV three terminal line 1254 (Fairmont-Chicopee-Shawinigan), and rebuild/construct a two terminal line 1601 from Fairmont 16H switching station to Shawinigan 55E substation. Add a 2nd high-speed protection scheme. Revision is because the conductor is being revised from 2x1590 kcmil ACSR to 2x1272 kcmil ACSS based on the new NU standard. The two conductor sizes have comparable ratings. Also, the line number changed from 1604 to 1601. | 2013-12-01 | Approved | 2012-05-04
NU-08-T21-Rev. 1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the Southwick – North Bloomfield 115 kV line 1768 and South Agawam – North Bloomfield double-circuit 115-kV line 1821/1836 to be disconnected at North Bloomfield. Line 1836 will also be disconnected at South Agawam. Lines 1768 and 1821 will be connected (joined) at Granby Junction (approximately 5 miles north of North Bloomfield) to form a new Southwick to South Agawam 115 kV line. The line portion from South Agawam to the CT/MA border will utilize 1272 kcmil ACSS conductor and will be placed on the same structures as the new Agawam to North Bloomfield 345-kV line 3216. The portion from the CT/MA border to Granby Junction will cross bundle the existing circuits 1821/1836. The other portion from Granby Junction to Southwick will utilize the same conductors on the existing structures. Also, the reactors at South Agawam in series with lines 1821 and 1836 will be disconnected and removed. Revision is because based on the new NU standard, the conductor is being revised from 1590 kcmil ACSR to 1272 kcmil ACSS for the line portion from South Agawam to the CT/MA border. The two conductor sizes havecomparable ratings. | 2013-12-01 | Approved | 2012-05-04
NU-08-T22-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to rebuild the 115-kV line 1781 from Agawam 16C substation to South Agawam 42E substation. Line 1781 will share some transmission structures with the new 345-kV Agawam to North Bloomfield line 3216. Add a 2nd high-speed protection scheme. Revision is because the conductor is being revised from 1272 kcmil ACSR to 1272 kcmil ACSS based on the new NU standard. | 2013-12-01 | Approved | 2012-05-04
NU-08-T23-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to rebuild the 115-kV line 1782 from Agawam 16C substation to South Agawam 42E substation. Add a 2nd high-speed protection scheme. Revision is because the conductor is being revised from 1272 kcmil ACSR to 1272 kcmil ACSS based on the new NU standard. | 2013-12-01 | Approved | 2012-05-04
NU-08-T24-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to rebuild the 115-kV line 1845 from Ludlow 19S substation to Shawinigan 55E substation. Add a 2nd high-speed protection scheme. Revision is because the conductor is being revised from 2x1272 kcmil ACSR to 2x1272 kcmil ACSS based on the new NU standard. | 2013-12-01 | Approved | 2012-05-04
NU-08-T25-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to construct a new 345-kV line from Ludlow 19S substation to Agawam 16C substation. Revision is because the conductor is being revised from 2x1590 kcmil ACSR to 2x1590 kcmil ACSS based on the new NU standard. | 2013-12-01 | Approved | 2012-05-04
NU-08-T26-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to construct a new 345-kV line from Agawam 16C substation to North Bloomfield 2A substation. Revision is because the conductor is being revised from 2x1590 kcmil ACSR to 2x1590 kcmil ACSS based on the new NU standard. | 2013-12-01 | Approved | 2012-05-04
NU-08-T27-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to establish a 0.44 mile 115-kV line 1556 between the East Springfield 5J substation and the new Cadwell 50F switching station, utilizing the existing 1723 line section between these two substations on the ROW. Install a 1250A, 3% (on 100 MVA base) reactor in series with the new 1556 line. Revision is because of the need to install a 1250A, 3% (on 100 MVA base) reactor in series with the new 1556 line to resolve short-circuit issues at East Springfield 5J substation. The line number changed from 5001 to 1556. | 2013-12-01 | Approved | 2012-05-04
NU-08-T28-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to establish a 0.44 mile 115-kV line 1645 between the East Springfield 5J substation and the new Cadwell 50F switching station, utilizing the existing 1481 line section between these two substations on the ROW. Install a 1250A, 3% (on 100 MVA base) reactor in series with the new 1645 line. Revision is because of the need to install a 1250A, 3% (on 100 MVA base) reactor in series with the new 1645 line to resolve short-circuit issues at East Springfield 5J substation. The line number changed from 5002 to 1645. | 2013-12-01 | Approved | 2012-05-04
NU-08-T29-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to expand Ludlow 19S 345-kV substation by adding one complete breaker and a half bay. Replace the existing two 345/115-kV autotransformers with the new standard higher impedance autotransformers (3 single phase units) due to short-circuit issues. Terminate line 3196, and re-terminate lines 3419, 301, and the 3X autotransformer. Replace 115-kV circuit breakers 44T and 46T with breakers having 3000A ratings. Replace bus connected circuit breakers 1X3 and 3X3 with breakers having 4000A ratings. Revision is because two 120 MVAR 345-kV capacitor banks are being eliminated. Four (4) 115-kV circuit breakers are being replaced instead of five. Circuit breakers 44T and 46T will have a nameplate rating of 3000A instead of 4000A. | 2013-12-01 | Approved | 2012-05-04
NU-08-T30-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to build a new 345-kV substation at the existing 115-kV Agawam 16C substation site with two breaker and a half bays, and install two 345/115 kV standard autotransformers. Terminate lines 3196 (Agawam to Ludlow) and 3216 (Agawam to North Bloomfield). Add a complete 115-kV breaker and a half bay. Re-terminate line 1781 into a new 115-kV bay position. Replace 115-kV circuit breakers 24T, 25T, and 26T with new breakers having a 4000A nameplate rating and a 63 kA interrupting capability. Replace 115-kV circuit breaker 10K associated with the capacitor banks with a 63 kA breaker. The Agawam 16C Substation 345-kV and 115-kV voltage classes are to be classified as NPCC Bulk Power System (BPS) facilities. Revision is because Agawam Autotransformers #1 and #2 swapped positions. | 2013-12-01 | Approved | 2012-05-04
NU-08-T31-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to construct a new 115-kV station name Cadwell 50F Switching Station located in Springfield, MA, in a ring bus configuration consisting of five (5) 115-kV circuit breakers with a nameplate rating of 3000A and an interrupting capability of 63 kA. Install a 1250A, 3% (on 100 MVA base) reactor in series with each line 1556 and 1645. Revision is because of the need to install a 1250A, 3% (on 100 MVA base) reactor in series with each line 1556 and 1645 to resolve short-circuit issues at East Springfield 5J substation. The Cadwell circuit breaker numbers have changed. | 2013-12-01 | Approved | 2012-05-04
NU-08-T32-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to build a new Fairmont 16H Switching Station using a breaker and a half arrangement. Install fifteen (15) new 115-kV circuit breakers to form five (5) complete breaker and a half bays. Also add new circuit breaker 20T at the end of the south bus. All new 115-kV circuit breakers will have an interrupting capability of 63 kA. Circuit breakers 13T, 14T, and 15T are to have a 4000 A nameplate rating. All the other circuit breakers will have a nameplate rating of 3000 A. Revision is because a new Fairmont switching station will be built instead of expanding and reconfiguring the existing one. The existing seven (7) circuit breakers are being replaced to minimize outages during construction and for short-circuit considerations. The Fairmont circuit breaker numbers have changed. | 2013-12-01 | Approved | 2012-05-04
NU-08-T33-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to modify South Agawam 42E Substation to accommodate the newly formed 115-kV line 1768, South Agawam to Southwick. The reactor at South Agawam substation in series with line 1821 will be disconnected. Revision is because the reactor at South Agawam substation in series with line 1821 will be disconnected instead of being bypassed. A typo was also corrected noting that the line portion from South Agawam substation to the CT/MA border will share the same structures as the Agawam (not Ludlow) to North Bloomfield 345-kV line. | 2013-12-01 | Approved | 2012-05-04
NU-08-T39-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the Shawinigan 55E Substation, to replace the 115-kV circuit breakers 4T and 6T with new circuit breakers having a 4000 A nameplate rating, and replace circuit breakers 1T and 2T with new circuit breakers having a 3000 A nameplate rating. All the new 115-kV circuit breakers will have an interrupting capability of 63 kA. Revision is because of the need to replace circuit breakers 1T and 2T with new circuit breakers having a 3000 A nameplate rating. | 2013-12-01 | Approved | 2012-05-04
NU-08-T60-Rev.1 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to build a new Bulk Power System 345-kV transmission substation at the existing 115-kV North Bloomfield 2A Substation site. The New 345-kV substation will have two (2) breakers and a half bays consisting of six (6) 345-kV circuit breakers rated at 3000 A nameplate, 50 kA interrupting capability. Add a second 345/115-kV autotransformer. Terminate the 3216 (Agawam to North Bloomfield) and 3642 (Manchester to North Bloomfield) lines. Disconnect 115-kV lines 1768, 1821, and 1836 from this substation, which opens the 115-kV tie-lines to Massachusetts. Replace 115-kV circuit breakers 10K, 20K and 3X1 with new circuit breakers having an interrupting capability of 63 kA. Revision is because a 3rd 345-kV bay was eliminated (due to CCRP being deferred) and the 345-kV lines and autotransformers are connected into different bay positions. | 2013-12-01 | Approved | 2012-05-04
NU-12-T10 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the Chicopee 18L Substation, to replace circuit breakers 1T and 2T with new circuit breakers having a nameplate rating of 3000 A and an interrupting capability of 63 kA. Proposed in-service date is December 2013. | 2013-12-01 | Approved | 2012-05-04
NU-12-T11 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to separate the 3-terminal 395 line at Meekville Junction. The existing Barbour Hill portion will remain connected to the Manchester portion and re-numbered as the 3557 line. A new 345-kV line from Manchester to Meekville Junction will be built using 2-1590 kcmil ACSS conductor and connected to the existing line to North Bloomfield to form a new 3642 line. | 2013-12-01 | Approved | 2012-05-04
NU-12-T12 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the Manchester 345-kV 3A substation to add circuit breaker 24T with a nameplate rating of 3000 A and an interrupting capability of 50 kA. Re-terminate line 3557 (Barbour Hill to Manchester) and terminate line 3642 (North Bloomfield to Manchester). | 2013-12-01 | Approved | 2012-05-04
NU-12-T13 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to reconductor the 1784 line using 1590 kcmil ACSS conductor. Replace the existing series reactor at North Bloomfield 2A substation with a 2% (on 100 MVA base) reactor having ratings that match (or exceed) the new conductor ratings. | 2013-12-01 | Approved | 2012-05-04
NU-12-T14 | 2012-04-03 | Greater Springfield Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to install a 345-kV variable 75-150 MVAR reactor and one 345-kV circuit breaker at the Beseck 9F Substation. | 2013-12-01 | Approved | 2012-05-04
NU-08-T52-Rev.1 | 2012-04-03 | Interstate Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to construct a new 345-kV transmission line from the Card 11F Substation to the Lake Road 27E Substation. Revision is because the conductor is being revised from 2x1590 kcmil ACSR to 2x1590 kcmil ACSS based on the new NU standard. | 2013-12-01 | Approved | 2012-05-04
NU-08-T54-Rev.1 | 2012-04-03 | Interstate Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to construct a new 345-kV transmission line from Lake Road 27E Substation to the Connecticut/Rhode Island state border, which will be the NU section of the new line connecting to the National Grid USA, West Farnum Substation. Revision is because the conductor is being revised from 2x1590 kcmil ACSR to 2x1590 kcmil ACSS based on the new NU standard. | 2013-12-01 | Approved | 2012-05-04
NU-08-T59-Rev.1 | 2012-04-03 | Interstate Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) for Card 11F Substation, to expand the existing 345-kV ring bus by adding three (3) new 345-kV circuit breakers rated at 3000A nameplate, 50 kA interrupting capability. Terminate transmission line 3271. Revision is because Card 11F 345-kV substation is being revised not to be reconfigured into a breaker and a half arrangement. The requirement for Card 11F 115-kV substation to become a BPS facility has been eliminated since it is already classified as part of the NPCC Bulk Power System (BPS). | 2013-12-01 | Approved | 2012-05-04
NU-08-T51-Rev.1 | 2012-04-03 | Central Connecticut Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to build a new 345-kV transmission line from North Bloomfield 2A Substation to the Frost Bridge 8R Substation. Revision is because the conductor is being revised from 2x1590 kcmil ACSR to 2x1590 kcmil ACSS based on the new NU standard. | 2017-12-01 | Approved Withdrawn | 2012-05-04
NU-12-T15 | 2012-04-03 | Central Connecticut Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to expand North Bloomfield 2A Substation by adding a 3rd 345-kV bay consisting of two 345-kV circuit breakers having a nameplate rating of 3000 A and an interrupting capability of 50 kA. Terminate the new North Bloomfield to Frost Bridge 345-kV line. | 2017-12-01 | Approved Withdrawn | 2012-05-04
NU-12-T16 | 2012-04-03 | Central Connecticut Reliability Project | Transmission notification from Northeast Utilities Service Company (“NU”) to install the second 345-kV variable 75-150 MVAR reactor and one 345-kV circuit breaker at the Beseck 9F Substation. | 2017-12-01 | Approved | 2012-05-04
ALG-12-G01 | 2012-04-04 | Algonquin Generator Capacity Increase Project | Generator notification from Algonquin Power (“ALG”) for the capacity increase to the existing Dexter generator (Resource ID #392) located in Windsor Locks, CT through the construction of a new 16.44 MW gas turbine generator. The project will be connected to the Dexter 13.8 kV substation alongside an industrial load and existing Algonquin Power combined cycle plant which consists of a 40 MW gas turbine generator and a 16 MW steam turbine generator. | 2012-07-01 | Approved | 2012-05-16
DEM-12-X01 | 2012-04-05 | Brayton Point 1 & 2 Static Exciter Replacement Project | Transmission notification from Dominion Energy New England (“DEM”) for the replacement of the existing voltage regulators and static excitation systems on the Brayton Point steam generating units 1 & 2 due to equipment obsolescence with GE EX 2011e digital excitation systems and power systems. Equipment replacement for Unit 1 will be during the spring 2012 overhaul. Equipment replacement for Unit 2 will be during the spring 2014 overhaul. | 2014-04-01 | Approved | 2012-05-16
IBR-12-G01 | 2012-03-30 | Groton Wind Generation and Transmission Project | Generator notification from Iberdrola Renewables (”IBR”) on behalf of Groton Wind, LLC for the construction of twenty four 2.0 MW wind turbine generators totaling 48 MWs net output power located in Grafton County, NH. | 2012-09-30 | Approved | 2012-05-16
IBR-12-T01 | 2012-03-30 | Groton Wind Generation and Transmission Project | Transmission notification from Iberdrola Renewables (”IBR”) on behalf of Groton Wind, LLC for the construction of the Groton Wind Collector Substation consisting of 34.5/115 kV transformer rated at 30/40/50 MVA with an impedance of aprox. 9%, connecting the Groton Wind Project with the new NU 115 kV Huckins Hill Switching Station on the Beebe River – Ashland Tap 115 kV Line E115. | 2012-09-30 | Approved | 2012-05-16
NU-12-T06 | 2012-03-30 | Groton Wind Generation and Transmission Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the construction of the 115 kV Huckins Hill Switching Station with three 115-kV circuit breakers, bifurcating 115-kV Line E115 located in Holderness, NH, providing a point of interconnection for the proposed generator project. | 2012-10-01 | Approved | 2012-05-16
NU-12-T07 | 2012-03-30 | Groton Wind Generation and Transmission Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the upgrade of the thermal capability of the existing 115 kV Line E115, Huckins Hill (POI)- Ashland Tap; to achieve the required summer thermal LTE rating of 150 MVA. The upgrade will result in summer thermal ratings of 125/159/164 MVA and winter thermal ratings of 153/180/185 MVA. The upgrade is to be achieve by increasing the maximum allowable conductor temperature to 140C. | 2013-12-01 | Approved | 2012-05-16
NU-12-T08 | 2012-03-30 | Groton Wind Generation and Transmission Project | Transmission notification from Northeast Utilities Service Company (“NU”) for the addition of two 115-kV circuit breakers to the Merrimack Substation. The circuit breakers will be placed in series with existing bus tie circuit breakers ‘BT12’ and ‘BT23’. | 2014-12-01 | Approved | 2012-05-16
FLP-12-X01 | 2012-03-24 | Shepaug Automatic Voltage Regulator Replacement | Transmission notification from First Light Power Resources (“FLP”) for the replacement of the existing Automatic Voltage Regulator on the Shepaug Hydro generator, interconnected at the Shepaug 69 kV substation with a Basler DECS400 voltage regulator. | 2012-09-24 | Approved | 2012-05-16
NSTAR-12-G02 | 2012-04-09 | Airport Way Nominee Solar Project | Generator notification from NSTAR Electric and Gas Company (“NSTAR) for the construction of a 1.24 MW solar array in Barnstable, MA. Generator will be interconnected through a recloser to a street lateral of the 23 kV #92A feeder out of NSTAR’s Hyannis Junction Substation #961. | 2012-05-01 | Notification | 2012-04-30
NEP-12-GNF07 | 2012-04-10 | Devens Solar Project | Generator notification from New England Power Company (“NEP”) on behalf of Citizens Energy Corporation (“CEC”) for the construction of a 2.5 MW solar array located in Devens, MA. Project will interconnect to the Devens Utilities 13.8 kV distribution system fed by the Devens West Maine Substation. | 2012-08-01 | Notification | 2012-04-30
BBHP-12-G01 | 2012-03-23 | Medway Hydro Capacity Increase Project | Generator Notification from Bangor Hydro Electric Company on behalf of Black Bear Hydro Partners (“BBHP”) for a 0.8 MW capacity increase to the existing Medway Hydro generator (Resource ID #16525) located in Penobscot, ME. Project will increase net capacity to 4.776 MWs. | 2013-09-01 | Notification | 2012-04-30
BBHP-12-G02 | 2012-03-23 | Stillwater Station B Capacity Increase Project | Generator Notification from Bangor Hydro Electric Company on behalf of Black Bear Hydro Partners (“BBHP”) for the construction of a 2.4 MW hydro generator located in Penobscot, ME. Generator will be interconnected to the existing BHE 12.5 kV Stillwater Avenue Substation. | 2012-08-01 | Notification | 2012-04-30
BBHP-12-G03 | 2012-03-23 | Orono Station B Capacity Increase Project | Generator Notification from Bangor Hydro Electric Company on behalf of Black Bear Hydro Partners (“BBHP”) for the construction of a 4.0 MW hydro generator located in Penobscot, ME. Generator will be interconnected to the existing BHE 12.5 kV Orono Substation. | 2012-08-01 | Notification | 2012-04-30
UI-08-T05-Rev.2 | 2012-03-20 | Grand Avenue Switching Station Modernization | Transmission notification from United Illuminating Company (“UI”) to revise the previously approved Grand Avenue Switching Station Project. Due to physical construction reasons involving the underground duct line and the Grand Avenue GIS equipment, the 88003A and 89003B underground 115 kV lines will have their terminations at Grand Avenue Switching Station swapped. | 2012-05-01 | Notification | 2012-04-30
NU-12-G01 | 2012-03-27 | Hartford Water Pollution Control Facility Steam Generator Project | Generator notification from Northeast utilities Service Company (“NU”) for the construction of a 2MW steam turbine generator located in Hartford, CT. Generator will interconnect to the CL&P South Meadow 115kV Substation, Primary circuit 1A130 and Alternate 1A116. | 2012-03-30 | Notification | 2012-04-30
NEP-12-GNF03 | 2012-04-05 | Quabbin Solar Project | Generator notification from New England Power Company (“NEP”) for the construction of a 2 MW solar array located in Barre, MA. Generator will interconnect to the NGRID 13.8 kV distribution circuit #604W2 supplied from the Barre Substation. | 2012-03-02 | Notification | 2012-04-30
FW-12-G01 | 2012-02-29 | Bull Hill Wind Generation and Transmission Project – QP #317 | Generation notification from First Wind LLC (“FW”) on behalf of Blue Sky East, LLC for the construction of nineteen 1.815 MW wind turbine generators (34.5 MWs gross) and interconnecting to the Bangor Hydro Electric Company (“BHE”) 115 kV Line 66 by means of a new BHE switching Station and FW Bull Hill Switching Station located in Eastbrook, ME. | 2012-09-30 | Approved | 2012-03-21
FW-12-T01 | 2012-02-29 | Bull Hill Wind Generation and Transmission Project – QP #317 | Transmission notification from First Wind LLC (“FW”) on behalf of Blue Sky East, LLC for the construction of a new Bull Hill Substation to interconnect the Bangor Hydro Electric (BHE”) Bull Hill Switching Station and the Bull Hill Wind Farm. | 2012-09-30 | Approved | 2012-03-21
BHE-12-T01 | 2012-02-29 | Bull Hill Wind Generation and Transmission Project – QP #317 | Transmission notification from Bangor Hydro Electric Company (“BHE”) for the construction of a new Bull Hill, Switching Station with a new three breaker ring bus,segmenting the existing BHE Line 66 between Rebel Hill and Deblois Switching Stations to service the Bull Hill wind Farm. | 2012-09-30 | Approved | 2012-03-21
BHE-12-T02 | 2012-02-29 | Bull Hill Wind Generation and Transmission Project – QP #317 | Transmission notification from Bangor Hydro Electric Company (“BHE”) for the rerate of the 4 mile overhead existing BHE line 69 from present summer LTE rating of 39MVA to a minimum summer LTE rating of 45MVA from the Columbia Tap in Columbia, ME to the Epping Switching Station in Epping, ME.. Engineering on this effort is ongoing but it is anticipated that with clearance changes this rerating can be done without changing the conductor. | 2013-03-01 | Approved | 2012-03-21
CMP-12-X01 | 2012-02-14 | Rumford Temporary SPS and PSS Project | Transmission notification from Central Maine Power Company (“CMP”) for the temporary Rumford Area SPS (NPCC Type III SPS) being installed to reject generation at Rumford Power Associates (RPA) for faults on Sections: 210, 211, 217, 221, 228, 243, various Rumford Area buses, and breaker failure conditions at Kimball Road during the construction of Section 243A as part of the Maine Power Reliability Program (MPRP). This change is required to maintain system stability during the construction period. The expected duration of the 115 kV transmission outages is expected to be from 10 to 12 months from the Fall of 2012 to the Fall of 2013. | 2012-09-01 | Approved | 2012-03-21
CPEM-12-X01 | 2012-02-14 | Rumford Temporary SPS and PSS Project | Transmission notification from Capital Power Corporation (“CPEM”) on behalf of Rumford Power for the installation of a Power System Stabilizer at Rumford Power Inc. The expected installation of this software is to be completed prior to November 1, 2012 in preparation for certain transmission outages in the local area commencing in the Fall of 2012 to the Fall of 2013. | 2012-11-01 | Approved | 2012-03-21
NSTAR-12-G05 | 2012-03-05 | Dartmouth Solar Project | Generator notification from NSTAR Electric and Gas Company (“NSTAR”) for the construction of a 3.0 MW photovoltaic solar array located in Dartmouth, MA. Generator will be interconnected to the NSTAR Industrial Park Substation #636, 13.2 kV feeder #107. | 2012-07-01 | Notification | 2012-03-21
NSTAR-12-G03 | 2012-03-05 | Edgartown Solar Project | Generator notification from NSTAR Electric and Gas Company (“NSTAR”) for the construction of a 1.083 MW photovoltaic solar array located in Edgartown, MA. Generator will be interconnected to the NSTAR Falmouth Substation #933, 23 kV #99 Line. | 2012-08-01 | Notification | 2012-03-21
NSTAR-12-G04 | 2012-03-05 | Dennis Landfill Solar Project | Generator notification from NSTAR Electric and Gas Company (“NSTAR”) for the construction of a 2.5 MW photovoltaic solar array located in Dennis, MA. Generator will be interconnected to the NSTAR #92B 23 kV distribution feeder our of the Harwich Substation #968. | 2012-05-01 | Notification | 2012-03-21
NSTAR-10-T07-Rev.1 | 2012-02-15 | Line 123 Reconnect Project | Transmission notification from NSTAR Electric and Gas Company (“NSTAR”) to revise the original PPA for this project (NSTAR-10-T07) described expanding the Barnstable 115 kV Substation with a fifthbay. The existing Barnstable – Hyannis #124 line was going to be reconnected to the new fifth bay position and the Barnstable – Hyannis #123 Line was going to be reconnected to the present #124 Line position. However, in order to avoid 115 kV crossovers for a future line from Barnstable supplying the lower Cape area, the Line #124 was reconnected to Bay #6 and Line #123 was reconnected to Bay #5. | 2011-12-01 | Notification | 2012-03-21
BLP-12-T01 | 2012-02-04 | Stockhouse Road Substation Project | Transmission notification from Bozrah Light & Power (“BLP”) for the installation of a new 115 kV, 3000 ampere, 40 kA circuit breaker in series with the 1490 and 1070 lines. New wave traps and line protection will be installed to enable sectionalizing of a faulted circuit without interrupting 100% of the load from Stockhouse Road. New SF6 1200 ampere circuit switchers and 1200 ampere disconnect switches have been installed for high side protection and electrical isolation of the three power transformers. | 2012-04-01 | Approved | 2012-03-05
TCMWD-11-G01 | 2012-01-25 | Kibby Wind Expansion Project – QP #310 | Generator notification from TransCanada Maine Wind Development (“TCMWD”) for the construction of 11 Vestas V90 Wind Turbine generators each rated at 3.0 MWs (33 MWs net output) and interconnecting to the Kibby Expansion Substation located in Franklin County, ME. | 2012-09-01 | Approved | 2012-03-05
TCMWD-11-T01 | 2012-01-25 | Kibby Wind Expansion Project – QP #310 | Transmission notification from TransCanada Maine Wind Development (“TCMWD”) for the construction of a 115/34.5 kV substation interconnecting to Section 267 approximately 1200 ft. from the existing Kibby Wind Farm. Also construct one string collector operating at 34.5 kV nominal tying into the Kibby Substation using approximately 5.8 miles of 1113 KCML ACSR at 34.5 kV. In addition, install an under load tap changing 121/34.5 kV step up transformer (25/33/41.5 MVA at the collector substation. | 2012-09-01 | Approved | 2012-03-05
CMP-11-T07 | 2012-01-25 | Kibby Wind Expansion Project – QP #310 | Transmission notification from Central Maine Power Company (“CMP”) to construct facilities to interconnect the TransCanada Maine Wind Development Project Q310, 33 MW wind farm into the CMP transmission system by tying into customer owned Section 267 approximately 1,200 feet from the existing Kibby Wind collector substation. This PPA covers the required CMP system upgrades include installing four +/- 4 MVAR dynamic reactive sources at Bigelow Substation; installing a dedicated 115/34.5 kV transformer for the dynamic reactive sources at Bigelow Substation; automating the high-voltage switching controls for both 18 MVAR shunt capacitor banks at Wyman Hydro Substation; and installing an additional 5.4 MVAR shunt capacitor at Starks Substation. | 2012-09-01 | Approved | 2012-03-05
MPP-12-X01 | 2012-02-06 | Millennium AVR Replacement Project | Transmission notification from Millennium Power Partners (“MPP”) for the replacement of the existing WDR2000 automatic voltage regulator (AVR) systems for the combustion turbine and steam turbine units with a Basler ECS/RW AVR systems. Replacement is due to the existing AVR has become obsolete. | 2012-04-01 | Approved | 2012-03-05
NSTAR-12-T02 | 2012-02-06 | Brook Street Station 115 kV Bay Addition Project | Transmission notification form NSTAR Electric and Gas Company (“NSTAR”) for the new 115 kV Bay at Brook Street Station with a new 30/40/50 MVA 115/23 kV transformer located in Plympton, MA. | 2011-12-01 | Approved | 2012-03-05
UI-12-T04 | 2012-02-06 | East Shore Substation Capacity Upgrade Project | Transmission notification form United Illuminating Company (“UI”) for the reconfiguration of the 60 and 70 bays of the existing breaker-and-a-half configuration of the East Shore 115 kV Substation, including the addition of new 115 kV circuit breakers and disconnect switches, and modification of the 115 kV bus. In addition, installation of two (2) new 30/40/50 MVA, 118/14.9 kV power transformers, with load tap changers (LTCs) and installation of a new Powe Delivery Center (PDC) for interconnecting the existing distribution circuits. Also,removal of the existing distribution substation, including 115 kV oil circuit breakers, 22T and 32T. | 2013-06-01 | Approved | 2012-03-05
RPM-09-G01-Rev.1 | 2012-01-18 | Johnston Landfill Generator and Transformer Project Revision | Generator notification from Rhode Island GenCo, LLC (“RPM”) for the reduction in MW output of the Johnston Landfill Gas Generator from 38.6 MWs to 32.6 MWs due to diminished gas supply. | 2012-10-03 | Approved | 2012-03-05
RPM-09-T01-Rev.1 | 2012-01-18 | Johnston Landfill Generator and Transformer Project Revision | Transmission notification from Rhode Island GenCo,LLC (“RPM”) for the rating reduction of a 35 MVA 13.8/115 kV generator step up transformer at the Johnston LFG generating plant and interconnecting to the NGRID Ridgewood #124 Switchyard. Reduction reflects the change in generation output of the Johnston Landfill Gas Generator. | 2012-10-03 | Approved | 2012-03-05
CMP-11-T02-Rev.1 | 2012-01-30 | Lakewood PPA Revision | Transmission notification revision from Central Maine Power Company (“CMP”) to Sectionalize Section 241 by adding four 115 kV circuit breakers in a ring bus configuration at the existing Lakewood Substation. Also, install a second 115/34.5 kV 20/37 MVA transformer at the existing Lakewood Substation. Construct 4 miles of new 115 kV Bluejay (1113 45/7) conductor from the Section 83 corridor to the Lakewood Substation in the existing Section 83B (future Section 241) Right-of-Way. Also, rebuild the existing 115 kV line Section 83B (future Section 241) with Bluejay (1113 45/7) conductor (4 miles). The previous submittal of PPA CMP-11-T02, did not capture the proposed Lakewood project in its entirety. The associated transmission line work was inadvertently omitted from the application. | 2013-12-01 | Approved | 2012-03-05
CMP-12-T01 | 2012-01-30 | Leeds Substation Project | Transmission notification from Central Maine Power Company (“CMP”) to Tap Line Section 200 roughly 14.1 miles north of the Gulf Island 115 kV Substation, between pole structures 133 and 134. Install a 115/34.5 kV 20/37 MVA transformer and three 34.5 kV distribution circuits. | 2012-02-01 | Approved | 2012-03-05
NEP-12-GNF02 | 2012-01-17 | Lightolier Wind Project | Generator notification from New England Power Company) (”NEP”) for the installation of one 2 MW wind turbine generator interconnected to the NGRID 13.8 kV distribution system through 13.8 kV circuit #28W51 via a new 13.8 kV tap on Sykes Road in Fall River, MA. | 2012-01-31 | Notification | 2012-03-05
CMP-12-T02 | 2012-01-30 | North Augusta Substation Upgrade Project | Transmission notification from Central Maine Power Company (“CMP”) for the sectionalize of Section 213 by adding two 115 kV circuit breakers at the existing North Augusta Substation. Also install a 115/34.5 kV 20/37 MVA transformer at the existing North Augusta. | 2013-12-01 | Approved | 2012-03-05
NSTAR-12-T03 | 2012-02-06 | West Medway AutoTransformer Replacement Project | Transmission notification from NSTAR Electric and Gas Company (“NSTAR”) for the replacement of the existing 345/230 kV auto transformer (345A) at West Medway Substation located in Medway, MA. | 2013-02-01 | Approved | 2012-03-05
NSTAR-12-T04 | 2012-02-06 | West Medway AutoTransformer Replacement Project | Transmission notification from NSTAR Electric and Gas Company (“NSTAR”) for the replacement of the existing 345/230 kV auto transformer (345B) at West Medway Substation located in Medway, MA. | 2013-02-01 | Approved | 2012-03-05
CTMEEC-11-T01 | 2011-12-22 | South Norwalk Substation Project | Transmission notification from Connecticut Transmission Municipal Electric Energy Cooperative (“CTMEEC”) on behalf of South Norwalk Electric and Water District for the construction of a new 115/13.8 kV Substation having a 115 kV bus tie breaker and two 40 MVA two winding transformers located in Norwalk CT. Interconnecting via a looped tap into a 6.37 mile overhead transmission line 1890 “E” extending from South Norwalk 115 kV Substation to Sherwood 115 kV Substation located in Westport CT via a tap into the 0.17 mile overhead transmission line segment 1890 “W” from the South Norwalk 115 kV Substation to the Ely Avenue Junction located in Norwalk CT. | 2013-06-01 | Approved | 2012-02-03
HW-12-G01 | 2012-01-09 | Highland Wind Transmission Project | Generation Notification from Highland Wind LLC (“HW”) for the construction of thirty nine 3.0 MW Siemens wind turbine generators for a total nameplate output of 117 MWs located in Highland Plantation, ME. | 2013-12-01 | Approved Withdrawn | 2012-02-03
HW-12-T01 | 2012-01-09 | Highland Wind Transmission Project | Transmission Notification from Highland Wind LLC (“HW”) for the construction Of the Highland Wind Collector Substation and interconnection of a generator lead connecting the Highland Wind generator project with the CMP 115 kV Wyman Hydro Substation. | 2013-12-01 | Approved Withdrawn | 2012-02-03
CMP-11-T04 | 2012-01-09 | Highland Wind Transmission Project | Transmission Notification from Central Maine Power Company (“CMP”) for the construction of facilities to terminate the Highland Wind generator lead on Bus 3 at Wyman Hydro Substation next to Section 241, including necessary transmission structures to cross the Kennebec River, and taller H Frame structures on Sections 215, 63, and 83 within the Wyman Hydro Substation to accommodate the Highland Wind generator lead crossing underneath them. | 2013-12-01 | Approved Withdrawn | 2012-02-03
UI-12-T03 | 2011-12-20 | 8300 Reconfiguration Project | Transmission notification from United Illuminating Company for the installation of a new fifth breaker and one half bay to the 115 kV gas insulated switch gear (GIS) at Grand Avenue Switching Station located in New Haven, CT. | 2013-06-01 | Approved | 2012-02-03
UI-12-T02 | 2011-12-20 | 8300 Reconfiguration Project | Transmission notification from United Illuminating Company for the Relocation of the Mill River end of the existing 8300 115 kV line from Quinnipiac Substation into a new terminal position at the Grand Avenue Switching Station located in New Haven, CT | 2013-06-01 | Approved | 2012-02-03
UI-12-T01 | 2011-12-20 | 8300 Reconfiguration Project | Transmission notification from United Illuminating Company for the installation of a new 260 foot 115 kV transmission line between the existing 8300 line terminal at Mill River and a new terminal position at Grand Avenue located in New Haven, CT. | 2013-06-01 | Approved | 2012-02-03
NU-12-X01 | 2012-01-06 | Altresco 41A 1715/1816 SPS Modification | Transmission notification from Northeast Utilities Service Company (“NU) for the Altresco 41A 1715/1816 SPS Modification from the Altresco 41A Substation to the Doreen 19A Substation Line #1715 and from the Altresco 41A Substation to the Doreen 19A Substation Line #1816 located in Pittsfield, MA. Winter set points will be changed from 475 amperes to 580 amperes. Summer set point will remain at 475 amperes. Also, modifications will be made to the SPS to facilitate changing the SPS relay set point for the summer and winter periods via SCADA control command initiated by CONVEX. | 2012-03-31 | Approved | 2012-02-03
PPHC-12-G01 | 2012-01-06 | Altresco Generator Increase and SPS Modification Project | Generator notification from Pawtucket Power Holding Company, LLC (“PPHC”) for a 8.95 MW increase in gross winter output generation output for each of the three gas turbines and a 0.06 MW increase in gross winter output of the steam turbine generator at the Altresco generating station located in Pittsfield, MA.. | 2012-03-31 | Approved | 2012-02-03
NSTAR-11-G07 | 2011-01-09 | Fairhaven Wind Project | Generation notification form NSTAR Electric and Gas Company (“NSTAR”) for the construction of two 1.5 MW wind turbine generators (3.0 MWs total net output) located in Fairhaven, MA. Generator will interconnect to the Arsene Street Substation #654 13.2 kV feeders #220 and #221. | 2012-04-01 | Notification | 2012-02-03
NSTAR-11-G16 | 2011-01-09 | Kingston Wind Project | Generation notification form NSTAR Electric and Gas Company (“NSTAR”) for the construction of a 2.0 MW wind turbine generator located in Kingston, MA. Generator will interconnect to the NSTAR #17 23 kV distribution feeder out of the NSTAR Kingston Substation #735. | 2011-12-01 | Notification Withdrawn | 2/3/2012 3/17/2020
NEPM-11-G02 | 2011-12-07 | Southbridge Landfill Generator | Construction of a 1.5 MW Landfill Gas generator located in Southbridge, MA. Generator will interconnect to 413L4. | 2011-12-09 | Approved | 2012-01-05
BHE-06-T02 Rev. 1 | 2011-10-21 | BHE Downeast Reliability Project Rev. 1 | Change in project line numbers from Tap L57 from Boggy Brook in Hancock to Tap L69 near Harrington Substation located in Harrington, ME. In addition. Overhead line distance has been revised from 35 miles to 43 miles. Also, two small transformers were replace with one larger one rated at 20/26.7/33.3 MVA at Trunk. | 2012-12-01 | Approved | 2012-01-05
NSTAR-11-T12 | 2011-12-02 | Trapelo Road Station Upgrade | Addition of a new 115/14 kV transformer at the Trapelo Road Station #450. The transformer will be tapped off the existing 320-508 line between Waltham and Lexington. In addition, two 115 kV breakers will be installed between the taps of the transformers 110A and 110C in a series breaker configuration. The section of the 115 kV line between Trapelo Road and Waltham will be renumbered to 450-508. | 2012-06-01 | Approved | 2012-01-05
NU-11-T14 | 2011-11-30 | West Springfield 8C Substation Restoration | Construction of a Gas Insulated Substation The new substation will be built on the existing substation easement and configured in a breaker-and-half design. Existing yard structures will be demolished, and a new control house, battery building, and storage building constructed. Existing transformers and pipe cables will not be relocated. Connections into the GIS will be made using underground cables. New structures will be constructed in the yard to transition from underground cable to overhead conductors connecting to distribution and generation transformers. The structures serving distribution transformers 8C-1X and 8C-2X will be designed to allow installation of transformer high side motor operated disconnect switches. | 2014-12-31 | Approved | 2012-01-05
GDF-11-G01 | 2011-10-31 | Northfield Solar Generator | Construction of a 1.7 MW net output photovoltaic generator located in Northfield, MA and interconnecting to the French King 21B 115 kV Substation via WMECO’s 21B8 13.8 kV distribution circuit | 2012-01-01 | Approved | 2011-11-21
NU-11-G08 | 2011-10-28 | CCSU Fuel Cell generator | Construction of a 1.4 MW total net output fuel cell generator located in New Britain, CT and interconnecting to the New Britain, CT/CL&P Feeder Numbers 7L82. | 2011-11-16 | Approved | 2011-11-21
NU-11-G06 | 2011-10-20 | Whatley Solar Generator | Construction of three 0.50 MW (1.5 MW total net output) photovoltaic generators located in Whately, MA and interconnecting to the Podick 18G 115 kV Substation via WMECO’s 18G8 13.8 distribution circuit. | 2012-06-01 | Approved | 2011-11-21
NU-11-G07 | 2011-10-21 | Rvermore-Citizens Agawam Solar Generator | Construction of three 0.50 MW (1.5 MW total net output) photovoltaic generators located in Agawam, MA and interconnecting to the Agawam 16C 115 kV Substation via WMECO’s 16C16 13.8 distribution circuit. | 2012-06-01 | Approved | 2011-11-21
NEP-11-T11 | 2011-10-24 | Johnston Transformer Replacement | Replacement of the existing Johnston Substation transformer rated at 115/12.47 kV with a new transformer rated at 115/12.47 kV and 33/44/55 MVA located in Johnston, RI. | 2012-10-01 | Approved | 2011-11-21
BHE-11-T01 | 2011-10-21 | BHE Harrington Transformer Replacement | Replacement of the Harrington T1 115/34.5 kV load serving transformer and regulators with a thermally larger unit rated at 8/24/33.6 MVA with LTC. | 2nd Quarter 2012 | Approved | 2011-11-21
BHE-11-T02 | 2011-10-21 | BHE Ellsworth Falls Transformer Replacement | Replacement of the Ellsworth Falls T2 115/34.5 kV load serving transformer with a thermally larger unit rated at 62.6 MVA with LTC. | 2nd Quarter 2012 | Approved | 2011-11-21
HE-11-G02 | 2011-10-21 | Mueller Road Solar Generator | Construction of a 2.691 MW (net) photovoltaic generator located in Holyoke, MA and interconnecting to the 39C4 West Holyoke Substation distribution feeder supplied from the Ingleside 52W transmission Substation. | 2011-10-19 | Approved | 2011-10-26
NU-11-G05 | 2011-10-03 | Route 57 Solar Generator | Construction and interconnection of three 0.5 MW photovoltaic generators (1.5 MWs net output) interconnecting to the Silver 30A 115 kV substation via the WEMECO 30A6 13.8 kV line located in Agawam, MA. | 2012-06-01 | Approved | 2011-10-26
NEP-11-T10 | 2011-10-04 | G 33 Line Reconductoring | Reconductoring of the G-33 69 kV transmission line from the Vernon Substation to the Bellows Falls substation in VT. | 2012-04-01 | Approved | 2011-10-26
NSTAR-11-G14 | 2011-10-07 | MWRA Charlestown Wind generator | Construction of a 1.5 MW wind turbine generator located in Charlestown, MA and interconnecting to the NSTAR Mystic Station #250, 14 kV Line 585-114H. | 2011-10-01 | Approved | 2011-10-26
NSTAR-11-T11 | 2011-10-03 | 201-501 and 201-502 Line Reconductoring | Reconductoring of the 201-501 (D-130) and 201-502 (C-129N) 115 kV transmission lines from Medway substation #65 in Medway, MA to the Depot Street Sub Tap in Milford, MA. | 2013-06-01 | Approved | 2011-10-26
NSTAR-11-G11-Rev.1 | 2011-09-14 | Dartmouth Landfill Generator | Revision of the project interconnection of the previously approved 1.25 MW photovoltaic generator by GLC Dartmouth, LLC located in Dartmouth, MA. and interconnecting to the NSTAR Fisher Road Substation #657. Interconnection will now consist of three 200 volt, 500 kW inverters interconnecting via three separate, 500 kVA 200 Volt to 13.2kV step up transformers. | 2012-12-01 | Approved | 2011-10-26
HGE-11-G01 | 2011-09-21 | Meadow Street Solar Generator | Construction of a 0.82 MW (net) photovoltaic generator located in Holyoke, MA and interconnecting to the 62W9 distribution feeder supplied from the Ingleside 52W transmission Substation. | 2011-10-19 | Approved | 2011-10-26
VELCO-11-T08 | 2011-10-03 | Georgia Transformer | Installation of a 115/34.5 kV step down transformer at the Georgia Substation located in Georgia, VT. The installation of the transformer is proposed to relieve loading on existing nearby transformers and the local sub-transmission system, and to prevent loss of load in the St. Albans/East Fairfax area. | 2014-12-01 | Approved | 2011-10-26
TCPM-11-G01 | 2011-10-12 | Kibby Reactive Capability Reduction | Reduction of the MVAR leading capability of the Kibby Wind Farm from 0.86 MVAR per turbine to 0.35 MVAR per turbine to alleviate potential low voltage tripping issues at the generator. | 2011-10-07 | Approved | 2011-10-26
GMP-11-G01 | 2011-10-05 | Kingdom Wind Generator | Construction of twenty one 3.075 MW Vestas V112 wind turbine generators for a total net power output of 64.575 MWs and interconnecting to the new Vermont Electric Cooperative 46 kV Lowell Substation located in Lowell, VT. QP #311 interconnects twenty wind turbines, QP #367 adds one additional wind turbine. | 2012-10-01 | Approved | 2011-10-21
GenOn-11-G01 | 2011-09-23 | Kendall 3 Generator | Repowering of Kendall Steam Unit #3 with the installation of a back-pressure-steam turbine (“BPST”), air-cooled-condenser, and new generator controls. This modification will increase the maximum net power generation capability of Unit #3 by about 9MW for a total of approximately 28.5 MWs. | 2014-05-31 | Approved | 2011-10-26
NSTAR-11-G11 | 2011-09-14 | Dartmouth Landfill Solar Generator | Construction of a 1.25 MW photovoltaic generator by GLC Dartmouth, LLC located in Dartmouth, MA. and interconnecting to the NSTAR Fisher Road Substation #657. | 2011-12-01 | Approved | 2011-09-26
NU-11-T12 | 2011-09-12 | Black Rock 115 kV/69 kV Transformer and Line 680 Obsolete Terminal Equipment | Replacement of the 11H-4X 115/69 kV autotransformer and terminal equipment at the Black Rock 115 kV Substation and replacement of obsolete terminal equipment associated with the 680 Line at Black Rock located in New Britain, CT. | 21/31/2011 | Approved | 2011-09-26
NU-11-G02 | 2011-07-22 | Easthampton Solar Generator | Construction of a 2 MW photovoltaic generator located in Easthampton, MA and interconnecting to the Gunn 15A 115 kV substation via the WEMECO 15A3 23 kV line. | 2011-11-15 | Approved | 2011-09-07
NU-11-T11 | 2011-08-08 | Merrimack Station Service Load | Installation of two 115 kV circuit breakers at the Merrimack 115 kV substation, providing positions for two 115/4.16 kV transformers, for installing a new stack emissions scrubber system at the Merrimack generating station which will increase the station service load to approximately 19 MWs, 10.6 MVar at 0.87 p.f. lagging. | 2012-06-01 | Approved | 2011-09-07
NEP-11GNF01 | 2011-06-29 | Mt. Wachusett Community College Wind Turbine Generator | Installation of a 3.3 MW wind turbine generator located in Gardner, MA. Generator will interconnect to the Park St. #601 Substation at the 601W3 13.8 kV distribution feeder. | 2011-07-10 | Approved | 2011-09-07
BBHP-11-G01 | 2011-07-17 | Black Bear Hydro Generator | Addition of two hydro generators increasing the capability of the resource from 8 MWs to 9.083 MWs (net output) located in Milford, ME. Generators will interconnect to the existing Milford 46 kV substation. | 2011-09-01 | Approved | 2011-09-07
NU-11-G04 | 2011-08-10 | ASML US Generator | Construction of a 1.8 MW net output diesel generator located in Wilton, CT. Generator will interconnect to the Wilton 35A substation 13.8 kV on the 35A6 feeder bus A2 normal via the 115 kV Wilton-Ridgefield-Peacable 1470 Line. | 2011-09-16 | Approved | 2011-09-07
NU-11-G03 | 2011-08-12 | Indian Orchard Photovoltaic Generator | Construction of a 0.5 MW net output photovoltaic generator located in Springfield, MA. Generator will interconnect to the Orchard 27A substation. | 2011-11-01 | Approved | 2011-09-07
NU-04-T26-Rev. 1 | 2011-08-15 | South Meaadow 115 kV BPS Upgrade | Revision of the in service date of the South Meadow 115 kV Substation Bulk Power System Upgrade (BPS) to December 31, 2013. | 2013-12-31 | Approved | 2011-09-07
ECO-11-G02 | 2011-07-15 | Canton Mountain Wind Generator | Construction of seven 2.75 ME GE wind turbine generators with a total net output of 19.25 MWs located in Canton ME. | 2013-10-01 | Approved | 2011-08-29
ECO-11-T02 | 2011-07-15 | Canton Mountain Wind Transmission | Installation of a 1.0 mile overhead 34.5 kV transmission line from Canton Mountain Wind to the 115 kV SRW/Ludden Lane Substation located in Canton, ME. where it will interconnect to a new 15/20/25 MVA 34.5/115 kV step up transformer. | 2013-10-01 | Approved | 2011-08-29
MMWEC-11-G04 | 2011-05-24 | Ameresco/Chicopee Landfill Generator | Construction of four 1.8 MW landfill gas generators with a total net output of 7.383 MWs and interconnecting to the 13.8 kV distribution system in Chicopee, MA. | 2011-05-01 | Approved | 2011-08-29
VELCO-11-G01 | 2011-08-15 | Georgia Mountain Wind | Construction of four 2.75 wind turbine generators with a total net output of 11.0 MWs and interconnecting to the 34.5 radial transmission line feeding the Husky Tap on the Milton to Fairfax Falls 34.5 kV line located in Milton, VT. | 2012-11-30 | Approved | 2011-08-29
VELCO-11-G02 | 2011-08-15 | Fair Haven Biomass Generator | Construction of a 32.3 MW (net output) biomass generator located in Fair Haven, VT. | 2013-03-31 | Approved Withdrawn | 8/29/2011 6/9/2015
VELCO-11-T05 | 2011-08-15 | Fair Haven Biomass Transmission | Construction of a new three breaker rig bus substation connecting two 115 kV lines and the generator lead to the Beaver Wood Fair Haven generation plant. The substation will be located on the K-7 115 kV line (Whitehall-Blissville) in Fair Haven, VT. | 2013-03-31 | Approved Withdrawn | 8/29/2011 6/9/2015
VELCO-11-T06 | 2011-08-15 | Fair Haven Biomass Transmission | Construction of a 2.5 mile 115 kV transmission line from the Fair Haven substation to the Beaver Wood Fair Haven generation plant. | 2013-03-31 | Approved Withdrawn | 8/29/2011 6/9/2015
VELCO-11-T07 | 2011-08-15 | Fair Haven Biomass Transmission | Interconnection of the Fair Haven generator with a 115/13.8 kV transformer and 115/4.16 kV transformer. | 2013-03-31 | Approved Withdrawn | 8/29/2011 6/9/2015
CMP-11-X01 | 2011-08-09 | Maxcys/Bucksport SPS Modification | Revise the Maxcys/Bucksport Special Protection System (SPS) as part of construction sequencing for MPRP. During MPRP construction, the energization of one portion of the new path, 345 kV Section 3023 between Albion Road and Orrington substations, the Albion Road 345/115 kV autotransformer will require a modification of the Maxcys/Bucksport SPS. | 2012-01-01 | Approved | 2011-08-29
PSEG-11-G01 | 2011-06-29 | Bridgeport Harbor 3 Generation Capacity Increase | 5 MW increase in total net power output at the Bridgeport Harbor 3 Generator. Project increases net power output from 380 MWs to 385.0 MWs. | 2011-08-01 | Approved | 2011-07-28
NEP-11-T07 | 2011-06-29 | North Shore 115 kV Reconductoring Project | Reconductoring of 9.31 miles of the overhead S-145/T146 115 kV transmission lines from Tewksbury #22 Substation to the North Reading Tap. Projected effective date of the project is June 2014. | 2014-06-01 | Approved | 2011-07-28
NEP-11-T08 | 2011-06-29 | North Shore 115 kV Reconductoring Project | Reconductoring of 14.5 miles of the overhead B-154N/C-155N 115 kV transmission lines from King Street Tap to the South Danvers #42 Substation. Projected effective date of the project is June 2014. | 2014-06-01 | Approved | 2011-07-28
NEP-11-T09 | 2011-06-29 | North Shore 115 kV Reconduxctoring Project | Reconductoring of 8.2 miles of the overhead Y-151 115 kV transmission line from Tewksbury Junction to West Methuen #63 Substation. Projected effective date of the project is June 2014. | 2014-06-01 | Approved | 2011-07-28
NSTAR-11-T06 | 2011-04-29 | NSTAR Autosectionalized Switches | Installation of three new 2000 Amp, 115 kV, SEECO motor operated autosectionalized switches with dead line detection at the following locations: New switch # S791 to be installed on 115 kV line 211-503 on the tap to North Woburn and Reading Municipal. In service date of the project is September 24, 2011. New switch #S792 to be installed on 115 kV line 211-504 on the tap to North Woburn and Reading Municipal. In Service date of the project is October 12, 2011. New switch #19159 to be installed just outside Kingston Substation #735 on the leg of the #191 line proceeding to Auburn Street Station. In service date of the project is November 12, 2011. | 09/24/2011, 10/12/2011, 11/12/2011 | Approved | 2011-06-09
NU-11-T10 | 2011-05-11 | Stamford Reliability/South End Substation | Installation of a 115/13/2 kV transformer and two 115 kV circuit breakers at the South End Substation. | 2011-12-31 | Approved | 2011-06-09
NU-11-T09 | 2011-05-06 | 1410 115 kV Line Upgrade | Upgrade of the 8.71 mile overhead 1410 115 kV Transmission Line from Montville 4J Substation to Buddington 16L Substation. | 2012-12-01 | Approved | 2011-06-09
NSTAR-11-T03 | 2011-04-29 | Reconductor 128-518/P-168 115 kV Line | Reconductoring of the 128-518/P-168 115 kV Line from Chelsea to Revere. Line 128-518 / P-168 is 1.05 miles in length and is jointly owned by NSTAR and National Grid. The NSTAR section of the line (128-518) is 0.85 miles long and the National Grid section (P-168) is 0.2 miles long. The 1.05 mile line upgrade will be performed by NSTAR to provide higher thermal capacity. The upgraded NSTAR portion of the circuit will have a summer thermal rating of 363 MVA Normal and 63 MVA LTE. The upgraded National Grid portion of the circuit will have a summer thermal rating of 269 MVA Normal and 269 MVA LTE. | 2011-12-01 | Approved | 2011-06-07
MMWEC-11-G01 | 2011-04-05 | Stony Brook Energy Center uprate | Generation notification from Massachusetts Municipal Wholesale Electric Company (“MMWEC”) for the revision to the generation capability of Stony Brook Energy Center generation facility (Unit 1A, 1B, 1C, 2A, 2B, Steam Turbine). The revised Generator Notification is for 552.9 MWs Gross at 0 degrees and 440 MWs Net at 90 degrees. | 2011-05-01 | Approved Withdrawn | 4/21/2011 1/14/2015
MMWEC-11-G02 | 2011-05-10 | Ipswich Wind | Installation of a 1.6 MW wind turbine generator located in Ipswich, MA. Installation will be made to the Fowlers Lane Substation and supplied by 23 kV Line 2373 or Line 2394 Feed from NGRID King Street Substation. | 2011-06-29 | Approved | 2011-06-07
MMWEC-11-G03 | 2011-05-10 | Axio/Chicopee Solar | Installation of a 2.0 MW photovoltaic generator located in Chicopee, MA. Installation will be made to the 18L12 Feeder out of Chicopee Electric Light Department’s 18L Substation. | 2011-12-01 | Approved | 2011-06-07
NEP-11-T04 | 2011-04-15 | Hopkinton Substation | Construction of a 115/13.2 kV Substation located in Hopkinton, RI. Two 24/32/40 MVA rated 115 kV to 13.2 transformers will serve the local distribution system. An in-line 200 A continuous, 40 kA interrupting capable circuit breaker will provide protection. The existing 1870S Line will be split into 1870S Line from Wood River to Hopkinton and the 1814 Line from Hopkinton to Shunock. | 2014-03-01 | Approved | 2011-06-07
ECO-11-G01 | 2011-05-09 | Saddleback Wind Generation | Construction of twelve GE 2.75-103 2.75 MW wind turbine generators (33 MWs total) located in Carthage, ME. | 2013-09-01 | Approved | 2011-06-07
ECO-11-T01 | 2011-05-09 | Saddleback Wind Transmission | 9.0 mile transmission line interconnection of the Saddleback Wind Generator to the new 115 kV Ludden Lane Substation in Canton, ME along with the installation 34.5/115 kV Step up Transformer. | 2013-09-01 | Approved | 2011-06-07
CMP-11-T03 | 2011-05-09 | Ludden Lane Substation | Construction of the Ludden Lane 115 kV Substation consisting of a three breaker ring bus to interconnect the Saddleback Wind generating facility. CMP’s existing Section 229 will be sectionalized into two line sections at the transmission corridor with two new transmission segments constructed and extended into the new Ludden Lane Substation, a distance of approximately 0.2 miles each. The portion of Section 229 between Ludden Lane Substation and Riley Substation will be renumbered as Section 280 and the portion between Ludden Lane Substation and Rumford IP Substation will remain as Section 229. | 2013-09-01 | Approved | 2011-06-07
HE-11-T01 | 2011-05-06 | South Holyoke Substation | Interconnection of the South Holyoke Substation (formally known as Lyman Substation) in Holyoke, MA. Project will consist of a new 115/34.5/13.8 kV Substation for the purpose of relocating the distribution load and hydroelectric generation from the HG & E Prospect 24B Substation to the proposed 115 kV South Holyoke Substation. Substation consists of two 18/24/30 MVA transformers with LTC; (each one to supply a 13.8 kV distribution bus); and two 115kV-34.5, 36/48/60 MVA transformers with LTC to connect the larger hydroelectric generation and major new loads. | 2012-12-01 | Approved | 2011-06-07
NU-11-T03 | 2011-03-03 | North Simsbury Substation | Installation of a 115 kV tie breaker to split the existing 1784 line into two separate lines from the Northeast Simsbury Substation in North Simsbury, CT to the North Bloomfield Substation in North Bloomfield, CT and from the Northeast Simsbury Substation to the Canton Substation in Canton, CT. | 2013-06-01 | Approved | 2011-03-30
NEP-11-T02 | 2011-01-14 | Field Substation | Replacement of two 40 MVA 115/13.8 kV transformers with two 55 MVA 115/13.8 kV transformers at the Field Substation located in Quincy, MA. Install a 115 kV bus tie composed of one circuit switcher in series with one motor operated disconnect switch at Field St. Also addition of two 115 kV in-line breakers at Field St. substation on the 532N/533N lines (Field St. to North Quincy). Install two 115 kV circuit switchers on the 532S/533S lines (Edgar to Field St.). | 2014-05-01 | Approved | 2011-03-30
NEP-11-T03 | 2011-01-14 | North Quincy Substation | Installation of two 115 kV circuit switchers on the terminals of the 532N/533N lines (Field St. – North Quincy). Replacement of two 115 kV circuit switchers 1T115 and 2T115 at North Quincy Substation located in Quincy, MA. | 2014-05-01 | Approved | 2011-03-30
NSTAR-11-T04 | 2011-02-22 | Chelsea Substation | Installation of a new 115 kV, 36.7 MVAR shunt capacitor at the Chelsea Substation located in Chelsea, MA. The new capacitor bank is needed to support the sagging transmission voltages in the Chelsea -Revere load area for contingencies that result in the loss of 115 kV line 488-518 between Mystic and Chelsea. The Chelsea capacitor is also being installed as a part of the effort to meet Year 2011 ISO-NE Operating Procedure No.17 “Load Power Factor Correction” requirements for the Boston Load Power Factor Area. The main project components consist of the 36.7 MVAR capacitor and a 115 kV circuit breaker with a Synchronous Switching Controller. | 2011-11-01 | Approved | 2011-03-30
GRE-11-G01 | 2011-02-16 | Granite Ridge Generation Station | Revision to the generation capability of Granite Ridge Energy generation facility as stated on the original 18.4 application (NEP-00-G04) and approved September 2000. The revised Generator Notification is for 821 MWs Gross at 0 degrees and 678 MWs net at 90 degrees. | 2011-03-01 | Approved | 2011-03-30
NSTAR-11-G04 | 2011-03-04 | AD Makepeace Solar Generaton Station | Installation of a 3.6 MW photovoltaic generator located in Wareham, MA. Installation will be made to the NSTAR #83 23 kV distribution feeder out of the NSTAR Wareham Substation #714 | 2011-10-01 | Approved | 2011-03-30
NSTAR-11-T05 | 2011-03-07 | Line 336 Transmission Line/Medway Disconnect | Reconductor of the 345 kV Line 336 from ANP Blackstone to NEA Bellingham Tap. Upgrade five 345 kV disconnect switches at West Medway Station from 2000 Amp to 3000 Amp associated with Line 336 (four breaker disconnect switches – 101A, 101B, 102A, 102B and one line disconnect swotch T902). Upgrade the bussing CTs on the West Medway 345B auto transformer from 2000 Amp to 3000 Amp and upgrade the metering equipment at the West Medway Station associated with Line 336. | 2012-12-31 | Approved | 2011-03-30
CMP-11-T01 | 2011-03-04 | Saco Bay Transmission | Installation of a new 115 kV radial line from Louden Substation to a new Vallee Lane Substation located in Old Orchard Beach, ME. A new Goosefare distribution Substation will be tapped mid way. In addition, a 115/34 kV transformer will be installed at the Vallee Lane Substation and a 115/12 kV transformer will be installed at the Goosefare Substation. | 2012-12-01 | Approved | 2011-03-30
NEP-11-T05 | 2011-02-16 | Everett Substation | Replacement of two existing 115-13.8Y/7.96 24/32/40 MVA transformers with two 115-13.8Y/7.96 kV 33/44/55 MVA transformers and replace five 115 kV air breaks with five 115 kV circuit switchers located in Everett, MA. | 2013-11-01 | Approved | 2011-03-30
NU-11-T01 | 2011-01-26 | Oak Hill Substation | Installation of two 13.3 MVar capacitor banks at the Oak Hill 115 kV substation located in Concord County, NH. | 2012-12-01 | Approved | 2011-02-28
VELCO-11-T02 | 2011-02-07 | Vernon Substation | Relocate the existing fixed 60 MVAR 345 kV reactor from VELCO New Haven Substation to VELCO Vernon Substation. | 2011-12-01 | Approved | 2011-03-23
VELCO-11-T03 | 2011-02-07 | Coolidge Substation | Installation of two new 34 to 60 MVAR 345 kV variable reactors at the VELCO Coolidge Substation with reactor breakers. | 2011-10-01 | Approved | 2011-03-23
VELCO-11-T04 | 2011-02-07 | New Haven Substation | Replace the existing fixed 60 MVAR 345 kV reactor and reactor breaker with one new 34 to 60 MVAR 345 kV variable reactor at the New Haven Substation on the 370 Line. The existing reactor will be relocated to the Vernon Substation (reference VELCO-11-02). | 2012-01-01 | Approved | 2011-03-23
DEM-11-G01 | 2011-02-09 | Manchester Street Generation Station | Winter uprate of the Manchester Street generators 9/9A (ID #323), 10/10A (ID #321) and 11/11A (ID# 322) from 164 MWs (winter SCC) to 170 MWs (winter SCC). | 2011-02-01 | Approved | 2011-02-28
DEM-11-X01 | 2011-02-09 | Manchester Street Generating Station | Upgrade of the existing static exciters on the CT and ST generators 9/9A (ID #323), 10/10A (ID #321) and 11/11A (ID# 322). | 2011-03-01 | Approved | 2011-02-28
NSTAR-11-G06 | 2011-02-01 | O'Donnell Family Trust Wind Farm Generating Station | Installation of three 2.0 MW Gamesa G87-2.0 wind turbines (6 MWs total output) located in Kingston, MA. Wind turbines will interconnect to the NSTAR #14 23 kV feeder at the West Pond Substation. | 2011-06-01 | Approved | 2011-02-28
NU-11-G01 | 2010-01-28 | UMASS Generation Station | Installation of one 4MW steam turbine generator and one 2 MW steam turbine generator located in Amherst, MA. Generators will serve the campus load and will not export. The proposed generators are connected to the UMass Central Heating Plant which is supplied via the distribution feeders 18G1and 18G2 from the Podick 18G Substation. | 2011-02-16 | Approved Withdrawn | 2/28/2011 11/5/2011
NU-11-T02 | 2011-01-26 | Merrimack Substation | Installation of a 115 kV circuit breaker and a new manual disconnect switch at the Northeast Utilities Merrimack Substation between Bus #1 and the existing combustion turbine transformer MT3 located in Merrimack, NH. | 2011-12-01 | Approved | 2011-02-28
NSTAR-11-T02 | 2011-02-03 | 320-507 & 320-508 Transmission Lines | Reconductoring of 5.2 miles the overhead 320-507 and 320-508 115 kV lines from Lexington Station 320 in Lexington, MA to Waltham Station 282 in Waltham, MA. | 2012-06-01 | Approved | 2011-03-02
MMWEC-09-G01-Rev.1 | 2011-02-07 | Berkshire Wind Generation Station | Revise the resource from voltage control mode to power factor control mode for the ten GE 1.5 MW wind turbines (15 MWs net) located on Brodie Mt., Lanesboro, MA. | 2011-03-01 | Approved | 2011-03-02
NSTAR-11-G01 | 2011-02-10 | Falmouth Wind II Generation Station | Installation of a 1.65 MW Vestas Model V82 MKII wind turbine generator located in Falmouth, MA. Generator will interconnect at the NSTAR Falmouth Substation #933 23 kV feeder #98A. | 2011-01-15 | Approved Withdrawn | 3/2/2011 3/14/2023
NSTAR-11-G05 | 2011-02-10 | Dartmouth Solar Park Generation Station | Installation of a 1.6 MW photovoltaic generator located in Dartmouth, MA. Generator will interconnect at the NSTAR Industrial Park Substation #636, 13.2 kV feeder #107. | 2011-02-01 | Approved | 2011-03-02
VELCO-11-T01 | 2011-01-10 | Jay Tap Substation | Construction of a new 4 breaker ring substation connecting two 115 kV lines and two 115/46 kV step-down transformers. The substation will be located on the K-41 line, approximately 13 mi west of the Moshers Tap. The normally open point on the 46 kV system between Vermont and Canada will be at the Moshers Corner 359 Switch. | 2012-06-01 | Approved Withdrawn | 8/29/2011 7/23/2015
VELCO-10-X01 | 2011-01-10 | Vermont Yankee SPS | Removal of the Vermont Yankee capacitor bank Special Protection System (SPS). The VY capacitor bank SPS automatically disconnects the 30 MVAr 115 kV capacitor bank any time the VY T4 345/115 kV autotransformer trips. This SPS was originally proposed to prevent a high change in voltage (delta V) when switching the 30 MVAr capacitor bank with the T4 autotransformer out of service. With the addition of the Coolidge Connector project, primarily the new Vernon 345/115 kV autotransformer, the high delta V concern with one autotransformer out of service has been eliminated. | 2011-07-01 | Approved | 2011-02-07
VELCO-11-X02 | 2011-01-10 | Vernon Road | Removal of the Vernon Road Under Voltage Load Shedding (UVLS) scheme. The Vernon Road UVLS scheme automatically disconnects both transformers at Vernon Road when the station low side voltage drops below 0.91 pu. This UVLS scheme was originally proposed to mitigate low voltages on the PSNH system near Keene for certain contingencies, such as loss of the Vermont Yankee (VY) T4 345/115 kV autotransformer. Since the installation of the scheme, various upgrades have been implemented, and as a result, the UVLS scheme will not trigger even under N-1-1 contingency scenarios. The upgrades in chronological order are the Chestnut Hill capacitor banks, the VY capacitor banks, the Fitzwilliam 345/115 kV autotransformer, and the Coolidge Connector project, which includes the Newfane injection to the local 46 kV system near Vernon Road. | 2011-07-01 | Approved | 2011-02-07
FPLE-10-G01 | 2011-01-11 | Gulf Island Generation Station | Upgrade of the Gulf Island generating Units 1 & 3 (Asset ID# 328). Upgrades include replacement of turbine runner and rewinding of Unit 1 and replacement of turbine runner on Unit 3. Work will increase generation output from 33.6 MWs to 38.9 MWs. | 2010-12-08 | Approved | 2011-02-07
NSTAR-11-G02 | 2011-01-06 | AFCEE Wind Generation Station | Installation of two 1.5 MW GE Model 1.5SLE wind turbines (3 MW Net) and interconnecting at the Pave Paws 115/23 kV substation located in Bourne, MA. | 2011-11-01 | Approved | 2011-02-07
SRTC-11-G01 | 2011-01-06 | Indian Rivier Hydro Generation Station | Installation of a 1.3 MW hydro generator and interconnecting within a new automatic loop scheme between a sectionalized recloser on the 19J1 circuit and a tie recloser between the 19J1 and 19 J2 circuit, supplied from the Blandford substation located in Russell, MA. | 2011-01-01 | Approved | 2011-02-07
NSTAR-11-T01 | 2011-01-07 | Mendall Rd Tap Station, Rochester Substation, Harwich Tap Sation | Installation of seven new 2000 ampere, 115 kV SEECO motor operated autosectionlizing switches with dead end detection | 2012-01-01 | Approved | 2011-02-07
NEP-11-T01 | 2011-01-07 | A127/B128W Transmission Line | 67 miles of overhead reconductoring of the B128W and 50 miles of overhead reconductoring for portions of the A-127W 115 kV lines from Harriman Substation in Readsboro, VT to Structure 510 in Milbury, MA. | 2014-11-01 | Approved | 2011-02-07
NEP-10-T12 | 2010-12-03 | S9 Transmission Line | Reconductor of the S9 115 kV Transmission Line from Plymouth St. to Water St. Tap. Create a loop from the 115 kV lines C3 and S9 by installing two new 115 kV breakers at Phillips Lane Substation #95 and operating the Norwell Substation #96 motor operated load break S9961 in a normally closed position. | 2013-10-01 | Approved | 2010-12-27
NEP-10-T06 | 2010-12-03 | Norwell Substation | Replacement of the existing 115/13.8Y/7.96 kV 15/20/25 MVA LTC transformer with a 115/13.8Y/7.96 kV 24/32/40 MVA LTC transformer and add a new 1200A – 20 kA 115 kV circuit switcher and update corresponding relays and controls at the Norwell Substation. | 2011-06-01 | Approved | 2010-12-27
NEP-10-G01 | 2010-12-02 | Douglas Woods Wind Farm Generation Station | Construction of the Douglas Woods Wind Farm consisting of twelve 2.5 MW wind turbines with a total output power of 30 MWs located in Douglas, MA. | 2012-12-01 | Approved Withdrawn | 12/27/2010 9/18/2013
NEP-10-T11 | 2010-12-02 | Douglas Woods Wind Farm Substation | Construction of a new interconnection substation with a single breaker and two load-break switches located in Webster, MA. In addition, construction of two new 69 kV line taps connecting the interconnecting substation to the S-19 69 kV transmission line. Connect the interconnection substation to the proposed generator substation. Upgrade the relaying for S-19 and T-20 line at Millbury and Meadow Street. | 2012-12-01 | Approved Withdrawn | 12/27/2010 9/18/2013
NEP-10-T13 | 2010-12-02 | Douglas Woods Wind Farm Substation | Construction of a new generator 69/34.5 kV substation with a 69/34.5, 18/24/30 MVA transformer and 34.5 kV switchgear to interconnect the proposed 30 MW Douglas Wind Farm | 2012-12-01 | Approved Withdrawn | 12/27/2010 9/18/2013
NEP-10-T02 | 2010-12-01 | G185S Transmission line | Upgrade of the existing 115 kV transmission line from Kent County substation to Davisville tap. In addition, replace 5.3 miles of 795 ACSR conductor to 954 ACSS. | 2013-10-01 | Approved | 2010-12-27
NSTAR-10-T07 | 2010-11-03 | Barnstable Substation | Expansion of the Barnstable 115 kV Substation with a 5th bay. The existing Barnstable – Hyannis #124 line will be reconnected to the new 5th bay position and the second Barnstable-Hyannis #123 line will be reconnected to the present #124 line position. | 2012-12-01 | Approved | 2010-11-22
CMP-10-T04 | 2010-11-01 | Hotel Road Substation | Replacement of one 115 kV automatic sectionalized switch with a 115 kV circuit breaker and the addition of a second 20/37 MVA 115/34.5 kV transformer at the Hotel Road Substation. | 2011-02-01 | Approved | 2010-11-22
UI-08-T05-Rev. 1 | 2010-11-01 | Grand Avenue Switching Station | Revision of PPA UI-08-T05 as approved by the Reliability Committee on December 18, 2008. PPA revision reflects a repositioning of some bays of the proposed breaker and a half configuration. | 2010-12-01 | Approved | 2010-11-22
PP-06-T01 | 2010-10-27 | Waterside Generation Station | Intent to withdraw PP-08-T01 due to the withdrawal of the Waterside Generator and Transmission Project. | 2010-12-01 | Approved Withdrawn | 07/25/2006 11/17/2006
PP-06-G01 | 2010-10-27 | Waterside Generation Station | Intent to withdraw PP-08-G01 due to the withdrawal of the Waterside Generator and Transmission Project. | 2010-12-01 | Approved Withdrawn | 07/25/2006 11/17/2006
CMP-10-T03 | 2010-11-01 | Bowman Street Substation | Addition of a second 20/37 MVA 115/34.5 kV transformer at Bowman Street Substation. | 2011-02-01 | Approved | 2010-11-22
NEP-10-T08 | 2010-10-27 | Meadowbrook Substation | Installation of two new 115/13.2 kV 33/44/55 MVA transformers tapped off the A-153 and I-161 lines and installation of two 115 kV circuit switchers at the Meadowbrook Substation located in Chelmsford, MA. Project upgrades tow radial 115 kV lines; I161 and A-153 to 795 ACSS from Sandy Pond, Tewksbury to Meadowbrook | 2014-06-01 | Approved | 2010-11-22
NU-09-T01-Rev.1 | 2010-11-09 | Eliot Switching Station | In conjunction with the MPRP Project, a name change of a 345 kV switching station changing from Three Rivers to Eliot and a change of the in service date of the project from June 2012 to December 2013. | 2013-12-01 | Approved | 2010-11-22
CMP-09-T05 | 2010-11-09 | Browns Crossing Substation | Withdrawal of the Browns Crossing Substation to remove the existing 115/12.47 kV substation and replace it with a 34.5 kV distribution substation, to make room on the right-of-way for new facilities. Browns Crossing load will be fed 34.5 kV out of Bowman Street. | 2010-12-01 | Approved | 2010-11-22
CMP-08-T29-Rev.1 | 2010-11-09 | Section 80 Transmission Line | Withdrawal of the Rebuild Existing Transmission Line Section 80, entire 23 miles from Coopers Mills Substation to Highland Substation, to create space in the Right-Of-Way to facilitate construction of new facilities. | 2010-12-01 | Approved | 2010-11-22
CMP-08-T23-Rev.1 | 2010-11-09 | Cape Substation | Withdrawal of the Cape Substation to add a new 115 kV breaker at the existing Cape Substation for terminating the new 115 kV line Section 263 from East Deering Substation. | 2010-12-01 | Approved | 2010-11-22
CMP-08-T12-Rev.1 | 2010-11-09 | Maine Yankee Substation | Withdrawal of the Maine Yankee 345 kV Substation to add a third bay to the existing breaker-and-a-half Substation, add four new 345 kV breakers, and re-terminate line Sections 375, 377, and 392. | 2010-12-01 | Approved | 2010-11-22
CMP-08-T10-Rev.1 | 2010-11-09 | East Deering Substation | Withdrawal of the East Deering Substation to construct a new three-breaker 115 kV ring bus for terminating a new 115 kV transmission line Section 262 from Raven Farm Substation and terminating a new 115 kV underground transmission line Section 263 approximately 4 miles in length to existing Cape Substation, and providing termination for a 115/34 kV transformer to serve the local area distribution system. | 2010-12-01 | Approved | 2010-11-22
CMP-08-T09-Rev.1 | 2010-11-09 | Highland Substation | Withdrawal of the Highland Substation to add a new 115 kV breaker at Highland to re-terminate Section 226 from Newcastle Substation. Terminate new 115 kV line Section 244 from Coopers Mills to previous Section 226 location. | 2010-12-01 | Approved | 2010-11-22
CMP-09-T07-Rev.1 | 2010-11-09 | Section 250 Transmission Line | Rebuild of the first 10 miles of existing Section 250 out of Three Rivers Substation to create space in the Right-Of-Way to facilitate construction of new facilities. Total Section 250 line distance is 19.5 miles, with remaining 9.5 miles composed of 795 kcmil ACSR 36/1 Coot conductor. | 2013-04-01 | Approved | 2010-11-22
CMP-09-T06-Rev.1 | 2010-11-09 | Section 160 Transmission Line | Reconductor of 1.1 miles of existing Section 160 out of Cape Substation to Hinckley Pond Substation for thermal capacity. | 2013-12-01 | Approved | 2010-11-22
CMP-09-T03-Rev.1 | 2010-11-09 | Monmouth Substation | Construct a new 115 kV Monmouth Substation consisting of two 115 kV breakers to split the existing Section 212 into two segments. Terminate Section 212 from Larrabee Road, terminate Section 269 from Bowman Street, and terminate two distribution transformers. This substation will serve the load presently served from Days Corner and Wales Corner Substations, which will be retired, along with the removal of 21.6 miles of 34 kV Section 41. | 2012-09-01 | Approved | 2010-11-22
CMP-09-T02-Rev.1 | 2010-11-09 | Middle Street Substation | Construct a new five breaker 115 kV Substation, configured initially as a ring-bus, to terminate a new 115 kV line Section 255 to Larrabee Road Substation, a new 115 kV underground circuit Section 256 to Lewiston Lower Substation, and three distribution transformers. | 2012-07-01 | Approved | 2010-11-22
CMP-08-T36-Rev.2 | 2010-11-09 | Section 212 Transmission Line | Rebuild of the entire 21.9 miles of existing Section 212, from Bowman Street Substation to the new Larrabee Road Substation to create space in the Right-Of-Way to facilitate construction of new facilities. The rebuilt line will terminate at Monmouth S/S and be renamed to Section 269 between Bowman Street and Monmouth. | 2012-08-01 | Approved | 2010-11-22
CMP-08-T35-Rev.2 | 2010-11-09 | Section 229 Transmission Line | Rebuild of the first 13.9 miles of existing Section 229 from Rumford IP Substation to Riley Substation to create space in the Right-Of-Way to facilitate construction of new facilities. Total Section 229 line distance is 15.2 miles with the remaining 1.3 miles composed of 795 kcmil ACSR 36/1 Coot conductor. | 2012-02-01 | Approved | 2010-11-22
CMP-08-T34-Rev.2 | 2010-11-09 | Section 89 Transmission Line | Rebuild of the first 5.1 miles of existing Section 89 from Livermore Falls Substation to Riley Substation, to create space in the Right-Of-Way to facilitate construction of new facilities. Total Section 89 line distance is 7.4 miles, with the remaining 2.3 miles composed of 795 kcmil ACSR 36/1 Coot conductor. | 2011-10-01 | Approved | 2010-11-22
CMP-08-T33-Rev.2 | 2010-11-09 | Section 88 Transmission Line | Rebuild of the first 4.9 miles of existing Section 88 out of Coopers Mills Substation to create space in the Right-Of-Way to facilitate construction of new facilities. Total Section 88 line distance from Coopers Mills to Augusta East Side is 11 miles, with the remaining 6.1 miles composed of 795 kcmil ACSR 36/1 Coot conductor. | 2011-12-01 | Approved | 2010-11-22
CMP-08-T32-Rev.2 | 2010-11-09 | Section 60 Transmission Line | Rebuild of the entire 12.4 miles of existing Section 60 from Coopers Mills Substation to Bowman Street Substation to create space in the Right-Of-Way to facilitate construction of new facilities. | 2011-11-01 | Approved | 2010-11-22
CMP-08-T31-Rev.2 | 2010-11-09 | Section 167 Transmission Line | Rebuild of the first 3.0 miles of existing Section 167 out of Surowiec Substation to create space in the Right-Of-Way to facilitate construction of new facilities. Total Section 167 line distance from Surowiec to Moshers is 21.0 miles, with the remaining 18.0 miles composed of 795 kcmil ACSR 36/1 Coot conductor (16.9 miles) and 795 kcmil ACSR 26/7 Drake conductor (1.1 miles). | 2011-06-01 | Approved | 2010-11-22
CMP-08-T30-Rev.1 | 2010-11-09 | Section 166 Transmission Line | Rebuild of the first 3.2 miles of existing Section 166 out of Surowiec Substation to create space in the Right-Of-Way to facilitate construction of new facilities. Total Section 166 line distance from Surowiec to Spring Street is 24.2 miles, with the remaining 21.0 miles composed of 795 kcmil ACSR 36/1 Coot conductor (19.8 miles) and 795 kcmil ACSR 26/7 Drake conductor (1.21 miles). | 2011-08-01 | Approved | 2010-11-22
CMP-08-T26-Rev.2 | 2010-11-09 | Section 203 Transmission Line | Rebuild of the first 25 miles of existing Section 203 out of Detroit Substation to create space in the Right-Of-Way to facilitate construction of new facilities. Total Section 203 line distance from Detroit to Bucksport is 34.1 miles, with the remaining 9.1 miles composed of 795 kcmil ACSR 36/1 Coot conductor (8.6 miles) and 795 kcmil ACSR 30/19 Mallard conductor (0.5 miles). | 2012-02-01 | Approved | 2010-11-22
CMP-08-T24-Rev.2 | 2010-11-09 | Section 66 Transmission Line | Rebuild of the first 1.8 miles of existing Section 66 out of Detroit Substation to create space in the Right-Of-Way to facilitate construction of new facilities. Total Section 66 line distance from Detroit to Wyman Hydro is 33.4 miles, with the remaining 31.6 miles composed of 795 kcmil ACSR 36/1 Coot conductor. | 2011-03-01 | Approved | 2010-11-22
CMP-08-T22-Rev.2 | 2010-11-09 | Livermore Falls Substation | Livermore Falls Substation to construct a three-bay breaker-and-a-half substation with eight 115 kV breakers to terminate existing Sections 63 from Sturtevant, 89 from Riley, 200 from Larrabee Road, and new Sections 251 from Larrabee Road and 243A from Rumford IP; and termination of existing 115/34.5 kV and 115/12 kV distribution transformers to serve the local distribution load. | 2013-07-01 | Approved | 2010-11-22
CMP-08-T21-Rev.3 | 2010-11-09 | Rumford Industrial Falls Substation | Install two new 115 kV line switches on the proposed CMP 115 kV Section 243 from Rumford 115 kV Substation to Rumford IP Substation to create a junction near Rumford IP Substation. Install a third 115 kV line switch to terminate a new 115 kV transmission line Section 243A from Livermore Falls at the junction of Section 243. | 2012-08-01 | Approved | 2010-11-22
CMP-08-T19-Rev.2 | 2010-11-09 | Larrabee Road Substation | Construct a new 345 kV and 115 kV substation to NPCC BPS standards. Construct a two-bay breaker-and-a-half substation with six 345 kV breakers to terminate new 345 kV transmission line Sections 3025 from Coopers Mills Substation and 3026 from Surowiec Substation; and termination of a new 240/448 MVA 345/115/13.8 kV autotransformer with two 40 MVAR reactors connected on the tertiary winding. Construct a five-bay breaker-and-a-half substation with fifteen 115 kV breakers to terminate existing Sections 61 from Norway, 64 from Surowiec, 200 from Livermore Falls, 201 from Crowleys, 212 from Monmouth (new substation), and 268 from Gulf Island and new Sections 251 from Livermore Falls and Sections 255 from Middle Street; and relocation of an existing 30 MVAR switched capacitor bank. | 2014-08-01 | Approved | 2010-11-22
CMP-08-T18-Rev.2 | 2010-11-09 | Gulf Island Substation | Remove terminations for existing 115 kV line Sections 61, 64, 200, 201, and 212 (reterminate at new Larrabee Road Substation). Relocate 30 MVAR 115 kV capacitor bank to new Larrabee Road Substation. Section 268 from Larrabee Road Substation to Gulf Island Substation will supply the existing 115/34.5 kV transformer at Gulf Island. Section 268 is a partially new 115 kV transmission line comprised of a 1.0 mile segment from the old Section 212 with 795 kcmil ACSR 36/1 Coot conductor and a 0.4 mile segment of new 115 kV overhead transmission line built with 1113 kcmil ACSR 45/7 Bluejay conductor. | 2013-05-01 | Approved | 2010-11-22
CMP-08-T17-Rev.2 | 2010-11-09 | Lewiston Lower Substation | Remove existing 115/34.5 kV transformer (T5) and terminations. Add a new 115 kV breaker to terminate the new 115 kV underground Section 256 from the new Middle Street Substation. | 2012-06-01 | Approved | 2010-11-22
CMP-08-T16-Rev.2 | 2010-11-09 | Maguire Road Substation | Construct a new 345 kV Switchyard to NPCC BPS standards. Construct a two-bay breaker-and-a-half substation with six 345 kV breakers to terminate new 345 kV transmission line Sections 3021 from South Gorham Substation and 3022 from Eliot Substation; and termination of a new 240/448 MVA 345/115/13.8 kV autotransformer. Construct an additional breaker-and-a-half bay onto existing 115 kV substation with addition of two new 115 kV breakers to terminate autotransformer. New 345 kV transmission line Section 3021 is approximately 21 miles in length to South Gorham Substation and new 345 kV transmission line Section 3022 approximately 19.2 miles in length to the Eliot Switching Station. | 2011-12-01 | Approved | 2010-11-22
CMP-08-T15-Rev.2 | 2010-11-09 | South Gorham Substation | Construct a new 345 kV and 115 kV substation to NPCC BPS standards. (Note: South Gorham exists today as a tap to Section 386 and is designed and built to BPS standards), and shall consist of an eight-breaker 345 kV three-bay breaker-and-a-half bus configuration and provide termination for a new 345 kV transmission line Section 3021 approximately 21 miles in length to Maguire Road Substation, provide for terminating the existing line Sections 3040 to Raven Farm Substation and 386 to Buxton Substation, provide for the termination of one existing 240/448 MVA 345/115/13.8 kV autotransformer (T1) and the termination of a second new 240/448 MVA 345/115/13.8 kV autotransformer (T2) with low-side (115 kV) breaker. Replace twelve existing 115 kV definite purpose breakers with Independent Pole Tripping (IPT) breakers to mitigate short-circuit and TRV requirements (K219-1, K220-1, K223-1, KT1L, K162/219, K169/220, K223/231, K162-3, K169-3, K231-1, KT2L, KB2/CAP). Also, rebuild 1.7 miles of existing Section 238 between Louden and Maguire Road to create space in the Right-Of-Way to facilitate construction of new facilities. | 2011-07-01 | Approved | 2010-11-22
CMP-08-T13-Rev.2 | 2010-11-09 | Surowiec Substation | Add eight new 345 kV breakers, with one of these new breakers an upgrade of breaker K374/377 to Independent Pole Tripping (IPT) capability, to the existing 345 kV bus to create a four-bay, breaker and-a-half configuration; terminate a new 345 kV transmission line Section 3026 from the new Larrabee Road Substation; terminate a new 345 kV transmission line Section 3020 from the new Raven Farm Substation; and split line Section 375 into two line segments, Section 375 to Maine Yankee Substation and Section 3038 to Buxton Substation, and terminate both line Sections into the new Surowiec 345 kV bus arrangement. Provide termination for the two existing 345 kV transmission lines Section 374 and Section 377, and the existing 240/448 MVA 345/115/13.8 kV autotransformer (T1). In addition, install one 115 kV breaker to create a two breaker bay for terminating Section 208 from Raymond Substation. | 2013-04-01 | Approved | 2010-11-22
CMP-08-T08-Rev.2 | 2010-11-09 | Belfast 115 kV Substation | Addition of two 115 kV breakers to the existing 115 kV bus to split Section 86 into two segments and build new 115 kV line from the right-of-way into the Belfast Substation. This will allow for termination of Section 86 from Bucksport Substation and Section 266 from Lincolnville. Addition of a 10.8 MVAR capacitor bank and associated breakers on the 34.5 kV bus. | 2014-09-01 | Approved | 2010-11-22
CMP-08-T04-Rev.2 | 2010-11-09 | Albion Road Substation | Construct a new 345 kV and 115 kV substation to NPCC BPS standards. Construct a three breaker 345 kV ring bus to terminate new 345 kV transmission line Sections 3023 from Orrington Substation and 3024 from Coopers Mills Substation; and termination of a new 240/448 MVA 345/115/13.8 kV autotransformer with two 40 MVAR reactors connected on the tertiary winding. Construct a four-bay breaker-and-a-half substation with ten 115 kV breakers to terminate existing Sections 67 from Detroit, 84 from Winslow, 259 (formerly 67A) from Heywood Road, 257 (formerly 67) from Coopers Mills and 258 (formerly 84) from Coopers Mills | 2014-03-01 | Approved | 2010-11-22
CMP-10-T07 | 2010-11-09 | Section 375/377 Double Circuit Tower | Section 377 will be removed from the double circuit structures with Section 375 and added to a new double circuit structure that will also accommodate 115 kV Section 81 for 2.5 miles. | 2013-06-01 | Approved | 2010-11-22
CMP-10-T06 | 2010-11-09 | Section 65/205 Double Circuit Tower | Separation from Bucksport Substation to Orrington Substation. | 2012-12-01 | Approved | 2010-11-22
CMP-10-T05 | 2010-11-09 | Norway Substation | Replace existing 115 kV line switch 61-4 and circuit switcher K87-1 at Norway Substation with 115 kV circuit breakers to terminate existing Section 61/61A to Larrabee Road and Hotel Road Substations, and Section 87 to Kimball Road Substation. This substation will continue to serve the load presently served from Norway’s 34.5 kV and 12 kV busses. | 2014-09-01 | Approved | 2010-11-22
CMP-10-X04 | 2010-11-09 | Orrington T1 SPS | Retirement of the Orrington T1 Special Protection System (SPS), NPCC #182 – Type III. | 2014-07-01 | Approved | 2010-11-22
CMP-10-X03 | 2010-11-09 | Bucksport 65/205/Reverse Power SPS | Retirement of the Bucksport 65/205 Reverse Power Special Protection System (SPS), NPCC #22 – Type III. | 2014-07-01 | Approved | 2010-11-22
CMP-10-X02 | 2010-11-09 | Section 386 SPS | Retirement of the Section 386 Temporary Special Protection System (SPS), NPCC #198 – Type I. | 2012-12-01 | Approved | 2010-11-22
CMP-10-X01 | 2010-11-09 | Maxcy/Bucksport SPS | Retirement of the Maxcys - Bucksport Special Protection System (SPS), NPCC #178 – Type I. | 2014-07-01 | Approved | 2010-11-22
CMP-09-T04-Rev.1 | 2010-11-09 | Spring Street Substation | Remove terminations for 115 kV Sections 232 from Westbrook Substation and Section 234 from Redbrook and connect these two circuits together in Right-of-Way. The newly formed circuit connecting Westbrook to Redbrook will be designated as Section 234. | 2014-12-01 | Approved | 2010-11-22
CMP-08-T37-Rev.2 | 2010-11-09 | Section 86 Transmission Line | Rebuild of an 8.7 mile portion and reconductor a 0.5 mile portion of existing Section 86 between Bucksport Substation and Section 86A tap and new 0.25 mile line into Belfast 115 Substation to uprate thermal capacity. The reconductor preserves the existing structures that comprise the Penobscot River crossing leaving Bucksport. Total Section 86 line distance from Bucksport to Belfast is 15.7 miles, with the remaining 6.2 miles composed of 1272 kcmil AAC 61/0 Narcissus. | 2011-05-01 | Approved | 2010-11-22
CMP-08-T25-Rev.2 | 2010-11-09 | Section 67 Transmission Line | Rebuild of the first 1.8 miles of existing Section 67 out of Detroit Substation and additional 1.3 mile and 0.3 mile segments to create space in the Right-Of-Way to facilitate construction of new facilities. Total Section 67 line distance from Detroit to Albion Road is 19.4 miles, with the remaining 16.0 miles composed of 795 kcmil ACSR 26/7 Drake conductor. Rebuild segments totaling 10.4 miles of Section 67 between Albion Road and Coopers Mills Substation which is redesignated to Section 257 to create space in the Right-Of-Way to facilitate construction of new facilities. Total Section 257 line distance from Albion Road to Coopers Mills is 21.2 miles, with the remaining 10.8 miles composed of 795 kcmil ACSR 26/7 Drake conductor. | 2011-02-01 | Approved | 2010-11-22
CMP-08-T27-Rev.2 | 2010-11-09 | Section 84 Transmission Line | Rebuild of a 12.3 mile portion of existing Section 84 between Coopers Mills Substation and Albion Road Substation (now designated Section 258) and utilize 8.9 miles of existing Section 67 to create space in the Right-Of-Way to facilitate construction of new facilities. The remaining 4.7 miles from Albion Road Substation to Winslow Substation is unchanged and remains designated Section 84. | 2014-10-01 | Approved | 2010-11-22
CMP-08-T14-Rev.2 | 2010-11-09 | New Raven Farm Substation | Construct a new 345 kV substation to NPCC BPS standards. Construct a two-bay breaker-and-a-half substation with four 345 kV breakers to terminate existing 345 kV transmission line Sections 3040 from South Gorham and 3039 from W.F. Wyman Substations (Section 386 between South Gorham and W.F. Wyman split into two segments – 3039 and 3040) and new 345 kV transmission line Section 3020 to Surowiec Substation. The Raven Farm Substation shall be operated as a ring bus but configured for a future full breaker-and-a-half layout. | 2013-03-01 | Approved | 2010-11-22
CMP-08-T11-Rev.2 | 2010-11-09 | Coopers Mill Substation | Construct a new 345 kV and 115 kV substation to NPCC BPS standards and replace the existing Maxcys Substation. Construct a three-bay breaker-and-a-half substation with nine 345 kV breakers to terminate existing 345 kV transmission line Sections 388 from Orrington Substation and 392 from Maine Yankee Substation and new 345 kV transmission line Sections 3024 from Albion Road Substation and 3025 from Larrabee Road Substation; and termination of a new 240/448 MVA 345/115/13.8 kV autotransformer with two 40 MVAR reactors connected on the tertiary winding. Construct a five-bay breaker-and-a-half substation with fifteen 115 kV breakers to terminate existing Sections 80 from Highland, 60 from Bowman St., 68 from Mason, 88 from Augusta East Side, 257 (formerly 67) from Albion Road and 258 (formerly 84) from Albion Road and new Section 254 from Orrington; termination of existing 115/34.5 kV distribution transformer; and termination of the two existing 50 MVAR switched capacitor banks. | 2014-08-01 | Approved | 2010-11-22
CMP-08-T03-Rev.2 | 2010-11-09 | Orrington Substation | Install one 345 kV breaker in existing two-bay breaker-and-a-half for retermination of existing 345 kV line Section 388 from Coopers Mills Substation (formerly Maxcys) which will also utilize partial new construction to location in Right-of-Way near the junction of 115 kV Section 203. The new Section 3023 between Orrington Substation and Albion Road Substation (to pass by Detroit Substation with no termination) will utilize the existing structures and conductors of Section 388 from Orrington to the junction of Section 203. Install two 115 kV breakers in a new fourth-bay of the breaker-and-a-half substation, and build a new 115 kV line, Section 254, from Orrington to Coopers Mills Substation. 2.4 miles of existing Section 388 (portion which will become 3023) will be rebuilt at the vicinity of the Penobscot River crossing to make room on right-of way for Section 254 which will utilize existing river crossing portion of Section 388. | 2014-07-01 | Approved | 2010-11-22
UI-10-T02 | 2010-10-22 | New Haven Harbor Transmission Line | Terminate and connect the 115 kV underground line connecting the New Haven Harbor Peaking Plant to the East Shore 115 kV Substation with the installation of two additional 115 kV 3000 A 63 kA circuit breakers at East Shore 115 kV Substation to accommodate the generation interconnection. | 2012-06-01 | Approved | 2010-11-22
PSEG-10-T01 | 2010-10-22 | New Haven Harbor Transformer | Installation of a 13.8/115 kV Step Up Transformer and 1000 ft. underground transmission interconnection to the East Shore 115 kV Substation. | 2012-06-01 | Approved | 2010-11-22
PSEG-10-G01 | 2010-10-22 | New Haven Harbor Generator | Construction and interconnection of three GE LM6000 gas turbine generators each rated at 71.176 MVA and 51 MWs. Total gross output totals for a 153 MW located in New Haven, CT. | 2012-06-01 | Approved | 2010-11-22
VELCO-10-T06 | 2010-10-29 | Bennington Substation | Rebuild of the existing straight bus Bennington substation to a new 6 breaker ring substation connecting two 115 kV lines, one 115/69 kV transformer and two 115/46 kV step down transformers. | 2013-03-01 | Approved | 2010-11-22
VELCO-10-T05 | 2010-10-29 | Ascutney Substation | Rebuild of the existing straight bus Asuctney substation to a new 6 breaker ring substation connecting four 115 kV lines and a 115/46 kV step down transformer. | 2013-03-01 | Approved | 2010-11-22
VELCO-10-T04 | 2010-10-29 | Georgia Substation | Rebuild of the existing straight bus Georgia substation to a new 6 breaker ring substation connecting four 115 kV lines, one 25 MVAR capacitor bank and a future 115/34.5 kV step down transformer (to be added one year later). | 2013-03-01 | Approved | 2010-11-22
NU-10-T20 | 2010-10-12 | 310-348 & 371-383 Double Circuit Towers and Retire Milstons SLOD SPS | Split the 310-348 and 371-383 double circuit towers and eliminate the associated double circuit tower contingencies. The 310-348 double circuit tower construction extends north out of the Millstone 345-kV Substation approximately four miles while the 371-383 double circuit tower construction extends north out of Millstone 345-kV Substation approximately two miles. Project includes change in conductor type on #310 circuit to 2-1272 ACSS and #371 circuit to 2-954 ACSS. This Project will include the retirement of the Millstone Severe Line Outage Detection (SLOD) Special Protection System (SPS) once the configuration of the 345-kV lines has been completed. The SLOD SPS is a Northeast Power Coordinating Council (NPCC) Type I SPS (NPCC SPS #23). | 2013-12-01 | Approved | 2010-11-02
NMLD-10-T02 | 2010-10-08 | Dean Street 495 Substation | Replace aging transformers A & B and install new transformer D. Also install 5th and 6th circuit breakers in existing 115 kV ring bus to interconnect third transformer. | 2010-11-30 | Approved | 2010-11-02
NMLD-10-T01 | 2010-10-08 | Ellis Avenue 469 Substation | Expansion of the Ellis Ave. #469 Substation in Norwood, MA, to add six 13.8 kV distribution feeders for use by NSTAR. Install third 33/44/55 MVA, 115 kV to 13.8 transformer and related 115 kV switching equipment. Also install 5th and 6th circuit breakers in existing 115 kV ring bus to interconnect third transformer. | 2010-11-05 | Approved | 2010-11-02
RMLD-10-T01 | 2010-09-27 | Reading 494 Substation | Replacement of three existing Reading 115/13.8 kV transformers at the Reading 494 Substation with larger transformers (36/48/60 MVA). | 2010-10-01 | Approved | 2010-11-02
VELCO-10-T03 | 2010-10-04 | Essex Switch | Operate the Essex #230 switch normally closed. | 2011-03-01 | Approved | 2010-11-22
VELCO-10-T02 | 2010-10-04 | West Rutland Substation | Installation of two 25 MVAR capacitor banks at the West Rutland 115 kV substation to resolve criteria violations for contingencies, in particular the loss of the Coolidge – West Rutland 345 kV line. | 2012-03-01 | Approved | 2010-11-22
BHE-10-T03 | 2010-10-01 | Orrington Substation | Add a series breaker adjacent to existing Orrington breaker K396-1 such that a line fault on 396 and a stuck breaker K396-1 would not result in the loss of the Orrington T1 autotransformer, potentially resulting in loss of all three autotransformers on the BHE system. | 2012-12-01 | Approved | 2010-10-22
BHE-10-T02 | 2010-10-01 | Keene Road Substation | Installation of a top rated 300MVA autotransformer between the Keene Rd 345kV and Keene Rd 115kV facilities. This includes the addition of several breakers at the Keene Rd 115kV substation to complete the breaker and half scheme as well as the enabling of transmission protection schemes at the Keene Rd 345kV substation such that the 396 and 3001 line sections will operate independently. The circuit breaker between the Chester SVC and the new autotransformer will be operated normally open. This PPA compliments previously approved BHE-10-T01 to complete the Keene Rd facility. | 2010-12-01 | Approved | 2010-10-22
NU-10-T19 | 2010-08-24 | Southwick Substation | Replace two existing transformers (115/14.4 kV (1X) and 114/13.8 kV (2X)) at the Southwick 29A substation. New transformers will be rated at 110/23 kV. The proposed in service date for the 2X transformer is 2011 and the proposed in service date for the 1X transformer is 2013. | 2011 & 2013 | Approved | 2010-09-28
BHE-10-G01 | 2010-09-14 | PPL Great Works Generation Station | Reconnect 9.5MW gas turbine “behind the fence” generation at a mill complex in Old Town Maine (aka Red Shield/Old Town – Asset ID#12163). The facility presently has ISO-NE approval to export up to 16MW and requests the ability to not only interconnect the noted generator, but to expand this export capability to 27.1 MWs. | 2010-09-30 | Approved | 2010-09-28
NU-10-T09 | 2010-09-03 | Agawam 16C Substation | Modifications at Agawam 16C 115-kV substation to make it NPCC Bulk Power System (BPS) compliant. This is required for the Pioneer Valley Energy Center generator to interconnect to the pre-NEEWS/GSRP system. | 2013-12-01 | Approved Withdrawn | 11/2/2010 12/18/2012
NU-10-T08 | 2010-09-03 | East Springfield 5J Substation | Modifications at East Springfield 5J substation to make it NPCC Bulk Power System (BPS) compliant. This is required for the Pioneer Valley Energy Center generator to interconnect to the pre-NEEWS/GSRP system. | 2013-12-01 | Approved Withdrawn | 11/2/2010 12/18/2012
NU-10-T07 | 2010-09-03 | Buck Pond 34B Substation | Upgrade the following terminal equipment at Buck Pond substation for the 1657 (Buck Pond to Southampton Jct.) line terminal to match or exceed the conductor ratings: substation conductor, manual switch, wave trap, primary and back up relays and metering. Upgrading the terminal equipment will result in the 1657 (Buck Pond to Southampton Jct.) line conductor being the limiting facility. | 2013-12-01 | Approved Withdrawn | 11/2/2010 12/18/2012
NU-10-T06 | 2010-09-03 | Buck Pond 34B Substation | Upgrade the following terminal equipment at Buck Pond 34B substation for the 1302 (Buck Pond to PVEC) line terminal to match or exceed the conductor ratings: substation conductor, manual switch, wave trap, primary and backup relays and metering. Upgrading the terminal equipment will result in the 1302 (Buck Pond to PVEC) line conductor being the limiting facility. This assumes that the Pioneer Valley Energy Center generator will back down its generation (manually) in 15 minutes such that the loading is below the line LTE rating during emergency operating conditions. | 2013-12-01 | Approved Withdrawn | 11/2/2010 12/18/2012
NU-10-T05 | 2010-09-03 | Agawam 16C Substation | Upgrade the following terminal equipment at Agawam 16C substation for the 1302 (Agawam to Pochassic tap) line terminal to match or exceed the conductor ratings: substation conductor, manual switch, wave trap, Watt/VAR transducer inside breaker 16C-35T-2 control cabinet, primary and backup relays and metering. Upgrading the terminal equipment will result in the 1302 (Agawam to Pochasstap) line conductor being the limiting facility. This assumes that the Pioneer Valley Energy Center generator will back down its generation (manually) in 15 minutes such that the loading is below the line LTE rating during emergency operating conditions upgrade the following terminal equipment at Buck Pond 34B substation for the 1302 (Buck Pond to PVEC) line terminal to match or exceed the conductor ratings: substation conductor, manual switch, wave trap, primary and backup relays and metering. Upgrading the terminal equipment will result in the 1302 (Buck Pond to PVEC) line conductor being the limiting facility. This assumes that the Pioneer Energy Center generator will back down its generation (manually) in 15 minutes such that the loading is below the line LTE rating during emergency operating conditions. | 2013-12-01 | Approved Withdrawn | 11/2/2010 12/18/2012
NU-10-T04 | 2010-09-03 | Fairmont 16H Switching Station | Fairmont 16H switching station to be NPCC Bulk Power System (BPS) compliant by adding a second DC system. This is required for the Pioneer Valley Energy Center generator to interconnect to the post-NEEWS/GSRP system. | 2013-12-01 | Approved Withdrawn | 11/2/2010 12/18/2012
NU-10-T03 | 2010-09-03 | Pioneer Valley Switching Station | Installation of a new four breaker 115 kV switching station in a ring bus configuration consisting of four 115 kV 40 kA circuit breakers associated breaker disconnects, control house, and protection and controls. Loop line 1302 (between Buck Pond and Pochassic tap) into the new switching station and terminate to establish new lines from Buck Pond 34B substation to PVEC switching station (length approximately 1.0 mile) and from Pochassic substation tap to PVEC switching station (length approximately 2.12 miles). Also, terminate the leads for the steam turbine generator step-up transformer and the gas turbine generator step-up transformer into the new switching station. | 2013-12-01 | Approved Withdrawn | 11/2/2010 12/18/2012
EMI-10-X01 | 2010-09-07 | Pioneer Valley Energy Center SPS | Special Protection System (SPS) SPS to protect against loading in excess of DAL on HG&E lines (1657, 1292 &1525) in the event of the loss of the 1302 south coupled with a loss of both the 1327&1428 lines due to a DCT failure with Mt. Tom generating at full capacity. | 2013-12-01 | Approved Withdrawn | 11/2/2010 12/18/2012
EMI-10-T02 | 2010-09-07 | Pioneer Valley Energy Center Substation | Generator Step Up Transformer to interconnect the PVEC Steam Turbine generator to the PVEC substation at the 115 kV 1302 transmission line between Buck Pond and Pochassic substations. | 2013-12-01 | Approved Withdrawn | 11/2/2010 12/18/2012
EMI-10-T01 | 2010-09-07 | Pioneer Valley Energy Center Substation | Generator Step Up Transformer to interconnect the PVEC Combustion Turbine generator to the PVEC substation at the 115 kV 1302 transmission line between Buck Pond and Pochassic substations. | 2013-12-01 | Approved Withdrawn | 11/2/2010 12/18/2012
EMI-10-G01 | 2010-09-07 | Pioneer Valley Energy Center Generation Station | Construction and interconnection for a 400 MW combined cycle generator in Westfield, MA. | 2013-12-01 | Approved Withdrawn | 11/2/2010 12/18/2012
BHE-08-T03 | 2010-09-08 | Keene Road Substation | Withdrawal of the Keene Rd PPA (BHE-08-T03). This application (recommended for approval by the NEPOOL RC November 2008) has been superseded by the BHE-10-T01 (see above) and a future PPA that will address the related 115kV changes and the addition of the auto transformer. | 2010-12-01 | Approved | 2010-09-21
BHE-10-X01 | 2010-09-08 | Chester SVC | Disable the Chester Static VAR Compensator (SVC) Supplemental Modulation Control (SMC – a.k.a SMF). This control was added to the SVC, as part of the original installation, to permit better coordination with what was commonly known as the Keswick GCX SPS. The GCX SPS was removed from service with the installation of the Northeast Reliability Interconnect Project (NRI – line 390) in 2007. Recent studies associated with the Keene Rd project were performed with Keene Rd in-service and the system changes associated with the NRI, as well as with and without the planned MPRP changes. These studies indicated that there was unacceptable system response with the SMC in service, and acceptable response with the SMC removed from service. | 2010-10-01 | Approved | 2010-09-21
BHE-10-T01 | 2010-09-08 | Keene Road Substation | Add breakers into Line 396 near the Chester SVC. These breakers will initially be installed such that their operation imitates the present line configuration with respect to line faults and relay response. It is anticipated that an additional application will be brought forward with the addition of a transformer at this facility, at which time the protection and operation of the Keene Road 345kV breakers will be modified to be in line with that application. | 2012-10-01 | Approved | 2010-09-21
CMP-10-T02 | 2010-09-09 | Starks Switching Station | Addition of four 115 kV circuit breakers in a breaker and a half configuration and two 18 MVAR capacitor bank at a new Starks Switching Station. | 2012-12-01 | Approved | 2010-09-28
NU-10-T18 | 2010-07-14 | Lost Nation - Paris Drummer Transmission | Upgrade of the 12.5 mile overhead 115 kV O154 Line from Lost Nation - Northumberland, NH to Paris-Drummer NH. | 2012-10-01 | Approved | 2010-08-25
NU-10-T17 | 2010-07-14 | Lost Nation - Whitefield Transmission | Upgrade of the 18 mile overhead 115 kV D142 Line from Lost Nation - Northumberland, NH to Whitefield NH. | 2012-10-01 | Approved | 2010-08-25
NU-10-T16 | 2010-07-14 | Berlin - Whitefield Transmission | Upgrade of the 27 mile overhead 115 kV S136 Line from Berlin, NH to Whitefield NH. | 2012-10-01 | Approved | 2010-08-25
NU-10-T15 | 2010-07-14 | Berlin Substation | Installation of a generator step up transformer rated at 48/64/80 MVA, 13.8/118 kV, 0.92 mile 115 kV circuit. In addition, installation of a 115 kV circuit breaker connection to the 115 kV Berlin Substation. | 2012-10-01 | Approved | 2010-08-25
NU-10-G04 | 2010-07-14 | Laidlaw Berlin Biopower Generator | Construction of a 65.9 MW wood fired biomass generator interconnecting to the Berlin Substation in Berlin, NH | 2012-10-01 | Approved | 2010-08-25
NU-10-T14 | 2010-07-13 | Berlin Substation | Installation of a generator step up transformer rated at 30/36 MVA, 13.8/115 kV, 0.5 mile 115 kV circuit. In addition, installation of a 115 kV circuit breaker connection to the 115 kV Berlin Substation. | 2012-09-01 | Approved | 2010-08-25
NU-10-G03 | 2010-07-13 | CPD Berlin Biomass Generator | Construction of a 29 MW wood fired biomass generator interconnecting to the Berlin Substation in Berlin, NH. | 2012-08-01 | Approved | 2010-08-25
NU-10-G02 | 2010-07-08 | Bradley Energy Center | Installation of a 1.8 MW natural gas fired generator to the existing Bradley Energy Center Generators (new total output is 5.65 MWs net) interconnecting at the 27.6 kV Enfield 12C Substation feeder 12C48 located in Windsor Locks, CT. | 2010-07-18 | Approved | 2010-07-27
SG-10-G01 | 2010-07-01 | Waterbury Generator Station | Capacity increase for the Waterbury generator of 7.8 MWs (50 degrees) and 5.5 MWs (0 degrees) located in Waterbury, CT. | 2010-08-01 | Approved | 2010-07-27
NU-10-T13 | 2010-07-09 | Derry Transformer | Construction of a new 30 MVA 115/12.47 kV transformer in Derry, NH. | 2011-12-01 | Approved | 2010-07-27
NU-10-T12 | 2010-07-09 | Thorton Substation | Construction of a new Thornton Substation with a 44.8 MVA 115/34.5 kV transformer for the Merrimack, NH area to eliminate distribution issues in the area. | 2012-06-01 | Approved | 2010-07-27
UI-10-G03 | 2010-06-07 | Milford Fuel Cell | Construction of three gas-fired fuel cell generators, each rated at 2.8 MWs and a gas fired induction generator with an output of 1.8 MWs (10.2.MWs total) located in Milford CT. Project will interconnect at the UI 13.8 kV distribution system at Milton 115/13.8 kV substation via two 13.8 kV circuits. In addition, a 13.8 kV isolation transformer will be utilized to interconnect each fuel cell, while a 2.5 MVA, 6/6/13.8 kV step up transformer will interconnect the generator to the 13.8 kV bus. | 2011-05-01 | Approved Withdrawn | 7/27/2010 8/15/2013
NSTAR-10-G02 | 2010-06-08 | Notis Wind I | Construction of one 1.65 MW wind turbine generator interconnecting at the NSTAR Falmouth Substation #933 via a 23 kV feeder #98A located in East Falmouth, MA. | 2010-06-15 | Approved | 2010-06-17
ECO-10-G02 | 2010-06-03 | Spruce Mountain Wind | Project expansion of Spruce Mountain Wind Project (#290) for construction of one 2 MW wind turbine generators with a total output of 2 MWs to be located in Woodstock, ME. | 2010-11-01 | Approved | 2010-06-17
ECO-10-G01 | 2010-06-03 | Spruce Mountain Wind | Construction of nine 2 MW wind turbine generators with a total output of 18 MWs to be located in Woodstock, ME. | 2010-11-01 | Approved | 2010-06-17
NU-10-T11 | 2010-06-02 | Caldwell Switching Station | Construction of a 115/13.8 kV Generator Step Up (GSU) Transformer at Palmer Renewable Energy Center generating station and generator lead to interconnect to dwell 115 kV switching station. In addition, install a 115 kV, 63 kA circuit breaker at Palmer Renewable Energy Center generation station, a 115 kV, 63 kA circuit breaker at Cadwell 115 kV switching station and associated disconnect switches, protection and controls. | 2012-05-01 | Approved | 2010-06-17
NU-10-G01 | 2010-06-02 | Palmer Renewable Energy Center | Construction of a 37 MW wood burning steam generator to be located in Springfield, MA. | 2012-05-20 | Approved | 2010-06-17
MMWEC-10-T01 | 2010-05-04 | Stony Brook Substation | Installation of one 15.0/345 kV step up transformer and one 16.5/345 kV step up transformer interconnected through a single 345 kV circuit breaker to Stony Brook 54B substation 345 kV bus. In addition, install one 345 kV circuit breaker to provide switching capability/isolation for the existing Stony Brook generation. | 2014-05-31 | Approved Withdrawn | 1/17/2012 10/16/2012
MMWEC-10-G01 | 2010-05-04 | Stony Brook Generation Station | Construction of a 280 MW Combined Cycle generator located in Ludlow, MA. | 2014-05-31 | Approved Withdrawn | 1/17/2012 10/16/2012
CMP-10-T01 | 2010-04-20 | Glass Face Switching Station | Central Maine Power proposal for the construction of the Glass Face Switching Station consisting of a new 115 kV bus with one new 115 kV circuit breaker for Section 271 feeding north to Roxbury substation and one new 115 kV breaker for the Longfellow Wind Collector Substation. The new Switching Station will be located aprox. 9200 ft. from CMP’s existing Rumford 115 kV Substation. | 2011-12-01 | Approved Withdrawn | 1/17/2012 10/16/2012
FW-10-T01 | 2010-04-21 | Longfellow Wind Substation | First Wind proposal for the construction of the Longfellow Wind Collector Substation rated at 30/40/50 MVA interconnecting the Longfellow Wind Project with the new CMP S270 line by means of CMP Glass Face switching station. | 2011-12-31 | Approved Withdrawn | 1/17/2012 10/16/2012
FW-10-G01 | 2010-04-21 | Longfellow Wind Generator | First Wind proposal for the construction and installation of twenty 2.5 MW wind turbine generators totaling 50 MWs rated at 16.4 MVARs leading and lagging. Project is located in Rumford, ME. | 2011-12-31 | Approved Withdrawn | 1/17/2012 10/16/2012
VELCO-10-T01 | 2010-04-12 | Deerfield Wind Substation | Vermont Electric Company proposal for the construction of a 3 breaker ring substation connecting to the Y25 line, between the Bennington 69 kV and the Sleepy Hollow/Searsburg Wind tap. | 2011-12-01 | Approved Withdrawn | 5/24/2010 2/25/2015
IBR-10-T01 | 2010-04-12 | Deerfield Wind Transmission | Iberdrola Renewables proposal on behalf of Deerfield Wind for the construction and installation of the Deerfield Wind Collector Substation consisting of a 34.5/69 kV transformer rated at 18/24/30 MVA with an impedance of 8%, interconnecting the Deerfield Wind Project with the new CVPS 69 kV interconnection switchyard on the Bennington-Searsburg 69 kV line (Line Y25N). rated at 9.9 MVARs leading and lagging. Project is located in Bennington County, VT. | 2011-10-01 | Approved Withdrawn | 5/24/2010 2/25/2015
IBR-10-G01 | 2010-04-12 | Deerfield Wind Generator | Iberdrola Renewables proposal on behalf of Deerfield Wind for the construction and installation of fifteen 2.0 MW wind turbine generators totaling 30 MWs rated at 9.9 MVARs leading and lagging. Project is located in Bennington County, VT. | 2011-12-31 | Approved Withdrawn | 5/24/2010 2/25/2015
NEP-10-T01 | 2010-02-09 | East Main Street Transformer and Breaker | New England Power Company proposal for the installation of a 115/13.8 kV 24/32/40 MVA transformer at the East Main Street Substation located in Westborough, MA. In addition, installation of a new 0.3 mile tap line and inline breaker to loop the 115 kV E-157 line at the East Main Street Substation. | 2013 | Approved | 2010-04-26
UI-10-G02 | 2010-03-19 | Sikorsky Aircraft Generator | United Illuminating proposal for the installation a 9.2 MW Gas Turbine Generator interconnecting at the UI 13.8 kV distribution system at Trap Falls 115/13.8 kV Substation, via four 13.8 kV circuits. | 2010-08-01 | Approved | 2010-03-18
TLMP-10-T01 | 2010-02-16 | Taunton Transmission | Taunton Municipal Lighting Plant proposal to reconductor the 115 kV V-5 and S-8 tap lines interconnecting the Cleary Substation to the New England Power Company (“NGRID”) transmission lines that run from Bridgewater Substation to Somerset Substation. In addition, construct a new three bay (9 breaker) breaker and a half 115 kV substation to replace the existing ring bus in the Cleary Substation and interconnect four existing 115 kV lines, the existing and proposed generator, and distribution load. | 2013-12-31 | Approved Withdrawn | 3/18/2010 10/19/2011
TLMP-10-G01 | 2010-02-16 | Taunton Generator | Taunton Municipal Lighting Plant proposal for the construction of a new 301 MW combined cycle generator interconnecting at the Cleary Substation | 2013-12-31 | Approved Withdrawn | 3/18/2010 10/19/2011
NEP-10-T03 | 2010-02-16 | Taunton Transmission | New England Power Company proposal to upgrade the junctions of tap lines to the Cleary substation on the 115 kV V5 and S8 lines and upgrade the terminal elements of the 115 kV V5 line inside the Somerset substation and replacement of a 115 kV breaker 1620 at Bridgewater substation. | 2012-03-01 | Approved Withdrawn | 3/18/2010 10/19/2011
NU-10-T02 | 2010-03-04 | MeridenTransmission | Northeast Utility System Company Proposal for the addition of a 1.1 mile radial 345 kV line from the new three breaker 345 kV ring substation to the Meridian generating facility. | 2010-06-01 | Approved Withdrawn | 3/18/2010 8/15/2010
NU-10-T01 | 2010-03-04 | Meriden Substation | Northeast Utility System Company proposal for the addition of a three breaker, 345 kV ring bus substation by splitting the 3754 line (Southington – Beseck 345 kV line) aprox. 5 miles from the Southington 345 kV Substation. | 2010-06-01 | Approved Withdrawn | 3/18/2010 8/15/2010
NRG-10-T01 | 2010-03-04 | Meriden 345 kv Ring Bus | NRG Energy proposal for construction of a new 345 kV 3 breaker ring bus on the 3754 line (Southington-Beseck 345 kV Line). A radial 1.1 mile 345 kV transmission line will connect the project collector bus at Meridian to the new 345 kV ring bus on the 3745 Line. | 2010-06-01 | Approved Withdrawn | 3/18/2010 8/15/2010
NRG-10-G01 | 2010-03-04 | Meriden Generator | NRG Energy proposal for construction of a 510 MW (net output) combined cycle generator interconnecting to a the transmission system at a new 345 kV 3 breaker ring bus on the 3754 line (Southington-Beseck 345 kV line. | 2012-06-01 | Approved Withdrawn | 3/18/2010 8/15/2010
BMLD-10-T01 | 2010-01-07 | Belmont Substation | Belmont Municipal Light Department proposal to construct a new 115 kV to 13.8 kV distribution substation interconnected to two existing 115 kV underground cables running between North Cambridge Station and Brighton Station. Both circuits are to be extended to a ring bus in the new substation that will interconnect two new 115 kV to 13.8 kV transformers. Ring bus will be equipped with redundant high speed relaying to comply with NPCC BPS requirements. | 2012 | Approved | 2010-03-01
UI-10-G01 | 2010-01-11 | Yale Sterling Power Plant | United Illuminating proposal for the construction of two gas turbine generators, each with a net rating of 7.3 MW Winter and 6.5 MW Summer interconnecting via four 13.8 kV circuits at the UI Water Street 115/13.8 kV Substation located in New Haven, CT. | 2010-03-01 | Approved | 2010-01-21
NU-09-G03 | 2010-01-04 | Merrimack 2 Generator Uprate | Northeast Utility System Company proposal to increase the generating capacity on the Merrimack 2 generator (Asset #490) located in Bow, New Hampshire, by 17 MWs from 351.5 MWs to 368.5 MWs. | 2010-06-01 | Approved | 2010-01-21
NU-09-X05 | 2010-01-04 | Merrimack 2 PSS | Northeast Utility System Company proposal to addand enable a digital Power System Stabilizer (PSS) to the Merrimack # 2 generator located in Bow, New Hampshire. | 2010-01-01 | Approved | 2010-01-21
NSTAR-10-T01 | 2010-01-06 | West Walpole 345 kV Reactor | NSTAR Gas & Electric proposal to install a new 345 kV, 160 MVAR regulating shunt reactor in order to absorb excess reactive power and installation of a 345 kV circuit breaker with synchronous switching controller at the West Walpole Substation located in Walpole, MA. | 2010-05-01 | Approved | 2010-01-21
CMP-09-X02 | 2010-01-20 | 386 SPS | Central Maine Power proposal to Expand the existing Buxton to Yarmouth Transfer Trip on Section 386 into a Special Protection System, to due to the addition of the 345 kV breakers at South Gorham. | 2010-03-01 | Approved | 2010-01-21
NSTAR-09-T11 | 2009-12-03 | West Framingham 115 kV Capacitor Bank | NSTAR Gas & Electric addition of a new 115 kV 54 MVAR capacitor bank and 115 kV circuit breaker (#5) to switch the capacitor bank in and out of service to counter effects of low voltage due to a loss of the 455-507 from Sherborn. | 2010-06-01 | Approved | 2009-12-17
ANGEN-09-G01 | 2009-09-29 | Ansonia Generator | Ansonia Generation, LLC proposal for construction of a combined cycle generator (1 gas turbine and 1 steam turbine) with a net rating of 63 MWs Summer and 68 MWs Winter, located in Ansonia CT. | 2012-05-31 | Approved Withdrawn | 11/5/2009 5/5/2012
ANGEN-09-T01 | 2009-09-29 | Ansonia Generator Transmission Line | Ansonia Generation, LLC proposal for installation of a ¼ mile overhead 115 kV transmission line from the Ansonia Generator to the Ansonia substation located in Ansonia, CT. | 2012-05-31 | Approved Withdrawn | 11/5/2009 5/5/2012
UI-09-T02 | 2009-10-01 | Ansonia Substation | United Illuminating proposal to terminate and connect the 115 kV transmission line from the Ansonia Generator to the Ansonia 115 kV substation. Substation will be reconfigured into a three-breaker ring bus by the installation of two additional 115 kV 50 kA circuit breakers. | 2012-05-31 | Approved Withdrawn | 11/5/2009 5/5/2012
UI-09-T01 | 2009-09-28 | Shelton 115/13.8 kV Substation | Project will consist of installation of two 115 kV line terminal structures, one 115 kV SF6 gas insulated circuit breaker, twelve vertical break disconnect switches, two 30/40/50 MVA, 118/14.9 kV power transformers with load tap changers, two prefabricated Power Distribution Centers with 13.8 kV metal clad switchgear, a 13.8 kV bus duct system connecting the power transformers to the PDCs and connecting the PDCs to each other. The overhead 1560 line will be sectionalized by looping it into the Shelton Substation to result in a Shelton-Trap Falls line aprox. 3500 feet in length and a Shelton – Stevenson line aprox. 8.2 miles long. | 2013-06-01 | Approved | 2009-11-05
NU-09-T17 | 2009-09-25 | Line Reconfiguration for Shelton Substation | Looping of the 1560S line into and out of the proposed Shelton Substation. | 2013-06-01 | Approved | 2009-11-05
RPM-09-G01 | 2009-10-02 | Ridgewood CoGen Generator | Ridgewood Rhode Island Generation, LLC, proposal for construction and interconnection of six 6.3 MW Solar Taurus 60 combustion turbine generators and one 13 MW steam turbine generator totaling 49.2 MWs, located in Johnston, RI. | 2011-06-01 | Approved | 2009-11-05
RPM-09-T01 | 2009-10-02 | Ridgewood CoGen Transformer | Ridgewood Rhode Island Generation, LLC, proposal to install a 70 MVA 13.8/115 kV generator step up transformer connected to the the 115 kV system via the S-171 main line, which shares right of way with the 115 kV T-172 Hartford Avenue – Drumrock substations. | 2011-06-01 | Approved | 2009-11-05
NEP-09-T02 | 2009-10-13 | Ridgewood CoGen Substation | NGRID Proposal to construct a new 115 kV, three breaker ring bus substation in Johnson, RI. Loop in and interconnect the 171S line into the new substation an connect the Ridgewood generation plant to the new substation | 2011-06-01 | Approved | 2009-11-05
NEP-09-T04 | 2009-10-19 | Long Term Lower SEMA | Reconductor the Bell Rock to High Hill 115 kV D21 Line | Fall 2012 | Approved | 2009-11-05
NSTAR-09-T05 | 2009-10-19 | Long Term Lower SEMA | Expand the Carver 345 kV Substation with a fourth bay comprised of two 345 kV circuit breakers. Reconnect the existing #322 line into the new fourth bay position. Connect a new 345 kV line to the present #322 line position. The new 17.9 mile overhead line 345 kV line will be constructed from Carver 345 kV to the vicinity of the Bourne 115 kV Substation on existing right of way. At Bourne, the existing Canal–Barnstable #120 line will be cut and the line section from Canal will be connected to Bourne 115 kV. The line section from Bourne–Barnstable will be connected to the new 345 kV line from Carver. The Bourne to Sandwich portion of the Bourne-Barnstable 120 Line section will be operated at 345 kV. (See NSTAR-09-T07 for a description of the Sandwich Substation. | Fall 2012 | Approved | 2009-11-05
NSTAR-09-T06 | 2009-10-19 | Long Term Lower SEMA | The existing Canal – Bourne #126 line will be reconnected to the #121 line position and the #120 line from the Canal 345 kV Substation will be connected to the present #126 line position. | Fall 2012 | Approved | 2009-11-05
NSTAR-09-T07 | 2009-10-19 | Long Term Lower SEMA | Install a new nominally 550 MVA 345/115kV auto-transformer at Sandwich and install a 345 kV and 115 kV circuit breaker on either side of the auto-transformer. The high side of the auto-transformer will be supplied with a 345 kV line from Carver 345 kV (see NSTAR-09-T05). | Fall 2012 | Approved | 2009-11-05
NSTAR-09-T08 | 2009-10-19 | Long Term Lower SEMA | Separate existing 345 kV double circuit tower (DCT) crossing of Cape Cod Canal. The two 345 kV lines are on DCT structures for a single span crossing Cape Cod Canal. The two 345 kV lines are the Canal – Pilgrim – Auburn #342 line and Canal – Carver #322 line. | Fall 2012 | Approved | 2009-11-05
DEM-09-X01 | 2009-08-17 | Salem Harbor 2 Exciter Replacement | Dominion Energy New England, Inc. proposal for replacement of the Excitation Control System (AVR) at Salem Harbor 2 Generator Station. Plans include replacing the existing Salem Harbor 2 exciter with a GE Ex 2100 static excitation system. | 2009-11-01 | Approved | 2009-09-29
RHW-09-G01 | 2009-09-04 | Record Hill Wind Collector Substation | Record Hill Wind LLC’s proposal for construction of twenty-two 2.3 MW Siemens wind turbine generators with a combined net output of 50.6 MWs located in Roxbury, ME. | 2010-07-01 | Approved | 2009-09-29
RHW-09-T01 | 2009-09-04 |  | Construct a new Record Hill Wind substation connecting Record Hill Wind project with the new CMP Roxbury 115 kV substation fed from the Rumford substation. | 2010-07-01 | Approved | 2009-09-29
CMP-09-T09 | 2009-09-08 | Rumford 115 kV Substation Modifications | Record Hill Wind Collector Substation | 2010-07-01 | Approved | 2009-09-29
CMP-09-T10 | 2009-09-08 | Roxbury Substation | New Roxbury Substation: Transformer T2 (115/34.5 kV, 10/14 MVA) will be moved from the Rumford 115 kV Substation to the new Roxbury 115 kV Substation. Transformer T2 will be used to supply the existing 34.5 kV Frye Substation and transmission Sections 52 to Andover Substation and Section 54 to Rangeley Substation. The new Roxbury Substation will consist of two 115 kV circuit breakers, one for the feed to T2, and one to terminate the new 115 kV line Section 270 from the Rumford 115 kV Substation (reference CMP-09-T09). The new Roxbury Substation will serve as the Point of Interconnection for QP#197, 50.6 MW Record Hill Wind Farm (reference under separate cover: RHW-09-G01, RHW-09-T01). | 2010-07-01 | Approved | 2009-09-29
GMP-09-G01 | 2009-08-24 | GMP Gorge Generator Addition | Green Mountain Power Corp. proposal for construction of a three dual fuel (gas/oil) Solar Titan 130-205015 Axial Turbine combustion turbine generating units at the Gorge Substation located in Colchester, VT. Generator combined gross output of 42 MWs (14 MWs per unit). The existing combustion turbine will be replaced. The generator set will be stepped-up to 34.5 kV by one GSU and interconnect at the existing Gorge substation 35.5 kV bus. | 2011-06-01 | Approved Withdrawn | 9/29/2009 11/13/2012
FPL-09-X02 | 2009-08-21 | Wyman 2 Exciter Replacement | Replace the exictation control system (AVR) at Wyman 2 Generator Station. Plans include the replacing the existing Wyman 2 exciter with a Basler DESC-400 digital controller, which will be aded to the existing rotating DC exciter in the place of Amplidyne type voltage regulator. | 2009-10-01 | Approved | 2009-09-29
NU-09-T13 | 2009-08-26 | Waterside Ring Bus | Transmission PPA for Waterside 22M 3rd 115 kV circuit breaker addition on 15 kV A2 bus position. Re-terminate Waterside Power connection through new underground cable. Relocate circuit breaker 22M-1X1-2 between new 115 kV A1 bus and 115 kV A2 bus and renumber to 22M-1T-2. Re-terminate 1440 line (Glenbrook-Waterside) into new 115 kV A1 bus and complete associated protective relaying schemes. | 09/01/2009 and 04/01/2010 | Approved | 2009-09-29
NU-09-T14 | 2009-08-26 | Waterside Ring Bus | Transmission PPA for Waterside 22M to install three-breaker 115 kV ring bus. Install 3rd circuit breaker (22M-4T-2, 63 kA interrupting and 3 kA continuous current rating) on the 115 kV A3 bus between Glenbrook-Waterside 1440 Line and Waterside-Cos Cob Railroad 1740 Line. Install two 115 kV disconnects and install a 115 kV underground cable to connect 3rd circuit breaker (22M-4T-2) to 115 kV A1 bus to complete ring bus configuration. Complete associated protective relaying schemes. Replace obsolete CCVT’s 1740-22M-H1 PH 1, 2, & 3. Upgrade line limiting terminal equipment for Waterside 22M 1740 Line. | 2011-06-01 | Approved | 2009-09-29
NU-09-X02 | 2009-08-26 | Waterside Relay | Upgrade protective relaying to include second high-speed relay scheme on the 1440 line between Glenbrook and Waterside substations. | 2011-06-01 | Approved | 2009-09-29
MATEP-09-G01 | 2009-10-04 | MATEP Generator | Proposal for construction of a third Siemens SGT-400 gas turbine generator located in Boston, MA. Net output is 12.5 MWs through the existing interconnection with NSTAR via three 13.8 kV tie lines from Brighton Station #329. | 2012-06-01 | Approved Withdrawn | 9/29/2009 1/22/2013
NU-09-G02 | 2009-07-06 | Foxwoods CHP Generator Addition | Generator PPA for construction and interconnection of two gas turbine generators, each with a net rating of 8.28 MWs Winter and 6.68 MWs Summer. Project will be located at Foxwoods Resort and Casino, CT. Generator 1 will interconnect at the Tunnel 12S5 and 12S3. Generator 2 will interconnect at the Mystic 13K48. | 2010-02-01 | Approved | 2009-08-27
NOBLE-09-G02 | 2009-07-02 | Granite Reliable Wind | Generator PPA proposal for the construction of thirty-three 3.00 MW Vestas wind turbine generators totaling 99.0 MWs located in Coos County, NH, a collector system, collector substation and 5.8 mile 115 kV overhead line interconnecting at the NU (PSNH) Paris Substation. | 2010-12-01 | Approved | 2009-07-28
NOBLE-09-T02 | 2009-07-02 | Granite Reliabile Power Substation | Transmission PPA for the construction of a new Granite Reliable Power collector substation and installation of a 34.5/115 kV GSU rated at 66/88/110 MVA. Also included is the installation of a 5.8 mile 115 kV line Y185 from Granite Reliable Power Collector Substation to the Paris Switching Substation located in Dummer, NH. | 2010-12-02 | Approved | 2009-07-28
NU-09-T08 | 2009-07-01 | Paris Switching Station | Transmission PPA for the construction of a new 115 kV Paris Switching Station with three 115 kV circuit breakers, bifurcating 115 kV line W179, providing a three terminal point of interconnection for the proposed generator project located in Dummer, NH. | 2010-12-01 | Approved | 2009-07-28
NU-09-T09 | 2009-07-01 | Upgrade of W179 East Line | Transmission PPA for the upgrade the thermal capability of the existing 115 kV overhead line W179-East (Paris-Pontook-Berlin) from Paris - Dummer, NH to Berlin - Berlin, NH to achieve the required summer thermal LTE rating of 101 MVA. Upgrade will result in summer thermal ratings of 114/114/114 MVA and winter thermal ratings of 133/133/133 MVA | 2010-12-01 | Approved | 2009-07-28
NU-09-T10 | 2009-07-01 | Upgrade of W179 West Line | Transmission PPA for the upgrade the thermal capability of the existing 115 kV overhead line W179-West (Lost Nation-Paris) from Lost Nation – Northumberland, NH to Paris – Dummer, NH to achieve the required summer thermal LTE rating of 101 MVA. Upgrade will result in summer thermal ratings of 123/123/123 MVA and winter thermal ratings of 141/141/141 MVA | 2010-12-01 | Approved | 2009-07-28
NU-09-T11 | 2009-07-01 | 1J95 Switch Close at Littleton 115 kV Substation | Transmission PPA for the closing an existing switch, 1J95, at the Littleton 115 kV Substation. Creates a three terminal line between Moore–Littleton–Whitefield Substations. Protection and controls relaying is to be added to the Littleton terminal. | 2010-12-01 | Approved | 2009-07-28
NU-09-T12 | 2009-07-01 | Upgrade of D142 Line | Transmission PPA for the upgrade the thermal capability of the existing 115 kV overhead line D142 (Lost Nation-Whitefield) from Lost Nation – Northumberland, NH to Whitefield – Whitefield, NH to achieve the required summer thermal LTE rating of 81 MVA. Upgrade will result in summer thermal ratings of 84/97/126 MVA and winter thermal ratings of 111/105/127 MVA | 2010-12-01 | Approved | 2009-07-28
NU-09-X01 | 2009-07-01 | Beebe River Auto-Switch Controls | Transmission PPA for the addition of automatic switching controls, based on voltage, for the existing Beebe River 115 kV capacitor banks, 3x 13.3 MVAR banks located at Beebe River – Campton, NH. This is required to mitigate post-contingency 115 kV over voltages. | 2010-12-01 | Approved | 2009-07-28
DEM-09-G01 | 2009-06-06 | Brayton Point 3 Uprate | Dominion Energy Marketing’s proposal to increase the output capability of the Brayton Point #3 generator by 36 MWs in the summer (previously 612 MWs) and 31 MWs in the winter (previously 633 MWs) through a turbine steam path efficiency upgrade and a corresponding upward revision to the original generator rating by the OEM, Siemens Westinghouse, following future modifications to increase hydrogen gas cooling. The generator modifications will change the nameplate rating from 695 MVA at 0.93 pf to 745 MVA at 0.94 pf, and decrease the reactive lagging capability to 234 MVAR (previously 260 MVAR). Reactive leading capability will not change. | 2011-12-01 | Approved | 2009-07-28
CMP-09-T08 Rev.1 | 2009-06-06 | Madison Electric Works Substation Revision | Sectionalize Section 63 into two parts by adding two 115 kV circuit breakers at the Sturtevant 115 kV Substation; Section 63N to Wyman Hydro Substation and 63S to Livermore Falls Substation. In addition, a 25 MVAR capacitor bank will be added at the Sturtevant 115 kV Substation. | 2010-03-01 | Approved | 2009-07-28
NOBLE-09-G01 | 2009-06-12 | Passadumkeag Wind | Generator PPA proposal for the construction of twenty-five 1.54 MW GE wind turbine generators totaling 38.5 MWs with their own dedicated 575/34.5 kV GSU to be located in Penobscot County, ME. Project is to be interconnected through three collector strings operating at 34.5 kV nominal. String one will interconnect 5 generator wind turbines. String two will interconnect 14 generator wind turbines. String three will interconnect 6 generator wind turbines. Each string shall tie into one 34.5 kV collector bus. | 2011-11-01 | Approved Withdrawn | 7/27/2009 5/24/2011
NOBLE-09-T01 | 2009-06-12 | Passadumkeag Transmission Line Installation | Transmission PPA for the construction of a new 10 mile 34.5 kV transmission line from the new Noble Passadumkeag Windpark to the Bangor Hydro Electric Passadumkeag 115 kV three breaker ring bus and Substation tapping Line 64 linking Graham 115 kV and Keene Road 115 kV. | 2011-11-01 | Approved Withdrawn | 7/27/2009 5/24/2011
BHE-09-T09 | 2009-06-12 | Install GSUs at Passadumkeag Substation | Transmission PPA for the installation of one 34.5/115 kV and 45 MVA step-up transformer at the Passadumkeag 115 kV Substation. | 2011-11-01 | Approved Withdrawn | 7/27/2009 5/24/2011
NU-09-T02 | 2009-05-18 | 2nd Deerfield Auto Transformer | Transmission PPA for the construction of the 2nd Deerfield 345/115 kV autotransformer. | 2011-06-01 | Approved | 2009-06-26
NU-09-T03 | 2009-05-18 | Rebuild L175 Line | Transmission PPA to rebuild 115 kV L175 Line | 2011-06-01 | Approved | 2009-06-26
NU-09-T04 | 2009-05-18 | Reconductor M183 Line | Transmission PPA to reconductor portion of the 115 kV M183 Line | 2011-06-01 | Approved | 2009-06-26
NU-09-T05 | 2009-05-18 | Reconductor C129 Line | Transmission PPA to reconductor portion of the 115 kV C129 Line | 2011-06-01 | Approved | 2009-06-26
NU-09-T06 | 2009-05-18 | Circuit Breaker Replacement at Deerfield Substation | Transmission PPA for the replacement of five (5) 115 kV Circuit Breakers at the Deerfield Substation. | 2011-06-01 | Approved | 2009-06-26
NU-09-T07 | 2009-05-18 | Transformer Addition at Rochester Substation | Transmission PPA for the addition of a 115/34.5 kV transformer at the Rochester Substation. | 2011-06-01 | Approved | 2009-06-26
FLP-09-G01 | 2009-06-03 | Northfield Efficiency Improvement | Replacement of the hydraulic runners and rewind each of the motor generator stators for each of the 4 generators sequentially over a 4 year period. Resulting work will increase the capacity of each generator from 270 MWs to 292 MWs. | 06/01/2011 - Gen 1 | Approved | 2009-06-29
FLP-09-T01 | 2009-06-03 | Replace Northfield GSU | Replacement of the 666 MVA 3X generator step-up transformer. | 2011-06-01 | Approved | 2009-06-29
TEL-08-G01-Rev.1 | 2009-05-31 | Towantic Generator | Generation PPA for construction and operation of combined cycle generating facility increasing the capacity of the generator from 540 MWs to 568 MWs, located in Oxford, CT | 2013-04-01 | Approved Withdrawn | 6/29/2009 2/14/2012
TEL-08-T01-Rev.1 | 2009-05-31 | Towantic GSU | Transmission PPA for construction and operation of generator leads and generator step-up transformer for the generation facility. | 2013-04-01 | Approved Withdrawn | 6/29/2009 2/14/2012
NU-08-T73-Rev.2 | 2009-06-02 | Towantic Substation | Construction of Towantic 115 kV substation and termination of 1575, 1585, and 1990 115 kV lines to Towantic 115 kV substation. | 2013-04-01 | Approved Withdrawn | 6/29/2009 2/14/2012
NU-08-T74-Rev.1 | 2009-06-02 | Reconductor 1585N Line | Reconductor/rebuild 115 kV 1585N Line | 2013-04-01 | Approved Withdrawn | 6/29/2009 2/14/2012
NU-08-T75-Rev.1 | 2009-06-02 | 1990S Line Series Reactor | 1990S Line Series Reactor | 2013-04-01 | Approved Withdrawn | 6/29/2009 2/14/2012
NSTAR-09-T03 | 2009-04-28 | Edgar Station Shunt Reactor | Installation of two (2) 115 kV, 40 MVAR shunt reactors each with a 115 kV circuit breaker with a synchronous switching controller. One reactor will connect to the Edgar 115 kV North bus, and the other reactor will connect to the Edgar 115 kV South bus. Installation of the reactors is required to absorb excess reactive power during light load periods. | 2009-12-01 | Approved | 2009-06-01
VELCO-09-T02 | 2009-05-04 | Lyndonville Substation | Construct a new 4-breaker ring substation at Lyndonville with a 56 MVA 115/34.5 kV transformer with a 0.19 pu impedance on a 100 MVA base and two 115 kV 12.5 MVAr capacitor banks. The Lyndonville substation prevents loss of load for loss of the St. Johnsbury transformer by providing redundant service to the area and allow for expected load growth at a local ski resort. | 2011-12-01 | Approved | 2009-06-01
FW-09-G01-Rev.1 | 2009-04-30 | Dundee Wind Revision | Evergreen Wind III, LLC proposes the interconnection of its Dundee Mountain Wind Units 1 - 22 (the “Project”) located at Dundee Mountain in Penobscot County, Maine. The Project will consist of 22 General Electric wind turbines, each containing a 1.545 MW, 575-V line-to-line, variable-speed wound-rotor induction generator. | 2009-12-01 | Approved | 2009-06-01
FPL-09-X01 | 2009-05-04 | Seabrook PSS | FPL‟s proposal to commission the Seabrook Power System Stabilizer (PSS) originally installed during the 2006 capacity uprate in order to enhance positive damping characteristics of the generator. | 2009-05-01 | Approved | 2009-05-28
NEP-09-T01 | 2009-04-07 | Devens Transmission Reinforcement | Convert two 69 kV lines (U-21E and V-22E), approximately 0.5 circuit miles each, from Ayer substation to a new 115 kV switching station within the Devens Commerce Center (utilizing 1590 ACSR conductor). At Ayer substation, reconfigure the in-line 115 kV circuit breaker so that is on the Pratts Jct side of the K-137 line. | 2011-06-01 | Approved | 2009-07-28
NSTAR-09-T02 | 2009-04-06 | Woburn Mobile Transformer | NSTAR’s proposal for installation of a 50 MVA, 115/14.4 kV mobile transformer at Woburn Station 211. The mobile transformer installation will provide N-1 distribution system capacity to cover possible transformer contingencies throughout the Woburn-Burlington Region. | 2009-06-01 | Approved | 2010-06-03
NSTAR-09-G02 | 2009-04-06 | Falmouth Wind I Generation Station | Installation of a 1.65 MW Vestas Model V82 MKII wind turbine generator located in Falmouth, MA. Generator will interconnect at the NSTAR Falmouth Substation #933 23 kV feeder #98A. | 2009-01-15 | Approved Withdrawn | 6/3/2010 3/14/2023
NEP-07-T47-Rev.1 (Revision available) | 2009-04-03 | Auburn Street Upgrades | Addition of 2nd 345/115kV 448 MVA transformer, expansion of the 345kV switchyard, construction of new breaker and third 115 kV switchyard rated at 63kA, and removal of two 115 kV ring buses. | 2012-06-01 | Approved | 2010-02-10
NEP-07-T48-Rev.1 | 2009-04-03 | Dupont Substation Expansion | Addition of two 115 kV circuit breakers rated at 40 kA and addition of 2nd 115/13.8 kV 60 MVA transformer | 2012-06-01 | Approved | 2010-02-10
NEP-09-T03 | 2009-04-03 | Avon Substation | Construction of new 115/13.8 kV substation off A94 line between Parkview and Auburn St. Load at the Avon substation to be supplied by a 40 MVA 115/13.8 kV transformer. | 2012-06-01 | Approved | 2010-02-10
BRP-09-G01 | 2009-03-10 | Bear Swamp Generator Upgrade | Proposed upgrade to increase each of the two hydro generators by 33 MWs (66 MWs total). In addition, the upgrade will expand each generator’s MVAr capacity by 15 MVAr lagging and 86 MVAr leading. Phased in-service dates: for Unit 1, March 31, 2011; and for Unit 2, March 30, 2012. | 03/31/2011 - Gen 1, 03/30/2012 - Gen 2 | Approved Withdrawn | 4/29/2009 8/23/2011
FW09-G01 | 2009-03-04 | Dundee Wind | Generation PPA for the construction of twenty-one 1.54 MW GE wind turbine generators, totaling 32 MW, to be located in Penobscot County, ME. Each turbine will be interconnected along a collector string running approximately 41,000 foot to a circuit breaker at Rollins Mountain Substation. | 2009-12-01 | Approved | 2009-04-29
FW-08-G01-Rev.1 | 2009-03-04 | Stetson Wind Phase II | Generation PPA for the updating the unit count at Rollins Wind | 2009-12-01 | Approved | 2009-04-29
FW-08-T01-Rev.1 | 2009-03-04 | Stetson Wind Phase II GSU | Transmission PPA for each generator to be interconnected via its own 1.75 MVA 575V/34.5/115 kV step-up transformer and via a collector string to Rollins Mountain substation 39,000 feet away. In addition, upgrading the 34.5/115 kV Rollins Mountain substation transformer from 20/26.6/33.2 MVA to 34.5/50/62.5 MVA. | 2009-12-01 | Approved | 2009-04-29
FW-09-G02 | 2009-03-04 | Jimmy/Owl Wind | Generation PPA for the construction of seventeen 1.54 MW GE wind turbine generators, totaling 26 MW, to be located in Washington County, ME. Each turbine will be interconnected along a collector string running approximately 39,000 foot to a circuit breaker at Stetson Mountain Substation. | 2009-12-01 | Approved | 2009-04-29
UPC-07-G01-Rev.2 | 2009-03-04 | Stetson Wind Phase I | Generation PPA updating the unit count at Stetson Wind | 2009-12-01 | Approved | 2009-04-29
UPC-07-T01-Rev.1 | 2009-03-04 | Stetson Wind Phase I GSU | Transmission PPA for each generator to be interconnected via its own 1.75 MVA 575V/34.5/115 kV step-up transformer and via a collector string to Stetson Phase I substation 41,000 feet away. In addition, upgrading the 34.5/115 kV Stetson Phase I transformer from 37.5/50/62 MVA to 60/80/100 MVA. | 2009-12-01 | Approved | 2008-12-23
CMP-09-T01 | 2009-01-20 | Section 241 Transmission Line | Central Maine Power’s Transmission PPA for constructing a new 38.8-mi.115 kV line, Section 241, between the proposed Heywood Road Substation in Benton, ME, and the Wyman Hydro Station in Bingham, ME, as a parallel line to the existing 115 kV Section 83 Line | 2012-12-01 | Approved | 2009-03-20
CMP-06-T13-Rev.1 | 2009-01-20 | Heywood Road Substation | Central Maine Power’s Transmission PPA for constructing a new Heywood Road Substation in Benton, ME, revised for a change in scope. | 2009-03-01 | Approved | 2009-03-20
NEP-08-T62 | 2008-12-31 | Bloomingdale-Vernon Hills Underground Cable | New England Power’s Transmission PPA for constructing a new 3.6-mi. 115 kV underground line between Bloomingdale and Vernon Hill Substations in MA and for reconfiguring the #M-165 and #E-157 Lines at Millbury #2 115 kV Substation into separate breaker positions. This plan improves the recovery time for the loss of supply to the Worcester area. | 2013-06-01 | Approved | 2009-02-27
WRP-08-G01 | 2009-01-21 | Watertown Biomass Generator | Generation PPA for the construction of a steam turbine generator with a net output of 26.25 MW. The unit’s boiler will be fueled primarily with chipped or ground wood waste and secondarily with natural gas. | 2010-11-01 | Approved Withdrawn | 2/24/2009 10/20/2010
WRP-08-T01 | 2009-01-21 | Watertown Biomass Interconnection | Transmission PPA for its interconnection via a 24/40 MVA 115/13.8 kV step-up transformer to a tap from the 115 kV #1238 Carmel Hill-Frost Bridge Line. | 2010-11-01 | Approved Withdrawn | 2/24/2009 10/20/2010
NU-08-T78 | 2008-12-23 | Watertown Biomass Substation | Supporting Transmission PPA for the construction of the Watertown Biomass 115 kV Substation by looping the #1238 Line into the substation to a ring bus for terminating the 300-foot lead to the generator transformer. | 2010-11-01 | Approved Withdrawn | 2/24/2009 10/20/2010
NU-07-T04 Rev.1 | 2008-03-01 | Russell Biomass Power Plant | Russell Biomass Power transmission upgrades. | 2011-06-01 | Approved Withdrawn | 6/6/2007 5/15/2012
NSTAR-08-T01 | 2008-02-14 | Mystic Station #250 | Install two West bus and two East bus 115 kV circuit breakers, and move the connection of 115/14 kV transformer 110B to an open board position. | 2008-11-01 | Approved | 2008-03-10
DEM-08-T01 | 2008-02-08 | Millstone Unit 2 | Project will replace existing three phase GSU transformer for Millstone Unit 2 with three single phase Mitsubishi GSU units and ISO phase bus so that the new TRF impedance is within +/- 4% of existing TRF. | 2008-05-01 | Approved | 2008-03-03
NU-08-T01 | 2008-02-05 | Devon and Trumball 115 kV Substation | Trumbull 45P Substation (UI) - CL&P Modifications. | 2008-06-01 | Approved | 2008-03-13
BHE-08-T02 | 2008-02-01 | Boggy Brook 115kV & Ellsworth Falls 46kV | New 28MVA top rated transformer from Boggy Brook 115kV to Ellsworth Falls 46kV, replacing T3 which has a top rating of 15MVA and was sourced from Ellsworth Falls 34.5kV. | 2008-10-01 | Approved | 2008-03-31
APNA-08-T01 | 0/30/2008 | Brockton Power | Brockton Power Project | 2010-12-01 | Approved Withdrawn | 3/10/2008 5/27/2017
APNA-08-G01 | 2008-01-30 | Brockton Power | Brockton Power Project | 2010-12-01 | Approved Withdrawn | 3/10/2008 5/27/2017
NEP-08-T02 | 2008-01-30 | Brockton Substation | Construct a new 115kV Brockton substation. Construct a new 115kV line connecting the Brockton power plant with the Brockton substation. | 2010-06-01 | Approved Withdrawn | 3/10/2008 5/27/2017
NEP-08-T03 | 2008-01-30 | F19N Line | Reconductor the F19N line. Replace the in-line 19-1 switch. | 2010-06-01 | Approved Withdrawn | 3/10/2008 5/27/2017
NEP-08-T04 | 2008-01-30 | Bridgewater | Replace the Bridgewater 1631 circuit breaker with a new one rated at 63kA IC. | 2010-06-01 | Approved Withdrawn | 3/10/2008 5/27/2017
NEP-08-T05 | 2008-01-30 | Brockton | Reconductor F19S line between Brockton and Belmont tap. Replace the in-line 19-2 switch. Upgrade S1 line terminal equipment at Belmont substation. | 2010-06-01 | Approved Withdrawn | 3/10/2008 5/27/2017
NEP-08-T06 | 2008-01-30 | Auburn and Bridgewater | Replace seven 115 kV breakers at Auburn St. and one 115kV breaker at Bridgewater. | 2010-06-01 | Approved | 2008-03-10
NEP-08-T07 | 2008-01-30 | Tewksbury 22A/22 | Create a new 345-115 kV substation at Wakefield Junction by looping the 345 kV # 339 line from Tewksbury to Golden Hills and the two 115 kV lines S-145 and T-146 from Tewksbury to Golden Hills to Salem Harbor into new switchgear; install four 345-115 kV 448 MVA autotransformers; The new substation will include three bays of 345 kV gas insulated switchgear (GIS) in a breaker-and-third configuration with independent pole tripping (IPT) capable units and three bay positions for future expansion as well as three bays of 115 kV gas insulated switchgear (GIS) in breaker-and-third configuration with independent pole tripping (IPT) capable units and one bay position for expansion. The relay systems at the at the remote ends of the involved lines (Tewksbury 22/22A, Mystic 250, Maplewood, Lynn No. 21, and Salem Harbor) shall be modified to coordinate with those installed at the new Wakefield Junction substation on the 345 kV and 115 kV systems. | 2009-05-01 | Approved | 2008-04-01
NEP-08-T08 | 2008-01-30 | Golden Hills | Reconfigure the 115kV terminals at Golden Hills. Bypass and remove the existing two 115kV breaker and half schemes, tieing the S-145 to the F-158N and the T-146 to the Q-169 line. De-gas and remove the existing 115kV gas-insulated switchgear (GIS). Reconfigure the 345kV terminals at Golden Hills. Bypass and remove the existing three 345kV breaker and half schemes, tieing the 339 and the 349X and 349Y lines. De-gas and remove the existing 345kV gas-insulated switchgear (GIS). Remove the 2-345/115 kV transformers. | 2009-04-01 | Approved | 2008-04-01
NEP-08-T09 | 2008-01-30 | Wakefield Junction | Reconductor 2.2 miles of the present S-145 and T-146 115 kV lines from Wakefield Junction to Golden Hills Tap. This will increase the ratings of the 115kV lines to Normal 359 MVA / LTE 446 MVA / STE 524 MVA / DAL 692 MVA during summer and Normal 446 MVA / LTE 511 MVA / STE 607 MVA and DAL 741 MVA in the winter. | 2009-06-01 | Approved | 2008-04-01
NEP-08-T10 | 2008-01-30 | Melrose #2 Substation | Convert the Melrose # 2 substation from supply by three 115kV lines , S-145, T-146 and Q-169 to two 115kV lines Q-169 and F-158N from Wakefield Junction #88. Replace three 115-23kV step-down transformers with two 115-23kV 33/44/55 MVA units. | 2009-06-01 | Approved | 2008-04-01
NEP-08-T11 | 2008-01-30 | Revere #7 Substation | 115kV 30MVAr capacitor bank installation at Revere #7 installed off the A-179 115kV line via a 40kA synchronous closing circuit breaker. | 2009-06-01 | Approved | 2008-04-01
NEP-08-T12 | 2008-01-30 | West Amesbury and King Street Substations | King Street - West Amesbury convert a 7 mile 23kV sub transmission line, the 2377, to 115 kV from King Street Substation to the West Amesbury Substation West Amesbury Substation - Install an outdoor 115 kV bus with four breakers bays, install additional four 3000 Amp 115kV breakers; IC 63kA and 3000A disconnect switches (NEP-05-T11 installed one breaker and one 115/23 kV transformer) for a total of five breakers installed, ultimate layout to allow the addition of an additional four breakers in the future. Also install a 45/60/75 MVA 115/23 kV transformer and circuit switcher along with a 40MVA 115/13.2 kV transformer along with a circuit switcher. King Street Substation install one 3000 Amp. 115kV breaker, IC 63 KAmp along with 3000 Amp disconnect switches. | 2009-06-01 | Approved | 2008-04-01
NSTAR-08-T02 | 2008-01-25 | Newton Substation #292 | Upgrade Newton #292 | 2008-06-01 | Approved | 2008-03-10
NSTAR-08-T03 | 2008-01-25 | Walpole Station | Replace 110A and 110C transformers with new transformers. | 2008-06-01 | Approved | 2008-03-10
UI-08-T01 | 2008-01-24 | Trumbull 45P Substation | Construct a new 115/13.8 kV substation in Trumbull, Connecticut (CT) to be known as Trumbull 45P Substation. Install two new 118/14.9 kV, 24/32/40 MVA transformers at Trumbull 45P Substation, and three 115 kV circuit breakers in a ring bus arrangement. Terminate the existing 1730 line at Trumbull 45P Substation. | 2008-06-01 | Approved | 2008-03-13
BHE-08-T01 | 2008-01-09 | Graham 115 kV & Graham 46 kV | New 100MVA top rated transformer from Graham 115kV to Graham 46kV, replacing T9 which has a top rating of 28MVA. | 2007-11-01
NU-08-G01 | 2008-01-04 | Kimberly Clark Corporation | KC-New Milford #1, #2, #3. | 2008-04-20 | Approved | 2008-03-10
BELD-07-T02 | 2007-12-07 | Station 11 and Station 16 | 115-16-11 Underground Cable Upgrade | 2010-06-01
BELD-07-T03 | 2007-12-07 | Station 16 & Station 10 | 115-10-16 Underground Cable Upgrade | 2010-06-01
NEP-07-T44 | 2007-12-04 | Belmont Substation | Terminal equipment (buswork and line drops) at Belmont 115 kV substation. Install two high speed protection systems. | 2008-10-01 | Approved | 2008-01-28
NEP-07-T45 | 2007-12-04 | E. Bridgewater Substation | Reconductor L1 Line with 795 ACSR. | 2008-06-01 | Approved | 2008-01-28
NEP-07-T46 | 2007-12-04 | Bridgewater 115 kV Substation | Bridgewater 115 kV substation upgrades: replace three 115kV breakers with 63kA & upgrade G18, F19 lines terminal equipment (buswork, disconnect switches and wavetraps) | 2009-06-01 | Approved | 2008-01-28
NU-07-G04 | 2007-11-30 | UNH Cogen | UNH Cogen | 2007-12-01 | Approved | 2008-02-07
NEP-06-T06 Rev.2 | 2007-11-27 | Bellows Falls Substation | Replace the three existing, three-winding GSUs with two new two-winding 115-6.6 kV, 24/32/40 MVA GSUs (No. 1 and No. 2). Install a new 115-69 kV, 33.6/44.8/56 MVA autotransformer (No. 4) and a new 115-46 kV, 30/40/50 MVA autotransformer (No. 5) to replace the capacity provided by the existing three-windings GSUs. Install a new 115kV 30MVar capacitor bank (C1) for system voltage support. Remove the existing 69-46 kV, 8 MVA autotransformer (No. 3). Replace three 115kV Oil Circuit Breakers (OCB) (W-149S, J-136N and I-135N) with Gas Circuit Breakers (GCB) (W- 149, J-136 and I-135); Install two new 115kV circuit switchers (4T-115 and 5T-115); Install one new 115kV GCB for the C1 capacitor bank (C1). Install one new 69 kV GCB (G33). Install one new 115kV bus tie breaker (115BT). | 2010-10-01 | Approved | 2008-01-28
NU-07-T22 | 2007-11-16 | Waterford 25Y | Construction of a 115-kV bus with a 115-kV tie breaker to be known as the new Waterford 25Y substation. Addition of two 60 MVA 115/23-kV two-winding transformers. Loop existing circuit 1605 (New Waterford Substation 115-kV- Cohanzie Junction- Montville 115-kV-Willaims 115-kV substations). Loop new circuit 1617 (Flanders 115-kV to New Waterford Substation 115-kV). | 2010-05-30 | Approved | 2008-01-11
BELD-07-G01 | 2007-11-14 | Thomas A. Watson Generating Station | Thomas A. Watson Generating Station | 2009-03-03 | Approved with conditions | 2008-02-28
BELD-07-T01 | 2007-11-14 | Thomas A. Watson Generating Station | Thomas A. Watson Generating Station 115 kV interconnection. | 2009-03-03 | Approved with conditions | 2008-02-28
NEP-07-X03 | 2007-10-29 | Comerford Phase I HVdc Runback SPS | Retirement of the Comerford Phase I HVdc Runback SPS | 2007-03-31 | Approved | 2007-12-21
CMP-07-T05 | 2007-10-25 | Bigelow Substation | Install one 115 kV breaker at Bigelow substation in association with the Kibby Wind Farm project. | 2008-12-01 | Approved | 2007-12-21
CMP-07-T06 | 2007-10-25 | Wyman Hydro Substation | Install two switched 115 kV capacitor banks, 18 MVAr each, at Wyman Hydro substation in association with the Kibby Wind Farm project | 2008-12-01 | Approved | 2007-12-21
NRG-07-G03 | 2007-10-24 | Middletown Unit 11 | Middletown Unit 11 | 2009-01-31 | Withdrawn | 2011-08-23
CMP-07-T04 | 2007-10-23 | Wyman Hydro and Detroit Substations | Install two (2) 115 kV breakers on Section 66 between Detroit and Wyman Hydro substations in Athens, Maine and construct a new 115/12.47 kV substation for the purpose of supplying an initial load of 3 MW for a new customer. This new substation will become the new distribution source for the Athens area to replace the existing Harmony substation. | 2009-06-01 | Approved | 2007-12-21
GRE-07-T01 | 2007-10-23 | Granite Ridge Energy | Steam turbine GSU transformer replacement. | 2007-12-01 | Approved | 2007-12-20
GRE-07-T02 | 2007-10-23 | Granite Ridge Energy | Tap Setting Change for Each of Two Combustion Turbine GSU Transformers. | 2008-12-01 | Approved | 2007-12-20
MPP-07-G01 | 2007-10-23 | L'Energia Energy Center | Steam/Turbine Generator Unit reactivation. | 2008-08-01 | Approved with conditions | 2007-12-18
NRG-07-G02 | 2007-10-23 | Devon Station | Devon Units 15-18 | 2009-03-31 | Approved with conditions | 2007-12-18
NU-07-T14 | 2007-10-18 | Berkshire Substation | A second 345/115-kV auto transformer, identical to the existing transformer will be installed, and energized, at Berkshire substation. | 2008-06-30 | Approved | 2008-02-07
TCPM-07-G01 | 2007-10-17 | Kibby Wind Power | Kibby Wind Power Project | 2008-12-31 | Approved | 2007-12-21
TCPM-07-T01 | 2007-10-15 | Kibby Wind Farm and Central Maine Power Bigelow | 115/34.5 kV substation and 115 kV transmission line. | 2008-12-31 | Approved | 2007-12-21
NEP-07-T14 | 2007-10-02 | Greendale Sub | Upgrade Greendale 115 kV breaker. | 2009-06-01 | Approved | 2007-12-17
NEP-07-T15 | 2007-10-02 | P-142 Overheard Line | Reconductor P-142 overhead line. | 2010-06-01 | Approved | 2007-12-17
NEP-07-T16 | 2007-10-02 | O-141S Overhead Line | Reconductor O-141S overhead line. | 2010-06-01 | Approved | 2007-12-17
NEP-07-T17 | 2007-10-02 | Millbury Sub | Upgrade Millbury 115 kV terminal equipment. | 2009-06-01 | Approved | 2007-12-17
NEP-07-T18 | 2007-10-02 | Carpenter Hill | Replace five 115 kV breakers at Carpenter Hill. | 2009-06-01 | Approved | 2007-12-17
NEP-07-T19 | 2007-10-02 | Wachusett Substation | Install 3rd Wachusett 345-115 kV autotransformer. | 2011-06-01 | Approved | 2007-12-17
NEP-07-T20 | 2007-10-02 | W-175 115 kV Line | Reconductor W-175 115 kV line. | 2011-06-01 | Approved | 2007-12-17
NEP-07-T21 | 2007-10-02 | Searsburg 69 kV Station | Searsburg 69 kV : Install in-line breaker. | 2010-06-01 | Approved | 2007-12-17
NEP-07-T22 | 2007-10-02 | Millbury | Reconductor A-127E and B-128E 115 kV lines. | 2010-06-01 | Approved | 2007-12-17
NEP-07-T23 | 2007-10-02 | Cabot Tap | Reconductor portions of A-127W 115 kV line. | 2010-06-01 | Approved | 2007-12-17
NEP-07-T24 | 2007-10-02 | Deerfield #4 | 2nd Deerfield 115-69 kV autotransformer. | 2010-06-01 | Approved | 2007-12-17
NEP-07-T25 | 2007-10-02 | Bear Swamp | Reconductor and Retension E205W 230 kV line. | 2011-06-01 | Approved | 2007-12-17
NEP-07-T26 | 2007-10-02 | Adams Substation | Adams substation - Add 115 kV Breaker. | 2011-06-01 | Approved | 2007-12-17
NEP-07-T27 | 2007-10-02 | Pratts Jct | Upgrade I-135S and J-136S 115 kV Circuits. | 2010-06-01 | Approved | 2007-12-17
NEP-07-T28 | 2007-10-02 | Pratts Jct | Upgrade Pratts Jct 230-115 kV autotransformer T8 and install 230 kV breaker. | 2010-06-01 | Approved | 2007-12-17
NEP-07-T29 | 2007-10-02 | Bear Swamp | Upgrade Pratts Jct 230-115 kV autotransformer T8 and install 230 kV breaker. | 2010-06-01 | Approved | 2007-12-17
NEP-07-T30 | 2007-10-02 | Millbury | Build new 115 kV Overhead Line from Millbury to Tower 510 (Auburn). | 2011-06-01 | Approved | 2007-12-17
NEP-07-T31 | 2007-10-02 | Millbury | Install one (1) 115 kV breaker at Millbury to terminate new line to Tower 510. | 2011-06-01 | Approved | 2007-12-17
NEP-07-T32 | 2007-10-02 | Webster Street | Install two 115 kV breakers at Webster St. | 2010-06-01 | Approved | 2007-12-17
NEP-07-T33 | 2007-10-02 | E Winchendon & Otter River | Build new 115 kV Overhead Line from E Winchendon substation to Otter River Substation. | 2011-06-01 | Approved Withdrawn | 12/17/2007 5/19/2020
NEP-07-T34 | 2007-10-02 | E Winchendon | Install one (1) 115 kV breaker at E Winchendon sub to terminate new line to Otter River. | 2011-06-01 | Approved Withdrawn | 12/17/2007 5/19/2020
NEP-07-T35 | 2007-10-02 | Otter River Substation | Expand Otter River substation to 6 breaker ring bus configuration and install two new 115-69 kV transformers. | 2011-06-01 | Approved Withdrawn | 12/17/2007 5/19/2020
NEP-07-T36 | 2007-10-02 | East Westminster | Install in-line 69 kV Breaker at E Westminster Substation (associated with Otter River substation reinforcement). | 2011-06-01 | Approved Withdrawn | 12/17/2007 5/19/2020
NEP-07-T37 | 2007-10-02 | Palmer Sub | Convert O-15S 69 kV line to 115 kV. | 2011-06-01 | Approved | 2007-12-17
NEP-07-T38 | 2007-10-02 | Palmer Sub | Install additional 115 kV breaker at Palmer to terminate converted O-15S line, and upgrade Palmer 115 kV buswork. Install 115/23 kV transformer. | 2011-06-01 | Approved | 2007-12-17
NEP-07-T39 | 2007-10-02 | Hampden Sub | Build new 115 kV swiching station in Hampden MA. This station will connect the NU 1515 line to the National Grid O-15S line via a four breaker ring bus. | 2011-06-01 | Approved | 2007-12-17
NEP-07-T40 | 2007-10-02 | Hampden Sub | Convert Hampden 69/13 kV transformer to 115/13 kV for O-15S line conversion to 115 kV. | 2011-06-01 | Approved | 2007-12-17
NEP-07-T41 | 2007-10-02 | Hampden Sub | Convert E Longmeadow 69/13 kV transformer T1 to 115/13 kV for O-15S line conversion to 115 kV. | 2011-06-01 | Approved | 2007-12-17
NEP-07-T42 | 2007-10-02 | Shaker Rd | Convert Shaker Rd 69/13 kV transformer to 115/13 kV for O-15S line conversion to 115 kV. | 2011-06-01 | Approved | 2007-12-17
NEP-07-T43 | 2007-10-02 | Carpenter Hill | Carpenter Hill transformer Upgrades: - Install a 115-69 kV transformer (56 MVA) at Carpenter Hill. - Replace Carpenter Hill 345-115 kV autotransformer T1 (300 MVA) with a standard 448 MVA transformer. | 2015-06-01 | Approved | 2007-12-17
NU-07-T15 | 2007-10-01 | Frost Bridge 345/115-kV Substation | Replace the 345/115-kV Autotransformer at Frost Bridge Substation. | 2007-11-01 | Approved | 2007-10-20
NU-07-T17 | 2007-10-01 | North Bloomfield 115-kV Substation | Install 2% Series Reactor w/ by-pass Switch on 1784 Line at North Bloomfield Substation. | 2009-12-01 | Approved | 2007-10-20
NEP-05-T11 Rev.1 | 2007-09-25 | West Amesbury Substation | 345 kV air-insulated substation addition, addition of one 345-115kV 448 MVA transformers, one 345 kV transformer high side circuit breaker, tapping the 345kV #394 line at West Amesbury substation, between Seabrook and Ward Hill, 115 kV air-insulated substation, one 115/23 kV 45/60/75 MVA transformer, and transfer of approximately 64 MW of local load from the King Street 23 kV system to the new West Amesbury 23 kV system. | 2009-03-01 | Approved | 2007-10-20
GMP-07-G02 | 2007-09-18 | Essex Junction #19 | Essex Junction #19 Asset ID #1221 | 2007-11-18
NEP-07-T03 | 2007-09-12 | Tewksbury 22A/22 | Create a new 345-115 kV substation at Wakefield Junction by looping the 345 kV # 339 line from Tewksbury to Golden Hills and the two 115 kV lines S-145 and T-146 from Tewksbury to Golden Hills to Salem Harbor into new switchgear; install four 345-115 kV 448 MVA autotransformers; The new substation will include three bays of 345 kV gas insulated switchgear (GIS) in a breaker-and-third configuration with independent pole tripping (IPT) capable units and three bay positions for future expansion as well as three bays of 115 kV gas insulated switchgear (GIS) in breaker-and-third configuration with independent pole tripping (IPT) capable units and one bay position for expansion. | 2009-06-01
NEP-07-T04 | 2007-09-12 | Golden Hills Substation | Reconfigure the 115kV terminals at Golden Hills. Bypass the existing two 115kV breaker and half schemes, tieing the S-145 to the F-158N and the T-146 to the Q-169 line. De-gas and remove the existing 115kV gas-insulated switchgear (GIS). | 2009-06-01
NEP-07-T05 | 2007-09-12 | Wakefield Junction | Reconductor 2.2 miles of the present S-145 and T-146 115 kV lines from Wakefield Junction to Golden Hills Tap. This will increase the ratings of the 115kV lines to Normal 359 MVA / LTE 446 MVA / STE 524 MVA / DAL 692 MVA during summer and Normal 446 MVA / LTE 511 MVA / STE 607 MVA and DAL 741 MVA in the winter | 2009-06-01
NEP-07-T06 | 2007-09-12 | Melrose #2 Substation | Convert the Melrose # 2 substation from supply by three 115kV lines , S-145, T-146 and Q-169 to two 115kV lines Q-169 and F-158N from Wakefield Junction #88 (as described in NEP-07-T03). Replace three 115-23kV step-down transformers with two 115-23kV 33/44/55 MVA units. | 2009-06-01
NEP-07-T07 | 2007-09-12 | Revere #7 Substation | 115 kV 30MVAr capacitor bank installation at Revere #7 installed off the A-179 115kV line via a 40kA synchronous closing circuit breaker. | 2009-06-01
NU-07-T16 | 2007-09-11 | Jackman Substation | Installation of temporary F162 Line Special Protection System. | 2006-11-01 | Approved | 2007-09-27
NU-06-T06 Rev.1 | 2007-09-05 | Fitzwilliam | New Substation - Fitzwilliam Autotransformer Impedance Change | 2007-12-01
NU-06-T10 Rev.1 | 2007-09-05 | Fitzwilliam | New Substation - Fitzwilliam Autotransformer Impedance change from one 3 phase unit to 3 (single phase) units. | 2008-12-31 | Approved | 2007-09-27
NU-07-T12 | 2007-09-04 | Rood Avenue 24J | Addition of a 46.7 MVA 115/23-kV two-winding transformer at new substation. Construct a 115kV bus with a 115-kV tie breaker at new substation, 3. Loop the line 1751 (Manchester 3A, Northwest Hartford 2N, N Bloomfield 2A) into the new substation, and at Manchester substation, addition of a 115-kV circuit breaker at 1751 line terminal and upgrade relay and wave trap. | 2009-06-01 | Approved | 2007-09-27
NU-07-T13 | 2007-09-04 | Enfield 12C Substation | Add a second 115/23-kV transformer (47 MVA) and new switchgear at Enfield 12C. | 2008-05-01 | Approved | 2007-09-27
BHE-07-G01 | 2007-08-27 | Lincoln, ME | New 13.5MW biomass co-generation addition to the existing mill load and generation facilities in Lincoln, Maine. | 2007-11-01 | Approved | 2007-09-27
CVPS-07-G01 | 2007-08-23 | St. Albans Diesel Plant 1 & 2 | St. Albans Diesel Plant 1 & 2 - St. Albans, Vermont - Welden St. 34.5 kV Bus. | 2007-11-01 | Approved | 2007-09-27
NEP-07-T12 | 2007-07-30 | Auburn Street 115 kV Substation | Install two new 115 kV circuit breakers at the Auburn Street south ring bus and reconnect the Auburn - Kingston #191 line to a new 115 kV bus position at Auburn Street. This is required by the new Brook Street - Auburn Street proposed #194 line addition. | 2007-09-30 | Approved | 2007-08-17
NSTAR-07-T08 | 2007-07-30 | Carver 345 kV Substation | Expand Carver Substation. | 2008-09-30 | Approved | 2007-08-17
NSTAR-07-T09 | 2007-07-30 | Tremont 115 kV Substation | Install one 115 kV circuit breaker at the Tremont 115 kV Substation. Install a second 8.3 mile Carver - Tremont 115 kV line as the proposed #134 line on the same towers as the 127 and 128 lines. | 2007-09-30 | Approved | 2007-08-17
NSTAR-07-T10 | 2007-07-30 | Brook Street 115 kV Substation | Expand the Brook Street 115 kV Substation with five 115 kV circuit breakers into a breaker-and a half design. Connect the spare conductors of the Jordan Road - Auburn Street #342 line as a new circuit from the Brook Street Substation to the Auburn Street. | 2007-09-30 | Approved | 2007-08-17
NSTAR-07-T11 | 2007-07-30 | Kingston 115 kV Substation | Upgrade the Kingston terminal of the Kingston -Auburn #191 line by replacing a disconnect switch at the Kingston 115 kV Substation. Reduce the clearing of the #117 line at Kingston for a fault at Brook Street from 47 cycles to 29 cycles. | 2007-09-30 | Approved | 2007-08-17
NSTAR-07-T12 | 2007-07-30 | Barnstable 115 kV Substation | Expand the Barnstable 115 kV Substation with a 5th bay with two 115 kV circuit breakers. Install a 100 MVAR STATCOM dynamic voltage control device at the Barnstable Substation. | 2007-09-30 | Approved | 2007-08-17
VELCO-07-T04 | 2007-07-29 | Duxbury | Construct from the proposed Duxbury Switching station a 9.5 mile 115 kV 1272 ACSR line to Stowe Vermont where the voltage will be stepped down from 115 kV to 34.5 kV in a four breaker ring substation. | 2008-09-30 | Approved | 2007-08-16
UPC-07-G02 | 2007-07-24 | Sheffield Wind | Sheffield Wind Project | 2008-04-01 | Approved with conditions | 2007-08-16
UPC-07-T02 | 2007-07-24 | Sheffield Wind Project Substation | Sheffield Wind Project Substation | 2008-04-01 | Approved with conditions | 2007-08-16
VELCO-07-T03 | 2007-07-24 | Sheffield 115 kV | Construction of a three-breaker 115 kV ring station, located between Irasburg and St Johnsbury, to interconnect the Sheffield wind project. | 2008-04-01 | Approved with conditions | 2007-08-16
VELCO-07-T01 | 2007-07-19 | Middlesex Substation | Installation of a 115 kV breaker in existing Middlesex Substation. | 2007-12-01 | Approved | 2007-08-16
VELCO-07-T02 | 2007-07-19 | Duxbury Switching Station | Construct new three SCADA controlled 115 kV switching station in Duxbury, VT. | 2007-12-01 | Approved | 2007-08-16
DEM-07-G01 | 2007-06-26 | Millstone Power Station | Millstone Power Station Unit 3 Power Uprate. | 2008-11-01 | Approved with conditions | 2007-08-14
NU-07-T10 | 2007-06-22 | Scobie Pond Substation | Add 3rd Scobie Pond 345/115-kV Autotransformer. | 2008-05-01 | Approved | 2007-07-27
NU-07-T11 | 2007-06-22 | Mammoth Road Substation | Add 2nd Mammoth Rd. 115/34.5-kV Transformer. | 2008-05-01 | Approved | 2007-07-27
NSTAR-07-G01 | 2007-06-20 | MATEP 474 Brookline Avenue | Relocation of MATEP's existing Diesel Generators #2 #3 and #4 for a total of 20.25MW from the present 14kV distribution connection at Brighton Station #329 to a new 14kV distribution connection at Colburn Street Station #350. | 2007-09-15 | Approved | 2007-08-16
UI-07-T01 | 2007-06-20 | Baird Substation | Replace Two 115-kV Circuit Breakers at Baird Substation. | 2007-06-01
BHE-07-T01 | 2007-06-15 | Keene Road Substation | Keene Road substation breaker addition. | 2007-05-01 | Approved | 2007-07-27
UPC-07-G01 | 2007-06-15 | Stetson Mountain Wind Units 1-40 | New 60MW wind generation addition on Stetson Mountain. | 2008-07-01 | Approved | 2007-07-27
UPC-07-T01 | 2007-06-15 | Keene Road Substation | 115 kV transmission line/generator lead addition. This transmission line will be the generator lead from the BHE Keene Road substation to the Stetson Wind V Project. | 2007-12-01 | Approved with conditions | 2007-07-27
NU-07-T09 | 2007-05-22 | Silver Substation | Silver Substation Replace 30MVA Transformer with 47MVA Transformer Project. | 2007-06-01 | Approved | 2007-06-15
NU-07-T07 | 2007-05-21 | Swanzey Substation | Swanzey Substation Replace 5MVA Transformer with 15MVA Transformer Project. | 2009-06-01 | Approved | 2007-06-15
NU-07-T06 | 2007-05-14 | Jackman Substation | Jackman Substation replace 20MVA transformer with a 44MVA transformer. | 2008-06-01 | Approved | 2007-06-15
ENB-07-DR01 | 2007-05-11 | New Boston | Put New Boston Unit 1 into deactivated reserve status. | 2007-08-01 | Approved | 2007-07-10
NU-07-T04 | 2007-05-11 | Russell Biomass | Construct and interconnect a nominally rated 55 MW, General Electric turbine generator at Russell, MA, via a 65 MVA 13.8/115 kV generator step-up transformer and 5.3 miles of 115 kV transmission line to the 115 kV #1512 Line, between Elm Substation and Granville Junction. | 2009-06-01 | Approved with conditions Withdrawn | 6/6/2007 5/15/2012
NU-07-T05 | 2007-05-11 | Ludlow 345 kV | Ludlow 345 kV 6T circuit breaker addition. | 2008-06-01 | Approved | 2007-06-15
NSTAR-07-T05 | 2007-05-10 | Walpole Station | Install new 37/50/62.5 MVA, 117/15.12 kV Transformer 110B. | 2007-06-01 | Approved with conditions | 2007-06-15
FLP-07-X01 | 2007-05-08 | Mount Tom Generating Station | Replace existing Amplidyne voltage regulator with a dual Basler DECS-400. | 2007-05-30 | Approved | 2007-06-06
NRG-07-G01 | 2007-05-02 | Cos Cob | Cos Cob 13 & 14 generation. | 2008-02-01 | Approved with conditions | 2007-05-15
NRG-07-T01 | 2007-05-02 | Cos Cob Village | Generator lead and new generator step up transformer For Cos Cob Station. | 2008-02-01 | Approved with conditions | 2007-06-06
GB-07-RR01 | 2007-05-01 | Newport Diesel | Retirement of the Newport diesels assets #522-523. | 2007-07-01 | Approved | 2007-06-08
NU-07-G03 | 2007-05-01 | Biomass-Fired Power Plant | Interconnect a nominally rated 55 MW, General Electric turbine generator at Russell, MA, via a 65 MVA 13.8/115 kV generator step-up transformer and 5.3 miles of 115 kV transmission line to the 115 kV #1512 Line. | 2009-06-01 | Approved with conditions Withdrawn | 6/6/2007 5/15/2012
NU-07-G02 | 2007-04-30 | Plainfield Renewable Energy | Construct and interconnect a nominally rated 44 MW, wood-fired General Electric turbine generator at Plainfield, CT, via a 50MVA 13.8/115 kV generator step-up transformer and 0.5 mile of 115 kV radial transmission line tapped on the 115 kV #1505 Line between Fry Brook Substation and Plainfield Junction. | 2008-12-29
NSTAR-07-T04 | 2007-04-27 | 115 kV | Installation of three new 115 kV shunt capacitor banks and and the uprate of three | 2007-06-01 | Approved | 2007-06-05
UI-05-T01 Rev.1 | 2007-04-27 | Singer, Pequonnock, and Bridgeport Substations | Withdraw: Construct Singer 345-kV Substation, Modify Pequonnock 115-kV Substation, and Modify Bridgeport Energy's Interconnection. | 2009-12-01
UI-05-T02 Rev.1 | 2007-04-27 | East Devon Substation & Singer Substation | Build two 345-kV underground circuits from East Devon Substation to Singer Substation. | 2009-12-01 | Approved with conditions | 2007-06-08
UI-05-T03 Rev.1 | 2007-04-27 | Elmwest Substation & West River Substation | Withdraw previous application to install two 115-kV circuit breakers at Elmwest Substation | 2007-04-27 | Approved with conditions | 2007-06-08
UI-05-T05 Rev.1 | 2007-04-27 | Baird, Bridgeport RESCO, Broadway, Devon Tie... | Reclassify and Modify Eight Existing Substations as Northeast Power Coordinating Council (NPCC) Bulk Power System (BPS) Facilities, Independent of NRI Status. Facilities being reclassified are Baird 115-kV, Bridgeport RESCO 115-kV, Broadway 115-kV, Devon Tie 115-kV, Mill River 115-kV, Water Street 115-kV, and West River 115-kV. | 2009-12-01 | Approved with conditions | 2007-06-08
PMLD-07-RR01 | 2007-04-25 | Princeton Wind Farm | Retirement of the Princeton Wind Farm, Asset No. 968. | 2007-05-01 | Approved | 2007-05-16
NEP-07-T02 | 2007-04-24 | West Methuen | 115 kV Transmission Line G-133W and 115 kV circuit breaker and disconnect switches @ West Methuen. | 2007-12-01 | Approved | 2007-06-08
NU-03-T15 Rev.1 | 2007-04-21 | Machester & Hopewell Substations | Re-conductor the 115-kV 1767 line from Manchester to Hopewell substations in Connecticut. | 2007-04-01 | Approved | 2007-06-08
NU-07-G05 | 2007-04-18 | UMASS Amherst | UMASS Amherst #1 11.25 MVA Generator. | 2008-03-31 | Approved with conditions | 2007-07-23
TCH-07-G01 | 2007-04-17 | Vernon Station | The installation of four new 4 MW 2.8 meter semi-Kaplan hydro units, and the removal of four units that have been retired in place, designated #5, 6, 7, and 8. | 2007-12-31 | Approved with conditions | 2007-06-05
TCH-07-G02 | 2007-04-17 | Comerford Station | Replacement of all waterwheels at Comerford Station. | 2007-03-01 | Approved with conditions | 2007-06-05
NU-07-X02 | 2007-03-22 | Merrimack Generating Station | Merrimack Unit 2 voltage regulator replacement. | 2007-05-01 | Approved | 2007-04-11
DEM-07-X02 | 2007-03-21 | Salem Harbor Unit 3 (Asset ID # 553) | Generator excitation system replacement. | 2007-05-01 | Approved | 2007-04-11
NU-06-T15 Rev.1 | 2007-03-21 | Barbour Hill 23J | Barbour Hill 23J 345/115-kV substation - 600 MVA autotransformer. | 2008-06-30 | Approved | 2007-04-11
NU-07-T03 | 2007-03-20 | Plainfield Renewable Energy | 115-kV Transmission Line (Plainfield, CT - Frybrook/Plainfield, CT). | 2009-07-30
DEVON-07-G01 | 2007-03-16 | Devon Station | Devon Unit 7 return to service. | 2007-10-04 | Approved with conditions | 2007-04-17
DEVON-07-G02 | 2007-03-16 | Devon Substation | Devon Unit 8 return to service. | 2007-06-06 | Approved with conditions | 2007-04-17
GMP-07-G01 | 2007-03-15 | Essex Junction | Construction of Asset ID 410, Essex Hydro Min. Flow unit #9, rated at .830 MW. | 2007-03-15 | Approved | 2007-09-27
GMP-07-410-C-5 | 2007-03-14 | Essex Junction | Construction of Asset ID 410, Essex Hydro Min. Flow unit #5, rated at .830 MW. | 2007-06-15
GMP-07-RR01 | 2007-03-14 | Essex #19 | Retirement of Asset ID 1221, Essex Diesels units IC #5, rated at 1.0 MW. | 2007-05-01 | Approved | 2007-06-08
GMP-07-RR02 | 2007-03-14 | Essex #19 | Retirement of Asset ID 1221, Essex Diesels units IC #6, rated at 1.0 MW. | 2007-05-01 | Approved | 2007-06-08
GMP-07-RR03 | 2007-03-14 | Essex #19 | Retirement of Asset ID 1221, Essex Diesels units IC #7 rated at 1.0 MW. | 2007-05-01 | Approved | 2007-06-08
GMP-07-RR04 | 2007-03-14 | Essex #19 | Retirement of Asset ID 1221, Essex Diesels units IC #8, rated at 1.0 MW. | 2007-05-01 | Approved | 2007-06-08
RESERVE | 2007-03-14 | Essex Junction | RESERVE | 2007-05-01
NU-05-T35 Rev.2 | 2007-03-06 | Beacon Falls Substation | Reconductor the 115-kV 1570 Line Tap into Beacon Falls Substation. | 2009-12-01 | Approved | 2007-04-11
NEP-04-T24 Rev.1 | 2007-02-27 | L-190 Line | Construction of a new 12.3 mile extension of the L-190 115 kV line from the Old Baptist Road Tap to the West Kingston Substation with 1590 ACSR. | 2008-06-01 | Approved with conditions | 2007-04-11
NEP-04-T25 Rev.1 | 2007-02-27 | West Kingston Substation | Install 2nd 115 kV breaker and two (2) disconnect switches, replace existing 115 kV breaker #7085 and associated disconnect switches,install new 115 kV bus structures and conductors, install new substation fence, install new dead end structures with two (2) motor operated air break switches for the G185S and L190 lines within the new substation fence, and reterminate the West Kingston No. 2 115-34.5 kV transformer to the new line from the 1870N line. | 2008-06-01 | Approved with conditions | 2007-04-11
NEP-04-T26 Rev.1 | 2007-02-27 | L-190 Line | Reconductor the 115 kV Line L190 from Kent County Substation to Old Baptist Road Tap. | 2008-06-01 | Approved with conditions | 2007-04-11
NEP-04-T27 Rev.1 | 2007-02-27 | West Kingston and Kenyon | Reconductor the 115 kV Line 1870N from West Kingston Substation to Kenyon Substation. | 2008-06-01 | Approved with conditions | 2007-04-11
NEP-04-T28 Rev.1 | 2007-02-27 | Kenyon and Wood River | Reconductor the 115 kV Line 1870 from Kenyon Substation to Wood River Substation. | 2008-06-01 | Approved with conditions | 2007-04-11
NEP-07-X01 | 2007-02-26 | Wood River and Shunock Substations | Removal of the 1870 Special Protection System following completion of the L-190 extension, West Kingston Substation expansion, L-190 reconductoring, 1870N reconductoring, and 1870 reconductoring as part of the Southern Rhode Island Project. | 2008-07-01 | Approved with conditions | 2007-04-11
NU-05-T23 Rev.1 | 2007-02-26 | Scovill Rock 345 kV Switching Station | Expand the 345 kV Scovill Rock Switching Station and terminate associated 345 kV Lines. | 2009-12-01 | Approved with conditions | 2007-04-11
NU-05-T24 Rev.1 | 2007-02-26 | Beseck Junction | Construct Beseck 345 kV Switching Station and terminate associated 345 kV Lines. | 2009-12-01 | Approved with conditions | 2007-04-11
NU-07-T02 | 2007-02-20 | Weare Substation | 44.8 MVA 115/34.5kV transformer, two 115kV circuit breakers which will sectionalize the F162 Line. A 115kV 28.8 MVAR capacitor bank at Jackman Substation. | 2008-06-01 | Approved | 2007-04-11
CMEEC-07-T01 | 2007-02-02 | Wallingford 115 kV Substation | Construction of new 115-kV circuit breaker and line position and addition of a new generator step-up transformer at the Wallingford 115-kV Substation to interconnect the proposed Pierce Generation Unit. | 2007-07-08 | Approved with conditions | 2007-03-08
CMEEC-07-G01 | 2007-02-01 | Pierce Generation Unit | Wallingford Pierce Generator | 2007-10-01 | Approved with conditions | 2007-03-08
CMP-07-T01 | 2007-01-31 | Maine Yankee 115 kV | Add a new distribution substation with a 10/14 MVA, 115/12.47 kV transformer, at the former Maine Yankee 115 kV yard. Section 207A already exists at the proposed site. | 2007-06-01 | Approved | 2007-03-09
NU-07-X01 | 2007-01-31 | Millstone 345kV Substation | Millstone SLOD Type 1 SPS. | 2007-03-30 | Approved | 2007-03-09
SHELD-07-T01 | 2007-01-31 | Pineshed 23F Substation | Replace the existing 2X transformer, which is rated 15/20/25 MVA with a larger transformer rated 33/44/55 MVA. | 2008-05-15 | Approved | 2007-04-11
CMP-06-T11 Rev.1 | 2007-01-30 | Buxton Substation | Install four 345 kV breakers in a breaker-and-a-half configuration at Buxton substation and re-terminate Section 386 and Section 374. | 2007-12-01 | Approved | 2007-03-09
NEP-07-T01 | 2007-01-30 | Monroe Converter Station | To retire the Monroe converter station and related Phase I HVDC facilities; retain four (4) 20 Mvar of switched shunt reactors and four (4) 31.5 Mvar of switched capacitors. | 2007-03-31 | Approved with conditions | 2007-03-08
NSTAR-07-X01 | 2007-01-29 | Edgar | Trip setting of existing Edgar Special Protection System. | 2007-01-04 | Approved | 2007-03-20
NU-04-T03 Rev.1 | 2007-01-29 | Norwalk & Peaceable 115 kV Stations | 115-kV line from Norwalk to Peaceable (1470) reconfiguration. | 2005-11-01 | Approved | 2007-03-09
NU-05-T09 Rev.1 | 2007-01-29 | Norwalk and Glenbrook Substations | Installation of two, 115-kV 3500 kcmil XLPE cables between Glenbrook and Norwalk. | 2008-12-01 | Approved | 2007-03-09
NU-04-T01 Rev.1 | 2007-01-25 | Plumtree and Norwalk 345 kV Stations | 345-kV Plumtree to Norwalk line and associated substation changes. | 2006-03-20 | Approved | 2007-03-09
NU-07-T01 | 2007-01-19 | Monadnock | Mobile 35 MVA 115/34.5-kV Transformer Installed at Monadnock, located in Monadnock New Hampshire in the Public Service Company of New Hampshire (PSNH) service territory. | 2006-07-01 | Approved | 2007-03-09
NSTAR-07-T03 | 2007-01-17 | Fisher Road Substation | Upgrade the Fisher Road Substation #657 Transformer #1 from a 10/12 MVA 115/13.2kV non-LTC transformer to a 12/16/20 [22.4] MVA 115/13.2kV transformer with LTC, remove secondary regulators, and associated upgrades. | 2007-06-15 | Approved | 2007-03-09
DEM-07-X01 | 2007-01-03 | Brayton Point Station | Replacement of Automatic Voltage Regulator on Brayton Point Unit 3. | 2006-05-01 | Approved with conditions | 2007-01-18
NU-07-G01 | 2007-01-02 | Pratt and Whitney | 9 MVA, 7.2 MW @ 0.8 PF Gas Turbine Generator. | 2007-09-30 | Approved with conditions | 2007-03-18
EME-06-T01 Rev.1 | 2006-12-29 | Nash Stream Substation | Construction of the new Maine Mountain Windpower's Electric Harvest Substation. | 2007-12-31 | Approved | 2007-03-18
BP-06-T01 | 2006-12-28 | Rumford Falls Hydro | Re-connect existing Rumford Falls Hydro generation through new 11.5 kV : 115 kV generator step up transformer to new NewPage 115 kV Substation. | 2008-06-01 | Approved | 2007-03-18
CMP-06-T17 | 2006-12-21 | Rumford Substation | Add three 115 kV breakers in a ring-bus configuration, with a spare position for a future 115 kV circuit breaker, at a new NewPage 115 kV Substation, in Rumford, Maine, at the radial terminus of 115 kV line Section 218. | 2008-06-01 | Approved | 2007-01-18
NEP-06-T12 | 2006-12-20 | Sandy Pond HVDC | Convert two (2) existing 345 kV capacitor banks at Sandy Pond HVDC yard to 5th Harmonic Filters. | 2007-09-30 | Approved | 2007-01-18
NSTAR-07-T01 | 2006-11-29 | Marshfield Substation #739 | Upgrade Marshfield Substation #739 from a 12/16/20 MVA transformer to a 30/40/50 MVA transformer, and upgrade associated ancillary equipment. | 2007-06-01 | Approved | 2007-01-18
NSTAR-07-T02 | 2006-11-29 | Otis Substation #915 | Upgrade Otis Substation #915 from a 16/21/26 MVA transfomer to a 30/40/50 MVA transformer. | 2007-06-01 | Approved | 2007-01-18
CMP-06-T13 | 2006-11-28 | Benton Switching Station | Install six (6) 115 kV breakers in a ring-bus configuration and a 20 MVAr capacitor bank at the proposed new Benton 115 kV switching station in Benton, Maine. | 2008-12-01 | Approved with conditions | 2007-01-18
NEP-06-T06 Rev.1 | 2006-11-21 | Bellows Falls Substation | Bellows Falls Substation revitalization. | 2008-05-01 | Approved | 2007-03-21
NU-06-G01 | 2006-11-19 | Lempster Wind Generating Facility | Modification of the existing protective relaying scheme that transfer trips the Hemp Hill generation for loss of the Webster-North Road and North Road-Ascutney 115 kV transmission lines. | 2006-11-01 | Approved with conditions | 2006-12-27
BHE-05-G01 Rev.1 | 2006-11-16 | Georgia Pacific Mill | Interconnect a 16 MW generator at Georgia Pacific. | 2002-05-31 | Approved with conditions | 2006-11-30
CON-06-RR01 | 2006-10-30 | Asset # 1259 | Retirement of generator, J&L Electric Biomass One (Asset # 1259). | 2006-11-01 | Approved | 2007-03-20
CON-06-RR02 | 2006-10-30 | Asset # 10566 | Retirement of generator, J&L Electric Biomass One (Asset # 10566). | 2006-11-01 | Approved | 2007-03-20
NEP-06-T11 | 2006-10-19 | Wareham St. Substation | Close the E1-M1 115kV line loop at Wareham St. substation by adding three 115kV circuit breakers on the ring bus. | 2007-10-01 | Approved with conditions | 2006-12-14
NSTAR-06-T07 | 2006-10-18 | Tremont Substation | Addition of two bus tie breakers to Tremont 115-kV Substation to Sectionalize the Bus. | 2006-12-15 | Approved | 2006-12-14
VELCO-03-T02 Rev.1 | 2006-10-18 | Blissville 115 kV | Upgrade the Blissville substation with a phase angle regulating transformer (PAR) rated 350 MVA and +/-60. | 2006-12-21 | Approved | 2006-12-18
VELCO-03-T06 Rev.1 | 2006-10-18 | Granite 115 kV and 230 kV | At the Granite substation, replace the existing 230/115 kV autotransformer, and add a second 230/115 kV autotransformer, two 115 kV PARs rated 350 MVA and +/-60o, three 115 kV breakers, four 25 MVAr synchronous condensers, and 230 kV bus work with two breakers. | 2007-12-31 | Approved | 2006-12-20
VELCO-03-T07 Rev.1 | 2006-10-18 | Granite 115 kV | Reconductor the Granite-Barre 115 kV line. | 2006-05-01 | Approved | 2006-12-18
VELCO-03-T10 Rev.1 | 2006-10-18 | West Rutland 345 kV | Construct a new 35.7 mi 345 kV line with bundled 954 ACSR conductors from West Rutland to New Haven. | 2006-12-31 | Approved | 2006-12-18
VELCO-03-T11 Rev.1 | 2006-10-18 | Vergennes | Construct a new Vergennes 115 kV substation with two breakers, and a 115/34.5 kV 15 MVA transformer. | 2007-06-01 | Approved | 2006-12-19
VELCO-03-T15 Rev.1 | 2006-10-18 | Queen City | Rebuild the Queen City 115 kV substation from a radial bus to a six-position, four-breaker 115 kV ring bus. | 2007-06-01 | Approved | 2006-12-19
VELCO-03-T16 Rev.1 | 2006-10-18 | 115 kV line New Haven - Queen City | Replace the 27.2-mile 46kV/34.5 kV sub-transmission line with a 115 kV line from New Haven to Vergennes to North Ferrisburg to Charlotte to Shelburne to Queen City, single pole construction with 1272 ACSR conductors. Approximately 1.7 miles of this line will be underground 2500 MCM CU between Shelburne and Queen City. | 2007-12-31 | Approved | 2006-12-18
VELCO-06-T06 | 2006-10-18 | West Rutland 115 kV | Increase the length of the K-30 line (West Rutland-Middlebury) by approximately 1,050 feet. | 2006-12-31 | Approved | 2006-12-18
VELCO-06-T07 | 2006-10-18 | Middlebury 115 kV | Decrease the length of the K-63 line (Middlebury-New Haven) by approximately 600 feet. | 2006-12-31 | Approved | 2006-12-18
VELCO-06-T08 | 2006-10-18 | New Haven 115 kV | Increase the length of the K-43 line (New Haven-Williston) by approximately 1,100 feet. | 2006-12-31 | Approved | 2006-12-18
DEM-06-X01 | 2006-10-17 | Salem Harbor Unit 1 | Project will replace existing rotating AC excitation system for Salem Harbor Unit 1 with GE EX2100 static excitation system. | 2006-11-01 | Approved with conditions | 2006-11-14
NU-05-T22 | 2006-10-17 | Cedar Heights | Two new 115 kV circuit breakers and 115/13.8 kV transformer. | 2007-05-01 | Approved | 2005-11-08
NEP-06-T10 | 2006-10-11 | Melrose | At Melrose #25 substation, install a new 115/13.8kV low profile substation with two 55MVA transformers. | 2006-11-15 | Approved | 2006-11-14
VELCO-06-X01 | 2006-10-07 | Highgate | Modify the Highgate HVDC Converter runback schemes. | 2007-06-01 | Approved | 2006-10-24
ENB-06-DR01 Rev.1 | 2006-09-27 | New Boston | New Boston Unit 1 deactivation. | 2006-11-15 | Approved | 2006-10-24
NEP-06-T09 | 2006-09-20 | Auburn St. Substation | Install new 345kV gas circuit breaker on line #335 at Auburn St. | 2006-06-01 | Approved | 2006-10-24
CMEEC-06-T01 | 2006-09-18 | Buddington | New 16L-4T-2 115-kV circuit breaker and 1410 line relay replacement. | 2006-10-31 | Approved | 2006-10-24
CMP-06-T12 | 2006-09-08 | Anson Substation | Tap Sect. 63B (customer owned) and construct a new 115/34.5 kV substation. | 2006-12-31 | Approved | 2006-10-27
VELCO-06-T03 | 2006-09-07 | East Avenue Substation | Rebuild the East Avenue substation to a 4-breaker ring. | 2007-06-01 | Approved | 2006-10-24
VELCO-06-T04 | 2006-09-07 | Gorge Substation | Construct a new 2-breaker substation at Gorge. | 2010-06-01 | Approved | 2006-10-24
VELCO-06-T05 | 2006-09-07 | Tafts Corner | Rebuild the K-25 line from H-frame to single-pole and construct a new single-pole 115 kV line on the same ROW. | 2009-06-01 | Approved | 2006-10-24
NEP-05-T06 | 2006-08-18 | Tewksbury 22 Substation | Swapping of the L-164 and A-153 115 kV radial line positions. | 2005-11-01 | Approved | 2005-07-25
NEP-05-T10 | 2006-08-16 | Snow St Substation | Replacement of two 115/23kV transformers with two 115/13.2kV transformers at Snow St substation in Southbridge, Massachusetts. | 2006-04-01 | Approved | 2005-09-02
NEP-05-T11 | 2006-08-16 | West Amesbury Substation | West Amesbury substation installation of the 345/115 kV and 115/23 kV transformers and a 345 kV and a 115 kV breakers. | 2005-09-20 | Approved | 2005-11-08
NEP-05-T13 | 2006-08-16 | Shaker Road Substation | Replacement of existing 69/13.8 kV transformer at Shaker Road substation. | 2005-11-14 | Approved | 2005-12-27
NU-05-T27 | 2006-08-15 | East Devon and Devon 115 kV Substations | Build Two 115 kV Circuits from East Devon Substation to Devon Substation. | 2009-12-01 | Approved | 2005-12-20
NU-05-T31 | 2006-08-15 | Devon 115 kV Substation | Install an additional 115 kV circuit breaker and permanently open the 1480 bus tie at the Devon 115 kV Substation. | 2009-12-01 | Approved | 2005-12-20
NU-05-T51 | 2006-08-14 | Haddam Neck 14B and Southington 4C Substations | Upgrade the Line 362 terminals at the Haddam Neck 14B and Southington 4C substations. | 2006-12-30 | Approved | 2005-12-27
NSTAR-06-G01 | 2006-07-19 | Medical Area Total Energy Plant | Medical Area Total Energy Plant. | 2006-12-21 | Approved | 2006-09-11
NU-06-T15 | 2006-07-18 | Barbour Hill | New 345-115 kV 600 MVA autotransformer to be located at the Barbour Hill 23J Substation. | 2008-06-30 | Approved | 2006-09-11
NU-06-T18 | 2006-07-13 | Oak Hill | Proposes adding a 2nd distribution transformer at Oak Hill substation and two breakers. | 2007-06-30 | Approved | 2006-09-11
NU-06-T19 | 2006-07-13 | Timber Swamp | Adding a new 345/34.5kV transformer and construct a four breaker ring bus at Timber Swamp Substation. | 2007-06-30 | Approved | 2006-09-11
PP-06-G01 | 2006-07-13 | Waterside Power | Construction of the 210.9 MW gross (at 50 F) Waterside Power Generation Project. | 2010-03-10 | Approved Withdrawn | 7/25/2006 11/17/2010
PP-06-T01 | 2006-07-13 | Waterside 22M Substation | Interconnecting the Waterside Power Generation Project at the Waterside 22M Substation. | 2010-03-10 | Approved Withdrawn | 7/25/2006 11/17/2010
NU-06-T16 | 2006-07-10 | Waterside | Replace 69MW of emergency peaking generation with an interconnection request of permanent generation. | 2010-03-01 | Approved | 2006-07-25
NU-06-X02 | 2006-07-10 | South End Substation | South End Substation and 1977 line relaying modifications. | 2010-03-01 | Approved | 2006-07-25
NU-06-T17 | 2006-07-05 | Scobie Pond | Reinforcement of the Scobie Pond 115 kV Substation to the Hudson 115 kV Substation. | 2008-05-01 | Approved | 2006-07-25
CMP-06-T03 | 2006-06-30 | Wyman Hydro Substation | Modification of the current configuration at Wyman Hydro with regard to Section 215 and Section 63. | 2007-07-01 | Approved | 2006-06-16
NEP-06-G02 | 2006-06-30 | Lowell | Install a new 115 kV tap (0.1 mile) utilizing 795 ACSR by tapping J-162 line to interconnect Lowell Power generation facilities. | 2007-12-01 | Approved Withdrawn | 7/25/2006 12/18/2012
NEP-06-T07 | 2006-06-30 | Lowell | Install a new 115 kV tap (0.1 mile) utilizing Lowell Power generation facilities. | 2007-12-01 | Approved Withdrawn | 7/25/2006 12/18/2012
NEP-06-T08 | 2006-06-30 | Sandy Pond | At Sandy Pond 115 kV substation replace two 115 kV circuit breakers. | 2007-12-01
CMP-06-T05 | 2006-06-13 | Maguire Road | Installation of nine (9) 115 kV circuit breakers in a breaker and a half configuration. | 2007-12-01 | Approved | 2006-06-23
CMP-06-T06 | 2006-06-13 | Louden and Maguire Road | The rebuild of 12 miles of 115 kV Section 163 between the Louden and the Maguire Road Substations. | 2008-01-01 | Approved | 2006-06-23
CMP-06-T07 | 2006-06-13 | Quaker Hill and Three Rivers | The rebuild of 9 miles of 115 kV Section 197 between the Quaker Hill and the Three Rivers Substations. | 2008-01-01 | Approved | 2006-06-23
CMP-06-T08 | 2006-06-13 | South Gorham and Louden | The rebuild of 9 miles of 115 kV Section 219 between the South Gorham and the Louden Substations. | 2008-12-01 | Approved | 2006-06-23
CMP-06-T09 | 2006-06-13 | South Gorham and Louden | The reconductoring of 9 miles of 115 kV Section 220 between the South Gorham and Louden Substations. | 2008-01-01 | Approved | 2006-06-23
CMP-06-T10 | 2006-06-13 | Sanford | The installation of a 30MVAr capacitor at the Sanford Substation. | 2007-12-01 | Approved | 2006-06-23
CMP-06-T11 | 2006-06-13 | Buxton | The installation of three (3) 345 kV breakers at the Buxton Substation by expanding the existing breaker and a half configuration. | 2008-12-01 | Approved | 2006-06-23
NU-06-X01 | 2006-06-13 | Lake Road | Modify the existing Lake Road Type III generation rejection special protection system (SPS). | 2006-12-31 | Approved with conditions | 2006-09-11
CMP-06-T02 | 2006-06-12 | Raymond Substation | Add (2) 115 kV line breakers and 2nd transformer. | 2006-12-31 | Approved | 2006-06-23
CMP-06-T04 | 2006-06-06 | Louden and Branch Brook Substations | Construction of a new 115 kV West Kennebunk Substation. | 2006-12-31 | Approved | 2006-06-23
EME-06-G01 | 2006-05-30 | Maine Mountain Power Windfarm | Addition of a new wind powered generating station, the Maine Mountain Power Windfarm. | 2007-12-31 | Approved with conditions | 2006-06-16
EME-06-T01 | 2006-05-24 | Nash Stream Substation | Construction of the new Maine Mountain Windpower's Electric Harvest Substation. | 2007-12-31 | Approved with conditions | 2006-06-10
NEP-06-G01 | 2006-05-24 | Fitchburg | Construction of the 7.2 MW Westminster Landfill Generation Project. | 2007-06-01 | Approved | 2006-06-16
DEVON-06-G01 | 2006-05-09 | Devon Station | Interconnection of Devon Power LLC's Unit #10. | 2006-06-29 | Approved with conditions | 2006-06-23
NEP-06-RR01 | 2006-05-06 | Nantucket | Retirement of six Nantucket diesel generators. | 2006-10-31 | Approved | 2006-07-25
NSTAR-06-T01 | 2006-05-02 | Chelsea Substation | Construct a six breaker 115 kV ring bus at Chelsea Substation #488. | 2006-06-01 | Approved with conditions | 2006-05-10
ENB-06-DR01 | 2006-05-01 | New Boston | Deactivated Reserve Asset # 505, the New Boston Unit No. 1 generating plant. | 2007-01-01 | Approved | 2006-07-25
NEP-06-T01 | 2006-05-01 | Sykes Road | Install a new 115 kV Tap from the M13 line, a 40 MVA 115/13.8 kV transformer, a 115 kV circuit switcher, and two 115 kV wave traps. | 2007-04-01 | Approved with conditions | 2006-06-16
NU-06-T13 | 2006-04-18 | Dooley 30K | Installation of a 115 kV circuit breaker. | 2006-06-01 | Approved | 2006-05-10
NU-06-T14 | 2006-04-18 | Sasco Creek 21R | Installation of a temporary 18 MVA, 115/13.8 kV transformer and a 115 kV circuit breaker at the Sasco Creek 51R Substation. | 2006-06-01 | Approved Withdrawn | 5/10/2006 6/20/2012
BHE-06-T01 | 2006-04-17 | Boggy Brook | Construction of a new 115 kV radial overhead transmission Line 61. | 2007-12-01 | Approved | 2006-05-10
BHE-06-T02 | 2006-04-14 | Boggy Brook | 35 miles of new 115 kV network transmission line originating as a tap on the new Line 61. | 2009-12-01 | Approved | 2006-05-10
NU-06-T12 | 2006-04-13 | Deerfield Substation | Install a new 345-kV circuit breaker at the Deerfield Substation. | 2006-06-01 | Approved | 2006-05-10
NEP-06-T06 | 2006-04-12 | Bellows Falls | Transmission upgrades in support of the Bellows Falls No. 14 Station Revitalization Project. | 2008-05-01 | Approved | 2006-05-10
NSTAR-06-T06 | 2006-03-24 | Sudbury Substation | Installation of a 52.5 MVA, 118 kV capacitor bank and a 115 kV isolating circuit breaker at the Sudbury Substation. | 2006-06-01 | Approved | 2006-05-10
NEP-06-X03 | 2006-03-23 | Millennium Power Plant | Activate power system stabilizers and modify excitation system parameters. | 2005-11-01 | Approved | 2006-04-07
NSTAR-06-T05 | 2006-03-23 | Needham Substation | Addition of a 37/50/62.5 MVA, 117/15.12 kV transformer at the Needham #148 Substation. | 2006-06-01 | Approved | 2006-05-10
CMP-06-X01 | 2006-03-01 | Maxcy's and Bucksport | NPCC Type I Special Protection System. | 2007-01-01 | Approved | 2006-03-24
NU-06-T06 | 2006-03-01 | Greggs Falls and Jackman | The F162 115 kV transmission line will be replaced with a new 1590 kcmil ACSR transmission line. | 2009-12-31 | Approved | 2006-03-24
NU-06-T07 | 2006-03-01 | Garvins and Webster | The V182 115-kV transmission line will be replaced with a new 1590 kcmil ACSR transmission line. | 2009-12-31 | Approved | 2006-03-24
NU-06-T08 | 2006-03-01 | Keene and Chestnut Hill | Replace a 5 mile section of the A152 115-kV transmission line with a new 1590 kcmil ACSR transmission line. | 2009-12-31 | Approved | 2006-03-24
NU-06-T09 | 2006-03-01 | Monadnock | Replace the 115-kV tap conductor that connects the Monadnock Substation. | 2009-12-31 | Approved | 2006-03-24
NU-06-T10 | 2006-03-01 | Fitzwilliam | Construction of a new 600MVA, 345/115-kV substation in Fitzwilliam, New Hampshire. | 2009-12-31 | Approved | 2006-03-24
NU-06-T11 | 2006-03-01 | Webster | Replace limiting secondary equipment at the Webster Substation 115 kV bus on the M127 115 kV transmission line terminal. | 2009-12-31 | Approved | 2006-03-24
WGE-06-T01 | 2006-03-01 | Buck Pond Substation | Addition of a second 25 MVA self cool/46.667 MVA FOA, 115/23 kV distribution transformer at the Buck Pond Substation. | 2007-06-01 | Approved | 2006-04-07
NSTAR-06-T02 | 2006-02-14 | Tremont Substation | Upgrading the existing Tremont Substation #113 transformer from a 12 MVA 115/23 kV transformer to a 12/16/20 MVA 115/23 kV transformer. | 2006-06-01 | Approved | 2006-03-24
NSTAR-06-T03 | 2006-02-14 | Orleans Substation | Upgrading the existing Orleans Substation #119 transformer from a 20/26/33 MVA 115/23 kV transformer to a 30/40/50 MVA 115/23 kV transformer. | 2006-06-01 | Approved | 2006-03-24
NSTAR-06-T04 | 2006-02-14 | Rochester Substation | Upgrading the existing Rochester Substation #114 transformer from a 5/7 MVA 115/13.2 kV transformer to a 10/12.5 MVA 115/13.2 kV transformer. | 2006-06-01 | Approved | 2006-03-24
NEP-06-T03 | 2006-02-06 | Bellows Falls and Ascutney Tap | Retension the 115 kV W-149S line between Bellows Falls substation and Ascutney Tap. | 2006-04-01 | Approved | 2006-03-24
NEP-06-T04 | 2006-02-06 | Bellows Falls | Reconductoring the 51 mile long 115 kV I-135N Line between the Bellows Falls Substation and the Flagg Pond Substation. | 2008-06-01 | Approved | 2006-03-24
UI-06-T01 | 2006-02-06 | Milvon Substation | Replace fixed tap transformers at Milvon Substation with Load Tap Changing (LTC) transformers. | 2006-06-01 | Approved | 2006-03-22
UI-06-T02 | 2006-02-06 | Ansonia Substation | Replace fixed tap transformers at Ansonia Substation with Load Tap Changing (LTC) transformers. | 2006-12-01 | Approved | 2006-03-24
VELCO-06-T01 | 2006-02-06 | Coolidge Substation | Install a dynamic reactive device capable of a 150 MVAr range. | 2009-06-01 | Approved | 2006-03-24
VELCO-06-T02 | 2006-02-06 | North Rutland | Replacement of the 800 ampere K35 breaker. | 2009-06-01 | Approved | 2006-03-24
NEP-06-T02 | 2006-02-01 | E. Bridgewater | Install new 115 kV tap to the L1 line and 115/13.8 kV transformer at East Bridgewater substation. | 2006-12-30 | Approved | 2006-02-17
NU-06-T03 | 2006-02-01 | Scobie Pond | Addition of the Brentwood 115/34.5 kV substation. | 2006-05-01 | Approved | 2006-02-17
NU-06-T04 | 2006-02-01 | Scobie Pond | Addition of 115 kV Line N124. | 2006-05-01 | Approved | 2006-02-17
NU-06-T05 | 2006-02-01 | Scobie Pond 115 kV Substation | Reconfiguration of the 115 kV Scobie Pond Substation. | 2006-05-01 | Approved | 2006-02-17
NEP-06-X01 | 2006-01-31 | Moore and Comerford | Replacement of existing BJ-30 type voltage regulators with new voltage regulators. | 2010-12-31 | Approved | 2006-02-17
CES-06-DR01 | 2006-01-27 | Androscoggin Energy Center | Place in Deactivated Reserve the Androscoggin Energy Center. | 2006-04-30 | Approved | 2006-04-07
NU-05-T52 | 2006-01-26 | Oxford Substation | Construction of the new Oxford 26N 115/13.8 kV Substation. | 2008-05-01 | Approved | 2006-01-26
NU-06-T02 | 2006-01-18 | South End 1G | Addition of a 3rd 115 kV circuit breaker back-to-back with the existing Breaker 6T at the South End 1G Substation. | 2007-05-01 | Approved | 2006-02-17
NU-06-T01 | 2006-01-06 | 115 kV Ludlow 19S Substation | Addition of a circuit breaker in the 42T position at the 115 kV ludlow 19S Substation. | 2006-03-08 | Approved | 2006-02-17
NU-05-T55 | 2005-12-23 | Saco Valley Substation | Addition of a phase angle regulator on the Y-138 line with two 115 kV circuit breakers and a bypass switch. Addition of a 115 kV circuit breaker on the K1214 line connecting Saco Valley to the Maine border. | 2008-12-31 | Approved | 2006-01-26
NU-05-T56 | 2005-12-23 | White Lake Substation | Addition of a 14.4 MVar 115 kV capacitor bank with a 115 kV circuit switcher. Addition of a 7.2 MVar 115 kV capacitor bank with a 115 kV circuit switcher. Addition of 115 kV circuit breakers on the Y138 and B112 lines. | 2008-12-31 | Approved | 2006-01-26
NU-05-T57 | 2005-12-23 | Beebe River Substation | Addition of a phase angle regulator at the Saco Valley substation with circuit breakers at White Lake and Saco Valley and capacitors at White Lake and Beebe River. | 2006-12-31 | Approved | 2006-01-26
NSTAR-05-T09 | 2005-12-15 | Lexington Substation | Install a new 345 kV, 160 MVAR regulating shunt reactor at Lexington substation. | 2006-05-01 | Approved | 2005-12-27
VELCO-03-T01 Rev.1 | 2005-12-15 | VELCO Sandbar Substation | Upgrade existing VELCO Sandbar Substation. | 2004-06-03 | Approved | 2005-12-27
NU-05-T53 | 2005-12-14 | Mansfield 12J | Replacement of circuit breakers at Mansfield 12J. | 2006-01-26 | Approved | 2006-01-26
NU-05-T23 | 2005-11-23 | Scovill Rock 345 kV Switching Station | Add 4 new 345 kV circuit breakers at Scovill Rock Substation. | 2009-12-01 | Approved | 2005-12-20
NU-05-T24 | 2005-11-23 | Beseck Junction | Construct a 345-kV Switching Station at Beseck Junction. | 2009-12-01 | Approved | 2005-12-20
NU-05-T25 | 2005-11-23 | East Devon 345 kV Substation | Construct East Devon 345 kV and 115 kV Substations. | 2009-12-01 | Approved | 2005-12-20
NU-05-T26 | 2005-11-23 | Beseck and East Devon 345 kV Substations | Build the 345 kV 3029 Line between Beseck Switching Station and East Devon Substation. | 2009-12-01 | Approved | 2005-12-20
NU-05-T28 | 2005-11-23 | 3165 & 3177 345 kV lines | Build Two 345-kV Underground Cables from East Devon Substation to Singer Substation. | 2009-12-01 | Approved | 2005-12-20
NU-05-T29 | 2005-11-23 | Norwalk 345 kV & 115 kV Substations | Expand the 345-kV Substation at Norwalk and Install Transfer Trip Relaying Scheme on the 1389 Line between Norwalk and Flax Hill Substations. | 2009-12-01 | Approved | 2005-12-20
NU-05-T30 | 2005-11-23 | Norwalk and Singer 345 kV Substations | Build two 345 kV underground cables from Singer Substation to Norwalk Substation. | 2009-12-01 | Approved | 2005-12-20
NU-05-T32 | 2005-11-23 | Norwalk Harbor Substation | Replace the 138/115 kV autotransformer at Norwalk Harbor Substation. | 2009-12-01 | Approved | 2005-12-20
NU-05-T34 | 2005-11-23 | North Wallingford and East Meriden Substations | Rebuild Portions of the 115 kV 1466 Line between North Wallingford-East Meriden substations. | 2009-12-01 | Approved | 2005-12-20
NU-05-T35 | 2005-11-23 | Beacon Falls Substation | Reconductor the 115-kV 1570 line tap into Beacon Falls Substation. | 2009-12-01 | Approved | 2005-12-20
NU-05-T36 | 2005-11-23 | Southington and June Street 115 kV Substations | Rebuild a portion of the 115 kV 1610 line between Cook Hill Junction and June Street Substation. | 2009-12-01 | Approved | 2005-12-20
NU-05-T37 | 2005-11-23 | Devon and Wallingford 115 kV Substations | Rebuild portions of the 115 kV 1640 line between Cook Hill Junction and Devon Substation. | 2009-12-01 | Approved | 2005-12-20
NU-05-T38 | 2005-11-23 | Branford and New Haven 115 kV Substations | Rebuild a portion of the 115 kV 1655 line between East Wallingford Junction and New Haven Junction. | 2009-12-01 | Approved | 2005-12-20
NU-05-T39 | 2005-11-23 | Devon and June Street 115 kV Substations | Rebuild a portion of the 115 kV 1685 line between June Street and Devon substations. | 2009-12-01 | Approved | 2005-12-20
NU-05-T40 | 2005-11-23 | Devon 115 kV Substation | Remove the 115-kV 1690 line from Devon Substation to Cook Hill Junction. | 2009-12-01 | Approved | 2005-12-20
NU-05-T41 | 2005-11-23 | Devon 115 kV Substation | Rebuild the 115-kV 1780 and 1790 lines from Devon Substation to Devon Tie Switching Station. | 2009-12-01 | Approved | 2005-12-20
NU-05-T42 | 2005-11-23 | East Meriden and Haddam 115 kV Substations | Rebuild a portion of the 115-kV 1975 line between East Meriden and Haddam substations. | 2009-12-01 | Approved | 2005-12-20
NU-05-T43 | 2005-11-23 | Flax Hill 115 kV Substation | Reclassify Flax Hill 115 kV Substation as an NPCC Bulk Power System Facility. | 2009-12-01 | Approved | 2005-12-20
NU-05-T44 | 2005-11-23 | Glenbrook, Southington, and Millstone Substations | Replace six 115-kV and two 345-kV circuit breakers to mitigate over-duty conditions. | 2009-12-01 | Approved | 2005-12-20
NU-05-X02 | 2005-11-23 | Scovill Rock 345 kV Switching Station | Formerly NU-05-T33 - Modify the Cross Sound Cable 387 line end-open special protection system. | 2009-12-01 | Approved | 2005-12-20
UI-05-T01 | 2005-11-23 | Singer & Pequonnock substations | Contruct Singer 345 kV Substation, Modify Pequonnock 115 kV Substation, and Modify Bridgeport Energy's Interconnection. | 2009-12-31 | Approved | 2005-12-20
UI-05-T02 | 2005-11-23 | 3165 & 3177 345 kV lines | Install two 345 kV underground circuits from East Devon to Singer substation. | 2009-12-31 | Approved | 2005-12-20
UI-05-T03 | 2005-11-23 | Elmwest substation | Install two 115 kV circuit breakers at Elmwest substation. | 2009-12-31 | Approved | 2005-12-20
UI-05-T04 | 2005-11-23 | Devon Station and Devon Tie Switching Station | Rebuild 1780 and 1790 circuits from Devon substation to Devon Tie Switching Station | 2009-12-31 | Approved | 2005-12-20
UI-05-T05 | 2005-11-23 | Baird, Bridgeport RESCO, Broadway, Devon Tie... | Elmwest, Mill River, Water Street, & West River to be modified & reclassified. | 2009-12-31 | Approved | 2005-12-20
VELCO-02-T01 Rev.1 | 2005-11-01 | Highgate Substation | Rebuild the existing VELCO and CZN Highgate Substations into a single Highgate Substation with a 115 kV ring bus, now revised to reflect a changed ring bus design. | 2005-12-01 | Approved | 2005-11-08
VELCO-02-T03 Rev.1 | 2005-11-01 | St. Johnsbury Substation | Modify St. Johnsbury substation and replace switch 39-3 with a circuit breaker, now revised to reflect the replacement of both the 39-3 and 29-3 motor operated switches with circuit breakers. | 2005-12-01 | Approved | 2005-11-08
VELCO-03-T03 Rev.1 | 2005-11-01 | Hartford Substation | Upgrade Hartford Substation to add a 24.75 MVAR capacitor bank. | 2005-12-01 | Approved | 2005-12-27
NSTAR-05-G01 | 2005-10-09 | BioGen Idec Campus | Adding a generator at the BioGen Idec Campus. | 2005-12-15 | Approved | 2005-10-14
NU-05-T20 | 2005-09-27 | Stepstone 35L Substation | Construction of the new Stepstone 35L Substation. | 2007-06-01 | Approved | 2005-11-08
NU-05-T21 | 2005-09-23 | Green Hill 30R | Installation of a third 47 MVA 115/13.2 kV distribution transformer and a 115 kV circuit breaker, with associated disconnects, at the Green Hill 30R Substation. | 2007-06-01 | Approved | 2005-11-08
NEP-05-T12 | 2005-09-19 | Hobart Street Substation | Additional third transformer at Hobart Street Substation. | 2006-04-01 | Approved | 2005-10-14
NU-05-T19 | 2005-09-08 | Cos Cob, Tomac, and South End Substations | Line 1750 (5 spans) and terminal equipment at South End. | 2006-12-01 | Approved | 2005-10-14
CMP-05-T01 | 2005-08-31 | Kimball Road Substation | Install two new 30 MVAR capacitor banks and 115/34 kV transformer at the Kimball Rd Substation. | 2007-05-01 | Approved | 2005-11-08
NU-05-T18 | 2005-08-30 | Dooley 30K | Addition of a 115/13.2 kV 2 winding transformer at Dooley 30K. | 2005-06-30 | Approved | 2005-10-14
NU-05-T17 | 2005-08-23 | Haddam 11C Substation | Install 115/23 kV, 28/37.3/46.7 MVA distribution transformer and a 115 kV circuit breaker at Haddam 11C Substation. | 2004-12-01 | Approved | 2005-10-14
NSTAR-05-T08 | 2005-08-03 | Tremont Substation | Upgrade Tremont #114 transformer to a 12/16/20 MVA 115/23kV. | 2005-08-08 | Approved | 2005-10-14
EMI-05-G01 | 2005-07-15 | Nantucket | Installation of a new offshore wind powered generating system. | 2006-06-01 | Approved | 2005-10-06
NSTAR-05-T07 | 2005-07-15 | Cape Wind | Two 115 kV underground/submarine lines + 4-115 kV shunt reactors. | 2006-12-31 | Approved Withdrawn | 10/6/2005 1/1/2014
NSTAR-05-X02 | 2005-07-15 | Barnstable | Modify the Barnstable SPS for the 2nd Nantucket interconnection project, to ramp down gen to 300 MW. | 2006-12-31 | Approved Withdrawn | 10/6/2005 1/1/2014
NSTAR-05-X03 | 2005-07-15 | Canal substation | Install SPS at Canal to trip Canal #2 or Cape Wind for l/o 322/345 DCT. | 2006-12-31 | Approved Withdrawn | 10/6/2005 1/1/2014
NEP-05-T07 | 2005-07-13 | Ward Hill Substation | Expansion of the 345 and 115 kV switchgear. | 2006-06-01 | Approved | 2005-10-06
NEP-05-T08 | 2005-07-13 | Salem Harbor Substation | Installation of two 63 MVAr 115 kV capacitor banks. | 2005-12-31 | Approved | 2005-10-06
NEP-05-T09 | 2005-07-13 | Golden Hills and Lynn Substations | Reconductor the 115 kV Q-169 line between Golden Hills Substation and Lynn Substation. | 2006-06-01 | Approved | 2005-09-02
NEP-05-X01 | 2005-07-13 | South Danvers Substation | Protection Modifications to meet NPCC requirements | 2007-12-31 | Approved | 2005-10-06
NEP-05-X02 | 2005-07-13 | East Methuen substation | Protection Modifications to meet NPCC requirements | 2007-12-31 | Approved | 2005-10-06
NEP-05-X03 | 2005-07-13 | West Methuen substation | Protection modifications to meet NPCC requirements | 2007-12-31 | Approved | 2005-10-06
NSTAR-05-T06 | 2005-07-11 | Mystic and Chelsea Substations | Upgrade 115 kV line 488-518 / P-168 between Mystic and Chelsea stations. | 2005-12-01 | Approved | 2005-09-02
NU-05-T05 | 2005-07-01 | Barbour Hill | Add second 115/23 kV, 47 MVA transformer and 115 kV circuit breaker. | 2006-12-01 | Approved | 2005-07-25
NU-05-T14 | 2005-06-28 | Pleasant and Woodland Substations | Install 2-14.4 MVAR 115 kV capacitor banks at both Pleasant and Woodland. | 2006-05-31 | Approved | 2005-07-25
NU-05-T11 | 2005-06-22 | Three Rivers 115 kV Substation | Add a 115 kV circuit breaker to the Three Rivers Substation on Line N133. | 2004-05-01 | Approved | 2005-07-25
NU-05-T12 | 2005-06-20 | Millstone 15G | Remove circuit breakers 3t and 6T due to the retirement of Millstone Unit 1. | 2005-09-30 | Approved | 2005-06-24
NU-05-T09 | 2005-06-14 | Glenbrook and Norwalk Substations | Installation of two, 115-kV 3500 kcmil XLPE cables between Glenbrook and Norwalk Substations. | 2008-12-31 | Approved | 2005-08-03
NU-05-T15 | 2005-06-10 | Plumtree 30G | Install a new 115 kV circuit breaker and a 47 MVA 115/13.8 kV transformer. | 2007-03-30 | Approved | 2005-09-01
NU-05-RR02 | 2005-06-07 | Beech Mill Hydro-Electric Facility | Retirement of Beech River Mill hydro-electric facility. | 2005-09-01 | Approved | 2005-06-24
NU-05-T08 | 2005-06-03 | Fairmont 16H | Install circuit switchers at Fairmont 16H substation. | 2005-11-15 | Approved | 2005-07-25
NU-03-T13 Rev.2 | 2005-05-31 | Haddam 11C Substation | Upgrades to the Haddam 11C Substation. | 2005-12-01 | Approved | 2005-07-25
DEM-05-T01 | 2005-05-27 | Brayton Point Station | Install 115 kV station service supply system for new air emission control equipment. | 2005-10-31 | Approved with conditions | 2005-06-24
LOWELL-05-DR01 | 2005-05-20 | Lowell Power | Request to deactivate upon approval of application. | 2005-06-01 | Approved | 2005-05-17
NSTAR-05-T05 | 2005-05-17 | North Cambridge Station #509 | In service Fall 2005. Install shunt reactor and IPT circuit breaker w/ synchronous controller. | 2005-10-31 | Approved | 2005-05-17
NU-05-T10 | 2005-05-16 | 1750 Line at Cos Cob 11R | Upgrade terminal equipment on the 1750 line at Cos Cob 11R. | 2005-06-01 | Approved | 2005-06-24
NU-05-T06 | 2005-05-03 | Ashland, Hudson, & Long Hill | Replace existing distributuin 115/34.5 kv transformers with 44.8 MVA transformers. | 2006-06-06 | Approved | 2005-06-24
NU-05-T04 | 2005-04-28 | Wilton 35A | New substation with two 115/13.8 transformers connecting on the 1470 line. | 2007-03-31 | Approved | 2005-06-24
NSTAR-05-T04 | 2005-04-26 | Chelsea Substation | Replace the 115/13.8 kV Chelsea Station #488 transformer 110C. | 2005-06-01 | Approved | 2005-06-24
CMEEC-05-G01 | 2005-04-22 | South Norwalk Electric Works Substation | Reactivation of the SNEW emergency engine with a nominal rating of 1.1 MW gross and net. | 2005-06-01 | Approved with conditions | 2005-05-20
CNEEC-05-G01 | 2005-04-22 | South Norwalk | Reactivate the SNEW EE unit (old name SNES Diesel #5) | 2005-06-05 | Approved with conditions | 2005-05-20
NU-05-T07 | 2005-03-28 | Flanders 11Y | 115 kV circuit breaker circuit switcher and MOD addition. | 2006-06-01 | Approved | 2005-04-06
BHE-05-G01 | 2005-03-01 | Georgia Pacific Mill | Interconnect a 16 MW generator at Georgia Pacific. | 2005-03-13 | Approved with conditions | 2005-03-21
CMP-05-G01 | 2005-02-23 | Union Street substation | 6 MW temporary generation to be used as backup for contingency coverage. | 2005-06-06 | Approved | 2005-03-10
NSTAR-05-T03 | 2005-02-23 | Dover Station | Install an additional 115/13.8 kv transformer at Dover station. | 2005-05-31 | Approved with conditions | 2005-03-21
NEP-05-T05 | 2005-02-22 | East Dracut | New 115/13kV trans., replace existing trans. and install two 115kV circuit switchers at East Dracut. | 2005-03-10 | Approved | 2005-03-10
NSTAR-05-T02 | 2005-02-22 | Barnstable substation - Merchant's Way | Expand Barnstable sub with 4th bay, new line Barnstable-Merchant's Way, 2 cap banks(Falmouth&Orleans). | 2005-12-15 | Approved | 2005-03-10
NSTAR-05-X01 | 2005-02-22 | Barnstable Substation | SPS will trip the #118 line, Mashpee load and block Nantucket load transfer for loss of 122/120 DCT. | 2005-12-15 | Approved | 2005-03-10
NEP-05-T04 | 2005-02-17 | 115 kV line E-183W | Relocate line E-183W between Franklin Square substation and the Phillipsdale Tap. | 2006-05-01 | Approved | 2005-03-10
NEP-05-T03 | 2005-02-15 | Merchant's Way | New distribution substation to be know as "Merchant's Way." | 2005-12-15 | Approved | 2005-03-10
NU-05-T03 | 2005-02-15 | Tioga Power Project | Build two new 115 kV substations; Bedford & N. Merrimack & line upgrades. | 2005-06-01 | Approved | 2005-03-23
NU-05-T02 | 2005-02-03 | Amherst Substation | Amherst transformer replacement - existing 18/24/30 MVA; new 28/37/47 MVA | 2005-05-31 | Approved | 2005-03-10
DEM-05-RR01 | 2005-02-02 | Salem Harbor Station | Retirement of Salem Harbor unit 1. | 2005-05-03 | Not approved | 2005-02-25
DEM-05-RR02 | 2005-02-02 | Salem Harbor Station | Retirement of Salem Harbor unit 2. | 2005-05-03 | Not approved | 2005-02-25
DEM-05-RR03 | 2005-02-02 | Salem Harbor Station | Retirement of Salem Harbor unit 3. | 2005-05-03 | Not approved | 2005-02-25
DEM-05-RR04 | 2005-02-02 | Salem Harbor Station | Retirement of Salem Harbor unit 4. | 2005-05-03 | Not approved | 2005-02-25
NEP-05-G01 | 2005-01-24 | Hoosac Wind Farm | Connection of 20, 1.5 MW wind turbines w/2 collector stations. | 2005-12-31 | Approved with conditions | 2005-02-05
NEP-05-T01 | 2005-01-24 | Hoosac Wind Farm substation | New 69/34.5 kV substation connected to Y-25S line between Deerfield and Harriman. | 2005-12-31 | Approved with conditions | 2005-02-08
NEP-05-T02 | 2005-01-24 | Y-25S | Reconductor 69 kV Y-25S line between Deerfield 5 and Harriman substations. | 2005-12-31 | Approved | 2005-02-08
VELCO-05-T01 | 2005-01-24 | Y-25 Line & Bennington Substation | Reconductor the 69 kV Y-25 line from Bennington to NGRID border & replace 115/69 trans. @ Bennington | 2005-06-01 | Approved | 2005-02-08
NU-05-G01 | 2005-01-21 | UCONN Co-Gen Facility | Interconnection of new CC generation with no net injection to NE system. | 2005-06-01 | Approved with conditions | 2005-03-21
NU-05-T01 | 2005-01-21 | UCONN Project Interconnection | Interconnection of UCONN generation to the 800 line between Mansfield and Card substations. | 2005-06-01 | Approved with conditions | 2005-03-21
NEP-04-T05 Rev.1 | 2005-01-10 | Wachusett No. 47 | Expansion of the existing Wachusett sub. to loop 345 kV lines 314 & 343. Add new 345 kV GIS sub. | 2006-09-29 | Approved | 2005-01-28
NSTAR-05-T01 | 2005-01-04 | Framingham and Speen Street Stations | The relocation of 115 kV Line 433-507 from a double circuit tower structure onto a set of new structures to be constructed. | 2005-06-01 | Approved | 2005-01-28
ENTERGY-03-X01 | 2005-01-03 | Vermont Yankee Substation | Install an NPCC Type III Special Protection System (for tripping the proposed 30 MVAR cap bank). | 2005-03-30
NU-04-X01 Rev.1 | 2005-01-03 | Lake Road | Modify the existing Lake Road Type III Special Protection System (SPS). | 2006-12-01 | Approved with conditions | 2005-01-28
NEP-04-G01 Rev.1 | 2004-12-22 | Fotistar Peabody | Construct a new simple cycle plant with a net capability of 97.2 MW. | 2006-05-01 | Approved | 2005-01-28
NU-04-T41 | 2004-12-22 | West Side 7A | Replacement of a 110/14.4 kV autotransformer at West Side 7A. | 2005-01-30 | Approved | 2005-01-28
UI-04-T04 | 2004-12-07 | Pequonnock 115 kV Substation | Uprate the 15 existing gas circuit breakers at the Pequonock 115 kV substation. | 2005-07-31 | Approved | 2005-01-28
NEP-04-T30 | 2004-11-23 | Foristar Peabody | Construction of the Fortistar Peabody 115 kV switchyard. | 2006-05-01 | Approved | 2005-01-28
NSTAR-04-T04 Rev.1 | 2004-11-23 | Stoughton Station | Phase I: New 345 kV Stoughton open air switching station with numerous associated upgrades. Phase II: Additional parallel cables to those installed in Phase I, numerous associated upgrades. Addition to the NSTAR Electric 345 kV Transmission Reliability Project as previously identified in the original submittal of NSTAR-04-T04 with the following protection system upgrades: Type III SPS. | 2006-06-01 | Approved with conditions | 2005-02-10
NU-04-T39 | 2004-11-23 | Portland 21H Substation | Replace the 115/13.2 kV transformer, add bus tie CB and add 3 circuit switchers. | 2006-05-31 | Approved | 2005-01-28
NEP-04-T27 | 2004-11-22 | West Kingston and Kenyon | Reconductoring 4.3 miles of the 115 kV 1870N Line portion from the West Kingston No. 62 Substation to the Kenyon No. 68 Substation. | 2007-06-01 | Approved | 2005-01-28
NEP-04-T28 | 2004-11-22 | Kenyon and Wood River | Reconductoring 3.9 miles of the 115 kV 1870 Line portion from the Kenyon No. 68 Substation to the Wood River No. 85 Substation. | 2007-06-01 | Approved | 2005-01-28
NSTAR-04-T05 | 2004-11-22 | Mamonet Substation | The replacement of an existing 12/16/20 MVA, 115/23 kV transformer with a 30/40/50 MVA, 115/23 kV transformer at the Manomet 115 kV Substation. | 2005-06-01 | Approved | 2004-12-17
NSTAR-04-T07 | 2004-11-22 | Roxbury | Construct a new 115/14 kV substation in Roxbury, MA. | 2005-06-01 | Approved | 2004-12-17
NU-04-T37 | 2004-11-18 | Plumtree & Triangle Substations | Bring the Plumtree-Middle River-Triangle area performance in compliance with planning criteria. | 2007-05-31 | Approved | 2004-12-17
NU-04-T38 | 2004-11-04 | Three Rivers 115 kV Substation | Addition of a 115 kV circuit breaker to line N133 for providing fault isolation. | 2004-05-31
BHE-04-T01 | 2004-10-26 | Graham and Rebel Hill Substations | Reconductoring of 13 miles of BHE 115 kV transmission, utilizing size 795 kcm conductor and the replacement of 71 structures. | 2005-07-01 | Approved | 2004-12-17
BHE-04-T02 | 2004-10-26 | Boggy Brook and Rebel Hill Substations | Reconductoring of 13.7 miles of BHE 115 kV transmission, utilizing size 795 kcm conductor and the replacement of 63 structures. | 2005-07-01 | Approved | 2004-12-17
NU-04-T17 | 2004-10-20 | Farmington 1C | Installation of 115/23 kV transformer and two 115 kV breakers at Farmington substation. | 2004-12-30 | Approved | 2004-11-18
NU-04-T36 | 2004-10-20 | Todd 30L | Installation of 115-13.8 kV transformer and 115 kV circuit reaker at Todd substation. | 2004-10-31 | Approved | 2004-11-10
NEP-04-T24 | 2004-10-18 | L190 line | Extend 115 kV line L190 from Davisville/Old Baptist Road tap to West Kingston substation. | 2007-05-31 | Approved | 2004-11-10
NEP-04-T25 | 2004-10-18 | West Kingston | Rebuild West Kingston Substation; install two 115 kV breakers, four disconnect switches. | 2007-05-31 | Approved | 2004-11-10
NEP-04-T26 | 2004-10-18 | L190 line | Reconductor the 115 kV line L190 from Kent County substation to Davisville/Old Baptist Road Tap. | 2007-05-31 | Approved | 2004-11-10
NU-04-G02 | 2004-10-17 | Uncasville 1Q | New 14.5 MW duel-fuel gas turbine will operate to reduce load at the cogeneration facility. | 2004-11-14 | Approved | 2004-11-08
BEMI-04-G03 | 2004-10-14 | Powersville Road | Temporarily interconnect two units of the Weldon Power Station to the Bangor Hydro line 84 during the generation frequency conversion. | 2004-03-22 | Approved with conditions | 2004-11-10
BEMI-04-G04 | 2004-10-14 | Powersville Road | Permanently reconnecting the four converted units (19.2 MW converted from 40 Hz to 60 Hz). | 2005-08-14 | Approved with conditions | 2004-11-10
UI-04-T03 | 2004-10-13 | 1710/1730 Pequonnock - Seaview 115 kV cables | Maintain the ratings of the 1710/1730 cable circuits. The measures being undertaken will not result in changes in transmission line ratings or capacity. | 2004-09-30 | Approved | 2004-11-08
CMP-04-T02 | 2004-10-11 | Fore River Substation | Construct the new Fore River 115 kV to 12.47 kV distribution substation. The new substation will tap the 275 115 cable between Sewall St. and Cape substations. | 2005-06-30 | Approved | 2004-11-08
NU-04-T20 Rev.1 | 2004-10-07 | Tracy 14M | Construct new 345/115 kV Killingly 2G substation for installation of the new autotransformer. | 2006-11-30
NEP-04-T22 Rev.1 | 2004-09-23 | Whitins Pond Substation | Install a new tap at the existing Whitins Pond substation to the 115 kV R-144 line, a 55 MVA 115/13.8 kV transformer, and a 115 kV circuit switcher; replace a 20 MVA 115/13.8 kV transformer with a 55 MVA unit and 115 kV air break w/ circuit switcher. | 2006-06-30 | Approved | 2004-11-10
NEP-04-T23 Rev.1 | 2004-09-23 | Rocky Hill Substation | Install a new tap at the existing Rocky Hill substation to the 115 kV D-130 line, a 55 MVA 115/13.8 kV transformer, a 115 kV circuit switcher, and two in-line load breaks. | 2006-06-30 | Approved | 2004-11-10
LOWELL-04-DR01 | 2004-09-22 20:00 | Lowell Power, LLC | Place Lowell Power LLC generating unit into deactivated reserve.
LOWELL-04-DR01 | 2004-09-22 20:00 | Lowell Power, LLC | WITHDRAWN: Place Lowell Power LLC generating unit into deactivated reserve.
CMEEC-04-G02 | 2004-09-20 | SNEW Power Station | Install three 16.3 MW (net) generators interconnected to the Norwalk 9S substation through distribution lines. | 2006-05-31 | Approved with conditions Withdrawn | 10/7/2004 8/23/2011
UI-04-T02 | 2004-09-19 | East Shore - Grand Avenue - Totoket Junction | Relocation of structures, overhead and underground lines for the I-95 New Haven Harbor Crossing Corridor Improvement Program. (387, 1460, 8100, 8200, 88003A&B, 8500 lines with no changes to configuration and length.) | 2005-01-31 | Approved | 2004-10-08
HGE-04-T01 | 2004-09-13 | Ingleside 52W Substation | Addition of third 115/13.8 kV transformer and second 115 kV circuit breaker. | 2005-10-14 | Approved | 2004-10-07
NU-04-T35 | 2004-08-29 | Ashfield substation | Replace the single set of 115 kV fuses with two circuit switchers to allow for automatic transfer of Ashfield substation load. | 2004-11-29 | Approved | 2004-10-07
NEP-04-T22 | 2004-08-26 | Whitins Pond Substation | Install a new tap at the existing Whitins Pond substation to the 115 kV R-144 line, a 55 MVA 115/13.8 kV transformer, and a 115 kV circuit switcher; replace a 20 MVA 115/13.8 kV transformer with a 55 MVA unit and 115 kV air break w/ circuit switcher. | 2006-06-30
NEP-04-T23 | 2004-08-26 | Rocky Hill Substation | Install a new tap at the existing Rocky Hill substation to the 115 kV D-130 line, a 55 MVA 115/13.8 kV transformer, a 115 kV circuit switcher, and two in-line load breaks. | 2006-06-30
NU-04-T34 | 2004-08-26 | Rochester Substation | Addition of a second 115 kV line and 115 kV circuit breaker to the Rochester substation. | 2004-09-30 | Approved | 2004-09-02
NEP-04-T19 | 2004-08-23 | X-176 115 kV line | Upgrade the X-176 115 kV circuit (Palmer substation - NEP/NU border). This involves reconductoring of the overhead line as well as terminal equipment upgrades at Palmer substation. | 2005-04-01 | Approved | 2004-10-07
FPLE-04-G02 | 2004-08-19 | Seabrook Station | The Seabrook Power Uprate will increase the output of the Seabrook Station to a maximum gross output of 1,318 MW. Phase II will occur after approval by the NRC of a license amendment to reduce the measurement uncertainty of the secondary coolant flow. | 2006-09-30 | Approved with conditions | 2004-09-02
FPLE-04-G02 Rev.1 | 2004-08-19 | Seabrook Station | Removal of conditions 5 and 6 in ISO Approval Letter. The Seabrook Power Uprate will increase the output of the Seabrook Station to a maximum gross output of 1,318 MW. Phase II will occur after approval by the NRC of a license amendment to reduce the measurement uncertainty of the secondary coolant flow. | 2006-09-30 | Approved with conditions | 2006-10-24
NU-04-G01 | 2004-08-19 | Berkshire WindPower | Connect 10, 1.5 MW wind turbine generators. These generators will connect at distribution voltage at the Partridge 115 kV substation. | 2004-12-31 | Approved with conditions | 2004-09-02
NU-04-T33 | 2004-08-17 | Shaws Hill Substation | Install a second 115/13.8 kV transformer and a 115 kV tie breaker. | 2005-06-29 | Approved | 2004-09-02
CMEEC-04-G01 | 2004-08-03 | Norwalk 9S | Installation of three Catapillar diesel generators. | 2004-07-31 | Approved with conditions | 2004-08-12
NU-04-T25 | 2004-08-02 | Berlin Substation | Upgrade the Berlin substation to bulk power system standards. | 2007-12-30 | Approved | 2004-09-02
NU-04-T26 | 2004-08-02 | South Meadow Substation | Upgrade the South Meadow substation to bulk power system standards. | 2005-12-30 | Approved | 2004-09-02
NU-04-T27 | 2004-08-02 | Southwest Hartford substation | Upgrade the Southwest Hartford substation to bulk power system standards. | 2008-12-30 | Approved | 2004-09-02
NU-04-T28 | 2004-08-02 | East Hartford substation | Upgrade the East Hartford substation to bulk power system standards. | 2006-12-30 | Approved | 2004-09-02
NU-04-T29 | 2004-08-02 | Northwest Hartford Substation | Upgrade the Northwest Hartford substation to bulk power system standards. | 2006-12-30 | Approved | 2004-09-02
NU-04-T30 | 2004-08-02 | East Springfield substation | Upgrade the East Springfield substation to bulk power system standards. | 2005-12-30 | Approved | 2004-09-02
NU-04-T31 | 2004-08-02 | South Agawam substation | Upgrade the South Agawam substation to bulk power system standards. | 2007-12-30 | Approved | 2004-09-02
NU-04-T32 | 2004-08-02 | Garvins Substation | Upgrade the Garvins substation to bulk power system standards. | 2008-12-30 | Approved | 2004-09-02
NU-04-T15 | 2004-07-12 | Hanover 12F Substation | Installation of 115-23 kV transformer and circuit switchers with removal of 115 kV breaker at Hanover substation. | 2004-04-30 | Approved | 2004-08-03
NSTAR-04-T04 | 2004-07-08 | Stoughton 345 kV Switching Station | Phase I: New 345 kV Stoughton open air switching station with numerous associated upgrades. Phase II: Additional parallel cables to those installed in Phase I, numerous associated upgrades. | 2006-06-01 | Approved with conditions | 2004-08-03
NU-04-T24 | 2004-07-07 | Canton 5R | Install of a 47 MVA 115/ 23 kV distribution transformer at the Canton 5R Substation to be used as emergency backup in the event of a failure of 1X or 2X. | 2004-12-30 | Approved | 2004-07-26
NEP-01-G01 Rev.1 | 2004-07-06 20:00 | UAE Lowell Power | WITHDRAW: Construct new simple cycle generating plant consisting of 2 CT's with a combined net capacity of 95.2 MW at 20 degrees F to be built adjacent to existing UAE Lowell Facility | 2001-05-31 20:00 | Approved | 2004-08-03 20:00
NEP-02-G01 Rev.1 | 2004-07-06 | Tewksbury Substation | WITHDRAW: Construct a new gas-fired, simple cycle generation plant consisting of 3-CTs designated the UAE Tewksbury Station with a combined net capability of 548.6 MW at 20 F, 554.6 MW at 50 F and 540.0 MW at 90 F. | 2002-12-31 | Approved | 2004-08-03
NEP-02-T02 Rev.1 | 2004-07-06 | Tewksbury Substation | WITHDRAW: Installation of two (2) new 345 kV two-breaker GIS bays along with associated buswork switches and terminal equipment. | 2002-12-31 | Approved | 2004-08-03
NU-04-T23 | 2004-06-22 | Falls Village (9A) | Replace two Generator Step-Up Transformers with a single Generator Step-Up Transformer at Falls Village (9A) Substation. | 2004-09-30 | Approved | 2004-07-26
NU-04-T10 | 2004-06-17 | South End Substation | Upgrade line 1977 terminal equipment at South End Substation. | 2005-05-31 | Approved | 2004-07-26
NU-04-X01 | 2004-06-16 | Lake Road Generation Plant | Modify the existing Lake Road Type III Special Protection System (SPS). | 2006-11-30 | Approved with conditions | 2004-08-03
NSTAR-04-T03 | 2004-06-15 | East Cambridge Substation | Addition of the new 115kV/13.8 kV East Cambridge substation. | 2005-08-31 | Approved with conditions | 2004-09-02
NEP-04-T20 | 2004-06-10 | Reconductor B-154N & C-155N lines | Reconductor 115 kV lines B-154N & C-155N. | 2005-11-30 | Approved | 2004-07-26
NEP-04-T21 | 2004-06-10 | Reconductor line G-133E. | Reconductor 115 kV line G-133E. | 2005-11-30 | Approved | 2004-07-26
NU-04-T22 | 2004-05-27 | Fort Hill Farms | Add a second 115/34.5 kV autotransformer at the Fort Hill Farms substation. | 2004-06-29 | Approved | 2004-06-24
NSTAR-04-T02 | 2004-05-24 | Chelsea Station #488 | Replace the 115/13.8 kV Chelsea Station 110A and 110B transformers. Add 115 kV circuit breaker and 115/13.8 kV Chelsea transformer 110C. | 2004-05-31 | Approved | 2004-06-04
NU-04-T19 | 2004-05-18 | Chester Substation | Addition of a second transformer and 115 kV circuit breaker to the Chester Substation. | 2004-05-31 | Approved with conditions | 2004-06-04
NU-04-T20 | 2004-05-18 | Tracy 14M | Reconfigure the Tracy Substation and add three 115 kV circuit breakers. Sectionalize the 345 kV 347 line. Addition of a new 345/115 kV auto-transformer at the Tracy Substation. | 2006-11-30 | Approved | 2004-08-03
NU-04-T21 | 2004-05-18 | Card 11F | Addition of a new 345 kV circuit breaker in series with the Card Substation 11F-2T-2 circuit breaker. This upgrade is associated with the Tracy Autotransformer Project. | 2006-11-30 | Approved | 2004-08-03
PP-04-G01 | 2004-05-12 | Waterside 22M | Temporary installation of three TM2500 gas turbine generators at the Waterside Substation. This installation will interconnect the machines through a single GSU to the existing mobile transformer position on the 1440 line side of the Waterside bus. | 2004-05-31 | Approved with conditions | 2004-05-23
NU-04-T18 | 2004-05-10 | Waterside 22M | Temporary installation of three TM2500 gas turbine generators at the Waterside Substation. This installation is temporary and shall expire on December 31, 2004. | 2004-05-31 | Approved | 2004-05-23
NU-04-T16 | 2004-05-09 | Torrington Terminal 8A Substation | 1788 and 1900 line terminal equipment at Torrington Terminal substation will be upgraded. Following these upgrades, the lines will be conductor limited. | 2004-06-03 | Approved | 2004-06-04
BEMI-04-G02 | 2004-04-25 | Berlin, NH | A new cogeneration unit is added to the existing load and generation at Fraser Paper Berlin/Gorham system, which includes the existing James River hydro aggregate. This represents a capacity increase from 13 MW to 25 MW. | 2004-04-30 | Approved with conditions | 2004-05-06
NEP-04-T16 | 2004-04-25 | Point Street | Add second 13/115 kV transformer at Point Street S/S and connect it through a new tap with T3 line between Franklin Square and Point St. Install a circuit switcher in line T3 toward South St. | 2004-05-31 | Approved | 2004-06-04
NEP-04-T17 | 2004-04-25 | Johnston Substation | Add second 13/115 kV transformer at Johnston S/S and connect it to the existing tap off the T-172 line. | 2004-05-31 | Approved | 2004-06-04
NEP-04-T18 | 2004-04-25 | Kilvert Street | Install a tap off the I-187 line in Warwick, RI and connect the proposed Kilvert St. distribution S/S with the tap through. | 2004-05-31 | Approved | 2004-06-04
NU-04-T13 | 2004-04-18 | Cos Cob Railrod 11R Substation | Add a circuit breaker at the Cos Cob Railroad substation on the 1750 line. | 2004-12-30 | Approved | 2004-05-06
NSTAR-04-T01 | 2004-04-15 | Framingham Station #240 | Replace the 115/13.8 kV Framingham Transformers 110B and 110C. | 2004-05-31 | Approved | 2004-05-07
NU-04-T11 | 2004-04-15 | 115 kV line Z156 | Addition of a 115 kV radial line connecting the Schiller Substation to the existing Portsmouth Substation. The new line will supply the Portsmouth substation. | 2004-05-31 | Approved | 2004-05-06
NU-04-T12 | 2004-04-15 | Pleasant 16B | Addition of a 3rd 30 MVA 115/23 kV transformer and 2-115 kV circuit breakers. The need for this additional transformer is load growth, no additional load at Pleasant. No load being swapped to Pleasant. | 2004-05-31 | Approved | 2004-05-06
NU-04-T14 | 2004-04-15 | Blandford 19J Substation | Replace the existing 12/16 MVA transformer with a new 18/24/30 MVA transformer at Blandford substation. | 2004-06-30 | Approved | 2004-05-06
NU-02-T04 Rev.A | 2004-04-14 20:00 | Shunock 32P - N. Stonington | Addition of a new 115 kV substation: Shunock 32P - North Stonington, CT (proposed) - this revision represents the change from one three winding transformer to two two winding transformers at Shunock for increased reliability. | 2005-04-30 20:00 | Approved | 2004-05-06 20:00
DNC-04-G01 | 2004-03-31 | Millstone Power Station | Millstone Unit No. 3 power uprate consists of replacing all three LP steam turbine rotors. | 2004-04-30 | Approved with conditions | 2004-04-07
MIR-04-DR04 Rev.1 | 2004-03-31 | Kendall Steam 3 | Place the Kendall Steam 3 generating unit into deactivated reserve. | 2004-09-30 | Approved with conditions | 2004-09-22
NEP-04-G01 | 2004-03-21 | Johnston Substation | Add six new units rated at 12 MVA total to the landfill gas burning facility connected to the 23 kV distribution line at terminating at Johnston 23/115 kV substation. | 2004-05-31 | Approved | 2004-04-07
NEP-04-T14 | 2004-03-21 | Lynn # 21 | Install two 3-phase 115/13.8 kV transformers, two 115 kV circuit switchers, and replace two sacrificial airbreaks with circuit switchers. | 2006-11-30 | Approved | 2004-04-07
NEP-04-T15 | 2004-03-21 | Railyard # 49 | Install one 3-phase 115/13.8 kV transformer and a 115 kV circuit switcher. | 2005-06-30 | Approved | 2004-04-07
NEP-04-T01 | 2004-03-08 | Woodside | Install 69 kV breaker at Woodside. Operate W-23 line normally closed at Woodside. | 2003-12-31 | Approved with conditions | 2004-04-08
NEP-04-T02 | 2004-03-08 | Wachusett | Install second 115 - 69 kV transformer at Wachusett substation. | 2003-12-31 | Approved with conditions | 2004-04-08
NEP-04-T03 | 2004-03-08 | Millbury | Replace two 115 - 60 kV autotransformers at Millbury substaion. | 2003-12-31 | Approved with conditions | 2004-04-08
NEP-04-T04 | 2004-03-08 | Pratts Junction | Transfer half of Prospect St. load to Pratts Jct. Install two additional 115 - 69 kV autotransformers and replace all 8 69 kV circuit breakers at Pratts Jct. Substation. | 2003-12-31 | Approved with conditions | 2004-04-08
NEP-04-T05 | 2004-03-08 | Wachusett | Install two 345 - 115 kV autotransformers (448 MVA) and two additional 115 - 69 kV autotransformers at Wachusett Station. | 2004-12-31 | Approved with conditions | 2004-04-08
NEP-04-T06 | 2004-03-08 | Quinsigamond Jct - Greendale - Nashua St. | Reconductor O-141N 115 kV line (Quinsigamond Jct - Greendale - Nashua St.) | 2004-12-31 | Approved with conditions | 2004-04-08
NEP-04-T07 | 2004-03-08 | Wachusett - W. Boylston | Reconductor P-142 115 kV line (Wachusett - W. Boylston) | 2007-12-31 | Approved with conditions | 2004-04-08
NEP-04-T08 | 2004-03-08 | Wachusett - Fitch Road | Reconductor M-39 69 kV line (Wachusett - Fitch Rd.) | 2004-12-31 | Approved with conditions | 2004-04-08
NEP-04-T09 | 2004-03-08 | Pratts Jct. - Fitch Road | Reconductor N-40 69 kV line (Pratts Jct. - Fitch Rd.) and upgrade 69 kV terminal equipment at Pratts Jct. | 2004-12-31 | Approved with conditions | 2004-04-08
NEP-04-T10 | 2004-03-08 | Rolf Ave. | Upgrade 115 kV breaker at Rolfe Avenue substation. | 2004-12-31 | Approved with conditions | 2004-04-08
NEP-04-T11 | 2004-03-08 | Carpenter Hill - W. Charlton | Reconductor W-175 115 kV line (Carpenter Hill - W. Charlton). | 2004-12-31 | Approved with conditions | 2004-04-08
NEP-04-T12 | 2004-03-08 | West Boylston | Upgrade West Boylston 115 kV substation to meet NPCC bulk power system requirements. | 2004-12-31 | Approved with conditions | 2004-04-08
NEP-04-T13 | 2004-03-08 | Marlboro Tap | Upgrade W-23 69 kV disconnect device at the Marlboro Tap. | 2004-12-31 | Approved with conditions | 2004-04-08
CMP-04-T01 | 2004-02-12 | Bolt Hill Substation | Add a 115/34/5 kV transformer at Bolt Hill substation as part of the Southern York County System Reinforcement Project | 2004-05-31 | Approved | 2004-03-12
NU-02-T09 Rev.1 | 2004-02-11 | Glenbrook Substation | Install a new 115 kV 1977-line position at the Glenbrook substation, tap existing Darien to South End 1977-line forming a new three terminal transmission line. Install new primary and backup 1977 line protection at Glenbrook, Darien, and South End. | 2004-05-31 | Approved | 2004-04-08
BEMI-04-G01 | 2004-01-26 | Berlin Substation | A new COGEN unit is being installed at the Fraser Paper Berlin/Gorham load and generation complex. The 13 MW capability of the aggregate will remain the same. | 2004-02-29 | Approved with conditions | 2004-02-10
FPLE-04-G01 | 2004-01-22 | Seabrook Nuclear Station | Phase I of the Seabrook Power Uprate will increase the maximum gross output by 86 MW (1209 MW to 1295 MW). | 2004-04-01 | Approved with conditions | 2004-02-10
FPLE-04-G01 Condition 3 | 2004-01-22 | Seabrook Nuclear Station | Phase I of the Seabrook Power Uprate will increase the maximum gross output by 86 MW (1209 MW to 1295 MW). REMOVAL OF CONDITION 3. | 2004-04-01 | Approved with conditions | 2004-05-09
UI-04-T01 | 2004-01-22 | Pequonnock | Install a 3% series reactor (100 MVA base), with bypass switch, in the Bridgeport Harbor 2 generator leads. | 2005-05-31 | Approved | 2004-04-07
NU-04-T01 | 2004-01-19 | Norwalk-Plumtree Substations | New 345 kV circuit between Norwalk and Plumtree substations. | 2005-10-31 | Approved with conditions | 2004-02-10
NU-04-T02 | 2004-01-19 | Plumtree to Peaceable Substations | Reconfiguration of the existing 115 kV 1565 line between Plumtree and Peaceable. | 2005-10-31 | Approved with conditions | 2004-02-10
NU-04-T03 | 2004-01-19 | Norwalk to Peacable Substations | Reconfiguration of the existing 115 kV 1470 line between Norwalk and Peaceable. | 2005-10-31 | Approved with conditions | 2004-02-10
NU-04-T04 | 2004-01-19 | 1910 line at Southington | Install 3% series reactor (100 MVA base) with bypass switch on the 1910 line at Southington. | 2005-10-31 | Approved with conditions | 2004-02-10
NU-04-T05 | 2004-01-19 | 1950 line at Southington | Install 3% series reactor (100 MVA base) with bypass switch on the 1950 line at Southington. | 2005-10-31 | Approved with conditions | 2004-02-10
NU-04-T06 | 2004-01-19 | Long Mountain | Install the 7T breaker at Long Mountain 345 kV and reterminate the 398 line (Long Mtn. - Pleasant Valley). | 2005-10-31 | Approved with conditions | 2004-02-10
NU-04-T07 | 2004-01-19 | 348 Line | Replace limiting terminal equipment on the 345 kV 348 line (Millstone to Southington). | 2005-10-31 | Approved with conditions | 2004-02-10
NU-04-T08 | 2004-01-19 | Norwalk Harbor | Replace 3T, 5T, and 6T circuit breakers at Norwalk Harbor substation. | 2005-10-31 | Approved with conditions | 2004-02-10
NU-04-T09 | 2004-01-19 | Glenbrook | Install Type III SPS at Glenbrook Substation. | 2005-10-31 | Approved with conditions | 2004-02-10
SNE-01-G01 Rev.1 | 2003-12-08 | West Medway Station | WITHDRAW: New Gas Trubine Generating plant consisting of three single-cycle natural gas fired generators (Units 4, 5 & 6). | 2002-05-31
CMP-03-G01 Rev.3 | 2003-12-04 | Redington Mountain Windpower | Add a 30 MW generation plant; consisting of 15, 1.8 MW wind turbines, connecting to the new 115 kV Electric Harvest substation. | 2004-11-30 | Approved with conditions | 2003-12-11
ENTERGY-03-G02 Rev.1 | 2003-12-01 | Vermont Yankee | The project will uprate the output of the Vermont Yankee Nuclear Power Station to a maximum gross output of 667 MW to be implemented in two phases. Modified Conditions. | 2004-06-01 | Approved | 2004-03-12
NEP-03-T03 Rev.1 | 2003-11-17 | Woodside | WITHDRAW: Install 69 kV breaker at Woodside. Operate W-23 line normally closed at Woodside. | 2003-11-17
NEP-03-T04 Rev.1 | 2003-11-17 | Wachusett | WITHDRAW: Install second 115 - 69 kV transformer at Wachusett substation. | 2003-11-17
NEP-03-T05 Rev.1 | 2003-11-17 | Millbury | WITHDRAW: Replace two 115 - 60 kV autotransformers at Millbury substaion. | 2003-11-17
NEP-03-T06 Rev.1 | 2003-11-17 | Pratts Junction | WITHDRAW: Transfer half of Prospect St. load to Pratts Jct. Install two additional 115 - 69 kV autotransformers and replace all 8 69 kV circuit breakers at Pratts Jct. Substation. | 2001-01-01
NEP-03-T07 Rev.1 | 2003-11-17 | Wachusett | WITHDRAW: Install two 345 - 115 kV autotransformers (448 MVA) and two additional 115 - 69 kV autotransformers at Wachusett Station. | 2003-11-17
NEP-03-T08 Rev.1 | 2003-11-17 | Quinsigamond Jct - Greendale - Nashua St. | WITHDRAW: Reconductor O-141N 115 kV line (Quinsigamond Jct - Greendale - Nashua St.) | 2003-11-17
NEP-03-T09 Rev.1 | 2003-11-17 | Wachusett - W. Boylston | WITHDRAW: Reconductor P-142 115 kV line (Wachusett - W. Boylston) | 2003-11-17
NEP-03-T10 Rev.1 | 2003-11-17 | Wachusett - Fitch Road | WITHDRAW: Reconductor M-39 69 kV line (Wachusett - Fitch Rd.) | 2003-11-17
NEP-03-T11 Rev.1 | 2003-11-17 | Pratts Jct. - Fitch Road | WITHDRAW: Reconductor N-40 69 kV line (Pratts Jct. - Fitch Rd.) and upgrade 69 kV terminal equipment at Pratts Jct. | 2003-11-17
NEP-03-T12 Rev.1 | 2003-11-17 | Rolf Ave. | WITHDRAW: Upgrade 115 kV breaker at Rolfe Avenue substation. | 2003-11-17
NEP-03-T13 Rev.1 | 2003-11-17 | Carpenter Hill - W. Charlton | WITHDRAW: Reconductor W-175 115 kV line (Carpenter Hill - W. Charlton) | 2003-11-17
NEP-03-T14 Rev.1 | 2003-11-17 | West Boylston | WITHDRAW: Upgrade West Boylston 115 kV substation to meet NPCC bulk power system requirements. | 2003-11-17
NEP-03-T15 Rev.1 | 2003-11-17 | Marlboro Tap | WITHDRAW: Upgrade W-23 69 kV disconnect device at the Marlboro Tap. | 2003-11-17
INDECK-00-G01 Rev.1 | 2003-11-09 | Indeck - North Smithfield Energy Center | WITHDRAW: Construction of a new 350 MW gas turbine combined cycle facility. | 2003-06-30 | Approved | 2003-12-10
CMP-03-G01 Rev.2 | 2003-11-06 | Redington Mountain Windpower | Add a 30 MW generation plant; consisting of 15, 1.8 MW wind turbines, connecting to the new 115 kV Electric Harvest substation. | 2004-11-30
CMP-03-G01 Rev.1 | 2003-11-05 19:00 | Redington Mountain Windpower | Add a 30 MW generation plant; consisting of 15, 1.8 MW wind turbines, connecting to the new 115 kV Electric Harvest substation. | 2004-11-30 19:00
CMP-03-T05 Rev.1 | 2003-11-05 | Electric Harvest 115 kV Substation | A new Endless Energy substation will be constructed and connected to CMP's Bigelow substation. | 2004-11-30 | Approved with conditions | 2003-12-10
CMP-03-T05 | 2003-11-04 19:00 | Electric Harvest 115 kV Substation | A new Endless Energy substation will be constructed and connected to CMP's Bigelow substation. | 2004-11-30 19:00
CMP-03-G01 | 2003-11-04 | Redington Mountain Windpower | Add a 30 MW generation plant; consisting of 15, 1.8 MW wind turbines, connecting to the new 115 kV Electric Harvest substation. | 2004-11-30 | Approved
CMP-03-T04 | 2003-11-02 | Challenger Drive | Tap the 115 kV section 75 (Hotel Road - Lewiston Lower) and add the Challenger Drive distribution substation. | 2004-06-30 | Approved | 2003-11-18
NSTAR-01-T01 Rev.1 | 2003-10-30 | West Medway Station | WITHDRAW: Modify the West Medway 345 kV station to install breaker 113 and connect the Sithe 345 kV generator lead. Upgrade breakers 101, 103, 104, 106, 107 and 109. | 2003-12-11 | Approved | 2003-12-11
MMED-03-T01 | 2003-10-29 | New substation Bird Road | Construct a new 115 - 13.8 kV substation in Mansfield, MA. The station will consist of a single 115 - 13.8 kV transformer and will connect on the E1 line. | 2006-05-31 | Approved | 2003-11-19
NEP-00-G05 Rev.1 | 2003-10-26 | Brockton Power Generating Plant | WITHDRAW: Construction of a 288 MW Winter/267 Summer Combined Cycle Plant | 2002-12-31 | Approved | 2003-11-18
NEP-00-T16 Rev.1 | 2003-10-26 | 328 line | WITHDRAW: Construct a three breaker ring bus substation on the 328 line for the interconnection of the North Smithfield power plant. | 2002-02-28 | Approved | 2003-12-10
NEP-00-T22 Rev.1 | 2003-10-26 | Brockton Power | WITHDRAW: Construct three bkr ring bus. | 2002-04-30 | Approved | 2003-11-18
NEP-00-T23 Rev.1 | 2003-10-26 | Brockton Power | WITHDRAW: Reconductor F19 Line. | 2002-04-30 | Approved | 2003-11-18
NEP-00-T24 Rev.1 | 2003-10-26 | Brockton Power | WITHDRAW: Replace the 1601 Bkr. | 2002-04-30 | Approved | 2003-11-18
NEP-00-T25 Rev.1 | 2003-10-26 | Brockton Power | WITHDRAW: Rebuild the S8 line. | 2002-04-30 | Approved | 2003-11-18
NEP-00-T26 Rev.1 | 2003-10-26 | Brockton Power | WITHDRAW: Upgrade thermal capacity of the northern Auburn Street 115 kV ring bus. | 2002-04-30 | Approved | 2003-11-18
NEP-00-X05 Rev.1 | 2003-10-26 | Brockton Power | WITHDRAW: Install Type III SPS at Auburn Street station. | 2002-04-30 | Approved | 2003-11-18
NEP-01-T12 Rev.1 | 2003-10-26 | Millbury Station Bkr #314 | WITHDRAW: Upgrade breaker 314 at the Millbury station to achieve Independent Pole tripping capability. | 2002-05-31 | Approved | 2003-12-11
NEP-03-T16 | 2003-10-26 | E1 115 kV line | Split the existing E1 line into two independent line sections by adding two circuit breakers. | 2006-05-31 | Approved | 2003-11-18
NEP-03-T17 | 2003-10-26 | E1 115 kV line | Extend 115 kV line E1 from Easton and terminate at the new Bird Road substation at Mansfield. | 2006-05-31 | Approved | 2003-11-18
NU-03-T13 Rev.1a | 2003-10-26 | Haddam | Reconfigure Haddam Substation 11C to a breaker and a half scheme, install 345/115 kV auto-transformer, install shunt capacitor, tap the 345 kV 348 line & the 115 kV 1620 line terminating at Haddam. Rev. 1: change in rating & impedance of autotransformer. | 2005-04-30 | Approved | 2003-11-18
NU-03-T24 Rev.1 | 2003-10-18 | Webster | WITHDRAW: Replacement of an air break switch (J40) with a 2000 amp circuit breaker at the PSNH Webster 115 kV substation. | 2003-10-23
NU-03-T25 | 2003-10-15 | Pine Hill | Addition of a second transformer and 115 kV circuit breaker to the PSNH Pine Hill substation. | 2002-12-31 | Approved | 2003-11-18
NU-03-T13 Rev.1 | 2003-10-09 20:00 | Haddam | Reconfigure Haddam Substation 11C to a breaker and a half scheme, install 345/115 kV auto-transformer, install shunt capacitor, tap the 345 kV 348 line & the 115 kV 1620 line terminating at Haddam. Rev. 1: change in rating & impedance of autotransformer. | 2005-04-30 20:00
NU-03-T24 | 2003-10-09 | Webster | Replacement of an air break switch (J40) with a 2000 amp circuit breaker at the PSNH Webster 115 kV substation. | 2003-10-23 | Approved | 2004-06-25
NU-03-T23 | 2003-10-08 | Amherst | Addition of a second transformer and 345 kV ring bus to the Amherst 345 kV substation. | 2003-11-14 | Approved | 2003-11-18
NU-03-T17 Rev.1 | 2003-10-06 | Southington 4C | Add 115/13.8 kV transformer and 115 kV breaker at Southington 4C substation. | 2003-12-30 | Approved | 2003-09-08
CMP-03-T03 | 2003-10-01 | Crowley's 115 kV substation | Install a 50 MVAR capacitor bank at the Crowley's 115 kV substation to provide reactive supply for power factor correction per OP-17 Power Factor Survey. | 2003-10-31 | Approved | 2003-11-18
DNC-03-G01 | 2003-09-29 | Millstone | Replace the two LP rotors on Millstone Unit No. 2 steam turbine. This will increase the real power output to 905.7 MW net winter, 897.5 MW net summer. | 2003-10-31 | Approved with conditions | 2003-10-07
FPLE-03-RR01 | 2003-09-28 | Mason | Retire Mason Unit # 3. | 2003-11-01 | Approved | 2003-10-08
FPLE-03-RR02 | 2003-09-28 | Mason | Retire Mason Unit # 4. | 2003-11-01 | Approved | 2003-10-08
FPLE-03-RR03 | 2003-09-28 | Mason | Retire Mason Unit # 5. | 2003-11-01 | Approved | 2003-10-08
ENTERGY-03-T01 | 2003-09-25 | Vermont Yankee | Install two 115 kV 15 MVAR switched shunt capacitor banks and one 115 kV 30 MVAR switched shunt capacitor bank at the Vermont Yankee 115 kV substation. | 2003-04-01 | Approved with conditions | 2003-10-08
NU-03-G01 | 2003-09-24 | Kleen Energy | Construct an 634.2 MW gross winter/634.0 MW gross summer combined cycle gas/oil plant. | 2006-05-31 | Approved with conditions | 2003-10-08
NU-03-T22 | 2003-09-24 | Kleen Energy | Addition of new Kleen Energy 345 kV switchyard. | 2006-05-31 | Approved | 2003-10-08
NEP-03-T05 | 2003-09-23 20:00 | Millbury | Replace two 115 - 60 kV autotransformers at Millbury substaion.
NEP-03-T06 | 2003-09-23 20:00 | Pratts Junction | Transfer half of Prospect St. load to Pratts Jct. Install two additional 115 - 69 kV autotransformers and replace all 8 69 kV circuit breakers at Pratts Jct. Substation.
NEP-03-T07 | 2003-09-23 20:00 | Wachusett | Install two 345 - 115 kV autotransformers (448 MVA) and two additional 115 - 69 kV autotransformers at Wachusett Station.
NEP-03-T08 | 2003-09-23 20:00 | Quinsigamond Jct - Greendale - Nashua St. | Reconductor O-141N 115 kV line (Quinsigamond Jct - Greendale - Nashua St.)
NEP-03-T09 | 2003-09-23 20:00 | Wachusett - W. Boylston | Reconductor P-142 115 kV line (Wachusett - W. Boylston)
NEP-03-T10 | 2003-09-23 20:00 | Wachusett - Fitch Road | Reconductor M-39 69 kV line (Wachusett - Fitch Rd.)
NEP-03-T11 | 2003-09-23 20:00 | Pratts Jct. - Fitch Road | Reconductor N-40 69 kV line (Pratts Jct. - Fitch Rd.) and upgrade 69 kV terminal equipment at Pratts Jct.
NEP-03-T12 | 2003-09-23 20:00 | Rolf Ave. | Upgrade 115 kV breaker at Rolfe Avenue substation.
NEP-03-T13 | 2003-09-23 20:00 | Carpenter Hill - W. Charlton | Reconductor W-175 115 kV line (Carpenter Hill - W. Charlton)
NEP-03-T14 | 2003-09-23 20:00 | West Boylston | Upgrade West Boylston 115 kV substation to meet NPCC bulk power system requirements.
NEP-03-T15 | 2003-09-23 20:00 | Marlboro Tap | Upgrade W-23 69 kV disconnect device at the Marlboro Tap.
NEP-03-T03 | 2003-09-23 | Woodside | Install 69 kV breaker at Woodside. Operate W-23 line normally closed at Woodside. | 2003-10-01
NEP-03-T04 | 2003-09-23 | Wachusett | Install second 115 - 69 kV transformer at Wachusett substation. | 2004-10-01
NU-03-T21 | 2003-08-27 | East Springfield 5J | Add third 115/13.8 kV transformer at East Springfield. | 2003-12-29 | Approved | 2003-10-08
NU-03-T19 | 2003-08-24 | Franconia 22H | Replace the 3X 115 kV 13.8 kV transformer at Franconia. | 2003-06-29 | Approved | 2003-10-08
NU-03-T17 | 2003-08-17 | Southington 4C | Add 115/13.8 kV transformer and 115 kV breaker at Southington 4C substation. | 2003-12-31 | Approved | 2003-09-08
NU-03-T18 | 2003-08-17 | Torrington Terminal 8A | Add 115 kV/13.2 kV transformer at Torrington Terminal 8A substation. | 2003-11-30 | Approved | 2003-09-08
UI-03-T02 | 2003-07-24 | 115 kV lines 8809A and 8909B | Increase the clearance between UI lines 8809A and 8909B and railroad conductors. | 2003-09-30 | Approved | 2003-08-06
NSTAR-02-T03 Rev.1 | 2003-07-22 | Barnstable 115 kV | Install a 15 MVAR 115 kV shunt capacitor bank at the Barnstable 115 kV substation. | 2003-11-30 | Approved | 2003-08-07
NU-03-T16 | 2003-07-20 | Southwick | Add second 115 - 13.8 kV transformer at Southwick to provide additional load serving capacity. | 2002-08-31 | Approved | 2003-09-08
NU-03-T12 | 2003-07-17 | Portsmouth Substation | Addition of the Portsmouth Substation 50 MVA, 115/34.5 kV transformer. | 2003-05-31 | Approved | 2003-08-06
NU-03-T13 | 2003-07-17 | Haddam | Reconfigure Haddam Substation 11C to a breaker and a half scheme, install 345/115 kV auto-transformer, install shunt capacitor, tap the 345 kV 348 line and the 115 kV 1620 line terminating at Haddam. | 2005-04-30 | Approved | 2003-08-07
NU-03-T14 | 2003-07-17 | Branford Substation | Install a 115 kV, 37.8 Mvar (nominal) shunt capacitor bank at the Branford Substation. | 2005-04-30 | Approved | 2003-08-06
NU-03-T15 | 2003-07-17 | 115 kV line Manchester - Hopewell | Reconductor the 115 kV line 1767 from Manchester Substation (Manchester, CT) to Hopewell Substation (Glastonbury, CT). | 2005-04-30 | Approved | 2003-08-07
UI-03-T01 | 2003-07-17 | Devon Tie Switching Station | Replace the four existing 115 kV oil circuit breakers with four new SF6 gas circuit breakers. | 2003-09-30 | Approved | 2003-08-06
NEP-03-T02 | 2003-06-23 | Sherman Road | Install circuit breaker 140A in series with existing circuit breaker 140 at Sherman Road. | 2003-09-30 | Approved | 2003-08-06
NSTAR-03-T06 2 | 2003-06-03 20:00 | Mystic | Replace the 115/13.8 kV Mystic 110A and 110B transformers | 2003-06-30 20:00
NSTAR-03-T05 | 2003-06-03 | Sudbury | Replace the 115/13.8 kV Sudbury 110A and 110B transformers. | 2003-06-30
NSTAR-03-T07 | 2003-06-03 | K Street | New K Street 115/14kV substation. | 2003-06-30 | Approved | 2003-06-16
NSTAR-03-T08 | 2003-06-03 | Sudbury Station | Two new 115/13.8 kV LTC transformers will be installed at Sudbury Station #342 to replace the existing transformers 110A and 110B. | 2003-06-30 | Approved | 2003-06-15
NSTAR-03-T09 | 2003-06-03 | Mystic Station | Two new 115/13.8 kV LTC transformers will be installed at Mystic Station #250 to replace the existing transformers 110A and 110B. | 2003-06-30 | Approved | 2003-06-16
NU-03-T11 | 2003-06-03 | Great Bay | Addition of 115 kV substation Great Bay which will segment the H141 line between Scobie Pond and Ocean Road. | 2003-05-31 | Approved | 2003-06-15
NSTAR-03-T03 | 2003-05-22 | Dover | Relocation of 115 kv / 53.6 MVAR capacitor bank from Needham to Dover substation | 2003-05-31 | Approved | 2003-06-16
NSTAR-03-T04 | 2003-05-22 | North Woburn | Addition of a third 115/13.8 kV transformer at North Woburn substation. | 2003-05-31 | Approved | 2003-06-16
NU-03-T06 | 2003-05-18 | Middle River | Add third 115/13.8 kv transformer at Middle River to increase load serving capacity. | 2002-05-31 | Approved | 2003-06-16
NU-03-T07 | 2003-05-18 | Cos Cob | Add 115/13.8 kv transformer at Cos Cob to increase load serving capacity. | 2002-05-31 | Approved | 2003-06-16
NU-03-T08 | 2003-05-18 | Peaceable | Add second 115/13.8 kv transformer at Peaceable to increase load serving capacity. | 2002-11-30 | Approved | 2003-06-15
NU-03-T09 | 2003-05-18 | Card | Add sedond 115/13.8 kV transformer at Card to increase load serving capacity. | 2002-08-31 | Approved | 2003-06-16
NU-03-T10 | 2003-05-14 | Waterside | GE TM2500 to be interconnected in the existing mobile transformer position. This installation to be removed on October 1, 2003. The GTs to be connected to the Waterside bus through a single 13.8 kV - 115 kV GSU. | 2003-05-31 | Approved with conditions | 2003-06-05
CMEEC-03-G01 | 2003-05-12 | South Norwalk | Add GE TM2500 generator for summer '03 operation for dispatchable or emergency operation. | 2003-06-01 | Approved with conditions | 2003-06-17
PP-03-G01 | 2003-05-12 | Waterside | Make three GE TM2500 generators available for summer '03 emergency operation. | 2003-05-27 | Approved with conditions | 2003-06-05
ENB-03-RR01 | 2003-05-08 | K Street | Retire Generating unit New Boston 1. | 2003-12-30 | Not approved | 2003-09-08
NU-02-T22 | 2003-05-01 | Madbury | Addition of two 25.2 Mvar fixed shunt capacitor banks to the Madbury 115 kV substation. | 2004-05-31 | Approved | 2003-06-15
NSTAR-03-T06 | 2003-04-27 | Canal | Expand the Canal 345 kV substation with a third bay and install a second Canal to Bourne 345/115 kV auto transformer w/115 kV overhead line. | 2003-05-31 | Approved with conditions | 2003-05-12
NSTAR-03-G01 | 2003-04-03 | MATEP | Addition of two 12.5 MW CT generators to the existing installed generation. Aggregate MATEP generation will not provide a net power interchange to the NSTAR system. | 2003-04-30 | Approved | 2003-04-16
PPLW-03-DR01 | 2003-04-01 | PPL Wallingford Unit 2 | Place PPL Wallingford Unit No. 2 in deactivated reserve status. | 2003-06-30 | Not approved | 2003-06-09
PPLW-03-DR02 | 2003-04-01 | PPL Wallingford Unit 3 | Place PPL Wallingford Unit No. 3 in deactivated reserve status. | 2003-06-30 | Not approved | 2003-06-09
PPLW-03-DR03 | 2003-04-01 | PPL Wallingford Unit 4 | Place PPL Wallingford Unit No. 4 in deactivated reserve status. | 2003-06-30 | Not approved | 2003-06-09
PPLW-03-DR04 | 2003-04-01 | PPL Wallingford Unit 5 | Place PPL Wallingford Unit No. 5 in deactivated reserve status. | 2003-06-30 | Not approved | 2003-06-09
CMP-99-G02 Rev.2 | 2003-03-30 19:00 | Westbrook Units 1, 2, 3 | Removal of 18.4 Subordinate status of Westbrook Energy Center Project: New 578 MW generation plant
VELCO-03-T18 | 2003-03-27 | Tafts Corner | Construct a new 115/34.5 kV substation Tafts Corner by tapping the 115 kV Essex to Williston line. | 2004-06-01 | Approved | 2003-02-16
NU-03-T05 | 2003-03-25 | Connecticut Yankee | The existing 115 kV substation is being reduced in size. The Haddam - CY 1206 and the P&W - CY 1772 lines will be tied together at the existing CY termination structures. | 2003-09-29 | Approved | 2003-04-16
NEP-03-T01 | 2003-03-20 | King Street | Addition of a forth 75 MVA, 115 kV transformer at the King Street substation to provide firm backup to the sub-transmission circuits supplied by the existing transformers. | 2003-06-30 | Approved | 2003-04-16
CMP-03-T01 | 2003-03-12 | Gulf Island Substation | Install a 30 MVAR switched shunt capacitor bank at Gulf Island substation on the 115 kV bus # 3. | 2005-12-31 | Approved with conditions | 2003-03-19
CMP-03-T02 | 2003-03-12 | Kimball Road Substation | Install a 30 MVAR switched shunt capacitor bank at Kimball Road substation on the 115 kV bus # 1. | 2005-12-31 | Approved with conditions | 2003-03-19
CMP-03-X01 | 2003-03-12 | Maine Yankee DCT SPS | Modify existing Maine Yankee DCT SPS to send a signal to NBP Maritimes Islanding SPS for additional generation rejection to remove the requirement for NEPOOL thermal exclusion. | 2005-12-31 | Approved with conditions | 2003-03-19
NU-00-T07 Rev.1 | 2003-03-12 | Towantic Substation | WITHDRAW: Construct a new 115 kV Towantic substation to facilitate the interconnection of the generators on the 1575, 1585, and 1990 lines. Install a 4% reactor on the 1990S line, improve clearances on the 1580 line, improve the rating of the 1585 line. | 2002-12-31 | Approved | 2003-04-16
BHE-03-T01 | 2003-03-11 | Line 3016: Orrington - Point Lepreau | Construct the new 345 kV line 3016 from Orrington, ME to Point Lepreau, New Brunswick. | 2005-12-31 | Approved with conditions | 2003-03-19
BHE-03-T02 | 2003-03-11 | New series compensation for section 388, Orrington | Addition of 25 ohm series capacitor on the 388 line to be located at or near Orrington. | 2005-12-31 | Approved with conditions | 2003-03-19
NMLD-02-T01 Rev.1 | 2003-03-04 19:00 | Ellis Ave Substation | Construct a new 115/13.8 kV substation at Ellis Ave - connected to the exisitng Dean St Subst. Via a 2.2 mile cable. Application being revised with and updated "as built" oneline diagram. | 2002-11-30 19:00
CPN-00-G01 Rev.1 | 2003-03-02 | Towantic Energy Project | WITHDRAW: New 548 MW gas-fired combined cycle power plant. | 2003-03-02 | Approved | 2003-04-16
NEP-03-X01 | 2003-02-23 | Carpenter Hill | The V-174 overload SPS will be removed following V-174 line reconductoring. The new conductor is sized adequately to allow removal of the V-174 overload SPS. | 2003-05-31 | Approved | 2003-04-15
NEP-03-X02 | 2003-02-23 | Brayton Point & West Farnum | NEP studies have identified protection modifications required at Brayton Point & West Farnum substations to maintain compliance with NPCC and NEPOOL criteria. | 2003-11-30 | Approved | 2003-04-16
NU-02-T11 Rev.1 | 2003-02-23 | Glenbrook Substation | Installation of three (3) 50.4 Mvar mechanically switched shunt capacitor banks, one on the B bus & two on the A bus, as part of the overall static var system being installed to assist in maintaining acceptable voltages during a DCT line contingency | 2004-05-31 | Approved | 2003-03-09
NU-03-X01 | 2003-02-20 | Millstone | Retire Millstone failed breaker detector SPS. Millstone station is no longer capable of exceeding the 2200 MW threshold required by this SPS. | 2003-03-31 | Approved | 2003-03-10
NU-03-X02 | 2003-02-20 | Millstone | Retire Millstone double line trip detector SPS. Millstone station is no longer capable of exceeding the 2200 MW threshold required by this SPS. | 2003-03-31 | Approved | 2003-03-10
NU-03-T01 | 2003-02-18 | Stony Hill | Addition of two 115 kV 37.8 Mvar mechanically switched shunt capacitor banks at Stony Hill. | 2003-05-31 | Approved | 2003-03-09
NU-03-T02 | 2003-02-18 | Stony Hill | Addition of two 13.8 kV interconnected +/- 8 Mvar DVAR devices at Stony Hill substation. | 2003-05-31 | Approved | 2003-03-09
NU-03-T03 | 2003-02-18 | Bates Rock | Addition of a 13.8 kV 8 Mvar shunt mechanically switched capacitor bank controlled by a DVAR device at Bates Rock substation. | 2003-05-31 | Approved | 2003-03-09
NU-03-T04 | 2003-02-18 | Bates Rock | Addition of a 13.8 kV interconnected +/- 8 Mvar DVAR device at Bates Rock substation. | 2003-05-31 | Approved | 2003-03-09
NU-02-T10 Rev.1 | 2003-01-21 | Glenbrook Substation | Installation of two +/- 75 Mvar STATCOMs connected to the 115 kV System at the Glenbrook Substation to assist in maintaining acceptable voltages during a DCT line contingency. An additional circuit breaker bay is required. | 2003-11-30 | Approved | 2003-03-09
BHE-02-G01 | 2003-01-09 | Powersville Road | Change in capability for GLHA/GNP generation. | 2003-05-23 | Approved | 2003-01-28
BHE-02-T04 | 2003-01-09 | Powersville Road - Millinocket Sub4 | New GLHA transmission line 6. | 2003-04-30 | Approved | 2003-01-28
BHE-02-T05 | 2003-01-09 | MS#4 | New 15 MVAR manually switched capacitor bank at MS#4. | 2003-04-30 | Approved | 2003-01-28
BHE-02-T06 | 2003-01-09 | Powersville Road | New Great Lakes Hydro America/Great Northern Paper Powersville Road substation. | 2003-04-30 | Approved | 2003-01-28
FPLE-00-G01 Rev.1 | 2002-12-29 | IDC Bellingham Power Project | WITHDRAW: application to construction of 560 MW winter / 450 MW summer generating station. | 2002-12-29
BHE-02-T01 | 2002-12-23 | Line 62 115 kV | New transmission line 62 to new Keene Road 115 kV Switching Station to the new Powersville Road 115 kV Substation. | 2003-04-30 | Approved | 2003-01-28
BHE-02-T02 | 2002-12-23 | Keene Road 115 kV | New Keene Road switching station. | 2003-04-30 | Approved | 2003-01-28
BHE-02-T03 | 2002-12-23 | Graham 115 kV | Graham 115 kV substation reconfiguration. | 2003-04-30 | Approved | 2003-01-28
NSTAR-02-T04 | 2002-12-22 | West Walpole | Replace West Walpole circuit breakers 104, 105, 108, and 109 with IPT capability breakers. | 2003-06-01 | Approved | 2003-01-09
VELCO-03-T01 | 2002-12-19 | Sandbar | Installation of a Phase Angle Regulating Transformer on the PV20 tie to the NYPA Plattsburgh Substation to be located at the Sandbar 115 kV Substation. | 2004-04-30 | Approved | 2003-01-09
VELCO-03-T02 | 2002-12-19 | Blissville | Installation of a Phase Angle Regulating Transformer on the Blissville to Whitehall tie line to the Niagara Mohawks Whitehall Substation to be located at the Blissville 115 kV Substation. | 2004-11-30 | Approved | 2003-01-09
VELCO-03-T03 | 2002-12-19 | Hartford | Upgrade Hartford substation with a 24.75 MVAR capacitor bank and a breaker on the K26 line. | 2004-11-30 | Approved | 2003-01-09
VELCO-03-T04 | 2002-12-19 | Williston | At Williston substation, replace the two breaker radial bus with a three breaker ring bus. | 2004-11-30 | Approved | 2003-01-09
VELCO-03-T05 | 2002-12-19 | Essex | Add a line breaker on the K24 line at Essex substation. | 2004-11-30 | Approved | 2003-01-09
VELCO-03-T06 | 2002-12-19 | Granite | Granite substation upgrades to include: add LTC transformer, add a 230 kV, 550 MVA, 60 PAR, expand 115 kV ring bus, add two 24.75 MVAR cap banks, add +/-75 MVAR dynamic voltage control device. | 2005-11-30 | Approved | 2003-01-09
VELCO-03-T07 | 2002-12-19 | 115 kV line K26 Granite - Barre | Reconductor the 115 kV K26 line Granite to Barre. | 2005-11-30 | Approved | 2003-01-09
VELCO-03-T08 | 2002-12-19 | West Rutland | Close the 345 kV ring at West Rutland substation with two breakers. | 2006-11-30 | Approved | 2003-01-09
VELCO-03-T09 | 2002-12-19 | New Haven | New Haven substation: Rebuild to add 345 bus work, two LTC transformers, a 60 MVAR shunt reactor and six breaker ring bus. | 2006-11-30 | Approved | 2003-01-09
VELCO-03-T10 | 2002-12-19 | New 345 kV line West Rutland - New Haven | Add new 35.5 mile 345 kV line from West Rutland sub. to New Haven sub. | 2006-11-30 | Approved | 2003-01-09
VELCO-03-T11 | 2002-12-19 | Vergennes | Rebuild Vergennes sub to 115 kV with a 115/12.5 kV, 12 MVA transformer and in/out breakers. | 2006-11-30 | Approved | 2003-01-09
VELCO-03-T12 | 2002-12-19 | North Ferrisburg | Rebuild North Ferrisburg sub to 115 kV primary with a 115/12.5kV, 12 MVA transformer. | 2006-11-30 | Approved | 2003-01-09
VELCO-03-T13 | 2002-12-19 | Charlotte | Rebuild Charlotte sub to 115 kV primary with a 115/12.5kV, 12 MVA transformer. | 2006-11-30 | Approved | 2003-01-09
VELCO-03-T14 | 2002-12-19 | Shelburne | Rebuild Shelburne sub to 115 kV primary with a 115/12.5kV, 12 MVA transformer. | 2006-11-30 | Approved | 2003-01-09
VELCO-03-T15 | 2002-12-19 | Queen City | Rebuild Queen City sub from 115 kV radial bus to a five breaker 115 kV ring bus. | 2006-11-30 | Approved | 2003-01-09
VELCO-03-T16 | 2002-12-19 | 115 kV line New Haven - Queen City | Replace 27.2 46 kV/34.5 kV subtransmission line with 115 kV line from New Haven to Vergennes to North Ferrisburg to Charlotte to Shelburne to Queen City. | 2006-11-30 | Approved | 2003-01-09
VELCO-03-T17 | 2002-12-19 | Granite | Expand the Granite dynamic voltage control device from +/- 75 MVAR to +/- 150 MVAR and add two 24.75 cap banks. | 2007-11-30 | Approved | 2003-01-09
NU-02-T21 | 2002-12-17 | Ocean Road | Addition of (2) 25.4 Mvar fixed shunt capacitor banks to Ocean Road 115 kV substation. | 2003-05-31 | Approved | 2003-01-09
NU-02-T23 | 2002-12-17 | Three Rivers | Addition of (2) 25.4 Mvar fixed shunt capacitor banks to the Three Rivers 115 kV substation. | 2003-05-31 | Approved | 2003-01-09
NU-02-X27 | 2002-12-11 | Shunock | Relocate/duplicate the SPS relaying at the Mystic s/s 13k to the new Shunock s/s 32P. | 2004-04-30 | Approved | 2003-01-09
NEP-02-T20 | 2002-12-01 | Raynham Substation | Add two 115 kV/13.8 kV transformers and associated equipment at Raynham substation. | 2003-06-01 | Approved | 2002-12-16
NU-02-T24 | 2002-11-25 | Glenbrook, Frost Bridge, Hanover, Manchester, Mont | Replace overstressed 115 kV breakers at Glenbrook, Frost Bridge, Hanover, Manchester, Montville, and Norwalk substations. | 2003-12-30 | Approved | 2002-12-16
NU-02-T25 | 2002-11-25 | West Springfield, East Springfield, and Clinton | Replace overstressed 115 kV breakers at West Springfield, East Springfield, and Clinton substations. | 2003-12-30 | Approved | 2002-12-16
NU-02-T26 | 2002-11-24 | Norwalk Harbor, CT - Northport, NY 1385 cable | Replace the existing 1385-circuit cables from Norwalk Harbor, CT to Northport, NY with three separate 3-phase circuits. | 2004-05-31 | Approved | 2002-12-16
BELD-02-T01 Rev.1 | 2002-11-21 | Middle Street Substation | Close the Braintree 115 kV loop at Middle Street substation by closing circuit breaker #102. | 2003-05-31 | Approved | 2002-12-16
BELD-02-T02 Rev.1 | 2002-11-21 | Potter Substation | Install a 115 kV, 3 ohm series reactor at Potter station on cable 115-10-16. Install 115 kV circuit switcher to isolate Potter GSU. | 2003-05-31 | Approved | 2002-12-16
BELD-02-X01 Rev.1 | 2002-11-21 | Grove St.-Plain St. 115-9-5 Line | Install a second high speed protection group on BELD cable 115-9-4 between Grove Street and Plain Street. | 2003-05-31 | Approved | 2002-12-16
DNC-02-RR01 | 2002-11-18 | Millstone Power Station | Permanently retire Millstone Unit No. 1 and to permanently remove fuel from the reactor vessel. | 2002-11-18 | Approved | 2002-12-16
NU-02-T19 | 2002-11-17 | Southington Substation | Install three 115 kV 50.4 Mvar mechanically switched shunt capacitor banks at the Southington substation. | 2003-05-31 | Approved | 2002-12-16
NU-02-T20 | 2002-11-17 | Frost Bridge Substation | Install two 115 kV 50.4 Mvar mechanically switched shunt capacitor banks at the Frost Bridge substation. | 2003-05-31 | Approved | 2002-12-16
NSTAR-02-T03 | 2002-11-14 | Hyannis Junction | Increase the size of the existing 115 kV shunt capacitor located at Hyannis Junction from 40 MVAR to 55 MVAR. | 2003-03-31 | Approved | 2002-12-16
ENTERGY-02-T01 Rev.1 | 2002-10-24 | Vermont Yankee Station | Replacement of the Vermont Yankee GSU. | 2002-09-30 | Approved with conditions | 2002-12-17
SNE-02-G01 | 2002-10-22 | New Boston | Reactivation of New Boston Unit 1 due to fire at New Boston Unit 2. | 2002-10-31 | Approved | 2002-10-29
SNE-02-RR02 | 2002-10-22 | New Boston | Retirement of New Boston Unit 2 due to fire. | 2002-10-31 | Approved | 2002-10-29
ENTERGY-02-T01 | 2002-10-20 | Vermont Yankee Station | Replacement of the Vermont Yankee GSU. | 2002-09-30 | Approved | 2002-11-06
NEP-02-X02 | 2002-09-26 20:00 | ANP Bellingham | Installation of a type III Special Protection System (SPS) at the ANP Bellingham generating plant to trip the Unit 2 generator breaker following the tripping of breaker 03-20 initiatyed by the 3520 line relaying | 2002-10-31 19:00 | Approved | 2002-10-20 20:00
BELD-02-T01 | 2002-09-25 | Middle Street Substation | Close the Braintree 115 kV loop at Middle Street Substation. | 2003-05-31 | Approved | 2002-12-17
BELD-02-T02 | 2002-09-25 | Potter Substation | Installation of a 115 kV, three (3) ohm series reactor inserted in the Station ring bus between Breaker #162 and Cable 115-10-16. | 2003-05-31 | Approved | 2002-12-17
BELD-02-X01 | 2002-09-25 | Middle Street Substation | Install a second high speed protection group on BELD calbe 115-9-4 between Grove St. and Plain St. Substations. | 2003-05-31 | Approved | 2002-12-17
NU-02-T18 | 2002-09-19 | Webster-Laconia J125 Line | Construct a second 14 mile 115 kV line, in the exisiting rights of way, between Webster and Laconia. | 2003-05-31 | Approved | 2002-10-20
VELCO-02-T01 | 2002-09-02 | Highgate Substation | Rebuild the existing VELCO and CZN Highgate Substations into a single Highgate Substation with a 115 kV ring bus. | 2004-11-30 | Approved | 2002-09-25
VELCO-02-T02 | 2002-09-02 | Irasburg Substation | Expand existing Irasburg substation to accommodate in and out circuit breakers. | 2004-11-30 | Approved | 2002-09-25
VELCO-02-T03 | 2002-09-02 | St. Johnsbury Substation | Modify St. Johnsbury substation and replace switch 39-3 with a circuit breaker. | 2004-11-30 | Approved | 2002-09-25
VELCO-02-T04 | 2002-09-02 | St. Albans tap | At the St. Albans tap point, construct a switching station with SCADA controled circuit switchers on the lines toward Highgate and Georgia. | 2004-11-30 | Approved | 2002-09-25
VELCO-02-T05 | 2002-09-02 | Irasburge Substation | Build a 6.6 mile double circuit 115 kV line between Moshers tap and the Irasburg substation | 2004-11-30 | Approved | 2002-09-25
NEP-02-T19 | 2002-08-28 | 447-508 line | Add a 3-phase 24/32/48 MVA xfmr to be connected to 447-508 line at the S. Randolph Substation. | 2004-06-01 | Approved | 2002-09-25
NEP-02-T14 | 2002-08-11 | Fitch Rd. Substation Rebuild | Rebuild the 69 kV Fitch Rd. Substation which is in-line breaker arrangement with a breaker and a half design. | 2002-09-01 | Approved | 2002-09-25
NU-02-T17 | 2002-07-28 | 364 Line | Upgrade the 345 kV 363 line terminals from Montville 4J to Haddam Neck 14B. | 2003-11-30 | Approved | 2002-08-11
NU-02-T15 | 2002-07-25 | 1310 line & 1635 line | Replace exisitng conductor in the Manchester-Wapping Junction section of the 1310 line and the Wapping Junction-Barbour Hill section of the 1635 line. | 2005-05-31 | Approved | 2002-08-11
NU-02-T16 | 2002-07-25 | 625 line | Convert the exisiting 625 line from 69 kV to 115 kV from Babbour Hill Substation To Rockville Substation. | 2002-08-31 | Approved | 2002-08-11
NEP-02-T17 | 2002-07-22 | Kent County Sbstation | Add 3-phase 33/44/56 MVA transformer to be connected to K-189 Line at the Kent County Substation. | 2003-06-01 | Approved | 2002-08-11
NEP-02-T15 | 2002-07-21 | Read Street Substation | New 115/13 kV 40 MVA transformer at the Read Street Substation. | 2004-06-01 | Approved | 2002-08-11
NEP-02-T16 | 2002-07-21 | Chartley Pond Substation | Replacement of the 115/23 kV (T2) with 55 MVA transformer at Chartley Pond Substation. | 2003-06-01 | Approved | 2002-08-11
NEP-02-T01 Rev.1 | 2002-07-06 | Tewksbury Substation | WITHDRAW: Installation of four (4) 345 kV breakers along with associated buswork, switches and terminal equipment | 2002-12-31 | Approved | 2004-08-03
NEP-02-X02 | 2002-07-01 20:00 | Carpenter Hill to Millbury 2 Subst. | Removal of the V-174 Overlad SPS at Carpenter Hill, which is no longer required following completion of the reconductoring (NEP-02-T13) | 2003-05-31 20:00
CMP-02-T02 | 2002-07-01 | Spring St. Substation | Addition of a second 30/40/50 MVA 115/34.5 kV transformer and the installation of high & low side breakers at the Spring Street Substation. | 2002-11-30 | Approved | 2002-07-17
NEP-02-T13 | 2002-07-01 | Carpenter Hill to Millbury 2 Subst. | Reconductoring of the 115 kV line V-174 from Carpenter Hill subst #435 to Millbury 2 subst #302. | 2003-05-31 | Approved | 2002-07-17
NEP-02-X02 Rev.1 | 2002-07-01 | Carpenter Hill to Millbury 2 Subst. | WITHDRAW application to remove of the V-174 Overlad SPS at Carpenter Hill, which is no longer required following completion of the reconductoring (NEP-02-T13). | 2003-05-31
NEP-97-T09 | 2002-07-01 | Carpenter Hill to Millbury Subst. | WITHDRAW - Reconductoring of the 115 kV line V-174 from Carpenter Hill subst #435 to Millbury | 2002-07-16 | Approved | 2002-07-17
NEP-98-T08B | 2002-07-01 | West Medway to ANP Bellingham | WITHDRAW - Reconductor 345 kV line 3520 from West Medway to ANP-Bellingham with 2-1113 kcmil ACSR conductor. | 2002-07-01 | Approved | 2002-07-16
NEP-98-T09 Rev.1 | 2002-07-01 | Millbury to Sandy Pond | WITHDRAW - Reconductor 345 kV line 343 from Millbury to Sandy Pond with 2-1113 kcmil ACSR conductor, and upgrade associated disconnect switches at Sandy Pond. | 2002-07-01 | Approved | 2002-07-16
NEP-98-T10 Rev.1 | 2002-07-01 | Millbury to West Medway | WITHDRAW - Reconductor 345 kV line 323 from Millbury to West Medway with 2-1113 kcmil ACSR conductor. | 2002-07-16 | Approved | 2002-07-16
NEP-98-T11 Rev.1 | 2002-07-01 | Millbury Substation | WITHDRAW - Upgrade 345 kV terminal equipment and buswork on lines 302 and 314 at Millbury substation. | 2002-07-01 | Approved | 2002-07-16
NEP-98-T12 Rev.1 | 2002-07-01 | Carpenter Hill to NEP/NU Boarder | WITHDRAW - Reconductor 345 kV line 301 from Carpenter Hill to the NEP/NU border with 2-1113 kcmil ACSR conductor. | 2002-07-01 | Approved | 2002-07-16
NEP-98-T13 Rev.1 | 2002-07-01 | Millbury to Carpenter Hill | WITHDRAW - Reconductor 345 kV line 302 from Millbury to Carpenter Hill with 2-1113 kcmil ACSR conductor. | 2002-07-01 | Approved | 2002-07-16
NEP-98-T14 Rev.1 | 2002-07-01 | Chartley Pond Subst. | WITHDRAW - Upgrade 115 kV terminal equipment on line C-181S at Chartley Pond substation. | 2002-07-01 | Approved | 2002-07-16
NEP-98-T15 Rev.1 | 2002-07-01 | Millbury substation | WITHDRAW - Upgrade 115 kV terminal equipment and buswork on lines P-142 and C-129N at Millbury substation. | 2002-07-01 | Approved | 2002-07-16
NEP-98-T16 Rev.1 | 2002-07-01 | Medway to Depot St to Milford Power | WITHDRAW - Reconductor 115 kV line C-129N from Medway to the Depot Street tap, and the Depot Street tap to Milford Power with 795 kcmil ACSR conductor. | 2002-07-01 | Approved | 2002-07-16
NEP-98-T17 Rev.1 | 2002-07-01 | Davisville tap to W. Kingston | WITHDRAW - Reconductor 115 kV line G-185S from the Davisville tap to West Kingston with 795 kcmil ACSR conductor, and replace the 115 kV circuit breaker and associated disconnect switches at West Kingston. | 2002-07-01 | Approved | 2002-07-16
NEP-98-T18 Rev.1 | 2002-07-01 | Palmer to Carpenter Hill | WITHDRAW - Reconductor 115 kV line W-175 from Palmer to Carpenter Hill with 1590 kcmil ACSR conductor. | 2002-07-01 | Approved | 2002-07-16
NEP-02-T11 | 2002-06-24 | South Wrentham Station | Install 3rd 115/23 kV Transformer (37.3 MVA) at S. Wrentham Station, Wrentham, MA. | 2003-05-31 | Approved | 2002-07-17
NEP-02-T12 | 2002-06-24 | Slayton Hill Substation | Install 2nd 115/13.8 kV transformer at the Slayton Hill Substation. | 2003-05-31 | Approved | 2002-07-17
NU-02-T12 | 2002-06-24 | North Simsbury Substation | Addition of new 115/23 kV Northeast Substation to be supplied by tapping the exisitng N. Bloomfield to Canton 1784 line. | 1999-02-28 | Approved | 2002-07-17
NU-02-T13 | 2002-06-24 | Great Bay Substation | Addition of new 115/34.5 kV Great Bay Substation to be supplied by tapping the exisitng Scobie Pond to Ocean Rd H141 line | 2003-05-31
NU-02-T14 | 2002-06-24 | Pine Hill Substation | Addition of new 115/34.5 kV Pine Hill substatioin to be suplied by tapping the exisitng Greggs to Deerfield O161 line | 2003-05-31 | Approved | 2002-07-17
CMEEC-02-DR01 | 2002-06-20 | South Norwalk 1 | Deactivation of generator due to economics of repairing & evironmental compliance. | 2002-06-30 | Approved | 2002-07-17
CMEEC-02-DR02 | 2002-06-20 | South Norwalk 2 & 4 | Deactivation of generator due to economics of repairing & evironmental compliance. | 2002-06-30 | Approved | 2002-07-17
CMEEC-02-DR03 | 2002-06-20 | South Norwalk 3 & 5 | Deactivation of generator due to economics of repairing & evironmental compliance. | 2002-06-30 | Approved | 2002-07-17
CMEEC-02-DR04 | 2002-06-20 | South Norwalk 6 | Deactivation of generator due to economics of repairing & evironmental compliance. | 2002-06-30 | Approved | 2002-07-17
NEP-02-T10 | 2002-05-28 | Marcus Beebe Substation | Replacement of the existing 40 MVA 115/13.8 kV T-2 transformer at the Marcus Beebe Substation with a new 55 MVA transformer. | 2002-06-30 | Approved | 2002-06-14
NEP-02-G01 | 2002-05-27 | UAE Tewksbury Substation | Construct a new gas-fired, simple cycle generation plant. | 2002-12-31 | Approved | 2002-06-12
NEP-02-T08 | 2002-05-27 | Sandy Pond Substation | Replacement of the existing 115 kV circuit breakers K-137W, K-137T, L-138W, and L-138T with four (4) new 115 kV GIS circuit breakers with a 63 kAIC rating at the Sandy Pond Substation. | 2002-12-31 | Approved | 2002-06-14
NEP-02-T09 | 2002-05-27 | Golden Hills Substation | Replacement of the existing 115 kV breakers F-158 and 45-58 with two (2) new 115 kV circuit breakers with a 63 kAIC rating at the Golden Hills Substation. | 2002-12-31 | Approved | 2002-06-14
NSTAR-02-T01 | 2002-05-23 | Needham Substation | Replacement of the existing 30/40 MVA 115/13.8 kV non-LTC transformer 110B with a new 37/50/62.5 LTC transformer at Needham Substation #148. | 2002-05-31 | Approved | 2002-06-13
NSTAR-02-T02 | 2002-05-23 | Waltham Substation | Replacement of the existing 30/40 MVA 115/13.8 kV LTC transformer 110A with a new 37/50/62.5 LTC transformer at Waltham Substation. | 2002-05-31 | Approved | 2002-06-13
NU-02-T03 | 2002-05-05 | Mystic Substation | Addition of 2-shunt 115 kV 25.2 MVAR mechanically switched capacitor banks at the Mystic Substation. | 2002-07-31 | Approved | 2002-06-14
NU-02-T04 | 2002-05-05 | Shunock 32P - N. Stonington | Addition of a new 115 kC substation: Shunock 32P -North Stonington, CT (proposed). | 2003-04-30 | Approved | 2002-06-13
NU-00-T04 Rev.1 | 2002-05-01 20:00 | Transmission Upgrades | Application revised to reflect new generator GSU configuration (from 2-ABB gen's to 3-GE gen's) and name of the new substation on the 362 line to South Kensington Subst. | 2002-06-29 20:00
NRG-02-DR01 | 2002-05-01 | Devon Substation | Request for Deactivated Reserve status of the Devon Generator 7. | 2002-07-31 | Not approved | 2002-07-24
NRG-02-DR02 | 2002-05-01 | Devon Substation | Request for Deactivated Reserve status of the Devon Generator 8. | 2002-07-31 | Not approved | 2002-07-24
NRG-02-DR03 | 2002-05-01 | Devon Substation | Request for Deactivated Reserve status of the Devon Generator 10. | 2002-07-31 | Not approved | 2002-07-24
NU-02-T09 | 2002-05-01 | Glenbrook Substation | Tapping of the 1977 115 kV line (Darien Substation to South End Substation) at the Glenbrook Substation to convert it to a three terminal line. | 2004-05-31 | Approved | 2002-06-13
NU-02-T10 | 2002-05-01 | Glenbrook Substation | Installation of a +/- 150 Mvar STATCOM connected to the 115 kV System at the Glenbrook Substation to assist in maintaining acceptable voltages during a DCT line contingency. | 2004-05-31 | Approved | 2002-06-13
NU-02-T11 | 2002-05-01 | Glenbrook Substation | Installation of three (3) 50.4 Mvar mechanically switched shunt capacitor banks at the Glenbrook Substation as part of the overall static var system being installed to assist in maintaining acceptable voltages during a DCT line contingency. | 2004-05-31 | Approved | 2002-06-13
SNE-02-RR01 | 2002-05-01 | New Boston | Retirement of the New Boston Unit 1 due to termination of the RMR Agreement on July 1, 2002. | 2002-06-30 | Approved | 2002-06-14
NU-02-T08 | 2002-04-28 | Waterside Substation | Provide for the temporary inteconnection of the Waterside CT's through a single GSU. | 2002-05-31 | Approved | 2002-05-12
NU-02-T05 | 2002-03-21 | Scobie Substation | Addition of a second 400 MVA, 345/115 kV Autotransformer at the Scobie Subsation to eleiminate unacceptable branch loadings & voltage conditions during contingency conditions. | 2004-11-30 | Approved | 2002-04-11
NU-02-T06 | 2002-03-21 | Scobie Pond 115 kV Substation | Reconfigure the Scobie Pond 115 kV Substation from a straight line bus configuration to a breaker-and-half scheme to reliablity interconnect the second 345/115 kV autotransformer. | 2004-11-30 | Approved | 2002-04-12
NU-02-T07 | 2002-03-21 | G146 Line | Rebuild the 115 kV Deerfield-Garvins G146 Line with 1272 MCM ACSR conductor to increase power flow capability and eliminate branch loadings under normal & contingency operations. | 2003-11-30 | Approved | 2002-04-12
CONED-02-G01 Rev.1 | 2002-03-07 | West Springfield Station | Redevelopment of the exisiting West Springfield Power Plant, installation of 2 GE LM6000 CT, rated at 49 MW each. | 2002-04-30 | Approved | 2002-03-14
CONED-02-G01 | 2002-02-24 | West Springfield Station | Redevelopment of the exisiting West Springfield Power Plant, installation of 2 GE LM6000 CT, rated at 49 MW each. | 2002-04-30 | Approved | 2002-03-14
CONED-02-RR01 | 2002-02-24 | West Springfield Station | Retirement of the existing West Springfield Units 1 & 2 (48 MW each). | 2002-03-31 | Approved | 2002-03-14
NU-02-T02 | 2002-02-21 | West Springfield Station | Connect the West Springfield Power Plant replacement units GT-1 and GT-2 at the West Springfield Substation. | 2002-03-31 | Approved | 2002-03-15
CMP-99-G03 Rev.1 | 2002-02-18 19:00 | Gorham Units 1, 2 & 3 - WITHDRAW | Withdraw - New 850 MW generation plant at Buxton Sta. | 2001-11-30 19:00 | Approved | 2002-03-11 19:00
CMP-99-T04 Rev.2 | 2002-02-18 19:00 | Buxton Substation -WITHDRAW | Withdraw - 10 mile 345 kV circuit from Buxton Sta. to Gorham Energy Project | 2000-11-30 19:00 | Approved | 2002-03-11 19:00
NEP-02-T01 | 2002-02-14 | UAE Tewksbury Substation | Add 4-345 kV breakers and associated buswork, switches and termial equipment at the new Tewksbury Generation Station. Also add underground cable from generation polant to steel structure outside the Substation fence. | 2002-12-31 | Approved | 2002-06-14
NEP-02-T02 | 2002-02-14 | UAE Tewksbury Substation | Add (2) 345 kV two-breaker GIS bays; relocate the 337 line and 338 line to the two new GIS bays; install a stell structure outside the substation to transistion the underground cable generator lead to the overhead position presently occupied by 337 line. | 2002-12-31 | Approved | 2002-06-14
NEP-02-T03 | 2002-02-14 | Auburn Street Substation | Install a 115 kV breaker at Auburn Street Substation on the low of the 210 autotransformer. | 2002-05-31 | Approved | 2002-03-11
NEP-02-T04 | 2002-02-14 | Auburn Street Substation | Reconductor the 115 kV line F19 from Bridgewater station to the S1 tap to provide higher thermal capacity. | 2002-05-31 | Approved | 2002-03-11
NEP-02-T05 | 2002-02-14 | Auburn Street Substation | Reconductor the 115 kV line G18 from Bridgewater station to Dupont substation to provide thermal capacity. | 2002-05-31 | Approved | 2002-03-11
NEP-02-T06 | 2002-02-14 | Phillips Lane Substation | At the new Phillips Lane Substation add: one 3-phase 28/33.3/46.5 MVA 115/13.2 kV Xfmr, one 115 kV circuit switcher and a 7.2 MVAR 13.8 kV capacity bank. | 2002-02-28 | Approved | 2002-03-11
NEP-02-T07 | 2002-02-14 | Burtt Rd. Substation | Second 115/13 kV trasformer addition at Burtt Rd. Substation. | 2002-06-30 | Approved | 2002-03-11
NRG-02-G01 | 2002-02-14 | Meriden Power Units 1 and 2 | Revise & Replace App PDC-00-G01. New Application for Installation of two-unit Meriden Power project totaling 546 MW winter / 500 MW summer (10/8/04 removal of subordinate status & 3rd conditon of approval requiring additional short circuit anayses.) | 2003-05-31 | Approved | 2004-10-07
CMP-02-T01 | 2002-02-04 | Sanfod Substation | Install a 30.6 MVAR Capacitor bank at the Sanford 115 kV Substation. This capacitor bank was removed from the Maine Yankee substation (CMP-98-T01) in 1998. | 2002-04-01 | Approved | 2002-03-11
NU-00-T25 Rev.1 | 2002-01-22 | Scovill Rock | Withdraw Application for Installing a new 9T bkr at Scovill Rock and reterminate the 376 line between the 8T and new 9T bkr. | 2002-05-01 | Approved | 2002-02-12
NU-00-X26 Rev.1 | 2002-01-22 | Scovill Rock | Install type III SPS at Scovill Rock to runback the East Shore HVdc Facility in the event the 387 line is open ended at Scovill Rock. | 2002-04-30 | Approved | 2002-02-12
NU-02-T01 | 2002-01-22 | N. Bloomfield (2A) to Bloomfield (3B) | Replace terminal wave traps on the 115 kV Bloomfield - N. Bloomfield 1777 line. | 2002-04-30 | Approved | 2002-02-12
NMLD-02-T01 | 2001-12-26 | Ellis Ave Substation | Construct a new 115/13.8 kV substation at Ellis Ave - connected to the exisitng Dean St Subst. Via a 2.2 mile cable. | 2002-12-31 | Approved | 2002-02-12
NSTAR-01-T05 | 2001-12-26 | Oak Street Substation | Construct a new distribution substation with a 30/40/50 MVA 115/23 kV transformer to be connected to the Bourne to Barnstable #122 115 kV. | 2003-08-31 | Approved | 2002-02-12
NSTAR-02-X01 | 2001-12-26 | Ellis Ave Substation | Install a redundant high-speed protection system between Holbrook substation, Dean St substation, & the new Ellis Ave Substation | 2002-09-01 | Approved | 2002-02-12
NEP-01-T15 | 2001-12-18 | Northboro Road Substation | Install a 54 MVAR capacitor at the Northboro Rd 115 kV Substation to provide needed voltage support in the Central MA area. | 2001-12-31 | Approved | 2002-02-12
NEP-01-T16 | 2001-12-18 | Millbury Substation | Install a 63 MVAR capcitor at the Millbury 115 kV substation to provide needed voltage support in the Central MA area. | 2001-12-31 | Approved | 2002-02-12
NEP-01-T17 | 2001-12-18 | MWRA Substation | Tap the W-23, 69 kV line to provide load supply to a new MWRA water treatment facility. | 2002-12-31 | Approved | 2002-02-12
VELCO-01-T02 | 2001-12-17 | Sand Bar Substation | Removal of the second cap. Bank at Sand Bar Subst. And relation to the Essex Subst. 115 kV ring bus as bank #5. | 2002-05-31 | Approved | 2002-02-12
VELCO-01-T03 | 2001-12-17 | Essex Substation | Addition of one new 24.75 MVAR cap bank to the Essex Subst. 115 kV ring bus as bank #6 | 2002-05-31 | Approved | 2002-02-12
NSTAR-01-X04 | 2001-12-04 | Mystic Substation | Removal of the Type III SPS at the Mystic 345 kV Subst. Originally the SPS was installed to provide first contigency thermal coverage; four additioanl 345 kV circuits (line 349 XY, 372, 324 & 351) have been installed eliminated the need for the SPS. | 2001-12-31 | Approved | 2002-02-12
NU-01-G01 | 2001-12-02 | Cabot Hydro Station | Capacity Change - redesign Cabot Station generators (6) by converting their V output from 6.9 kV to 13.8 kV, tie the six generators together through a single collector bus, & utilize a single GSU as described in NU-01-T14. | 2003-12-31 | Approved | 2002-02-12
NU-01-T14 | 2001-12-02 | Cabot 19G/Montague 21C | Reconfiguration of the Cabot Station (19G) interconnection to the Montague Substation (21C) by replacing four (4) GSUs and a series 9/115 kV transformer with one (1) GSU (13.8/115 kV) based on the absence of preexisting 69 kV cirucits at Montague. | 2001-12-31 | Approved | 2002-02-12
NU-01-X02 | 2001-11-04 | Lake Road | Installation of a Type III SPS to be connected to all units when either the 330 or 347 lines are open, to protect the units from excessive torque during faults in which there are high import/exports conditions.. | 2001-10-31 | Approved | 2001-12-20
NU-01-T11 | 2001-10-29 | Fort Hill Substation | Installation of a new 115/34.5 kV, 40 MVA Substation in Montville, CT (Fort Hill Substation). | 2002-01-31 | Approved | 2001-12-20
INDECK-01-G01 | 2001-10-18 | Indeck - Alexandria Energy Center | Reactivation of a renewable resource generating facility with a capability of 14/6 MW. | 2002-06-01 | Approved | 2001-12-20
NEP-01-T14 | 2001-09-26 | Billerica Substation | Add two 115 kV circuit switchers with motor operated disconnect switch and associated terminal equipment. | 2002-06-30 | Approved | 2001-11-14
NEP-01-T13 | 2001-08-21 | Northboro Road Substation | Add 2nd radial 115 kV line from Northboro Road substation to the Hudson town line. Install one new 115 kV tie circuit breaker in existing bay at Northboro Road station. | 2002-11-30 | Approved | 2002-02-12
MIR-01-G01 Rev.1 | 2001-08-15 | Kendall Station | Construct new gas fired generator (Kendall CT) with a net capability of 187 MW (Winter) and 170 MW (Summer) adjacent to the existing Kendall Steam Units at Kendall Station. | 2002-05-31
MIR-01-G01 | 2001-07-31 | Kendall Station | Construct new gas fired generator (Kendall CT) with a net capability of 187 MW (Winter) and 170 MW (Summer) adjacent to the existing Kendall Steam Units at Kendall Station. | 2002-05-31
NSTAR-01-T03 | 2001-07-31 | Kendall Station to the Putnam Station | Install 2.5 miles of solid-dielectric cable, routed in concrete duct, from the Kendall 115 kV Station to the Putnam 115 kV Substation. Connect the Kendall 115 kV generator cable to the Putnam 115 kV Substation. | 2002-05-31
NSTAR-01-T04 | 2001-07-31 | North Cambridge Station | Install two 115 kV series reactors (2.0 ohms) at the North Cambridge Station #509 in each of the 115 kV lines #329-530 and #329-531. | 2002-05-31
NU-01-T10 Rev.1 | 2001-07-30 20:00 | RESCIND APPLICATION for North Bloomfield 2A Substa | RESCIND APPLICATION for the Upgrade the 1784 line's terminal equipment at the North Bloomfield end. | 2003-05-31 20:00
NU-01-X10 | 2001-07-30 | 1732 Line | Remove the exisiting Canton to Weingart Jct. Rd 1732 line's thermal overload relay. | 2002-05-31
NU-01-T05 | 2001-07-25 20:00 | Balck Pond Jct. | Deparation of three double circuit 345 kV support structures to single circuit support structures for the 348 & 387 line | 2003-05-31 20:00
NSTAR-01-T02 | 2001-07-12 | Chelsea Substation | Replace the 115/13.8 kV Chelsea Transformers 110A and 110B. | 2001-08-01
NU-01-T09 Rev.1 | 2001-07-05 20:00 | Canton 5R Substation | Add one 115 kV, 39.3 MVAR mechanically switched shunt capacitor bank at the Canton 5R substation | 2003-05-31 20:00
NU-01-T10 | 2001-07-05 20:00 | North Bloomfield 2A Substation | Upgrade the 1784 line's terminal equipment at the North Bloomfield end. | 2003-05-31 20:00
NU-01-T07 | 2001-07-05 | 1732 line | Rebuild the Canton-Weingart, 1732 line. | 2002-05-31
NU-01-T08 | 2001-07-05 | Canton 5R Substation | Add two (2) 115-kV, 26.2 MVAR mechanically switched shunt capacitor banks at the Canton 5R substation. | 2003-05-31
NU-01-T09 | 2001-07-05 | Canton 5R Substation | Add one (1) 115-kV, 39.3 MVAR mechanically switched shunt capacitor bank at the Franklin Drive 1B substation. | 2003-05-31
NU-99-T10 Rev.2 | 2001-07-05 | 1781 and 1782 lines | Interim Interconnection for the Berkshire Power Generating Station (276 MW). | 2002-09-30
CMP-01-T01 | 2001-06-28 | Redbrook Substation | Tap Section 160 and add a 115/34.5 kV Xfmr at Redbrook Substation & install 2-bkrs to Section 160 at Pleasant Hill Substation. | 2001-09-30
CMP-01-T02 | 2001-06-28 | Lincolnville Substation | Construct new 115 kV to 34.5 kV, 14 MVA substation and will tap Section 86. | 2001-09-30
NEP-01-T08 | 2001-06-21 | Shrewsbury Electric Light Plant, Rolfe Ave Subst. | Install two 30/40/50 MVA 115/13.8 kV transformers, two 115 kV circuit switchers and a new 69 kV breaker to complete the 69 kV ring bus. | 2002-05-31
NU-01-T06 | 2001-06-13 | Chestnut Hill Substation | Addition of two 26.2 MVAR capacitor banks at the NU Chestnut Hill 115 kV Substation. | 2002-04-01
NU-01-T01 | 2001-06-05 | Merrimack Substation | Replace exisitng 230/115 kV autotransformer at the Merrimack Substation with a larger autotransformer to provide approxiamte 300 MVA of summer LTE transformation capability. | 2002-12-30
NEP-01-X01 | 2001-06-04 | Bridgewater Station | Remvoe the U6 line type III SPS at Bridgewater Station based on the elimination of the conditions requireng its use. | 2001-05-31
NEP-01-T12 | 2001-06-03 | Millbury Station Bkr #314 | Upgrade breaker 314 at the Millbury station to achieve Independent Pole tripping capability. | 2002-05-31
NSTAR-01-T01 | 2001-06-03 | West Medway Station | Modify the West Medway 345 kV station to install breaker 113 and connect the Sithe 345 kV generator lead. Upgrade breakers 101, 103, 104, 106, 107 and 109 | 2002-06-01
SNE-01-G01 | 2001-06-03 | West Medway Station | New Gas Trubine Generating plant consisting of three single-cycle natural gas fired generators (Units 4, 5 & 6). | 2002-05-31
VELCO-01-T01 | 2001-05-30 | Coolidge Substation | Additional of two 24.75 MVAR capacitor banks & associated breakers at the Coolidge Substation. | 2002-05-31
NEP-01-T11 | 2001-05-29 | South Danvers Substation | South Danvers Substation - Tap the C155 Nline and rearrange the exisitng two taps oon the C-155S & B-154 lines to serve the exisiting theree 115/23 kV xfmrs. | 2001-11-30
NEP-01-T03 | 2001-05-28 | Westford Substation | Installation of a new 115/13.2 kV Substation in Wesford, MA that will tap the K-137E 115 kV line between Littleton and Bellerica. | 2001-12-31
NU-01-T05 | 2001-05-17 20:00 | Schiller-Bolt Hill N133 Line | Replace limiting termianl equipment on the 115 kV Schiller - Bolt Hill N133 line
NU-01-T04 | 2001-05-14 | Cobble Mtn. Substation | Reconfigure Cobble Mtn Substation by removing the three GSU's and replacing with one GSU. | 2001-11-30
NEP-01-T07 | 2001-04-22 | Gilbert Street Substation | Add four 115 kV circuit switches with MOD's and two electrically inter-locked motor operated 115 kV disconnect switches between lines C-181N and D-182S. | 2001-05-31
NEP-00-G01 | 2001-04-15 | AES Londonderry Stage I Station | Request to Withdraw - New gas-fired combined cycle generation plant consisting of two combustion turbine generators, one steam turbine generator, three generator step-up transformers and three 230 kV generation leads. | 2002-05-31
NEP-00-T02 | 2001-04-15 | North Litchfield Substation | Request to Withdraw - Add two new 230 kV three-breaker ring buses and associated switches and terminal equipment to sectionalize: 1) line A-201 into A-201N and A-201S, and 2) line B-202 into B-202N and B-202S. | 2001-07-31
NEP-00-T03 | 2001-04-15 | AES Generation Station to North Litchfield Substat | Request to Withdraw - Add two 230 kV breakers w/ associated buswork, switches and terminal equip. at new AES Generation Station. Add new 230 KV double circuit line from generation plant to N.Litchfield Subst. | 2001-11-30
NEP-00-T04 | 2001-04-15 | Tewksbury & Pratts Junction Substations | Request to Withdraw - At Tewksbury Subst: Upgrade the 115 kV buswork & terminal equip.; replace 8-115 kV breakers; upgrade 3-230 kV bkrs; install high speed pilot protection group to seven lines; upgrade Pratts Jct. Substation 115 buswork & terminal equip | 2001-11-30
NEP-00-T05 | 2001-04-15 | North Litchfield and Tewksbury Substations | Request to Withdraw - Re-conductor the 230 kV line A-201S between the North Litchfield and Tewksbury Substations; upgrade Tewksbury Substation 230 kV buswork and terminal equipment. | 2001-11-30
NEP-00-T06 | 2001-04-15 | Tewksbury Substation | Request to Withdraw - Replace 230/115 kV Transformer with a total three phase rating of 500 MVA and reconfigure 230 kV yard at Tewksbury Substation. | 2002-05-31
NEP-00-X01 | 2001-04-15 | Comerford Phase I HVdc | Request to Withdraw - Modify the existing Comerford Phase I HVdc Type III Special Protection System to transfer trip signal to initiate runback of the Phase I HVdc generation from the Tewksbury Substation to the new North Litchfield Substation. | 2001-07-31
NEP-00-X02 | 2001-04-15 | North Litchfield and Tewksbury substations | Request to Withdraw - Add two new NPCC Type III SPS to trip the AES Stage I generation. | 2001-11-30
NEP-01-G01 Rev.1 | 2001-04-10 20:00 | UAE Lowell Power | Construct new simple cycle generating plant consisting of 2 CT's with a combined net capacity of 95.2 MW at 20 degrees F to be built adjacent to existing UAE Lowell Facility | 2001-05-31 20:00
NSTAR-00-T24 Rev.1 | 2001-03-27 | Framingham Station No. 240 | Add second 115 kV autogtransformer at Framingham Station No. 240. | 2002-06-01
NSTAR-00-X04 | 2001-03-27 | Framingham to Sherborn Line | Request to Withdrawal - installation of Redundant High Speed Relaying on Framingham to Sherborn 115 kV Line No. 240-508. | 2001-04-10
NEP-01-G01 | 2001-03-25 | UAE Lowell Power | Construct new simple cycle generating plant consisting of 2 CT's with a combined net capacity of 95.2 MW at 20 degrees F to be built adjacent to existing UAE Lowell Facility. | 2001-05-31
NU-01-T02 | 2001-03-13 | Stony Hill 48C Substation | Install a 115 kV 25.2 MVAR mechanically switched shunt capacitor bank at the Stony Hill 48C Substation. | 2001-02-11
NU-01-T03 | 2001-03-13 | Rocky River 12Y Substation | Install a 115 kV 25.2 MVAR mechanically switched shunt capacitor bank at the Rocky River 12Y Substation. | 2001-02-11
NEP-00-X06 Rev.1 | 2001-03-12 | North Quincy & Field Street Stations | Request to Withdraw - Modify exisitng protections schemes at the Quincy & Field Street substations as the result of the Fore River new generation project. | 2001-03-12
NU-00-T05 Rev.1 | 2001-03-07 | Merrimack Substation | Request to Withdraw - Replace/upgrade or make a parallel addition to the 230/115 kV transformer at the Merrimack Substation to provide 300 MVA of summer LTE transformation capacity. | 2001-03-07
NU-00-X01 Rev.1 | 2001-03-07 | Merrimack Substation | Request to Withdraw - Add one new NPCC Type III SPS at the Merrimack Substation to monitor loading on the Merrimack autotransformer so as to trip an AES Londonderrry unit whenever an overload condition is detected on the Merrimack autotransformer. | 2001-03-07
MIR-01-X01 | 2001-03-01 | Canal Unit 1 Exciter | Replacement of the Canal Unit #1 Exciter. | 2001-04-30
NSTAR-00-T06 Rev.1 | 2001-03-01 | Edgar Station | Revised previous submittal to remove the requirement to install two high-speed protection systems on the Edgar-North Quincy-Dewar St Lines 517-532, 517-533, 517-524, 517-525 as confirmed by add'l analysis. | 2002-04-01
NEP-01-T04 | 2001-02-20 | Fitch Rd Substation | Reconductor and rebuild the radial 69 KV line W-23 from Fitch Rd Substation to Woodside Substation to 795 ACSR. | 2001-11-30
NEP-01-T05 | 2001-02-20 | Warren Trasformer No. 2 | Replace the 115/13.2 kV Warren Transformer No. 2. | 2002-06-01
NEP-01-T06 | 2001-02-20 | Beverly Substation | Tap the M-191 Line & install a new 115/13.2 kV substation (Beverly #12). | 2002-06-01
NEP-01-T03 Rev.1 | 2001-02-07 | Westford Substation | Request to Withdraw - Install new 115/13.2 kV substation in Westford MA. | 2001-12-31
NEP-01-T01 | 2001-01-30 | Wareham St. Substation | Install third 24/32/40 MVA 115 kV - 13.8 kV power transmformer at the Wareham St. Substation. | 2001-06-30
NEP-01-T02 | 2001-01-30 | East Bridgewater Station | Upgrade radial 115 kV line L1 from the E20 tap to East Bridgewater station for greater thermal capabilty | 2002-04-30
NEP-00-G02 Rev.1 | 2001-01-28 | Hope Energy (RISE) | Contruct a new combined cycle generating plant consisting of two combustion turbine generators and one steam turbine generator. | 2001-05-31
BE-98-T05 Rev.3 | 2001-01-14 | West Medway #446 345 kV switchyard | Modify/upgrade facilities at West Medway #446 345 kV switchyard wih the replacement of 345 kV breakers, associated disconnect switches and other misc. equipment. | 2001-01-14
NU-00-T24 | 2000-12-19 19:00 | Montville - Bean Hill | Request to Withdraw - Remove clearance limitation and increase summer ratings of the Montville - Bean Hill #1000 Line | 2000-05-31 20:00
NEP-00-T29 | 2000-11-28 | Devens Commerce Center | Reconductor U-21 69kV radial line from Ayer to Pratt Junction substation, install relays & rearrange supply to Devenos Commerce Center | 2001-05-31
NEP-00-T28 | 2000-11-21 | North Quincy Station | Install new 115/32.2 kV substation - Woodchuck Hill & tap the B-154N line between King St. and Middletown. | 2000-12-31
VELCO-00-T04 Rev.1 | 2000-11-15 | Coolidge Substation/West Rutland Substation | Reconnect & Reenergize (345 kV) the Coolidge substation to West Rutland substation. | 2002-06-01
VELCO-00-T06 Rev.1 | 2000-11-15 | West Rutland Substation | Rebuild the West Rutland substation to incorporate interconnection through 345 kV bkrs & into a six bkr ring bus. | 2002-06-01
NEP-00-X06 | 2000-11-08 | North Quincy & Field Street Stations | Modify exisitng protections schemes at the Quincy & Field Street substations as the result of the Fore River new generation project. | 2002-04-01
NEP-00-T27 | 2000-11-07 | Kent County Substation | Install 115/12.47 kV transformer at Kent County Substation; will tap bus #2. | 2001-12-31
NU-00-T25 | 2000-11-05 | Scovill Rock | Install new 9T bkr at Scovill Rock and reterminate the 376 line between the 8T and new 9T bkr. | 2002-04-30
NU-00-X26 | 2000-11-05 | Scovill Rock | Install type III SPS at Scovill Rock to runback the East Shore HVdc Facility in the event the 387 line is open ended at Scovill Rock. | 2002-04-30
NEP-00-G05 Rev.1 | 2000-11-01 | Brockton Power Generating Plant | Construction of a 288 MW Winter/267 Summer Combined Cycle Plant. | 2002-12-31
VELCO-00-T04 | 2000-11-01 | Coolidge Substation/West Rutland Substation | Reconnect & Reenergize (345 kV) the Coolidge substation to West Rutland substation. | 2002-06-01
VELCO-00-T05 | 2000-11-01 | Coolidge Substation/West Rutland Substation | Construct a three breaker 345 kV ring bus. | 2002-06-01
VELCO-00-T06 | 2000-11-01 | West Rutland Substation | Rebuild the West Rutland substation to incorporate interconnection through 345 kV bkrs & into a six bkr ring bus. | 2002-06-01
VELCO-00-T07 | 2000-11-01 | West Rutland Substation | Rebuild the West Rutland Substation to West Rutland Tap. | 2002-06-01
VELCO-00-T08 | 2000-11-01 | Cold River Substation | Replace Motor Operated SCADA control switches at Cold River Substation. | 2002-06-01
VELCO-00-T09 | 2000-11-01 | Blissville Substation | Replace Motor Operated SCADA control switches at Blissville Substation. | 2002-06-01
NSTAR-00-T24 | 2000-10-30 | Framingham Station No. 240 | Add second 115 kV autogtransformer at Framingham Station No. 240 | 2002-06-01
NSTAR-00-T25 | 2000-10-30 | West Medway Station No. 446 | Replacement existing autotransformer No. 345B. | 2002-06-01
NSTAR-00-T26 | 2000-10-30 | Walpole Station No. 447 | Replace existing autotransformer. | 2002-06-01
NSTAR-00-T27 | 2000-10-30 | Waltham Station No. 282 | Replacement existing autotransformer. | 2002-06-01
NSTAR-00-T28 | 2000-10-30 | Waltham Station No. 282 | Add third 115 kV phase angle regulating transformer. | 2002-06-01
NSTAR-00-T29 | 2000-10-30 | West Medway/Waltham Stations | Modification of towers on the 282-602 line & 240-601 line. | 2002-06-01
NSTAR-00-T30 | 2000-10-30 | Sudbury/Speen St. Stations | Rebuild the 342-507 line. | 2002-06-01
NSTAR-00-T31 | 2000-10-30 | Towers between Speen St. & Framingham | Replace towers on the 433-507 line. | 2002-06-01
NSTAR-00-T32 | 2000-10-30 | Sherborn Rd. Station No. 274 | Replace bkrs & disconnect switches. | 2002-06-01
NU-00-T21 | 2000-10-29 | Greggs | Greggs Substation - F1620 Bkr Replacement. | 2001-12-30
NU-00-T22 | 2000-10-29 | Greggs | Greggs Sustation - J1140 Bkr Replacement. | 2001-12-30
NU-00-T23 | 2000-10-29 | Merrimack | Merrimack Substation - D121 Bkr Replacement. | 2001-12-30
NSTAR-00-T15 | 2000-10-15 | Associated Xmission for Sithe Mystic Station | Modify the Mystic 345 kV station to install line 351. | 2001-11-30
NSTAR-00-T23 | 2000-10-15 | Sithe Mystic Station | Install three 115 kV shunt reactors, one each at K Street, Woburn and Lexington. | 2002-04-01
NEP-00-T22 | 2000-10-10 | Brockton Power | Construct a three breaker ring bus station. | 2002-04-30
NEP-00-T23 | 2000-10-10 | Brockton Power | Reconductor F19 Line from Brockton Power to Auburn Street. | 2002-04-30
NEP-00-T24 | 2000-10-10 | Brockton Power | Replace the 1601 breaker at Bridgewater Station. | 2002-04-30
NEP-00-T25 | 2000-10-10 | Brockton Power | Rebuild the S8 line from Bridgewater Station to Somerset Station. | 2002-04-30
NEP-00-T26 | 2000-10-10 | Brockton Power | Upgrade thermal capacity of the northern Auburn Street 115 kV ring bus. | 2002-04-30
NEP-00-X05 | 2000-10-10 | Brockton Power | Install Type III SPS at Auburn Street station. | 2002-04-30
SNE-00-G02 | 2000-10-10 | Sithe Mystic Station | Construction of a 1700 MW Winter/1413 Summer Combined Cycle Plant | 2001-12-31
NEP-00-G05 | 2000-10-09 | Brockton Power Generating Plant | Construction of a 288 MW Winter/267 Summer Combined Cycle Plant. | 2002-12-31
NSTAR-00-T16 | 2000-10-09 | Sithe Mystic Station | Construct a new 5-breaker 115 kV ring station at Mystic to connect lines 211-514 (Mystic to Woburn), 423-515 (Mystic to Everett) and 488-518 (Mystic to Chelsea) and the Sithe 115 kV steam unit #13. | 2002-04-01
NSTAR-00-T17 | 2000-10-09 | Sithe Mystic Station | Install line 351 and a 115 kV shunt reactor at North Cambridge. | 2001-11-30
NSTAR-00-T18 | 2000-10-09 | Sithe Mystic Station | Separate line 346XY into two lines 346 & 465. | 2001-11-30
NSTAR-00-T19 | 2000-10-09 | Associated Xmission for Sithe Mystic Station | Reconductor lines 250-516 and 250-517. | 2002-04-01
NSTAR-00-T20 | 2000-10-09 | Sithe Mystic Station | Improve cable cooling on lines 329-510 and 329-511 (Mystic to Somerville to Brighton). | 2002-04-01
NSTAR-00-T21 | 2000-10-09 | Sithe Mystic Station | Improve cable cooling on lines 385-510 & 385-511 between High Street and Kingston Street. | 2002-04-01
NSTAR-00-T22 | 2000-10-09 | Sithe Mystic Station | Replace the Mystic autotransformer. | 2001-11-30
NSTAR-00-X03 | 2000-10-09 | Sithe Mystic Station | Install a Type III SPS to trip the Sithe steam unit following a stuck breaker contingency between 211-514 and 423-515 or 488-518. | 2002-04-01
NSTAR-00-T14 | 2000-10-02 | Line #282-507 | Reconductor 115 KV Line #282, Waltham, to Station # 342, Sudbury. | 2001-05-31
NU-00-T13 | 2000-10-01 | Capacitor Bank Replacement at Berlin | 115 kV Capacitor bank (6A-13K) replacement at Berlin. | 2000-12-31
NEP-00-G04 | 2000-09-21 | AES Londonderry | Construction of 767 MW Winter/ 678 MW Summer Combined Cycle gas/oil plant. | 2002-05-31
NEP-00-T18 | 2000-09-21 | AES Londonderry | Construction of new N. Litchfield substation. | 2002-05-31
NEP-00-T19 | 2000-09-21 | AES Londonderry | Construction of a new 230 KV double circuit line from Londonderry to N. Litchfield | 2002-05-31
NEP-00-T20 | 2000-09-21 | AES Londonderry | Replacement of substation transformer #2 at NEP Tewksbury; install pilot protection on various lines; Replace Pratts Junction 115 KV buswork. | 2002-05-31
NEP-00-T21 | 2000-09-21 | AES Londonderry | Re-tension NEP 230 KV line B202S & Upgrade buswork. | 2002-05-31
NEP-00-X03 | 2000-09-21 | AES Londonderry | Modify Comerford Phase I HVdc Special Protection System. | 2002-05-31
NEP-00-X04 | 2000-09-21 | AES Londonderry | Install a Type III Special Protection System at N. Litchfield substation. | 2002-05-31
NU-00-T14 | 2000-09-21 | AES Londonderry | Rebuild R-187 from Greggs to Scobie. | 2002-05-31
NU-00-T15 | 2000-09-21 | AES Londonderry | Rebuild R-169 Line from Three Rivers to Dover. | 2002-05-31
NU-00-T16 | 2000-09-21 | AES Londonderry | Replacement of 115 KV circuit breaker at Greggs Falls substation (O1610). | 2002-05-31
NU-00-T17 | 2000-09-21 | AES Londonderry | Replacement of 115 KV circuit breaker at Merrimack substation (H137). | 2002-05-31
NU-00-T18 | 2000-09-21 | AES Londonderry | Line Reactor at Greggs Substation. | 2002-05-31
NU-00-T20 | 2000-09-21 | AES Londonderry | Construct 3 breaker substation at Watts Brook on R-187 line. | 2002-05-31
NU-00-X19 | 2000-09-21 | AES Londonderry | Install Type III Special Protection System at Greggs Falls substation. | 2002-05-31
NU-00-T12 | 2000-09-04 | Capacitor Bank Replacement at Plumtree | Capacitor bank replacement at Plumtree. | 2000-12-31
NEP-00-T17 | 2000-08-07 | Sherman Road | Replace protection equipment at the Sherman Road terminal of line 347. | 2000-08-31
BE-99-T04 | 2000-07-31 | 303N Line Upgrade Cancellation | Withdrawal of Application BE-99-T04. | 2000-07-31
BHE-00-G01 | 2000-07-31 | Beaver Chester Generating Plant | Reactivate 14.7 MW biomass fired generation. | 2000-08-31
FPLE-00-G01 | 2000-07-31 | IDC Bellingham Power Project | Construction of 560 MW winter / 450 MW summer generating station. | 2003-01-31
NSTAR-00-T04 | 2000-07-31 | 345 kV Ring Station | Construct a five-breaker 345 kV ring station to interconnect the IDC plant. | 2002-06-01
NSTAR-00-T05 | 2000-07-31 | 345 kV West Medway breakers | Upgrade West Medway breakers to address short circuit and stability concerns. | 2002-06-01
NSTAR-00-T06 | 2000-07-31 | Edgar Station | Modify Edgar station to connect the three Sithe units, split line 478-502XY into two separate line and relocate the Edgar to North Quincy 115 kV cables. | 2002-06-01
NSTAR-00-T07 | 2000-07-31 | Holbrook Station | Modify Holbrook Station by splitting and relocating lines, upgrading/retrofitting 115 kV breakers. | 2002-06-01
NSTAR-00-T08 | 2000-07-31 | Edgar breaker #10 and Grove Street Breaker | Upgrade Edgar breaker #10 and Grove Street breaker to address short circuit concerns. | 2002-06-01
NSTAR-00-T09 | 2000-07-31 | 115 kV transmission line 478-508 and 478-509 | Remove conductor to ground clearance limitations to achieve the full capability of the conductors. | 2002-06-01
NSTAR-00-T10 | 2000-07-31 | 115 kV transmission line 478-502 and 478-503 | Split line 478-502XY into lines 478-502 and 478-503 and re-conductor the resulting two lines. | 2002-06-01
NSTAR-00-T11 | 2000-07-31 | 115 kV transmission lines 447-508 and 447-509 | Remove conductor to ground clearance limitations to achieve the full capability of the 795 ACSR conductors. | 2002-06-01
NSTAR-00-T12 | 2000-07-31 | 115 kV transmission line 65-508 | Upgrade the line to achieve a minimum LTE rating of 220 MVA. | 2002-06-01
NSTAR-00-T13 | 2000-07-31 | 115 kV transmission line 65-502XY | Upgrade the line to achieve a minimum LTE rating of 220 MVA. | 2002-06-01
NSTAR-00-X01 | 2000-07-31 | SPS at IDC | Install a Type II SPS to trip the steam unit for any stuck breaker fault at the IDC interconnection station. | 2002-06-01
NSTAR-00-X02 | 2000-07-31 | Type III SPS | Install a Type III SPS to trip the Sithe steam unit and one gas unit for a 5% STE violation upon loss of two or more of the four lines out ot the Sithe Fore River plant after a 5-second delay. | 2002-06-01
PGE-00-G01 | 2000-07-26 | Lake Road Generating plant | Construction of a three-unit natural gas fired combined cycle power facility with a nominal rating of 792 MW. | 2004-08-01 | Approved | 2000-09-18
NU-00-T11 | 2000-07-24 | Lake Road | Provide a connection for the three Lake Road generators to the New England 345 kV transmission system on the 347 Line near the Connecticut-Rhode Island border. | 2000-08-31
SNE-00-G01 | 2000-07-10 | Fore River Station generation plant | Construct an 843 MW winter/700 MW summer combined cycle gas plant. | 2002-04-30
NU-00-G01 | 2000-07-06 20:00 | PPL Wallingford Energy | Construction of five new generating units. 10/8/04: removal of condition 3 of approval pertaining to additional short circuit related anayses.) | 2001-05-31 20:00 | Approved | 2004-10-07 20:00
NU-00-T08 | 2000-07-06 | Wallingford Energy | Substation and Transmission Upgrades to Interconnect the Wallingford Energy. | 2001-05-31
NEP-00-T15 | 2000-07-05 | Shaker Road Substation | Replace existing 69/13.2 kV transformer T-2 at Shaker Road Substation, MA. | 2001-05-31
NEP-00-T16 | 2000-07-02 | 328 Line | Construct a three breaker ring bus substation on the 328 line for the interconnection of the North Smithfield power plant. | 2002-02-28
INDECK-00-G01 | 2000-06-28 | Indeck - North Smithfield Energy Center | Construction of a new 350 MW gas turbine combined cycle facility. | 2003-06-30
NU-99-T10 Rev.1 | 2000-06-21 | 1781 and 1782 lines | Interim interconnection for the Berkshire Power Generating Station | 2001-08-31
CPN-00-G01 | 2000-06-04 | Towantic Energy Project | New 548 MW gas-fired combined cycle power plant. | 2002-12-30
NU-00-T07 | 2000-05-30 | Towantic Energy | Construct a new 115 kV Towantic substation to facilitate the interconnection of the generators on the 1575, 1585, and 1990 lines. Install a 4% reactor on the 1990S line, improve clearances on the 1580 line, improve the rating of the 1585 line. | 2001-12-30
NU-00-T06 | 2000-05-29 | Glenbrook Substation | Reconductor two 115-kV transmission line sections: line 1880 from Glenbrok 1K substation to Rowayton Junction and line 1890 from Glenbrook 1K to Ely Ave. | 2002-05-31
NEP-00-T13 | 2000-05-24 | Litchfield Street Substation | Install a new 115/13.8 kV substation at Litchfield Street. | 2001-12-31
NEP-00-T14 | 2000-05-24 | Point Street Substation | Install a New 115/12.47 kV substation at Point Street. | 2000-12-31
BE-98-T05 Rev.2 | 2000-05-08 | West Medway #446 345 kV switchyard | Modify/upgrade facilities at West Medway #446 345 kV switchyard wih the replacement of 345 kV breakers, associated disconnect switches and other misc. equipment. | 2000-05-08
UI-00-T01 | 2000-05-04 | East Main Street Substation | Relocation of East Main Street Substation. | 2001-06-30
VELCO-00-G01 | 2000-05-03 | Sandbar Substation | Installation of 25 MVA generator (former NRG owned, Somerset Jet #1), to maintain VELCO 115 kV voltage at Sandbar substation. | 2000-05-31
VELCO-00-T03 | 2000-05-03 | Sandbar Substation | Transmission facilities related to the installation of the 25 MVA former Somerset Jet #1 at the Sandbar 115 kV substation. | 2000-05-31
NU-00-T05 | 2000-05-01 20:00 | Merrimack Substation | Replace/upgrade or make a parallel addition to the 230/115 kV transformer at the Merrimack Substation to provide 300 MVA of summer LTE transformation capacity. | 2002-05-31 20:00
NU-00-X01 | 2000-05-01 20:00 | Merrimack Substation | Add one new NPCC Type III SPS at the Merrimack Substation to monitor loading on the Merrimack autotransformer so as to trip an AES Londonderrry unit whenever an overload condition is detected on the Merrimack autotransformer. | 2001-11-30 19:00
NEP-00-G02 | 2000-05-01 | Hope Energy (RISE) | Contruct a new combined cycle generating plant consisting of two combustion turbine generators and one steam turbine generator. | 2001-05-31
NEP-00-T07 | 2000-05-01 | Drumrock | Replace terminal equipment (circuit breakers, disconnect switches, buswork) on 115 kV line S171S and T-172S at Drumrock, and reduce local breaker failure clearing time for all six 115 kV circuit breakers at Drumrock. | 2001-05-31
NEP-00-T08 | 2000-05-01 | Woonsocket | Replace terminal equipment (circuit breakers, buswork) on 115 kV lines S-171N and T-172N at Woonsocket. | 2001-05-31
NEP-00-T09 | 2000-05-01 | Hartford Avenue | Replace two 115 kV circuit breakers (S171S and T172S) at Hartford Avenue to provide Independent Pole Tripping capability. | 2001-05-31
NEP-00-T10 | 2000-05-01 | Drumrock to Kent County | Reconductor 1.0 mile of 115 kV line G-185N from Drumrock to Kent County with 795 ACSR. | 2001-05-31
NEP-00-T11 | 2000-05-01 | W. Farnum and Riverside | Reconductor 1.9 miles of 115 kV line H-17 between W. Farnum and Riverside with 795 ACSR. | 2001-05-31
NEP-00-T12 | 2000-05-01 | Hope Energy / Hartford Ave. to Drumrock | Construct two tap lines from 115 kV lines S-171S and T-172S to the Hope Energy site, and construct a four breaker ring bus substation to terminate the two transmission lines and the two generator step-up transformers. | 2001-05-31
SNE-00-RR01 | 2000-04-25 | Edgar Jet No. 1 | Retirement of Edgar Jet No. 1. | 2000-07-25
SNE-00-RR02 | 2000-04-25 | Edgar Jet No. 2 | Retirement of Edgar Jet No. 2. | 2000-07-25
VELCO-00-T02 | 2000-04-17 | Sand Bar Switching Station | Installation of a 25 MVAR capacitor bank at Sand Bar Switching Station. | 2000-05-31
PDC-00-G01 | 2000-04-10 20:00 | Meriden Power Units 1 and 2 | Installation of two-unit Meriden Power project totaling 575 MW winter / 535 MW summer | 2002-05-31 20:00
PDC-00-G01 Rev.1 | 2000-04-10 20:00 | Meriden Power Units 1 and 2 | Installation of two-unit Meriden Power project totaling 575 MW winter / 535 MW summer This resubmittal indicates a CHANGE in DESIGN to GE from ABB | 2003-05-31 20:00
NU-00-T04 | 2000-04-10 | Southington 4C | Upgrade 345 kV terminal at Southington 4C to match the conductor rating; install 3-breaker substation at Southington to Haddam Neck 362 line; add a 2% reactor at both the Southington to Canal 1950 line and the Southington to Todd 1910 line. | 2002-06-29
CMEEC-00-RR01 | 2000-04-05 20:00 | A. L. Pierce | Retirement of A. L. Pierce unit | 2000-06-30 20:00
BHE-00-RR01 | 2000-04-03 | Graham Unit 4 | Retire Graham Unit 4. | 2000-03-29
BHE-00-RR02 | 2000-04-03 | Graham Unit 5 | Retire Graham Unit 5. | 2000-03-29
CMP-00-G01 | 2000-04-03 | Portsmouth Naval Shipyard | Replace a 3.5 MW Steam Turbine-Generator with a 5.3 MW Gas Turbine-Generator at the Portsmouth Naval Shipyard. | 2000-11-16
NU-00-T01 | 2000-04-03 | Long Mountain Substation | Add two 345 kV breakers at the Long Mountain substation. | 2001-02-28
NSTAR-00-T02 | 2000-04-02 | Canton Substation | Install additional 40 MVA 115/13.8 kV Transformer at Station 470 Canton | 2000-06-30
NU-00-T02 | 2000-03-27 | Scobie Substation | Add on 115 kV circuit breaker at the Scobie Substation. | 2000-11-30
NU-00-T03 | 2000-03-27 | Scobie and Deerfield Substations | Replace six 345 kV wave traps at the Scobie and Deerfield Substations; upgrade protection systems on the 345 kV 385 and 391 lines. | 2000-11-30
CMP-99-T03 Rev.1 | 2000-03-08 | Quaker Hill Substation | Rebuild approximately ten (10) miles of Section 140 from Maguire Road to Quaker Hill Substation utilizing 1113 ACSR conductor. | 2000-12-31
NSTAR-00-T01 | 2000-03-08 | North Cambridge Station #509 | Addition of a 115 kV 80 MVAr shunt reactor at Station #509 in North Cambridge. | 2000-04-30
UI-00-G01 | 2000-02-23 | English 7 | Reactivate English Station Unit 7. | 2000-05-31
UI-00-G02 | 2000-02-23 | English 8 | Reactivate English Station Unit 8. | 2000-05-31
NEP-00-T01 | 2000-02-06 | Johnston Substation | Tap S-171S Johnston tap line and install two 115 kV Airbreak switches, a 115 kV circuit switcher and one 24/32/40 MVA transformer. | 2001-05-31
BHE-00-T01 | 2000-01-30 | Orrington Substation, Line 65 | Rerate existing Line 65 from Orrington Substation to the Bucksport town line, which is the BHE share of this line. | 2000-01-31
BHE-00-T02 | 2000-01-30 | Orrington Substation, Line 205 | Rerate existing Line 205 from Orrington Substation to the Bucksport town line, which is the BHE share of this line. | 2000-02-29
BHE-00-T03 | 2000-01-30 | Orrington Substation, Line 248 | Rerate existing Line 248 from Orrington Substation to the Graham Substation. | 2000-03-31
BHE-00-T04 | 2000-01-30 | Orrington Substation, Line 249 | Rerate existing Line 249 from Orrington Substation to the Graham Substation. | 2000-03-31
VELCO-00-T01 | 2000-01-30 | Williston Substation | Replace 230-3 115 kV circuit switcher at Williston Substation with a circuit breaker. | 2000-03-30
RMLD-00-T01 | 2000-01-11 | North Reading Substation | New 115kV substation with taps off NEES transmission circuits S-145 and T-146 in the town of North Reading. | 2000-05-31
CMP-00-T01 | 2000-01-04 | Androscoggin | Add two 115/13.8 kV transformers at Androscoggin Energy Center to connect to International Paper in Jay, Maine. | 2000-01-31
NRGPM-99-RR-578 | 2000-01-03 | Somerset Jet 1 | Retirement of Somerset Jet 1. | 2000-03-05
NRGPM-99-RR-579 | 2000-01-03 | Somerset Jet 2 | Retirement of Somerset Jet 2. | 2000-03-05
NEP-99-T16 | 1999-12-30 | Brayton Point Substation | Rebuild Brayton Pt. 345 kV Switchyard using breaker and 1/2 design. | 2004-10-02
NEP-99-X02 | 1999-12-30 | Brayton Point Substation | Install Type III SPS at Brayton Pt. 345 kV Substation | 2004-10-02
NEP-99-T15 | 1999-11-14 19:00 | Pinehurst Substation | Tap M-139 line and install a 2nd 24/32/40 MVA 115/13.2 kV transformer and two 115 kV circuit switchers | 2000-05-31 20:00
NEP-99-T14 | 1999-11-01 19:00 | Deerfield Substation | Rebuilding of the 6.8 mile two-wire portion of the I-9/J-10 69 kV Adams - Deerfield (MA) lines to a single-wire line | 1999-10-31 19:00
EUA-99-G01 | 1999-10-26 20:00 | BFGSI Fall River Electric | New 7.45 MW landfill gas generator to be built by Browning Ferris Gas Services, Inc. | 1999-11-30 19:00
SP-99-T01 | 1999-10-20 20:00 | Somerset Generating Station | Replace 078 115 kV breaker at Somerset Generating Station | 2000-02-29 19:00
BE-99-T05 | 1999-10-12 20:00 | Mystic - Kingston Street Stations | New 345 kV line between Mystic station and Kingston Street station
BE-99-T06 | 1999-10-12 20:00 | Kingston Street station | New 345/115 kV autotransformer at Kingston Street station
BE-99-T07 | 1999-10-12 20:00 | K Street station | New 115 kV 80 MVAR shunt reactor at K Street station
BE-99-T08 | 1999-10-05 20:00 | North Cambridge autotransformer | Replacement of the current North Cambridge 345B autotransformer with a new autotransformer. | 1999-10-31 19:00
NEP-99-T11 | 1999-09-30 20:00 | Millbury Substation | 69 kV Substation | 2000-11-30 19:00
CMP-99-T03 | 1999-09-29 20:00 | Quaker Hill Substation | Rebuild 10 miles of Section 140 from Maguire Rd. to Quaker Hill Substation | 2000-12-31 19:00
EUA-98-G01 | 1999-09-23 20:00 | Tiverton Units 1 & 2 | Modification of conditions for approval of EUA-98-G01 to remove requirement to replace two EUA breakers at Somerset Station and add requirement to replace OCB 078 at Somerset Power | 1999-11-30 19:00
NEP-99-T08 | 1999-09-14 20:00 | Vernon and Deerfield 4 Substations | Convert double circuit 69 kV lines to single circuit | 2000-09-30 20:00
NEP-99-T09 | 1999-09-14 | East Webster Substation | Reconductor 69 kV line | 2000-05-31
NEP-99-T12 | 1999-09-13 20:00 | Burtt Road Substation | Tap T-146 line and install a new substation with a 115 kV circuit switcher and one 24/32/40 MVA transformer | 2000-03-19 19:00
NEP-99-T13 | 1999-09-13 20:00 | Golden Rock Substation | Tap G-133W line and install a new substation with a 115 kV circuit switcher and one 30/40/50 MVA transformer | 2001-01-14 19:00
NEP-99-T04 | 1999-09-09 20:00 | Sandy Pond Substation | Addition of one 115 kV Circuit Breaker | 1999-12-30 19:00
CMP-99-G02 | 1999-09-07 20:00 | Westbrook Units 1, 2, 3 | New 578 MW generation plant | 1999-12-31 19:00
CMP-99-G02 Rev.1 | 1999-09-07 20:00 | Westbrook Units 1, 2, 3 | New 578 MW generation plant | 2000-12-31 19:00
CMP-99-T05 Rev.2 | 1999-09-07 20:00 | Spring Street Substation, Westbrook Substation, So | Add new breakers, rebuild transmission line and add new transmission line to accommodate new Westbrook Energy Center plant | 2000-05-31 20:00
CMP-99-G04 | 1999-09-02 20:00 | Bucksport Unit 1 | Add 174 MW generating plant to 115 kV system at Champion International Corp. | 2000-10-31 19:00
CMP-99-G04 Rev.1 | 1999-09-02 20:00 | Bucksport Unit 1 | Add 174 MW generating plant to 115 kV system at Champion International Corp. | 2000-10-31 19:00
CMP-99-G04 Rev.2 | 1999-09-02 20:00 | Bucksport Unit 1 | Add 174 MW generating plant to 115 kV system at Champion International Corp. | 2000-10-31 19:00
CMP-99-T06 | 1999-09-02 20:00 | Bucksport Substation | Connect generator lead with 115 kV system at Champion International Corp. | 2000-03-31 19:00
CMP-99-T06 Rev.3 | 1999-09-02 20:00 | Bucksport Energy | Connect generator lead with 115 kV system at Champion International Corp. | 2000-03-31 19:00
NU-99-T09 | 1999-09-02 | Newington Energy | Transmission upgrades to interconnect the Newington Energy Project | 2002-04-30
CMP-99-G03 | 1999-09-01 20:00 | Gorham Units 1, 2 & 3 | New 850 MW generation plant at Buxton Sta. | 2001-11-30 19:00
CMP-99-G03 Rev.1 | 1999-09-01 20:00 | Gorham Units 1, 2 & 3 | New 850 MW generation plant at Buxton Sta. | 2001-11-30 19:00
CMP-99-T04 | 1999-09-01 20:00 | Buxton Substation / Gorham Energy | 10 mile 345 kV circuit from Buxton Sta. to Gorham Energy Project | 2000-11-30 19:00
CMP-99-T04 Rev.2 | 1999-09-01 20:00 | Buxton Substation / Gorham Energy | 10 mile 345 kV circuit from Buxton Sta. to Gorham Energy Project | 2000-11-30 19:00
EUA-99-T02 | 1999-09-01 20:00 | Sherman Road Station | Upgrade 345 kV Breaker #141 at Sherman Road Station | 2000-01-31 19:00
NEP-97-T07 | 1999-09-01 20:00 | Carpenter Hill | Carpenter Hill 115 kV Switchyard and Type III SPS | 1999-09-30 20:00
NEP-99-T06 | 1999-09-01 20:00 | ANP Milford | Addition of one 115 kV circuit breaker | 1999-08-31 20:00
NEP-99-T10 | 1999-09-01 20:00 | Narragansett Blackburn Substation / Amtrak Warwick | Two 115 kV taps to supply Amtrak traction power system
CONED-99-G01 | 1999-09-01 | Newington Energy Units 1 and 2 | New 525 MW generating plant. | 2002-04-30
CMP-99-X01 | 1999-08-31 20:00 | Maxcys | Modify Maxcys SPS timer
NEP-98-T08-B | 1999-08-25 20:00 | ANP-Bellingham | Reconductor 2.2 mi. of 345 kV line between W. Medway and ANP-Bellingham
BE-98-T02-A | 1999-08-24 20:00 | ANP-Blackstone | Upgrade facilities for ANP Blackstone
BE-98-T02-B | 1999-08-24 20:00 | West Medway to NEA tap | Reconductor 5.5 mi. of 345 kV line between West Medway #446 and the NEA tap
BE-98-T02-C | 1999-08-24 20:00 | ANP Blackstone to NEA tap | Reconductor 2.6 mi. of 345 kV line between ANP-Blackstone tap and NEA tap
EUA-98-T04-A | 1999-08-24 20:00 | Sherman Road Station | Upgrade Sherman Rd. Station facilities for ANP Blackstone | 2000-04-30 20:00
EUA-98-T04-B | 1999-08-24 20:00 | Sherman Road Station | Upgrade Sherman Rd. Station facilities | 2000-04-30 20:00
NEP-98-T08-A | 1999-08-24 20:00 | ANP-Bellingham | Upgrade facilities for ANP Bellingham
NEP-99-T03 | 1999-08-23 20:00 | ANP Milford | Reconductor 115 kV D-130 tap (ANP Milford tap - Depot tap) | 1999-03-31 19:00
MPC-99-G01 | 1999-05-04 20:00 | Milford Power | Construct an 287 MW winter/268 MW summer combined cycle gas/oil plant. | 2000-09-30 20:00
NU-99-T04 | 1999-05-04 20:00 | Milford Power | Associated Transmission Upgrades for Milford Power Plant | 2000-09-30 20:00