## Slide 1
October 17, 2018 | Westborough, ma
Brent Oberlin
Director, Transmission Planning
Planning Advisory Committee Meeting
Regional System Plan Transmission Projects and Asset Condition October 2018 Update

## Slide 2: Table of Contents
    Slide
Highlights 3
October 2018 Changes 4 – 14
Status of Major Transmission Projects 15 – 16
October Asset Condition Changes 17 – 19
Appendix 20 – 26

## Slide 3: Highlights of the Project List Update
Major cost estimate changes that occurred between the June 2018 and October 2018 Project List:
  (CT) – GHCC – Project 1590 - Add 115 kV 3.7 mile hybrid overhead/underground line from Newington to Southwest Hartford and associated terminal equipment including 1.4% series reactor. (project cost decreased $29.8M). Work on this project has been revised from an all underground line to a hybrid overhead/underground line.
  2 New Projects (MA) Southeast SEMA/RI Reliability Project – West Medway 345 kV circuit breaker upgrades (MA) Southeast SEMA/RI Reliability Project – Medway 115 kV circuit breaker replacements
  12 Upgrades on the project list have been placed in-service since the June 2018 update: (CT) SWCT- 4 projects in-service (CT) GHCC – 3 projects in-service (MA) 1779 line partial rebuild (MA) Greater Boston - 1 project in-service – X-24/E-157W DCT separation (MA) SEMA/RI – 1 project in-service – Reconductor/upgrade 112 line Tremont Substation #713 to Industrial Tap and terminal equipment (MA) Sandy Pond Substation refurbishment (MA) Sandy Pond control house rebuild
3

## Slide 4: October 2018 Changes, cont.
Project ID # | Transmission System Upgrades | Cost (in millions $) | Improvement/Need
1789 | West Medway 345 kV Circuit Breaker Upgrades (Massachusetts) Southeast Massachusetts/Rhode Island Reliability Project | 6.3 | Upgraded to meet system short circuit levels
1790 | Medway 115 kV Circuit Breaker Replacements (Massachusetts) Southeast Massachusetts/Rhode Island Reliability Project | 4.9 | Upgraded to meet system short circuit levels
2 New Projects and Corresponding Need

## Slide 5: October 2018 Changes, cont.
12 Projects Placed In-Service and Corresponding Needs
Project ID # | Transmission System Upgrades | Cost (in millions $) | Improvement/Need
1564 | Install a new 115 kV line from Plumtree to Brookfield Junction (3.4 miles) (Connecticut) SWCT | 20.1 | Addresses N-1 interruption concerns in the SWCT area
1568 | Loop the 1570 line in and out of Pootatuck Substation (Connecticut) SWCT | 1.8 | Improve load serving capability in the SWCT area
1578 | Install a synchronous condenser (+25/-12.5 MVAR) at Stony Hill (Connecticut) SWCT | 22.2 | Resolve voltage issues in the Housatonic Valley area
1621 | Pootatuck 115 kV Ring Bus Expansion and Capacitor Bank Addition (Connecticut) SWCT | 11.0 | Improve load serving capability in the SWCT area and resolves low voltage issues
1584 | Separation of 115 kV DCT corresponding to the Frost Bridge to Campville (1191) line and the Thomaston to Campville (1921) line and add a breaker at Campville 115 kV substation (Connecticut) GHCC | 5.5 | Improve load serving capability in the Northwest Connecticut area

## Slide 6: October 2018 Changes, cont.
12 Projects Placed In-Service and Corresponding Needs
Project ID # | Transmission System Upgrades | Cost (in millions $) | Improvement/Need
1593 | Add a 115 kV 25.2 MVAR capacitor at Westside 115 kV substation (Connecticut) GHCC | 2.9 | Improve load serving capability in the GHCC area
1603 | Redesign the Green Hill 115 kV substation from a straight bus to a ring bus and add two 25.2 MVAR capacitor banks (Connecticut) GHCC | 11.5 | Improve load serving capability in the GHCC area
1606 | 1779 Line Partial Rebuild (Connecticut) | 26.6 | Resolves asset condition issues
1330 | X-24/E-157W DCT Separation (Massachusetts) Greater Boston – Western Suburbs | 2.4 | Resolves thermal overloads
1734 | Reconductor/Upgrade 112 Line Tremont Substation #713 to Industrial Tap and terminal equipment (Massachusetts) Southeast MA/RI Reliability Project | 4.8 | Resolves thermal overloads

## Slide 7: October 2018 Changes, cont.
12 Projects Placed In-Service and Corresponding Needs
Project ID # | Transmission System Upgrades | Cost (in millions $) | Improvement/Need
1526 | Sandy Pond Substation refurbishment (Massachusetts) Sandy Pond Asset Condition | 14.1 | Resolves asset condition issues
1489 | Sandy Pond control house rebuild (Massachusetts) Sandy Pond Asset Condition | 12.6 | Resolves asset condition issues

## Slide 8: October 2018 Changes, cont.
Cost Estimate Comparisons of Reliability Projects
June 2018 vs. October 2018 Update (1)
(1) Transmission Owners provided all estimated costs, which may not meet the guidelines described in Planning Procedure 4, Attachment D
(2) May not sum exactly due to rounding
(3) The cost estimates for projects in the "Major Projects" category are moved to the "Other Projects" category once they are fully completed.

## Slide 9: October 2018 Changes, cont.
Note: Numbers shown represent project quantities
Investment of New England Transmission Reliability Projects by Status through 2022
Note: Future total $ are shown at the end of the project. Totals do not reflect or show phasing in over time or the depreciation of prior projects. Total costs are associated with the year projects are placed in-service as reported in the Project List.

## Slide 10: October 2018 Changes, cont.
Cumulative Investment of New England Transmission Reliability Projects through 2026
Note: Future total $ are shown at the end of the project. Totals do not reflect or show phasing in over time or the depreciation of prior projects. Total costs are associated with the year projects are placed in-service as reported in the Project List.
Note: UC – Under Construction, PL – Planned, PR – Proposed

## Slide 11: October 2018 Changes, cont.
Reliability Project Counts and Aggregated Cost Estimates by Project Stage with Applied Accuracy Ranges (1)
(1) All costs provided by Transmission Owners. The costs in the table reflect all projected in-service dates
(2) Efforts need to be made to describe projects on a more consistent basis
(3) All estimates may not yet be at this level of accuracy; many estimates may be -25%/+50%
(4) Not included here are the costs of reliability projects for which no estimates have been provided. Estimates for these projects are noted as TBD in the Project Listing and are only Concept Projects.
(5) May not add up due to rounding.

## Slide 12: October 2018 Changes, cont.
Note: Future total $ are shown at the end of the project. Totals do not reflect or show phasing in over time or the depreciation of prior projects. Total costs are associated with the year projects are placed in-service as reported in the Project List.
Project Cost Estimate Tolerances by Status and Year in Millions $

## Slide 13: October 2018 Changes, cont.
Project Cost Estimate Tolerances by Status and Year in Millions $
Note: Future total $ are shown at the end of the project. Totals do not reflect or show phasing in over time or the depreciation of prior projects. Total costs are associated with the year projects are placed in-service as reported in the Project List.

## Slide 14: October 2018 Changes, cont.
Project Cost Estimate Tolerances by Status and Year in Millions $
Note: Future total $ are shown at the end of the project. Totals do not reflect or show phasing in over time or the depreciation of prior projects. Total costs are associated with the year projects are placed in-service as reported in the Project List.

## Slide 15: Status of Major Transmission Projects
 | PPA | TCA | Construction
Pittsfield/Greenfield Project | Approved 12/12, 01/16, 05/16 | Partial 2/11/16, 7/17/17 | Project completion 2014-2020
Maine Power Reliability Program (MPRP) | Approved 7/08, 2/09, 11/10 | Approved 1/29/10 | Project completion 2014-2018
Vermont Solution – Connecticut River Valley | Approved 4/15 | Approved 12/1/17 | Project completion 2016-2018
Southwest Connecticut (SWCT) | Approved 4/15 | Partial 7/16/15, 4/15/16, 5/13/16, 1/3/18 | Project completion 2013-2020
Southeast MA/RI Reliability | Approved 5/17, 4/18 | Not Submitted | Project completion 2017-2021

## Slide 16: Status of Major Transmission Projects, cont.
 | PPA | TCA | Construction
Central/Western MA Reinforcements | Approved 12/07, 3/11 | Group 1 2/29/2012 | Project completion 2009-2019
Greater Boston – North, South, Central and Suburbs | Approved 4/15, 5/15, 6/16 | TCA Submitted | Project completion 2013-2021
New Hampshire Solution – Western, Central, Southern and Seacoast | 3/13 | Seacoast 11/5/15 Southern 1/7/16 Western 12/17/15 Central 11/25/15 | Project completion 2013-2020
Greater Hartford & Central Connecticut (GHCC) | 4/15 | Partial 10/4/2016 | Project completion 2015-2019

## Slide 17: October 2018 Asset Condition
Project ID # | Transmission System Upgrades | Cost (in millions $)
90 | Canal Station #980 BPS and Asset Condition Upgrades Project (Massachusetts) | 17.9
91 | Railroad Corridor Transmission Line Asset Condition Upgrades (Connecticut) | 376.3
92 | Robinson Avenue Station #102 Asset Condition Upgrades (Massachusetts) | 8.3
3 New Projects

## Slide 18: October 2018 Asset Condition, cont.
3 Projects Placed In-Service
Project ID # | Transmission System Upgrades | Cost (in millions $)
51 | Replace the Deerfield TB-14 autotransformer and bus upgrades to accommodate new transformer specifications (New Hampshire) | 5.3
48 | Southern CT Loop Line Structure Replacements - 1508 115 kV (Connecticut) | 15.9
45 | 345 kV 354 Line Structure Replacements (Massachusetts) | 7.0

## Slide 19: October 2018 Changes, cont.
Cumulative Investment of New England Transmission Reliability Projects and Asset Condition through 2026
Note: Future total $ are shown at the end of the project. Totals do not reflect or show phasing in over time or the depreciation of prior projects. Total costs are associated with the year projects are placed in-service as reported in the Project and Asset Condition Lists.
Note: RSP - UC – Under Construction, PL – Planned, PR – Proposed, IS – In-service Asset Condition - AUC – Under Construction, APL – Planned, APR – Proposed, AIS – In-service

## Slide 20: Appendix

## Slide 21: Summary: Project Listing Definitions
ISO New England Inc. Transmission, Markets and Services Tariff Section II
  Attachment K, Regional System Planning Process
    Definition of Needs Assessment
    Definition of Solution Studies
  Project Listing Subcategories
    Concept: shall include a transmission project that is being considered by its proponent as a potential solution to meet a need identified by the ISO in a Needs Assessment or the RSP, but for which there is little or no analysis available to support the transmission project. (Project not well-defined, costs not well-defined, solution implementation not supportable).
    Proposed: The project will include a regulated transmission solution that has been proposed in response to a specific Needs Assessment on the RSP and has been evaluated or further defined and developed in a Solutions Study and communicated to PAC. (Project well-defined, cost estimate quality sufficient for comparison of alternatives).
    Planned: The project will include a Transmission upgrade that has been approved by the ISO, pursuant to Section I.3.9 (presumes Needs Assessment and Solutions Study have been completed). (Still subject to Schedule 12C review for Transmission Cost Allocation)

## Slide 22: Project Listing
Project Listing Column
Definitions for:
  Reliability Projects
  Interconnection Projects
  Market Efficiency Upgrades
  Elective Projects
  Projects In-Service
  Cancelled Projects

## Slide 23: Project Listing – Column Definitions
Part Number (Part #)
  The Part #’s designate the ‘need’ category of the project. Original categories are not changed when a project is placed ‘In-Service’ or ‘Cancelled’.
  Part 1 – These projects are Reliability Upgrades.
    1a: Planned or Under Construction
    1b: Concept or Proposed
  Part 2 – These projects are Generator Interconnection Upgrades.
    2a: Planned (I.3.9 approval with Generator Interconnection Agreement including FCM related transmission upgrades to meet the Capacity Capability Interconnection Standard), or Under Construction
    2b: Concept or Proposed (at a minimum, a completed System Impact Study and I.3.9 approval but no Generator Interconnection Agreement)
  Part 3 – These projects are Market Efficiency Upgrades.
    3a: Planned or Under Construction
    3b: Concept or Proposed
  Part 4 – These projects may be promoted by any entity electing to support the cost of transmission changes. The entity sponsoring the changes will have their own justification for their actions.
    4a: Planned or Under Construction
    4b: Concept or Proposed

## Slide 24
Project ID
  This number is generated from ISO-NE System Planning Information Tracking System. It may change in the future as the tracking system evolves.
Primary Equipment Owner
  The company listed here is the responsible equipment owner / provider designated to design and implement the project.
Other Equipment Owner
For projects that involve multiple Transmission Owners, the company listed here is also a responsible equipment owner / provider designated to design and implement the project.
Projected Month/Year of In-Service
  The month/year entered is the date the project is expected to be placed in service.
Major Project
Name given to a project that consists of smaller subprojects.
Project / Project Component
  A brief, high-level description of the project is entered here. It will either include major pieces of substation equipment and/or types of line work to be performed.
Project Listing – Column Definitions, cont.

## Slide 25
Status
  In Service: The project has been placed in operation.
  Under Construction: The project has received necessary approvals and a significant level of engineering or construction is underway.
  Planned: The project will include a Transmission upgrade that has been approved by the ISO.
  Proposed: The project will include a regulated transmission solution that has been proposed in response to a specific Needs Assessment on the RSP and has been evaluated or further defined and developed in a Solutions Study and communicated to PAC.
  Concept: Shall include a transmission project that is being considered by its proponent as a potential solution to meet a need identified by the ISO in a Needs Assessment or the RSP, but for which there is little or no analysis available to support the transmission project.
  Cancelled: Project has been cancelled.
Project Listing – Column Definitions, cont.

## Slide 26
PPA Approval (Review of Market Participant’s Proposed Plans)
  A date in this column signifies when the project received approval pursuant to Section I.3.9 of the ISO-New England Tariff. This approval indicates that the project will have no adverse impact on the stability, reliability, or operating characteristics of the system. A ‘no’ indicates that an approval is required, but has not been received yet. An ‘NR’ indicates that an I.3.9 approval is not required.
TCA Approval (Transmission Cost Allocation)
  A date in this column signifies when the project PTF costs were reviewed and approved. This approval indicates that it has been agreed whether, and by how much, the scope of the project and associated costs exceed regional needs. An ‘NR’ indicates that a TCA approval is not applicable either because the project has been cancelled or no/very minimal PTF costs are involved.
Estimated Costs
  The pool-supported project cost estimate presented here should be the best estimate available. It is understood that the estimate accuracy may vary dependent on the maturity of the project.
  Accuracy tolerances for these estimates are targeted as follows:
  Concept Project
  Proposed Project that has been reviewed and approved to proceed by ISO-NE (+50%/-25%),
  I.3.9-Approved Project (+/-25%), and
  TCA-Approved Project (+/-10%)
Project Listing – Column Definitions, cont.