## ISO-NE Project Listing Upd copy (hidden)
April '10 ISO-NEW ENGLAND Project Listing Update (DRAFT)
Primary Driver | Part# | Project ID | Primary Equipment Owner | Other Equipment Owner(s) | Projected In-Service Month/Year | Major Project | Project | Oct-07 Status | Apr-08 Status | Jul-08 Status | Oct-08 Status | Apr -09 Status | Jul-09 Status | Oct-09 Status | Apr-10 Status | PPA (I.3.9) Approval | TCA Approval | Oct-07 Estimated Costs | Apr-08 Estimated PTF Costs | Jul-08 Estimated PTF Costs | Oct-08 Estimated PTF Costs | Apr-09 Estimated PTF Costs | Jul-09 Estimated PTF Costs | Oct-09 Estimated PTF Costs | Apr-10 Estimated PTF Costs | Column T | DELTA | Status Change
TABLE A | [26 empty] | Column T - Column S
MAINE
Reliability Upgrade | 1a | 144 | Bangor Hydro-Electric Company |  | 12/2010 | Keene Rd Autotransformer | Installation of a 345/115 kV autotransformer at Keene Rd Substation. | Concept | Concept | Concept | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | No | No | 20000000 | 20000000 | 20000000 | 20000000 | 29000000 | 29000000 | 29000000 | 29000000 | 29000000 | 0 | 0
Reliability Upgrade | 1a | 625 | Central Maine Power Company |  | 04/2010 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Rumford Industrial Park capacitor bank. | Proposed | Concept | Planned | Planned | Planned | Planned | Under Construction | Under Construction | 2007-11-30 | No | TBD | TBD | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 0 | 0
Reliability Upgrade | 1a | 1128 | Central Maine Power Company |  | 07/2010 | CMP-LSP Hotel Road Substation | Add 115/34kV transformer with 115kV breaker at Hotel Rd. |  |  |  |  | Planned | Planned | Planned | Planned | 2008-08-20 | NR | TBD | TBD | Portion of 5,400,000 (above) |  | 800000 | 800000 | 800000 | 800000 | 800000 | 0 | 0
Reliability Upgrade | 1a | 624 | Central Maine Power Company |  | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (New Page - Rumford Industrial Park) | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2007-11-30 | No | TBD | TBD | Portion of 5,400,000 (above) | Portion of 5,400,000 (above) | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 | Part of project 625 |  | 0
Reliability Upgrade | 1a | 905 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-07-31 | 2010-01-29 | TBD | TBD | 1354000000 | 1354000000 | 1510000000 | 1510000000 | 1510000000 | 1510000000 | 1510000000 | 0 | 0
Reliability Upgrade | 1a | 906 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Coopers Mills-Highland, Larrabee Road-Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | 0
Reliability Upgrade | 1a | 907 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 84 (Albion Road-Coopers Mills), Section 203 (Detroit-Orrington), Section 80 (Coopers Mills-Highland), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | 0
Reliability Upgrade | 1a | 908 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road) | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | 0
Reliability Upgrade | 1a | 909 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | 0
Reliability Upgrade | 1a | 1025 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377 & Maine Yankee 375/392, 115kV Bucksport 65/205) and Maine Yankee 345 kV re-termination | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | 0
Reliability Upgrade | 1a | 1026 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Three Rivers) | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | $70,000,000 (NU portion of MPRP) | $70,000,000 (NU portion of MPRP) | Portion of CMP $1.51B and portion of NU is $35.1M | Portion of CMP $1.51B and portion of NU is $35.1M | Portion of CMP $1.51B and portion of NU is $35.1M | Portion of CMP $1.51B and portion of NU is $36.0M | 36000000 | 900000 | 0
Reliability Upgrade | 1a | 1027 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV Line Construction (Elm Street-East Deering, East Deering -Cape) | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | 0
Reliability Upgrade | 1a | 1028 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Portion of CMP $1.354B and portion of NU $70M | Portion of CMP $1.354B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD |  | 0
Reliability Upgrade | 1a | 1029 | Central Maine Power Company |  | 11/2010 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformer at South Gorham | Concept | Concept | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | 0
Reliability Upgrade | 1a | 1158 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Two 40 MVAR reactors at Albion Road, two 40 MVAR reactors at Larabee Road, two 40 MVAR at Coopers Mills | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | 0
Reliability Upgrade | 1a | 1030 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Raven Farm, Maguire Road) | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 7/31/2008 & 2/26/09 | 2010-01-29 | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program |  | 0
Reliability Upgrade | 1a | 143 | Bangor Hydro-Electric Company |  | 12/2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation to Harrington Substation. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2006-05-10 | 2008-06-13 | 45000000 | 66100000 | 66100000 | 66100000 | 66100000 | 66100000 | 66100000 | 66100000 | 66100000 | 0 | 0
Reliability Upgrade | 1a | 1129 | Central Maine Power Company |  | 05/2012 |  | New 115kV line between Wyman Hydro and Heywood Rd. parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | Concept | Concept |  | Planned | Planned | Planned | Planned | 2009-01-26 | No | 10100000 | 10100000 | 6100000 |  | 19500000 | 19500000 | 19500000 | 32800000 | 32800000 | 13300000 | 0
Reliability Upgrade | 1a | 1144 | Central Maine Power Company |  | 09/2010 | Heywood Road Project | Circuit switcher replacements at Detroit, Lakewood, Rice Rips and Winslow | Concept | Concept | Concept | Concept |  | Under Construction | Under Construction | Under Construction | 2009-03-20 | 2009-07-20 | TBD | TBD | TBD | TBD |  | Part of Heywood Road Project | Part of Heywood Road Project | Part of Heywood Road Project | Part of the Heywood Road Project |  | 1
Generator Interconnection Upgrade | 2a | 770 | Central Maine Power Company |  | 12/2010 | Queue Position 137 | Installation of New Page Substation (aka Railroad Street Substation) with (3) circuit breakers tapping Section 218 115kV. | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | 2007-03-18 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1159 | Central Maine Power Company |  | 07/2010 | Queue Position 197 | Add a new 115kV breaker and new 115kV line termination at the former T2 position at Rumford 115kV substation | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed |  | Planned | 2009-09-29 | NR | NR | NR | NR | NR | NR | NR |  | NR | NR |  | 0
NEW HAMPSHIRE | [27 empty] | 0
Reliability Upgrade | 1a | 277 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Proposed | Concept | Concept | Concept | Concept | Planned | Planned | Planned | 2009-06-29 | No | TBD | TBD | TBD | TBD | TBD | 56600000 | 56600000 | 56000000 | 56000000 | -600000 | 1
Reliability Upgrade | 1a | 1137 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115kV breakers and add 1-115kV breaker at Deerfield Substation | [5 empty] | Planned | Planned | Planned | 2009-06-29 | No | TBD | TBD | TBD | TBD |  | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project |  | 1
Reliability Upgrade | 1a | 1138 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rebuild 115kV L175 line | [5 empty] | Planned | Planned | Planned | 2009-06-29 | No | TBD | TBD | TBD | TBD |  | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project |  | 1
Reliability Upgrade | 1a | 1139 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV M183 Line | [5 empty] | Planned | Planned | Planned | 2009-06-29 | No | TBD | TBD | TBD | TBD |  | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project |  | 1
Reliability Upgrade | 1a | 1140 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | [5 empty] | Planned | Planned | Planned | 2009-06-29 | No | TBD | TBD | TBD | TBD |  | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project |  | 1
Reliability Upgrade | 1a | 1141 | Northeast Utilities |  | 2015 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | [5 empty] | Planned | Planned | Planned | 2009-06-29 | No | TBD | TBD | TBD | TBD |  | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project |  | 1
Reliability Upgrade | 1a | 680 | National Grid, USA |  | 03/2013 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2008-01-28 | No | 11497000 | 11497000 | 11497000 | 11497000 | 11497000 | 11497000 | 7393000 | 7393000 | 7393000 | 0 | 0
Reliability Upgrade | 1a | 674 | National Grid, USA |  | 12/2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-01 | No | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 7720000 | 22115000 | 22115000 | 14395000 | 0
Elective | 4a | 1142 | FPL New England Division |  | 04/2011 |  | Seabrook Station Reconfiguration and Circuit Breaker addition Stage s 1 & 2 | Concept | Concept | Concept | Concept |  | Planned | Planned | Planned | 2008-11-20 | NR | TBD | TBD | TBD | TBD |  | TBD | NR | TBD | TBD |  | 1
Generator Interconnection Upgrade | 2a | 724 | National Grid, USA |  | TBD | NGRID Comerford Substation | NGRID Comerford Substation. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2007-06-12 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
VERMONT | [27 empty] | 0
Reliability Upgrade | 1a | 139 | Vermont Electric Power Company |  | 12/2015 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Under Construction | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 01/10/2003 | 03/31/2003 | 11000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 20000000 | 0 | 0
Reliability Upgrade | 1a | 1145 | Vermont Electric Power Company |  | 12/2010 | Burlington Gorge Project | Installation of a 3-breaker 115kV ring substation and 115/34.5kV transformer on the East Ave. - Tafts Coners 115kV line | Planned | Planned | Planned | Planned | Under Construction |  | Planned | Planned | 10/24/2006 | No | 30000000 | 25142000 | 25142000 | 25142000 | 25142000 |  | 14000000 | 14000000 | 14000000 | 0 | 1
Reliability Upgrade | 1a | 323 | Vermont Electric Power Company |  | 12/2010 | Vermont Southern Loop Project | New VY - Newfane - Coolidge 345 kV line with requisite station upgrades. | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | 2008-10-01 | No | 200000000 | 135300000 | 135300000 | 135300000 | 136368000 | 136368000 | 136368000 | 136368000 | 136368000 | 0 | 0
Reliability Upgrade | 1a | 1032 | Vermont Electric Power Company |  | 09/2010 | Vermont Southern Loop Project | Installation of a new 345/115kV substation called Vernon including a new 345/115kV autotransformer | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | 2008-10-01 | No | Part of Vermont Southern Loop Project | 64600000 | 64600000 | 64600000 | 69815000 | 69815000 | 69815000 | 69815000 | 69815000 | 0 | 0
Reliability Upgrade | 1a | 1033 | Vermont Electric Power Company |  | 12/2010 | Vermont Southern Loop Project (VELCO LSP - Newfane Substation) | Installation of a new 345/115kV substation called Newfane | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | 2008-10-01 | No | Part of Vermont Southern Loop Project | 38500000 | 38500000 | 38500000 | 16664000 | 16664000 | 16664000 | 16664000 | 16664000 | 0 | 0
Reliability Upgrade | 1a | 1034 | Vermont Electric Power Company |  | 12/2010 | Vermont Southern Loop Project | Loop new 345kV Line into Newfane Substation. | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | 2008-10-01 | No | Part of Vermont Southern Loop Project | 18000000 | 18000000 | 18000000 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 | Part of project 323 |  | 0
Reliability Upgrade | 1a | 1035 | Vermont Electric Power Company |  | 12/2010 | Vermont Southern Loop Project | Expansion of Coolidge 345kV substation | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | 2008-10-01 | No | Part of Vermont Southern Loop Project | 18000000 | 18000000 | 18000000 | 20117000 | 20117000 | 20117000 | 20117000 | 20117000 | 0 | 0
Reliability Upgrade | 1a | 1146 | Vermont Electric Power Company |  | 02/2011 | Lyndonville Project | Installation of a 4-breaker ring 115 kV substation consisting of two 115kV 12.5 MVAR capacitor banks and 115/34.5 kV transformer interconnecting to the Irasburg - St. Johnsbury 115kV line | Proposed | Proposed | Proposed | Planned | Under Construction |  | Planned | Planned | 2009-06-01 | No | Part of Vermont Southern Loop Project | 18000000 | 18000000 | 18000000 | 20117000 |  | 9000000 | 9000000 | 9000000 | 0 | 1
Generator Interconnection Upgrade | 2a | 1036 | Vermont Electric Power Company |  | 10/2010 | Queue Position 172 | Installation of 3-breaker 115kV ring bus interconnection of the St. Johnsbury-Irasburg 115kV K39 line. |  | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | 08/16/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
MASSACHUSETTS | [27 empty] | 0
Reliability Upgrade | 1a | 1152 | National Grid, USA |  | 2010-08-01 |  | Bear Swamp - Pratts Jumction 230kV Line Refurbishment Project (E205E) |  |  | Proposed | Planned | Planned |  | Planned | Planned | NR | NR |  |  | TBD | 360000 | 360000 |  | 43596000 | 43596000 | 43596000 | 0 | 1
Reliability Upgrade | 1a | 887 | National Grid, USA |  | 09/2012 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Proposed | Concept | Concept | Planned | Planned | Planned | Planned | Planned | 2008-01-28 | No | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 76000000 | 76000000 | 46000000 | 0
Reliability Upgrade | 1a | 921 | National Grid, USA |  | 06/2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Proposed | Concept | Concept | Planned | Planned | Planned | Planned | Planned | 2008-01-28 | No | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 12100000 | 40000000 | 40000000 | 27900000 | 0
Reliability Upgrade | 1a | 919 | National Grid, USA |  | 12/2012 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Proposed | Concept | Concept | Planned | Planned | Planned | Planned | Planned | 2008-01-28 | No | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 0 | 0
Reliability Upgrade | 1a | 59 | National Grid, USA |  | 06/2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2007-11-01 | 2003-01-31 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | 400000 | Part of RSP 921 | Part of RSP 921 |  | 0
Reliability Upgrade | 1a | 783 | National Grid, USA |  | 03/2011 | Merrimack Valley/North Shore Reliability Project | Extend the 115kV by addition of 115kV Breaker and K-153 line from King St. to W. Amesbury 115kV station. (W. Amesbury 345/115kV Station becomes PTF) | Proposed | Concept | Concept | Concept | Concept | Planned | Planned | Planned | 2008-04-01 | No | 7200000 | 29340000 | 29340000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 30349000 | 0 | 1
Reliability Upgrade | 1a | 779 | National Grid, USA |  | 04/2010 | Merrimack Valley/North Shore Reliability Project | Bypass and remove Golden Hills 345 kV substation. | Proposed | Concept | Concept | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | 2008-04-01 | No | 1600000 | 1600000 | 1600000 | 4000000 | 5132609 | 5132609 | 5132609 | 5507195 | 5507195 | 374586 | 0
Reliability Upgrade | 1a | 840 | NSTAR Electric Company |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Proposed | Concept | Concept | Concept | Planned | Planned | Planned | Planned | 2008-04-01 | No | 5400000 | 5400000 | 5400000 | 5400000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 0 | 0
Reliability Upgrade | 1a | 775 | National Grid, USA |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Addition of 4 breakers and relocation of T1 and T2 into new bays at Sandy Pond. | Proposed | Concept | Concept | Planned | Planned | Planned | Planned | Planned | 2008-06-27 | No | TBD | TBD | TBD | 20100000 | 20100000 | 20100000 | 20100000 | 20100000 | 20100000 | 0 | 0
Reliability Upgrade | 1a | 776 | National Grid, USA |  | 09/2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Proposed | Concept | Concept | Planned | Planned | Planned | Planned | Planned | 2008-06-27 | No | 640000 | 640000 | 640000 | 2865876 | 2865876 | 2865876 | 2865876 | 3125000 | 3125000 | 259124 | 0
Reliability Upgrade | 1a | 782 | National Grid, USA |  | 10/2014 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor n Railyard. | Proposed | Concept | Concept | Planned | Planned | Planned | Planned | Planned | 2008-06-27 | No | 37600000 | 37600000 | 37600000 | 37600000 | 38100000 | 38100000 | 38100000 | 43912000 | 43912000 | 5812000 | 0
Reliability Upgrade | 1a | 1165 | NSTAR Electric Company |  | 12/2011 | Mystic Breaker Additions Project | Move Transformer 110B Connection at Mystic | Proposed | Planned | Planned | Planned | Planned | Planned |  | Planned | 2008-03-10 | No | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 |  | 1700000 | 1700000 | 1700000 | 0
Reliability Upgrade | 1a | 904 | NSTAR Electric Company |  | 12/2010 | Mystic IPT Breaker Project | Upgrade (5) 115 kV breakers #1, #7, #15 #19 and #20 at Mystic to IPT. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | NR | NR | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 1500000 | 1500000 | 510000 | 0
Reliability Upgrade | 1a | 1119 | NSTAR Electric Company |  | 06/2010 | Greater Boston Reliability Project | Upgrade West Medway-West Walpole 345kV line #325 | Concept | Concept | Concept |  | Proposed | Proposed | Proposed | Under Construction | NR | NR | 5000000 | 5000000 | 5000000 |  | 1300000 | 2200000 | 2200000 | 2200000 | 2200000 | 0 | 0
Reliability Upgrade | 1a | 842 | NSTAR Electric Company |  | 06/2010 | Boston Area 115 kV Enhancements | Add 115 kV 54 MVAR capacitor bank at W. Framingham. | Proposed | Concept | Concept | Concept | Proposed | Proposed | Proposed | Planned | 2009-12-28 | NR | 1200000 | 1200000 | 1200000 | TBD | 3000000 | 3000000 | 3700000 | 2650000 | 2650000 | -1050000 | 0
Reliability Upgrade | 1a | 1120 | NSTAR Electric Company |  | 06/2010 |  | Install 345kV 160 MVAR shunt ractor at W. Walpole | Concept | Concept | Concept |  | Proposed | Proposed | Proposed | Under Construction | 2010-01-19 | No | 5000000 | 5000000 | 5000000 |  | 6000000 | 7200000 | 7200000 | 7200000 | 7200000 | 0 | 0
Reliability Upgrade | 1a | 1113 | NSTAR Electric Company |  | 12/2010 |  | Install 115kV Breaker #31 at K St. |  |  |  | Concept | Proposed | Proposed | Proposed | Planned | 2009-12-15 | No |  |  |  | TBD | 2100000 | 2100000 | 2960000 | 2800000 | 2800000 | -160000 | 0
Reliability Upgrade | 1a | 1068 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to vicinity of Bourne and connect to existing #120 line and install a 345KV - 115kV auto-transformer at new substation about 3 miles west of the Barnstable Substation 7 |  |  | Concept | Concept | Proposed | Proposed | Proposed | Planned | 11/2009 | No |  |  | TBD | TBD | 110000000 | 110000000 | 110000000 | 110000000 | 110000000 | 0 | 0
Reliability Upgrade | 1a | 592 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing | Concept | Concept | Concept | Concept | Proposed | Proposed | Proposed | Planned | 11/2009 | No | 5000000 | 5000000 | 5000000 | TBD | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA |  | 0
Reliability Upgrade | 1a | 1118 | NSTAR Electric Company | National Grid, USA | 12/2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 |  |  |  | Concept | Proposed | Proposed | Proposed | Planned | 11/2009 | No | 5000000 | 5000000 | 5000000 | TBD | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA |  | 0
Reliability Upgrade | 1a | 929 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 1381849 | 1381849 | 1381849 | 1381849 | 1381849 | 1381849 | 1381849 | 1381849 | 1381849 | 0 | 0
Reliability Upgrade | 1a | 931 | National Grid, USA |  | 01/2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 531481 | 0 | 0
Reliability Upgrade | 1a | 928 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 1945218 | 1945218 | 1945218 | 1945218 | 1945218 | 1945218 | 2300000 | 2300000 | 2300000 | 0 | 0
Reliability Upgrade | 1a | 934 | National Grid, USA |  | 09/2011 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | 12/17/2007 | No | 818480 | 818480 | 818480 | 818480 | 818480 | 818480 | 818480 | Part of RSP 935 | Part of RSP 935 |  | 0
Reliability Upgrade | 1a | 935 | National Grid, USA |  | 09/2011 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | 12/17/2007 | No | 5208509 | 5208509 | 5208509 | 5208509 | 5208509 | 5208509 | 5208509 | 10200000 | 10200000 | 4991491 | 0
Reliability Upgrade | 1a | 938 | National Grid, USA |  | 05/2012 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 3068556 | 3068556 | 3068556 | 3068556 | 3068556 | 3068556 | 3068556 | 3068556 | 3068556 | 0 | 0
Reliability Upgrade | 1a | 939 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Reconductor and retension (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 3287738 | 3287738 | 3287738 | 3287738 | 3389658 | 3389658 | 3389658 | 3389658 | 3389658 | 0 | 0
Reliability Upgrade | 1a | 940 | National Grid, USA |  | 04/2011 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 6235744 | 6235744 | 6235744 | 6235744 | 6235744 | 6235744 | 6235744 | 6235744 | 6235744 | 0 | 0
Reliability Upgrade | 1a | 942 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 2767180 | 2767180 | 2767180 | 2767180 | 2767180 | 2767180 | 2767180 | 3650000 | 3650000 | 882820 | 0
Reliability Upgrade | 1a | 927 | National Grid, USA |  | 07/2010 | Central/Western Massachusetts Upgrades | Greendale - replace 115 kV breaker and upgrade to 2000A. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 584629 | 584629 | 584629 | 584629 | 584629 | 584629 | 584629 | 680000 | 680000 | 95371 | 0
Reliability Upgrade | 1a | 925 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 318888 | 318888 | 318888 | 318888 | 318888 | 318888 | 318888 | 318888 | 318888 | 0 | 0
Reliability Upgrade | 1a | 926 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 4889621 | 4889621 | 4889621 | 4889621 | 6027520 | 6027520 | 6027520 | 6027520 | 6027520 | 0 | 0
Reliability Upgrade | 1a | 932 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 372036 | 372036 | 372036 | 372036 | 372036 | 372036 | 372036 | 372036 | 372036 | 0 | 0
Reliability Upgrade | 1a | 924 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 2147181 | 2147181 | 2147181 | 2147181 | 2147181 | 2147181 | 2147181 | 2147181 | 2147181 | 0 | 0
Reliability Upgrade | 1a | 941 | National Grid, USA |  | 06/2012 | Central/Western Massachusetts Upgrades | Install new Z126 Millbury - Tower #510 115 kV line. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 5753542 | 5753542 | 5753542 | 5753542 | 7909203 | 7909203 | 7909203 | 13748000 | 13748000 | 5838797 | 0
Reliability Upgrade | 1a | 943 | National Grid, USA |  | 01/2011 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 1073995 | 1073995 | 1073995 | 1073995 | 1073995 | 1073995 | 1073995 | 1073995 | 1073995 | 0 | 0
Reliability Upgrade | 1a | 944 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 11411849 | 11411849 | 11411849 | 9898000 | 11411849 | 11411849 | 11411849 | 16530000 | 16530000 | 5118151 | 0
Reliability Upgrade | 1a | 950 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 1016897 | 1016897 | 1016897 | 899312 | 1016897 | 1016897 | 1016897 | 1016897 | 1016897 | 0 | 0
Reliability Upgrade | 1a | 953 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 10846906 | 10846906 | 10846906 | 9444260 | 10248067 | 10248067 | 10248067 | 10248067 | 10248067 | 0 | 0
Reliability Upgrade | 1a | 954 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | E Westminster - install new 115 kV breaker, including disconnect switches. Assumes no new control house. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 903909 | 903909 | 903909 | 799506 | 903909 | 903909 | 903909 | 903909 | 903909 | 0 | 0
Reliability Upgrade | 1a | 945 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Adams - install third 115 kV breaker to complete ring bus. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 1581841 | 1581841 | 1581841 | 1581841 | 1581841 | 1581841 | 1584841 | 1584841 | 1584841 | 0 | 0
Reliability Upgrade | 1a | 946 | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer - E Longmeadow - Shaker Rd line to 115 kV. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 14809054 | 14809054 | 14809054 | 14809054 | 9604032 | 9604032 | 9604032 | 9962060 | 9962060 | 358028 | 0
Reliability Upgrade | 1a | 947 | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Reconductor 115 kV line from Palmer to new Hampden Substation. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 14170733 | 14170733 | 14170733 | 14170733 | 2632635 | 2632635 | 2632635 | 2632635 | 2632635 | 0 | 0
Reliability Upgrade | 1a | 948 | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 5649430 | 5649430 | 5649430 | 5649430 | 5649430 | 5649430 | 5649430 | 5649430 | 5649430 | 0 | 0
Reliability Upgrade | 1a | 949 | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 1694829 | 1694829 | 1694829 | 1694829 | 1694829 | 1694829 | 1500000 | 1500000 | 1500000 | 0 | 0
Reliability Upgrade | 1a | 952 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Reconductor E Winchendon - J136 Tap within I135/J136 ROW w/795 ACSR. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 932156 | 932156 | 932156 | 932156 | 932156 | 932156 | 932156 | 932156 | 932156 | 0 | 0
Reliability Upgrade | 1a | 937 | National Grid, USA |  | 05/2012 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 6602875 | 6602875 | 6602875 | 6602875 | 6602875 | 6602875 | 6602875 | 6602875 | 6602875 | 0 | 0
Reliability Upgrade | 1a | 955 | National Grid, USA |  | 11/2011 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 10779113 | 10779113 | 10779113 | 10779113 | 10779113 | 10779113 | 10779113 | 12213934 | 12213934 | 1434821 | 0
Reliability Upgrade | 1a | 162 | National Grid, USA |  | 04/2011 |  | Q-169 Golden Hills to Lynn 115 kV line upgrade. | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | 2005-09-02 | 2008-04-25 | 4335000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 12390000 | 0 | 0
Reliability Upgrade | 1a | 902 | National Grid, USA |  | 10/2010 | Middleboro Municipal | Close the E1-M1 loop at Middleboro's Wareham St Sub. | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | 12/01/2006 | NR | TBD | 715000 | 715000 | 715000 | 715000 | 715000 | 715000 | 715000 | 715000 | 0 | 0
Reliability Upgrade | 1a | 1000 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-06-27 | No | TBD | TBD | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 22000000 | 0 | 0
Reliability Upgrade | 1a | 951 | National Grid, USA |  | 02/2013 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon 115 kV line. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 12/17/2007 | No | 7231271 | 7231271 | 7231271 | 6400522 | 7455440 | 7455440 | 7455440 | 7455440 | 7455440 | 0 | 0
Reliability Upgrade | 1a | 687 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | 714000000 | 714000000 | 714000000 | 714000000 | 714000000 | 714000000 | 714000000 | 0 | 0
Reliability Upgrade | 1a | 826 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 196 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 818 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115kV line South Agawam to Southwick (1768) | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 819 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 820 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 823 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVAR Capacitor additions | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 828 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 829 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1010 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 259 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 688 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1100 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1101 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1102 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1103 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1104 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1105 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1070 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1071 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1072 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1073 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1074 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1075 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1078 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1079 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1080 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1076 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project |  | 0
Reliability Upgrade | 1a | 1077 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115kV line |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project |  | 0
Reliability Upgrade | 1a | 673 | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Proposed | Concept | Concept | Concept | Planned | Planned | Planned | Planned | 2009-02-27 | No | 525000 | 525000 | 525000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 2200000 | 0 | 0
Reliability Upgrade | 1a | 676 | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Proposed | Concept | Concept | Concept | Planned | Planned | Planned | Planned | 2009-02-27 | No | 6800000 | 6800000 | 6800000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 30000000 | 0 | 0
Reliability Upgrade | 1a | 1067 | NSTAR Electric Company |  | 12/2010 | NPCC BPS Compliance | Tremont Station |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | NR | No |  |  |  | 7100000 | 11200000 | 11200000 | 12800000 | 12370000 | 12370000 | -430000 | 0
Reliability Upgrade | 1a | 1066 | NSTAR Electric Company |  | 09/2011 | NPCC BPS Compliance | Needham Station |  |  |  | Proposed | Proposed | Concept | Concept | Planned | NR | No |  |  |  | 7500000 | 9300000 | 9300000 | 9300000 | 10531000 | 10531000 | 1231000 | 1
Reliability Upgrade | 1a | 1065 | NSTAR Electric Company |  | 07/2012 | NPCC BPS Compliance | Waltham Station |  |  |  | Proposed | Proposed | Concept | Proposed | Planned | NR | No |  |  |  | 22000000 | 24300000 | 24300000 | 26600000 | 23190000 | 23190000 | -3410000 | 1
Generator Interconnection Upgrade | 2a | 1045 | National Grid, USA |  | 06/2010 | Lowell Power | Upgrade 137T and K-137W 115 kV circuit breakers at Sandy Pond. |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2006-07-25 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 505 | National Grid, USA |  | 12/2010 | Hoosac Wind Farm | Tap Y-25S line between Harriman and Deerfield 5. Construct 69/34.5 kV substation and 34.5 kV line connecting 30 MW generating facility with the 69 kV system. | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 02/01/2005 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 595 | NSTAR Electric Company |  | 01/2012 | Cape Wind | Expansion of Barnstable 115 kV substation to include 5th bay and (2) circuit breakers, addition of a 3rd breaker in the planned 4th bay, and (2) 35MVAr shunt reactors. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 596 | NSTAR Electric Company |  | 01/2012 | Cape Wind | Installation of (2) 115 kV circuits out of Barnstable substation to interconnect Cape Wind. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 598 | NSTAR Electric Company |  | 01/2012 | Cape Wind | At Canal 345 kV substation, install a redundant breaker in series with breaker #312. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 599 | NSTAR Electric Company |  | 01/2012 | Cape Wind | Upgrade the Bourne 115 kV breaker #12272 with an IPT breaker. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 600 | NSTAR Electric Company |  | 01/2012 | Cape Wind | Installation of differential insulation and additional grounding at each tower that is common for the 342 and 322 345 kV lines. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1048 | NSTAR Electric Company |  | 01/2012 | Cape Wind | Convert Canal 345 kV SPS to include tripping of Cape Wind for the simultaneous loss of 342 and 322 345 kV lines. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2005-10-06 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1046 | National Grid, USA |  | 06/2011 | Queue Position 178 | Reconductor 115 kV F19 Line (Auburn - Brockton Tap). |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | 2008-03-10 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1047 | National Grid, USA |  | 06/2011 | Queue Position 178 | Replace Bridgewater 115 kV 1631 circuit breaker with 63 kA breaker. |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | 2008-03-10 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 622 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Interconnection to WMECO's 115-kV 1512 line through a new Substation. | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | 06/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1043 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Upgrade the 1768 line terminal equipment at Southwick Substation. | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | 06/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1044 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Upgrade the 1512 line terminal equipment at Southwick Substation. | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | 06/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1058 | National Grid, USA |  | 06/2011 | Billerica Power | Interconnection to Tewksbury 115 kV Substation via O-193 Line and refurbish section of J-162 line. |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1059 | National Grid, USA |  | 06/2011 | Billerica Power | Re-terminate line tap section (Perry Street) of J-162 Line to new bay position at Tewksbury. |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1060 | National Grid, USA |  | 06/2011 | Billerica Power | Reconductor 2.8 mi. of the M-139 115 kV line. |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1061 | National Grid, USA |  | 06/2011 | Billerica Power | Replace (16) 115 kV circuit breakers at Tewksbury 22 w/ IPT capability if all generators w/ higher Queue Position are constructed. The quantity of breaker upgrades subject to Queued generators constructed. |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1062 | National Grid, USA |  | 06/2011 | Billerica Power | Upgrade #137T and #K-137W 115 kV circuit breakers at Sandy Pond (if not completed as part of Merrimack Valley/North Shore Project). |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-07-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1014 | Northeast Utilities |  | 2014 | Queue Position 196 | Northfield Mountain 345 kV replace generator step-up transformer (3X) and associated generator equipment. This project also consists of upgrading four existing turbine generators one per year. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Under Construction | 2009-06-29 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Elective | 4a | 1057 | Braintree Electric Light Department |  | 06/2010 |  | Upgrade 115-10-16 underground 115 kV cable. |  |  | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-17 | No |  |  | TBD | TBD | TBD | TBD | NR | TBD | TBD |  | 0
RHODE ISLAND | [25 empty] | 0 | 0 | 0
Reliability Upgrade | 1a | 484 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 690000 | 690000 | 690000 | 690000 | 690000 | 690000 | 690000 | 580000 | 580000 | -110000 | 0
Reliability Upgrade | 1a | 791 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 11560000 | 0 | 0
Reliability Upgrade | 1a | 913 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 3250000 | 0 | 0
Reliability Upgrade | 1a | 914 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 28150000 | 0 | 0
Reliability Upgrade | 1a | 915 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 19450000 | 0 | 0
Reliability Upgrade | 1a | 916 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 11800000 | 0 | 0
Reliability Upgrade | 1a | 917 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 0 | 0
Reliability Upgrade | 1a | 918 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 3180000 | 0 | 0
Reliability Upgrade | 1a | 792 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Admiral St-Franklin Square (Q143 and R144) 115 kV UG recabling. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 22500000 | 22500000 | 22500000 | 22500000 | 39200000 | 39200000 | 39200000 | 39200000 | 39200000 | 0 | 0
Reliability Upgrade | 1a | 793 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | 2008-04-25 | No | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 6400000 | 0 | 0
Reliability Upgrade | 1a | 786 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Terminal upgrades at Drumrock, Chartley Pond, and Brayton Point. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Under Construction | 2008-04-25 | No | 2000000 | 2000000 | 2000000 | 565000 | 565000 | 565000 | 1000000 | 1000000 | 1000000 | 0 | 0
Reliability Upgrade | 1a | 787 | National Grid, USA |  | 06/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | West Farnum breaker replacements. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Under Construction | 2008-04-25 | No | 6500000 | 6500000 | 6500000 | 7600000 | 7631000 | 7631000 | 7631000 | 7631000 | 7631000 | 0 | 0
Reliability Upgrade | 1a | 788 | National Grid, USA |  | 06/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Kent County substation expansion. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Under Construction | 2008-04-25 | No | 25000000 | 25000000 | 25000000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 42300000 | 0 | 0
Reliability Upgrade | 1a | 790 | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Under Construction | 2008-04-25 | No | 24000000 | 24000000 | 24000000 | 50600000 | 50600000 | 50600000 | 50600000 | 50600000 | 50600000 | 0 | 0
Reliability Upgrade | 1a | 1098 | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street |  |  | Planned | Planned | Planned | Planned | Planned | Under Construction | 2008-04-25 | No |  |  | TBD | 23000000 | 37529000 | 37529000 | 37529000 | 37529000 | 37529000 | 0 | 0
Reliability Upgrade | 1a | 190 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | 53000000 | 53000000 | 53000000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 0 | 0
Reliability Upgrade | 1a | 1094 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | TBD | 20800000 | 20800000 | 20800000 | 25000000 | 25000000 | 25000000 | 0 | 0
Reliability Upgrade | 1a | 1095 | National Grid, USA |  | 06/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | TBD | 73800000 | 73800000 | 73800000 | 73800000 | 73800000 | 73800000 | 0 | 0
Reliability Upgrade | 1a | 794 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | 50000000 | 50000000 | 50000000 | 55800000 | 55800000 | 55800000 | 55800000 | 55800000 | 55800000 | 0 | 0
Reliability Upgrade | 1a | 796 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | 347 Reconductor from Sherman Road to CT/RI Border. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | 10000000 | 10000000 | 10000000 | 16400000 | 16400000 | 16400000 | 16400000 | 16400000 | 16400000 | 0 | 0
Reliability Upgrade | 1a | 797 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | 3361 Upgrade 345kV terminal equipment at Sherman Road. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | 3000000 | 3000000 | 3000000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 0 | 0
Reliability Upgrade | 1a | 795 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV line. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | 92000000 | 92000000 | 92000000 | 99900000 | 99900000 | 99900000 | 99900000 | 99900000 | 99900000 | 0 | 0
Reliability Upgrade | 1a | 1106 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | Part of $92,000,000 above | Part of $92,000,000 above | Part of $92,000,000 above | Part of $99,900,000 above | Part of $99,900,000 above | Part of $99,900,000 above | Part of $99,900,000 above | Part of $99,900,000 above | Part of $99,900,000 above |  | 0
Reliability Upgrade | 1a | 798 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | 500000 | 500000 | 500000 | 4900000 | 4900000 | 4900000 | 4900000 | 4900000 | 4900000 | 0 | 0
Reliability Upgrade | 1a | 799 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | 2200000 | 2200000 | 2200000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 4500000 | 0 | 0
Reliability Upgrade | 1a | 1096 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | TBD | 5800000 | 5800000 | 5800000 | 12000000 | 12000000 | 12000000 | 0 | 0
Reliability Upgrade | 1a | 800 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S, T-172N and T-172S with associated terminal equipment upgrades. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2009-11-05 | No | 62000000 | 62000000 | 62000000 | 7300000 | 7300000 | 7300000 | 10000000 | 10000000 | 10000000 | 0 | 0
Reliability Upgrade | 1a | 1097 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | TBD | 129800000 | 129800000 | 129800000 | 129800000 | 129800000 | 129800000 | 0 | 0
Reliability Upgrade | 1a | 1099 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | TBD | 4100000 | 4100000 | 4100000 | 6000000 | 6000000 | 6000000 | 0 | 0
Reliability Upgrade | 1a | 1109 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | TBD | 360000 | 360000 | 360000 | 1000000 | 1000000 | 1000000 | 0 | 0
CONNECTICUT | [27 empty] | 0
Reliability Upgrade | 1a | 1055 | Northeast Utilities |  | 2010 | CT LSP - Waterside Substation | Waterside Substation - add a 115/13.2-kV transformer and a 115-kV circuit breaker. |  |  | Concept | Concept | Concept | Concept | Concept | Planned | 2009-09-29 | NR |  |  | TBD | 4107000 | 4107000 | 4107000 | 4107000 | 2619000 | 2619000 | -1488000 | 0
Reliability Upgrade | 1a | 1049 | United Illuminating Company |  | 12/2010 |  | East Shore 115 kV Capacitor Bank Transient Recovery |  | Concept | Concept | Planned | Planned | Planned | Planned | Planned | NR | NR |  | 1200000 | 1200000 | 3000000 | 3000000 | 3000000 | 3000000 | 4050000 | 4050000 | 1050000 | 0
Reliability Upgrade | 1a | 582 | Northeast Utilities |  | 12/2010 |  | Separate 310 and 368 345-KV lines and create 368/1767 DCT | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-07-18 | No | TBD | TBD | 15500000 | 16000000 | 16000000 | 16000000 | 16000000 | 16000000 | 16000000 | 0 | 0
Reliability Upgrade | 1a | 1112 | United Illuminating Company |  | 12/2010 |  | Water Street 115kV circuit breaker and switch replacements. |  |  |  | Planned | Planned | Planned | Planned | Planned | NR | NR |  |  |  | 1000000 | 1000000 | 1000000 | 1000000 | 2840000 | 2840000 | 1840000 | 0
Reliability Upgrade | 1a | 809 | Northeast Utilities |  | 12/2010 |  | Upgrade terminal equipment at Bunker Hill 115 kV substation. | Proposed | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | NR | NR | TBD | TBD | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 516000 | 516000 | -484000 | 0
Reliability Upgrade | 1a | 1147 | Northeast Utilities |  | 2011 |  | Waterside Substation - install a three-breaker 115kV ring bus | Proposed | Concept | Concept | Concept | Concept |  | Proposed | Planned | 2009-09-29 | NR | TBD | TBD | TBD | TBD | TBD |  | 4000000 | 5055000 | 5055000 | 1055000 | 1
Reliability Upgrade | 1a | 1148 | Northeast Utilities |  | 2011 |  | Add a 2nd high speed relay on the Glennbrook to Waterside 115kV 1440 | Planned | Concept | Concept | Concept | Concept |  | Proposed | Planned | 2009-09-29 | NR | TBD | TBD | TBD | TBD | TBD |  | 600000 | Part of Project #1147 | Part of Project #1147 |  | 1
Reliability Upgrade | 1a | 974 | United Illuminating Company |  | 04/2013 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Proposed | Concept | Concept | Planned | Planned | Planned | Planned | Planned | NR | No | 4500000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 0 | 0
Reliability Upgrade | 1a | 816 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 0
Reliability Upgrade | 1a | 1054 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Manchester - Meekvile Jct. line (395/1448) separation. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 14000000 | 0 | 0
Reliability Upgrade | 1a | 576 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | 313000000 | 313000000 | 313000000 | 313000000 | 313000000 | 313000000 | 313000000 | 0 | 0
Reliability Upgrade | 1a | 1114 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) |  | 0
Reliability Upgrade | 1a | 814 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Central Connecticut Relaibility Project) | Reconductor a portion of the Manchester to Scovill Rock 353 345-kV line and terminal work. | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | 15000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 0 | 0
Reliability Upgrade | 1a | 802 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | 251000000 | 251000000 | 251000000 | 251000000 | 251000000 | 251000000 | 251000000 | 0 | 0
Reliability Upgrade | 1a | 1084 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Loop the Millstone - Manchester (310) 345 kV line into the Card substation. |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 1085 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 1086 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 1087 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 1088 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 1089 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Killingly 3G substation 345kV breaker addition |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 1090 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Millstone 15G substation breaker 14T upgrade 50kA |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 1091 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Southington 4C substation breaker 19T upgrade to 63kA |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 810 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 191 | Northeast Utilities | National Grid, USA | 12/2013 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) |  | 0
Reliability Upgrade | 1a | 807 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Interstate Reliability Project) | Install 480 MVAR's of capacitors at the Montville 345 kV substation | Proposed | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No | TBD | TBD | 21000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 33000000 | 0 | 0
Reliability Upgrade | 1a | 1092 | Northeast Utilities |  | 12/2013 | NEEWS (BPS) 2 | Upgrade the Card 115 kV, East Hartford 115 kV, Agawam 115 kV, Barbour Hill 115 kV, and North Bloomfield 345 kV Substations to BPS standards. |  |  | Proposed | Planned | Planned | Planned | Planned | Planned | 2008-09-24 | No |  |  | TBD | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 0 | 0
Reliability Upgrade | 1a | 1056 | Northeast Utilities |  | 12/2011 | CT LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. |  |  | Concept | Concept | Planned | Planned | Planned | Planned | 2008-12-12 | No |  |  | TBD | TBD | 9751000 | 9751000 | 9751000 | 10969000 | 10969000 | 1218000 | 0
Reliability Upgrade | 1a | 1110 | United Illuminating Company |  | 12/2010 |  | Broadway 115/13.8 kV Substation Addition |  |  |  | Proposed | Planned | Planned | Planned | Under Construction | 2008-12-08 | NR |  |  |  | 1000000 | 800000 | 1200000 | 1200000 | 1200000 | 1200000 | 0 | 0
Reliability Upgrade | 1a | 1111 | United Illuminating Company |  | 2011-08-01 |  | Metro North Union Avenue 115/26.4 kV Substation |  |  |  | Proposed | Planned | Planned | Planned | Planned | 2009-01-07 | 2009-11-10 |  |  |  | 8700000 | 8700000 | 10543000 | 10543000 | 10543000 | 10543000 | 0 | 0
Reliability Upgrade | 1a | 976 | United Illuminating Company |  | 05/2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Concept | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | 2009-01-07 | No | 40000000 | 38900000 | 38900000 | 48000000 | 48000000 | 48000000 | 48000000 | 66000000 | 66000000 | 18000000 | 0
Reliability Upgrade | 1a | 721 | United Illuminating Company |  | 06/2016 |  | New Shelton 115/13.8 kV substation | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Planned | 2009-11-05 | No | 5500000 | 26610000 | 7370000 | 11300000 | 11300000 | 11300000 | 11300000 | 19500000 | 19500000 | 8200000 | 0
Reliability Upgrade | 1a | 879 |  | Bangor Hydro-Electric Company, New England Power Company, Northeast Utilities System Com | TBD | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 03/01/2007 | NR | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 420000 | 0 | 0
Generator Interconnection Upgrade | 2a | 983 | Northeast Utilities |  | 09/2012 | Queue Position 207/241 | Rebuild 115 kV 1585N Line between new substation and Bunker Hill. | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | 2008-09-26 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1107 | Northeast Utilities |  | 09/2012 | Queue Position 207/241 | Interconnection to new 115 kV substation consisting of (14) circuit breakers in a breaker and a half configuration that sectionalizes the existing 1575, 1585, and 1990 lines. |  |  | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | 2008-09-26 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1108 | Northeast Utilities |  | 09/2012 | Queue Position 207/241 | Installation of a 2.5% series reactor on the 1990S Line at the new substation. |  |  | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | 2008-09-26 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 331 | Northeast Utilities |  | TBD | Kleen Energy | Install 5-breaker ring bus interconnecting between Scovill Rock and Manchester on the 345 kV 353 Line. | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | See Note (5) | 10/08/2003 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 1
Generator Interconnection Upgrade | 2a | 1121 | Northeast Utilities |  | 06/2010 | Queue Position 161-2 | Four units connected to 384 line through a new 345kV Substation: unit #4 wll also connect to Substation | Planned | Planned | Planned |  | Proposed | Proposed | Planned | Planned | 2008-12-08 | NR | NR | NR | NR |  | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2a | 1149 | Northeast Utilities |  | 06/2010 | Queue Position 161-1 | Four units connected at Devon Substation | Planned | Planned | Planned |  | Proposed |  | Under Construction | Under Construction | 2007-12-08 | NR | NR | NR | NR |  | NR | NR | NR | NR | NR |  | 1
Generator Interconnection Upgrade | 2a | 1122 | Northeast Utilities |  | 11/2010 | Queue Position 191 | One turbine connected to #1238 Line (Frost Bridge to Carmel) via a new 3-breaker ring bus Substation | Planned | Planned | Planned |  | Proposed | Proposed | Proposed | Proposed | 2009-02-24 | NR | NR | NR | NR |  | NR | NR | NR | NR | NR |  | 0
Reliability Upgrade | 1a | 1050 | United Illuminating Company |  | 12/2011 |  | Devon Tie 115kV Switching Station BPS Compliance |  | Concept | Concept | Concept | Planned | Planned | Planned | Planned | NR | NR |  | 2620000 | 2620000 | 2620000 | 2620000 | 2620000 | 2620000 | 3240000 | 3240000 | 620000 | 0
TABLE B | [27 empty] | 0
MAINE | [27 empty] | 0
Reliability Upgrade | 1b | 148 | Central Maine Power Company |  | 06/2012 | CMP LSP - Saco Bay Area Reinforcement Project | Establish a new Vallee Lane 115/34.5 kV substation and 115 kV line from Louden S/S to Vallee Lane Substation. | Proposed | Proposed | Concept | Concept | Proposed | Proposed | Proposed | Proposed | No | NR | 14000000 | 14000000 | 16900000 | 16900000 | 16900000 | 100000 | 100000 | 100000 | 100000 | 0 | 0
Reliability Upgrade | 1b | 1116 | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Concept | Concept | Proposed |  | Concept | Concept | Concept | Proposed | No | No | TBD | TBD | Part of Maine Power Reliability Program |  | TBD | TBD | TBD | 37126000 | 37126000 | 37126000 | 0
Reliability Upgrade | 1b | 1031 | Bangor Hydro-Electric Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station | Concept | Concept | Proposed | Proposed | Concept | Concept | Concept | Concept | No | No | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | TBD | TBD | TBD | TBD | TBD |  | 0
Reliability Upgrade | 1b | 1154 | Bangor Hydro-Electric Company |  | 12/2013 | Maine Power Reliability Program (MPRP) | Rebuild Line 66 | Concept | Concept | Proposed | Proposed | Concept | Concept |  | Concept | No | No | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | TBD | TBD |  | TBD | TBD |  | 0
Reliability Upgrade | 1b | 1155 | Bangor Hydro-Electric Company |  | 12/2013 | Maine Power Reliability Program (MPRP) | Capacitor Bank Addition (10 MVAr at Trenton and Epping) | Concept | Concept | Proposed | Proposed | Concept | Concept |  | Concept | No | No | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | TBD | TBD |  | TBD | TBD |  | 0
Reliability Upgrade | 1b | 1156 | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | Orrington Shunt Cap Reconfiguration | Concept | Concept | Proposed | Proposed | Concept | Concept |  | Concept | No | No | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | TBD | TBD |  | TBD | TBD |  | 0
Reliability Upgrade | 1b | 1157 | Bangor Hydro-Electric Company |  | 12/2010 |  | Bangor Hydro Synchrophasors | Concept | Concept | Proposed | Proposed | Concept | Concept |  | Concept | No | No | TBD | TBD | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | TBD | TBD |  | 100000 | 100000 | 100000 | 0
Reliability Upgrade | 1b | 1130 | Central Maine Power Company |  | 12/2011 | Sturtevant Improvements | Add 115kV circuit breakers & 25 MVAR capacitor bank at Sturtevant Substation; Re-rate Section 63 between Wyman Hydro & Madison Substation | Planned | Concept | Concept |  | Proposed | Proposed | Proposed | Proposed | 2009-07-28 | No | 10100000 | 10100000 | 6100000 |  | 2000000 | 3000000 | 3000000 | 3000000 | 3000000 | 0 | 0
Reliability Upgrade | 1b | 1131 | Central Maine Power Company |  | 12/2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Planned | Concept | Concept |  | Proposed | Proposed | Proposed | Proposed | No | NR | 10100000 | 10100000 | 6100000 |  | 600000 | 600000 | 600000 | 600000 | 600000 | 0 | 0
Reliability Upgrade | 1b | 1132 | Central Maine Power Company |  | 12/2011 | CMP-LSP Maxcy's Substation | Add 115/34kV transformer (coordinate with MPRP) | Planned | Concept | Concept |  | Proposed | Proposed | Proposed | Proposed | No | NR | 10100000 | 10100000 | 6100000 |  | 600000 | 600000 | 600000 | 600000 | 600000 | 0 | 0
Reliability Upgrade | 1b | 1133 | Central Maine Power Company |  | 10/2010 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation & new 34kV line from Leeds to Turner | Planned | Concept | Concept |  | Proposed | Proposed | Proposed | Proposed | No | NR | 10100000 | 10100000 | 6100000 |  | 2500000 | 300000 | 300000 | 300000 | 300000 | 0 | 0
Reliability Upgrade | 1b | 1135 | Central Maine Power Company |  | TBD | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer | [5 empty] | Proposed | Proposed | Proposed | No | No | 10100000 | 10100000 | 6100000 |  |  | 1500000 | 1500000 | 1500000 | 1500000 | 0 | 1
Elective | 4b | 1018 | Bangor Hydro-Electric Company | NSTAR | TBD | QP-283 | HVDC between Orrington, ME and Boston, MA | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Elective | 4b | 1160 | Central Maine Power Company |  | TBD | QP-278 | 1000 MW HVDC between Maine Yankee, ME and South Boston, MA | Concept | Concept | Concept | Concept | Concept | Concept |  | Concept | No | No | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD |  | 0
Elective | 4b | 1163 | Maine Electric Power Company |  | TBD | QP-322 | 345kV Tie Line - between Houlton, ME and MEPCO Line | Concept | Concept | Concept | Concept | Concept | Concept |  | Concept | No | No | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD |  | 0
Elective | 4b | 1164 | Maine Electric Power Company |  | TBD | QP-324 | 345kV Tie Line - between Bridgewater, ME and MEPCO Line | Concept | Concept | Concept | Concept | Concept | Concept |  | Concept | No | No | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD |  | 0
NEW HAMPSHIRE | [27 empty] | 0
Reliability Upgrade | 1b | 1143 | Northeast Utilities |  | TBD |  | Littleton 115kV breaker addition and reconfiguration | Proposed | Concept | Concept | Concept |  | Proposed | Proposed | Proposed | No | No | TBD | TBD | TBD | TBD |  | 5338000 | 5338000 | 6642000 | 6642000 | 1304000 | 1
VERMONT | [27 empty] | 0
Reliability Upgrade | 1b | 318 | Vermont Electric Power Company |  | 12/2011 |  | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems through the 1,250 MW Vermont state load level. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 7000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 9000000 | 0 | 0
Reliability Upgrade | 1b | 325 | Vermont Electric Power Company |  | 12/2011 | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 3000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 0 | 0
Reliability Upgrade | 1b | 324 | Vermont Electric Power Company |  | TBD |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 60000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 | TBD | TBD | #VALUE! | 0
Generator Interconnection Upgrade | 2b | 1037 | Vermont Electric Power Company | Central Vermont Public Service | 12/2010 | Queue Position 276 | Installation of 3-breaker 115kV ring bus interconnection of the Bennington-Searsburg 69kV Y25N line. | Proposed | Concept | Concept | Concept | Concept | Concept |  | Concept | No | NR | 60000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 |  | NR | NR |  | 0
Generator Interconnection Upgrade | 4b | 1162 | Vermont Electric Power Company |  | TBD | OP-314 | 345/230 kV DC line between Plattsburg, NY and New Haven, CT | Proposed | Concept | Concept | Concept | Concept | Concept |  | Concept | No | NR | 60000000 | 100000000 | 100000000 | 100000000 | 100000000 | 100000000 |  | NR | NR |  | 0
MASSACHUSETTS | [27 empty] | 0
Reliability Upgrade | 1b | 785 | National Grid, USA |  | 07/2017 | Merrimack Valley/North Shore Reliability Project | Re-conductor F-158N (Golden Hills-Maplewood-Everett) 115 kV line. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 1330000 | 1330000 | 1330000 | 1330000 | 1330000 | 1330000 | 1330000 | 1330000 | 1330000 | 0 | 0
Reliability Upgrade | 1b | 1153 | NSTAR Electric Company |  | 12/2011 | Boston Area 115 kV Enhancements | Reliability Upgrades at West Framingham Station | Concept | Concept | Concept | Concept | Proposed |  | Concept | Concept | No | No | TBD | TBD | TBD | TBD | Part of Long Term Lower SEMA |  | 3000000 | 3000000 | 3000000 | 0 | 1
Reliability Upgrade | 1b | 843 | NSTAR Electric Company |  | 12/2013 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 1200000 | 1200000 | 1200000 | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Reliability Upgrade | 1b | 965 | NSTAR Electric Company |  | 12/2012 | Boston Area 115 kV Enhancements | Add third 115kV line from W. Walpole to Holbrook | Proposed | Proposed | Proposed | Concept | Concept | Concept | Concept | Concept | No | No | 2500000 | 2500000 | 2500000 | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Reliability Upgrade | 1b | 964 | NSTAR Electric Company |  | 06/2011 | Boston Area 115 kV Enhancements | Relocate 115kV terminals at W. Walpole to mitigate breaker failure #8. | Proposed | Concept | Concept | Concept | Proposed | Proposed | Proposed | Proposed | No | No | 600000 | 600000 | 600000 | TBD | 5600000 | 5600000 | 5600000 | 5600000 | 5600000 | 0 | 0
Reliability Upgrade | 1b | 969 | NSTAR Electric Company |  | 06/2015 | Boston Area 115 kV Enhancements | Add a new 54 MVAR capacitor bank at Chelsea. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 2780000 | 2780000 | 1580000 | 0
Reliability Upgrade | 1b | 301 | NSTAR Electric Company |  | 12/2011 | Boston Area 115 kV Enhancements | Reconductor 115-kV circuits 320-507 and 320-508. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 0 | 0
Reliability Upgrade | 1b | 593 | NSTAR Electric Company |  | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Canal to Barnstable/Falmouth | Concept | Concept | Concept | Concept | Proposed | Concept | Concept | Concept | No | No | TBD | TBD | TBD | TBD | Part of Long Term Lower SEMA | TBD | TBD | TBD | TBD |  | 1
Reliability Upgrade | 1b | 970 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345 kV line from Lexington to Waltham. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 15000000 | 15000000 | 15000000 | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Reliability Upgrade | 1b | 971 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 12000000 | 12000000 | 12000000 | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Reliability Upgrade | 1b | 1166 | NSTAR Electric Company |  | 12/2010 |  | Terminal upgrades at W. Walpole and W, Medway for #325 line | Concept | Concept | Concept |  | Proposed | Proposed |  | Proposed | NR | NR | 5000000 | 5000000 | 5000000 |  | 1300000 | 2200000 |  | 1350000 | 1350000 | 1350000 | 0
Reliability Upgrade | 1b | 1167 | NSTAR Electric Company |  | 12/2010 |  | Replace three 40kA 115kV circuit breakers at Carver with 63kV breakers | Concept | Concept | Concept |  | Proposed | Proposed |  | Concept | No | No | 5000000 | 5000000 | 5000000 |  | 6000000 | 7200000 |  | 850000 | 850000 | 850000 | 0
Reliability Upgrade | 1b | 956 | National Grid, USA |  | 01/2015 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 7021534 | 0 | 0
Reliability Upgrade | 1b | 1136 | National Grid, USA |  | 12/2012 |  | New 115kV Switching Station at Devens Convert 69kV lines to 115kV, Reconfigure 115kV Supply at Ayer Substation | [5 empty] | Proposed | Proposed | Proposed | 2009-07-28 | No |  |  | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) |  | 9200000 | 9200000 | 9200000 | 9200000 | 0 | 1
Reliability Upgrade | 1b | 824 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Reliability Upgrade | 1b | 1168 | Holyoke Gas & Electric |  | TBD |  | Loop/extend the 1525 (Holyoke Fairmont South 115kV) line into the new Lyman Substation | Proposed | Concept | Concept | Concept | Concept | Concept |  | Concept | No | No | TBD | TBD | TBD | TBD | TBD | TBD |  | TBD | TBD |  | 0
Reliability Upgrade | 1b | 825 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Upgrade the Pleasant to Blanford 115-kV line and the Blanford to Granville Jct. portion of the 115-kV line 1512. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Generator Interconnection Upgrade | 2b | 1123 | Northeast Utilities |  | TBD | Queue Position 236 | New Substation on 1302 Line; terminal upgrades at Buck Pond and Agawam | Concept | Concept | Concept |  | Concept | Concept | Concept | Concept | No | NR | NR | NR | NR |  | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2b | 880 | National Grid, USA | Northeast Utilities | 06/2011 | Queue Position 177 | Sutton Energy - 345 kV Carpenter Hill-Millbury Line. | Concept | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2b | 1042 | National Grid, USA |  | 06/2013 | Queue Position 165 | Replace (2) 345 kV circuit breakers at Sandy Pond | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
RHODE ISLAND | [27 empty] | 0
Generator Interconnection Upgrade | 2b | 881 | National Grid, USA | Northeast Utilities | 06/2012 | Queue Position 201 | RISEP - 345 kV RISE Substation. | Concept | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
CONNECTICUT | [27 empty] | 0
Reliability Upgrade | 1b | 1150 | United Illuminating Company |  | 12/2010 |  | Grand Avenue - West River 115 kV Pumping Plant Replacements | Concept | Concept | Concept | Proposed | Proposed |  | Proposed | Proposed | NR | NR | 5500000 | 26610000 | 7370000 | 11300000 | 11300000 |  | 1200000 | 2900000 | 2900000 | 1700000 | 1
Reliability Upgrade | 1b | 1151 | United Illuminating Company |  | 12/2011 |  | West River 115kV Switching Station Fault Duty Migration | Concept | Concept | Concept | Proposed | Proposed |  | Proposed | Proposed | NR | NR | 5500000 | 26610000 | 7370000 | 11300000 | 11300000 |  | 3500000 | 3500000 | 3500000 | 0 | 1
Reliability Upgrade | 1b | 975 | United Illuminating Company |  | 06/2015 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 33000000 | 44300000 | 44300000 | 44300000 | 44300000 | 44300000 | 44300000 | 65000000 | 65000000 | 20700000 | 0
Reliability Upgrade | 1b | 699 | United Illuminating Company |  | 12/2014 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | 75000000 | 46540000 | 46540000 | 46540000 | 10000000 | 10000000 | 10000000 | 11100000 | 11100000 | 1100000 | 0
Reliability Upgrade | 1b | 801 | Northeast Utilities |  | TBD |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Reliability Upgrade | 1b | 85 | Northeast Utilities |  | TBD |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Planned | Concept | Concept | Concept | Concept | Concept | Concept | Concept | 08/04/2004 | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Generator Interconnection Upgrade | 2b | 1124 | Northeast Utilities |  | TBD | Queue Position 222 | New Substation on Haddam Neck-Southington 345kV line | Planned | Concept | Concept |  | Proposed | Proposed | Proposed | Proposed | No | NR | TBD | TBD | TBD |  | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2b | 1125 | Northeast Utilities |  | TBD | Queue Position 240 | 345kV on Montville Substation | Planned | Concept | Concept |  | Concept | Concept | Concept | Concept | No | NR | TBD | TBD | TBD |  | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 4b | 1161 | United Illuminating Company |  | TBD | Queue Position 271 | 1000 MW HVDC between Hertel, QC or Clay NY and Singer, CT | Planned | Concept | Concept |  | Concept | Concept |  | Concept | No | NR | TBD | TBD | TBD |  | NR | NR |  | NR | NR |  | 0
IN-SERVICE PROJECTS | [25 empty] | 5189345881 | #VALUE! | 25
Reliability Upgrade | 1a | 320 | Vermont Electric Power Company |  | 10/2009 | Lamoille County Project | Middlesex Substation 115 kV breaker addition. | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | 08/16/2007 | 02/07/2008 | 4000000 | 4857000 | 4857000 | 4857000 | 4857000 | 4857000 | 4857000 | 4857000 | 4857000 | 0 | 0
Reliability Upgrade | 1a | 322 | Vermont Electric Power Company |  | 10/2009 | Lamoille County Project | Installation of new Duxbury Substation that involves looping in and out of the Middlesex - Essex 115 kV (K24) line. | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | 08/16/2007 | 02/07/2008 | 3000000 | Part of Lamoille County Project | Part of Lamoille County Project | Part of Lamoille County Project | Part of Lamoille County Project | Part of Lamoille County Project | Part of Lamoille County Project | Part of Lamoille County Project | Part of Lamoille County Project |  | 0
Reliability Upgrade | 1a | 321 | Vermont Electric Power Company |  | 11/2009 | Burlington Project | Burlington 115kV Loop - 5 mi of new line & rebuilding 5 miles of existing line between two existing substations with expansion of the East Avenue substation. | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | 10/24/2006 | 05/23/2007 | 30000000 | 25142000 | 25142000 | 25142000 | 25142000 | 25142000 | 25142000 | 25142000 | 25142000 | 0 | 0
Reliability Upgrade | 1a | 1063 | NSTAR Electric Company |  | 12/2009 |  | Install (2) 115kV 40 MVAR shunt reactors at Edgar Station |  |  |  | Concept | Proposed | Planned | Under Construction | In-service | 05/2009 | No |  |  |  | TBD | 5400000 | 5400000 | 5400000 | 3745000 | 3745000 | -1655000 | 1
Reliability Upgrade | 1a | 777 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Build Wakefield Junction station with four 345/115 kV autotransformers. | Proposed | Concept | Concept | Under Construction | Under Construction | Under Construction | Under Construction | In-service | 2008-04-01 | No | 76840000 | 76840000 | 76840000 | 95000000 | 95000000 | 95000000 | 95000000 | 95000000 | 95000000 | 0 | 0
Reliability Upgrade | 1a | 161 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Loop 345 kV 339 line and 115 kV S-145/T-146 into new Wakefield Jct. Substation. | Proposed | Concept | Concept | Under Construction | Under Construction | Under Construction | Under Construction | In-service | 2008-04-01 | No | 14000000 | 14000000 | 14000000 | 3200000 | 4986431 | 4986431 | 4986431 | 5406900 | 5406900 | 420469 | 0
Reliability Upgrade | 1a | 961 | NSTAR Electric Company |  | 12/2009 | Mystic Breaker Additions Project | Install (2) new 115 kV East Bus breakers #30 and #32 at Mystic. | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | 2008-03-10 | No | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3689000 | 3689000 | -111000 | 0
Reliability Upgrade | 1a | 903 | NSTAR Electric Company |  | 12/2009 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #2, #4, #5, and #16 at Mystic to IPT and separate controls with Boston Gen units #5 and #6. | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | NR | NR | 1240000 | 1240000 | 1240000 | 1240000 | 1240000 | 1240000 | 1240000 | 1576000 | 1576000 | 336000 | 0
Reliability Upgrade | 1a | 930 | National Grid, USA |  | 11/2009 | Central/Western Massachusetts Upgrades | Reconductor Nashua St - Quinsigamond Jct (O141) 115 kV line w/636 ACSS. | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | 12/17/2007 | No | 1562553 | 1562553 | 1562553 | 1765000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 0 | 0
Reliability Upgrade | 1a | 933 | National Grid, USA |  | 01/2010 | Central/Western Massachusetts Upgrades | Reconductor Pratts Jct - Flagg Pond I-135S & J-136S 115 kV lines w/795 ACSS. | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | 12/17/2007 | No | 5952582 | 5952582 | 5952582 | 5952582 | 6137112 | 6137112 | 6137112 | 11200000 | 11200000 | 5062888 | 0
Reliability Upgrade | 1a | 211 | Northeast Utilities |  | 11/2009 | NU LSP - Rood Ave Substation | New Rood Ave (formally Windsor) distribution substation with 115kV terminal modifications. | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | 2008-04-25 | 02/15/2008 | TBD | 9162029 | 9162029 | 9162029 | 9162029 | 9162029 | 9162029 | 8681000 | 8681000 | -481029 | 0
Reliability Upgrade | 1a | 789 | National Grid, USA |  | 12/2009 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Reconductoring of T7 115 kV line. | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | In-service | 2008-04-25 | No | 11200000 | 11200000 | 11200000 | 20900000 | 23304000 | 23304000 | 23304000 | 23304000 | 23304000 | 0 | 0
Reliability Upgrade | 1b | 963 | NSTAR Electric Company |  | 12/2009 | Boston Area 115 kV Enhancements | Add a new 115kV breaker # 11 Relocate 447-509 and add control and protection at Holbrook. | Proposed | Concept | Concept | Concept | Proposed | Proposed | Proposed | In-service | 2009-08-19 | NR | 600000 | 600000 | 600000 | TBD | 3400000 | 4000000 | 4000000 | 1276800 | 1276800 | -2723200 | 0
Generator Interconnection Upgrade | 2b | 863 | Northeast Utilities |  | 2008 | Queue Position 217 | Northfield Mountain 345 kV replace generator step-up transformer (1X) and associated generator equipment. | Concept | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | In-service | 2008-04-25 | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Reliability Upgrade | 1a | 1051 | Central Maine Power Company |  | 09/2009 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Riley 115 kV capacitor bank. |  | Concept | Planned | Planned | Planned | Under Construction | In-service | In-service | 2007-11-30 | No | TBD | TBD | Portion of 5,400,000 (above) | Portion of 5,400,000 (above) | Part of Project 625 | Part of Project 625 | Part of Project 625 | Part of Project 625 | Part of Project 625 |  | 1
Generator Interconnection Upgrade | 2a | 1134 | Central Maine Power Company |  | 09/2009 | Kibby Wind Farm | Separate Section 215 from Section 63 and terminate Section 215 at newly established breaker position in Wyman Hydro S/S, which includes re-rating of Section 215. Expand Bigelow S/S & add capacitor banks at Lakewood, Guilford, Wyman Hydro Station & Sturtevant S/S's. |  |  |  |  | Planned | Under Construction | In-service | In-service | 2006-06-16 | NR |  |  |  |  | NR | NR | NR | NR | NR |  | 1
Reliability Upgrade | 1a | 579 | Central Maine Power Company |  | 06/2008 | Maguire Road Project | Addition of (4) 345 kV breakers at Buxton. | Planned | Planned | In-Service | In-Service |  |  |  |  | 03/01/2007 | No | 5000000 | 5000000 | 11700000 | 11700000 |  |  |  |  | #TBDs | 17
Reliability Upgrade | 1a | 587 | Northeast Utilities |  | 2008-05-13 |  | Install third 345/115-kV autotransformer at Scobie Substation. | Planned | Under Construction | In-Service | In-Service |  |  |  |  | 07/01/2007 | No | TBD | 19257000 | 12948000 | 12948000
Reliability Upgrade | 1a | 282 | Northeast Utilities |  | 2008-05-26 | NU LSP - Weare Substation | Install new 115 kV Weare Street Substation and Jackman capacitors. | Planned | Under Construction | In-Service | In-Service |  |  |  |  | 03/01/2007 | 05/01/2007 | 11643000 | 11633000 | 11633000 | 11633000
Reliability Upgrade | 1a | 580 | Northeast Utilities |  | 2008-05-30 | Scobie Pond to Hudson Reinforcement Project | Install new 115-kV Scobie - Hudson line. | Under Construction | Under Construction | In-Service | In-Service |  |  |  |  | 07/31/2006 | No | 30145000 | 30243000 | 30947000 | 30947000
Reliability Upgrade | 1a | 685 | National Grid, USA |  | 03/2008 |  | New 345 kV gas circuit breaker at Auburn St. Substation on the 335 Line. | Under Construction | Under Construction | In-Service | In-Service |  |  |  |  | 10/01/2006 | 10/01/2006 | 860000 | 860000 | 860000 | 860000
Reliability Upgrade | 1a | 293 | NSTAR Electric Company |  | 04/2008 |  | Upgrade Canal 345-kV breaker #612 to IPT. | Proposed | Under Construction | In-Service | In-Service |  |  |  |  | NR | NR | 450000 | 450000 | 450000 | 450000
Reliability Upgrade | 1a | 56 | Bangor Hydro-Electric Company |  | 12/2007 | Northeast Reliability Interconnect Project | Point Lepreau to Orrington - New 345 kV line as well as capacity expansion from Orrington to Maine Yankee. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 03/01/2003 | 09/28/2007 | 144000000 | 144000000 | 144000000 | 144000000 | 144000000 | 144000000 | 144000000 | 144000000
Reliability Upgrade | 1a | 154 | Central Maine Power Company | Northeast Utilities | 2008-08-01 | Maguire Road Project | Rebuild Louden - Maguire Road 115 kV Line S163. | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 03/01/2007 | No | 3000000 | 3000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000
Reliability Upgrade | 1a | 715 | Central Maine Power Company |  | 2008-08-01 | Maguire Road Project | Rebuild South Gorham to Louden 115 kV Line S219. | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 03/01/2007 | No | 3000000 | 3000000 | 4900000 | 4900000 | 4900000 | 4900000 | 4900000 | 4900000 | #TBDs | 17
Reliability Upgrade | 1a | 716 | Central Maine Power Company |  | 2008-08-01 | Maguire Road Project | Reconductor South Gorham to Louden 115 kV Line S220. | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 03/01/2007 | No | 3000000 | 3000000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000 | 2500000
Reliability Upgrade | 1a | 149 | Central Maine Power Company |  | 2008-08-01 | Maguire Road Project | Convert Maguire Road to a switching substation by replacing switches with breakers. | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 03/01/2007 | No | 7500000 | 7500000 | 17700000 | 17700000 | 17700000 | 17700000 | 17700000 | 17700000
Reliability Upgrade | 1a | 717 | Central Maine Power Company |  | 2008-08-01 | Maguire Road Project | Install a 115 kV 50 MVAr capacitor bank at Maguire Road. | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 03/01/2007 | No | 1500000 | 1500000 | Portion of $17,700,000 (above) | Portion of $17,700,000 (above) | Portion of $17,700,000 (above) | Portion of $17,700,000 (above) | Portion of $17,700,000 (above) | Portion of $17,700,000 (above)
Reliability Upgrade | 1a | 155 | Central Maine Power Company | Northeast Utilities | 01/2009 | Maguire Road Project | Rebuild Three Rivers - Quaker Hill 115 kV Line K197. | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | 03/01/2007 | 2009-01-09 | 3000000 | 3000000 | 5500000 | 5500000 | 5500000 | 5500000 | 5500000 | 5500000
Reliability Upgrade | 1a | 461 | Central Maine Power Company |  | 12/2007 | MEPCO SPS | Redesign/replacement of the Maxcy's Cross Trip and Bucksport Overcurrent Type 1 Special Protection Systems. | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 03/24/2006 | No | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000
Reliability Upgrade | 1a | 147 | Central Maine Power Company |  | 02/2008 | Raymond Substation Project | Add 115/34.5 kV transformer at Raymond Substation on Section 208/209 along with (2) 115 kV in-line circuit breakers. | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 06/01/2006 | No | 4800000 | 1523000 | 1523000 | 1523000 | 1523000 | 1523000 | 1523000 | 1523000
Reliability Upgrade | 1a | 627 | Central Maine Power Company |  | 12/2007 | Rumford-Woodstock-Kimball Road Corridor Project | Reterminate (3) 115 kV lines and add (2) bus-tie breakers at Kimball Road. | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2007-11-30 | 2008-03-31 | TBD | 2441000 | 2441000 | 2441000 | 2441000 | 2441000 | 2441000 | 2441000
Reliability Upgrade | 1a | 910 | Central Maine Power Company |  | 12/2008 | Rumford-Woodstock-Kimball Road Corridor Project | Rebuild Section 211 Woodstock - Rumford. | Proposed | Concept | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 2007-11-30 | No | TBD | TBD | 6800000 | 6800000 | 8400000 | 8400000 | 8400000 | 8400000 |  | 0
Reliability Upgrade | 1a | 626 | Central Maine Power Company |  | 04/2009 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of 115/34.5 kV transformer and six new 115 kV breakers and a half substation at Woodstock. | Proposed | Concept | Planned | Planned | Planned | In-service | In-service | In-service | 2007-11-30 | No | TBD | TBD | 7400000 | 7400000 | 8000000 | 8000000 | 8000000 | 8000000 | 8000000 | 0 | 0
Reliability Upgrade | 1a | 575 | Central Maine Power Company |  | 05/2009 | Heywood Road Project | New Heywood Rd 115kV switchyard with (6) 115kV circuit breakers (3) 115kV line retensionings and 115kV 20 MVAr capacitor bank at Heywood Rd. | Planned | Concept | Concept | Concept | Under Construction | In-service | In-service | In-service | 2009-03-20 | 2009-07-20 | 10100000 | 10100000 | 6100000 | 6100000 | 7000000 | 7000000 | 7000000 | 7000000 | 7000000 | 0 | 1
Reliability Upgrade | 1a | 1127 | Central Maine Power Company |  | 05/2009 | CMP-LSP Newcastle Substation | Add 115/34kV transformer with two 115kV breakers |  | Concept | Planned |  | Under Construction | In-service | In-service | In-service | 2008-08-20 | 2008-08-20 | TBD | TBD | Portion of 5,400,000 (above) |  | 1300000 | 1300000 | 1300000 | 1300000 | 1300000 | 0 | 1
Reliability Upgrade | 1a | 267 | Northeast Utilities | Central Maine Power Company | 2009-08-01 | Y138 Closing | White Lake - Saco Valley (Y138) Line Closing - Add PAR on Y138 at Saco Valley, retension lines, upgrade Beebe terminal, and add capacitor banks at White Lake and Beebe. | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | 01/01/2006 | No | 28565000 | 28412000 | 28412000 | 28412000 | 27775000 | 27775000 | 27775000 | 27775000 | 27775000 | 0 | 0
Reliability Upgrade | 1a | 936 | National Grid, USA |  | 07/2009 | Central/Western Massachusetts Upgrades | Reconductor (P142/P142S) Rolfe Avenue - West Bolyston 115 kV line w/1590 ACSR. | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | 12/17/2007 | No | 2107320 | 2107320 | 2107320 | 2890000 | 3000000 | 3000000 | 3000000 | 3000000 | 3000000 | 0 | 1
Reliability Upgrade | 1a | 923 | National Grid, USA |  | 12/2008 | Auburn Area Transmission System Upgrades | Reconductor 115 kV A94 line and associated substation upgrades. | Proposed | Concept | Concept | Planned | In-Service | In-Service | In-Service | In-Service | 2008-01-28 | No | 2870000 | 2870000 | 2870000 | 3400000 | 2400000 | 2400000 | 2400000 | 2400000 |  | 0
Reliability Upgrade | 1a | 922 | National Grid, USA |  | 02/2009 | Auburn Area Transmission System Upgrades | Reconductor 115kV L1 line and associated substation upgrades. | Proposed | Concept | Concept | Planned | In-Service | In-Service | In-Service | In-Service | 2008-01-28 | No | 700000 | 700000 | 700000 | 1050000 | 800000 | 800000 | 800000 | 800000 |  | 0
Reliability Upgrade | 1a | 543 | National Grid, USA |  | 2008-08-01 | Greater Rhode Island Transmission Reinforcements | New Tower Hill Rd. Substation tapped off of (G185S) 115 kV line. | Proposed | Concept | Planned | In-Service | In-Service | In-Service | In-Service | In-Service | 2008-04-25 | No | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000 | 2400000
Reliability Upgrade | 1a | 774 | National Grid, USA |  | 10/2007 | Merrimack Valley/North Shore Reliability Project | Reconductor G-133W 115 kV line and replace terminal equipment at West Methuen. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 06/01/2007 | No | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000 | 2600000
Reliability Upgrade | 1a | 778 | National Grid, USA |  | 07/2008 | Merrimack Valley/North Shore Reliability Project | Reconductor S-145/T146 115 kV lines between Wakefield Jct. and Golden Hills Tap. | Proposed | Concept | Concept | In-Service | In-Service | In-Service | In-Service | In-Service | 2008-04-01 | No | 3750000 | 3750000 | 3750000 | 3220000 | 3220000 | 3220000 | 3220000 | 3220000
Reliability Upgrade | 1a | 781 | National Grid, USA |  | 10/2008 | Merrimack Valley/North Shore Reliability Project | Install 115 kV 30 MVAr capacitor bank at Revere. | Proposed | Concept | Concept | Planned | In-Service | In-Service | In-Service | In-Service | 2008-04-01 | No | 1900000 | 1900000 | 1900000 | 1500000 | 1727000 | 1727000 | 1727000 | 1727000 |  | 0
Reliability Upgrade | 1a | 169 | National Grid, USA |  | 11/2007 | Southwest Rhode Island Reliability Enhancements | Reconductor W. Kingston - Kenyon 115 kV 1870N line. | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 2005-01-01 | 03/29/2005 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000 | 3500000
Reliability Upgrade | 1a | 170 | National Grid, USA |  | 03/2008 | Southwest Rhode Island Reliability Enhancements | Extend L-190 line to W. Kingston. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 11/10/2004 | 03/29/2005 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000 | 13400000
Reliability Upgrade | 1a | 173 | National Grid, USA |  | 03/2008 | Southwest Rhode Island Reliability Enhancements | Rebuild W. Kingston to include 115 kV ring bus. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 11/10/2004 | 03/29/2005 | 4830000 | 4830000 | 4830000 | 4830000 | 4830000 | 4830000 | 4830000 | 4830000
Reliability Upgrade | 1a | 168 | National Grid, USA |  | 09/2008 | Southwest Rhode Island Reliability Enhancements | Reconductor Kenyon - Wood River 115 kV 1870 line. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 2005-01-01 | 03/29/2005 | 2600000 | 2600000 | 2600000 | 2600000 | 2234232 | 2234232 | 2234232 | 2234232 |  | 0
Reliability Upgrade | 1a | 171 | National Grid, USA |  | 10/2008 | Southwest Rhode Island Reliability Enhancements | Reconductoring L-190 between Kent Co. and Davisville. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 11/10/2004 | 03/29/2005 | 3000000 | 3000000 | 3000000 | 3000000 | 2666291 | 2666291 | 2666291 | 2666291 |  | 0
Reliability Upgrade | 1a | 900 | National Grid, USA |  | 11/2008 | Southwest Rhode Island Reliability Enhancements | Wood River substation upgrades. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 04/07/2007 | 05/07/2007 | 240000 | 240000 | 240000 | 240000 | 130000 | 130000 | 130000 | 130000 |  | 0
Reliability Upgrade | 1a | 899 | National Grid, USA |  | 12/2008 | Southwest Rhode Island Reliability Enhancements | Kenyon substation upgrades. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 04/07/2007 | 05/07/2007 | 278000 | 278000 | 278000 | 278000 | 278000 | 278000 | 278000 | 278000
Reliability Upgrade | 1a | 594 | National Grid, USA |  | 07/2008 |  | Upgrade the Auburn 345 kV breaker #2130 with an IPT breaker. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 10/01/2006 | 10/01/2006 | 720000 | 720000 | 720000 | 720000 | 720000 | 720000 | 720000 | 720000 |  | 0
Reliability Upgrade | 1a | 166 | National Grid, USA |  | 06/2009 |  | Replace (16) 115 kV breakers at Tewksbury 22. | Planned | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | NR | NR | 1500000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 3300000 | 0 | 0
Reliability Upgrade | 1a | 176 | Northeast Utilities |  | 07/2009 | Monadnock Area Reliability Project | New Fitzwilliam 345/115kV substation along with 345 kV breakers. | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | 2007-09-27 | No | 54358000 | 54358000 | 54358000 | 76100000 | 76100000 | 76100000 | 76100000 | 76100000 | 76100000 | 0 | 0
Reliability Upgrade | 1a | 174 | National Grid, USA |  | 06/2009 | Monadnock Area Reliability Project | Reconductor I-135 (Bellows Falls-Monadnock Tap-Flagg Pond) 115 kV line. | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | 03/24/2006 | No | 9600000 | 9600000 | 9600000 | 9600000 | 9600000 | 15778000 | 15778000 | 15778000 | 15778000 | 0 | 0
Reliability Upgrade | 1a | 179 | Northeast Utilities |  | 02/2008 | Monadnock Area Reliability Project | Rebuild 115-kV Jackman to Greggs F-162 line. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 03/24/2006 | No | Portion of 54,358,000 (above) | Portion of 54,358,000 (above) | Portion of 54,358,000 (above) | Portion of 54,358,000 (above) | Portion of 54,358,000 (above) | Portion of 54,358,000 (above) | Portion of 54,358,000 (above) | Portion of 54,358,000 (above)
Reliability Upgrade | 1a | 177 | Northeast Utilities |  | 12/2008 | Monadnock Area Reliability Project | Replace limiting terminal equipment at Webster Substation on line to North Road. | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | 03/24/2006 | No | Portion of 54,358,000 (above) | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 180 | Northeast Utilities |  | 12/2008 | Monadnock Area Reliability Project | Rebuild 115 kV Keene to Swanzey A-152 line. | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | 03/24/2006 | No | Portion of 54,358,000 (above) | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 178 | Northeast Utilities |  | 02/2009 | Monadnock Area Reliability Project | Rebuild 115 kV Garvins to Webster V-182 line. | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 03/24/2006 | No | Portion of 54,358,000 (above) | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 569 | Northeast Utilities-CT |  | 2007 | Norwalk-Glenbrook Cable Project | Replace two 115-kV circuit breakers at Cos Cob. | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 08/01/2005 | No | 500000 | 500000 | 500000 | 500000 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 |  | -500000
Reliability Upgrade | 1a | 243 | Northeast Utilities |  | 09/2008 | Norwalk-Glenbrook Cable Project | Expand and upgrade to BPS and remove SPS at Glenbrook 115 kV substation. | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 08/01/2005 | No | 8350000 | 8390000 | 8390000 | 8390000 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 |  | -8390000
Reliability Upgrade | 1a | 570 | Northeast Utilities |  | 10/2008 | Norwalk-Glenbrook Cable Project | Add second high speed relay system on the 1450 line. | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 08/01/2005 | No | 792000 | 788000 | 788000 | 788000 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 |  | -788000
Reliability Upgrade | 1a | 571 | Northeast Utilities |  | 12/2008 | Norwalk-Glenbrook Cable Project | Upgrade Flax Hill Substation to BPS. | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 08/01/2005 | No | 2175000 | 2175000 | 2175000 | 2175000 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 | Part of Norwalk-Glenbrook Cable Project 3 |  | -2175000
Reliability Upgrade | 1a | 248 | Northeast Utilities |  | 12/2008 | Norwalk-Glenbrook Cable Project | Install two new 115 kV cables from Norwalk to Glenbrook (accommodate 345 kV class cable). | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 08/01/2005 | No | 183230000 | 222850000 | 222850000 | 222850000 | 249,372,000 3 | 249,372,000 3 | 249,372,000 3 | 249,372,000 3 |  | -222850000
Reliability Upgrade | 1a | 208 | Northeast Utilities |  | 12/2008 | NU LSP - Oxford Substation | Install new Oxford (previously Jack's Hill) 115 kV substation. | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | 06/01/2007 | 5710287 | 5710287 | 5710287 | 5710287 | 4459000 | 4459000 | 4459000 | 4459000 |  | 0
Reliability Upgrade | 1a | 201 | Northeast Utilities |  | 05/2008 | NU LSP - Wilton Substation | Install new 115 kV Wilton Substation. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 2008-04-25 | 08/01/2006 | 3915000 | 3915000 | 3915000 | 3915000 | 3915000 | 3915000 | 3915000 | 3915000
Reliability Upgrade | 1a | 551 | Northeast Utilities |  | 10/2007 | Southwest Connecticut Reliability Project PH II (M-N) | Rebuild the 1466 115-kV line from East Meriden to North Wallingford and the 1588 115-kV rebuild from North Wallingford to Colony. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 04/01/2007 | No | 805000 | 805000 | 805000 | 805000 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 |  | -805000
Reliability Upgrade | 1a | 236 | Northeast Utilities |  | 2008-03-01 | Southwest Connecticut Reliability Project PH II (M-N) | Rebuild 115 kV lines (1640,1685,1610) between Devon and Cook Hill Jct. (UG section of 1640 near Cook Hill). | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 228 | Northeast Utilities |  | 2008-03-19 | Southwest Connecticut Reliability Project PH II (M-N) | Installation of new Beseck Jct. 345 kV switching station in Wallingford. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 04/01/2007 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 222 | Northeast Utilities |  | 2008-03-27 | Southwest Connecticut Reliability Project PH II (M-N) | Install new 345 kV line from Scovill Rock to Chestnut Jct. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | 1047000000 | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 223 | Northeast Utilities | United Illuminating Company | 2008-03-28 | Southwest Connecticut Reliability Project PH II (M-N) | Install (2) new 345 kV lines from Black Pond Jct. to Beseck Jct. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 02/01/2007 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 225 | Northeast Utilities |  | 2008-03-28 | Southwest Connecticut Reliability Project PH II (M-N) | Install new 345 kV line from Oxbow Jct. to Beseck Jct. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 237 | Northeast Utilities |  | 2008-04-28 | Southwest Connecticut Reliability Project PH II (M-N) | Rebuild 115-kV lines-1975 from Beseck to Oxbow Junction and 1655 from East Wallingford Jct. to New Haven Jct. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 244 | Northeast Utilities |  | 2008-06-20 | Southwest Connecticut Reliability Project PH II (M-N) | Reconductor 115 kV 1570 and 1575 line taps into Beacon Falls Substation. | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 2008-04-25 | No | 5887000 | 5887000 | 5692000 | 5692000 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 |  | -5692000
Reliability Upgrade | 1a | 239 | Northeast Utilities |  | 07/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install (1) new 115 kV circuit breaker at Devon Substation in series with 7R-2T. | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | 5206000 | 5206000 | 5009000 | 5009000 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 |  | -5009000
Reliability Upgrade | 1a | 245 | Northeast Utilities |  | 07/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Disconnect Milford Power from Devon Substation and reconnect to East Devon Jct. Substation. | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 227 | Northeast Utilities |  | 2008-08-01 | Southwest Connecticut Reliability Project PH II (M-N) | Install new 345 kV line from Beseck Jct. to East Devon. | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 229 | Northeast Utilities | United Illuminating Company | 2008-08-01 | Southwest Connecticut Reliability Project PH II (M-N) | Install new East Devon 345 kV substation and new East Devon 115 kV substation in Milford. | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 232 | Northeast Utilities |  | 09/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install two 115 kV circuits between East Devon and Devon. | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | 1047000000 | 1047000000 | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 246 | Northeast Utilities |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Add second 345/115 kV autotransformer at Norwalk Substation along with shunt reactors and 345 kV circuit breakers. | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | 1047000000 | $978,182,000 4 | $978,182,000 4 | $978,182,000 4 | $978,182,000 4 |  | 0
Reliability Upgrade | 1a | 226 | Northeast Utilities | United Illuminating Company | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install two 345 kV underground cables from Singer(UI) to Norwalk. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 235 | Northeast Utilities |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Expand Norwalk 345-kV substation and install transfer trip relaying scheme on the 1389 115 kV line between Norwalk and Flax Hill. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 247 | Northeast Utilities |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Replace Norwalk Harbor 138/115 kV autotransformer. | Planned | Planned | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | 8351000 | 8351000 | 8351000 | 8351000 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 |  | -8351000
Reliability Upgrade | 1a | 684 | Northeast Utilities |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Replace (6) 115 kV breakers (4-Glenbrook, 1-Glenbrook Statcom, 1-Southington #1) and (3) 345-kV circuit breakers at Millstone and replace (4) 345- kV breakers with 500-kV breakers at Long Mountain substation. | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | 11321000 | 11321000 | 11321000 | 11321000 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 | Part of SWCT (M-N) Reliability Project 4 |  | -11321000
Reliability Upgrade | 1a | 202 | Northeast Utilities |  | 05/2008 |  | Install new 345/115 kV autotransformer at Barbour Hill Substation. | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 09/30/2006 | 2008-02-07 | 44153000 | 44153000 | 44153000 | 44153000 | 44153000 | 44153000 | 44153000 | 44153000
Reliability Upgrade | 1a | 104 | Northeast Utilities |  | 07/2008 |  | Replace 138-kV Norwwalk (CT)-Northport(NY) 1385 cable. | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 2002-12-01 | 2007-06-01 | 71743727 | 71743727 | 71743727 | 71743727 | 71743727 | 71743727 | 71743727 | 71743727
Reliability Upgrade | 1a | 250 | Northeast Utilities |  | 12/2008 |  | Add a 345 kV breaker at Ludlow Substation. | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | 06/01/2007 | 2007-08-01 | 1800000 | 1644885 | 1644885 | 1644885 | 1644885 | 1644885 | 1644885 | 1644885
Reliability Upgrade | 1a | 1009 | Northeast Utilities |  | 05/2009 |  | Install a 2% reactor on the North Bloomfield-Canton 115kV line and also replacement fo the Frostbridge 345/115kV autotransformer | Proposed | Concept | Planned | Under Construction | Under Construction | In-service | In-service | In-service | 2007-10-20 | 2009-10-16 | TBD | TBD | 2075000 | 2075000 | 3638000 | 3089000 | 3089000 | 3089000 | 3089000 | 0 | 0
Reliability Upgrade | 1a | 203 | Northeast Utilities |  | 05/2009 | NU LSP - Stepstone Substation | Install new Stepstone 115 kV substation in Guilford. | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | 2005-11-08 | 2006-04-24 | 4465000 | 4465000 | 4465000 | 4465000 | 6332000 | 6332000 | 6332000 | 6332000 | 6332000 | 0 | 0
Reliability Upgrade | 1a | 841 | NSTAR Electric Company |  | 11/2008 | Mystic Breaker Additions Project | Install (2) new 115 kV West Bus breakers #29 and #31 at Mystic. | Proposed | Planned | Planned | Planned | In-Service | In-Service | In-Service | In-Service | 2008-03-10 | No | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000 | 2300000
Reliability Upgrade | 1a | 1040 | NSTAR Electric Company |  | 12/2008 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #11, #8, #17 and #3 at Mystic to IPT | Planned | Planned | Planned | Planned | In-Service | In-Service | In-Service | In-Service | NR | NR | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000 | 990000
Reliability Upgrade | 1a | 116 | NSTAR Electric Company |  | 04/2009 | NSTAR 345 kV Transmission Reliability Project | Add 2nd 345 kV UG Cables from Stoughton to Mattapan Sq.to K Street and install another new autotransformer at K. St. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 02/10/2005 | 09/15/2005 | 283144600 | 283144600 | 283144600 | 307900000 | 307900000 | 307900000 | 307900000 | 307900000
Reliability Upgrade | 1a | 572 | NSTAR Electric Company |  | 04/2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 345 kV 160 MVAR shunt reactors at Stoughton. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 02/10/2005 | 09/15/2005 | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 573 | NSTAR Electric Company |  | 04/2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 345 kV 160 MVAR shunt reactors at K St. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 02/10/2005 | 09/15/2005 | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 772 | NSTAR Electric Company |  | 04/2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 115 kV breaker at K St. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 02/01/2005 | 09/01/2005 | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 574 | NSTAR Electric Company |  | 12/2007 | NSTAR LSP - Colburn St Substation | Add 4th 115/14 kV transformer and (2) 115 kV breakers at Colburn St. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 12/01/2004 | NR | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000
Reliability Upgrade | 1a | 694 | NSTAR Electric Company |  | 06/2008 | Short Term Lower SEMA Upgrades | Add new 115 kV line from Brook Street to Auburn Street. | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 08/17/2007 | No | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000
Reliability Upgrade | 1a | 833 | NSTAR Electric Company |  | 06/2008 | Short Term Lower SEMA Upgrades | Add (5) new 115 kV circuit breakers at Brook Street. | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 08/17/2007 | No | 7900000 | 7900000 | 7900000 | 7900000 | 7900000 | 7900000 | 7900000 | 7900000
Reliability Upgrade | 1a | 960 | NSTAR Electric Company |  | 06/2008 | Short Term Lower SEMA Upgrades | Install a new 115kV line termination at Auburn St south bus. | Planned | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 08/17/2007 | No | 3060000 | 3060000 | 3060000 | 3060000 | 3060000 | 3060000 | 3060000 | 3060000
Reliability Upgrade | 1a | 832 | NSTAR Electric Company |  | 07/2009 | Short Term Lower SEMA Upgrades | Add(1) 115kV SVC (0-112 MVARs lagging) at Barnstable. | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | 08/17/2007 | No | 16000000 | 16000000 | 16000000 | 16000000 | $86.6 M (Total NSTAR Project Cost | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade | 82000000 | -4600000 | 0
Reliability Upgrade | 1a | 695 | NSTAR Electric Company |  | 07/2009 | Short Term Lower SEMA Upgrades | Loop (355) 345 kV line in and out of Carver Substation and add (5) new 345 kV circuit breakers at Carver substation. | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | 08/17/2007 | No | 10800000 | 10800000 | 10800000 | 10800000 | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | -4600000 | 1
Reliability Upgrade | 1a | 830 | NSTAR Electric Company |  | 07/2009 | Short Term Lower SEMA Upgrades | Add a second 345/115 kV Auto transformer at Carver substation and add (1) new 345 kV circuit breaker and (3) new 115 kV circuit breakers at Carver substation. | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | 08/17/2007 | No | 8000000 | 8000000 | 8000000 | 8000000 | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA |  | 1
Reliability Upgrade | 1a | 831 | NSTAR Electric Company |  | 07/2009 | Short Term Lower SEMA Upgrades | Add a second 115 kV line from Carver to Tremont and add (2) new 115 kV circuit breakers at Carver substation and (1) new 115 kV circuit breaker at Tremont substation. | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | 08/17/2007 | No | 2500000 | 2500000 | 2500000 | 2500000 | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA |  | 1
Reliability Upgrade | 1a | 713 | NSTAR Electric Company |  | 09/2007 |  | Add 115 kV 20 MVAr capacitor bank at Harwich/Harwich Tap. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 06/01/2007 | NR | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000 | 900000
Reliability Upgrade | 1a | 838 | NSTAR Electric Company |  | 10/2007 |  | Upgrade Canal 345 kV breaker #512 to IPT. | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000
Reliability Upgrade | 1a | 500 | NSTAR Electric Company |  | 11/2007 |  | Install new 115 kV circuit breaker at Sandwich. | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2008-02-05 | NR | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000 | 250000
Reliability Upgrade | 1a | 834 | NSTAR Electric Company |  | 06/2008 |  | Upgrade Canal 345 kV breaker #112 to IPT. | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | NR | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000
Reliability Upgrade | 1a | 1064 | NSTAR Electric Company |  | 04/2009 |  | Install (1) 345kV 160 MVAR shunt reactor at Mystic Station |  |  |  | Planned | Planned | In-service | In-service | In-service | 2008-09-26 | No |  |  |  | 8000000 | 10400000 | 10400000 | 10400000 | 10400000 | 10400000 | 0 | 0
Reliability Upgrade | 1a | 302 | NSTAR Electric Company |  | 05/2009 | Boston Area 115 kV Enhancements | DCT separation of Framingham to Speen St. 433-507 circuit. | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | 01/18/2005 | 03/01/2005 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 3100000 | 0 | 0
Reliability Upgrade | 1a | 238 | United Illuminating Company |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Build new Singer 345 kV substation with (12) circuit breakers, (2) autos, (4) shunt reactors along with reconnecting Bridgeport Energy thru one of the new autos. Includes 115 kV connection from Singer to Pequonnock substation. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | 147000000 | 147000000 | 162264000 | 162264000 | 162264000 | 162264000 | 162264000 | 162264000
Reliability Upgrade | 1a | 224 | United Illuminating Company | Northeast Utilities | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install new 345 kV line from East Devon to Singer(UI). | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/14/2006 | No | 159000000 | 159000000 | 157476000 | 157476000 | 157476000 | 157476000 | 157476000 | 157476000
Reliability Upgrade | 1a | 313 | United Illuminating Company | Northeast Utilities | 06/2008 | UI LSP - Trumbull Substation | New Trumbull 115/13.8 kV Substation and 115 kV switching station. | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 2008-03-13 | No | 5500000 | 8930000 | 8930000 | 8930000 | 8930000 | 8930000 | 8930000 | 8930000
Reliability Upgrade | 1a | 845 | United Illuminating Company |  | 05/2008 |  | Replace Quinnipiac 115 kV Oil Circuit Breaker. | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | NR | 400000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000 | 650000
Reliability Upgrade | 1a | 846 | United Illuminating Company |  | 11/2008 |  | Replace Mix Avenue 115 kV Oil Circuit Breaker & foundation. | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | NR | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 |  | 0
Reliability Upgrade | 1a | 410 | Vermont Electric Power Company |  | 12/2004 | Northwest Vermont Reliability Project | Sandbar PAR | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 01/10/2003 | 03/31/2003 | 6100000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 |  | 0
Reliability Upgrade | 1a | 132 | Vermont Electric Power Company |  | 12/2005 | Northwest Vermont Reliability Project | Hartford 115kV Breaker - Replace an existing 115kV motorized SCADA controlled disconnect switch with a circuit breaker at Hartford substation on the line toward Wilder sub and add one 25 MVAR cap. Bank | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 01/10/2003 | 03/31/2003 | 2200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 | 3200000 |  | 0
Reliability Upgrade | 1a | 133 | Vermont Electric Power Company |  | 12/2005 | Northwest Vermont Reliability Project | Essex K24 Line Breaker | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 01/10/2003 | 03/31/2003 | 800000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 |  | 0
Reliability Upgrade | 1a | 135 | Vermont Electric Power Company |  | 12/2006 | Northwest Vermont Reliability Project | Blissville PAR | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 01/10/2003 | 2006-12-18 | 8400000 | 10100000 | 10100000 | 10100000 | 10100000 | 10100000 | 10100000 | 10100000 |  | 0
Reliability Upgrade | 1a | 137 | Vermont Electric Power Company |  | 01/2007 | Northwest Vermont Reliability Project | New Haven-West Rutland 345kV line, 345/115 New Haven Sub with 115kV ring bus, and close the 345 kV ring bus at West Rutland | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 01/10/2003 | 2006-12-18 | 66400000 | 83300000 | 83300000 | 83300000 | 83300000 | 83300000 | 83300000 | 83300000 |  | 0
Reliability Upgrade | 1a | 134 | Vermont Electric Power Company |  | 11/2007 | Northwest Vermont Reliability Project | Convert Williston into a ring bus configuration. | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 01/10/2003 | 03/31/2003 | 4300000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 | 5400000 |  | 0
Reliability Upgrade | 1a | 138 | Vermont Electric Power Company |  | 12/2008 | Northwest Vermont Reliability Project | N. Haven - Vergennes - Q. City 115 kV line. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/10/2003 | 2006-12-18 | 56200000 | 70200000 | 70200000 | 70200000 | 70200000 | 70200000 | 70200000 | 70200000 |  | 0
Reliability Upgrade | 1a | 136 | Vermont Electric Power Company |  | 04/2009 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 1: two 115 kV PARs, four 25 MVAR Cap. banks, four +25/-12.5 MVAR synchronous condenders, and two 230/115 transformers. | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | 01/10/2003 | 03/31/2003 | 60800000 | 62400000 | 62400000 | 62400000 | 62400000 | 62400000 | 62400000 | 62400000 |  | 0
Reliability Upgrade | 1a | 182 | Vermont Electric Power Company |  | 09/2009 | Monadnock Area Reliability Project | Upgrade bus cable at N. Rutland and K35 115 kV breaker at Rutland. | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | 03/24/2006 | NR | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 0 | 0
Generator Interconnection Upgrade | 2a | 847 | Bangor Hydro-Electric Company |  | 12/2008 | Stetson Wind | Interconnect 60 MW of wind via 115 kV generator lead into Keene Road Substation. | Proposed | Planned | Planned | Planned | In-Service | In-Service | In-Service | In-Service | 07/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2a | 621 | Northeast Utilities |  | 10/2007 | AL Pierce | Interconnection to Wallingford (CMEEC) substation. | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2007-03-08 | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2a | 727 | Northeast Utilities |  | 12/2007 | CL&P P&WA Aircraft Substation | CL&p P&WA Aircraft Substation. | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 01/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2a | 728 | Northeast Utilities |  | 06/2008 | Cos Cob Redevelopment | Installation of a second high-speed protection system on the 1440 115 kV line. | Proposed | Planned | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | 06/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR
CANCELLED PROJECTS
Elective | 4b | 984 | Central Maine Power Company | Maine Public Service | TBD | MEPCO-MPS 345 kV Interconnection | MEPCO-MPS 345 kV Interconnection. | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Reliability Upgrade | 1b | 275 | Northeast Utilities |  | TBD |  | Merrimack 115-kV substation - Protection Separation Upgrade. | Proposed | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD |  | 0
Generator Interconnection Upgrade | 2a | 327 | Central Maine Power Company |  | 12/2010 | Queue Position 138 | Separate Section 215 from Section 63 and terminate Section 215 at newly established breaker position in Wyman Hydro S/S, which includes re-rating of Section 215. Expand Bigelow S/S and add capacitor banks at Lakewood, Guilford, and Sturtevant S/S's. |  |  |  | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | 2003-12-03 | NR |  |  |  |  | NR | NR | NR | NR | 0
Reliability Upgrade | 1b | 912 | Central Maine Power Company |  | 12/2009 | CMP LSP - Anson Substation | Add 115 kV circuit breakers and transformer at Anson Section 63. | Proposed | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | TBD | TBD | TBD | NR | NR | NR | NR |  | 1
Reliability Upgrade | 1b | 106 | Northeast Utilities |  | TBD |  | Upgrade the Southwest Hartford Substation to Bulk Power System standards (BPS). | Planned | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | 08/04/2004 | No | TBD | TBD | TBD | TBD | TBD | NR | NR | NR | NR |  | 1
Reliability Upgrade | 1b | 1069 | NSTAR Electric Company |  | 07/2011 | NPCC BPS Compliance | Bourne Station |  |  |  | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | No | No |  |  |  | 8800000 | NR | NR | NR | NR | NR |  | 1
Reliability Upgrade | 1a | 187 | Vermont Electric Power Company |  | 12/2010 | Monadnock Area Reliability Project | Coolidge +/- 75 MVAr STATCOM with 50 MVArs of new capacitors at Coolidge and functional dynamic equivalent. | Planned | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | 03/24/2006 | No | 30000000 | 50000000 | 50000000 | NR | NR | NR | NR | NR | NR | -50000000 | 1
Reliability Upgrade | 1b | 920 | National Grid, USA |  | 06/2010 | Auburn Area Transmission System Upgrades | Belmont substation - Upgrade Bus work. | Proposed | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | 2008-01-28 | No | 470000 | 470000 | 470000 | NR | NR | NR | NR | NR | NR | -470000 | 1
Reliability Upgrade | 1b | 1117 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install 115kV 50 MVAR capacitor bank at Falmouth |  |  |  | Concept | Proposed | Proposed | Cancelled | Cancelled | No | No | 5000000 | 5000000 | 5000000 | TBD | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA |  | 0
Reliability Upgrade | 1b | 337 | NSTAR Electric Company |  | 12/2010 | Long Term Lower SEMA Upgrades | Canal to Oak Street #399 345 kV line. | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR |  | 1
Reliability Upgrade | 1b | 338 | NSTAR Electric Company |  | 12/2010 | Long Term Lower SEMA Upgrades | Move Canal 345/115 Auto-transformer to Oak Street. | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | TBD | NR | NR | NR | NR | NR | NR |  | 1
Reliability Upgrade | 1b | 967 | NSTAR Electric Company |  | 12/2010 | Boston Area 115 kV Enhancements | Reconductor N. Woburn Tap to Reading Tap (Line 211-503 & 211-504). | Proposed | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | 2000000 | 2000000 | 2000000 | NR | NR | NR | NR | NR | NR | -2000000 | 1
Reliability Upgrade | 1b | 808 | Northeast Utilities |  | TBD |  | Upgrade Scitico substation. | Proposed | Concept | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | 9000000 | NR | NR | NR | NR | NR | NR | -9000000 | 1
Generator Interconnection Upgrade | 2b | 861 | Northeast Utilities |  | 01/2010 | Queue Position 190 | Mount Tom - W Mass. Mt. Tom 115 kV Substation. | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2b | 869 | Northeast Utilities |  | 06/2013 | Queue Position 226 | Rebuild 345 kV 326 Line | Proposed | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2b | 1041 | Northeast Utilities |  | 06/2013 | Queue Position 226 | Rebuild 115 kV U181 Line | Proposed | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Reliability Upgrade | 1b | 258 | Northeast Utilities |  | 2010-2011 | Springfield 115 kV Reinforcements | Retire low capacity Breckwood to East Springfield 115-kV cable. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 686 | Northeast Utilities |  | 2010-2011 | Springfield 115 kV Reinforcements | Installation of a new 115-kV cable circuit between East Springfield and Clinton Substations. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 827 | Northeast Utilities |  | 2010-2011 | Springfield 115 kV Reinforcements | Installation of two 115-kV cable circuits between East Springfield and Breckwood substations. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 496 | Northeast Utilities |  | 2011-2013 | Springfield 115 kV Reinforcements | Additional uprating or rebuilding of the existing 115 kV overhead lines in the Springfield area. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 822 | Massachusetts Municipal Whol | Northeast Utilities | 2011-2013 | NEEWS (Greater Springfield Reliability Project) | Install two new 115-kV lines from Stony Brook (MMWEC) to line tap#1113 and tap #1134. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 999 | Northeast Utilities |  | 2011-2013 | NEEWS (Greater Springfield Reliability Project) | Replace West Springfield to Breckwood 115 kV cable. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 821 | Northeast Utilities |  | 2011-2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild/Reconductor a portion of the Fairmont 1134 and 1113 115-kV lines up to where it taps the new Stony Brook lines. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 813 | Northeast Utilities |  | 2011-2013 | NEEWS (Central Connecticut Reliability Project) | Add 345-kV shunt reactors at Frost Bridge, and North Bloomfield substations. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 815 | Northeast Utilities |  | 2011-2013 | NEEWS (Central Connecticut Reliability Project) | Reconductor the East Hartford to the Riverside tap 1786 115-kV line. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 803 | Northeast Utilities |  | 2011-2013 | NEEWS (Interstate Reliability Project) | Reconfigure the Millstone to Manchester 310 line into Card 345-kV substation. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 805 | Northeast Utilities |  | 2011-2013 | NEEWS (Interstate Reliability Project) | Install new Northwest Hartford to Southwest Hartford 115kV cable. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 806 | Northeast Utilities |  | 2011-2013 | NEEWS (Interstate Reliability Project) | Install new Southwest Hartford to South Meadow 115 kV Cable. | Proposed | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1126 | Northeast Utilities |  | TBD | Queue Position 161-4 | Two units and repowering of #6 Montville 345kV Substation | Planned | Concept | Concept |  | Proposed | Cancelled | Cancelled | Cancelled | 2008-06-09 | NR | TBD | TBD | TBD |  | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 316 | United Illuminating Company |  | 06/2012 |  | New Fairfield 115/13.8 kV substation | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | No | No | 5500000 | 14030000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 0 | 0
Reliability Upgrade | 1b | 977 | United Illuminating Company |  | 06/2013 |  | New Orange 115/13.8 kV substation | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | No | No | 5500000 | 14450000 | 7550000 | 7550000 | 7550000 | 7550000 | 7550000 | 7550000 | 7550000 | 0 | 0
Reliability Upgrade | 1b | 980 | United Illuminating Company |  | 06/2014 |  | New Hamden 115/13.8 kV substation. | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | No | No | 5500000 | 15330000 | 7750000 | 7750000 | 7750000 | 7750000 | 7750000 | 7750000 | 7750000 | 0 | 0
Reliability Upgrade | 1b | 317 | United Illuminating Company |  | 06/2014 |  | New North Branford 115/13.8-kV substation. | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | No | No | 4000000 | 16260000 | 7750000 | 7750000 | 7750000 | 7750000 | 7750000 | 7750000 | 7750000 | 0 | 0
Reliability Upgrade | 1a | 608 | United Illuminating Company |  | 12/2012 |  | Upgrade Water Street, Broadway, Mill River, West River, Baird, Bridgeport RESCO, and Devon Tie substations to BPS standards. | Planned | Planned | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | 2006-01-20 | No | 19500000 | 19500000 | NR | NR | NR | NR | NR | NR
Reliability Upgrade | 1b | 249 | Northeast Utilities |  | TBD |  | Install new 115 kV line from Norwalk Harbor Station to Glenbrook Substation (accommodate 345 kV class cable). | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | No | No | TBD | TBD | NR | NR | NR | NR | NR | NR
Generators w/ NO Feasibility Study completed - hide from Project List for now!
Generator Interconnection Upgrade | 2b | 737 | Northeast Utilities |  | 06/2010 | Queue Position 161 | Montville Substation. | Proposed | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1017 | Northeast Utilities |  | 09/2009 | Queue Position 222 | Haddam Neck-Southington 345-kV line. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 882 | United Illuminating Company | Northeast Utilities | 12/2009 | Queue Position 193 | Ansonia - UI Ansonia 115 kV substation. | Concept | Proposed | Proposed | Proposed | Proposed |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 982 | Northeast Utilities |  | 05/2010 | Queue Position 181 | Lake Road #4 - tap the 345 kV line. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1037 | Vermont Electric Power Company | Central Vermont Public Service | 12/2010 | Queue Position 134 | Installation of 3-breaker 115kV ring bus interconnection on the Bennington-Searsburg 69kV Y25N Line. |  | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR | NR |  | 0
Generator Interconnection Upgrade | 2b | 619 | Northeast Utilities |  | 07/2010 | Queue Position 125 | Interconnection to CL&P's Norwalk Harbor substation. | Proposed | Proposed | Proposed | Proposed | Proposed |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generators w/ NO interconnection upgrades required! (RESERVE IN SPITS and REMOVE FROM PROJECT LISTING)
Generator Interconnection Upgrade | 2b | 730 | Northeast Utilities |  | 05/2008 | Queue Position 160 | CL&P Middletown Substation. | Concept | Proposed | Proposed | Proposed | Proposed |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 849 | Northeast Utilities |  | 12/2008 | Queue Position 186 | Shepaug - 115 kV substation. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 857 | Northeast Utilities |  | 06/2010 | Queue Position 186 | Shepaug - 115 kV substation. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 736 | Northeast Utilities |  | 01/2009 | Queue Position 161 | CL&P Middletown Substation or CL&P Scovill Rock Substation. | Proposed | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 850 | Northeast Utilities |  | 06/2009 | Queue Position 175 | CL&P Stony Hill 115 kV Substation or 345 kV line # 321. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 852 | Northeast Utilities |  | 07/2009 | Queue Position 191 | Watertown - 115 kV line #1238 or #1191. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 853 | Northeast Utilities |  | 07/2009 | Queue Position 199 | CL&P Baldwin 115kV substation. | Concept | Concept | Proposed | Proposed | Proposed |  |  |  | 2008-06-09 | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 620 | Northeast Utilities |  | 12/2009 | Queue Position 145 | Interconnection to CL&P's 115-kV 1607 line. | Proposed | Proposed | Proposed | Proposed | Proposed |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 854 | Northeast Utilities |  | 01/2010 | Queue Position 190 | Falls Village - 69 kV Substation. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 855 | Northeast Utilities |  | 01/2010 | Queue Position 190 | Stevenson - CL&P Stevenson 115 kV Substation. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 856 | Northeast Utilities |  | 01/2010 | Queue Position 190 | Tunnel- CL&P Tunnel 115 kV Substation. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 851 | Northeast Utilities |  | 06/2010 | Queue Position 182 | CL&P Stony Hill 115 kV Substation #175. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 858 | Northeast Utilities |  | 06/2010 | Queue Position 192 | CPV Danbury - CL&P Plumtree Substation. | Concept | Concept | Concept | Concept | Concept |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2b | 883 | United Illuminating Company |  | 2009 | Queue Position 159 | Bridgeport Energy II - UI 345 kV Singer Substation. | Concept | Proposed | Proposed | Proposed | Proposed |  |  |  | No | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2a | 848 | Northeast Utilities |  | 11/2008 | Queue Position 183 | Millstone 3 - 345 kV Substation. | Concept | Proposed | Proposed | Proposed | Proposed |  |  |  | 08/15/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2a | 733 | Northeast Utilities |  | 12/2008 | Plainfield Renewable Energy Project | CL&P Fry Brook Substation. | Proposed | Planned | Planned | Planned | Planned |  |  |  | 06/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2a | 735 | Northeast Utilities |  | 01/2009 | Middletown 11 | NU Middletown Substation. | Proposed | Planned | Planned | Planned | Planned |  |  |  | 12/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR
Generator Interconnection Upgrade | 2a | 734 | Northeast Utilities |  | 03/2009 | Devon Units | Devon Substation. | Proposed | Planned | Planned | Planned | Planned |  |  |  | 12/01/2007 | NR | NR | NR | NR | NR | NR | NR | NR | NR
REMOVE FROM SPITS and PROJECT LISTING
Reliability Upgrade | 1b | 817 (merged w/ ID 816) | Northeast Utilities |  | 2011-2013 | NEEWS (Greater Springfield Reliability Project) | Reconfigure/Modify North Bloomfield, Northwest Hartford, Southwest Hartford and South Meadow 115-kV substations. | Proposed | Concept | Concept | Concept | Concept |  |  |  | No | No | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Reliability Upgrade | 1a | 1081 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | BPS requirements for Springfield stations |  |  | Proposed | Planned | Planned |  |  |  | 2008-09-24 | No |  |  | TBD | 18500000 | 18500000 | 18500000 | 18500000 | 18500000 | 18500000 | 18500000 | 1
Reliability Upgrade | 1a | 1082 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | BPS Requirements for Connecticut stations |  |  | Proposed | Planned | Planned |  |  |  | 2008-09-24 | No |  |  | TBD | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 1
Reliability Upgrade | 1a | 1083 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Central Connecticut Relaibility Project) | BPS Requirements |  |  | Proposed | Planned | Planned |  |  |  | 2008-09-24 | No |  |  | TBD | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 6200000 | 1
Reliability Upgrade | 1a | 1093 | Northeast Utilities |  | 2011-2013 | NEEWS (Ancillary Project) | NU's BPS Requirements for NEEWS |  |  |  | Proposed | Proposed |  |  |  | No | No |  |  |  | 39000000 | 39000000 | 39000000 | 39000000 | 39000000
KEEP IN SPITS and DON'T SHOW I/S for JUL-08 PROJECT LISTING
Reliability Upgrade | 1a | 611 | Northeast Utilities |  | 2006-11-01 | Southwest Connecticut Reliability Project PH II (M-N) | Remove a portion of the 115 kV 1690 line from Devon to Cook Hill Jct. | Under Construction | Under Construction | In-Service | In-Service | In-Service |  |  |  | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 230 | Northeast Utilities |  | 2006-12-22 | Southwest Connecticut Reliability Project PH II (M-N) | Expand Scovill Rock 345 kV substation. | Under Construction | Under Construction | In-Service | In-Service | In-Service |  |  |  | 04/01/2007 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 231 | Northeast Utilities | United Illuminating Company | 2007-10-22 | Southwest Connecticut Reliability Project PH II (M-N) | Rebuild 115 kV Devon to Devon Switching Station(UI) 1780 and 1790 lines. | Planned | Under Construction | In-Service | In-Service | In-Service |  |  |  | 01/14/2006 | No | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 6a | 780 | National Grid, USA |  | 2008-08-01 | Merrimack Valley/North Shore Reliability Project | Revise Melrose supply configuration. | Proposed | Concept | Concept | In-Service | In-Service |  |  |  | 2008-04-01 | No | 4100000 | 4100000 | 4100000 | 5100000 | 5100000 | 5100000 | 5100000 | 5100000 |  | -4100000
Reliability Upgrade | 6a | 1052 | National Grid, USA |  | 11/2010 | Merrimack Valley/North Shore Reliability Project | Reconductor I-161 115 kV line from Meadowbrook to North Chelmsford. |  | Concept | Concept | Planned | Planned |  |  |  | 2008-06-27 | No |  | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project
Reliability Upgrade | 6a | 1053 | National Grid, USA |  | 11/2010 | Merrimack Valley/North Shore Reliability Project | Reconductor A-153 115 kV line from Meadowbrook to North Chelmsford. |  | Concept | Concept | Planned | Planned |  |  |  | 2008-06-27 | No |  | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project | Part of Merrimack Valley/North Shore Project
Notes
1 Project pending solution documentation for the Greater Rhode Island Transmission Reinforcements.
2 The Northeast Utilities' estimated costs for the NEEWS BPS upgrades are shared among the Greater Springfield, Central Connecticut, and Interstate portions of the NEEWS Project.
3 The total TCA (NU-07-TCA-24) PTF cost is $234.2 million for the Norwalk - Glenbrook Project. The forecasted PTF cost is $249.4 million.
4 The total TCA (NU-08-TCA-01) PTF cost is $1.05 billion for Northeast Utilities portion of the Middletown-Norwalk Project. The forecasted PTF cost is $978.2 million.
5 The project was completed in December 2009, and was energized and placed in service under the jurisdicition of CONVEX but has since been isolated and de-energized due to a significant incident at the power plant
Local Project Listing Links
| NSTAR: |  | http://www.nstar.com/business/rates_tariffs/open_access/
| CMP: |  | http://www.cmpco.com/SuppliersAndPartners/TransmissionServices/CMPTransmissionSvc/lsp.html
| BHE: |  | http://www.bhe.com/data/OASIS/LSP.html
| VELCO: |  | http://www.vermontspc.com/default.aspx
| NU: |  | http://www.transmission-nu.com/business/ferc890postings.asp
| NGRID: |  | http://www.nationalgridus.com/oasis/filings_studies.asp
| UI: |  | http://www.uinet.com/uinet/resources/file/ebcfda4ccb73dd/UI%20Local%20System%20Plan.pdf

## ISO-NEProject Oct 09Listing PAC (hidden)
October '09 ISO-NEW ENGLAND Project Listing Update
Primary Driver | Part# | Project ID | Primary Equipment Owner | Other Equipment Owner(s) | Projected In-Service Month/Year | Major Project | Project | Jul-09 Status | Oct-09 Status | PPA (I.3.9) Approval | TCA Approval | Jul-09 Estimated PTF Costs | Oct-09 Estimated PTF Costs
TABLE A
MAINE
Reliability Upgrade | 1a | 144 | Bangor Hydro-Electric Company |  | 12/2010 | Keene Rd Autotransformer | Installation of a 345/115 kV autotransformer at Keene Rd Substation. | Under Construction | Under Construction | No | No | 29000000 | 29000000
Reliability Upgrade | 1a | 625 | Central Maine Power Company |  | 02/2010 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Rumford Industrial Park capacitor bank. | Planned | Under Construction | 2007-11-30 | No | 5400000 | 5400000
Reliability Upgrade | 1a | 1128 | Central Maine Power Company |  | 07/2010 | CMP-LSP Hotel Road Substation | Add 115/34kV transformer with 115kV breaker at Hotel Rd. | Planned | Planned | 2008-08-20 | NR | 800000 | 800000
Reliability Upgrade | 1a | 624 | Central Maine Power Company |  | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (New Page - Rumford Industrial Park) | Planned | Planned | 2007-11-30 | No | Part of project 625 | Part of project 625
Reliability Upgrade | 1a | 905 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Planned | Planned | 2008-07-31 | No | 1510000000 | 1510000000
Reliability Upgrade | 1a | 906 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Coopers Mills-Highland, Larrabee Road-Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 907 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 84 (Albion Road-Coopers Mills), Section 203 (Detroit-Orrington), Section 80 (Coopers Mills-Highland), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 908 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377 & Maine Yankee 375/392, 115kV Bucksport 65/205) and Maine Yankee 345 kV re-termination | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1026 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Three Rivers) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Portion of CMP $1.51B and portion of NU is $35.1M | Portion of CMP $1.51B and portion of NU is $35.1M
Reliability Upgrade | 1a | 1027 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV Line Construction (Elm Street-East Deering, East Deering -Cape) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1028 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD
Reliability Upgrade | 1a | 1029 | Central Maine Power Company |  | 11/2010 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformer at South Gorham | Under Construction | Under Construction | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1030 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Raven Farm, Maguire Road) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 143 | Bangor Hydro-Electric Company |  | 12/2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation to Harrington Substation. | Planned | Planned | 2006-05-10 | 2008-06-13 | 66100000 | 66100000
Reliability Upgrade | 1a | 1129 | Central Maine Power Company |  | 05/2012 |  | New 115kV line between Wyman Hydro and Heywood Rd. parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | Planned | 2009-01-26 | No | 19500000 | 19500000
Reliability Upgrade | 1a | 1144 | Central Maine Power Company |  | 04/2010 | Heywood Road Project | Circuit switcher replacements at Detroit, Lakewood, Rice Rips and Winslow | Under Construction | Under Construction | 2009-03-20 | 2009-07-20 | Part of Heywood Road Project | Part of Heywood Road Project
Generator Interconnection Upgrade | 2a | 770 | Central Maine Power Company |  | 12/2010 | Queue Position 137 | Installation of New Page Substation (aka Railroad Street Substation) with (3) circuit breakers tapping Section 218 115kV. | Proposed | Proposed | 2007-03-18 | NR | NR | NR
NEW HAMPSHIRE
Reliability Upgrade | 1a | 277 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Planned | Planned | 2009-06-29 | No | 56600000 | 56600000
Reliability Upgrade | 1a | 1137 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115kV breakers and add 1-115kV breaker at Deerfield Substation | Planned | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1138 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rebuild 115kV L175 line | Planned | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1139 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV M183 Line | Planned | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1140 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | Planned | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1141 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | Planned | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 680 | National Grid, USA |  | 09/2012 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | Planned | 2008-01-28 | No | 11497000 | 7393000
Reliability Upgrade | 1a | 674 | National Grid, USA |  | 09/2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | Planned | 2008-04-01 | No | 12000000 | 7720000
Elective | 4a | 1142 | FPL New England Division |  | 10/2009 |  | Seabrook Station Reconfiguration and Circuit Breaker addition Stage s 1 & 2 | Planned | Planned | 2008-11-20 | NR | TBD | TBD
Generator Interconnection Upgrade | 2a | 724 | National Grid, USA |  | 11/2009 | NGRID Comerford Substation | NGRID Comerford Substation. | Planned | Planned | 2007-06-12 | NR | NR | NR
VERMONT
Reliability Upgrade | 1a | 320 | Vermont Electric Power Company |  | 10/2009 | Lamoille County Project | Middlesex Substation 115 kV breaker addition. | Under Construction | Under Construction | 08/16/2007 | 02/07/2008 | 4857000 | 4857000
Reliability Upgrade | 1a | 322 | Vermont Electric Power Company |  | 10/2009 | Lamoille County Project | Installation of new Duxbury Substation that involves looping in and out of the Middlesex - Essex 115 kV (K24) line. | Under Construction | Under Construction | 08/16/2007 | 02/07/2008 | Part of Lamoille County Project | Part of Lamoille County Project
Reliability Upgrade | 1a | 139 | Vermont Electric Power Company |  | 12/2010 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Planned | Planned | 01/10/2003 | 03/31/2003 | 20000000 | 20000000
Reliability Upgrade | 1a | 321 | Vermont Electric Power Company |  | 12/2009 | Burlington Project | Burlington 115kV Loop - 5 mi of new line & rebuilding 5 miles of existing line between two existing substations with expansion of the East Avenue substation. | Under Construction | Under Construction | 10/24/2006 | 05/23/2007 | 25142000 | 25142000
Reliability Upgrade | 1a | 1145 | Vermont Electric Power Company |  | 09/2011 | Burlington Project | Installation of a 3-breaker 115kV ring substation and 115/34.5kV transformer on the East Ave. - Tafts Coners 115kV line |  | Planned | 10/24/2006 | No |  | 14000000
Reliability Upgrade | 1a | 323 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | New VY - Newfane - Coolidge 345 kV line with requisite station upgrades. | Under Construction | Under Construction | 2008-10-01 | No | 136368000 | 136368000
Reliability Upgrade | 1a | 1032 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Installation of a new 345/115kV substation called Vernon including a new 345/115kV autotransformer | Under Construction | Under Construction | 2008-10-01 | No | 69815000 | 69815000
Reliability Upgrade | 1a | 1033 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project (VELCO LSP - Newfane Substation) | Installation of a new 345/115kV substation called Newfane | Under Construction | Under Construction | 2008-10-01 | No | 16664000 | 16664000
Reliability Upgrade | 1a | 1034 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Loop new 345kV Line into Newfane Substation. | Under Construction | Under Construction | 2008-10-01 | No | Part of project 323 | Part of project 323
Reliability Upgrade | 1a | 1035 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Expansion of Coolidge 345kV substation | Under Construction | Under Construction | 2008-10-01 | No | 20117000 | 20117000
Reliability Upgrade | 1a | 1146 | Vermont Electric Power Company |  | 12/2012 | Lyndonville Project | Installation of a 3-breaker 115kV righ station consisting of two 115kV 12.5 MVAR capacitor banks and 115/34.5 kV transformer interconnecting to the Irasburg - St. Johnsbury 115kV line |  | Planned | 2009-06-01 | No |  | 9000000
Generator Interconnection Upgrade | 2a | 1036 | Vermont Electric Power Company |  | 12/2009 | Queue Position 172 | Installation of 3-breaker 115kV ring bus interconnection of the St. Johnsbury-Irasburg 115kV K39 line. | Planned | Planned | 08/16/2007 | NR | NR | NR
MASSACHUSETTS
Reliability Upgrade | 1a | 1063 | NSTAR Electric Company |  | 12/2009 |  | Install (2) 115kV 40 MVAR shunt reactors at Edgar Station | Planned | Under Construction | 05/2009 | No | 5400000 | 5400000
Reliability Upgrade | 1a | 1152 | National Grid, USA |  | 2010-08-01 |  | Bear Swamp - Pratts Jumction 230kV Line Refurbishment Project (E205E) |  | Planned | NR | NR |  | 43596000
Reliability Upgrade | 1a | 887 | National Grid, USA |  | 09/2012 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Planned | Planned | 2008-01-28 | No | 30000000 | 30000000
Reliability Upgrade | 1a | 921 | National Grid, USA |  | 01/2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | Planned | 2008-01-28 | No | 12100000 | 12100000
Reliability Upgrade | 1a | 919 | National Grid, USA |  | 09/2012 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | Planned | 2008-01-28 | No | 4600000 | 4600000
Reliability Upgrade | 1a | 783 | National Grid, USA |  | 03/2011 | Merrimack Valley/North Shore Reliability Project | Extend the 115kV by addition of 115kV Breaker and K-153 line from King St. to W. Amesbury 115kV station. (W. Amesbury 345/115kV Station becomes PTF) | Planned | Planned | 2008-04-01 | No | 30349000 | 30349000
Reliability Upgrade | 1a | 777 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Build Wakefield Junction station with four 345/115 kV autotransformers. | Under Construction | Under Construction | 2008-04-01 | No | 95000000 | 95000000
Reliability Upgrade | 1a | 161 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Loop 345 kV 339 line and 115 kV S-145/T-146 into new Wakefield Jct. Substation. | Under Construction | Under Construction | 2008-04-01 | No | 4986431 | 4986431
Reliability Upgrade | 1a | 779 | National Grid, USA |  | 04/2010 | Merrimack Valley/North Shore Reliability Project | Bypass and remove Golden Hills 345 kV substation. | Under Construction | Under Construction | 2008-04-01 | No | 5132609 | 5132609
Reliability Upgrade | 1a | 840 | NSTAR Electric Company |  | 10/2010 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | Planned | 2008-04-01 | No | 7300000 | 7300000
Reliability Upgrade | 1a | 775 | National Grid, USA |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Addition of 4 breakers and relocation of T1 and T2 into new bays at Sandy Pond. | Planned | Planned | 2008-06-27 | No | 20100000 | 20100000
Reliability Upgrade | 1a | 776 | National Grid, USA |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | Planned | 2008-06-27 | No | 2865876 | 2865876
Reliability Upgrade | 1a | 782 | National Grid, USA |  | 10/2013 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor n Railyard. | Planned | Planned | 2008-06-27 | No | 38100000 | 38100000
Reliability Upgrade | 1a | 961 | NSTAR Electric Company |  | 11/2010 | Mystic Breaker Additions Project | Install (2) new 115 kV East Bus breakers #30 and #32 at Mystic and move Transformer 110B Connection. | Planned | Under Construction | 2008-03-10 | No | 3800000 | 3800000
Reliability Upgrade | 1a | 903 | NSTAR Electric Company |  | 12/2009 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #2, #4, #5, and #16 at Mystic to IPT and separate controls with Boston Gen units #5 and #6. | Planned | Under Construction | NR | NR | 1240000 | 1240000
Reliability Upgrade | 1a | 904 | NSTAR Electric Company |  | 12/2010 | Mystic IPT Breaker Project | Upgrade (5) 115 kV breakers #1, #7, #15 #19 and #20 at Mystic to IPT and separate controls with Boston Gen #4. | Planned | Planned | NR | NR | 990000 | 990000
Reliability Upgrade | 1a | 59 | National Grid, USA |  | 01/2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | Planned | 2007-11-01 | 2003-01-31 | 400000 | 400000
Reliability Upgrade | 1a | 929 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | Planned | 12/17/2007 | No | 1381849 | 1381849
Reliability Upgrade | 1a | 931 | National Grid, USA |  | 01/2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | Planned | 12/17/2007 | No | 531481 | 531481
Reliability Upgrade | 1a | 928 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | Planned | 12/17/2007 | No | 1945218 | 2300000
Reliability Upgrade | 1a | 930 | National Grid, USA |  | 12/2009 | Central/Western Massachusetts Upgrades | Reconductor Nashua St - Quinsigamond Jct (O141) 115 kV line w/636 ACSS. | Planned | Under Construction | 12/17/2007 | No | 2300000 | 2300000
Reliability Upgrade | 1a | 934 | National Grid, USA |  | 10/2010 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Planned | Planned | 12/17/2007 | No | 818480 | 818480
Reliability Upgrade | 1a | 935 | National Grid, USA |  | 07/2010 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Planned | Planned | 12/17/2007 | No | 5208509 | 5208509
Reliability Upgrade | 1a | 933 | National Grid, USA |  | 12/2009 | Central/Western Massachusetts Upgrades | Reconductor Pratts Jct - Flagg Pond I-135S & J-136S 115 kV lines w/795 ACSS. | Planned | Under Construction | 12/17/2007 | No | 6137112 | 6137112
Reliability Upgrade | 1a | 938 | National Grid, USA |  | 06/2010 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | Planned | 12/17/2007 | No | 3068556 | 3068556
Reliability Upgrade | 1a | 939 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Reconductor and retension (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | Planned | Planned | 12/17/2007 | No | 3389658 | 3389658
Reliability Upgrade | 1a | 940 | National Grid, USA |  | 04/2011 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS. | Planned | Planned | 12/17/2007 | No | 6235744 | 6235744
Reliability Upgrade | 1a | 942 | National Grid, USA |  | 10/2010 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | Planned | 12/17/2007 | No | 2767180 | 2767180
Reliability Upgrade | 1a | 927 | National Grid, USA |  | 07/2010 | Central/Western Massachusetts Upgrades | Greendale - replace 115 kV breaker and upgrade to 2000A. | Planned | Planned | 12/17/2007 | No | 584629 | 584629
Reliability Upgrade | 1a | 925 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | Planned | 12/17/2007 | No | 318888 | 318888
Reliability Upgrade | 1a | 926 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | Planned | 12/17/2007 | No | 6027520 | 6027520
Reliability Upgrade | 1a | 932 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | Planned | 12/17/2007 | No | 372036 | 372036
Reliability Upgrade | 1a | 924 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | Planned | Planned | 12/17/2007 | No | 2147181 | 2147181
Reliability Upgrade | 1a | 941 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Install new Millbury - Tower #510 115 kV line. | Planned | Planned | 12/17/2007 | No | 7909203 | 7909203
Reliability Upgrade | 1a | 943 | National Grid, USA |  | 01/2011 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | Planned | 12/17/2007 | No | 1073995 | 1073995
Reliability Upgrade | 1a | 944 | National Grid, USA |  | 07/2012 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Planned | Planned | 12/17/2007 | No | 11411849 | 11411849
Reliability Upgrade | 1a | 950 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | Planned | 12/17/2007 | No | 1016897 | 1016897
Reliability Upgrade | 1a | 953 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | Planned | 12/17/2007 | No | 10248067 | 10248067
Reliability Upgrade | 1a | 954 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | E Westminster - install new 115 kV breaker, including disconnect switches. Assumes no new control house. | Planned | Planned | 12/17/2007 | No | 903909 | 903909
Reliability Upgrade | 1a | 945 | National Grid, USA |  | 02/2013 | Central/Western Massachusetts Upgrades | Adams - install third 115 kV breaker to complete ring bus. | Planned | Planned | 12/17/2007 | No | 1581841 | 1584841
Reliability Upgrade | 1a | 946 | National Grid, USA |  | 04/2013 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer - E Longmeadow - Shaker Rd line to 115 kV. | Planned | Planned | 12/17/2007 | No | 9604032 | 9604032
Reliability Upgrade | 1a | 947 | National Grid, USA |  | 04/2013 | Central/Western Massachusetts Upgrades | Reconductor 115 kV line from Palmer to new Hampden Substation. | Planned | Planned | 12/17/2007 | No | 2632635 | 2632635
Reliability Upgrade | 1a | 948 | National Grid, USA |  | 07/2012 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | Planned | 12/17/2007 | No | 5649430 | 5649430
Reliability Upgrade | 1a | 949 | National Grid, USA |  | 07/2012 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | Planned | 12/17/2007 | No | 1694829 | 1500000
Reliability Upgrade | 1a | 952 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Reconductor E Winchendon - J136 Tap within I135/J136 ROW w/795 ACSR. | Planned | Planned | 12/17/2007 | No | 932156 | 932156
Reliability Upgrade | 1a | 937 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | Planned | 12/17/2007 | No | 6602875 | 6602875
Reliability Upgrade | 1a | 955 | National Grid, USA |  | 11/2011 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | Planned | 12/17/2007 | No | 10779113 | 10779113
Reliability Upgrade | 1a | 162 | National Grid, USA |  | 04/2011 |  | Q-169 Golden Hills to Lynn 115 kV line upgrade. | Under Construction | Under Construction | 2005-09-02 | 2008-04-25 | 12390000 | 12390000
Reliability Upgrade | 1a | 902 | National Grid, USA |  | 03/2012 | Middleboro Municipal | Close the E1-M1 loop at Middleboro's Wareham St Sub. | Under Construction | Under Construction | 12/01/2006 | NR | 715000 | 715000
Reliability Upgrade | 1a | 1000 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | Planned | Planned | 2008-06-27 | No | 22000000 | 22000000
Reliability Upgrade | 1a | 951 | National Grid, USA |  | 02/2013 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon 115 kV line. | Planned | Planned | 12/17/2007 | No | 7455440 | 7455440
Reliability Upgrade | 1a | 687 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | Planned | 2008-09-24 | No | 714000000 | 714000000
Reliability Upgrade | 1a | 826 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 196 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115kV line South Agawam to Southwick (1768) | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVAR Capacitor additions | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1074 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1076 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Planned | Planned | 2008-09-24 | No | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1077 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115kV line | Planned | Planned | 2008-09-24 | No | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1078 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 673 | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | Planned | 2009-02-27 | No | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Planned | Planned | 2009-02-27 | No | 30000000 | 30000000
Generator Interconnection Upgrade | 2a | 1045 | National Grid, USA |  | 06/2010 | Lowell Power | Upgrade 137T and K-137W 115 kV circuit breakers at Sandy Pond. | Planned | Planned | 2006-07-25 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 505 | National Grid, USA |  | 07/2010 | Hoosac Wind Farm | Tap Y-25S line between Harriman and Deerfield 5. Construct 69/34.5 kV substation and 34.5 kV line connecting 30 MW generating facility with the 69 kV system. | Planned | Planned | 02/01/2005 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 595 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Expansion of Barnstable 115 kV substation to include 5th bay and (2) circuit breakers, addition of a 3rd breaker in the planned 4th bay, and (2) 35MVAr shunt reactors. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 596 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Installation of (2) 115 kV circuits out of Barnstable substation to interconnect Cape Wind. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 598 | NSTAR Electric Company |  | 11/2010 | Cape Wind | At Canal 345 kV substation, install a redundant breaker in series with breaker #312. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 599 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Upgrade the Bourne 115 kV breaker #12272 with an IPT breaker. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 600 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Installation of differential insulation and additional grounding at each tower that is common for the 342 and 322 345 kV lines. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1048 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Convert Canal 345 kV SPS to include tripping of Cape Wind for the simultaneous loss of 342 and 322 345 kV lines. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1046 | National Grid, USA |  | 06/2011 | Queue Position 178 | Reconductor 115 kV F19 Line (Auburn - Brockton Tap). | Proposed | Proposed | 2008-03-10 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1047 | National Grid, USA |  | 06/2011 | Queue Position 178 | Replace Bridgewater 115 kV 1631 circuit breaker with 63 kA breaker. | Proposed | Proposed | 2008-03-10 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 622 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Interconnection to WMECO's 115-kV 1512 line through a new Substation. | Proposed | Proposed | 06/01/2007 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1043 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Upgrade the 1768 line terminal equipment at Southwick Substation. | Proposed | Proposed | 06/01/2007 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1044 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Upgrade the 1512 line terminal equipment at Southwick Substation. | Proposed | Proposed | 06/01/2007 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1058 | National Grid, USA |  | 06/2011 | Billerica Power | Interconnection to Tewksbury 115 kV Substation via O-193 Line and refurbish section of J-162 line. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1059 | National Grid, USA |  | 06/2011 | Billerica Power | Re-terminate line tap section (Perry Street) of J-162 Line to new bay position at Tewksbury. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1060 | National Grid, USA |  | 06/2011 | Billerica Power | Reconductor 2.8 mi. of the M-139 115 kV line. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1061 | National Grid, USA |  | 06/2011 | Billerica Power | Replace (16) 115 kV circuit breakers at Tewksbury 22 w/ IPT capability if all generators w/ higher Queue Position are constructed. The quantity of breaker upgrades subject to Queued generators constructed. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1062 | National Grid, USA |  | 06/2011 | Billerica Power | Upgrade #137T and #K-137W 115 kV circuit breakers at Sandy Pond (if not completed as part of Merrimack Valley/North Shore Project). | Planned | Planned | 2008-07-08 | NR | NR | NR
Elective | 4a | 1057 | Braintree Electric Light Department |  | 06/2010 |  | Upgrade 115-10-16 underground 115 kV cable. | Planned | Planned | 2008-04-17 | No | TBD | TBD
RHODE ISLAND
Reliability Upgrade | 1a | 484 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Planned | Planned | 2008-04-25 | No | 690000 | 690000
Reliability Upgrade | 1a | 791 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | Planned | 2008-04-25 | No | 11560000 | 11560000
Reliability Upgrade | 1a | 913 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | Planned | 2008-04-25 | No | 3250000 | 3250000
Reliability Upgrade | 1a | 914 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | Planned | 2008-04-25 | No | 28150000 | 28150000
Reliability Upgrade | 1a | 915 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | Planned | 2008-04-25 | No | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | Planned | 2008-04-25 | No | 11800000 | 11800000
Reliability Upgrade | 1a | 917 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | Planned | 2008-04-25 | No | 7000000 | 7000000
Reliability Upgrade | 1a | 918 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | Planned | 2008-04-25 | No | 3180000 | 3180000
Reliability Upgrade | 1a | 792 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Admiral St-Franklin Square (Q143 and R144) 115 kV UG recabling. | Planned | Planned | 2008-04-25 | No | 39200000 | 39200000
Reliability Upgrade | 1a | 793 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | Planned | 2008-04-25 | No | 6400000 | 6400000
Reliability Upgrade | 1a | 786 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Terminal upgrades at Drumrock, Chartley Pond, and Brayton Point. | Planned | Planned | 2008-04-25 | No | 565000 | 1000000
Reliability Upgrade | 1a | 787 | National Grid, USA |  | 12/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | West Farnum breaker replacements. | Planned | Planned | 2008-04-25 | No | 7631000 | 7631000
Reliability Upgrade | 1a | 788 | National Grid, USA |  | 06/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Kent County substation expansion. | Planned | Planned | 2008-04-25 | No | 42300000 | 42300000
Reliability Upgrade | 1a | 789 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Reconductoring of T7 115 kV line. | Planned | Planned | 2008-04-25 | No | 23304000 | 23304000
Reliability Upgrade | 1a | 790 | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Planned | Planned | 2008-04-25 | No | 50600000 | 50600000
Reliability Upgrade | 1a | 1098 | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Planned | Planned | 2008-04-25 | No | 37529000 | 37529000
Reliability Upgrade | 1a | 190 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | Planned | 2008-09-24 | No | 69600000 | 69600000
Reliability Upgrade | 1a | 1094 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | Planned | 2008-09-24 | No | 20800000 | 25000000
Reliability Upgrade | 1a | 1095 | National Grid, USA |  | 06/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | Planned | 2008-09-24 | No | 73800000 | 73800000
Reliability Upgrade | 1a | 794 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | Planned | 2008-09-24 | No | 55800000 | 55800000
Reliability Upgrade | 1a | 796 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | 347 Reconductor from Sherman Road to CT/RI Border. | Planned | Planned | 2008-09-24 | No | 16400000 | 16400000
Reliability Upgrade | 1a | 797 | National Grid, USA |  | 12/2012 | NEEWS (Interstate Reliability Project) | 3361 Upgrade 345kV terminal equipment at Sherman Road. | Planned | Planned | 2008-09-24 | No | 8300000 | 8300000
Reliability Upgrade | 1a | 795 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV line. | Planned | Planned | 2008-09-24 | No | 99900000 | 99900000
Reliability Upgrade | 1a | 1106 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | Planned | Planned | 2008-09-24 | No | Part of $99,900,000 above | Part of $99,900,000 above
Reliability Upgrade | 1a | 798 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Planned | Planned | 2008-09-24 | No | 4900000 | 4900000
Reliability Upgrade | 1a | 799 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | Planned | Planned | 2008-09-24 | No | 4500000 | 4500000
Reliability Upgrade | 1a | 1096 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | Planned | 2008-09-24 | No | 5800000 | 12000000
Reliability Upgrade | 1a | 800 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S, T-172N and T-172S with associated terminal equipment upgrades. | Planned | Planned | 2008-09-24 | No | 7300000 | 10000000
Reliability Upgrade | 1a | 1097 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County | Planned | Planned | 2008-09-24 | No | 129800000 | 129800000
Reliability Upgrade | 1a | 1099 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | Planned | 2008-09-24 | No | 4100000 | 6000000
Reliability Upgrade | 1a | 1109 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Planned | Planned | 2008-09-24 | No | 360000 | 1000000
CONNECTICUT
Reliability Upgrade | 1a | 211 | Northeast Utilities |  | 11/2009 | NU LSP - Rood Ave Substation | New Rood Ave (formally Windsor) distribution substation with 115kV terminal modifications. | Under Construction | Under Construction | 2008-04-25 | 02/15/2008 | 9162029 | 9162029
Reliability Upgrade | 1a | 1049 | United Illuminating Company |  | 12/2010 |  | East Shore 115 kV Capacitor Bank Transient Recovery | Planned | Planned | NR | NR | 3000000 | 3000000
Reliability Upgrade | 1a | 582 | Northeast Utilities |  | 12/2010 |  | Separate 310 and 368 345-KV lines and create 368/1767 DCT | Planned | Planned | 2008-07-18 | No | 16000000 | 16000000
Reliability Upgrade | 1a | 1112 | United Illuminating Company |  | 12/2010 |  | Water Street 115kV circuit breaker and switch replacements. | Planned | Planned | NR | NR | 1000000 | 1000000
Reliability Upgrade | 1a | 974 | United Illuminating Company |  | 12/2011 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Planned | Planned | NR | No | 6700000 | 6700000
Reliability Upgrade | 1a | 816 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1054 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Manchester - Meekvile Jct. line (395/1448) separation. | Planned | Planned | 2008-09-24 | No | 14000000 | 14000000
Reliability Upgrade | 1a | 576 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | Planned | 2008-09-24 | No | 313000000 | 313000000
Reliability Upgrade | 1a | 1114 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1a | 814 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Central Connecticut Relaibility Project) | Reconductor a portion of the Manchester to Scovill Rock 353 345-kV line and terminal work. | Planned | Planned | 2008-09-24 | No | 9000000 | 9000000
Reliability Upgrade | 1a | 802 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | Planned | 2008-09-24 | No | 251000000 | 251000000
Reliability Upgrade | 1a | 1084 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Loop the Millstone - Manchester (310) 345 kV line into the Card substation. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1085 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1086 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1087 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1088 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1089 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Killingly 3G substation 345kV breaker addition | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1090 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Millstone 15G substation breaker 14T upgrade 50kA | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1091 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Southington 4C substation breaker 19T upgrade to 63kA | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | Northeast Utilities | National Grid, USA | 12/2013 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 807 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Interstate Reliability Project) | Install 480 MVAR's of capacitors at the Montville 345 kV substation | Planned | Planned | 2008-09-24 | No | 33000000 | 33000000
Reliability Upgrade | 1a | 1092 | Northeast Utilities |  | 12/2013 | NEEWS (BPS) 2 | Upgrade the Card 115 kV, East Hartford 115 kV, Agawam 115 kV, Barbour Hill 115 kV, and North Bloomfield 345 kV Substations to BPS standards. | Planned | Planned | 2008-09-24 | No | 37000000 | 37000000
Reliability Upgrade | 1a | 1056 | Northeast Utilities |  | 12/2011 | CT LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Planned | Planned | 2008-12-12 | No | 9751000 | 9751000
Reliability Upgrade | 1a | 1110 | United Illuminating Company |  | 12/2010 |  | Broadway 115/13.8 kV Substation Additon | Planned | Planned | 2008-12-08 | No | 1200000 | 1200000
Reliability Upgrade | 1a | 1111 | United Illuminating Company |  | 12/2010 |  | Metro North Union Avenue 115/26.4 kV Substation | Planned | Planned | 2009-01-07 | No | 10543000 | 10543000
Reliability Upgrade | 1a | 976 | United Illuminating Company |  | 05/2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Planned | Planned | 2009-01-07 | No | 48000000 | 48000000
Reliability Upgrade | 1a | 879 |  | Bangor Hydro-Electric Company, New England Power Company, Northeast Utilities System Com | TBD | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | Planned | 03/01/2007 | NR | 420000 | 420000
Generator Interconnection Upgrade | 2a | 983 | Northeast Utilities |  | 09/2012 | Queue Position 207/241 | Rebuild 115 kV 1585N Line between new substation and Bunker Hill. | Proposed | Proposed | 2008-09-26 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1107 | Northeast Utilities |  | 09/2012 | Queue Position 207/241 | Interconnection to new 115 kV substation consisting of (14) circuit breakers in a breaker and a half configuration that sectionalizes the existing 1575, 1585, and 1990 lines. | Proposed | Proposed | 2008-09-26 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1108 | Northeast Utilities |  | 09/2012 | Queue Position 207/241 | Installation of a 2.5% series reactor on the 1990S Line at the new substation. | Proposed | Proposed | 2008-09-26 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 331 | Northeast Utilities |  | 10/2009 | Kleen Energy | Install 5-breaker ring bus interconnecting between Scovill Rock and Manchester on the 345 kV 353 Line. | Under Construction | Under Construction | 10/08/2003 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1121 | Northeast Utilities |  | 10/2009 | Queue Position 161-2 | Four units connected to 384 line through a new 345kV Substation: unit #4 wll also connect to Substation | Proposed | Planned | 2008-12-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1149 | Northeast Utilities |  | 06/2010 | Queue Position 161-1 | Four units connected at Devon Substation |  | Under Construction | 2007-12-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1122 | Northeast Utilities |  | 11/2010 | Queue Position 191 | One turbine connected to #1238 Line (Frost Bridge to Carmel) via a new 3-breaker ring bus Substation | Proposed | Proposed | 2009-02-24 | NR | NR | NR
Reliability Upgrade | 1a | 1050 | United Illuminating Company |  | 12/2011 |  | Devon Tie 115kV Switching Station BPS Compliance | Planned | Planned | NR | NR | 2620000 | 2620000
TABLE B
MAINE
Reliability Upgrade | 1b | 148 | Central Maine Power Company |  | 06/2012 | CMP LSP - Saco Bay Area Reinforcement Project | Establish a new Vallee Lane 115/34.5 kV substation and 115 kV line from Louden S/S to Vallee Lane Substation. | Proposed | Proposed | No | NR | 100000 | 100000
Reliability Upgrade | 1b | 1116 | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1031 | Bangor Hydro-Electric Company |  | 01/2012 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station, Rebuild Line 66, and Capacitior Bank Additions (10MVAr at Trenton, Downeast & Handcock County area) | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1130 | Central Maine Power Company |  | 12/2011 | Sturtevant Improvements | Add 115kV circuit breakers & 25 MVAR capacitor bank at Sturtevant Substation; Re-rate Section 63 between Wyman Hydro & Madison Substation | Proposed | Proposed | No | No | 3000000 | 3000000
Reliability Upgrade | 1b | 1131 | Central Maine Power Company |  | 12/2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Proposed | Proposed | No | NR | 600000 | 600000
Reliability Upgrade | 1b | 1132 | Central Maine Power Company |  | 12/2011 | CMP-LSP Maxcy's Substation | Add 115/34kV transformer (coordinate with MPRP) | Proposed | Proposed | No | NR | 600000 | 600000
Reliability Upgrade | 1b | 1133 | Central Maine Power Company |  | 10/2010 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation & new 34kV line from Leeds to Turner | Proposed | Proposed | No | NR | 300000 | 300000
Reliability Upgrade | 1b | 1135 | Central Maine Power Company |  | TBD | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer | Proposed | Proposed | No | No | 1500000 | 1500000
Elective | 4b | 1018 | Bangor Hydro-Electric Company |  | TBD | Orrington-Boston HVDC | Orrington substation reconfiguration and addition of new HVDC cable system terminating in Boston area. | Concept | Concept | No | No | TBD | TBD
Elective | 4b | 984 | Central Maine Power Company | Maine Public Service | TBD | MEPCO-MPS 345 kV Interconnection | MEPCO-MPS 345 kV Interconnection. | Concept | Concept | No | No | TBD | TBD
NEW HAMPSHIRE
Reliability Upgrade | 1b | 275 | Northeast Utilities |  | TBD |  | Merrimack 115-kV substation - Protection Separation Upgrade. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1143 | Northeast Utilities |  | TBD |  | Littleton 115kV breaker addition and reconfiguration | Proposed | Proposed | No | No | 5338000 | 5338000
VERMONT
Reliability Upgrade | 1b | 318 | Vermont Electric Power Company |  | 12/2011 |  | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems through the 1,250 MW Vermont state load level. | Concept | Concept | No | No | 9000000 | 9000000
Reliability Upgrade | 1b | 325 | Vermont Electric Power Company |  | 12/2011 | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | Concept | No | No | 5000000 | 5000000
Reliability Upgrade | 1b | 324 | Vermont Electric Power Company |  | 12/2012 |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | Concept | No | No | 100000000 | 100000000
MASSACHUSETTS
Reliability Upgrade | 1b | 785 | National Grid, USA |  | 07/2017 | Merrimack Valley/North Shore Reliability Project | Re-conductor F-158N (Golden Hills-Maplewood-Everett) 115 kV line. | Concept | Concept | No | No | 1330000 | 1330000
Reliability Upgrade | 1b | 963 | NSTAR Electric Company |  | 12/2009 | Boston Area 115 kV Enhancements | Add a new 115kV breaker # 11 Relocate 447-509 and add control and protect at Holbrook. | Proposed | Proposed | No | No | 4000000 | 4000000
Reliability Upgrade | 1b | 842 | NSTAR Electric Company |  | 06/2010 | Boston Area 115 kV Enhancements | Add 115 kV 54 MVAR capacitor bank at W. Framingham. | Proposed | Proposed | No | No | 3000000 | 3700000
Reliability Upgrade | 1b | 1153 | NSTAR Electric Company |  | 06/2010 | Boston Area 115 kV Enhancements | Reliability Upgrades at West Framingham Station |  | Concept | No | No |  | 3000000
Reliability Upgrade | 1b | 843 | NSTAR Electric Company |  | 12/2013 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 965 | NSTAR Electric Company |  | 12/2012 | Boston Area 115 kV Enhancements | Add third 115kV line from Walpole to Holbrook | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 964 | NSTAR Electric Company |  | 06/2011 | Boston Area 115 kV Enhancements | Relocate 115kV terminals at W. Walpole to mitigate breaker failure #8. | Proposed | Proposed | No | No | 5600000 | 5600000
Reliability Upgrade | 1b | 969 | NSTAR Electric Company |  | 06/2018 | Boston Area 115 kV Enhancements | Add a new 54 MVAR capacitor bank at Chelsea. | Concept | Concept | No | No | 1200000 | 1200000
Reliability Upgrade | 1b | 301 | NSTAR Electric Company |  | 12/2011 | Boston Area 115 kV Enhancements | Reconductor 115-kV circuits 320-507 and 320-508. | Concept | Concept | No | No | 4600000 | 4600000
Reliability Upgrade | 1b | 1113 | NSTAR Electric Company |  | 12/2010 |  | Install KSt Breaker #31 | Proposed | Proposed | No | No | 2100000 | 2960000
Reliability Upgrade | 1b | 593 | NSTAR Electric Company |  | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Canal to Barnstable/Falmouth | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1068 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to Sandwich and a a 345-115kV auto-transformer at Sandwich | Proposed | Proposed | No | No | 110000000 | 110000000
Reliability Upgrade | 1b | 592 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing | Proposed | Proposed | No | No | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1118 | NSTAR Electric Company | National Grid, USA | 12/2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 | Proposed | Proposed | No | No | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1067 | NSTAR Electric Company |  | 12/2010 | NPCC BPS Compliance | Tremont Station | Proposed | Proposed | No | No | 11200000 | 12800000
Reliability Upgrade | 1b | 1066 | NSTAR Electric Company |  | 09/2011 | NPCC BPS Compliance | Needham Station | Concept | Concept | No | No | 9300000 | 9300000
Reliability Upgrade | 1b | 1065 | NSTAR Electric Company |  | 07/2012 | NPCC BPS Compliance | Waltham Station | Concept | Proposed | No | No | 24300000 | 26600000
Reliability Upgrade | 1b | 970 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345 kV line from Lexington to Waltham. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 971 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1119 | NSTAR Electric Company |  | 12/2010 | Greater Boston Reliability Project | Upgrade West Medway-West Walpole 345kV line #325 | Proposed | Proposed | No | No | 2200000 | 2200000
Reliability Upgrade | 1b | 1120 | NSTAR Electric Company |  | 06/2010 |  | Install 345kV 160 MVAR shunt ractor at W. Walpole | Proposed | Proposed | No | No | 7200000 | 7200000
Reliability Upgrade | 1b | 956 | National Grid, USA |  | 05/2013 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Concept | Concept | No | No | 7021534 | 7021534
Reliability Upgrade | 1b | 1136 | National Grid, USA |  | 12/2012 |  | New 115kV Switching Station at Devens Convert 69kV lines to 115kV, Reconfigure 115kV Supply at Ayer Substation | Proposed | Proposed | 2009-07-28 | No | 9200000 | 9200000
Reliability Upgrade | 1b | 824 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 825 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Upgrade the Pleasant to Blanford 115-kV line and the Blanford to Granville Jct. portion of the 115-kV line 1512. | Concept | Concept | No | No | TBD | TBD
Generator Interconnection Upgrade | 2b | 863 | Northeast Utilities |  | 06/2010 | Queue Position 217 | Northfield Mountain - W. Mass Northfield 345 kV substation. | Proposed | Proposed | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1014 | Northeast Utilities |  | 06/2010 | Queue Position 196 | 345 kV Northfield Substation | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1123 | Northeast Utilities |  | TBD | Queue Position 236 | New Substation on 1302 Line; terminal upgrades at Buck Pond and Agawam | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 880 | National Grid, USA | Northeast Utilities | 06/2011 | Queue Position 177 | Sutton Energy - 345 kV Carpenter Hill-Millbury Line. | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1042 | National Grid, USA |  | 06/2013 | Queue Position 165 | Replace (2) 345 kV circuit breakers at Sandy Pond | Concept | Concept | No | NR | NR | NR
RHODE ISLAND
Generator Interconnection Upgrade | 2b | 881 | National Grid, USA | Northeast Utilities | 06/2012 | Queue Position 201 | RISEP - 345 kV RISE Substation. | Concept | Concept | No | NR | NR | NR
CONNECTICUT
Reliability Upgrade | 1b | 1055 | Northeast Utilities |  | 2010 | CT LSP - Waterside Substation | Waterside Substation - add a 115/13.2-kV transformer and a 115-kV circuit breaker. | Concept | Concept | No | No | 4107000 | 4107000
Reliability Upgrade | 1b | 809 | Northeast Utilities |  | 12/2009 |  | Upgrade terminal equipment at Bunker Hill 115 kV substation. | Proposed | Proposed | No | No | 1000000 | 1000000
Reliability Upgrade | 1b | 1150 | United Illuminating Company |  | 10/2011 |  | Grand Avenue - West River 115 kV Pumping Plant Replacements |  | Proposed | NR | NR |  | 1200000
Reliability Upgrade | 1b | 1151 | United Illuminating Company |  | 12/2011 |  | West River 115kV Switching Station Fault Duty Migration |  | Proposed | NR | NR |  | 3500000
Reliability Upgrade | 1b | 721 | United Illuminating Company |  | 06/2013 |  | New Shelton 115/13.8 kV substation | Proposed | Proposed | No | No | 11300000 | 11300000
Reliability Upgrade | 1b | 975 | United Illuminating Company |  | 12/2013 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | Concept | No | No | 44300000 | 44300000
Reliability Upgrade | 1b | 699 | United Illuminating Company |  | 12/2012 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | Concept | No | No | 10000000 | 10000000
Reliability Upgrade | 1b | 1147 | Northeast Utilities |  | 2011 |  | Waterside Substation - install a three-breaker 115kV ring bus |  | Proposed | No | No |  | 4000000
Reliability Upgrade | 1b | 1148 | Northeast Utilities |  | 2011 |  | Add a 2nd high speed relay on the Glennbrook to Waterside 115kV 1440 |  | Proposed | No | No |  | 600000
Reliability Upgrade | 1b | 801 | Northeast Utilities |  | TBD |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 85 | Northeast Utilities |  | TBD |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | Concept | 08/04/2004 | No | TBD | TBD
Generator Interconnection Upgrade | 2b | 1124 | Northeast Utilities |  | TBD | Queue Position 2422 | New Substation on Haddam Neck-Southington 345kV line | Proposed | Proposed | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1125 | Northeast Utilities |  | TBD | Queue Position 240 | 345kV on Montville Substation | Concept | Concept | No | NR | NR | NR
IN-SERVICE PROJECTS
Reliability Upgrade | 1a | 1051 | Central Maine Power Company |  | 09/2009 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Riley 115 kV capacitor bank. | Under Construction | In-service | 2007-11-30 | No | Part of Project 625 | Part of Project 625
Generator Interconnection Upgrade | 2a | 1134 | Central Maine Power Company |  | 09/2009 | Kibby Wind Farm | Separate Section 215 from Section 63 and terminate Section 215 at newly established breaker position in Wyman Hydro S/S, which includes re-rating of Section 215. Expand Bigelow S/S & add capacitor banks at Lakewood, Guilford, Wyman Hydro Station & Sturtevant S/S's. | Under Construction | In-service | 2006-06-16 | NR | NR | NR
Reliability Upgrade | 1a | 267 | Northeast Utilities | Central Maine Power Company | 2009-08-01 | Y138 Closing | White Lake - Saco Valley (Y138) Line Closing - Add PAR on Y138 at Saco Valley, retension lines, upgrade Beebe terminal, and add capacitor banks at White Lake and Beebe. | Under Construction | In-service | 01/01/2006 | No | 27775000 | 27775000
Reliability Upgrade | 1a | 936 | National Grid, USA |  | 07/2009 | Central/Western Massachusetts Upgrades | Reconductor (P142/P142S) Rolfe Avenue - West Bolyston 115 kV line w/1590 ACSR. | Under Construction | In-service | 12/17/2007 | No | 3000000 | 3000000
Reliability Upgrade | 1a | 176 | Northeast Utilities |  | 07/2009 | Monadnock Area Reliability Project | New Fitzwilliam 345/115kV substation along with 345 kV breakers. | Under Construction | In-service | 2007-09-27 | No | 76100000 | 76100000
Reliability Upgrade | 1a | 174 | National Grid, USA |  | 06/2009 | Monadnock Area Reliability Project | Reconductor I-135 (Bellows Falls-Monadnock Tap-Flagg Pond) 115 kV line. | Under Construction | In-service | 03/24/2006 | No | 15778000 | 15778000
Reliability Upgrade | 1a | 832 | NSTAR Electric Company |  | 07/2009 | Short Term Lower SEMA Upgrades | Add(1) 115kV SVC (0-112 MVARs lagging) at Barnstable. | Under Construction | In-service | 08/17/2007 | No | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade
Reliability Upgrade | 1a | 182 | Vermont Electric Power Company |  | 09/2009 | Monadnock Area Reliability Project | Upgrade bus cable at N. Rutland and K35 115 kV breaker at Rutland. | Under Construction | In-service | 03/24/2006 | NR | 1000000 | 1000000
CANCELLED PROJECTS
Reliability Upgrade | 1b | 1117 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install 115kV 50 MVAR capacitor bank at Falmouth | Proposed | Cancelled | No | No | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Notes
1 Project pending solution documentation for the Greater Rhode Island Transmission Reinforcements.
2 The Northeast Utilities' estimated costs for the NEEWS BPS upgrades are shared among the Greater Springfield, Central Connecticut, and Interstate portions of the NEEWS Project.
3 The total TCA (NU-07-TCA-24) PTF cost is $234.2 million for the Norwalk - Glenbrook Project. The forecasted PTF cost is $249.4 million.
4 The total TCA (NU-08-TCA-01) PTF cost is $1.05 billion for Northeast Utilities portion of the Middletown-Norwalk Project. The forecasted PTF cost is $978.2 million.
Local Project Listing Links
| NSTAR: |  | http://www.nstar.com/business/rates_tariffs/open_access/
| CMP: |  | http://www.cmpco.com/SuppliersAndPartners/TransmissionServices/CMPTransmissionSvc/lsp.html
| BHE: |  | http://www.bhe.com/data/OASIS/LSP.html
| VELCO: |  | http://www.vermontspc.com/default.aspx
| NU: |  | http://www.transmission-nu.com/business/ferc890postings.asp
| NGRID: |  | http://www.nationalgridus.com/oasis/filings_studies.asp
| UI: |  | http://www.uinet.com/uinet/resources/file/ebcfda4ccb73dd/UI%20Local%20System%20Plan.pdf

## ISO-NE JulyProject Listing-PAC (hidden)
July '09 ISO-NEW ENGLAND Project Listing Update (DRAFT)
Primary Driver | Part# | Project ID | Primary Equipment Owner | Other Equipment Owner(s) | Projected In-Service Month/Year | Major Project | Project | Apr -09 Status | Jul-09 Status | PPA (I.3.9) Approval | TCA Approval | Apr-09 Estimated PTF Costs | Jul-09 Estimated PTF Costs
TABLE A
MAINE
Reliability Upgrade | 1a | 1051 | Central Maine Power Company |  | 09/2009 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Riley 115 kV capacitor bank. | Planned | Under Construction | 2007-11-30 | No | Part of Project 625 | Part of Project 625
Reliability Upgrade | 1a | 144 | Bangor Hydro-Electric Company |  | 12/2010 | Keene Rd Autotransformer | Installation of a 345/115 kV autotransformer at Keene Rd Substation. | Under Construction | Under Construction | No | No | 29000000 | 29000000
Reliability Upgrade | 1a | 625 | Central Maine Power Company |  | 02/2010 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Rumford Industrial Park capacitor bank. | Planned | Planned | 2007-11-30 | No | 5400000 | 5400000
Reliability Upgrade | 1a | 1128 | Central Maine Power Company |  | 07/2010 | CMP-LSP Hotel Road Substation | Add 115/34kV transformer with 115kV breaker at Hotel Rd. | Planned | Planned | 2008-08-20 | NR | 800000 | 800000
Reliability Upgrade | 1a | 624 | Central Maine Power Company |  | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (New Page - Rumford Industrial Park). | Planned | Planned | 2007-11-30 | No | Part of project 625 | Part of project 625
Reliability Upgrade | 1a | 905 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Planned | Planned | 2008-07-31 | No | 1510000000 | 1510000000
Reliability Upgrade | 1a | 906 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Coopers Mills-Highland, Larrabee Road-Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 907 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 84 (Albion Road-Coopers Mills), Section 203 (Detroit-Orrington), Section 80 (Coopers Mills-Highland), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 908 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377 & Maine Yankee 375/392, 115kV Bucksport 65/205) and Maine Yankee 345 kV re-termination | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1026 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Three Rivers) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Portion of CMP $1.51B and portion of NU is $35.1M | Portion of CMP $1.51B and portion of NU is $35.1M
Reliability Upgrade | 1a | 1027 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV Line Construction (Elm Street-East Deering, East Deering -Cape) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1028 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD
Reliability Upgrade | 1a | 1029 | Central Maine Power Company |  | 12/2009 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformer at South Gorham | Under Construction | Under Construction | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1030 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Raven Farm, Maguire Road) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 143 | Bangor Hydro-Electric Company |  | 12/2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation to Harrington Substation. | Planned | Planned | 2006-05-10 | 2008-06-13 | 66100000 | 66100000
Reliability Upgrade | 1a | 1129 | Central Maine Power Company |  | 05/2012 |  | New 115kV line between Wyman Hydro and Heywood Rd. parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | Planned | 2009-01-26 | No | 19500000 | 19500000
Reliability Upgrade | 1a | 1144 | Central Maine Power Company |  | 04/2010 | Heywood Road Project | Circuit switcher replacements at Detroit, Lakewood, Rice Rips and Winslow |  | Under Construction | 2009-03-20 | 2009-07-20 |  | Part of Heywood Road Project
Generator Interconnection Upgrade | 2a | 1134 | Central Maine Power Company |  | 12/2010 | Kibby Wind Farm | Separate Section 215 from Section 63 and terminate Section 215 at newly established breaker position in Wyman Hydro S/S, which includes re-rating of Section 215. Expand Bigelow S/S & add capacitor banks at Lakewood, Guilford, Wyman Hydro Station & Sturtevant S/S's. | Planned | Under Construction | 2006-06-16 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 770 | Central Maine Power Company |  | TBD | Queue Position 137 | Installation of New Page Substation (aka Railroad Street Substation) with (3) circuit breakers tapping Section 218 115 kV. | Proposed | Proposed | 2007-03-18 | NR | NR | NR
NEW HAMPSHIRE
Reliability Upgrade | 1a | 267 | Northeast Utilities | Central Maine Power Company | 2009-08-01 | Y138 Closing | White Lake - Saco Valley (Y138) Line Closing - Add PAR on Y138 at Saco Valley, retension lines, upgrade Beebe terminal, and add capacitor banks at White Lake and Beebe. | Under Construction | Under Construction | 01/01/2006 | No | 27775000 | 27775000
Reliability Upgrade | 1a | 176 | Northeast Utilities |  | 2009-08-01 | Monadnock Area Reliability Project | New Fitzwilliam 345/115kV substation along with 345 kV breakers. | Under Construction | Under Construction | 2007-09-27 | No | 76100000 | 76100000
Reliability Upgrade | 1a | 174 | National Grid, USA |  | 2009-08-01 | Monadnock Area Reliability Project | Reconductor I-135 (Bellows Falls-Monadnock Tap-Flagg Pond) 115 kV line. | Under Construction | Under Construction | 03/24/2006 | No | 9600000 | 15778000
Reliability Upgrade | 1a | 277 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Concept | Planned | 2009-06-29 | No | TBD | 56600000
Reliability Upgrade | 1a | 1137 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115kV breakers and add 1-115kV breaker at Deerfield Substation |  | Planned | 2009-06-29 | No |  | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1138 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rebuild 115kV L175 line |  | Planned | 2009-06-29 | No |  | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1139 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV M183 Line |  | Planned | 2009-06-29 | No |  | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1140 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line |  | Planned | 2009-06-29 | No |  | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1141 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades |  | Planned | 2009-06-29 | No |  | Part of 2nd Deerfield 345/115kV Autotransformer Project
Elective | 4b | 1142 | FPL New England Division |  | 10/2009 |  | Seabrook Station Reconfiguration and Circuit Breaker addition Stages 1 &2 |  | Planned | 2008-11-20 | NR |  | TBD
Reliability Upgrade | 1a | 680 | National Grid, USA |  | 06/2012 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | Planned | 2008-01-28 | No | 11497000 | 11497000
Reliability Upgrade | 1a | 674 | National Grid, USA |  | 05/2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | Planned | 2008-04-01 | No | 12000000 | 12000000
Generator Interconnection Upgrade | 2a | 724 | National Grid, USA |  | 11/2009 | NGRID Comerford Substation | NGRID Comerford Substation. | Planned | Planned | 2007-06-12 | NR | NR | NR
VERMONT
Reliability Upgrade | 1a | 320 | Vermont Electric Power Company |  | 09/2009 | Lamoille County Project | Middlesex Substation 115 kV breaker addition. | Under Construction | Under Construction | 08/16/2007 | 02/07/2008 | 4857000 | 4857000
Reliability Upgrade | 1a | 322 | Vermont Electric Power Company |  | 09/2009 | Lamoille County Project | Installation of new Duxbury Substation that involves looping in and out of the Middlesex - Essex 115 kV (K24) line. | Under Construction | Under Construction | 08/16/2007 | 02/07/2008 | Part of Lamoille County Project | Part of Lamoille County Project
Reliability Upgrade | 1a | 139 | Vermont Electric Power Company |  | 12/2010 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Planned | Planned | 01/10/2003 | 03/31/2003 | 20000000 | 20000000
Reliability Upgrade | 1a | 182 | Vermont Electric Power Company |  | 09/2009 | Monadnock Area Reliability Project | Upgrade bus cable at N. Rutland and K35 115 kV breaker at Rutland. | Under Construction | Under Construction | 03/24/2006 | No | 1000000 | 1000000
Reliability Upgrade | 1a | 321 | Vermont Electric Power Company |  | 12/2009 |  | Burlington 115kV Loop - 5 mi of new line & rebuilding 5 miles of existing line between two existing substations with expansion of the East Avenue substation. | Under Construction | Under Construction | 10/24/2006 | 05/23/2007 | 25142000 | 25142000
Reliability Upgrade | 1a | 323 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | New VY - Newfane - Coolidge 345 kV line with requisite station upgrades. | Under Construction | Under Construction | 2008-10-01 | No | 136368000 | 136368000
Reliability Upgrade | 1a | 1032 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Installation of a new 345/115kV substation called Vernon including a new 345/115kV autotransformer | Under Construction | Under Construction | 2008-10-01 | No | 69815000 | 69815000
Reliability Upgrade | 1a | 1033 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project (VELCO LSP - Newfane Substation) | Installation of a new 345/115kV substation called Newfane | Under Construction | Under Construction | 2008-10-01 | No | 16664000 | 16664000
Reliability Upgrade | 1a | 1034 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Loop new 345kV Line into Newfane Substation. | Under Construction | Under Construction | 2008-10-01 | No | Part of project 323 | Part of project 323
Reliability Upgrade | 1a | 1035 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Expansion of Coolidge 345kV substation | Under Construction | Under Construction | 2008-10-01 | No | 20117000 | 20117000
Generator Interconnection Upgrade | 2a | 1036 | Vermont Electric Power Company |  | 12/2009 | Queue Position 172 | Installation of 3-breaker 115kV ring bus interconnection of the St. Johnsbury-Irasburg 115kV K39 line. | Planned | Planned | 08/16/2007 | NR | NR | NR
MASSACHUSETTS
Reliability Upgrade | 1a | 1063 | NSTAR Electric Company |  | 12/2009 |  | Install (2) 115kV 40 MVAR shunt reactors at Edgar Station | Proposed | Planned | 05/2009 | No | 5400000 | 5400000
Reliability Upgrade | 1a | 887 | National Grid, USA |  | 09/2012 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Planned | Planned | 2008-01-28 | No | 30000000 | 30000000
Reliability Upgrade | 1a | 921 | National Grid, USA |  | 01/2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | Planned | 2008-01-28 | No | 12100000 | 12100000
Reliability Upgrade | 1a | 919 | National Grid, USA |  | 12/2012 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | Planned | 2008-01-28 | No | 4600000 | 4600000
Reliability Upgrade | 1a | 783 | National Grid, USA |  | 03/2011 | Merrimack Valley/North Shore Reliability Project | Extend the 115kV by addition of 115kV Breaker and K-153 line from King St. to W. Amesbury 115kV station. (W. Amesbury 345/115kV Station becomes PTF) | Concept | Planned | 2008-04-01 | No | 30349000 | 30349000
Reliability Upgrade | 1a | 777 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Build Wakefield Junction station with four 345/115 kV autotransformers. | Under Construction | Under Construction | 2008-04-01 | No | 95000000 | 95000000
Reliability Upgrade | 1a | 161 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Loop 345 kV 339 line and 115 kV S-145/T-146 into new Wakefield Jct. Substation. | Under Construction | Under Construction | 2008-04-01 | No | 4986431 | 4986431
Reliability Upgrade | 1a | 779 | National Grid, USA |  | 04/2010 | Merrimack Valley/North Shore Reliability Project | Bypass and remove Golden Hills 345 kV substation. | Under Construction | Under Construction | 2008-04-01 | No | 5132609 | 5132609
Reliability Upgrade | 1a | 840 | NSTAR Electric Company |  | 10/2010 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | Planned | 2008-04-01 | No | 7300000 | 7300000
Reliability Upgrade | 1a | 775 | National Grid, USA |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Addition of 4 breakers and relocation of T1 and T2 into new bays at Sandy Pond. | Planned | Planned | 2008-06-27 | No | 20100000 | 20100000
Reliability Upgrade | 1a | 776 | National Grid, USA |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | Planned | 2008-06-27 | No | 2865876 | 2865876
Reliability Upgrade | 1a | 782 | National Grid, USA |  | 10/2013 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor n Railyard. | Planned | Planned | 2008-06-27 | No | 38100000 | 38100000
Reliability Upgrade | 1a | 961 | NSTAR Electric Company |  | 11/2010 | Mystic Breaker Additions Project | Install (2) new 115 kV East Bus breakers #30 and #32 at Mystic and move Transformer 110B Connection. | Planned | Planned | 2008-03-10 | No | 3800000 | 3800000
Reliability Upgrade | 1a | 903 | NSTAR Electric Company |  | 12/2009 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #2, #4, #5, and #16 at Mystic to IPT and separate controls with Boston Gen units #5 and #6. | Planned | Planned | NR | NR | 1240000 | 1240000
Reliability Upgrade | 1a | 904 | NSTAR Electric Company |  | 12/2010 | Mystic IPT Breaker Project | Upgrade (5) 115 kV breakers #1, #7, #15 #19 and #20 at Mystic to IPT and separate controls with Boston Gen #4. | Planned | Planned | NR | NR | 990000 | 990000
Reliability Upgrade | 1a | 59 | National Grid, USA |  | 01/2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | Planned | 2007-11-01 | 2003-01-31 | 400000 | 400000
Reliability Upgrade | 1a | 832 | NSTAR Electric Company |  | 2009-08-01 | Short Term Lower SEMA Upgrades | Add(1) 115kV SVC (0-112 MVARs lagging) at Barnstable. | Under Construction | Under Construction | 08/17/2007 | No | $86.6 M (Total NSTAR Project Cost | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade
Reliability Upgrade | 1a | 929 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | Planned | 12/17/2007 | No | 1381849 | 1381849
Reliability Upgrade | 1a | 931 | National Grid, USA |  | 01/2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | Planned | 12/17/2007 | No | 531481 | 531481
Reliability Upgrade | 1a | 936 | National Grid, USA |  | 07/2009 | Central/Western Massachusetts Upgrades | Reconductor (P142/P142S) Rolfe Avenue - West Bolyston 115 kV line w/1590 ACSR. | Planned | Under Construction | 12/17/2007 | No | 3000000 | 3000000
Reliability Upgrade | 1a | 928 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | Planned | 12/17/2007 | No | 1945218 | 1945218
Reliability Upgrade | 1a | 930 | National Grid, USA |  | 12/2009 | Central/Western Massachusetts Upgrades | Reconductor Nashua St - Quinsigamond Jct (O141) 115 kV line w/636 ACSS. | Planned | Planned | 12/17/2007 | No | 2300000 | 2300000
Reliability Upgrade | 1a | 934 | National Grid, USA |  | 10/2010 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Planned | Planned | 12/17/2007 | No | 818480 | 818480
Reliability Upgrade | 1a | 935 | National Grid, USA |  | 07/2010 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Planned | Planned | 12/17/2007 | No | 5208509 | 5208509
Reliability Upgrade | 1a | 933 | National Grid, USA |  | 04/2010 | Central/Western Massachusetts Upgrades | Reconductor Pratts Jct - Flagg Pond I-135S & J-136S 115 kV lines w/795 ACSS. | Planned | Planned | 12/17/2007 | No | 6137112 | 6137112
Reliability Upgrade | 1a | 938 | National Grid, USA |  | 06/2010 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | Planned | 12/17/2007 | No | 3068556 | 3068556
Reliability Upgrade | 1a | 939 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Reconductor and retension (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | Planned | Planned | 12/17/2007 | No | 3389658 | 3389658
Reliability Upgrade | 1a | 940 | National Grid, USA |  | 04/2011 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS. | Planned | Planned | 12/17/2007 | No | 6235744 | 6235744
Reliability Upgrade | 1a | 942 | National Grid, USA |  | 10/2010 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | Planned | 12/17/2007 | No | 2767180 | 2767180
Reliability Upgrade | 1a | 927 | National Grid, USA |  | 07/2010 | Central/Western Massachusetts Upgrades | Greendale - replace 115 kV breaker and upgrade to 2000A. | Planned | Planned | 12/17/2007 | No | 584629 | 584629
Reliability Upgrade | 1a | 925 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | Planned | 12/17/2007 | No | 318888 | 318888
Reliability Upgrade | 1a | 926 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | Planned | 12/17/2007 | No | 6027520 | 6027520
Reliability Upgrade | 1a | 932 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | Planned | 12/17/2007 | No | 372036 | 372036
Reliability Upgrade | 1a | 924 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | Planned | Planned | 12/17/2007 | No | 2147181 | 2147181
Reliability Upgrade | 1a | 941 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Install new Millbury - Tower #510 115 kV line. | Planned | Planned | 12/17/2007 | No | 7909203 | 7909203
Reliability Upgrade | 1a | 943 | National Grid, USA |  | 01/2011 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | Planned | 12/17/2007 | No | 1073995 | 1073995
Reliability Upgrade | 1a | 944 | National Grid, USA |  | 07/2012 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Planned | Planned | 12/17/2007 | No | 11411849 | 11411849
Reliability Upgrade | 1a | 950 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | Planned | 12/17/2007 | No | 1016897 | 1016897
Reliability Upgrade | 1a | 953 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | Planned | 12/17/2007 | No | 10248067 | 10248067
Reliability Upgrade | 1a | 954 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | E Westminster - install new 115 kV breaker, including disconnect switches. Assumes no new control house. | Planned | Planned | 12/17/2007 | No | 903909 | 903909
Reliability Upgrade | 1a | 945 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | Adams - install third 115 kV breaker to complete ring bus. | Planned | Planned | 12/17/2007 | No | 1581841 | 1581841
Reliability Upgrade | 1a | 946 | National Grid, USA |  | 04/2013 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer - E Longmeadow - Shaker Rd line to 115 kV. | Planned | Planned | 12/17/2007 | No | 9604032 | 9604032
Reliability Upgrade | 1a | 947 | National Grid, USA |  | 04/2013 | Central/Western Massachusetts Upgrades | Reconductor 115 kV line from Palmer to new Hampden Substation. | Planned | Planned | 12/17/2007 | No | 2632635 | 2632635
Reliability Upgrade | 1a | 948 | National Grid, USA |  | 07/2012 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | Planned | 12/17/2007 | No | 5649430 | 5649430
Reliability Upgrade | 1a | 949 | National Grid, USA |  | 07/2012 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | Planned | 12/17/2007 | No | 1694829 | 1694829
Reliability Upgrade | 1a | 952 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Reconductor E Winchendon - J136 Tap within I135/J136 ROW w/795 ACSR. | Planned | Planned | 12/17/2007 | No | 932156 | 932156
Reliability Upgrade | 1a | 937 | National Grid, USA |  | 03/2011 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | Planned | 12/17/2007 | No | 6602875 | 6602875
Reliability Upgrade | 1a | 955 | National Grid, USA |  | 11/2011 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | Planned | 12/17/2007 | No | 10779113 | 10779113
Reliability Upgrade | 1a | 951 | National Grid, USA |  | 02/2013 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon 115 kV line. | Planned | Planned | 12/17/2007 | No | 7455440 | 7455440
Reliability Upgrade | 1a | 162 | National Grid, USA |  | 04/2011 |  | Q-169 Golden Hills to Lynn 115 kV line upgrade. | Under Construction | Under Construction | 2005-09-02 | 2008-04-25 | 12390000 | 12390000
Reliability Upgrade | 1a | 902 | National Grid, USA |  | 03/2012 | Middleboro Municipal | Close the E1-M1 loop at Middleboro's Wareham St Sub. | Under Construction | Under Construction | 12/01/2006 | NR | 715000 | 715000
Reliability Upgrade | 1a | 1000 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | Planned | Planned | 2008-06-27 | No | 22000000 | 22000000
Reliability Upgrade | 1a | 687 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | Planned | 2008-09-24 | No | 714000000 | 714000000
Reliability Upgrade | 1a | 826 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 196 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115kV line South Agawam to Southwick (1768) | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVAR Capacitor additions | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1074 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1076 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Planned | Planned | 2008-09-24 | No | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1077 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115kV line | Planned | Planned | 2008-09-24 | No | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1078 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 673 | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | Planned | 2009-02-27 | No | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Planned | Planned | 2009-02-27 | No | 30000000 | 30000000
Generator Interconnection Upgrade | 2a | 1045 | National Grid, USA |  | 06/2010 | Lowell Power | Upgrade 137T and K-137W 115 kV circuit breakers at Sandy Pond. | Planned | Planned | 2006-07-25 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 505 | National Grid, USA |  | 07/2010 | Hoosac Wind Farm | Tap Y-25S line between Harriman and Deerfield 5. Construct 69/34.5 kV substation and 34.5 kV line connecting 30 MW generating facility with the 69 kV system. | Planned | Planned | 02/01/2005 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 595 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Expansion of Barnstable 115 kV substation to include 5th bay and (2) circuit breakers, addition of a 3rd breaker in the planned 4th bay, and (2) 35MVAr shunt reactors. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 596 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Installation of (2) 115 kV circuits out of Barnstable substation to interconnect Cape Wind. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 598 | NSTAR Electric Company |  | 11/2010 | Cape Wind | At Canal 345 kV substation, install a redundant breaker in series with breaker #312. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 599 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Upgrade the Bourne 115 kV breaker #12272 with an IPT breaker. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 600 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Installation of differential insulation and additional grounding at each tower that is common for the 342 and 322 345 kV lines. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1048 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Convert Canal 345 kV SPS to include tripping of Cape Wind for the simultaneous loss of 342 and 322 345 kV lines. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1046 | National Grid, USA |  | 06/2011 | Queue Position 178 | Reconductor 115 kV F19 Line (Auburn - Brockton Tap). | Proposed | Proposed | 2008-03-10 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1047 | National Grid, USA |  | 06/2011 | Queue Position 178 | Replace Bridgewater 115 kV 1631 circuit breaker with 63 kA breaker. | Proposed | Proposed | 2008-03-10 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 622 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Interconnection to WMECO's 115-kV 1512 line through a new Substation. | Proposed | Proposed | 06/01/2007 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1043 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Upgrade the 1768 line terminal equipment at Southwick Substation. | Proposed | Proposed | 06/01/2007 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1044 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Upgrade the 1512 line terminal equipment at Southwick Substation. | Proposed | Proposed | 06/01/2007 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1058 | National Grid, USA |  | 06/2011 | Billerica Power | Interconnection to Tewksbury 115 kV Substation via O-193 Line and refurbish section of J-162 line. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1059 | National Grid, USA |  | 06/2011 | Billerica Power | Re-terminate line tap section (Perry Street) of J-162 Line to new bay position at Tewksbury. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1060 | National Grid, USA |  | 06/2011 | Billerica Power | Reconductor 2.8 mi. of the M-139 115 kV line. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1061 | National Grid, USA |  | 06/2011 | Billerica Power | Replace (16) 115 kV circuit breakers at Tewksbury 22 w/ IPT capability if all generators w/ higher Queue Position are constructed. The quantity of breaker upgrades subject to Queued generators constructed. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1062 | National Grid, USA |  | 06/2011 | Billerica Power | Upgrade #137T and #K-137W 115 kV circuit breakers at Sandy Pond (if not completed as part of Merrimack Valley/North Shore Project). | Planned | Planned | 2008-07-08 | NR | NR | NR
Elective | 4a | 1057 | Braintree Electric Light Department |  | 06/2010 |  | Upgrade 115-10-16 underground 115 kV cable. | Planned | Planned | 2008-04-17 | No | TBD | TBD
RHODE ISLAND
Reliability Upgrade | 1a | 484 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Planned | Planned | 2008-04-25 | No | 690000 | 690000
Reliability Upgrade | 1a | 791 | National Grid, USA |  | 06/2013 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | Planned | 2008-04-25 | No | 11560000 | 11560000
Reliability Upgrade | 1a | 913 | National Grid, USA |  | 06/2013 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | Planned | 2008-04-25 | No | 3250000 | 3250000
Reliability Upgrade | 1a | 914 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | Planned | 2008-04-25 | No | 28150000 | 28150000
Reliability Upgrade | 1a | 915 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | Planned | 2008-04-25 | No | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | Planned | 2008-04-25 | No | 11800000 | 11800000
Reliability Upgrade | 1a | 917 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | Planned | 2008-04-25 | No | 7000000 | 7000000
Reliability Upgrade | 1a | 918 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | Planned | 2008-04-25 | No | 3180000 | 3180000
Reliability Upgrade | 1a | 792 | National Grid, USA |  | 06/2013 | Greater Rhode Island Transmission Reinforcements 1 | Admiral St-Franklin Square (Q143 and R144) 115 kV UG recabling. | Planned | Planned | 2008-04-25 | No | 39200000 | 39200000
Reliability Upgrade | 1a | 793 | National Grid, USA |  | 06/2013 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | Planned | 2008-04-25 | No | 6400000 | 6400000
Reliability Upgrade | 1a | 786 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Terminal upgrades at Drumrock, Chartley Pond, and Brayton Point. | Planned | Planned | 2008-04-25 | No | 565000 | 565000
Reliability Upgrade | 1a | 787 | National Grid, USA |  | 12/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | West Farnum breaker replacements. | Planned | Planned | 2008-04-25 | No | 7631000 | 7631000
Reliability Upgrade | 1a | 788 | National Grid, USA |  | 12/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Kent County substation expansion. | Planned | Planned | 2008-04-25 | No | 42300000 | 42300000
Reliability Upgrade | 1a | 789 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Reconductoring of T7 115 kV line. | Planned | Planned | 2008-04-25 | No | 23304000 | 23304000
Reliability Upgrade | 1a | 790 | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Planned | Planned | 2008-04-25 | No | 50600000 | 50600000
Reliability Upgrade | 1a | 1098 | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Planned | Planned | 2008-04-25 | No | 37529000 | 37529000
Reliability Upgrade | 1a | 190 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | Planned | 2008-09-24 | No | 69600000 | 69600000
Reliability Upgrade | 1a | 1094 | National Grid, USA |  | 06/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | Planned | 2008-09-24 | No | 20800000 | 20800000
Reliability Upgrade | 1a | 1095 | National Grid, USA |  | 06/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | Planned | 2008-09-24 | No | 73800000 | 73800000
Reliability Upgrade | 1a | 794 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | Planned | 2008-09-24 | No | 55800000 | 55800000
Reliability Upgrade | 1a | 796 | National Grid, USA |  | 11/2012 | NEEWS (Interstate Reliability Project) | 347 Reconductor from Sherman Road to CT/RI Border. | Planned | Planned | 2008-09-24 | No | 16400000 | 16400000
Reliability Upgrade | 1a | 797 | National Grid, USA |  | 12/2012 | NEEWS (Interstate Reliability Project) | 3361 Upgrade 345kV terminal equipment at Sherman Road. | Planned | Planned | 2008-09-24 | No | 8300000 | 8300000
Reliability Upgrade | 1a | 795 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV line. | Planned | Planned | 2008-09-24 | No | 99900000 | 99900000
Reliability Upgrade | 1a | 1106 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | Planned | Planned | 2008-09-24 | No | Part of $99,900,000 above | Part of $99,900,000 above
Reliability Upgrade | 1a | 798 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Planned | Planned | 2008-09-24 | No | 4900000 | 4900000
Reliability Upgrade | 1a | 799 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | Planned | Planned | 2008-09-24 | No | 4500000 | 4500000
Reliability Upgrade | 1a | 1096 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | Planned | 2008-09-24 | No | 5800000 | 5800000
Reliability Upgrade | 1a | 800 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S, T-172N and T-172S with associated terminal equipment upgrades. | Planned | Planned | 2008-09-24 | No | 7300000 | 7300000
Reliability Upgrade | 1a | 1097 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County | Planned | Planned | 2008-09-24 | No | 129800000 | 129800000
Reliability Upgrade | 1a | 1099 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | Planned | 2008-09-24 | No | 4100000 | 4100000
Reliability Upgrade | 1a | 1109 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Planned | Planned | 2008-09-24 | No | 360000 | 360000
CONNECTICUT
Reliability Upgrade | 1a | 211 | Northeast Utilities |  | 10/2009 | NU LSP - Rood Ave Substation | New Rood Ave (formally Windsor) distribution substation with 115kV terminal modifications. | Under Construction | Under Construction | 2008-04-25 | 02/15/2008 | 9162029 | 9162029
Reliability Upgrade | 1a | 1049 | United Illuminating Company |  | 12/2010 |  | East Shore 115 kV Capacitor Bank Transient Recovery | Planned | Planned | NR | NR | 3000000 | 3000000
Reliability Upgrade | 1a | 582 | Northeast Utilities |  | 12/2010 |  | Separate 310 and 368 345-KV lines and create 368/1767 DCT | Planned | Planned | 2008-07-18 | No | 16000000 | 16000000
Reliability Upgrade | 1a | 1112 | United Illuminating Company |  | 12/2010 |  | Water Street 115kV circuit breaker and switch replacements. | Planned | Planned | NR | NR | 1000000 | 1000000
Reliability Upgrade | 1a | 974 | United Illuminating Company |  | 12/2011 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Planned | Planned | NR | No | 6700000 | 6700000
Reliability Upgrade | 1a | 816 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1054 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Manchester - Meekvile Jct. line (395/1448) separation. | Planned | Planned | 2008-09-24 | No | 14000000 | 14000000
Reliability Upgrade | 1a | 576 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | Planned | 2008-09-24 | No | 313000000 | 313000000
Reliability Upgrade | 1a | 1114 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1a | 814 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Central Connecticut Relaibility Project) | Reconductor a portion of the Manchester to Scovill Rock 353 345-kV line and terminal work. | Planned | Planned | 2008-09-24 | No | 9000000 | 9000000
Reliability Upgrade | 1a | 802 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | Planned | 2008-09-24 | No | 251000000 | 251000000
Reliability Upgrade | 1a | 1084 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Loop the Millstone - Manchester (310) 345 kV line into the Card substation. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1085 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1086 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1087 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1088 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1089 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Killingly 3G substation 345kV breaker addition | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1090 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Millstone 15G substation breaker 14T upgrade 50kA | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1091 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Southington 4C substation breaker 19T upgrade to 63kA | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | Northeast Utilities | National Grid, USA | 12/2013 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 807 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Interstate Reliability Project) | Install 480 MVAR's of capacitors at the Montville 345 kV substation | Planned | Planned | 2008-09-24 | No | 33000000 | 33000000
Reliability Upgrade | 1a | 1092 | Northeast Utilities |  | 12/2013 | NEEWS (BPS) 2 | Upgrade the Card 115 kV, East Hartford 115 kV, Agawam 115 kV, Barbour Hill 115 kV, and North Bloomfield 345 kV Substations to BPS standards. | Planned | Planned | 2008-09-24 | No | 37000000 | 37000000
Reliability Upgrade | 1a | 1056 | Northeast Utilities |  | 12/2011 | CT LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Planned | Planned | 2008-12-12 | No | 9751000 | 9751000
Reliability Upgrade | 1a | 1110 | United Illuminating Company |  | 06/2010 |  | Broadway 115/13.8 kV Substation Additon | Planned | Planned | 2008-12-08 | No | 800000 | 1200000
Reliability Upgrade | 1a | 1111 | United Illuminating Company |  | 09/2010 |  | Metro North Union Avenue 115/26.4 kV Substation | Planned | Planned | 2009-01-07 | No | 8700000 | 10543000
Reliability Upgrade | 1a | 976 | United Illuminating Company |  | 05/2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Planned | Planned | 2009-01-07 | No | 48000000 | 48000000
Reliability Upgrade | 1a | 1050 | United Illuminating Company |  | 12/2011 |  | Devon Tie 115kV Switching Station BPS Compliance | Planned | Planned | NR | NR | 2620000 | 2620000
Reliability Upgrade | 1a | 879 |  | Bangor Hydro-Electric Company, New England Power Company, Northeast Utilities System Com | TBD | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | Planned | 03/01/2007 | NR | 420000 | 420000
Generator Interconnection Upgrade | 2a | 983 | Northeast Utilities |  | 10/2010 | Queue Position 207/241 | Rebuild 115 kV 1585N Line between new substation and Bunker Hill. | Proposed | Proposed | 2008-09-26 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1107 | Northeast Utilities |  | 10/2010 | Queue Position 207/241 | Interconnection to new 115 kV substation consisting of (14) circuit breakers in a breaker and a half configuration that sectionalizes the existing 1575, 1585, and 1990 lines. | Proposed | Proposed | 2008-09-26 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1108 | Northeast Utilities |  | 10/2010 | Queue Position 207/241 | Installation of a 2.5% series reactor on the 1990S Line at the new substation. | Proposed | Proposed | 2008-09-26 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 331 | Northeast Utilities |  | 11/2010 | Kleen Energy | Install 5-breaker ring bus interconnecting between Scovill Rock and Manchester on the 345 kV 353 Line. | Planned | Under Construction | 10/08/2003 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1121 | Northeast Utilities |  | 06/2010 | Queue Position 161-2 | Four units connected to 384 line through a new 345kV Substation: unit #4 wll also connect to Substation | Proposed | Proposed | 2008-12-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1122 | Northeast Utilities |  | 11/2010 | Queue Position 191 | One turbine connected to #1238 Line (Frost Bridge to Carmel) via a new 3-breaker ring bus Substation | Proposed | Proposed | 2009-02-24 | NR | NR | NR
TABLE B
MAINE
Reliability Upgrade | 1b | 148 | Central Maine Power Company |  | 06/2012 | CMP LSP - Saco Bay Area Reinforcement Project | Establish a new Vallee Lane 115/34.5 kV substation and 115 kV line. | Proposed | Proposed | No | NR | 16900000 | 100000
Reliability Upgrade | 1b | 1116 | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1031 | Bangor Hydro-Electric Company |  | 01/2012 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station, Rebuild Line 66, and Capacitior Bank Additions (10MVAr at Trenton, Downeast & Handcock County area) | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1130 | Central Maine Power Company |  | 12/2011 | Sturtevant Improvements | Add 115kV circuit breakers & 25 MVAR capacitor bank at Sturtevant Substation; Re-rate Section 63 between Wyman Hydro & Madison Substation | Proposed | Proposed | No | No | 2000000 | 3000000
Reliability Upgrade | 1b | 1131 | Central Maine Power Company |  | 12/2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Proposed | Proposed | No | NR | 600000 | 600000
Reliability Upgrade | 1b | 1132 | Central Maine Power Company |  | 12/2011 | CMP-LSP Maxcy's Substation | Add 115/34kV transformer (coordinate with MPRP) | Proposed | Proposed | No | NR | 600000 | 600000
Reliability Upgrade | 1b | 1133 | Central Maine Power Company |  | 10/2010 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation & new 34kV line from Leeds to Turner | Proposed | Proposed | No | NR | 2500000 | 300000
Reliability Upgrade | 1b | 1135 | Central Maine Power Company |  | TBD | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer |  | Proposed | No | No |  | 1500000
Elective | 4b | 1018 | Bangor Hydro-Electric Company |  | TBD | Orrington-Boston HVDC | Orrington substation reconfiguration and addition of new HVDC cable system terminating in Boston area. | Concept | Concept | No | No | TBD | TBD
Elective | 4b | 984 | Central Maine Power Company | Maine Public Service | TBD | MEPCO-MPS 345 kV Interconnection | MEPCO-MPS 345 kV Interconnection. | Concept | Concept | No | No | TBD | TBD
NEW HAMPSHIRE
Reliability Upgrade | 1b | 275 | Northeast Utilities |  | TBD |  | Merrimack 115-kV substation - Protection Separation Upgrade. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1143 | Northeast Utilities |  | TBD |  | Littleton 115kV breaker addition and reconfiguration |  | Proposed | No | No |  | 5338000
VERMONT
Reliability Upgrade | 1b | 318 | Vermont Electric Power Company |  | 12/2011 |  | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems through the 1,250 MW Vermont state load level. | Concept | Concept | No | No | 9000000 | 9000000
Reliability Upgrade | 1b | 325 | Vermont Electric Power Company |  | 12/2011 | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | Concept | No | No | 5000000 | 5000000
Reliability Upgrade | 1b | 324 | Vermont Electric Power Company |  | 12/2012 |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | Concept | No | No | 100000000 | 100000000
MASSACHUSETTS
Reliability Upgrade | 1b | 785 | National Grid, USA |  | 07/2017 | Merrimack Valley/North Shore Reliability Project | Re-conductor F-158N (Golden Hills-Maplewood-Everett) 115 kV line. | Concept | Concept | No | No | 1330000 | 1330000
Reliability Upgrade | 1b | 963 | NSTAR Electric Company |  | 12/2009 | Boston Area 115 kV Enhancements | Add a new 115kV breaker # 11 Relocate 447, 509 and add control and protect at Holbrook. | Proposed | Proposed | No | No | 3400000 | 4000000
Reliability Upgrade | 1b | 842 | NSTAR Electric Company |  | 06/2010 | Boston Area 115 kV Enhancements | Add 115 kV 54 MVAR capacitor bank at W. Framingham. | Proposed | Proposed | No | No | 3000000 | 3000000
Reliability Upgrade | 1b | 843 | NSTAR Electric Company |  | 12/2013 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 965 | NSTAR Electric Company |  | 12/2012 | Boston Area 115 kV Enhancements | Add third 115kV line from Walpole to Holbrook | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 964 | NSTAR Electric Company |  | 06/2011 | Boston Area 115 kV Enhancements | Relocate 115kV terminals at W. Walpole to mitigate breaker failure #8. | Proposed | Proposed | No | No | 5600000 | 5600000
Reliability Upgrade | 1b | 969 | NSTAR Electric Company |  | 06/2018 | Boston Area 115 kV Enhancements | Add a new 54 MVAR capacitor bank at Chelsea. | Concept | Concept | No | No | 1200000 | 1200000
Reliability Upgrade | 1b | 301 | NSTAR Electric Company |  | 12/2011 | Boston Area 115 kV Enhancements | Reconductor 115-kV circuits 320-507 and 320-508. | Concept | Concept | No | No | 4600000 | 4600000
Reliability Upgrade | 1b | 1113 | NSTAR Electric Company |  | 06/2010 |  | Install KSt Breaker #31 | Proposed | Proposed | No | No | 2100000 | 2100000
Reliability Upgrade | 1b | 593 | NSTAR Electric Company |  | 2013 | Mid-Cape Reliability | Add a new 115 kV line from Canal to Barnstable. | Proposed | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1068 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to Sandwich and a a 345-115kV auto-transformer at Sandwich | Proposed | Proposed | No | No | 110000000 | 110000000
Reliability Upgrade | 1b | 592 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing | Proposed | Proposed | No | No | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1117 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install 115kV 50 MVAR capacitor bank at Falmouth | Proposed | Proposed | No | No | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1118 | NSTAR Electric Company | National Grid, USA | 12/2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 and 111 | Proposed | Proposed | No | No | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1067 | NSTAR Electric Company |  | 12/2010 | NPCC BPS Compliance | Tremont Station | Proposed | Proposed | No | No | 11200000 | 14122000
Reliability Upgrade | 1b | 1066 | NSTAR Electric Company |  | 09/2011 | NPCC BPS Compliance | Needham Station | Proposed | Concept | No | No | 9300000 | 9300000
Reliability Upgrade | 1b | 1065 | NSTAR Electric Company |  | 07/2012 | NPCC BPS Compliance | Waltham Station | Proposed | Concept | No | No | 24300000 | 24300000
Reliability Upgrade | 1b | 970 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345 kV line from Lexington to Waltham. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 971 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1119 | NSTAR Electric Company |  | 12/2010 | Greater Boston Reliability Project | Upgrade West Medway-West Walpole 345kV line (#325 ) | Proposed | Proposed | No | No | 1300000 | 2200000
Reliability Upgrade | 1b | 1120 | NSTAR Electric Company |  | 06/2010 |  | Install 345kV 160 MVAR shunt ractor at W. Walpole | Proposed | Proposed | No | No | 6000000 | 7200000
Reliability Upgrade | 1b | 956 | National Grid, USA |  | 05/2013 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Concept | Concept | No | No | 7021534 | 7021534
Reliability Upgrade | 1b | 824 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 825 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Upgrade the Pleasant to Blanford 115-kV line and the Blanford to Granville Jct. portion of the 115-kV line 1512. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1136 | National Grid, USA |  | 06/2011 |  | New 115kV Switching Station at Devens Convert 69kV lines to 115kV, Reconfigure 115kV Supply at Ayer Substation |  | Proposed |  | No |  | 9200000
Generator Interconnection Upgrade | 2b | 863 | Northeast Utilities |  | 06/2010 | Queue Position 217 | Northfield Mountain - W. Mass Northfield 345 kV substation. | Proposed | Proposed | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1014 | Northeast Utilities |  | 06/2010 | Queue Position 196 | 345 kV Northfield Substation | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1123 | Northeast Utilities |  | TBD | Queue Position 236 | New Substation on 1302 Line; terminal upgrades at Buck Pond and Agawam | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 880 | National Grid, USA | Northeast Utilities | 06/2011 | Queue Position 177 | Sutton Energy - 345 kV Carpenter Hill-Millbury Line. | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1042 | National Grid, USA |  | 06/2013 | Queue Position 165 | Replace (2) 345 kV circuit breakers at Sandy Pond | Concept | Concept | No | NR | NR | NR
RHODE ISLAND
Generator Interconnection Upgrade | 2b | 881 | National Grid, USA | Northeast Utilities | 06/2012 | Queue Position 201 | RISEP - 345 kV RISE Substation. | Concept | Concept | No | NR | NR | NR
CONNECTICUT
Reliability Upgrade | 1b | 1055 | Northeast Utilities |  | 2010 | CT LSP - Waterside Substation | Waterside Substation - add a 115/13.2-kV transformer and a 115-kV circuit breaker. | Concept | Concept | No | No | 4107000 | 4107000
Reliability Upgrade | 1b | 809 | Northeast Utilities |  | 12/2009 |  | Upgrade terminal equipment at Bunker Hill 115 kV substation. | Proposed | Proposed | No | No | 1000000 | 1000000
Reliability Upgrade | 1b | 721 | United Illuminating Company |  | 06/2013 |  | New Shelton 115/13.8 kV substation | Proposed | Proposed | No | No | 11300000 | 11300000
Reliability Upgrade | 1b | 975 | United Illuminating Company |  | 12/2013 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | Concept | No | No | 44300000 | 44300000
Reliability Upgrade | 1b | 699 | United Illuminating Company |  | 12/2012 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | Concept | No | No | 10000000 | 10000000
Reliability Upgrade | 1b | 801 | Northeast Utilities |  | TBD |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 85 | Northeast Utilities |  | TBD |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | Concept | 08/04/2004 | No | TBD | TBD
Generator Interconnection Upgrade | 2b | 1124 | Northeast Utilities |  | TBD | Queue Position 2422 | New Substation on Haddam Neck-Southington 345kV line | Proposed | Proposed | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1125 | Northeast Utilities |  | TBD | Queue Position 240 | 345kV on Montville Substation | Concept | Concept | No | NR | NR | NR
IN-SERVICE PROJECTS
Reliability Upgrade | 1a | 626 | Central Maine Power Company |  | 04/2009 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of 115/34.5 kV transformer and six new 115 kV breakers and a half substation at Woodstock. | Planned | In-service | 2007-11-30 | No | 8000000 | 8000000
Reliability Upgrade | 1a | 575 | Central Maine Power Company |  | 05/2009 | Heywood Road Project | New Heywood Rd 115kV switchyard with (6) 115kV circuit breakers (3) 115kV line retensionings and 115kV 20 MVAr capacitor bank at Heywood Rd. | Under Construction | In-service | 2009-03-20 | 2009-07-20 | 7000000 | 7000000
Reliability Upgrade | 1a | 1127 | Central Maine Power Company |  | 05/2009 | CMP-LSP Newcastle Substation | Add 115/34kV transformer with two 115kV breakers | Under Construction | In-service | 2008-08-20 | 2008-08-20 | 1300000 | 1300000
Reliability Upgrade | 1a | 166 | National Grid, USA |  | 06/2009 |  | Replace (16) 115 kV breakers at Tewksbury 22. | Under Construction | In-service | NR | NR | 3300000 | 3300000
Reliability Upgrade | 1a | 1009 | Northeast Utilities |  | 05/2009 |  | Install a 2% reactor on the North Bloomfield-Canton 115kV line and also replacement fo the Frostbridge 345/115kV autotransformer | Under Construction | In-service | 2007-10-20 | 2009-10-16 | 3638000 | 3089000
Reliability Upgrade | 1a | 203 | Northeast Utilities |  | 05/2009 | NU LSP - Stepstone Substation | Install new Stepstone 115 kV substation in Guilford. | Under Construction | In-service | 2005-11-08 | 2006-04-24 | 6332000 | 6332000
Reliability Upgrade | 1a | 1064 | NSTAR Electric Company |  | 04/2009 |  | Install (1) 345kV 160 MVAR shunt reactor at Mystic Station | Planned | In-service | 2008-09-26 | No | 10400000 | 10400000
Reliability Upgrade | 1a | 302 | NSTAR Electric Company |  | 05/2009 | Boston Area 115 kV Enhancements | DCT separation of Framingham to Speen St. 433-507 circuit. | Under Construction | In-service | 01/18/2005 | 03/01/2005 | 3100000 | 3100000
Reliability Upgrade | 1a | 695 | NSTAR Electric Company |  | 07/2009 | Short Term Lower SEMA Upgrades | Loop (355) 345 kV line in and out of Carver Substation and add (5) new 345 kV circuit breakers at Carver substation. | Under Construction | In-service | 08/17/2007 | No | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 830 | NSTAR Electric Company |  | 07/2009 | Short Term Lower SEMA Upgrades | Add a second 345/115 kV Auto transformer at Carver substation and add (1) new 345 kV circuit breaker and (3) new 115 kV circuit breakers at Carver substation. | Under Construction | In-service | 08/17/2007 | No | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 831 | NSTAR Electric Company |  | 07/2009 | Short Term Lower SEMA Upgrades | Add a second 115 kV line from Carver to Tremont and add (2) new 115 kV circuit breakers at Carver substation and (1) new 115 kV circuit breaker at Tremont substation. | Under Construction | In-service | 08/17/2007 | No | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA
CANCELLED PROJECTS
Generator Interconnection Upgrade | 2b | 861 | Northeast Utilities |  | 01/2010 | Queue Position 190 | Mount Tom - W Mass. Mt. Tom 115 kV Substation. | Concept | Cancelled | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 869 | Northeast Utilities |  | 06/2013 | Queue Position 226 | Rebuild 345 kV 326 Line | Concept | Cancelled | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1041 | Northeast Utilities |  | 06/2013 | Queue Position 226 | Rebuild 115 kV U181 Line | Concept | Cancelled | No | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1126 | Northeast Utilities |  | TBD | Queue Position 161-4 | Two units and repowering of #6 Montville 345kV Substation | Proposed | Cancelled | 2008-06-09 | NR | NR | NR
Reliability Upgrade | 1b | 316 | United Illuminating Company |  | 06/2012 |  | New Fairfield 115/13.8 kV substation | Concept | Cancelled | No | No | 7450000 | 7450000
Reliability Upgrade | 1b | 977 | United Illuminating Company |  | 06/2013 |  | New Orange 115/13.8 kV substation | Concept | Cancelled | No | No | 7550000 | 7550000
Reliability Upgrade | 1b | 980 | United Illuminating Company |  | 06/2014 |  | New Hamden 115/13.8 kV substation. | Concept | Cancelled | No | No | 7750000 | 7750000
Reliability Upgrade | 1b | 317 | United Illuminating Company |  | 06/2014 |  | New North Branford 115/13.8-kV substation. | Concept | Cancelled | No | No | 7750000 | 7750000
Notes
1 Project pending solution documentation for the Greater Rhode Island Transmission Reinforcements.
2 The Northeast Utilities' estimated costs for the NEEWS BPS upgrades are shared among the Greater Springfield, Central Connecticut, and Interstate portions of the NEEWS Project.
3 The total TCA (NU-07-TCA-24) PTF cost is $234.2 million for the Norwalk - Glenbrook Project. The forecasted PTF cost is $249.4 million.
4 The total TCA (NU-08-TCA-01) PTF cost is $1.05 billion for Northeast Utilities portion of the Middletown-Norwalk Project. The forecasted PTF cost is $978.2 million.
Local Project Listing Links
| NSTAR: |  | http://www.nstar.com/business/rates_tariffs/open_access/
| CMP: |  | http://www.cmpco.com/SuppliersAndPartners/TransmissionServices/CMPTransmissionSvc/lsp.html
| BHE: |  | http://www.bhe.com/data/OASIS/LSP.html
| VELCO: |  | http://www.vermontspc.com/About%20the%20VSPC/Home.aspx
| NU: |  | http://www.transmission-nu.com/business/pdfs/NU_Local_Transmission_Studies_List.pdf
| NGRID: |  | http://www.nationalgridus.com/oasis/
| UI: |  | http://www.uinet.com/uinet/resources/file/ebcfda4ccb73dd/UI%20Local%20System%20Plan.pdf

## Project List-April09 post (hidden)
April '09 ISO-NEW ENGLAND Project Listing Update (FINAL)
Primary Driver | Part# | Project ID | Primary Equipment Owner | Other Equipment Owner(s) | Projected In-Service Month/Year | Major Project | Project | Oct-08 Status | Apr -09 Status | PPA (I.3.9) Approval | TCA Approval | Oct-08 Estimated PTF Costs | Apr-09 Estimated PTF Costs
TABLE A
MAINE
Reliability Upgrade | 1a | 575 | Central Maine Power Company |  | 05/2009 | Heywood Road Project | New Heywood Rd 115kV switchyard with (6) 115kV circuit breakers (3) 115kV line retensionings and 115kV 20 MVAr capacitor bank at Heywood Rd. | Concept | Under Construction | 01/01/2007 | 2009-01-26 | 6100000 | 7000000
Reliability Upgrade | 1a | 1129 | Central Maine Power Company |  | 12/2012 | Heywood Road Project | New 115kV line between Wyman Hydro and Heywood Rd. parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination |  | Planned | 2009-01-26 | No |  | 19500000
Reliability Upgrade | 1a | 626 | Central Maine Power Company |  | 04/2009 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of 115/34.5 kV transformer and six new 115 kV breakers and a half substation at Woodstock. | Planned | Planned | 2007-11-30 | No | 7400000 | 8000000
Reliability Upgrade | 1a | 1051 | Central Maine Power Company |  | 05/2009 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Riley 115 kV capacitor bank. | Planned | Planned | 2007-11-30 | No | Portion of 5,400,000 (above) | Part of Project 625
Reliability Upgrade | 1a | 625 | Central Maine Power Company |  | 02/2010 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Rumford Industrial Park capacitor bank. | Planned | Planned | 2007-11-30 | No | 5400000 | 5400000
Reliability Upgrade | 1a | 624 | Central Maine Power Company |  | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (New Page - Rumford Industrial Park). | Planned | Planned | 2007-11-30 | No | Portion of 5,400,000 (above) | Part of project 625
Reliability Upgrade | 1a | 1127 | Central Maine Power Company |  | 05/2009 | CMP-LSP Newcastle Substation | Add 115/34kV transformer with two 115kV breakers |  | Under Construction | 2008-08-20 | 2008-08-20 |  | 1300000
Reliability Upgrade | 1a | 1128 | Central Maine Power Company |  | 07/2010 | CMP-LSP Hotel Road Substation | Add 115/34kV transformer with 115kV breaker at Hotel Rd. |  | Planned | 2008-08-20 | No |  | 800000
Reliability Upgrade | 1a | 144 | Bangor Hydro-Electric Company |  | 12/2010 | Keene Rd Autotransformer | Installation of a 345/115 kV autotransformer at Keene Rd Substation. | Proposed | Under Construction | No | No | 20000000 | 29000000
Reliability Upgrade | 1a | 905 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Planned | Planned | 2008-07-31 | No | 1354000000 | 1510000000
Reliability Upgrade | 1a | 906 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Coopers Mills-Highland, Larrabee Road-Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 907 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 84 (Albion Road-Coopers Mills), Section 203 (Detroit-Orrington), Section 80 (Coopers Mills-Highland), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 908 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New capacitor (10.8 MVAr at Belfast) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377 & Maine Yankee 375/392, 115kV Bucksport 65/205) and Maine Yankee 345 kV re-termination | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1026 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Three Rivers) | Planned | Planned | 7/31/2008 & 2/26/09 | No | $70,000,000 (NU portion of MPRP) | Portion of CMP $1.51B and portion of NU is $35.1M
Reliability Upgrade | 1a | 1027 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV Line Construction (Elm Street-East Deering, East Deering -Cape) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1028 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Portion of CMP $1.354B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD
Reliability Upgrade | 1a | 1029 | Central Maine Power Company |  | 12/2009 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformer at South Gorham | Planned | Under Construction | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1030 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Raven Farm, Maguire Road) | Planned | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 143 | Bangor Hydro-Electric Company |  | 12/2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation to Harrington Substation. | Planned | Planned | 2006-05-10 | 2008-06-13 | 66100000 | 66100000
Generator Interconnection Upgrade | 2a | 1134 | Central Maine Power Company |  | 12/2010 | Kibby Wind Farm | Separate Section 215 from Section 63 and terminate Section 215 at newly established breaker position in Wyman Hydro S/S, which includes re-rating of Section 215. Expand Bigelow S/S & add capacitor banks at Lakewood, Guilford, Wyman Hydro Station & Sturtevant S/S's. |  | Planned | 2006-06-16 | NR |  | NR
Generator Interconnection Upgrade | 2a | 770 | Central Maine Power Company |  | TBD | Queue Position 137 | Installation of New Page Substation (aka Railroad Street Substation) with (3) circuit breakers tapping Section 218 115 kV. | Proposed | Proposed | 2007-03-18 | NR | NR | NR
NEW HAMPSHIRE
Reliability Upgrade | 1a | 267 | Northeast Utilities | Central Maine Power Company | 07/2009 | Y138 Closing | White Lake - Saco Valley (Y138) Line Closing - Add PAR on Y138 at Saco Valley, retension lines, upgrade Beebe terminal, and add capacitor banks at White Lake and Beebe. | Under Construction | Under Construction | 01/01/2006 | No | 28412000 | 27775000
Reliability Upgrade | 1a | 174 | National Grid, USA |  | 07/2009 | Monadnock Area Reliability Project | Reconductor I-135 (Bellows Falls-Monadnock Tap-Flagg Pond) 115 kV line. | Planned | Under Construction | 03/24/2006 | No | 9600000 | 9600000
Reliability Upgrade | 1a | 176 | Northeast Utilities |  | 2009-08-01 | Monadnock Area Reliability Project | New Fitzwilliam 345/115kV substation along with 345 kV breakers. | Under Construction | Under Construction | 2007-09-27 | No | 76100000 | 76100000
Reliability Upgrade | 1a | 680 | National Grid, USA |  | 11/2011 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | Planned | 2008-01-28 | No | 11497000 | 11497000
Reliability Upgrade | 1a | 674 | National Grid, USA |  | 10/2012 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | Planned | 2008-04-01 | No | 12000000 | 12000000
Generator Interconnection Upgrade | 2a | 724 | National Grid, USA |  | 11/2009 | NGRID Comerford Substation | NGRID Comerford Substation. | Planned | Planned | 2007-06-12 | NR | NR | NR
VERMONT
Reliability Upgrade | 1a | 320 | Vermont Electric Power Company |  | 09/2009 | Lamoille County Project | Middlesex Substation 115 kV breaker addition. | Under Construction | Under Construction | 08/16/2007 | 02/07/2008 | 4857000 | 4857000
Reliability Upgrade | 1a | 322 | Vermont Electric Power Company |  | 09/2009 | Lamoille County Project | Installation of new Duxbury Substation that involves looping in and out of the Middlesex - Essex 115 kV (K24) line. | Under Construction | Under Construction | 08/16/2007 | 02/07/2008 | Part of Lamoille County Project | Part of Lamoille County Project
Reliability Upgrade | 1a | 139 | Vermont Electric Power Company |  | 12/2010 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Planned | Planned | 01/10/2003 | 03/31/2003 | 20000000 | 20000000
Reliability Upgrade | 1a | 182 | Vermont Electric Power Company |  | 09/2009 | Monadnock Area Reliability Project | Upgrade bus cable at N. Rutland and K35 115 kV breaker at Rutland. | Planned | Under Construction | 03/24/2006 | No | 1000000 | 1000000
Reliability Upgrade | 1a | 321 | Vermont Electric Power Company |  | 12/2009 |  | Burlington 115kV Loop - 5 mi of new line & rebuilding 5 miles of existing line between two existing substations with expansion of the East Avenue substation. | Planned | Under Construction | 10/24/2006 | 05/23/2007 | 25142000 | 25142000
Reliability Upgrade | 1a | 323 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | New VY - Newfane - Coolidge 345 kV line with requisite station upgrades. | Planned | Under Construction | 2008-10-01 | No | 135300000 | 136368000
Reliability Upgrade | 1a | 1032 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Installation of a new 345/115kV substation called Vernon including a new 345/115kV autotransformer | Planned | Under Construction | 2008-10-01 | No | 64600000 | 69815000
Reliability Upgrade | 1a | 1033 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project (VELCO LSP - Newfane Substation) | Installation of a new 345/115kV substation called Newfane | Planned | Under Construction | 2008-10-01 | No | 38500000 | 16664000
Reliability Upgrade | 1a | 1034 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Loop new 345kV Line into Newfane Substation. | Planned | Under Construction | 2008-10-01 | No | 18000000 | Part of project 323
Reliability Upgrade | 1a | 1035 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Expansion of Coolidge 345kV substation | Planned | Under Construction | 2008-10-01 | No | 18000000 | 20117000
Generator Interconnection Upgrade | 2a | 1036 | Vermont Electric Power Company |  | 12/2009 | Queue Position 172 | Installation of 3-breaker 115kV ring bus interconnection of the St. Johnsbury-Irasburg 115kV K39 line. | Planned | Planned | 08/16/2007 | NR | NR | NR
MASSACHUSETTS
Reliability Upgrade | 1a | 887 | National Grid, USA |  | 05/2012 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Planned | Planned | 2008-01-28 | No | 30000000 | 30000000
Reliability Upgrade | 1a | 921 | National Grid, USA |  | 01/2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | Planned | 2008-01-28 | No | 12100000 | 12100000
Reliability Upgrade | 1a | 919 | National Grid, USA |  | 12/2012 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | Planned | 2008-01-28 | No | 4600000 | 4600000
Reliability Upgrade | 1a | 840 | NSTAR Electric Company |  | 10/2010 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Concept | Planned | 2008-04-01 | No | 5400000 | 7300000
Reliability Upgrade | 1a | 775 | National Grid, USA |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Addition of 4 breakers and relocation of T1 and T2 into new bays at Sandy Pond. | Planned | Planned | 2008-06-27 | No | 20100000 | 20100000
Reliability Upgrade | 1a | 777 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Build Wakefield Junction station with four 345/115 kV autotransformers. | Under Construction | Under Construction | 2008-04-01 | No | 95000000 | 95000000
Reliability Upgrade | 1a | 161 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Loop 345 kV 339 line and 115 kV S-145/T-146 into new Wakefield Jct. Substation. | Under Construction | Under Construction | 2008-04-01 | No | 3200000 | 4986431
Reliability Upgrade | 1a | 779 | National Grid, USA |  | 04/2010 | Merrimack Valley/North Shore Reliability Project | Bypass and remove Golden Hills 345 kV substation. | Under Construction | Under Construction | 2008-04-01 | No | 4000000 | 5132609
Reliability Upgrade | 1a | 776 | National Grid, USA |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | Planned | 2008-06-27 | No | 2865876 | 2865876
Reliability Upgrade | 1a | 782 | National Grid, USA |  | 10/2013 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor n Railyard. | Planned | Planned | 2008-06-27 | No | 37600000 | 38100000
Reliability Upgrade | 1a | 961 | NSTAR Electric Company |  | 11/2010 | Mystic Breaker Additions Project | Install (2) new 115 kV East Bus breakers #30 and #32 at Mystic and move Transformer 110B Connection. | Planned | Planned | 2008-03-10 | No | 3800000 | 3800000
Reliability Upgrade | 1a | 302 | NSTAR Electric Company |  | 07/2009 | Boston Area 115 kV Enhancements | DCT separation of Framingham to Speen St. 433-507 circuit. | Under Construction | Under Construction | 01/18/2005 | 03/01/2005 | 3100000 | 3100000
Reliability Upgrade | 1a | 903 | NSTAR Electric Company |  | 12/2009 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #2, #4, #5, and #16 at Mystic to IPT and separate controls with Boston Gen units #5 and #6. | Planned | Planned | NR | NR | 1240000 | 1240000
Reliability Upgrade | 1a | 904 | NSTAR Electric Company |  | 12/2010 | Mystic IPT Breaker Project | Upgrade (5) 115 kV breakers #1, #7, #15 #19 and #20 at Mystic to IPT and separate controls with Boston Gen #4. | Planned | Planned | NR | NR | 990000 | 990000
Reliability Upgrade | 1a | 59 | National Grid, USA |  | 01/2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | Planned | 03/12/2002 | 2003-01-31 | 400000 | 400000
Reliability Upgrade | 1a | 695 | NSTAR Electric Company |  | 04/2009 | Short Term Lower SEMA Upgrades | Loop (355) 345 kV line in and out of Carver Substation and add (5) new 345 kV circuit breakers at Carver substation. | Planned | Under Construction | 08/17/2007 | No | 10800000 | $86.6 M (Total NSTAR Project Cost)
Reliability Upgrade | 1a | 830 | NSTAR Electric Company |  | 04/2009 | Short Term Lower SEMA Upgrades | Add a second 345/115 kV Auto transformer at Carver substation and add (1) new 345 kV circuit breaker and (3) new 115 kV circuit breakers at Carver substation. | Planned | Under Construction | 08/17/2007 | No | 8000000 | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 831 | NSTAR Electric Company |  | 06/2009 | Short Term Lower SEMA Upgrades | Add a second 115 kV line from Carver to Tremont and add (2) new 115 kV circuit breakers at Carver substation and (1) new 115 kV circuit breaker at Tremont substation. | Planned | Under Construction | 08/17/2007 | No | 2500000 | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 832 | NSTAR Electric Company |  | 09/2009 | Short Term Lower SEMA Upgrades | Add(1) 115kV SVC (0-112 MVARs lagging) at Barnstable. | Planned | Under Construction | 08/17/2007 | No | 16000000 | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 931 | National Grid, USA |  | 06/2009 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | Planned | 12/17/2007 | No | 531481 | 531481
Reliability Upgrade | 1a | 930 | National Grid, USA |  | 12/2009 | Central/Western Massachusetts Upgrades | Reconductor Nashua St - Quinsigamond Jct (O141) 115 kV line w/636 ACSS. | Planned | Planned | 12/17/2007 | No | 1765000 | 2300000
Reliability Upgrade | 1a | 934 | National Grid, USA |  | 12/2009 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Planned | Planned | 12/17/2007 | No | 818480 | 818480
Reliability Upgrade | 1a | 933 | National Grid, USA |  | 04/2010 | Central/Western Massachusetts Upgrades | Reconductor Pratts Jct - Flagg Pond I-135S & J-136S 115 kV lines w/795 ACSS. | Planned | Planned | 12/17/2007 | No | 5952582 | 6137112
Reliability Upgrade | 1a | 938 | National Grid, USA |  | 06/2010 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | Planned | 12/17/2007 | No | 3068556 | 3068556
Reliability Upgrade | 1a | 942 | National Grid, USA |  | 06/2010 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | Planned | 12/17/2007 | No | 2767180 | 2767180
Reliability Upgrade | 1a | 935 | National Grid, USA |  | 07/2010 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Planned | Planned | 12/17/2007 | No | 5208509 | 5208509
Reliability Upgrade | 1a | 927 | National Grid, USA |  | 07/2010 | Central/Western Massachusetts Upgrades | Greendale - replace 115 kV breaker and upgrade to 2000A. | Planned | Planned | 12/17/2007 | No | 584629 | 584629
Reliability Upgrade | 1a | 929 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | Planned | 12/17/2007 | No | 1381849 | 1381849
Reliability Upgrade | 1a | 936 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Reconductor (P142/P142S) Rolfe Avenue - West Bolyston 115 kV line w/1590 ACSR. | Planned | Planned | 12/17/2007 | No | 2890000 | 3000000
Reliability Upgrade | 1a | 928 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | Planned | 12/17/2007 | No | 1945218 | 1945218
Reliability Upgrade | 1a | 924 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | Planned | Planned | 12/17/2007 | No | 2147181 | 2147181
Reliability Upgrade | 1a | 943 | National Grid, USA |  | 01/2011 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | Planned | 12/17/2007 | No | 1073995 | 1073995
Reliability Upgrade | 1a | 946 | National Grid, USA |  | 03/2011 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer - E Longmeadow - Shaker Rd line to 115 kV. | Planned | Planned | 12/17/2007 | No | 14809054 | 9604032
Reliability Upgrade | 1a | 947 | National Grid, USA |  | 03/2011 | Central/Western Massachusetts Upgrades | Reconductor 115 kV line from Palmer to new Hampden Substation. | Planned | Planned | 12/17/2007 | No | 14170733 | 2632635
Reliability Upgrade | 1a | 940 | National Grid, USA |  | 04/2011 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS. | Planned | Planned | 12/17/2007 | No | 6235744 | 6235744
Reliability Upgrade | 1a | 945 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Adams - install third 115 kV breaker to complete ring bus. | Planned | Planned | 12/17/2007 | No | 1581841 | 1581841
Reliability Upgrade | 1a | 948 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | Planned | 12/17/2007 | No | 5649430 | 5649430
Reliability Upgrade | 1a | 949 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | Planned | 12/17/2007 | No | 1694829 | 1694829
Reliability Upgrade | 1a | 952 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Reconductor E Winchendon - J136 Tap within I135/J136 ROW w/795 ACSR. | Planned | Planned | 12/17/2007 | No | 932156 | 932156
Reliability Upgrade | 1a | 925 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | Planned | 12/17/2007 | No | 318888 | 318888
Reliability Upgrade | 1a | 926 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | Planned | 12/17/2007 | No | 4889621 | 6027520
Reliability Upgrade | 1a | 932 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | Planned | 12/17/2007 | No | 372036 | 372036
Reliability Upgrade | 1a | 937 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | Planned | 12/17/2007 | No | 6602875 | 6602875
Reliability Upgrade | 1a | 955 | National Grid, USA |  | 11/2011 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | Planned | 12/17/2007 | No | 10779113 | 10779113
Reliability Upgrade | 1a | 939 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Reconductor and retension (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | Planned | Planned | 12/17/2007 | No | 3287738 | 3389658
Reliability Upgrade | 1a | 941 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Install new Millbury - Tower #510 115 kV line. | Planned | Planned | 12/17/2007 | No | 5753542 | 7909203
Reliability Upgrade | 1a | 944 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Planned | Planned | 12/17/2007 | No | 9898000 | 11411849
Reliability Upgrade | 1a | 950 | National Grid, USA |  | 02/2012 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | Planned | 12/17/2007 | No | 899312 | 1016897
Reliability Upgrade | 1a | 953 | National Grid, USA |  | 02/2012 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | Planned | 12/17/2007 | No | 9444260 | 10248067
Reliability Upgrade | 1a | 954 | National Grid, USA |  | 02/2012 | Central/Western Massachusetts Upgrades | E Westminster - install new 115 kV breaker, including disconnect switches. Assumes no new control house. | Planned | Planned | 12/17/2007 | No | 799506 | 903909
Reliability Upgrade | 1a | 951 | National Grid, USA |  | 02/2013 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon 115 kV line. | Planned | Planned | 12/17/2007 | No | 6400522 | 7455440
Reliability Upgrade | 1a | 1064 | NSTAR Electric Company |  | 04/2009 |  | Install (1) 345kV 160 MVAR shunt reactor at Mystic Station | Planned | Planned | 2008-09-26 | No | 8000000 | 10400000
Reliability Upgrade | 1a | 166 | National Grid, USA |  | 06/2009 |  | Replace (16) 115 kV breakers at Tewksbury 22. | Under Construction | Under Construction | NR | NR | 3300000 | 3300000
Reliability Upgrade | 1a | 162 | National Grid, USA |  | 04/2010 |  | Q-169 Golden Hills to Lynn 115 kV line upgrade. | Under Construction | Under Construction | 2005-09-02 | 2008-04-25 | 12390000 | 12390000
Reliability Upgrade | 1a | 673 | National Grid, USA |  | 07/2010 | Worcestor Area Reinforcements | Bloomingdale Substation - #27 install 115 kV breaker. | Concept | Planned | 2009-02-27 | No | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | National Grid, USA |  | 03/2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) | Concept | Planned | 2009-02-27 | No | 30000000 | 30000000
Reliability Upgrade | 1a | 1000 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | Planned | Planned | 2008-06-27 | No | 22000000 | 22000000
Reliability Upgrade | 1a | 1076 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1077 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 902 | National Grid, USA |  | 03/2012 | Middleboro Municipal | Close the E1-M1 loop at Middleboro's Wareham St Sub. | Under Construction | Under Construction | 12/01/2006 | NR | 715000 | 715000
Reliability Upgrade | 1a | 687 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | Planned | 2008-09-24 | No | 714000000 | 714000000
Reliability Upgrade | 1a | 826 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 196 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115kV line South Agawam to Southwick (1768) | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVAR Capacitor additions | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1074 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1078 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Generator Interconnection Upgrade | 2a | 1045 | National Grid, USA |  | 06/2010 | Lowell Power | Upgrade 137T and K-137W 115 kV circuit breakers at Sandy Pond. | Planned | Planned | 2006-07-25 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 505 | National Grid, USA |  | 07/2010 | Hoosac Wind Farm | Tap Y-25S line between Harriman and Deerfield 5. Construct 69/34.5 kV substation and 34.5 kV line connecting 30 MW generating facility with the 69 kV system. | Planned | Planned | 02/01/2005 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 595 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Expansion of Barnstable 115 kV substation to include 5th bay and (2) circuit breakers, addition of a 3rd breaker in the planned 4th bay, and (2) 35MVAr shunt reactors. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 596 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Installation of (2) 115 kV circuits out of Barnstable substation to interconnect Cape Wind. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 598 | NSTAR Electric Company |  | 11/2010 | Cape Wind | At Canal 345 kV substation, install a redundant breaker in series with breaker #312. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 599 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Upgrade the Bourne 115 kV breaker #12272 with an IPT breaker. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 600 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Installation of differential insulation and additional grounding at each tower that is common for the 342 and 322 345 kV lines. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1048 | NSTAR Electric Company |  | 11/2010 | Cape Wind | Convert Canal 345 kV SPS to include tripping of Cape Wind for the simultaneous loss of 342 and 322 345 kV lines. | Planned | Planned | 2005-10-06 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1046 | National Grid, USA |  | 06/2011 | Queue Position 178 | Reconductor 115 kV F19 Line (Auburn - Brockton Tap). | Proposed | Proposed | 2008-03-10 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1047 | National Grid, USA |  | 06/2011 | Queue Position 178 | Replace Bridgewater 115 kV 1631 circuit breaker with 63 kA breaker. | Proposed | Proposed | 2008-03-10 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 622 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Interconnection to WMECO's 115-kV 1512 line through a new Substation. | Proposed | Proposed | 06/01/2007 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1043 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Upgrade the 1768 line terminal equipment at Southwick Substation. | Proposed | Proposed | 06/01/2007 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1044 | Northeast Utilities |  | 06/2011 | Queue Position 135 | Upgrade the 1512 line terminal equipment at Southwick Substation. | Proposed | Proposed | 06/01/2007 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1058 | National Grid, USA |  | 06/2011 | Billerica Power | Interconnection to Tewksbury 115 kV Substation via O-193 Line and refurbish section of J-162 line. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1059 | National Grid, USA |  | 06/2011 | Billerica Power | Re-terminate line tap section (Perry Street) of J-162 Line to new bay position at Tewksbury. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1060 | National Grid, USA |  | 06/2011 | Billerica Power | Reconductor 2.8 mi. of the M-139 115 kV line. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1061 | National Grid, USA |  | 06/2011 | Billerica Power | Replace (16) 115 kV circuit breakers at Tewksbury 22 w/ IPT capability if all generators w/ higher Queue Position are constructed. The quantity of breaker upgrades subject to Queued generators constructed. | Planned | Planned | 2008-07-08 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1062 | National Grid, USA |  | 06/2011 | Billerica Power | Upgrade #137T and #K-137W 115 kV circuit breakers at Sandy Pond (if not completed as part of Merrimack Valley/North Shore Project). | Planned | Planned | 2008-07-08 | NR | NR | NR
Elective | 4a | 1057 | Braintree Electric Light Department |  | 06/2010 |  | Upgrade 115-10-16 underground 115 kV cable. | Planned | Planned | 2008-04-17 | No | TBD | TBD
RHODE ISLAND
Reliability Upgrade | 1a | 484 | National Grid, USA |  | 01/2010 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Planned | Planned | 2008-04-25 | No | 690000 | 690000
Reliability Upgrade | 1a | 792 | National Grid, USA |  | 01/2011 | Greater Rhode Island Transmission Reinforcements 1 | Admiral St-Franklin Square (Q143 and R144) 115 kV UG recabling. | Planned | Planned | 2008-04-25 | No | 22500000 | 39200000
Reliability Upgrade | 1a | 913 | National Grid, USA |  | 02/2011 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | Planned | 2008-04-25 | No | 3250000 | 3250000
Reliability Upgrade | 1a | 793 | National Grid, USA |  | 02/2011 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | Planned | 2008-04-25 | No | 6400000 | 6400000
Reliability Upgrade | 1a | 791 | National Grid, USA |  | 06/2011 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | Planned | 2008-04-25 | No | 11560000 | 11560000
Reliability Upgrade | 1a | 914 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | Planned | 2008-04-25 | No | 28150000 | 28150000
Reliability Upgrade | 1a | 915 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | Planned | 2008-04-25 | No | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | Planned | 2008-04-25 | No | 11800000 | 11800000
Reliability Upgrade | 1a | 917 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | Planned | 2008-04-25 | No | 7000000 | 7000000
Reliability Upgrade | 1a | 918 | National Grid, USA |  | 01/2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | Planned | 2008-04-25 | No | 3180000 | 3180000
Reliability Upgrade | 1a | 786 | National Grid, USA |  | 06/2009 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Terminal upgrades at Drumrock, Chartley Pond, and Brayton Point. | Planned | Planned | 2008-04-25 | No | 565000 | 565000
Reliability Upgrade | 1a | 789 | National Grid, USA |  | 11/2009 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Reconductoring of T7 115 kV line. | Planned | Planned | 2008-04-25 | No | 20900000 | 23304000
Reliability Upgrade | 1a | 787 | National Grid, USA |  | 12/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | West Farnum breaker replacements. | Planned | Planned | 2008-04-25 | No | 7600000 | 7631000
Reliability Upgrade | 1a | 788 | National Grid, USA |  | 12/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Kent County substation expansion. | Planned | Planned | 2008-04-25 | No | 42300000 | 42300000
Reliability Upgrade | 1a | 790 | National Grid, USA |  | 10/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Planned | Planned | 2008-04-25 | No | 50600000 | 50600000
Reliability Upgrade | 1a | 1098 | National Grid, USA |  | 10/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Planned | Planned | 2008-04-25 | No | 23000000 | 37529000
Reliability Upgrade | 1a | 1094 | National Grid, USA |  | 06/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | Planned | 2008-09-24 | No | 20800000 | 20800000
Reliability Upgrade | 1a | 1095 | National Grid, USA |  | 06/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | Planned | 2008-09-24 | No | 73800000 | 73800000
Reliability Upgrade | 1a | 795 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV line. | Planned | Planned | 2008-09-24 | No | 99900000 | 99900000
Reliability Upgrade | 1a | 1106 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | Planned | Planned | 2008-09-24 | No | Part of $99,900,000 above | Part of $99,900,000 above
Reliability Upgrade | 1a | 798 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | E-183E upgrade of 115kV terminal equipment at Franklin Square. | Planned | Planned | 2008-09-24 | No | 4900000 | 4900000
Reliability Upgrade | 1a | 799 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | Planned | Planned | 2008-09-24 | No | 4500000 | 4500000
Reliability Upgrade | 1a | 1096 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | Planned | 2008-09-24 | No | 5800000 | 5800000
Reliability Upgrade | 1a | 800 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S, T-172N and T-172S with associated terminal equipment upgrades. | Planned | Planned | 2008-09-24 | No | 7300000 | 7300000
Reliability Upgrade | 1a | 1097 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County | Planned | Planned | 2008-09-24 | No | 129800000 | 129800000
Reliability Upgrade | 1a | 1099 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | Planned | 2008-09-24 | No | 4100000 | 4100000
Reliability Upgrade | 1a | 1109 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Planned | Planned | 2008-09-24 | No | 360000 | 360000
Reliability Upgrade | 1a | 796 | National Grid, USA |  | 11/2012 | NEEWS (Interstate Reliability Project) | 347 Reconductor from Sherman Road to CT/RI Border. | Planned | Planned | 2008-09-24 | No | 16400000 | 16400000
Reliability Upgrade | 1a | 797 | National Grid, USA |  | 12/2012 | NEEWS (Interstate Reliability Project) | 3361 Upgrade 345kV terminal equipment at Sherman Road. | Planned | Planned | 2008-09-24 | No | 8300000 | 8300000
Reliability Upgrade | 1a | 190 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | Planned | 2008-09-24 | No | 69600000 | 69600000
Reliability Upgrade | 1a | 794 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | Planned | 2008-09-24 | No | 55800000 | 55800000
CONNECTICUT
Reliability Upgrade | 1a | 1009 | Northeast Utilities |  | 05/2009 |  | Install a 2% reactor on the North Bloomfield-Canton 115kV line. | Under Construction | Under Construction | 2007-10-20 | No | 2075000 | 3638000
Reliability Upgrade | 1a | 203 | Northeast Utilities |  | 05/2009 | NU LSP - Stepstone Substation | Install new Stepstone 115 kV substation in Guilford. | Under Construction | Under Construction | 2005-11-08 | 2006-04-24 | 4465000 | 6332000
Reliability Upgrade | 1a | 211 | Northeast Utilities |  | 10/2009 | NU LSP - Rood Ave Substation | New Rood Ave (formally Windsor) distribution substation with 115kV terminal modifications. | Under Construction | Under Construction | 2008-04-25 | 02/15/2008 | 9162029 | 9162029
Reliability Upgrade | 1a | 1110 | United Illuminating Company |  | 06/2010 |  | Broadway 115/13.8 kV Substation Additon | Proposed | Planned | 2008-12-08 | NR | 1000000 | 800000
Reliability Upgrade | 1a | 1111 | United Illuminating Company |  | 09/2010 |  | Metro North Union Avenue 115/26.4 kV Substation | Proposed | Planned | 2009-01-07 | No | 8700000 | 8700000
Reliability Upgrade | 1a | 1049 | United Illuminating Company |  | 12/2010 |  | East Shore 115 kV Capacitor Bank Transient Recovery | Planned | Planned | NR | NR | 3000000 | 3000000
Reliability Upgrade | 1a | 582 | Northeast Utilities |  | 12/2010 |  | Separate 310 and 368 345-KV lines and create 368/1767 DCT | Planned | Planned | 2008-07-18 | No | 16000000 | 16000000
Reliability Upgrade | 1a | 1050 | United Illuminating Company |  | 12/2010 |  | Devon Tie 115kV Switching Station BPS Compliance | Concept | Planned | NR | NR | 2620000 | 2620000
Reliability Upgrade | 1a | 1112 | United Illuminating Company |  | 12/2010 |  | Water Street 115kV circuit breaker and switch replacements. | Planned | Planned | NR | NR | 1000000 | 1000000
Reliability Upgrade | 1a | 1056 | Northeast Utilities |  | 12/2011 | CT LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Concept | Planned | 2008-12-12 | No | TBD | 9751000
Reliability Upgrade | 1a | 974 | United Illuminating Company |  | 12/2011 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Planned | Planned | NR | No | 6700000 | 6700000
Reliability Upgrade | 1a | 976 | United Illuminating Company |  | 05/2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Proposed | Planned | 2009-01-07 | No | 48000000 | 48000000
Reliability Upgrade | 1a | 816 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1054 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Manchester - Meekvile Jct. line (395/1448) separation. | Planned | Planned | 2008-09-24 | No | 14000000 | 14000000
Reliability Upgrade | 1a | 576 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | Planned | 2008-09-24 | No | 313000000 | 313000000
Reliability Upgrade | 1a | 1114 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1a | 814 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Central Connecticut Relaibility Project) | Reconductor a portion of the Manchester to Scovill Rock 353 345-kV line and terminal work. | Planned | Planned | 2008-09-24 | No | 9000000 | 9000000
Reliability Upgrade | 1a | 802 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | Planned | 2008-09-24 | No | 251000000 | 251000000
Reliability Upgrade | 1a | 1084 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Loop the Millstone - Manchester (310) 345 kV line into the Card substation. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1085 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1086 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1087 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1088 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1089 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Killingly 3G substation 345kV breaker addition | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1090 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Millstone 15G substation breaker 14T upgrade 50kA | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1091 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Southington 4C substation breaker 19T upgrade to 63kA | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | Northeast Utilities | National Grid, USA | 12/2013 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 807 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Interstate Reliability Project) | Install 480 MVAR's of capacitors at the Montville 345 kV substation | Planned | Planned | 2008-09-24 | No | 33000000 | 33000000
Reliability Upgrade | 1a | 1092 | Northeast Utilities |  | 12/2013 | NEEWS (BPS) 2 | Upgrade the Card 115 kV, East Hartford 115 kV, Agawam 115 kV, Barbour Hill 115 kV, and North Bloomfield 345 kV Substations to BPS standards. | Planned | Planned | 2008-09-24 | No | 37000000 | 37000000
Reliability Upgrade | 1a | 879 |  | Bangor Hydro-Electric Company, New England Power Company, Northeast Utilities System Com | TBD | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | Planned | 03/01/2007 | NR | 420000 | 420000
Generator Interconnection Upgrade | 2a | 983 | Northeast Utilities |  | 10/2010 | Queue Position 207 | Rebuild 115 kV 1585N Line between new substation and Bunker Hill. | Proposed | Proposed | 2008-09-26 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1107 | Northeast Utilities |  | 10/2010 | Queue Position 207 | Interconnection to new 115 kV substation consisting of (14) circuit breakers in a breaker and a half configuration that sectionalizes the existing 1575, 1585, and 1990 lines. | Proposed | Proposed | 2008-09-26 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1108 | Northeast Utilities |  | 10/2010 | Queue Position 207 | Installation of a 2.5% series reactor on the 1990S Line at the new substation. | Proposed | Proposed | 2008-09-26 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 331 | Northeast Utilities |  | 11/2010 | Kleen Energy | Install 5-breaker ring bus interconnecting between Scovill Rock and Manchester on the 345 kV 353 Line. | Planned | Planned | 10/08/2003 | NR | NR | NR
Generator Interconnection Upgrade | 2a | 1121 | Northeast Utilities |  | 06/2010 | Queue Position 161-2 | Four units connected to 384 line through a new 345kV Substation: unit #4 wll also connect to Substation |  | Proposed | 2008-12-08 | NR |  | NR
Generator Interconnection Upgrade | 2a | 1122 | Northeast Utilities |  | 11/2010 | Queue Position 191 | One turbine connected to #1238 Line (Frost Bridge to Carmel) via a new 3-breaker ring bus Substation |  | Proposed | 2009-02-24 | NR |  | NR
Generator Interconnection Upgrade | 2a | 1126 | Northeast Utilities |  | TBD | Queue Position 161-4 | Two units and repowering of #6 Montville 345kV Substation |  | Proposed | 2008-06-09 | NR |  | NR
TABLE B
MAINE
Reliability Upgrade | 1b | 1130 | Central Maine Power Company |  | 12/2009 | Sturtevant Improvements | Add 115kV circuit breakers & capacitor bank at Sturtevant Substation |  | Proposed | No | No |  | 2000000
Reliability Upgrade | 1b | 148 | Central Maine Power Company |  | 06/2010 | CMP LSP - Saco Bay Area Reinforcement Project | Establish a new Old Orchard Beach 115/34.5 kV substation and 115 kV line. | Concept | Proposed | No | No | 16900000 | 16900000
Reliability Upgrade | 1b | 1133 | Central Maine Power Company |  | 10/2010 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation & new 34kV line from Leeds to Turner |  | Proposed | No | No |  | 300000
Reliability Upgrade | 1b | 1116 | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild |  | Concept | No | No |  | TBD
Reliability Upgrade | 1b | 1031 | Bangor Hydro-Electric Company |  | 01/2012 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station, Rebuild Line 66, and Capacitior Bank Additions (10MVAr at Treneton, Downeast & Handcock County area) | Proposed | Concept | No | No | Part of Maine Power Reliability Program | TBD
Reliability Upgrade | 1b | 1131 | Central Maine Power Company |  | 12/2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer |  | Proposed | No | No |  | 600000
Reliability Upgrade | 1b | 1132 | Central Maine Power Company |  | 12/2011 | CMP-LSP Maxcy's Substation | Add 115/34kV transformer (coordinate with MPRP) |  | Proposed | No | No |  | 600000
Elective | 4b | 1018 | Bangor Hydro-Electric Company |  | TBD | Orrington-Boston HVDC | Orrington substation reconfiguration and addition of new HVDC cable system terminating in Boston area. | Concept | Concept | No | No | TBD | TBD
Elective | 4b | 984 | Central Maine Power Company | Maine Public Service | TBD | MEPCO-MPS 345 kV Interconnection | MEPCO-MPS 345 kV Interconnection. | Concept | Concept | No | No | TBD | TBD
NEW HAMPSHIRE
Reliability Upgrade | 1b | 275 | Northeast Utilities |  | TBD |  | Merrimack 115-kV substation - Protection Separation Upgrade. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 277 | Northeast Utilities |  | TBD |  | Add 2nd 345 kV autotransformer at Deerfield and associated substation work | Concept | Concept | No | No | TBD | TBD
Generator Interconnection Upgrade | 2b | 869 | Northeast Utilities |  | 06/2013 | Queue Position 165 | Rebuild 345 kV 326 Line | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1041 | Northeast Utilities |  | 06/2013 | Queue Position 165 | Rebuild 115 kV U181 Line | Concept | Concept | No | NR | NR | NR
VERMONT
Reliability Upgrade | 1b | 318 | Vermont Electric Power Company |  | 12/2011 |  | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems through the 1,250 MW Vermont state load level. | Concept | Concept | No | No | 9000000 | 9000000
Reliability Upgrade | 1b | 325 | Vermont Electric Power Company |  | 12/2011 | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | Concept | No | No | 5000000 | 5000000
Reliability Upgrade | 1b | 324 | Vermont Electric Power Company |  | 12/2012 |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | Concept | No | No | 100000000 | 100000000
MASSACHUSETTS
Reliability Upgrade | 1b | 1063 | NSTAR Electric Company |  | 12/2009 |  | Install (2) 115kV 40 MVAR shunt reactors at Edgar Station | Concept | Proposed | No | No | TBD | 5400000
Reliability Upgrade | 1b | 963 | NSTAR Electric Company |  | 12/2009 | Boston Area 115 kV Enhancements | Add a new 115kV breaker # 11 at Holbrook. | Concept | Proposed | No | No | TBD | 3400000
Reliability Upgrade | 1b | 842 | NSTAR Electric Company |  | 06/2010 | Boston Area 115 kV Enhancements | Add 115 kV 54 MVAR capacitor bank at W. Framingham. | Concept | Proposed | No | No | TBD | 3000000
Reliability Upgrade | 1b | 964 | NSTAR Electric Company |  | 12/2011 | Boston Area 115 kV Enhancements | Add a new series breaker # 8 at W. Walpole. | Concept | Proposed | No | No | TBD | 5600000
Reliability Upgrade | 1b | 965 | NSTAR Electric Company |  | 12/2012 | Boston Area 115 kV Enhancements | Add third 115kV line from Walpole to Holbrook | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 969 | NSTAR Electric Company |  | 12/2012 | Boston Area 115 kV Enhancements | Add a new 54 MVAR capacitor bank at Chelsea. | Concept | Concept | No | No | 1200000 | 1200000
Reliability Upgrade | 1b | 301 | NSTAR Electric Company |  | 12/2012 | Boston Area 115 kV Enhancements | Reconductor 115-kV circuits 320-507 and 320-508. | Concept | Concept | No | No | 4600000 | 4600000
Reliability Upgrade | 1b | 843 | NSTAR Electric Company |  | 12/2013 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1119 | NSTAR Electric Company |  | 12/2009 | Greater Boston Reliability Project | Remove limiting ground clearance conditions on West Medway-West Walpole 345kV line (#325 ) |  | Proposed | No | No |  | 1300000
Reliability Upgrade | 1b | 970 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345 kV line from Lexington to Waltham. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 971 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 1113 | NSTAR Electric Company |  | 06/2010 |  | Install KSt Breaker #301 | Concept | Proposed | No | No | TBD | 2100000
Reliability Upgrade | 1b | 1120 | NSTAR Electric Company |  | 06/2010 |  | Install 345kV 160 MVAR shunt ractor at W. Walpole |  | Proposed | No | No |  | 6000000
Reliability Upgrade | 1b | 1067 | NSTAR Electric Company |  | 12/2010 | NPCC BPS Compliance | Tremont Station | Proposed | Proposed | No | No | 7100000 | 11200000
Reliability Upgrade | 1b | 1066 | NSTAR Electric Company |  | 09/2011 | NPCC BPS Compliance | Needham Station | Proposed | Proposed | No | No | 7500000 | 9300000
Reliability Upgrade | 1b | 1065 | NSTAR Electric Company |  | 07/2012 | NPCC BPS Compliance | Waltham Station | Proposed | Proposed | No | No | 22000000 | 24300000
Reliability Upgrade | 1b | 783 | National Grid, USA |  | 12/2010 | Merrimack Valley/North Shore Reliability Project | Extend the 115kV by addition of 115kV Breaker and K-153 line from King St. to W. Amesbury 115kV station. (W. Amesbury 345/115kV Station becomes PTF) | Concept | Concept | 2008-04-01 | No | 30349000 | 30349000
Reliability Upgrade | 1b | 785 | National Grid, USA |  | 07/2017 | Merrimack Valley/North Shore Reliability Project | Re-conductor F-158N (Golden Hills-Maplewood-Everett) 115 kV line. | Concept | Concept | No | No | 1330000 | 1330000
Reliability Upgrade | 1b | 1068 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to Sandwich and a a 345-115kV auto-transformer at Sandwich | Concept | Proposed | No | No | TBD | 110000000
Reliability Upgrade | 1b | 593 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Add a new 115 kV line from Canal to Barnstable. | Concept | Proposed | No | No | TBD | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 592 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing | Concept | Proposed | No | No | TBD | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1117 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install 115kV 50 MVAR capacitor bank at Falmouth | Concept | Proposed | No | No | TBD | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1118 | NSTAR Electric Company | National Grid, USA | 12/2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 and 111 | Concept | Proposed | No | No | TBD | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 956 | National Grid, USA |  | 05/2013 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Concept | Concept | No | No | 7021534 | 7021534
Reliability Upgrade | 1b | 824 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 825 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Upgrade the Pleasant to Blanford 115-kV line and the Blanford to Granville Jct. portion of the 115-kV line 1512. | Concept | Concept | No | No | TBD | TBD
Generator Interconnection Upgrade | 2b | 861 | Northeast Utilities |  | 01/2010 | Queue Position 190 | Mount Tom - W Mass. Mt. Tom 115 kV Substation. | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 863 | Northeast Utilities |  | 06/2010 | Queue Position 217 | Northfield Mountain - W. Mass Northfield 345 kV substation. | Proposed | Proposed | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1014 | Northeast Utilities |  | 06/2010 | Queue Position 196 | 345 kV Northfield Substation | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 880 | National Grid, USA | Northeast Utilities | 06/2011 | Queue Position 177 | Sutton Energy - 345 kV Carpenter Hill-Millbury Line. | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1042 | National Grid, USA |  | 06/2013 | Queue Position 165 | Replace (2) 345 kV circuit breakers at Sandy Pond | Concept | Concept | No | NR | NR | NR
Generator Interconnection Upgrade | 2b | 1123 | Northeast Utilities |  | TBD | Queue Position 236 | New Substation on 1302 Line; terminal upgrades at Buck Pond and Agawam |  | Concept | No | NR |  | NR
RHODE ISLAND
Generator Interconnection Upgrade | 2b | 881 | National Grid, USA | Northeast Utilities | 06/2012 | Queue Position 201 | RISEP - 345 kV RISE Substation. | Concept | Concept | No | NR | NR | NR
CONNECTICUT
Reliability Upgrade | 1b | 809 | Northeast Utilities |  | 12/2009 |  | Upgrade terminal equipment at Bunker Hill 115 kV substation. | Proposed | Proposed | No | No | 1000000 | 1000000
Reliability Upgrade | 1b | 1055 | Northeast Utilities |  | 2010 | CT LSP - Waterside Substation | Waterside Substation - add a 115/13.2-kV transformer and a 115-kV circuit breaker. | Concept | Concept | No | No | 4107000 | 4107000
Reliability Upgrade | 1b | 721 | United Illuminating Company |  | 06/2011 |  | New Shelton 115/13.8 kV substation | Proposed | Proposed | No | No | 11300000 | 11300000
Reliability Upgrade | 1b | 316 | United Illuminating Company |  | 06/2012 |  | New Fairfield 115/13.8 kV substation | Concept | Concept | No | No | 7450000 | 7450000
Reliability Upgrade | 1b | 699 | United Illuminating Company |  | 12/2012 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | Concept | No | No | 46540000 | 10000000
Reliability Upgrade | 1b | 977 | United Illuminating Company |  | 06/2013 |  | New Orange 115/13.8 kV substation | Concept | Concept | No | No | 7550000 | 7550000
Reliability Upgrade | 1b | 975 | United Illuminating Company |  | 12/2013 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | Concept | No | No | 44300000 | 44300000
Reliability Upgrade | 1b | 980 | United Illuminating Company |  | 06/2014 |  | New Hamden 115/13.8 kV substation. | Concept | Concept | No | No | 7750000 | 7750000
Reliability Upgrade | 1b | 317 | United Illuminating Company |  | 06/2014 |  | New North Branford 115/13.8-kV substation. | Concept | Concept | No | No | 7750000 | 7750000
Reliability Upgrade | 1b | 801 | Northeast Utilities |  | TBD |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Concept | Concept | No | No | TBD | TBD
Reliability Upgrade | 1b | 85 | Northeast Utilities |  | TBD |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | Concept | 08/04/2004 | No | TBD | TBD
Generator Interconnection Upgrade | 2b | 1124 | Northeast Utilities |  | TBD | Queue Position 222 | New Substation on Haddam Neck-Southington 345kV line |  | Proposed | No | NR |  | NR
Generator Interconnection Upgrade | 2b | 1125 | Northeast Utilities |  | TBD | Queue Position 240 | 345kV on Montville Substation |  | Concept | No | NR |  | NR
IN-SERVICE PROJECTS
Reliability Upgrade | 1a | 579 | Central Maine Power Company |  | 06/2008 | Maguire Road Project | Addition of (4) 345 kV breakers at Buxton. | In-Service |  | 03/01/2007 | No | 11700000
Reliability Upgrade | 1a | 587 | Northeast Utilities |  | 2008-05-13 |  | Install third 345/115-kV autotransformer at Scobie Substation. | In-Service |  | 07/01/2007 | No | 12948000
Reliability Upgrade | 1a | 282 | Northeast Utilities |  | 2008-05-26 | NU LSP - Weare Substation | Install new 115 kV Weare Street Substation and Jackman capacitors. | In-Service |  | 03/01/2007 | 05/01/2007 | 11633000
Reliability Upgrade | 1a | 580 | Northeast Utilities |  | 2008-05-30 | Scobie Pond to Hudson Reinforcement Project | Install new 115-kV Scobie - Hudson line. | In-Service |  | 07/31/2006 | No | 30947000
Reliability Upgrade | 1a | 685 | National Grid, USA |  | 03/2008 |  | New 345 kV gas circuit breaker at Auburn St. Substation on the 335 Line. | In-Service |  | 10/01/2006 | 10/01/2006 | 860000
Reliability Upgrade | 1a | 293 | NSTAR Electric Company |  | 04/2008 |  | Upgrade Canal 345-kV breaker #612 to IPT. | In-Service |  | NR | NR | 450000
Reliability Upgrade | 1a | 155 | Central Maine Power Company | Northeast Utilities | 01/2009 | Maguire Road Project | Rebuild Three Rivers - Quaker Hill 115 kV Line K197. | Under Construction | In-Service | 03/01/2007 | 2009-01-09 | 5500000 | 5500000
Reliability Upgrade | 1a | 910 | Central Maine Power Company |  | 12/2008 | Rumford-Woodstock-Kimball Road Corridor Project | Rebuild Section 211 Woodstock - Rumford. | Under Construction | In-Service | 2007-11-30 | No | 6800000 | 8400000
Reliability Upgrade | 1a | 923 | National Grid, USA |  | 12/2008 | Auburn Area Transmission System Upgrades | Reconductor 115 kV A94 line and associated substation upgrades. | Planned | In-Service | 2008-01-28 | No | 3400000 | 2400000
Reliability Upgrade | 1a | 922 | National Grid, USA |  | 02/2009 | Auburn Area Transmission System Upgrades | Reconductor 115kV L1 line and associated substation upgrades. | Planned | In-Service | 2008-01-28 | No | 1050000 | 800000
Reliability Upgrade | 1a | 781 | National Grid, USA |  | 10/2008 | Merrimack Valley/North Shore Reliability Project | Install 115 kV 30 MVAr capacitor bank at Revere. | Planned | In-Service | 2008-04-01 | No | 1500000 | 1727000
Reliability Upgrade | 1a | 168 | National Grid, USA |  | 09/2008 | Southwest Rhode Island Reliability Enhancements | Reconductor Kenyon - Wood River 115 kV 1870 line. | Under Construction | In-Service | 2005-01-01 | 03/29/2005 | 2600000 | 2234232
Reliability Upgrade | 1a | 171 | National Grid, USA |  | 10/2008 | Southwest Rhode Island Reliability Enhancements | Reconductoring L-190 between Kent Co. and Davisville. | Under Construction | In-Service | 11/10/2004 | 03/29/2005 | 3000000 | 2666291
Reliability Upgrade | 1a | 900 | National Grid, USA |  | 11/2008 | Southwest Rhode Island Reliability Enhancements | Wood River substation upgrades. | Under Construction | In-Service | 04/07/2007 | 05/07/2007 | 240000 | 130000
Reliability Upgrade | 1a | 899 | National Grid, USA |  | 12/2008 | Southwest Rhode Island Reliability Enhancements | Kenyon substation upgrades. | Under Construction | In-Service | 04/07/2007 | 05/07/2007 | 278000 | 278000
Reliability Upgrade | 1a | 177 | Northeast Utilities |  | 12/2008 | Monadnock Area Reliability Project | Replace limiting terminal equipment at Webster Substation on line to North Road. | Under Construction | In-Service | 03/24/2006 | No | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 180 | Northeast Utilities |  | 12/2008 | Monadnock Area Reliability Project | Rebuild 115 kV Keene to Swanzey A-152 line. | Under Construction | In-Service | 03/24/2006 | No | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 178 | Northeast Utilities |  | 02/2009 | Monadnock Area Reliability Project | Rebuild 115 kV Garvins to Webster V-182 line. | Under Construction | In-Service | 03/24/2006 | No | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 248 | Northeast Utilities |  | 12/2008 | Norwalk-Glenbrook Cable Project | Install two new 115 kV cables from Norwalk to Glenbrook (accommodate 345 kV class cable). | Under Construction | In-Service | 08/01/2005 | No | 222850000 | $249,372,000 3
Reliability Upgrade | 1a | 569 | Northeast Utilities-CT |  | 2007 | Norwalk-Glenbrook Cable Project | Replace two 115-kV circuit breakers at Cos Cob. | In-Service | In-Service | 08/01/2005 | No | 500000 | Part of Norwalk-Glenbrook Cable Project 3
Reliability Upgrade | 1a | 243 | Northeast Utilities |  | 09/2008 | Norwalk-Glenbrook Cable Project | Expand and upgrade to BPS and remove SPS at Glenbrook 115 kV substation. | In-Service | In-Service | 08/01/2005 | No | 8390000 | Part of Norwalk-Glenbrook Cable Project 3
Reliability Upgrade | 1a | 570 | Northeast Utilities |  | 10/2008 | Norwalk-Glenbrook Cable Project | Add second high speed relay system on the 1450 line. | In-Service | In-Service | 08/01/2005 | No | 788000 | Part of Norwalk-Glenbrook Cable Project 3
Reliability Upgrade | 1a | 571 | Northeast Utilities |  | 12/2008 | Norwalk-Glenbrook Cable Project | Upgrade Flax Hill Substation to BPS. | Under Construction | In-Service | 08/01/2005 | No | 2175000 | Part of Norwalk-Glenbrook Cable Project 3
Reliability Upgrade | 1a | 208 | Northeast Utilities |  | 12/2008 | NU LSP - Oxford Substation | Install new Oxford (previously Jack's Hill) 115 kV substation. | Under Construction | In-Service | 01/14/2006 | 06/01/2007 | 5710287 | 4459000
Reliability Upgrade | 1a | 246 | Northeast Utilities |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Add second 345/115 kV autotransformer at Norwalk Substation along with shunt reactors and 345 kV circuit breakers. | Under Construction | In-Service | 01/14/2006 | No | 1047000000 | $978,182,000 4
Reliability Upgrade | 1a | 226 | Northeast Utilities | United Illuminating Company | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install two 345 kV underground cables from Singer(UI) to Norwalk. | Under Construction | In-Service | 01/14/2006 | No | Part of SWCT (M-N) Reliability Project | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 235 | Northeast Utilities |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Expand Norwalk 345-kV substation and install transfer trip relaying scheme on the 1389 115 kV line between Norwalk and Flax Hill. | Under Construction | In-Service | 01/14/2006 | No | Part of SWCT (M-N) Reliability Project | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 247 | Northeast Utilities |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Replace Norwalk Harbor 138/115 kV autotransformer. | Under Construction | In-Service | 01/14/2006 | No | 8351000 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 684 | Northeast Utilities |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Replace (6) 115 kV breakers (4-Glenbrook, 1-Glenbrook Statcom, 1-Southington #1) and (3) 345-kV circuit breakers at Millstone and replace (4) 345- kV breakers with 500-kV breakers at Long Mountain substation. | Under Construction | In-Service | 01/14/2006 | No | 11321000 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 551 | Northeast Utilities |  | 10/2007 | Southwest Connecticut Reliability Project PH II (M-N) | Rebuild the 1466 115-kV line from East Meriden to North Wallingford and the 1588 115-kV rebuild from North Wallingford to Colony. | In-Service | In-Service | 04/01/2007 | No | 805000 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 244 | Northeast Utilities |  | 2008-06-20 | Southwest Connecticut Reliability Project PH II (M-N) | Reconductor 115 kV 1570 and 1575 line taps into Beacon Falls Substation. | In-Service | In-Service | 04/01/2007 | No | 5692000 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 239 | Northeast Utilities |  | 07/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install (1) new 115 kV circuit breaker at Devon Substation in series with 7R-2T. | In-Service | In-Service | 04/01/2007 | No | 5009000 | Part of SWCT (M-N) Reliability Project 4
Reliability Upgrade | 1a | 250 | Northeast Utilities |  | 12/2008 |  | Add a 345 kV breaker at Ludlow Substation. | Planned | In-service | 06/01/2007 | 2007-08-01 | 1644885 | 1644885
Reliability Upgrade | 1a | 841 | NSTAR Electric Company |  | 11/2008 | Mystic Breaker Additions Project | Install (2) new 115 kV West Bus breakers #29 and #31 at Mystic. | Planned | In-Service | 2008-03-10 | No | 2300000 | 2300000
Reliability Upgrade | 1a | 1040 | NSTAR Electric Company |  | 12/2008 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #11, #8, #17 and #3 at Mystic to IPT | Planned | In-Service | NR | NR | 990000 | 990000
Reliability Upgrade | 1a | 116 | NSTAR Electric Company |  | 04/2009 | NSTAR 345 kV Transmission Reliability Project | Add 2nd 345 kV UG Cables from Stoughton to Mattapan Sq.to K Street and install another new autotransformer at K. St. | Under Construction | In-Service | 02/10/2005 | 09/15/2005 | 307900000 | 307900000
Reliability Upgrade | 1a | 572 | NSTAR Electric Company |  | 04/2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 345 kV 160 MVAR shunt reactors at Stoughton. | Under Construction | In-Service | 02/10/2005 | 09/15/2005 | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 573 | NSTAR Electric Company |  | 04/2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 345 kV 160 MVAR shunt reactors at K St. | Under Construction | In-Service | 02/10/2005 | 09/15/2005 | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 772 | NSTAR Electric Company |  | 04/2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 115 kV breaker at K St. | Under Construction | In-Service | 02/01/2005 | 09/01/2005 | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 238 | United Illuminating Company |  | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) | Build new Singer 345 kV substation with (12) circuit breakers, (2) autos, (4) shunt reactors along with reconnecting Bridgeport Energy thru one of the new autos. Includes 115 kV connection from Singer to Pequonnock substation. | Under Construction | In-Service | 01/14/2006 | No | 162264000 | 162264000
Reliability Upgrade | 1a | 224 | United Illuminating Company | Northeast Utilities | 12/2008 | Southwest Connecticut Reliability Project PH II (M-N) 4 | Install new 345 kV line from East Devon to Singer(UI). | Under Construction | In-Service | 01/14/2006 | No | 157476000 | 157476000
Reliability Upgrade | 1a | 846 | United Illuminating Company |  | 11/2008 |  | Replace Mix Avenue 115 kV Oil Circuit Breaker & foundation. | Under Construction | In-Service | NR | NR | 450000 | 450000
Reliability Upgrade | 1a | 138 | Vermont Electric Power Company |  | 12/2008 | Northwest Vermont Reliability Project | N. Haven - Vergennes - Q. City 115 kV line. | Under Construction | In-Service | 01/10/2003 | 2006-12-18 | 70200000 | 70200000
Reliability Upgrade | 1a | 136 | Vermont Electric Power Company |  | 04/2009 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 1: two 115 kV PARs, four 25 MVAR Cap. banks, four +25/-12.5 MVAR synchronous condenders, and two 230/115 transformers. | Under Construction | In-Service | 01/10/2003 | 03/31/2003 | 62400000 | 62400000
Generator Interconnection Upgrade | 2a | 847 | Bangor Hydro-Electric Company |  | 12/2008 | Stetson Wind | Interconnect 60 MW of wind via 115 kV generator lead into Keene Road Substation. | Planned | In-Service | 07/01/2007 | NR | NR | NR
CANCELLED PROJECTS
Reliability Upgrade | 1b | 912 | Central Maine Power Company |  | 12/2009 | CMP LSP - Anson Substation | Add 115 kV circuit breakers and transformer at Anson Section 63. | Concept | Cancelled | No | No | TBD | NR
Reliability Upgrade | 1b | 106 | Northeast Utilities |  | TBD |  | Upgrade the Southwest Hartford Substation to Bulk Power System standards (BPS). | Concept | Cancelled | 08/04/2004 | No | TBD | NR
Reliability Upgrade | 1b | 1069 | NSTAR Electric Company |  | 07/2011 | NPCC BPS Compliance | Bourne Station | Proposed | Cancelled | No | No | 8800000 | NR
Notes
1 Project pending solution documentation for the Greater Rhode Island Transmission Reinforcements.
2 The Northeast Utilities' estimated costs for the NEEWS BPS upgrades are shared among the Greater Springfield, Central Connecticut, and Interstate portions of the NEEWS Project.
3 The total TCA (NU-07-TCA-24) PTF cost is $234.2 million for the Norwalk - Glenbrook Project. The forecasted PTF cost is $249.4 million.
4 The total TCA (NU-08-TCA-01) PTF cost is $1.05 billion for Northeast Utilities portion of the Middletown-Norwalk Project. The forecasted PTF cost is $978.2 million.
Local Project Listing Links
| NSTAR: |  | http://www.nstar.com/business/rates_tariffs/open_access/
| CMP: |  | http://www.cmpco.com/SuppliersAndPartners/TransmissionServices/CMPTransmissionSvc/lsp.html
| BHE: |  | http://www.bhe.com/data/OASIS/LSP.html
| VELCO: |  | http://www.vermontspc.com/About%20the%20VSPC/Home.aspx
| NU: |  | http://www.transmission-nu.com/business/pdfs/NU_Local_Transmission_Studies_List.pdf
| NGRID: |  | http://www.nationalgridus.com/oasis/
| UI: |  | http://www.uinet.com/uinet/resources/file/ebcfda4ccb73dd/UI%20Local%20System%20Plan.pdf

## CostSumW-TBD-Mar 12 (hidden)
COST COMPARISON OF RELIABILITY PROJECTS November 2011 vs March 2012
| RTEP02 (in millions $) | RTEP03 (in millions $) | As of April '04 Plan Update (in millions $) | As of July '04 Plan Update (in millions $) | As of October '04 Plan Update (in millions $) | As of April '05 Plan Update (in millions $) | As of July '05 Plan Update (in millions $) | As of Oct '05 Plan Update (in millions $) | As of April '06 Plan Update (in millions $) | As of July 2006 Plan Update (in millions $) | As of October 2006 Plan Update (in millions $) | As of April 2007 Plan Update (in millions $) | As of July 2007 Plan Update (in millions $) | As of October 2007 Plan Update (in millions $) | As of April 2008 Plan Update (in millions $) | As of July 2008 Plan Update (in millions $) | As of October 2008 Plan Update (in millions $) | As of April 2009 Plan Update (in millions $) | As of June 2011 Plan Update (in millions $) | As of November 2011 Plan Update (in millions $) | As of March 2012 Plan Update (in millions $) | Change in Plan Estimate (in millions $) | Reasons for Change
MAJOR PROJECTS
Maine Power Reliability Program | [14 empty] | TBD | 1424 | 1424 | 1545.1 | 1546 | 1440 | 1440 | 0
Merrimack Valley / North Shore Reliability Project | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | 14 | 133.82 | 151.56 | 151.56 | 151.56 | 151.56 | 207.1649 | 212.7109 | 216.8471 | 197 | 198 | 1
Long Term Lower SEMA Upgrades | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | 14 | 133.82 | 151.56 | 151.56 | 151.56 | 151.56 | TBD | 110 | 113 | 112.5 | 112.5 | 0
New England East - West Solution (NEEWS) | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | TBD | TBD | 272.7 (3) | 272.7 (2) | 272.7 (2) | 1600.7 | 1872.36 | 1872.36 | 1928 | 1845 | 1878.14 | 33.14
NEEWS (Greater Springfield Reliability Project) $746.80
NEEWS (Rhode Island Reliability Project) $225.8
NEEWS (Central Connecticut Reliability Project) $301.00
NEEWS (Interstate Reliability Project) $604.66
Greater Rhode Island Transmission Reinforcements (including Advanced NEEWS) | [18 empty] | 279 | 242 | 242 | 0
Pittsfield/Greenfield Project | [18 empty] | 129 | 129 | 133 | 4
Greater Boston - North, South, Central, Western Suburbs | [18 empty] | 292 | 265 | 417 | 152
New Hampshire Solution - Southern, Central, Seacoast, Northern | [18 empty] | 278.805 |  | 453 | 453
Vermont Solution - Northwestern, Central, Southwestern | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | TBD | 194.8 | 181.99 | 181.99 | 181.99 | 181.99 | 258.945 | 292.609 | 278.805 |  | 485 | 485
SUBTOTAL (2) | 0 | 125 | 202 | 125 | 125 | 125 | 125 | 125 | 125 | 357 | 385 | 805.64 | 1101.01 | 758.11 | 757.81 | 2085.81 | 3762.4699 | 4032.7799 | 5061.4571 | 4230.5 | 5358.64 | 1128.14
OTHER PROJECTS | 149.9 | 181.3 | 187.6 | 792.2 | 828.9 | 1025.5 | 1287 | 1369.896 | 1430.112 | 1472.4118 | 1589.3948 | 1666.3467 | 2180.5252 | 2678.5122 | 2576.6241 | 2594.6841 | 2594.934 | 2690.4727 | 5282 | 5351.55 | 5482.0719 | 130.5219 | Various | MAJOR PROJECTS | 5358.64
[24 empty] | NEW PROJECTS | 3.9
NEW PROJECTS | 0 | 521.7 | 567.1 | 0 | 0 | 14.4 | [14 empty] | 3.9 | 3.9 | Preliminary estimates reported for 8 of 17 new projects | TBD NOW W/ COSTS | 132.3
[24 empty] | OTHER PROJECTS | 5482.0719 | 5482.0719 | VERIFICATION of RED CELL
PROJECTS WHOSE COST ESTIMATES WERE PREVIOUSLY REPORTED AS TO BE DETERMINED (TBD) | [5 empty] | 0 | [14 empty] | 132.3 | 132.3 | First estimates reported for projects. | GRAND TOTAL | 10976.9119
TOTAL (2) | 149.9 | 828 | 2201.1 1 | 2270.4 1 | 953.9 | 1164.9 | 1412 | 1495 | 1555.112 | 1829.412 | 1974.395 | 2471.987 | 3281.836 | 3436.623 | 3334.4341 | 4680.4941 | 6357.4039 | 6723.2526 | 10343.4571 | 9582.05 | 10976.9119 | 633.4548
Minus 'concept' | [18 empty] | -142 | -128.3 | -132
Minus 'in-service' |  | In-Service Projects | 76.2 | -130.8 | -143.4 | -172.2 | -216.8 | -265.726 | -410.4503 | -429 | -503.791 | -899.8087 | -973.8387 | -977.7067 | -1165.1757 | -1328.4137 | -1452.0644 | -3452.6538 | -4386.6457 | -4421.2027 | -4661.3677
Aggregate estimate of active projects in the Plan (2) |  |  | 2124.9 | 2139.6 | 2159.5 | 992.7 | 1195.2 | 1229.274 | 1144.6617 | 1400.412 | 1470.504 | 1572.1783 | 2307.9973 | 2458.9163 | 2169.2584 | 3352.0804 | 4905.3395 | 3270.5988 | 5814.8114 | 5032.5473 | 6183.5442 |  |  | ACTIVE COSTS | 6315.5442 | (typed in Project Total from Master File)
[24 empty] | IN SERVICE | 240.165 | (typed in from In-service tab)
[20 empty] | 5160.8473 | 6315.5442
Note on BC33: Barbara Lynch: Type in number in green into cell AQ22

## CostSumW-TBD-Jun11-final (hidden)
COST COMPARISON OF RELIABILITY PROJECTS April 2011 vs June 2011
| RTEP02 (in millions $) | RTEP03 (in millions $) | As of April '04 Plan Update (in millions $) | As of July '04 Plan Update (in millions $) | As of October '04 Plan Update (in millions $) | As of April '05 Plan Update (in millions $) | As of July '05 Plan Update (in millions $) | As of Oct '05 Plan Update (in millions $) | As of April '06 Plan Update (in millions $) | As of July 2006 Plan Update (in millions $) | As of October 2006 Plan Update (in millions $) | As of April 2007 Plan Update (in millions $) | As of July 2007 Plan Update (in millions $) | As of October 2007 Plan Update (in millions $) | As of April 2008 Plan Update (in millions $) | As of July 2008 Plan Update (in millions $) | As of October 2008 Plan Update (in millions $) | As of April 2009 Plan Update (in millions $) | As of April 2011 Plan Update (in millions $) | As of June 2011 Plan Update (in millions $) | Change in Plan Estimate (in millions $) | Reasons for Change
MAJOR 345 kV PROJECTS
Maine Power Reliability Program | [14 empty] | TBD | 1424 | 1424 | 1545.1 | 1546 | 1546 | 0
Merrimack Valley / North Shore Reliability Project | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | 14 | 133.82 | 151.56 | 151.56 | 151.56 | 151.56 | 207.1649 | 212.7109 | 216.8471 | 216.8471 | 0
Long Term Lower SEMA Upgrades | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | 14 | 133.82 | 151.56 | 151.56 | 151.56 | 151.56 | TBD | 110 | 106.5 | 112.5 | 6
New England East - West Solution (NEEWS) (including Ancillary components) | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | TBD | TBD | 272.7 (3) | 272.7 (2) | 272.7 (2) | 1600.7 | 1872.36 | 1872.36 | 1991.8 | 1928 | -63.8
Pittsfield/Greenfield Project | [18 empty] | 129 | 129 | 0
Greater Boston - North, South, Central | [18 empty] | 292 | 292 | 0
Greater Rhode Island Transmission Reinforcements (including Advanced NEEWS) | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | TBD | 194.8 | 181.99 | 181.99 | 181.99 | 181.99 | 258.945 | 292.609 | 278.805 | 278.805 | 0
SUBTOTAL (2) | 0 | 125 | 202 | 125 | 125 | 125 | 125 | 125 | 125 | 357 | 385 | 805.64 | 1101.01 | 758.11 | 757.81 | 2085.81 | 3762.4699 | 4032.7799 | 4560.9521 | 4503.1521 | -57.8
OTHER PROJECTS | 149.9 | 181.3 | 187.6 | 792.2 | 828.9 | 1025.5 | 1287 | 1369.896 | 1430.112 | 1472.4118 | 1589.3948 | 1666.3467 | 2180.5252 | 2678.5122 | 2576.6241 | 2594.6841 | 2594.934 | 2690.4727 | 5061.3612 | 5282 | 220.6388 | Various | MAJOR PROJECTS | 4503.1521
[23 empty] | NEW PROJECTS | 39
NEW PROJECTS | 0 | 521.7 | 567.1 | 0 | 0 | 14.4 | [13 empty] | 39 | 39 | Preliminary estimates reported for 8 of 17 new projects | TBD NOW W/ COSTS | 7.3
[23 empty] | OTHER PROJECTS | 5475.0793 | 5282 | VERIFICATION of RED CELL
PROJECTS WHOSE COST ESTIMATES WERE PREVIOUSLY REPORTED AS TO BE DETERMINED (TBD) | [5 empty] | 0 | [13 empty] | 7.3 | 7.3 | First estimates reported for projects. | GRAND TOTAL | 9830.5314
TOTAL (2) | 149.9 | 828 | 2201.1 1 | 2270.4 1 | 953.9 | 1164.9 | 1412 | 1495 | 1555.112 | 1829.412 | 1974.395 | 2471.987 | 3281.836 | 3436.623 | 3334.4341 | 4680.4941 | 6357.4039 | 6723.2526 | 9622.3133 | 9831.4521 | 209.1388
Minus 'concept' | [18 empty] | -139.1 | -142.2
Minus 'in-service' |  | In-Service Projects | 76.2 | -130.8 | -143.4 | -172.2 | -216.8 | -265.726 | -410.4503 | -429 | -503.791 | -899.8087 | -973.8387 | -977.7067 | -1165.1757 | -1328.4137 | -1452.0644 | -3452.6538 | -4328.1457 | -4386.6457
Aggregate estimate of active projects in the Plan (2) |  |  | 2124.9 | 2139.6 | 2159.5 | 992.7 | 1195.2 | 1229.274 | 1144.6617 | 1400.412 | 1470.504 | 1572.1783 | 2307.9973 | 2458.9163 | 2169.2584 | 3352.0804 | 4905.3395 | 3270.5988 | 5155.0676 | 5302.6064 |  |  | ACTIVE COSTS | 5443.8857 | (typed in from Master File)
[23 empty] | IN SERVICE | 58.5 | (typed in from In-service tab)
Note on BA25: Barbara Lynch: Type in number in red from cell AQ24 also added in Vt Southern Loop Project +194
Note on BA33: rvega: I updated the In-service tab and Total Deviation tab with the 58.5 as well

## CostSumW-TBD-Apr11-RV-Input (hidden)
COST COMPARISON OF RELIABILITY PROJECTS October 2010 vs April 2011
| RTEP02 (in millions $) | RTEP03 (in millions $) | As of April '04 Plan Update (in millions $) | As of July '04 Plan Update (in millions $) | As of October '04 Plan Update (in millions $) | As of April '05 Plan Update (in millions $) | As of July '05 Plan Update (in millions $) | As of Oct '05 Plan Update (in millions $) | As of April '06 Plan Update (in millions $) | As of July 2006 Plan Update (in millions $) | As of October 2006 Plan Update (in millions $) | As of April 2007 Plan Update (in millions $) | As of July 2007 Plan Update (in millions $) | As of October 2007 Plan Update (in millions $) | As of April 2008 Plan Update (in millions $) | As of July 2008 Plan Update (in millions $) | As of October 2008 Plan Update (in millions $) | As of April 2009 Plan Update (in millions $) | As of October 2010 Plan Update (in millions $) | As of April 2011 Plan Update (in millions $) | Change in Plan Estimate (in millions $) | Reasons for Change
MAJOR 345 kV PROJECTS
Maine Power Reliability Program | [14 empty] | TBD | 1424 | 1424 | 1545.1 | 1356 | 1547 | 191
Vermont Southern Loop Project | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | 14 | 72 | 200 | 200 | 274.4 | 274.4 | 274.4 | 242.964 | 207.781 | 193.5 | -14.281
Merrimack Valley / North Shore Reliability Project | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | 14 | 133.82 | 151.56 | 151.56 | 151.56 | 151.56 | 207.1649 | 212.7109 | 218 | 216.8471 | -1.1529
Long Term Lower SEMA Upgrades | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | 14 | 133.82 | 151.56 | 151.56 | 151.56 | 151.56 | TBD | 110 | 106.5 | 106.5 | 0
New England East - West Solution (NEEWS) (including Ancillary components) | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | TBD | TBD | 272.7 (3) | 272.7 (2) | 272.7 (2) | 1600.7 | 1872.36 | 1872.36 | 1881 | 1991.8 | 110.8
Pittsfield/Greenfield Project | [19 empty] | 129 | 129
Greater Boston - North, South, Central | [19 empty] | 292 | 292
Greater Rhode Island Transmission Reinforcements (including Advanced NEEWS) | TBD | 125 | 125 | 125 | 125 | 125 | 125 .0 2 | 125 .0 2 | 125 2 | TBD | TBD | 194.8 | 181.99 | 181.99 | 181.99 | 181.99 | 258.945 | 292.609 | 292.609 | 278.805 | -13.804
SUBTOTAL (2) | 0 | 250 | 327 | 250 | 250 | 250 | 125 | 125 | 125 | 357 | 399 | 877.64 | 1301.01 | 958.11 | 1032.21 | 2360.21 | 4036.8699 | 4275.7439 | 4062.59 | 4755.4521 | 692.8621
OTHER PROJECTS | 149.9 | 181.3 | 187.6 | 792.2 | 828.9 | 1025.5 | 1287 | 1369.896 | 1430.112 | 1472.4118 | 1589.3948 | 1666.3467 | 2180.5252 | 2678.5122 | 2576.6241 | 2594.6841 | 2594.934 | 2690.4727 | 4966 | 4952 | -14 | Various | MAJOR PROJECTS | 4755.4521
[23 empty] | NEW PROJECTS | 110.3612
NEW PROJECTS | 0 | 521.7 | 567.1 | 0 | 0 | 14.4 | [13 empty] | 110.3612 | 110.3612 | Preliminary estimates reported for 8 of 17 new projects | TBD NOW W/ COSTS | 0
[23 empty] | OTHER PROJECTS | 4950.1226 | 4952 | VERIFICATION of RED CELL
PROJECTS WHOSE COST ESTIMATES WERE PREVIOUSLY REPORTED AS TO BE DETERMINED (TBD) | [5 empty] | 0 | [13 empty] | 0 | 0 | First estimates reported for projects. | GRAND TOTAL | 9815.9359
TOTAL (2) | 149.9 | 953 | 2201.1 1 | 2270.4 1 | 1078.9 | 1289.9 | 1412 | 1495 | 1555.112 | 1829.412 | 1988.395 | 2543.987 | 3481.836 | 3636.623 | 3608.8341 | 4954.8941 | 6631.8039 | 6966.2166 | 9028.59 | 9817.8133 | 789.2233
Minus 'concept' | [18 empty] | -141 | -139.1
Minus 'in-service' |  | In-Service Projects | 76.2 | -130.8 | -143.4 | -172.2 | -216.8 | -265.726 | -410.4503 | -429 | -503.791 | -899.8087 | -973.8387 | -977.7067 | -1165.1757 | -1328.4137 | -1452.0644 | -3452.6538 | -3960.0717 | -4328.1457
Aggregate estimate of active projects in the Plan (2) |  |  | 2124.9 | 2139.6 | 2159.5 | 1117.7 | 1195.2 | 1229.274 | 1144.6617 | 1400.412 | 1484.504 | 1644.1783 | 2507.9973 | 2658.9163 | 2443.6584 | 3626.4804 | 5179.7395 | 3513.5628 | 4927.5183 | 5350.5676 |  |  | ACTIVE COSTS | 5487.7902 | (typed in from Master File)
[23 empty] | IN SERVICE | 368.074 | (typed in from In-service tab)
Note on AQ6: rvega: Includes RSP ID 1116 (Line 64 Rebuild) project. Confirm whether or not this project should be included in the cost estimate for MPRP. The October 2010 Update cost for MPRP excludes this project.
Note on BA26: Barbara Lynch: Type in number in red from cell AQ23
Note on A27: rvega: Since this is zero for the April-11 Update, consider hiding this row. Don't delete it.

## Projects I-S for October09 (hidden)
April 10 -NEW ENGLAND Project Listing Update (DRAFT)
Primary Driver | Part# | Project ID | Primary Equipment Owner | Other Equipment Owner(s) | Projected In-Service Month/Year | Major Project | Project | Oct-07 Status | Apr-08 Status | Jul-08 Status | Jul-09 Status | Oct-09 Status | I.3.9 Approval | TCA Approval | Oct-07 Estimated Costs | Apr-08 Estimated Costs | Jul-08 Estimated Costs | Jul-09 Estimated Costs | Oct 09 Estimated Costs | Why Needed
IN-SERVICE PROJECTS
Reliability Upgrade | 1a | 1051 | Central Maine Power Company |  | 09/2009 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Riley 115 kV capacitor bank. |  | Concept | Planned | Under Construction | In-service | 2007-11-30 | No | TBD | TBD |  | Part of Project 625 | Part of Project 625 |  | 8000000
Reliability Upgrade | 1a | 267 | Northeast Utilities | Central Maine Power Company | 2009-08-01 | Y138 Closing | White Lake - Saco Valley (Y138) Line Closing - Add PAR on Y138 at Saco Valley, retension lines, upgrade Beebe terminal, and add capacitor banks at White Lake and Beebe. | Planned | Under Construction | Under Construction | Under Construction | In-service | 01/01/2006 | No | 28565000 | 28412000 |  | 27775000 | 27775000 |  | 1300000
Reliability Upgrade | 1a | 936 | National Grid, USA |  | 07/2009 | Central/Western Massachusetts Upgrades | Reconductor (P142/P142S) Rolfe Avenue - West Bolyston 115 kV line w/1590 ACSR. | Proposed | Planned | Planned | Under Construction | In-service | 12/17/2007 | No | 2107320 | 2107320 |  | 3000000 | 3000000 |  | 3300000
Reliability Upgrade | 1a | 176 | Northeast Utilities |  | 07/2009 | Monadnock Area Reliability Project | New Fitzwilliam 345/115kV substation along with 345 kV breakers. | Planned | Under Construction | Under Construction | Under Construction | In-service | 2007-09-27 | No | 54358000 | 54358000 |  | 76100000 | 76100000 |  | 3089000
Reliability Upgrade | 1a | 174 | National Grid, USA |  | 06/2009 | Monadnock Area Reliability Project | Reconductor I-135 (Bellows Falls-Monadnock Tap-Flagg Pond) 115 kV line. | Planned | Planned | Planned | Under Construction | In-service | 03/24/2006 | No | 9600000 | 9600000 |  | 15778000 | 15778000 |  | 6332000
Reliability Upgrade | 1a | 832 | NSTAR Electric Company |  | 07/2009 | Short Term Lower SEMA Upgrades | Add(1) 115kV SVC (0-112 MVARs lagging) at Barnstable. | Planned | Planned | Planned | Under Construction | In-service | 08/17/2007 | No | 16000000 | 16000000 |  | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade |  | 10400000
Reliability Upgrade | 1a | 182 | Vermont Electric Power Company |  | 09/2009 | Monadnock Area Reliability Project | Upgrade bus cable at N. Rutland and K35 115 kV breaker at Rutland. | Planned | Planned | Planned | Under Construction | In-service | 03/24/2006 | NR | 03/24/2006 | No | 1000000 | 1000000 | 1000000 |  | 3100000
[18 empty] | Total | 205653000
1000000

## Sorted by Status Nov 11 (hidden)
November 2011 ISO-NEW ENGLAND Project Listing Update (DRAFT)(7)
Primary Driver | Part# | Project ID | State | Primary Equipment Owner | Other Equipment Owner(s) | Projected In-Service Month/Year | Major Project | Project | Jun-11 Status | Oct-11 Status | PPA (I.3.9) Approval | TCA Approval | Jun-11 Estimated PTF Costs | Oct-11 Estimated PTF Costs
Reliability Upgrade | 1b | 1031 | ME | Bangor Hydro-Electric Company |  | 12/2013 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station | Concept | Concept | 2010-10-22 | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1154 | ME | Bangor Hydro-Electric Company |  | 12/2013 | Maine Power Reliability Program (MPRP) | Rerate Line 66 | Concept | Concept | 2010-10-22 | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1155 | ME | Bangor Hydro-Electric Company |  | 12/2014 | Maine Power Reliability Program (MPRP) | Capacitor Bank Addition (10 MVAr at Trenton 34.5kV and Epping) | Concept | Concept | 2010-10-22 | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 325 | VT | Vermont Electric Power Company |  | TBD | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 324 | VT | Vermont Electric Power Company |  | TBD |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 139 | VT | Vermont Electric Power Company |  | TBD | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Concept | Concept | 01/10/2003 | 03/31/2003 | TBD | TBD | TBD
Reliability Upgrade | 1b | 1250 | VT | Vermont Electric Power Company |  | 2016 | VELCO LSP - West Rutland Substation | Installation of a 115/46kV transformer at West Rutland between breakers K30 and K34 | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 593 | MA | NSTAR Electric Company |  | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Bourne and Barnstable/Falmouth/equivalent | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1177 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - North | Reconductor 211-503/504 from North Woburn Tap to Reading | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1178 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - North | Install 115kV Capacitor Bank at North Woburn | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1190 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - North | Install a second 345/115kV Auto Transformer at Woburn | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 970 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Add a new 345 kV line from Lexington to Waltham. | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 971 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1176 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Install an oil circulation pipe and heat exchangers at K Street and Chatham Street sections of 250-516/517 circuits | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1189 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - Central | Install 3rd 115kV Circuit between Waltham and Brighton | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1198 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Add a second 115kV line from Woburn to Burlington | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1199 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Install a new 230/115kV auto transformer at Sudbury or equivalent | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1191 | MA | NSTAR Electric Company |  | 12/2012 |  | Rebuild Section of Line 322 (Canal-Carver) | Concept | Concept | No | No | 12200000 | 12200000 | 12200000
Reliability Upgrade | 1b | 1181 | MA | NSTAR Electric Company |  | 12/2013 |  | Rebuild the High Hill 115kV Substation to a Breaker and a half desgin | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1204 | MA | NSTAR Electric Company |  | 06/2012 |  | Rebuild the Mashpee Substation to a Ring Bus and install an overvoltage trip relay on the Mashpee 115kV Capacitor Bank | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1205 | MA | NSTAR Electric Company |  | 12/2013 | Mid-Cape Reliability Project | Separate 120 (Canal-Barnstable) /122 (Oak St-Barnstable) DCT | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1206 | MA | NSTAR Electric Company |  | 12/2011 |  | Install a new 230kV breaker for line 282-602 (West Medway-Waltham) at W. Medway for system resoration | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1247 | MA | NSTAR Electric Company |  | TBD |  | Rebuild the Acushnet 115kV Substation | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1248 | MA | NSTAR Electric Company |  | 12/2014 |  | Rebuild the Kingston Substation to a breaker and a half scheme | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1249 | MA | NSTAR Electric Company |  | 12/2013 |  | Rebuild the Wareham Substation to a breaker and a half scheme | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1207 | MA | NSTAR Electric Company |  | 2012 | Belmont Transmission Interconnection | Build a new 115kV Substation for the Belmont Transmission Interconnection | Concept | Concept | 2010-02-26 | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1255 | MA | CELD (Chicopee Electric Light Department) |  | 12/2013 | CELD 115/13.8kV Substation | 115/13.8kV substation on Memorial Dr. with two transformers and twelve feeders looped into 1904 (1723) line between Piper and Fairmont substations |  | Concept | No | No |  | TBD | TBD
Reliability Upgrade | 1b | 1234 | RI | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | Install a 115kV redundant breaker in series with breaker #1713 at West Farmum Substation and upgrade to current BPS standards | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1084 | CT | Northeast Utilities |  | TBD | Greater Hartford Central Connecticut Project | Loop the Millstone - Manchester (310) 345 kV line into the Card substation (2) | Concept | Concept | 2008-09-24 | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1086 | CT | Northeast Utilities |  | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow (2) | Concept | Concept | 2008-09-24 | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1087 | CT | Northeast Utilities |  | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford (2) | Concept | Concept | 2008-09-24 | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1088 | CT | Northeast Utilities |  | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow (2) | Concept | Concept | 2008-09-24 | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 975 | CT | United Illuminating Company |  | 06/2015 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | Concept | No | No | 105000000 | 105000000 | 105000000
Reliability Upgrade | 1b | 699 | CT | United Illuminating Company |  | 12/2014 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | Concept | No | No | 11100000 | 11100000 | 11100000
Reliability Upgrade | 1b | 801 | CT | Northeast Utilities |  | TBD |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 85 | CT | Northeast Utilities |  | TBD |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | Concept | 08/04/2004 | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1228 | CT | Northeast Utilities |  | TBD | Stamford Area | Additional circuit into the Stamford Area (Glenbrook-South End) | Concept | Concept | No | No | TBD | TBD | TBD |  | Concept
Reliability Upgrade | 1b | 1229 | CT | Northeast Utilities |  | TBD |  | Replace 115kV 1990 (Frost Bridge-Stevenson) lattice structure | Concept | Concept | No | No | TBD | TBD | TBD | 40 | 128300000 |  | 128300000
Reliability Upgrade | 1b | 1230 | CT | Northeast Utilities |  | TBD | LSP - Greater Hartford Area | 115kV breaker addition at Northeast Simsbury Substation | Concept | Concept | 2011-03-30 | No | TBD | TBD | TBD | 40 | 128300000 |  | 128300000
Reliability Upgrade | 1b | 1243 | CT | CMEEC |  | 10/2013 | TTD's Fitch St 115kV Substation | TTD 115/27kV substation with two transformers and a 115kV circuit breaker looped into 1416 line (between Compo and Darien substations) | Concept | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1a | 1197 | ME | Bangor Hydro-Electric Company |  | 12/2013 | Keene Rd Autotransformer | Orrington 345kV Series Breaker Addition | Planned | Planned | 2010-10-22 | 2011-06-16 | 1761250 | 1761250 | 1761250
Reliability Upgrade | 1a | 907 | ME | Central Maine Power Company |  | 05/2014 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 203 (Detroit-Orrington), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | ME | Central Maine Power Company |  | 2014-08-02 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast forming Sections 86 & 266 | Planned | Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | ME | Central Maine Power Company |  | 05/2014 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377, 115kV Bucksport 65/205) | Planned | Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1026 | ME | Central Maine Power Company | Northeast Utilities | 12/2013 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction associated with (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Elliot Switching Station) line work | Planned | Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 1/29/2010 (CMP) 4/14/2011 (NU) | Portion of CMP $1.47B and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | 36000000
Reliability Upgrade | 1a | 1028 | ME | Central Maine Power Company | Northeast Utilities | 12/2013 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 1/29/2010 (CMP) 4/14/2011 (NU) | Portion of CMP $1.47B and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M
Reliability Upgrade | 1a | 1030 | ME | Central Maine Power Company |  | 11/2013 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Maguire Road) | Planned | Planned | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1132 | ME | Central Maine Power Company |  | 2014-08-02 | Maine Power Reliability Program (MPRP) | Add 115/34kV transformer at Coopers Mills | Planned | Planned | 7/31/08 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1129 | ME | Central Maine Power Company |  | 05/2012 |  | New 115kV line between Wyman Hydro and Rice Rips Tap, parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | Planned | 2009-01-26 | 2010-12-28 | 32800000 | 32800000 | 32800000
Reliability Upgrade | 1a | 1135 | ME | Central Maine Power Company |  | 02/2012 | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer | Planned | Planned | 2007-12-21 | NR | 1500000 | 1500000 | 1500000
Reliability Upgrade | 1a | 1184 | ME | Central Maine Power Company |  | 05/2012 | Starks Switching Station | Add 4-115kV circuit breakers in a breaker-and a-half configuration on Section 63 and 2-18 MVAr cap banks at a new Starks Switching Station | Planned | Planned | 2010-09-20 | 2011-03-25 | 10750000 | 9750000 | 9750000
Reliability Upgrade | 1a | 1251 | ME | Central Maine Power Company |  | 12/2012 | Lakewood Substation Expansion | Sectionalize Section 241 by adding four 115kV circuit breakers at Lakewood Substation and install a second 115/34.5 kV transformer | Planned | Planned | 2011-04-21 | No | 13700000 | 13700000 | 13700000
Reliability Upgrade | 1a | 1141 | NH | Northeast Utilities |  | 2015 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | Planned | Planned | 2009-06-29 | 2011-07-15 | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 680 | NH | National Grid, USA |  | 06/2013 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | Planned | 2008-01-28 | No | 7393000 | 7393000 | 7393000
Reliability Upgrade | 1a | 674 | NH | National Grid, USA |  | 12/2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | Planned | 2008-04-01 | No | 19460000 | 19460000 | 19460000
Reliability Upgrade | 1a | 1172 | VT | Vermont Electric Power Company |  | 06/2012 | Vermont Shunt Reactors | Install 345kV 60 MVAr shunt reactors (two at Coolidge and one at New Haven and relocate the New Haven reactor to Vernon) to address high voltage concerns | Planned | Planned | 2011-03-23 | No | 20000000 | 20000000 | 20000000
Reliability Upgrade | 1a | 318 | VT | Vermont Electric Power Company |  | 12/2012 | Georgia Substation Rebuild | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems due to breaker failure contingencies | Planned | Planned | 2010-11-22 | No | 16000000 | 16000000 | 16000000
Reliability Upgrade | 1a | 1169 | VT | Vermont Electric Power Company |  | 12/2012 | Ascutney Substation Rebuild | Rebuild the existing Ascutney substation 115kV bus into a ring bus, to address reliability problems due to breaker failure contingencies | Planned | Planned | 2010-11-22 | No | 14500000 | 14500000 | 14500000
Reliability Upgrade | 1a | 1170 | VT | Vermont Electric Power Company |  | 06/2013 | Bennington Substation Rebuild | Rebuild the exiting Bennington substation 115kV bus into a ring bus to address reliability problems due to breaker failure contingencies | Planned | Planned | 2010-11-22 | No | 23000000 | 28000000 | 28000000
Reliability Upgrade | 1a | 1171 | VT | Vermont Electric Power Company |  | 12/2011 | West Rutland Capacitor Rebuild | Install two 115kV 25 MVAr capacitor banks at West Rutland to address low voltage concerns | Planned | Planned | 2010-11-02 | NR | 2400000 | 2400000 | 2400000
Reliability Upgrade | 1a | 1194 | VT | Vermont Electric Power Company |  | 12/2012 | LSP Jay Substation | Construct a new 4-breaker ring substation at Jay with two 115/46kV transformers | Planned | Planned | 2011-02-07 | No | 6500000 | 6500000 | 6500000
Reliability Upgrade | 1a | 1195 | VT | Vermont Electric Power Company |  | 03/2013 | Highgate Refurbishment | Replace Highgate controls and cooling system | Planned | Planned | NR | No | 35600000 | 35600000 | 35600000
Reliability Upgrade | 1a | 921 | MA | National Grid, USA |  | 12/2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | Planned | 2008-01-28 | No | 40000000 | 40000000 | 40000000
Reliability Upgrade | 1a | 919 | MA | National Grid, USA |  | 04/2014 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | Planned | 2010-02-10 | No | 9200000 | 13600000 | 13600000
Reliability Upgrade | 1a | 59 | MA | National Grid, USA |  | 12/2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | Planned | 2008-01-28 | No | Part of RSP 921 | Part of RSP 921 | Part of RSP 921
Reliability Upgrade | 1a | 840 | MA | NSTAR Electric Company |  | 12/2012 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | Planned | 2008-04-01 | 2011-01-10 | 5900000 | 5900000 | 5900000
Reliability Upgrade | 1a | 776 | MA | National Grid, USA |  | 11/2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | Planned | 2008-06-27 | No | 3125000 | 3125000 | 3125000
Reliability Upgrade | 1a | 782 | MA | National Grid, USA |  | 01/2016 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor and Railyard. | Planned | Planned | 2008-06-27 | No | 43912000 | 43912000 | 43912000
Reliability Upgrade | 1a | 1068 | MA | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to vicinity of Bourne and connect to existing #120 line and install a 345KV - 115kV auto-transformer at new substation about 3 miles west of the Barnstable Substation Loop Line #115 in and out of the new Substation. Create a new line position at the Bourne Substation and connect the Bourne-Canal section of Line #120 | Planned | Planned | 07/2011 | No | 106500000 | 106500000 | 106500000
Reliability Upgrade | 1a | 592 | MA | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing. The lines being separated are 322 (Canal-Carver) and 342 (Canal-Pilgrim-Auburn) | Planned | Planned | 07/2011 | No | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1a | 1118 | MA | National Grid, USA | NSTAR Electric Company | 12/2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 (Bellrock-High Hill) | Planned | Planned | 07/2011 | No | 6000000 | 6000000 | 6000000
Reliability Upgrade | 1a | 1187 | MA | National Grid, USA |  | 06/2014 | A127/B128 Conductor Refurbishment | A127/B128 Conductor Refurbishment - Tower 510 to Harriman Substation, VT | Planned | Planned | 12/17/2007 01/20/11 | NR | 65000000 | 65000000 | 65000000
Reliability Upgrade | 1a | 929 | MA | National Grid, USA |  | 09/2013 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | Planned | 12/17/2007 | No | 2500000 | 2500000 | 2500000
Reliability Upgrade | 1a | 931 | MA | National Grid, USA |  | 01/2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | Planned | 12/17/2007 | No | 531481 | 531481 | 531481
Reliability Upgrade | 1a | 928 | MA | National Grid, USA |  | 06/2013 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | Planned | 12/17/2007 | No | 3400000 | 3400000 | 3400000
Reliability Upgrade | 1a | 938 | MA | National Grid, USA |  | 05/2013 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | Planned | 12/17/2007 | No | 5430000 | 5430000 | 5430000
Reliability Upgrade | 1a | 940 | MA | National Grid, USA |  | 06/2014 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS (A127 West reconductoring. Tower 510 to Paxton, French King to French King). | Planned | Planned | 12/17/2007 | No | 18000000 | 18000000 | 18000000
Reliability Upgrade | 1a | 942 | MA | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | Planned | 12/17/2007 | No | 3650000 | 3650000 | 3650000
Reliability Upgrade | 1a | 925 | MA | National Grid, USA |  | 11/2012 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | Planned | 12/17/2007 | No | Part of RSP 926 | Part of RSP 926 | Part of RSP 926
Reliability Upgrade | 1a | 926 | MA | National Grid, USA |  | 11/2012 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | Planned | 12/17/2007 | No | 14700000 | 14700000 | 14700000
Reliability Upgrade | 1a | 932 | MA | National Grid, USA |  | 11/2012 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | Planned | 12/17/2007 | No | Part of RSP 926 | Part of RSP 926 | Part of RSP 926
Reliability Upgrade | 1a | 941 | MA | National Grid, USA |  | 2013-08-01 | Central/Western Massachusetts Upgrades | Install new Z126 Millbury - Tower #510 115 kV line. | Planned | Planned | 12/17/2007 | No | 13748000 | 13748000 | 13748000
Reliability Upgrade | 1a | 943 | MA | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | Planned | 12/17/2007 | No | 4100000 | 4100000 | 4100000
Reliability Upgrade | 1a | 950 | MA | National Grid, USA |  | 02/2015 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | Planned | 12/17/2007 | No | 1016897 | 1016897 | 1016897
Reliability Upgrade | 1a | 953 | MA | National Grid, USA |  | 02/2015 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | Planned | 12/17/2007 | No | 10248067 | 10248067 | 10248067
Reliability Upgrade | 1a | 954 | MA | National Grid, USA |  | 02/2015 | Central/Western Massachusetts Upgrades | Westminster - install new 69kV breaker, including disconnect switches. | Planned | Planned | 12/17/2007 | No | 903909 | 903909 | 903909
Reliability Upgrade | 1a | 945 | MA | National Grid, USA |  | 05/2014 | Central/Western Massachusetts Upgrades | Adams - install two new 115 kV breakers and replace two existing 115kV breakers | Planned | Planned | 12/17/2007 | No | 5000000 | 5000000 | 5000000
Reliability Upgrade | 1a | 946 | MA | National Grid, USA |  | 04/2015 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer- Hampden to 115 kV. | Planned | Planned | 2011-03-29 | No | 16000000 | 16000000 | 16000000
Reliability Upgrade | 1a | 948 | MA | National Grid, USA |  | 05/2014 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | Planned | 2011-03-29 | No | 13400000 | 13400000 | 13400000
Reliability Upgrade | 1a | 949 | MA | National Grid, USA |  | 04/2015 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | Planned | 2011-03-29 | No | 1600000 | 1600000 | 1600000
Reliability Upgrade | 1a | 937 | MA | National Grid, USA |  | 12/2015 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | Planned | 12/17/2007 | No | 6602875 | 6602875 | 6602875
Reliability Upgrade | 1a | 955 | MA | National Grid, USA |  | 10/2012 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | Planned | 12/17/2007 | No | 13800000 | 13800000 | 13800000
Reliability Upgrade | 1a | 951 | MA | National Grid, USA |  | 01/2014 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon (H-134) 115 kV line. | Planned | Planned | 12/17/2007 | No | 7455440 | 7455440 | 7455440
Reliability Upgrade | 1a | 1217 | MA | Northeast Utilities |  | 12/2012 | Central/Western Massachusetts Upgrades | Subatation work at Ludlow (MA) and Scitico (CT) assoicaited with the new Hampden (MA) subsation project (Ngrid) | Planned | Planned | 12/17/2007 | No | 3140000 | 3140000 | 3140000
Reliability Upgrade | 1a | 687 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | Planned | 2008-09-24 | No | 795000000 | 718000000 | 718000000
Reliability Upgrade | 1a | 826 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1078 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1094 | MA | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | Planned | 2008-09-24 | No | 25000000 | 25000000 | 25000000
Reliability Upgrade | 1a | 1202 | MA | NSTAR Electric Company |  | 06/2013 | NEEWS (Ancillary Interstate Reliability Project) | Rebuild 1.2 mile length of line 336 with 2-900 ACSS conductor and replace 5, 345kV 2000 amp disconnect switches with 3000 amp switches at W. Medway station | Planned | Planned | 2011-03-30 | NR | 1700000 | 1700000 | 1700000
Reliability Upgrade | 1a | 791 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | Planned | 2008-04-25 | No | 11560000 | 11560000 | 11560000
Reliability Upgrade | 1a | 913 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | Planned | 2008-04-25 | No | 3250000 | 3250000 | 3250000
Reliability Upgrade | 1a | 914 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | Planned | 2008-04-25 | No | 28150000 | 28150000 | 28150000
Reliability Upgrade | 1a | 917 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | Planned | 2008-04-25 | No | 7000000 | 7000000 | 7000000
Reliability Upgrade | 1a | 793 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | Planned | 2008-04-25 | No | 6400000 | 6400000 | 6400000
Reliability Upgrade | 1a | 1268 | MA | Northeast Utilities |  | 12/2012 |  | 345kV Northfield Mountain to Berkshire (portion of 312) line structure replacements |  | Planned | NR | No |  | 7900000 | 7900000
Reliability Upgrade | 1a | 673 | MA | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | Planned | 2009-02-27 | No | 2200000 | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | MA | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Planned | Planned | 2009-02-27 | No | 30000000 | 30000000 | 30000000
Reliability Upgrade | 1a | 1257 | MA | National Grid, USA |  | 06/2014 | Salem Harbor Retirement | 115kV line Reconductoring of the S-145/T-146 from Tewksbury-North Reading Tap (9.3 miles each) |  | Planned | 2011-07-28 | No |  | 29000000 | 29000000
Reliability Upgrade | 1a | 1258 | MA | National Grid, USA |  | 06/2014 | Salem Harbor Retirement | 115kV line Reconductoring of the Y-151 from Tewksbury Junction - West Methuen (8.2 miles) |  | Planned | 2011-07-28 | No |  | 11500000 | 11500000
Reliability Upgrade | 1a | 1259 | MA | National Grid, USA |  | 06/2014 | Salem Harbor Retirement | 115kV line Reconductoring of the B154/C-155N from King St Tap - South Danvers (14.5 miles each way) |  | Planned | 2011-07-28 | No |  | 20000000 | 20000000
Reliability Upgrade | 1a | 1201 | MA | NSTAR Electric Company | NGRID | 12/2012 | Greater Boston - North | 115kV line Reconductoring of the P168/128-518 Line between Chelsea and Revere (NSTAR Portion of the line) | Proposed | Planned | 2011-03-25 | NR | 800000 | 1500000 | 1500000
Reliability Upgrade | 1a | 1168 | MA | Holyoke Gas & Electric |  | 12/2012 | North Canal 44P | Loop the 1525 (Holyoke Fairmont South 115kV) line into the new North Canal 44P | Proposed | Planned | 2011-05-25 | No | 4100000 | 4100000 | 4100000
Reliability Upgrade | 1a | 1256 | MA | Unitil |  | 06/2013 | Flagg Pond Upgrades | At Flagg Pond Substation upgrade terminal equipment on the I-135N, I-135S, J-136N and J-136S 115kV lines and Zone 3 relay upgrades for the J-136N 115kV line. |  | Planned | NR | NR |  | 2750000 | 2750000
Reliability Upgrade | 1a | 915 | RI | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | Planned | 2008-04-25 | No | 19450000 | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | RI | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | Planned | 2008-04-25 | No | 11800000 | 11800000 | 11800000
Reliability Upgrade | 1a | 918 | RI | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | Planned | 2008-04-25 | No | 3180000 | 3180000 | 3180000
Reliability Upgrade | 1a | 190 | RI | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | Planned | 2008-09-24 | No | 81800000 | 81800000 | 81800000
Reliability Upgrade | 1a | 1095 | RI | National Grid, USA |  | 12/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | Planned | 2008-09-24 | No | 73800000 | 73800000 | 73800000
Reliability Upgrade | 1a | 794 | RI | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | Planned | 2008-09-24 | No | 71700000 | 71700000 | 71700000
Reliability Upgrade | 1a | 795 | RI | National Grid, USA |  | 04/2013 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV (359) line. | Planned | Planned | 2008-09-24 | No | 69000000 | 69000000 | 69000000
Reliability Upgrade | 1a | 1106 | RI | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Kent County Substation Upgrades related to third 345/115 kV Autotransformer. | Planned | Planned | 2008-09-24 | No | 26000000 | 26000000 | 26000000
Reliability Upgrade | 1a | 798 | RI | National Grid, USA |  | 12/2011 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Planned | Planned | 2008-09-24 | No | 4900000 | 600000 | 600000
Reliability Upgrade | 1a | 1096 | RI | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | Planned | 2008-09-24 | No | 12000000 | 12000000 | 12000000
Reliability Upgrade | 1a | 1097 | RI | National Grid, USA |  | 01/2013 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County including S-175, T172N and T-172S with associated terminal equipment upgrade. | Planned | Planned | 2008-09-24 | No | 129800000 | 129800000 | 129800000
Reliability Upgrade | 1a | 1099 | RI | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | Planned | 2008-09-24 | No | 6000000 | 6000000 | 6000000
Reliability Upgrade | 1a | 1253 | RI | National Grid, USA |  | 04/2015 |  | New Crandall St. Substation 115-13 kV substation addition | Proposed | Planned | 2011-06-07 | No | 5000000 | 3000000 | 3000000
Reliability Upgrade | 1a | 1241 | RI | National Grid, USA |  | 06/2013 |  | Re-condustor G-185S (Kent County - Davisville Tap) | Planned | Planned | 2010-12-27 | No | 4200000 | 4200000 | 4200000
Reliability Upgrade | 1a | 1054 | CT | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Build a new 345 kV line from Manchester to Meekville Junction and re-terminate the 395 line at Meekville Junction | Planned | Planned | 2008-09-24 | No | 31000000 | 28800000 | 28800000
Reliability Upgrade | 1a | 576 | CT | Northeast Utilities |  | 2016 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | Planned | 2008-09-24 | No | 338000000 | 301000000 | 301000000
Reliability Upgrade | 1a | 1114 | CT | Northeast Utilities |  | 2016 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1a | 802 | CT | Northeast Utilities |  | 2015 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | Planned | 2008-09-24 | No | 251000000 | 218000000 | 218000000
Reliability Upgrade | 1a | 1085 | CT | Northeast Utilities |  | 2015 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | CT | Northeast Utilities |  | 2015 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | CT | Northeast Utilities | National Grid, USA | 2015 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1235 | CT | Northeast Utilities |  | 12/2015 | NEEWS (Ancillary Interstate Reliability Project) | Sag elimination on 1410 Line (Montville-Buddington) | Proposed | Planned | 2011-06-09 | No | 3500000 | 3000000 | 3000000
Reliability Upgrade | 1a | 1245 | CT | CMEEC |  | 12/2015 | NEEWS (Ancillary Interstate Reliability Project) | Sag elimination on 1410 Line (Montville-Buddington) | Proposed | Planned | 2011-06-09 | No | 60000 | 60000 | 60000
Reliability Upgrade | 1a | 1227 | CT | Northeast Utilities |  | 2012 | LSP - Stamford Area | Add 4th transformer and build a five breaker ring bus at South End Substation | Proposed | Planned | 2011-06-09 | No | 9100000 | 6400000 | 6400000
Reliability Upgrade | 1a | 1218 | CT | Northeast Utilities |  | 12/2013 | Millstone 345kV Circuit Separation project & SLOD SPS System Retirement | Separate the 345kV Double Circuit Tower 310/348 and 371/383 Tower configuration | Planned | Planned | 2010-11-02 | No | 25600000 | 25600000 | 25600000 | 104 | Planned |  | -25% | 25%
Reliability Upgrade | 1a | 721 | CT | United Illuminating Company |  | 06/2015 |  | New Shelton 115/13.8 kV substation | Planned | Planned | 2009-11-05 | No | 19500000 | 19500000 | 19500000 | 104 | 2699747919 |  | 2024810939.25 | 3374684898.75
Reliability Upgrade | 1a | 879 | CT | Bangor Hydro-Electric Company | New England Power Company, Northeast Utilities System Com | TBD | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | Planned | 03/01/2007 | NR | 420000 | 420000 | 420000
Reliability Upgrade | 1b | 1133 | ME | Central Maine Power Company |  | 12/2011 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation and new 34kV line from Leeds to Turner | Proposed | Proposed | No | NR | 300000 | 300000 | 300000
Reliability Upgrade | 1b | 1279 | ME | Central Maine Power Company |  | 12/2014 |  | New 345/115kV Autotransformer and 115kV switchyard at Raven Farm substation consisting of a four-bay breaker and a half configuration of eleven (11) breakers |  | Proposed | 2010-01-29 | No |  | 26126000 | 26126000
Reliability Upgrade | 1b | 1280 | ME | Central Maine Power Company |  | 12/2014 |  | New 115kV line section 244 and upgraded line section 80 between Coopers Mill and Highland Substations |  | Proposed | 2010-01-29 | No |  | 62735000 | 62735000
Reliability Upgrade | 1b | 1183 | NH | Northeast Utilities |  | 2014 | LSP New Peaselee Substation and 115/34.5KV transformer | New 115kV Peaselee Substation and transmission line work | Proposed | Proposed | No | No | 12400000 | 12400000 | 12400000
Reliability Upgrade | 1b | 1220 | NH | Northeast Utilities |  | 12/2015 | Greater Boston - North | Install a new 345kV circuit between Scobie and Pelham NH (this is NU's portion of the new Scobie-Tewksbury circuit) | Proposed | Proposed | No | No | 40100000 | 40100000 | 40100000
Reliability Upgrade | 1b | 1269 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Amherst Substation - New 345kV breaker and three 25MVar Capacitor Banks |  | Proposed | No | No |  | 19600000 | 19600000
Reliability Upgrade | 1b | 1270 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | New 115kV line from Fitzwilliiams to Monadnock |  | Proposed | No | No |  | 10500000 | 10500000
Reliability Upgrade | 1b | 1271 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Upgrade the Keene to Monadnock (T198) 115kV line |  | Proposed | No | No |  | 11900000 | 11900000
Reliability Upgrade | 1b | 1272 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Weare Substation - Add two 13.3 MVar 115V capacitors |  | Proposed | No | No |  | 3600000 | 3600000
Reliability Upgrade | 1b | 1273 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Rebuild A152 115kV line |  | Proposed | No | No |  | 22500000 | 22500000
Reliability Upgrade | 1b | 1274 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Rebuild N186 115kV line |  | Proposed | No | No |  | 2300000 | 2300000
Reliability Upgrade | 1b | 1275 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Upgrade the 381 345kV line |  | Proposed | No | No |  | 4200000 | 4200000
Reliability Upgrade | 1b | 1276 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Littleton Substation - Add a second 230/115kV autotransformer and associated 115kV substation work |  | Proposed | No | No |  | 16700000 | 16700000
Reliability Upgrade | 1b | 1277 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Webster Substation - Add four 26.6 MVar 115kV capacitors |  | Proposed | No | No |  | 11900000 | 11900000
Reliability Upgrade | 1b | 1278 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Saco Valley Substation - Add two 25 MVar dynamic Var devices |  | Proposed | No | No |  | 15800000 | 15800000
Reliability Upgrade | 1b | 1263 | NH | National Grid, USA |  | TBD | Northern New Hsmpshire Solution | New C-203 230kV line tap to Littleton NH Substation associated with 2nd 230/115kV auto project |  | Proposed | No | No |  | 1100000 | 1100000
Reliability Upgrade | 1b | 843 | MA | NSTAR Electric Company |  | 06/2012 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | Proposed | No | NR | 3200000 | 3450000 | 3450000
Reliability Upgrade | 1b | 965 | MA | NSTAR Electric Company |  | 06/2014 | Greater Boston - South | Add third 115kV line from W. Walpole to Holbrook | Proposed | Proposed | No | No | 19000000 | 19000000 | 19000000
Reliability Upgrade | 1b | 1175 | MA | NSTAR Electric Company |  | 12/2013 | Greater Boston - South | Upgrade the 115kV line 201-501 (Medway-Depot St.) and the 201-502 (Beaver Pond - Depot Street Tap) to a higher capacity line | Proposed | Proposed | No | NR | 3700000 | 3700000 | 3700000
Reliability Upgrade | 1b | 1214 | MA | National Grid, USA |  | 12/2015 | Greater Boston - South | Line Reconductoring of the C-129 Beaver Pond - Depot St. Tap) and D-130 (Depot St. Tap - Medway) 115kV lines | Proposed | Proposed | No | No | 500000 | 500000 | 500000
Reliability Upgrade | 1b | 1179 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - North | Install 2nd 345kV circuit between Bellerica/Burlington town line to Tewksbury | Proposed | Proposed | No | No | 33000000 | 33000000 | 33000000
Reliability Upgrade | 1b | 1200 | MA | NSTAR Electric Company |  | TBD | Greater Boston - North | Add a new 345kV UG circuit between Woburn and North Cambridge | Proposed | Proposed | No | No | 52000000 | 52000000 | 52000000
Reliability Upgrade | 1b | 1211 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | Install 2nd 345kV circuit between Tewksbury - Billerica/Burlington Town Line (NSTAR Border) | Proposed | Proposed | No | No | 32700000 | 32700000 | 32700000
Reliability Upgrade | 1b | 1212 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | 115kV Line Reconductoring of M-139/N-140 Tewksbury-Pinehurst (6.1 miles each) | Proposed | Proposed | No | No | 57000000 | 11600000 | 11600000
Reliability Upgrade | 1b | 1213 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | Install new 345kV circuit between NH/MA border and Tewksbury (this is NGRID's portion of the new Scobie-Tewksbury circuit) | Proposed | Proposed | No | No | 23370000 | 23370000 | 23370000
Reliability Upgrade | 1b | 1215 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | New 115kV line between Wakefield - Everett | Proposed | Proposed | No | No | 20000000 | 20000000 | 20000000
Reliability Upgrade | 1b | 1254 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | Substation work at Revere Substation to increase ratings on the 128-515P/168 line between Chelsea and Revere | Concept | Proposed | No | No | TBD | 1000000 | 1000000
Reliability Upgrade | 1b | 1260 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | 115kV Line reconductoring of the F-158N/S Wakefield Jct - Everett (7.36 miles) |  | Proposed | No | No | TBD | 3500000 | 3500000
Reliability Upgrade | 1b | 1261 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | 115kV Line reconductoring of the S-145T-146 from North Reading Tap - Wakefield Jct (5.1 miles each) |  | Proposed | No | No | TBD | 10800000 | 10800000
Reliability Upgrade | 1b | 1262 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | 115kV Line reconductoring of theY-151 from Tewksbury Junction - Tewksbury Substation (1.6 miles) |  | Proposed | No | No | TBD | 1250000 | 1250000
Reliability Upgrade | 1b | 1208 | MA | National Grid, USA |  | 12/2014 | Pittsfield / Greenfield Project | Separation and reconductoring of Cabot Taps (A-127 and Y-177 115kV lines) | Proposed | Proposed | No | No | 7400000 | 7400000 | 7400000
Reliability Upgrade | 1b | 1209 | MA | National Grid, USA |  | 12/2014 | Pittsfield / Greenfield Project | Reconductoring of A-127 between Erving and Cabot Tap with 1590 ACSS | Proposed | Proposed | No | No | 12000000 | 12000000 | 12000000
Reliability Upgrade | 1b | 1210 | MA | National Grid, USA |  | 12/2014 | Pittsfield / Greenfield Project | Harriman 115kV breaker upgrades | Proposed | Proposed | No | No | 1100000 | 1100000 | 1100000
Reliability Upgrade | 1b | 1221 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Modify Northfield Mountain 16R substation and install a 345/115Kv autotransformer | Proposed | Proposed | No | No | 108500000 | 108500000 | 108500000
Reliability Upgrade | 1b | 1222 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Build a new 115kV three breaker Swithching Station (Erving) ring bus | Proposed | Proposed | No | No | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1223 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Build a new 115kV line from Northfield Mountain to the new Erving Switching Station | Proposed | Proposed | No | No | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1224 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Install 115kV 14.4 MVAR capacitor banks at Cumberland, Podick and Amherst Substations | Proposed | Proposed | No | No | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1225 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Rebuild the Cumberland to Montague 1361 115kV line and terminal work at Cumberland and Montague | Proposed | Proposed | No | No | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1226 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Proposed | Proposed | No | No | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 956 | MA | National Grid, USA |  | 01/2015 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Proposed | Proposed | No | No | 7021534 | 7021534 | 7021534
Reliability Upgrade | 1b | 1252 | MA | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | Re-conductor 345kV 328 line (West Farnum-Sherman Rd) | Concept | Proposed | No | No | TBD | 36500000 | 36500000
Reliability Upgrade | 1b | 1233 | RI | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | New Sherman Road 345kV AIS Substation | Concept | Proposed | No | No | TBD | 36600000 | 36600000 | 45 | Proposed |  | -25% | 25%
Reliability Upgrade | 1b | 1242 | CT | CMEEC |  | 10/2012 | SNEW 115kV substation | SNEW 115/13.8kV substation with two transformers and a 115kV circuit breaker looped into the 1890 line (between Norwalk Hbr - Ely Ave) | Proposed | Proposed | No | No | 2000000 | 2000000 | 2000000 | 45 | 706902534 |  | 530176900.5 | 883628167.5
Reliability Upgrade | 1b | 1244 | CT | CMEEC |  | 10/2011 | 115kV Circuit Breaker Installation | Install 115kV Bus Tie Circuit Breaker at Stock House Rd Substation | Proposed | Proposed | No | No | 750000 | 750000 | 750000
Reliability Upgrade | 1b | 1246 | CT | United Illuminating Company |  | 09/2013 | 8300 Line Reconfiguration Project | Reconfiguration of 115kV (8300) line from Mill River to Quinnipiac | Proposed | Proposed | No | No | 17400000 | 17400000 | 17400000
Reliability Upgrade | 1a | 1116 | ME | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Under Construction | Under Construction | 2010-10-22 | 2011-06-16 | 37126000 | 37626000 | 37626000
Reliability Upgrade | 1a | 1156 | ME | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | Orrington Shunt Cap Reconfiguration | Under Construction | Under Construction | 2010-10-22 | 2011-06-16 | 2260262 | 2260262 | 2260262
Reliability Upgrade | 1a | 905 | ME | Central Maine Power Company |  | 2014-08-02 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Under Construction | Under Construction | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | 1470187000 | 1364108000 | 1364108000
Reliability Upgrade | 1a | 906 | ME | Central Maine Power Company |  | 05/2014 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Larrabee Road-Middle St,Middle St -Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Under Construction | Under Construction | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 908 | ME | Central Maine Power Company |  | 07/2014 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road); Coopers Mills autotransforme replaces Maxcy's autotransformer | Under Construction | Under Construction | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1158 | ME | Central Maine Power Company |  | 07/2014 | Maine Power Reliability Program (MPRP) | Two 40 MVAR reactors at Albion Road, two 40 MVAR reactors at Larabee Road, two 40 MVAR at Coopers Mills | Under Construction | Under Construction | 7/31/2008 & 2/26/09 & 11/22/10 | 2010-01-29 | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 143 | ME | Bangor Hydro-Electric Company |  | 12/2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation (2 new breakers) to Harrington Substation to Epping Substation (3 new breakers) | Under Construction | Under Construction | 2006-05-10 | 2008-06-13 | 66100000 | 66100000 | 66100000
Reliability Upgrade | 1a | 1131 | ME | Central Maine Power Company |  | 11/2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Planned | Under Construction | 2010-11-22 | NR | 600000 | 600000 | 600000
Reliability Upgrade | 1a | 1196 | ME | Bangor Hydro-Electric Company |  | 01/2012 | SVC Filter Upgrade (Part of Keene Rd Auto-transformer ID 144) | Upgrade of filter bank at Chester SVC facility | Under Construction | Under Construction | 2011-07-15 | 2011-07-15 | 3500000 | 3500000 | 3500000
Reliability Upgrade | 1a | 1219 | NH | Northeast Utilities |  | 12/2011 |  | Install 115kV two 13.3 MVAR capacitor banks at Oak Hill substation | Planned | Under Construction | 2011-02-28 | NR | 3800000 | 4000000 | 4000000
Reliability Upgrade | 1a | 277 | NH | Northeast Utilities |  | 11/2011 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Under Construction | Under Construction | 2009-06-29 | 2011-07-15 | 52000000 | 52000000 | 52000000
Reliability Upgrade | 1a | 1140 | NH | Northeast Utilities |  | 10/2011 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | Under Construction | Under Construction | 2009-06-29 | 2011-07-15 | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1182 | NH | Northeast Utilities |  | 06/2012 | LSP New Eagle Substation and 115/34.5KV transformer | New 115kV Eagle Substation connected to 115/34.5kV Thornton Substation | Planned | Under Construction | 2010-07-27 | No | 22800000 | 22800000 | 22800000
Reliability Upgrade | 1a | 887 | MA | National Grid, USA |  | 06/2013 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Under Construction | Under Construction | 2010-02-10 | No | 66300000 | 58000000 | 58000000
Reliability Upgrade | 1a | 1165 | MA | NSTAR Electric Company |  | 12/2011 | Mystic Breaker Additions Project | Move Transformer 110B Connection at Mystic | Planned | Under Construction | 2008-03-10 | NR | 1700000 | 2600000 | 2600000
Reliability Upgrade | 1a | 934 | MA | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Under Construction | Under Construction | 12/17/2007 | No | Part of RSP 935 | Part of RSP 935 | Part of RSP 935
Reliability Upgrade | 1a | 935 | MA | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Under Construction | Under Construction | 12/17/2007 | No | 10200000 | 10200000 | 10200000
Reliability Upgrade | 1a | 944 | MA | National Grid, USA |  | 03/2012 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Planned | Under Construction | 12/17/2007 | No | 16530000 | 15700000 | 15700000
Reliability Upgrade | 1a | 1076 | MA | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Under Construction | Under Construction | 2008-09-24 | No | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 196 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct the 115kV line South Agawam to Southwick (1768) | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Under Construction | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Under Construction | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVar Capacitor additions | Under Construction | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Under Construction | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Under Construction | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Under Construction | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1074 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1109 | MA | National Grid, USA |  | 12/2011 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Planned | Under Construction | 2008-09-24 | No | 1000000 | 1000000 | 1000000
Reliability Upgrade | 1a | 790 | MA | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Under Construction | Under Construction | 2008-04-25 | No | 52000000 | 52000000 | 52000000
Reliability Upgrade | 1a | 1098 | MA | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Under Construction | Under Construction | 2008-04-25 | No | 22000000 | 22000000 | 22000000
Reliability Upgrade | 1a | 1092 | MA | Northeast Utilities |  | 12/2013 | Agawam (BPS) | Upgrade the Agawam 115kV, Subtations to BPS standards together with other misc. subatation upgrades | Under Construction | Under Construction | 2008-09-24 | No | 13600000 | 12100000 | 12100000
Reliability Upgrade | 1a | 1216 | MA | Northeast Utilities |  | 04/2012 |  | 345kV Ludlow - Northfield (portion of 354) Line Structure replacements | Under Construction | Under Construction | NR | No | 17000000 | 25100000 | 25100000
Reliability Upgrade | 1a | 1266 | MA | Northeast Utilities |  | 12/2011 |  | 115kV Pleasant to Blandford (portion of 1421) Line structure replacement |  | Under Construction | NR | No |  | 9960000 | 9960000
Reliability Upgrade | 1a | 1267 | MA | Northeast Utilities |  | 12/2011 |  | 115kV Blandford to Southwick (portion of 1512) Line structure replacement |  | Under Construction | NR | No |  | 9600000 | 9600000
Reliability Upgrade | 1a | 969 | MA | NSTAR Electric Company |  | 11/2012 | Greater Boston - North | Add a new 115kV 36.7 MVAR capacitor bank at Chelsea. | Planned | Under Construction | 2011-03-30 | NR | 1500000 | 1500000 | 1500000
Reliability Upgrade | 1a | 301 | MA | NSTAR Electric Company |  | 12/2011 | Greater Boston - Central | Reconductor 115-kV circuits 320-507 and 320-508. (Lexington - Waltham) | Concept | Under Construction | 2011-02-15 | No | 8400000 | 9600000 | 9600000
Reliability Upgrade | 1a | 1066 | MA | NSTAR Electric Company |  | 12/2011 | NPCC BPS Compliance | Needham Station | Under Construction | Under Construction | NR | No | 6500000 | 8000000 | 8000000
Reliability Upgrade | 1a | 1065 | MA | NSTAR Electric Company |  | 07/2012 | NPCC BPS Compliance | Waltham Station | Under Construction | Under Construction | NR | No | 14700000 | 14700000 | 14700000
Reliability Upgrade | 1a | 484 | RI | National Grid, USA |  | 11/2011 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Planned | Under Construction | 2008-04-25 | No | 580000 | 580000 | 580000
Reliability Upgrade | 1a | 1193 | CT | United Illuminating Company |  | 12/2012 |  | North Haven 115kV Capacitor Bank TRV Mitigation Project | Under Construction | Under Construction | NR | NR | 5100000 | 4900000 | 4900000
Reliability Upgrade | 1a | 974 | CT | United Illuminating Company |  | 05/2013 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Under Construction | Under Construction | NR | No | 16900000 | 16900000 | 16900000
Reliability Upgrade | 1a | 816 | CT | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Planned | Under Construction | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1056 | CT | Northeast Utilities |  | 12/2011 | LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Under Construction | Under Construction | 2008-12-12 | 2011-04-14 | 10969000 | 10969000 | 10969000
Reliability Upgrade | 1a | 1111 | CT | United Illuminating Company |  | 01/2012 |  | Union Avenue 115/26.4 kV Substation | Under Construction | Under Construction | 2009-01-07 | 2009-11-10 | 10543000 | 13500000 | 13500000 | 58 | UnderConstruction |  | -10% | 10%
Reliability Upgrade | 1a | 976 | CT | United Illuminating Company |  | 05/2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Under Construction | Under Construction | 1/7/2009 & 11/22/2010 | No | 70000000 | 70000000 | 70000000 | 58 | 1925903262 |  | 1733312935.8 | 2118493588.2
Reliability Upgrade | 1a | 1050 | CT | United Illuminating Company |  | 12/2011 |  | Devon Tie 115kV Switching Station BPS Compliance | Under Construction | Under Construction | NR | NR | 4000000 | 4000000 | 4000000 | Total w/ Concept | 5460853715 | 247 | 4416600775.55 | 2118493588.2
[15 empty] | 5460853715 | Total w/o Concept | 5332553715 | 207 | 4288300775.55 | 5348690245

## Sorted by status 10-09 (hidden)
October '09 ISO-NEW ENGLAND Project Listing Update (DRAFT)
Primary Driver | Part# | Project ID | Primary Equipment Owner | Other Equipment Owner(s) | Projected In-Service Month/Year | Major Project | Project | Oct-09 Status | PPA (I.3.9) Approval | TCA Approval | Jul-09 Estimated PTF Costs | Oct-09 Estimated PTF Costs | Column T | Min Tolerance | Max Tolerance | # of Projects
Reliability Upgrade | 1b | 1116 | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1031 | Bangor Hydro-Electric Company |  | 01/2012 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station, Rebuild Line 66, and Capacitior Bank Additions (10MVAr at Trenton, Downeast & Handcock County area) | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 275 | Northeast Utilities |  | TBD |  | Merrimack 115-kV substation - Protection Separation Upgrade. | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 318 | Vermont Electric Power Company |  | 12/2011 |  | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems through the 1,250 MW Vermont state load level. | Concept | No | No | 9000000 | 9000000 | 9000000
Reliability Upgrade | 1b | 325 | Vermont Electric Power Company |  | 12/2011 | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | No | No | 5000000 | 5000000 | 5000000
Reliability Upgrade | 1b | 324 | Vermont Electric Power Company |  | 12/2012 |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | No | No | 100000000 | 100000000 | 100000000
Reliability Upgrade | 1b | 785 | National Grid, USA |  | 07/2017 | Merrimack Valley/North Shore Reliability Project | Re-conductor F-158N (Golden Hills-Maplewood-Everett) 115 kV line. | Concept | No | No | 1330000 | 1330000 | 1330000
Reliability Upgrade | 1b | 1153 | NSTAR Electric Company |  | 06/2010 | Boston Area 115 kV Enhancements | Reliability Upgrades at West Framingham Station | Concept | No | No |  | 3000000 | 3000000
Reliability Upgrade | 1b | 843 | NSTAR Electric Company |  | 12/2013 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 965 | NSTAR Electric Company |  | 12/2012 | Boston Area 115 kV Enhancements | Add third 115kV line from Walpole to Holbrook | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 969 | NSTAR Electric Company |  | 06/2018 | Boston Area 115 kV Enhancements | Add a new 54 MVAR capacitor bank at Chelsea. | Concept | No | No | 1200000 | 1200000 | 1200000
Reliability Upgrade | 1b | 301 | NSTAR Electric Company |  | 12/2011 | Boston Area 115 kV Enhancements | Reconductor 115-kV circuits 320-507 and 320-508. | Concept | No | No | 4600000 | 4600000 | 4600000
Reliability Upgrade | 1b | 593 | NSTAR Electric Company |  | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Canal to Barnstable/Falmouth | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1066 | NSTAR Electric Company |  | 09/2011 | NPCC BPS Compliance | Needham Station | Concept | No | No | 9300000 | 9300000 | 9300000
Reliability Upgrade | 1b | 970 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345 kV line from Lexington to Waltham. | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 971 | NSTAR Electric Company |  | 12/2012 | Greater Boston Reliability Project | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 956 | National Grid, USA |  | 05/2013 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Concept | No | No | 7021534 | 7021534 | 7021534
Reliability Upgrade | 1b | 824 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 825 | Northeast Utilities |  | TBD | Pittsfield / Greenfield Project | Upgrade the Pleasant to Blanford 115-kV line and the Blanford to Granville Jct. portion of the 115-kV line 1512. | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 1055 | Northeast Utilities |  | 2010 | CT LSP - Waterside Substation | Waterside Substation - add a 115/13.2-kV transformer and a 115-kV circuit breaker. | Concept | No | No | 4107000 | 4107000 | 4107000
Reliability Upgrade | 1b | 975 | United Illuminating Company |  | 12/2013 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | No | No | 44300000 | 44300000 | 44300000
Reliability Upgrade | 1b | 699 | United Illuminating Company |  | 12/2012 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | No | No | 10000000 | 10000000 | 10000000
Reliability Upgrade | 1b | 801 | Northeast Utilities |  | TBD |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Concept | No | No | TBD | TBD | TBD
Reliability Upgrade | 1b | 85 | Northeast Utilities |  | TBD |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | 08/04/2004 | No | TBD | TBD | TBD | -50% | 200%
[13 empty] | 198858534 | 99429267 | 596575602 | 24
Reliability Upgrade | 1a | 1128 | Central Maine Power Company |  | 07/2010 | CMP-LSP Hotel Road Substation | Add 115/34kV transformer with 115kV breaker at Hotel Rd. | Planned | 2008-08-20 | NR | 800000 | 800000 | 800000
Reliability Upgrade | 1a | 624 | Central Maine Power Company |  | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (New Page - Rumford Industrial Park) | Planned | 2007-11-30 | No | Part of project 625 | Part of project 625 | Part of project 625
Reliability Upgrade | 1a | 905 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Planned | 2008-07-31 | No | 1510000000 | 1510000000 | 1510000000
Reliability Upgrade | 1a | 906 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Coopers Mills-Highland, Larrabee Road-Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 907 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 84 (Albion Road-Coopers Mills), Section 203 (Detroit-Orrington), Section 80 (Coopers Mills-Highland), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 908 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road) | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377 & Maine Yankee 375/392, 115kV Bucksport 65/205) and Maine Yankee 345 kV re-termination | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1026 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Three Rivers) | Planned | 7/31/2008 & 2/26/09 | No | Portion of CMP $1.51B and portion of NU is $35.1M | Portion of CMP $1.51B and portion of NU is $35.1M | 35100000
Reliability Upgrade | 1a | 1027 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 115kV Line Construction (Elm Street-East Deering, East Deering -Cape) | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1028 | Central Maine Power Company | Northeast Utilities | 12/2012 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | 7/31/2008 & 2/26/09 | No | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD
Reliability Upgrade | 1a | 1030 | Central Maine Power Company |  | 12/2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Raven Farm, Maguire Road) | Planned | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 143 | Bangor Hydro-Electric Company |  | 12/2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation to Harrington Substation. | Planned | 2006-05-10 | 2008-06-13 | 66100000 | 66100000 | 66100000
Reliability Upgrade | 1a | 1129 | Central Maine Power Company |  | 05/2012 |  | New 115kV line between Wyman Hydro and Heywood Rd. parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | 2009-01-26 | No | 19500000 | 19500000 | 19500000
Reliability Upgrade | 1a | 277 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Planned | 2009-06-29 | No | 56600000 | 56600000 | 56600000
Reliability Upgrade | 1a | 1137 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115kV breakers and add 1-115kV breaker at Deerfield Substation | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1138 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rebuild 115kV L175 line | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1139 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV M183 Line | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1140 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1141 | Northeast Utilities |  | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | Planned | 2009-06-29 | No | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 680 | National Grid, USA |  | 09/2012 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | 2008-01-28 | No | 11497000 | 7393000 | 7393000
Reliability Upgrade | 1a | 674 | National Grid, USA |  | 09/2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | 2008-04-01 | No | 12000000 | 7720000 | 7720000
Reliability Upgrade | 1a | 139 | Vermont Electric Power Company |  | 12/2010 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Planned | 01/10/2003 | 03/31/2003 | 20000000 | 20000000 | 20000000
Reliability Upgrade | 1a | 1145 | Vermont Electric Power Company |  | 09/2011 | Burlington Project | Installation of a 3-breaker 115kV ring substation and 115/34.5kV transformer on the East Ave. - Tafts Coners 115kV line | Planned | 10/24/2006 | No |  | 14000000 | 14000000
Reliability Upgrade | 1a | 1146 | Vermont Electric Power Company |  | 12/2012 | Lyndonville Project | Installation of a 3-breaker 115kV righ station consisting of two 115kV 12.5 MVAR capacitor banks and 115/34.5 kV transformer interconnecting to the Irasburg - St. Johnsbury 115kV line | Planned | 2009-06-01 | No |  | 9000000 | 9000000
Reliability Upgrade | 1a | 887 | National Grid, USA |  | 09/2012 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Planned | 2008-01-28 | No | 30000000 | 30000000 | 30000000
Reliability Upgrade | 1a | 921 | National Grid, USA |  | 01/2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | 2008-01-28 | No | 12100000 | 12100000 | 12100000
Reliability Upgrade | 1a | 919 | National Grid, USA |  | 09/2012 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | 2008-01-28 | No | 4600000 | 4600000 | 4600000
Reliability Upgrade | 1a | 783 | National Grid, USA |  | 03/2011 | Merrimack Valley/North Shore Reliability Project | Extend the 115kV by addition of 115kV Breaker and K-153 line from King St. to W. Amesbury 115kV station. (W. Amesbury 345/115kV Station becomes PTF) | Planned | 2008-04-01 | No | 30349000 | 30349000 | 30349000
Reliability Upgrade | 1a | 840 | NSTAR Electric Company |  | 10/2010 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | 2008-04-01 | No | 7300000 | 7300000 | 7300000
Reliability Upgrade | 1a | 775 | National Grid, USA |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Addition of 4 breakers and relocation of T1 and T2 into new bays at Sandy Pond. | Planned | 2008-06-27 | No | 20100000 | 20100000 | 20100000
Reliability Upgrade | 1a | 776 | National Grid, USA |  | 06/2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | 2008-06-27 | No | 2865876 | 2865876 | 2865876
Reliability Upgrade | 1a | 782 | National Grid, USA |  | 10/2013 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor n Railyard. | Planned | 2008-06-27 | No | 38100000 | 38100000 | 38100000
Reliability Upgrade | 1a | 904 | NSTAR Electric Company |  | 12/2010 | Mystic IPT Breaker Project | Upgrade (5) 115 kV breakers #1, #7, #15 #19 and #20 at Mystic to IPT and separate controls with Boston Gen #4. | Planned | NR | NR | 990000 | 990000 | 990000
Reliability Upgrade | 1a | 59 | National Grid, USA |  | 01/2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | 2007-11-01 | 2003-01-31 | 400000 | 400000 | 400000
Reliability Upgrade | 1a | 929 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | 12/17/2007 | No | 1381849 | 1381849 | 1381849
Reliability Upgrade | 1a | 931 | National Grid, USA |  | 01/2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | 12/17/2007 | No | 531481 | 531481 | 531481
Reliability Upgrade | 1a | 928 | National Grid, USA |  | 12/2010 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | 12/17/2007 | No | 1945218 | 2300000 | 2300000
Reliability Upgrade | 1a | 934 | National Grid, USA |  | 10/2010 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Planned | 12/17/2007 | No | 818480 | 818480 | 818480
Reliability Upgrade | 1a | 935 | National Grid, USA |  | 07/2010 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Planned | 12/17/2007 | No | 5208509 | 5208509 | 5208509
Reliability Upgrade | 1a | 938 | National Grid, USA |  | 06/2010 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | 12/17/2007 | No | 3068556 | 3068556 | 3068556
Reliability Upgrade | 1a | 939 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Reconductor and retension (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | Planned | 12/17/2007 | No | 3389658 | 3389658 | 3389658
Reliability Upgrade | 1a | 940 | National Grid, USA |  | 04/2011 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS. | Planned | 12/17/2007 | No | 6235744 | 6235744 | 6235744
Reliability Upgrade | 1a | 942 | National Grid, USA |  | 10/2010 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | 12/17/2007 | No | 2767180 | 2767180 | 2767180
Reliability Upgrade | 1a | 927 | National Grid, USA |  | 07/2010 | Central/Western Massachusetts Upgrades | Greendale - replace 115 kV breaker and upgrade to 2000A. | Planned | 12/17/2007 | No | 584629 | 584629 | 584629
Reliability Upgrade | 1a | 925 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | 12/17/2007 | No | 318888 | 318888 | 318888
Reliability Upgrade | 1a | 926 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | 12/17/2007 | No | 6027520 | 6027520 | 6027520
Reliability Upgrade | 1a | 932 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | 12/17/2007 | No | 372036 | 372036 | 372036
Reliability Upgrade | 1a | 924 | National Grid, USA |  | 10/2011 | Central/Western Massachusetts Upgrades | Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | Planned | 12/17/2007 | No | 2147181 | 2147181 | 2147181
Reliability Upgrade | 1a | 941 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Install new Millbury - Tower #510 115 kV line. | Planned | 12/17/2007 | No | 7909203 | 7909203 | 7909203
Reliability Upgrade | 1a | 943 | National Grid, USA |  | 01/2011 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | 12/17/2007 | No | 1073995 | 1073995 | 1073995
Reliability Upgrade | 1a | 944 | National Grid, USA |  | 07/2012 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Planned | 12/17/2007 | No | 11411849 | 11411849 | 11411849
Reliability Upgrade | 1a | 950 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | 12/17/2007 | No | 1016897 | 1016897 | 1016897
Reliability Upgrade | 1a | 953 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | 12/17/2007 | No | 10248067 | 10248067 | 10248067
Reliability Upgrade | 1a | 954 | National Grid, USA |  | 12/2013 | Central/Western Massachusetts Upgrades | E Westminster - install new 115 kV breaker, including disconnect switches. Assumes no new control house. | Planned | 12/17/2007 | No | 903909 | 903909 | 903909
Reliability Upgrade | 1a | 945 | National Grid, USA |  | 02/2013 | Central/Western Massachusetts Upgrades | Adams - install third 115 kV breaker to complete ring bus. | Planned | 12/17/2007 | No | 1581841 | 1584841 | 1584841
Reliability Upgrade | 1a | 946 | National Grid, USA |  | 04/2013 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer - E Longmeadow - Shaker Rd line to 115 kV. | Planned | 12/17/2007 | No | 9604032 | 9604032 | 9604032
Reliability Upgrade | 1a | 947 | National Grid, USA |  | 04/2013 | Central/Western Massachusetts Upgrades | Reconductor 115 kV line from Palmer to new Hampden Substation. | Planned | 12/17/2007 | No | 2632635 | 2632635 | 2632635
Reliability Upgrade | 1a | 948 | National Grid, USA |  | 07/2012 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | 12/17/2007 | No | 5649430 | 5649430 | 5649430
Reliability Upgrade | 1a | 949 | National Grid, USA |  | 07/2012 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | 12/17/2007 | No | 1694829 | 1500000 | 1500000
Reliability Upgrade | 1a | 952 | National Grid, USA |  | 06/2011 | Central/Western Massachusetts Upgrades | Reconductor E Winchendon - J136 Tap within I135/J136 ROW w/795 ACSR. | Planned | 12/17/2007 | No | 932156 | 932156 | 932156
Reliability Upgrade | 1a | 937 | National Grid, USA |  | 12/2011 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | 12/17/2007 | No | 6602875 | 6602875 | 6602875
Reliability Upgrade | 1a | 955 | National Grid, USA |  | 11/2011 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | 12/17/2007 | No | 10779113 | 10779113 | 10779113
Reliability Upgrade | 1a | 1000 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | Planned | 2008-06-27 | No | 22000000 | 22000000 | 22000000
Reliability Upgrade | 1a | 951 | National Grid, USA |  | 02/2013 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon 115 kV line. | Planned | 12/17/2007 | No | 7455440 | 7455440 | 7455440
Reliability Upgrade | 1a | 687 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | 2008-09-24 | No | 714000000 | 714000000 | 714000000
Reliability Upgrade | 1a | 826 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 196 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115kV line South Agawam to Southwick (1768) | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVAR Capacitor additions | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1074 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1076 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Planned | 2008-09-24 | No | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1077 | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115kV line | Planned | 2008-09-24 | No | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1078 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 673 | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | 2009-02-27 | No | 2200000 | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Planned | 2009-02-27 | No | 30000000 | 30000000 | 30000000
Reliability Upgrade | 1a | 484 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Planned | 2008-04-25 | No | 690000 | 690000 | 690000
Reliability Upgrade | 1a | 791 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | 2008-04-25 | No | 11560000 | 11560000 | 11560000
Reliability Upgrade | 1a | 913 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | 2008-04-25 | No | 3250000 | 3250000 | 3250000
Reliability Upgrade | 1a | 914 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | 2008-04-25 | No | 28150000 | 28150000 | 28150000
Reliability Upgrade | 1a | 915 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | 2008-04-25 | No | 19450000 | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | 2008-04-25 | No | 11800000 | 11800000 | 11800000
Reliability Upgrade | 1a | 917 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | 2008-04-25 | No | 7000000 | 7000000 | 7000000
Reliability Upgrade | 1a | 918 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | 2008-04-25 | No | 3180000 | 3180000 | 3180000
Reliability Upgrade | 1a | 792 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Admiral St-Franklin Square (Q143 and R144) 115 kV UG recabling. | Planned | 2008-04-25 | No | 39200000 | 39200000 | 39200000
Reliability Upgrade | 1a | 793 | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | 2008-04-25 | No | 6400000 | 6400000 | 6400000
Reliability Upgrade | 1a | 786 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Terminal upgrades at Drumrock, Chartley Pond, and Brayton Point. | Planned | 2008-04-25 | No | 565000 | 1000000 | 1000000
Reliability Upgrade | 1a | 787 | National Grid, USA |  | 12/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | West Farnum breaker replacements. | Planned | 2008-04-25 | No | 7631000 | 7631000 | 7631000
Reliability Upgrade | 1a | 788 | National Grid, USA |  | 06/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Kent County substation expansion. | Planned | 2008-04-25 | No | 42300000 | 42300000 | 42300000
Reliability Upgrade | 1a | 789 | National Grid, USA |  | 11/2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Reconductoring of T7 115 kV line. | Planned | 2008-04-25 | No | 23304000 | 23304000 | 23304000
Reliability Upgrade | 1a | 790 | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Planned | 2008-04-25 | No | 50600000 | 50600000 | 50600000
Reliability Upgrade | 1a | 1098 | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Planned | 2008-04-25 | No | 37529000 | 37529000 | 37529000
Reliability Upgrade | 1a | 190 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | 2008-09-24 | No | 69600000 | 69600000 | 69600000
Reliability Upgrade | 1a | 1094 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | 2008-09-24 | No | 20800000 | 25000000 | 25000000
Reliability Upgrade | 1a | 1095 | National Grid, USA |  | 06/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | 2008-09-24 | No | 73800000 | 73800000 | 73800000
Reliability Upgrade | 1a | 794 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | 2008-09-24 | No | 55800000 | 55800000 | 55800000
Reliability Upgrade | 1a | 796 | National Grid, USA |  | 12/2013 | NEEWS (Interstate Reliability Project) | 347 Reconductor from Sherman Road to CT/RI Border. | Planned | 2008-09-24 | No | 16400000 | 16400000 | 16400000
Reliability Upgrade | 1a | 797 | National Grid, USA |  | 12/2012 | NEEWS (Interstate Reliability Project) | 3361 Upgrade 345kV terminal equipment at Sherman Road. | Planned | 2008-09-24 | No | 8300000 | 8300000 | 8300000
Reliability Upgrade | 1a | 795 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV line. | Planned | 2008-09-24 | No | 99900000 | 99900000 | 99900000
Reliability Upgrade | 1a | 1106 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | Planned | 2008-09-24 | No | Part of $99,900,000 above | Part of $99,900,000 above | Part of $99,900,000 above
Reliability Upgrade | 1a | 798 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Planned | 2008-09-24 | No | 4900000 | 4900000 | 4900000
Reliability Upgrade | 1a | 799 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | Planned | 2008-09-24 | No | 4500000 | 4500000 | 4500000
Reliability Upgrade | 1a | 1096 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | 2008-09-24 | No | 5800000 | 12000000 | 12000000
Reliability Upgrade | 1a | 800 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S, T-172N and T-172S with associated terminal equipment upgrades. | Planned | 2008-09-24 | No | 7300000 | 10000000 | 10000000
Reliability Upgrade | 1a | 1097 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County | Planned | 2008-09-24 | No | 129800000 | 129800000 | 129800000
Reliability Upgrade | 1a | 1099 | National Grid, USA |  | 05/2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | 2008-09-24 | No | 4100000 | 6000000 | 6000000
Reliability Upgrade | 1a | 1109 | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Planned | 2008-09-24 | No | 360000 | 1000000 | 1000000
Reliability Upgrade | 1a | 1152 | National Grid, USA |  | 2010-08-01 |  | E205E Refurbishment Project | Planned | NR | NR |  | 43596000 | 43596000
Reliability Upgrade | 1a | 1049 | United Illuminating Company |  | 12/2010 |  | East Shore 115 kV Capacitor Bank Transient Recovery | Planned | NR | NR | 3000000 | 3000000 | 3000000
Reliability Upgrade | 1a | 582 | Northeast Utilities |  | 12/2010 |  | Separate 310 and 368 345-KV lines and create 368/1767 DCT | Planned | 2008-07-18 | No | 16000000 | 16000000 | 16000000
Reliability Upgrade | 1a | 1112 | United Illuminating Company |  | 12/2010 |  | Water Street 115kV circuit breaker and switch replacements. | Planned | NR | NR | 1000000 | 1000000 | 1000000
Reliability Upgrade | 1a | 974 | United Illuminating Company |  | 12/2011 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Planned | NR | No | 6700000 | 6700000 | 6700000
Reliability Upgrade | 1a | 816 | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Planned | 2008-09-24 | No | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1054 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Manchester - Meekvile Jct. line (395/1448) separation. | Planned | 2008-09-24 | No | 14000000 | 14000000 | 14000000
Reliability Upgrade | 1a | 576 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | 2008-09-24 | No | 313000000 | 313000000 | 313000000
Reliability Upgrade | 1a | 1114 | Northeast Utilities |  | 12/2013 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | 2008-09-24 | No | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1a | 814 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Central Connecticut Relaibility Project) | Reconductor a portion of the Manchester to Scovill Rock 353 345-kV line and terminal work. | Planned | 2008-09-24 | No | 9000000 | 9000000 | 9000000
Reliability Upgrade | 1a | 802 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | 2008-09-24 | No | 251000000 | 251000000 | 251000000
Reliability Upgrade | 1a | 1084 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Loop the Millstone - Manchester (310) 345 kV line into the Card substation. | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1085 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1086 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1087 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1088 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1089 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Killingly 3G substation 345kV breaker addition | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1090 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Millstone 15G substation breaker 14T upgrade 50kA | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1091 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Southington 4C substation breaker 19T upgrade to 63kA | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | Northeast Utilities |  | 12/2013 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | Northeast Utilities | National Grid, USA | 12/2013 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | 2008-09-24 | No | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 807 | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Interstate Reliability Project) | Install 480 MVAR's of capacitors at the Montville 345 kV substation | Planned | 2008-09-24 | No | 33000000 | 33000000 | 33000000
Reliability Upgrade | 1a | 1092 | Northeast Utilities |  | 12/2013 | NEEWS (BPS) 2 | Upgrade the Card 115 kV, East Hartford 115 kV, Agawam 115 kV, Barbour Hill 115 kV, and North Bloomfield 345 kV Substations to BPS standards. | Planned | 2008-09-24 | No | 37000000 | 37000000 | 37000000
Reliability Upgrade | 1a | 1056 | Northeast Utilities |  | 12/2011 | CT LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Planned | 2008-12-12 | No | 9751000 | 9751000 | 9751000
Reliability Upgrade | 1a | 1110 | United Illuminating Company |  | 12/2010 |  | Broadway 115/13.8 kV Substation Additon | Planned | 2008-12-08 | No | 1200000 | 1200000 | 1200000
Reliability Upgrade | 1a | 1111 | United Illuminating Company |  | 12/2010 |  | Metro North Union Avenue 115/26.4 kV Substation | Planned | 2009-01-07 | No | 10543000 | 10543000 | 10543000
Reliability Upgrade | 1a | 976 | United Illuminating Company |  | 05/2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Planned | 2009-01-07 | No | 48000000 | 48000000 | 48000000
Reliability Upgrade | 1a | 879 |  | Bangor Hydro-Electric Company, New England Power Company, Northeast Utilities System Com | TBD | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | 03/01/2007 | NR | 420000 | 420000 | 420000
Reliability Upgrade | 1a | 1050 | United Illuminating Company |  | 12/2011 |  | Devon Tie 115kV Switching Station BPS Compliance | Planned | NR | NR | 2620000 | 2620000 | 2620000 | -25% | 25%
[13 empty] | 4385548029 | 3289161021.75 | 5481935036.25 | 156
Reliability Upgrade | 1b | 148 | Central Maine Power Company |  | 06/2012 | CMP LSP - Saco Bay Area Reinforcement Project | Establish a new Vallee Lane 115/34.5 kV substation and 115 kV line from Louden S/S to Vallee Lane Substation. | Proposed | No | NR | 100000 | 100000 | 100000
Reliability Upgrade | 1b | 1130 | Central Maine Power Company |  | 12/2011 | Sturtevant Improvements | Add 115kV circuit breakers & 25 MVAR capacitor bank at Sturtevant Substation; Re-rate Section 63 between Wyman Hydro & Madison Substation | Proposed | No | No | 3000000 | 3000000 | 3000000
Reliability Upgrade | 1b | 1131 | Central Maine Power Company |  | 12/2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Proposed | No | NR | 600000 | 600000 | 600000
Reliability Upgrade | 1b | 1132 | Central Maine Power Company |  | 12/2011 | CMP-LSP Maxcy's Substation | Add 115/34kV transformer (coordinate with MPRP) | Proposed | No | NR | 600000 | 600000 | 600000
Reliability Upgrade | 1b | 1133 | Central Maine Power Company |  | 10/2010 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation & new 34kV line from Leeds to Turner | Proposed | No | NR | 300000 | 300000 | 300000
Reliability Upgrade | 1b | 1135 | Central Maine Power Company |  | TBD | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer | Proposed | No | No | 1500000 | 1500000 | 1500000
Reliability Upgrade | 1b | 1143 | Northeast Utilities |  | TBD |  | Littleton 115kV breaker addition and reconfiguration | Proposed | No | No | 5338000 | 5338000 | 5338000
Reliability Upgrade | 1b | 963 | NSTAR Electric Company |  | 12/2009 | Boston Area 115 kV Enhancements | Add a new 115kV breaker # 11 Relocate 447-509 and add control and protect at Holbrook. | Proposed | No | No | 4000000 | 4000000 | 4000000
Reliability Upgrade | 1b | 842 | NSTAR Electric Company |  | 06/2010 | Boston Area 115 kV Enhancements | Add 115 kV 54 MVAR capacitor bank at W. Framingham. | Proposed | No | No | 3000000 | 3700000 | 3700000
Reliability Upgrade | 1b | 964 | NSTAR Electric Company |  | 06/2011 | Boston Area 115 kV Enhancements | Relocate 115kV terminals at W. Walpole to mitigate breaker failure #8. | Proposed | No | No | 5600000 | 5600000 | 5600000
Reliability Upgrade | 1b | 1113 | NSTAR Electric Company |  | 12/2010 |  | Install KSt Breaker #31 | Proposed | No | No | 2100000 | 2960000 | 2960000
Reliability Upgrade | 1b | 1068 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to Sandwich and a a 345-115kV auto-transformer at Sandwich | Proposed | No | No | 110000000 | 110000000 | 110000000
Reliability Upgrade | 1b | 592 | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing | Proposed | No | No | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1118 | NSTAR Electric Company | National Grid, USA | 12/2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 | Proposed | No | No | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1067 | NSTAR Electric Company |  | 12/2010 | NPCC BPS Compliance | Tremont Station | Proposed | No | No | 11200000 | 12800000 | 12800000
Reliability Upgrade | 1b | 1065 | NSTAR Electric Company |  | 07/2012 | NPCC BPS Compliance | Waltham Station | Proposed | No | No | 24300000 | 26600000 | 26600000
Reliability Upgrade | 1b | 1119 | NSTAR Electric Company |  | 12/2010 | Greater Boston Reliability Project | Upgrade West Medway-West Walpole 345kV line #325 | Proposed | No | No | 2200000 | 2200000 | 2200000
Reliability Upgrade | 1b | 1120 | NSTAR Electric Company |  | 06/2010 |  | Install 345kV 160 MVAR shunt ractor at W. Walpole | Proposed | No | No | 7200000 | 7200000 | 7200000
Reliability Upgrade | 1b | 1136 | National Grid, USA |  | 12/2012 |  | New 115kV Switching Station at Devens Convert 69kV lines to 115kV, Reconfigure 115kV Supply at Ayer Substation | Proposed | 2009-07-28 | No | 9200000 | 9200000 | 9200000
Reliability Upgrade | 1b | 809 | Northeast Utilities |  | 12/2009 |  | Upgrade terminal equipment at Bunker Hill 115 kV substation. | Proposed | No | No | 1000000 | 1000000 | 1000000
Reliability Upgrade | 1b | 1150 | United Illuminating Company |  | 10/2011 |  | Grand Avenue - West River 115 kV Pumping Plant Replacements | Proposed | NR | NR |  | 1200000 | 1200000
Reliability Upgrade | 1b | 1151 | United Illuminating Company |  | 12/2011 |  | West River 115kV Switching Station Fault Duty Migration | Proposed | NR | NR |  | 3500000 | 3500000
Reliability Upgrade | 1b | 721 | United Illuminating Company |  | 06/2013 |  | New Shelton 115/13.8 kV substation | Proposed | No | No | 11300000 | 11300000 | 11300000
Reliability Upgrade | 1b | 1147 | Northeast Utilities |  | 2011 |  | Waterside Substation - install a three-breaker 115kV ring bus | Proposed | No | No |  | 4000000 | 4000000
Reliability Upgrade | 1b | 1148 | Northeast Utilities |  | 2011 |  | Add a 2nd high speed relay on the Glennbrook to Waterside 115kV 1440 | Proposed | No | No |  | 600000 | 600000 | -25% | 25%
[13 empty] | 217298000 | 162973500 | 271622500 | 25
Reliability Upgrade | 1a | 144 | Bangor Hydro-Electric Company |  | 12/2010 | Keene Rd Autotransformer | Installation of a 345/115 kV autotransformer at Keene Rd Substation. | Under Construction | No | No | 29000000 | 29000000 | 29000000
Reliability Upgrade | 1a | 625 | Central Maine Power Company |  | 02/2010 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Rumford Industrial Park capacitor bank. | Under Construction | 2007-11-30 | No | 5400000 | 5400000 | 5400000
Reliability Upgrade | 1a | 1029 | Central Maine Power Company |  | 11/2010 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformer at South Gorham | Under Construction | 7/31/2008 & 2/26/09 | No | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1144 | Central Maine Power Company |  | 04/2010 | Heywood Road Project | Circuit switcher replacements at Detroit, Lakewood, Rice Rips and Winslow | Under Construction | 2009-03-20 | 2009-07-20 | Part of Heywood Road Project | Part of Heywood Road Project | Part of the Heywood Road Project
Reliability Upgrade | 1a | 320 | Vermont Electric Power Company |  | 10/2009 | Lamoille County Project | Middlesex Substation 115 kV breaker addition. | Under Construction | 08/16/2007 | 02/07/2008 | 4857000 | 4857000 | 4857000
Reliability Upgrade | 1a | 322 | Vermont Electric Power Company |  | 10/2009 | Lamoille County Project | Installation of new Duxbury Substation that involves looping in and out of the Middlesex - Essex 115 kV (K24) line. | Under Construction | 08/16/2007 | 02/07/2008 | Part of Lamoille County Project | Part of Lamoille County Project | Part of Lamoille County Project
Reliability Upgrade | 1a | 321 | Vermont Electric Power Company |  | 12/2009 | Burlington Project | Burlington 115kV Loop - 5 mi of new line & rebuilding 5 miles of existing line between two existing substations with expansion of the East Avenue substation. | Under Construction | 10/24/2006 | 05/23/2007 | 25142000 | 25142000 | 25142000
Reliability Upgrade | 1a | 323 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | New VY - Newfane - Coolidge 345 kV line with requisite station upgrades. | Under Construction | 2008-10-01 | No | 136368000 | 136368000 | 136368000
Reliability Upgrade | 1a | 1032 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Installation of a new 345/115kV substation called Vernon including a new 345/115kV autotransformer | Under Construction | 2008-10-01 | No | 69815000 | 69815000 | 69815000
Reliability Upgrade | 1a | 1033 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project (VELCO LSP - Newfane Substation) | Installation of a new 345/115kV substation called Newfane | Under Construction | 2008-10-01 | No | 16664000 | 16664000 | 16664000
Reliability Upgrade | 1a | 1034 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Loop new 345kV Line into Newfane Substation. | Under Construction | 2008-10-01 | No | Part of project 323 | Part of project 323 | Part of project 323
Reliability Upgrade | 1a | 1035 | Vermont Electric Power Company |  | 06/2011 | Vermont Southern Loop Project | Expansion of Coolidge 345kV substation | Under Construction | 2008-10-01 | No | 20117000 | 20117000 | 20117000
Reliability Upgrade | 1a | 1063 | NSTAR Electric Company |  | 12/2009 |  | Install (2) 115kV 40 MVAR shunt reactors at Edgar Station | Under Construction | 05/2009 | No | 5400000 | 5400000 | 5400000
Reliability Upgrade | 1a | 777 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Build Wakefield Junction station with four 345/115 kV autotransformers. | Under Construction | 2008-04-01 | No | 95000000 | 95000000 | 95000000
Reliability Upgrade | 1a | 161 | National Grid, USA |  | 11/2009 | Merrimack Valley/North Shore Reliability Project | Loop 345 kV 339 line and 115 kV S-145/T-146 into new Wakefield Jct. Substation. | Under Construction | 2008-04-01 | No | 4986431 | 4986431 | 4986431
Reliability Upgrade | 1a | 779 | National Grid, USA |  | 04/2010 | Merrimack Valley/North Shore Reliability Project | Bypass and remove Golden Hills 345 kV substation. | Under Construction | 2008-04-01 | No | 5132609 | 5132609 | 5132609
Reliability Upgrade | 1a | 961 | NSTAR Electric Company |  | 11/2010 | Mystic Breaker Additions Project | Install (2) new 115 kV East Bus breakers #30 and #32 at Mystic and move Transformer 110B Connection. | Under Construction | 2008-03-10 | No | 3800000 | 3800000 | 3800000
Reliability Upgrade | 1a | 903 | NSTAR Electric Company |  | 12/2009 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #2, #4, #5, and #16 at Mystic to IPT and separate controls with Boston Gen units #5 and #6. | Under Construction | NR | NR | 1240000 | 1240000 | 1240000
Reliability Upgrade | 1a | 930 | National Grid, USA |  | 12/2009 | Central/Western Massachusetts Upgrades | Reconductor Nashua St - Quinsigamond Jct (O141) 115 kV line w/636 ACSS. | Under Construction | 12/17/2007 | No | 2300000 | 2300000 | 2300000
Reliability Upgrade | 1a | 933 | National Grid, USA |  | 12/2009 | Central/Western Massachusetts Upgrades | Reconductor Pratts Jct - Flagg Pond I-135S & J-136S 115 kV lines w/795 ACSS. | Under Construction | 12/17/2007 | No | 6137112 | 6137112 | 6137112
Reliability Upgrade | 1a | 162 | National Grid, USA |  | 04/2011 |  | Q-169 Golden Hills to Lynn 115 kV line upgrade. | Under Construction | 2005-09-02 | 2008-04-25 | 12390000 | 12390000 | 12390000
Reliability Upgrade | 1a | 902 | National Grid, USA |  | 03/2012 | Middleboro Municipal | Close the E1-M1 loop at Middleboro's Wareham St Sub. | Under Construction | 12/01/2006 | NR | 715000 | 715000 | 715000
Reliability Upgrade | 1a | 211 | Northeast Utilities |  | 11/2009 | NU LSP - Rood Ave Substation | New Rood Ave (formally Windsor) distribution substation with 115kV terminal modifications. | Under Construction | 2008-04-25 | 02/15/2008 | 9162029 | 9162029 | 9162029 | -10% | 10%
[13 empty] | 453626181 | 408263562.9 | 498988799.1 | 23
[12 empty] | GRAND TOTAL | 5255330744 | 3796853851.4 | 6849121937.35 | 228
[14 empty] | 99429267 | 596575602 | 24

## Sorted by ISD then status 10-09 (hidden)
October '09 ISO-NEW ENGLAND Project Listing Update (DRAFT)
Primary Driver | Part# | Project ID | Primary Equipment Owner | Projected In-Service Month/Year |  | Major Project | Project | Oct-09 Status | Oct-09 Estimated PTF Costs | Column T
Reliability Upgrade | 1b | 963 | NSTAR Electric Company | 12/2009 | 2009 | Boston Area 115 kV Enhancements | Add a new 115kV breaker # 11 Relocate 447-509 and add control and protect at Holbrook. | Proposed | 4000000 | 4000000
Reliability Upgrade | 1b | 809 | Northeast Utilities | 12/2009 | 2009 |  | Upgrade terminal equipment at Bunker Hill 115 kV substation. | Proposed | 1000000 | 1000000
Reliability Upgrade | 1a | 320 | Vermont Electric Power Company | 10/2009 | 2009 | Lamoille County Project | Middlesex Substation 115 kV breaker addition. | Under Construction | 4857000 | 4857000
Reliability Upgrade | 1a | 322 | Vermont Electric Power Company | 10/2009 | 2009 | Lamoille County Project | Installation of new Duxbury Substation that involves looping in and out of the Middlesex - Essex 115 kV (K24) line. | Under Construction | Part of Lamoille County Project | Part of Lamoille County Project
Reliability Upgrade | 1a | 321 | Vermont Electric Power Company | 12/2009 | 2009 | Burlington Project | Burlington 115kV Loop - 5 mi of new line & rebuilding 5 miles of existing line between two existing substations with expansion of the East Avenue substation. | Under Construction | 25142000 | 25142000
Reliability Upgrade | 1a | 1063 | NSTAR Electric Company | 12/2009 | 2009 |  | Install (2) 115kV 40 MVAR shunt reactors at Edgar Station | Under Construction | 5400000 | 5400000
Reliability Upgrade | 1a | 777 | National Grid, USA | 11/2009 | 2009 | Merrimack Valley/North Shore Reliability Project | Build Wakefield Junction station with four 345/115 kV autotransformers. | Under Construction | 95000000 | 95000000
Reliability Upgrade | 1a | 161 | National Grid, USA | 11/2009 | 2009 | Merrimack Valley/North Shore Reliability Project | Loop 345 kV 339 line and 115 kV S-145/T-146 into new Wakefield Jct. Substation. | Under Construction | 4986431 | 4986431
Reliability Upgrade | 1a | 903 | NSTAR Electric Company | 12/2009 | 2009 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #2, #4, #5, and #16 at Mystic to IPT and separate controls with Boston Gen units #5 and #6. | Under Construction | 1240000 | 1240000
Reliability Upgrade | 1a | 930 | National Grid, USA | 12/2009 | 2009 | Central/Western Massachusetts Upgrades | Reconductor Nashua St - Quinsigamond Jct (O141) 115 kV line w/636 ACSS. | Under Construction | 2300000 | 2300000
Reliability Upgrade | 1a | 933 | National Grid, USA | 12/2009 | 2009 | Central/Western Massachusetts Upgrades | Reconductor Pratts Jct - Flagg Pond I-135S & J-136S 115 kV lines w/795 ACSS. | Under Construction | 6137112 | 6137112
Reliability Upgrade | 1a | 211 | Northeast Utilities | 11/2009 | 2009 | NU LSP - Rood Ave Substation | New Rood Ave (formally Windsor) distribution substation with 115kV terminal modifications. | Under Construction | 9162029 | 9162029
Reliability Upgrade | 1b | 1153 | NSTAR Electric Company | 06/2010 | 2010 | Boston Area 115 kV Enhancements | Reliability Upgrades at West Framingham Station | Concept | 3000000 | 3000000
Reliability Upgrade | 1b | 1055 | Northeast Utilities | 2010 | 2010 | CT LSP - Waterside Substation | Waterside Substation - add a 115/13.2-kV transformer and a 115-kV circuit breaker. | Concept | 4107000 | 4107000
Reliability Upgrade | 1a | 1128 | Central Maine Power Company | 07/2010 | 2010 | CMP-LSP Hotel Road Substation | Add 115/34kV transformer with 115kV breaker at Hotel Rd. | Planned | 800000 | 800000
Reliability Upgrade | 1a | 624 | Central Maine Power Company | 2010 | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (New Page - Rumford Industrial Park) | Planned | Part of project 625 | Part of project 625
Reliability Upgrade | 1a | 139 | Vermont Electric Power Company | 12/2010 | 2010 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Planned | 20000000 | 20000000
Reliability Upgrade | 1a | 840 | NSTAR Electric Company | 10/2010 | 2010 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | 7300000 | 7300000
Reliability Upgrade | 1a | 904 | NSTAR Electric Company | 12/2010 | 2010 | Mystic IPT Breaker Project | Upgrade (5) 115 kV breakers #1, #7, #15 #19 and #20 at Mystic to IPT and separate controls with Boston Gen #4. | Planned | 990000 | 990000
Reliability Upgrade | 1a | 928 | National Grid, USA | 12/2010 | 2010 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | 2300000 | 2300000
Reliability Upgrade | 1a | 934 | National Grid, USA | 10/2010 | 2010 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Planned | 818480 | 818480
Reliability Upgrade | 1a | 935 | National Grid, USA | 07/2010 | 2010 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Planned | 5208509 | 5208509
Reliability Upgrade | 1a | 938 | National Grid, USA | 06/2010 | 2010 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | 3068556 | 3068556
Reliability Upgrade | 1a | 942 | National Grid, USA | 10/2010 | 2010 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | 2767180 | 2767180
Reliability Upgrade | 1a | 927 | National Grid, USA | 07/2010 | 2010 | Central/Western Massachusetts Upgrades | Greendale - replace 115 kV breaker and upgrade to 2000A. | Planned | 584629 | 584629
Reliability Upgrade | 1a | 484 | National Grid, USA | 11/2010 | 2010 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Planned | 690000 | 690000
Reliability Upgrade | 1a | 786 | National Grid, USA | 11/2010 | 2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Terminal upgrades at Drumrock, Chartley Pond, and Brayton Point. | Planned | 1000000 | 1000000
Reliability Upgrade | 1a | 787 | National Grid, USA | 12/2010 | 2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | West Farnum breaker replacements. | Planned | 7631000 | 7631000
Reliability Upgrade | 1a | 789 | National Grid, USA | 11/2010 | 2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Reconductoring of T7 115 kV line. | Planned | 23304000 | 23304000
Reliability Upgrade | 1a | 1152 | National Grid, USA | 2010-08-01 | 2010 |  | E205E Refurbishment Project | Planned | 43596000 | 43596000
Reliability Upgrade | 1a | 1049 | United Illuminating Company | 12/2010 | 2010 |  | East Shore 115 kV Capacitor Bank Transient Recovery | Planned | 3000000 | 3000000
Reliability Upgrade | 1a | 582 | Northeast Utilities | 12/2010 | 2010 |  | Separate 310 and 368 345-KV lines and create 368/1767 DCT | Planned | 16000000 | 16000000
Reliability Upgrade | 1a | 1112 | United Illuminating Company | 12/2010 | 2010 |  | Water Street 115kV circuit breaker and switch replacements. | Planned | 1000000 | 1000000
Reliability Upgrade | 1a | 1110 | United Illuminating Company | 12/2010 | 2010 |  | Broadway 115/13.8 kV Substation Additon | Planned | 1200000 | 1200000
Reliability Upgrade | 1a | 1111 | United Illuminating Company | 12/2010 | 2010 |  | Metro North Union Avenue 115/26.4 kV Substation | Planned | 10543000 | 10543000
Reliability Upgrade | 1b | 1133 | Central Maine Power Company | 10/2010 | 2010 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation & new 34kV line from Leeds to Turner | Proposed | 300000 | 300000
Reliability Upgrade | 1b | 842 | NSTAR Electric Company | 06/2010 | 2010 | Boston Area 115 kV Enhancements | Add 115 kV 54 MVAR capacitor bank at W. Framingham. | Proposed | 3700000 | 3700000
Reliability Upgrade | 1b | 1113 | NSTAR Electric Company | 12/2010 | 2010 |  | Install KSt Breaker #31 | Proposed | 2960000 | 2960000
Reliability Upgrade | 1b | 1067 | NSTAR Electric Company | 12/2010 | 2010 | NPCC BPS Compliance | Tremont Station | Proposed | 12800000 | 12800000
Reliability Upgrade | 1b | 1119 | NSTAR Electric Company | 12/2010 | 2010 | Greater Boston Reliability Project | Upgrade West Medway-West Walpole 345kV line #325 | Proposed | 2200000 | 2200000
Reliability Upgrade | 1b | 1120 | NSTAR Electric Company | 06/2010 | 2010 |  | Install 345kV 160 MVAR shunt ractor at W. Walpole | Proposed | 7200000 | 7200000
Reliability Upgrade | 1a | 144 | Bangor Hydro-Electric Company | 12/2010 | 2010 | Keene Rd Autotransformer | Installation of a 345/115 kV autotransformer at Keene Rd Substation. | Under Construction | 29000000 | 29000000
Reliability Upgrade | 1a | 625 | Central Maine Power Company | 02/2010 | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Rumford Industrial Park capacitor bank. | Under Construction | 5400000 | 5400000
Reliability Upgrade | 1a | 1029 | Central Maine Power Company | 11/2010 | 2010 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformer at South Gorham | Under Construction | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1144 | Central Maine Power Company | 04/2010 | 2010 | Heywood Road Project | Circuit switcher replacements at Detroit, Lakewood, Rice Rips and Winslow | Under Construction | Part of Heywood Road Project | Part of the Heywood Road Project
Reliability Upgrade | 1a | 779 | National Grid, USA | 04/2010 | 2010 | Merrimack Valley/North Shore Reliability Project | Bypass and remove Golden Hills 345 kV substation. | Under Construction | 5132609 | 5132609
Reliability Upgrade | 1a | 961 | NSTAR Electric Company | 11/2010 | 2010 | Mystic Breaker Additions Project | Install (2) new 115 kV East Bus breakers #30 and #32 at Mystic and move Transformer 110B Connection. | Under Construction | 3800000 | 3800000
Reliability Upgrade | 1b | 1116 | Bangor Hydro-Electric Company | 12/2011 | 2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Concept | TBD | TBD
Reliability Upgrade | 1b | 318 | Vermont Electric Power Company | 12/2011 | 2011 |  | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems through the 1,250 MW Vermont state load level. | Concept | 9000000 | 9000000
Reliability Upgrade | 1b | 325 | Vermont Electric Power Company | 12/2011 | 2011 | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | 5000000 | 5000000
Reliability Upgrade | 1b | 301 | NSTAR Electric Company | 12/2011 | 2011 | Boston Area 115 kV Enhancements | Reconductor 115-kV circuits 320-507 and 320-508. | Concept | 4600000 | 4600000
Reliability Upgrade | 1b | 1066 | NSTAR Electric Company | 09/2011 | 2011 | NPCC BPS Compliance | Needham Station | Concept | 9300000 | 9300000
Reliability Upgrade | 1a | 1145 | Vermont Electric Power Company | 09/2011 | 2011 | Burlington Project | Installation of a 3-breaker 115kV ring substation and 115/34.5kV transformer on the East Ave. - Tafts Coners 115kV line | Planned | 14000000 | 14000000
Reliability Upgrade | 1a | 783 | National Grid, USA | 03/2011 | 2011 | Merrimack Valley/North Shore Reliability Project | Extend the 115kV by addition of 115kV Breaker and K-153 line from King St. to W. Amesbury 115kV station. (W. Amesbury 345/115kV Station becomes PTF) | Planned | 30349000 | 30349000
Reliability Upgrade | 1a | 929 | National Grid, USA | 06/2011 | 2011 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | 1381849 | 1381849
Reliability Upgrade | 1a | 939 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor and retension (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | Planned | 3389658 | 3389658
Reliability Upgrade | 1a | 940 | National Grid, USA | 04/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS. | Planned | 6235744 | 6235744
Reliability Upgrade | 1a | 925 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | 318888 | 318888
Reliability Upgrade | 1a | 926 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | 6027520 | 6027520
Reliability Upgrade | 1a | 932 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | 372036 | 372036
Reliability Upgrade | 1a | 924 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | Planned | 2147181 | 2147181
Reliability Upgrade | 1a | 941 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Install new Millbury - Tower #510 115 kV line. | Planned | 7909203 | 7909203
Reliability Upgrade | 1a | 943 | National Grid, USA | 01/2011 | 2011 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | 1073995 | 1073995
Reliability Upgrade | 1a | 952 | National Grid, USA | 06/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor E Winchendon - J136 Tap within I135/J136 ROW w/795 ACSR. | Planned | 932156 | 932156
Reliability Upgrade | 1a | 937 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | 6602875 | 6602875
Reliability Upgrade | 1a | 955 | National Grid, USA | 11/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | 10779113 | 10779113
Reliability Upgrade | 1a | 1000 | Northeast Utilities | 12/2011 | 2011 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | Planned | 22000000 | 22000000
Reliability Upgrade | 1a | 1076 | Northeast Utilities | 12/2011 | 2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Planned | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1077 | Northeast Utilities | 12/2011 | 2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115kV line | Planned | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 788 | National Grid, USA | 06/2011 | 2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Kent County substation expansion. | Planned | 42300000 | 42300000
Reliability Upgrade | 1a | 790 | National Grid, USA | 12/2011 | 2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Planned | 50600000 | 50600000
Reliability Upgrade | 1a | 1098 | National Grid, USA | 12/2011 | 2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Planned | 37529000 | 37529000
Reliability Upgrade | 1a | 974 | United Illuminating Company | 12/2011 | 2011 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Planned | 6700000 | 6700000
Reliability Upgrade | 1a | 1056 | Northeast Utilities | 12/2011 | 2011 | CT LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Planned | 9751000 | 9751000
Reliability Upgrade | 1a | 1050 | United Illuminating Company | 12/2011 | 2011 |  | Devon Tie 115kV Switching Station BPS Compliance | Planned | 2620000 | 2620000
Reliability Upgrade | 1b | 1130 | Central Maine Power Company | 12/2011 | 2011 | Sturtevant Improvements | Add 115kV circuit breakers & 25 MVAR capacitor bank at Sturtevant Substation; Re-rate Section 63 between Wyman Hydro & Madison Substation | Proposed | 3000000 | 3000000
Reliability Upgrade | 1b | 1131 | Central Maine Power Company | 12/2011 | 2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Proposed | 600000 | 600000
Reliability Upgrade | 1b | 1132 | Central Maine Power Company | 12/2011 | 2011 | CMP-LSP Maxcy's Substation | Add 115/34kV transformer (coordinate with MPRP) | Proposed | 600000 | 600000
Reliability Upgrade | 1b | 964 | NSTAR Electric Company | 06/2011 | 2011 | Boston Area 115 kV Enhancements | Relocate 115kV terminals at W. Walpole to mitigate breaker failure #8. | Proposed | 5600000 | 5600000
Reliability Upgrade | 1b | 1150 | United Illuminating Company | 10/2011 | 2011 |  | Grand Avenue - West River 115 kV Pumping Plant Replacements | Proposed | 1200000 | 1200000
Reliability Upgrade | 1b | 1151 | United Illuminating Company | 12/2011 | 2011 |  | West River 115kV Switching Station Fault Duty Migration | Proposed | 3500000 | 3500000
Reliability Upgrade | 1b | 1147 | Northeast Utilities | 2011 | 2011 |  | Waterside Substation - install a three-breaker 115kV ring bus | Proposed | 4000000 | 4000000
Reliability Upgrade | 1b | 1148 | Northeast Utilities | 2011 | 2011 |  | Add a 2nd high speed relay on the Glennbrook to Waterside 115kV 1440 | Proposed | 600000 | 600000
Reliability Upgrade | 1a | 323 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project | New VY - Newfane - Coolidge 345 kV line with requisite station upgrades. | Under Construction | 136368000 | 136368000
Reliability Upgrade | 1a | 1032 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project | Installation of a new 345/115kV substation called Vernon including a new 345/115kV autotransformer | Under Construction | 69815000 | 69815000
Reliability Upgrade | 1a | 1033 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project (VELCO LSP - Newfane Substation) | Installation of a new 345/115kV substation called Newfane | Under Construction | 16664000 | 16664000
Reliability Upgrade | 1a | 1034 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project | Loop new 345kV Line into Newfane Substation. | Under Construction | Part of project 323 | Part of project 323
Reliability Upgrade | 1a | 1035 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project | Expansion of Coolidge 345kV substation | Under Construction | 20117000 | 20117000
Reliability Upgrade | 1a | 162 | National Grid, USA | 04/2011 | 2011 |  | Q-169 Golden Hills to Lynn 115 kV line upgrade. | Under Construction | 12390000 | 12390000
Reliability Upgrade | 1b | 1031 | Bangor Hydro-Electric Company | 01/2012 | 2012 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station, Rebuild Line 66, and Capacitior Bank Additions (10MVAr at Trenton, Downeast & Handcock County area) | Concept | TBD | TBD
Reliability Upgrade | 1b | 324 | Vermont Electric Power Company | 12/2012 | 2012 |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | 100000000 | 100000000
Reliability Upgrade | 1b | 965 | NSTAR Electric Company | 12/2012 | 2012 | Boston Area 115 kV Enhancements | Add third 115kV line from Walpole to Holbrook | Concept | TBD | TBD
Reliability Upgrade | 1b | 970 | NSTAR Electric Company | 12/2012 | 2012 | Greater Boston Reliability Project | Add a new 345 kV line from Lexington to Waltham. | Concept | TBD | TBD
Reliability Upgrade | 1b | 971 | NSTAR Electric Company | 12/2012 | 2012 | Greater Boston Reliability Project | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | TBD | TBD
Reliability Upgrade | 1b | 699 | United Illuminating Company | 12/2012 | 2012 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | 10000000 | 10000000
Reliability Upgrade | 1a | 905 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Planned | 1510000000 | 1510000000
Reliability Upgrade | 1a | 906 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Coopers Mills-Highland, Larrabee Road-Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 907 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 84 (Albion Road-Coopers Mills), Section 203 (Detroit-Orrington), Section 80 (Coopers Mills-Highland), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 908 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377 & Maine Yankee 375/392, 115kV Bucksport 65/205) and Maine Yankee 345 kV re-termination | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1026 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Three Rivers) | Planned | Portion of CMP $1.51B and portion of NU is $35.1M | 35100000
Reliability Upgrade | 1a | 1027 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 115kV Line Construction (Elm Street-East Deering, East Deering -Cape) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1028 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD
Reliability Upgrade | 1a | 1030 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Raven Farm, Maguire Road) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 143 | Bangor Hydro-Electric Company | 12/2012 | 2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation to Harrington Substation. | Planned | 66100000 | 66100000
Reliability Upgrade | 1a | 1129 | Central Maine Power Company | 05/2012 | 2012 |  | New 115kV line between Wyman Hydro and Heywood Rd. parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | 19500000 | 19500000
Reliability Upgrade | 1a | 277 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Planned | 56600000 | 56600000
Reliability Upgrade | 1a | 1137 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115kV breakers and add 1-115kV breaker at Deerfield Substation | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1138 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rebuild 115kV L175 line | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1139 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV M183 Line | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1140 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1141 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 680 | National Grid, USA | 09/2012 | 2012 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | 7393000 | 7393000
Reliability Upgrade | 1a | 1146 | Vermont Electric Power Company | 12/2012 | 2012 | Lyndonville Project | Installation of a 3-breaker 115kV righ station consisting of two 115kV 12.5 MVAR capacitor banks and 115/34.5 kV transformer interconnecting to the Irasburg - St. Johnsbury 115kV line | Planned | 9000000 | 9000000
Reliability Upgrade | 1a | 887 | National Grid, USA | 09/2012 | 2012 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Planned | 30000000 | 30000000
Reliability Upgrade | 1a | 921 | National Grid, USA | 01/2012 | 2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | 12100000 | 12100000
Reliability Upgrade | 1a | 919 | National Grid, USA | 09/2012 | 2012 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | 4600000 | 4600000
Reliability Upgrade | 1a | 775 | National Grid, USA | 06/2012 | 2012 | Merrimack Valley/North Shore Reliability Project | Addition of 4 breakers and relocation of T1 and T2 into new bays at Sandy Pond. | Planned | 20100000 | 20100000
Reliability Upgrade | 1a | 776 | National Grid, USA | 06/2012 | 2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | 2865876 | 2865876
Reliability Upgrade | 1a | 59 | National Grid, USA | 01/2012 | 2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | 400000 | 400000
Reliability Upgrade | 1a | 944 | National Grid, USA | 07/2012 | 2012 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Planned | 11411849 | 11411849
Reliability Upgrade | 1a | 948 | National Grid, USA | 07/2012 | 2012 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | 5649430 | 5649430
Reliability Upgrade | 1a | 949 | National Grid, USA | 07/2012 | 2012 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | 1500000 | 1500000
Reliability Upgrade | 1a | 673 | National Grid, USA | 12/2012 | 2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | National Grid, USA | 12/2012 | 2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Planned | 30000000 | 30000000
Reliability Upgrade | 1a | 1095 | National Grid, USA | 06/2012 | 2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | 73800000 | 73800000
Reliability Upgrade | 1a | 797 | National Grid, USA | 12/2012 | 2012 | NEEWS (Interstate Reliability Project) | 3361 Upgrade 345kV terminal equipment at Sherman Road. | Planned | 8300000 | 8300000
Reliability Upgrade | 1a | 795 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV line. | Planned | 99900000 | 99900000
Reliability Upgrade | 1a | 1106 | National Grid, USA | 05/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | Planned | Part of $99,900,000 above | Part of $99,900,000 above
Reliability Upgrade | 1a | 798 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Planned | 4900000 | 4900000
Reliability Upgrade | 1a | 799 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | Planned | 4500000 | 4500000
Reliability Upgrade | 1a | 1096 | National Grid, USA | 05/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | 12000000 | 12000000
Reliability Upgrade | 1a | 800 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S, T-172N and T-172S with associated terminal equipment upgrades. | Planned | 10000000 | 10000000
Reliability Upgrade | 1a | 1097 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County | Planned | 129800000 | 129800000
Reliability Upgrade | 1a | 1099 | National Grid, USA | 05/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | 6000000 | 6000000
Reliability Upgrade | 1a | 1109 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Planned | 1000000 | 1000000
Reliability Upgrade | 1a | 976 | United Illuminating Company | 05/2012 | 2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Planned | 48000000 | 48000000
Reliability Upgrade | 1b | 148 | Central Maine Power Company | 06/2012 | 2012 | CMP LSP - Saco Bay Area Reinforcement Project | Establish a new Vallee Lane 115/34.5 kV substation and 115 kV line from Louden S/S to Vallee Lane Substation. | Proposed | 100000 | 100000
Reliability Upgrade | 1b | 1068 | NSTAR Electric Company | 12/2012 | 2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to Sandwich and a a 345-115kV auto-transformer at Sandwich | Proposed | 110000000 | 110000000
Reliability Upgrade | 1b | 592 | NSTAR Electric Company | 12/2012 | 2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing | Proposed | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1118 | NSTAR Electric Company | 12/2012 | 2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 | Proposed | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1065 | NSTAR Electric Company | 07/2012 | 2012 | NPCC BPS Compliance | Waltham Station | Proposed | 26600000 | 26600000
Reliability Upgrade | 1b | 1136 | National Grid, USA | 12/2012 | 2012 |  | New 115kV Switching Station at Devens Convert 69kV lines to 115kV, Reconfigure 115kV Supply at Ayer Substation | Proposed | 9200000 | 9200000
Reliability Upgrade | 1a | 902 | National Grid, USA | 03/2012 | 2012 | Middleboro Municipal | Close the E1-M1 loop at Middleboro's Wareham St Sub. | Under Construction | 715000 | 715000
Reliability Upgrade | 1b | 843 | NSTAR Electric Company | 12/2013 | 2013 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | TBD | TBD
Reliability Upgrade | 1b | 593 | NSTAR Electric Company | 2013 | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Canal to Barnstable/Falmouth | Concept | TBD | TBD
Reliability Upgrade | 1b | 956 | National Grid, USA | 05/2013 | 2013 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Concept | 7021534 | 7021534
Reliability Upgrade | 1b | 975 | United Illuminating Company | 12/2013 | 2013 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | 44300000 | 44300000
Reliability Upgrade | 1a | 674 | National Grid, USA | 09/2013 | 2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | 7720000 | 7720000
Reliability Upgrade | 1a | 782 | National Grid, USA | 10/2013 | 2013 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor n Railyard. | Planned | 38100000 | 38100000
Reliability Upgrade | 1a | 931 | National Grid, USA | 01/2013 | 2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | 531481 | 531481
Reliability Upgrade | 1a | 950 | National Grid, USA | 12/2013 | 2013 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | 1016897 | 1016897
Reliability Upgrade | 1a | 953 | National Grid, USA | 12/2013 | 2013 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | 10248067 | 10248067
Reliability Upgrade | 1a | 954 | National Grid, USA | 12/2013 | 2013 | Central/Western Massachusetts Upgrades | E Westminster - install new 115 kV breaker, including disconnect switches. Assumes no new control house. | Planned | 903909 | 903909
Reliability Upgrade | 1a | 945 | National Grid, USA | 02/2013 | 2013 | Central/Western Massachusetts Upgrades | Adams - install third 115 kV breaker to complete ring bus. | Planned | 1584841 | 1584841
Reliability Upgrade | 1a | 946 | National Grid, USA | 04/2013 | 2013 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer - E Longmeadow - Shaker Rd line to 115 kV. | Planned | 9604032 | 9604032
Reliability Upgrade | 1a | 947 | National Grid, USA | 04/2013 | 2013 | Central/Western Massachusetts Upgrades | Reconductor 115 kV line from Palmer to new Hampden Substation. | Planned | 2632635 | 2632635
Reliability Upgrade | 1a | 951 | National Grid, USA | 02/2013 | 2013 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon 115 kV line. | Planned | 7455440 | 7455440
Reliability Upgrade | 1a | 687 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | 714000000 | 714000000
Reliability Upgrade | 1a | 826 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 196 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115kV line South Agawam to Southwick (1768) | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVAR Capacitor additions | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1074 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1078 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 190 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | 69600000 | 69600000
Reliability Upgrade | 1a | 1094 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | 25000000 | 25000000
Reliability Upgrade | 1a | 794 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | 55800000 | 55800000
Reliability Upgrade | 1a | 796 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | 347 Reconductor from Sherman Road to CT/RI Border. | Planned | 16400000 | 16400000
Reliability Upgrade | 1a | 816 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1054 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Manchester - Meekvile Jct. line (395/1448) separation. | Planned | 14000000 | 14000000
Reliability Upgrade | 1a | 576 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | 313000000 | 313000000
Reliability Upgrade | 1a | 1114 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1a | 814 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Ancillary Central Connecticut Relaibility Project) | Reconductor a portion of the Manchester to Scovill Rock 353 345-kV line and terminal work. | Planned | 9000000 | 9000000
Reliability Upgrade | 1a | 802 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | 251000000 | 251000000
Reliability Upgrade | 1a | 1084 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Loop the Millstone - Manchester (310) 345 kV line into the Card substation. | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1085 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1086 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1087 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1088 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1089 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Killingly 3G substation 345kV breaker addition | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1090 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Millstone 15G substation breaker 14T upgrade 50kA | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1091 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Southington 4C substation breaker 19T upgrade to 63kA | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 807 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Ancillary Interstate Reliability Project) | Install 480 MVAR's of capacitors at the Montville 345 kV substation | Planned | 33000000 | 33000000
Reliability Upgrade | 1a | 1092 | Northeast Utilities | 12/2013 | 2013 | NEEWS (BPS) 2 | Upgrade the Card 115 kV, East Hartford 115 kV, Agawam 115 kV, Barbour Hill 115 kV, and North Bloomfield 345 kV Substations to BPS standards. | Planned | 37000000 | 37000000
Reliability Upgrade | 1b | 721 | United Illuminating Company | 06/2013 | 2013 |  | New Shelton 115/13.8 kV substation | Proposed | 11300000 | 11300000
Reliability Upgrade | 1a | 791 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | 11560000 | 11560000
Reliability Upgrade | 1a | 913 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | 3250000 | 3250000
Reliability Upgrade | 1a | 914 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | 28150000 | 28150000
Reliability Upgrade | 1a | 915 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | 11800000 | 11800000
Reliability Upgrade | 1a | 917 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | 7000000 | 7000000
Reliability Upgrade | 1a | 918 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | 3180000 | 3180000
Reliability Upgrade | 1a | 792 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Admiral St-Franklin Square (Q143 and R144) 115 kV UG recabling. | Planned | 39200000 | 39200000
Reliability Upgrade | 1a | 793 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | 6400000 | 6400000
Reliability Upgrade | 1b | 785 | National Grid, USA | 07/2017 | 2017 | Merrimack Valley/North Shore Reliability Project | Re-conductor F-158N (Golden Hills-Maplewood-Everett) 115 kV line. | Concept | 1330000 | 1330000
Reliability Upgrade | 1b | 969 | NSTAR Electric Company | 06/2018 | 2018 | Boston Area 115 kV Enhancements | Add a new 54 MVAR capacitor bank at Chelsea. | Concept | 1200000 | 1200000
Reliability Upgrade | 1b | 275 | Northeast Utilities | TBD | tbd |  | Merrimack 115-kV substation - Protection Separation Upgrade. | Concept | TBD | TBD
Reliability Upgrade | 1b | 824 | Northeast Utilities | TBD | tbd | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Concept | TBD | TBD
Reliability Upgrade | 1b | 825 | Northeast Utilities | TBD | tbd | Pittsfield / Greenfield Project | Upgrade the Pleasant to Blanford 115-kV line and the Blanford to Granville Jct. portion of the 115-kV line 1512. | Concept | TBD | TBD
Reliability Upgrade | 1b | 801 | Northeast Utilities | TBD | tbd |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Concept | TBD | TBD
Reliability Upgrade | 1b | 85 | Northeast Utilities | TBD | tbd |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | TBD | TBD
Reliability Upgrade | 1a | 879 |  | TBD | tbd | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | 420000 | 420000
Reliability Upgrade | 1b | 1135 | Central Maine Power Company | TBD | tbd | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer | Proposed | 1500000 | 1500000
Reliability Upgrade | 1b | 1143 | Northeast Utilities | TBD | tbd |  | Littleton 115kV breaker addition and reconfiguration | Proposed | 5338000 | 5338000
5255330774

## Macro1 (hidden)
Macro1 | Auto_Open
Macro10
Macro11
Macro12
Macro13
Macro14
Macro15
Macro16
Macro2
Macro3
Macro4
Macro5
Macro6
Macro7
Macro8
Macro9
Recover

## SortbyISD-StatusWInS-Nov11 (hidden)
October 2011 ISO-NEW ENGLAND Project Listing Update (DRAFT)(7)
Primary Driver | Part# | Project ID | State | Primary Equipment Owner |  | Projected In-Service Month/Year | Major Project | Project | Oct-11 Status | Oct-11 Estimated PTF Costs
Reliability Upgrade | 1a | 1197 | ME | Bangor Hydro-Electric Company |  | 12/2013 | Keene Rd Autotransformer | Orrington 345kV Series Breaker Addition | Planned | 1761250 | 1761250
Reliability Upgrade | 1a | 1116 | ME | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Under Construction | 37626000 | 37626000
Reliability Upgrade | 1a | 1156 | ME | Bangor Hydro-Electric Company |  | 12/2011 | Maine Power Reliability Program (MPRP) | Orrington Shunt Cap Reconfiguration | Under Construction | 2260262 | 2260262
Reliability Upgrade | 1a | 905 | ME | Central Maine Power Company |  | 2014-08-02 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Under Construction | 1364108000 | 1364108000
Reliability Upgrade | 1a | 906 | ME | Central Maine Power Company |  | 05/2014 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Larrabee Road-Middle St,Middle St -Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Under Construction | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 907 | ME | Central Maine Power Company |  | 05/2014 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 203 (Detroit-Orrington), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 908 | ME | Central Maine Power Company |  | 07/2014 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road); Coopers Mills autotransforme replaces Maxcy's autotransformer | Under Construction | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | ME | Central Maine Power Company |  | 2014-08-02 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast forming Sections 86 & 266 | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | ME | Central Maine Power Company |  | 05/2014 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377, 115kV Bucksport 65/205) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1026 | ME | Central Maine Power Company |  | 12/2013 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction associated with (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Elliot Switching Station) line work | Planned | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | 36000000
Reliability Upgrade | 1a | 1028 | ME | Central Maine Power Company |  | 12/2013 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M
Reliability Upgrade | 1a | 1158 | ME | Central Maine Power Company |  | 07/2014 | Maine Power Reliability Program (MPRP) | Two 40 MVAR reactors at Albion Road, two 40 MVAR reactors at Larabee Road, two 40 MVAR at Coopers Mills | Under Construction | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1030 | ME | Central Maine Power Company |  | 11/2013 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Maguire Road) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1132 | ME | Central Maine Power Company |  | 2014-08-02 | Maine Power Reliability Program (MPRP) | Add 115/34kV transformer at Coopers Mills | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 143 | ME | Bangor Hydro-Electric Company |  | 12/2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation (2 new breakers) to Harrington Substation to Epping Substation (3 new breakers) | Under Construction | 66100000 | 66100000
Reliability Upgrade | 1a | 1129 | ME | Central Maine Power Company |  | 05/2012 |  | New 115kV line between Wyman Hydro and Rice Rips Tap, parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | 32800000 | 32800000
Reliability Upgrade | 1a | 1131 | ME | Central Maine Power Company |  | 11/2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Under Construction | 600000 | 600000
Reliability Upgrade | 1a | 1135 | ME | Central Maine Power Company |  | 02/2012 | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer | Planned | 1500000 | 1500000
Reliability Upgrade | 1a | 1196 | ME | Bangor Hydro-Electric Company |  | 01/2012 | SVC Filter Upgrade (Part of Keene Rd Auto-transformer ID 144) | Upgrade of filter bank at Chester SVC facility | Under Construction | 3500000 | 3500000
Reliability Upgrade | 1a | 1184 | ME | Central Maine Power Company |  | 05/2012 | Starks Switching Station | Add 4-115kV circuit breakers in a breaker-and a-half configuration on Section 63 and 2-18 MVAr cap banks at a new Starks Switching Station | Planned | 9750000 | 9750000
Reliability Upgrade | 1a | 1251 | ME | Central Maine Power Company |  | 12/2012 | Lakewood Substation Expansion | Sectionalize Section 241 by adding four 115kV circuit breakers at Lakewood Substation and install a second 115/34.5 kV transformer | Planned | 13700000 | 13700000
Reliability Upgrade | 1a | 1219 | NH | Northeast Utilities |  | 12/2011 |  | Install 115kV two 13.3 MVAR capacitor banks at Oak Hill substation | Under Construction | 4000000 | 4000000
Reliability Upgrade | 1a | 277 | NH | Northeast Utilities |  | 11/2011 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Under Construction | 52000000 | 52000000
Reliability Upgrade | 1a | 1140 | NH | Northeast Utilities |  | 10/2011 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | Under Construction | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1141 | NH | Northeast Utilities |  | 2015 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1182 | NH | Northeast Utilities |  | 06/2012 | LSP New Eagle Substation and 115/34.5KV transformer | New 115kV Eagle Substation connected to 115/34.5kV Thornton Substation | Under Construction | 22800000 | 22800000
Reliability Upgrade | 1a | 680 | NH | National Grid, USA |  | 06/2013 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | 7393000 | 7393000
Reliability Upgrade | 1a | 674 | NH | National Grid, USA |  | 12/2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | 19460000 | 19460000
Reliability Upgrade | 1a | 1172 | VT | Vermont Electric Power Company |  | 06/2012 | Vermont Shunt Reactors | Install 345kV 60 MVAr shunt reactors (two at Coolidge and one at New Haven and relocate the New Haven reactor to Vernon) to address high voltage concerns | Planned | 20000000 | 20000000
Reliability Upgrade | 1a | 318 | VT | Vermont Electric Power Company |  | 12/2012 | Georgia Substation Rebuild | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems due to breaker failure contingencies | Planned | 16000000 | 16000000
Reliability Upgrade | 1a | 1169 | VT | Vermont Electric Power Company |  | 12/2012 | Ascutney Substation Rebuild | Rebuild the existing Ascutney substation 115kV bus into a ring bus, to address reliability problems due to breaker failure contingencies | Planned | 14500000 | 14500000
Reliability Upgrade | 1a | 1170 | VT | Vermont Electric Power Company |  | 06/2013 | Bennington Substation Rebuild | Rebuild the exiting Bennington substation 115kV bus into a ring bus to address reliability problems due to breaker failure contingencies | Planned | 28000000 | 28000000
Reliability Upgrade | 1a | 1171 | VT | Vermont Electric Power Company |  | 12/2011 | West Rutland Capacitor Rebuild | Install two 115kV 25 MVAr capacitor banks at West Rutland to address low voltage concerns | Planned | 2400000 | 2400000
Reliability Upgrade | 1a | 1194 | VT | Vermont Electric Power Company |  | 12/2012 | LSP Jay Substation | Construct a new 4-breaker ring substation at Jay with two 115/46kV transformers | Planned | 6500000 | 6500000
Reliability Upgrade | 1a | 1195 | VT | Vermont Electric Power Company |  | 03/2013 | Highgate Refurbishment | Replace Highgate controls and cooling system | Planned | 35600000 | 35600000
Reliability Upgrade | 1a | 887 | MA | National Grid, USA |  | 06/2013 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Under Construction | 58000000 | 58000000
Reliability Upgrade | 1a | 921 | MA | National Grid, USA |  | 12/2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | 40000000 | 40000000
Reliability Upgrade | 1a | 919 | MA | National Grid, USA |  | 04/2014 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | 13600000 | 13600000
Reliability Upgrade | 1a | 59 | MA | National Grid, USA |  | 12/2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | Part of RSP 921 | Part of RSP 921
Reliability Upgrade | 1a | 840 | MA | NSTAR Electric Company |  | 12/2012 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | 5900000 | 5900000
Reliability Upgrade | 1a | 776 | MA | National Grid, USA |  | 11/2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | 3125000 | 3125000
Reliability Upgrade | 1a | 782 | MA | National Grid, USA |  | 01/2016 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor and Railyard. | Planned | 43912000 | 43912000
Reliability Upgrade | 1a | 1165 | MA | NSTAR Electric Company |  | 12/2011 | Mystic Breaker Additions Project | Move Transformer 110B Connection at Mystic | Under Construction | 2600000 | 2600000
Reliability Upgrade | 1a | 1068 | MA | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to vicinity of Bourne and connect to existing #120 line and install a 345KV - 115kV auto-transformer at new substation about 3 miles west of the Barnstable Substation Loop Line #115 in and out of the new Substation. Create a new line position at the Bourne Substation and connect the Bourne-Canal section of Line #120 | Planned | 106500000 | 106500000
Reliability Upgrade | 1a | 592 | MA | NSTAR Electric Company |  | 12/2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing. The lines being separated are 322 (Canal-Carver) and 342 (Canal-Pilgrim-Auburn) | Planned | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1a | 1118 | MA | National Grid, USA |  | 12/2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 (Bellrock-High Hill) | Planned | 6000000 | 6000000
Reliability Upgrade | 1a | 1187 | MA | National Grid, USA |  | 06/2014 | A127/B128 Conductor Refurbishment | A127/B128 Conductor Refurbishment - Tower 510 to Harriman Substation, VT | Planned | 65000000 | 65000000
Reliability Upgrade | 1a | 929 | MA | National Grid, USA |  | 09/2013 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | 2500000 | 2500000
Reliability Upgrade | 1a | 931 | MA | National Grid, USA |  | 01/2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | 531481 | 531481
Reliability Upgrade | 1a | 928 | MA | National Grid, USA |  | 06/2013 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | 3400000 | 3400000
Reliability Upgrade | 1a | 934 | MA | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Under Construction | Part of RSP 935 | Part of RSP 935
Reliability Upgrade | 1a | 935 | MA | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Under Construction | 10200000 | 10200000
Reliability Upgrade | 1a | 938 | MA | National Grid, USA |  | 05/2013 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | 5430000 | 5430000
Reliability Upgrade | 1a | 940 | MA | National Grid, USA |  | 06/2014 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS (A127 West reconductoring. Tower 510 to Paxton, French King to French King). | Planned | 18000000 | 18000000
Reliability Upgrade | 1a | 942 | MA | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | 3650000 | 3650000
Reliability Upgrade | 1a | 925 | MA | National Grid, USA |  | 11/2012 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | Part of RSP 926 | Part of RSP 926
Reliability Upgrade | 1a | 926 | MA | National Grid, USA |  | 11/2012 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | 14700000 | 14700000
Reliability Upgrade | 1a | 932 | MA | National Grid, USA |  | 11/2012 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | Part of RSP 926 | Part of RSP 926
Reliability Upgrade | 1a | 941 | MA | National Grid, USA |  | 2013-08-01 | Central/Western Massachusetts Upgrades | Install new Z126 Millbury - Tower #510 115 kV line. | Planned | 13748000 | 13748000
Reliability Upgrade | 1a | 943 | MA | National Grid, USA |  | 12/2012 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | 4100000 | 4100000
Reliability Upgrade | 1a | 944 | MA | National Grid, USA |  | 03/2012 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Under Construction | 15700000 | 15700000
Reliability Upgrade | 1a | 950 | MA | National Grid, USA |  | 02/2015 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | 1016897 | 1016897
Reliability Upgrade | 1a | 953 | MA | National Grid, USA |  | 02/2015 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | 10248067 | 10248067
Reliability Upgrade | 1a | 954 | MA | National Grid, USA |  | 02/2015 | Central/Western Massachusetts Upgrades | Westminster - install new 69kV breaker, including disconnect switches. | Planned | 903909 | 903909
Reliability Upgrade | 1a | 945 | MA | National Grid, USA |  | 05/2014 | Central/Western Massachusetts Upgrades | Adams - install two new 115 kV breakers and replace two existing 115kV breakers | Planned | 5000000 | 5000000
Reliability Upgrade | 1a | 946 | MA | National Grid, USA |  | 04/2015 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer- Hampden to 115 kV. | Planned | 16000000 | 16000000
Reliability Upgrade | 1a | 948 | MA | National Grid, USA |  | 05/2014 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | 13400000 | 13400000
Reliability Upgrade | 1a | 949 | MA | National Grid, USA |  | 04/2015 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | 1600000 | 1600000
Reliability Upgrade | 1a | 937 | MA | National Grid, USA |  | 12/2015 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | 6602875 | 6602875
Reliability Upgrade | 1a | 955 | MA | National Grid, USA |  | 10/2012 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | 13800000 | 13800000
Reliability Upgrade | 1a | 951 | MA | National Grid, USA |  | 01/2014 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon (H-134) 115 kV line. | Planned | 7455440 | 7455440
Reliability Upgrade | 1a | 1217 | MA | Northeast Utilities |  | 12/2012 | Central/Western Massachusetts Upgrades | Subatation work at Ludlow (MA) and Scitico (CT) assoicaited with the new Hampden (MA) subsation project (Ngrid) | Planned | 3140000 | 3140000
Reliability Upgrade | 1a | 1076 | MA | Northeast Utilities |  | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Under Construction | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 687 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | 718000000 | 718000000
Reliability Upgrade | 1a | 826 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 196 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct the 115kV line South Agawam to Southwick (1768) | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVar Capacitor additions | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1074 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1078 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | MA | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1109 | MA | National Grid, USA |  | 12/2011 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Under Construction | 1000000 | 1000000
Reliability Upgrade | 1a | 1094 | MA | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | 25000000 | 25000000
Reliability Upgrade | 1a | 1202 | MA | NSTAR Electric Company |  | 06/2013 | NEEWS (Ancillary Interstate Reliability Project) | Rebuild 1.2 mile length of line 336 with 2-900 ACSS conductor and replace 5, 345kV 2000 amp disconnect switches with 3000 amp switches at W. Medway station | Planned | 1700000 | 1700000
Reliability Upgrade | 1a | 791 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | 11560000 | 11560000
Reliability Upgrade | 1a | 913 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | 3250000 | 3250000
Reliability Upgrade | 1a | 914 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | 28150000 | 28150000
Reliability Upgrade | 1a | 917 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | 7000000 | 7000000
Reliability Upgrade | 1a | 793 | MA | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | 6400000 | 6400000
Reliability Upgrade | 1a | 790 | MA | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Under Construction | 52000000 | 52000000
Reliability Upgrade | 1a | 1098 | MA | National Grid, USA |  | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Under Construction | 22000000 | 22000000
Reliability Upgrade | 1a | 1092 | MA | Northeast Utilities |  | 12/2013 | Agawam (BPS) | Upgrade the Agawam 115kV, Subtations to BPS standards together with other misc. subatation upgrades | Under Construction | 12100000 | 12100000
Reliability Upgrade | 1a | 1216 | MA | Northeast Utilities |  | 04/2012 |  | 345kV Ludlow - Northfield (portion of 354) Line Structure replacements | Under Construction | 25100000 | 25100000
Reliability Upgrade | 1a | 1266 | MA | Northeast Utilities |  | 12/2011 |  | 115kV Pleasant to Blandford (portion of 1421) Line structure replacement | Under Construction | 9960000 | 9960000
Reliability Upgrade | 1a | 1267 | MA | Northeast Utilities |  | 12/2011 |  | 115kV Blandford to Southwick (portion of 1512) Line structure replacement | Under Construction | 9600000 | 9600000
Reliability Upgrade | 1a | 1268 | MA | Northeast Utilities |  | 12/2012 |  | 345kV Northfield Mountain to Berkshire (portion of 312) line structure replacements | Planned | 7900000 | 7900000
Reliability Upgrade | 1a | 673 | MA | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | MA | National Grid, USA |  | 12/2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Planned | 30000000 | 30000000
Reliability Upgrade | 1a | 1257 | MA | National Grid, USA |  | 06/2014 | Salem Harbor Retirement | 115kV line Reconductoring of the S-145/T-146 from Tewksbury-North Reading Tap (9.3 miles each) | Planned | 29000000 | 29000000
Reliability Upgrade | 1a | 1258 | MA | National Grid, USA |  | 06/2014 | Salem Harbor Retirement | 115kV line Reconductoring of the Y-151 from Tewksbury Junction - West Methuen (8.2 miles) | Planned | 11500000 | 11500000
Reliability Upgrade | 1a | 1259 | MA | National Grid, USA |  | 06/2014 | Salem Harbor Retirement | 115kV line Reconductoring of the B154/C-155N from King St Tap - South Danvers (14.5 miles each way) | Planned | 20000000 | 20000000
Reliability Upgrade | 1a | 969 | MA | NSTAR Electric Company |  | 11/2012 | Greater Boston - North | Add a new 115kV 36.7 MVAR capacitor bank at Chelsea. | Under Construction | 1500000 | 1500000
Reliability Upgrade | 1a | 1201 | MA | NSTAR Electric Company |  | 12/2012 | Greater Boston - North | 115kV line Reconductoring of the P168/128-518 Line between Chelsea and Revere (NSTAR Portion of the line) | Planned | 1500000 | 1500000
Reliability Upgrade | 1a | 301 | MA | NSTAR Electric Company |  | 12/2011 | Greater Boston - Central | Reconductor 115-kV circuits 320-507 and 320-508. (Lexington - Waltham) | Under Construction | 9600000 | 9600000
Reliability Upgrade | 1a | 1066 | MA | NSTAR Electric Company |  | 12/2011 | NPCC BPS Compliance | Needham Station | Under Construction | 8000000 | 8000000
Reliability Upgrade | 1a | 1065 | MA | NSTAR Electric Company |  | 07/2012 | NPCC BPS Compliance | Waltham Station | Under Construction | 14700000 | 14700000
Reliability Upgrade | 1a | 1168 | MA | Holyoke Gas & Electric |  | 12/2012 | North Canal 44P | Loop the 1525 (Holyoke Fairmont South 115kV) line into the new North Canal 44P | Planned | 4100000 | 4100000
Reliability Upgrade | 1a | 1256 | MA | Unitil |  | 06/2013 | Flagg Pond Upgrades | At Flagg Pond Substation upgrade terminal equipment on the I-135N, I-135S, J-136N and J-136S 115kV lines and Zone 3 relay upgrades for the J-136N 115kV line. | Planned | 2750000 | 2750000
Reliability Upgrade | 1a | 484 | RI | National Grid, USA |  | 11/2011 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Under Construction | 580000 | 580000
Reliability Upgrade | 1a | 915 | RI | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | RI | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | 11800000 | 11800000
Reliability Upgrade | 1a | 918 | RI | National Grid, USA |  | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | 3180000 | 3180000
Reliability Upgrade | 1a | 190 | RI | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | 81800000 | 81800000
Reliability Upgrade | 1a | 1095 | RI | National Grid, USA |  | 12/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | 73800000 | 73800000
Reliability Upgrade | 1a | 794 | RI | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | 71700000 | 71700000
Reliability Upgrade | 1a | 795 | RI | National Grid, USA |  | 04/2013 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV (359) line. | Planned | 69000000 | 69000000
Reliability Upgrade | 1a | 1106 | RI | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Kent County Substation Upgrades related to third 345/115 kV Autotransformer. | Planned | 26000000 | 26000000
Reliability Upgrade | 1a | 798 | RI | National Grid, USA |  | 12/2011 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Planned | 600000 | 600000
Reliability Upgrade | 1a | 1096 | RI | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | 12000000 | 12000000
Reliability Upgrade | 1a | 1097 | RI | National Grid, USA |  | 01/2013 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County including S-175, T172N and T-172S with associated terminal equipment upgrade. | Planned | 129800000 | 129800000
Reliability Upgrade | 1a | 1099 | RI | National Grid, USA |  | 06/2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | 6000000 | 6000000
Reliability Upgrade | 1a | 1253 | RI | National Grid, USA |  | 04/2015 |  | New Crandall St. Substation 115-13 kV substation addition | Planned | 3000000 | 3000000
Reliability Upgrade | 1a | 1241 | RI | National Grid, USA |  | 06/2013 |  | Re-condustor G-185S (Kent County - Davisville Tap) | Planned | 4200000 | 4200000
Reliability Upgrade | 1a | 1193 | CT | United Illuminating Company |  | 12/2012 |  | North Haven 115kV Capacitor Bank TRV Mitigation Project | Under Construction | 4900000 | 4900000
Reliability Upgrade | 1a | 974 | CT | United Illuminating Company |  | 05/2013 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Under Construction | 16900000 | 16900000
Reliability Upgrade | 1a | 816 | CT | Northeast Utilities |  | 12/2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1054 | CT | Northeast Utilities |  | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Build a new 345 kV line from Manchester to Meekville Junction and re-terminate the 395 line at Meekville Junction | Planned | 28800000 | 28800000
Reliability Upgrade | 1a | 576 | CT | Northeast Utilities |  | 2016 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | 301000000 | 301000000
Reliability Upgrade | 1a | 1114 | CT | Northeast Utilities |  | 2016 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1a | 802 | CT | Northeast Utilities |  | 2015 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | 218000000 | 218000000
Reliability Upgrade | 1a | 1085 | CT | Northeast Utilities |  | 2015 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | CT | Northeast Utilities |  | 2015 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | CT | Northeast Utilities |  | 2015 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1235 | CT | Northeast Utilities |  | 12/2015 | NEEWS (Ancillary Interstate Reliability Project) | Sag elimination on 1410 Line (Montville-Buddington) | Planned | 3000000 | 3000000
Reliability Upgrade | 1a | 1245 | CT | CMEEC |  | 12/2015 | NEEWS (Ancillary Interstate Reliability Project) | Sag elimination on 1410 Line (Montville-Buddington) | Planned | 60000 | 60000
Reliability Upgrade | 1a | 1227 | CT | Northeast Utilities |  | 2012 | LSP - Stamford Area | Add 4th transformer and build a five breaker ring bus at South End Substation | Planned | 6400000 | 6400000
Reliability Upgrade | 1a | 1056 | CT | Northeast Utilities |  | 12/2011 | LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Under Construction | 10969000 | 10969000
Reliability Upgrade | 1a | 1218 | CT | Northeast Utilities |  | 12/2013 | Millstone 345kV Circuit Separation project & SLOD SPS System Retirement | Separate the 345kV Double Circuit Tower 310/348 and 371/383 Tower configuration | Planned | 25600000 | 25600000
Reliability Upgrade | 1a | 1111 | CT | United Illuminating Company |  | 01/2012 |  | Union Avenue 115/26.4 kV Substation | Under Construction | 13500000 | 13500000
Reliability Upgrade | 1a | 976 | CT | United Illuminating Company |  | 05/2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Under Construction | 70000000 | 70000000
Reliability Upgrade | 1a | 721 | CT | United Illuminating Company |  | 06/2015 |  | New Shelton 115/13.8 kV substation | Planned | 19500000 | 19500000
Reliability Upgrade | 1a | 879 | CT | Bangor Hydro-Electric Company |  | TBD | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | 420000 | 420000
Reliability Upgrade | 1a | 1050 | CT | United Illuminating Company |  | 12/2011 |  | Devon Tie 115kV Switching Station BPS Compliance | Under Construction | 4000000 | 4000000
Reliability Upgrade | 1b | 1031 | ME | Bangor Hydro-Electric Company |  | 12/2013 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station | Concept | TBD | TBD
Reliability Upgrade | 1b | 1154 | ME | Bangor Hydro-Electric Company |  | 12/2013 | Maine Power Reliability Program (MPRP) | Rerate Line 66 | Concept | TBD | TBD
Reliability Upgrade | 1b | 1155 | ME | Bangor Hydro-Electric Company |  | 12/2014 | Maine Power Reliability Program (MPRP) | Capacitor Bank Addition (10 MVAr at Trenton 34.5kV and Epping) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1133 | ME | Central Maine Power Company |  | 12/2011 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation and new 34kV line from Leeds to Turner | Proposed | 300000 | 300000
Reliability Upgrade | 1b | 1279 | ME | Central Maine Power Company |  | 12/2014 |  | New 345/115kV Autotransformer and 115kV switchyard at Raven Farm substation consisting of a four-bay breaker and a half configuration of eleven (11) breakers | Proposed | 26126000 | 26126000
Reliability Upgrade | 1b | 1280 | ME | Central Maine Power Company |  | 12/2014 |  | New 115kV line section 244 and upgraded line section 80 between Coopers Mill and Highland Substations | Proposed | 62735000 | 62735000
Reliability Upgrade | 1b | 1183 | NH | Northeast Utilities |  | 2014 | LSP New Peaselee Substation and 115/34.5KV transformer | New 115kV Peaselee Substation and transmission line work | Proposed | 12400000 | 12400000
Reliability Upgrade | 1b | 1220 | NH | Northeast Utilities |  | 12/2015 | Greater Boston - North | Install a new 345kV circuit between Scobie and Pelham NH (this is NU's portion of the new Scobie-Tewksbury circuit) | Proposed | 40100000 | 40100000
Reliability Upgrade | 1b | 1269 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Amherst Substation - New 345kV breaker and three 25MVar Capacitor Banks | Proposed | 19600000 | 19600000
Reliability Upgrade | 1b | 1270 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | New 115kV line from Fitzwilliiams to Monadnock | Proposed | 10500000 | 10500000
Reliability Upgrade | 1b | 1271 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Upgrade the Keene to Monadnock (T198) 115kV line | Proposed | 11900000 | 11900000
Reliability Upgrade | 1b | 1272 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Weare Substation - Add two 13.3 MVar 115V capacitors | Proposed | 3600000 | 3600000
Reliability Upgrade | 1b | 1273 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Rebuild A152 115kV line | Proposed | 22500000 | 22500000
Reliability Upgrade | 1b | 1274 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Rebuild N186 115kV line | Proposed | 2300000 | 2300000
Reliability Upgrade | 1b | 1275 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Upgrade the 381 345kV line | Proposed | 4200000 | 4200000
Reliability Upgrade | 1b | 1276 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Littleton Substation - Add a second 230/115kV autotransformer and associated 115kV substation work | Proposed | 16700000 | 16700000
Reliability Upgrade | 1b | 1277 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Webster Substation - Add four 26.6 MVar 115kV capacitors | Proposed | 11900000 | 11900000
Reliability Upgrade | 1b | 1278 | NH | Northeast Utilities |  | TBD | Western New Hampshire Solution | Saco Valley Substation - Add two 25 MVar dynamic Var devices | Proposed | 15800000 | 15800000
Reliability Upgrade | 1b | 1263 | NH | National Grid, USA |  | TBD | Northern New Hsmpshire Solution | New C-203 230kV line tap to Littleton NH Substation associated with 2nd 230/115kV auto project | Proposed | 1100000 | 1100000
Reliability Upgrade | 1b | 325 | VT | Vermont Electric Power Company |  | TBD | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | TBD | TBD
Reliability Upgrade | 1b | 324 | VT | Vermont Electric Power Company |  | TBD |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | TBD | TBD
Reliability Upgrade | 1b | 139 | VT | Vermont Electric Power Company |  | TBD | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Concept | TBD | TBD
Reliability Upgrade | 1b | 1250 | VT | Vermont Electric Power Company |  | 2016 | VELCO LSP - West Rutland Substation | Installation of a 115/46kV transformer at West Rutland between breakers K30 and K34 | Concept | TBD | TBD
Reliability Upgrade | 1b | 843 | MA | NSTAR Electric Company |  | 06/2012 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Proposed | 3450000 | 3450000
Reliability Upgrade | 1b | 593 | MA | NSTAR Electric Company |  | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Bourne and Barnstable/Falmouth/equivalent | Concept | TBD | TBD
Reliability Upgrade | 1b | 965 | MA | NSTAR Electric Company |  | 06/2014 | Greater Boston - South | Add third 115kV line from W. Walpole to Holbrook | Proposed | 19000000 | 19000000
Reliability Upgrade | 1b | 1175 | MA | NSTAR Electric Company |  | 12/2013 | Greater Boston - South | Upgrade the 115kV line 201-501 (Medway-Depot St.) and the 201-502 (Beaver Pond - Depot Street Tap) to a higher capacity line | Proposed | 3700000 | 3700000
Reliability Upgrade | 1b | 1214 | MA | National Grid, USA |  | 12/2015 | Greater Boston - South | Line Reconductoring of the C-129 Beaver Pond - Depot St. Tap) and D-130 (Depot St. Tap - Medway) 115kV lines | Proposed | 500000 | 500000
Reliability Upgrade | 1b | 1177 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - North | Reconductor 211-503/504 from North Woburn Tap to Reading | Concept | TBD | TBD
Reliability Upgrade | 1b | 1178 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - North | Install 115kV Capacitor Bank at North Woburn | Concept | TBD | TBD
Reliability Upgrade | 1b | 1179 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - North | Install 2nd 345kV circuit between Bellerica/Burlington town line to Tewksbury | Proposed | 33000000 | 33000000
Reliability Upgrade | 1b | 1190 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - North | Install a second 345/115kV Auto Transformer at Woburn | Concept | TBD | TBD
Reliability Upgrade | 1b | 1200 | MA | NSTAR Electric Company |  | TBD | Greater Boston - North | Add a new 345kV UG circuit between Woburn and North Cambridge | Proposed | 52000000 | 52000000
Reliability Upgrade | 1b | 1211 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | Install 2nd 345kV circuit between Tewksbury - Billerica/Burlington Town Line (NSTAR Border) | Proposed | 32700000 | 32700000
Reliability Upgrade | 1b | 1212 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | 115kV Line Reconductoring of M-139/N-140 Tewksbury-Pinehurst (6.1 miles each) | Proposed | 11600000 | 11600000
Reliability Upgrade | 1b | 1213 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | Install new 345kV circuit between NH/MA border and Tewksbury (this is NGRID's portion of the new Scobie-Tewksbury circuit) | Proposed | 23370000 | 23370000
Reliability Upgrade | 1b | 1215 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | New 115kV line between Wakefield - Everett | Proposed | 20000000 | 20000000
Reliability Upgrade | 1b | 1254 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | Substation work at Revere Substation to increase ratings on the 128-515P/168 line between Chelsea and Revere | Proposed | 1000000 | 1000000
Reliability Upgrade | 1b | 1260 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | 115kV Line reconductoring of the F-158N/S Wakefield Jct - Everett (7.36 miles) | Proposed | 3500000 | 3500000
Reliability Upgrade | 1b | 1261 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | 115kV Line reconductoring of the S-145T-146 from North Reading Tap - Wakefield Jct (5.1 miles each) | Proposed | 10800000 | 10800000
Reliability Upgrade | 1b | 1262 | MA | National Grid, USA |  | 12/2015 | Greater Boston - North | 115kV Line reconductoring of theY-151 from Tewksbury Junction - Tewksbury Substation (1.6 miles) | Proposed | 1250000 | 1250000
Reliability Upgrade | 1b | 970 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Add a new 345 kV line from Lexington to Waltham. | Concept | TBD | TBD
Reliability Upgrade | 1b | 971 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | TBD | TBD
Reliability Upgrade | 1b | 1176 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Install an oil circulation pipe and heat exchangers at K Street and Chatham Street sections of 250-516/517 circuits | Concept | TBD | TBD
Reliability Upgrade | 1b | 1189 | MA | NSTAR Electric Company |  | 12/2015 | Greater Boston - Central | Install 3rd 115kV Circuit between Waltham and Brighton | Concept | TBD | TBD
Reliability Upgrade | 1b | 1198 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Add a second 115kV line from Woburn to Burlington | Concept | TBD | TBD
Reliability Upgrade | 1b | 1199 | MA | NSTAR Electric Company |  | TBD | Greater Boston - Central | Install a new 230/115kV auto transformer at Sudbury or equivalent | Concept | TBD | TBD
Reliability Upgrade | 1b | 1208 | MA | National Grid, USA |  | 12/2014 | Pittsfield / Greenfield Project | Separation and reconductoring of Cabot Taps (A-127 and Y-177 115kV lines) | Proposed | 7400000 | 7400000
Reliability Upgrade | 1b | 1209 | MA | National Grid, USA |  | 12/2014 | Pittsfield / Greenfield Project | Reconductoring of A-127 between Erving and Cabot Tap with 1590 ACSS | Proposed | 12000000 | 12000000
Reliability Upgrade | 1b | 1210 | MA | National Grid, USA |  | 12/2014 | Pittsfield / Greenfield Project | Harriman 115kV breaker upgrades | Proposed | 1100000 | 1100000
Reliability Upgrade | 1b | 1221 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Modify Northfield Mountain 16R substation and install a 345/115Kv autotransformer | Proposed | 108500000 | 108500000
Reliability Upgrade | 1b | 1222 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Build a new 115kV three breaker Swithching Station (Erving) ring bus | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1223 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Build a new 115kV line from Northfield Mountain to the new Erving Switching Station | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1224 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Install 115kV 14.4 MVAR capacitor banks at Cumberland, Podick and Amherst Substations | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1225 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Rebuild the Cumberland to Montague 1361 115kV line and terminal work at Cumberland and Montague | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1226 | MA | Northeast Utilities |  | 11/2014 | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 956 | MA | National Grid, USA |  | 01/2015 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Proposed | 7021534 | 7021534
Reliability Upgrade | 1b | 1252 | MA | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | Re-conductor 345kV 328 line (West Farnum-Sherman Rd) | Proposed | 36500000 | 36500000
Reliability Upgrade | 1b | 1191 | MA | NSTAR Electric Company |  | 12/2012 |  | Rebuild Section of Line 322 (Canal-Carver) | Concept | 12200000 | 12200000
Reliability Upgrade | 1b | 1181 | MA | NSTAR Electric Company |  | 12/2013 |  | Rebuild the High Hill 115kV Substation to a Breaker and a half desgin | Concept | TBD | TBD
Reliability Upgrade | 1b | 1204 | MA | NSTAR Electric Company |  | 06/2012 |  | Rebuild the Mashpee Substation to a Ring Bus and install an overvoltage trip relay on the Mashpee 115kV Capacitor Bank | Concept | TBD | TBD
Reliability Upgrade | 1b | 1205 | MA | NSTAR Electric Company |  | 12/2013 | Mid-Cape Reliability Project | Separate 120 (Canal-Barnstable) /122 (Oak St-Barnstable) DCT | Concept | TBD | TBD
Reliability Upgrade | 1b | 1206 | MA | NSTAR Electric Company |  | 12/2011 |  | Install a new 230kV breaker for line 282-602 (West Medway-Waltham) at W. Medway for system resoration | Concept | TBD | TBD
Reliability Upgrade | 1b | 1247 | MA | NSTAR Electric Company |  | TBD |  | Rebuild the Acushnet 115kV Substation | Concept | TBD | TBD
Reliability Upgrade | 1b | 1248 | MA | NSTAR Electric Company |  | 12/2014 |  | Rebuild the Kingston Substation to a breaker and a half scheme | Concept | TBD | TBD
Reliability Upgrade | 1b | 1249 | MA | NSTAR Electric Company |  | 12/2013 |  | Rebuild the Wareham Substation to a breaker and a half scheme | Concept | TBD | TBD
Reliability Upgrade | 1b | 1207 | MA | NSTAR Electric Company |  | 2012 | Belmont Transmission Interconnection | Build a new 115kV Substation for the Belmont Transmission Interconnection | Concept | TBD | TBD
Reliability Upgrade | 1b | 1255 | MA | CELD (Chicopee Electric Light Department) |  | 12/2013 | CELD 115/13.8kV Substation | 115/13.8kV substation on Memorial Dr. with two transformers and twelve feeders looped into 1904 (1723) line between Piper and Fairmont substations | Concept | TBD | TBD
Reliability Upgrade | 1b | 1233 | RI | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | New Sherman Road 345kV AIS Substation | Proposed | 36600000 | 36600000
Reliability Upgrade | 1b | 1234 | RI | National Grid, USA |  | 12/2015 | NEEWS (Interstate Reliability Project) | Install a 115kV redundant breaker in series with breaker #1713 at West Farmum Substation and upgrade to current BPS standards | Concept | TBD | TBD
Reliability Upgrade | 1b | 1084 | CT | Northeast Utilities |  | TBD | Greater Hartford Central Connecticut Project | Loop the Millstone - Manchester (310) 345 kV line into the Card substation (2) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1086 | CT | Northeast Utilities |  | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow (2) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1087 | CT | Northeast Utilities |  | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford (2) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1088 | CT | Northeast Utilities |  | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow (2) | Concept | TBD | TBD
Reliability Upgrade | 1b | 975 | CT | United Illuminating Company |  | 06/2015 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | 105000000 | 105000000
Reliability Upgrade | 1b | 699 | CT | United Illuminating Company |  | 12/2014 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | 11100000 | 11100000
Reliability Upgrade | 1b | 801 | CT | Northeast Utilities |  | TBD |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Concept | TBD | TBD
Reliability Upgrade | 1b | 85 | CT | Northeast Utilities |  | TBD |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | TBD | TBD
Reliability Upgrade | 1b | 1228 | CT | Northeast Utilities |  | TBD | Stamford Area | Additional circuit into the Stamford Area (Glenbrook-South End) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1229 | CT | Northeast Utilities |  | TBD |  | Replace 115kV 1990 (Frost Bridge-Stevenson) lattice structure | Concept | TBD | TBD
Reliability Upgrade | 1b | 1230 | CT | Northeast Utilities |  | TBD | LSP - Greater Hartford Area | 115kV breaker addition at Northeast Simsbury Substation | Concept | TBD | TBD
Reliability Upgrade | 1b | 1242 | CT | CMEEC |  | 10/2012 | SNEW 115kV substation | SNEW 115/13.8kV substation with two transformers and a 115kV circuit breaker looped into the 1890 line (between Norwalk Hbr - Ely Ave) | Proposed | 2000000 | 2000000
Reliability Upgrade | 1b | 1243 | CT | CMEEC |  | 10/2013 | TTD's Fitch St 115kV Substation | TTD 115/27kV substation with two transformers and a 115kV circuit breaker looped into 1416 line (between Compo and Darien substations) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1244 | CT | CMEEC |  | 10/2011 | 115kV Circuit Breaker Installation | Install 115kV Bus Tie Circuit Breaker at Stock House Rd Substation | Proposed | 750000 | 750000
Reliability Upgrade | 1b | 1246 | CT | United Illuminating Company |  | 09/2013 | 8300 Line Reconfiguration Project | Reconfiguration of 115kV (8300) line from Mill River to Quinnipiac | Proposed | 17400000 | 17400000
IN-SERVICE PROJECTS | [10 empty] | 5460853715
Reliability Upgrade | 1a | 582 | CT | Northeast Utilities | 2011 | 06/2011 |  | Separate 310(Manchester-Millstone) and 368 (Manchester-Card) 345-KV lines and create 368/1767 DCT | In-service | 11350000 | 11350000
Reliability Upgrade | 1a | 1147 | CT | Northeast Utilities | 2011 | 07/2011 |  | Waterside Substation - install a three-breaker 115kV ring bus | In-service | 4616000 | 4616000
Reliability Upgrade | 1a | 1151 | CT | United Illuminating Company | 2011 | 06/2011 |  | West River 115kV Switching Station Fault Duty Mitigation | In-service | 2900000 | 2900000
Reliability Upgrade | 1a | 799 | RI | National Grid, USA | 2011 | 07/2011 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | In-service | 4500000 | 4500000
Reliability Upgrade | 1a | 1264 | RI | National Grid, USA | 2011 | 06/2011 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | In-service | Part of RSP 1105 | Part of RSP 1105
Reliability Upgrade | 1a | 924 | MA | National Grid, USA | 2011 | 07/2011 | Central/Western Massachusetts Upgrades | Carpenter Hill - Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | In-service | 4200000 | 4200000
Reliability Upgrade | 1a | 1137 | NH | Northeast Utilities | 2011 | 04/2011 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115kV breakers and add 1-115kV breaker at Deerfield Substation | In-service | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1143 | NH | Northeast Utilities | 2011 | 06/2011 |  | Littleton 115kV breaker addition and reconfiguration | In-service | 7011000 | 7011000
Reliability Upgrade | 1a | 624 | ME | Central Maine Power Company | 2011 | 07/2011 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (Rumford Industrial Park - Rumford) | In-service | Part of project 625 | Part of project 625
34577000

## Sorted by ISDthenStatus Nov11 (hidden)
November 2011 ISO-NEW ENGLAND Project Listing Update (DRAFT)(7)
Primary Driver | Part# | Project ID | Primary Equipment Owner |  | Projected In-Service Month/Year | Major Project | Project | Nov-11 Status | Nov-11 Estimated PTF Costs
Reliability Upgrade | 1b | 1206 | NSTAR Electric Company | 2011 | 12/2011 |  | Install a new 230kV breaker for line 282-602 (West Medway-Waltham) at W. Medway for system resoration | Concept | TBD | TBD
Reliability Upgrade | 1a | 1171 | Vermont Electric Power Company | 2011 | 12/2011 | West Rutland Capacitor Rebuild | Install two 115kV 25 MVAr capacitor banks at West Rutland to address low voltage concerns | Planned | 2400000 | 2400000
Reliability Upgrade | 1a | 798 | National Grid, USA | 2011 | 12/2011 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Planned | 600000 | 600000
Reliability Upgrade | 1b | 1133 | Central Maine Power Company | 2011 | 12/2011 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation and new 34kV line from Leeds to Turner | Proposed | 300000 | 300000
Reliability Upgrade | 1b | 1244 | CMEEC | 2011 | 10/2011 | 115kV Circuit Breaker Installation | Install 115kV Bus Tie Circuit Breaker at Stock House Rd Substation | Proposed | 750000 | 750000
Reliability Upgrade | 1a | 1116 | Bangor Hydro-Electric Company | 2011 | 12/2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Under Construction | 37626000 | 37626000
Reliability Upgrade | 1a | 1156 | Bangor Hydro-Electric Company | 2011 | 12/2011 | Maine Power Reliability Program (MPRP) | Orrington Shunt Cap Reconfiguration | Under Construction | 2260262 | 2260262
Reliability Upgrade | 1a | 1131 | Central Maine Power Company | 2011 | 11/2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Under Construction | 600000 | 600000
Reliability Upgrade | 1a | 1219 | Northeast Utilities | 2011 | 12/2011 |  | Install 115kV two 13.3 MVAR capacitor banks at Oak Hill substation | Under Construction | 4000000 | 4000000
Reliability Upgrade | 1a | 277 | Northeast Utilities | 2011 | 11/2011 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Under Construction | 52000000 | 52000000
Reliability Upgrade | 1a | 1140 | Northeast Utilities | 2011 | 10/2011 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | Under Construction | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1165 | NSTAR Electric Company | 2011 | 12/2011 | Mystic Breaker Additions Project | Move Transformer 110B Connection at Mystic | Under Construction | 2600000 | 2600000
Reliability Upgrade | 1a | 1076 | Northeast Utilities | 2011 | 12/2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Under Construction | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1109 | National Grid, USA | 2011 | 12/2011 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Under Construction | 1000000 | 1000000
Reliability Upgrade | 1a | 790 | National Grid, USA | 2011 | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Under Construction | 52000000 | 52000000
Reliability Upgrade | 1a | 1098 | National Grid, USA | 2011 | 12/2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Under Construction | 22000000 | 22000000
Reliability Upgrade | 1a | 1266 | Northeast Utilities | 2011 | 12/2011 |  | 115kV Pleasant to Blandford (portion of 1421) Line structure replacement | Under Construction | 9960000 | 9960000
Reliability Upgrade | 1a | 1267 | Northeast Utilities | 2011 | 12/2011 |  | 115kV Blandford to Southwick (portion of 1512) Line structure replacement | Under Construction | 9600000 | 9600000
Reliability Upgrade | 1a | 301 | NSTAR Electric Company | 2011 | 12/2011 | Greater Boston - Central | Reconductor 115-kV circuits 320-507 and 320-508. (Lexington - Waltham) | Under Construction | 9600000 | 9600000 | 1-2011 Concept
Reliability Upgrade | 1a | 1066 | NSTAR Electric Company | 2011 | 12/2011 | NPCC BPS Compliance | Needham Station | Under Construction | 8000000 | 8000000 | 2-2011 Planned
Reliability Upgrade | 1a | 484 | National Grid, USA | 2011 | 11/2011 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Under Construction | 580000 | 580000 | 2-2011 Proposed
Reliability Upgrade | 1a | 1056 | Northeast Utilities | 2011 | 12/2011 | LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Under Construction | 10969000 | 10969000 | 18-2011 UnderConstruct
Reliability Upgrade | 1a | 1050 | United Illuminating Company | 2011 | 12/2011 |  | Devon Tie 115kV Switching Station BPS Compliance | Under Construction | 4000000 | 4000000
Reliability Upgrade | 1b | 1191 | NSTAR Electric Company | 2012 | 12/2012 |  | Rebuild Section of Line 322 (Canal-Carver) | Concept | 12200000 | 12200000
Reliability Upgrade | 1b | 1204 | NSTAR Electric Company | 2012 | 06/2012 |  | Rebuild the Mashpee Substation to a Ring Bus and install an overvoltage trip relay on the Mashpee 115kV Capacitor Bank | Concept | TBD | TBD
Reliability Upgrade | 1b | 1207 | NSTAR Electric Company | 2012 | 2012 | Belmont Transmission Interconnection | Build a new 115kV Substation for the Belmont Transmission Interconnection | Concept | TBD | TBD
Reliability Upgrade | 1a | 1129 | Central Maine Power Company | 2012 | 05/2012 |  | New 115kV line between Wyman Hydro and Rice Rips Tap, parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | 32800000 | 32800000
Reliability Upgrade | 1a | 1135 | Central Maine Power Company | 2012 | 02/2012 | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer | Planned | 1500000 | 1500000
Reliability Upgrade | 1a | 1184 | Central Maine Power Company | 2012 | 05/2012 | Starks Switching Station | Add 4-115kV circuit breakers in a breaker-and a-half configuration on Section 63 and 2-18 MVAr cap banks at a new Starks Switching Station | Planned | 9750000 | 9750000
Reliability Upgrade | 1a | 1251 | Central Maine Power Company | 2012 | 12/2012 | Lakewood Substation Expansion | Sectionalize Section 241 by adding four 115kV circuit breakers at Lakewood Substation and install a second 115/34.5 kV transformer | Planned | 13700000 | 13700000
Reliability Upgrade | 1a | 1172 | Vermont Electric Power Company | 2012 | 06/2012 | Vermont Shunt Reactors | Install 345kV 60 MVAr shunt reactors (two at Coolidge and one at New Haven and relocate the New Haven reactor to Vernon) to address high voltage concerns | Planned | 20000000 | 20000000
Reliability Upgrade | 1a | 318 | Vermont Electric Power Company | 2012 | 12/2012 | Georgia Substation Rebuild | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems due to breaker failure contingencies | Planned | 16000000 | 16000000
Reliability Upgrade | 1a | 1169 | Vermont Electric Power Company | 2012 | 12/2012 | Ascutney Substation Rebuild | Rebuild the existing Ascutney substation 115kV bus into a ring bus, to address reliability problems due to breaker failure contingencies | Planned | 14500000 | 14500000
Reliability Upgrade | 1a | 1194 | Vermont Electric Power Company | 2012 | 12/2012 | LSP Jay Substation | Construct a new 4-breaker ring substation at Jay with two 115/46kV transformers | Planned | 6500000 | 6500000
Reliability Upgrade | 1a | 921 | National Grid, USA | 2012 | 12/2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | 40000000 | 40000000
Reliability Upgrade | 1a | 59 | National Grid, USA | 2012 | 12/2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | Part of RSP 921 | Part of RSP 921
Reliability Upgrade | 1a | 840 | NSTAR Electric Company | 2012 | 12/2012 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | 5900000 | 5900000
Reliability Upgrade | 1a | 776 | National Grid, USA | 2012 | 11/2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | 3125000 | 3125000
Reliability Upgrade | 1a | 1068 | NSTAR Electric Company | 2012 | 12/2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to vicinity of Bourne and connect to existing #120 line and install a 345KV - 115kV auto-transformer at new substation about 3 miles west of the Barnstable Substation Loop Line #115 in and out of the new Substation. Create a new line position at the Bourne Substation and connect the Bourne-Canal section of Line #120 | Planned | 106500000 | 106500000
Reliability Upgrade | 1a | 592 | NSTAR Electric Company | 2012 | 12/2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing. The lines being separated are 322 (Canal-Carver) and 342 (Canal-Pilgrim-Auburn) | Planned | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1a | 1118 | National Grid, USA | 2012 | 12/2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 (Bellrock-High Hill) | Planned | 6000000 | 6000000
Reliability Upgrade | 1a | 942 | National Grid, USA | 2012 | 12/2012 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | 3650000 | 3650000
Reliability Upgrade | 1a | 925 | National Grid, USA | 2012 | 11/2012 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | Part of RSP 926 | Part of RSP 926
Reliability Upgrade | 1a | 926 | National Grid, USA | 2012 | 11/2012 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | 14700000 | 14700000
Reliability Upgrade | 1a | 932 | National Grid, USA | 2012 | 11/2012 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | Part of RSP 926 | Part of RSP 926
Reliability Upgrade | 1a | 943 | National Grid, USA | 2012 | 12/2012 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | 4100000 | 4100000
Reliability Upgrade | 1a | 955 | National Grid, USA | 2012 | 10/2012 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | 13800000 | 13800000
Reliability Upgrade | 1a | 1217 | Northeast Utilities | 2012 | 12/2012 | Central/Western Massachusetts Upgrades | Subatation work at Ludlow (MA) and Scitico (CT) assoicaited with the new Hampden (MA) subsation project (Ngrid) | Planned | 3140000 | 3140000
Reliability Upgrade | 1a | 1268 | Northeast Utilities | 2012 | 12/2012 |  | 345kV Northfield Mountain to Berkshire (portion of 312) line structure replacements | Planned | 7900000 | 7900000
Reliability Upgrade | 1a | 673 | National Grid, USA | 2012 | 12/2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | National Grid, USA | 2012 | 12/2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Planned | 30000000 | 30000000
Reliability Upgrade | 1a | 1201 | NSTAR Electric Company | 2012 | 12/2012 | Greater Boston - North | 115kV line Reconductoring of the P168/128-518 Line between Chelsea and Revere (NSTAR Portion of the line) | Planned | 1500000 | 1500000
Reliability Upgrade | 1a | 1168 | Holyoke Gas & Electric | 2012 | 12/2012 | North Canal 44P | Loop the 1525 (Holyoke Fairmont South 115kV) line into the new North Canal 44P | Planned | 4100000 | 4100000
Reliability Upgrade | 1a | 1095 | National Grid, USA | 2012 | 12/2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | 73800000 | 73800000
Reliability Upgrade | 1a | 1106 | National Grid, USA | 2012 | 06/2012 | NEEWS (Rhode Island Reliability Project) | Kent County Substation Upgrades related to third 345/115 kV Autotransformer. | Planned | 26000000 | 26000000
Reliability Upgrade | 1a | 1096 | National Grid, USA | 2012 | 06/2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | 12000000 | 12000000
Reliability Upgrade | 1a | 1099 | National Grid, USA | 2012 | 06/2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | 6000000 | 6000000
Reliability Upgrade | 1a | 1227 | Northeast Utilities | 2012 | 2012 | LSP - Stamford Area | Add 4th transformer and build a five breaker ring bus at South End Substation | Planned | 6400000 | 6400000
Reliability Upgrade | 1b | 843 | NSTAR Electric Company | 2012 | 06/2012 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Proposed | 3450000 | 3450000
Reliability Upgrade | 1b | 1242 | CMEEC | 2012 | 10/2012 | SNEW 115kV substation | SNEW 115/13.8kV substation with two transformers and a 115kV circuit breaker looped into the 1890 line (between Norwalk Hbr - Ely Ave) | Proposed | 2000000 | 2000000
Reliability Upgrade | 1a | 143 | Bangor Hydro-Electric Company | 2012 | 12/2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation (2 new breakers) to Harrington Substation to Epping Substation (3 new breakers) | Under Construction | 66100000 | 66100000
Reliability Upgrade | 1a | 1182 | Northeast Utilities | 2012 | 06/2012 | LSP New Eagle Substation and 115/34.5KV transformer | New 115kV Eagle Substation connected to 115/34.5kV Thornton Substation | Under Construction | 22800000 | 22800000
Reliability Upgrade | 1a | 934 | National Grid, USA | 2012 | 12/2012 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Under Construction | Part of RSP 935 | Part of RSP 935
Reliability Upgrade | 1a | 935 | National Grid, USA | 2012 | 12/2012 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Under Construction | 10200000 | 10200000
Reliability Upgrade | 1a | 944 | National Grid, USA | 2012 | 03/2012 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Under Construction | 15700000 | 15700000
Reliability Upgrade | 1a | 1216 | Northeast Utilities | 2012 | 04/2012 |  | 345kV Ludlow - Northfield (portion of 354) Line Structure replacements | Under Construction | 25100000 | 25100000 | 3-2012 Concept
Reliability Upgrade | 1a | 969 | NSTAR Electric Company | 2012 | 11/2012 | Greater Boston - North | Add a new 115kV 36.7 MVAR capacitor bank at Chelsea. | Under Construction | 1500000 | 1500000 | 32-2012 Planned
Reliability Upgrade | 1a | 1065 | NSTAR Electric Company | 2012 | 07/2012 | NPCC BPS Compliance | Waltham Station | Under Construction | 14700000 | 14700000 | 2 -2012 Proposed
Reliability Upgrade | 1a | 1193 | United Illuminating Company | 2012 | 12/2012 |  | North Haven 115kV Capacitor Bank TRV Mitigation Project | Under Construction | 4900000 | 4900000 | 12 -2012 UnderConstruct
Reliability Upgrade | 1a | 1111 | United Illuminating Company | 2012 | 01/2012 |  | Union Avenue 115/26.4 kV Substation | Under Construction | 13500000 | 13500000
Reliability Upgrade | 1a | 976 | United Illuminating Company | 2012 | 05/2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Under Construction | 70000000 | 70000000
Reliability Upgrade | 1a | 1196 | Bangor Hydro-Electric Company | 2012 | 01/2012 | SVC Filter Upgrade (Part of Keene Rd Auto-transformer ID 144) | Upgrade of filter bank at Chester SVC facility | Under Construction | 3500000 | 3500000
Reliability Upgrade | 1b | 1031 | Bangor Hydro-Electric Company | 2013 | 12/2013 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station | Concept | TBD | TBD
Reliability Upgrade | 1b | 1154 | Bangor Hydro-Electric Company | 2013 | 12/2013 | Maine Power Reliability Program (MPRP) | Rerate Line 66 | Concept | TBD | TBD
Reliability Upgrade | 1b | 1155 | Bangor Hydro-Electric Company | 2013 | 12/2014 | Maine Power Reliability Program (MPRP) | Capacitor Bank Addition (10 MVAr at Trenton 34.5kV and Epping) | Concept | TBD | TBD
Reliability Upgrade | 1b | 593 | NSTAR Electric Company | 2013 | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Bourne and Barnstable/Falmouth/equivalent | Concept | TBD | TBD
Reliability Upgrade | 1b | 1181 | NSTAR Electric Company | 2013 | 12/2013 |  | Rebuild the High Hill 115kV Substation to a Breaker and a half desgin | Concept | TBD | TBD
Reliability Upgrade | 1b | 1205 | NSTAR Electric Company | 2013 | 12/2013 | Mid-Cape Reliability Project | Separate 120 (Canal-Barnstable) /122 (Oak St-Barnstable) DCT | Concept | TBD | TBD
Reliability Upgrade | 1b | 1249 | NSTAR Electric Company | 2013 | 12/2013 |  | Rebuild the Wareham Substation to a breaker and a half scheme | Concept | TBD | TBD
Reliability Upgrade | 1b | 1255 | CELD (Chicopee Electric Light Department) | 2013 | 12/2013 | CELD 115/13.8kV Substation | 115/13.8kV substation on Memorial Dr. with two transformers and twelve feeders looped into 1904 (1723) line between Piper and Fairmont substations | Concept | TBD | TBD
Reliability Upgrade | 1b | 1243 | CMEEC | 2013 | 10/2013 | TTD's Fitch St 115kV Substation | TTD 115/27kV substation with two transformers and a 115kV circuit breaker looped into 1416 line (between Compo and Darien substations) | Concept | TBD | TBD
Reliability Upgrade | 1a | 1197 | Bangor Hydro-Electric Company | 2013 | 12/2013 | Keene Rd Autotransformer | Orrington 345kV Series Breaker Addition | Planned | 1761250 | 1761250
Reliability Upgrade | 1a | 1026 | Central Maine Power Company | 2013 | 12/2013 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction associated with (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Elliot Switching Station) line work | Planned | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | 36000000
Reliability Upgrade | 1a | 1028 | Central Maine Power Company | 2013 | 12/2013 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | Portion of CMP $1.364 (billion) and portion of NU is $36.0M | Portion of CMP $1.364 (billion) and portion of NU is $36.0M
Reliability Upgrade | 1a | 1030 | Central Maine Power Company | 2013 | 11/2013 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Maguire Road) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 680 | National Grid, USA | 2013 | 06/2013 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | 7393000 | 7393000
Reliability Upgrade | 1a | 674 | National Grid, USA | 2013 | 12/2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | 19460000 | 19460000
Reliability Upgrade | 1a | 1170 | Vermont Electric Power Company | 2013 | 06/2013 | Bennington Substation Rebuild | Rebuild the exiting Bennington substation 115kV bus into a ring bus to address reliability problems due to breaker failure contingencies | Planned | 28000000 | 28000000
Reliability Upgrade | 1a | 1195 | Vermont Electric Power Company | 2013 | 03/2013 | Highgate Refurbishment | Replace Highgate controls and cooling system | Planned | 35600000 | 35600000
Reliability Upgrade | 1a | 929 | National Grid, USA | 2013 | 09/2013 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | 2500000 | 2500000
Reliability Upgrade | 1a | 931 | National Grid, USA | 2013 | 01/2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | 531481 | 531481
Reliability Upgrade | 1a | 928 | National Grid, USA | 2013 | 06/2013 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | 3400000 | 3400000
Reliability Upgrade | 1a | 938 | National Grid, USA | 2013 | 05/2013 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | 5430000 | 5430000
Reliability Upgrade | 1a | 941 | National Grid, USA | 2013 | 2013-08-01 | Central/Western Massachusetts Upgrades | Install new Z126 Millbury - Tower #510 115 kV line. | Planned | 13748000 | 13748000
Reliability Upgrade | 1a | 687 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | 718000000 | 718000000
Reliability Upgrade | 1a | 826 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1078 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1202 | NSTAR Electric Company | 2013 | 06/2013 | NEEWS (Ancillary Interstate Reliability Project) | Rebuild 1.2 mile length of line 336 with 2-900 ACSS conductor and replace 5, 345kV 2000 amp disconnect switches with 3000 amp switches at W. Medway station | Planned | 1700000 | 1700000
Reliability Upgrade | 1a | 1256 | Unitil | 2013 | 06/2013 | Flagg Pond Upgrades | At Flagg Pond Substation upgrade terminal equipment on the I-135N, I-135S, J-136N and J-136S 115kV lines and Zone 3 relay upgrades for the J-136N 115kV line. | Planned | 2750000 | 2750000
Reliability Upgrade | 1a | 795 | National Grid, USA | 2013 | 04/2013 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV (359) line. | Planned | 69000000 | 69000000
Reliability Upgrade | 1a | 1097 | National Grid, USA | 2013 | 01/2013 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County including S-175, T172N and T-172S with associated terminal equipment upgrade. | Planned | 129800000 | 129800000
Reliability Upgrade | 1a | 1241 | National Grid, USA | 2013 | 06/2013 |  | Re-condustor G-185S (Kent County - Davisville Tap) | Planned | 4200000 | 4200000
Reliability Upgrade | 1a | 1054 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Build a new 345 kV line from Manchester to Meekville Junction and re-terminate the 395 line at Meekville Junction | Planned | 28800000 | 28800000
Reliability Upgrade | 1a | 1218 | Northeast Utilities | 2013 | 12/2013 | Millstone 345kV Circuit Separation project & SLOD SPS System Retirement | Separate the 345kV Double Circuit Tower 310/348 and 371/383 Tower configuration | Planned | 25600000 | 25600000
Reliability Upgrade | 1b | 1175 | NSTAR Electric Company | 2013 | 12/2013 | Greater Boston - South | Upgrade the 115kV line 201-501 (Medway-Depot St.) and the 201-502 (Beaver Pond - Depot Street Tap) to a higher capacity line | Proposed | 3700000 | 3700000
Reliability Upgrade | 1b | 1246 | United Illuminating Company | 2013 | 09/2013 | 8300 Line Reconfiguration Project | Reconfiguration of 115kV (8300) line from Mill River to Quinnipiac | Proposed | 17400000 | 17400000
Reliability Upgrade | 1a | 887 | National Grid, USA | 2013 | 06/2013 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Under Construction | 58000000 | 58000000
Reliability Upgrade | 1a | 196 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct the 115kV line South Agawam to Southwick (1768) | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVar Capacitor additions | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | 9-2013 Concept
Reliability Upgrade | 1a | 1074 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project) | 27 - 2013 Planned
Reliability Upgrade | 1a | 1092 | Northeast Utilities | 2013 | 12/2013 | Agawam (BPS) | Upgrade the Agawam 115kV, Subtations to BPS standards together with other misc. subatation upgrades | Under Construction | 12100000 | 12100000 | 2 -2013 Proposed
Reliability Upgrade | 1a | 974 | United Illuminating Company | 2013 | 05/2013 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Under Construction | 16900000 | 16900000 | 24 -2013 UnderConstruct
Reliability Upgrade | 1a | 816 | Northeast Utilities | 2013 | 12/2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Under Construction | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1b | 1248 | NSTAR Electric Company | 2014 | 12/2014 |  | Rebuild the Kingston Substation to a breaker and a half scheme | Concept | TBD | TBD
Reliability Upgrade | 1b | 699 | United Illuminating Company | 2014 | 12/2014 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | 11100000 | 11100000
Reliability Upgrade | 1a | 907 | Central Maine Power Company | 2014 | 05/2014 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 203 (Detroit-Orrington), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | Central Maine Power Company | 2014 | 2014-08-02 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast forming Sections 86 & 266 | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | Central Maine Power Company | 2014 | 05/2014 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377, 115kV Bucksport 65/205) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1132 | Central Maine Power Company | 2014 | 2014-08-02 | Maine Power Reliability Program (MPRP) | Add 115/34kV transformer at Coopers Mills | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 919 | National Grid, USA | 2014 | 04/2014 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | 13600000 | 13600000
Reliability Upgrade | 1a | 1187 | National Grid, USA | 2014 | 06/2014 | A127/B128 Conductor Refurbishment | A127/B128 Conductor Refurbishment - Tower 510 to Harriman Substation, VT | Planned | 65000000 | 65000000
Reliability Upgrade | 1a | 940 | National Grid, USA | 2014 | 06/2014 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS (A127 West reconductoring. Tower 510 to Paxton, French King to French King). | Planned | 18000000 | 18000000
Reliability Upgrade | 1a | 945 | National Grid, USA | 2014 | 05/2014 | Central/Western Massachusetts Upgrades | Adams - install two new 115 kV breakers and replace two existing 115kV breakers | Planned | 5000000 | 5000000
Reliability Upgrade | 1a | 948 | National Grid, USA | 2014 | 05/2014 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | 13400000 | 13400000
Reliability Upgrade | 1a | 951 | National Grid, USA | 2014 | 01/2014 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon (H-134) 115 kV line. | Planned | 7455440 | 7455440
Reliability Upgrade | 1a | 791 | National Grid, USA | 2014 | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | 11560000 | 11560000
Reliability Upgrade | 1a | 913 | National Grid, USA | 2014 | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | 3250000 | 3250000
Reliability Upgrade | 1a | 914 | National Grid, USA | 2014 | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | 28150000 | 28150000
Reliability Upgrade | 1a | 917 | National Grid, USA | 2014 | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | 7000000 | 7000000
Reliability Upgrade | 1a | 793 | National Grid, USA | 2014 | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | 6400000 | 6400000
Reliability Upgrade | 1a | 1257 | National Grid, USA | 2014 | 06/2014 | Salem Harbor Retirement | 115kV line Reconductoring of the S-145/T-146 from Tewksbury-North Reading Tap (9.3 miles each) | Planned | 29000000 | 29000000
Reliability Upgrade | 1a | 1258 | National Grid, USA | 2014 | 06/2014 | Salem Harbor Retirement | 115kV line Reconductoring of the Y-151 from Tewksbury Junction - West Methuen (8.2 miles) | Planned | 11500000 | 11500000
Reliability Upgrade | 1a | 1259 | National Grid, USA | 2014 | 06/2014 | Salem Harbor Retirement | 115kV line Reconductoring of the B154/C-155N from King St Tap - South Danvers (14.5 miles each way) | Planned | 20000000 | 20000000
Reliability Upgrade | 1a | 915 | National Grid, USA | 2014 | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | National Grid, USA | 2014 | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | 11800000 | 11800000
Reliability Upgrade | 1a | 918 | National Grid, USA | 2014 | 12/2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | 3180000 | 3180000
Reliability Upgrade | 1b | 1279 | Central Maine Power Company | 2014 | 12/2014 |  | New 345/115kV Autotransformer and 115kV switchyard at Raven Farm substation consisting of a four-bay breaker and a half configuration of eleven (11) breakers | Proposed | 26126000 | 26126000
Reliability Upgrade | 1b | 1280 | Central Maine Power Company | 2014 | 12/2014 |  | New 115kV line section 244 and upgraded line section 80 between Coopers Mill and Highland Substations | Proposed | 62735000 | 62735000
Reliability Upgrade | 1b | 1183 | Northeast Utilities | 2014 | 2014 | LSP New Peaselee Substation and 115/34.5KV transformer | New 115kV Peaselee Substation and transmission line work | Proposed | 12400000 | 12400000
Reliability Upgrade | 1b | 965 | NSTAR Electric Company | 2014 | 06/2014 | Greater Boston - South | Add third 115kV line from W. Walpole to Holbrook | Proposed | 19000000 | 19000000
Reliability Upgrade | 1b | 1208 | National Grid, USA | 2014 | 12/2014 | Pittsfield / Greenfield Project | Separation and reconductoring of Cabot Taps (A-127 and Y-177 115kV lines) | Proposed | 7400000 | 7400000
Reliability Upgrade | 1b | 1209 | National Grid, USA | 2014 | 12/2014 | Pittsfield / Greenfield Project | Reconductoring of A-127 between Erving and Cabot Tap with 1590 ACSS | Proposed | 12000000 | 12000000
Reliability Upgrade | 1b | 1210 | National Grid, USA | 2014 | 12/2014 | Pittsfield / Greenfield Project | Harriman 115kV breaker upgrades | Proposed | 1100000 | 1100000
Reliability Upgrade | 1b | 1221 | Northeast Utilities | 2014 | 11/2014 | Pittsfield / Greenfield Project | Modify Northfield Mountain 16R substation and install a 345/115Kv autotransformer | Proposed | 108500000 | 108500000
Reliability Upgrade | 1b | 1222 | Northeast Utilities | 2014 | 11/2014 | Pittsfield / Greenfield Project | Build a new 115kV three breaker Swithching Station (Erving) ring bus | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1223 | Northeast Utilities | 2014 | 11/2014 | Pittsfield / Greenfield Project | Build a new 115kV line from Northfield Mountain to the new Erving Switching Station | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1224 | Northeast Utilities | 2014 | 11/2014 | Pittsfield / Greenfield Project | Install 115kV 14.4 MVAR capacitor banks at Cumberland, Podick and Amherst Substations | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1225 | Northeast Utilities | 2014 | 11/2014 | Pittsfield / Greenfield Project | Rebuild the Cumberland to Montague 1361 115kV line and terminal work at Cumberland and Montague | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project
Reliability Upgrade | 1b | 1226 | Northeast Utilities | 2014 | 11/2014 | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Proposed | Part of Pittsfield/Greenfield Project | Part of Pittsfield/Greenfield Project | 2-2014 Concept
Reliability Upgrade | 1a | 905 | Central Maine Power Company | 2014 | 2014-08-02 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Under Construction | 1364108000 | 1364108000 | 21 - 2014 Planned
Reliability Upgrade | 1a | 906 | Central Maine Power Company | 2014 | 05/2014 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Larrabee Road-Middle St,Middle St -Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Under Construction | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | 13 -2014 Proposed
Reliability Upgrade | 1a | 908 | Central Maine Power Company | 2014 | 07/2014 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road); Coopers Mills autotransforme replaces Maxcy's autotransformer | Under Construction | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program | 4 -2014 UnderConstruct
Reliability Upgrade | 1a | 1158 | Central Maine Power Company | 2014 | 07/2014 | Maine Power Reliability Program (MPRP) | Two 40 MVAR reactors at Albion Road, two 40 MVAR reactors at Larabee Road, two 40 MVAR at Coopers Mills | Under Construction | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1b | 1177 | NSTAR Electric Company | 2015 | 12/2015 | Greater Boston - North | Reconductor 211-503/504 from North Woburn Tap to Reading | Concept | TBD | TBD
Reliability Upgrade | 1b | 1178 | NSTAR Electric Company | 2015 | 12/2015 | Greater Boston - North | Install 115kV Capacitor Bank at North Woburn | Concept | TBD | TBD
Reliability Upgrade | 1b | 1190 | NSTAR Electric Company | 2015 | 12/2015 | Greater Boston - North | Install a second 345/115kV Auto Transformer at Woburn | Concept | TBD | TBD
Reliability Upgrade | 1b | 1189 | NSTAR Electric Company | 2015 | 12/2015 | Greater Boston - Central | Install 3rd 115kV Circuit between Waltham and Brighton | Concept | TBD | TBD
Reliability Upgrade | 1b | 1234 | National Grid, USA | 2015 | 12/2015 | NEEWS (Interstate Reliability Project) | Install a 115kV redundant breaker in series with breaker #1713 at West Farmum Substation and upgrade to current BPS standards | Concept | TBD | TBD
Reliability Upgrade | 1b | 975 | United Illuminating Company | 2015 | 06/2015 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | 105000000 | 105000000
Reliability Upgrade | 1a | 1141 | Northeast Utilities | 2015 | 2015 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 950 | National Grid, USA | 2015 | 02/2015 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | 1016897 | 1016897
Reliability Upgrade | 1a | 953 | National Grid, USA | 2015 | 02/2015 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | 10248067 | 10248067
Reliability Upgrade | 1a | 954 | National Grid, USA | 2015 | 02/2015 | Central/Western Massachusetts Upgrades | Westminster - install new 69kV breaker, including disconnect switches. | Planned | 903909 | 903909
Reliability Upgrade | 1a | 946 | National Grid, USA | 2015 | 04/2015 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer- Hampden to 115 kV. | Planned | 16000000 | 16000000
Reliability Upgrade | 1a | 949 | National Grid, USA | 2015 | 04/2015 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | 1600000 | 1600000
Reliability Upgrade | 1a | 937 | National Grid, USA | 2015 | 12/2015 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | 6602875 | 6602875
Reliability Upgrade | 1a | 1094 | National Grid, USA | 2015 | 12/2015 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | 25000000 | 25000000
Reliability Upgrade | 1a | 190 | National Grid, USA | 2015 | 12/2015 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | 81800000 | 81800000
Reliability Upgrade | 1a | 794 | National Grid, USA | 2015 | 12/2015 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | 71700000 | 71700000
Reliability Upgrade | 1a | 1253 | National Grid, USA | 2015 | 04/2015 |  | New Crandall St. Substation 115-13 kV substation addition | Planned | 3000000 | 3000000
Reliability Upgrade | 1a | 802 | Northeast Utilities | 2015 | 2015 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | 218000000 | 218000000
Reliability Upgrade | 1a | 1085 | Northeast Utilities | 2015 | 2015 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | Northeast Utilities | 2015 | 2015 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | Northeast Utilities | 2015 | 2015 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1235 | Northeast Utilities | 2015 | 12/2015 | NEEWS (Ancillary Interstate Reliability Project) | Sag elimination on 1410 Line (Montville-Buddington) | Planned | 3000000 | 3000000
Reliability Upgrade | 1a | 1245 | CMEEC | 2015 | 12/2015 | NEEWS (Ancillary Interstate Reliability Project) | Sag elimination on 1410 Line (Montville-Buddington) | Planned | 60000 | 60000
Reliability Upgrade | 1a | 721 | United Illuminating Company | 2015 | 06/2015 |  | New Shelton 115/13.8 kV substation | Planned | 19500000 | 19500000
Reliability Upgrade | 1b | 1220 | Northeast Utilities | 2015 | 12/2015 | Greater Boston - North | Install a new 345kV circuit between Scobie and Pelham NH (this is NU's portion of the new Scobie-Tewksbury circuit) | Proposed | 40100000 | 40100000
Reliability Upgrade | 1b | 1214 | National Grid, USA | 2015 | 12/2015 | Greater Boston - South | Line Reconductoring of the C-129 Beaver Pond - Depot St. Tap) and D-130 (Depot St. Tap - Medway) 115kV lines | Proposed | 500000 | 500000
Reliability Upgrade | 1b | 1179 | NSTAR Electric Company | 2015 | 12/2015 | Greater Boston - North | Install 2nd 345kV circuit between Bellerica/Burlington town line to Tewksbury | Proposed | 33000000 | 33000000
Reliability Upgrade | 1b | 1211 | National Grid, USA | 2015 | 12/2015 | Greater Boston - North | Install 2nd 345kV circuit between Tewksbury - Billerica/Burlington Town Line (NSTAR Border) | Proposed | 32700000 | 32700000
Reliability Upgrade | 1b | 1212 | National Grid, USA | 2015 | 12/2015 | Greater Boston - North | 115kV Line Reconductoring of M-139/N-140 Tewksbury-Pinehurst (6.1 miles each) | Proposed | 11600000 | 11600000
Reliability Upgrade | 1b | 1213 | National Grid, USA | 2015 | 12/2015 | Greater Boston - North | Install new 345kV circuit between NH/MA border and Tewksbury (this is NGRID's portion of the new Scobie-Tewksbury circuit) | Proposed | 23370000 | 23370000
Reliability Upgrade | 1b | 1215 | National Grid, USA | 2015 | 12/2015 | Greater Boston - North | New 115kV line between Wakefield - Everett | Proposed | 20000000 | 20000000
Reliability Upgrade | 1b | 1254 | National Grid, USA | 2015 | 12/2015 | Greater Boston - North | Substation work at Revere Substation to increase ratings on the 128-515P/168 line between Chelsea and Revere | Proposed | 1000000 | 1000000
Reliability Upgrade | 1b | 1260 | National Grid, USA | 2015 | 12/2015 | Greater Boston - North | 115kV Line reconductoring of the F-158N/S Wakefield Jct - Everett (7.36 miles) | Proposed | 3500000 | 3500000 | 6 -2015 Concept
Reliability Upgrade | 1b | 1261 | National Grid, USA | 2015 | 12/2015 | Greater Boston - North | 115kV Line reconductoring of the S-145T-146 from North Reading Tap - Wakefield Jct (5.1 miles each) | Proposed | 10800000 | 10800000 | 18 - 2015 Planned
Reliability Upgrade | 1b | 1262 | National Grid, USA | 2015 | 12/2015 | Greater Boston - North | 115kV Line reconductoring of theY-151 from Tewksbury Junction - Tewksbury Substation (1.6 miles) | Proposed | 1250000 | 1250000 | 14 -2015 Proposed
Reliability Upgrade | 1b | 956 | National Grid, USA | 2015 | 01/2015 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Proposed | 7021534 | 7021534 | 0 -2015 UnderConstruct
Reliability Upgrade | 1b | 1252 | National Grid, USA | 2015 | 12/2015 | NEEWS (Interstate Reliability Project) | Re-conductor 345kV 328 line (West Farnum-Sherman Rd) | Proposed | 36500000 | 36500000
Reliability Upgrade | 1b | 1233 | National Grid, USA | 2015 | 12/2015 | NEEWS (Interstate Reliability Project) | New Sherman Road 345kV AIS Substation | Proposed | 36600000 | 36600000 | 1 -2016 Concept
Reliability Upgrade | 1b | 1250 | Vermont Electric Power Company | 2016 | 2016 | VELCO LSP - West Rutland Substation | Installation of a 115/46kV transformer at West Rutland between breakers K30 and K34 | Concept | TBD | TBD | 3 - 2016 Planned
Reliability Upgrade | 1a | 782 | National Grid, USA | 2016 | 01/2016 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor and Railyard. | Planned | 43912000 | 43912000 | 0 -2016 Proposed
Reliability Upgrade | 1a | 576 | Northeast Utilities | 2016 | 2016 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | 301000000 | 301000000 | 0 -2016 UnderConstruct
Reliability Upgrade | 1a | 1114 | Northeast Utilities | 2016 | 2016 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1b | 325 | Vermont Electric Power Company | TBD | TBD | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | TBD | TBD
Reliability Upgrade | 1b | 324 | Vermont Electric Power Company | TBD | TBD |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | TBD | TBD
Reliability Upgrade | 1b | 139 | Vermont Electric Power Company | TBD | TBD | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Concept | TBD | TBD | 18 - Concept TBD
Reliability Upgrade | 1b | 970 | NSTAR Electric Company | TBD | TBD | Greater Boston - Central | Add a new 345 kV line from Lexington to Waltham. | Concept | TBD | TBD | 1- Planned TBD
Reliability Upgrade | 1b | 971 | NSTAR Electric Company | TBD | TBD | Greater Boston - Central | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | TBD | TBD | 12- Proposed TBD
Reliability Upgrade | 1b | 1176 | NSTAR Electric Company | TBD | TBD | Greater Boston - Central | Install an oil circulation pipe and heat exchangers at K Street and Chatham Street sections of 250-516/517 circuits | Concept | TBD | TBD
Reliability Upgrade | 1b | 1198 | NSTAR Electric Company | TBD | TBD | Greater Boston - Central | Add a second 115kV line from Woburn to Burlington | Concept | TBD | TBD
Reliability Upgrade | 1b | 1199 | NSTAR Electric Company | TBD | TBD | Greater Boston - Central | Install a new 230/115kV auto transformer at Sudbury or equivalent | Concept | TBD | TBD
Reliability Upgrade | 1b | 1247 | NSTAR Electric Company | TBD | TBD |  | Rebuild the Acushnet 115kV Substation | Concept | TBD | TBD
Reliability Upgrade | 1b | 1084 | Northeast Utilities | TBD | TBD | Greater Hartford Central Connecticut Project | Loop the Millstone - Manchester (310) 345 kV line into the Card substation (2) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1086 | Northeast Utilities | TBD | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow (2) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1087 | Northeast Utilities | TBD | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford (2) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1088 | Northeast Utilities | TBD | TBD | Greater Hartford Central Connecticut Project | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow (2) | Concept | TBD | TBD
Reliability Upgrade | 1b | 801 | Northeast Utilities | TBD | TBD |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Concept | TBD | TBD
Reliability Upgrade | 1b | 85 | Northeast Utilities | TBD | TBD |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | TBD | TBD
Reliability Upgrade | 1b | 1228 | Northeast Utilities | TBD | TBD | Stamford Area | Additional circuit into the Stamford Area (Glenbrook-South End) | Concept | TBD | TBD
Reliability Upgrade | 1b | 1229 | Northeast Utilities | TBD | TBD |  | Replace 115kV 1990 (Frost Bridge-Stevenson) lattice structure | Concept | TBD | TBD
Reliability Upgrade | 1b | 1230 | Northeast Utilities | TBD | TBD | LSP - Greater Hartford Area | 115kV breaker addition at Northeast Simsbury Substation | Concept | TBD | TBD
Reliability Upgrade | 1a | 879 | Bangor Hydro-Electric Company | TBD | TBD | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | 420000 | 420000
Reliability Upgrade | 1b | 1269 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | Amherst Substation - New 345kV breaker and three 25MVar Capacitor Banks | Proposed | 19600000 | 19600000
Reliability Upgrade | 1b | 1270 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | New 115kV line from Fitzwilliiams to Monadnock | Proposed | 10500000 | 10500000
Reliability Upgrade | 1b | 1271 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | Upgrade the Keene to Monadnock (T198) 115kV line | Proposed | 11900000 | 11900000
Reliability Upgrade | 1b | 1272 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | Weare Substation - Add two 13.3 MVar 115V capacitors | Proposed | 3600000 | 3600000
Reliability Upgrade | 1b | 1273 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | Rebuild A152 115kV line | Proposed | 22500000 | 22500000
Reliability Upgrade | 1b | 1274 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | Rebuild N186 115kV line | Proposed | 2300000 | 2300000
Reliability Upgrade | 1b | 1275 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | Upgrade the 381 345kV line | Proposed | 4200000 | 4200000
Reliability Upgrade | 1b | 1276 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | Littleton Substation - Add a second 230/115kV autotransformer and associated 115kV substation work | Proposed | 16700000 | 16700000
Reliability Upgrade | 1b | 1277 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | Webster Substation - Add four 26.6 MVar 115kV capacitors | Proposed | 11900000 | 11900000
Reliability Upgrade | 1b | 1278 | Northeast Utilities | TBD | TBD | Western New Hampshire Solution | Saco Valley Substation - Add two 25 MVar dynamic Var devices | Proposed | 15800000 | 15800000
Reliability Upgrade | 1b | 1263 | National Grid, USA | TBD | TBD | Northern New Hsmpshire Solution | New C-203 230kV line tap to Littleton NH Substation associated with 2nd 230/115kV auto project | Proposed | 1100000 | 1100000
Reliability Upgrade | 1b | 1200 | NSTAR Electric Company | TBD | TBD | Greater Boston - North | Add a new 345kV UG circuit between Woburn and North Cambridge | Proposed | 52000000 | 52000000
5460853715

## SORTED-ByISD-Then STATUS10-09-2 (hidden)
October '09 ISO-NEW ENGLAND Project Listing Update (DRAFT)
Primary Driver | Part# | Project ID | Primary Equipment Owner | Projected In-Service Month/Year | Projected In-Service Year | Major Project | Project | Oct -09 Status | Oct-09 Estimated PTF Costs
Data Set for Investment Chart by Status
[11 empty] | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | TBD
[10 empty] | In-Service | 2006: 493.8219; Data Set for Investment Chart by Status 2007: 326.52; Data Set for Investment Chart by Status 2008: 1912.1831; Data Set for Investment Chart by Status 2009: 800; Data Set for Investment Chart by Status 2010: 11.2
[10 empty] | Under Construction | Data Set for Investment Chart by Status 2010: 304.8332; Data Set for Investment Chart by Status 2011: 153.019
[10 empty] | Planned | Data Set for Investment Chart by Status 2010: 107.4322; Data Set for Investment Chart by Status 2011: 157.0976; Data Set for Investment Chart by Status 2012: 2468.4786; Data Set for Investment Chart by Status 2013: 1602.4638; Data Set for Investment Chart by Status 2014: 173.902; Data Set for Investment Chart by Status 2015: 20 | 0.42
[10 empty] | Proposed | Data Set for Investment Chart by Status 2010: 4.55; Data Set for Investment Chart by Status 2011: 50.426; Data Set for Investment Chart by Status 2012: 9.3 | 6.838
[10 empty] | Concept |  |  |  |  | 0.95 | 21.6 | 0 | 0 | 11.1 | 74.8015 |  | 1.33 | 1.2 | 0
[10 empty] | total |  |  | 1912.1831 | 800 | 428.9654 | 382.1426 | 2477.7786 | 1602.4638 | 185.002 | 94.8015 | 0 | 1.33 | 1.2 | 7.258
[13 empty] | NOTE- Total I/S costs as of Oct 2008 Update: |  |  | 1431150385
Data Set for Investment Chart - cumulative
[13 empty] | In-Service | UC+PL+PR | UC+PL+PR+C
[12 empty] | 2002 | 15.8
[12 empty] | 2009-10-09 | 3876.3238 | 3876.3238 | 3876.3238 | 131315 | 0.0059039
[12 empty] | 2009-12-09 | 3876.3238 | 3876.3238 | 3876.3238 | 131315 | 0.0059039
[12 empty] | 2010 | 3876.3238 | 4293.1392 | 4294.0892 | 131330 | 0.0065379
[12 empty] | 2011 | 3876.3238 | 4653.6818 | 4676.2318 | 132350 | 0.0070324
[12 empty] | 2012 | 3876.3238 | 7131.4603 | 7154.0103 | 134015 | 0.010643
[12 empty] | 2013 | 3876.3238 | 8733.9241 | 8756.4741 | 134635 | 0.012974
Reliability Upgrade | 1a | 910 | Central Maine Power Company | 12/2008 | 2008 | Rumford-Woodstock-Kimball Road Corridor Project | Rebuild Section 211 Woodstock - Rumford. | In-Service | 8400000 | 8400000
Reliability Upgrade | 1a | 177 | Northeast Utilities | 12/2008 | 2008 | Monadnock Area Reliability Project | Replace limiting terminal equipment at Webster Substation on line to North Road. | In-Service | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 180 | Northeast Utilities | 12/2008 | 2008 | Monadnock Area Reliability Project | Rebuild 115 kV Keene to Swanzey A-152 line. | In-Service | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 138 | Vermont Electric Power Company | 12/2008 | 2008 | Northwest Vermont Reliability Project | N. Haven - Vergennes - Q. City 115 kV line. | In-Service | 70200000 | 70200000
Reliability Upgrade | 1a | 923 | National Grid, USA | 12/2008 | 2008 | Auburn Area Transmission System Upgrades | Reconductor 115 kV A94 line and associated substation upgrades. | In-Service | 2400000 | 2400000
Reliability Upgrade | 1a | 781 | National Grid, USA | 10/2008 | 2008 | Merrimack Valley/North Shore Reliability Project | Install 115 kV 30 MVAr capacitor bank at Revere. | In-Service | 1727000 | 1727000
Reliability Upgrade | 1a | 841 | NSTAR Electric Company | 11/2008 | 2008 | Mystic Breaker Additions Project | Install (2) new 115 kV West Bus breakers #29 and #31 at Mystic. | In-Service | 2300000 | 2300000
Reliability Upgrade | 1a | 1040 | NSTAR Electric Company | 12/2008 | 2008 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #11, #8, #17 and #3 at Mystic to IPT | In-Service | 990000 | 990000
Reliability Upgrade | 1a | 168 | National Grid, USA | 09/2008 | 2008 | Southwest Rhode Island Reliability Enhancements | Reconductor Kenyon - Wood River 115 kV 1870 line. | In-Service | 2234232 | 2234232
Reliability Upgrade | 1a | 899 | National Grid, USA | 12/2008 | 2008 | Southwest Rhode Island Reliability Enhancements | Kenyon substation upgrades. | In-Service | 278000 | 278000
Reliability Upgrade | 1a | 171 | National Grid, USA | 10/2008 | 2008 | Southwest Rhode Island Reliability Enhancements | Reconductoring L-190 between Kent Co. and Davisville. | In-Service | 2666291 | 2666291
Reliability Upgrade | 1a | 900 | National Grid, USA | 11/2008 | 2008 | Southwest Rhode Island Reliability Enhancements | Wood River substation upgrades. | In-Service | 130000 | 130000
Reliability Upgrade | 1a | 846 | United Illuminating Company | 11/2008 | 2008 |  | Replace Mix Avenue 115 kV Oil Circuit Breaker & foundation. | In-Service | 450000 | 450000
Reliability Upgrade | 1a | 208 | Northeast Utilities | 12/2008 | 2008 | NU LSP - Oxford Substation | Install new Oxford (previously Jack's Hill) 115 kV substation. | In-Service | 4459000 | 4459000
Reliability Upgrade | 1a | 571 | Northeast Utilities | 12/2008 | 2008 | Norwalk-Glenbrook Cable Project | Upgrade Flax Hill Substation to BPS. | In-Service | Part of project 248 | Part of project 248
Reliability Upgrade | 1a | 248 | Northeast Utilities | 12/2008 | 2008 | Norwalk-Glenbrook Cable Project | Install two new 115 kV cables from Norwalk to Glenbrook (accommodate 345 kV class cable). | In-Service | 249372000 | 249372000
Reliability Upgrade | 1a | 246 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Add second 345/115 kV autotransformer at Norwalk Substation along with shunt reactors and 345 kV circuit breakers. | In-Service | 978182000 | 978182000
Reliability Upgrade | 1a | 238 | United Illuminating Company | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Build new Singer 345 kV substation with (12) circuit breakers, (2) autos, (4) shunt reactors along with reconnecting Bridgeport Energy thru one of the new autos. Includes 115 kV connection from Singer to Pequonnock substation. | In-Service | 162264000 | 162264000
Reliability Upgrade | 1a | 224 | United Illuminating Company | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install new 345 kV line from East Devon to Singer(UI). | In-Service | 157476000 | 157476000
Reliability Upgrade | 1a | 226 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install two 345 kV underground cables from Singer(UI) to Norwalk. | In-Service | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 235 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Expand Norwalk 345-kV substation and install transfer trip relaying scheme on the 1389 115 kV line between Norwalk and Flax Hill. | In-Service | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 247 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Replace Norwalk Harbor 138/115 kV autotransformer. | In-Service | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 684 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Replace (6) 115 kV breakers (4-Glenbrook, 1-Glenbrook Statcom, 1-Southington #1) and (3) 345-kV circuit breakers at Millstone and replace (4) 345- kV breakers with 500-kV breakers at Long Mountain substation. | In-Service | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 250 | Northeast Utilities | 12/2008 | 2008 |  | Add a 345 kV breaker at Ludlow Substation. | In-Service | 1644885 | 1644885
Reliability Upgrade | 1a | 155 | Central Maine Power Company | Northeast Utilities | 2009 | Maguire Road Project | Rebuild Three Rivers - Quaker Hill 115 kV Line K197. | In-Service | 5500000 | 5500000
Reliability Upgrade | 1a | 178 | Northeast Utilities | 02/2009 | 2009 | Monadnock Area Reliability Project | Rebuild 115 kV Garvins to Webster V-182 line. | In-Service | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 922 | National Grid, USA | 02/2009 | 2009 | Auburn Area Transmission System Upgrades | Reconductor 115kV L1 line and associated substation upgrades. | In-Service | 800000 | 800000
Reliability Upgrade | 1a | 116 | NSTAR Electric Company | 04/2009 | 2009 | NSTAR 345 kV Transmission Reliability Project | Add 2nd 345 kV UG Cables from Stoughton to Mattapan Sq.to K Street and install another new autotransformer at K. St. | In-Service | 307900000 | 307900000
Reliability Upgrade | 1a | 572 | NSTAR Electric Company | 04/2009 | 2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 345 kV 160 MVAR shunt reactors at Stoughton. | In-Service | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 573 | NSTAR Electric Company | 04/2009 | 2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 345 kV 160 MVAR shunt reactors at K St. | In-Service | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 772 | NSTAR Electric Company | 04/2009 | 2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 115 kV breaker at K St. | In-Service | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 136 | Vermont Electric Power Company | 04/2009 | 2009 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 1: two 115 kV PARs, four 25 MVAR Cap. banks, four +25/-12.5 MVAR synchronous condenders, and two 230/115 transformers. | In-Service | 62400000 | 62400000
Reliability Upgrade | 1a | 695 | NSTAR Electric Company | 07/2009 | 2009 | Short Term Lower SEMA Upgrades | Loop (355) 345 kV line in and out of Carver Substation and add (5) new 345 kV circuit breakers at Carver substation. | In-Service | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 830 | NSTAR Electric Company | 07/2009 | 2009 | Short Term Lower SEMA Upgrades | Add a second 345/115 kV Auto transformer at Carver substation and add (1) new 345 kV circuit breaker and (3) new 115 kV circuit breakers at Carver substation. | In-Service | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 831 | NSTAR Electric Company | 07/2009 | 2009 | Short Term Lower SEMA Upgrades | Add a second 115 kV line from Carver to Tremont and add (2) new 115 kV circuit breakers at Carver substation and (1) new 115 kV circuit breaker at Tremont substation. | In-Service | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 626 | Central Maine Power Company | 04/2009 |  | Rumford-Woodstock-Kimball Road Corridor Project | Addition of 115/34.5 kV transformer and six new 115 kV breakers and a half substation at Woodstock. | In-service | 8000000 | 8000000
Reliability Upgrade | 1a | 575 | Central Maine Power Company | 05/2009 |  | Heywood Road Project | New Heywood Rd 115kV switchyard with (6) 115kV circuit breakers (3) 115kV line retensionings and 115kV 20 MVAr capacitor bank at Heywood Rd. | In-service | 7000000 | 7000000
Reliability Upgrade | 1a | 1127 | Central Maine Power Company | 05/2009 |  | CMP-LSP Newcastle Substation | Add 115/34kV transformer with two 115kV breakers | In-service | 1300000 | 1300000
Reliability Upgrade | 1a | 166 | National Grid, USA | 06/2009 |  |  | Replace (16) 115 kV breakers at Tewksbury 22. | In-service | 3300000 | 3300000
Reliability Upgrade | 1a | 1009 | Northeast Utilities | 05/2009 |  |  | Install a 2% reactor on the North Bloomfield-Canton 115kV line and also replacement fo the Frostbridge 345/115kV autotransformer | In-service | 3089000 | 3089000
Reliability Upgrade | 1a | 203 | Northeast Utilities | 05/2009 |  | NU LSP - Stepstone Substation | Install new Stepstone 115 kV substation in Guilford. | In-service | 6332000 | 6332000
Reliability Upgrade | 1a | 1064 | NSTAR Electric Company | 04/2009 |  |  | Install (1) 345kV 160 MVAR shunt reactor at Mystic Station | In-service | 10400000 | 10400000
Reliability Upgrade | 1a | 1051 | Central Maine Power Company | 09/2009 |  | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Riley 115 kV capacitor bank. | In-service | Part of Project 625 | Part of Project 625
Reliability Upgrade | 1a | 267 | Northeast Utilities | 2009-08-01 |  | Y138 Closing | White Lake - Saco Valley (Y138) Line Closing - Add PAR on Y138 at Saco Valley, retension lines, upgrade Beebe terminal, and add capacitor banks at White Lake and Beebe. | In-service | 27775000 | 27775000
Reliability Upgrade | 1a | 936 | National Grid, USA | 07/2009 |  | Central/Western Massachusetts Upgrades | Reconductor (P142/P142S) Rolfe Avenue - West Bolyston 115 kV line w/1590 ACSR. | In-service | 3000000 | 3000000
Reliability Upgrade | 1a | 176 | Northeast Utilities | 07/2009 |  | Monadnock Area Reliability Project | New Fitzwilliam 345/115kV substation along with 345 kV breakers. | In-service | 76100000 | 76100000 | bar: 2006
Reliability Upgrade | 1a | 174 | National Grid, USA | 06/2009 |  | Monadnock Area Reliability Project | Reconductor I-135 (Bellows Falls-Monadnock Tap-Flagg Pond) 115 kV line. | In-service | 15778000 | 15778000
Reliability Upgrade | 1a | 832 | NSTAR Electric Company | 07/2009 |  | Short Term Lower SEMA Upgrades | Add(1) 115kV SVC (0-112 MVARs lagging) at Barnstable. | In-service | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade | 82000000
Reliability Upgrade | 1a | 182 | Vermont Electric Power Company | 09/2009 |  | Monadnock Area Reliability Project | Upgrade bus cable at N. Rutland and K35 115 kV breaker at Rutland. | In-service | 1000000 | 1000000 | bar: 2006
Reliability Upgrade | 1a | 302 | NSTAR Electric Company | 05/2009 |  | Boston Area 115 kV Enhancements | DCT separation of Framingham to Speen St. 433-507 circuit. | In-service | 3100000 | 3100000 | bar: 2006
Reliability Upgrade | 1a | 320 | Vermont Electric Power Company | 10/2009 | 2009 | Lamoille County Project | Middlesex Substation 115 kV breaker addition. | In-service | 4857000 | 4857000
Reliability Upgrade | 1a | 322 | Vermont Electric Power Company | 10/2009 | 2009 | Lamoille County Project | Installation of new Duxbury Substation that involves looping in and out of the Middlesex - Essex 115 kV (K24) line. | In-service | Part of Lamoille County Project | Part of Lamoille County Project
Reliability Upgrade | 1a | 321 | Vermont Electric Power Company | 11/2009 | 2009 | Burlington Project | Burlington 115kV Loop - 5 mi of new line & rebuilding 5 miles of existing line between two existing substations with expansion of the East Avenue substation. | In-service | 25142000 | 25142000
Reliability Upgrade | 1a | 1063 | NSTAR Electric Company | 12/2009 | 2009 |  | Install (2) 115kV 40 MVAR shunt reactors at Edgar Station | In-service | 3745000 | 3745000
Reliability Upgrade | 1a | 777 | National Grid, USA | 11/2009 | 2009 | Merrimack Valley/North Shore Reliability Project | Build Wakefield Junction station with four 345/115 kV autotransformers. | In-service | 95000000 | 95000000
Reliability Upgrade | 1a | 161 | National Grid, USA | 11/2009 | 2009 | Merrimack Valley/North Shore Reliability Project | Loop 345 kV 339 line and 115 kV S-145/T-146 into new Wakefield Jct. Substation. | In-service | 5406900 | 5406900
Reliability Upgrade | 1a | 961 | NSTAR Electric Company | 12/2009 | 2009 | Mystic Breaker Additions Project | Install (2) new 115 kV East Bus breakers #30 and #32 at Mystic. | In-service | 3689000 | 3689000
Reliability Upgrade | 1a | 903 | NSTAR Electric Company | 12/2009 | 2009 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #2, #4, #5, and #16 at Mystic to IPT and separate controls with Boston Gen units #5 and #6. | In-service | 1576000 | 1576000
Reliability Upgrade | 1a | 930 | National Grid, USA | 11/2009 | 2009 | Central/Western Massachusetts Upgrades | Reconductor Nashua St - Quinsigamond Jct (O141) 115 kV line w/636 ACSS. | In-service | 2300000 | 2300000
Reliability Upgrade | 1a | 211 | Northeast Utilities | 11/2009 | 2009 | NU LSP - Rood Ave Substation | New Rood Ave (formally Windsor) distribution substation with 115kV terminal modifications. | In-service | 8681000 | 8681000
Reliability Upgrade | 1a | 789 | National Grid, USA | 12/2009 | 2009 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Reconductoring of T7 115 kV line. | In-service | 23304000 | 23304000
Reliability Upgrade | 1b | 963 | NSTAR Electric Company | 12/2009 | 2009 | Boston Area 115 kV Enhancements | Add a new 115kV breaker # 11 Relocate 447-509 and add control and protection at Holbrook. | In-service | 1276800 | 1276800 | 2006: inservice; Data Set for Investment Chart by Status 2007: 2009 additional $174,977,700
Reliability Upgrade | 1a | 933 | National Grid, USA | 01/2010 | 2010 | Central/Western Massachusetts Upgrades | Reconductor Pratts Jct - Flagg Pond I-135S & J-136S 115 kV lines w/795 ACSS. | In-service | 11200000 | 11200000 | 2006: inservice; Data Set for Investment Chart by Status 2007: 2010 $11,200,00
Reliability Upgrade | 1b | 1167 | NSTAR Electric Company | 12/2010 | 2010 |  | Replace three 40kA 115kV circuit breakers at Carver with 63kV breakers | Concept | 850000 | 850000
Reliability Upgrade | 1b | 1157 | Bangor Hydro-Electric Company | 12/2010 | 2010 |  | Bangor Hydro Synchrophasors | Concept | 100000 | 100000
Reliability Upgrade | 1a | 1128 | Central Maine Power Company | 07/2010 | 2010 | CMP-LSP Hotel Road Substation | Add 115/34kV transformer with 115kV breaker at Hotel Rd. | Planned | 800000 | 800000 | Data Set for Investment Chart by Status 2007: 2010; Data Set for Investment Chart by Status 2008: Concept; Data Set for Investment Chart by Status 2009: 2
Reliability Upgrade | 1a | 624 | Central Maine Power Company | 2010 | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (New Page - Rumford Industrial Park) | Planned | Part of project 625 | Part of project 625 | Data Set for Investment Chart by Status 2007: 2010; Data Set for Investment Chart by Status 2008: Planned; Data Set for Investment Chart by Status 2009: 15
Reliability Upgrade | 1a | 1145 | Vermont Electric Power Company | 12/2010 | 2010 | Burlington Gorge Project | Installation of a 3-breaker 115kV ring substation and 115/34.5kV transformer on the East Ave. - Tafts Coners 115kV line | Planned | 14000000 | 14000000 | Data Set for Investment Chart by Status 2007: 2010; Data Set for Investment Chart by Status 2008: Proposed; Data Set for Investment Chart by Status 2009: 1
Reliability Upgrade | 1a | 1152 | National Grid, USA | 2010-08-01 | 2010 |  | Bear Swamp - Pratts Jumction 230kV Line Refurbishment Project (E205E) | Planned | 43596000 | 43596000 | Data Set for Investment Chart by Status 2007: 2010; Data Set for Investment Chart by Status 2008: Under Construction; Data Set for Investment Chart by Status 2009: 18
Reliability Upgrade | 1a | 842 | NSTAR Electric Company | 06/2010 | 2010 | Boston Area 115 kV Enhancements | Add 115 kV 54 MVAR capacitor bank at W. Framingham. | Planned | 2650000 | 2650000
Reliability Upgrade | 1a | 1113 | NSTAR Electric Company | 12/2010 | 2010 |  | Install 115kV Breaker #31 at K St. | Planned | 2800000 | 2800000
Reliability Upgrade | 1a | 928 | National Grid, USA | 12/2010 | 2010 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | 2300000 | 2300000
Reliability Upgrade | 1a | 927 | National Grid, USA | 07/2010 | 2010 | Central/Western Massachusetts Upgrades | Greendale - replace 115 kV breaker and upgrade to 2000A. | Planned | 680000 | 680000
Reliability Upgrade | 1a | 924 | National Grid, USA | 12/2010 | 2010 | Central/Western Massachusetts Upgrades | Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | Planned | 2147181 | 2147181
Reliability Upgrade | 1a | 1067 | NSTAR Electric Company | 12/2010 | 2010 | NPCC BPS Compliance | Tremont Station | Planned | 12370000 | 12370000
Reliability Upgrade | 1a | 484 | National Grid, USA | 11/2010 | 2010 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Planned | 580000 | 580000
Reliability Upgrade | 1a | 1055 | Northeast Utilities | 2010 | 2010 | CT LSP - Waterside Substation | Waterside Substation - add a 115/13.2-kV transformer and a 115-kV circuit breaker. | Planned | 2619000 | 2619000
Reliability Upgrade | 1a | 1049 | United Illuminating Company | 12/2010 | 2010 |  | East Shore 115 kV Capacitor Bank Transient Recovery | Planned | 4050000 | 4050000
Reliability Upgrade | 1a | 582 | Northeast Utilities | 12/2010 | 2010 |  | Separate 310 and 368 345-KV lines and create 368/1767 DCT | Planned | 16000000 | 16000000
Reliability Upgrade | 1a | 1112 | United Illuminating Company | 12/2010 | 2010 |  | Water Street 115kV circuit breaker and switch replacements. | Planned | 2840000 | 2840000
Reliability Upgrade | 1b | 1133 | Central Maine Power Company | 10/2010 | 2010 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation & new 34kV line from Leeds to Turner | Proposed | 300000 | 300000
Reliability Upgrade | 1a | 1166 | NSTAR Electric Company | 12/2010 | 2010 | Greater Boston Reliability Project | Terminal upgrades at W. Walpole and W, Medway for #325 line | Proposed | 1350000 | 1350000
Reliability Upgrade | 1b | 1150 | United Illuminating Company | 12/2010 | 2010 |  | Grand Avenue - West River 115 kV Pumping Plant Replacements | Proposed | 2900000 | 2900000
Reliability Upgrade | 1a | 144 | Bangor Hydro-Electric Company | 12/2010 | 2010 | Keene Rd Autotransformer | Installation of a 345/115 kV autotransformer at Keene Rd Substation. | Under Construction | 29000000 | 29000000
Reliability Upgrade | 1a | 625 | Central Maine Power Company | 04/2010 | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Rumford Industrial Park capacitor bank. | Under Construction | 5400000 | 5400000
Reliability Upgrade | 1a | 1029 | Central Maine Power Company | 11/2010 | 2010 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformer at South Gorham | Under Construction | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1144 | Central Maine Power Company | 09/2010 | 2010 | Heywood Road Project | Circuit switcher replacements at Detroit, Lakewood, Rice Rips and Winslow | Under Construction | Part of Heywood Road Project | Part of the Heywood Road Project
Reliability Upgrade | 1a | 323 | Vermont Electric Power Company | 12/2010 | 2010 | Vermont Southern Loop Project | New VY - Newfane - Coolidge 345 kV line with requisite station upgrades. | Under Construction | 136368000 | 136368000
Reliability Upgrade | 1a | 1032 | Vermont Electric Power Company | 09/2010 | 2010 | Vermont Southern Loop Project | Installation of a new 345/115kV substation called Vernon including a new 345/115kV autotransformer | Under Construction | 69815000 | 69815000
Reliability Upgrade | 1a | 1033 | Vermont Electric Power Company | 12/2010 | 2010 | Vermont Southern Loop Project (VELCO LSP - Newfane Substation) | Installation of a new 345/115kV substation called Newfane | Under Construction | 16664000 | 16664000
Reliability Upgrade | 1a | 1034 | Vermont Electric Power Company | 12/2010 | 2010 | Vermont Southern Loop Project | Loop new 345kV Line into Newfane Substation. | Under Construction | Part of project 323 | Part of project 323
Reliability Upgrade | 1a | 1035 | Vermont Electric Power Company | 12/2010 | 2010 | Vermont Southern Loop Project | Expansion of Coolidge 345kV substation | Under Construction | 20117000 | 20117000
Reliability Upgrade | 1a | 779 | National Grid, USA | 04/2010 | 2010 | Merrimack Valley/North Shore Reliability Project | Bypass and remove Golden Hills 345 kV substation. | Under Construction | 5507195 | 5507195
Reliability Upgrade | 1a | 904 | NSTAR Electric Company | 12/2010 | 2010 | Mystic IPT Breaker Project | Upgrade (5) 115 kV breakers #1, #7, #15 #19 and #20 at Mystic to IPT. | Under Construction | 1500000 | 1500000
Reliability Upgrade | 1a | 1119 | NSTAR Electric Company | 06/2010 | 2010 | Greater Boston Reliability Project | Upgrade West Medway-West Walpole 345kV line #325 | Under Construction | 2200000 | 2200000
Reliability Upgrade | 1a | 1120 | NSTAR Electric Company | 06/2010 | 2010 |  | Install 345kV 160 MVAR shunt ractor at W. Walpole | Under Construction | 7200000 | 7200000
Reliability Upgrade | 1a | 902 | National Grid, USA | 10/2010 | 2010 | Middleboro Municipal | Close the E1-M1 loop at Middleboro's Wareham St Sub. | Under Construction | 715000 | 715000
Reliability Upgrade | 1a | 786 | National Grid, USA | 11/2010 | 2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Terminal upgrades at Drumrock, Chartley Pond, and Brayton Point. | Under Construction | 1000000 | 1000000
Reliability Upgrade | 1a | 787 | National Grid, USA | 06/2010 | 2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | West Farnum breaker replacements. | Under Construction | 7631000 | 7631000
Reliability Upgrade | 1a | 809 | Northeast Utilities | 12/2010 | 2010 |  | Upgrade terminal equipment at Bunker Hill 115 kV substation. | Under Construction | 516000 | 516000 | Data Set for Investment Chart by Status 2007: 2011; Data Set for Investment Chart by Status 2008: Concept; Data Set for Investment Chart by Status 2009: 5
Reliability Upgrade | 1a | 1110 | United Illuminating Company | 12/2010 | 2010 |  | Broadway 115/13.8 kV Substation Addition | Under Construction | 1200000 | 1200000 | Data Set for Investment Chart by Status 2007: 2011; Data Set for Investment Chart by Status 2008: Planned; Data Set for Investment Chart by Status 2009: 24
Reliability Upgrade | 1b | 301 | NSTAR Electric Company | 12/2011 | 2011 | Boston Area 115 kV Enhancements | Reconductor 115-kV circuits 320-507 and 320-508. | Concept | 4600000 | 4600000 | Data Set for Investment Chart by Status 2007: 2011; Data Set for Investment Chart by Status 2008: Proposed; Data Set for Investment Chart by Status 2009: 6
Reliability Upgrade | 1b | 1156 | Bangor Hydro-Electric Company | 12/2011 | 2011 | Maine Power Reliability Program (MPRP) | Orrington Shunt Cap Reconfiguration | Concept | TBD | TBD | Data Set for Investment Chart by Status 2007: 2011; Data Set for Investment Chart by Status 2008: Under Construction; Data Set for Investment Chart by Status 2009: 6
Reliability Upgrade | 1b | 318 | Vermont Electric Power Company | 12/2011 | 2011 |  | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems through the 1,250 MW Vermont state load level. | Concept | 9000000 | 9000000
Reliability Upgrade | 1b | 325 | Vermont Electric Power Company | 12/2011 | 2011 | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | 5000000 | 5000000
Reliability Upgrade | 1b | 1153 | NSTAR Electric Company | 12/2011 | 2011 | Boston Area 115 kV Enhancements | Reliability Upgrades at West Framingham Station | Concept | 3000000 | 3000000
Reliability Upgrade | 1a | 1146 | Vermont Electric Power Company | 02/2011 | 2011 | Lyndonville Project | Installation of a 4-breaker ring 115 kV substation consisting of two 115kV 12.5 MVAR capacitor banks and 115/34.5 kV transformer interconnecting to the Irasburg - St. Johnsbury 115kV line | Planned | 9000000 | 9000000
Reliability Upgrade | 1a | 783 | National Grid, USA | 03/2011 | 2011 | Merrimack Valley/North Shore Reliability Project | Extend the 115kV by addition of 115kV Breaker and K-153 line from King St. to W. Amesbury 115kV station. (W. Amesbury 345/115kV Station becomes PTF) | Planned | 30349000 | 30349000
Reliability Upgrade | 1a | 1165 | NSTAR Electric Company | 12/2011 | 2011 | Mystic Breaker Additions Project | Move Transformer 110B Connection at Mystic | Planned | 1700000 | 1700000
Reliability Upgrade | 1a | 929 | National Grid, USA | 06/2011 | 2011 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | 1381849 | 1381849
Reliability Upgrade | 1a | 939 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor and retension (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | Planned | 3389658 | 3389658
Reliability Upgrade | 1a | 940 | National Grid, USA | 04/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS. | Planned | 6235744 | 6235744
Reliability Upgrade | 1a | 942 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | 3650000 | 3650000
Reliability Upgrade | 1a | 925 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | 318888 | 318888
Reliability Upgrade | 1a | 926 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | 6027520 | 6027520
Reliability Upgrade | 1a | 932 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | 372036 | 372036
Reliability Upgrade | 1a | 943 | National Grid, USA | 01/2011 | 2011 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | 1073995 | 1073995
Reliability Upgrade | 1a | 944 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Planned | 16530000 | 16530000
Reliability Upgrade | 1a | 945 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Adams - install third 115 kV breaker to complete ring bus. | Planned | 1584841 | 1584841
Reliability Upgrade | 1a | 952 | National Grid, USA | 06/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor E Winchendon - J136 Tap within I135/J136 ROW w/795 ACSR. | Planned | 932156 | 932156
Reliability Upgrade | 1a | 955 | National Grid, USA | 11/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | 12213934 | 12213934
Reliability Upgrade | 1a | 1000 | Northeast Utilities | 12/2011 | 2011 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | Planned | 22000000 | 22000000
Reliability Upgrade | 1a | 1076 | Northeast Utilities | 12/2011 | 2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Planned | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1077 | Northeast Utilities | 12/2011 | 2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115kV line | Planned | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1066 | NSTAR Electric Company | 09/2011 | 2011 | NPCC BPS Compliance | Needham Station | Planned | 10531000 | 10531000
Reliability Upgrade | 1a | 1147 | Northeast Utilities | 2011 | 2011 |  | Waterside Substation - install a three-breaker 115kV ring bus | Planned | 5055000 | 5055000
Reliability Upgrade | 1a | 1148 | Northeast Utilities | 2011 | 2011 |  | Add a 2nd high speed relay on the Glennbrook to Waterside 115kV 1440 | Planned | Part of Project #1147 | Part of Project #1147
Reliability Upgrade | 1a | 1056 | Northeast Utilities | 12/2011 | 2011 | CT LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Planned | 10969000 | 10969000
Reliability Upgrade | 1a | 1111 | United Illuminating Company | 2011-08-01 | 2011 |  | Metro North Union Avenue 115/26.4 kV Substation | Planned | 10543000 | 10543000
Reliability Upgrade | 1a | 1050 | United Illuminating Company | 12/2011 | 2011 |  | Devon Tie 115kV Switching Station BPS Compliance | Planned | 3240000 | 3240000
Reliability Upgrade | 1b | 1116 | Bangor Hydro-Electric Company | 12/2011 | 2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Proposed | 37126000 | 37126000
Reliability Upgrade | 1b | 1130 | Central Maine Power Company | 12/2011 | 2011 | Sturtevant Improvements | Add 115kV circuit breakers & 25 MVAR capacitor bank at Sturtevant Substation; Re-rate Section 63 between Wyman Hydro & Madison Substation | Proposed | 3000000 | 3000000
Reliability Upgrade | 1b | 1131 | Central Maine Power Company | 12/2011 | 2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Proposed | 600000 | 600000
Reliability Upgrade | 1b | 1132 | Central Maine Power Company | 12/2011 | 2011 | CMP-LSP Maxcy's Substation | Add 115/34kV transformer (coordinate with MPRP) | Proposed | 600000 | 600000
Reliability Upgrade | 1b | 964 | NSTAR Electric Company | 06/2011 | 2011 | Boston Area 115 kV Enhancements | Relocate 115kV terminals at W. Walpole to mitigate breaker failure #8. | Proposed | 5600000 | 5600000
Reliability Upgrade | 1b | 1151 | United Illuminating Company | 12/2011 | 2011 |  | West River 115kV Switching Station Fault Duty Migration | Proposed | 3500000 | 3500000
Reliability Upgrade | 1a | 934 | National Grid, USA | 09/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Under Construction | Part of RSP 935 | Part of RSP 935 | Data Set for Investment Chart by Status 2007: 2012; Data Set for Investment Chart by Status 2008: Concept; Data Set for Investment Chart by Status 2009: 4
Reliability Upgrade | 1a | 935 | National Grid, USA | 09/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Under Construction | 10200000 | 10200000 | Data Set for Investment Chart by Status 2007: 2012; Data Set for Investment Chart by Status 2008: Planned; Data Set for Investment Chart by Status 2009: 49
Reliability Upgrade | 1a | 162 | National Grid, USA | 04/2011 | 2011 |  | Q-169 Golden Hills to Lynn 115 kV line upgrade. | Under Construction | 12390000 | 12390000 | Data Set for Investment Chart by Status 2007: 2012; Data Set for Investment Chart by Status 2008: Proposed; Data Set for Investment Chart by Status 2009: 2
Reliability Upgrade | 1a | 788 | National Grid, USA | 06/2011 | 2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Kent County substation expansion. | Under Construction | 42300000 | 42300000 | Data Set for Investment Chart by Status 2007: 2012; Data Set for Investment Chart by Status 2008: Under Construction; Data Set for Investment Chart by Status 2009: 10
Reliability Upgrade | 1a | 790 | National Grid, USA | 12/2011 | 2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Under Construction | 50600000 | 50600000
Reliability Upgrade | 1a | 1098 | National Grid, USA | 12/2011 | 2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Under Construction | 37529000 | 37529000
Reliability Upgrade | 1b | 970 | NSTAR Electric Company | 12/2012 | 2012 | Greater Boston Reliability Project | Add a new 345 kV line from Lexington to Waltham. | Concept | TBD | TBD
Reliability Upgrade | 1b | 971 | NSTAR Electric Company | 12/2012 | 2012 | Greater Boston Reliability Project | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | TBD | TBD
Reliability Upgrade | 1b | 1031 | Bangor Hydro-Electric Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station | Concept | TBD | TBD
Reliability Upgrade | 1b | 965 | NSTAR Electric Company | 12/2012 | 2012 | Boston Area 115 kV Enhancements | Add third 115kV line from W. Walpole to Holbrook | Concept | TBD | TBD
Reliability Upgrade | 1a | 905 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Planned | 1510000000 | 1510000000
Reliability Upgrade | 1a | 906 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Coopers Mills-Highland, Larrabee Road-Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 907 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 84 (Albion Road-Coopers Mills), Section 203 (Detroit-Orrington), Section 80 (Coopers Mills-Highland), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 908 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377 & Maine Yankee 375/392, 115kV Bucksport 65/205) and Maine Yankee 345 kV re-termination | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1026 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Three Rivers) | Planned | Portion of CMP $1.51B and portion of NU is $36.0M | 36000000
Reliability Upgrade | 1a | 1027 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 115kV Line Construction (Elm Street-East Deering, East Deering -Cape) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1028 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD
Reliability Upgrade | 1a | 1158 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Two 40 MVAR reactors at Albion Road, two 40 MVAR reactors at Larabee Road, two 40 MVAR at Coopers Mills | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1030 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Raven Farm, Maguire Road) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 143 | Bangor Hydro-Electric Company | 12/2012 | 2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation to Harrington Substation. | Planned | 66100000 | 66100000
Reliability Upgrade | 1a | 1129 | Central Maine Power Company | 05/2012 | 2012 |  | New 115kV line between Wyman Hydro and Heywood Rd. parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | 32800000 | 32800000
Reliability Upgrade | 1a | 277 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Planned | 56000000 | 56000000
Reliability Upgrade | 1a | 1137 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115kV breakers and add 1-115kV breaker at Deerfield Substation | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1138 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rebuild 115kV L175 line | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1139 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV M183 Line | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1140 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 887 | National Grid, USA | 09/2012 | 2012 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Planned | 76000000 | 76000000
Reliability Upgrade | 1a | 921 | National Grid, USA | 06/2012 | 2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | 40000000 | 40000000
Reliability Upgrade | 1a | 919 | National Grid, USA | 12/2012 | 2012 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | 4600000 | 4600000
Reliability Upgrade | 1a | 840 | NSTAR Electric Company | 06/2012 | 2012 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | 7300000 | 7300000
Reliability Upgrade | 1a | 775 | National Grid, USA | 06/2012 | 2012 | Merrimack Valley/North Shore Reliability Project | Addition of 4 breakers and relocation of T1 and T2 into new bays at Sandy Pond. | Planned | 20100000 | 20100000
Reliability Upgrade | 1a | 776 | National Grid, USA | 09/2012 | 2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | 3125000 | 3125000
Reliability Upgrade | 1a | 59 | National Grid, USA | 06/2012 | 2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | Part of RSP 921 | Part of RSP 921
Reliability Upgrade | 1a | 1068 | NSTAR Electric Company | 12/2012 | 2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to vicinity of Bourne and connect to existing #120 line and install a 345KV - 115kV auto-transformer at new substation about 3 miles west of the Barnstable Substation 7 | Planned | 110000000 | 110000000 | bar: 2006
Reliability Upgrade | 1a | 592 | NSTAR Electric Company | 12/2012 | 2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing | Planned | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1a | 1118 | NSTAR Electric Company | 12/2012 | 2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 | Planned | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1a | 938 | National Grid, USA | 05/2012 | 2012 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | 3068556 | 3068556
Reliability Upgrade | 1a | 941 | National Grid, USA | 06/2012 | 2012 | Central/Western Massachusetts Upgrades | Install new Z126 Millbury - Tower #510 115 kV line. | Planned | 13748000 | 13748000
Reliability Upgrade | 1a | 946 | National Grid, USA | 12/2012 | 2012 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer - E Longmeadow - Shaker Rd line to 115 kV. | Planned | 9962060 | 9962060
Reliability Upgrade | 1a | 947 | National Grid, USA | 12/2012 | 2012 | Central/Western Massachusetts Upgrades | Reconductor 115 kV line from Palmer to new Hampden Substation. | Planned | 2632635 | 2632635
Reliability Upgrade | 1a | 948 | National Grid, USA | 12/2012 | 2012 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | 5649430 | 5649430
Reliability Upgrade | 1a | 949 | National Grid, USA | 12/2012 | 2012 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | 1500000 | 1500000
Reliability Upgrade | 1a | 937 | National Grid, USA | 05/2012 | 2012 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | 6602875 | 6602875
Reliability Upgrade | 1a | 673 | National Grid, USA | 12/2012 | 2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | National Grid, USA | 12/2012 | 2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Planned | 30000000 | 30000000
Reliability Upgrade | 1a | 1065 | NSTAR Electric Company | 07/2012 | 2012 | NPCC BPS Compliance | Waltham Station | Planned | 23190000 | 23190000
Reliability Upgrade | 1a | 1095 | National Grid, USA | 06/2012 | 2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | 73800000 | 73800000
Reliability Upgrade | 1a | 795 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV line. | Planned | 99900000 | 99900000
Reliability Upgrade | 1a | 1106 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | Planned | Part of $99,900,000 above | Part of $99,900,000 above
Reliability Upgrade | 1a | 798 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Planned | 4900000 | 4900000
Reliability Upgrade | 1a | 799 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | Planned | 4500000 | 4500000
Reliability Upgrade | 1a | 1096 | National Grid, USA | 05/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | 12000000 | 12000000
Reliability Upgrade | 1a | 800 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S, T-172N and T-172S with associated terminal equipment upgrades. | Planned | 10000000 | 10000000
Reliability Upgrade | 1a | 1097 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County | Planned | 129800000 | 129800000
Reliability Upgrade | 1a | 1099 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | 6000000 | 6000000
Reliability Upgrade | 1a | 1109 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Planned | 1000000 | 1000000
Reliability Upgrade | 1a | 976 | United Illuminating Company | 05/2012 | 2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Planned | 66000000 | 66000000
Reliability Upgrade | 1b | 148 | Central Maine Power Company | 06/2012 | 2012 | CMP LSP - Saco Bay Area Reinforcement Project | Establish a new Vallee Lane 115/34.5 kV substation and 115 kV line from Louden S/S to Vallee Lane Substation. | Proposed | 100000 | 100000
Reliability Upgrade | 1b | 1136 | National Grid, USA | 12/2012 | 2012 |  | New 115kV Switching Station at Devens Convert 69kV lines to 115kV, Reconfigure 115kV Supply at Ayer Substation | Proposed | 9200000 | 9200000
Reliability Upgrade | 1b | 593 | NSTAR Electric Company | 2013 | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Canal to Barnstable/Falmouth | Concept | TBD | TBD | Data Set for Investment Chart by Status 2007: 2013; Data Set for Investment Chart by Status 2008: Concept; Data Set for Investment Chart by Status 2009: 4
Reliability Upgrade | 1b | 1154 | Bangor Hydro-Electric Company | 12/2013 | 2013 | Maine Power Reliability Program (MPRP) | Rebuild Line 66 | Concept | TBD | TBD | Data Set for Investment Chart by Status 2007: 2013; Data Set for Investment Chart by Status 2008: Planned; Data Set for Investment Chart by Status 2009: 58
Reliability Upgrade | 1b | 1155 | Bangor Hydro-Electric Company | 12/2013 | 2013 | Maine Power Reliability Program (MPRP) | Capacitor Bank Addition (10 MVAr at Trenton and Epping) | Concept | TBD | TBD | Data Set for Investment Chart by Status 2007: 2013; Data Set for Investment Chart by Status 2008: Proposed; Data Set for Investment Chart by Status 2009: 6
Reliability Upgrade | 1b | 843 | NSTAR Electric Company | 12/2013 | 2013 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | TBD | TBD | Data Set for Investment Chart by Status 2007: 2013; Data Set for Investment Chart by Status 2008: Under Construction; Data Set for Investment Chart by Status 2009: 6
Reliability Upgrade | 1a | 680 | National Grid, USA | 03/2013 | 2013 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | 7393000 | 7393000
Reliability Upgrade | 1a | 674 | National Grid, USA | 12/2013 | 2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | 22115000 | 22115000
Reliability Upgrade | 1a | 931 | National Grid, USA | 01/2013 | 2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | 531481 | 531481
Reliability Upgrade | 1a | 950 | National Grid, USA | 12/2013 | 2013 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | 1016897 | 1016897
Reliability Upgrade | 1a | 953 | National Grid, USA | 12/2013 | 2013 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | 10248067 | 10248067
Reliability Upgrade | 1a | 954 | National Grid, USA | 12/2013 | 2013 | Central/Western Massachusetts Upgrades | E Westminster - install new 115 kV breaker, including disconnect switches. Assumes no new control house. | Planned | 903909 | 903909
Reliability Upgrade | 1a | 951 | National Grid, USA | 02/2013 | 2013 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon 115 kV line. | Planned | 7455440 | 7455440
Reliability Upgrade | 1a | 687 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | 714000000 | 714000000
Reliability Upgrade | 1a | 826 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 196 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115kV line South Agawam to Southwick (1768) | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVAR Capacitor additions | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1074 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1078 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 190 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | 69600000 | 69600000
Reliability Upgrade | 1a | 1094 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | 25000000 | 25000000
Reliability Upgrade | 1a | 794 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | 55800000 | 55800000
Reliability Upgrade | 1a | 796 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | 347 Reconductor from Sherman Road to CT/RI Border. | Planned | 16400000 | 16400000
Reliability Upgrade | 1a | 797 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | 3361 Upgrade 345kV terminal equipment at Sherman Road. | Planned | 8300000 | 8300000
Reliability Upgrade | 1a | 974 | United Illuminating Company | 04/2013 | 2013 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Planned | 6700000 | 6700000
Reliability Upgrade | 1a | 816 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1054 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Manchester - Meekvile Jct. line (395/1448) separation. | Planned | 14000000 | 14000000
Reliability Upgrade | 1a | 576 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | 313000000 | 313000000
Reliability Upgrade | 1a | 1114 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1a | 814 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Ancillary Central Connecticut Relaibility Project) | Reconductor a portion of the Manchester to Scovill Rock 353 345-kV line and terminal work. | Planned | 9000000 | 9000000
Reliability Upgrade | 1a | 802 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | 251000000 | 251000000
Reliability Upgrade | 1a | 1084 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Loop the Millstone - Manchester (310) 345 kV line into the Card substation. | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1085 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1086 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1087 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1088 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1089 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Killingly 3G substation 345kV breaker addition | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1090 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Millstone 15G substation breaker 14T upgrade 50kA | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1091 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Southington 4C substation breaker 19T upgrade to 63kA | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 807 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Ancillary Interstate Reliability Project) | Install 480 MVAR's of capacitors at the Montville 345 kV substation | Planned | 33000000 | 33000000
Reliability Upgrade | 1a | 1092 | Northeast Utilities | 12/2013 | 2013 | NEEWS (BPS) 2 | Upgrade the Card 115 kV, East Hartford 115 kV, Agawam 115 kV, Barbour Hill 115 kV, and North Bloomfield 345 kV Substations to BPS standards. | Planned | 37000000 | 37000000
Reliability Upgrade | 1b | 699 | United Illuminating Company | 12/2014 | 2014 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | 11100000 | 11100000 | Data Set for Investment Chart by Status 2008: 2014; Data Set for Investment Chart by Status 2009: Concept; Data Set for Investment Chart by Status 2010: 1
Reliability Upgrade | 1a | 782 | National Grid, USA | 10/2014 | 2014 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor n Railyard. | Planned | 43912000 | 43912000 | Data Set for Investment Chart by Status 2008: 2014; Data Set for Investment Chart by Status 2009: Planned; Data Set for Investment Chart by Status 2010: 10
Reliability Upgrade | 1a | 791 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | 11560000 | 11560000 | Data Set for Investment Chart by Status 2008: 2014; Data Set for Investment Chart by Status 2009: Proposed; Data Set for Investment Chart by Status 2010: 0
Reliability Upgrade | 1a | 913 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | 3250000 | 3250000 | Data Set for Investment Chart by Status 2008: 2014; Data Set for Investment Chart by Status 2009: Under Construction; Data Set for Investment Chart by Status 2010: 0
Reliability Upgrade | 1a | 914 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | 28150000 | 28150000
Reliability Upgrade | 1a | 915 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | 11800000 | 11800000
Reliability Upgrade | 1a | 917 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | 7000000 | 7000000
Reliability Upgrade | 1a | 918 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | 3180000 | 3180000
Reliability Upgrade | 1a | 792 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Admiral St-Franklin Square (Q143 and R144) 115 kV UG recabling. | Planned | 39200000 | 39200000
Reliability Upgrade | 1a | 793 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | 6400000 | 6400000
Reliability Upgrade | 1b | 969 | NSTAR Electric Company | 06/2015 | 2015 | Boston Area 115 kV Enhancements | Add a new 54 MVAR capacitor bank at Chelsea. | Concept | 2780000 | 2780000
Reliability Upgrade | 1b | 956 | National Grid, USA | 01/2015 | 2015 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Concept | 7021534 | 7021534
Reliability Upgrade | 1b | 975 | United Illuminating Company | 06/2015 | 2015 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | 65000000 | 65000000
Reliability Upgrade | 1a | 1141 | Northeast Utilities | 2015 | 2015 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 139 | Vermont Electric Power Company | 12/2015 | 2015 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Planned | 20000000 | 20000000
Reliability Upgrade | 1a | 721 | United Illuminating Company | 06/2016 | 2016 |  | New Shelton 115/13.8 kV substation | Planned | 19500000 | 19500000
Reliability Upgrade | 1b | 785 | National Grid, USA | 07/2017 | 2017 | Merrimack Valley/North Shore Reliability Project | Re-conductor F-158N (Golden Hills-Maplewood-Everett) 115 kV line. | Concept | 1330000 | 1330000
Reliability Upgrade | 1b | 824 | Northeast Utilities | TBD | TBD | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Concept | TBD | TBD
Reliability Upgrade | 1b | 825 | Northeast Utilities | TBD | TBD | Pittsfield / Greenfield Project | Upgrade the Pleasant to Blanford 115-kV line and the Blanford to Granville Jct. portion of the 115-kV line 1512. | Concept | TBD | TBD
Reliability Upgrade | 1a | 910 | Central Maine Power Company | 12/2008 | 2008 | Rumford-Woodstock-Kimball Road Corridor Project | Rebuild Section 211 Woodstock - Rumford. | In-Service | 8400000 | 8400000 | bar: 2006 to Data Set for Investment Chart by Status 2011
Reliability Upgrade | 1a | 177 | Northeast Utilities | 12/2008 | 2008 | Monadnock Area Reliability Project | Replace limiting terminal equipment at Webster Substation on line to North Road. | In-Service | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 180 | Northeast Utilities | 12/2008 | 2008 | Monadnock Area Reliability Project | Rebuild 115 kV Keene to Swanzey A-152 line. | In-Service | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 138 | Vermont Electric Power Company | 12/2008 | 2008 | Northwest Vermont Reliability Project | N. Haven - Vergennes - Q. City 115 kV line. | In-Service | 70200000 | 70200000
Reliability Upgrade | 1a | 923 | National Grid, USA | 12/2008 | 2008 | Auburn Area Transmission System Upgrades | Reconductor 115 kV A94 line and associated substation upgrades. | In-Service | 2400000 | 2400000
Reliability Upgrade | 1a | 781 | National Grid, USA | 10/2008 | 2008 | Merrimack Valley/North Shore Reliability Project | Install 115 kV 30 MVAr capacitor bank at Revere. | In-Service | 1727000 | 1727000
Reliability Upgrade | 1a | 841 | NSTAR Electric Company | 11/2008 | 2008 | Mystic Breaker Additions Project | Install (2) new 115 kV West Bus breakers #29 and #31 at Mystic. | In-Service | 2300000 | 2300000
Reliability Upgrade | 1a | 1040 | NSTAR Electric Company | 12/2008 | 2008 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #11, #8, #17 and #3 at Mystic to IPT | In-Service | 990000 | 990000
Reliability Upgrade | 1a | 168 | National Grid, USA | 09/2008 | 2008 | Southwest Rhode Island Reliability Enhancements | Reconductor Kenyon - Wood River 115 kV 1870 line. | In-Service | 2234232 | 2234232
Reliability Upgrade | 1a | 899 | National Grid, USA | 12/2008 | 2008 | Southwest Rhode Island Reliability Enhancements | Kenyon substation upgrades. | In-Service | 278000 | 278000
Reliability Upgrade | 1a | 171 | National Grid, USA | 10/2008 | 2008 | Southwest Rhode Island Reliability Enhancements | Reconductoring L-190 between Kent Co. and Davisville. | In-Service | 2666291 | 2666291
Reliability Upgrade | 1a | 900 | National Grid, USA | 11/2008 | 2008 | Southwest Rhode Island Reliability Enhancements | Wood River substation upgrades. | In-Service | 130000 | 130000
Reliability Upgrade | 1a | 846 | United Illuminating Company | 11/2008 | 2008 |  | Replace Mix Avenue 115 kV Oil Circuit Breaker & foundation. | In-Service | 450000 | 450000
Reliability Upgrade | 1a | 208 | Northeast Utilities | 12/2008 | 2008 | NU LSP - Oxford Substation | Install new Oxford (previously Jack's Hill) 115 kV substation. | In-Service | 4459000 | 4459000
Reliability Upgrade | 1a | 571 | Northeast Utilities | 12/2008 | 2008 | Norwalk-Glenbrook Cable Project | Upgrade Flax Hill Substation to BPS. | In-Service | Part of project 248 | Part of project 248
Reliability Upgrade | 1a | 248 | Northeast Utilities | 12/2008 | 2008 | Norwalk-Glenbrook Cable Project | Install two new 115 kV cables from Norwalk to Glenbrook (accommodate 345 kV class cable). | In-Service | 249372000 | 249372000
Reliability Upgrade | 1a | 246 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Add second 345/115 kV autotransformer at Norwalk Substation along with shunt reactors and 345 kV circuit breakers. | In-Service | 978182000 | 978182000
Reliability Upgrade | 1a | 238 | United Illuminating Company | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Build new Singer 345 kV substation with (12) circuit breakers, (2) autos, (4) shunt reactors along with reconnecting Bridgeport Energy thru one of the new autos. Includes 115 kV connection from Singer to Pequonnock substation. | In-Service | 162264000 | 162264000
Reliability Upgrade | 1a | 224 | United Illuminating Company | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install new 345 kV line from East Devon to Singer(UI). | In-Service | 157476000 | 157476000
Reliability Upgrade | 1a | 226 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Install two 345 kV underground cables from Singer(UI) to Norwalk. | In-Service | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 235 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Expand Norwalk 345-kV substation and install transfer trip relaying scheme on the 1389 115 kV line between Norwalk and Flax Hill. | In-Service | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 247 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Replace Norwalk Harbor 138/115 kV autotransformer. | In-Service | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 684 | Northeast Utilities | 12/2008 | 2008 | Southwest Connecticut Reliability Project PH II (M-N) | Replace (6) 115 kV breakers (4-Glenbrook, 1-Glenbrook Statcom, 1-Southington #1) and (3) 345-kV circuit breakers at Millstone and replace (4) 345- kV breakers with 500-kV breakers at Long Mountain substation. | In-Service | Part of SWCT (Middletown-Norwalk) Reliability Project | Part of SWCT (Middletown-Norwalk) Reliability Project
Reliability Upgrade | 1a | 250 | Northeast Utilities | 12/2008 | 2008 |  | Add a 345 kV breaker at Ludlow Substation. | In-Service | 1644885 | 1644885
Reliability Upgrade | 1a | 155 | Central Maine Power Company | Northeast Utilities | 2009 | Maguire Road Project | Rebuild Three Rivers - Quaker Hill 115 kV Line K197. | In-Service | 5500000 | 5500000
Reliability Upgrade | 1a | 178 | Northeast Utilities | 02/2009 | 2009 | Monadnock Area Reliability Project | Rebuild 115 kV Garvins to Webster V-182 line. | In-Service | Part of Monadnock Area Reliability Project | Part of Monadnock Area Reliability Project
Reliability Upgrade | 1a | 922 | National Grid, USA | 02/2009 | 2009 | Auburn Area Transmission System Upgrades | Reconductor 115kV L1 line and associated substation upgrades. | In-Service | 800000 | 800000
Reliability Upgrade | 1a | 116 | NSTAR Electric Company | 04/2009 | 2009 | NSTAR 345 kV Transmission Reliability Project | Add 2nd 345 kV UG Cables from Stoughton to Mattapan Sq.to K Street and install another new autotransformer at K. St. | In-Service | 307900000 | 307900000
Reliability Upgrade | 1a | 572 | NSTAR Electric Company | 04/2009 | 2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 345 kV 160 MVAR shunt reactors at Stoughton. | In-Service | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 573 | NSTAR Electric Company | 04/2009 | 2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 345 kV 160 MVAR shunt reactors at K St. | In-Service | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 772 | NSTAR Electric Company | 04/2009 | 2009 | NSTAR 345 kV Transmission Reliability Project | Add (1) 115 kV breaker at K St. | In-Service | Part of NSTAR 345 kV Reliability Project | Part of NSTAR 345 kV Reliability Project
Reliability Upgrade | 1a | 136 | Vermont Electric Power Company | 04/2009 | 2009 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 1: two 115 kV PARs, four 25 MVAR Cap. banks, four +25/-12.5 MVAR synchronous condenders, and two 230/115 transformers. | In-Service | 62400000 | 62400000
Reliability Upgrade | 1a | 695 | NSTAR Electric Company | 07/2009 | 2009 | Short Term Lower SEMA Upgrades | Loop (355) 345 kV line in and out of Carver Substation and add (5) new 345 kV circuit breakers at Carver substation. | In-Service | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 830 | NSTAR Electric Company | 07/2009 | 2009 | Short Term Lower SEMA Upgrades | Add a second 345/115 kV Auto transformer at Carver substation and add (1) new 345 kV circuit breaker and (3) new 115 kV circuit breakers at Carver substation. | In-Service | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 831 | NSTAR Electric Company | 07/2009 | 2009 | Short Term Lower SEMA Upgrades | Add a second 115 kV line from Carver to Tremont and add (2) new 115 kV circuit breakers at Carver substation and (1) new 115 kV circuit breaker at Tremont substation. | In-Service | Part of Short Term Lower SEMA | Part of Short Term Lower SEMA
Reliability Upgrade | 1a | 626 | Central Maine Power Company | 04/2009 |  | Rumford-Woodstock-Kimball Road Corridor Project | Addition of 115/34.5 kV transformer and six new 115 kV breakers and a half substation at Woodstock. | In-service | 8000000 | 8000000
Reliability Upgrade | 1a | 575 | Central Maine Power Company | 05/2009 |  | Heywood Road Project | New Heywood Rd 115kV switchyard with (6) 115kV circuit breakers (3) 115kV line retensionings and 115kV 20 MVAr capacitor bank at Heywood Rd. | In-service | 7000000 | 7000000
Reliability Upgrade | 1a | 1127 | Central Maine Power Company | 05/2009 |  | CMP-LSP Newcastle Substation | Add 115/34kV transformer with two 115kV breakers | In-service | 1300000 | 1300000
Reliability Upgrade | 1a | 166 | National Grid, USA | 06/2009 |  |  | Replace (16) 115 kV breakers at Tewksbury 22. | In-service | 3300000 | 3300000
Reliability Upgrade | 1a | 1009 | Northeast Utilities | 05/2009 |  |  | Install a 2% reactor on the North Bloomfield-Canton 115kV line and also replacement fo the Frostbridge 345/115kV autotransformer | In-service | 3089000 | 3089000
Reliability Upgrade | 1a | 203 | Northeast Utilities | 05/2009 |  | NU LSP - Stepstone Substation | Install new Stepstone 115 kV substation in Guilford. | In-service | 6332000 | 6332000
Reliability Upgrade | 1a | 1064 | NSTAR Electric Company | 04/2009 |  |  | Install (1) 345kV 160 MVAR shunt reactor at Mystic Station | In-service | 10400000 | 10400000
Reliability Upgrade | 1a | 1051 | Central Maine Power Company | 09/2009 |  | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Riley 115 kV capacitor bank. | In-service | Part of Project 625 | Part of Project 625
Reliability Upgrade | 1a | 267 | Northeast Utilities | 2009-08-01 |  | Y138 Closing | White Lake - Saco Valley (Y138) Line Closing - Add PAR on Y138 at Saco Valley, retension lines, upgrade Beebe terminal, and add capacitor banks at White Lake and Beebe. | In-service | 27775000 | 27775000
Reliability Upgrade | 1a | 936 | National Grid, USA | 07/2009 |  | Central/Western Massachusetts Upgrades | Reconductor (P142/P142S) Rolfe Avenue - West Bolyston 115 kV line w/1590 ACSR. | In-service | 3000000 | 3000000
Reliability Upgrade | 1a | 176 | Northeast Utilities | 07/2009 |  | Monadnock Area Reliability Project | New Fitzwilliam 345/115kV substation along with 345 kV breakers. | In-service | 76100000 | 76100000 | bar: 2006
Reliability Upgrade | 1a | 174 | National Grid, USA | 06/2009 |  | Monadnock Area Reliability Project | Reconductor I-135 (Bellows Falls-Monadnock Tap-Flagg Pond) 115 kV line. | In-service | 15778000 | 15778000
Reliability Upgrade | 1a | 832 | NSTAR Electric Company | 07/2009 |  | Short Term Lower SEMA Upgrades | Add(1) 115kV SVC (0-112 MVARs lagging) at Barnstable. | In-service | $82 M (Total NSTAR Project Cost Including Brook St. Station upgrade | 82000000
Reliability Upgrade | 1a | 182 | Vermont Electric Power Company | 09/2009 |  | Monadnock Area Reliability Project | Upgrade bus cable at N. Rutland and K35 115 kV breaker at Rutland. | In-service | 1000000 | 1000000 | bar: 2006
Reliability Upgrade | 1a | 302 | NSTAR Electric Company | 05/2009 |  | Boston Area 115 kV Enhancements | DCT separation of Framingham to Speen St. 433-507 circuit. | In-service | 3100000 | 3100000 | bar: 2006
Reliability Upgrade | 1b | 963 | NSTAR Electric Company | 12/2009 | 2009 | Boston Area 115 kV Enhancements | Add a new 115kV breaker # 11 Relocate 447-509 and add control and protect at Holbrook. | Proposed | 4000000 | 4000000
Reliability Upgrade | 1b | 809 | Northeast Utilities | 12/2009 | 2009 |  | Upgrade terminal equipment at Bunker Hill 115 kV substation. | Proposed | 1000000 | 1000000
Reliability Upgrade | 1a | 320 | Vermont Electric Power Company | 10/2009 | 2009 | Lamoille County Project | Middlesex Substation 115 kV breaker addition. | Under Construction | 4857000 | 4857000
Reliability Upgrade | 1a | 322 | Vermont Electric Power Company | 10/2009 | 2009 | Lamoille County Project | Installation of new Duxbury Substation that involves looping in and out of the Middlesex - Essex 115 kV (K24) line. | Under Construction | Part of Lamoille County Project | Part of Lamoille County Project
Reliability Upgrade | 1a | 321 | Vermont Electric Power Company | 12/2009 | 2009 | Burlington Project | Burlington 115kV Loop - 5 mi of new line & rebuilding 5 miles of existing line between two existing substations with expansion of the East Avenue substation. | Under Construction | 25142000 | 25142000 | Data Set for Investment Chart by Status 2007: 2009; Data Set for Investment Chart by Status 2008: Concept; Data Set for Investment Chart by Status 2009: 0
Reliability Upgrade | 1a | 1063 | NSTAR Electric Company | 12/2009 | 2009 |  | Install (2) 115kV 40 MVAR shunt reactors at Edgar Station | Under Construction | 5400000 | 5400000 | Data Set for Investment Chart by Status 2007: 2009; Data Set for Investment Chart by Status 2008: Planned; Data Set for Investment Chart by Status 2009: 0
Reliability Upgrade | 1a | 777 | National Grid, USA | 11/2009 | 2009 | Merrimack Valley/North Shore Reliability Project | Build Wakefield Junction station with four 345/115 kV autotransformers. | Under Construction | 95000000 | 95000000 | Data Set for Investment Chart by Status 2007: 2009; Data Set for Investment Chart by Status 2008: Proposed; Data Set for Investment Chart by Status 2009: 2
Reliability Upgrade | 1a | 161 | National Grid, USA | 11/2009 | 2009 | Merrimack Valley/North Shore Reliability Project | Loop 345 kV 339 line and 115 kV S-145/T-146 into new Wakefield Jct. Substation. | Under Construction | 4986431 | 4986431 | Data Set for Investment Chart by Status 2007: 2009; Data Set for Investment Chart by Status 2008: Under Construction; Data Set for Investment Chart by Status 2009: 10
Reliability Upgrade | 1a | 903 | NSTAR Electric Company | 12/2009 | 2009 | Mystic IPT Breaker Project | Upgrade (4) 115 kV breakers #2, #4, #5, and #16 at Mystic to IPT and separate controls with Boston Gen units #5 and #6. | Under Construction | 1240000 | 1240000
Reliability Upgrade | 1a | 930 | National Grid, USA | 12/2009 | 2009 | Central/Western Massachusetts Upgrades | Reconductor Nashua St - Quinsigamond Jct (O141) 115 kV line w/636 ACSS. | Under Construction | 2300000 | 2300000
Reliability Upgrade | 1a | 933 | National Grid, USA | 12/2009 | 2009 | Central/Western Massachusetts Upgrades | Reconductor Pratts Jct - Flagg Pond I-135S & J-136S 115 kV lines w/795 ACSS. | Under Construction | 6137112 | 6137112
Reliability Upgrade | 1a | 211 | Northeast Utilities | 11/2009 | 2009 | NU LSP - Rood Ave Substation | New Rood Ave (formally Windsor) distribution substation with 115kV terminal modifications. | Under Construction | 9162029 | 9162029
Reliability Upgrade | 1b | 1153 | NSTAR Electric Company | 06/2010 | 2010 | Boston Area 115 kV Enhancements | Reliability Upgrades at West Framingham Station | Concept | 3000000 | 3000000
Reliability Upgrade | 1b | 1055 | Northeast Utilities | 2010 | 2010 | CT LSP - Waterside Substation | Waterside Substation - add a 115/13.2-kV transformer and a 115-kV circuit breaker. | Concept | 4107000 | 4107000
Reliability Upgrade | 1a | 1128 | Central Maine Power Company | 07/2010 | 2010 | CMP-LSP Hotel Road Substation | Add 115/34kV transformer with 115kV breaker at Hotel Rd. | Planned | 800000 | 800000 | Data Set for Investment Chart by Status 2007: 2010; Data Set for Investment Chart by Status 2008: Concept; Data Set for Investment Chart by Status 2009: 2
Reliability Upgrade | 1a | 624 | Central Maine Power Company | 2010 | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Install 115 kV line (New Page - Rumford Industrial Park) | Planned | Part of project 625 | Part of project 625 | Data Set for Investment Chart by Status 2007: 2010; Data Set for Investment Chart by Status 2008: Planned; Data Set for Investment Chart by Status 2009: 21
Reliability Upgrade | 1a | 139 | Vermont Electric Power Company | 12/2010 | 2010 | Northwest Vermont Reliability Project | Granite Sub Upgrade Phase 2: synchronous condensers expanded to +200/- 100 MVAR and two 25 MVAR capacitor banks. | Planned | 20000000 | 20000000 | Data Set for Investment Chart by Status 2007: 2010; Data Set for Investment Chart by Status 2008: Proposed; Data Set for Investment Chart by Status 2009: 6
Reliability Upgrade | 1a | 840 | NSTAR Electric Company | 10/2010 | 2010 | Merrimack Valley/North Shore Reliability Project | Upgrade the 115 kV line (Line 423-515) from Mystic-Everett by adding a new parallel cable to the existing 115 kV cable. (NSTAR portion only) | Planned | 7300000 | 7300000 | Data Set for Investment Chart by Status 2007: 2010; Data Set for Investment Chart by Status 2008: Under Construction; Data Set for Investment Chart by Status 2009: 6
Reliability Upgrade | 1a | 904 | NSTAR Electric Company | 12/2010 | 2010 | Mystic IPT Breaker Project | Upgrade (5) 115 kV breakers #1, #7, #15 #19 and #20 at Mystic to IPT and separate controls with Boston Gen #4. | Planned | 990000 | 990000
Reliability Upgrade | 1a | 928 | National Grid, USA | 12/2010 | 2010 | Central/Western Massachusetts Upgrades | Millbury -upgrade terminal equipment for O-141, P-142, B-128, A-127 circuit breakers. | Planned | 2300000 | 2300000
Reliability Upgrade | 1a | 934 | National Grid, USA | 10/2010 | 2010 | Central/Western Massachusetts Upgrades | Reconductor #2 Tap from Tower 510 - Webster St. 115 kV circuit. | Planned | 818480 | 818480
Reliability Upgrade | 1a | 935 | National Grid, USA | 07/2010 | 2010 | Central/Western Massachusetts Upgrades | Reconductor from (A-127E/B-128E) Millbury - Tower 510 115 kV line. | Planned | 5208509 | 5208509
Reliability Upgrade | 1a | 938 | National Grid, USA | 06/2010 | 2010 | Central/Western Massachusetts Upgrades | Deerfield - install a new 115/69KV autotransformer and a 69kV breaker and disconnect switches. | Planned | 3068556 | 3068556
Reliability Upgrade | 1a | 942 | National Grid, USA | 10/2010 | 2010 | Central/Western Massachusetts Upgrades | Webster St. - add two 115 kV circuit breakers. | Planned | 2767180 | 2767180
Reliability Upgrade | 1a | 927 | National Grid, USA | 07/2010 | 2010 | Central/Western Massachusetts Upgrades | Greendale - replace 115 kV breaker and upgrade to 2000A. | Planned | 584629 | 584629
Reliability Upgrade | 1a | 484 | National Grid, USA | 11/2010 | 2010 | Greater Rhode Island Transmission Reinforcements 1 | Add (1) new 115 kV breaker at Woonsocket. | Planned | 690000 | 690000
Reliability Upgrade | 1a | 786 | National Grid, USA | 11/2010 | 2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Terminal upgrades at Drumrock, Chartley Pond, and Brayton Point. | Planned | 1000000 | 1000000
Reliability Upgrade | 1a | 787 | National Grid, USA | 12/2010 | 2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | West Farnum breaker replacements. | Planned | 7631000 | 7631000
Reliability Upgrade | 1a | 789 | National Grid, USA | 11/2010 | 2010 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Reconductoring of T7 115 kV line. | Planned | 23304000 | 23304000
Reliability Upgrade | 1a | 1152 | National Grid, USA | 2010-08-01 | 2010 |  | E205E Refurbishment Project | Planned | 43596000 | 43596000
Reliability Upgrade | 1a | 1049 | United Illuminating Company | 12/2010 | 2010 |  | East Shore 115 kV Capacitor Bank Transient Recovery | Planned | 3000000 | 3000000
Reliability Upgrade | 1a | 582 | Northeast Utilities | 12/2010 | 2010 |  | Separate 310 and 368 345-KV lines and create 368/1767 DCT | Planned | 16000000 | 16000000
Reliability Upgrade | 1a | 1112 | United Illuminating Company | 12/2010 | 2010 |  | Water Street 115kV circuit breaker and switch replacements. | Planned | 1000000 | 1000000
Reliability Upgrade | 1a | 1110 | United Illuminating Company | 12/2010 | 2010 |  | Broadway 115/13.8 kV Substation Additon | Planned | 1200000 | 1200000
Reliability Upgrade | 1a | 1111 | United Illuminating Company | 12/2010 | 2010 |  | Metro North Union Avenue 115/26.4 kV Substation | Planned | 10543000 | 10543000
Reliability Upgrade | 1b | 1133 | Central Maine Power Company | 10/2010 | 2010 | CMP-LSP Leeds Substation | Add 115/34kV Leeds Substation & new 34kV line from Leeds to Turner | Proposed | 300000 | 300000
Reliability Upgrade | 1b | 842 | NSTAR Electric Company | 06/2010 | 2010 | Boston Area 115 kV Enhancements | Add 115 kV 54 MVAR capacitor bank at W. Framingham. | Proposed | 3700000 | 3700000
Reliability Upgrade | 1b | 1113 | NSTAR Electric Company | 12/2010 | 2010 |  | Install KSt Breaker #31 | Proposed | 2960000 | 2960000
Reliability Upgrade | 1b | 1067 | NSTAR Electric Company | 12/2010 | 2010 | NPCC BPS Compliance | Tremont Station | Proposed | 12800000 | 12800000
Reliability Upgrade | 1b | 1119 | NSTAR Electric Company | 12/2010 | 2010 | Greater Boston Reliability Project | Upgrade West Medway-West Walpole 345kV line #325 | Proposed | 2200000 | 2200000
Reliability Upgrade | 1b | 1120 | NSTAR Electric Company | 06/2010 | 2010 |  | Install 345kV 160 MVAR shunt ractor at W. Walpole | Proposed | 7200000 | 7200000
Reliability Upgrade | 1a | 144 | Bangor Hydro-Electric Company | 12/2010 | 2010 | Keene Rd Autotransformer | Installation of a 345/115 kV autotransformer at Keene Rd Substation. | Under Construction | 29000000 | 29000000
Reliability Upgrade | 1a | 625 | Central Maine Power Company | 02/2010 | 2010 | Rumford-Woodstock-Kimball Road Corridor Project | Addition of Rumford Industrial Park capacitor bank. | Under Construction | 5400000 | 5400000
Reliability Upgrade | 1a | 1029 | Central Maine Power Company | 11/2010 | 2010 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformer at South Gorham | Under Construction | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1144 | Central Maine Power Company | 04/2010 | 2010 | Heywood Road Project | Circuit switcher replacements at Detroit, Lakewood, Rice Rips and Winslow | Under Construction | Part of Heywood Road Project | Part of the Heywood Road Project
Reliability Upgrade | 1a | 779 | National Grid, USA | 04/2010 | 2010 | Merrimack Valley/North Shore Reliability Project | Bypass and remove Golden Hills 345 kV substation. | Under Construction | 5132609 | 5132609
Reliability Upgrade | 1a | 961 | NSTAR Electric Company | 11/2010 | 2010 | Mystic Breaker Additions Project | Install (2) new 115 kV East Bus breakers #30 and #32 at Mystic and move Transformer 110B Connection. | Under Construction | 3800000 | 3800000
Reliability Upgrade | 1b | 1116 | Bangor Hydro-Electric Company | 12/2011 | 2011 | Maine Power Reliability Program (MPRP) | L 64 Rebuild | Concept | TBD | TBD
Reliability Upgrade | 1b | 318 | Vermont Electric Power Company | 12/2011 | 2011 |  | Rebuild the existing Georgia substation 115 kV bus into a ring bus to address reliability problems through the 1,250 MW Vermont state load level. | Concept | 9000000 | 9000000 | Data Set for Investment Chart by Status 2007: 2011; Data Set for Investment Chart by Status 2008: Concept; Data Set for Investment Chart by Status 2009: 5
Reliability Upgrade | 1b | 325 | Vermont Electric Power Company | 12/2011 | 2011 | VELCO LSP - Chelsea Substation | Replace (2) SCADA controlled motorized disconnect switches with 115 kV circuit breakers at the existing Chelsea substation to maintain adequate supply to the load. | Concept | 5000000 | 5000000 | Data Set for Investment Chart by Status 2007: 2011; Data Set for Investment Chart by Status 2008: Planned; Data Set for Investment Chart by Status 2009: 23
Reliability Upgrade | 1b | 301 | NSTAR Electric Company | 12/2011 | 2011 | Boston Area 115 kV Enhancements | Reconductor 115-kV circuits 320-507 and 320-508. | Concept | 4600000 | 4600000 | Data Set for Investment Chart by Status 2007: 2011; Data Set for Investment Chart by Status 2008: Proposed; Data Set for Investment Chart by Status 2009: 8
Reliability Upgrade | 1b | 1066 | NSTAR Electric Company | 09/2011 | 2011 | NPCC BPS Compliance | Needham Station | Concept | 9300000 | 9300000 | Data Set for Investment Chart by Status 2007: 2011; Data Set for Investment Chart by Status 2008: Under Construction; Data Set for Investment Chart by Status 2009: 6
Reliability Upgrade | 1a | 1145 | Vermont Electric Power Company | 09/2011 | 2011 | Burlington Project | Installation of a 3-breaker 115kV ring substation and 115/34.5kV transformer on the East Ave. - Tafts Coners 115kV line | Planned | 14000000 | 14000000
Reliability Upgrade | 1a | 783 | National Grid, USA | 03/2011 | 2011 | Merrimack Valley/North Shore Reliability Project | Extend the 115kV by addition of 115kV Breaker and K-153 line from King St. to W. Amesbury 115kV station. (W. Amesbury 345/115kV Station becomes PTF) | Planned | 30349000 | 30349000
Reliability Upgrade | 1a | 929 | National Grid, USA | 06/2011 | 2011 | Central/Western Massachusetts Upgrades | Searsburg - install in-line 69 kV breaker for operational flexibility. | Planned | 1381849 | 1381849
Reliability Upgrade | 1a | 939 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor and retension (E205W) Harriman - Bear Swamp Tap 230 kV circuit. | Planned | 3389658 | 3389658
Reliability Upgrade | 1a | 940 | National Grid, USA | 04/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor sections of A127W line w/795 ACSS. | Planned | 6235744 | 6235744
Reliability Upgrade | 1a | 925 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - supply 13 kV from T3 and T4. | Planned | 318888 | 318888
Reliability Upgrade | 1a | 926 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - replace T8 autotransformer with 230 kV 333 mVA, upgrade breaker and bus to 115 kV. Install high side 230 kV breaker. | Planned | 6027520 | 6027520
Reliability Upgrade | 1a | 932 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Pratts Jct. - increase thermal rating of I-135 and J-136 buswork. | Planned | 372036 | 372036
Reliability Upgrade | 1a | 924 | National Grid, USA | 10/2011 | 2011 | Central/Western Massachusetts Upgrades | Replace five 115 kV-25 kA breakers with 115 kV-50 kA breakers and upgrade disconnect switch (175-3) to 2000A. | Planned | 2147181 | 2147181
Reliability Upgrade | 1a | 941 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Install new Millbury - Tower #510 115 kV line. | Planned | 7909203 | 7909203
Reliability Upgrade | 1a | 943 | National Grid, USA | 01/2011 | 2011 | Central/Western Massachusetts Upgrades | Millbury - new 115 kV breaker position for new line to Twr 510. | Planned | 1073995 | 1073995
Reliability Upgrade | 1a | 952 | National Grid, USA | 06/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor E Winchendon - J136 Tap within I135/J136 ROW w/795 ACSR. | Planned | 932156 | 932156
Reliability Upgrade | 1a | 937 | National Grid, USA | 12/2011 | 2011 | Central/Western Massachusetts Upgrades | Bear Swamp - install one 230-115 kV 333 mVA auto, one 115 kV breaker and upgrade various terminal equipment. | Planned | 6602875 | 6602875
Reliability Upgrade | 1a | 955 | National Grid, USA | 11/2011 | 2011 | Central/Western Massachusetts Upgrades | Reconductor (W175) W Charlton - Little Rest - Palmer w/1590 ACSR. | Planned | 10779113 | 10779113
Reliability Upgrade | 1a | 1000 | Northeast Utilities | 12/2011 | 2011 | Agawam-West Springfield Project | Separate and reconductor the 1311 and 1412 (West Springfield - Agawam) 115 kV double circuit. | Planned | 22000000 | 22000000
Reliability Upgrade | 1a | 1076 | Northeast Utilities | 12/2011 | 2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1311) 115kV line | Planned | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 1077 | Northeast Utilities | 12/2011 | 2011 | Agawam-West Springfield Project | Add a 2nd high speed protection scheme to Agawam to West Springfield (1412) 115kV line | Planned | Part of Agawam-West Springfield Project | Part of Agawam-West Springfield Project
Reliability Upgrade | 1a | 788 | National Grid, USA | 06/2011 | 2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Kent County substation expansion. | Planned | 42300000 | 42300000
Reliability Upgrade | 1a | 790 | National Grid, USA | 12/2011 | 2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | Berry Street 345/115 kV substation. | Planned | 50600000 | 50600000
Reliability Upgrade | 1a | 1098 | National Grid, USA | 12/2011 | 2011 | Greater Rhode Island Transmission Reinforcements (Advanced NEEWS) | 345/115kV line interconnections at Berry Street | Planned | 37529000 | 37529000
Reliability Upgrade | 1a | 974 | United Illuminating Company | 12/2011 | 2011 |  | East Shore 115 kV Oil Circuit Breaker & Disconnect Replacements. | Planned | 6700000 | 6700000
Reliability Upgrade | 1a | 1056 | Northeast Utilities | 12/2011 | 2011 | CT LSP - Sherwood Substation | Sherwood Substation - add a 115/13.8-kV substation with two transformers and a 115-kV circuit breaker. | Planned | 9751000 | 9751000
Reliability Upgrade | 1a | 1050 | United Illuminating Company | 12/2011 | 2011 |  | Devon Tie 115kV Switching Station BPS Compliance | Planned | 2620000 | 2620000
Reliability Upgrade | 1b | 1130 | Central Maine Power Company | 12/2011 | 2011 | Sturtevant Improvements | Add 115kV circuit breakers & 25 MVAR capacitor bank at Sturtevant Substation; Re-rate Section 63 between Wyman Hydro & Madison Substation | Proposed | 3000000 | 3000000
Reliability Upgrade | 1b | 1131 | Central Maine Power Company | 12/2011 | 2011 | CMP-LSP Bowman St. Substation | Add 115/34kV transformer | Proposed | 600000 | 600000
Reliability Upgrade | 1b | 1132 | Central Maine Power Company | 12/2011 | 2011 | CMP-LSP Maxcy's Substation | Add 115/34kV transformer (coordinate with MPRP) | Proposed | 600000 | 600000
Reliability Upgrade | 1b | 964 | NSTAR Electric Company | 06/2011 | 2011 | Boston Area 115 kV Enhancements | Relocate 115kV terminals at W. Walpole to mitigate breaker failure #8. | Proposed | 5600000 | 5600000
Reliability Upgrade | 1b | 1150 | United Illuminating Company | 10/2011 | 2011 |  | Grand Avenue - West River 115 kV Pumping Plant Replacements | Proposed | 1200000 | 1200000
Reliability Upgrade | 1b | 1151 | United Illuminating Company | 12/2011 | 2011 |  | West River 115kV Switching Station Fault Duty Migration | Proposed | 3500000 | 3500000
Reliability Upgrade | 1b | 1147 | Northeast Utilities | 2011 | 2011 |  | Waterside Substation - install a three-breaker 115kV ring bus | Proposed | 4000000 | 4000000
Reliability Upgrade | 1b | 1148 | Northeast Utilities | 2011 | 2011 |  | Add a 2nd high speed relay on the Glennbrook to Waterside 115kV 1440 | Proposed | 600000 | 600000
Reliability Upgrade | 1a | 323 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project | New VY - Newfane - Coolidge 345 kV line with requisite station upgrades. | Under Construction | 136368000 | 136368000
Reliability Upgrade | 1a | 1032 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project | Installation of a new 345/115kV substation called Vernon including a new 345/115kV autotransformer | Under Construction | 69815000 | 69815000
Reliability Upgrade | 1a | 1033 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project (VELCO LSP - Newfane Substation) | Installation of a new 345/115kV substation called Newfane | Under Construction | 16664000 | 16664000 | Data Set for Investment Chart by Status 2007: 2012; Data Set for Investment Chart by Status 2008: Concept; Data Set for Investment Chart by Status 2009: 6
Reliability Upgrade | 1a | 1034 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project | Loop new 345kV Line into Newfane Substation. | Under Construction | Part of project 323 | Part of project 323 | Data Set for Investment Chart by Status 2007: 2012; Data Set for Investment Chart by Status 2008: Planned; Data Set for Investment Chart by Status 2009: 43
Reliability Upgrade | 1a | 1035 | Vermont Electric Power Company | 06/2011 | 2011 | Vermont Southern Loop Project | Expansion of Coolidge 345kV substation | Under Construction | 20117000 | 20117000 | Data Set for Investment Chart by Status 2007: 2012; Data Set for Investment Chart by Status 2008: Proposed; Data Set for Investment Chart by Status 2009: 6
Reliability Upgrade | 1a | 162 | National Grid, USA | 04/2011 | 2011 |  | Q-169 Golden Hills to Lynn 115 kV line upgrade. | Under Construction | 12390000 | 12390000 | Data Set for Investment Chart by Status 2007: 2012; Data Set for Investment Chart by Status 2008: Under Construction; Data Set for Investment Chart by Status 2009: 1
Reliability Upgrade | 1b | 1031 | Bangor Hydro-Electric Company | 01/2012 | 2012 | Maine Power Reliability Program (MPRP) | Rebel Hill Switching Station, Rebuild Line 66, and Capacitior Bank Additions (10MVAr at Trenton, Downeast & Handcock County area) | Concept | TBD | TBD
Reliability Upgrade | 1b | 324 | Vermont Electric Power Company | 12/2012 | 2012 |  | Granite to Middlesex 230-kV line with necessary substation upgrades to mitigate several reliability concerns, including those related to the potential Highgate contract termination. | Concept | 100000000 | 100000000
Reliability Upgrade | 1b | 965 | NSTAR Electric Company | 12/2012 | 2012 | Boston Area 115 kV Enhancements | Add third 115kV line from Walpole to Holbrook | Concept | TBD | TBD
Reliability Upgrade | 1b | 970 | NSTAR Electric Company | 12/2012 | 2012 | Greater Boston Reliability Project | Add a new 345 kV line from Lexington to Waltham. | Concept | TBD | TBD
Reliability Upgrade | 1b | 971 | NSTAR Electric Company | 12/2012 | 2012 | Greater Boston Reliability Project | Add a new 345/230 kV auto at Waltham and 230 kV switching facilities. | Concept | TBD | TBD
Reliability Upgrade | 1b | 699 | United Illuminating Company | 12/2012 | 2012 |  | Naugatuck Valley 115 kV reliability improvement. | Concept | 10000000 | 10000000
Reliability Upgrade | 1a | 905 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Orrington-Albion Rd-Coopers Mills, Coopers Mills-Larrabee Road, Larrabee Road-Suroweic). | Planned | 1510000000 | 1510000000
Reliability Upgrade | 1a | 906 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 115kV line construction (Orrington-Coopers Mills, Coopers Mills-Highland, Larrabee Road-Lewiston Lower, Larrabee Road-Livermore Falls, Livermore Falls-Rumford IP) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 907 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Rebuild Existing 115kV lines: Sections 86 (Bucksport-Belfast), Section 84 (Albion Road-Coopers Mills), Section 203 (Detroit-Orrington), Section 80 (Coopers Mills-Highland), Sections 60 & 212 (Coopers Mills-Bowman St-Larrabee Road), Sections 89 & 229 (Livermore Falls-Riley-Rumford IP) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 908 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Albion Road, Larrabee Road) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 909 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Add 2-115kV breakers & rebuild 86A, new .25 mile transmission at Belfast | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1025 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Separation of Double Circuit Towers (345kV Kennebec River Crossing 375/377 & Maine Yankee 375/392, 115kV Bucksport 65/205) and Maine Yankee 345 kV re-termination | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1026 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345kV Line Construction (Surowiec-Raven Farm, South Gorham-Maguire Road, Maguire Road-Three Rivers) | Planned | Portion of CMP $1.51B and portion of NU is $35.1M | 35100000
Reliability Upgrade | 1a | 1027 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 115kV Line Construction (Elm Street-East Deering, East Deering -Cape) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 1028 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | Rebuild existing 115kV Line (Section 250, Maguire Rd-Three Rivers) | Planned | Portion of CMP $1.51B and portion of NU is TBD | Portion of CMP $1.51B and portion of NU is TBD
Reliability Upgrade | 1a | 1030 | Central Maine Power Company | 12/2012 | 2012 | Maine Power Reliability Program (MPRP) | New 345/115kV Autotransformers (Raven Farm, Maguire Road) | Planned | Part of Maine Power Reliability Program | Part of Maine Power Reliability Program
Reliability Upgrade | 1a | 143 | Bangor Hydro-Electric Company | 12/2012 | 2012 | Down East Reliability Improvement | Contruct 115 kV from Trenton tap (part of Hancock Reliability Project) to new Tunk Lake Substation to Harrington Substation. | Planned | 66100000 | 66100000
Reliability Upgrade | 1a | 1129 | Central Maine Power Company | 05/2012 | 2012 |  | New 115kV line between Wyman Hydro and Heywood Rd. parallel to exiting Section 83. Install a 115kV circuit breaker at Wyman Hydro termination | Planned | 19500000 | 19500000
Reliability Upgrade | 1a | 277 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Add 2nd 345/115 kV autotransformer and 3-345kV breakers at Deerfield substation. | Planned | 56600000 | 56600000
Reliability Upgrade | 1a | 1137 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Replace 5-115kV breakers and add 1-115kV breaker at Deerfield Substation | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1138 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rebuild 115kV L175 line | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1139 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV M183 Line | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1140 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Reconductor 115kV C129 Line | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 1141 | Northeast Utilities | 2012 | 2012 | 2nd Deerfield 345/115kV Autotransformer Project | Rochester Substation Upgrades | Planned | Part of 2nd Deerfield 345/115kV Autotransformer Project | Part of 2nd Deerfield 345/115kV Autotransformer Project
Reliability Upgrade | 1a | 680 | National Grid, USA | 09/2012 | 2012 |  | Rebuild Bellows Falls Substation and install 115 kV capacitor bank. | Planned | 7393000 | 7393000
Reliability Upgrade | 1a | 1146 | Vermont Electric Power Company | 12/2012 | 2012 | Lyndonville Project | Installation of a 3-breaker 115kV righ station consisting of two 115kV 12.5 MVAR capacitor banks and 115/34.5 kV transformer interconnecting to the Irasburg - St. Johnsbury 115kV line | Planned | 9000000 | 9000000
Reliability Upgrade | 1a | 887 | National Grid, USA | 09/2012 | 2012 | Auburn Area Transmission System Upgrades | Expand Auburn St Substation to include 2nd 345/115 kV autotransformer and 345 kV ring bus. | Planned | 30000000 | 30000000
Reliability Upgrade | 1a | 921 | National Grid, USA | 01/2012 | 2012 | Auburn Area Transmission System Upgrades | Bridgewater substation - Upgrade Bus work and convert to BPS substation. | Planned | 12100000 | 12100000
Reliability Upgrade | 1a | 919 | National Grid, USA | 09/2012 | 2012 | Auburn Area Transmission System Upgrades | Dupont substation - Upgrade Buswork and convert to BPS substation. | Planned | 4600000 | 4600000
Reliability Upgrade | 1a | 775 | National Grid, USA | 06/2012 | 2012 | Merrimack Valley/North Shore Reliability Project | Addition of 4 breakers and relocation of T1 and T2 into new bays at Sandy Pond. | Planned | 20100000 | 20100000
Reliability Upgrade | 1a | 776 | National Grid, USA | 06/2012 | 2012 | Merrimack Valley/North Shore Reliability Project | Re-conductor O-167 (NGRID portion of Mystic - Everett) 115 kV line. | Planned | 2865876 | 2865876
Reliability Upgrade | 1a | 59 | National Grid, USA | 01/2012 | 2012 | Auburn Reliability Transmission System Upgrades | G18, F19 line terminals 115kV upgrades at Bridgewater sub | Planned | 400000 | 400000 | bar: 2006
Reliability Upgrade | 1a | 944 | National Grid, USA | 07/2012 | 2012 | Central/Western Massachusetts Upgrades | Wachusett - install one 345 kV, 448 mVA transformer, one 345 kV breaker, and one 115 kV breaker. | Planned | 11411849 | 11411849
Reliability Upgrade | 1a | 948 | National Grid, USA | 07/2012 | 2012 | Central/Western Massachusetts Upgrades | Hampden - build new 115 kV substation at 1515/O-15S intersection (4 breaker ring). | Planned | 5649430 | 5649430
Reliability Upgrade | 1a | 949 | National Grid, USA | 07/2012 | 2012 | Central/Western Massachusetts Upgrades | Palmer - add 115 kV breaker position for O15S conversion, includes thermal upgrade of W-175 bay. | Planned | 1500000 | 1500000
Reliability Upgrade | 1a | 673 | National Grid, USA | 12/2012 | 2012 | Worcestor Area Reinforcements | Add new 115kV bay to separate the M-165 & E-157 terminal at Millbury #2 Substation | Planned | 2200000 | 2200000
Reliability Upgrade | 1a | 676 | National Grid, USA | 12/2012 | 2012 | Worcestor Area Reinforcements | New Bloomingdale to Vernon Hill 115 kV (UG Cable-3.6 mi.) new 115kV breaker at Bloomingdale & Vernon Hill | Planned | 30000000 | 30000000
Reliability Upgrade | 1a | 1095 | National Grid, USA | 06/2012 | 2012 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV West Farnum Substation Equipment | Planned | 73800000 | 73800000
Reliability Upgrade | 1a | 797 | National Grid, USA | 12/2012 | 2012 | NEEWS (Interstate Reliability Project) | 3361 Upgrade 345kV terminal equipment at Sherman Road. | Planned | 8300000 | 8300000
Reliability Upgrade | 1a | 795 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | New Kent County to West Farnum 345kV line. | Planned | 99900000 | 99900000
Reliability Upgrade | 1a | 1106 | National Grid, USA | 05/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Installation of third 345/115kV autotransformer at Kent County. | Planned | Part of $99,900,000 above | Part of $99,900,000 above
Reliability Upgrade | 1a | 798 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Upgrade of 115kV terminal equipment at Franklin Square. | Planned | 4900000 | 4900000
Reliability Upgrade | 1a | 799 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | G-185N (Kent County-Drumrock) 115 kV reconductor. | Planned | 4500000 | 4500000
Reliability Upgrade | 1a | 1096 | National Grid, USA | 05/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Drumrock substation: Terminal equipment upgrades, Protection modifications and upgrades to meet BPS standards | Planned | 12000000 | 12000000
Reliability Upgrade | 1a | 800 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Reconductoring of short segments of S-171S, T-172N and T-172S with associated terminal equipment upgrades. | Planned | 10000000 | 10000000
Reliability Upgrade | 1a | 1097 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Relocate and Rebuild 115kV lines in the same ROW associated with new 345kV line from W. Farnum to Kent County | Planned | 129800000 | 129800000
Reliability Upgrade | 1a | 1099 | National Grid, USA | 05/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | Hartford Ave 115kV terminal equipment upgrades | Planned | 6000000 | 6000000
Reliability Upgrade | 1a | 1109 | National Grid, USA | 06/2012 | 2012 | NEEWS (Rhode Island Reliability Project) | South Wrentham 115kv terminal equipment upgrades | Planned | 1000000 | 1000000
Reliability Upgrade | 1a | 976 | United Illuminating Company | 05/2012 | 2012 |  | Grand Avenue 115 kV Switching Station Rebuild. | Planned | 48000000 | 48000000
Reliability Upgrade | 1b | 148 | Central Maine Power Company | 06/2012 | 2012 | CMP LSP - Saco Bay Area Reinforcement Project | Establish a new Vallee Lane 115/34.5 kV substation and 115 kV line from Louden S/S to Vallee Lane Substation. | Proposed | 100000 | 100000
Reliability Upgrade | 1b | 1068 | NSTAR Electric Company | 12/2012 | 2012 | Long Term Lower SEMA Upgrades | Install a new 345kV line from Carver to Sandwich and a a 345-115kV auto-transformer at Sandwich | Proposed | 110000000 | 110000000
Reliability Upgrade | 1b | 592 | NSTAR Electric Company | 12/2012 | 2012 | Long Term Lower SEMA Upgrades | Separate existing 345kV double circuit Cape Cod Canal crossing | Proposed | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1118 | NSTAR Electric Company | 12/2012 | 2012 | Long Term Lower SEMA Upgrades | Upgrade 115kV line D21 | Proposed | Part of Long Term Lower SEMA | Part of Long Term Lower SEMA
Reliability Upgrade | 1b | 1065 | NSTAR Electric Company | 07/2012 | 2012 | NPCC BPS Compliance | Waltham Station | Proposed | 26600000 | 26600000
Reliability Upgrade | 1b | 1136 | National Grid, USA | 12/2012 | 2012 |  | New 115kV Switching Station at Devens Convert 69kV lines to 115kV, Reconfigure 115kV Supply at Ayer Substation | Proposed | 9200000 | 9200000
Reliability Upgrade | 1a | 902 | National Grid, USA | 03/2012 | 2012 | Middleboro Municipal | Close the E1-M1 loop at Middleboro's Wareham St Sub. | Under Construction | 715000 | 715000
Reliability Upgrade | 1b | 843 | NSTAR Electric Company | 12/2013 | 2013 | Boston Area 115 kV Enhancements | Install (2) new 115 kV breakers at Trapelo Road. | Concept | TBD | TBD
Reliability Upgrade | 1b | 593 | NSTAR Electric Company | 2013 | 2013 | Mid Cape Reliability Project | Add a new 115 kV line from Canal to Barnstable/Falmouth | Concept | TBD | TBD | Data Set for Investment Chart by Status 2007: 2013; Data Set for Investment Chart by Status 2008: Concept; Data Set for Investment Chart by Status 2009: 4
Reliability Upgrade | 1b | 956 | National Grid, USA | 05/2013 | 2013 | Central/Western Massachusetts Upgrades | Carpenter Hill - replace one 345 kV, 448 MVA autotransformer and upgrade thermal rating of bus to at least 580 MVA. | Concept | 7021534 | 7021534 | Data Set for Investment Chart by Status 2007: 2013; Data Set for Investment Chart by Status 2008: Planned; Data Set for Investment Chart by Status 2009: 59
Reliability Upgrade | 1b | 975 | United Illuminating Company | 12/2013 | 2013 |  | Pequonnock 115 kV Fault Duty Mitigation. | Concept | 44300000 | 44300000 | Data Set for Investment Chart by Status 2007: 2013; Data Set for Investment Chart by Status 2008: Proposed; Data Set for Investment Chart by Status 2009: 1
Reliability Upgrade | 1a | 674 | National Grid, USA | 09/2013 | 2013 |  | Replace Comerford 230 kV breakers and add (1) 230 kV bus tie breaker. | Planned | 7720000 | 7720000 | Data Set for Investment Chart by Status 2007: 2013; Data Set for Investment Chart by Status 2008: Under Construction; Data Set for Investment Chart by Status 2009: 0
Reliability Upgrade | 1a | 782 | National Grid, USA | 10/2013 | 2013 | Merrimack Valley/North Shore Reliability Project | Replace existing S145/T146 UG cables with higher capacity cables between Salem Harbor n Railyard. | Planned | 38100000 | 38100000
Reliability Upgrade | 1a | 931 | National Grid, USA | 01/2013 | 2013 | Central/Western Massachusetts Upgrades | Park St. - incremental cost of designing for 115 kV instead of 69 kV. | Planned | 531481 | 531481
Reliability Upgrade | 1a | 950 | National Grid, USA | 12/2013 | 2013 | Central/Western Massachusetts Upgrades | E Winchendon - install 115 kV breaker and 115 kV disconnect switch. | Planned | 1016897 | 1016897
Reliability Upgrade | 1a | 953 | National Grid, USA | 12/2013 | 2013 | Central/Western Massachusetts Upgrades | Otter River - expand substation into 6-breaker ring bus with four 115 kV breakers and install two transformers. | Planned | 10248067 | 10248067
Reliability Upgrade | 1a | 954 | National Grid, USA | 12/2013 | 2013 | Central/Western Massachusetts Upgrades | E Westminster - install new 115 kV breaker, including disconnect switches. Assumes no new control house. | Planned | 903909 | 903909
Reliability Upgrade | 1a | 945 | National Grid, USA | 02/2013 | 2013 | Central/Western Massachusetts Upgrades | Adams - install third 115 kV breaker to complete ring bus. | Planned | 1584841 | 1584841
Reliability Upgrade | 1a | 946 | National Grid, USA | 04/2013 | 2013 | Central/Western Massachusetts Upgrades | Convert 69 kV (O-15S) Palmer - E Longmeadow - Shaker Rd line to 115 kV. | Planned | 9604032 | 9604032
Reliability Upgrade | 1a | 947 | National Grid, USA | 04/2013 | 2013 | Central/Western Massachusetts Upgrades | Reconductor 115 kV line from Palmer to new Hampden Substation. | Planned | 2632635 | 2632635
Reliability Upgrade | 1a | 951 | National Grid, USA | 02/2013 | 2013 | Central/Western Massachusetts Upgrades | Install new Otter River - E Winchendon 115 kV line. | Planned | 7455440 | 7455440
Reliability Upgrade | 1a | 687 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Fairmont 16H Substation Expansion | Planned | 714000000 | 714000000
Reliability Upgrade | 1a | 826 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | South Agawam 42E Substation Reconfigure | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 196 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line (3216), Agawam (MA) - North Bloomfield (CT) | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 818 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Reconstruct a new 115kV line South Agawam to Southwick (1768) | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 819 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Build new 345kV line Ludlow - Agawam (3196) | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 820 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Expansion of Agawam 16C 115 kV Substation to include new 345 kV station with two 345/115-kV autotransformers. | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 823 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Ludlow 19S 345 kV Substation Expansion, two 345/115kV Autotransformers replacements. Add two 345kV 120 MVAR Capacitor additions | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 828 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Breckwood 115kV circuit 1322 Reactor Bypass and Open Breckwook Substation 1T breaker and maintain breaker in the normally open position | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 829 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Piper (1230) 115 kV line. | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1010 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Build 115-kV Cadwell switching 50F station. | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 259 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Cadwell to Orchard (1426) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 688 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Cadwell (1481) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1100 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to Chicopee (1314) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1101 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Orchard (1552) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1102 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Piper (1601) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1103 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Chicopee (1602) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1104 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Cadwell (1603) 115kV line and add 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1105 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Fairmont to Shawinigan (1604) 115kV line and add a 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1070 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1781) 115kV line and add a 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1071 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Agawam to South Agawam (1782) 115kV line and add a 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1072 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Rebuild Ludlow to Shawinigan (1845) 115kV line and add 2nd High Speed Protection | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1073 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5001) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1074 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Reterminate Cadwell to East Springfield (5002) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1075 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Add 2nd high speed protection scheme to Agawam to Elm (1007) 115kV line if the Russell Biomass Plant, queue position #135 is constructed | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1078 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Pineshed (1327) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1079 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Add a 2nd high speed protection scheme to Fairmont to Mt. Tom (1428) 115kV line | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1080 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | Replace 4T and 6T 115kV circuit breaker to Shawinigan substation | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 190 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | New Millbury to West Farnum (366) 345kV line. | Planned | 69600000 | 69600000
Reliability Upgrade | 1a | 1094 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Upgrade and expand the 345kV Millbury Substation equipment | Planned | 25000000 | 25000000
Reliability Upgrade | 1a | 794 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | New West Farnum to Connecticut/Rhode Island border (341) 345kV line (to Lake Road). | Planned | 55800000 | 55800000
Reliability Upgrade | 1a | 796 | National Grid, USA | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | 347 Reconductor from Sherman Road to CT/RI Border. | Planned | 16400000 | 16400000
Reliability Upgrade | 1a | 816 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Greater Springfield Reliability Project) | North Bloomfield 2A Substation Expansion - add a second 345/115-kV autotransformer | Planned | Part of NEEWS (Greater Springfield Reliability Project) | Part of NEEWS (Greater Springfield Reliability Project)
Reliability Upgrade | 1a | 1054 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Ancillary Greater Springfield Reliability Project) | Manchester - Meekvile Jct. line (395/1448) separation. | Planned | 14000000 | 14000000
Reliability Upgrade | 1a | 576 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Central Connecticut Reliability Project) | Build new 345kV line (3208) North Bloomfield to Frost Bridge. | Planned | 313000000 | 313000000
Reliability Upgrade | 1a | 1114 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Central Connecticut Reliability Project) | Frost Bridge 18R substation expansion - add a 345/115kV autotransformer. | Planned | Part of NEEWS (Central Connecticut Reliability Project) | Part of NEEWS (Central Connecticut Reliability Project)
Reliability Upgrade | 1a | 814 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Ancillary Central Connecticut Relaibility Project) | Reconductor a portion of the Manchester to Scovill Rock 353 345-kV line and terminal work. | Planned | 9000000 | 9000000
Reliability Upgrade | 1a | 802 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Build new 345kV line (3271) Card to Lake Road | Planned | 251000000 | 251000000
Reliability Upgrade | 1a | 1084 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Loop the Millstone - Manchester (310) 345 kV line into the Card substation. | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1085 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Card 11F substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1086 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1704, SW Hartford to South Meadow | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1087 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to line 115kV 1722 SW Hartford NW Hartford | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1088 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Add 2nd high speed protection to 115kV line 1786, East Hartford to Riverside to South Meadow | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1089 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Killingly 3G substation 345kV breaker addition | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1090 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Millstone 15G substation breaker 14T upgrade 50kA | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 1091 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Southington 4C substation breaker 19T upgrade to 63kA | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 810 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Lake Road 27E 345 kV substation expansion | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 191 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Interstate Reliability Project) | Build Lake Road to Connecticut/Rhode Island border (341) 345-kV line (to West Farnum). | Planned | Part of NEEWS (Interstate Reliability Project) | Part of NEEWS (Interstate Reliability Project)
Reliability Upgrade | 1a | 807 | Northeast Utilities | 12/2013 | 2013 | NEEWS (Ancillary Interstate Reliability Project) | Install 480 MVAR's of capacitors at the Montville 345 kV substation | Planned | 33000000 | 33000000
Reliability Upgrade | 1a | 1092 | Northeast Utilities | 12/2013 | 2013 | NEEWS (BPS) 2 | Upgrade the Card 115 kV, East Hartford 115 kV, Agawam 115 kV, Barbour Hill 115 kV, and North Bloomfield 345 kV Substations to BPS standards. | Planned | 37000000 | 37000000
Reliability Upgrade | 1b | 721 | United Illuminating Company | 06/2013 | 2013 |  | New Shelton 115/13.8 kV substation | Proposed | 11300000 | 11300000
Reliability Upgrade | 1a | 791 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | New 115 kV circuit between Somerset and Brayton Point. | Planned | 11560000 | 11560000
Reliability Upgrade | 1a | 913 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Brayton Point substation reinforcements to accommodate the new 115 kV line. | Planned | 3250000 | 3250000
Reliability Upgrade | 1a | 914 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | New third circuit between Somerset and Bell Rock. | Planned | 28150000 | 28150000
Reliability Upgrade | 1a | 915 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Reconductor M13 and L14 between Bell Rock and Dexter + Reconductor 69 kV lines 61 and 62. | Planned | 19450000 | 19450000
Reliability Upgrade | 1a | 916 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Conversion of Jepson 69 kV substation to 115 kV substation. | Planned | 11800000 | 11800000
Reliability Upgrade | 1a | 917 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Bell Rock substation expansion. | Planned | 7000000 | 7000000
Reliability Upgrade | 1a | 918 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Dexter substation changes. | Planned | 3180000 | 3180000
Reliability Upgrade | 1a | 792 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Admiral St-Franklin Square (Q143 and R144) 115 kV UG recabling. | Planned | 39200000 | 39200000
Reliability Upgrade | 1a | 793 | National Grid, USA | 12/2014 | 2014 | Greater Rhode Island Transmission Reinforcements 1 | Somerset substation reinforcements. | Planned | 6400000 | 6400000
Reliability Upgrade | 1b | 785 | National Grid, USA | 07/2017 | 2017 | Merrimack Valley/North Shore Reliability Project | Re-conductor F-158N (Golden Hills-Maplewood-Everett) 115 kV line. | Concept | 1330000 | 1330000
Reliability Upgrade | 1b | 969 | NSTAR Electric Company | 06/2018 | 2018 | Boston Area 115 kV Enhancements | Add a new 54 MVAR capacitor bank at Chelsea. | Concept | 1200000 | 1200000
Reliability Upgrade | 1b | 275 | Northeast Utilities | TBD | tbd |  | Merrimack 115-kV substation - Protection Separation Upgrade. | Concept | TBD | TBD
Reliability Upgrade | 1b | 824 | Northeast Utilities | TBD | tbd | Pittsfield / Greenfield Project | Reconductor the Woodland to Pleasant 1371 115-kV line and terminal work at Woodland substation. | Concept | TBD | TBD
Reliability Upgrade | 1b | 825 | Northeast Utilities | TBD | tbd | Pittsfield / Greenfield Project | Upgrade the Pleasant to Blanford 115-kV line and the Blanford to Granville Jct. portion of the 115-kV line 1512. | Concept | TBD | TBD
Reliability Upgrade | 1b | 801 | Northeast Utilities | TBD | tbd |  | Build Manchester to East Hartford 115-kV cable with a series reactor. | Concept | TBD | TBD
Reliability Upgrade | 1b | 85 | Northeast Utilities | TBD | tbd |  | Upgrade the South Meadow Substation to Bulk Power System standards (BPS). | Concept | TBD | TBD
Reliability Upgrade | 1a | 879 |  | TBD | tbd | Dynamic Swing Reorder Project | Upgrade 7 of 8 Dynamic Swing Recorders in New England to comply with NERC, NPCC, and ISO-NE Standards. | Planned | 420000 | 420000
Reliability Upgrade | 1b | 1135 | Central Maine Power Company | TBD | tbd | CMP-Athens Substation LSP | Add two 115kV circuit breakers on Section 66; and 115/12kV transformer | Proposed | 1500000 | 1500000
Reliability Upgrade | 1b | 1143 | Northeast Utilities | TBD | tbd |  | Littleton 115kV breaker addition and reconfiguration | Proposed | 5338000 | 5338000

## ISO-NE Asset Condition 0622
June 2022 ISO-NEW ENGLAND Asset Condition Update - ISO-NE Public
Primary Driver | Section # | Asset Condition ID | State | Primary Equipment Owner | Other Equipment Owner(s) | Footnote Number | Projected In-Service Month/Year | Asset Condition Grouping | Description | Mar-16 Status | Jun-16 Status | Oct-16 Status | Mar-17 Status | Jun-17 Status | Oct-17 Status | Mar-18 Status | Jun-18 Status | Oct-18 Status | Mar-19 Status | Jun-19 Status | Oct-19 Status | Mar-20 Status | Jun-20 Status | Oct-20 Status | Mar-21 Status | Jun-21 Status | Oct-21 Status | Mar-22 Status | Jun-22 Status | PPA (I.3.9) Approval | TCA Approval | Mar-16 Estimated PTF Costs | Jun-16 Estimated PTF Costs | Oct-16 Estimated PTF Costs | Mar-17 Estimated PTF Costs | Jun-17 Estimated PTF Costs | Oct-17 Estimated PTF Costs | Mar-18 Estimated PTF Costs | Jun-18 Estimated PTF Costs | Oct-18 Estimated PTF Costs | Mar-19 Estimated PTF Costs | Jun-19 Estimated PTF Costs | Oct-19 Estimated PTF Costs | Mar-20 Estimated PTF Costs | Jun-20 Estimated PTF Costs | Oct-20 Estimated PTF Costs | Mar-21 Estimated PTF Costs | Jun-21 Estimated PTF Costs | Oct-21 Estimated PTF Costs | Mar-22 Estimated PTF Costs | Jun-22 Estimated PTF Costs
Asset Condition
Table A
Maine
New Hampshire
Asset Condition | 1a | 326 | NH | Eversource |  |  | 2022-12-01 |  | Laminated Wood Structure Replacement Program Phase II - S188 115 kV Line | [18 empty] | Under Construction | Under Construction | NR | No | [18 empty] | 7342000 | 7342000
Asset Condition | 1a | 289 | NH | Eversource |  |  | 2022-05-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - K105 Line | [16 empty] | Proposed | Proposed | Under Construction | Under Construction | NR | No | [16 empty] | 14700000 | 14700000 | 16503000 | 16503000
Asset Condition | 1a | 290 | NH | Eversource |  |  | 2022-12-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - X116 Line | [16 empty] | Proposed | Proposed | Under Construction | Under Construction | NR | No | [16 empty] | 26000000 | 26000000 | 24646000 | 24646000
Asset Condition | 1a | 291 | NH | Eversource |  |  | 2022-12-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - Z119 Line | [16 empty] | Proposed | Proposed | Under Construction | Under Construction | NR | No | [16 empty] | 25400000 | 25400000 | 23443000 | 23443000
Asset Condition | 1a | 298 | NH | Eversource |  |  | 2022-05-01 |  | 115 kV Structure and Shield Wire Replacements - Line D121 | [17 empty] | Under Construction | Under Construction | Under Construction | NR | No | [17 empty] | 13105000 | 13105000 | 13105000
Asset Condition | 1a | 278 | NH | Eversource |  |  | 2022-11-01 |  | Amherst substation Protection & Controls Upgrades | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | NR | 2021-08-21 | [15 empty] | 6100000 | 6100000 | 6100000 | 6100000 | 6081000
Asset Condition | 1a | 279 | NH | Eversource |  |  | 2022-11-01 |  | Webster-Beebe River 115 kV Corridor Asset Condition and OPGW Project - A111 Line | [15 empty] | Proposed | Proposed | Planned | Under Construction | Under Construction | 2021-07-15 | No | [15 empty] | 35940000 | 35940000 | 53501000 | 53501000 | 53501000
Asset Condition | 1a | 280 | NH | Eversource |  |  | 2023-12-11 |  | Webster-Beebe River 115 kV Corridor Asset Condition and OPGW Project - E115 Line | [15 empty] | Proposed | Proposed | Planned | Planned | Planned | 2021-07-15 | No | [15 empty] | 55116000 | 55116000 | 55116000 | 55116000 | 55116000
Asset Condition | 1a | 281 | NH | Eversource |  |  | 2024-06-01 |  | Webster-Beebe River 115 kV Corridor Asset Condition and OPGW Project - Z180 Line | [15 empty] | Proposed | Proposed | Planned | Planned | Planned | 2021-07-15 | No | [15 empty] | 9669000 | 9669000 | 9669000 | 9669000 | 9669000
Asset Condition | 1a | 282 | NH | Eversource |  |  | 2022-12-01 |  | 345 kV Line Structure Replacements - Line 373 | [15 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [15 empty] | 9351000 | 9351000 | 9351000 | 9351000 | 9351000
Asset Condition | 1a | 87 | NH | New Hampshire Transmission |  |  | 2022-06-01 | Seabrook 345 kV GIS Switchyard Phase 3 Equipment Replacement Part of Asset Condition #85 | Phase 3 of multi-phase project involving like for like equipment replacement. Phase 3 includes replacing three approximately 1,000 ft. long horizontal gas-insulated lines (GIL) comprising the three phases of the 345 kV Seabrook-Ward Hill 394 line, and replacing two GIS 345 kV Circuit Breakers and related switches that are the 394 line termination equipment. Post-top insulators located in the open-air to GIS transition yard will also be replaced. Phase 3 also includes replacing Breaker Failure Relay Protection Systems for the 394 line. | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2019-04-21 | [6 empty] | Part of Project #86 | Part of Project #86 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85
Asset Condition | 1a | 321 | NH | Eversource |  |  | 2022-12-01 |  | Laminated Wood Structure Replacement Program Phase II - A152 115 kV Line | [18 empty] | Proposed | Under Construction | NR | No | [18 empty] | 15264000 | 17476000
Asset Condition | 1a | 322 | NH | Eversource |  |  | 2022-12-01 |  | Laminated Wood Structure Replacement Program Phase II - V191 115 kV Line | [18 empty] | Proposed | Under Construction | NR | No | [18 empty] | 11024000 | 10114000
Asset Condition | 1a | 323 | NH | Eversource |  |  | 2022-12-01 |  | 115 kV Structure and Shield Wire Replacements - T198 Line | [18 empty] | Proposed | Under Construction | NR | No | [18 empty] | 19100000 | 19113000
Vermont
Asset Condition | 1a | 283 | VT | Vermont Electric Power Company |  |  | 2022-12-01 |  | Line K22 Asset Condition Structure Refurbishment | [15 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-08-20 | [15 empty] | 9720000 | 9720000 | 9720000 | 9720000 | 9720000
Asset Condition | 1a | 284 | VT | Vermont Electric Power Company |  |  | 2024-12-01 |  | Line K24 Asset Condition Structure Refurbishment | [15 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-08-20 | [15 empty] | 15240000 | 15240000 | 15240000 | 15240000 | 15240000
Asset Condition | 1a | 285 | VT | Vermont Electric Power Company |  |  | 2022-12-01 |  | Line K34 Asset Condition Structure Refurbishment | [15 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-08-20 | [15 empty] | 6710000 | 6710000 | 6710000 | 6710000 | 6710000
Asset Condition | 1a | 232 | VT | Vermont Electric Power Company |  |  | 2025-12-01 |  | Line 340 Asset Condition Structure Refurbishment | [13 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-01-29 | [13 empty] | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000
Asset Condition | 1a | 305 | VT | Vermont Electric Power Company |  |  | 2025-12-01 |  | Line K42 Asset Condition Line Replacement | [18 empty] | Proposed | Planned | 2022-03-17 | No | [18 empty] | 49000000 | 49000000
Massachusetts
Asset Condition | 1a | 306 | MA | National Grid, USA |  |  | 2023-05-01 |  | V-174 115 kV Line Asset Condition Refurbishments and OPGW installation | [18 empty] | Under Construction | Under Construction | NR | No | [18 empty] | 26300000 | 26300000
Asset Condition | 1a | 307 | MA | National Grid, USA |  |  | 2022-05-01 |  | M-139/N-140 115 kV Lines Pilot Protection Schemes | [18 empty] | Under Construction | Under Construction | NR | No | [18 empty] | 9400000 | 9400000
Asset Condition | 1a | 251 | MA | Eversource |  |  | 2022-12-01 |  | 345 kV Line Structure Replacement - Line 312 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | NR | No | [15 empty] | 19300000 | 19300000 | 21160000 | 21160000 | 21160000
Asset Condition | 1a | 237 | MA | National Grid, USA |  |  | 2027-12-01 |  | A-1 & B-2 69 kV Line Asset Condition Project | [13 empty] | Concept | Concept | Concept | Concept | Proposed | Planned | Planned | 2020-06-02 | No | [17 empty] | 347300000 | 347300000 | 347300000
Asset Condition | 1a | 294 | MA | National Grid, USA |  |  | 2025-08-01 |  | Millbury #2 Substation Protection Scheme Upgrade and Asset Condition Refurbishments | [17 empty] | Planned | Under Construction | Under Construction | NR | 2022-04-11 | [17 empty] | 28040000 | 28040000 | 28040000
Asset Condition | 1a | 297 | MA | Eversource |  |  | 2025-12-01 |  | 282-520 & 282-521 115 kV Lines HPFF Refurbishment | [17 empty] | Planned | Planned | Planned | NR | No | [17 empty] | 69600000 | 69600000 | 69600000
Asset Condition | 1a | 270 | MA | National Grid, USA |  |  | 2022-06-01 |  | S-145/T-146 115 kV Line Reconductoring - North Reading Substation to Wallace Substation | [15 empty] | Planned | Planned | Planned | Under Construction | Under Construction | 2020-12-11 | No | [15 empty] | 16540000 | 16540000 | 16540000 | 16540000 | 16540000
Asset Condition | 1a | 240 | MA | National Grid, USA |  |  | 2022-10-01 | Boston 2028 Project | Rebuild the Golden Hills #90 Substation | [14 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-04-08 | [14 empty] | 9345000 | 10180000 | 10180000 | 10180000 | 10180000 | 10180000
Asset Condition | 1a | 194 | MA | Eversource |  |  | 2023-12-01 |  | 110-510 & 110-511 lines 115 kV HPFF refurbishment | [11 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | 2020-04-29 | No | [11 empty] | 95000000 | 95000000 | 95000000 | 95000000 | 95000000 | 95000000 | 97995000 | 97995000 | 97995000
Asset Condition | 1a | 208 | MA | Eversource |  |  | 2022-12-01 |  | 115 kV Wood Pole Replacement - 1421 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [12 empty] | 15750000 | 15750000 | 22656000 | 22656000 | 22656000 | 22656000 | 22656000 | 22656000
Asset Condition | 1a | 63 | MA | Eversource |  |  | 2023-06-01 |  | Lexington Station #320 Asset Condition Upgrade Project | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 07/01/2020 | [6 empty] | 14300000 | 14300000 | 14300000 | 14300000 | 14300000 | 14300000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000
Asset Condition | 1a | 28 | MA | Eversource |  |  | 2023-06-01 |  | 115 kV GIS breaker replacement at Kingston Street #514 Substation |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 07/01/2020 |  |  |  | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 39082000 | 39082000 | 39082000 | 39082000 | 39082000 | 39082000 | 39082000 | 39082000
Asset Condition | 1a | 90 | MA | Eversource |  |  | 2023-12-11 |  | Canal Station #980 BPS and Asset Condition Upgrade Project | [8 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 06/30/2020 | [8 empty] | 17923000 | 17923000 | 17923000 | 17923000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000
Asset Condition | 1a | 43 | MA | Eversource |  |  | 2022-12-01 |  | K Street #385 115 kV Control House | [5 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2018-04-17 | [5 empty] | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000
Asset Condition | 1a | 44 | MA | Eversource |  |  | 2026-12-01 |  | Mystic #250 115 kV Control House | [5 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2018-04-17 | [5 empty] | 23900000 | 23900000 | 23900000 | 23900000 | 23900000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000
Asset Condition | 1a | 53 | MA | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 2 | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [6 empty] | 12353000 | 12353000 | 11353000 | 11353000 | 11353000 | 13044000 | 13044000 | 13044000 | 13044000 | 13044000 | 13044000 | 13044000 | 17732000 | 17732000
Asset Condition | 1a | 25 | MA | Taunton Municipal Light Plant |  |  | 2022-09-01 |  | Cleary 115 kV ring bus asset replacement - replace existing ring bus with new 115 kV switching station on an adjacent site and reconnect lines and transformers |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | NR |  |  |  | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000
Asset Condition | 1a | 26 | MA | Eversource |  |  | 2023-12-01 |  | Rebuild Bourne Substation as a breaker and one half scheme |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | 2018-04-30 | 2021-08-21 |  |  |  | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 76000000 | 76000000 | 76000000 | 76000000 | 69893000 | 69893000 | 69893000 | 69893000
Asset Condition | 1a | 27 | MA | Eversource |  |  | 2023-12-11 |  | Kingston Substation #735 Asset Condition Replacement |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | 2018-04-30 | No |  |  |  | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 10428000 | 10428000 | 10428000
Asset Condition | 1a | 92 | MA | National Grid, USA |  | 2 | 2022-09-01 |  | Robinson Avenue Station #102 Asset Condition Upgrades | [8 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-01-29 | [8 empty] | 8300000 | 8300000 | 8300000 | 8300000 | 10340000 | 10340000 | 10340000 | 10430000 | 10430000 | 14892000 | 14892000 | 18020000
Asset Condition | 1a | 145 | MA | National Grid, USA |  |  | 2023-11-01 |  | Carpenter Hill Control House Rebuild | [9 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | NR | 2022-04-11 | [9 empty] | 6860000 | 6860000 | 6860000 | 6860000 | 6860000 | 14485000 | 14485000 | 14485000 | 14485000 | 14485000 | 14485000
Asset Condition | 1a | 146 | MA | National Grid, USA |  |  | 2024-05-01 |  | 327 Line Asset Condition Refurbishments | [9 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-01-29 | [9 empty] | 60400000 | 60400000 | 60400000 | 60400000 | 60400000 | 87877000 | 87877000 | 87877000 | 87877000 | 87877000 | 87877000
Asset Condition | 1a | 149 | MA | National Grid, USA |  |  | 2025-12-01 |  | 315 Line Asset Condition Refurbishments - MA Portion | [9 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-01-29 | [9 empty] | 53500000 | 53500000 | 53500000 | 53500000 | 53500000 | 99072000 | 99072000 | 99072000 | 99072000 | 99072000 | 99072000
Asset Condition | 1a | 181 | MA | Eversource |  |  | 2022-06-01 |  | 345 kV Structure Replacement Projects - Line 312 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [11 empty] | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000
Asset Condition | 1a | 271 | MA | National Grid, USA |  |  | 2023-05-01 |  | V-148S Asset Condition Refurbishment and Switch Replacement - MA Portion | [15 empty] | Proposed | Proposed | Proposed | Proposed | Planned | 2022-03-17 | No | [15 empty] | 10411000 | 10411000 | 10411000 | 10411000 | 10411000
Connecticut
Asset Condition | 1a | 309 | CT | Eversource |  |  | 2023-10-01 |  | Southwest Connecticut (SWCT) Substation Relay Upgrades - Glenbrook 115 kV | [18 empty] | Under Construction | Under Construction | NR | No | [18 empty] | 10034000 | 10034000
Asset Condition | 1a | 310 | CT | Eversource |  |  | 2023-10-01 |  | Southwest Connecticut (SWCT) Substation Relay Upgrades - Plumtree 115 kV and 345 kV | [18 empty] | Under Construction | Under Construction | NR | No | [18 empty] | 19300000 | 19300000
Asset Condition | 1a | 311 | CT | Eversource |  |  | 2023-10-01 |  | Southwest Connecticut (SWCT) Substation Relay Upgrades - Norwalk 115 kV and 345 kV | [18 empty] | Under Construction | Under Construction | NR | No | [18 empty] | 16358000 | 16358000
Asset Condition | 1a | 303 | CT | Eversource |  |  | 2022-12-01 |  | 115 kV Wood Pole Replacement - Line 1751 | [17 empty] | Proposed | Under Construction | Under Construction | NR | No | [17 empty] | 28800000 | 28794000 | 28794000
Asset Condition | 1a | 260 | CT | Eversource |  |  | 2023-03-01 |  | Copper Conductor and Shield Wire Replacement - Line 1825 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | No | No | [15 empty] | 7300000 | 7300000 | 7300000 | 7286000 | 7286000
Asset Condition | 1a | 262 | CT | Eversource |  |  | 2022-12-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 310 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | NR | No | [15 empty] | 59200000 | 59200000 | 61333000 | 61333000 | 61333000
Asset Condition | 1a | 263 | CT | Eversource |  |  | 2022-12-01 |  | 345 kV Line Structure Replacement - Line 330 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | NR | No | [15 empty] | 6600000 | 6600000 | 8039000 | 8039000 | 8039000
Asset Condition | 1a | 266 | CT | Eversource |  |  | 2022-12-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 387 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | NR | No | [15 empty] | 10200000 | 10200000 | 10200000 | 12781000 | 12781000
Asset Condition | 1a | 268 | CT | Eversource |  |  | 2022-12-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 3424 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | NR | No | [15 empty] | 14900000 | 14900000 | 14900000 | 14900000 | 14900000
Asset Condition | 1a | 230 | CT | Eversource |  |  | 2022-09-01 |  | 115 kV Wood Pole Replacement - 1910 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | NR | No | [12 empty] | 10300000 | 10300000 | 10300000 | 10300000 | 10300000 | 10300000 | 8226000 | 8226000
Asset Condition | 1a | 265 | CT | Eversource |  |  | 2023-12-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 383 | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | NR | No | [15 empty] | 16300000 | 16300000 | 16778000 | 16778000 | 16778000
Asset Condition | 1a | 267 | CT | Eversource |  |  | 2022-12-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 3041 | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | NR | No | [15 empty] | 14400000 | 14534000 | 14534000 | 14534000 | 14534000
Asset Condition | 1a | 269 | CT | Eversource |  |  | 2022-12-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 3754 | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | NR | No | [15 empty] | 5000000 | 5000000 | 5000000 | 5000000 | 5000000
Asset Condition | 1a | 221 | CT | Eversource |  |  | 2022-12-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1410 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | NR | No | [12 empty] | 13000000 | 13000000 | 13000000 | 10091000 | 10091000 | 10091000 | 10091000 | 8353000
Asset Condition | 1a | 245 | CT | Eversource |  |  | 2022-06-01 |  | Southington Substation Relay Replacement Project | [15 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-08-21 | [15 empty] | 9400000 | 9362000 | 9362000 | 9362000 | 9362000
Asset Condition | 1a | 219 | CT | Eversource |  |  | 2022-12-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1256 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [12 empty] | 10640000 | 10640000 | 14826000 | 14826000 | 14826000 | 14826000 | 14826000 | 14826000
Asset Condition | 1a | 224 | CT | Eversource |  |  | 2022-05-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1618 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2020-08-28 | [12 empty] | 9770000 | 9770000 | 8767000 | 8767000 | 8767000 | 8767000 | 8767000 | 8767000
Asset Condition | 1a | 225 | CT | Eversource |  |  | 2022-12-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1732 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [12 empty] | 7900000 | 7900000 | 13877000 | 13877000 | 13877000 | 13877000 | 13877000 | 13877000
Asset Condition | 1a | 67 | CT | Eversource |  |  | 2022-06-01 |  | Manchester Control House Expansion | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2020-10-08 | [6 empty] | 21400000 | 21400000 | 21400000 | 21400000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000
Asset Condition | 1a | 170 | CT | Eversource |  |  | 2022-09-01 |  | 345 kV Structure Replacement Projects - Line 364 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [11 empty] | 17300000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000
Asset Condition | 1a | 178 | CT | Eversource |  |  | 2023-03-01 |  | 345 kV Structure Replacement Projects - Line 3754 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [11 empty] | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000
Asset Condition | 1a | 19 | CT | United Illuminating Company |  |  | 2023-04-01 | UI Coastal Substation Flood Mitigation Study Project | Congress 115 kV Substation Flood Wall |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | NR | No |  |  |  | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 31770000 | 31770000 | 31770000
Asset Condition | 1a | 20 | CT | United Illuminating Company |  |  | 2024-04-01 | UI Coastal Substation Flood Mitigation Study Project | Grand Avenue - Mill River 115 kV Substation Flood Wall |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | NR | No |  |  |  | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 41800000 | 41800000 | 41800000
Asset Condition | 1a | 21 | CT | United Illuminating Company |  |  | 2023-03-01 | UI Coastal Substation Flood Mitigation Study Project | Singer 345kV Substation Flood Wall |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | NR | No |  |  |  | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 21960000 | 21960000 | 21960000
Asset Condition | 1a | 22 | CT | United Illuminating Company |  |  | 2024-09-01 | UI Coastal Substation Flood Mitigation Study Project | Pequonnock 115kV Substation rebuild with a new substation adjacent to the existing one |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | 2016-12-28 | 2022-04-11 |  |  |  | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 106100000 | 106106899
Asset Condition | 1a | 91 | CT | United Illuminating Company |  |  | 2025-01-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8809A-2 Line (Pequonnock-Congress) | [8 empty] | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [8 empty] | 376300000 |  | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320
Asset Condition | 1a | 151 | CT | United Illuminating Company |  |  | 2025-01-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8809B-2 Line (Pequonnock - Congress) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320
Asset Condition | 1a | 152 | CT | United Illuminating Company |  |  | 2028-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild portion of 1130 Line (Pequonnock - UI Str. B737) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614
Asset Condition | 1a | 153 | CT | United Illuminating Company |  |  | 2028-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 1430 Line (Ash Creek - ESE Str. B648) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220
Asset Condition | 1a | 154 | CT | United Illuminating Company |  |  | 2026-08-08 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 91001-1 Line (Pequonnock - Bridgeport Resco) & 91001-2 Line (Bridgeport Resco - Ash Creek) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324
Asset Condition | 1a | 155 | CT | United Illuminating Company |  |  | 2028-05-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88005A-1 Line (Milvon - Woodmont) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764
Asset Condition | 1a | 156 | CT | United Illuminating Company |  |  | 2028-05-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88005B-1 Line (Milvon - Woodmont) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764
Asset Condition | 1a | 157 | CT | United Illuminating Company |  |  | 2026-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8804A Line (Woodmont - Allings Crossing) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339
Asset Condition | 1a | 158 | CT | United Illuminating Company |  |  | 2026-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8804B Line (Woodmont - Allings Crossing) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339
Asset Condition | 1a | 159 | CT | United Illuminating Company |  |  | 2024-01-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003A-3 Line (Allings Crossing - Elmwest) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532
Asset Condition | 1a | 160 | CT | United Illuminating Company |  |  | 2024-01-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003B-3 Line (Allings Crossing - Elmwest) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532
Asset Condition | 1a | 161 | CT | United Illuminating Company |  |  | 2024-10-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003A-2 Line (Elmwest - West River) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175
Asset Condition | 1a | 162 | CT | United Illuminating Company |  |  | 2024-10-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003B-2 Line (Elmwest - West River) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175
Asset Condition | 1a | 314 | CT | Eversource |  |  | 2022-06-01 |  | 345 kV Structure and Shield Wire Replacements - 352 Line | [18 empty] | Proposed | Under Construction | NR | No | [18 empty] | 5800000 | 5782000
Asset Condition | 1a | 302 | CT | Eversource |  |  | 2025-06-01 |  | 690 Line Rebuild and Asset Condition Project | [17 empty] | Proposed | Proposed | Under Construction | 2021-07-15 | No | [17 empty] | 11000000 | 11000000 | 11045000
Asset Condition | 1a | 220 | CT | Eversource |  |  | 2023-06-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1280 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | NR | No | [12 empty] | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000
Rhode Island
Asset Condition | 1a | 150 | RI | National Grid, USA |  |  | 2025-06-01 |  | 315 Line Asset Condition Refurbishments - RI Portion | [9 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | NR | 2021-01-29 | [9 empty] | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 25107000 | 25107000 | 25107000 | 25107000 | 25107000 | 25107000
Asset Condition | 1a | 272 | RI | National Grid, USA |  |  | 2023-05-01 |  | V-148S Asset Condition Refurbishment and Switch Replacement - RI Portion | [15 empty] | Proposed | Proposed | Proposed | Proposed | Planned | 2022-03-17 | No | [15 empty] | 14322000 | 14322000 | 14322000 | 14322000 | 14322000
Table B
Maine
New Hampshire
Asset Condition | 1b | 324 | NH | Eversource |  |  | 2024-03-01 |  | P145 Line Rebuild - Asset Condition and OPGW | [18 empty] | Proposed | Proposed | No | No | [18 empty] | 52000000 | 52000000
Asset Condition | 1b | 325 | NH | Eversource |  |  | 2022-12-01 |  | Laminated Wood Structure Replacement Program Phase II - R187 115 kV Line | [18 empty] | Proposed | Proposed | NR | No | [18 empty] | 7541000 | 7541000
Asset Condition | 1b | 308 | NH | National Grid, USA |  |  | 2027-09-01 |  | Moore #20 Substation Asset Condition and Separation | [18 empty] | Proposed | Proposed | No | No | [18 empty] | 49307000 | 49307000
Asset Condition | 1b | 97 | NH | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 3 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Vermont
Asset Condition | 1b | 235 | VT | National Grid, USA |  |  | 2025-07-01 |  | Vernon #13 Substation Asset Replacements | [13 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Proposed | No | No | [19 empty] | 39690000
Massachusetts
Asset Condition | 1b | 329 | MA | Eversource |  |  | 2022-12-01 |  | 115 kV Line Structure and OPGW Replacements - Line 1428 | [19 empty] | Proposed | NR | No | [19 empty] | 7994000
Asset Condition | 1b | 328 | MA | National Grid, USA |  |  | 2026-12-01 |  | Bridgewater #16 Substation Asset Condition Upgrades | [19 empty] | Proposed | No | No | [19 empty] | 25950000
Asset Condition | 1b | 315 | MA | Eversource |  |  | 2023-03-01 |  | 115 kV Structure Replacements and Shield Wire - 191 Line | [18 empty] | Proposed | Proposed | NR | No | [18 empty] | 19200000 | 19200000
Asset Condition | 1b | 316 | MA | Eversource |  |  | 2022-12-01 |  | 115 kV Structure Replacements and Shield Wire - 117 Line | [18 empty] | Proposed | Proposed | NR | No | [18 empty] | 5900000 | 5880000
Asset Condition | 1b | 317 | MA | Eversource |  |  | 2023-12-11 |  | Edgar Station #150 Brown Glass and Obsolete Equipment Replacement | [18 empty] | Proposed | Proposed | NR | No | [18 empty] | 6500000 | 6500000
Asset Condition | 1b | 318 | MA | Eversource |  |  | 2022-06-01 |  | 115 kV Structure Replacements - 211-508 Line | [18 empty] | Proposed | Proposed | NR | No | [18 empty] | 5800000 | 5800000
Asset Condition | 1b | 319 | MA | Eversource |  |  | 2022-07-01 |  | 115 kV Structure Replacements - 391-508 Line | [18 empty] | Proposed | Proposed | NR | No | [18 empty] | 5000000 | 5000000
Asset Condition | 1b | 320 | MA | Eversource |  |  | 2022-09-01 |  | 115 kV Structure Replacements - 533-508 Line | [18 empty] | Proposed | Proposed | NR | No | [18 empty] | 5000000 | 5000000
Asset Condition | 1b | 293 | MA | Eversource |  |  | 2024-06-01 |  | Ludlow 19S 345 kV Full BPS Separation and Asset Condition Project | [16 empty] | Proposed | Proposed | Proposed | Proposed | NR | No | [16 empty] | 42900000 | 42900000 | 42900000 | 42900000
Asset Condition | 1b | 250 | MA | Eversource |  |  | 2023-12-11 |  | Copper Conductor and Shield Wire Replacement - Line 1231/1242 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | No | No | [15 empty] | 97000000 | 97000000 | 97000000 | 97000000 | 97000000
Asset Condition | 1b | 234 | MA | National Grid, USA |  |  | 2026-10-01 |  | Chestnut Hill #702 Substation Asset Replacements | [13 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No
Asset Condition | 1b | 236 | MA | National Grid, USA |  |  | 2026-11-01 |  | Deerfield #4 Substation Asset Replacements | [13 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No
Asset Condition | 1b | 94 | MA | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 5 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Asset Condition | 1b | 95 | MA | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 4 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Asset Condition | 1b | 96 | MA | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 3 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Connecticut
Asset Condition | 1b | 312 | CT | Eversource |  |  | 2022-12-01 |  | Laminated Wood Structure Replacement Program Phase II - 3403 345 kV Line | [18 empty] | Proposed | Proposed | NR | No | [18 empty] | 8422000 | 8422000
Asset Condition | 1b | 255 | CT | Eversource |  |  | 2026-12-01 |  | Copper Conductor and Shield Wire Replacement - Line 1560/1808 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | NR | No | [15 empty] | 19700000 | 19700000 | 19700000 | 19700000 | 19700000
Asset Condition | 1b | 256 | CT | Eversource |  |  | 2026-12-01 |  | Copper Conductor and Shield Wire Replacement - Line 1580/1142/1808 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | No | No | [15 empty] | 68100000 | 68100000 | 68100000 | 68100000 | 68100000
Asset Condition | 1b | 258 | CT | Eversource |  |  | 2026-12-01 |  | Copper Conductor and Shield Wire Replacement - Line 1268/1485/1887 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | No | No | [15 empty] | 29600000 | 29600000 | 29600000 | 29600000 | 29600000
Asset Condition | 1b | 259 | CT | Eversource |  |  | 2024-06-01 |  | Copper Conductor and Shield Wire Replacement - Line 1163/1550 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | NR | No | [15 empty] | 16700000 | 16700000 | 16700000 | 16700000 | 16700000
Asset Condition | 1b | 239 | CT | United Illuminating Company |  |  | 2024-11-01 |  | Derby Junction to Ansonia Corridor 115 kV Transmission Upgrades | [13 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | NR | No | [13 empty] | 22374000 | 22374000 | 22374000 | 22374000 | 36000000 | 36000000 | 36000000
Asset Condition | 1b | 213 | CT | Eversource |  |  | 2023-12-11 |  | 115 kV Wood Pole Replacement - 1000 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | NR | No | [12 empty] | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000
Asset Condition | 1b | 216 | CT | Eversource |  |  | 2023-12-11 |  | 115 kV Wood Pole Replacement - 1080 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | NR | No | [12 empty] | 24180000 | 24180000 | 24180000 | 24180000 | 24180000 | 24180000 | 24180000 | 24180000
Rhode Island
Asset Condition | 1b | 98 | RI | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 5 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Asset Condition | 1b | 99 | RI | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 4 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
In-service
Maine
Asset Condition | 1a | 24 | ME | MEPCO |  |  | 2020-09-01 |  | Section 396 & 3001 Structure Replacement |  |  |  | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2019-12-10 |  |  |  | 16900000 | 16900000 | 16900000 | 16900000 | 16000000 | 16000000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000
Asset Condition | 1a | 23 | ME | MEPCO |  |  | 2019-06-01 |  | Section 388 & 3023 Structure Replacement |  |  |  | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No |  |  |  | 101600000 | 101600000 | 101600000 | 82400000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000
Vermont
Asset Condition | 1a | 195 | VT | Vermont Electric Power Company |  |  | 2021-07-01 |  | Sand Bar Substation - Mitigate several Asset Condition concerns: Control House, P&C, circuit breakers, switches | [11 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | NR | 2021-02-19 | [11 empty] | 10600000 | 10600000 | 10600000 | 10600000 | 10640000 | 10640000 | 10640000 | 10640000 | 10640000
Asset Condition | 1a | 233 | VT | Vermont Electric Power Company |  |  | 2020-12-01 |  | Line K41 Asset Condition Structure Refurbishment | [13 empty] | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2021-01-29 | [13 empty] | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000
Asset Condition | 1a | 196 | VT | Vermont Electric Power Company |  |  | 2020-12-01 |  | Berlin Substation - Mitigate several Asset Condition concerns: Control House, P&C, circuit breakers & switches. Install a second protection system. | [11 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2021-02-01 | [11 empty] | 5872719 | 5550000 | 5550000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000
Asset Condition | 1a | 11 | VT | Vermont Electric Power Company |  |  | 2018-12-01 | Structure Condition Improvement | Replacement of 115 kV, 230 kV and 345 kV structures as part of the VELCO asset maintenance activities addressing our aging and degrading transmission line infrastructure. 100 to 300 structures will be replaced every year based on outage availability |  | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2017-12-01 |  | 185000000 | 185000000 | 185000000 | 160200000 | 160200000 | 160200000 | 160200000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000
Asset Condition | 1a | 3 | VT | Vermont Electric Power Company |  |  | 2017-05-01 | Essex STATCOM Refurbishment | Replace Essex STATCOM power electronics and controls | Proposed | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2017-08-13 | 27850000 | 27850000 | 27850000 | 27850000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000
New Hampshire
Asset Condition | 1a | 327 | NH | Eversource |  |  | 2022-02-01 |  | Laminated Wood Structure Replacement Program Phase II - M164 115 kV Line | [18 empty] | Under Construction | In-Service | NR | No | [18 empty] | 6024000 | 6024000
Asset Condition | 1a | 203 | NH | Eversource |  |  | 2022-04-01 |  | 115 kV Wood Pole and Shield Wire Replacement - K174 | [12 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | NR | No | [12 empty] | 14740000 | 14740000 | 14740000 | 16240000 | 16240000 | 16240000 | 16240000 | 16240000
Asset Condition | 1a | 288 | NH | Eversource |  |  | 2021-09-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - L175 Line | [16 empty] | Proposed | Under Construction | In-Service | In-Service | NR | No | [16 empty] | 19300000 | 19300000 | 19300000 | 19300000
Asset Condition | 1a | 286 | NH | Eversource |  |  | 2021-12-01 |  | Eddy Substation Control House Relocation and Rebuild | [16 empty] | Under Construction | Under Construction | In-Service | In-Service | 2019-07-10 | 2021-08-23 | [16 empty] | 6051000 | 6051000 | 6051000 | 6051000
Asset Condition | 1a | 287 | NH | Eversource |  |  | 2021-11-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - G128 Line | [16 empty] | Under Construction | Under Construction | In-Service | In-Service | NR | No | [16 empty] | 12632000 | 12632000 | 12632000 | 12632000
Asset Condition | 1a | 273 | NH | Eversource |  |  | 2021-12-01 |  | Copper Conductor and Shield Wire Replacement Projects - C129 Line | [15 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | NR | No | [15 empty] | 18500000 | 12145000 | 12145000 | 12145000 | 12145000
Asset Condition | 1a | 275 | NH | Eversource |  |  | 2021-11-01 |  | Copper Conductor and Shield Wire Replacement Projects - G128 Line | [15 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | NR | No | [15 empty] | 7600000 | 5044000 | 5044000 | 5044000 | 5044000
Asset Condition | 1a | 276 | NH | Eversource |  |  | 2021-11-01 |  | Copper Conductor and Shield Wire Replacement Projects - L163 Line | [15 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | NR | No | [15 empty] | 23300000 | 23310000 | 23310000 | 23310000 | 23310000
Asset Condition | 1a | 277 | NH | Eversource |  |  | 2021-11-01 |  | Copper Conductor and Shield Wire Replacement Projects - X104 | [15 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | NR | No | [15 empty] | 6994000 | 6994000 | 6994000 | 6994000 | 6994000
Asset Condition | 1b | 274 | NH | Eversource |  |  | 2022-01-01 |  | Copper Conductor and Shield Wire Replacement Projects - D108 Line | [15 empty] | Proposed | Proposed | Proposed | In-service | In-service | 2021-09-22 | No | [15 empty] | 6700000 | 6700000 | 6750000 | 6750000 | 6750000
Asset Condition | 1a | 200 | NH | Eversource |  |  | 2021-06-01 |  | 115 kV Wood Pole Replacement - F139 | [12 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | NR | No | [12 empty] | 8000000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000
Asset Condition | 1a | 187 | NH | Eversource |  |  | 2021-02-01 |  | 345 kV Structure Replacement Projects - Line 367 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | No | [11 empty] | 14100000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000
Asset Condition | 1a | 104 | NH | Eversource |  |  | 2021-02-01 |  | 115 kV Structure Replacement Project - Line L163 | [9 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | No | [9 empty] | 14000000 | 14000000 | 14000000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000
Asset Condition | 1a | 86 | NH | New Hampshire Transmission |  |  | 2020-11-01 | Seabrook 345 kV GIS Switchyard Phase 2 Equipment Replacement Part of Asset Condition #85 | Phase 2 of mulit-phase project involving like for like equipment replacement. Phase 2 includes replacing three approximately 1,000 ft. long horizontal gas-insulated lines (GIL) comprising the three phases of the 345 kV Seabrook-Scobie Pond 363 line, and replacing two GIS 345 kV Circuit Breakers and related switches that are the 363 line termination equipment. Post-top insulators for the 363 line located in the open-air to GIS transition yard will also be replaced. Phase 2 also includes replacing Breaker Failure Relay Protection Systems for the 363 line. | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2019-04-21 | [6 empty] | Part of Project #86 | Part of Project #86 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85
Asset Condition | 1a | 206 | NH | Eversource |  |  | 2020-11-01 |  | 115 kV Wood Pole and Shield Wire Replacement - Y138 | [12 empty] | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [12 empty] | 8490000 | 8490000 | 8475000 | 8475000 | 8475000 | 8475000 | 8475000 | 8475000
Asset Condition | 1a | 198 | NH | Eversource |  |  | 2020-09-01 |  | 115 kV Wood Pole Replacement - B143 | [12 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [12 empty] | 7410000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000
Asset Condition | 1a | 199 | NH | Eversource |  |  | 2020-11-01 |  | 115 kV Wood Pole Replacement - C129 | [12 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [12 empty] | 9100000 | 9045000 | 9045000 | 9045000 | 9045000 | 9045000 | 10048000 | 10048000
Asset Condition | 1a | 201 | NH | Eversource |  |  | 2020-11-01 |  | 115 kV Wood Pole Replacement - G128 | [12 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [12 empty] | 6910000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000
Asset Condition | 1a | 205 | NH | Eversource |  |  | 2020-12-01 |  | 115 kV Wood Pole and Shield Wire Replacement - M127 | [12 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [12 empty] | 33430000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000
Asset Condition | 1a | 105 | NH | Eversource |  |  | 2020-09-01 |  | 115 kV Structure Replacement Project - Line A152 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 6100000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000
Asset Condition | 1a | 188 | NH | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 373 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 10300000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000
Asset Condition | 1a | 189 | NH | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 379 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 9700000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000
Asset Condition | 1a | 191 | NH | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 385 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 14000000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000
Asset Condition | 1a | 192 | NH | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 391 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 16400000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000
Asset Condition | 1b | 202 | NH | Eversource |  |  | 2020-12-01 |  | 115 kV Wood Pole Replacement - K105 | [12 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | NR | NR | [12 empty] | 6080000 | 6080000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000
Asset Condition | 1b | 204 | NH | Eversource |  |  | 2020-03-01 |  | 115 kV Wood Pole Replacement - L175 | [12 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | NR | NR | [12 empty] | 5250000 | 5250000 | 5250000 | 3809000 | 3809000 | 3809000 | 3809000 | 3809000
Asset Condition | 1a | 186 | NH | Eversource |  |  | 2020-03-01 |  | 345 kV Structure Replacement Projects - Line 326 | [11 empty] | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 5200000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000
Asset Condition | 1a | 100 | NH | Eversource |  |  | 2020-01-01 |  | 115 kV Structure Replacement Project - Line A126 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 8300000 | 8300000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000
Asset Condition | 1a | 101 | NH | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line H123 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 6000000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000
Asset Condition | 1a | 102 | NH | Eversource |  |  | 2019-12-01 |  | 115 kV Structure Replacement Project - Line H141 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 7700000 | 7700000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000
Asset Condition | 1a | 103 | NH | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line K174 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 8700000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000
Asset Condition | 1a | 190 | NH | Eversource |  |  | 2020-01-01 |  | 345 kV Structure Replacement Projects - Line 381 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 8300000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000
Asset Condition | 1a | 85 | NH | New Hampshire Transmission |  |  | 2019-12-01 | Seabrook 345 kV GIS Switchyard Like-for Like Equipment Replacement | Phase 1 of mulit-phase project involving like for like equipment replacement. Phase 1 included replacing three approximately 1,000 ft. long horizontal gas-insulated lines (GIL) comprising the three phases of the 345kV Seabrook-to-Timberswamp 369 line. Post-top insulators for the 369 line located in the open-air to GIS transition yard were also replaced. A bridge covering the GILs where they go below grade and then resurface upon entering the fenced-in Protected Area where the GIS Switchyard is located was replaced during this phase. | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-04-21 | [6 empty] | 77017000 | 77017000 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778
Asset Condition | 1a | 52 | NH | Eversource |  |  | 2018-11-01 | Eversource Energy Autotransformer Replacement Plan | Replace the Littleton TB-41 autotransformer and bus upgrades to accommodate new transformer specifications | [5 empty] | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2018-01-29 | NR | [5 empty] | 6200000 | 3891000 | 3891000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000
Asset Condition | 1a | 55 | NH | Eversource |  |  | 2018-07-01 |  | 345 kV Structure Replacement Project - Line 307 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 12900000 | 12900000 | 12900000 | 12900000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000
Asset Condition | 1a | 56 | NH | Eversource |  |  | 2018-08-05 |  | 345 kV Structure Replacement Project - Line 326 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 12300000 | 12300000 | 12300000 | 12300000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000
Asset Condition | 1a | 57 | NH | Eversource |  |  | 2018-11-01 |  | 345 kV Structure Replacement Project - Line 367 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 15800000 | 15800000 | 15800000 | 15800000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000
Asset Condition | 1a | 58 | NH | Eversource |  |  | 2018-11-01 |  | 345 kV Structure Replacement Project - Line 379 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 14800000 | 14800000 | 14800000 | 14800000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000
Asset Condition | 1a | 59 | NH | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 381 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 13600000 | 13600000 | 13600000 | 13600000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000
Asset Condition | 1a | 60 | NH | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 391 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 19600000 | 19600000 | 19600000 | 19600000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000
Asset Condition | 1a | 51 | NH | Eversource |  |  | 2018-07-01 | Eversource Energy Autotransformer Replacement Plan | Replace the Deerfield TB-14 autotransformer and bus upgrades to accommodate new transformer specifications | [5 empty] | Proposed | Proposed | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2018-01-29 | 2020-10-08 | [5 empty] | 7700000 | 4779000 | 4779000 | 5300000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000
Asset Condition | 1a | 36 | NH | Eversource |  |  | 2018-03-01 |  | Install two 40 MVAR reactors on the Scobie 115 kV bus, to accommodate the loss of the reactors connected on the 13.8 kV teriary winding of the TB30 transformer |  |  |  |  | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2017-05-24 | 2018-08-24 |  |  |  |  | 5200000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000
Asset Condition | 1a | 5 | NH | New Hampshire Transmission |  |  | 2017-11-01 | Seabrook 345 kV GIS Breaker Removal and Bus Upgrade | Phase 2 - Remove Breaker 11 and upgrade sections of Bus 1 | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2016-02-23 | 2018-09-11 | 4271787 | 4271787 | 4271787 | 11991000 | 11991000 | 11991000 | 11991000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000
Asset Condition | 1a | 35 | NH | Eversource |  |  | 2017-06-01 |  | Scobie Pond TB30 345/115 kV transformer replacement project |  |  |  |  | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2017-05-24 | 2018-08-24 |  |  |  |  | 10300000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000
Asset Condition | 1a | 4 | NH | New Hampshire Transmission |  |  | 2016-11-01 | Seabrook 345 kV GIS Breaker Removal and Bus Upgrade | Phase 1 - Remove Breaker 22, remove Bus 4 and upgrade sections of Bus 2 | Proposed | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2016-02-23 | 2018-09-11 | 5140351 | 5140351 | 5140351 | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0)
Connecticut
Asset Condition | 1a | 313 | CT | Eversource |  |  | 2022-04-01 |  | 345 kV Structure and Shield Wire Replacements - 329 Line | [18 empty] | Under Construction | In-Service | NR | No | [18 empty] | 6242000 | 6242000
Asset Condition | 1a | 261 | CT | Eversource |  |  | 2022-03-01 |  | 115 kV Wood Pole and Shield Wire Replacement 2020-2023 - Line 1465 | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | NR | No | [15 empty] | 8770000 | 8770000 | 8770000 | 8770000 | 8770000
Asset Condition | 1a | 164 | CT | Eversource |  |  | 2022-03-01 |  | 345 kV Structure Replacement Projects - Line 310 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | NR | No | [11 empty] | 19900000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000
Asset Condition | 1a | 172 | CT | Eversource |  |  | 2022-03-01 |  | 345 kV Structure Replacement Projects - Line 383 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | NR | No | [11 empty] | 22200000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000
Asset Condition | 1a | 257 | CT | Eversource |  |  | 2021-12-01 |  | Copper Conductor and Shield Wire Replacement - Line 1588 | [15 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | 2021-06-17 | No | [15 empty] | 9600000 | 9600000 | 9611000 | 9611000 | 9611000
Asset Condition | 1a | 264 | CT | Eversource |  |  | 2022-01-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 368 | [15 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | NR | No | [15 empty] | 8800000 | 8800000 | 9860000 | 9860000 | 9860000
Asset Condition | 1a | 227 | CT | Eversource |  |  | 2021-11-01 |  | 115 kV Wood Pole Replacement - 1756 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | In-Service | In-Service | NR | No | [12 empty] | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 24469000 | 24469000 | 24469000
Asset Condition | 1a | 292 | CT | Eversource |  |  | 2021-12-01 |  | Branford 11J A3 Bus Replacement Project | [16 empty] | Under Construction | Under Construction | In-Service | In-Service | NR | 2021-08-22 | [16 empty] | 10322000 | 10322000 | 10322000 | 10322000
Asset Condition | 1a | 244 | CT | Eversource |  |  | 2021-09-01 |  | 115 kV Copper Conductor and Wood Pole Replacement - Line 1191 | [14 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | 10/5/2020 | 2021-08-21 | [14 empty] | 38050000 | 38050000 | 38054000 | 38054000 | 38054000 | 38054000
Asset Condition | 1a | 242 | CT | Eversource |  |  | 2021-08-07 |  | Horton Cove Asset Condition and OPGW Project | [14 empty] | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-Service | 2020-11-06 | No | [14 empty] | 13400000 | 13949000 | 13949000 | 13949000 | 13949000 | 13949000
Asset Condition | 1a | 130 | CT | Eversource |  |  | 2021-12-01 |  | 115 kV Structure Replacement Project - Line 1465 | [9 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-Service | NR | 2021-02-19 | [9 empty] | 7000000 | 7000000 | 7000000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000
Asset Condition | 1a | 223 | CT | Eversource |  |  | 2021-09-01 |  | 115 kV Wood Pole Replacement - 1607 | [12 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | NR | No | [12 empty] | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000
Asset Condition | 1a | 166 | CT | Eversource |  |  | 2021-11-01 |  | 345 kV Structure Replacement Projects - Line 330 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | NR | No | [11 empty] | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000
Asset Condition | 1a | 167 | CT | Eversource |  |  | 2021-03-01 |  | 345 kV Structure Replacement Projects - Line 348 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | NR | No | [11 empty] | 19400000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000
Asset Condition | 1a | 173 | CT | Eversource |  |  | 2021-11-01 |  | 345 kV Structure Replacement Projects - Line 387 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | NR | No | [11 empty] | 18200000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000
Asset Condition | 1a | 176 | CT | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 3419 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | NR | No | [11 empty] | 11900000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000
Asset Condition | 1a | 124 | CT | Eversource |  |  | 2021-09-01 |  | 115 kV Structure Replacement Project - Line 1448 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | NR | 2021-02-19 | [9 empty] | 6900000 | 6926000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000
Asset Condition | 1a | 144 | CT | Eversource |  |  | 2021-10-01 |  | Millstone Substation 15G High Creep Insulator Replacement | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | NR | 2020-10-08 | [9 empty] | 11500000 | 11500000 | 11500000 | 11500000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000
Asset Condition | 1a | 139 | CT | Eversource |  |  | 2021-08-07 |  | 115 kV Structure Replacement Project - Line 1772 | [9 empty] | In-service | In-service | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | NR | 2021-02-19 | [9 empty] | 10000000 | 10000000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000
Asset Condition | 1b | 218 | CT | Eversource |  |  | 2021-10-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1232 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | In-Service | In-Service | NR | NR | [12 empty] | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 2422000 | 2422000
Asset Condition | 1a | 241 | CT | Eversource |  |  | 2021-05-01 |  | Glenbrook STATCOM Replacement | [14 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | 2021-04-14 | 2021-08-21 | [14 empty] | 21600000 | 21624000 | 18699000 | 18699000 | 18699000 | 18699000
Asset Condition | 1a | 243 | CT | Eversource |  |  | 2021-06-01 |  | 115 kV Lattice Tower Asset Condition and OPGW Project - Line 1768 | [14 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | 2020-11-06 | 2021-08-21 | [14 empty] | 22600000 | 22929000 | 22929000 | 22929000 | 22929000 | 22929000
Asset Condition | 1a | 217 | CT | Eversource |  |  | 2021-08-07 |  | 115 kV Wood Pole Replacement - 1208 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | NR | No | [12 empty] | 8960000 | 8960000 | 9577000 | 9577000 | 9577000 | 9577000 | 9577000 | 9577000
Asset Condition | 1a | 229 | CT | Eversource |  |  | 2021-02-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1766 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | NR | No | [12 empty] | 16600000 | 16600000 | 16556000 | 16556000 | 16556000 | 16556000 | 16556000 | 16556000
Asset Condition | 1a | 214 | CT | Eversource |  |  | 2021-03-01 |  | 115 kV Wood Pole Replacement - 1042 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | No | [12 empty] | 6080000 | 6080000 | 8273000 | 8273000 | 8273000 | 8273000 | 8273000 | 8273000
Asset Condition | 1a | 228 | CT | Eversource |  |  | 2021-04-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1765 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | NR | [12 empty] | 14700000 | 14700000 | 8801000 | 8801000 | 3800000 | 3800000 | 3800000 | 3800000
Asset Condition | 1a | 79 | CT | Eversource |  |  | 2018-05-01 |  | 345 kV Structure Replacement Project - Line 398 | [6 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | 2019-12-16 | [6 empty] | 7800000 | 7800000 | 7800000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000
Asset Condition | 1a | 82 | CT | Eversource |  |  | 2020-05-01 |  | Laminated Structure Replacement Project - Line 1505/1607 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | No | [6 empty] | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000
Asset Condition | 1a | 127 | CT | Eversource |  |  | 2021-02-01 |  | 115 kV Structure Replacement Project - Line 1635 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | 2021-02-19 | [9 empty] | 5700000 | 5764000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000
Asset Condition | 1a | 134 | CT | Eversource |  |  | 2020-11-01 |  | 115 kV Structure Replacement Project - Line 1765 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | 2021-02-19 | [9 empty] | 12300000 | 12300000 | 12300000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000
Asset Condition | 1a | 122 | CT | Eversource |  |  | 2021-03-01 |  | 115 kV Structure Replacement Project - Line 1310 | [9 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | 2021-02-19 | [9 empty] | 8300000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000
Asset Condition | 1a | 246 | CT | Eversource |  |  | 2018-12-01 |  | Prior Year Wood Structure Asset Condition Replacement - Line 329 345 kV | [15 empty] | In-service | In-service | In-service | In-service | In-service | NR | No | [15 empty] | 5925000 | 5925000 | 5925000 | 5925000 | 5925000
Asset Condition | 1a | 247 | CT | Eversource |  |  | 2018-12-01 |  | Prior Year Wood Structure Asset Condition Replacement - Line 352 345 kV | [15 empty] | In-service | In-service | In-service | In-service | In-service | NR | No | [15 empty] | 5998000 | 5998000 | 5998000 | 5998000 | 5998000
Asset Condition | 1a | 215 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1043 | [12 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | No | [12 empty] | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000
Asset Condition | 1a | 163 | CT | Eversource |  |  | 2020-12-01 |  | 667 69 kV line rebuild and asset condition project | [10 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 7/25/2019 8/28/2020 | 2020-04-28 | [10 empty] | 24080000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000
Asset Condition | 1a | 120 | CT | Eversource |  |  | 2020-10-01 |  | 115 kV Structure Replacement Project - Line 1261/1598 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2021-02-19 | [9 empty] | 18300000 | 18300000 | 18300000 | 20352000 | 20352000 | 20352000 | 20352000 | 20352000 | 20352000 | 23854000 | 23854000
Asset Condition | 1a | 129 | CT | Eversource |  |  | 2020-08-01 |  | 115 kV Structure Replacement Project - Line 1726 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2021-02-19 | [9 empty] | 16300000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000
Asset Condition | 1a | 76 | CT | Eversource |  |  | 2020-05-01 |  | 345 kV Structure Replacement Project - Line 371 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | 12/16/2019 2/19/2020 | [6 empty] | 10600000 | 10600000 | 10600000 | 11546000 | 11546000 | 11546000 | 11546000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000
Asset Condition | 1a | 83 | CT | Eversource |  |  | 2020-05-01 |  | Laminated Structure Replacement Project - Line 1675/1080 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [6 empty] | 17800000 | 17800000 | 17800000 | 17800000 | 17800000 | 17800000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000
Asset Condition | 1a | 89 | CT | Eversource |  |  | 2020-06-01 |  | Montville 16X Transformer Replacement | [7 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | 2018-05-16 | NR | [7 empty] | 6300000 | 6300000 | 6300000 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676
Asset Condition | 1a | 119 | CT | Eversource |  |  | 2019-06-01 |  | 115 kV Structure Replacement Project - Line 1256 | [9 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 12200000 | 12200000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000
Asset Condition | 1a | 126 | CT | Eversource |  |  | 2019-04-01 |  | 115 kV Structure Replacement Project - Line 1620 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 10000000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000
Asset Condition | 1a | 168 | CT | Eversource |  |  | 2020-06-01 |  | 345 kV Structure Replacement Projects - Line 352 | [11 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 12500000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000
Asset Condition | 1a | 222 | CT | Eversource |  |  | 2020-06-01 |  | 115 kV Wood Pole Replacement - Line 1505 | [12 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [12 empty] | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000
Asset Condition | 1a | 231 | CT | Eversource |  |  | 2020-04-01 |  | 115 kV Line Rebuild and Asset Condition Project - Line 1355 | [12 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [12 empty] | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000
Asset Condition | 1a | 17 | CT | United Illuminating Company |  |  | 2020-06-01 |  | East Shore 345 kV circuit switcher replacement project. Replace 345 kV circuit switchers with dead tank breakers |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In Service | In Service | In Service | In Service | In Service | In-service | In-service | 2016-07-19 | 2019-10-30 |  |  | 10931000 | 10931000 | 10931000 | 10931000 | 9234000 | 9234000 | 9234000 | 9234000 | 9234000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000
Asset Condition | 1a | 18 | CT | United Illuminating Company |  |  | 2020-06-01 | UI Coastal Substation Flood Mitigation Study Project | East Shore - Raising Impacted 115 kV Equipment |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In Service | In Service | In Service | In Service | In Service | In-service | In-service | NR | 2019-10-30 |  |  |  | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000
Asset Condition | 1a | 70 | CT | Eversource |  |  | 2020-04-01 |  | Oil Circuit Breaker Replacement Project at the Plumtree Substation | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [6 empty] | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000
Asset Condition | 1a | 197 | CT | United Illuminating Company |  |  | 2019-10-01 |  | 1130 Line Optical Ground Wire (OPGW) Replacement | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-10-30 | [11 empty] | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000
Asset Condition | 1a | 171 | CT | Eversource |  |  | 2019-12-01 |  | 345 kV Structure Replacement Projects - Line 368 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 7300000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000
Asset Condition | 1a | 175 | CT | Eversource |  |  | 2019-10-01 |  | 345 kV Structure Replacement Projects - Line 3252 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000
Asset Condition | 1a | 177 | CT | Eversource |  |  | 2019-07-01 |  | 345 kV Structure Replacement Projects - Line 3424 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 7900000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000
Asset Condition | 1a | 193 | CT | Eversource |  |  | 2019-12-01 |  | 115 kV Structure Replacement Projects - Line 1470 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [11 empty] | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000
Asset Condition | 1a | 50 | CT | Eversource |  |  | 2019-11-01 | Eversource Energy Autotransformer Replacement Plan | Replace the Card 11F-5X autotransformer. Foundation and bus upgrades to accommodate new transformer specifications | [5 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2018-05-16 | No | [5 empty] | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000
Asset Condition | 1a | 49 | CT | Eversource |  |  | 2020-01-01 |  | Southern CT Loop Line Structure Replacements - 1655 115 kV | [5 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 06/30/2020 | [5 empty] | 14800000 | 14800000 | 14800000 | 14800000 | 17100000 | 17100000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000
Asset Condition | 1a | 137 | CT | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line 1769 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 8200000 | 8200000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000
Asset Condition | 1a | 140 | CT | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line 1783 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 8200000 | 8200000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000
Asset Condition | 1a | 141 | CT | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line 1785 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 9000000 | 9000000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000
Asset Condition | 1b | 165 | CT | Eversource |  |  | 2019-12-01 |  | 345 kV Structure Replacement Projects - Line 321 | [11 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 6500000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000
Asset Condition | 1a | 169 | CT | Eversource |  |  | 2019-08-07 |  | 345 kV Structure Replacement Projects - Line 362 | [11 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000
Asset Condition | 1a | 174 | CT | Eversource |  |  | 2019-07-01 |  | 345 kV Structure Replacement Projects - Line 3041 | [11 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000
Asset Condition | 1b | 84 | CT | Eversource |  |  | 2018-12-01 |  | Laminated Structure Replacement Project - Line 1921 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [6 empty] | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000
Asset Condition | 1a | 135 | CT | Eversource |  |  | 2018-06-01 |  | 115 kV Structure Replacement Project - Line 1766 | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 5800000 | 5800000 | 5800000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000
Asset Condition | 1a | 115 | CT | Eversource |  |  | 2019-09-01 |  | 1608 115 kV Line Cable Replacement | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2019-12-19 | 2020-04-28 | [9 empty] | 11300000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000
Asset Condition | 1a | 117 | CT | Eversource |  |  | 2019-05-01 |  | 115 kV Structure Replacement Project - Line 1050 | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 7300000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000
Asset Condition | 1a | 47 | CT | Eversource |  |  | 2019-05-01 |  | Southern CT Loop Line Structure Replacements - 1342 115 kV | [5 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-10 | [5 empty] | 30300000 | 30300000 | 30300000 | 30300000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000
Asset Condition | 1a | 68 | CT | Eversource |  |  | 2019-04-01 |  | Card-Montville-Tunnel Corridor Asset Condition and OPGW Installation Project | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-10-16 | [6 empty] | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000
Asset Condition | 1a | 73 | CT | Eversource |  |  | 2018-11-01 |  | 345 kV Structure Replacement Project - Line 330 | [6 empty] | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 13500000 | 13500000 | 13500000 | 13500000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000
Asset Condition | 1a | 116 | CT | Eversource |  |  | 2019-01-01 |  | 1880 115 kV Line Cable Replacement | [9 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-04-28 | [9 empty] | 7200000 | 7200000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000
Asset Condition | 1a | 34 | CT | Eversource |  |  | 2018-12-01 |  | Devon Control House Modifications |  |  |  |  | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-04-17 |  |  |  |  | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000
Asset Condition | 1a | 69 | CT | Eversource |  |  | 2018-12-01 |  | Oil Circuit Breaker Replacement Project at the Frost Bridge Substation | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-08-24 | [6 empty] | 7250000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000
Asset Condition | 1a | 71 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 310 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 16500000 | 16500000 | 16500000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000
Asset Condition | 1a | 72 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 321 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 12/16/2019 2/19/202 | [6 empty] | 6000000 | 6000000 | 6000000 | 5847000 | 5847000 | 5847000 | 5847000 | 5847000 | 5847000 | 7462000 | 7462000 | 7462000 | 7462000 | 7462000
Asset Condition | 1a | 75 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 364 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 14300000 | 14300000 | 14300000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000
Asset Condition | 1a | 74 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 348 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 16000000 | 16000000 | 16000000 | 16000000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000
Asset Condition | 1a | 77 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 383 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 15500000 | 15500000 | 15500000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000
Asset Condition | 1a | 78 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 387 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 13100000 | 13100000 | 13100000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000
Asset Condition | 1a | 80 | CT | Eversource |  |  | 2018-07-01 |  | 345 kV Structure Replacement Project - Line 3041 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 9700000 | 9700000 | 9700000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000
Asset Condition | 1a | 81 | CT | Eversource |  |  | 2018-09-01 |  | 345 kV Structure Replacement Project - Line 3642 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 9900000 | 9900000 | 9900000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000
Asset Condition | 1a | 125 | CT | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1565 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 11500000 | 11500000 | 11500000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000
Asset Condition | 1a | 131 | CT | Eversource |  |  | 2018-11-01 |  | 115 kV Structure Replacement Project - Line 1751 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 12500000 | 12500000 | 12500000 | Part of Asset Condition #226 | Part of Asset Condition #226 | Part of Asset Condition #226 | Part of Asset Condition #226 | Part of Asset Condition #226 | 4467000 | 4467000 | 4467000
Asset Condition | 1a | 133 | CT | Eversource |  |  | 2018-09-01 |  | 115 kV Structure Replacement Project - Line 1759 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 7300000 | 7300000 | 7300000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000
Asset Condition | 1a | 136 | CT | Eversource |  |  | 2018-04-01 |  | 115 kV Structure Replacement Project - Line 1767 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 5400000 | 5400000 | 5400000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000
Asset Condition | 1a | 138 | CT | Eversource |  |  | 2018-10-01 |  | 115 kV Structure Replacement Project - Line 1770 (the 1770 line has been replaced by the Plumtree to Stony Hill 1268 line and the Stony Hill to Bates Rock 1485 line) | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 16300000 | 16300000 | 16300000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000
Asset Condition | 1a | 142 | CT | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1768-CT | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 5200000 | 5200000 | 5200000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000
Asset Condition | 1a | 143 | CT | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1910 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 5800000 | 5800000 | 5800000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000
Asset Condition | 1a | 48 | CT | Eversource |  |  | 2018-07-01 |  | Southern CT Loop Line Structure Replacements - 1508 115 kV | [5 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-08-24 | [5 empty] | 16600000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000
Asset Condition | 1a | 46 | CT | Eversource |  |  | 2017-12-01 |  | Southern CT Loop Line Structure Replacements - 1261/1598 115 kV | [5 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-04-17 | [5 empty] | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000
Asset Condition | 1a | 33 | CT | Eversource |  |  | 2017-06-01 |  | 1410 and 100 Line Structure Replacements |  |  |  |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2017-12-01 |  |  |  |  | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000
Asset Condition | 1a | 39 | CT | Eversource |  |  | 2017-11-01 |  | 3419 line (portion in Connecticut) asset condition and OPGW project |  |  |  |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-02 |  |  |  |  | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38
Asset Condition | 1a | 29 | CT | Eversource |  |  | 2017-09-01 |  | 1620/1975 line structure replacement |  |  |  | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 12/1/2017 2/19/2021 |  |  |  | 15500000 | 12500000 | 11093000 | 11093000 | 11093000 | 11093000 | 11093000 | 11093000 | 11093000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000
Asset Condition | 1a | 30 | CT | Eversource |  |  | 2016-12-01 |  | 3424 line Asset Condition and Storm Hardening |  |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-03 |  |  |  | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000
Asset Condition | 1a | 16 | CT | Eversource |  |  | 2016-06-01 |  | 3419 line (portion in Connecticut) asset condition and storm hardening. Asset conditon - replace 24 wood poles H-frame with direct embed steel wood pole equivalent or wood located in MA & CT. |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-03 |  |  | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1
Asset Condition | 1a | 6 | CT | Eversource |  |  | 2014-09-01 |  | 1570 line clearance remediation. Devon S/S to Beacon Falls S/S. 31 conductor span locations were found to have NESC clearance discrepancies. | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2016-12-16 | 6500000 | 6500000 | 6500000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000
Massachusetts
Asset Condition | 1a | 296 | MA | National Grid, USA |  |  | 2022-03-01 |  | X-176 115 kV Line Asset Condition Refurbishments | [17 empty] | Planned | Under Construction | In-service | NR | 2022-04-11 | [17 empty] | 18520000 | 18520000 | 18520000
Asset Condition | 1a | 65 | MA | Eversource |  |  | 2020-06-01 |  | Laminated Structure Replacement Project - Line 1512 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [6 empty] | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000
Asset Condition | 1a | 299 | MA | Eversource |  |  | 2021-12-01 |  | 115 kV Structure Replacements - Line 456-522 | [17 empty] | Under Construction | In-Service | In-Service | NR | No | [17 empty] | 5672000 | 5672000 | 5672000
Asset Condition | 1a | 300 | MA | Eversource |  |  | 2021-11-01 |  | 115 kV Structure Replacements - Line 240-510 | [17 empty] | Under Construction | In-Service | In-Service | NR | No | [17 empty] | 11636000 | 11636000 | 11636000
Asset Condition | 1a | 253 | MA | Eversource |  |  | 2021-10-01 |  | 345 kV Line Structure Replacement - Line 338 | [15 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | NR | No | [15 empty] | 8700000 | 8700000 | 8700000 | 8700000 | 8700000
Asset Condition | 1a | 207 | MA | Eversource |  |  | 2021-10-01 |  | 115 kV Wood Pole Replacement - 1161 | [12 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | NR | No | [12 empty] | 17100000 | 17100000 | 17100000 | 22578000 | 22578000 | 22578000 | 22578000 | 22578000
Asset Condition | 1b | 301 | MA | Eversource |  |  | 2021-11-01 |  | 230 kV Structure Replacements - Line 342-603 | [17 empty] | Proposed | In-Service | In-Service | NR | No | [17 empty] | 5451000 | 5451000 | 5451000
Asset Condition | 1a | 295 | MA | National Grid, USA |  |  | 2022-02-01 |  | C-129N/D-130 115 kV Line Fiber Installation | [17 empty] | Under Construction | In-service | In-service | NR | 2022-04-11 | [17 empty] | 11220000 | 11220000 | 11220000
Asset Condition | 1a | 304 | MA | Eversource |  |  | 2021-04-01 |  | 478-508 & 478-509 115 kV Lines Asset Condition & OPGW | [17 empty] | In-Service | In-Service | In-Service | NR | No | [17 empty] | 5866000 | 5866000 | 5866000
Asset Condition | 1b | 252 | MA | Eversource |  |  | 2021-06-01 |  | 345 kV Line Structure Replacement - Line 319 | [15 empty] | Proposed | Proposed | In-service | In-service | In-service | NR | No | [15 empty] | 7800000 | 7800000 | 7838000 | 7838000 | 7838000
Asset Condition | 1a | 107 | MA | Eversource |  |  | 2021-06-01 |  | 349X/Y 345 kV Cable Replacement | [9 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | 2019-10-07 | 06/30/2020 | [9 empty] | 72400000 | 72400000 | 72400000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000
Asset Condition | 1a | 210 | MA | Eversource |  |  | 2021-03-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1394 | [12 empty] | Proposed | Proposed | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | No | [12 empty] | 7070000 | 7070000 | 7070000 | 8877000 | 8877000 | 8877000 | 8877000 | 8877000
Asset Condition | 1a | 212 | MA | Eversource |  |  | 2021-03-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1976 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | No | [12 empty] | 7470000 | 7470000 | 9688000 | 9688000 | 9688000 | 9688000 | 9688000 | 9688000
Asset Condition | 1b | 254 | MA | Eversource |  |  | 2021-04-01 |  | 115 kV Wood Pole Asset Condition Project - Line 455-507 | [15 empty] | Proposed | In-Service | In-Service | In-Service | In-Service | NR | No | [15 empty] | 5191000 | 5191000 | 5191000 | 5191000 | 5191000
Asset Condition | 1a | 64 | MA | Eversource |  |  | 2021-03-01 |  | 345 kV Structure Replacement Project - Line 393 | [6 empty] | Proposed | Proposed | Proposed | In-service | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | 2019-12-16 | [6 empty] | 10000000 | 10000000 | 10000000 | 10000000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000
Asset Condition | 1a | 184 | MA | Eversource |  |  | 2021-03-01 |  | 345 kV Structure Replacement Project - Line 393 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | No | [11 empty] | 11000000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000
Asset Condition | 1a | 248 | MA | Eversource |  |  | 2017-12-01 |  | Prior Year Wood Structure Asset Condition Replacement - Line 338 345 kV | [15 empty] | In-service | In-service | In-service | In-service | In-service | NR | No | [15 empty] | 5804000 | 5804000 | 5804000 | 5804000 | 5804000
Asset Condition | 1a | 249 | MA | Eversource |  |  | 2019-06-01 |  | Prior Year Wood Structure Asset Condition Replacement - Line 455-507 115 kV | [15 empty] | In-service | In-service | In-service | In-service | In-service | NR | No | [15 empty] | 10296000 | 10296000 | 10296000 | 10296000 | 10296000
Asset Condition | 1a | 209 | MA | Eversource |  |  | 2020-10-01 |  | 115 kV Wood Pole Replacement - 1512 | [12 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | No | [12 empty] | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000
Asset Condition | 1a | 32 | MA | Eversource |  |  | 2020-12-01 |  | West Medway Substation #446 Asset Condition Upgrade |  |  |  |  | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2017-12-01 |  |  |  |  | 18900000 | 18900000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000
Asset Condition | 1a | 42 | MA | Eversource |  |  | 2020-12-01 |  | Brighton #329 115 kV Control House | [5 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2018-04-17 | [5 empty] | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000
Asset Condition | 1a | 147 | MA | National Grid, USA |  |  | 2022-02-01 |  | 303 Line Asset Condition Refurbishments | [9 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 24700000 | 24700000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000
Asset Condition | 1a | 148 | MA | National Grid, USA |  |  | 2020-05-01 |  | 3520 Line Asset Condition Refurbishments | [9 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 6900000 | 6900000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000
Asset Condition | 1a | 211 | MA | Eversource |  |  | 2020-07-01 |  | 115 kV Wood Pole and Shield Wire Replacement - Line 1858 | [12 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [12 empty] | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000
Asset Condition | 1b | 238 | MA | Eversource |  |  | 2020-06-01 |  | 115 kV Granville Junction to Atwater 1853 line (formerly 1512) OPGW Project | [13 empty] | Proposed | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | NR | [13 empty] | 5000000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000
Asset Condition | 1a | 180 | MA | Eversource |  |  | 2019-08-01 |  | 345 kV Structure Replacement Projects - Line 3361 | [11 empty] | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 6300000 | 6300000 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951
Asset Condition | 1b | 185 | MA | Eversource |  |  | 2020-03-01 |  | 345 kV Structure Replacement Projects - Line 3419 | [11 empty] | Proposed | Proposed | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | No | [11 empty] | 26000000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000
Asset Condition | 1a | 108 | MA | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line 65-508 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 19500000 | 19500000 | 19500000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000
Asset Condition | 1a | 112 | MA | Eversource |  |  | 2019-12-01 |  | 115 kV Structure Replacement Project - Line 1962 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 20300000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000
Asset Condition | 1a | 114 | MA | Eversource |  |  | 2019-11-01 |  | 115 kV Structure Replacement Project - Line F132 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 11000000 | 11000000 | 11000000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000
Asset Condition | 1a | 179 | MA | Eversource |  |  | 2019-10-01 |  | 345 kV Structure Replacement Projects - Line 336 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 6600000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000
Asset Condition | 1a | 182 | MA | Eversource |  |  | 2019-11-01 |  | 345 kV Structure Replacement Projects - Line 354 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 29600000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000
Asset Condition | 1b | 183 | MA | Eversource |  |  | 2019-09-01 |  | 345 kV Structure Replacement Projects - Line 381 | [11 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 12500000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000
Asset Condition | 1a | 88 | MA | National Grid, USA |  |  | 2019-12-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 1 | [6 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [6 empty] | 1384000 | 1384000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2908881 | 2908881 | 2908881
Asset Condition | 1a | 66 | MA | Eversource |  |  | 2019-05-01 |  | Laminated Structure Replacement Project - Line 1211/1161 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [6 empty] | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12598500 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000
Asset Condition | 1a | 109 | MA | Eversource |  |  | 2019-03-01 |  | 115 kV Structure Replacement Project - Line 1327 | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [9 empty] | 7800000 | 7800000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000
Asset Condition | 1a | 110 | MA | Eversource |  |  | 2019-03-01 |  | 115 kV Structure Replacement Project - Line 1428 | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 12100000 | 12100000 | 12100000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000
Asset Condition | 1a | 15 | MA | Eversource |  |  | 2019-05-01 |  | Install a new Medway control house which is to be built to BPS standards in a location within the existing station footprint. |  |  | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2016-01-26 | 2017-07-17 |  |  | 11800000 | 11800000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000
Asset Condition | 1a | 37 | MA | Eversource |  |  | 2018-11-01 |  | New Mt. Tom protection system control house |  |  |  |  | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-10-16 |  |  |  |  | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000
Asset Condition | 1a | 62 | MA | Eversource |  |  | 2018-12-01 |  | Oil Circuit Breaker Replacement Project at the Agawam Substation | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [6 empty] | 5400000 | 5400000 | 5400000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000
Asset Condition | 1a | 111 | MA | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1447 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [9 empty] | 6600000 | 6600000 | 6600000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000
Asset Condition | 1a | 113 | MA | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1768-MA | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 3000000 | 3000000 | 3000000 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142
Asset Condition | 1a | 45 | MA | Eversource |  |  | 2018-07-01 |  | 345 kV 354 Line Structure Replacements | [5 empty] | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-10-16 | [5 empty] | 10148000 | 10148000 | 7017000 | 7017000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000
Asset Condition | 1a | 40 | MA | National Grid, USA |  | 1 | 2018-05-01 |  | Salem Harbor Substation - 115 kV oil circuit breaker replacements |  |  |  |  | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR |  |  |  |  | 6000000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000
Asset Condition | 1a | 61 | MA | Eversource |  |  | 2017-09-01 |  | 1231/1242 Structure Replacement Project | [6 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-02-15 | [6 empty] | 7966000 | 7966000 | 7966000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000
Asset Condition | 1a | 38 | MA | Eversource |  |  | 2017-12-01 |  | 3419 line (portion in Massachusetts) asset condition and OPGW project |  |  |  |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-03 |  |  |  |  | 13700000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000
Asset Condition | 1a | 41 | MA | Eversource |  |  | 2013-06-01 |  | Scotia Street Substation Project | [5 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2017-07-17 | [5 empty] | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000
Asset Condition | 1a | 12 | MA | Eversource |  |  | 2017-07-01 |  | Doreen-Oswald Jct. 1211 115 kV Line Structure Replacement |  | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-03 |  | 14800000 | 14800000 | 14800000 | 11500000 | 11500000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000
Asset Condition | 1a | 31 | MA | Eversource |  |  | 2016-05-01 |  | 345 kV GIS breaker replacements at Kingston Street #514 |  |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-05-11 |  |  |  | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000
Asset Condition | 1a | 13 | MA | Eversource |  |  | 2017-01-01 |  | Ludlow-Thorndike-Palmer (WMA portion) of the X176 115 KV Line Rebuild |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2016-12-16 |  | 14900000 | 8928000 | 8928000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000
Asset Condition | 1a | 2 | MA | National Grid, USA |  |  | 2016-10-01 | Crystal Lake Substation Upgrades | Crystal Lake Substation Upgrades | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2016-05-05 | 2018-10-10 | 6950000 | 6950000 | 6950000 | 6950000 | 6950000 | 6950000 | 6950000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000
Asset Condition | 1a | 1 | MA | Eversource |  |  | 2016-06-01 |  | 3419 line (portion in Massachusetts) asset condition and storm hardening. Asset condition - replace 24 wood poles H-frame with direct embed steel wood pole equivalent or wood located in MA & CT. | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 01/03/2018 | 14500000 | 14500000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000
Asset Condition | 1a | 14 | MA | Eversource |  |  | 2015-12-01 |  | 1231/1242 Line Clearance remediation Project |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2016-12-16 |  |  | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000
Asset Condition | 1a | 7 | MA | Eversource |  |  | 2015-12-01 |  | 115 kV line 136 Falmouth Tap - West Barnstable Complete structure replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2015-11-25 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000
Asset Condition | 1a | 8 | MA | Eversource |  |  | 2015-05-01 |  | 381 Line Structure Replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2015-11-25 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000
Asset Condition | 1a | 9 | MA | Eversource |  |  | 2015-12-01 |  | 354 Line Structure Replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2015-11-25 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000
Asset Condition | 1a | 10 | MA | Eversource |  |  | 2014-07-01 |  | 312 Line Structure Replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2015-11-25 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000
Rhode Island
Asset Condition | 1a | 54 | RI | National Grid, USA |  |  | 2019-12-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 1 | [6 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | NR | [6 empty] | 427000 | 427000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1174157 | 1174157 | 1174157
CANCELLED PROJECTS
Asset Condition | 1b | 226 | CT | Eversource |  |  | 2023-12-11 |  | 115 kV Wood Pole Replacement - 1751 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | NR | No | [12 empty] | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000
Asset Condition | 1b | 93 | VT | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 4 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No
Asset Condition | 1b | 106 | NH | Eversource |  |  | 2023-12-11 |  | 115 kV Structure Replacement Project - Line X178 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000
Asset Condition | 1b | 118 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Structure Replacement Project - Line 1191 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000
Asset Condition | 1b | 121 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Structure Replacement Project - Line 1280 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000
Asset Condition | 1b | 123 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Structure Replacement Project - Line 1410 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000
Asset Condition | 1b | 132 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Structure Replacement Project - Line 1756 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 7000000 | 7000000 | 7000000 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227
Asset Condition | 1a | 128 | CT | Eversource |  |  | 2019-12-01 |  | 115 kV Structure Replacement Project - Line 1675 | [9 empty] | Proposed | Under Construction | Cancelleed | Cancelleed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000
Notes:
1 The original cost for Asset Condition project #40 was above the $5 million threshold. The current project is close to the threshold so this project will remain on the list.
2 Individual projects are less than $5M each.
Grandfathered projects on May 18, 2015 are not applicable to the Asset Condition list
Asset Condition List - Status Definitions:
The Section #'s designate the "need" category of the project. Original categories are not changed when a project is placed In-service or Cancelled
Sections - These projects are Asset Condition Upgrades
1a: Planned or Under construction
1b: Concept or Proposed
Concept - Project is under consideration to address an asset condition issue that have be presented to PAC or TOPAC. Costs are not provided
Proposed - Asset owner has determined that the solution is appropriate to address the asset condition issue and the solution has been presented to the P A C. Costs must be provided
Planned - PPA has been approved, if needed. Costs must be provided
Under Construction - Implementation of project is underway Costs must be provided
In-service - Project is in-service. Costs must be provided
Description of PAC interaction and inclusion on the Asset Condition list:
1. If the asset condition issue is on PTF and the PTF cost is greater than $5M, a presentation will be made to the PAC and the project will be added to the Asset Condition list.
2. If the asset condition issue is on the PTF and non-PTF, a presentation will be made to the TOPAC and if the cost of the PTF portion is greater than $5M, a presentation will be made to the PAC and the project will be added to the Asset Condition list.
3. If the asset condition issue is only on the non-PTF, but the corrective action results in changes to the PTF, a presentation will be made to the TOPAC and the project will be added to the Asset Condition list. There is no requirement to discuss the project with the PAC.

## ACL_sortable
Primary Driver | Section # | Asset Condition ID | State | Primary Equipment Owner | Other Equipment Owner(s) | Footnote Number | Projected In-Service Month/Year | Asset Condition Grouping | Description | Mar-16 Status | Jun-16 Status | Oct-16 Status | Mar-17 Status | Jun-17 Status | Oct-17 Status | Mar-18 Status | Jun-18 Status | Oct-18 Status | Mar-19 Status | Jun-19 Status | Oct-19 Status | Mar-20 Status | Jun-20 Status | Oct-20 Status | Mar-21 Status | Jun-21 Status | Oct-21 Status | Mar-22 Status | Jun-22 Status | PPA (I.3.9) Approval | TCA Approval | Mar-16 Estimated PTF Costs | Jun-16 Estimated PTF Costs | Oct-16 Estimated PTF Costs | Mar-17 Estimated PTF Costs | Jun-17 Estimated PTF Costs | Oct-17 Estimated PTF Costs | Mar-18 Estimated PTF Costs | Jun-18 Estimated PTF Costs | Oct-18 Estimated PTF Costs | Mar-19 Estimated PTF Costs | Jun-19 Estimated PTF Costs | Oct-19 Estimated PTF Costs | Mar-20 Estimated PTF Costs | Jun-20 Estimated PTF Costs | Oct-20 Estimated PTF Costs | Mar-21 Estimated PTF Costs | Jun-21 Estimated PTF Costs | Oct-21 Estimated PTF Costs | Mar-22 Estimated PTF Costs | Jun-22 Estimated PTF Costs
Asset Condition | 1a | 326 | NH | Eversource |  |  | 2022-12-01 |  | Laminated Wood Structure Replacement Program Phase II - S188 115 kV Line | [18 empty] | Under Construction | Under Construction | NR | No | [18 empty] | 7342000 | 7342000
Asset Condition | 1a | 327 | NH | Eversource |  |  | 2022-02-01 |  | Laminated Wood Structure Replacement Program Phase II - M164 115 kV Line | [18 empty] | Under Construction | In-Service | NR | No | [18 empty] | 6024000 | 6024000
Asset Condition | 1a | 289 | NH | Eversource |  |  | 2022-05-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - K105 Line | [16 empty] | Proposed | Proposed | Under Construction | Under Construction | NR | No | [16 empty] | 14700000 | 14700000 | 16503000 | 16503000
Asset Condition | 1a | 290 | NH | Eversource |  |  | 2022-12-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - X116 Line | [16 empty] | Proposed | Proposed | Under Construction | Under Construction | NR | No | [16 empty] | 26000000 | 26000000 | 24646000 | 24646000
Asset Condition | 1a | 291 | NH | Eversource |  |  | 2022-12-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - Z119 Line | [16 empty] | Proposed | Proposed | Under Construction | Under Construction | NR | No | [16 empty] | 25400000 | 25400000 | 23443000 | 23443000
Asset Condition | 1a | 298 | NH | Eversource |  |  | 2022-05-01 |  | 115 kV Structure and Shield Wire Replacements - Line D121 | [17 empty] | Under Construction | Under Construction | Under Construction | NR | No | [17 empty] | 13105000 | 13105000 | 13105000
Asset Condition | 1a | 278 | NH | Eversource |  |  | 2022-11-01 |  | Amherst substation Protection & Controls Upgrades | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | NR | 2021-08-21 | [15 empty] | 6100000 | 6100000 | 6100000 | 6100000 | 6081000
Asset Condition | 1a | 279 | NH | Eversource |  |  | 2022-11-01 |  | Webster-Beebe River 115 kV Corridor Asset Condition and OPGW Project - A111 Line | [15 empty] | Proposed | Proposed | Planned | Under Construction | Under Construction | 2021-07-15 | No | [15 empty] | 35940000 | 35940000 | 53501000 | 53501000 | 53501000
Asset Condition | 1a | 280 | NH | Eversource |  |  | 2023-12-11 |  | Webster-Beebe River 115 kV Corridor Asset Condition and OPGW Project - E115 Line | [15 empty] | Proposed | Proposed | Planned | Planned | Planned | 2021-07-15 | No | [15 empty] | 55116000 | 55116000 | 55116000 | 55116000 | 55116000
Asset Condition | 1a | 281 | NH | Eversource |  |  | 2024-06-01 |  | Webster-Beebe River 115 kV Corridor Asset Condition and OPGW Project - Z180 Line | [15 empty] | Proposed | Proposed | Planned | Planned | Planned | 2021-07-15 | No | [15 empty] | 9669000 | 9669000 | 9669000 | 9669000 | 9669000
Asset Condition | 1a | 282 | NH | Eversource |  |  | 2022-12-01 |  | 345 kV Line Structure Replacements - Line 373 | [15 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [15 empty] | 9351000 | 9351000 | 9351000 | 9351000 | 9351000
Asset Condition | 1a | 203 | NH | Eversource |  |  | 2022-04-01 |  | 115 kV Wood Pole and Shield Wire Replacement - K174 | [12 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | NR | No | [12 empty] | 14740000 | 14740000 | 14740000 | 16240000 | 16240000 | 16240000 | 16240000 | 16240000
Asset Condition | 1a | 87 | NH | New Hampshire Transmission |  |  | 2022-06-01 | Seabrook 345 kV GIS Switchyard Phase 3 Equipment Replacement Part of Asset Condition #85 | Phase 3 of multi-phase project involving like for like equipment replacement. Phase 3 includes replacing three approximately 1,000 ft. long horizontal gas-insulated lines (GIL) comprising the three phases of the 345 kV Seabrook-Ward Hill 394 line, and replacing two GIS 345 kV Circuit Breakers and related switches that are the 394 line termination equipment. Post-top insulators located in the open-air to GIS transition yard will also be replaced. Phase 3 also includes replacing Breaker Failure Relay Protection Systems for the 394 line. | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2019-04-21 | [6 empty] | Part of Project #86 | Part of Project #86 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85
Asset Condition | 1a | 283 | VT | Vermont Electric Power Company |  |  | 2022-12-01 |  | Line K22 Asset Condition Structure Refurbishment | [15 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-08-20 | [15 empty] | 9720000 | 9720000 | 9720000 | 9720000 | 9720000
Asset Condition | 1a | 284 | VT | Vermont Electric Power Company |  |  | 2024-12-01 |  | Line K24 Asset Condition Structure Refurbishment | [15 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-08-20 | [15 empty] | 15240000 | 15240000 | 15240000 | 15240000 | 15240000
Asset Condition | 1a | 285 | VT | Vermont Electric Power Company |  |  | 2022-12-01 |  | Line K34 Asset Condition Structure Refurbishment | [15 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-08-20 | [15 empty] | 6710000 | 6710000 | 6710000 | 6710000 | 6710000
Asset Condition | 1a | 232 | VT | Vermont Electric Power Company |  |  | 2025-12-01 |  | Line 340 Asset Condition Structure Refurbishment | [13 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-01-29 | [13 empty] | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000
Asset Condition | 1a | 306 | MA | National Grid, USA |  |  | 2023-05-01 |  | V-174 115 kV Line Asset Condition Refurbishments and OPGW installation | [18 empty] | Under Construction | Under Construction | NR | No | [18 empty] | 26300000 | 26300000
Asset Condition | 1a | 307 | MA | National Grid, USA |  |  | 2022-05-01 |  | M-139/N-140 115 kV Lines Pilot Protection Schemes | [18 empty] | Under Construction | Under Construction | NR | No | [18 empty] | 9400000 | 9400000
Asset Condition | 1a | 251 | MA | Eversource |  |  | 2022-12-01 |  | 345 kV Line Structure Replacement - Line 312 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | NR | No | [15 empty] | 19300000 | 19300000 | 21160000 | 21160000 | 21160000
Asset Condition | 1a | 237 | MA | National Grid, USA |  |  | 2027-12-01 |  | A-1 & B-2 69 kV Line Asset Condition Project | [13 empty] | Concept | Concept | Concept | Concept | Proposed | Planned | Planned | 2020-06-02 | No | [17 empty] | 347300000 | 347300000 | 347300000
Asset Condition | 1a | 294 | MA | National Grid, USA |  |  | 2025-08-01 |  | Millbury #2 Substation Protection Scheme Upgrade and Asset Condition Refurbishments | [17 empty] | Planned | Under Construction | Under Construction | NR | 2022-04-11 | [17 empty] | 28040000 | 28040000 | 28040000
Asset Condition | 1a | 296 | MA | National Grid, USA |  |  | 2022-03-01 |  | X-176 115 kV Line Asset Condition Refurbishments | [17 empty] | Planned | Under Construction | In-service | NR | 2022-04-11 | [17 empty] | 18520000 | 18520000 | 18520000
Asset Condition | 1a | 297 | MA | Eversource |  |  | 2025-12-01 |  | 282-520 & 282-521 115 kV Lines HPFF Refurbishment | [17 empty] | Planned | Planned | Planned | NR | No | [17 empty] | 69600000 | 69600000 | 69600000
Asset Condition | 1b | 329 | MA | Eversource |  |  | 2022-12-01 |  | 115 kV Line Structure and OPGW Replacements - Line 1428 | [19 empty] | Proposed | NR | No | [19 empty] | 7994000
Asset Condition | 1a | 270 | MA | National Grid, USA |  |  | 2022-06-01 |  | S-145/T-146 115 kV Line Reconductoring - North Reading Substation to Wallace Substation | [15 empty] | Planned | Planned | Planned | Under Construction | Under Construction | 2020-12-11 | No | [15 empty] | 16540000 | 16540000 | 16540000 | 16540000 | 16540000
Asset Condition | 1a | 240 | MA | National Grid, USA |  |  | 2022-10-01 | Boston 2028 Project | Rebuild the Golden Hills #90 Substation | [14 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-04-08 | [14 empty] | 9345000 | 10180000 | 10180000 | 10180000 | 10180000 | 10180000
Asset Condition | 1a | 194 | MA | Eversource |  |  | 2023-12-01 |  | 110-510 & 110-511 lines 115 kV HPFF refurbishment | [11 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | 2020-04-29 | No | [11 empty] | 95000000 | 95000000 | 95000000 | 95000000 | 95000000 | 95000000 | 97995000 | 97995000 | 97995000
Asset Condition | 1a | 208 | MA | Eversource |  |  | 2022-12-01 |  | 115 kV Wood Pole Replacement - 1421 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [12 empty] | 15750000 | 15750000 | 22656000 | 22656000 | 22656000 | 22656000 | 22656000 | 22656000
Asset Condition | 1a | 63 | MA | Eversource |  |  | 2023-06-01 |  | Lexington Station #320 Asset Condition Upgrade Project | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 07/01/2020 | [6 empty] | 14300000 | 14300000 | 14300000 | 14300000 | 14300000 | 14300000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000
Asset Condition | 1a | 28 | MA | Eversource |  |  | 2023-06-01 |  | 115 kV GIS breaker replacement at Kingston Street #514 Substation |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 07/01/2020 |  |  |  | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 39082000 | 39082000 | 39082000 | 39082000 | 39082000 | 39082000 | 39082000 | 39082000
Asset Condition | 1a | 90 | MA | Eversource |  |  | 2023-12-11 |  | Canal Station #980 BPS and Asset Condition Upgrade Project | [8 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 06/30/2020 | [8 empty] | 17923000 | 17923000 | 17923000 | 17923000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000
Asset Condition | 1a | 43 | MA | Eversource |  |  | 2022-12-01 |  | K Street #385 115 kV Control House | [5 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2018-04-17 | [5 empty] | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000
Asset Condition | 1a | 44 | MA | Eversource |  |  | 2026-12-01 |  | Mystic #250 115 kV Control House | [5 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2018-04-17 | [5 empty] | 23900000 | 23900000 | 23900000 | 23900000 | 23900000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000
Asset Condition | 1a | 53 | MA | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 2 | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [6 empty] | 12353000 | 12353000 | 11353000 | 11353000 | 11353000 | 13044000 | 13044000 | 13044000 | 13044000 | 13044000 | 13044000 | 13044000 | 17732000 | 17732000
Asset Condition | 1a | 25 | MA | Taunton Municipal Light Plant |  |  | 2022-09-01 |  | Cleary 115 kV ring bus asset replacement - replace existing ring bus with new 115 kV switching station on an adjacent site and reconnect lines and transformers |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | NR |  |  |  | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000
Asset Condition | 1a | 26 | MA | Eversource |  |  | 2023-12-01 |  | Rebuild Bourne Substation as a breaker and one half scheme |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | 2018-04-30 | 2021-08-21 |  |  |  | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 76000000 | 76000000 | 76000000 | 76000000 | 69893000 | 69893000 | 69893000 | 69893000
Asset Condition | 1a | 27 | MA | Eversource |  |  | 2023-12-11 |  | Kingston Substation #735 Asset Condition Replacement |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | 2018-04-30 | No |  |  |  | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 10428000 | 10428000 | 10428000
Asset Condition | 1a | 92 | MA | National Grid, USA |  | 2 | 2022-09-01 |  | Robinson Avenue Station #102 Asset Condition Upgrades | [8 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-01-29 | [8 empty] | 8300000 | 8300000 | 8300000 | 8300000 | 10340000 | 10340000 | 10340000 | 10430000 | 10430000 | 14892000 | 14892000 | 18020000
Asset Condition | 1a | 145 | MA | National Grid, USA |  |  | 2023-11-01 |  | Carpenter Hill Control House Rebuild | [9 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | NR | 2022-04-11 | [9 empty] | 6860000 | 6860000 | 6860000 | 6860000 | 6860000 | 14485000 | 14485000 | 14485000 | 14485000 | 14485000 | 14485000
Asset Condition | 1a | 146 | MA | National Grid, USA |  |  | 2024-05-01 |  | 327 Line Asset Condition Refurbishments | [9 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-01-29 | [9 empty] | 60400000 | 60400000 | 60400000 | 60400000 | 60400000 | 87877000 | 87877000 | 87877000 | 87877000 | 87877000 | 87877000
Asset Condition | 1a | 149 | MA | National Grid, USA |  |  | 2025-12-01 |  | 315 Line Asset Condition Refurbishments - MA Portion | [9 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-01-29 | [9 empty] | 53500000 | 53500000 | 53500000 | 53500000 | 53500000 | 99072000 | 99072000 | 99072000 | 99072000 | 99072000 | 99072000
Asset Condition | 1a | 181 | MA | Eversource |  |  | 2022-06-01 |  | 345 kV Structure Replacement Projects - Line 312 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [11 empty] | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000
Asset Condition | 1a | 309 | CT | Eversource |  |  | 2023-10-01 |  | Southwest Connecticut (SWCT) Substation Relay Upgrades - Glenbrook 115 kV | [18 empty] | Under Construction | Under Construction | NR | No | [18 empty] | 10034000 | 10034000
Asset Condition | 1a | 310 | CT | Eversource |  |  | 2023-10-01 |  | Southwest Connecticut (SWCT) Substation Relay Upgrades - Plumtree 115 kV and 345 kV | [18 empty] | Under Construction | Under Construction | NR | No | [18 empty] | 19300000 | 19300000
Asset Condition | 1a | 311 | CT | Eversource |  |  | 2023-10-01 |  | Southwest Connecticut (SWCT) Substation Relay Upgrades - Norwalk 115 kV and 345 kV | [18 empty] | Under Construction | Under Construction | NR | No | [18 empty] | 16358000 | 16358000
Asset Condition | 1a | 313 | CT | Eversource |  |  | 2022-04-01 |  | 345 kV Structure and Shield Wire Replacements - 329 Line | [18 empty] | Under Construction | In-Service | NR | No | [18 empty] | 6242000 | 6242000
Asset Condition | 1a | 303 | CT | Eversource |  |  | 2022-12-01 |  | 115 kV Wood Pole Replacement - Line 1751 | [17 empty] | Proposed | Under Construction | Under Construction | NR | No | [17 empty] | 28800000 | 28794000 | 28794000
Asset Condition | 1a | 260 | CT | Eversource |  |  | 2023-03-01 |  | Copper Conductor and Shield Wire Replacement - Line 1825 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | No | No | [15 empty] | 7300000 | 7300000 | 7300000 | 7286000 | 7286000
Asset Condition | 1a | 262 | CT | Eversource |  |  | 2022-12-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 310 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | NR | No | [15 empty] | 59200000 | 59200000 | 61333000 | 61333000 | 61333000
Asset Condition | 1a | 263 | CT | Eversource |  |  | 2022-12-01 |  | 345 kV Line Structure Replacement - Line 330 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | NR | No | [15 empty] | 6600000 | 6600000 | 8039000 | 8039000 | 8039000
Asset Condition | 1a | 266 | CT | Eversource |  |  | 2022-12-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 387 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | NR | No | [15 empty] | 10200000 | 10200000 | 10200000 | 12781000 | 12781000
Asset Condition | 1a | 268 | CT | Eversource |  |  | 2022-12-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 3424 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | NR | No | [15 empty] | 14900000 | 14900000 | 14900000 | 14900000 | 14900000
Asset Condition | 1a | 230 | CT | Eversource |  |  | 2022-09-01 |  | 115 kV Wood Pole Replacement - 1910 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | NR | No | [12 empty] | 10300000 | 10300000 | 10300000 | 10300000 | 10300000 | 10300000 | 8226000 | 8226000
Asset Condition | 1a | 261 | CT | Eversource |  |  | 2022-03-01 |  | 115 kV Wood Pole and Shield Wire Replacement 2020-2023 - Line 1465 | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | NR | No | [15 empty] | 8770000 | 8770000 | 8770000 | 8770000 | 8770000
Asset Condition | 1a | 265 | CT | Eversource |  |  | 2023-12-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 383 | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | NR | No | [15 empty] | 16300000 | 16300000 | 16778000 | 16778000 | 16778000
Asset Condition | 1a | 267 | CT | Eversource |  |  | 2022-12-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 3041 | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | NR | No | [15 empty] | 14400000 | 14534000 | 14534000 | 14534000 | 14534000
Asset Condition | 1a | 269 | CT | Eversource |  |  | 2022-12-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 3754 | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | NR | No | [15 empty] | 5000000 | 5000000 | 5000000 | 5000000 | 5000000
Asset Condition | 1a | 221 | CT | Eversource |  |  | 2022-12-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1410 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | NR | No | [12 empty] | 13000000 | 13000000 | 13000000 | 10091000 | 10091000 | 10091000 | 10091000 | 8353000
Asset Condition | 1a | 245 | CT | Eversource |  |  | 2022-06-01 |  | Southington Substation Relay Replacement Project | [15 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-08-21 | [15 empty] | 9400000 | 9362000 | 9362000 | 9362000 | 9362000
Asset Condition | 1a | 219 | CT | Eversource |  |  | 2022-12-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1256 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [12 empty] | 10640000 | 10640000 | 14826000 | 14826000 | 14826000 | 14826000 | 14826000 | 14826000
Asset Condition | 1a | 224 | CT | Eversource |  |  | 2022-05-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1618 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2020-08-28 | [12 empty] | 9770000 | 9770000 | 8767000 | 8767000 | 8767000 | 8767000 | 8767000 | 8767000
Asset Condition | 1a | 225 | CT | Eversource |  |  | 2022-12-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1732 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [12 empty] | 7900000 | 7900000 | 13877000 | 13877000 | 13877000 | 13877000 | 13877000 | 13877000
Asset Condition | 1a | 67 | CT | Eversource |  |  | 2022-06-01 |  | Manchester Control House Expansion | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2020-10-08 | [6 empty] | 21400000 | 21400000 | 21400000 | 21400000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000
Asset Condition | 1a | 164 | CT | Eversource |  |  | 2022-03-01 |  | 345 kV Structure Replacement Projects - Line 310 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | NR | No | [11 empty] | 19900000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000
Asset Condition | 1a | 170 | CT | Eversource |  |  | 2022-09-01 |  | 345 kV Structure Replacement Projects - Line 364 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [11 empty] | 17300000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000
Asset Condition | 1a | 172 | CT | Eversource |  |  | 2022-03-01 |  | 345 kV Structure Replacement Projects - Line 383 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | NR | No | [11 empty] | 22200000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000
Asset Condition | 1a | 178 | CT | Eversource |  |  | 2023-03-01 |  | 345 kV Structure Replacement Projects - Line 3754 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [11 empty] | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000
Asset Condition | 1a | 19 | CT | United Illuminating Company |  |  | 2023-04-01 | UI Coastal Substation Flood Mitigation Study Project | Congress 115 kV Substation Flood Wall |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | NR | No |  |  |  | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 31770000 | 31770000 | 31770000
Asset Condition | 1a | 20 | CT | United Illuminating Company |  |  | 2024-04-01 | UI Coastal Substation Flood Mitigation Study Project | Grand Avenue - Mill River 115 kV Substation Flood Wall |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | NR | No |  |  |  | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 41800000 | 41800000 | 41800000
Asset Condition | 1a | 21 | CT | United Illuminating Company |  |  | 2023-03-01 | UI Coastal Substation Flood Mitigation Study Project | Singer 345kV Substation Flood Wall |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | NR | No |  |  |  | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 21960000 | 21960000 | 21960000
Asset Condition | 1a | 22 | CT | United Illuminating Company |  |  | 2024-09-01 | UI Coastal Substation Flood Mitigation Study Project | Pequonnock 115kV Substation rebuild with a new substation adjacent to the existing one |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | 2016-12-28 | 2022-04-11 |  |  |  | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 106100000 | 106106899
Asset Condition | 1a | 91 | CT | United Illuminating Company |  |  | 2025-01-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8809A-2 Line (Pequonnock-Congress) | [8 empty] | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [8 empty] | 376300000 |  | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320
Asset Condition | 1a | 151 | CT | United Illuminating Company |  |  | 2025-01-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8809B-2 Line (Pequonnock - Congress) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320
Asset Condition | 1a | 152 | CT | United Illuminating Company |  |  | 2028-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild portion of 1130 Line (Pequonnock - UI Str. B737) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614
Asset Condition | 1a | 153 | CT | United Illuminating Company |  |  | 2028-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 1430 Line (Ash Creek - ESE Str. B648) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220
Asset Condition | 1a | 154 | CT | United Illuminating Company |  |  | 2026-08-08 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 91001-1 Line (Pequonnock - Bridgeport Resco) & 91001-2 Line (Bridgeport Resco - Ash Creek) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324
Asset Condition | 1a | 155 | CT | United Illuminating Company |  |  | 2028-05-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88005A-1 Line (Milvon - Woodmont) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764
Asset Condition | 1a | 156 | CT | United Illuminating Company |  |  | 2028-05-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88005B-1 Line (Milvon - Woodmont) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764
Asset Condition | 1a | 157 | CT | United Illuminating Company |  |  | 2026-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8804A Line (Woodmont - Allings Crossing) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339
Asset Condition | 1a | 158 | CT | United Illuminating Company |  |  | 2026-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8804B Line (Woodmont - Allings Crossing) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339
Asset Condition | 1a | 159 | CT | United Illuminating Company |  |  | 2024-01-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003A-3 Line (Allings Crossing - Elmwest) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532
Asset Condition | 1a | 160 | CT | United Illuminating Company |  |  | 2024-01-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003B-3 Line (Allings Crossing - Elmwest) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532
Asset Condition | 1a | 161 | CT | United Illuminating Company |  |  | 2024-10-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003A-2 Line (Elmwest - West River) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175
Asset Condition | 1a | 162 | CT | United Illuminating Company |  |  | 2024-10-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003B-2 Line (Elmwest - West River) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175
Asset Condition | 1a | 150 | RI | National Grid, USA |  |  | 2025-06-01 |  | 315 Line Asset Condition Refurbishments - RI Portion | [9 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | NR | 2021-01-29 | [9 empty] | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 25107000 | 25107000 | 25107000 | 25107000 | 25107000 | 25107000
Asset Condition | 1a | 321 | NH | Eversource |  |  | 2022-12-01 |  | Laminated Wood Structure Replacement Program Phase II - A152 115 kV Line | [18 empty] | Proposed | Under Construction | NR | No | [18 empty] | 15264000 | 17476000
Asset Condition | 1a | 322 | NH | Eversource |  |  | 2022-12-01 |  | Laminated Wood Structure Replacement Program Phase II - V191 115 kV Line | [18 empty] | Proposed | Under Construction | NR | No | [18 empty] | 11024000 | 10114000
Asset Condition | 1a | 323 | NH | Eversource |  |  | 2022-12-01 |  | 115 kV Structure and Shield Wire Replacements - T198 Line | [18 empty] | Proposed | Under Construction | NR | No | [18 empty] | 19100000 | 19113000
Asset Condition | 1b | 324 | NH | Eversource |  |  | 2024-03-01 |  | P145 Line Rebuild - Asset Condition and OPGW | [18 empty] | Proposed | Proposed | No | No | [18 empty] | 52000000 | 52000000
Asset Condition | 1b | 325 | NH | Eversource |  |  | 2022-12-01 |  | Laminated Wood Structure Replacement Program Phase II - R187 115 kV Line | [18 empty] | Proposed | Proposed | NR | No | [18 empty] | 7541000 | 7541000
Asset Condition | 1b | 308 | NH | National Grid, USA |  |  | 2027-09-01 |  | Moore #20 Substation Asset Condition and Separation | [18 empty] | Proposed | Proposed | No | No | [18 empty] | 49307000 | 49307000
Asset Condition | 1b | 97 | NH | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 3 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Asset Condition | 1a | 305 | VT | Vermont Electric Power Company |  |  | 2025-12-01 |  | Line K42 Asset Condition Line Replacement | [18 empty] | Proposed | Planned | 2022-03-17 | No | [18 empty] | 49000000 | 49000000
Asset Condition | 1b | 235 | VT | National Grid, USA |  |  | 2025-07-01 |  | Vernon #13 Substation Asset Replacements | [13 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Proposed | No | No | [19 empty] | 39690000
Asset Condition | 1b | 315 | MA | Eversource |  |  | 2023-03-01 |  | 115 kV Structure Replacements and Shield Wire - 191 Line | [18 empty] | Proposed | Proposed | NR | No | [18 empty] | 19200000 | 19200000
Asset Condition | 1b | 316 | MA | Eversource |  |  | 2022-12-01 |  | 115 kV Structure Replacements and Shield Wire - 117 Line | [18 empty] | Proposed | Proposed | NR | No | [18 empty] | 5900000 | 5880000
Asset Condition | 1b | 317 | MA | Eversource |  |  | 2023-12-11 |  | Edgar Station #150 Brown Glass and Obsolete Equipment Replacement | [18 empty] | Proposed | Proposed | NR | No | [18 empty] | 6500000 | 6500000
Asset Condition | 1b | 318 | MA | Eversource |  |  | 2022-06-01 |  | 115 kV Structure Replacements - 211-508 Line | [18 empty] | Proposed | Proposed | NR | No | [18 empty] | 5800000 | 5800000
Asset Condition | 1b | 319 | MA | Eversource |  |  | 2022-07-01 |  | 115 kV Structure Replacements - 391-508 Line | [18 empty] | Proposed | Proposed | NR | No | [18 empty] | 5000000 | 5000000
Asset Condition | 1b | 320 | MA | Eversource |  |  | 2022-09-01 |  | 115 kV Structure Replacements - 533-508 Line | [18 empty] | Proposed | Proposed | NR | No | [18 empty] | 5000000 | 5000000
Asset Condition | 1b | 293 | MA | Eversource |  |  | 2024-06-01 |  | Ludlow 19S 345 kV Full BPS Separation and Asset Condition Project | [16 empty] | Proposed | Proposed | Proposed | Proposed | NR | No | [16 empty] | 42900000 | 42900000 | 42900000 | 42900000
Asset Condition | 1b | 250 | MA | Eversource |  |  | 2023-12-11 |  | Copper Conductor and Shield Wire Replacement - Line 1231/1242 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | No | No | [15 empty] | 97000000 | 97000000 | 97000000 | 97000000 | 97000000
Asset Condition | 1a | 271 | MA | National Grid, USA |  |  | 2023-05-01 |  | V-148S Asset Condition Refurbishment and Switch Replacement - MA Portion | [15 empty] | Proposed | Proposed | Proposed | Proposed | Planned | 2022-03-17 | No | [15 empty] | 10411000 | 10411000 | 10411000 | 10411000 | 10411000
Asset Condition | 1b | 328 | MA | National Grid, USA |  |  | 2026-12-01 |  | Bridgewater #16 Substation Asset Condition Upgrades | [19 empty] | Proposed | No | No | [19 empty] | 25950000
Asset Condition | 1b | 234 | MA | National Grid, USA |  |  | 2026-10-01 |  | Chestnut Hill #702 Substation Asset Replacements | [13 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No
Asset Condition | 1b | 236 | MA | National Grid, USA |  |  | 2026-11-01 |  | Deerfield #4 Substation Asset Replacements | [13 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No
Asset Condition | 1b | 94 | MA | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 5 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Asset Condition | 1b | 95 | MA | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 4 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Asset Condition | 1b | 96 | MA | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 3 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Asset Condition | 1b | 312 | CT | Eversource |  |  | 2022-12-01 |  | Laminated Wood Structure Replacement Program Phase II - 3403 345 kV Line | [18 empty] | Proposed | Proposed | NR | No | [18 empty] | 8422000 | 8422000
Asset Condition | 1a | 314 | CT | Eversource |  |  | 2022-06-01 |  | 345 kV Structure and Shield Wire Replacements - 352 Line | [18 empty] | Proposed | Under Construction | NR | No | [18 empty] | 5800000 | 5782000
Asset Condition | 1a | 302 | CT | Eversource |  |  | 2025-06-01 |  | 690 Line Rebuild and Asset Condition Project | [17 empty] | Proposed | Proposed | Under Construction | 2021-07-15 | No | [17 empty] | 11000000 | 11000000 | 11045000
Asset Condition | 1b | 255 | CT | Eversource |  |  | 2026-12-01 |  | Copper Conductor and Shield Wire Replacement - Line 1560/1808 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | NR | No | [15 empty] | 19700000 | 19700000 | 19700000 | 19700000 | 19700000
Asset Condition | 1b | 256 | CT | Eversource |  |  | 2026-12-01 |  | Copper Conductor and Shield Wire Replacement - Line 1580/1142/1808 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | No | No | [15 empty] | 68100000 | 68100000 | 68100000 | 68100000 | 68100000
Asset Condition | 1b | 258 | CT | Eversource |  |  | 2026-12-01 |  | Copper Conductor and Shield Wire Replacement - Line 1268/1485/1887 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | No | No | [15 empty] | 29600000 | 29600000 | 29600000 | 29600000 | 29600000
Asset Condition | 1b | 259 | CT | Eversource |  |  | 2024-06-01 |  | Copper Conductor and Shield Wire Replacement - Line 1163/1550 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | NR | No | [15 empty] | 16700000 | 16700000 | 16700000 | 16700000 | 16700000
Asset Condition | 1b | 239 | CT | United Illuminating Company |  |  | 2024-11-01 |  | Derby Junction to Ansonia Corridor 115 kV Transmission Upgrades | [13 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | NR | No | [13 empty] | 22374000 | 22374000 | 22374000 | 22374000 | 36000000 | 36000000 | 36000000
Asset Condition | 1b | 213 | CT | Eversource |  |  | 2023-12-11 |  | 115 kV Wood Pole Replacement - 1000 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | NR | No | [12 empty] | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000
Asset Condition | 1b | 216 | CT | Eversource |  |  | 2023-12-11 |  | 115 kV Wood Pole Replacement - 1080 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | NR | No | [12 empty] | 24180000 | 24180000 | 24180000 | 24180000 | 24180000 | 24180000 | 24180000 | 24180000
Asset Condition | 1a | 220 | CT | Eversource |  |  | 2023-06-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1280 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | NR | No | [12 empty] | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000
Asset Condition | 1a | 272 | RI | National Grid, USA |  |  | 2023-05-01 |  | V-148S Asset Condition Refurbishment and Switch Replacement - RI Portion | [15 empty] | Proposed | Proposed | Proposed | Proposed | Planned | 2022-03-17 | No | [15 empty] | 14322000 | 14322000 | 14322000 | 14322000 | 14322000
Asset Condition | 1b | 98 | RI | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 5 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Asset Condition | 1b | 99 | RI | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 4 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Asset Condition | 1a | 24 | ME | MEPCO |  |  | 2020-09-01 |  | Section 396 & 3001 Structure Replacement |  |  |  | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2019-12-10 |  |  |  | 16900000 | 16900000 | 16900000 | 16900000 | 16000000 | 16000000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000
Asset Condition | 1a | 23 | ME | MEPCO |  |  | 2019-06-01 |  | Section 388 & 3023 Structure Replacement |  |  |  | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No |  |  |  | 101600000 | 101600000 | 101600000 | 82400000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000
Asset Condition | 1a | 195 | VT | Vermont Electric Power Company |  |  | 2021-07-01 |  | Sand Bar Substation - Mitigate several Asset Condition concerns: Control House, P&C, circuit breakers, switches | [11 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | NR | 2021-02-19 | [11 empty] | 10600000 | 10600000 | 10600000 | 10600000 | 10640000 | 10640000 | 10640000 | 10640000 | 10640000
Asset Condition | 1a | 233 | VT | Vermont Electric Power Company |  |  | 2020-12-01 |  | Line K41 Asset Condition Structure Refurbishment | [13 empty] | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2021-01-29 | [13 empty] | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000
Asset Condition | 1a | 196 | VT | Vermont Electric Power Company |  |  | 2020-12-01 |  | Berlin Substation - Mitigate several Asset Condition concerns: Control House, P&C, circuit breakers & switches. Install a second protection system. | [11 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2021-02-01 | [11 empty] | 5872719 | 5550000 | 5550000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000
Asset Condition | 1a | 11 | VT | Vermont Electric Power Company |  |  | 2018-12-01 | Structure Condition Improvement | Replacement of 115 kV, 230 kV and 345 kV structures as part of the VELCO asset maintenance activities addressing our aging and degrading transmission line infrastructure. 100 to 300 structures will be replaced every year based on outage availability |  | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2017-12-01 |  | 185000000 | 185000000 | 185000000 | 160200000 | 160200000 | 160200000 | 160200000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000
Asset Condition | 1a | 3 | VT | Vermont Electric Power Company |  |  | 2017-05-01 | Essex STATCOM Refurbishment | Replace Essex STATCOM power electronics and controls | Proposed | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | No | 2017-08-13 | 27850000 | 27850000 | 27850000 | 27850000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000
Asset Condition | 1a | 288 | NH | Eversource |  |  | 2021-09-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - L175 Line | [16 empty] | Proposed | Under Construction | In-Service | In-Service | NR | No | [16 empty] | 19300000 | 19300000 | 19300000 | 19300000
Asset Condition | 1a | 286 | NH | Eversource |  |  | 2021-12-01 |  | Eddy Substation Control House Relocation and Rebuild | [16 empty] | Under Construction | Under Construction | In-Service | In-Service | 2019-07-10 | 2021-08-23 | [16 empty] | 6051000 | 6051000 | 6051000 | 6051000
Asset Condition | 1a | 287 | NH | Eversource |  |  | 2021-11-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - G128 Line | [16 empty] | Under Construction | Under Construction | In-Service | In-Service | NR | No | [16 empty] | 12632000 | 12632000 | 12632000 | 12632000
Asset Condition | 1a | 273 | NH | Eversource |  |  | 2021-12-01 |  | Copper Conductor and Shield Wire Replacement Projects - C129 Line | [15 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | NR | No | [15 empty] | 18500000 | 12145000 | 12145000 | 12145000 | 12145000
Asset Condition | 1a | 275 | NH | Eversource |  |  | 2021-11-01 |  | Copper Conductor and Shield Wire Replacement Projects - G128 Line | [15 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | NR | No | [15 empty] | 7600000 | 5044000 | 5044000 | 5044000 | 5044000
Asset Condition | 1a | 276 | NH | Eversource |  |  | 2021-11-01 |  | Copper Conductor and Shield Wire Replacement Projects - L163 Line | [15 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | NR | No | [15 empty] | 23300000 | 23310000 | 23310000 | 23310000 | 23310000
Asset Condition | 1a | 277 | NH | Eversource |  |  | 2021-11-01 |  | Copper Conductor and Shield Wire Replacement Projects - X104 | [15 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | NR | No | [15 empty] | 6994000 | 6994000 | 6994000 | 6994000 | 6994000
Asset Condition | 1b | 274 | NH | Eversource |  |  | 2022-01-01 |  | Copper Conductor and Shield Wire Replacement Projects - D108 Line | [15 empty] | Proposed | Proposed | Proposed | In-service | In-service | 2021-09-22 | No | [15 empty] | 6700000 | 6700000 | 6750000 | 6750000 | 6750000
Asset Condition | 1a | 200 | NH | Eversource |  |  | 2021-06-01 |  | 115 kV Wood Pole Replacement - F139 | [12 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | NR | No | [12 empty] | 8000000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000
Asset Condition | 1a | 187 | NH | Eversource |  |  | 2021-02-01 |  | 345 kV Structure Replacement Projects - Line 367 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | No | [11 empty] | 14100000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000
Asset Condition | 1a | 104 | NH | Eversource |  |  | 2021-02-01 |  | 115 kV Structure Replacement Project - Line L163 | [9 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | No | [9 empty] | 14000000 | 14000000 | 14000000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000
Asset Condition | 1a | 86 | NH | New Hampshire Transmission |  |  | 2020-11-01 | Seabrook 345 kV GIS Switchyard Phase 2 Equipment Replacement Part of Asset Condition #85 | Phase 2 of mulit-phase project involving like for like equipment replacement. Phase 2 includes replacing three approximately 1,000 ft. long horizontal gas-insulated lines (GIL) comprising the three phases of the 345 kV Seabrook-Scobie Pond 363 line, and replacing two GIS 345 kV Circuit Breakers and related switches that are the 363 line termination equipment. Post-top insulators for the 363 line located in the open-air to GIS transition yard will also be replaced. Phase 2 also includes replacing Breaker Failure Relay Protection Systems for the 363 line. | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2019-04-21 | [6 empty] | Part of Project #86 | Part of Project #86 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85
Asset Condition | 1a | 206 | NH | Eversource |  |  | 2020-11-01 |  | 115 kV Wood Pole and Shield Wire Replacement - Y138 | [12 empty] | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [12 empty] | 8490000 | 8490000 | 8475000 | 8475000 | 8475000 | 8475000 | 8475000 | 8475000
Asset Condition | 1a | 198 | NH | Eversource |  |  | 2020-09-01 |  | 115 kV Wood Pole Replacement - B143 | [12 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [12 empty] | 7410000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000
Asset Condition | 1a | 199 | NH | Eversource |  |  | 2020-11-01 |  | 115 kV Wood Pole Replacement - C129 | [12 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [12 empty] | 9100000 | 9045000 | 9045000 | 9045000 | 9045000 | 9045000 | 10048000 | 10048000
Asset Condition | 1a | 201 | NH | Eversource |  |  | 2020-11-01 |  | 115 kV Wood Pole Replacement - G128 | [12 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [12 empty] | 6910000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000
Asset Condition | 1a | 205 | NH | Eversource |  |  | 2020-12-01 |  | 115 kV Wood Pole and Shield Wire Replacement - M127 | [12 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [12 empty] | 33430000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000
Asset Condition | 1a | 105 | NH | Eversource |  |  | 2020-09-01 |  | 115 kV Structure Replacement Project - Line A152 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 6100000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000
Asset Condition | 1a | 188 | NH | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 373 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 10300000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000
Asset Condition | 1a | 189 | NH | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 379 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 9700000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000
Asset Condition | 1a | 191 | NH | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 385 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 14000000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000
Asset Condition | 1a | 192 | NH | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 391 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 16400000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000
Asset Condition | 1b | 202 | NH | Eversource |  |  | 2020-12-01 |  | 115 kV Wood Pole Replacement - K105 | [12 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | NR | NR | [12 empty] | 6080000 | 6080000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000
Asset Condition | 1b | 204 | NH | Eversource |  |  | 2020-03-01 |  | 115 kV Wood Pole Replacement - L175 | [12 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | NR | NR | [12 empty] | 5250000 | 5250000 | 5250000 | 3809000 | 3809000 | 3809000 | 3809000 | 3809000
Asset Condition | 1a | 186 | NH | Eversource |  |  | 2020-03-01 |  | 345 kV Structure Replacement Projects - Line 326 | [11 empty] | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 5200000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000
Asset Condition | 1a | 100 | NH | Eversource |  |  | 2020-01-01 |  | 115 kV Structure Replacement Project - Line A126 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 8300000 | 8300000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000
Asset Condition | 1a | 101 | NH | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line H123 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 6000000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000
Asset Condition | 1a | 102 | NH | Eversource |  |  | 2019-12-01 |  | 115 kV Structure Replacement Project - Line H141 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 7700000 | 7700000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000
Asset Condition | 1a | 103 | NH | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line K174 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 8700000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000
Asset Condition | 1a | 190 | NH | Eversource |  |  | 2020-01-01 |  | 345 kV Structure Replacement Projects - Line 381 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 8300000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000
Asset Condition | 1a | 85 | NH | New Hampshire Transmission |  |  | 2019-12-01 | Seabrook 345 kV GIS Switchyard Like-for Like Equipment Replacement | Phase 1 of mulit-phase project involving like for like equipment replacement. Phase 1 included replacing three approximately 1,000 ft. long horizontal gas-insulated lines (GIL) comprising the three phases of the 345kV Seabrook-to-Timberswamp 369 line. Post-top insulators for the 369 line located in the open-air to GIS transition yard were also replaced. A bridge covering the GILs where they go below grade and then resurface upon entering the fenced-in Protected Area where the GIS Switchyard is located was replaced during this phase. | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-04-21 | [6 empty] | 77017000 | 77017000 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778
Asset Condition | 1a | 52 | NH | Eversource |  |  | 2018-11-01 | Eversource Energy Autotransformer Replacement Plan | Replace the Littleton TB-41 autotransformer and bus upgrades to accommodate new transformer specifications | [5 empty] | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2018-01-29 | NR | [5 empty] | 6200000 | 3891000 | 3891000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000
Asset Condition | 1a | 55 | NH | Eversource |  |  | 2018-07-01 |  | 345 kV Structure Replacement Project - Line 307 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 12900000 | 12900000 | 12900000 | 12900000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000
Asset Condition | 1a | 56 | NH | Eversource |  |  | 2018-08-05 |  | 345 kV Structure Replacement Project - Line 326 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 12300000 | 12300000 | 12300000 | 12300000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000
Asset Condition | 1a | 57 | NH | Eversource |  |  | 2018-11-01 |  | 345 kV Structure Replacement Project - Line 367 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 15800000 | 15800000 | 15800000 | 15800000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000
Asset Condition | 1a | 58 | NH | Eversource |  |  | 2018-11-01 |  | 345 kV Structure Replacement Project - Line 379 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 14800000 | 14800000 | 14800000 | 14800000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000
Asset Condition | 1a | 59 | NH | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 381 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 13600000 | 13600000 | 13600000 | 13600000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000
Asset Condition | 1a | 60 | NH | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 391 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 19600000 | 19600000 | 19600000 | 19600000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000
Asset Condition | 1a | 51 | NH | Eversource |  |  | 2018-07-01 | Eversource Energy Autotransformer Replacement Plan | Replace the Deerfield TB-14 autotransformer and bus upgrades to accommodate new transformer specifications | [5 empty] | Proposed | Proposed | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2018-01-29 | 2020-10-08 | [5 empty] | 7700000 | 4779000 | 4779000 | 5300000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000
Asset Condition | 1a | 36 | NH | Eversource |  |  | 2018-03-01 |  | Install two 40 MVAR reactors on the Scobie 115 kV bus, to accommodate the loss of the reactors connected on the 13.8 kV teriary winding of the TB30 transformer |  |  |  |  | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2017-05-24 | 2018-08-24 |  |  |  |  | 5200000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000
Asset Condition | 1a | 5 | NH | New Hampshire Transmission |  |  | 2017-11-01 | Seabrook 345 kV GIS Breaker Removal and Bus Upgrade | Phase 2 - Remove Breaker 11 and upgrade sections of Bus 1 | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2016-02-23 | 2018-09-11 | 4271787 | 4271787 | 4271787 | 11991000 | 11991000 | 11991000 | 11991000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000
Asset Condition | 1a | 35 | NH | Eversource |  |  | 2017-06-01 |  | Scobie Pond TB30 345/115 kV transformer replacement project |  |  |  |  | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2017-05-24 | 2018-08-24 |  |  |  |  | 10300000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000
Asset Condition | 1a | 4 | NH | New Hampshire Transmission |  |  | 2016-11-01 | Seabrook 345 kV GIS Breaker Removal and Bus Upgrade | Phase 1 - Remove Breaker 22, remove Bus 4 and upgrade sections of Bus 2 | Proposed | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2016-02-23 | 2018-09-11 | 5140351 | 5140351 | 5140351 | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0)
Asset Condition | 1a | 257 | CT | Eversource |  |  | 2021-12-01 |  | Copper Conductor and Shield Wire Replacement - Line 1588 | [15 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | 2021-06-17 | No | [15 empty] | 9600000 | 9600000 | 9611000 | 9611000 | 9611000
Asset Condition | 1a | 264 | CT | Eversource |  |  | 2022-01-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 368 | [15 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | NR | No | [15 empty] | 8800000 | 8800000 | 9860000 | 9860000 | 9860000
Asset Condition | 1a | 227 | CT | Eversource |  |  | 2021-11-01 |  | 115 kV Wood Pole Replacement - 1756 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | In-Service | In-Service | NR | No | [12 empty] | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 24469000 | 24469000 | 24469000
Asset Condition | 1a | 292 | CT | Eversource |  |  | 2021-12-01 |  | Branford 11J A3 Bus Replacement Project | [16 empty] | Under Construction | Under Construction | In-Service | In-Service | NR | 2021-08-22 | [16 empty] | 10322000 | 10322000 | 10322000 | 10322000
Asset Condition | 1a | 244 | CT | Eversource |  |  | 2021-09-01 |  | 115 kV Copper Conductor and Wood Pole Replacement - Line 1191 | [14 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | 10/5/2020 | 2021-08-21 | [14 empty] | 38050000 | 38050000 | 38054000 | 38054000 | 38054000 | 38054000
Asset Condition | 1a | 242 | CT | Eversource |  |  | 2021-08-07 |  | Horton Cove Asset Condition and OPGW Project | [14 empty] | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-Service | 2020-11-06 | No | [14 empty] | 13400000 | 13949000 | 13949000 | 13949000 | 13949000 | 13949000
Asset Condition | 1a | 130 | CT | Eversource |  |  | 2021-12-01 |  | 115 kV Structure Replacement Project - Line 1465 | [9 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-Service | NR | 2021-02-19 | [9 empty] | 7000000 | 7000000 | 7000000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000
Asset Condition | 1a | 223 | CT | Eversource |  |  | 2021-09-01 |  | 115 kV Wood Pole Replacement - 1607 | [12 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | NR | No | [12 empty] | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000
Asset Condition | 1a | 166 | CT | Eversource |  |  | 2021-11-01 |  | 345 kV Structure Replacement Projects - Line 330 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | NR | No | [11 empty] | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000
Asset Condition | 1a | 167 | CT | Eversource |  |  | 2021-03-01 |  | 345 kV Structure Replacement Projects - Line 348 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | NR | No | [11 empty] | 19400000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000
Asset Condition | 1a | 173 | CT | Eversource |  |  | 2021-11-01 |  | 345 kV Structure Replacement Projects - Line 387 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | NR | No | [11 empty] | 18200000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000
Asset Condition | 1a | 176 | CT | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 3419 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | NR | No | [11 empty] | 11900000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000
Asset Condition | 1a | 124 | CT | Eversource |  |  | 2021-09-01 |  | 115 kV Structure Replacement Project - Line 1448 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | NR | 2021-02-19 | [9 empty] | 6900000 | 6926000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000
Asset Condition | 1a | 144 | CT | Eversource |  |  | 2021-10-01 |  | Millstone Substation 15G High Creep Insulator Replacement | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | NR | 2020-10-08 | [9 empty] | 11500000 | 11500000 | 11500000 | 11500000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000
Asset Condition | 1a | 139 | CT | Eversource |  |  | 2021-08-07 |  | 115 kV Structure Replacement Project - Line 1772 | [9 empty] | In-service | In-service | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | NR | 2021-02-19 | [9 empty] | 10000000 | 10000000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000
Asset Condition | 1b | 218 | CT | Eversource |  |  | 2021-10-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1232 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | In-Service | In-Service | NR | NR | [12 empty] | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 2422000 | 2422000
Asset Condition | 1a | 241 | CT | Eversource |  |  | 2021-05-01 |  | Glenbrook STATCOM Replacement | [14 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | 2021-04-14 | 2021-08-21 | [14 empty] | 21600000 | 21624000 | 18699000 | 18699000 | 18699000 | 18699000
Asset Condition | 1a | 243 | CT | Eversource |  |  | 2021-06-01 |  | 115 kV Lattice Tower Asset Condition and OPGW Project - Line 1768 | [14 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | 2020-11-06 | 2021-08-21 | [14 empty] | 22600000 | 22929000 | 22929000 | 22929000 | 22929000 | 22929000
Asset Condition | 1a | 217 | CT | Eversource |  |  | 2021-08-07 |  | 115 kV Wood Pole Replacement - 1208 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | NR | No | [12 empty] | 8960000 | 8960000 | 9577000 | 9577000 | 9577000 | 9577000 | 9577000 | 9577000
Asset Condition | 1a | 229 | CT | Eversource |  |  | 2021-02-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1766 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | NR | No | [12 empty] | 16600000 | 16600000 | 16556000 | 16556000 | 16556000 | 16556000 | 16556000 | 16556000
Asset Condition | 1a | 214 | CT | Eversource |  |  | 2021-03-01 |  | 115 kV Wood Pole Replacement - 1042 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | No | [12 empty] | 6080000 | 6080000 | 8273000 | 8273000 | 8273000 | 8273000 | 8273000 | 8273000
Asset Condition | 1a | 228 | CT | Eversource |  |  | 2021-04-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1765 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | NR | [12 empty] | 14700000 | 14700000 | 8801000 | 8801000 | 3800000 | 3800000 | 3800000 | 3800000
Asset Condition | 1a | 79 | CT | Eversource |  |  | 2018-05-01 |  | 345 kV Structure Replacement Project - Line 398 | [6 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | 2019-12-16 | [6 empty] | 7800000 | 7800000 | 7800000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000
Asset Condition | 1a | 82 | CT | Eversource |  |  | 2020-05-01 |  | Laminated Structure Replacement Project - Line 1505/1607 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | No | [6 empty] | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000
Asset Condition | 1a | 127 | CT | Eversource |  |  | 2021-02-01 |  | 115 kV Structure Replacement Project - Line 1635 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | 2021-02-19 | [9 empty] | 5700000 | 5764000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000
Asset Condition | 1a | 134 | CT | Eversource |  |  | 2020-11-01 |  | 115 kV Structure Replacement Project - Line 1765 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | 2021-02-19 | [9 empty] | 12300000 | 12300000 | 12300000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000
Asset Condition | 1a | 122 | CT | Eversource |  |  | 2021-03-01 |  | 115 kV Structure Replacement Project - Line 1310 | [9 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | 2021-02-19 | [9 empty] | 8300000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000
Asset Condition | 1a | 246 | CT | Eversource |  |  | 2018-12-01 |  | Prior Year Wood Structure Asset Condition Replacement - Line 329 345 kV | [15 empty] | In-service | In-service | In-service | In-service | In-service | NR | No | [15 empty] | 5925000 | 5925000 | 5925000 | 5925000 | 5925000
Asset Condition | 1a | 247 | CT | Eversource |  |  | 2018-12-01 |  | Prior Year Wood Structure Asset Condition Replacement - Line 352 345 kV | [15 empty] | In-service | In-service | In-service | In-service | In-service | NR | No | [15 empty] | 5998000 | 5998000 | 5998000 | 5998000 | 5998000
Asset Condition | 1a | 215 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1043 | [12 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | No | [12 empty] | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000
Asset Condition | 1a | 163 | CT | Eversource |  |  | 2020-12-01 |  | 667 69 kV line rebuild and asset condition project | [10 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | 7/25/2019 8/28/2020 | 2020-04-28 | [10 empty] | 24080000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000
Asset Condition | 1a | 120 | CT | Eversource |  |  | 2020-10-01 |  | 115 kV Structure Replacement Project - Line 1261/1598 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2021-02-19 | [9 empty] | 18300000 | 18300000 | 18300000 | 20352000 | 20352000 | 20352000 | 20352000 | 20352000 | 20352000 | 23854000 | 23854000
Asset Condition | 1a | 129 | CT | Eversource |  |  | 2020-08-01 |  | 115 kV Structure Replacement Project - Line 1726 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2021-02-19 | [9 empty] | 16300000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000
Asset Condition | 1a | 65 | MA | Eversource |  |  | 2020-06-01 |  | Laminated Structure Replacement Project - Line 1512 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [6 empty] | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000
Asset Condition | 1a | 76 | CT | Eversource |  |  | 2020-05-01 |  | 345 kV Structure Replacement Project - Line 371 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | 12/16/2019 2/19/2020 | [6 empty] | 10600000 | 10600000 | 10600000 | 11546000 | 11546000 | 11546000 | 11546000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000
Asset Condition | 1a | 83 | CT | Eversource |  |  | 2020-05-01 |  | Laminated Structure Replacement Project - Line 1675/1080 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [6 empty] | 17800000 | 17800000 | 17800000 | 17800000 | 17800000 | 17800000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000
Asset Condition | 1a | 89 | CT | Eversource |  |  | 2020-06-01 |  | Montville 16X Transformer Replacement | [7 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | 2018-05-16 | NR | [7 empty] | 6300000 | 6300000 | 6300000 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676
Asset Condition | 1a | 119 | CT | Eversource |  |  | 2019-06-01 |  | 115 kV Structure Replacement Project - Line 1256 | [9 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 12200000 | 12200000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000
Asset Condition | 1a | 126 | CT | Eversource |  |  | 2019-04-01 |  | 115 kV Structure Replacement Project - Line 1620 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 10000000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000
Asset Condition | 1a | 168 | CT | Eversource |  |  | 2020-06-01 |  | 345 kV Structure Replacement Projects - Line 352 | [11 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 12500000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000
Asset Condition | 1a | 222 | CT | Eversource |  |  | 2020-06-01 |  | 115 kV Wood Pole Replacement - Line 1505 | [12 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [12 empty] | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000
Asset Condition | 1a | 231 | CT | Eversource |  |  | 2020-04-01 |  | 115 kV Line Rebuild and Asset Condition Project - Line 1355 | [12 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [12 empty] | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000
Asset Condition | 1a | 17 | CT | United Illuminating Company |  |  | 2020-06-01 |  | East Shore 345 kV circuit switcher replacement project. Replace 345 kV circuit switchers with dead tank breakers |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In Service | In Service | In Service | In Service | In Service | In-service | In-service | 2016-07-19 | 2019-10-30 |  |  | 10931000 | 10931000 | 10931000 | 10931000 | 9234000 | 9234000 | 9234000 | 9234000 | 9234000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000
Asset Condition | 1a | 18 | CT | United Illuminating Company |  |  | 2020-06-01 | UI Coastal Substation Flood Mitigation Study Project | East Shore - Raising Impacted 115 kV Equipment |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In Service | In Service | In Service | In Service | In Service | In-service | In-service | NR | 2019-10-30 |  |  |  | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000
Asset Condition | 1a | 70 | CT | Eversource |  |  | 2020-04-01 |  | Oil Circuit Breaker Replacement Project at the Plumtree Substation | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [6 empty] | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000
Asset Condition | 1a | 197 | CT | United Illuminating Company |  |  | 2019-10-01 |  | 1130 Line Optical Ground Wire (OPGW) Replacement | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-10-30 | [11 empty] | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000
Asset Condition | 1a | 171 | CT | Eversource |  |  | 2019-12-01 |  | 345 kV Structure Replacement Projects - Line 368 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 7300000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000
Asset Condition | 1a | 175 | CT | Eversource |  |  | 2019-10-01 |  | 345 kV Structure Replacement Projects - Line 3252 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000
Asset Condition | 1a | 177 | CT | Eversource |  |  | 2019-07-01 |  | 345 kV Structure Replacement Projects - Line 3424 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 7900000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000
Asset Condition | 1a | 193 | CT | Eversource |  |  | 2019-12-01 |  | 115 kV Structure Replacement Projects - Line 1470 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [11 empty] | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000
Asset Condition | 1a | 50 | CT | Eversource |  |  | 2019-11-01 | Eversource Energy Autotransformer Replacement Plan | Replace the Card 11F-5X autotransformer. Foundation and bus upgrades to accommodate new transformer specifications | [5 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2018-05-16 | No | [5 empty] | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000
Asset Condition | 1a | 49 | CT | Eversource |  |  | 2020-01-01 |  | Southern CT Loop Line Structure Replacements - 1655 115 kV | [5 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 06/30/2020 | [5 empty] | 14800000 | 14800000 | 14800000 | 14800000 | 17100000 | 17100000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000
Asset Condition | 1a | 137 | CT | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line 1769 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 8200000 | 8200000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000
Asset Condition | 1a | 140 | CT | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line 1783 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 8200000 | 8200000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000
Asset Condition | 1a | 141 | CT | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line 1785 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 9000000 | 9000000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000
Asset Condition | 1b | 165 | CT | Eversource |  |  | 2019-12-01 |  | 345 kV Structure Replacement Projects - Line 321 | [11 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 6500000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000
Asset Condition | 1a | 169 | CT | Eversource |  |  | 2019-08-07 |  | 345 kV Structure Replacement Projects - Line 362 | [11 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000
Asset Condition | 1a | 174 | CT | Eversource |  |  | 2019-07-01 |  | 345 kV Structure Replacement Projects - Line 3041 | [11 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000
Asset Condition | 1b | 84 | CT | Eversource |  |  | 2018-12-01 |  | Laminated Structure Replacement Project - Line 1921 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [6 empty] | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000
Asset Condition | 1a | 135 | CT | Eversource |  |  | 2018-06-01 |  | 115 kV Structure Replacement Project - Line 1766 | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 5800000 | 5800000 | 5800000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000
Asset Condition | 1a | 115 | CT | Eversource |  |  | 2019-09-01 |  | 1608 115 kV Line Cable Replacement | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2019-12-19 | 2020-04-28 | [9 empty] | 11300000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000
Asset Condition | 1a | 117 | CT | Eversource |  |  | 2019-05-01 |  | 115 kV Structure Replacement Project - Line 1050 | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 7300000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000
Asset Condition | 1a | 47 | CT | Eversource |  |  | 2019-05-01 |  | Southern CT Loop Line Structure Replacements - 1342 115 kV | [5 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-10 | [5 empty] | 30300000 | 30300000 | 30300000 | 30300000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000
Asset Condition | 1a | 68 | CT | Eversource |  |  | 2019-04-01 |  | Card-Montville-Tunnel Corridor Asset Condition and OPGW Installation Project | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-10-16 | [6 empty] | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000
Asset Condition | 1a | 73 | CT | Eversource |  |  | 2018-11-01 |  | 345 kV Structure Replacement Project - Line 330 | [6 empty] | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 13500000 | 13500000 | 13500000 | 13500000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000
Asset Condition | 1a | 116 | CT | Eversource |  |  | 2019-01-01 |  | 1880 115 kV Line Cable Replacement | [9 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-04-28 | [9 empty] | 7200000 | 7200000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000
Asset Condition | 1a | 34 | CT | Eversource |  |  | 2018-12-01 |  | Devon Control House Modifications |  |  |  |  | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-04-17 |  |  |  |  | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000
Asset Condition | 1a | 69 | CT | Eversource |  |  | 2018-12-01 |  | Oil Circuit Breaker Replacement Project at the Frost Bridge Substation | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-08-24 | [6 empty] | 7250000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000
Asset Condition | 1a | 71 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 310 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 16500000 | 16500000 | 16500000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000
Asset Condition | 1a | 72 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 321 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 12/16/2019 2/19/202 | [6 empty] | 6000000 | 6000000 | 6000000 | 5847000 | 5847000 | 5847000 | 5847000 | 5847000 | 5847000 | 7462000 | 7462000 | 7462000 | 7462000 | 7462000
Asset Condition | 1a | 75 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 364 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 14300000 | 14300000 | 14300000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000
Asset Condition | 1a | 74 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 348 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 16000000 | 16000000 | 16000000 | 16000000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000
Asset Condition | 1a | 77 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 383 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 15500000 | 15500000 | 15500000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000
Asset Condition | 1a | 78 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 387 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 13100000 | 13100000 | 13100000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000
Asset Condition | 1a | 80 | CT | Eversource |  |  | 2018-07-01 |  | 345 kV Structure Replacement Project - Line 3041 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 9700000 | 9700000 | 9700000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000
Asset Condition | 1a | 81 | CT | Eversource |  |  | 2018-09-01 |  | 345 kV Structure Replacement Project - Line 3642 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 9900000 | 9900000 | 9900000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000
Asset Condition | 1a | 125 | CT | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1565 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 11500000 | 11500000 | 11500000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000
Asset Condition | 1a | 131 | CT | Eversource |  |  | 2018-11-01 |  | 115 kV Structure Replacement Project - Line 1751 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 12500000 | 12500000 | 12500000 | Part of Asset Condition #226 | Part of Asset Condition #226 | Part of Asset Condition #226 | Part of Asset Condition #226 | Part of Asset Condition #226 | 4467000 | 4467000 | 4467000
Asset Condition | 1a | 133 | CT | Eversource |  |  | 2018-09-01 |  | 115 kV Structure Replacement Project - Line 1759 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 7300000 | 7300000 | 7300000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000
Asset Condition | 1a | 136 | CT | Eversource |  |  | 2018-04-01 |  | 115 kV Structure Replacement Project - Line 1767 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 5400000 | 5400000 | 5400000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000
Asset Condition | 1a | 138 | CT | Eversource |  |  | 2018-10-01 |  | 115 kV Structure Replacement Project - Line 1770 (the 1770 line has been replaced by the Plumtree to Stony Hill 1268 line and the Stony Hill to Bates Rock 1485 line) | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 16300000 | 16300000 | 16300000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000
Asset Condition | 1a | 142 | CT | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1768-CT | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 5200000 | 5200000 | 5200000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000
Asset Condition | 1a | 143 | CT | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1910 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 5800000 | 5800000 | 5800000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000
Asset Condition | 1a | 48 | CT | Eversource |  |  | 2018-07-01 |  | Southern CT Loop Line Structure Replacements - 1508 115 kV | [5 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-08-24 | [5 empty] | 16600000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000
Asset Condition | 1a | 46 | CT | Eversource |  |  | 2017-12-01 |  | Southern CT Loop Line Structure Replacements - 1261/1598 115 kV | [5 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-04-17 | [5 empty] | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000
Asset Condition | 1a | 33 | CT | Eversource |  |  | 2017-06-01 |  | 1410 and 100 Line Structure Replacements |  |  |  |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2017-12-01 |  |  |  |  | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000
Asset Condition | 1a | 39 | CT | Eversource |  |  | 2017-11-01 |  | 3419 line (portion in Connecticut) asset condition and OPGW project |  |  |  |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-02 |  |  |  |  | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38
Asset Condition | 1a | 29 | CT | Eversource |  |  | 2017-09-01 |  | 1620/1975 line structure replacement |  |  |  | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 12/1/2017 2/19/2021 |  |  |  | 15500000 | 12500000 | 11093000 | 11093000 | 11093000 | 11093000 | 11093000 | 11093000 | 11093000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000
Asset Condition | 1a | 30 | CT | Eversource |  |  | 2016-12-01 |  | 3424 line Asset Condition and Storm Hardening |  |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-03 |  |  |  | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000
Asset Condition | 1a | 16 | CT | Eversource |  |  | 2016-06-01 |  | 3419 line (portion in Connecticut) asset condition and storm hardening. Asset conditon - replace 24 wood poles H-frame with direct embed steel wood pole equivalent or wood located in MA & CT. |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-03 |  |  | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1
Asset Condition | 1a | 6 | CT | Eversource |  |  | 2014-09-01 |  | 1570 line clearance remediation. Devon S/S to Beacon Falls S/S. 31 conductor span locations were found to have NESC clearance discrepancies. | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2016-12-16 | 6500000 | 6500000 | 6500000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000
Asset Condition | 1a | 299 | MA | Eversource |  |  | 2021-12-01 |  | 115 kV Structure Replacements - Line 456-522 | [17 empty] | Under Construction | In-Service | In-Service | NR | No | [17 empty] | 5672000 | 5672000 | 5672000
Asset Condition | 1a | 300 | MA | Eversource |  |  | 2021-11-01 |  | 115 kV Structure Replacements - Line 240-510 | [17 empty] | Under Construction | In-Service | In-Service | NR | No | [17 empty] | 11636000 | 11636000 | 11636000
Asset Condition | 1a | 253 | MA | Eversource |  |  | 2021-10-01 |  | 345 kV Line Structure Replacement - Line 338 | [15 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | NR | No | [15 empty] | 8700000 | 8700000 | 8700000 | 8700000 | 8700000
Asset Condition | 1a | 207 | MA | Eversource |  |  | 2021-10-01 |  | 115 kV Wood Pole Replacement - 1161 | [12 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | NR | No | [12 empty] | 17100000 | 17100000 | 17100000 | 22578000 | 22578000 | 22578000 | 22578000 | 22578000
Asset Condition | 1b | 301 | MA | Eversource |  |  | 2021-11-01 |  | 230 kV Structure Replacements - Line 342-603 | [17 empty] | Proposed | In-Service | In-Service | NR | No | [17 empty] | 5451000 | 5451000 | 5451000
Asset Condition | 1a | 295 | MA | National Grid, USA |  |  | 2022-02-01 |  | C-129N/D-130 115 kV Line Fiber Installation | [17 empty] | Under Construction | In-service | In-service | NR | 2022-04-11 | [17 empty] | 11220000 | 11220000 | 11220000
Asset Condition | 1a | 304 | MA | Eversource |  |  | 2021-04-01 |  | 478-508 & 478-509 115 kV Lines Asset Condition & OPGW | [17 empty] | In-Service | In-Service | In-Service | NR | No | [17 empty] | 5866000 | 5866000 | 5866000
Asset Condition | 1b | 252 | MA | Eversource |  |  | 2021-06-01 |  | 345 kV Line Structure Replacement - Line 319 | [15 empty] | Proposed | Proposed | In-service | In-service | In-service | NR | No | [15 empty] | 7800000 | 7800000 | 7838000 | 7838000 | 7838000
Asset Condition | 1a | 107 | MA | Eversource |  |  | 2021-06-01 |  | 349X/Y 345 kV Cable Replacement | [9 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | 2019-10-07 | 06/30/2020 | [9 empty] | 72400000 | 72400000 | 72400000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000
Asset Condition | 1a | 210 | MA | Eversource |  |  | 2021-03-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1394 | [12 empty] | Proposed | Proposed | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | No | [12 empty] | 7070000 | 7070000 | 7070000 | 8877000 | 8877000 | 8877000 | 8877000 | 8877000
Asset Condition | 1a | 212 | MA | Eversource |  |  | 2021-03-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1976 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | No | [12 empty] | 7470000 | 7470000 | 9688000 | 9688000 | 9688000 | 9688000 | 9688000 | 9688000
Asset Condition | 1b | 254 | MA | Eversource |  |  | 2021-04-01 |  | 115 kV Wood Pole Asset Condition Project - Line 455-507 | [15 empty] | Proposed | In-Service | In-Service | In-Service | In-Service | NR | No | [15 empty] | 5191000 | 5191000 | 5191000 | 5191000 | 5191000
Asset Condition | 1a | 64 | MA | Eversource |  |  | 2021-03-01 |  | 345 kV Structure Replacement Project - Line 393 | [6 empty] | Proposed | Proposed | Proposed | In-service | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | 2019-12-16 | [6 empty] | 10000000 | 10000000 | 10000000 | 10000000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000
Asset Condition | 1a | 184 | MA | Eversource |  |  | 2021-03-01 |  | 345 kV Structure Replacement Project - Line 393 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | No | [11 empty] | 11000000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000
Asset Condition | 1a | 248 | MA | Eversource |  |  | 2017-12-01 |  | Prior Year Wood Structure Asset Condition Replacement - Line 338 345 kV | [15 empty] | In-service | In-service | In-service | In-service | In-service | NR | No | [15 empty] | 5804000 | 5804000 | 5804000 | 5804000 | 5804000
Asset Condition | 1a | 249 | MA | Eversource |  |  | 2019-06-01 |  | Prior Year Wood Structure Asset Condition Replacement - Line 455-507 115 kV | [15 empty] | In-service | In-service | In-service | In-service | In-service | NR | No | [15 empty] | 10296000 | 10296000 | 10296000 | 10296000 | 10296000
Asset Condition | 1a | 209 | MA | Eversource |  |  | 2020-10-01 |  | 115 kV Wood Pole Replacement - 1512 | [12 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | No | [12 empty] | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000
Asset Condition | 1a | 32 | MA | Eversource |  |  | 2020-12-01 |  | West Medway Substation #446 Asset Condition Upgrade |  |  |  |  | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2017-12-01 |  |  |  |  | 18900000 | 18900000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000
Asset Condition | 1a | 42 | MA | Eversource |  |  | 2020-12-01 |  | Brighton #329 115 kV Control House | [5 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2018-04-17 | [5 empty] | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000
Asset Condition | 1a | 147 | MA | National Grid, USA |  |  | 2022-02-01 |  | 303 Line Asset Condition Refurbishments | [9 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 24700000 | 24700000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000
Asset Condition | 1a | 148 | MA | National Grid, USA |  |  | 2020-05-01 |  | 3520 Line Asset Condition Refurbishments | [9 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 6900000 | 6900000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000
Asset Condition | 1a | 211 | MA | Eversource |  |  | 2020-07-01 |  | 115 kV Wood Pole and Shield Wire Replacement - Line 1858 | [12 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [12 empty] | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000
Asset Condition | 1b | 238 | MA | Eversource |  |  | 2020-06-01 |  | 115 kV Granville Junction to Atwater 1853 line (formerly 1512) OPGW Project | [13 empty] | Proposed | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | NR | [13 empty] | 5000000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000
Asset Condition | 1a | 180 | MA | Eversource |  |  | 2019-08-01 |  | 345 kV Structure Replacement Projects - Line 3361 | [11 empty] | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 6300000 | 6300000 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951
Asset Condition | 1b | 185 | MA | Eversource |  |  | 2020-03-01 |  | 345 kV Structure Replacement Projects - Line 3419 | [11 empty] | Proposed | Proposed | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | No | [11 empty] | 26000000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000
Asset Condition | 1a | 108 | MA | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line 65-508 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 19500000 | 19500000 | 19500000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000
Asset Condition | 1a | 112 | MA | Eversource |  |  | 2019-12-01 |  | 115 kV Structure Replacement Project - Line 1962 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 20300000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000
Asset Condition | 1a | 114 | MA | Eversource |  |  | 2019-11-01 |  | 115 kV Structure Replacement Project - Line F132 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 11000000 | 11000000 | 11000000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000
Asset Condition | 1a | 179 | MA | Eversource |  |  | 2019-10-01 |  | 345 kV Structure Replacement Projects - Line 336 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 6600000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000
Asset Condition | 1a | 182 | MA | Eversource |  |  | 2019-11-01 |  | 345 kV Structure Replacement Projects - Line 354 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 29600000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000
Asset Condition | 1b | 183 | MA | Eversource |  |  | 2019-09-01 |  | 345 kV Structure Replacement Projects - Line 381 | [11 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [11 empty] | 12500000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000
Asset Condition | 1a | 88 | MA | National Grid, USA |  |  | 2019-12-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 1 | [6 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [6 empty] | 1384000 | 1384000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2908881 | 2908881 | 2908881
Asset Condition | 1a | 66 | MA | Eversource |  |  | 2019-05-01 |  | Laminated Structure Replacement Project - Line 1211/1161 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [6 empty] | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12598500 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000
Asset Condition | 1a | 109 | MA | Eversource |  |  | 2019-03-01 |  | 115 kV Structure Replacement Project - Line 1327 | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [9 empty] | 7800000 | 7800000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000
Asset Condition | 1a | 110 | MA | Eversource |  |  | 2019-03-01 |  | 115 kV Structure Replacement Project - Line 1428 | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 12100000 | 12100000 | 12100000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000
Asset Condition | 1a | 15 | MA | Eversource |  |  | 2019-05-01 |  | Install a new Medway control house which is to be built to BPS standards in a location within the existing station footprint. |  |  | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2016-01-26 | 2017-07-17 |  |  | 11800000 | 11800000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000
Asset Condition | 1a | 37 | MA | Eversource |  |  | 2018-11-01 |  | New Mt. Tom protection system control house |  |  |  |  | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-10-16 |  |  |  |  | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000
Asset Condition | 1a | 62 | MA | Eversource |  |  | 2018-12-01 |  | Oil Circuit Breaker Replacement Project at the Agawam Substation | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [6 empty] | 5400000 | 5400000 | 5400000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000
Asset Condition | 1a | 111 | MA | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1447 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [9 empty] | 6600000 | 6600000 | 6600000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000
Asset Condition | 1a | 113 | MA | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1768-MA | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | No | [9 empty] | 3000000 | 3000000 | 3000000 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142
Asset Condition | 1a | 45 | MA | Eversource |  |  | 2018-07-01 |  | 345 kV 354 Line Structure Replacements | [5 empty] | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-10-16 | [5 empty] | 10148000 | 10148000 | 7017000 | 7017000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000
Asset Condition | 1a | 40 | MA | National Grid, USA |  | 1 | 2018-05-01 |  | Salem Harbor Substation - 115 kV oil circuit breaker replacements |  |  |  |  | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR |  |  |  |  | 6000000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000
Asset Condition | 1a | 61 | MA | Eversource |  |  | 2017-09-01 |  | 1231/1242 Structure Replacement Project | [6 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-02-15 | [6 empty] | 7966000 | 7966000 | 7966000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000
Asset Condition | 1a | 38 | MA | Eversource |  |  | 2017-12-01 |  | 3419 line (portion in Massachusetts) asset condition and OPGW project |  |  |  |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-03 |  |  |  |  | 13700000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000
Asset Condition | 1a | 41 | MA | Eversource |  |  | 2013-06-01 |  | Scotia Street Substation Project | [5 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2017-07-17 | [5 empty] | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000
Asset Condition | 1a | 12 | MA | Eversource |  |  | 2017-07-01 |  | Doreen-Oswald Jct. 1211 115 kV Line Structure Replacement |  | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-03 |  | 14800000 | 14800000 | 14800000 | 11500000 | 11500000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000
Asset Condition | 1a | 31 | MA | Eversource |  |  | 2016-05-01 |  | 345 kV GIS breaker replacements at Kingston Street #514 |  |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-05-11 |  |  |  | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000
Asset Condition | 1a | 13 | MA | Eversource |  |  | 2017-01-01 |  | Ludlow-Thorndike-Palmer (WMA portion) of the X176 115 KV Line Rebuild |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2016-12-16 |  | 14900000 | 8928000 | 8928000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000
Asset Condition | 1a | 2 | MA | National Grid, USA |  |  | 2016-10-01 | Crystal Lake Substation Upgrades | Crystal Lake Substation Upgrades | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2016-05-05 | 2018-10-10 | 6950000 | 6950000 | 6950000 | 6950000 | 6950000 | 6950000 | 6950000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000
Asset Condition | 1a | 1 | MA | Eversource |  |  | 2016-06-01 |  | 3419 line (portion in Massachusetts) asset condition and storm hardening. Asset condition - replace 24 wood poles H-frame with direct embed steel wood pole equivalent or wood located in MA & CT. | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 01/03/2018 | 14500000 | 14500000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000
Asset Condition | 1a | 14 | MA | Eversource |  |  | 2015-12-01 |  | 1231/1242 Line Clearance remediation Project |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2016-12-16 |  |  | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000
Asset Condition | 1a | 7 | MA | Eversource |  |  | 2015-12-01 |  | 115 kV line 136 Falmouth Tap - West Barnstable Complete structure replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2015-11-25 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000
Asset Condition | 1a | 8 | MA | Eversource |  |  | 2015-05-01 |  | 381 Line Structure Replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2015-11-25 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000
Asset Condition | 1a | 9 | MA | Eversource |  |  | 2015-12-01 |  | 354 Line Structure Replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2015-11-25 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000
Asset Condition | 1a | 10 | MA | Eversource |  |  | 2014-07-01 |  | 312 Line Structure Replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2015-11-25 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000
Asset Condition | 1a | 54 | RI | National Grid, USA |  |  | 2019-12-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 1 | [6 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | NR | [6 empty] | 427000 | 427000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1174157 | 1174157 | 1174157
Asset Condition | 1b | 226 | CT | Eversource |  |  | 2023-12-11 |  | 115 kV Wood Pole Replacement - 1751 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | NR | No | [12 empty] | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000
Asset Condition | 1b | 93 | VT | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 4 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No
Asset Condition | 1b | 106 | NH | Eversource |  |  | 2023-12-11 |  | 115 kV Structure Replacement Project - Line X178 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000
Asset Condition | 1b | 118 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Structure Replacement Project - Line 1191 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000
Asset Condition | 1b | 121 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Structure Replacement Project - Line 1280 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000
Asset Condition | 1b | 123 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Structure Replacement Project - Line 1410 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000
Asset Condition | 1b | 132 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Structure Replacement Project - Line 1756 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 7000000 | 7000000 | 7000000 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227
Asset Condition | 1a | 128 | CT | Eversource |  |  | 2019-12-01 |  | 115 kV Structure Replacement Project - Line 1675 | [9 empty] | Proposed | Under Construction | Cancelleed | Cancelleed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000